## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2024 SF | CAR | Apayao | 501756 | CADACLAN INTEGRATED SCHOOL | CALANASAN (BAYAG) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135669 | Taneg ES | MANKAYAN | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 502168 | Mogao Integrated School | MANKAYAN | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135693 | Indaoac ES | TUBA | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 318904 | Tuba Central NHS | TUBA | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 305164 | Tublay National Trade High School | TUBLAY | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135940 | Tulaed ES | MAYOYAO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305186 | Tulaed NHS | MAYOYAO | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135945 | Danggo ES | TINOC | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135947 | Gumhang Elementary School | TINOC | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135949 | Impugong ES | TINOC | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305192 | Tinoc NHS | TINOC | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 135993 | Mabilong Elementary School | LUBUAGAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 305202 | Cawagayan National High School | PINUKPUK | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136186 | Kadaclan Elementary School | BARLIG | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136233 | Ambagiw ES | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136233 | Ambagiw ES | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 221006 | Mountain Province SPED Center | BONTOC (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 305924 | Mainit National High School | BONTOC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319203 | Saliok National High School | NATONIN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136306 | Marallag Elementary School | PARACELIS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136310 | Paracelis Central School | PARACELIS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319202 | San Rafael National High School | PARACELIS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 305257 | Namatec National High School | Sabangan | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 221012 | New LubonElementary School | TADIAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Mt. Province | 319221 | Balaoa National High School | TADIAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136093 | Calaccad Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136153 | Addang Primary School | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136158 | Balawag Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 220529 | San Pablo Primary School | CITY OF TABUK (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 501889 | Toppan Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 501889 | Toppan Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 501971 | Lacnog Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 502123 | Guilayon Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | 502380 | Appas Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Tabuk City | NOT-IN-NSBI | Tabuk City National High School - BANTAY EXT. | CITY OF TABUK (Capital) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 501757 | Lam-ayan Integrated School | BUGUIAS | Lone | 1 | - | - | 560 | 560 | 14 | - | - | 1925000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135517 | Balatoc Elementary School | ITOGON | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 305126 | Ampucao National High School | ITOGON | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 305539 | AMBIONG NATIONAL HIGH SCHOOL | LA TRINIDAD (Capital) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135741 | Awayan ES | AGUINALDO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135819 | Cambulo ES - Mattao Annex | BANAUE | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135845 | Umalbong ES | HINGYON | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135879 | Banga ES | LAGAWE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135888 | Luta PS | LAGAWE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135922 | Buninan PS | MAYOYAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135936 | Nattum PS (Abagong) | MAYOYAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 135970 | Bullalayao Primary School | BALBALAN | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 306053 | Eastern Balbalan National High School | BALBALAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 319116 | Balbalan National High school | BALBALAN | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 319116 | Balbalan National High school | BALBALAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 135989 | Dangoy Elementary School | LUBUAGAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136049 | Malaap Elementary School | PINUKPUK | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 305210 | Limos National High School - Dao-angan Extension | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 305542 | Malagnat National High School-Taggay Extension | PINUKPUK | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School-Pinococ Extension | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Malagnat NHS | PINUKPUK | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136071 | Kinama Elementary School | RIZAL (LIWAN) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | Lone | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Bagbag Elementary School Bulbul Annex | RIZAL (LIWAN) | Lone | 1 | 160 | - | - | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Rizal Central School Cadao Annex | RIZAL (LIWAN) | Lone | 1 | 120 | - | - | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Santor NHS | RIZAL (LIWAN) | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Kalinga | 136143 | Ambato-Legleg Elementary School | TINGLAYAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 134994 | Dugong ES | BUCAY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 135027 | Benben Elementary School | LA PAZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra |  | El Bernos Elementary School | LA PAZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 135104 | Lul-luno ES | LUBA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305077 | Bolbolo NHS | PILAR | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305093 | Pilar Rural High School | PILAR | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Abra | 500518 | An-anaao Integrated School | TAYUM | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 135229 | Ayayao ES | CALANASAN (BAYAG) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 135280 | Talifugo ES | CONNER | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 135285 | Atok Elementary School | FLORA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 502117 | San Jose Integrated School | FLORA | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 135298 | Baliwanan ES | KABUGAO (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 135347 | Sta. Lina ES | LUNA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Apayao | 219004 | Luyon ES | LUNA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Baguio City | 136380 | Adiwang Elementary School | BAGUIO CITY | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 305158 | Sinipsip National High School | BUGUIAS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135562 | Balakbak ES | KAPANGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135631 | Puguis Elementary School | LA TRINIDAD (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Benguet | 135724 | Langbis PS | TUBLAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135880 | Boliwong ES | LAGAWE (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135884 | Cudog ES | LAGAWE (Capital) | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 220020 | Ifugao SPED Center | LAGAWE (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305169 | Caba National High School | LAGAWE (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 319004 | Lagawe NHS | LAGAWE (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 135898 | Dunuan ES | LAMUT | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 500882 | Alupapan Integrated School | LAMUT | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | CAR | Ifugao | 305185 | Mayoyao NHS | MAYOYAO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2023 SF | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 530400 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Abra | 135058 | Cayapa ES | LAGANGILANG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Abra | 501729 | TABANGAO IS (ES) | LUBA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 328400 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 166300 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Abra | 135140 | Palang PS | SAN QUINTIN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 61100 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Abra | 305104 | Tineg National High School | TINEG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Abra | 135093 | Batayan PS | TUBO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [11 empty] | Missing in CAR updates under CY 2023 SF, found in CY 2022 instead | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | CAR | Apayao | 135361 | Barocboc ES | SANTA MARCELA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 269400 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | CAR | Apayao | 135362 | Consuelo Elementary School | SANTA MARCELA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 269400 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1392800 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 826700 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1632600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1493800 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 698400 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Baguio City | 340055 | Baguio City National Science High School (Senior High School-Stand Alone) | BAGUIO CITY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1508500 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305135 | Bokod NHS-Main | BOKOD | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 890100 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305163 | Tublay School of Home Industries - Annex (Ambuklao) | BOKOD | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 494500 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 318901 | Bokod NHS Annex - Daklan | BOKOD | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 677600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 135510 | Midas Elementary School | ITOGON | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 435700 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305125 | Alejo M. Pacalso Memorial National High School | ITOGON | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | Lone | 1 | - | 135 | - | 135 | 3 | - | 21 | 672750 | Regional Office Implementation | 55% Allocation for Regular Supplier | 763500 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | Lone |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | CAR | Benguet | 501809 | Palidan Integrated School | BAKUN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 324200 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 502174 | Abucot Integrated School | KABAYAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 501301 | Cayapas Integrated School | BUGUIAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 501203 | Datakan Integrated School | KAPANGAN | Lone | 1 | - | - | 800 | 800 | 20 | - | - | 2586000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 795600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 501759 | Bad-ayan Integrated School | BUGUIAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305162 | Tublay School of Home Industries | TUBLAY | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2835800 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 502170 | Boneng Integrated School | ATOK | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 449700 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 501761 | Sagpat Integrated School | KIBUNGAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305149 | Kibungan National High School | KIBUNGAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 502171 | Lubo Integrated School | KIBUNGAN | Lone | 1 |  | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 376700 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 305133 | Benguet National High School | LA TRINIDAD (Capital) | Lone | 1 | - | 585 | - | 585 | 13 | - | - | 1882400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1285700 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 502168 | Mogao Integrated School | MANKAYAN | Lone | 1 |  | 200 | - | 200 | 5 | - | - | 646500 | Regional Office Implementation | 55% Allocation for Regular Supplier | 442000 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 501810 | Tacadang Integrated School | KIBUNGAN | Lone | 1 | - | 70 |  | 70 | 1 | - | - | 222300 | Regional Office Implementation | 55% Allocation for Regular Supplier | 151400 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | CAR | Benguet | 135735 | Ciriaco Magno ES | TUBLAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 1 | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135748 | Damag ES Annex (Damag Proper) | AGUINALDO | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 380900 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 252600 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Ifugao |  | Asipulo National High School Annex | ASIPULO | Lone | 1 |  | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135813 | Banaue CS | BANAUE | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1502400 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135824 | Gohang ES | BANAUE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135825 | Kinakin ES | BANAUE | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135826 | Patilong ES | BANAUE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135827 | Poitan ES | BANAUE | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Ifugao | 135868 | Duit ES | KIANGAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | CAR | Ifugao |  | Lagawe NHS Annex | LAGAWE (Capital) | Lone | 1 |  | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | Lone |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | Lone | 1 | - | - | - | - | - | - | 14 | 158900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 126000 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 1
CY 2023 SF | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 63200 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 460900 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 164200 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | CAR | Mt. Province | 305256 | Tocucan National High School | BONTOC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 90500 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0
CY 2023 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | CAR | Mt. Province | 221004 | Cabunagan Primary School | TADIAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 141100 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1978000 | Completed | 1 | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | Lone | 1 | - | 720 | - | 720 | 16 | - | - | 2262240 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305085 | Dugong NHS | Bucay | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305092 | Pangtod NHS | BUCAY | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135192 | Pikek PS | DAGUIOMAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2022 SF | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | Lone | 1 | - | 810 | - | 810 | 18 | - | - | 2545020 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305102 | Tagodtod National High School | LAGANGILANG | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135202 | Baybayatin PS | LAGAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135142 | Quillat ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | Lone | 1 | - | - | 360 | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 305162 | Tublay School of Home Industries-Main | TUBLAY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135842 | Pitawan ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 305213 | Pasil National High School | PASIL | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305237 | Besao National High School | BESAO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136329 | Sabangan Elementary School | SABANGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305264 | Sadanga National Technical Vocational and Skills Training High School | SADANGA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Abra | 101016 | Abra Special Education Center | BANGUED (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134981 | Dangdangla Elementary School | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134983 | Sagap Elementary School | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134984 | San Antonio ES | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 318704 | Abra High School - Calot Extension | BANGUED (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134987 | Bangbangcag PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134988 | Bangcagan PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134990 | Bucay North ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134991 | Bugbog ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134992 | Calao ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134997 | Lublubnac PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134999 | Madalipay ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135001 | Pagala East PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501342 | Layugan Integrated School | BUCAY | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135026 | Abaquid ES | DANGLAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135039 | Padangitan ES | DANGLAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135016 | Cardona Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135021 | Mudiit ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135022 | Pacac ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135023 | Taping Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218501 | Libtec Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218521 | Lourdes Zapata Primary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135028 | Bulbulala ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135031 | Gongonot Elementary School | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135032 | Isit Elementary School | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135035 | Malabbaga ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135040 | Pidipid ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135042 | Sidongan PS | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135043 | Toon ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135047 | Bacag ES | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135055 | Buneg PS | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135064 | Lacub CS | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135067 | Lan-ag ES | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 318703 | Alfredo D. Bersamina NHS | LACUB | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135085 | Villa San Isidro ES | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218503 | Willy Castillo PS | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218514 | Taping Primary School | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305094 | Pulot National High School | LAGAYAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501341 | Ba-i Integrated School | LAGAYAN | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135136 | Langiden CS | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135137 | Mabungtot ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135138 | Malapaao ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135053 | Bonglo Elementary School | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135054 | Bulbulala PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135056 | Caoayan PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135060 | Diangay PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135063 | Kileng PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135068 | Lenneng ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135075 | Nalbuan ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135080 | Subagan PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135081 | Sucao ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218502 | Agat Primary School | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501115 | LICUAN INTEGRATED SCHOOL | LICUAN-BAAY (LICUAN) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135086 | Agumanay ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135088 | Ampalioc PS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135092 | Barit ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135094 | Botot ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135099 | Gayaman ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135102 | Lipting PS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135103 | Luba CS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135104 | Lul-luno ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501729 | TABANGAO IS | LUBA | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135049 | Bangilo ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135051 | Bayabas Elementary School | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135052 | Binasaran PS | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135061 | Dulao ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135070 | Liwang ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135071 | Malibcong CS | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135072 | Mataragan ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134993 | Catacdegan ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134996 | Liagan PS | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 134998 | Madago Elementary School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135005 | San Jose ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135007 | Sapdaan Elementary School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135009 | Sto. Tomas Barrio School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218520 | Casakgudan PS | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135120 | Dumayco Primary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135122 | Malamsit Elementary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135130 | Sta. Rosa Elementary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218519 | Tattawa Primary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135134 | Casilagan PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135139 | Nagdaingan ES | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135145 | Sulbec PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218510 | Pangtud PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218512 | Poblacion West PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 218517 | Banay PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135149 | Bolbolo ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135152 | Dalit ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135153 | Dintan ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305077 | Bolbolo NHS | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305083 | Dalit National High School | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305093 | Pilar Rural High School | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135168 | Abas ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135170 | Bantay Primary School | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135177 | Callaban PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135184 | Gangal Elementary School | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135186 | Lam-aoan PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135190 | Naguilian ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135191 | Nangas-Asan PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135193 | Sallapadan Bo. ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135195 | Ud-udiao ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135119 | Dalimag ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135123 | Manayday ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135126 | Olo ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305097 | San Isidro NHS | SAN ISIDRO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135197 | Alimosgan ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135201 | Baug PS | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135204 | Cabcaburao ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135209 | Daoidao ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135213 | Lam-Ag ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135218 | Nangobongan PS | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135221 | Quidaoen ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135224 | Silet ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135225 | Supiil ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135012 | Bagalay Elementary School | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135013 | Basbasa ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135014 | Bumagcat ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135018 | Don Marcos Rosales ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135025 | Velasco ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305086 | Gaddani NHS | TAYUM | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 500518 | Ananaao Integrated School | TAYUM | Lone | 1 | - | - | 120 | 120 | 3 | - | - | 393807.4303 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135087 | Alangtin Elementary School | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135089 | Amtuagan ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135093 | Batayan PS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135095 | Caocaoayan PS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135115 | Tubo CS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135116 | Tubtuba ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 135118 | Wayangan ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305084 | Dilong National High School | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305100 | Supo NHS | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 305103 | Tiempo NHS | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135672 | Omas Ampaguey ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135673 | Bayabas ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135675 | Ebbes ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135676 | Jose Gonzales ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135684 | Yabyabuan MG School | SABLAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 219527 | Amsalsal PS | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 305157 | Sablan NHS | SABLAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 318915 | Sablan NHS Extension-Balluay | SABLAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135720 | Baayan ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135724 | Langbis PS | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135725 | Dorencio ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135729 | Mamuyod ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135730 | Moran ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135732 | Pangablan Elementary School | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Benguet | 135735 | Ciriaco Magno ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135789 | Bukig Elementary School | ASIPULO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135792 | Duli Elementary School | ASIPULO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135801 | Nanlahyan PS | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135805 | Pula ES | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135806 | Pulpog PS | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 220001 | Cawayan PS - Annex (Alehwagon) | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 220006 | Asipulo CS - Annex | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 305174 | Natcak NHS | ASIPULO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 305175 | Camandag NHS | ASIPULO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135832 | Anao ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135834 | Bitu ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135835 | Cababuyan ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135837 | Humalophop ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135838 | Kayang PS | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135844 | Ubuag PS | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 135845 | Umalbong ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 220002 | Northern Cababuyan Elementary School - Annex | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Ifugao | 340118 | SHS within Namulditan ES | HINGYON | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136016 | Batong Buhay Elementary School | PASIL | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136022 | Colayo Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136023 | Dalupa Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136024 | Dangtalan Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136025 | Galdang Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136026 | Magsilay Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136027 | Pasil Central School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136028 | Pasil CS (Guinaang Annex ) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 136030 | Pasil CS ( Pugong Annex) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 220513 | Balinciagao ES - Limood Annex | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136188 | Latang Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136189 | Lias Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136190 | Lingoy Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136191 | Lingoy-Chatol Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136192 | Lunas Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136193 | Mog-ao Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136194 | Ogo-og Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | BARLIG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136237 | Bunga Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136240 | Gueday Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136241 | Lacmaan Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136243 | Masameyeo Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136244 | Panabungen Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136245 | Pangweo Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136246 | Payeo Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136247 | Suquib Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136317 | Data Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136319 | Gayang Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136320 | Labbay Primary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136322 | Legleg Primary School | SABANGAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136323 | Madepdeppas Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136325 | Napua Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136326 | Camatagan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136327 | Pingad-Bao-angan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136330 | Supang Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136331 | Tambingan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 319206 | Data National High School | SABANGAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136332 | Anabel Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136333 | Bekigan Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136334 | Belwang Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136336 | Demang Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136339 | Saclit Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305238 | Betwagan National High School | SADANGA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 319204 | Belwang National High School | SADANGA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136341 | Aguid Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136345 | Balugan Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136346 | Bangaan Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136348 | Kilong Primary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136349 | Nacagang Primary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305234 | Bangaan National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | CAR | Mt. Province | 319222 | Balugan National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1