## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | CATEGORY 2 | Unnamed: 46
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131457 | Ambacon ES | LAS NIEVES | 1st | 1 |  | Construction of Group Handwashing Facility for Elementary | 332182.19 |  | 327592.85 | completed | 1 | February 18, 2025 | February 18, 2025 | WINS 2024 - R XIII - AGUSAN DEL NORTE - 001 | WINS 2024 - R XIII - AGUSAN DEL NORTE - 001 | September 19, 2024 |  | November 19, 2024 |  |  | J-R3 Construction and Supply | WITH APPROVED REALIGNMENT from Baleguian ES | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 1
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1st | 1 |  | Construction of School Clinic | 3727536.02 |  | 3141911.69 | On-going | 0.4 | March 11, 2025 |  | SCHOOL CLINIC 2024 - R XIII - AGUSAN DEL NORTE - 003 | SCHOOL CLINIC 2024 - R XIII - AGUSAN DEL NORTE - 003 | September 30, 2024 | October 14, 2024 | October 24, 2024 | December 20, 2024 | December 23, 2024 | J-R3 Construction and Supply | with Time Extension | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0.4 | 0
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131546 | Santiago CES | SANTIAGO | 2nd | 1 |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 1921578.86 |  | 1830300.26 | On-going | 0.4 | [8 empty] | March 11, 2025 | MCLA Construction | with RTA submitted to CO; awaiting downloading of subaro | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0.4
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1st | 1 |  | Construction of School Clinic | 3727536.02 |  |  | completed | 1 | January 11, 2024 | Feb 19, 2025 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | December 1, 2024 | December 11, 2024 | January 4, 2024 | August 27, 2024 | October 14, 2024 | ILMAR CONSTRUCTION & SUPPLY | COMPLETED WAITING FOR FINAL INSPECTION | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 1
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1st |  |  | Construction of 2 Units Group Handwashing Facility for Elementary | 602766.77 |  |  | completed | 1 | November 27, 2024 | November 20, 2024 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | December 1, 2024 | December 11, 2024 | January 4, 2024 | August 27, 2024 | October 14, 2024 | ILMAR CONSTRUCTION & SUPPLY | COMPLETED WAITING FOR FINAL INSPECTION | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 1
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2nd | 1 |  | Construction of School Clinic | 3823114.17 |  | 2923591.71 | Completed | 1 | November 22, 2024 | November 4, 2024 | 10312534 | 10312534 | November 13, 2023 | November 9, 2023 | December 6, 2023 | May 24, 2024 | May 24, 2024 | ETP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | Lone | 1 |  | Construction of Group Handwashing Facility | 355236.65 |  | 900590.69 | completed | 1 | August 21, 2024 | August 21, 2024 | INFRA2023-005 | INFRA2023-005 | December 5, 2023 | December 11, 2023 | January 3, 2024 | January 29, 2024 | May 24, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 132311 | Kanihaan Elementary School | LIBJO (ALBOR) | Lone | 1 |  | Construction of Group Handwashing Facility | 412704.93 |  | 320750.32 | completed | 1 | August 21, 2024 | August 21, 2024 | INFRA2023-006 | INFRA2023-005 | December 6, 2023 | December 12, 2023 | January 4, 2024 | January 30, 2024 | May 25, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 132514 | Borres-Omega Elementary School | SAN JOSE (Capital) | Lone | 1 |  | Construction of Group Handwashing Facility | 362304.93 |  | 288158.47 | completed | 1 | August 21, 2024 | August 21, 2024 | INFRA2023-007 | INFRA2023-005 | December 7, 2023 | December 13, 2023 | January 5, 2024 | January 31, 2024 | May 26, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132127 | Corregidor Elementary Schoo | DAPA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 1 | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132128 | Dagohoy Elementary School | DAPA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 1 | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132178 | San Fernando Elementary School | DEL CARMEN | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 1 | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132147 | Catangnan Elementary School | GENERAL LUNA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 1 | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd | 1 |  | Water and Sanitation Facilities - 4-Seater | 1125598.1 |  | 961297.61 | completed | 1 | October 28, 2024 | October 18, 2024 | 2023-11-575 | FY-2023-INFRA-013 | February 24, 2024 | March 4, 2024 | March 18, 2024 | July 26, 2024 | August 9, 2024 | ARDRAW CONSTRUCTION AND SUPPLY | Re-bid; 1st Bidding Failure | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd |  |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 2226633.74 |  | 1994244.69 | completed | 1 | November 12, 2024 | November 21, 2024 | 2023-11-576 | FY-2023-INFRA-014 | December 10, 2023 | December 18, 2023 | January 5, 2024 | July 27, 2024 | August 9, 2024 | RJB CONSTRUCTION AND SUPPLY | with liquidated damages | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Norte | 132472 | Ellaperal ES | PLACER | 2nd | 1 |  | Construction of Toilets | 1001168.65 |  | 998235.23 | completed | 1 | July 27, 2024 | October 20, 2024 | 2024-001-WATSAN-CARAGA | INFRA002-2024 | November 9, 2023 | November 28, 2023 | November 28, 2023 | May 9, 2024 | May 13, 2024 | RJB CONSTRUCTION AND SUPPLY | With Time Extension/with LD | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Norte | 132472 | Ellaperal ES | PLACER | 2nd |  |  | Construction of Water System | 2084603.55 |  | 2081581.6 | Completed | 1 | July 28, 2024 | October 20, 2024 | 2024-001-WATER SYSTEM-CARAGA | INFRA001-2024 | November 9, 2023 | November 16, 2023 | November 28, 2023 | May 9, 2024 | May 13, 2024 | RJB CONSTRUCTION AND SUPPLY | With Time Extension/with LD | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Sur | 304877 | Carrascal National High School | CARRASCAL | 1st | 1 |  | Construction of School Clinic | 3349173.05 |  | 2536593.52 | Completed | 1 | March 12, 2025 | March 12, 2025 | SCHOOL CLINIC 2023 - R XIII - SURIGAO DEL SUR - 045 | 009 - 2024 | November 9, 2023 | November 15, 2023 | November 30, 2023 | February 19, 2024 | October 14, 2024 | TRIDENT ENGINEERING SERVICES | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st | 1 |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 1073605.29 |  | 2634115.51 | COmpleted | 1 | August 6, 2024 | Sept. 20, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st |  |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish | 352744.25 |  | 259813.99 | COmpleted | 1 | July 27, 2024 | August 26, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st |  |  | Construction of One (1) Unit One (1) Storey School Clinic | 3669893.83 |  | 2634115.51 | COmpleted | 1 | August 26, 2024 | Sept. 20, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1 | 0 |  | 4.25
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 131532 | Luis B. Azura Sr. Memorial ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245012.59 | BATCH 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 131536 | Tagbongabong ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245012.59 | BATCH 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 211510 | Poblacion Doz ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY | 154901.65 | BATCH 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132392 | Bagumbayan Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 312598.28 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272539.46 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132400 | New Mabuhay Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 311915.78 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272374.54 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 267198.6 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 269238.26 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 268530.05 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304809 | Osmeña-Sto. Niño National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 273301.69 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272515.24 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 288175.99 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 324401 | Llamera National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 274036.69 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132554 | Malinao Elementary School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 283907.25 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132558 | Sta Cruz Elementary School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 284673.26 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304854 | Tubajon National High School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 280774.54 | BATCH 1 |  | Completed | 1 | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238084.63 | BATCH 1 | 238047.35 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING (MODIFIED) | 86389.18 | BATCH 1 | 86348.69 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239467.07 | BATCH 1 | 239424.42 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 244760.64 | BATCH 1 | 243510.15 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132164 | Bitoon Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245995.82 | BATCH 1 | 244748.31 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132168 | Esperanza Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247049.6 | BATCH 1 | 245797.68 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132170 | Jamoyaon Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243894.53 | BATCH 1 | 242644.95 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241549.63 | BATCH 1 | 240300.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132180 | Tuboran Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246006.28 | BATCH 1 | 244736.44 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246266.38 | BATCH 1 | 245034.8 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241549.63 | BATCH 1 | 238009.55 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132148 | Consuelo Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 312008.76 | BATCH 1 | 311830.64 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241654.63 | BATCH 1 | 239922.89 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 243919.43 | BATCH 1 | 240191.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241686.13 | BATCH 1 | 238009.55 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132159 | Sta. Fe Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241595.83 | BATCH 1 | 239922.89 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242910.39 | BATCH 1 | 240191.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243005.93 | BATCH 1 | 240191.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132181 | Caridad Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247081.1 | BATCH 1 | 246984.18 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132183 | Datu Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY (Cement Finished) | 137908.58 | BATCH 1 | 137816.81 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132187 | Maasin Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 248065.5 | BATCH 1 | 247950.81 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 248076 | BATCH 1 | 243937.25 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132192 | San Roque Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245960.08 | BATCH 1 | 245919.69 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239134.63 | BATCH 1 | 237885.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238977.13 | BATCH 1 | 238912.02 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY (Cement Finished) | 137593.51 | BATCH 1 | 137571.74 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237784.34 | BATCH 1 | 237780.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 310007.82 | BATCH 1 | 309898.64 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132202 | Sto. Nino Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238893.13 | BATCH 1 | 238515.09 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132203 | Tambacan Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 309903.51 | BATCH 1 | 309851.29 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132206 | Alegria Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 232578.56 | BATCH 1 | 232555.7 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132209 | Libertad Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 233461.91 | BATCH 1 | 233404.36 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235186.63 | BATCH 1 | 235161.89 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132212 | Rizal Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 233593.16 | BATCH 1 | 233577.3 | Completed | 1 | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 230508.18 | BATCH 1 | 205068.48 | Completed | 1 | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132322 | Alipao ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 1 | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132327 | Ombong ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 1 | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 1 | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132345 | Cambuayon ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132347 | Dugsangon ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304817 | Campo National High School | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 244375.04 | BATCH 1 | 201588.81 | Completed | 1 | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132452 | Bunyasan ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132455 | Cantapoy ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236913.18 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236913.18 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132461 | Masgad ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239433.18 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304818 | Cantapoy National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241225.04 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304832 | Bunyasan National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247000.04 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237025.04 | BATCH 1 | 238804.5 | Completed | 1 | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132337 | Jubgan ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225258.18 | BATCH 1 | 196417.18 | Completed | 1 | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225258.18 | BATCH 1 | 196417.18 | Completed | 1 | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304843 | San Francisco National High School | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 196417.18 | Completed | 1 | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132526 | Dakung Patag ES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222108.18 | BATCH 1 | 194914.87 | Completed | 1 | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220533.18 | BATCH 1 | 194914.87 | Completed | 1 | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132535 | Tagbayani ES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222108.18 | BATCH 1 | 194914.87 | Completed | 1 | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. Memorial National High School | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 194914.87 | Completed | 1 | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 317808 | Dakung Patag National High School | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 194914.87 | Completed | 1 | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242583.18 | BATCH 1 | 208921.69 | Completed | 1 | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132543 | Laurel ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242583.18 | BATCH 1 | 208921.69 | Completed | 1 | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132544 | Lower Libas ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 208921.69 | Completed | 1 | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 208921.69 | Completed | 1 | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247525.04 | BATCH 1 | 208921.72 | Completed | 1 | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132567 | Timamana ES | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 214338.18 | BATCH 1 | 189530.34 | Completed | 1 | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218125.04 | BATCH 1 | 189530.34 | Completed | 1 | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218125.04 | BATCH 1 | 189530.34 | Completed | 1 | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132600 | Amag Elementary School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 230840.48 | BATCH 1 | 160261.49 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 001 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY SCHOOLS (WITH ROOFING, AND TILE FINISH COUNTER) | 232780.08 | BATCH 1 | 162256.7 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 002 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (WITH ROOFING, AND TILE FINISH COUNTER) | 239360.09 | BATCH 1 | 163234.65 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 003 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 223599.52 | BATCH 1 | 160833.41 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 004 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132685 | Gacub Elementary School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 251575.68 | BATCH 1 | 160810.28 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 005 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 304875 | Carmen National Agricultural High School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY SCHOOLS (WITH ROOFING, AND TILE FINISH COUNTER) | 225680.8 | BATCH 1 | 162300.75 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 006 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (WITH ROOFING, AND TILE FINISH COUNTER) | 230631.71 | BATCH 1 | 163277.34 | Completed | 1 | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 007 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132166 | Cancohoy Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259943.48 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132166 | Cancohoy Elementary School | DEL CARMEN | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132167 | Dumoyog Primary School | DEL CARMEN | 2 | 1 |  | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259943.48 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132173 | Lobogon Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254979.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132174 | Mabuhay Primary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259975.5 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132177 | Quezon Primary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 232510.86 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132153 | La Januza Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132153 | La Januza Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Improvement of Water System (Solar Powered Pump and Stainless Steel Tank and Piping) | 550000 | BATCH 2 | 549970.83 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132154 | Libertad Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132154 | Libertad Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132156 | Malinao Elementary Schol | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132160 | Suyangan Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269940.27 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132160 | Suyangan Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Secondary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 1 | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)