## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2024 SF | NCR | Manila | 305319 | Eulogio Rodriguez Vocational High School | CITY OF MANILA | 6th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136481 | J. Zamora Elementary School | PANDACAN | 6th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305317 | Elpidio Quirino High School | SAMPALOC | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305315 | Victoriano Mapa High School | SAN MIGUEL | 6th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305314 | Gen. E. Aguinaldo Integrated School | SANTA ANA | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6th | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 305399 | TaÃ±ong HS | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 305401 | Marikina Science HS | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 319904 | Kalumpang National High School | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 1440 | - | - | 1440 | 32 | - | - | 4928000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 150052 | Concepcion Integrated School | CITY OF MARIKINA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd | 1 | - | 1350 | - | 1350 | 30 | - | - | 4620000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Marikina City | 500052 | Concepcion Integrated School | CITY OF MARIKINA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 136870 | Wawa Elementary School | CITY OF NAVOTAS | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Pasay City | 136599 | Marcela Marcelo ES | PASAY CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Pasig City | 305422 | Rizal Experimental Station And Pilot School for Cottage Industries (RESPSCI) | CITY OF PASIG | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 340694 | Lucresia Kasilag Senior High School (SHS within E. Abada ES) | QUEZON CITY | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305337 | Justice Cecilia Muñoz Palma High School | QUEZON CITY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305352 | Juan Sumulong High School | QUEZON CITY | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305338 | Maligaya HS | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305341 | San Bartolome HS | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305635 | West Fairview High School | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 360867 | Leandro Locsin Integrated School | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Quezon City | 305344 | Sauyo HS | QUEZON CITY | 6th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Taguig | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 136797 | Malinta Elementary School | CITY OF VALENZUELA | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 136812 | Roberta de Jesus ES | CITY OF VALENZUELA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305436 | Polo National High School | CITY OF VALENZUELA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305437 | Dalandanan National High School | CITY OF VALENZUELA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 320404 | Bignay National High School | CITY OF VALENZUELA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305441 | Valenzuela NHS | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305443 | Gen. T. de Leon NHS | CITY OF VALENZUELA | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305444 | Maysan National High School | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136431 | T. Paez Integrated School (Elem.) | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136432 | J. P. Rizal Elementary School | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136434 | Gen. Vicente Lim Elementary School | TONDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136440 | J. C. de Jesus Elementary School | TONDO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136441 | R. Almario Elementary School | TONDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305288 | Dr. Juan G. Nolasco High School | TONDO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305289 | T. Paez Integrated School | TONDO | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305290 | Gregorio Perfecto High School | TONDO | 1st | 1 | - | 169 | - | 169 | 4 | - | - | 579700 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305292 | Antonio J. Villegas Vocational High School | TONDO | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136419 | Barrio Obrero Elementary School | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136420 | F. G. Calderon Elementary School | TONDO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136426 | Francisco Benitez Elementary School | TONDO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136427 | Lakan Dula Elementary School | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136429 | Librada Avelino ES | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136444 | Gen. Maximo Hizon Elementary School | TONDO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3rd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305303 | Raja Soliman Science and Technology High School | SAN NICOLAS | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305312 | Manila Science High School | ERMITA | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305311 | Manila High School | INTRAMUROS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136477 | Aurora A. Quezon Elementary School | MALATE | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136478 | H.J. Atienza Elementary School | MALATE | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136473 | Justo Lukban Elementary School | PACO | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 319401 | Pres. Corazon C. Aquino High School/Manila HS Annex | PORT AREA | 5th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 | 1260 | - | - | 1260 | 28 | - | - | 3791200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | City of San Juan | 136750 | Nicanor C. Ibuna ES | CITY OF SAN JUAN | Lone | 1 | 720 | - | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Las Piñas City | 136777 | Las Piñas Elementary School Central | CITY OF LAS PIÑAS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Las Piñas City | 340548 | Las Piñas City National Senior High School - Manuyo Campus | CITY OF LAS PIÑAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136690 | Makati ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136703 | Hen. Pio del Pilar ES Main | CITY OF MAKATI | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136707 | Maximo Estrella ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136714 | La Paz ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 305407 | San Isidro NHS | CITY OF MAKATI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 305409 | Gen. Pio del Pilar NHS | CITY OF MAKATI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136692 | Comembo ES | CITY OF MAKATI | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136693 | East Rembo ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136694 | Fort Bonifacio ES | CITY OF MAKATI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136695 | Pembo ES | CITY OF MAKATI | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136696 | Rizal ES | CITY OF MAKATI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 136711 | Pitogo ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 305411 | Fort Bonifacio HS | CITY OF MAKATI | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 305412 | Benigno "Ninoy" S. Aquino HS | CITY OF MAKATI | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Makati City | 320001 | Pitogo HS | CITY OF MAKATI | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305300 | Cayetano Arellano High School | SANTA CRUZ | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305304 | Esteban Abada High School | SAMPALOC | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305306 | Ramon Magsaysay High School | SAMPALOC | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC | 4th | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136467 | P. Burgos ES | TONDO | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5th | 1 | - | 495 | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2023 SF | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-10-11 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1st |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-10-11 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136630 | Sta. Quiteria ES | KALOOKAN CITY | 1st | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1640000 | Completed | 1 | 2025-02-16 | 2024-10-02 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136640 | Sto. Niño Elementary School | KALOOKAN CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-10-04 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 319701 | Cielito Zamora Senior High School | KALOOKAN CITY | 1st | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 | 2024-10-05 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136623 | Barrio San Jose ES | KALOOKAN CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 | 2024-09-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Las Piñas City | 136779 | Pulanlupa ES | CITY OF LAS PIÑAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Las Piñas City | 305430 | Las Piñas National High School | CITY OF LAS PIÑAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Technical Vocational HS | City Of Las Piñas | Lone | 1 | 0 | 0 | 640 | 640 | 16 | 0 | 0 | 2068800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1464000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Golden Acres ES - 8CL Golden Acres SHS - 24CL | Las Piñas City | Lone | 1 | 0 | 0 | 1280 | 1280 | 32 | 0 | 0 | 4137600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2928000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 |  | 1
CY 2023 SF | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-11-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-11-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Mandaluyong City | 502026 | Senate President Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 | 2025-03-07 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 4054400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2996000 | Completed | 1 | 2025-02-16 | 2025-04-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 1 | 2025-02-16 | 2025-04-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136423 | Mariano Ponce Elementary School | TONDO | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 1 | 2025-02-16 | 2025-05-02 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 1 | 2025-02-16 | 2025-05-05 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2nd | 1 | 0 | 0 | 480 | 480 | 12 | 0 | 0 | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1146000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3rd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 | 2025-05-06 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 900 | 0 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 1 | 2025-02-16 | 2025-04-16 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4th | 1 | 900 | 0 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 1 | 2025-02-16 | 2025-04-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5th | 1 | 990 | 0 | 0 | 990 | 22 | 0 | 0 | 3185600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2354000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5th | 1 | 1080 | 0 | 0 | 1080 | 24 | 0 | 0 | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2568000 | Completed | 1 | 2025-02-16 | 2025-05-09 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6th | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 1 | 2025-02-16 | 2025-04-15 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6th | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 4054400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2996000 | Completed | 1 | 2025-02-16 | 2025-05-03 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 1
CY 2023 SF | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2025-04-29 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Muntinlupa City | 281541 | Poblacion ES | Muntinlupa | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Navotas | 305453 | Navotas NHS | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Paranaque City | 136763 | F. Serrano Sr. ES - Don Bosco | CITY OF PARAÑAQUE | 2nd | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Pasig City | 136743 | San Miguel Elementary School | CITY OF PASIG | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Pasig City | 136731 | Oranbo ES | Pasig City | Lone | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Pasig City | 136727 | Kalawaan ES | Pasig City | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Pasig City | 340654 | SHS in Buting, Pasig City | Pasig City | Lone | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2025-03-05 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1st | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 305328 | Pugad Lawin HS | QUEZON CITY | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2nd | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 3636332 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5th | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5th | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136519 | Lucas R. Pascual Mem. ES | QUEZON CITY | 6th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | City of San Juan | 305609 | San Juan City Technical-Vocational and Livelihood -Senior High School | CITY OF SAN JUAN | Lone | 1 | 0 | 1080 | 0 | 1080 | 24 | 0 | 0 | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2460000 | Completed | 1 | 2025-02-16 | 2025-03-13 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1st | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Pateros | 1st | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1st | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 228002 | Gat. Andres Bonifacio Elmentary School | TAGUIG CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2nd | 1 | 0 | 900 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 1 | 2025-02-16 |  |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-11-27 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Valenzuela City |  | Veinte Reales HS | CITY OF VALENZUELA | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-11-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1640000 | Completed | 1 | 2025-02-16 | 2024-11-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd |  | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 | 2024-11-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 1 | 2025-02-16 | 2024-11-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1st | 1 | 0 | 260 | 0 | 260 | 6 | 0 | 0 | 837800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 593000 | Completed | 1 | 2025-02-16 | 2024-10-02 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY | 2nd | 1 | 0 | 90 | 0 | 90 | 2 | 0 | 0 | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 205000 | Completed | 1 | 2025-02-16 | 2024-09-09 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2nd | 1 | 585 | 0 | 0 | 585 | 13 | 0 | 0 | 1882400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1332500 | Completed | 1 | 2025-02-16 | 2024-09-25 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 136609 | Kaunlaran ES | KALOOKAN CITY | 2nd | 1 | 315 | 0 | 0 | 315 | 7 | 0 | 0 | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 717500 | Completed | 1 | 2025-02-16 | 2024-09-26 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2023 SF | NCR | Caloocan City | 305391 | M. B. Asistio, Sr. HS | KALOOKAN CITY | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 1 | 2025-02-16 | 2024-09-09 |  | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1