## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2023 SF | REGION III | Aurora | 104515 | Dibut ES | SAN LUIS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | REGION III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2nd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 1
CY 2023 SF | REGION III | Bulacan | 104804 | F. Mendoza Memorial ES | CALUMPIT | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | REGION III | Nueva Ecija | 105817 | Dimasalang Sur ES | TALAVERA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | REGION III | Nueva Ecija | 105588 | Sabangan Es To Palale Es | General Tinio (Papaya) | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1