## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | CATEGORY 2 | Unnamed: 46
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 2 | CONSTRUCTION OF TWO (2) UNITS OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 277014.74 | BATCH 1 | 274077.03 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100108 | Saoit ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100109 | Tanap ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100106 | Nagsurot Elementary School | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100050 | Dumalneg ES | DUMALNEG | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 138507.37 | BATCH 1 | 137749.04 | Completed | 1 | 2022-10-01 | 2022-09-30 |  |  | 2022-03-07 |  | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100720 | Bungro ES | SAN ILDEFONSO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100721 | Busiing ES | SAN ILDEFONSO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100615 | Pudoc Elementary School | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100614 | Nagtupacan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100661 | Pangada-Cabaroan Elementary School | SANTA CATALINA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100657 | Bernardo P. Ragasa Elementary School | SANTA CATALINA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 1 | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100345 | Tangilig ES | SUGPON | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100588 | Tubalina Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 1 | Construction of 4-seater Toilet | 576616.13 | BATCH 1 | 497261.21 | Completed | 1 | 2/16/2023 | 2/16/2023 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100569 | Dapdappig Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 1 | 2/16/2023 | 2/16/2023 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100367 | Tay-ac Elementary School | LIDLIDDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100553 | Taleb ES | NAGBUKEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 501026 | Bantugo-Mission Integrated School | NAGBUKEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 211937.93 | BATCH 1 | 195852.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100554 | Abaccan ES | SIGAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 195852.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 150504 | Matallucod PS | SIGAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 197690.78 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100337 | DANAC ELEMENTARY SCHOOL | SUGPON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 1 | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 |  | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300105 | Cambaly National High School | BAGULIN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 576355.99 | BATCH 1 | 569904.12 | Completed | 1 | 2022-09-08 | 2022-08-30 | LU - SHF - 2022 -01 |  | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100860 | Bagulin CES | BAGULIN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 556856.8 | BATCH 1 | 544372.51 | Completed | 1 | 2022-09-08 | 2022-08-30 | LU - SHF - 2022 -02 |  | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | VILLAR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100934 | Burgos CS | BURGOS | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 535452.49 | BATCH 1 | 525027.01 | Completed | 1 | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -03 |  | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | VILLAR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100998 | Cuenca ES | PUGO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 529334.23 | BATCH 1 | 520915.2 | Completed | 1 | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -04 |  | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300131 | Pugo Central National High School | PUGO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 530308.03 | BATCH 1 | 523933.32 | Completed | 1 | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -05 |  | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 1 | HEALTH FACILITIES | 406308.51 | BATCH 1 | 698595.17 | Completed | 1 | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -06 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 702386.18 | BATCH 2 | 698595.17 | Completed | 1 | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -06 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 702386.18 | BATCH 2 | 701773.25 | Completed | 1 | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -07 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100899 | Ma. Cristina ES | BANGAR | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 696429.23 | BATCH 2 | 695810.81 | Completed | 1 | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -08 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100901 | Paratong ES | BANGAR | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 695455.43 | BATCH 2 | 695187.04 | Completed | 1 | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -09 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 501196 | Parian Este Integrated School | BAUANG | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 705700.25 | BATCH 2 | 701933.55 | Completed | 1 | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -10 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100964 | Oaqui ES | LUNA | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 704226.68 | BATCH 2 | 701373.47 | Completed | 1 | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -11 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300124 | Oanari National High School | LUNA | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 704226.68 | BATCH 2 | 701373.47 | Completed | 1 | 2022-11-30 | November 28, 2022 | LU - SHF - 2022 -12 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 101075 | Urbiztondo ES | SAN JUAN | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 705484.66 | BATCH 2 | 704366.82 | Completed | 1 | 2022-11-30 | November 28, 2022 | LU - SHF - 2022 -13 |  | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction