## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE | Unnamed: 45
QRF 2019 | Region I | La Union | 101069 | Naguituban ES | San Juan | 1 | 1 | 2 | 1STY 2CL | 3607027.98 | 1 | 3583247.64 | Completed | 1 | 2019-10-20 | 2019-09-10 |  |  | 2019-06-06 | 2019-06-13 | 2019-06-28 | 2019-07-15 | 2019-07-22 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | previous yrs | FIRE |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region I | Candon City | 235501 | Candon South Central School SPED Center | CITY OF CANDON | 2 | 1 | 2 | REPAIR/ REHABILITATION | 901319.11 | 1 | 895387.37 | Completed | 1 | 2022-09-16 | 2022-11-09 |  |  | 2022-05-27 | 2022-05-31 | 2022-05-31 | 2022-07-13 | 2022-07-18 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1819327.09 | 1 | 1811418.37 | Completed | 1 | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-01 | 2022- LU-01 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100875 | Balaoan CES | BALAOAN | 1 | 1 | 11 | REPAIR/ REHABILITATION | 6693187.73 | 1 | 6527091.32 | Completed | 1 | 2022-12-22 | 2022-12-21 | QRF2022-RO1-LU-02 | 2022 - LU - 02 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.M.B.M. CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 1 | 0 | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100911 | Bauang North CS | BAUANG | 2 | 1 | 3 | REPAIR/ REHABILITATION | 1801364.18 | 1 | 1791987.88 | Completed | 1 | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-03 | 2022 - LU - 03 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | Laoag City | 153001 | Sto. Nino Elementary School | LAOAG CITY (Capital) | 1 | 1 | 3 | REPAIR/ REHABILITATION | 571180.68 | 1 | 567920.37 | Completed | 1 | Sept.18, 2022 | Sept. 15,2022 |  |  | June, 2022 | june, 2022 | 2022-07-01 | 2022-07-15 | 2022-08-04 | Elocin Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 101166 | Alaminos Central School | CITY OF ALAMINOS | 1st | 1 | 17 | REPAIR OF CLASSROOMS | 28000000 | 1 | Php27,723,177.18 | completed | 1 | 12/30/2023 | 12/19/2023 | 2023-03-001 | SPF-QRF2023-04-001 | March 14,2023-April 3, 2023 | 3/22/2023 | 2023-04-04 | 4/17/2023 | 4/25/2023 | Manimeld's construction and Iron Works | with additive VO- 276,822.82, revised contract amount 28,000,000, revised Completion date DEcember 30, 2023. Revised contract amount 28,000,000.00 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300155 | Alaminos City National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 54000000 | 1 | 27852257.7 | Completed | 1 | 5/17/2024 |  | 2023-07-12 | 2023-08-29 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Aylan Construction & Trading | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0.994 | 0.006 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300260 | Telbang National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 49200000 | 1 | 37566348.03 | Completed | 1 | 3/25/2024 |  | 2023-07-12 | 2023-08-28 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/29/2023 | T.G. Ocampo Construction and Surveying Services | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0.9874 | 0.0126 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 3272296.8 | 1 | 2727538.84 | Completed | 1 | 12/19/2023 | 12/17/2023 | 23043 | 23014.2 | 4/18/2023 | 4/26/2023 | 2023-08-06 | 6/19/2023 | 6/19/2023 | Elocin Construction | Savings (Php 544,757.96) was utilized to fund the project Repair and Rehabilitation of 5 Classrooms of the same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 40 | Replacement | 140000000 | 1 | 50451627.8 | Completed | 1 | 5/17/2024 |  | 2023-07-12 | 2023-08-31 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | ASS Construction/ MA Tejada Construction (Joint Venture) | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0.9502 | 0.0498 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 1188260.78 | 1 | 50525408.86 | Completed | 1 | 5/17/2024 |  | 2023-07-12 | 2023-08-31 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | ASS Construction/ MA Tejada Construction (Joint Venture) | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2nd | 1 | 4 | Replacement | 12000000 | 1 | 1178082.17 | Ongoing | 0.8538 | 2023-05-08 | 2023-05-08 | PB-INFRA-01-2023 |  | 3/26/2023 | 4/18/2023 | 4/18/2023 | 2023-04-05 | 2023-08-05 | M.A. Tejada Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.8538 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 8 | REPAIR OF CLASSROOMS | 4000000 | 1 | 3990008.65 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | VIKING III BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4th | 1 | 20 | REPAIR OF CLASSROOMS | 6000000 | 1 | 5908391.57 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | 24 | REPAIR OF CLASSROOMS | 6000000 | 1 | 4913922.28 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELMUEL JAY TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4th | 1 | 18 | REPAIR OF CLASSROOMS | 7000000 | 1 | 6943753.13 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | A.S.S. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102170 | North Central Elementary School | DAGUPAN CITY | 4th | 1 | 3 | REPAIR OF CLASSROOMS | 2100000 | 1 | 2086111.66 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELMUEL JAY TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4th | 1 | 5 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2971417.4 | completed | 1 | 12/13/2023 | 12/13/2023 |  |  | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELGRAM TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | 3 | Replacement | 9000000 | 1 | 7586101.37 | Completed | 1 | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/16/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 3 | Replacement | 9000000 | 1 | 7586101.37 | completed | 1 | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 | 8990670.28 | Completed | 1 | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-33 | 2023-06-07 | 7/16/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 | 8990670.28 | completed | 1 | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-33 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 10 | Replacement | 30000000 | 1 | 24413054.65 | Ongoing | 0.8 | 5/17/2024 |  | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0.8 | 0 | [6 empty] | REPLACEMENT | ongoing
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 2764628.2477 | 1 | 2262662.78 | Completed | 1 | 10/25/2023 | 12/27/2023 | PB-03-2023-1 | PB-03-2023-1 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100152 | Marcos Central School | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1842214.5794 | 1 | 1668320.78 | Completed | 1 | 7/26/2023 | 2023-05-08 | PB-03-2023-2 | PB-03-2023-2 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3858132.46 | 1 | 3011166.41 | Completed | 1 | 11/22/2023 | 12/27/2023 | PB-03-2023-4 | PB-03-2023-4 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2433485.53 | 1 | 1859917.48 | Completed | 1 | 2023-01-12 | 12/27/2023 | PB-03A-2023-3 | PB-03A-2023-3 | 4/13/2023 | 4/19/2023 | 2023-02-05 | 2023-08-05 | 5/29/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 100501 | Magsingal North Central School | MAGSINGAL | 1st | 1 | 12 | Replacement | 31559226.85 | 1 | 31529226.85 | Ongoing | 0.75 | 9/28/2024 |  | 2023-07-12 | 2023-08-35 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0.75 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 1410280.53 | 1 | 1409123.18 | Completed | 1 | 8/19/2023 | 8/18/2023 | 2023-04002-PB-Works |  | 4/24/2023 | 2023-02-05 | 5/23/2023 | 5/31/2023 | 6/21/2023 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 1880259.3 | 1 | 1454728.12 | Completed | 1 | 8/19/2023 | 8/18/2023 | 2023-04002-PB-Works |  | 4/24/2023 | 2023-02-05 | 5/23/2023 | 5/31/2023 | 6/21/2023 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300095 | Bacnotan National High School | BACNOTAN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1690747.91 | 1 | 1688435.11 | Completed | 1 | 7/18/2023 | 2023-12-07 | QRF2022-RO1-LU-01 | 2022 - LU - 04 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3295309.0192 | 1 | 2570259.41 | Completed | 1 | 2023-06-08 | 2023-02-08 | QRF2022-RO1-LU-06 | 2022 - LU - 06 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | DPV BUILDERS AND CONSTRUCTION SUPPLY | COMPLETED INCLUDING SSAVINGS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st |  | 12 | REPAIR OF CLASSROOMS | 6453979 | 1 | 4975440.38 | Completed | 1 | 2023-05-09 | 2023-01-09 | QRF2022-RO1-LU-07 | 2022-LU-07 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | DPV BUILDERS AND CONSTRUCTION SUPPLY | COMPLETED INCLUDING SSAVINGS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 100860 | Bagulin CES | BAGULIN | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1319380.58 | 1 | 1296139.72 | Completed | 1 | 7/17/2023 | 2023-12-07 | QRF2022-RO1-LU-05 | 2022-LU-05 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 101001 | Pugo Central School | PUGO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3610020.2541 | 1 | 3599857.82 | Completed | 1 | 2023-06-08 | 2023-02-08 | QRF2022-RO1-LU-08 | 2022-LU-08 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | EE MADAYAG CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 101096 | Damortis ES | SANTO TOMAS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3245119.9514 | 1 | 3204773.82 | Completed | 1 | 2023-06-08 | 2023-02-06 | QRF2022-RO1-LU-09 | 2022-LU-09 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | EE MADAYAG CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1965217.36 | 1 | 1965207.26 | Completed | 1 | June 01,2023 | August 18,2023 |  |  |  |  | 2/28/2023 | 3/15/2023 | 3/31/2023 | Elocin Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101132 | AGNO CENTRAL SCHOOL | AGNO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 927125.7 | 1 | 921100 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 8 | Replacement | 21412474.28 | 1 | 23887556.05 | Ongoing | 0.994 | 3/27/2024 |  | 2023-07-12 | 2023-08-37 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | MCB Construction & Supply | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0.994 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2781377.1 | 1 | 2769811.29 | Completed | 1 | 10/26/2023 | 2023-11-10 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Angelina T. Dizon Construction And Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1847200 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500618 | Pangascasan IS | SUAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1370306.45 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 8 | Replacement | 24934327.79 | 1 | 21465233.64 | completed | 1 | 2/26/2024 | 11/20/2024 | 2023-07-12 | 2023-08-36 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1824572.29 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Aldana Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 12 | Replacement | 32948933.15 | 1 | 29766091.35 | Ongoing | 0.6 | 9/16/2024 |  | 2023-07-12 | 2023-12-84 | 2023-06-07 | 7/13/2023 | 11/13/2023 | 12/19/2023 | 12/22/2023 | MCB Construction & Supply | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0.4936 | 0.1064 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6943245.24 | Completed | 1 | 2023-08-11 | 10/18/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 2023-10-07 | 2023-12-07 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5525014.04 | Completed | 1 | 11/22/2023 | 11/21/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 7/24/2023 | 7/26/2023 | WM Salayog constructiona nd SUpply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 16 | Replacement | 40963538.51 | 1 | 34088332.04 | Ongoing | 0.6 | 9/16/2024 |  | 2023-07-12 | 2023-12-84 | 2023-06-07 | 7/13/2023 | 11/13/2023 | 12/19/2023 | 12/22/2023 | MCB Construction & Supply | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0.5077 | 0.0923 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9210922.62 | Completed | 1 | 10/26/2023 | 10/24/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | ABC East Multi Builders And Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5530867.38 | Completed | 1 | 10/26/2023 | 10/24/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Manimeld'S Construction And Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6933376.41 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Elmuel Jay Trading And Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive NHS | CALASIAO | 3rd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9231257 | Completed | 1 | 10/26/2023 | 10/26/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Jeusmack Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3rd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6913442.43 | Completed | 1 | 10/26/2023 | 10/26/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Jeusmack Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101546 | Malasiqui I CS | MALASIQUI | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1384628.86 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Q&M Construction And Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui NHS | MALASIQUI | 3rd | 1 | 14 | REPAIR OF CLASSROOMS | 6489879.9 | 1 | 6461994.34 | Completed | 1 | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Elgram Trading And Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 1 | 0 |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 973850.07 | 1 | 917888.95 | completed | 1 | 2023-03-06 | 6/15/2023 | - | 2023-005 | 3/14/2023 | 3/22/2023 | APRIL 4,2023 | 4/14/2023 | 4/26/2023 | RGP SUCCESS VENTURES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9983672.11 | Ongoing | 0.9 | 5/17/2024 |  | 2023-07-12 | 2023-08-38 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.9 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 9 | Replacement | 22500000 | 1 | 22440043.66 | Ongoing | 0.82 | 5/17/2024 |  | 2023-07-12 | 2023-08-39 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0.8 | 0.02 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29857906 | Ongoing | 0.9 | 5/17/2024 |  | 2023-07-12 | 2023-08-39 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0.87 | 0.03 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932498 | Ongoing | 0.82 | 5/17/2024 |  | 2023-07-12 | 2023-08-38 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0.8 | 0.02 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1060966.05 | 1 | 1059997.66 | completed | 1 | 8/31/2023 | 8/31/2023 | INFRA-002-2023 | INFRA-002-2023 | 3/23/2023 | 3/30/2023 | 2023-12-04 | 4/20/2023 | 4/28/2023 | JD MADRID CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 1 | 0 |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9950511.25 | Ongoing | 0.95 | 5/17/2024 |  | 2023-07-12 | 2023-08-40 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimelds Construction and Iron Works | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.95 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 1048973.66 | 1 | 1048967.97 | completed | 1 | 8/31/2023 | 8/31/2023 | INFRA-002-2023 | INFRA-002-2023 | 3/23/2023 | 3/30/2023 | 2023-12-04 | 4/20/2023 | 4/28/2023 | JD MADRID CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932840.74 | Ongoing | 0.9 | 5/17/2024 |  | 2023-07-12 | 2023-08-40 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimelds Construction and Iron Works | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0.9 | 0 | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102269 | Badipa Elementary School | CITY OF URDANETA | 5th | 1 | 9 | REPAIR OF CLASSROOMS | 2016858.14 | 1 | 2011483.38 | completed | 1 | 8/30/2023 | 8/24/2023 | QRF REPAIR 2022-R1-URDANETA CITY-001 | 202303015 | 2023-08-03 | 4/20/2023 | 2023-03-05 | 2023-11-05 | 5/30/2023 | ELMUELJAY TARDING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 1 | 0 |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102294 | Don Amadeo Perez, Sr. Memorial Elementary Central School - East | CITY OF URDANETA | 5th | 1 | 4 | Replacement | 15313741.51 | 1 | 15263741.51 | completed | 1 | 2/26/2024 | 2024-12-08 | 2023-07-12 | 2023-08-36 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Vigan City | 300052 | Ilocos Sur National High School | CITY OF VIGAN (Capital) | 1st | 1 |  | Replacement | 125000000 | 1 | 41140168.88 | Ongoing | 0.99 | 5/17/2024 |  | 2023-07-12 | 2023-08-41 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | ASS Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0.994 | -0.004 | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1834811.6 | Completed | 1 | 9/28/2024 | 2024-07-08 | PB-19-2023-1 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100013 | Bangsirit ES | BACARRA | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 4925877 | 2-R | 4401231.88 | completed | 1 | 9/28/2024 | 2024-11-07 | PB-19-2023-2 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 634587.67 | completed | 1 | 9/28/2024 | 2024-03-05 | PB-19-2023-2 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100007 | Pasiocan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784970.3 | completed | 1 | 9/28/2024 | 2024-07-08 | PB-19-2023-1 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784635.64 | completed | 1 | 9/28/2024 | 2024-07-08 | PB-19-2023-1 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 320801 | BANBAN NHS | BANGUI | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1365141.42 | Completed | 1 | 2024-01-10 | 9/20/2024 | PB-19B-2023-7 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 895425.54 | Completed | 1 | 2024-01-10 | 9/20/2024 | PB-19B-2023-7 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2572715.41 | Completed | 1 | 2024-01-10 | 9/30/2024 | PB-19B-2023-6 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100167 | Dampig ES | PAGUDPUD | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1895646.18 | completed | 1 | 8/29/2024 | 2024-07-08 | PB-19-2023-8 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 3016937.09 | Completed | 1 | 8/29/2024 | 2024-07-08 | PB-19-2023-8 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100199 | Davila ES | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2506581.45 | Completed | 1 | 2024-04-11 | 2024-08-05 | PB-19B-2023-15 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-08-05 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2788000 | 2-R | 2314877.57 | Completed | 1 | 2024-04-11 | 2024-08-05 | PB-19B-2023-15 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-08-05 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1622920.46 | Completed | 1 | 2024-01-10 | 2024-11-08 | PB-19B-2023-16 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 3742897.43 | Completed | 1 | 8/29/2024 | 7/18/2024 | PB-19-2023-17 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 636101.98 | completed | 1 | 8/29/2024 | 7/18/2024 | PB-19-2023-17 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100213 | Surong PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 1012229.86 | Completed | 1 | 2024-01-10 | 2024-11-08 | PB-19B-2023-16 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100218 | Boyboy ES | PIDDIG | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 343985.21 | Completed | 1 | 11/24/2024 | 11/20/2024 | PB-19-2023-18 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 345057.91 | Completed | 1 | 11/24/2024 | 11/20/2024 | PB-19-2023-18 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 632610.25 | Completed | 1 | 11/24/2024 | 11/20/2024 | PB-19-2023-18 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100311 | Dasar ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1794270.16 | completed | 1 | 8/29/2024 | 8/27/2024 | PB-19A-2023-19 |  | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 633380 | 2-R | 454449.33 | Completed | 1 | 8/29/2024 | 8/29/2024 | PB-19A-2023-19 |  | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 3304000 | 2-R | 3296745.93 | Completed | 1 | 11/24/2024 | 11/20/2024 | PB-19-2023-18 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100324 | Tungel ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1480782.92 | completed | 1 | 8/29/2024 | 8/27/2024 | PB-19A-2023-19 |  | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 2814383.65 | Completed | 1 | 2024-09-12 | 12/27/2024 | PB-19-2023-20 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100041 | Turod ES | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 831704.72 | Completed | 1 | 12/28/2024 | 11/30/2024 | PB-19-2023-3 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100060 | Barbarangay ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1628202.96 | Completed | 1 | 11/30/2024 | 2024-11-08 | PB-19B-2023-9 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100063 | Caestebanan ES | BANNA (ESPIRITU) | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2520165.06 | Completed | 1 | 11/30/2024 | 11/19/2024 | PB-19B-2023-9 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4187330 | 2-R | 2857524.12 | Completed | 1 | 12/28/2024 | 11/30/2024 | PB-19-2023-3 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 320808 | Bamasesamar National High School | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1298980 | 2-R | 1160009.34 | completed | 1 | 9/13/2024 | 5/25/2024 | PB-19-2023-12 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1000219 | 2-R | 920129.09 | Completed | 1 | 2024-01-10 | 6/27/2024 | PB-19-2023-11 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100130 | Dingras West CES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 2-R | 3334927.64 | Completed | 1 | 10/31/2024 | 2024-05-10 | PB-01-2024 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-03-06 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100134 | Peralta ES | DINGRAS | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8600094.07 | Completed | 1 | 9/14/2024 | 8/24/2024 | PB-15-2023-1 |  | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region I | Ilocos Norte | 100124 | Saludares-Cali ES | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2498555 | 2-R | 2487632.44 | Completed | 1 | 2024-01-10 | 6/27/2024 | PB-19-2023-11 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100135 | San Esteban ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1828801.76 | completed | 1 | 9/13/2024 | 5/25/2024 | PB-19-2023-12 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100138 | Suyo ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1815871.21 | completed | 1 | 2024-01-10 | 6/27/2024 | PB-19-2023-11 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100151 | Mabuti ES | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1584474 | terminated | 0 |  |  | PB-19B-2023-9 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction | Terminated, building to be repaired was replaced by the DPWH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6265349.89 | Completed | 1 | 2024-06-11 | 12/27/2024 | PB-15-2023-2 |  | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 481818.73 | Completed | 1 | 2024-09-12 | 12/27/2024 | PB-19-2023-13 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100185 | Nagbacalan ES | PAOAY | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 4565891 | 2-R | 3621685.56 | Completed | 1 | 2024-09-12 | 12/27/2024 | PB-19-2023-13 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2576846.3 | Completed | 1 | 2024-09-12 | 12/27/2024 | PB-19-2023-14 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1114477.47 | Completed | 1 | 2024-09-12 | 12/27/2024 | PB-19-2023-14 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2743455.85 | Completed | 1 | 10/31/2024 | 2024-10-10 | PB-19B-2023-4 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100236 | Bicbica PS | PINILI | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8598431.5 | Completed | 1 | 10/31/2024 | 11/20/2024 | PB-15-2023-3 |  | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 545285.46 | Completed | 1 | 10/31/2024 | 2024-11-08 | PB-19B-2023-4 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6258355.82 | Completed | 1 | 2024-08-09 | 2024-05-10 | PB-15-2023-4 |  | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd |  | 3 | REPAIR OF CLASSROOMS | 2449998.96 | 2-R | 2440022.86 | Completed | 1 | 2024-10-10 | 11/30/2024 | PB-19-2023-5 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 341366.87 | Completed | 1 | 2024-10-10 | 11/30/2024 | PB-19-2023-5 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100276 | Barcelona ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1946864.79 | completed | 1 | 11/24/2024 | 2024-08-07 | PB-19-2023-10 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100284 | Santiago ES | SOLSONA | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 950000 | 2-R | 948168.99 | completed | 1 | 11/24/2024 | 2024-08-07 | PB-19-2023-10 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 1045358.69 | Completed | 1 | 11/24/2024 | 11/22/2024 | PB-19-2023-10 |  | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Batac City | 100079 | Magnuang ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 565554.92 | 1- R | 565543.22 | Completed | 1 | 2025-10-04 | 2/18/2025 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 100081 | Naguirangan-Capacuan ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4571722.38 | Ongoing | 0.9 | 6/19/2025 |  | 2024-002 | 24010 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,716,826.42) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Deped Building 2 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.75 | 0.15 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100085 | Quiling Elementary School | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4571722.38 | Ongoing | 0.9 | 6/19/2025 |  | 2024-002 | 24009 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,716,826.42) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Bagong Lipunan School Building - 3 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.75 | 0.15 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100086 | Sumader ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 261960.82 | 1- R | 261825.01 | Completed | 1 | 2025-10-04 | 1/28/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 100087 | Tabug ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4681175.28 | Ongoing | 0.9 | 6/19/2025 |  | 2024-002 | 24008 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,607,373.52) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Marcos Pre-Fab School Building 2 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.75 | 0.15 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100089 | Baay ES | CITY OF BATAC | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 1- NC | 6084631.32 | Ongoing | 0.5 | 8/18/2025 |  | 2024-003 | 24013 | Oct. 07, 2024 | Oct. 16, 2024 | Oct. 28, 2024 | Dec. 18, 2024 | Dec. 26, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 2,546,211.98) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of 12 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.4 | 0.1 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100091 | Baoa ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 220610.27 | 1- R | 220610.27 | Completed | 1 | 2025-10-04 | 1/28/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Batac City | 100093 | Biningan ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 800478.7 | 1- R | 800457.18 | Completed | 1 | 2025-10-04 | 3/18/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Batac City | 300005 | Batac National High School | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 362703.34 | 1- R | 362701.66 | Completed | 1 | 2025-10-04 | 2025-09-05 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0.9 | 0.1 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 674429.08 | 1- R | 673921.61 | Completed | 1 | 2025-10-04 | 2025-09-05 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0.9 | 0.1 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Ilocos Norte | 100053 | Nagbalagan ES | BANGUI | 1st | 1 | 4 | 2-UNITS 1STY2CL | 11671993.99 | 1- NC | 8642482.64 | Ongoing | 0.65 | 7/16/2025 |  | PB-07-2024-Lot 1 | PB-07-2024-Lot 1 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | Caixia Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.65 | 0 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100062 | Bugasi ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC | 6468375.49 | Ongoing | 0.9 | 4/17/2025 |  | PB-07-2024-Lot 2 | PB-07-2024-Lot 2 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | LAV Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.8 | 0.1 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 2 | Repair of Classrooms | 485255.7 | 1- R | 480277.72 | Completed | 1 | 3/30/2025 | 2025-01-04 | PB-14-2024-1 | PB-14-2024-1 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 1 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | reverted
QRF 2024 | Region I | Ilocos Norte | 100074 | VALDEZ ELEMENTARY SCHOOL | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC | 6558696.85 | Ongoing | 0.9 | 4/17/2025 |  | PB-07-2024-Lot 3 | PB-07-2024-Lot 3 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | Caixia Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.7 | 0.2 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | Repair of Classrooms | 443145.15 | 1- R | 438234.61 | completed | 1 | 3/30/2025 | 3/28/2025 | PB-14-2024-2 | PB-14-2024-2 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 2 | Repair of Classrooms | 637304.27 | 1- R | 632134.73 | completed | 1 | 3/30/2025 | 3/28/2025 | PB-14-2024-2 | PB-14-2024-2 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1st | 1 | 5 | Repair of Classrooms | 859025.56 | 1- R | 853025.56 | Completed | 1 | 2025-10-03 | 2025-01-04 | PB-14-2024-3 | PB-14-2024-3 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0.8 | 0.2 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 632738.78 | 1- R | 627346.34 | Completed | 1 | 3/30/2025 | 2025-01-04 | PB-14-2024-1 | PB-14-2024-1 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 1 | 0 |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 4 | Repair of Classrooms | 839105.83 | 1- R |  | Not yet started | 0 | [10 empty] | Deffered due to the issuance of Notice of Prohibited Use by the LGU | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Laoag City | 500742 | San Mateo Integrated School | LAOAG CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1234766.65 | 1- R | 1202187.77 | Completed | 1 | MAr.03,2025 | April 15,2025 | 2024-PB1-002 | 2024-pb1-002 | Oct.04,2024 | Oct.11,2024 | Oct.28,2024 | Nov.25,2025 | Dec.03,2024 | Elocin Construction | Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0.9 | 0.1 |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100002 | Bacarra CES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.77 | Ongoing | 0.7 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.2 | 0.5 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100006 | Nambaran ES | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597811.08 | Not yet started | 0 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647983.8 | Not yet started | 0 | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100010 | SPECIAL EDUCATION CENTER | BACARRA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3845845.18 | Ongoing | 0.5 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0.5 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100011 | Santo Cristo Elementary School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649206.51 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1946780.33 | Ongoing | 0.98 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.98 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100019 | Paninaan Elementary School | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2598258.05 | Ongoing | 0.95 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.45 | 0.5 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100022 | San Agustin ES | BACARRA | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 5850000 | 3-R | 5832130.29 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0.6 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100038 | Pasuc-Parang ES | BADOC | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2594696.51 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 639079.29 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100072 | Sinamar ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948623.74 | Ongoing | 0.4 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.3 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100106 | Nagsurot Elementary School | BURGOS | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945868.82 | Ongoing | 0.7 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.7 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100113 | Langayan ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.45 | 0.25 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646034.75 | Ongoing | 0.35 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.35 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945863.08 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.45 | 0.15 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100122 | Francisco ES | DINGRAS | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1285260.05 | Ongoing | 0.4 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.1 | 0.3 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100128 | Bacsil ES | DINGRAS | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.5 | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.5 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100156 | Santiago ES | MARCOS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4547749.73 | Ongoing | 0.6 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0.3 | 0.3 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100164 | Burayoc ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645894.62 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100165 | Caparispisan ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646009.29 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100177 | Subec ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645471.97 | Ongoing | 0.1 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100179 | Tarrag PS | PAGUDPUD | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Ongoing | 0.95 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.9 | 0.05 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100180 | Bacsil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649461.85 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100184 | Mumulaan ES | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247141.13 | Ongoing | 0.95 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0.5 | 0.45 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100188 | Paoay CES | PAOAY | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 6500000 | 3-R | 6494750 | Ongoing | 0.8 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0.3 | 0.5 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100189 | Paoay East Central ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.9 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.15 | 0.75 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100190 | Pasil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 636301.85 | Ongoing | 0.2 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100194 | Binsang ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.95 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.35 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100197 | Carusikis ES | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2596663.73 | Ongoing | 0.8 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 |  | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.65 | 0.15 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100198 | Dadaeman Elementary School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.1 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 3 | 1STY3CL | 9000000 | 3- NC | 8994759.45 | Ongoing | 0.35 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.15 | 0.2 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1293700 | Ongoing | 0.6 | 9/30/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100203 | Madalayap Elementary School | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2587210.91 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.4 | 0.2 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100205 | Naglicuan ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291108.21 | Ongoing | 0.5 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.4 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100207 | Pangil ES | PASUQUIN | 1st | 1 | 4 | 2STY4CL | 12000000 | 3- NC | 11997232.68 | Ongoing | 0.25 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0.2 | 0.05 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646523.89 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 626526.64 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100211 | Sta. Catalina ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 3235817.47 | Ongoing | 0.6 | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.4 | 0.2 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100214 | Tabungao ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295629.05 | Ongoing | 0.7 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.4 | 0.3 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100226 | Maruaya PS | PIDDIG | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.7 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3235817.47 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100240 | Darat ES | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.77 | Ongoing | 0.8 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.2 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100242 | Gulpeng PS | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 643005.08 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100244 | Nagtrigoan ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1261742.73 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100245 | Pugaoan-Bungro ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296958.76 | Ongoing | 0.8 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0.8 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100247 | Puzol Elementary School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2595871.43 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100252 | Barabar ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100254 | Bugnay ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647084.86 | Completed | 1 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 1400000 | 3-R | 1397903.98 | Completed | 1 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.9 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100257 | Filipinas East ES | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3894750.31 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948932.75 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100262 | Cabuloan Elementary School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644722.89 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100267 | Ruiz ES | SARRAT | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.7 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.7 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750.01 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100282 | Nagpatpatan ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.1 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100287 | Talugtog ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 0.1 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100288 | Alsem ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1932612.08 | Ongoing | 0.6 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0.4 | 0.2 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100296 | Esperanza ES | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1283338.55 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100306 | Visaya Elementary School | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Ongoing | 0.95 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0.9 | 0.05 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100314 | Lipay ES | VINTAR | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247441.15 | Ongoing | 0.15 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.15 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150003 | Nagbacalan West ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947773.07 | Completed | 1 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0.4 | 0.6 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150008 | San Isidro PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1288248.77 | Ongoing | 0.3 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0.3 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150023 | Casilian Primary School - Taguipuro Annex | BACARRA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296398.12 | Ongoing | 0.7 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0.7 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3895135.72 | Ongoing | 0.95 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0.65 | 0.3 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 0.1 | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300023 | Pagsanahan NHS | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291769.55 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644793.38 | Not yet started | 0 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500592 | Pandan Integrated School | SARRAT | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4522791.92 | Not yet started | 0 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597889.56 | Not yet started | 0 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502581 | Balaoi Integrated School | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647045.27 | Ongoing | 0.1 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.1 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502711 | Tubburan Integrated School | BACARRA | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3228809.88 | Ongoing | 0.5 | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0.5 | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502750 | Sto. Tomas Integrated School | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295964.13 | Not yet started | 0 | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Under Procurement