## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2023 SF | REGION I | Pangasinan Ii, Binalonan | 500375 | Sison Central Is | Sison | 5th | 1 | - | - | 640 | 640 | 16 | - | - | 2068800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1032725.2166 | Completed | 1 | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 1
CY 2023 SF | REGION I | Pangasinan Ii, Binalonan | 500379 | San Felipe Is | San Nicolas | 6th | 1 | - | - | 360 | 360 | 9 | - | - | 1163700 | Regional Office Implementation | 55% Allocation for Regular Supplier | 580907.9343 | Completed | 1 | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | REGION I | Urdaneta City | 500060 | San Jose Leet Is | Urdaneta City | 5th | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 258181.3041 | Completed | 1 | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | REGION I | Urdaneta City | 500061 | Don Alipio Fernandez ,Sr. Is | Urdaneta City | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 387271.9562 | Completed | 1 | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1