## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2023 SF | REGION VII | Cebu | 119196 | Luyang ES | CARMEN | 5th | 1 | 1800 | - | - | 1800 | 40 | - | - | 5792000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5th | 1 | 1800 | - | - | 1800 | 40 | - | - | 5792000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Cebu | 119419 | Liloan Nhs To Suba Es | Liloan | 5th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120032 | Awa-an ES | AYUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120052 | Nabhang ES | AYUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120059 | Tiguib ES | AYUNGON | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120184 | Manseje Elementary School | BINDOY (PAYABON) | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120199 | Binalbagan Elementary School | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120210 | Manggapa Elementary School | CANLAON CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120218 | Upper Lumapao ES | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120303 | MONGPONG PRIMARY SCHOOL | JIMALALUD | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120389 | Lamogong ES | MANJUYOD | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120398 | Sacsac ES | MANJUYOD | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120404 | Tanglad Elementary School | MANJUYOD | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120580 | Cambaye Elementary School | TAYASAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120599 | Suquib Elementary School | TAYASAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 312965 | Jose B. Cardenas MHS - Pula Ext. | CANLAON CITY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 312966 | Panciao High School | MANJUYOD | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120485 | Calabnugan Elementary School | Sibulan | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Negros Oriental | 120490 | Lo-oc ES | Sibulan | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0
CY 2023 SF | REGION VII | Siquijor | 303299 | Ponong High School | LARENA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0