## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of bldg Reverted | No. of bldg Not yet started | No. of bldg Under Procurement | No. of bldg On Going | No. of bldg Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | Implementing Unit | BBM TERM COMPLETED | AWAITING SUBMISSION OF RTA | batch of suballotment | STATUS.1 | Unnamed: 46 | NJ
GABALDON 2020 | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 6238558.58 | 1 | 6218000 | Completed | 1 | 2021-06-02 | 2021-05-13 | CY 2020 GABALDON - 001 | CY 2020 GABALDON - 001 | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-09-25 | 2020-11-27 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Bacolod City | 117449 | Andres Bonifacio I ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6638076.54 | 1 | 4653000 | Completed | 1 | 2021-12-27 | 2021-12-27 | r6bcd04142021-P25 | r6bcd04142021-P25 | 2021-04-16 | 2021-04-26 | 2021-05-10 | 2021-05-21 | 2021-07-30 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Iloilo | 116375 | Igbaras CES | IGBARAS | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 7538808.48 | 1 | 5490282.08 | Completed | 1 | 2022-09-30 | 2022-10-06 | Gab2020-RVI-022-ILOILO-B1-L1 | Gab2020-RVI-022-ILOILO-B1-L1 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises | On-going Rectification of Punchlisted Items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region VI | Iloilo | 116616 | New Lucena CES | NEW LUCENA | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5645882.9412 | 1 | 3604983.51 | Completed | 1 | 2021-05-13 | 2021-12-20 | Gab2020-RVI-022-ILOILO-B1-L2 | Gab2020-RVI-022-ILOILO-B1-L2 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Iloilo | 116119 | Cabatuan CES | CABATUAN | 3 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 6311025.38 | 1 | 4526000 | Completed | 1 | 2021-05-15 | 2021-09-20 | Gab2020-RVI-022-ILOILO-B1-L3 | Gab2020-RVI-022-ILOILO-B1-L | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-09 | RISM BUILDERS & CONST. SERVICES INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Iloilo | 116043 | Barotac Nuevo CES | BAROTAC NUEVO | 4 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 19897556.7664 | 1 | 12905885.78 | Completed | 1 | Ocober 30, 2022 | 2022-09-27 | Gab2020-RVI-022-ILOILO-B1-L4 | Gab2020-RVI-022-ILOILO-B1-L4 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises | On-going but with slow workmanship | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2020 | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 5863706.88 | 1 | 4204000 | Completed | 1 | 2021-11-22 | 2021-10-12 | Gab2020-RVI-022-ILOILO-B1-L4 | Gab2020-RVI-022-ILOILO-B1-L4 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-10-01 | 2021-06-22 | RISM Builders and Merchandising |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Iloilo City | 117626 | A. Montes ES I | ILOILO CITY (Capital) | 0 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 16198458.88 | 1 |  | Completed | 1 | [10 empty] | REQUEST FOR REALIGNMENT (Realignment of A. MONTES ES1 TO AREVALO ES 100%, RIZAL ES 100%, and ESTEBAN JUNTADOR SR. MEMORIAL ES 100%) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Iloilo City | 117629 | Jalandoni MS | ILOILO CITY (Capital) | 0 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 18915275.98 | 1 | 13229998.95 | Completed | 1 | 2021-07-19 | 06:43:12 | 20-12-006 | 20-12-006 | 2020-11-06 | 2020-11-13 | 2020-11-27 | 2020-12-04 | 2021-01-13 | 4SG Enterprises | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Kabankalan City | 117858 | Esteban R. Abada Memorial School(East) | Kabankalan City | 6 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12934200.86 | 1 |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6732754.41 | 1 | 3835451.66 | Completed | 1 | October 18, 2021 | [8 empty] | FOUR SG ENTERPRISES | Bidding Cancelled due to ECQ | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Negros Occidental | 117385 | Talisay ES | CITY OF TALISAY | 3 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3492344.95 | 1 | 3477970.42 | Completed | 1 | 2021-11-02 | Nov. 22, 2021 |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26D S.2020 |  | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Negros Occidental | 117385 | Talisay ES | CITY OF TALISAY | 3 |  | 2 | 1 | Rehabilitation of Gabaldon Building | 2816674.04 | 1 | 2789325.92 | Completed | 1 | 2021-11-02 | Nov. 22, 2021 |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26C S.2020 |  | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Negros Occidental | 117268 | Moises Padilla ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 14261569.8 | 1 | 14241535.89 | Completed | 1 | 2021-04-05 | 2021-03-30 | 6974325 | 20-11-002 | 2020-04-24 | 2020-05-04 | 2020-05-18 | 2020-11-18 | 2020-11-23 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Negros Occidental | 116963 | Cauayan CES | CAUAYAN | 6 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5284051.93 | 1 | 5262334.53 | Completed | 1 | 2021-04-05 | 2021-02-28 | 6974361 | 20-11-001 | 2020-04-24 | 2020-05-04 | 2020-05-18 | 2020-11-18 | 2020-11-23 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Negros Occidental | 117162 | Bocana ES | ILOG | 6 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1915596.29 | 1 | 1898971.66 | Completed | 1 | 2021-11-02 |  |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26A S.2020 |  | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Sagay City | 117692 | Elia T. Canoy Esperancilla Elementary School | SAGAY CITY | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2418204.21 | 1 | 1810000 | Completed | 1 | December 16, 2021 | August 21, 2021 | 02-2020 | 02-2020 | 2020-02-25 | 2020-03-03 | 2020-03-16 |  | June 21, 2021 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  |  |  |  | Completed
GABALDON 2020 | Region VI | Silay City | 117804 | Silay South Elementary School | SAGAY CITY | 3 | 1 | 29 | 1 | Rehabilitation of Gabaldon Building | 24820703.04 | 1 | 20338749.46 | Completed | 1 | 2022-09-30 |  |  | R6-D18-GAB-B2-2020 | March 27, 2020 | May 7, 2020 | May 19, 2020 | June 18, 2021 | July 27, 2021 | FOUR SG ENTERPRISES | On-going Rectification of Punchlisted Items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs |  | CY 2022 |  |  | Completed
GABALDON 2021 | Region VI | Aklan | 114738 | Naisud CS | IBAJAY | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 6399403 | 1 | 6335000 | COMPLETED | 1 | 2022-03-17 | 2022-03-04 | CY 2021 GABALDON - 001 | CY 2021 GABALDON - 001 | 2021-05-31 | 2021-06-07 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | COMPLETED
GABALDON 2021 | Region VI | Iloilo | 116012 | Balasan CES | BALASAN | 5 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 9800503 | 1 | 6455847.57 | COMPLETED | 1 | 2021-11-22 | 2021-11-08 | R-06-BEFF Gabaldon-2020-B2-L1 | R-06-BEFF Gabaldon-2020-B2-L1 | 2020-02-21 |  | 2020-03-10 | 2020-10-01 | 2021-06-25 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | COMPLETED
GABALDON 2021 | Region VI | Negros Occidental | 117212 | Tinongan ES | ISABELA | 5 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5776301 | 1 | 3692000 | completed | 1 | 2021-12-15 |  |  |  | 2021-06-08 | 2021-06-15 | 2021-06-28 | 2021-07-002 | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | completed
GABALDON 2021 | Region VI | Negros Occidental | 117116 | Bulata ES | CAUAYAN | 6 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4331131 | 1 | 2752000 | completed | 1 | 2021-12-15 |  |  |  | 2021-06-08 | 2021-06-15 | 2021-06-28 | 2021-07-003 | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | completed
GABALDON 2021 | Region VI | San Carlos City | 117772 | Codcod ES | San Carlos City | 1 | 1 | 1 | 1 | Completion of Abandoned Gabaldon | 396661 | 1 | 393994.87 | completed | 1 | 2021-12-26 | 2021-10-18 | 7774758-2021-GABALDON | 7774758-2021-GABALDON | 2021-06-17 | 2021-06-25 | 2021-07-07 | 2021-07-29 | 2021-08-06 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | completed
GABALDON 2021 | Region VI | San Carlos City | 117788 | Katingal-an ES | San Carlos City | 1 | 1 | 5 | 1 | Completion of Abandoned Gabaldon | 1511665 | 1 | 1501505.13 | completed | 1 | 2021-12-26 | 2021-12-20 | 7774758-2021-GABALDON | 7774758-2021-GABALDON | 2021-06-17 | 2021-06-25 | 2021-07-07 | 2021-07-29 | 2021-08-06 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | previous yrs | Division Office |  |  |  | completed
GABALDON 2023 | Region VI | Negros Occidental | 117113 | Hinigaran ES-A | HINIGARAN | 5 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 11443993.61 | 1 | 9126569.32 | completed | 1 | 7/24/2024 | 7/23/2024 | 2006-08-23 | JO# 25-11-002 | 8/25/2023 | 2023-01-09 | 9/14/2023 | No. 040 s. 2023 | 12/27/2023 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 1.25 | Division Office |  |  |  | completed
GABALDON 2024 | Region VI | Aklan | 114850 | Malay Elementary School | MALAY | 2nd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 8597231.29 | 1 | 8562000 | completed | 1 | 1/20/2025 | 1/20/2025 | DepEd-RO6-D1-2024GABALDON-012-2024 | DepEd-RO6-D1-2024GABALDON-012-2024 | 2024-08-05 | 5/15/2024 | 5/27/2024 | 6/19/2024 | 7/17/2024 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 2.25 | Division Office |  |  | 3 | completed
GABALDON 2024 | Region VI | Guimaras | 115895 | Igang Elementary School | NUEVA VALENCIA | Lone | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 7762335.08 | 1 | 7707000 | COMPLETED | 1 | 2024-03-12 | 2024-10-10 | Project 04-2024 | Project 04-2024 | 2024-01-03 | 2024-12-03 | 3/26/2024 | 6/25/2024 | 2024-01-07 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | completed and turn-over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 10.24 | Division Office |  |  | 3 | COMPLETED
GABALDON 2024 | Region VI | Himamaylan City | 117076 | Himamaylan Central School | CITY OF HIMAMAYLAN | 5th | 1 | 9 | 1 | Conservation and Restoration of Gabaldon School Building | 13950000 | 1 | 13850000 | Ongoing | 0.95 | 2025-01-06 |  | IB-sdhc-082024-007 | IB-sdhc-082024-007 | 8/14/2024 | 8/22/2024 | 2024-03-09 | 9/13/2024 | 2025-10-01 | RISM BUILDERS AND CONSTRUCTION SERVICES | for final inspection and punchlisting on June 7, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.05 |  |  | Division Office |  |  | 10 | Ongoing
GABALDON 2024 | Region VI | Iloilo | 116839 | Tigbauan CES | TIGBAUAN | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 13363220.1 | 1 | 13324432.63 | COMPLETED | 1 | 3/13/2025 | 2024-12-12 | BEFF2024-RVI-ILOILO-022-GAB-L1 | BEFF2024-RVI-ILOILO-022-GAB-L1 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 7/15/2024 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 3.25 | Division Office |  |  | 3 | COMPLETED
GABALDON 2024 | Region VI | Iloilo | 116394 | Janiuay Pilot ES | JANIUAY | 3rd | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 8456526.87 | 1 | 8446849.01 | COMPLETED | 1 | 2025-12-01 | 2025-08-04 | BEFF2024-RVI-ILOILO-022-GAB-L2 | BEFF2024-RVI-ILOILO-022-GAB-L2 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 7/15/2024 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0.95 | 0.05 |  |  | Division Office |  |  | 3 | Ongoing
GABALDON 2024 | Region VI | Iloilo | 116777 | Hugo T. Apelo MES | SARA | 5th | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 3758099.02 | 1 | 3750285.99 | COMPLETED | 1 | 2024-09-12 | 10/29/2024 | BEFF2024-RVI-ILOILO-022-GAB-L3 | BEFF2024-RVI-ILOILO-022-GAB-L3 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 2024-11-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 11.24 | Division Office |  |  | 3 | COMPLETED
GABALDON 2024 | Region VI | Negros Occidental | 117429 | Valladolid ES | VALLADOLID | 4th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 13287607.81 | 1 | 8258170.51 | Under Procurement | 0 |  |  | 2025-03-01 |  | 12/27/2024 | 2025-06-01 | 1/20/2025 | 3/19/2025 |  | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | Request for the release of Sub-ARO with RTAs was alredy submitted -still waiting from CO to provide us Sub-ARO. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Under Procurement
GABALDON 2024 | Region VI | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 16334630.93 | 1 | 10000000 | Under Procurement | 0 |  |  | 2025-02-01 |  | 12/27/2024 | 2025-07-01 | 1/20/2025 | 3/19/2025 |  | KEANNE CONSTRUCTION SERVICES | Request for the release of Sub-ARO with RTAs was alredy submitted -still waiting from CO to provide us Sub-ARO. | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | Division Office |  | 1 | 0 | Under Procurement