## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel | STATUS.1
LMS 2020 | Region VI | Antique | 114985 | Caloy-ahan PS | Bugasong | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 23766742.205 | 19613104.9 | Completed | 1 | 2022-10-30 | 2023-07-14 | R6-D2-2020BEFF-13-NC | R6-D2-2020BEFF-13-NC | 2021-07-12 | 2021-07-19 | 2021-08-02 | 2021-08-16 | 00:00:00 | Nesmark Construction Enterprises | Nearly completion on finishing works, and delivery of school furnitures. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | [6 empty] | CY 2023 |  |  | 1 | Completed
LMS 2020 | Region VI | Capiz | 115627 | Jamul-awon ES | PANAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 20180339.2794 | 13027738.3 | Completed | 1 | April 19, 2022 | 00:00:00 | R6-DepED-Capiz-CY2020-Last Mile School-Lot 2 | 0 | August 23, 2021 | September 1, 2021 | September 14, 2021 | October 11, 2021 | October 21, 2021 | ORANGEKONSTRUCT CIVIL ENGINEERING SERVICES | Schedule of pre-procurement 8/17/2021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | [6 empty] | CY 2022 |  |  | 0 | Completed
LMS 2020 | Region VI | Capiz | 310811 | YATING NATIONAL HIGH SCHOOL | PILAR | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE,AND WATER SYSTEM | 18733377.0103 | 11945444.38 | Completed | 1 | May 2, 2022 | 00:00:00 | R6-DepED-Capiz-CY2020-Last Mile School-Lot 1 | 0 | August 23, 2021 | September 1, 2021 | September 14, 2021 | October 11, 2021 | November 3, 2021 | GREATMAN BUILDERS | Schedule of pre-procurement 8/17/2021 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 0 | Completed
LMS 2020 | Region VI | Guimaras | 115914 | Panobolon ES | Nueva Valencia | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20808548.5734 | 20660439.7 | completed | 1 | March 27, 2022 | 2022-07-05 | 06-2021 | 06-2021 | June 22, 2021 | July 13, 2021 | July 27, 2021 | August 8, 2021 | August 24, 2021 | EZ Gold Construction and Supply | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | previous yrs | 1 | [5 empty] | CY 2022 |  |  | 1 | completed
LMS 2020 | Region VI | Iloilo | 501244 | Barasalon Integrated School | Janiuay I | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20311610.0883 | 17258671.73 | completed | 1 | 2022-02-26 | 2024-12-06 | LMS2020-RVI-022-ILOILO-B1-L1 | LMS2020-RVI-022-ILOILO-B1-L1 | 2021-07-27 | 2021-08-02 | 2021-08-17 | 2021-09-07 | 2021-09-29 | NOE'S Builders | -as of Feb2024- Liquidated damages were imposed; -For Termination; low paced workmasnhip; Based on the actual ocular | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | 1 | 1 | [7 empty] | 1 | completed
LMS 2021 | Region VI | Aklan | 500544 | Mambuquiao Integrated School | BATAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19683914.12 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1 | COMPLETED
LMS 2021 | Region VI | Aklan | 114804 | Bacyang PS | MADALAG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19567467.6 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 5.24 |  | 0 | 1 |  |  |  | CY 2024 |  |  | 1 | Completed
LMS 2021 | Region VI | Antique | 178514 | Omlot PS (realigned from Tigunhao PS) | Laua-an | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20850221.18 | 0 | Completed | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED. The school was re-aligned to Omlot PS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 |  | 0 | 1 | [6 empty] | 1 | Completed
LMS 2021 | Region VI | Capiz | 115617 | Bantigue ES | PANAY | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20322685.02 | 0 | ONGOING | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1 | ONGOING
LMS 2021 | Region VI | Iloilo | 501248 | Adgao-Tagpuan-Ingay Integrated School | TUBUNGAN | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17764390.36 | 0 | ONGOING | 0.98 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED; Rectification of Punchlist | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0.03 |  |  | 0 | 1 | [6 empty] | 1 | ONGOING
LMS 2021 | Region VI | Iloilo | 116180 | Caratagan PS | CALINOG | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 20557581.5038 | 0 | Not Yet Started | 0 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED. NPA threats | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | [6 empty] | 1 | ONGOING
LMS 2021 | Region VI | Kabankalan City | 117891 | Sagumayon PS | Kabankalan City | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 24548206.13 | 0 | ONGOING | 0.95 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.95 | 0 |  |  | 0 | 1 | [6 empty] | 1 | ONGOING
LMS 2021 | Region VI | Negros Occidental | 302631 | Florentina C. Recto MHS - Caliling Ext | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 12162474.45 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1 | COMPLETED
LMS 2021 | Region VI | Negros Occidental | 117008 | Patol Elementary School | CAUAYAN | 6 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17312723.74 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1 | COMPLETED
LMS 2021 | Region VI | Negros Occidental | 116982 | Talangnan ES | CAUAYAN | 6 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, PERIMETER FENCE (1 BAY = 3.0m), SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19254393.25 | 0 | COMPLETED | 1 | 00:00:00 | 00:00:00 | 0 | 0 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 00:00:00 | 0 | CO PROCURED inaugurated (August) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1 | COMPLETED
LMS 2022 | Region VI | Aklan | 114710 | TABUNGYAN ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 19158007.7445 | 18808160.79 | Completed | 1 | 2023-12-01 | 2023-12-05 | INFRA 2023-05-002 | 2023-07-001 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-10 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1 | Completed
LMS 2022 | Region VI | Aklan | 501181 | Vivo Integrated School | Tangalan | 2 | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM, PERIMETER FENCE 200 Meters | 19740374.5242 | 19000879.05 | Completed | 1 | 2023-12-01 | November 24, 2023 | INFRA 2023-05-002 | 2023-07-002 | 2023-05-11 | 2023-05-19 | 2023-06-02 | 2023-07-03 | 2023-07-06 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 1 | Completed
LMS 2022 | Region VI | Antique | 114975 | Buenavista ES | BELISON | 0 | 1 | 11 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM, AND REPAIR/REHABILITATION OF 7 CLASSROOMS | 21786950.5096 | 16550995.27 | Completed | 1 | 2023-12-01 | 2024-07-08 | R6-D2-2022BEFF-37-NC | R6-D2-2022BEFF-37-NC | 2022-11-25 | 2022-12-02 | 2022-12-09 | 2022-12-21 | 2022-12-21 | Nesmark Construction Enterprises | Completed as per approved plans and variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 9.24 |  | 1 | [7 empty] | 1 | Completed
LMS 2022 | Region VI | Antique | 115129 | Igcagay PS | LIBERTAD | 0 | 1 | 2 | CONSTRUCTION OF ONE(1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND REPAIR AND REHABILITATION OF 2 CLASSROOMS | 15795342.76 | 12901507.38 | Completed | 1 | 2023-12-01 | October 14, 2024 | R6-D2-BEFF2023-11-NC | R6-D2-BEFF2023-11-NC | 2023-06-19 | 2023-06-26 | 2023-07-03 | Augut 17, 2023 | 2023-08-29 | D' X-man Builders Corporation | Completed as per approved plans and variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | 1 | 4 | 15795342.76 |  |  |  | 1 | Completed
LMS 2022 | Region VI | Guimaras | 115853 | Miagos Primary School | SAN LORENZO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 12611496.1788 | 12298193.75 | Completed | 1 | 2023-12-01 | 2023-09-23 | 03-2022-lot 1 | No. 03-A-2022 | 2022-05-13 | 2022-05-25 | 2022-06-14 | 2022-07-01 | 2022-09-26 | ARRIANNE MERCHANDISING AND CONSTRUCTION SERVICES, INC | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.23 |  | 1 |  |  |  |  | CY 2023 |  |  | 0 | Completed
LMS 2022 | Region VI | Iloilo | 116117 | Tubod PS | BINGAWAN | 3 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS 7x36 (MODIFIED STANDARD DPWH-DEPED) WITH TOILET EACH CLASSROOM, SOLAR PANEL @ WATER SUPPLY SYSTEM | 16950819.24 | 13831624.51 | Completed | 1 | 2024-04-06 | 2024-08-07 | BEFF2022-RVI-022-LMS-L1 | BEFF2022-RVI-022-LMS-L1 | 17/04/2023 | 24/04/2023 | 2023-08-05 | 29/06/2023 | 2023-03-08 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 10.24 |  | 0 | 1 | 1 | 4 | 16950819.24 |  |  |  | 1 | Completed
LMS 2023 | Region VI | Aklan | 114931 | Lanipga Napatag Primary School | TANGALAN | 2 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 19969508.48 | 16152092.89 | Completed | 1 | 2023-12-31 | 2024-07-03 | DepED-RO6-D1-LMS2023-019-2023 | DepED-RO6-D1-LMS2023-019-2023 | 2023-04-26 | 2023-05-03 | 2023-05-15 | 2023-06-19 | 2023-06-27 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1 | Completed
LMS 2023 | Region VI | Antique | 115139 | Tinindugan Primary School | LIBERTAD | 0 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17170000 | 12901507.38 | Completed | 1 | 2024-05-01 | 2024-06-25 | R6-D2-BEFF2023-11-NC | R6-D2-BEFF2023-11-NC | 2023-06-12 | 2023-06-19 | 2023-07-03 | 2023-09-18 | 2023-11-28 | MJSb Builders and Supply | Completed as per POW and VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 1 | Completed
LMS 2023 | Region VI | Guimaras | 115859 | Tangaw Primary School | SAN LORENZO | 0 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) ROOFING, STEEL TRUSSES CONCRETE WORKS, MASONRY WORKS, ELECTRICAL WORKS, AND PLUMBINGWITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 17170000 | 12209995.28 | Completed | 1 | 2024-01-19 | 2024-03-15 | No. 03-2023 | No. 03-2023 | 2023-04-12 | 2023-04-28 | 2023-05-11 | 2023-06-06 | 2023-06-16 | Early Riser Construction | Completed with approved VO in the amount of 956,217.09 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0 | Completed
LMS 2023 | Region VI | Iloilo | 116107 | Cairohan PS | BINGAWAN | 3 | 1 | 2 | ONE (1) STOREY-TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY AND WATER SYSTEM | 18854193.63 | 12144077.99 | Completed | 1 | 2024-03-30 | 2024-08-07 | BEFF2023-RVI-022-LMS-L1 | BEFF2023-RVI-022-LMS-L1 | 2023-04-17 | 2023-04-24 | 2023-05-08 | 2023-06-29 | 2023-08-03 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1 | Completed
LMS 2023 | Region VI | Iloilo | 116099 | Malico PS | BATAD | 5 | 1 | 4 | ONE (1) STOREY-FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMON TOILET) WITH PROVISION OF RAIN WATER COLLECTOR SCHOOL FURNITURE, SOLAR PV ENERGY AND WATER SYSTEM | 23471443.86 | 15174823.71 | Completed | 1 | 2024-03-30 | 2024-08-08 | BEFF2023-RVI-022-LMS-L2 | BEFF2023-RVI-022-LMS-L2 | 2023-04-17 | 2023-04-24 | 2023-05-08 | 2023-06-29 | 2023-08-03 | CDJ Builders Corporation | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 3.25 | - | 0 | 1 |  |  |  |  | 1 |  | 1 | Completed
LMS 2024 | Region VI | Aklan | 114860 | Cogon Elementary School | MALINAO | 2nd | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21223289.1 | 20460400.84 | Completed | 1 | 2025-01-31 | 2025-02-14 | DepED-RO6-D1-2024-CY2024-LMS-056-2024 | DepED-RO6-D1-2024-CY2024-LMS-056-2024 | 2023-11-14 | 2023-11-21 | 2023-12-04 | 2024-01-19 | 2024-05-29 | GMO CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 3rd | 1 | Completed
LMS 2024 | Region VI | Antique | 115268 | Panpanan I ES | SAN REMIGIO | Lone | 1 | 2 | PROPOSED CONSTRUCTION OF ONE(1) UNIT - ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17377521.03 | 12162100.86 | On-going | 0.3 | 2025-09-19 | 00:00:00 | R6-D2-GAA2024-07-NC | R6-D2-GAA2024-07-NC | 2024-01-26 | 2024-02-02 | 2024-02-16 | 2024-04-05 | 2024-07-19 | MDG Const. & Supply | Already issued ressumption order last February 24, 2025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | [9 empty] | 3rd | 1 | Ongoing
LMS 2024 | Region VI | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2nd | 1 | 5 | CONSTRUCTION OF 1STY 5CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM with hauling cost | 16383838.38 | 15997903.42 | ONGOING | 0.75 | 2025-03-07 | 00:00:00 | 0 | 0 | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-08-06 | 2024-02-10 | Keanne construction services | With approved 150CD time extension due to unpassable road (landslide/manual hauling/unpassable road) Project ID and Contract ID to be confirmed from the BAC Secretariat | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.35 | 0.4 | [9 empty] | 4th | 1 | ONGOING
LMS 2024 | Region VI | Capiz | 500796 | Duluan Integrated School | MA-AYON | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 24242424.24 | 14878415.3 | ONGOING | 0.85 | 2025-06-19 | 00:00:00 | R6-DepEd-Capiz-CY 2024-BEFF-DuluanIS-Lot1 | CB No. 2024 - 032 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-14 | AMD ENGINEERING AND CONSTRUCTION SUPPLY | REQUESTED FOR 60 CD TIME EXTENSION. APPROVED LAST APRIL 2, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0.4 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region VI | Capiz | 501439 | Sinamongan Integrated School | PILAR | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 21919191.92 | 13454000 | ONGOING | 0.95 | 2025-05-03 | 00:00:00 | R6-DepEd-Capiz-CY 2024-BEFF-SinamonganIS-Lot2 | CB No. 2024 - 033 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-08-15 | 2024-10-25 | TUNGALA CONSTRUCTION SERVICES | SUBSTANTIALLY COMPLETED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.5 | 0.45 | [9 empty] | 5th | 1 | ONGOING
LMS 2024 | Region VI | Guimaras | 115903 | Paaralan ng Buhay ng Taras | NUEVA VALENCIA | Lone | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, AND WATER SYSTEM | 17188760.85 | 16914477.63 | Completed | 1 | 2024-10-26 | 2024-12-27 | No. 06-2024 | No. 06-2024 | 2023-10-16 | 2023-10-24 | 2023-11-05 | 2024-05-13 | 2024-05-24 | Early Riser Construction | With approved time extension due to unworkable weather conditions & change/increase of elevation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1.25 | [8 empty] | 5th | 0 | Completed
LMS 2024 | Region VI | Himamaylan City | 117066 | Balatogan Elementary School | CITY OF HIMAMAYLAN | 5th | 1 | 3 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17171717.17 | 16860289.87 | ONGOING | 0.75 | 2025-06-12 | 00:00:00 | 2024-10-0006 | 2024-10-0006 | 2024-06-29 | 2024-07-11 | 2024-07-23 | 2024-08-20 | 2024-10-08 | JCORD Construction | On going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.3 | 0.45 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region VI | Iloilo | 116833 | Lubog Primary School | TIGBAUAN | 1st | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 12634605.87 | ongoing | 0.5 | 2025-10-10 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L3 | BEFF2024-RVI-022-ILOILO-LMS-L3 | 2024-08-07 | 2024-08-14 | 2024-08-30 | 2024-09-13 | 2025-02-12 | EC Builders | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.2 | 0.3 | [9 empty] | 1st | 1 | ongoing
LMS 2024 | Region VI | Iloilo | 115973 | Aglay-ao Primary School | ANILAO | 4th | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 14058943.18 | ongoing | 0.4 | 2025-04-04 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L2 | BEFF2024-RVI-022-ILOILO-LMS-L2 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-12-23 | 2025-02-27 | CDJ Builders Corporation | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.25 | 0.15 | [9 empty] | 1st | 1 | ongoing
LMS 2024 | Region VI | Iloilo | 116064 | California PS | BAROTAC VIEJO | 5th | 1 | 4 | CONSTRUCTION OF 1STY 4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 19802964.97 | 13610045.75 | Not Yet Started | 0.3 | 2025-04-04 | 00:00:00 | BEFF2024-RVI-022-ILOILO-LMS-L1 | BEFF2024-RVI-022-ILOILO-LMS-L1 | 2024-07-03 | 2024-07-10 | 2024-07-22 | 2024-12-23 | 2025-02-27 | CDJ Builders Corporation | with NTP | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0.15 | 0.15 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region VI | Negros Occidental | 117026 | Gahit ES | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11139555.27 | ONGOING | 0.85 | 2025-03-03 | 00:00:00 | 23-11-29 | 24-09-005 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-17 | KEANNE CONSTRUCTION SERVICES | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.7 | 0.15 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region VI | Negros Occidental | 117262 | E. Basa ES | MOISES PADILLA (MAGALLON) | 5th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 9895300.9 | ONGOING | 0.85 | 2025-02-15 | 00:00:00 | 23-11-29 | 24-09-003 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-04 | CGGFR Construction and Construction Supply | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.75 | 0.1 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region VI | Negros Occidental | 180510 | Montelo ES | ILOG | 6th | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 11351550.98 | 11222892.59 | ONGOING | 0.85 | 2025-03-03 | 00:00:00 | 23-11-004 | 24-09-004 | 2023-11-20 | 2023-11-27 | 2023-12-11 | 2024-07-26 | 2024-09-20 | Par Builders | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.45 | 0.4 | [9 empty] | 1st | 1 | ONGOING