## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | NO. OF CL | SCOPE OF WORK | PROJECT ALLOCATION | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated/ Abandoned | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of CL Terminated/ Abandoned | No. of Sites Reverted.1 | No. of Sites Not yet started.1 | No. of Sites Under Procurement.1 | No. of Sites On Going.1 | No. of Sites Completed.1 | No. of Sites Terminated/ Abandoned.1 | Previous % | Difference | Month Completed | OGP SCHOOLS with DCP Packages | TO BE COMPLETED BY 2023 | TO BE COMPLETED BY 2023.1 | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | BBM ADMINISTRATION | Batch | Municipality Class | Provision of Solar Panel | STATUS.1
LMS 2020 | Region XI | Davao De Oro | 204004 | Kaluyapi ES | MARAGUSAN (SAN MARIANO) | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17551559.7796 | 0 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 7.23 | 1 | [5 empty] | CY 2023 |  |  | 1 | Completed
LMS 2021 | Region XI | Davao City | 108181 | Alon ES | DAVAO CITY | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 21434086.41 |  | Abandoned | 0.05 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.05 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Abandoned
LMS 2021 | Region XI | Davao City | 108181 | Alon ES | DAVAO CITY | 2 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE AND SOLAR PV ENERGY SYSTEM | 6520 |  | Abandoned | 0.02 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.02 | 0 |  |  | 0 | 0 | [6 empty] | 1 | Abandoned
LMS 2021 | Region XI | Davao De Oro |  | Amogad ES | LAAK (SAN VICENTE) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, AND WATER SYSTEM | 17426779.43 |  | Abandoned | 0.12 | [11 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.12 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Abandoned
LMS 2021 | Region XI | Davao del Norte | 204529 | Ngan PS | KAPALONG | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, , AND WATER SYSTEM | 15998850.0145 |  | Abandoned | 0.09 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.09 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Abandoned
LMS 2021 | Region XI | Davao del Norte |  | Ibuyag Logsi KM 31 Ext | Talaingod | 1 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - THREE (3) CLASSROOMS & ONE (1) STOREY - ONE (1) CLASSROOM SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, , AND WATER SYSTEM | 25796525.5025 |  | Abandoned | 0.1 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0.1 | 0 |  |  | 0 | 1 | [6 empty] | 1 | Abandoned
LMS 2021 | Region XI | Davao Oriental | 501608 | Modesto T. Veroy Sr. IS | CATEEL | 1 | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, TRANSMISSION LINE AND WATER SYSTEM | 14392154.4667 |  | Abandoned | 0.4 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0.4 | 0 |  |  | 0 | 1 | [6 empty] | 0 | Abandoned
LMS 2021 | Region XI | Davao Oriental | 501608 | Modesto T. Veroy Sr. IS | CATEEL | 1 |  | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, TRANSMISSION LINE AND WATER SYSTEM | 6520 |  | Abandoned | 0.3 | [10 empty] | Abandoned | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 |  |  | 0 | 0 | [6 empty] | 0 | Abandoned
LMS 2023 | Region XI | Davao del Norte | 101973 | Kamingawan ES | TALAINGOD | 1st | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, RAIN WATER COLLECTOR AND WATER SYSTEM | 19766589.1 |  | ongoing | 0.9 | [10 empty] | abandoned/ issued suspension due to unaccessable road | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.9 | 0 |  |  | 0 | [5 empty] | 2 |  | 1 | Abandoned
LMS 2023 | Region XI | Davao del Norte | 501904 | Dulyan Integrated School | TALAINGOD | 2nd | 1 | 2 | CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SOLAR PV ENERGY SYSTEM, SCHOOL FURNITURE, RAIN WATER COLLECTOR AND WATER SYSTEM | 16958383.69 |  | Completed | 1 | [10 empty] | abandoned/ issued suspension due to unaccessable road | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 |  |  | 0 | [5 empty] | 2 |  | 1 | Abandoned
LMS 2023 | Region XI | Mati City | 102157 | Catmonan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 13168096.28 | 12980986.68 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0 | COMPLETED
LMS 2023 | Region XI | Mati City | 129418 | Magum ES | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 12551905.33 | 12370674.27 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0 | COMPLETED
LMS 2023 | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 12355882.59 | 12174043.03 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | Matt Glass/Aluminum/Construction Supply and Allied Services | w/ time extension due to shearline | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 8.24 | - | 0 | 1 |  |  |  |  | 1 |  | 0 | COMPLETED
LMS 2023 | Region XI | Mati City | 102164 | Talucanga Elementary School | CITY OF MATI (Capital) | 2 | 1 | 4 | CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF SCHOOL FURNITURE | 14492041.68 | 11647469.14 | COMPLETED | 1 | 2024-06-09 | 2024-07-23 |  |  | June 23, 2023 | June 30, 2023 | July 12, 2023 | August 24, 2023 | 2023-09-04 | BQPC Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 6.24 | - | 0 | 1 |  |  |  | CY 2024 | 1 |  | 0 | COMPLETED
LMS 2024 | Region XI | Davao City | 137004 | Merol-O Elementary School | DAVAO CITY | 2nd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16861057.51 | 15858167.64 | Completed | 1 | Oct.25, 2024/Revised completion date: Dec. 24, 2024 |  | LMS-L001-2024 | #4 s. 2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Kiokong Construction | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 5th | 1 | Completed
LMS 2024 | Region XI | Davao City | 306041 | Manaong National High School | DAVAO CITY | 3rd | 1 | 4 | CONSTRUCTION OF 1STY4CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 16691097.64 | 15678874.9 | COMPLETED | 1 | Oct.25, 2024/Revised completion date: Dec. 24, 2024 |  | LMS-L001-2024 | #4 s. 2024 INF DL-XI | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Kiokong Construction | on-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 5th | 1 | COMPLETED
LMS 2024 | Region XI | Davao De Oro | 136925 | Puting Bato Elementary School | COMPOSTELA | 1st | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12681661.47 |  | Under Procurement | 0 | [10 empty] | as of April: postponed, submitted authority letter to CO allowing them to implement to other recipient NO RTA submitted to CO; as per DO this is for defferment; MGB Result; high susceptible to landslide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1 | not yet started
LMS 2024 | Region XI | Davao De Oro | 128336 | Mambatang ES | MABINI (DOÑA ALICIA) | 2nd | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - TWO (2) CLASSROOMS SCHOOL BUILDING (WITH COMMON TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 12458630.73 |  | Under Procurement | 0 | [10 empty] | as of April: postponed, submitted authority letter to CO allowing them to implement to other recipient NO RTA submitted to CO; as per DO this is for defferment; MGB Result; high susceptible to landslide | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [9 empty] | 1st | 1 | not yet started
LMS 2024 | Region XI | Davao del Norte | 301773 | DUGAYAN NHS | KAPALONG | 1st | 1 | 6 | CONSTRUCTION OF 2 STOREY 6 CLASRROOM SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 31313131.31 | 25611457.03 | ONGOING | 0.6 |  |  |  |  | 2024-01-10 | 2024-01-17 | 2024-01-30 | 2024-03-19 | 2024-06-04 | Mark Anthony Construction & Supply | ongoing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.6 | 0 | [9 empty] | 5th | 1 | ONGOING
LMS 2024 | Region XI | Davao del Sur | 128912 | Nodilla Elementary School | KIBLAWAN | 1st | 1 | 4 | CONSTRUCTION OF SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 21356418.04 |  | ONGOING | 0.27 | 2025-06-12 |  |  |  |  | May 28, 2024 | June 07, 2024 | August 09, 2024 |  | PHSMB CONSTRUCTION AND SUPPLY | for issuance NTP | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.27 | 0 | [9 empty] | 1st | 1 | ONGOING
LMS 2024 | Region XI | Davao Occidental | 205025 | Kangko ES | MALITA | Lone | 1 | 3 | CONSTRUCTION OF 1STY3CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM | 17231437.46 | 17048325.13 | Completed | 1 | February 24, 2024 |  | ITB W-03-2024 | contract no. 2024-010 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | resolution no. 09,s. 2024 | August 08, 2024 | Digos Constrak Corporation | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 2.25 | [8 empty] | 1st | 1 | Completed
LMS 2024 | Region XI | Davao Oriental | 501516 | Mc Arthur S. Madani Integrated School | CATEEL | 1st | 1 | 2 | CONSTRUCTION OF 1 UNIT 1STRY-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER - MC ARTHUR S. MADANI IS | 8496765.67 | 7108626.1 | COMPLETED | 1 | October 3, 2024 | November 29, 2024 |  | 2024-012 | December 8, 2023 | December 15, 2023 | December 27, 2023 | January 26, 2024 | June 4, 2024 | ELLE | w/ Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1 | COMPLETED
LMS 2024 | Region XI | Davao Oriental | 129310 | Logdeck Elementary School | LUPON | 2nd | 1 | 2 | CONSTRUCTION OF 1 UNIT 1STRY-2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER - LOGDECK ELEMENTARY SCHOOL | 8257545.94 | 6290078.09 | COMPLETED | 1 | September 26, 2024 | November 20, 2024 |  | 2024-011 | December 8, 2023 | December 15, 2023 | December 27, 2023 | January 26, 2024 | May 29, 2024 | Matt Glass | w/ Time Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 12.24 | [8 empty] | 1st | 1 | COMPLETED
LMS 2024 | Region XI | Panabo City | 129813 | Mabunao ES | CITY OF PANABO | 2nd | 1 | 2 | CONSTRUCTION OF 1STY2CL SCHOOL BUILDING (WITH TOILET) WITH PROVISION OF RAINWATER COLLECTOR, SOLAR PV ENERGY SYSTEM, WATER SYSTEM AND FLOOD MARKER | 9748536.16 | 7000000 | ONGOING | 0.51 |  |  |  |  | JUNE 28, 2024 | JULY 3, 2024 | JULY 18, 2024 | AUGUST 8, 2024 |  | RUPLINO SEISMUNDO CONSTRUCTION CORPORATION | on-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0.51 | 0 | [9 empty] | 1st | 1 | ONGOING