## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2024 SF | Region X | Bukidnon | 126265 | Danatag ES | BAUNGON | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126519 | Dona Pilar ES | LIBONA | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126643 | San Miguel ES | MANOLO FORTICH | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 500676 | DAGUMBAAN INTEGRATED SCHOOL | TALAKAG | 1st | 1 | - | - | 560 | 560 | 14 | - | - | 1925000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126504 | Cawayan ES | LANTAPAN | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126512 | Valbueco ES | LANTAPAN | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126756 | Kalagangan CES | SAN FERNANDO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126764 | Mahayag ES | SAN FERNANDO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126436 | Gutapol ES | KIBAWE | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126475 | Kitaotao CES | KITAOTAO | 3rd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127959 | Bayabas Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127972 | Bayanga Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127977 | Lumbia Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127987 | Upper Tignapoloan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 306046 | Pigsag-an National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 502012 | Balongkot Integrated School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127942 | East City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127943 | FS Catanico Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127944 | Gusa Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127954 | Tablon Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127964 | Camaman-an Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127965 | Indahag Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 304116 | Indahag National High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 500684 | Bugang Integrated School | SAGAY | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127667 | Amoros ES | CITY OF EL SALVADOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127681 | Ulaliman Elementary School | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 500799 | Pigsalohan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 500800 | Dukdokaan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2nd | 1 |  | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126548 | Mapulo Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126557 | Aglayan Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126558 | Bangcud Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126572 | San Roque Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126582 | Kalasungay Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501188 | Kibalabag Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501189 | Capitan Angel Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501190 | Magsaysay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501581 | Tuburan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501582 | Simaya Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501852 | Mabuhay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 501236 | MANSABAY ALTO IS | LOPEZ JAENA | 1ST | 1 | - | - | 180 | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127527 | Masubong Primary School | SAPANG DALAGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127602 | Balingasag CS | BALINGASAG | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127603 | Baliwagan CS | BALINGASAG | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127741 | C.Gadrinab ES | LAGONGLONG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127743 | Gaston ES | LAGONGLONG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127744 | Kabulawan ES | LAGONGLONG | 1st | 1 | - | 118 | - | 118 | 3 | - | - | 405900 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 380 | - | 380 | 8 | - | - | 1298000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127783 | Kibungsod CS | MAGSAYSAY (LINUGOS) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127823 | Medina CS | MEDINA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127855 | Inobulan ES | SALAY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127715 | Ampianga ES | SUGBONGCOGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127724 | Kaulayanan ES | SUGBONGCOGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127874 | Babanlagan ES | TALISAYAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304091 | Misamis Oriental General Comprehensive High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127712 | San Nicolas ES | JASAAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127926 | Lugait CS | LUGAIT | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127805 | Manticao CS | MANTICAO | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127935 | Naawan CS | NAAWAN | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127835 | Barra ES | OPOL | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 501747 | Malanang Integrated School | OPOL | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127872 | Sta. Cruz ES | TAGOLOAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 304047 | Oroquieta City NHS - Villaflor Campus | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 304049 | Rizal NHS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Oroquieta City | 500402 | Dullan IS | OROQUIETA CITY (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Ozamis City | 128181 | Felipe Carreon Central School | OZAMIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Tangub City | 128219 | Banglay Elementary School | TANGUB CITY | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Tangub City | 128238 | Aquino ES | TANGUB CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Tangub City | 128240 | Balatacan ES | TANGUB CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Tangub City | 501029 | Bintana Integrated School | TANGUB CITY | 2nd | 1 | - | - | 440 | 440 | 11 | - | - | 1512500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 126839 | Dabongdabong ES | CITY OF VALENCIA | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 126873 | Laligan Central School | CITY OF VALENCIA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 126874 | Lumbayao ES | CITY OF VALENCIA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 500703 | Dagat-Kidavao IS | CITY OF VALENCIA | 4th | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 501120 | Batangan Integrated School | CITY OF VALENCIA | 4th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Valencia City | 501122 | Lumbo Integrated School | CITY OF VALENCIA | 4th | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 500801 | Bantaawan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 240 | - |  | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 501025 | Sulpicio Lugod Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 501436 | Kamanikan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128082 | Luinab Elementary School | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128095 | Sta. Filomena Central School | ILIGAN CITY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128107 | Dona Matrona Actub Yanez MES (Bunawan ES) | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128110 | Kalubihon ES | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128137 | Cabili Village ES | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501369 | Bacolod Central Integrated School | BACOLOD | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127039 | Cayontor PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127049 | Tingintingin PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 200529 | Upper Tugar PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127093 | Bosque Elementary School | LINAMON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127126 | Batal ES | MATUNGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 200508 | Bubong Radapan P S | MATUNGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127159 | Bowi PS | PANTAR | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan ES | PANTAR | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 210 | 210 | 6 | - | - | 726000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 500689 | Lala Proper ES | LALA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127104 | Abucay -Cancamo ES (Olango ES) | MAGSAYSAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 501378 | Shiek Omar Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127174 | Barandia PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127188 | Sudlon ES | SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 137089 | Pangantapan Primary School | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 200505 | Pansur PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 127210 | SAPAD ELEMENTARY SCHOOL | SAPAD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 136949 | SULTAN LINDONGAN PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 136950 | BAYABAO PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126279 | San Miguel ELEMENTARY SCHOOL | BAUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126280 | SAN VICENTE ES | BAUNGON | 1st | 1 | 90 |  |  | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126622 | Camp 1 ES | MANOLO FORTICH | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126815 | Megbadiang ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126336 | Osmena Elementary School | DANGCAGAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126447 | Natulongan CS | KIBAWE | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126662 | Kuya ES | MARAMAG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 128001 | Canitoan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 127967 | South City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126884 | Bura Elementary School | CATARMAN | Lone | 1 | 131 | - | - | 131 | 3 | - | - | 394600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126889 | Mainit ES | CATARMAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126890 | Manduao ES | CATARMAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126929 | Cabuan es | GUINSILIBAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126901 | Pontod Elementary School | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | Lone | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126916 | Naasag ES | MAMBAJAO (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126918 | Quiboro ES | MAMBAJAO (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Gingoog City | 500811 | Pedro Maligmat Integrated School - Elem | GINGOOG CITY | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128086 | Miguel Obach MES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Iligan City | 128146 | Tipanoy ES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1088100 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 604500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126590 | Patpat Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 501195 | Candiisan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127395 | Malibacsan ELementary School | JIMENEZ | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 501871 | Panalsalan Integrated School | PLARIDEL | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126561 | Cabangahan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 126566 | Macote Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 303973 | Managok National High School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Malaybalay City | 314914 | Casisang National High School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127284 | Quezon ES | BALIANGAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127533 | Sapang Dalaga Central Elementary School | SAPANG DALAGA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127334 | Bitoon Elementary School | CLARIN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127339 | Dela Paz Elementary School | CLARIN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127538 | Cagay-Anon ES | SINACABAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127550 | San Isidro Bajo Primary School | SINACABAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Occidental | 127575 | Ozamiz Elementary School | TUDELA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1st | 1 | 157 | - | - | 157 | 4 | - | - | 474900 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 500522 | Kabulakan IS | BALINGOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0
CY 2024 SF | Region X | Misamis Oriental | 127733 | Mosangot ES | BINUANGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0
CY 2023 SF | Region X | Bukidnon | 126280 | San Vicente ES | BAUNGON | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126603 | LARAPAN ES | MALITBOG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126631 | KITAM-IS ES | MANOLO FORTICH | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126781 | KILABONG ES | SUMILAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126814 | MASIMAG ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126817 | MIGPAIT ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 500890 | Iba Integrated School | CABANGLASAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 314923 | Impasugong NHS-Kapitan Bayong Annex | IMPASUG-ONG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126405 | Malinao ES | KADINGILAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 649345 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126706 | Busco ES | QUEZON | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126716 | Miluya ES | QUEZON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126717 | Minsalirac ES | QUEZON | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 500677 | Dilapa Integrated School | QUEZON | 3rd | 1 | - | - | 120 | 120 | 3 | - | - | 347907 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Bukidnon | 126418 | FORCHACU III ES | KALILANGAN | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 127961 | Bongbongon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 127972 | Bayanga Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 127942 | East City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 127956 | Macabalan ES | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 675 | - | - | 675 | 15 | - | - | 1948035 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 1
CY 2023 SF | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 1 | March 7, 2024 | March 4 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Camiguin | 126884 | Bura ES | CATARMAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 322600 | Completed | 1 | April 11, 2024 | 2025-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Camiguin | 126929 | Cabuan es | GUINSILIBAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 1 | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Camiguin | 126901 | Pontod ES | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Camiguin | 129936 | Sagay CS | SAGAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | El Salvador | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Gingoog City | 501024 | Sangalan Integrated School | Ginggoog City | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 695814 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Gingoog City | 128045 | Talisay Elementary School | GINGOOG CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Gingoog City | 304132 | Kalipay National High School | GINGOOG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Gingoog City | 315501 | EUREKA NATIONAL HIGH SCHOOL | GINGOOG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 128093 | Echavez ES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 128156 | SUAREZ CENTRAL SCHOOL | ILIGAN CITY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 304140 | Don Jose F. Yañez MHS (Bunawan NHS) | ILIGAN CITY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 304150 | Iligan City NSOF | ILIGAN CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 304152 | Maria Cristina National High School | ILIGAN CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan Annex | ILIGAN CITY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Iligan City | 500698 | Del Carmen Integrated School | ILIGAN CITY | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier | 322600 | Completed | 1 | April 11, 2024 | 2025-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 1 | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 1 | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 1 | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 1 | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 1 | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 127166 | Pantar CES | PANTAR | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 1 | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1st |  | - | 180 | - | 180 | 4 | - | 14 | 738100 | Regional Office Implementation | 55% Allocation for Regular Supplier | 512200 | Completed | 1 | April 11, 2024 | 2001-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 11, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 11, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 127239 | Pigcarangan Integrated School | TUBOD (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 1 | April 11, 2024 | 2009-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 500249 | Carusa Integrated School | KAPATAGAN | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 508800 | Completed | 1 | April 16, 2024 | 2022-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 758400 | Completed | 1 | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 1 | April 16, 2024 | 2004-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2011-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 160 | 160 | 4 | - | 14 | 676100 | Regional Office Implementation | 55% Allocation for Regular Supplier | 472200 | Completed | 1 | April 16, 2024 | 2011-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 1 | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 1 | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 501240 | Calube Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 339200 | Completed | 1 | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 1 | April 16, 2024 | 2015-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 126591 | San Jose ES | CITY MALAYBALAY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 1 | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 314916 | Malaybalay City NHS | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 103610 | Damitan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 103647 | Pigpamulahan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 103677 | Incalbog Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 126576 | BCT Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote National HIgh School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 284400 | Completed | 1 | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote National HIgh School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 501190 | Magsaysay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 501579 | Kilap-agan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 1 | April 6, 2024 | 4/1 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 501580 | Casisang Central Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City | 501852 | Mabuhay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 1 | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Malaybalay City |  | Malaybalay City ALS Center | CITY MALAYBALAY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 758400 | Completed | 1 | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127527 | Masubong Primary School | SAPANG DALAGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 11, 2024 | 3/18 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127290 | Bonifacio CS | BONIFACIO | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 948000 | Completed | 1 | April 11, 2024 | 3/8 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127342 | Lupagan Elementary School | CLARIN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 1 | April 11, 2024 | 3/8 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127344 | Pan-ay ES | CLARIN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 1 | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127346 | Segatic Sur Es To Segatic Norte Ps | Clarin | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127355 | Ozamiz ES | CLARIN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 1 | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd |  | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Misamis Occidental | 127562 | Camating ES | TUDELA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 284400 | Completed | 1 | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 127604 | Binitinan ES | BALINGASAG | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 1 | March 7, 2024 | March 1 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 500251 | Lantad IS | BALINGASAG | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 339200 | Completed | 1 | March 7, 2024 | March 4 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 1 | July 30, 2024 | 6/3 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 853200 | Completed | 1 | July 30, 2024 | 6/3 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1st | 1 | - | 526 | - | 526 | 12 | - | - | 1694200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1109600 | Completed | 1 | July 30, 2024 | 6/7 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 127744 | Kabulawan ES | LAGONGLONG | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 1 | July 30, 2024 | 6/7 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | - | - | - | - | - | - | - | 0 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0
CY 2023 SF | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 1 | July 30, 2024 | 6/13 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1896000 | Completed | 1 | July 30, 2024 | 6/13 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 315322 | Damayuhan NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 20% Allocation for E-Bamboo | 189600 | Completed | 1 | July 30, 2024 | 6/17 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1896000 | Completed | 1 | July 30, 2024 | 6/17 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1137600 | Completed | 1 | July 30, 2024 | 6/21 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 1 | July 30, 2024 | 6/27 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1st |  | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 508800 | Completed | 1 | July 30, 2024 | 6/27 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 127738 | Sugbongcogon CS | SUGBONGCOGON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 1 | March 17, 2024 | 6/28 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 501161 | Luna Integrated School | CLAVERIA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 1 | March 17, 2024 | 2/9 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 1 | March 17, 2024 | 2/9 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 501158 | Tuod Integrated School | MANTICAO | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 1 | March 17, 2024 | 2/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Misamis Oriental | 501038 | Maribojoc Integrated School | TAGOLOAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 1 | March 17, 2024 | 2/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Oroquieta City | 127458 | Poblacion 2 ES | OROQUIETA CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 1 | March 17, 2024 | 3/8 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 1 | March 17, 2024 | 3/8 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 1 | March 17, 2024 | 3/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2023 SF | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | 7 | - | 341690 | Regional Office Implementation | 55% Allocation for Regular Supplier | 229100 | Completed | 1 | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2023 SF | Region X | Ozamis City | 128192 | Cruz Lanzado Saligan Elementary School | OZAMIS CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 1 | April 11, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2023 SF | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1163700 | Regional Office Implementation | 55% Allocation for Regular Supplier | 763200 | Completed | 1 | April 11, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2023 SF | Region X | Valencia City | 126875 | Mabuhay Elementary School | CITY OF VALENCIA | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 14400 | Completed | 1 | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Valencia City | 500703 | Dagat-Kidavao IS | CITY OF VALENCIA | 4th | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2023 SF | Region X | Valencia City | 500705 | Mt. Nebo ES | CITY OF VALENCIA | 4th | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 1 | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304011 | Marcela T. Mabanta NHS | KAUSWAGAN | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1413900 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304008 | Linamon NHS | LINAMON | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501557 | Matampay Integrated School | MATUNGAO | 1st |  | - | - | 180 | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 225 | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127370 | San Francisco ES | CONCEPCION | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 405 | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 225 | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 341233 | Kinoguitan SHS | KINOGUITAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 126889 | Mainit ES | CATARMAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 500686 | Sto. Niño Integrated School | CATARMAN | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 941880.9772 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 706410.7329 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Camiguin | 500962 | Bacnit Integrated School | SAGAY | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 706410.7329 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 325701 | SAN FRANCISCO DE ASIS NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 304065 | Cogon National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 304797 | Sinaloc National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2022 SF | Region X | El Salvador | 501927 | Kalabaylabay Integrated School | CITY OF EL SALVADOR | 2nd | 1 | - | - | 411 | 411 | 10 | - | - | 1208396.9323 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200529 | Upper Tugar PS | KAUSWAGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 315106 | Sultan Dimasangcay Mananggolo IS (Delabayan ES) | KAUSWAGAN | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501807 | Baraason Integrated School | KAUSWAGAN | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Inudaran PS | KAUSWAGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127139 | Pangi Elementary School | MATUNGAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200508 | Bubong Radapan P S | MATUNGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127168 | Pendulonan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127171 | Sigayan Adil PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan ES | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127173 | Tawanan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304019 | Pantar National High School | PANTAR | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200543 | Malimbato Primary School | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 459 | 459 | 11 | - | - | 1503757.5812 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Payong Dalamas ES | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501378 | Shiek Omar Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127174 | Barandia PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127176 | Buntong ES | SALVADOR | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127180 | Daligdigan PS | SALVADOR | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127183 | Mabatao ELEMENTARY SCHOOL | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127188 | Sudlon ES | SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200505 | Pansur PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Pangantapan PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Inasagan PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Inudaran PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Mindalano PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127192 | Carcum Prim. School | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 127193 | Dansalan PS | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 136948 | SULTAN MIMBISA LOMABAO PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 136949 | SULTAN LINDONGAN PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200533 | Beruar Elementary School | TANGCAL | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 200534 | Tangkal Proper IPS | TANGCAL | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2nd | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Brgy. Bayabao PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Lamaosa PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Lanao del Norte |  | Lingco-an PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127276 | Lipacon ES | BALIANGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127360 | Balongkot ES | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127362 | Debaloy ES | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127365 | Mantukoy PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127366 | Marugang Elementary School | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127367 | Migubay PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127373 | Upper Salimpono PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 201020 | Virayan PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501858 | New Casul Integrated School | CONCEPCION | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127476 | Baga PS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127477 | Bangko ES | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127478 | Camanucan Elementary School | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127479 | De La Paz Primary School | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127480 | F.T. Paylaga MPS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127481 | Map-An PS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127512 | Boundary Primary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127517 | Dasa Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127518 | Dioyo Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127519 | Disoy ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127520 | El Paraiso Primary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127521 | Feliciano Baguio PS | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127522 | Libertad Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127525 | Manalac ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127529 | Napilan Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127531 | Salimpono Elemntary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127532 | Salvador ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127536 | Upper Bautista PS | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127537 | Ventura Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 501884 | Bitibut Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 400 | 400 | 10 | - | - | 1177351.2215 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127543 | Dinas Elementary School | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127544 | Estrella ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127546 | Libertad Alto ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127549 | San Isidro Alto ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127550 | San Isidro Bajo Primary School | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Occidental | 127551 | San Lorenzo Ruiz ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 341228 | Mantangale SHS | BALINGOAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127719 | Buko ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 201506 | Kalitian ES | KINOGUITAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 360848 | Esperanza Senior High School | KINOGUITAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1st | 1 | - | - | 116 | 116 | 3 | - | - | 381218.5875 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127745 | Kamansi ES | LAGONGLONG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 341234 | Lagonglong SHS | LAGONGLONG | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2058072.7576 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127724 | Kaulayanan ES | SUGBONGCOGON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 500999 | G. Pelaez IS | GITAGUM | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2nd | 1 | - | 855 | - | 855 | 19 | - | - | 2793098.7425 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19 | 0 |  | 1
CY 2022 SF | Region X | Misamis Oriental | 501321 | Lubluban IS | LIBERTAD | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1