## HEALTH 2022-2024
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | CATEGORY 2
SCHOOL HEALTH FACILITIES 2024 | CAR | Abra | 134985 | Abang ES | BUCAY | Lone | 1 |  | Construction of 1 storey 7m x 9m Medical and Denatl Facilities | 2800000 |  | 2777723.92 | Completed | 100% | September 11, 2024 | September 18, 2024 | CAR-ABRA-2024-04-008 | CAR-ABRA-2024-04-008 | April 17, 2024 | April 24, 2024 | May 07, 2024 | May 16, 2024 | July 09, 2024 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | CAR | Apayao | 501344 | Butao Integrated School | CALANASAN (BAYAG) | Lone | 1 |  | Construction of Handwashing Facility,Comfort Room, and clinic | 5079441.86 |  | 5023658.56 | under procurement | 0% |  |  |  |  | September 17,2024 | Septemebr 25,2024 | October 7,2024 | October 28,2024 |  | HighLand Construction Services |  | 0 | 0 | 1 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | CAR | Benguet | 305138 | Loo National High School | BUGUIAS | Lone | 1 |  | Construction of Clinic, Comfort Room, Group Handwashing Facility | 4805722.03 |  | 4403550.47 | On-going | 85% | June 11, 2025 |  | SHFP-2024-01 | SHFP-2024-02 | August 06,2024 | August 14,2024 | August 27,2024 | December 18, 2024 | January 16, 2025 | CE-CE CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 1 | 0 | [5 empty] | 55% | 30%
SCHOOL HEALTH FACILITIES 2024 | CAR | Ifugao | 305190 | Sta. Maria National High School | ALFONSO LISTA (POTIA) | Lone | 1 |  | Construction of School Clinic, Toilet, Water System & Group Handwashing Facility | 6956039.99 |  | 6250490.52 | completed | 100% | December 25, 2024 | January 22,2025 |  | 2024-01 | December 18, 2023 | January 3, 2024 | January 16, 2024 | January 24, 2024 | May 23, 2024 | Habiling Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | Lone | 1 |  | Construction of School Clinic | 4458237.06 |  | 4285187.15 | On-going | 85% | November 12, 2024 |  | SCHOOL CLINIC 2024-CAR-KALINGA-001 | SCHOOL CLINIC 2024-CAR-KALINGA-001 | November 24, 2023 | December 4, 2023 | December 18, 2023 | February 6, 2024 | August 14, 2024 | EDEJUN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 1 | 0 | [5 empty] | 85% | 0%
SCHOOL HEALTH FACILITIES 2024 | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 |  | Construction of School Clinic, Water and Sanitation Facilities - 3-Seater with Overhead Water Tank, Group Handwashing Facility and Water System (Water Source at Higher Elevation than School Building) | 21529337.31 |  | 21313820.23 | On-going | 93% | March 2, 2025 |  | INFRA 2023-007 | INFRA 2023-007 | November 25, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | July 5, 2024 | CNL Construction | With time extension | 0 | 0 | 0 | 1 | 0 | [5 empty] | 83% | 10%
SCHOOL HEALTH FACILITIES 2024 | CAR | Tabuk City | 305926 | BANTAY NATIONAL HIGH SCHOOL | Tabuk City | 1st | 1 |  | Construction of School Clinic | 4565251.4 |  | 4299998.99 | completed | 100% | September 9, 2024 | August 27, 2024 | I-2023-6 | I-2023-6 | December 2 - December 21, 2023 | December 8, 2023 @ 8:00am | December 21, 2023 @ 1pm | January 22, 2024 | May 15, 2024 | Northpine Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131457 | Ambacon ES | LAS NIEVES | 1st | 1 |  | Construction of Group Handwashing Facility for Elementary | 332182.19 |  | 327592.85 | completed | 100% | February 18, 2025 | February 18, 2025 | WINS 2024 - R XIII - AGUSAN DEL NORTE - 001 | WINS 2024 - R XIII - AGUSAN DEL NORTE - 001 | September 19, 2024 |  | November 19, 2024 |  |  | J-R3 Construction and Supply | WITH APPROVED REALIGNMENT from Baleguian ES | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1st | 1 |  | Construction of School Clinic | 3727536.02 |  | 3141911.69 | On-going | 40% | March 11, 2025 |  | SCHOOL CLINIC 2024 - R XIII - AGUSAN DEL NORTE - 003 | SCHOOL CLINIC 2024 - R XIII - AGUSAN DEL NORTE - 003 | September 30, 2024 | October 14, 2024 | October 24, 2024 | December 20, 2024 | December 23, 2024 | J-R3 Construction and Supply | with Time Extension | 0 | 0 | 0 | 1 | 0 | [5 empty] | 40% | 0%
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Agusan del Norte | 131546 | Santiago CES | SANTIAGO | 2nd | 1 |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 1921578.86 |  | 1830300.26 | On-going | 40% | [8 empty] | March 11, 2025 | MCLA Construction | with RTA submitted to CO; awaiting downloading of subaro | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 40%
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1st | 1 |  | Construction of School Clinic | 3727536.02 |  |  | completed | 100% | January 11, 2024 | Feb 19, 2025 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | December 1, 2024 | December 11, 2024 | January 4, 2024 | August 27, 2024 | October 14, 2024 | ILMAR CONSTRUCTION & SUPPLY | COMPLETED WAITING FOR FINAL INSPECTION | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1st |  |  | Construction of 2 Units Group Handwashing Facility for Elementary | 602766.77 |  |  | completed | 100% | November 27, 2024 | November 20, 2024 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | SCHOOL CLINIC 2024 -R XIII-BAYUGAN CITY -001 | December 1, 2024 | December 11, 2024 | January 4, 2024 | August 27, 2024 | October 14, 2024 | ILMAR CONSTRUCTION & SUPPLY | COMPLETED WAITING FOR FINAL INSPECTION | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2nd | 1 |  | Construction of School Clinic | 3823114.17 |  | 2923591.71 | Completed | 100% | November 22, 2024 | November 4, 2024 | 10312534 | 10312534 | November 13, 2023 | November 9, 2023 | December 6, 2023 | May 24, 2024 | May 24, 2024 | ETP BUILDERS |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | Lone | 1 |  | Construction of Group Handwashing Facility | 355236.65 |  | 900590.69 | completed | 100% | August 21, 2024 | August 21, 2024 | INFRA2023-005 | INFRA2023-005 | December 5, 2023 | December 11, 2023 | January 3, 2024 | January 29, 2024 | May 24, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 132311 | Kanihaan Elementary School | LIBJO (ALBOR) | Lone | 1 |  | Construction of Group Handwashing Facility | 412704.93 |  | 320750.32 | completed | 100% | August 21, 2024 | August 21, 2024 | INFRA2023-006 | INFRA2023-005 | December 6, 2023 | December 12, 2023 | January 4, 2024 | January 30, 2024 | May 25, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Dinagat Island | 132514 | Borres-Omega Elementary School | SAN JOSE (Capital) | Lone | 1 |  | Construction of Group Handwashing Facility | 362304.93 |  | 288158.47 | completed | 100% | August 21, 2024 | August 21, 2024 | INFRA2023-007 | INFRA2023-005 | December 7, 2023 | December 13, 2023 | January 5, 2024 | January 31, 2024 | May 26, 2024 | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132127 | Corregidor Elementary Schoo | DAPA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 100% | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132128 | Dagohoy Elementary School | DAPA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 100% | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132178 | San Fernando Elementary School | DEL CARMEN | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 100% | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Siargao | 132147 | Catangnan Elementary School | GENERAL LUNA | 1st | 1 |  | Proposed Construction of Handwashing facility (option 1A with Roofing and with counter in tile finish) | 300000 |  | 295477.71 | completed | 100% | July 13, 2024 | July 9, 2024 | BEFF-INFRA2024-004 | BEFF-INFRA2024-004 | January 27, 2024 | February 7, 2024 | April 2, 2024 | April 10, 2024 | May 29, 2024 | ALLYDE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd | 1 |  | Water and Sanitation Facilities - 4-Seater | 1125598.1 |  | 961297.61 | completed | 100% | October 28, 2024 | October 18, 2024 | 2023-11-575 | FY-2023-INFRA-013 | February 24, 2024 | March 4, 2024 | March 18, 2024 | July 26, 2024 | August 9, 2024 | ARDRAW CONSTRUCTION AND SUPPLY | Re-bid; 1st Bidding Failure | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao City | 132248 | Cantiasay Elementaryn School | SURIGAO CITY (Capital) | 2nd |  |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 2226633.74 |  | 1994244.69 | completed | 100% | November 12, 2024 | November 21, 2024 | 2023-11-576 | FY-2023-INFRA-014 | December 10, 2023 | December 18, 2023 | January 5, 2024 | July 27, 2024 | August 9, 2024 | RJB CONSTRUCTION AND SUPPLY | with liquidated damages | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Norte | 132472 | Ellaperal ES | PLACER | 2nd | 1 |  | Construction of Toilets | 1001168.65 |  | 998235.23 | completed | 100% | July 27, 2024 | October 20, 2024 | 2024-001-WATSAN-CARAGA | INFRA002-2024 | November 9, 2023 | November 28, 2023 | November 28, 2023 | May 9, 2024 | May 13, 2024 | RJB CONSTRUCTION AND SUPPLY | With Time Extension/with LD | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Norte | 132472 | Ellaperal ES | PLACER | 2nd |  |  | Construction of Water System | 2084603.55 |  | 2081581.6 | Completed | 100% | July 28, 2024 | October 20, 2024 | 2024-001-WATER SYSTEM-CARAGA | INFRA001-2024 | November 9, 2023 | November 16, 2023 | November 28, 2023 | May 9, 2024 | May 13, 2024 | RJB CONSTRUCTION AND SUPPLY | With Time Extension/with LD | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Surigao del Sur | 304877 | Carrascal National High School | CARRASCAL | 1st | 1 |  | Construction of School Clinic | 3349173.05 |  | 2536593.52 | Completed | 100% | March 12, 2025 | March 12, 2025 | SCHOOL CLINIC 2023 - R XIII - SURIGAO DEL SUR - 045 | 009 - 2024 | November 9, 2023 | November 15, 2023 | November 30, 2023 | February 19, 2024 | October 14, 2024 | TRIDENT ENGINEERING SERVICES | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st | 1 |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 1073605.29 |  | 2634115.51 | COmpleted | 100% | August 6, 2024 | Sept. 20, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st |  |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish | 352744.25 |  | 259813.99 | COmpleted | 100% | July 27, 2024 | August 26, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st |  |  | Construction of One (1) Unit One (1) Storey School Clinic | 3669893.83 |  | 2634115.51 | COmpleted | 100% | August 26, 2024 | Sept. 20, 2024 | 2023-11-203 | 2023-11-203 | November 29, 2023 | December 7, 2023 | December 27, 2023 | January 10, 2024 | July 8, 2024 | CYL Construction and Supply | Completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 943148.5 |  | 933992.7 | completed | 100% | February 28, 2025 | February 7, 2025 | WINS2024-NCR-SANJUAN-002 | INFRA2024-004 | June 28, 2024 | July 8, 2025 | July 18, 2024 | November 11, 2024 | December 20, 2024 | Sherf Builders Corp | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 1098292.86 |  | 884385.37 | completed | 100% | October 14, 2024 | September 26, 2024 | WINS2024-NCR-SANJUAN-001 | INFRA-2024-001 | December 8, 2023 | December 15, 2023 | January 4, 2024 | January 9, 2024 | August 14, 2024 | J.G Mendoza Builders | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | Lone | 1 |  | Construction of Group Handwashing Facilities (with Roofing, with Counter, with Tile Finish) | 558579.85 |  | 553107.2 | completed | 100% | February 17, 2025 | February 7, 2025 | WINS2024-NCR-SANJUAN-002 | INFRA2024-004 | June 28, 2024 | July 8, 2025 | July 18, 2024 | November 11, 2024 | December 20, 2024 | Sherf Builders Corp | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Makati City | 136703 | Hen. Pio del Pilar ES Main | CITY OF MAKATI | 1st | 1 |  | Repair of School Clinic | 750000 |  | 748911.83 | On-going | 10% | July 18, 2025 |  | PB-SDO-MKT-2024-008 | SDO-MKT-25-013 | November 29, 2024 | December 6, 2024 | December 18, 2024 | December 23, 2024 | May 19, 2025 | J.R.C.F Construction | On-going | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 10%
SCHOOL HEALTH FACILITIES 2024 | NCR | Mandaluyong City | 500332 | Highway Hills Integrated School | CITY OF MANDALUYONG | Lone | 1 |  | Repair of classroom to be used/Converted to School Clinic | 750563.88 |  | 723815.73 | On-going | 10% | March 20, 2025 | March 20, 2025 | MANDALUYONG-003 | OSEC-NCR-221-7805 | October 24, 2024 | November 5, 2024 | November 12, 2024 | November 13, 2024 | January 6, 2025 | MAAV CONSTRUCTION SERVICES | for mobilization; with subaro downloaded already; Batch 15 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 10% | 0%
SCHOOL HEALTH FACILITIES 2024 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1st | 1 |  | Construction of School Clinic | 5000000 |  | 4949991.33 | COMPLETED | 100% | November 24, 2024 | May 6, 2025 | N/A | N/A | May 8, 2024 | May 18, 2024 | May 28, 2024 | June 25, 2024 | September 2, 2024 | LARZEN-DUTHCER CONSTRACTOR CORPORATION | Delayed due to double handling and typhoons | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Manila | 136428 | Gregoria de Jesus ES | TONDO | 2nd | 1 |  | Construction of School Clinic | 5000000 |  | 3761368.61 | COMPLETED | 100% | November 24, 2024 | December 2, 2024 | N/A | N/A | May 8, 2024 | May 18, 2024 | May 28, 2024 | June 25, 2024 | September 2, 2024 | OPEN BUILDERS INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | Lone | 1 |  | Repair of School Clinic | 947962.57 |  | 943482.23 | completed | 100% | December 3, 2024 | December 3, 2024 | 2024-006 | 2024-006 | June 21, 2024 | June 24, 2024 | June 26, 2024 | June 28, 2024 | September 4, 2024 | Ayana Construction | Received sub-aro August 12, 2024 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136769 | Baclaran Elementary School Unit II | CITY OF PARAÑAQUE | 1st | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 100% | August 18, 2024 | August 16, 2024 | PB-2024-Infra01a | PB-2024-Infra01a | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 100% | August 18, 2024 | August 16, 2024 | PB-2024-Infra01d | PB-2024-Infra01d | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2nd | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 100% | August 18, 2024 | August 16, 2024 | PB-2024-Infra01b | PB-2024-Infra01b | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | NCR | Paranaque City | 137129 | Don Bosco Elementary School | CITY OF PARAÑAQUE | 2nd | 1 |  | Repair of Classroom to be Used/Converted to School Clinic (7.00m x 9.00m) | 998176.98 |  | 716620.8 | completed | 100% | August 18, 2024 | August 16, 2024 | PB-2024-Infra01c | PB-2024-Infra01c | October 30, 2023 | November 6, 2023 | November 17, 2023 | March 21, 2024 | June 19, 2024 | RGDG Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | NCR | Pasig City | 136717 | Ilugin Elementary School | CITY OF PASIG | Lone | 1 |  | Rehabilitation of clinic | 1290256 |  | 997541.22 | completed | 100% | April 10, 2025 | April 8, 2024 | PB-2024-Infra01a | PB-2024-Infra01a | June 27, 2024 | July 4, 2024 | July 29, 2024 | August 12, 2024 | December 11. 2024 | Emica Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Pasig City | 136719 | Liberato Damian Elementary School | CITY OF PASIG | Lone | 1 |  | Rehabilitation of clinic | 1290256 |  | 997541.22 | completed | 100% | April 10, 2025 | April 8, 2024 | PB-2024-Infra01b | PB-2024-Infra01b | June 27, 2024 | July 4, 2024 | July 29, 2024 | August 12, 2024 | December 11. 2024 | Emica Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Taguig City and Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1st | 1 |  | Repair of School Clinic (9.8 x 11.50m) | 1300000 |  | 1269999.79 | completed | 100% | March 14, 2025 | April 22, 2025 | DTP-CY2024-infra-001 | DTP-CY2024-infra-001 | July 31, 2024 | August 7, 2024 | August 19, 2024 | August 27, 2024 | January 3, 2025 | Jepa Construction and Development Corp. | with subaro downloaded already batch 15 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | NCR | Taguig City and Pateros | 136881 | Bagong Tanyag Elementary School - Annex A | TAGUIG CITY | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 350000 |  | 347254.52 | completed | 100% | November 27, 2024 | November 11, 2024 | DTP-CY2024-infra-054 | BAC-SVP-2024-40 | August 1, 2024 | August 5, 2024 | August 5, 2024 | August 8, 2024 | October 14, 2024 | Sherf Builders Corporation | with subaro downloaded already batch 13 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 |  | Construction of School Clinic, Water and Sanitation Facilities - 4-Seater and Group Hadwashing Facility - For Secondary (Option 1B - with Roofing, with Counter, with Tile Finish) | 4975483.73 |  | 3864853.37 | On-going | 96% | SEPTEMBER 14, 2024 |  | Construction of School Clinic, Water and Sanitation Facilities - 4-Seater and Group Hadwashing Facility - For Secondary (Option 1B - with Roofing, with Counter, with Tile Finish) | INFRA 2023-123 | nov 13, 2023 | november 20, 2024 | december 4, 2023 | MAY 14, 2024 | MAY 17, 2024 | JIRK CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | [5 empty] | 95% | 1%
SCHOOL HEALTH FACILITIES 2024 | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 3rd | 1 |  | Construction/Repair of Health Facilities | 3516992.21 |  | 1193349.72 | Completed | 100% | March 22, 2025 | March 11, 2025 | Construction/Repair of Health Facilities of Cauayan North Central School | CW-003 S. 2024 | July 2, 2024 | July 10, 2024 | July 23, 2024 | August 6, 2024 | December 23, 2024 | Amianan Construction | with subaro downloaded already; Batch 15 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region II | City of Ilagan | 500080 | Lupigue Integrated School | ILAGAN CITY (CAPITAL) | 1st | 1 |  | Construction/Repair of Health Facilities | 3004753.81 |  | 2991910.63 | completed | 100% | October 3, 2024 | March 3, 2025 | 10437033 | INF-2024-03 | December 19, 2023 | December 27, 2023 | January 8, 2024 | January 12, 2024 | June 24, 2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region II | Isabela | 500019 | Yeban Integrated School | BENITO SOLIVEN | 2nd | 1 |  | Construction/Repair of Health Facilities | 1563881.72 |  | 1512875.56 | Completed | 100% | July 21, 2024 | July 19,2024 | Proj ID No. 2023-11-01 | 2024-0504 | November 11,2023 | November 20,2023 | December 5, 2023 | December 13, 2023 | May 15,2024 | CAMBERWELL CONSTRUCTION AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region II | Nueva Vizcaya | 300642 | PAIMA NATIONAL HIGH SCHOOL | BAYOMBONG | Lone | 1 |  | Construction/Repair of Health Facilities | 2119125.83 |  | 1486952.49 | COMPLETED | 100% | March 27, 2025 | April 4, 2025 | PB-3-003-SDO-CY2024HWF | PB-3-003-SDO-CY2024HWF | March 19, 2024 | March 17, 2025 | April 5, 2024 | June 24, 2024 | December 27, 2024 | B. Flores Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 95% | 5%
SCHOOL HEALTH FACILITIES 2024 | Region II | Quirino | 104224 | Aglipay West CS | AGLIPAY | Lone | 1 |  | Construction/Repair of Health Facilities | 281498.71 |  | 240747.08 | Completed | 100% | July 22, 2024 | July 17, 2024 | HEALTH FACILITIES 2024 - REGION II - QUIRINO - 001 | 55-12-22-2023 | December 23, 2023 | December 29, 2023 | January 11, 2024 | February 15, 2024 | June 7, 2024 | HABILING CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4th | 1 |  | Construction/Repair of Health Facilities | 1563881.72 |  | 1407012.83 | not yet started | 0% | August 1, 2025 |  | WINS 2024 - REG II - SANTIAGO - 001 | PI-CB-2024-004 | November 14, 2024 | November 21, 2024 | December 4, 2024 | December 14, 2024 |  | HJM CIBSTRUCTION | To be awarded | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region II | Tuguegarao City | 300669 | Cataggaman National High School | TUGUEGARAO CITY(Capital) | 3rd | 1 |  | Construction/Repair of Health Facilities | 281498.71 |  |  | not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region III | Balanga City | 502343 | Tanato Integrated School | CITY OF BALANGA (Capital) | 2nd | 1 |  | Construction of School Clinic | 3371042.12 |  | 2612069.69 | completed | 100% | December 25, 2024 | October 11, 2024 | CB-EPA-2023-003 | CB-EPA-2023-004 | November 29, 2023 | December 7, 2023 | December 19, 2023 | July 18, 2024 | August 12, 2024 | R.Z. TIGAS CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st | 1 |  | Construction of School Clinic | 3417948.14 |  | 2426684.86 | completed | 100% | August 28, 2024 | August 28, 2024 | School Clinic 2024-Region III-Bataan-003 | CON24-001 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | Rodmac Construction & Trading | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st |  |  | Construction of Group Handwashing | 483964.6 |  | 365876.45 | completed | 100% | July 29, 2024 | July 29, 2024 | WINS 2024-Region III-Bataan-004 | CON24-002 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | AR-ESBI Construction | completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st |  |  | Construction of Toilets | 813890.87 |  | 614266.62 | completed | 100% | July 29, 2024 | July 29, 2024 | WATSAN 2024-Region III-Bataan-001 | CON24-003 | October 25, 2023 to November 21, 2023 | November 7, 2023 | November 21, 2023 | December 13, 2023 | May 29, 2024 | AR-ESBI Construction | completed | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Bulacan | 104836 | Hagonoy Cs | HAGONOY | 1st | 1 |  | Construction of School Clinic | 2746771.01 |  | 2167776.11 | completed | 100% | October 10, 2024 | October 10, 2024 | PB-24-005 | PB-24-05-010 | December 5, 2023 | 12/14/2023 | 12/27/2023 | January 8, 2024 | June 5, 2024 | JFM ALTITUDE CONSTRUCTION CORP. |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Gapan City | 105314 | Bagong Silang ES | CITY OF GAPAN | 4th | 1 |  | Construction of handwashing facilities | 325467.63 |  | 320478.6 | Completed | 100% | June 19, 2024 | June 13, 2024 | RFQ2024-009 | RFQ2024-009 | August 6, 2024 | N/A | April 12, 2024 | April 12, 2024 | May 29, 2024 | JOYNIELTIN CONSTRUCTION AND TRADING | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1st | 1 |  | Construction of School Clinic | 3598832.44 |  | 3577749.05 | Completed | 100% | August 15, 2024 | August 15, 2024 | PB-2023-12-005 | SBC-2024-04-005 | December 4, 2023 | 12/14/2023 | December 26, 2023 | December 29, 2023 | May 17, 2024 | T.G Ocampo Construction and Surveying Services |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th | 1 |  | 2 units - Handwashing facility Option 1:Variant B | 600000 |  | 488546.2 | completed | 100% | October 10, 2024 | October 7, 2024 | 2023-001-INFRA | 2023-001-INFRA | November 21, 2023 | November 29, 2023 | December 12, 2023 | May 5, 2024 | May 10, 2024 | Emica Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Meycauayan City | 500439 | Bancal Integrated School | CITY OF MEYCAUAYAN | 4th |  |  | 2 units - Four seater toilet detached | 1600000 |  | 1348896.3 | completed | 100% | October 10, 2024 | October 7, 2024 | 2023-001-INFRA | 2023-001-INFRA | November 21, 2023 | November 29, 2023 | December 12, 2023 | May 5, 2024 | May 10, 2024 | Emica Builders and Supply |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Olongapo City | 107126 | Gordon Heights I Elementary School | OLONGAPO CITY | 1st | 1 |  | Construction of School Clinic | 3442212.05 |  | 3436165.64 | completed | 100% | April 25, 2025 | April 16, 2025 | 2024-06-207 | 2024-06-207 | July 3, 2024 | July 10, 2024 | July 22, 2024 | August 1, 2024 | December 26, 2024 | JFM Altitude | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 90% | 10%
SCHOOL HEALTH FACILITIES 2024 | Region III | Olongapo City | 107139 | Kalalake ES | OLONGAPO CITY | 1st | 1 |  | Construction of School Clinic | 3500000 |  | 3422255.63 | completed | 100% | April 25, 2025 | April 21, 2025 | 2024-06-207 | 2024-06-207 | July 3, 2024 | July 10, 2024 | July 22, 2024 | August 1, 2024 | December 26, 2024 | J.I. Viacrusis Construction | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 80% | 20%
SCHOOL HEALTH FACILITIES 2024 | Region III | Pampanga | 106298 | Moras Dela Paz ES | SANTO TOMAS | 4th | 1 |  | Construction of School Clinic | 3534027.65 |  | 3517524.14 | completed | 100% | August 28, 2024 | August 28, 2024 | I-2024-001 | I-2024-001 | November 16, 2023 | November 24, 2023 | December 6, 2023 | May 8, 2024 | May 13, 2024 | BFF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 |  | Construction of School Clinic | 3534027.65 |  | 3527033.97 | COMPLETED | 100% | September 3, 2024 | September 2, 2024 | N/A | Infrastructure 2024-001 | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 15, 2024 | May 22, 2024 | BFF CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Tarlac City | 106705 | San Manuel ES | CITY OF TARLAC (Capital) | 2nd | 1 |  | Construction of School Clinic | 3371042.12 |  | 2619888.88 | COMPLETED | 100% | September 25, 2024 | September 25, 2024 | TCSD-IP-01-2024 | TCSD-IP-01-L1 | November 21, 2023 | November 28, 2023 | December 11, 2023 | December 13, 2023 | May 27, 2024 | JFM ALTITUDE CONSTRUCTION CORP. | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Tarlac City | 106705 | San Manuel ES | CITY OF TARLAC (Capital) | 2nd |  |  | Construction of 2 - unit Group Hand Washing Facility - 10 faucets - for Elementary | 568209.5 |  | 469888.88 | Completed | 100% | June 26, 2024 | June 26, 2024 | TCSD-IP-01-2024 | TCSD-IP-01-L2 | November 21, 2023 | November 28, 2023 | December 11, 2023 | December 13, 2023 | May 27, 2024 | JFM ALTITUDE CONSTRUCTION CORP. | NONE | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region III | Zambales | 305574 | Bamban National High School | MASINLOC | 2nd | 1 |  | Construction of School Clinic | 3664744.58 |  | 3153468.2 | completed | 100% | September 16, 2024 | September 16, 2024 | Infra-2024-001 | Infra-2024-003 | November 23, 2023 | November 29, 2023 | December 11, 2023 | December 18, 2023 | June 7, 2024 | KAEE Construction Services |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 301418 | Antipolo NHS | CITY OF ANTIPOLO | 1st | 1 |  | Repair of Clinic | 815466.71 |  | 813834.07 | Completed | 100% | March 14, 2025 | Feb. 12, 2025 | N/A | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2nd | 1 |  | Repair of Clinic | 611000 |  | 603643.98 | Completed | 100% | March 14, 2025 | Feb. 12, 2025 | N/A | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Antipolo City | 109361 | Sumilang ES | CITY OF ANTIPOLO | 2nd | 1 |  | Construction of Water System | 2500000 |  | 2498521.95 | Completed | 100% | March 14, 2025 | March 5, 2025 | N/A | BEFF-ANT-2024-02 | July 10, 2024 | July 18, 2024 | July 30, 2024 | August 7, 2024 | Oct. 15, 2025 | HAWKSTOW CONST. AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107248 | Santol ES | Balayan | 1st | 1 |  | Construction of Group Handwashing Facility | 373029.78 |  | 370000 | Completed | 100% | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 001 | WINS 2024 - IVA - BATANGAS PROVINCE - 001 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 90% | 10%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107263 | Bauan East CS | Bauan | 2nd | 1 |  | Construction of Group Handwashing Facility | 373029.78 |  | 370000 | Completed | 100% | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 002 | WINS 2024 - IVA - BATANGAS PROVINCE - 002 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 30% | 70%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107337 | Calumayin School | Cuenca | 3rd | 1 |  | Construction of Group Handwashing Facility | 359254.72 |  | 350000 | Completed | 100% | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 003 | WINS 2024 - IVA - BATANGAS PROVINCE - 003 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 30% | 70%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Batangas | 107530 | Maugat East ES | Padre Garcia | 4th | 1 |  | Construction of Group Handwashing Facility | 366446.94 |  | 350000 | Completed | 100% | May 6, 2025 | April 25, 2025 | WINS 2024 - IVA - BATANGAS PROVINCE - 004 | WINS 2024 - IVA - BATANGAS PROVINCE - 004 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 17, 2024 | January 30, 2025 | Botey Construction | NONE | 0 | 0 | 0 | 0 | 1 | [5 empty] | 30% | 70%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 108016 | Aguinaldo Elementary School | KAWIT | 1st | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | On-going | 80% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Already working on the Finishing Works/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 80% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301174 | Binakayan National High School | KAWIT | 1st | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1199236.08 |  | 1195104.07 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 108019 | Florante Ilano Memorial Elementary School | KAWIT | 1st | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1144861.02 |  | 1140823.76 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107892 | Bancal Elementary School | CARMONA | 5th | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | On-going | 25% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 25% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107893 | Cabilang Baybay Elementary School | CARMONA | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1869086.95 |  | 1862721.32 | Completed | 100% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301177 | Carmona National High School | CARMONA | 5th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1199236.08 |  | 1195104.07 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107857 | Amadeo Elementary School | AMADEO | 7th | 1 |  | Construction of 4-Seater Toilet | 1729344.95 |  | 1722983 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107858 | Dagatan Elementary School | AMADEO | 7th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1821589.36 |  | 1815097.94 | Completed | 100% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301210 | Pangil National High School | AMADEO | 7th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1467459.85 |  | 1462528.61 | Completed | 100% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107839 | Alfonso Central School | ALFONSO | 8th | 1 |  | Construction of 4-Seater Toilet | 1778541.58 |  | 1771974.69 | Completed | 100% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | For completion of necessary documents for the completion of the project on the site/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 301165 | Alfonso Integrated High School | ALFONSO | 8th | 1 |  | Construction of Group Handwashing Facility - For Secondary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 2378202.03 |  | 2369501.2 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite | 107840 | Amuyong Elementary School | ALFONSO | 8th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 1144861.02 |  | 1140823.76 | On-going | 18% | May 14, 2025 |  | N/A | RIVACaviteBACInfra 006-2024 | August 1, 2024 | August 8, 2024 | August 27, 2024 | Jan. 6. 2025 | Jan. 14, 2025 | C.R. Bayot Gen. Construction and Trading | Slow Pace of Work/Clustered as 1 as Health Facilities Project | 0 | 0 | 0 | 1 | 0 | [5 empty] | 18% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Cavite City | 109632 | Ladislao Diwa Elementary School | CAVITE CITY | 1st | 1 |  | 8 units of Group Handwashing Facility Option 1B | 4864447.28 |  | 4134506.33 | Completed | 100% | February 17, 2025 | December 15, 2024 | 2024-06-0004 | 2024-06-0004 | June 4, 2024 | June 13, 2024 | June 26, 2024 | July 4, 2024 | September 20, 2024 | L2A Builders and Trading | * | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 108217 | Dela Paz Main ES | CITY OF BIÑAN | Lone | 1 |  | Construction of Group Handwashing Facilities | 555792.24 |  | 547697.65 | Completed | 100% | September 15, 2024 | September 13, 2024 | 10923021 | 10923021 | N/A - RFQ | N/A - RFQ | N/A - RFQ | June 25, 2024 | July 17, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 108217 | Dela Paz Main ES | CITY OF BIÑAN | Lone |  |  | Repair of Classroom to be Used/Converted to School Clinic | 1071103.22 |  | 930346.44 | Completed | 100% | August 18, 2024 | August 6, 2024 | R4A-BNN-2023-02 | R4A-BNN-2023-02 | December 27, 2023 - January 16, 2024 | January 4, 2024 | January 16, 2024 | February 7, 2024 | May 20, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 8.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 164526 | Southville 5A ES - Langkiwa | CITY OF BIÑAN | Lone | 1 |  | Construction of Water and Sanitation Facilities | 1115051.25 |  | 957782.88 | Completed | 100% | January 15, 2025 | January 17, 2025 | R4A-BNN-2024-05 | R4A-BNN-2024-05 | July 24 - August 13, 2024 | August 1, 2024 | August 13, 2024 | August 27, 2024 | October 17, 2024 | GS Motar Builders Construction & Trading | Waiting for the release of Sub-ARO | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | City of Biñan | 307934 | Southville 5A INHS | CITY OF BIÑAN | Lone | 1 |  | Construction of School Clinic | 3612913.97 |  | 3155056.04 | Completed | 100% | September 17, 2024 | December 11, 2024 | R4A-BNN-2023-03 | R4A-BNN-2023-03 | December 27, 2023 - January 16, 2024 | January 4, 2024 | January 16, 2024 | February 7, 2024 | May 20, 2024 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Gen. Trias City | 107948 | Ipilan Barrio School | CITY OF GENERAL TRIAS | 6th | 1 |  | Conversion of classroom to Health Center | 936863.31 |  | 818653.12 | Completed | 100% | March 27, 2025 | March 27, 2025 | 2024-12-001 | 2024-12-001 | July 8, 2024 | SVP | SVP | July 16, 2024 | December 27, 2024 | JKK Construction Services | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108200 | Bay CS | BAY | 2nd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2024 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108303 | Bambang ES | LOS BAÑOS | 2nd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2025 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3rd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2026 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108253 | Balayhangin ES | CALAUAN | 3rd | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2027 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108272 | Burol ES | CAVINTI | 4th | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2028 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Laguna | 108327 | Longos ES | KALAYAAN | 4th | 1 |  | Construction of Hand Washing Facilities | 208229.39 |  | 208055 | On-going | 15% | 9/16/2025 | - | R4a-2024-016 | R4a-2024-016 | 2024-09-27 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2029 | 2024-11-08 | 5/21/2025 | ELD Enterprises | Released NTP on May 19, 2025 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 15%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108556 | Aluyon Elementary School | BURDEOS | 1st | 1 |  | Construction of School Clinic | 5252051.98 |  | 108556 | Completed | 100% | November 20, 2024 | November 18, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108621 | Mangilag Norte ES | CANDELARIA | 2nd | 1 |  | Construction of School Clinic | 4675089.04 |  | 4200000 | Completed | 100% | September 17, 2024 | July 30, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 21, 2024 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 8.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108944 | AGDANGAN CENTRAL ES | AGDANGAN | 3rd | 1 |  | Construction of School Clinic | 4704018.14 |  | 3737566.6 | Completed | 100% | September 16, 2024 | September 13, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Quezon | 108503 | ALABAT CENTRAL ELEMENTARY SCHOOL | ALABAT | 4th | 1 |  | Construction of School Clinic | 4758321.11 |  | 4747000 | Completed | 100% | September 16, 2024 | September 11, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | Neniko Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 301417 | Angono National High School | ANGONO | 1st | 1 |  | Construction of Group Handwashing Facilities | 322353.43 |  | 293502.72 | On-going | 60% | May 6, 2025 |  | INFRA-2024-001 | INFRA-2024-001 | July 29, 2024 | August 6, 2024 | August 20, 2024 | August 30, 2024 | February 6, 2025 | RALB Construction | Clustered Contract | 0 | 0 | 0 | 1 | 0 | [5 empty] | 40% | 20%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109315 | San Vicente ES | ANGONO | 1st | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 293502.72 | On-going | 65% | May 6, 2025 |  | INFRA-2024-001 | INFRA-2024-001 | July 29, 2024 | August 6, 2024 | August 20, 2024 | August 30, 2024 | February 6, 2025 | RALB Construction | Clustered Contract | 0 | 0 | 0 | 1 | 0 | [5 empty] | 40% | 25%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109486 | Dulongbayan ES | SAN MATEO | 3rd | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 5230782.45 | Completed | 100% | November 20, 2024 | November 18, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 40% | 60%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 165504 | Patiis Elementary School | SAN MATEO | 3rd | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 4200000 | Completed | 100% | September 17, 2024 | July 30, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 21, 2024 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 20% | 80%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 342566 | San Jose Litex SHS | RODRIGUEZ (MONTALBAN) | 4th | 1 |  | Construction of Group Handwashing Facilities | 322353.43 |  | 3737566.6 | Completed | 100% | September 16, 2024 | September 13, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 50% | 50%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Rizal | 109479 | San Rafael ES | RODRIGUEZ (MONTALBAN) | 4th | 1 |  | Construction of Group Handwashing Facilities | 320411.31 |  | 4747000 | Completed | 100% | September 16, 2024 | September 11, 2024 | N/A | 2023-06-INFRAEPA | November 24, 2023 | December 1, 2023 | December 15, 2023 | December 29, 2023 | May 20, 2024 | Neniko Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 10% | 90%
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3rd | 1 |  | Construction of 3 Units Group Handwashing Facility - For Elementary (Option 3A - One-Sided, with Roofing, with Counter, with Tile Finish) | 360000 |  | 339381.46 | Completed | 100% | August 16, 2024 | August 15, 2024 | BEFF-H-001 | BEFF-H-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pablo City | 109755 | San Miguel Elementary School | SAN PABLO CITY | 3rd | 1 |  | Construction of School Clinic | 2500000 |  | 2350669.64 | Completed | 100% | October 30, 2024 | October 30, 2024 | BEFF-SH-001 | BEFF-SH-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | San Pedro City | 108426 | Pacita Complex I ES | SAN PEDRO | 1st | 1 |  | Construction of School Clinic | 4680001.53 |  | 3483584.6 | completed | 100% | October 29, 2024 | November 12, 2024 | 2023-PB-055 | 2023-PB-055 | November 17, 2023 | November 24, 2023 | January 11, 2024 | May 9, 2024 | June 1, 2024 | D&D Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1st | 1 |  | Construction of Water System (Deep Well Design with Solar - Powered Submersible Water Pump) | 2427369 |  | 2240000 | Completed | 100% | July 16, 2024 | July 12, 2024 | ITB-INFRA-2024-002 | ITB-INFRA-2024-002 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1st |  |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 754000 |  | 753000 | Completed | 100% | July 16, 2024 | July 27, 2024 | : ITB-INFRA-2024-001 | : ITB-INFRA-2024-001 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-A | Tayabas City | 109238 | Masin Elementary School | CITY OF TAYABAS | 1st | 1 |  | Construction of Group Hand Washing Facilities | 268500 |  | 267000 | Completed | 100% | June 16, 2024 | June 25, 2024 | : ITB-INFRA-2024-001 | : ITB-INFRA-2024-001 | November 9, 2023 | November 17, 2023 | December 1, 2023 | May 3, 2024 | May 10, 2024 | BOTEY CONSTRUCTION | paid | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IV-B | Romblon | 301769 | Odiongan National High School | ODIONGAN | Lone | 1 |  | Construction of School Clinic | 3104073.56 |  | 339381.46 | Completed | 100% | August 16, 2024 | August 15, 2024 | BEFF-H-001 | BEFF-H-001 | November 30, 2023 | December 11, 2023 | December 27, 2023 | January 12, 2024 | July 2, 2024 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 75% | 25%
SCHOOL HEALTH FACILITIES 2024 | Region IX | Dapitan City | 500675 | Kauswagan Integrated School | DAPITAN CITY | 1st | 1 |  | Construction of School Clinic | 3656520.52 |  | 3601234.72 | Completed | 100% | July 17, 2024 | - | SDODAP-INFRA-2023-005 | SDODAP-INFRA-2023-005 | November 14, 2023 | November 21, 2023 | December 07, 2023 | May 06, 2024 | May 17, 2024 | MORTE CONSTRUCTION | - | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region IX | Isabela City | 126028 | Cabunbata Elementary School | CITY OF ISABELA (Capital) | Lone | 1 |  | Construction of School Clinic | 3196585.16 |  | 3001865.23 | On-going | 99% | November 20, 2024 | - | INFRAEPA2024-03 | INFRAEPA2024-03 | - | November 15, 2023 | December 4, 2023 | May 16, 2024 | August 20, 2024 | AL-QATANI ENTERPRISES | none | 0 | 0 | 0 | 1 | 0 | [5 empty] | 95% | 4%
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303715 | Piñan National High School | PIÑAN (NEW PIÑAN) | 1st | 1 |  | Construction of School Clinic | 4139595.02 |  | 4113576.02 | Completed | 100% | August 15, 2024 | September 27, 0204 | 2024-03-CBZN | CB-2024-015 | December 12, 2023 | December 11, 2023 | December 27, 2023 | January 05, 2024 | May 15, 2024 | YSL Builder | none | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | Sindangan | 2nd | 1 |  | Construction of School Clinic | 4139595.02 |  | 4113576.02 | Completed | 100% | August 15, 2024 | July 18, 2024 | 2024-10-CBZN | CB-2024-016 | November 21, 2023 | November 24, 2023 | December 07, 2024 | December 22, 2023 | May 15, 2024 | YSL Builder | none | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3rd | 1 |  | Construction of School Clinic | 4139595.02 |  | 4077553.98 | Completed | 100% | August 13, 2024 | August 30, 2024 | 2024-11-CBZN | CB-2024-017 | November 21, 2023 | November 24, 2023 | December 07, 2024 | December 27, 2023 | May 15, 2024 | CPAN Engineering & Enterprises | none | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1st | 1 |  | Proposed Construction Of One (1) Storey - Health Facilities | 2812007.03 |  | 2806210.33 | Completed | 100% | August 13, 2024 | August 13, 2024 | ZDS-24-HF-01 | ZDS-24-HF-01 | November 13, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2024 | May 15, 2024 | CPIN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Sur | 303768 | Tabina National High School | TABINA | 2nd | 1 |  | Proposed Construction Of One (1) Storey - Health Facilities | 2859772.23 |  | 2854537.14 | Completed | 100% | August 13, 2024 | August 13, 2024 | ZDS-24-HF-02 | ZDS-24-HF-02 | November 13, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2024 | May 15, 2024 | AYUS BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga Sibugay | 125628 | Pangi Elementary School | Ipil | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish) | 282032.21 |  | 250149.56 | Completed | 100% | August 23, 2024 | November 22, 2024 | ZSY-2024HEALTH-01 | ZSY-2024HEALTH-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 25, 2024 | AAFIAH CONSTRUCTION | Rectification of Punchlisted Items | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region V | Camarines Norte | 112109 | Camacho Aler Elementary School | CAPALONGA | 1st | 1 |  | Construction of Water and Sanitation Facilities - 4-Seater, Rain Water Collector and 10 Faucets Handwashing Facility with Roofing, Counter Tile Finish 2 Units | 1862376 |  | 1844368.38 | COMPLETED | 100% | August 4, 2024 | July 30, 2024 | INFRA07-11-2023CN | INFRA07-11-2023CN | November 7, 2023 | November 15, 2023 | December 5, 2023 | January 16, 2024 | June 5, 2024 | Meltri Construction Services | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region V | Iriga City | 114445 | Iriga South CS | IRIGA CITY | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary 1 Unit (Option 1A - with Roofing, with Counter, with Tile Finish) and 1 Unit (OPTION 3A - One-Sided, without Roofing, with Counter, with Tile Finish) | 586727.75 |  | 586210.48 | COMPLETED | 100% | August 29, 2024 | August 23, 2024 | 2024-01-29-PR-011 | INFRA-24-06-06-001 | February 16, 2024 | February 26, 2024 | March 12, 2024 | March 18, 2024 | June 28, 2024 | Tripartite Eng'g and Construction | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region V | Ligao City | 111844 | Ligao West CES (Binatagan) | CITY OF LIGAO | 3rd | 1 |  | Construction of School Clinic | 2911074.79 |  | 2906241.32 | COMPLETED | 100% | September 15, 2024 |  | 2023-INFRA-01 | 2023-INFRA-01 | November 20, 2024 | December 4, 2024 | December 18, 2023 | May 15, 2024 | June 3, 2024 | La Abel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113770 | Monreal Central School | MONREAL | 1st | 1 |  | Construction of School Clinic | 3192342.78 |  | 3189548.77 | On-going | 80% | May 27, 2025 |  | INFRA 2024-08-001 | 2024-024 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 80%
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113876 | San Fernando CS | SAN FERNANDO | 1st | 1 |  | Construction of School Clinic | 3201465.5 |  | 3198180.97 | On-going | 90% | May 27, 2025 |  | INFRA 2024-08-001 | 2024-025 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0% | 90%
SCHOOL HEALTH FACILITIES 2024 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st | 1 |  | Construction of School Clinic | 3201465.5 |  | 3181448.42 | Completed | 100% | May 27, 2025 |  | INFRA 2024-08-001 | 2024-023 | August 12, 2024 | August 20, 2024 | September 2, 2024 | September 20, 2024 | December 28, 2024 | JOHNCB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | Region V | Sorsogon | 114183 | Vinisitahan ES | DONSOL | 1st | 1 |  | Construction of School Clinic | 2779451.4 |  | 2583307.17 | Completed | 100% | April 24, 2025 | April 24, 2025 | 24-06-002 | 24-06-002 | June 29, 2024 | July 23, 2024 | August 5, 2024 | August 27, 2024 | October 16, 2024 | Golden Tiller Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Aklan | 114625 | Altavas ES | ALTAVAS | 1st | 1 |  | Construction of School Clinic | 3957175.63 |  | 2501064.38 | COMPLETED | 100% | November 8, 2024 | November 7, 2024 | DepED-RO6-D1-2024-BEFF-HEALTHFACILITIES-057-2024 | DepED-RO6-D1-2024-BEFF-HEALTHFACILITIES-057-2024 | November 14, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2023 | 5/17.2024 | NEM CONSTRUCTION SUPPLIES & SERVICES | Completed |  | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region VI | Antique | 115268 | Panpanan I ES | SAN REMIGIO | Lone | 1 |  | Construction of School Clinic | 4520316.75 |  | 3355352.91 | On-going | 34% | November 27, 2024 |  | R6-D2-GAA2024-08-SHF | R6-D2-GAA2024-08-SHF | January 26, 2024 | February 2, 2024 | February 16, 2024 | April 5, 2024 | July 19, 2024 | MDG Const. & Supply | Already issued ressumption Order last Febryary 24, 2025 |  | 0 | 0 | 1 | 0 | [5 empty] | 34% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Bacolod City | 302714 | Mansilingan Agro-Industrial High School | BACOLOD CITY (Capital) | Lone | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2200000 | On-going | 45% | June 11, 2025 |  | HEALTH FACILITIES 2024 - REGION VI - BACOLOD -001 | R6BCD08182024-P129 | August 19, 2024 | August 27, 2024 | September 10, 2024 | October 4, 2024 | February 5, 2025 | KEANNE CONSTRUCTION SERVICES | with request for time extension |  | 0 | 0 | 1 | 0 | [5 empty] | 0% | 45%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Bago City | 117523 | Ma-ao Elementary School | BAGO CITY | 4th | 1 |  | Construction/Repair of Health Facilities | 2510592.22 |  |  | Under Procurement | 0% | [10 empty] | For Posting of Advertisement for interested Bidders |  | 0 | 1 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Capiz | 115413 | Balingasag Elementary School | CUARTERO | 2nd | 1 |  | Construction/Repair of Health Facilities | 5440093.41 |  | 3474057.78 | COMPLETED | 100% | March 8, 2025 | February 25, 2025 | R6-DEPED-CAPIZ-CY2024-BEFF-BALINGASAGES-LOT3 | CB No. 2024-034 | June 28, 2024 | July 10, 2024 | July 22, 2024 | August 15, 2024 | October 3, 2024 | MARIZALOI CONSTRUCTION | Completed |  | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VI | Escalante City | 117055 | Dian-ay Elementary School | CITY OF ESCALANTE | 1st | 1 |  | Construction/Repair of Health Facilities | 4012106.54 |  | 3950000 | completed | 100% | October 25, 2024 | February 3, 2025 | Health Facilities-Region VI- Escalante City-002 | 2024-004 | December 6, 2023 | December 15, 2023 | December 27, 2024 | December 29, 2023 | June 24, 2024 | Valkyrie Construction | Completed |  | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region VI | Iloilo | 311017 | Bancal NHS | ALIMODIAN | 2nd | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2442997.42 | On-going | 76% | July 28, 2025 | n/a | BEEF2024-RVI-022-ILOILO-CLINIC-L1 | BEEF2024-RVI-022-ILOILO-CLINIC-L1 | August 7, 2024 | August 14, 2024 | August 30, 2024 | October 4, 2024 | December 23, 2024 | Marissa's Construction | With time extension |  | 0 | 0 | 1 | 0 | [5 empty] | 40% | 36%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Iloilo City | 302738 | Iloilo City NHS | ILOILO CITY (Capital) | Lone | 1 |  | Construction/Repair of Health Facilities | 2513797.56 |  | 2250687.5 | On-going | 0% | October 29, 2025 | N/A | NONE | 2024-12-001 | October 15, 2024 | October 22, 2024 | November 5, 2024 | December 4, 2024 | March 27, 2025 | URBANCON Builders & Supply | Processing of Permits | URBANCON Builders & Supply | 0 | 0 | 1 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Kabankalan City | 117836 | Carol-an Elementary School | CITY OF KABANKALAN | 6th | 1 |  | Construction/Repair of Health Facilities | 2980787.62 |  | 2978318.85 | Completed | 100% | February 14, 2025 | February 10, 2025 | 2024-SB-01-PB001 | 2024-019 | July 10, 2024 | July 17, 2024 | July 31, 2024 | September 24, 2024 | October 15, 2024 | Rism BUILDERS AND CONSTRUCTION SERVICES, INC. | completed |  | 0 | 0 | 0 | 1 | [5 empty] | 25% | 75%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Negros Occidental | 311104 | Efegenio Lizares National High School | CITY OF TALISAY | 3rd | 1 |  | Construction/Repair of Health Facilities | 3308711.07 |  | 2534432.95 | Completed | 100% | December 13, 2024 | December 19, 2024 | 24-09-001 | 1932-11-23 | November 11, 2023 | November 27, 2023 | December 11, 2023 | July 25, 2024 | August 30, 2024 | Sunshine Sapphire Construction And Supply Inc | Completed |  | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Passi City | 302806 | Efraim M. Santibañez National High School | CITY OF PASSI | 4th | 1 |  | Construction/Repair of Health Facilities | 4426340.48 |  | 3385971.76 | Completed | 100% | December 8, 2024 | December 2, 2024 | BEFF-PSHF | RO6-D14-FY2024-BEFF-CHF-EMSNHS | February 12, 2024 | February 21, 2024 | March 3, 2024 | April 5, 2024 | July 4, 2024 | Early Riser Construction | 100% disbursement |  | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 2389970.5 |  | 2357719.21 | not yet started | 0% |  |  | 2025-005 | CON-2025-005 | March 3, 2025 | March 11, 2025 | March 25, 2025 | March 31, 2025 |  | Reubin L. Yap, Contractor | RTA send to C.O last May 20, 2025 waiting for Sub-ARO |  | 1 | 0 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2nd | 1 |  | Construction/Repair of Health Facilities | 3477585.56 |  | 2493000 | On-going | 80% | June 15, 2025 |  | CPB-INFRA-04-2024 | CPB-INFRA-04-2024 | July 23, 2024 | July 30, 2024 | August 12, 2024 | September 28, 2024 | January 6, 2025 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Ongoing |  | 0 | 0 | 1 | 0 | [5 empty] | 20% | 60%
SCHOOL HEALTH FACILITIES 2024 | Region VI | San Carlos City | 117747 | Greenville Elementary School | SAN CARLOS CITY | 1st | 1 |  | Construction/Repair of Health Facilities | 2732388.66 |  | 2700000 | Completed | 100% | November 8, 2024 | October 21, 2024 | 202310-0093 | 10388986-2023-10-0093 | December 14, 2023 | December 18, 2023 | December 27, 2023 | January 18, 2024 | May 24, 2024 | Valkyrie Construction | COMPLETED |  | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region VI | Silay City | 117814 | Eustaquio Lopez Elementary School | SILAY CITY | 3rd | 1 |  | Construction/Repair of Health Facilities | 2980787.62 |  | 2930085.02 | On-going | 72% | May 6, 2025 |  | 2024-07-ELES-001 | 2024-C-006 | June 29, 2024 | July 7, 2024 | July 22, 2024 | August 6, 2024 | January 6, 2025 | CGGFR Constrcution and Construction Supply |  |  | 0 | 0 | 1 | 0 | [5 empty] | 15% | 57%
SCHOOL HEALTH FACILITIES 2024 | Region VI | Victorias City | 117430 | Doña Andrea Palanca ES | CITY OF VICTORIAS | 3rd | 1 |  | Construction/Repair of Health Facilities | 3225253.91 |  | 1687612.07 | COMPLETED | 100% | September 28, 2024 | August 16, 2024 | School Clinic-01Carcar | BEFF 2024-REpair of Classroom to be used / convered to School Clinic (7.00mx9.00m) at Perrelos Elementary School | March 13, 2024 | March 19, 2024 | April 3, 2024 | April 17, 2024 | June 21, 2024 | A.O.S. Construction Services |  |  | 0 | 0 | 0 | 1 | [5 empty] | 0% | 100%
SCHOOL HEALTH FACILITIES 2024 | Region VII | Carcar City | 119161 | PERRELOS ELEMENTARY SCHOOL | Carcar City | 2nd | 1 |  | Convertion Of Classrooms to School Dental Clinic | 2257172.73 |  | 1687612.07 | COMPLETED | 100% | September 28, 2024 | August 16, 2024 | School Clinic-01Carcar | BEFF 2024-REpair of Classroom to be used / convered to School Clinic (7.00mx9.00m) at Perrelos Elementary School | March 13, 2024 | March 19, 2024 | April 3, 2024 | April 17, 2024 | June 21, 2024 | A.O.S. Construction Services |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119628 | Pitalo ES | SAN FERNANDO | 1st | 1 |  | Construction of School Clinic | 2726233.05 |  | 2701147.62 | completed | 100% | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-01 | CY 2024 BEFF Health-DepED-R7-Cebu-01 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | GELA CONSTRUCTION OPC |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2nd | 1 |  | Construction of School Clinic | 2726233.05 |  | 2700751.08 | completed | 100% | February 5, 2025 | January 9, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-02 | CY 2024 BEFF Health-DepED-R7-Cebu-02 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | BARR STEEL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119092 | Guibuangan Central ES | BARILI | 3rd | 1 |  | Construction of School Clinic | 2726233.05 |  | 2715451.46 | completed | 100% | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-03 | CY 2024 BEFF Health-DepED-R7-Cebu-03 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | RT CONSTRUCTION & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 500694 | Caputatan Norte Integrated School | MEDELLIN | 4th | 1 |  | Construction of School Clinic | 2810788.92 |  | 2790352.41 | completed | 100% | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-04 | CY 2024 BEFF Health-DepED-R7-Cebu-04 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | ANIELTHON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Cebu | 119192 | Francisco S. Villamor Sr.Elementary School | CARMEN | 5th | 1 |  | Construction of School Clinic | 2810788.92 |  | 2780858.27 | completed | 100% | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-05 | CY 2024 BEFF Health-DepED-R7-Cebu-05 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | GOLDEN HAMMER CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | CEBU | 119445 | MALABUYOC CES | MALABUYOC | 7th | 1 |  | Construction of School Clinic | 2726233.05 |  | 2696590.22 | completed | 100% | February 5, 2025 | February 5, 2025 | CY 2024 BEFF Health-DepED-R7-Cebu-06 | CY 2024 BEFF Health-DepED-R7-Cebu-06 | June 11, 2024 | June 18, 2024 | July 1, 2024 | July 22, 2024 | September 30, 2024 | HERO CONSTRUCTION & DEV'T CORP |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Guihulngan City | 120245 | Hilaitan ES | CITY OF GUIHULNGAN | 1st | 1 |  | Clinic & Watsan | 3525668.96 |  |  | not yet started | 0% | [10 empty] | waiting for the lifting of election ban | 0 | 1 | 0 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone | 1 |  | Construction of Hanwashing Facilities | 200898.19 |  | 188138.49 | completed | 100% | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone |  |  | Construction of School Clinic | 3010654.85 |  | 2153178.16 | completed | 100% | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Baybay City | 121135 | Caridad Elementary School | CITY OF BAYBAY | 5th | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish) | 387051.36 |  | 1063343.04 | Completed | 100% | August 2, 2024 | August 2, 2024 | 2023-12-I001 | 2023-12-I001 | December 4, 2023 | December 11, 2023 | December 27, 2023 | May 23, 2024 | May 27, 2024 | MELGAZO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Baybay City | 121135 | Caridad Elementary School | CITY OF BAYBAY | 5th |  |  | Construction of 1 unit Water Sanitation Facilities 4 Seater | 717391.46 |  |  | Completed | 100% | August 2, 2024 | August 2, 2024 | 2023-12-I001 | 2023-12-I001 | December 4, 2023 | December 11, 2023 | December 27, 2023 | May 23, 2024 | May 27, 2024 | MELGAZO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Biliran | 120761 | Iyosan ES | ALMERIA | Lone | 1 |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 674177.51 |  | 670221.45 | Completed | 100% | August 16, 2024 | August 16, 2024 | 2023INFRA-WSF-10 | CONSTRUCTION OF WATER&SANITATION-10 | November 23, 2023 | December 5, 2023 | December 19, 2023 | January 2, 2024 | June 13, 2024 | RK ENGINEERING | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 2945620.86 |  | 2935619.36 | COMPLETED | 100% | October 4, 2024 | September 30, 2024 | CY2024-BEFF-SHF-BOR-01 | CY2024-BEFF-SHF-BOR-01 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | LEXBUILD CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 65% | 35%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Construction of Group Handwashing Facilities | 336908.87 |  | 336639.44 | COMPLETED | 100% | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 0 | [5 empty] | 27% | 73%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Repair of Water and Sanitation Facilities - 4-Seater | 398282.76 |  | 398109.53 | COMPLETED | 100% | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 0 | [5 empty] | 19% | 81%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 122356 | Bato Elementary School | CITY OF BORONGAN (Capital) | Lone |  |  | Construction of Group Handwashing Facilities | 389754.19 |  | 389498.44 | COMPLETED | 100% | October 4, 2024 | September 1, 2024 | CY2024-BEFF-SHF-BOR-02 | CY2024-BEFF-SHF-BOR-02 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | MAX BUILDER CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 0 | [5 empty] | 31% | 69%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303500 | Eastern Samar National Comprehensive High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2980621.64 | COMPLETED | 100% | October 4, 2024 | September 30, 2024 | CY2024-BEFF-SHF-BOR-03 | CY2024-BEFF-SHF-BOR-03 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | TRIPLE Z MC CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 63% | 37%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303511 | Lalawigan National High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2685885.58 | COMPLETED | 100% | October 4, 2024 | July 14, 2024 | CY2024-BEFF-SHF-BOR-04 | CY2024-BEFF-SHF-BOR-04 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | GALACAN CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Borongan City | 303525 | Sta. Fe National High School | CITY OF BORONGAN (Capital) | Lone | 1 |  | Construction of School Clinic | 3001465.5 |  | 2985944.27 | COMPLETED | 100% | October 4, 2024 | October 2, 2024 | CY2024-BEFF-SHF-BOR-05 | CY2024-BEFF-SHF-BOR-05 | October 12, 2023 | October 23, 2023 | November 7, 2023 | November 27, 2023 | May 7, 2024 | YFL BUILDERS | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 33% | 67%
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | Lone | 1 |  | Construction of Group Handwashing Facilities | 236887.87 |  | 231835.72 | Completed | 100% | August 8, 2024 | July 16, 2024 | 122594 | CY2024-BEFF-SHF-L1 | October 13, 2023 | October 24, 2023 | November 8, 2023 | April 30, 2024 | May 3, 2024 | Galacan Construction Services |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | Lone |  |  | Construction of Water and Sanitation Facilities - Four (4) Seater | 588278.06 |  | 586845.33 | Completed | 100% | August 8, 2024 | July 16, 2024 | 122594 | CY2024-BEFF-SHF-L1 | October 13, 2023 | October 24, 2023 | November 8, 2023 | April 30, 2024 | May 3, 2024 | Galacan Construction Services |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st | 1 |  | Construction of Group Handwashing Facility | 335893.89 |  | 324120.6 | COMPLETED | 100% | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st |  |  | Construction of Toilets | 637216.59 |  | 619715.76 | COMPLETED | 100% | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Leyte | 121017 | Rizal ES | BABATNGON | 1st |  |  | Construction of School Clinic | 2828127.22 |  | 2394306.16 | COMPLETED | 100% | October 31, 2024 | October 25, 2024 | 2024-Health Facilities (RVIII)-LEYTE-L1 | 2024-Health Facilities (RVIII)-LEYTE-L1 | November 9, 2023 | November 17, 2023 | December 4, 2023 | May 17, 2024 | May 27, 2024 | JONI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Maasin City | 122176 | Tigbawan IS | CITY OF MAASIN (Capital) | 1st | 1 |  | Construction of 1 units Water Sanitation Facilities - 4-Seater | 717391.46 |  | 717164.64 | Completed | 100% | June 25, 2024 | August 14, 2024 | WATSAN-23-11-001 | WATSAN-23-11-001 | November 29, 2023 | December 12, 2023 | January 5, 2024 | March 12, 2024 | May 17, 2024 | RJM DESIGN & CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Northern Samar | 123180 | Inanahawan ES | PAMBUJAN | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish | 337875.84 |  | 328652.75 | Completed | 100% |  |  | HEALTH2024-RVIII-Northern Samar-L1 | HEALTH2024-RVIII-Northern Samar-L1 |  |  | November 20, 2023 |  |  | Sierra Construction |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Ormoc City | 124213 | Licuma Elementary School | ORMOC CITY | 4th | 1 |  | Construction of Group Handwashing Facility | 359000 |  | 356514.34 | Completed | 100% | July 6, 2024 | July 5, 2024 | WINS 2024 - RVIII - ORMOC CITY - 001 | RO-8-24-2965 | February 16, 2024 | February 23, 2024 | March 8, 2024 | March 11, 2024 | June 3, 2024 | Melgazo Construction and Supply | inaugurated | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires Integrated School | PAGSANGHAN | 1st | 1 |  | Repair of 2-Seater CR | 281354.26 |  | 279808.19 | Completed | 100% | June 26, 2024 | June 24, 2024 | HF2024 | 2024-003 | October 23, 2023 | NOVEMB ER 8, 2023 | December 1, 2023 | May 6, 2024 | May 13, 2024 | G I AND 4K CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 7.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122002 | Divisoria Elementary School | Bontoc | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3054837.71 | Completed | 100% | October 26, 2024 | January 17, 2025 | CY2024-BEFF-Health-L1 | CY2024-BEFF-Health-L1 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122014 | Paku Elementary | Bontoc | 1st | 1 |  | Construction of Group Handwashing Facility | 358954.48 |  | 341503.28 | Completed | 100% | October 18, 2024 | November 15, 2024 | CY2024-BEFF-Health-L4 | CY2024-BEFF-Health-L4 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122014 | Paku Elementary | Bontoc | 1st |  |  | Construction of WATSAN (4-Seater CR) | 693836.25 |  | 665660.59 | Completed | 100% | October 18, 2024 | November 15, 2024 | CY2024-BEFF-Health-L4 | CY2024-BEFF-Health-L4 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122194 | San Joaquin Elementary School | Macrohon | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3037411.47 | Completed | 100% | November 2, 2024 | January 15, 2025 | CY2024-BEFF-Health-L2 | CY2024-BEFF-Health-L2 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | RJM DESIGN & CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Southern Leyte | 122321 | San Isidro Elementary School | Tomas Oppus | 1st | 1 |  | Construction of School Clinic | 3100687.5 |  | 3054837.71 | Completed | 100% | October 26, 2024 | January 17, 2025 | CY2024-BEFF-Health-L3 | CY2024-BEFF-Health-L3 | October 20, 2023 | October 27, 2023 | November 10, 2023 | January 18, 2024 | June 13, 2024 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 4.25
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Tacloban City | 124234 | Camansihay Elementary School | TACLOBAN CITY (Capital) | 1st | 1 |  | Construction of Group Handwashing Facility | 348552.66 |  | 342044.52 | COMPLETED | 100% | August 31, 2024 | October 29, 2024 | CY 2024 BEFF_SCHOOL HEALTH FACILITIES-01 | 01-2024 BEFF SHF-01 | November 7, 2023 | November 14, 2023 | November 27, 2023 | November 30, 2023 | July 25, 2024 | DGJ CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region VIII | Tacloban City | 124234 | Camansihay Elementary School | TACLOBAN CITY (Capital) | 1st |  |  | Construction of One (1) Unit One (1) Storey School Clinic | 2858302.25 |  | 2833811.74 | COMPLETED | 100% | October 29, 2024 | October 29, 2024 | CY 2024 BEFF_SCHOOL HEALTH FACILITIES-01 | 01-2024 BEFF SHF-01 | November 7, 2023 | November 14, 2023 | November 27, 2023 | November 30, 2023 | July 25, 2024 | DGJ CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 0 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Bukidnon | 126263 | Balintad ES | BAUNGON | 1st | 1 |  | Construction/Repair of Health Facilities | 3250000 |  | 2851203.94 | Completed | 100% | October 22, 2024 | October 22, 2024 | PB-02-11-2023-0025 | 011-2024 | November 26, 2023 | December 4, 2023 | December 18, 2023 | December 27, 2023 | May 20, 2024 | TRI FB Construction & General Merchandise | Completed - UPDATED 2-2025 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Cagayan de Oro City | 127986 | Tignapoloan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 3792377.06 |  | 3104683.66 | Completed | 100% | September 10, 2024 | September 10, 2024 | Health-RX-Cagayan de Oro City-003 | 2024-007 | January 1, 2024 | January 15, 2024 | January 29, 2024 | February 12, 2024 | May 10, 2024 | HERA1 Strength Construction | Turned over to Medical Section | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Camiguin | 303994 | Mambajao National High School | SAGAY | Lone | 1 |  | Construction/Repair of Health Facilities | 3995351.01 |  | 3744327.68 | Completed | 100% | August 2, 2024 | September 30, 2024 | Infra-01-02-2024 | Infra-01-02-2024 | November 23, 2023 | December 1, 2023 | December 14, 2023 | January 8, 2024 | May 29, 2024 | Minkonstrak Engineering & General Services | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2nd | 1 |  | Construction/Repair of Health Facilities | 2994361 |  | 2352919.89 | Completed | 100% | October 7, 2024 | October 4, 2024 | 2024-03-0006 | 2024-04-0004 | March 4, 2024 | March 13, 2024 | March 26, 2024 | May 27, 2024 | June 6, 2024 | DICACE Construction & Supplies Trading | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Gingoog City | 315507 | Lunao National High School | GINGOOG CITY | 1st | 1 |  | Construction/Repair of Health Facilities | 2937873.19 |  | 2908494.46 | Completed | 100% | October 11, 2024 | - | HEALTH FACILITIES 2023 - REGION 10 - GINGOOG CITY - 016 | BEFF-2024-LNHS | November 3, 2023 | November 10, 2023 | November 21, 2023 | May 21, 2024 | June 7, 2024 | DCD Builders and Enterprises |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Iligan City | 128079 | Bagong Silang ES | ILIGAN CITY | Lone | 1 |  | Construction of School Clinic | 2933245.82 |  | 2199869.55 | Completed | 100% | October 1, 2024 | September 23, 2024 | INFRA-2023-11-01 | INFRA-2023-11-01 | November 28, 2023 | December 6, 2023 | December 21, 2023 | January 26, 2024 | May 29, 2024 | Abraham BM Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Lanao del Norte | 126937 | Alegria ES | BACOLOD | 1st | 1 |  | Construction/Repair of Health Facilities | 250000 |  | 240050.3 | Completed | 100% | March 5, 2025 | March 4, 2025 | 101-24-10-245 | 101-24-10-245 | NA | NA | NA | September 20, 2024 | NA | RARMAN CONSTRUCTION AND TRADING | ALTERNATIVE MODE OF PROCUREMENT BY SMALL VALUE PROCUREMENT | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Malaybalay City | 126534 | Bagong Silang Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 |  | Construction/Repair of Health Facilities | 3642255.6 |  | 3058004.97 | Completed | 100% | January 19, 2025 | - | 004-INFRA-2023 | 004-INFRA-2023 | November 29, 2023 | December 7, 2023 | December 19, 2023 | January 29, 2024 | September 1, 2024 | Vibranium Builder's Corporation | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 95% | 5%
SCHOOL HEALTH FACILITIES 2024 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1st | 1 |  | Construction of Health Facilities | 2994136.07 |  | 2991345.25 | Completed | 100% | November 12, 2024 | November 12, 2024 | HEALTH FACILITIES 2024 - REGION X - MISAMIS OCCIDENTAL - 001 | 009-2024 | November 29, 2023 | December 7, 2023 | December 19, 2023 | January 16, 2024 | July 15, 2024 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2024 | Region X | Misamis Oriental | 127602 | Balingasag CS | BALINGASAG | 1st | 1 |  | Construction/Repair of Health Facilities | 2784018.17 |  | 2250784.19 | Completed | 100% | November 27, 2024 | February 15, 2025 | PB-BAC1- Construction-2024-002 | N/A | January 17, 2024 | January 24, 2024 | February 5, 2024 | February 21, 2024 | August 29, 2024 | Trench Engineering and Construction Services | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 2933245.82 |  | 2924786.36 | Completed | 100% | 1 ‎February‎ ‎2025 | 1 ‎February‎ ‎2025 | INFRA-2023-DEPED OROQ-05 | n/a | November 23, 2024 | November 30, 2024 | December 14, 2023 | August 14, 2024 |  | RJLG Construction & supply | waiting for the issuance of NTP | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Ozamis City | 304167 | Ozamiz City National High School | OZAMIS CITY | 2nd | 1 |  | Construction of School Clinic and Construction of Toilet (4-Seater) with Handwashing | 3806245.25 |  | 3792882.61 | Completed | 100% | October 25, 2024 | January 30, 2025 | 092-CIVIL 2023-002 (EPA) | 092-CIVIL 2023-002 (EPA) | November 22, 2023 | November 29, 2023 | December 15, 2023 | January 2, 2024 | June 27, 2024 | Mitz and Nick Builders | with approved time extension | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 3.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Tangub City | 501029 | Bintana Integrated School | TANGUB CITY | 2nd | 1 |  | Construction/Repair of Health Facilities | 2969830.3 |  | 2910263.88 | Completed | 100% | November 26, 2024 | November 20, 2025 | Health Facilities 2023-Region X-Tangub 008 | n/a | November 23, 2024 | November 30, 2024 | December 12, 2023 | December 20, 2023 | July 4, 2024 | RIC Construction | with approved time extension | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region X | Valencia City | 126863 | Valencia City Central School | CITY OF VALENCIA | 4th | 1 |  | Construction/Repair of Health Facilities | 6820243.92 |  | 5774303.39 | completed | 100% | September 25, 2024 | - | 45292 | 008 s. 2024 | June 3, 2024 | February 2, 2024 | February 16, 2024 | February 26, 2024 | May 27, 2024 | JDE CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao City | 304359 | Daniel R. Aguinaldo NHS | DAVAO CITY | 1st | 1 |  | Construction of Health Facility with 2 units Comfort Rooms and 2 units Handwashing | 5163932.14 |  | 4464112.6 | Completed | 100% | Sept. 29, 2024 |  | BEFF-L002-2024 | #3s.2024 INF DL-XI | Oct 27-Nov 16, 2023 | Nov.3, 2023 | Nov.16, 2023 | Jan.12, 2024 | May 29, 2024 | Panabo General Contractors Development | work suspended due to change location and Approval of Demolition Permit | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao De Oro | 128302 | Kapatagan ES | LAAK (SAN VICENTE) | 2nd | 1 |  | Construction/Repair of Health Facilities | 5000000 |  | 3545990.37 | COMPLETED | 100% | June 5, 2025 | June 4, 2025 | SDDO-016-2024 | SDDO-016-2024 | Aug. 6, 2024 | Aug. 18, 2024 | September 9, 2024 | September 30, 2024 | January 6, 2025 | JJR ACE CONSTRUCTION AND SUPPLY CORP |  | 0 | 0 | 0 | 0 | 1 | [5 empty] | 70% | 30%
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao del Norte | 128652 | Gov. Dujali ES | SAN ISIDRO | 1st | 1 |  | Construction/Repair of Health Facilities | 3600000 |  | 3324097.66 | On-going | 98% |  |  |  |  | January 10, 2024 | January 17, 2024 | January 30, 2924 | March 19, 2024 | June 28, 2024 | MJTP Construction | On-going | 0 | 0 | 0 | 1 | 0 | [5 empty] | 98% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao del Sur | 304298 | Tacul Agricultural High School | MAGSAYSAY | 1st | 1 |  | Construction/Repair of Health Facilities | 4335202 |  | 3444215.43 | Completed | 100% | February 11, 2025 | February 11, 2025 | DS- SCHBLDG - 2024 - E - LOT 2 | DS- SCHBLDG - 2024 - E - LOT 2 | May 21, 2024 | May 28, 2024 | June 07, 2024 | August 09, 2024 | September 5, 2024 | IRE INDUSTRIAL FACILITIES CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao Occidental | 304292 | John Martin Johnson High School (Lamidan) | DON MARCELINO | Lone | 1 |  | Construction of School Clinic | 3265907.06 |  | 3263892.8 | Completed | 100% | November 14,2024 | November 14,2024 | ITB W-02-2024 | contract no. 2024-007 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | resolution no. 08,s. 2024 | July 17, 2024 | Digos Constrak Corporation | On-going | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 1.25
SCHOOL HEALTH FACILITIES 2024 | Region XI | Davao Oriental | 129356 | Gregorio Moralizon ES 1 | MANAY | 1st | 1 |  | Construction of School Clinic | 5110702.18 |  | 4002640.57 | Completed | 100% | August 20, 2024 | October 16, 2024 | GS 2023 154 | 2024-002 | December 8, 2023 | December 15, 2023 | December 27,2023 | May 2, 2024 | May 22, 2024 | ELLE | Completed w/ Time Extension | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 10.24
SCHOOL HEALTH FACILITIES 2024 | Region XI | Digos City | 304400 | Digos City NHS (Davao Del Sur NHS) | CITY OF DIGOS (Capital) | 1st | 1 |  | Construction of Clinic & Const of 4UNITS 3 Seater CR with Handwashing | 5487480.98 |  | 4236026.94 | Completed | 100% | Nov. 22, 2024 | Nov. 12, 2024 | 2015-02-24 | 2015-02-24 | March 6-26, 2024 | March 12, 2024 | March 26, 2024 | June 06,2024 | July 18, 2024 | RRJJ Quinto Builders Corp. | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 12.24
SCHOOL HEALTH FACILITIES 2024 | Region XI | Island Garden City of Samal | 128598 | Angel Villarica Central Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 |  | Construction/Repair of Health Facilities | 5500000 |  | 4553697.99 | Completed | 100% | September 20, 2024 | September 2, 2024 | infra 001-11-2023 | infra 001-11-2023 | October 31, 2023 | November 8, 2025 | November 20, 2023 | December 12, 2025 | May 23, 2024 | R. Fabale Const. Corp. | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 9.24
SCHOOL HEALTH FACILITIES 2024 | Region XI | Panabo City | 129783 | Gredu ES | CITY OF PANABO | 2nd | 1 |  | Construction/Repair of Health Facilities | 3000000 |  |  | deferred | 0% | [10 empty] | DO would like to revert- with request for additional fund | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region XI | Tagum City | 128768 | APOKON ELEMENTARY SCHOOL | CITY OF TAGUM (Capital) | 1st | 1 |  | Construction/Repair of Health Facilities | 3000000 |  | 2390532.83 | On-going | 95% | March 3, 2025 | June 30, 2025 | NEWCON 2024 - HEALTH FACILITY - RXI - TAGUM CITY – 001 | NEWCON 2024 - HEALTH FACILITY - RXI - TAGUM CITY – 001 | June 28, 2024 | July 8, 2024 | July 22, 2024 | Aug. 12, 2024 | Oct.. 8, 2024 | Al Handasa Const. | Physically Completed | 0 | 0 | 0 | 1 | 0 | [5 empty] | 95% | 0%
SCHOOL HEALTH FACILITIES 2024 | Region XII | General Santos City | 304641 | Fatima National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 |  | 1STY1CL Dental/Medical Clinic | 3538288.18 |  | 2761101.88 | On-going | 70% | 90 CD | On-Going | 011-2024 | 011-2024 | 2024-11-09 | 9/23/2024 | 2024-07-10 | 2024-11-10 | 01/13/2025 | BEBCON BUILDERS AND SUPPLY | On-Going | 0 | 0 | 0 | 1 | 0 | [5 empty] | 45% | 25%
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 |  | Construction of School Clinic | 2900000 |  | 2170506.18 | On-going | 65.87% | June 8, 2025 | N/A | DSC-24-06-111 | 2025-002 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | On-going | 0 | 0 | 0 | 1 | 0 | [5 empty] | 7.55% | 58.32%
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304575 | Tupi National High School | TUPI | 1st | 1 |  | Repair of School Clinic | 750000 |  | 1484161.96 | On-going | 98.78% | June 8, 2025 | N/A | DSC-24-06-111 | 2025-004 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | TUPI NHS AND TBOLI NHS ONE CONTRACT (CLUSTER) | 0 | 0 | 0 | 1 | 0 | [5 empty] | 78.65% | 20.13%
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304555 | Libertad National High School | SURALLAH | 2nd | 1 |  | Construction of School Clinic | 2900000 |  | 2189306.87 | On-going | 87.94% | June 8, 2025 | N/A | DSC-24-06-111 | 2025-003 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | On-going | 0 | 0 | 0 | 1 | 0 | [5 empty] | 26.4% | 61.54%
SCHOOL HEALTH FACILITIES 2024 | Region XII | South Cotabato | 304574 | Tboli National High School | T'BOLI | 2nd | 1 |  | Repair of School Clinic | 750000 |  | clustered to tupi nhs | On-going | 95.15% | June 8, 2025 | N/A | DSC-24-06-111 | 2025-004 | June 25, 2024 | July 3, 2024 | July 23, 2024 | September 6, 2024 | January 16, 2025 | RYCH CONSTRUCTION | TUPI NHS AND TBOLI NHS ONE CONTRACT (CLUSTER) | 0 | 0 | 0 | 1 | 0 | [5 empty] | 61.49% | 33.66%
SCHOOL HEALTH FACILITIES 2024 | Region XII | Sultan Kudarat | 304594 | Kalanawe II National High School | PRESIDENT QUIRINO | 1st | 1 |  | Construction/Repair of Health Facilities | 3374434.48 |  | 2555554.86 | Completed | 100% | 2024-12-07 | 2024-12-03 | 24-01-006 | 24-01-006-01 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-08 | Sept. 02, 2024 | Rivier-Stone Construction Services | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 2.25
SCHOOL HEALTH FACILITIES 2024 | Region XII | Sultan Kudarat | 130914 | Kapaya Elementary School | BAGUMBAYAN | 2nd | 1 |  | Construction/Repair of Health Facilities | 3374434.47 |  | 2332180.48 | Completed | 100% | 2024-12-08 | 2024-11-12 | 24-01-006 | 24-01-006-02 | 2024-04-05 | 2024-04-17 | 2024-04-29 | 2024-05-08 | Sept. 03, 2024 | RYCH Construction | Completed | 0 | 0 | 0 | 0 | 1 | [5 empty] | 100% | 0% |  | 11.24
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 587909.9 | BATCH 1 | 598446.55 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588264.49 | BATCH 1 | 587969.51 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588264.49 | BATCH 1 | 589439.51 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134989 | Bucay Central School | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 219019.24 | BATCH 1 | 589741.66 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 598902.18 | BATCH 1 | 587339.51 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 600675.13 | BATCH 1 | 220931.8 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135208 | Collago ES | LAGAYAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 622624.23 | BATCH 1 | 582396.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135178 | Daguioman CS | DAGUIOMAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221819.91 | BATCH 1 | 561396.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135030 | Danglas CS | DANGLAS | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 594221.59 | BATCH 1 | 218475.37 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135017 | Dolores CS | DOLORES | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 569116.64 | BATCH 1 | 579771.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134994 | Dugong ES | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 580463.51 | BATCH 1 | 573996.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135135 | Garreta ES | PIDIGAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563088.61 | BATCH 1 | 587229.53 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 561670.25 | BATCH 1 | 587229.53 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135064 | Lacub CS | LACUB | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 613085.77 | BATCH 1 | 599829.53 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 565216.15 | BATCH 1 | 630225.46 | Completed | 100% | 2022-10-12 | [8 empty] | BAJE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 565216.15 | BATCH 1 | 622120.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501115 | LICUAN INTEGRATED SCHOOL | LICUAN-BAAY (LICUAN) | 0 | 1 | 1 | CR/Watsan | 587909.9 | BATCH 1 | 559821.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588635.03 | BATCH 1 | 560871.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 564152.38 | BATCH 1 | 593421.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135105 | Luzong ES | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588633.26 | BATCH 1 | 564546.18 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305089 | Luzong NHS | LUBA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 588633.26 | BATCH 1 | 568591.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 134999 | Madalipay ES | BUCAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 574790.07 | BATCH 1 | 222675.37 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 591101.2 | BATCH 1 | 566491.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135071 | Malibcong CS | MALIBCONG | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 630815.26 | BATCH 1 | 564339.33 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 582945.64 | BATCH 1 | 612145.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 561670.25 | BATCH 1 | 562270.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 586491.54 | BATCH 1 | 562008.33 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305093 | Pilar Rural High School | PILAR | 0 |  | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223920.42 | BATCH 1 | 562795.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 590037.43 | BATCH 1 | 558963.33 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135041 | San Gregorio ES | LA PAZ | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 560606.48 | BATCH 1 | 587995.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305097 | San Isidro NHS | SAN ISIDRO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563443.2 | BATCH 1 | 587995.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223220.25 | BATCH 1 | 587995.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | 0 |  | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 566989.1 | BATCH 1 | 608554.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135144 | San Quintin CS | SAN QUINTIN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 563443.2 | BATCH 1 | 608680.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135110 | Supo ES | TUBO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 609539.87 | BATCH 1 | 585895.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305100 | Supo NHS | TUBO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 609539.87 | BATCH 1 | 563635.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 562734.02 | BATCH 1 | 223147.87 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 135024 | Tayum Central School | TAYUM | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 559897.3 | BATCH 1 | 562795.83 | Completed | 100% | 2022-10-12 | [8 empty] | TRAMS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135718 | Albis ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135719 | Ambongdolan ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-06-10 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135720 | Baayan ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135723 | Basil ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135673 | Bayabas MG School | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-05-10 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135677 | Michael G. Angel Elementary School | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-05-10 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135672 | Omas Ampaguey ES | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135731 | Palew ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135734 | Pontino ES | Tublay | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 129846.85 | BATCH 1 | 129475.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 135681 | Sablan CS | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 134297.31 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-05-10 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Benguet | 318915 | Sablan NHS Extension-Balluay | Sablan | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130580.61 | BATCH 1 | 130105.53 | Completed | 100% | 12/29/2022 | 2022-12-12 | HW-2022-01 | HW-2022-01 | April 6, 2022 | April 13, 2022 | April 26, 2022 | June 17, 2022 | August 1, 2022 | PBAJ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135832 | Anao ES | Hingyon | Lone District | 1 | 1 | PROPOSED NEW CONSTRUCTION OF WATER SYSTEM (Water Source at Higher Elevation than School Building) | 591692.97 | BATCH 1 | 589320.92 | Completed | 100% | October 22, 2022 | October 15, 2022 | n/a | 2022-04 | 2022-05-02 | 2022-05-12 | 2022-05-23 | 2022-06-13 | 2022-07-18 | MAGNUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135787 | Antipolo ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF WATER SYSTEM | 438803.69 | BATCH 1 | 438803.69 | Completed | 100% | December 5, 2022 | 2022-12-20 | n/a | 2022-07 | 2022-06-23 | 2022-06-06 | 2022-07-04 | 2024-09-10 | 2022-09-30 | SAKI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of Water System | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135833 | Bangtinon ES | Hingyon | Lone District | 1 | 1 | PROPOSED REPAIR/REHAB OF GROUP HANDWASHING FACILITY | 160638.45 | BATCH 1 | 160638.45 | Completed | 100% | November 20,2022 | March 15, 2023 | n/a | 2022-08 | 2022-06-23 | 2022-06-06 | 2022-07-04 | 2024-09-10 | 2022-09-30 | SAKI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135797 | Maloy PS | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF GROUP HANDWASHING FACILITY, WATER AND SANITATION FACILITIES AND WATER SYSTEM | 489944.01 | BATCH 1 | 489994.01 | Completed | 100% | February 3, 2023 | 2024-04-02 | n/a | 2022-09 | 2022-06-23 | 2022-06-06 | 2022-07-04 | 2024-09-10 | 2022-09-30 | SAKI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135804 | Panubtuban ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR/ REHABILITATION OF GROUP HANDWASHING FACILITY,WATER SYSTEM & TOILET | 336138.97 | BATCH 1 | 335148.19 | Completed | 100% | December 10, 2022 | 2023-02-10 | n/a | 2022-10 | 2022-06-23 | 2022-06-06 | 2022-06-30 | 2022-09-21 | 2022-10-06 | I.N.T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Ifugao | 135805 | Pula ES | Asipulo | Lone District | 1 | 1 | PROPOSED REPAIR AND REHABILITATION OF GROUP HANDWASHING FACILITY, WATER AND SANITATION FACILITIES AND WATER SYSTEM | 505264.65 | BATCH 1 | 504339.7 | Completed | 100% | December 25,2022 | 2023-08-28 | n/a | 2022-11 | 2022-06-23 | 2022-06-06 | 2022-06-30 | 2022-09-21 | 2022-10-06 | I.N.T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 333789.4 | BATCH 1 | 248136.22 | Completed | 100% | May 25, 2023 | November 13, 2023 | WINS 2022-Region CAR-Kalinga-002 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 286547.89 | BATCH 1 | 267150.33 | Completed | 100% | May 25, 2023 | September 20, 2023 | WINS 2022-Region CAR-Kalinga-001 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 294431.39 | BATCH 1 | 273396.27 | Completed | 100% | May 25, 2023 | March 23, 2023 | WINS 2022-Region CAR-Kalinga-006 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136019 | Cagaluan Elementary School | PASIL | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 285351.53 | BATCH 1 | 247212.58 | Completed | 100% | May 25, 2023 | March 23, 2023 | WINS 2022-Region CAR-Kalinga-007 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 297741.25 | BATCH 1 | 273075.17 | Completed | 100% | May 25, 2023 | September 20, 2023 | WINS 2022-Region CAR-Kalinga-004 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 136026 | Magsilay Elementary School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 183287.7 | BATCH 1 | 171865.61 | Completed | 100% | May 25, 2023 | March 30, 2023 | WINS 2022-Region CAR-Kalinga-003 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Kalinga | 305213 | Pasil National High School | PASIL | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 277236.14 | BATCH 1 | 251704.17 | Completed | 100% | May 25, 2023 | March 23, 2023 | WINS 2022-Region CAR-Kalinga-005 | WINS 2022-Region CAR-Kalinga | August 12, 2022 | August 19, 2022 | August 31, 2022 | October 14, 2022 | January 9, 2023 | Bagwis Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136344 | Antadao Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260764.31 | BATCH 1 | 255470.23 | Completed | 100% | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136234 | Banguitan Elementary School | Besao | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 217108.12 | BATCH 1 | 213877.03 | Completed | 100% | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136234 | Banguitan Elementary School | Besao | Lone District |  | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 256130.74 | BATCH 1 | 250701.89 | Completed | 100% | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305238 | Betwagan National High School | Sadanga | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 269803.57 | BATCH 1 | 265983.63 | Completed | 100% | 2022-09-04 | 2022-08-19 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136237 | Bunga Elementary School | Besao | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260688.35 | BATCH 1 | 255170.43 | Completed | 100% | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | Barlig | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 799989.82 | BATCH 1 | 791989.92 | Completed | 100% | 2022-09-17 |  | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136348 | Kilong Primary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 266005.56 | BATCH 1 | 263345.5 | Completed | 100% | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305236 | Lias National High School | Barlig | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260688.35 | BATCH 1 | 258081.47 | Completed | 100% | 2022-09-17 |  | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | POKLE'S CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136244 | Panabungen Elementary School | Besao | Lone District | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - THREE (3) SEATER | 692298.32 | BATCH 1 | 684065.57 | Completed | 100% | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136244 | Panabungen Elementary School | Besao | Lone District |  | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 266765.17 | BATCH 1 | 261711.93 | Completed | 100% | 2022-09-19 |  | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305262 | Pingad National High School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - TWO (2) SEATER | 253868.26 | BATCH 1 | 252531.2 | Completed | 100% | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - SIX (6) SEATER | 602317.33 | BATCH 1 | 600486.55 | Completed | 100% | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 319219 | Saclit National High School | Sadanga | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 250813.52 | BATCH 1 | 248133.63 | Completed | 100% | 2022-09-04 | 2022-08-08 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 305264 | Sadanga National Technical Vocational and Skills Training High School | Sadanga | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FIVE (5) SEATER | 562724.98 | BATCH 1 | 557251.21 | Completed | 100% | 2022-09-04 | 2022-09-02 | INF-2022 HFP-009 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | MR-G CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136330 | Supang Elementary School | Sabangan | Lone District | 1 | 1 | PROPOSED REPAIR OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 746156.8 | BATCH 1 | 743340.06 | Completed | 100% | 2022-09-20 |  | INF-2022 HFP-008 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-07 | CNL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136247 | Suquib Primary School | Besao | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 247431.03 | BATCH 1 | 243945.99 | Completed | 100% | 2022-09-19 | 2022-09-15 | INF-2022 HFP-007 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-06 | LIVINGSTONE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136352 | Taccong Primary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 261599.87 | BATCH 1 | 258983.87 | Completed | 100% | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136353 | Tanulong Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 260992.19 | BATCH 1 | 258382.27 | Completed | 100% | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Mt. Province | 136354 | Tetepan Elementary School | Sagada | Lone District | 1 | 1 | REPAIR OF GROUP HANDWASHING FACILITY | 250814.49 | BATCH 1 | 248306.74 | Completed | 100% | 2022-09-02 | 2022-08-13 | INF-2022 HFP-010 |  | 2022-02-24 | 2022-03-03 | 2022-03-17 | 2022-06-13 | 2022-07-04 | MHIGS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136000 | Appas Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 259832.23 | BATCH 1 | 255711.49 | Completed | 100% | July 29,2022 | July 29,2022 | I-2022-15 | I-2022-15 | April 8, 2022 | April 12, 2022 | April 12, 2022 | April 12, 2022 | July 4, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250747.63 | BATCH 1 | 245256.26 | Completed | 100% | July 29,2022 | July 29,2022 | I-2022-15 | I-2022-15 | April 8, 2022 | April 12, 2022 | April 12, 2022 | April 12, 2022 | July 4, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM | 273631.8 | BATCH 1 | 267655.16 | Completed | 100% | July 29,2022 | July 29,2022 | I-2022-15 | I-2022-15 | April 8, 2022 | April 12, 2022 | April 12, 2022 | April 12, 2022 | July 4, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 131532 | Luis B. Azura Sr. Memorial ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245012.59 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 131536 | Tagbongabong ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245012.59 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Agusan del Norte | 211510 | Poblacion Doz ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY | 154901.65 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132392 | Bagumbayan Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 312598.28 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272539.46 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132400 | New Mabuhay Elementary School | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 311915.78 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272374.54 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-01 | INFRA22-002-01 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 267198.6 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 269238.26 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 268530.05 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304809 | Osmeña-Sto. Niño National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 273301.69 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 272515.24 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 288175.99 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | infra22-002-02 | infra22-002-02 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 324401 | Llamera National High School | LIBJO (ALBOR) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 274036.69 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132554 | Malinao Elementary School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 283907.25 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 132558 | Sta Cruz Elementary School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 284673.26 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Dinagat Island | 304854 | Tubajon National High School | TUBAJON | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 280774.54 | BATCH 1 |  | Completed | 100% | 2022-10-29 | 2022-10-29 | INFRA22-002-03 | INFRA22-002-03 | 2022-03-24 | 2022-04-08 | 2022-04-21 | 2022-04-29 | 2022-07-29 | LVRO CONS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238084.63 | BATCH 1 | 238047.35 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING (MODIFIED) | 86389.18 | BATCH 1 | 86348.69 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239467.07 | BATCH 1 | 239424.42 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 244760.64 | BATCH 1 | 243510.15 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132164 | Bitoon Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245995.82 | BATCH 1 | 244748.31 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132168 | Esperanza Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247049.6 | BATCH 1 | 245797.68 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132170 | Jamoyaon Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243894.53 | BATCH 1 | 242644.95 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241549.63 | BATCH 1 | 240300.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132180 | Tuboran Elementary School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246006.28 | BATCH 1 | 244736.44 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246266.38 | BATCH 1 | 245034.8 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241549.63 | BATCH 1 | 238009.55 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132148 | Consuelo Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 312008.76 | BATCH 1 | 311830.64 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241654.63 | BATCH 1 | 239922.89 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 243919.43 | BATCH 1 | 240191.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241686.13 | BATCH 1 | 238009.55 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132159 | Sta. Fe Elementary School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241595.83 | BATCH 1 | 239922.89 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242910.39 | BATCH 1 | 240191.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243005.93 | BATCH 1 | 240191.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132181 | Caridad Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247081.1 | BATCH 1 | 246984.18 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132183 | Datu Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY (Cement Finished) | 137908.58 | BATCH 1 | 137816.81 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132187 | Maasin Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 248065.5 | BATCH 1 | 247950.81 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 248076 | BATCH 1 | 243937.25 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-042 | BEFF-INFRA2022-042 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132192 | San Roque Elementary School | PILAR | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245960.08 | BATCH 1 | 245919.69 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239134.63 | BATCH 1 | 237885.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-041 | BEFF-INFRA2022-041 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238977.13 | BATCH 1 | 238912.02 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY (Cement Finished) | 137593.51 | BATCH 1 | 137571.74 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237784.34 | BATCH 1 | 237780.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 310007.82 | BATCH 1 | 309898.64 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132202 | Sto. Nino Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238893.13 | BATCH 1 | 238515.09 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-043 | BEFF-INFRA2022-043 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | BAMBOE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132203 | Tambacan Elementary School | SAN ISIDRO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (WINS-HEALTH FCILITY) | 309903.51 | BATCH 1 | 309851.29 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132206 | Alegria Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 232578.56 | BATCH 1 | 232555.7 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132209 | Libertad Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 233461.91 | BATCH 1 | 233404.36 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235186.63 | BATCH 1 | 235161.89 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132212 | Rizal Elementary School | SANTA MONICA (SAPAO) | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 233593.16 | BATCH 1 | 233577.3 | Completed | 100% | January 9, 2023 |  | BEFF-INFRA2022-044 | BEFF-INFRA2022-044 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | November 25, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 230508.18 | BATCH 1 | 205068.48 | Completed | 100% | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132322 | Alipao ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 100% | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132327 | Ombong ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 100% | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 205068.48 | Completed | 100% | August 9, 2022 | September 1, 2022 | 008-BEFF 2022-CARAGA | 008-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132345 | Cambuayon ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132347 | Dugsangon ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304817 | Campo National High School | BACUAG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 244375.04 | BATCH 1 | 201588.81 | Completed | 100% | October 23, 2022 | September 1, 2022 | 009-BEFF 2022-CARAGA | 009-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Radian Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132452 | Bunyasan ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235233.18 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132455 | Cantapoy ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236913.18 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236913.18 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132461 | Masgad ES | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239433.18 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304818 | Cantapoy National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241225.04 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304832 | Bunyasan National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247000.04 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237025.04 | BATCH 1 | 238804.5 | Completed | 100% | December 8, 2022 | September 6, 2022 | 010-BEFF 2022-CARAGA | 015-2022 | April 5, 2022 | April 13, 2022 | April 25, 2022 | May 2, 2022 | June 16, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132337 | Jubgan ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225258.18 | BATCH 1 | 196417.18 | Completed | 100% | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225258.18 | BATCH 1 | 196417.18 | Completed | 100% | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304843 | San Francisco National High School | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 196417.18 | Completed | 100% | September 3, 2022 | April 3, 2023 | 011-BEFF 2022-CARAGA | 010-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132526 | Dakung Patag ES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222108.18 | BATCH 1 | 194914.87 | Completed | 100% | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220533.18 | BATCH 1 | 194914.87 | Completed | 100% | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132535 | Tagbayani ES | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222108.18 | BATCH 1 | 194914.87 | Completed | 100% | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. Memorial National High School | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 194914.87 | Completed | 100% | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 317808 | Dakung Patag National High School | SISON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228625.04 | BATCH 1 | 194914.87 | Completed | 100% | September 28, 2022 | April 3, 2023 | 012-BEFF 2022-CARAGA | 011-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242583.18 | BATCH 1 | 208921.69 | Completed | 100% | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132543 | Laurel ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242583.18 | BATCH 1 | 208921.69 | Completed | 100% | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132544 | Lower Libas ES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 208921.69 | Completed | 100% | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237333.18 | BATCH 1 | 208921.69 | Completed | 100% | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 247525.04 | BATCH 1 | 208921.72 | Completed | 100% | September 28, 2022 | April 3, 2023 | 013-BEFF 2022-CARAGA | 012-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 132567 | Timamana ES | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 214338.18 | BATCH 1 | 189530.34 | Completed | 100% | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218125.04 | BATCH 1 | 189530.34 | Completed | 100% | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218125.04 | BATCH 1 | 189530.34 | Completed | 100% | August 9, 2022 | August 9, 2023 | 014-BEFF 2022-CARAGA | 013-2022 | March 1, 2022 | March 8, 2022 | March 22, 2022 | March 23, 2022 | May 26, 2022 | Bamboe Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132600 | Amag Elementary School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 230840.48 | BATCH 1 | 160261.49 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 001 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY SCHOOLS (WITH ROOFING, AND TILE FINISH COUNTER) | 232780.08 | BATCH 1 | 162256.7 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 002 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (WITH ROOFING, AND TILE FINISH COUNTER) | 239360.09 | BATCH 1 | 163234.65 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 003 | 2022 - 009 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 223599.52 | BATCH 1 | 160833.41 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 004 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 132685 | Gacub Elementary School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, AND TILE FINISH COUNTER) | 251575.68 | BATCH 1 | 160810.28 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 005 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 304875 | Carmen National Agricultural High School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY SCHOOLS (WITH ROOFING, AND TILE FINISH COUNTER) | 225680.8 | BATCH 1 | 162300.75 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 006 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN | 1 | 1 | 1 | ONE (1) - UNIT GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (WITH ROOFING, AND TILE FINISH COUNTER) | 230631.71 | BATCH 1 | 163277.34 | Completed | 100% | November 20, 2022 | December 20, 2022 | WINS 2022 - R XIII - Surigao del Sur - 007 | 2022 - 010 | April 11, 2022 | April 19, 2022 | May 03, 2022 | September 01, 2022 | September 15, 2022 | RJ Construction and Supply | Completed with Liquidated Damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 2 | CONSTRUCTION OF TWO (2) UNITS OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 277014.74 | BATCH 1 | 274077.03 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100108 | Saoit ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100109 | Tanap ES | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100106 | Nagsurot Elementary School | BURGOS | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 128007.37 | BATCH 1 | 127774.04 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Norte | 100050 | Dumalneg ES | DUMALNEG | 1 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 138507.37 | BATCH 1 | 137749.04 | Completed | 100% | 2022-10-01 | 2022-09-30 | N/A | N/A | 2022-03-07 | N/A | 2022-03-14 | 2022-03-15 | 2022-06-03 | ELOCIN CONSTRUCTION | Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100720 | Bungro ES | SAN ILDEFONSO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100721 | Busiing ES | SAN ILDEFONSO | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100615 | Pudoc Elementary School | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100614 | Nagtupacan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100661 | Pangada-Cabaroan Elementary School | SANTA CATALINA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100657 | Bernardo P. Ragasa Elementary School | SANTA CATALINA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 190920.76 | Completed | 100% | 8/16/2022 | 2022-08-11 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-28 | MAPLE LEAF ENGINEERING AND CONSTRUCTION | Lot 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100345 | Tangilig ES | SUGPON | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100588 | Tubalina Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 1 | Construction of 4-seater Toilet | 576616.13 | BATCH 1 | 497261.21 | Completed | 100% | 2/16/2023 | 2/16/2023 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100569 | Dapdappig Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 100% | 2/16/2023 | 2/16/2023 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100367 | Tay-ac Elementary School | LIDLIDDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100553 | Taleb ES | NAGBUKEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 501026 | Bantugo-Mission Integrated School | NAGBUKEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 209887.02 | BATCH 1 | 195852.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 211937.93 | BATCH 1 | 195852.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100554 | Abaccan ES | SIGAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 195852.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 150504 | Matallucod PS | SIGAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 197690.78 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Ilocos Sur | 100337 | DANAC ELEMENTARY SCHOOL | SUGPON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER, WITH TILE FINISH) | 241387.02 | BATCH 1 | 203160.16 | Completed | 100% | 8/18/2022 | 2022-02-09 | Project Reference No. 8656850 | N/A | 2022-11-05 | 5/18/2022 | 5/31/2022 | 2022-10-06 | 2022-07-30 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | Lot 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300105 | Cambaly National High School | BAGULIN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 576355.99 | BATCH 1 | 569904.12 | Completed | 100% | 2022-09-08 | 2022-08-30 | LU - SHF - 2022 -01 | N/A | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100860 | Bagulin CES | BAGULIN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 556856.8 | BATCH 1 | 544372.51 | Completed | 100% | 2022-09-08 | 2022-08-30 | LU - SHF - 2022 -02 | N/A | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | VILLAR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100934 | Burgos CS | BURGOS | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 535452.49 | BATCH 1 | 525027.01 | Completed | 100% | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -03 | N/A | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | VILLAR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100998 | Cuenca ES | PUGO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 529334.23 | BATCH 1 | 520915.2 | Completed | 100% | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -04 | N/A | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300131 | Pugo Central National High School | PUGO | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 530308.03 | BATCH 1 | 523933.32 | Completed | 100% | 2022-09-08 | 2022-09-02 | LU - SHF - 2022 -05 | N/A | 2022-05-02 | 2022-05-10 | 2022-05-17 | 2022-05-24 | 2022-06-10 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 1 | HEALTH FACILITIES | 406308.51 | BATCH 1 | 698595.17 | Completed | 100% | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -06 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 1015926.56 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF FIVE (5) FAUCET HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 148342.88 | BATCH 1 | 145183.24 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 379853.81 | BATCH 1 | 373662.14 | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102837 | Gaggabutan Elementary School | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102838 | Illuru ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102840 | Liuan ES | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102844 | Rizal CS | RIZAL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 |  | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102916 | Cadongdongan ES | SANTA PRAXEDES | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Cagayan | 102921 | Sta. Praxedes CS | SANTA PRAXEDES | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 199297.51 | BATCH 1 |  | COMPLETED | 100% | January 20, 2023 | Februayr 19, 2023 | LMS 2022-RII-CAGAYAN-001 | INFRA 2022 - 067 |  |  |  |  | October 23, 2022 | GCPK CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 556351.41 | BATCH 1 | 549278.05 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103485 | Dadap Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103489 | Harana Elementary School | LUNA | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 155521 | Camarag Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103699 | Capayacan Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 192908.87 | BATCH 1 | 192696.91 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 147432.18 | BATCH 1 | 147240.72 | COMPLETED | 100% |  | 2022-09-29 | Project ID No 2022-03-03 | 2022-06-01 |  |  | March 22, 2022 | April 4, 2022 | June 2, 2022 | EDPIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103980 | Ambaguio CS | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242974.69 | BATCH 1 | 242974.69 | COMPLETED | 100% | Jan. 30, 2023 | Mar. 16, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | Mighty Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103982 | Ammoweg ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155541.67 | BATCH 1 | 155541.67 | COMPLETED | 100% | Jan. 23, 2023 | June 23, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103983 | Balong ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 170112.6 | BATCH 1 | 170112.6 | COMPLETED | 100% | Jan. 23, 2023 | June 28, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103991 | Labang ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 168465.12 | BATCH 1 | 168465.12 | COMPLETED | 100% | Jan. 23, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103992 | Laylaya PS | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 152314.3 | BATCH 1 | 152314.3 | COMPLETED | 100% | Jan. 20, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103995 | Napo ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 131576.8 | BATCH 1 | 131576.8 | COMPLETED | 100% | Jan. 21, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 103996 | Pacdal ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 176412.6 | BATCH 1 | 176412.6 | Completed | 100% | Jan. 21, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 137027 | Pihippi ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 137666.8 | BATCH 1 | 137666.8 | COMPLETED | 100% | Jan. 20, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 137029 | Hiket ES | AMBAGUIO | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 147956.8 | BATCH 1 | 147956.8 | Completed | 100% | Jan. 21, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Nov. 25, 2022 | Nov. 3, 2022 | Dec. 14, 2022 | Dec. 15, 2022 | Dec. 27, 2022 | CAB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104215 | Buenavista ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 172212.6 | BATCH 1 | 170901.32 | COMPLETED | 100% | Jan. 12, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Oct. 27, 2022 | Nov. 3, 2022 | Nov. 15, 2022 | Dec. 1, 2022 | Dec. 16, 2022 | IA Castañeda Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104218 | Gov. Juan Manzano ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 121076.8 | BATCH 1 | 119673.45 | COMPLETED | 100% | Jan. 9, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Oct. 27, 2022 | Nov. 3, 2022 | Nov. 15, 2022 | Dec. 1, 2022 | Dec. 16, 2022 | IA Castañeda Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104219 | Felix-Juana Brawner Community School | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 167749.48 | BATCH 1 | 166236.76 | COMPLETED | 100% | Jan. 12, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Oct. 27, 2022 | Nov. 3, 2022 | Nov. 15, 2022 | Dec. 1, 2022 | Dec. 16, 2022 | IA Castañeda Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104220 | Sawmill ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 186905.91 | BATCH 1 | 185457.59 | COMPLETED | 100% | Jan. 12, 2023 | May 30, 2023 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | PB10-01-CY2022BEFF-HWF-Infra-01-14 | Oct. 27, 2022 | Nov. 3, 2022 | Nov. 15, 2022 | Dec. 1, 2022 | Dec. 16, 2022 | IA Castañeda Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Nueva Vizcaya | 104222 | Villa Par-Pale ES | VILLAVERDE | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 174601.04 | BATCH 1 | - | reverted | 0% | - | - | - | - | - | - | - | - | - | - | Failure of Bidding (No taker) | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 1 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104374 | Gamis ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 100% |  |  |  |  | April 28, 2022 |  | May 5, 2022 | May 20, 2022 | August 24, 2022 | JIJOMER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104381 | Lumagui ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 100% |  |  |  |  | April 28, 2022 |  | May 5, 2022 | May 20, 2022 | August 24, 2022 | JIJOMER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104372 | Cardenas ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 100% |  |  |  |  | April 28, 2022 |  | May 5, 2022 | May 20, 2022 | August 24, 2022 | JIJOMER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104373 | Dibul ES | SAGUDAY | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 1 | 115897.83 | COMPLETED | 100% |  |  |  |  | April 28, 2022 |  | May 5, 2022 | May 20, 2022 | August 24, 2022 | JIJOMER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105566 | Alzate Village ES | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 | 200245.68 | COMPLETED | 100% | 2022-06-24 | 2022-06-17 | DEPED-NE-INFRA-031-2022 | INFRA-NE-SVP-08-2022 | 2022-05-03 | N/A | 2022-05-16 | N/A | 2022-05-25 | JOYUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105568 | Maeling Elementary School | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 | 200245.68 | COMPLETED | 100% | 2022-06-24 | 2022-06-17 | DEPED-NE-INFRA-031-2022 | INFRA-NE-SVP-08-2022 | 2022-05-03 | N/A | 2022-05-16 | N/A | 2022-05-25 | JOYUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105572 | Nampicuan Central School | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 | 200245.68 | COMPLETED | 100% | 2022-06-24 | 2022-06-17 | DEPED-NE-INFRA-031-2022 | INFRA-NE-SVP-08-2022 | 2022-05-03 | N/A | 2022-05-16 | N/A | 2022-05-25 | JOYUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Nueva Ecija | 105573 | Recuerdo ES | NAMPICUAN | 1 | 1 | 1 | PROPOSED REPAIR OF COMFORT ROOM WITH HAND WASHING | 201576.41 | BATCH 1 | 200245.68 | COMPLETED | 100% | 2022-06-24 | 2022-06-17 | DEPED-NE-INFRA-031-2022 | INFRA-NE-SVP-08-2022 | 2022-05-03 | N/A | 2022-05-16 | N/A | 2022-05-25 | JOYUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301073 | Balete National High School | BALETE | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 | Lot 1 - 1,044,849.92 | Completed | 100% | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107250 | Balete Central School | BALETE | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 501264 | Emilia L. Malabanan Integrated School | BALETE | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301158 | Tingloy National High School | TINGLOY | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 | Lot 2 - 1,067,097.15 | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107820 | Tingloy Central School | TINGLOY | 2 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 342199 | Tingloy Senior High School | TINGLOY | 2 | 1 | 2 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 429941.23 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 002 | WINS 2022 - RIVA - BATANGAS - 002 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | RRE ERECTORS AND TRADING SPECIALIST | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107666 | San Nicolas Central School | SAN NICOLAS | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 3 - 1,053,092.20 | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 307713 | San Nicolas Integrated High School | SAN NICOLAS | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 215767.21 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 301149 | Sta. Teresita National High School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Secondary (Option 1B - with Flat Roofing, with Counter with Tile Finish) | 215767.21 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107691 | Mohon Elementary School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 1 - 1,044,849.92 | Completed | 100% | 11/27/2022 | 11/27/2022 | WINS 2022 - RIVA - BATANGAS - 001 | WINS 2022 - RIVA - BATANGAS - 001 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 501541 | Sampa-Pacifico Integrated School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 | Lot 3 - 1,053,092.20 | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Batangas | 107690 | Irukan-Kalayaan Elementary School | SANTA TERESITA | 3 | 1 | 1 | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Flat Roofing, with Counter with Tile Finish) | 216320.41 | BATCH 1 |  | Completed | 100% | 11/27/2022 | 11/25/2022 | WINS 2022 - RIVA - BATANGAS - 003 | WINS 2022 - RIVA - BATANGAS - 003 | 6/20/2022 | 6/29/2022 | 2022-11-07 | 7/18/2022 | 2022-07-10 | MARAKESH ENTERPRISES | NONE | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107930 | Kabulusan Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 100% | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107932 | Kaypaaba Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 100% | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107927 | Castaños Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 100% | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Cavite | 107933 | Lumipa Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (1 UNIT OPTION 3A - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 163253.91 | BATCH 1 |  | Completed | 100% | [10 empty] | Didnt proceed on Procurement because the amount didnt exceed 1m, the project proceeded on Small Value Procurement | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108284 | Famy Elementary School | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301240 | Famy National Integrated High School | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONED SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 164504 | San Miguel ES | FAMY | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108285 | Mabitac ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108289 | Nanguma ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108291 | Paagahan ES | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 135765.31 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301255 | Paagahan Integrated National High School | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 307928 | Matalatala Integrated National High School | MABITAC | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132568.57 | Completed | 100% | 2022-10-18 | 2022-10-17 | R4A-2022-005 | R4A-2022-005 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | N.T. Sotelo Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108390 | Banilan ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108391 | Matikiw ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108392 | Casa Real ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108393 | Casinsin ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108398 | Kabulusan ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108400 | Maulawin ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108401 | Pakil ES | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 134178.71 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 301243 | Kabulusan Integrated National High School | PAKIL | 4 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 135658.97 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Memorial National High School | RIZAL | 3 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY OPTION 3A- ONE-SIDED WITHOUT ROOFING WITH COUNTER TILE FINISH | 133901.99 | BATCH 1 | 132992.21 | Completed | 100% | 2022-10-18 | 2022-10-14 | R4A-2022-006 | R4A-2022-006 | 2022-03-04 | 2022-03-11 | 2022-03-23 | 2022-06-08 | 2022-06-13 | Juncan Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250491.84 | BATCH 1 | 249279 | Completed | 100% | 9/28/2022 | 9/17/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109086 | Sampaloc ES I | SAMPALOC | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-10-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109087 | Sampaloc ES II (G-Hills) | SAMPALOC | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-10-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108944 | Agdangan Central Elementary School | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222213.29 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108945 | Binagbag ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108948 | Dayap ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108949 | E. Licup ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108957 | Salvacion ES | AGDANGAN | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108503 | Alabat Central Elementary School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 500866 | CB Encarnado Integrated School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501220 | RT Camacho Integrated School | ALABAT | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 243663.27 | BATCH 1 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108993 | Mainit Norte ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108995 | PAMBUHAN ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 250470.41 | BATCH 1 | 249821 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108996 | Perez CS | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108997 | Perez West Elementary School | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108998 | Pinagtubigan ES | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 501265 | Severo Tejada Integrated School | PEREZ | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 264120.41 | BATCH 1 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109015 | Concepcion ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109016 | Ilosong ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109017 | Plaridel CS | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 100% | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109018 | Tanauan ES | PLARIDEL | 4 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 223170.41 | BATCH 1 | 222920 | Completed | 100% | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109232 | Busal ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 177290.34 | BATCH 1 | 175668.2 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109234 | Ilasan ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109237 | Lawigue ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109241 | Pandakake ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 172162.36 | BATCH 1 | 170540.21 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109242 | South Palale ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109243 | Tayabas East CS | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109246 | Valencia ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 172162.36 | BATCH 1 | 170540.21 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109247 | Wakas ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109248 | West Palale ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH)Construction of Hand Washing Facilities | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109256 | Lalo ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109257 | Malao-A / Calantas ES | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109260 | Tayabas West CS II | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 161906.39 | BATCH 1 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 342576 | Buenaventura Alandy NHS | CITY OF TAYABAS | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (NEW OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 163526.53 | BATCH 1 | 161886.19 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Tayabas City | 109239 | Mate ES | CITY OF TAYABAS | 1 | 1 | 1 | Construction of 4-Seater Toilet | 586069.72 | BATCH 1 | 580800.58 | Completed | 100% | 2023-03-02 | 2023-05-08 | INFRA-2022-007 | INFRA-2022-007 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110741 | Algeciras ES | AGUTAYA | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF THREE (3) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 665864.2309 | BATCH 1 | 665294.01 | COMPLETED | 100% | April 21, 2024 | July 17, 2024 | 2023 - 07 - 001 - INFRA - LOT 1 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 1 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 18, 2023 | RBM2 CONSTRUCTION | OBLIGATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110964 | Cagayancillo CS | CAGAYANCILLO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 447119.7178 | BATCH 1 | 446622.04 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110970 | Sta Cruz ES | CAGAYANCILLO | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 447119.7178 | BATCH 1 | 674425.31 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301677 | Cagayancillo NHS | CAGAYANCILLO | 1 | 1 | 3 | PROPOSED CONSTRUCTION OF THREE (3) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 675176.8331 | BATCH 1 | 446622.04 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 110949 | Nangalao ES | LINAPACAN | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (UPDATED OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 444710.0724 | BATCH 1 | 444329.24 | COMPLETED | 100% | April 21, 2024 | July 17, 2024 | 2023 - 07 - 001 - INFRA - LOT 1 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 1 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 18, 2023 | RBM2 CONSTRUCTION | OBLIGATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 50% | 50% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 309165 | Nangalao NHS | LINAPACAN | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 449394.4926 | BATCH 1 | 449009.65 | COMPLETED | 100% | April 21, 2024 | July 17, 2024 | 2023 - 07 - 001 - INFRA - LOT 1 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 1 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 18, 2023 | RBM2 CONSTRUCTION | OBLIGATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 50% | 50% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 425039.931 | BATCH 1 | 424675.94 | COMPLETED | 100% | April 21, 2024 | July 17, 2024 | 2023 - 07 - 001 - INFRA - LOT 1 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 1 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 18, 2023 | RBM2 CONSTRUCTION | OBLIGATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301698 | Gaudencio Abordo Mem. National High School - Rizal NHS | MAGSAYSAY | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (UPDATED OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 425039.931 | BATCH 1 | 214903.86 | COMPLETED | 100% | April 21, 2024 | July 17, 2024 | 2023 - 07 - 001 - INFRA - LOT 1 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 1 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 18, 2023 | RBM2 CONSTRUCTION | OBLIGATED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111192 | Macatumbalen Elementary School | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 | 265754.04 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111193 | New Agutaya ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.178 | BATCH 1 | 265754.04 | TERMINATED | 5% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 263482.09 | BATCH 1 | 263188.81 | TERMINATED | 5% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111199 | Panindigan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 263473.62 | BATCH 1 | 263180.35 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111200 | Port Barton ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 | 265754.04 | TERMINATED | 10% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111191 | Kemdeng ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 | 265754.04 | TERMINATED | 5% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111190 | Irawan ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 | 265754.04 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 111204 | TDC ES | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 266050.1778 | BATCH 1 | 265754.04 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301660 | Alimanguan NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 268172.9547 | BATCH 1 | 267874.46 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301738 | San Vicente NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 265604.86 | BATCH 1 | 265309.23 | TERMINATED | 0% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Palawan | 301723 | Port Barton NHS | SAN VICENTE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 265604.86 | BATCH 1 | 265309.23 | TERMINATED | 50% | April 25, 2024 | TERMINATED | 2023 - 07 - 001 - INFRA - LOT 2 | CONTRACT NO. 2023 - 07 - 001 - INFRA - LOT 2 | July 12, 2023 | July 20, 2023 | August 4, 2023 | August 14, 2023 | August 22, 2023 | LCM | TERMINATED | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301777 | Tugdan NHS | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 178748.66 | BATCH 1 | 150785.18 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111262 | Gui-ob Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 | 149380.1 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111265 | San Roque Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 | 149380.11 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111255 | Alcantara CES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 171797.63 | BATCH 1 | 144865.1 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111266 | Tugdan ES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 | 149380.11 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 171004 | Felipe Madali MES | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 | 149380.1 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111261 | Don Manuel L. Solidum Memorial Elementary School | ALCANTARA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 177047.63 | BATCH 1 | 149380.11 | Completed | 100% | April 10, 2023 | April 17, 2023 | BEFF-HWF-2022-08 | BEFF-HWF-2022-08 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 | 185157.74 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-09 | BEFF-HWF-2022-09 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Sim Construction, Trading & Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111269 | Banton CES | BANTON | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 | 182907.52 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-09 | BEFF-HWF-2022-09 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Sim Construction, Trading & Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111393 | Balogo ES | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 | 154168.81 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-09 | BEFF-HWF-2022-09 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111397 | Calatrava Elementary School | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 | 154168.8 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-10 | BEFF-HWF-2022-10 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 309201 | Calatrava National High School | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 183998.66 | BATCH 1 | 155584.02 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-10 | BEFF-HWF-2022-10 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111412 | Josefina Fetalino Malayo ES | CALATRAVA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 | 154168.81 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-10 | BEFF-HWF-2022-10 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111319 | Tacasan ES | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 | 197411.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-11 | BEFF-HWF-2022-11 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 | 199003.14 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-11 | BEFF-HWF-2022-11 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111315 | Mahaba Elementary School | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 | 197411.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-11 | BEFF-HWF-2022-11 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111307 | Alegria ES | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 198047.63 | BATCH 1 | 197411.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-11 | BEFF-HWF-2022-11 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 301757 | Corcuera National High School | CORCUERA | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 199748.66 | BATCH 1 | 199003.14 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-11 | BEFF-HWF-2022-11 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111350 | Bunsoran ES | FERROL | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 158368.81 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-12 | BEFF-HWF-2022-12 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111351 | Claro M. Recto ES | FERROL | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 158368.8 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-12 | BEFF-HWF-2022-12 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111292 | Magdiwang ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 | 181661.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-13 | BEFF-HWF-2022-13 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111286 | Dulangan ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 186911.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-13 | BEFF-HWF-2022-13 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 309207 | Agutay NHS | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 189248.66 | BATCH 1 | 188503.13 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-13 | BEFF-HWF-2022-13 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111289 | Ipil ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 186911.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-13 | BEFF-HWF-2022-13 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111297 | Tampayan ES | MAGDIWANG | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 186911.75 | Completed | 100% | April 10, 2023 | July 2, 2023 | BEFF-HWF-2022-13 | BEFF-HWF-2022-13 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | RMR Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111394 | Bonga ES | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 158368.8 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-14 | BEFF-HWF-2022-14 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111401 | Concepcion Norte ES | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 182297.63 | BATCH 1 | 158368.81 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-14 | BEFF-HWF-2022-14 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-B | Romblon | 111415 | Talamban Elementary School | SANTA MARIA (IMELDA) | 0 | 1 | 1 | CONSTRUCTION OF GHWF | 187547.63 | BATCH 1 | 158368.81 | Completed | 100% | March 10, 2023 | April 17, 2023 | BEFF-HWF-2022-14 | BEFF-HWF-2022-14 | July 28, 2022 | August 10, 2022 | August 23, 2022 | September 8, 2022 | December 20, 2022 | Triple Peak Mountain Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124533 | Alvenda ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124534 | Buena Suerte ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124535 | Delampinas ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124539 | Juan C. Dumaog Sr. ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124544 | Tinglan ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124545 | Totongon ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124546 | Tubak ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 314119 | Mutia NHS Extension - Alvenda | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303714 | Mutia NHS Annex - Tubak | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108064.83 | BATCH 1 | 108064.83 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124738 | Bagacay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124741 | Calube ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124743 | Kanim ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124745 | Magsaysay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124746 | Marapong ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124750 | Sawang ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124753 | Sipaloc ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303694 | Kanim NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303695 | Sawang NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303737 | Sibutad NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 100% | 2022-10-31 | 2022-10-31 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 2022-04-13 | 2022-04-26 | 44656 | 2022-06-30 | YSL Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 501159 | Bogo Calabat IS | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259557.41 | BATCH 1 | 259557.41 | Completed | 100% | 2022-09-02 | 9/17/22 | ZDS-22-HWF-01 | ZDS-22-HWF-01 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Chioco Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125078 | Dawa ES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259399.91 | BATCH 1 | 259399.91 | Completed | 100% | 2022-09-02 | 9/17/22 | ZDS-22-HWF-02 | ZDS-22-HWF-02 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Chioco Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125080 | Josefina CES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 257509.91 | BATCH 1 | 257509.91 | Completed | 100% | 2022-09-02 | 9/17/22 | ZDS-22-HWF-02 | ZDS-22-HWF-02 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Chioco Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125090 | Upper Bag-ong Tudela ES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259452.41 | BATCH 1 | 259452.41 | Completed | 100% | 2022-09-02 | 9/17/22 | ZDS-22-HWF-01 | ZDS-22-HWF-01 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Chioco Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125385 | Lumangoy ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 258874.91 | BATCH 1 | 258874.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-05 | ZDS-22-HWF-05 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Ayus Builders and Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125386 | New Carmen ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 258822.41 | BATCH 1 | 258822.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Long Island Builders & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 196032 | Sominot CES-SPED | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256774.91 | BATCH 1 | 256774.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-03 | ZDS-22-HWF-03 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125395 | Tungawan ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256722.41 | BATCH 1 | 256722.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Long Island Builders & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125396 | Upper Sicpao ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256732.91 | BATCH 1 | 256732.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Long Island Builders & Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125394 | Eastern Sominot ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256738.16 | BATCH 1 | 256738.16 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-05 | ZDS-22-HWF-05 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Ayus Builders and Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125393 | Sominot CES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256774.91 | BATCH 1 | 256774.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-03 | ZDS-22-HWF-03 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125457 | Limas ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258454.91 | BATCH 1 | 258454.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-09 | ZDS-22-HWF-09 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125459 | Maragang ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256144.91 | BATCH 1 | 256144.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-07 | ZDS-22-HWF-07 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125463 | Nilo ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256165.91 | BATCH 1 | 256165.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-07 | ZDS-22-HWF-07 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125464 | Tigbao CES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256176.41 | BATCH 1 | 256176.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-06 | ZDS-22-HWF-06 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125465 | Timolan ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258664.91 | BATCH 1 | 258664.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-09 | ZDS-22-HWF-09 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125467 | Woodland ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258507.41 | BATCH 1 | 258507.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-08 | ZDS-22-HWF-08 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256186.91 | BATCH 1 | 256186.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-08 | ZDS-22-HWF-08 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256197.41 | BATCH 1 | 256197.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-06 | ZDS-22-HWF-06 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | JZ Mago Construction & Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125498 | Kapatagan ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259504.91 | BATCH 1 | 259504.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-10 | ZDS-22-HWF-10 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125499 | Limason ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259410.41 | BATCH 1 | 259410.41 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-11 | ZDS-22-HWF-11 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125500 | Linoguayan ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259399.91 | BATCH 1 | 259399.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-12 | ZDS-22-HWF-12 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | AJT Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125502 | Lunib ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259378.91 | BATCH 1 | 259378.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-12 | ZDS-22-HWF-12 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | AJT Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125507 | Vincenzo Sagun CES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 257509.91 | BATCH 1 | 257509.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-11 | ZDS-22-HWF-11 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303765 | Cogon NHS | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 257404.91 | BATCH 1 | 257404.91 | Completed | 100% | 2022-09-02 | 2022-09-02 | ZDS-22-HWF-10 | ZDS-22-HWF-10 | 2022-03-25 | 2022-04-01 | 2022-04-22 | 2022-06-16 | 6/27/2022 | Cpin Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235553.07 | BATCH 1 | 235553.07 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125843 | Baganipay ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238178.33 | BATCH 1 | 238178.33 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125853 | Samonte ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242903.07 | BATCH 1 | 242903.07 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125848 | Kawilan ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245570.59 | BATCH 1 | 245570.59 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125852 | Sagay ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 249780.83 | BATCH 1 | 249780.83 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125842 | Aurora PS | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 251849.59 | BATCH 1 | 251849.59 | Completed | 100% | 2022-08-28 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 2022-03-19 | 2022-03-28 | 44869 | 2022-04-29 | 2022-06-22 | Sibugay RGT Construction Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Norte | 112274 | San Ramon ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 6 | Construction Of Handwashing Facilities | 793742 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Norte | 112264 | L. Opeda Elementary School | SAN VICENTE | 2 | 1 | 4 | Construction Of Handwashing Facilities | 556309 | BATCH 1 | 554307.85 | Completed | 100% | 2022-02-12 | 2022-01-12 | INFRA02-05-2022CN | INFRA02-05-2022CN | 2022-02-08 | 2022-10-08 | 8/22/2022 | 2022-01-09 | 10/18/2022 | RidersCorner Construction and Gen. Mdse. | CoMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 114701 | Bagongbayan Elementary School | Buruanga | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 627587.16 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 302318 | BURUANGA NATIONAL HIGH SCHOOL | Buruanga | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 630917.76 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 302304 | Catalino M. Prado NHS | Lezo | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 634502.46 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 114934 | Tagas Elem. School | Tangalan | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 605906.24 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Aklan | 501181 | Vivo Integrated School | Tangalan | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 614740.94 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 114973 | Belison CS | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 114976 | Concepcion ES | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302347 | Belison NS | Belison | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115130 | Libertad Central School | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 10, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115133 | Paz ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 148181.01 | BATCH 1 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 11, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115136 | San Roque ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115138 | Tinigbas ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200217.28 | BATCH 1 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 115140 | Union ES | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 198277.26 | BATCH 1 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302363 | Libertad NVS | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Antique | 302383 | Union NHS | Libertad | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 200034.47 | BATCH 1 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115851 | Fiscal Jose M. Zambarrano, Sr. Memorial School | San Lorenzo (Buenavista III) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) with Rain Water Collector | 413873.68 | BATCH 1 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115857 | Silvestra Galarpe Melgar Memorial School | San Lorenzo (Buenavista III) | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) with Rain Water Collector | 413873.68 | BATCH 1 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115849 | Constancia Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2324096.02 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115850 | Doña Lucia C. Locsin Memorial School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2361288.64 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115854 | San Enrique Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2342692.33 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2370586.79 | BATCH 2 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2351990.84 | BATCH 2 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116107 | Cairohan PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225574.55 | BATCH 1 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116109 | Guinhulacan ES | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225034.27 | BATCH 1 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116111 | Maganhop PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226924.27 | BATCH 1 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | Bingawan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226414.55 | BATCH 1 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116594 | Abat Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221494.83 | BATCH 1 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116595 | Agmanaphao Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226278.99 | BATCH 1 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116600 | Dala-Singay Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228573.71 | BATCH 1 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116604 | Tipolo Elementary School | Mina | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228033.43 | BATCH 1 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116092 | Batad CES | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226338.15 | BATCH 1 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116096 | Calangag PS | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221630.39 | BATCH 1 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116101 | Tanao ES | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 224839.55 | BATCH 1 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 501483 | Bulak Integrated School | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 229098.71 | BATCH 1 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 501484 | Embarcadero Integrated School | Batad | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227328.99 | BATCH 1 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116759 | Aripdip Elementary School | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223848.71 | BATCH 1 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116762 | Calaigang ES | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225093.43 | BATCH 1 | 798308.53 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-18 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116768 | San Rafael CS | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 218869.83 | BATCH 1 | 912371.84 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-17 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | San Rafael | 5 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222603.99 | BATCH 1 | 798308.53 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-18 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117929 | Alburquerque Central ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-12 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117930 | Bahi Primary School | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-13 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117933 | Dangay ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-13 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117934 | Tagbuane ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-12 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117935 | Toril ES | Alburquerque | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-18 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117953 | Anda Central ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-22 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117954 | Bacong ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-24 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117955 | Badiang ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-20 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117957 | Candabong ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-24 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117958 | Casica PS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-25 | PBI2022-12 | 44707 | 2022-06-03 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117961 | Londag ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-18 | 2023-02-18 | PBI2022-12 | 44707 | 2022-06-03 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117963 | Porcenas ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-20 | 2023-02-20 | PBI2022-12 | 44707 | 2022-06-03 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117964 | Talisay ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 117966 | Virgen ES | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-25 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 186509 | Suba PS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-21 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302812 | Badiang NHS | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-22 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302829 | Candabong National High School | Anda | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130104.3 | Completed | 100% | 2023-02-25 | 2023-02-27 | N/A | PBI2022-12 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | LTS Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118012 | Batuan Central ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-23 | N/A | PBI2022-13 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118018 | Cantigdas Elementary School | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-23 | N/A | PBI2022-13 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118020 | Janlud ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-24 | N/A | PBI2022-13 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118025 | Rosariohan ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-14 | N/A | PBI2022-13 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118026 | Sta. Cruz ES | Batuan | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-24 | N/A | PBI2022-13 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118184 | Bacani ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-22 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118185 | Bogtongbod ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-22 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118186 | Bonbon Elementary School | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2023-10-04 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118188 | Buacao ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | Oct. 27 2023 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118189 | Buangan ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | Oct. 27 2023 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118190 | Cabog ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-22 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118191 | Caboy ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2023-10-26 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118192 | Cantoyoc PS | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-19 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118193 | Clarin Central ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-19 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118195 | Lajog ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2023-10-27 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118197 | Nahawan ES | Clarin | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 104085.11 | Completed | 100% | 2023-08-30 | 2024-02-19 | N/A | PBI 2023-01 | 2023-02-15 | 2022-06-03 | 2022-06-15 | 2023-04-04 | 2023-06-02 | Sombrio Const |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118201 | Canapnapan PS | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-03 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118202 | Cancatac ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-13 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118203 | Corella Central ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-30 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118204 | Sambog ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-30 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118205 | Tanday ES | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 186510 | Pandol Primary School | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-03 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 500212 | Canangcaan Integrated School | Corella | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-03 | N/A | PBI2022-08 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118206 | Cortes Central ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118207 | Dela Paz ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118208 | Fatima ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118209 | Loreto ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-03 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118210 | Lourdes ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118211 | Malayo ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118216 | San Roque ES | Cortes | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-31 | N/A | PBI2022-09 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118218 | Babag ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-18 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118219 | Cagawasan ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118220 | Caluasan ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118221 | Candelaria ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118222 | Can-oling ES | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118223 | Dagohoy Central Elementary | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118227 | Mahayag Elementary School | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118228 | Malitbog Elementary School | Dagohoy | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-10 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118630 | Abehilan ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118634 | Caimbang ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118635 | Cambansag Elementary | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118636 | Candungao ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118638 | Cansague Sur ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118641 | San Isidro Central ES | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 312327 | Candungao High School | San Isidro | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-23 | N/A | PBI2022-11 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118660 | Bayawahan ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-21 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118663 | Calinginan Norte Elementary School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-06 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118665 | Cambagui ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-06 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118668 | Lagtangan ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-24 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118671 | Magsaysay ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-24 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118672 | Sevilla Central ES | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-06 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302903 | Sevilla National High School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-03 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 302904 | Cambagui-Calinginan Norte National HS | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-03 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 312310 | Bayawahan National High School | Sevilla | 3 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-03-07 | N/A | PBI2022-14 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118699 | Cambuac Sur ES | Sikatuna | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-02-01 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Bohol | 118700 | Sikatuna Central ES | Sikatuna | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 130115.03 | BATCH 1 | 130007.16 | Completed | 100% | 2023-02-25 | 2023-01-30 | N/A | PBI2022-07 | 2022-05-26 | 2022-06-03 | 2022-06-15 | 2022-08-05 | 2022-11-28 | C Jansen Coons and Gen Msdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120431 | Jose R. Remollo ES (Cambaloctot ES) | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 193423.04 | BATCH 1 | 192459.09 | Completed | 100% | November 30, 2022 | 2023-04-07 | ITB 2022-08098 | SHF202210016 | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | August 9, 2022 | October 21, 2022 | Sagittarius Construction | with liquidated damages due to delayed completion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120438 | Siapo Elementary School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 79744.75 | BATCH 1 | 78628.58 | Completed | 100% | November 30, 2022 | 2023-04-07 | ITB 2022-08098 | SHF202210016 | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | August 9, 2022 | October 21, 2022 | Sagittarius Construction | with liquidated damages due to delayed completion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 303278 | Crisostomo O. Retes National High School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF THREE (3) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 218188.87 | BATCH 1 | 217530.71 | Completed | 100% | December 15, 2022 | 2023-04-07 | ITB 2022-08098 | SHF202210016 | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | August 9, 2022 | October 21, 2022 | Sagittarius Construction | with liquidated damages due to delayed completion | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120658 | Enrique Villanueva Central Elementary School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501427 | Larena Integrated School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120669 | Candaping Elementary School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501429 | Maria Integrated School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120699 | Catulayan Elementary School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303305 | Catulayan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501430 | San Juan Integrated School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 100% | October 31, 2022 | March 3, 2023 | 8573800 | 2022-35 | March 29, 2022 | April 5, 2022 | April 18, 2022 | April 21, 2022 | June 28, 2022 | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 438726 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 195826.21 | BATCH 1 | 438726 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120771 | Talahid Elementary school | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 218863 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120760 | Caucab ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 656930 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120772 | Tamarindo ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 2555274.37 | Completed | 100% | April 13, 2023 | June 2, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120766 | Pili ES | ALMERIA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 88547.33 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers | LOT 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 313202 | Biliran Science High School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376016.24 | BATCH 1 | 218209.49 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 218746.36 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120778 | Core Shelter ES | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 218209.49 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120781 | Julita ES | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 218183.64 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120774 | Biliran Central School | BILIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 196788.78 | BATCH 1 | 218863 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 370766.24 | BATCH 1 | 288269.18 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120789 | Capayas Elementary School | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 1324497.29 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 575528.38 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120785 | Balaquid ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 88547.33 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120791 | J.D. Garcia ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 160809.24 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services | LOT 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120793 | Looc ES | CABUCGAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 1322810.74 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services | LOT 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303328 | MANLABANG NHS | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 370766.24 | BATCH 1 | 287135.6 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services | LOT 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120802 | Caibiran Central School SPED Center | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 369993.96 | BATCH 1 | 1322810.74 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services | LOT 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376016.24 | BATCH 1 | 161464.81 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction | LOT 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120804 | Katipunan ES | CAIBIRAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 198888.78 | BATCH 1 | 1322458.55 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction | LOT 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120820 | Culaba CS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 2552153.71 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction | LOT 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303321 | Bool NHS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 376015.24 | BATCH 1 | 278375.67 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 757396.29 | BATCH 1 | 217798.32 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 386516.24 | BATCH 1 | 239230.73 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction | LOT 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303326 | Kawayan National High School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 381266.24 | BATCH 1 | 478096.99 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction | LOT 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120834 | Kawayan CS | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 | 2787822.73 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction | LOT 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 386516.24 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120829 | Bilwang ES | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 194688.78 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-09-01 | M.B Ang Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120839 | Masagongsong ES | KAWAYAN | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 193638.78 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-09-01 | QYT Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120853 | Maripipi Central School | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 282888.78 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-10-11 | VHITS DG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303329 | Maripipi NVS | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 809896.29 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-10-11 | VHITS DG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI | 0 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 460016.24 | BATCH 1 |  | Completed | 100% | [8 empty] | 2022-10-11 | VHITS DG |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122619 | Julag Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122621 | Magsaysay Elementary School | BALANGKAYAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122476 | Binalay Elementary School | GENERAL MACARTHUR | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122486 | Laurel Primary School | GENERAL MACARTHUR | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122513 | Parena Elementary School | GIPORLOS | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122514 | Paya Elementary School | GIPORLOS | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122475 | Batang Elementary School | HERNANI | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122498 | San Isidro Elementary School | HERNANI | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 224619.84 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122581 | Roxas Elementary School | JIPAPAD | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122343 | Beta-og Elementary School | LAWAAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122355 | Taguite Elementary School | LAWAAN | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122355 | Taguite Elementary School | LAWAAN | 0 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122446 | Bulawan Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122449 | Carayacay Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122462 | Maputi Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122463 | Maslog Central Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | MASLOG | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122532 | Anuron Elementary School | MERCEDES | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122535 | Banuyo Elementary School | MERCEDES | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122672 | Anislag Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122681 | Naga Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 192503 | San Isidro Elementary School | QUINAPONDAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-04 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122705 | Asgad Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122707 | Balud Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122711 | Butig Elementary School | SALCEDO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122723 | Caruyagon Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122724 | Casoroy Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122725 | Layog Primary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122729 | Putong Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122730 | San Isidro Elementary School | SAN JULIAN | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | 2022-11-08 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122733 | Alugan Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122740 | Natividad Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122741 | Pangpang Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122743 | Sta.Cruz Elementary School | SAN POLICARPO | 0 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 1 |  | Completed | 100% | 2022-11-12 | ################ | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121870 | Catoogan Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Group Handwashing Facility | 213784.24 | BATCH 1 | 191042.7 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121871 | Gapas Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 141434.75 | BATCH 1 | 99731.29 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121872 | Katipunan Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 510048.99 | BATCH 1 | 454693.74 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121875 | Pitogo Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Group Handwashing Facility | 213784.24 | BATCH 1 | 187720.2 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121882 | Victoria Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 141434.75 | BATCH 1 | 93314.12 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191513 | Baculanad Elementary School | SANTA FE | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 510048.99 | BATCH 1 | 464147.67 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121948 | Cantariwis Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Water System (Rainwater Collector) | 142484.75 | BATCH 1 | 121703.5 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Group Handwashing Facility | 219034.24 | BATCH 1 | 167390.35 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 515298.99 | BATCH 1 | 411575.87 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121517 | Anibong Elementary School | JULITA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 167698.02 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 168641.59 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121562 | Cabadiangan Elementary School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121574 | Luneta Elementary School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 80946.47 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121574 | Luneta Elementary School | LA PAZ | 2 |  | 1 | Constructiom of Water System (Rainwater Collector) | 131036.53 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303428 | Sta. Ana National High School | LA PAZ | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121615 | Batug Elementary School | MACARTHUR | 2 |  | 1 | Constructiom of Water System (Rainwater Collector) | 131036.53 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121622 | Maya Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121625 | Palale Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121626 | San Antonio Elementary School | MACARTHUR | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191556 | Burabod Primary School | MACARTHUR | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 492126.54 | BATCH 1 | 489063.08 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 191556 | Burabod Primary School | MACARTHUR | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1674771.64 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Deepwell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121709 | San Roque Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121713 | Wilson Elementary School | MAYORGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121815 | Dumarag Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194652.31 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BELGES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121815 | Dumarag Elementary School | PASTRANA | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1655149.9 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BELGES CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Deepwell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121821 | Macalpiay Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121823 | Manaybanay Elementary School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 192519.22 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121823 | Manaybanay Elementary School | PASTRANA | 2 |  | 1 | Constructiom of Water System (Deepwell with Solar Powered Submersible Water Pump) | 1687435.99 | BATCH 1 | 1675265.5 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | BENCH CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Deepwell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121825 | Pastrana Central School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 196399.35 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121912 | Guingauan Elementary School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121916 | San Pablo Elementary School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121917 | Tabontabon Central School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 194486.68 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303382 | Justimbaste-Remandaban National High School | TABONTABON | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 196399.35 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | GOOD-WORKS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121961 | Tunga Central School | TUNGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 195996.72 | BATCH 1 | 178255.88 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2 | 1 | 1 | Construction of Group Handwashing Facility | 197894.01 | BATCH 1 | 183049.21 | Completed | 100% |  |  |  |  | 14/04/2022 | 22/04/2022 | 2022-04-05 | 16/05/2022 |  | R. M. PADILLO BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121715 | Cabaliwan Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 224432.2 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121722 | Lamanoc Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 222332.82 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121726 | Macario Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 226470.51 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121727 | Mahalit Elementary School | MERIDA | 4 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 542359.28 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121731 | Minesite Elementary School | MERIDA | 4 | 1 | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 143759.38 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121733 | San Isidro Elementary School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 224815.85 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 303408 | Merida Vocational School | MERIDA | 4 | 1 | 1 | Construction of Group Handwashing Facility | 222239.82 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121409 | Katipunan Elementary School | HINDANG | 5 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 495622.41 | BATCH 1 | 492586.34 | Completed | 100% |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121410 | Ma-asin Elementary School | HINDANG | 5 | 1 | 1 | Construction of Group Handwashing Facility | 212218.74 | BATCH 1 | 201544.5 | Completed | 100% |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121412 | Mahilum Elementary School | HINDANG | 5 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 548624.93 | BATCH 1 | 505476.41 | Completed | 100% |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 313329 | Capudlosan National High School | HINDANG | 5 | 1 | 1 | Construction of Group Handwashing Facility | 209444.01 | BATCH 1 | 203673.63 | Completed | 100% |  |  |  |  | 2022-04-14 | 2022-04-22 | 2022-05-04 | 2022-05-16 |  | JAMR BUILDERS AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122776 | Alejandro Primary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 304683.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122780 | Caputian Primary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 243303.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122780 | Caputian Primary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 294183.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122781 | Frederick Elementary School | Allen | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122781 | Frederick Elementary School | Allen | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 304683.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122790 | Bagong Silang Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246978.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122790 | Bagong Silang Elementary School | Biri | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 309933.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122794 | Langub-Langub Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246978.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122794 | Langub-Langub Elementary School | Biri | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 310458.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122797 | SALVACION Elementary School | Biri | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 566721.62 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122827 | Sagao-Sawan Elementary School | Capul | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 570921.62 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122830 | Talugaan Primary School | Capul | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 314133.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123190 | Buenavista Elementary School | Rosario | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238053.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123190 | Buenavista Elementary School | Rosario | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 301533.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123193 | Kailingan Elementary School | Rosario | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 559371.62 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123202 | Rizal Elementary School | San Antonio | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242253.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123202 | Rizal Elementary School | San Antonio | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 305733.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123205 | Vinisitahan Elementary School | San Antonio | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 241203.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123221 | Bagong Sabang ES | SAN JOSE | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123221 | Bagong Sabang ES | SAN JOSE | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123225 | Gengarog Elementary School | San Jose | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235428.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123225 | Gengarog Elementary School | San Jose | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 298908.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123227 | Mandugang Elementary School | San Jose | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299958.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123249 | Sila Elementary School | San Vicente | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 576171.62 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123271 | Buenasuerte Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239628.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123271 | Buenasuerte Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 303108.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123272 | Buenos Aires Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 230703.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123272 | Buenos Aires Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 294183.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123278 | Lungib Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123278 | Lungib Elementary School | Victoria | 1 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123282 | San Miguel Elementary School | Victoria | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 236530.89 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122993 | Can Maria Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 555171.62 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122995 | Imelda Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 122995 | Imelda Elementary School | Lapinig | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123000 | Palanas Elementary School | Lapinig | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235953.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123000 | Palanas Elementary School | Lapinig | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123109 | Naparasan Elementary School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238578.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 123109 | Naparasan Elementary School | Mapanas | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 302058.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 193015 | Mapanas North Primary School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 239103.39 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 313622 | Magtaon National High School | Mapanas | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 237967.14 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Northern Samar | 313622 | Magtaon National High School | Mapanas | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Hand Water Pump - Manual) | 299433.55 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Hand Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123285 | Almagro CS | ALMAGRO | 1 | 1 | 1 | 1 UNIT GHW OPTION 1A | 240214.31 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123286 | Bacjao ES | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1A | 240214.31 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123289 | Guin-Ansan ES | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1A | 238114.31 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303588 | Almagro National High School | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1B | 252716.16 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303600 | Costa Rica National High School | ALMAGRO | 1 | 1 | 1 | NEW CON OF 1 UNIT GHW OPTION 1B | 247466.16 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501934 | Kerikite Integrated School | ALMAGRO | 1 | 1 | 1 | 1 UNIT GHW OPTION 2A AND 1 RAINWATER COLLECTOR | 308790.09 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123540 | De-It ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 154457.04 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123549 | Matuguinao CES | MATUGUINAO | 1 | 1 | 1 | NEW CON OF 2 UNITS GHW OPTION 1A | 459542.44 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123550 | Nagpapacao ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 152357.04 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123557 | San Isidro ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 153407.04 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193536 | Inubod ES | MATUGUINAO | 1 | 1 | 1 | 1 UNIT RAIN WATER COLLECTOR | 152388.27 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO | 1 | 1 | 1 | NEW CON OF 2 UNITS GHW OPTION 1B | 468796.14 | BATCH 1 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | JD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1 | 1 | 1 | NEW CON OF 4 SEATER CR | 587334.17 | BATCH 1 | 583043.74 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | BMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313713 | Villahermosa Integrated School | PAGSANGHAN | 1 | 1 | 1 | NEW CON OF 4 SEATER CR | 592584.17 | BATCH 1 | 585990.03 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | BMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123806 | Corocawayan ES | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.61 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123807 | Ilijan ES | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 163609.63 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123808 | Lobe-Lobe Elementary School | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.63 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123810 | Pinanangnan Elementary School | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 163831.45 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123812 | Sto. Nino CS | SANTO NIÑO | 1 | 1 | 1 | NEWCON GHW OPTION 2A | 166931.45 | BATCH 1 | 165709.63 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123813 | Takut ES | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 2 SEATER CR TYPE II | 240295.87 | BATCH 1 | 239262.6 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303638 | Villahermosa National High School | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 3 SEATER CR TYPE II | 303771.81 | BATCH 1 | 303114.51 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313703 | Cabunga-an Integrated School | SANTO NIÑO | 1 | 1 | 1 | REPAIR OF 3 SEATER CR TYPE II | 303771.81 | BATCH 1 | 303114.51 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123827 | Tagapul-an CS | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1A | 234176.55 | BATCH 1 | 233202.71 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303590 | Baquiw National High School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1B | 241428.41 | BATCH 1 | 240449.95 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303633 | Tagapul-an National High School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW OPTION 1B | 242216.16 | BATCH 1 | 240449.95 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1 | 1 | 1 | NEWCON GHW 1 UNIT OPTION 1A AND 1B | 451931.83 | BATCH 1 | 450762.66 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123583 | Bugho ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123589 | Cristina Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123590 | Dogongan Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 160631.45 | BATCH 1 | 160530.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123594 | Jidanao Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 161681.45 | BATCH 1 | 161580.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123599 | Mercedes ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 162731.45 | BATCH 1 | 162630.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123600 | Nagbac Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123602 | Salvacion Elementary School | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164729.15 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123603 | San Andres ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 162731.45 | BATCH 1 | 162630.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123606 | Tagbayaon ES | JIABONG | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 164831.45 | BATCH 1 | 164730.88 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123607 | VICTORY ELEMENTARY SCHOOL | JIABONG | 2 | 1 | 1 | NEWCON 4 SEATER CR | 576834.17 | BATCH 1 | 576698.57 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123611 | Kaluwayan Elementary School | MARABUT | 2 | 1 | 1 | REPAIR OF 2 UNITS 2 SEATER CR | 393819.59 | BATCH 1 | 392286.09 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123612 | Legaspi Elementary School | MARABUT | 2 | 1 | 1 | REPAIR OF CR AND HANDWASHING | 330478.67 | BATCH 1 | 327798.7 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123618 | San Roque ES | MARABUT | 2 | 1 | 1 | REPAIR OF CR AND HANDWASHING | 330478.67 | BATCH 1 | 327798.6 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123620 | Tinabanan ES | MARABUT | 2 | 1 | 1 | REPAIR OF 1 UNIT 2 SEATER CR | 235045.87 | BATCH 1 | 234322.76 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123713 | Bontod Elementary School | SAN SEBASTIAN | 2 | 1 | 1 | REPAIR OF 3 SEATER CR | 300621.81 | BATCH 1 | 299565.13 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123714 | Cabaywa ES | SAN SEBASTIAN | 2 | 1 | 1 | NEWCON GHW OPTION 2A | 159581.45 | BATCH 1 | 157633.05 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123719 | Hitaasan ES | SAN SEBASTIAN | 2 | 1 | 1 | REPAIR OF 4 SEATER CR | 351797.86 | BATCH 1 | 349786.19 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2 | 1 | 1 | NEWCON 4 SEATER CR | 582084.17 | BATCH 1 | 579365.72 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | VHITS DG BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123903 | San Juan ES | TALALORA | 2 | 1 | 1 | REPAIR OF 2 SEATER CR | 240295.87 | BATCH 1 | 239907.32 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123905 | Talalora CS | TALALORA | 2 | 1 | 1 | 1 GHW OPTION 1A AND REPAIR OF 2 SEATER CR | 464696.63 | BATCH 1 | 463062.49 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303608 | Independencia National High School | TALALORA | 2 | 1 | 1 | 2 GHW OPTION 1B AND REPAIR OF 3 SEATER CR | 750405.63 | BATCH 1 | 748718.27 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 501372 | Tatabunan Integrated School | TALALORA | 2 | 1 | 1 | NEW CON OF 1 GHW OPTION 1 C | 240830.73 | BATCH 1 | 238542.77 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | MAGA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123763 | Camayse ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 308790.09 | BATCH 1 | 307785.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123964 | Arteche Elementary School | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 309840.09 | BATCH 1 | 308310.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123966 | Boblaran ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 311940.09 | BATCH 1 | 310410.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123973 | MAPUTI ELEMENTARY SCHOOL | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 311940.09 | BATCH 1 | 309360.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123975 | Mombon Elementary School | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 308790.09 | BATCH 1 | 307260.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123983 | Tubigan ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 314040.09 | BATCH 1 | 312510.87 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 259288.78 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 266083.17 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | 2 |  | 3 | Repair of WATSAN | 247145.03 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 260609.97 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303466 | LUNGSODAAN NHS | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303466 | LUNGSODAAN NHS | HINUNDAYAN | 2 | 1 | 1 | Repair of WATSAN | 814934.28 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122079 | Kawayan Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 257126.83 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122080 | Libagon Central School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 255939.4 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122083 | Nahulid Elementary School | LIBAGON | 2 | 1 | 2 | Repair of WATSAN | 215370.53 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122084 | Otikon Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 257522.64 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 265043.05 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 265834.67 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122224 | Padre Burgos Central School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 258821.69 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 260856.16 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303476 | Pintuyan National High School | PINTUYAN | 2 | 1 | 3 | Repair of WATSAN | 241143.04 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 256335.21 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 257126.83 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 2 | 1 | 3 | Repair of WATSAN | 246248.82 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2 |  | 9 | Repair of WATSAN | 714626.33 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | 2 | 1 | 3 | Repair of WATSAN | 259764.65 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L1 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 262668.19 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 271322.98 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L2 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 263808.28 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303453 | Don Agustin F. Escaño NHS | TOMAS OPPUS | 1 |  | 2 | Repair of WATSAN | 207045.4 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 1 | 1 | 3 | Repair of WATSAN | 229168.94 | BATCH 1 |  | Completed | 100% |  |  | CY2022-BEFF-Health-B1-L3 |  | 2022-09-05 | 16/05/2022 | 30/05/2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303990 | CAMIGUIN NATIONAL HIGH SCHOOL | CATARMAN | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 797662.05 | BATCH 1 | 778341.11 | Completed | 100% | August 8, 2022 | October 8, 2022 | WINS 2022 - R X - Camiguin - 001 | PO NO 2022-06-174 | March 2, 2022 | N/A | March 18, 2022 | 2022-05-05 | June 9, 2022 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 315001 | MAAC NATIONAL HIGH SCHOOL | GUINSILIBAN | 2 | 1 | 1 | CONSTRUCTION OF ONE (1) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) INCLUDING MAIN WATER SUPPLY LINE AND DISTRIBUTION LINE IMPROVEMENT | 637839.07 | BATCH 1 | 619065.57 | Completed | 100% | August 8, 2022 | October 8, 2022 | WINS 2022 - R X - Camiguin - 002 | PO NO 2022-06-175 | March 2, 2022 | N/A | March 18, 2022 | 2022-05-05 | June 9, 2022 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303993 | SIXTO A. ABAO NHS | MAHINOG | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 810164.53 | BATCH 1 | 792296.97 | Completed | 100% | August 8, 2022 | October 8, 2022 | WINS 2022 - R X - Camiguin - 003 | PO NO 2022-06-176 | March 2, 2022 | N/A | March 18, 2022 | 2022-05-05 | June 9, 2022 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Camiguin | 303995 | EULALIO U. PABILLORE NHS | SAGAY | 2 | 1 | 4 | CONSTRUCTION OF FOUR (4) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B REVISED - ONE - SIDED, WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 812976.96 | BATCH 1 | 791979 | Completed | 100% | August 8, 2022 | October 8, 2022 | WINS 2022 - R X - Camiguin - 004 | PO NO 2022-06-177 | March 2, 2022 | N/A | March 18, 2022 | 2022-05-05 | June 9, 2022 | MINKONSTRAK ENGINEERING & GEN. SRVC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127667 | Amoros ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127673 | Hinigdaan ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 501927 | Kalabaylabay Integrated School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2D - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127675 | Kibonbon ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127669 | San Francisco de Asis ES (Calongonan ES) | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127679 | Sinaloc Elementary School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127680 | Taytay ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2A - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 111270 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (NEW OPTION 2C - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (NEW OPTION 2D - WITHOUT ROOFING, WITH COUNTER - PAINTED CEMENT FINISH) | 120000 | BATCH 1 | 107178.44 | Completed | 100% | December 24, 2022 | January 9, 2023 | 2022-03-0048 | 2022-08-0187 | March 28, 2022 | April 6, 2022 | April 18, 2022 | August 8, 2022 | August 24, 2022 | HID Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 12 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127042 | Jose Balazo Memorial Elementary School | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 216107.1 | BATCH 1 | 216000 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | March 28, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127043 | Kauswagan CES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213000 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127046 | Libertad ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213750.16 | BATCH 1 | 216214 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127048 | Tacub ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213000 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 315106 | Sultan Dimasangcay Mananggolo IS (Delabayan ES) | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 222078.51 | BATCH 1 | 216214 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 500453 | Kawit Oriental ES | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 217573.85 | BATCH 1 | 216214 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501807 | Baraason Integrated School | KAUSWAGAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 240157.07 | BATCH 1 | 222859.9 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-05(Infra) | 2022-05(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | GREEN Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 190000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127098 | Robocon ES | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220507.16 | BATCH 1 | 180000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 216578.43 | BATCH 1 | 190000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127093 | Bosque Elementary School | LINAMON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 221571.74 | BATCH 1 | 180000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127127 | Batangan ES | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215007.08 | BATCH 1 | 190000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127139 | Pangi Elementary School | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 180000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127144 | Somiorang PS | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 212807.05 | BATCH 1 | 180000 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215810.27 | BATCH 1 | 195407.87 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-06(Infra) | 2022-06(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 10, 2022 | GREEN Builder and Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 211707.04 | BATCH 1 | 211700 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127163 | Kalanganan Elementary School | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 210500 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127163 | Kalanganan Elementary School | PANTAR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 188544.87 | BATCH 1 | 188500 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213500 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213900 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 157528.33 | BATCH 1 | 157500 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 214353.19 | BATCH 1 | 214300 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 223510.37 | BATCH 1 | 223283.16 | completed | 100% | March 22, 2023 | March 21, 2023 | 2022-09(Infra) | 2022-09(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | October 11, 2022 | December 15, 2022 | HAFFY Construction Services | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220732.07 | BATCH 1 | 220700 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 160126.03 | BATCH 1 | 160100 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213900 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127212 | DIMAYON PS | TAGOLOAN | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 161424.88 | BATCH 1 | 161400 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213900 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127215 | Lininding Elementary School | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 213907.07 | BATCH 1 | 213500 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127216 | Payawan ES | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 160126.03 | BATCH 1 | 160100 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 219878.48 | BATCH 1 | 218134.3 | Completed | 100% | November 22, 2022 | November 22, 2022 | 2022-07(Infra) | 2022-07(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127100 | Datu Bebit Dalug ES (Baguiguicon ES) | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 220207.07 | BATCH 1 | 200000 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127103 | Magsaysay CS | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226182.13 | BATCH 1 | 200000 | Completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127104 | Abucay -Cancamo ES (Olango ES) | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227282.14 | BATCH 1 | 200000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 226703.48 | BATCH 1 | 200000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127177 | Camp 3 ES | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 257854.69 | BATCH 1 | 250000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-012(Infra) | 2022-012(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127177 | Camp 3 ES | SALVADOR | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 174718.76 | BATCH 1 | 170000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-012(Infra) | 2022-012(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127180 | Daligdigan PS | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 246620.02 | BATCH 1 | 240000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-012(Infra) | 2022-012(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127187 | Salvador CES | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 259855.64 | BATCH 1 | 259800 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-012(Infra) | 2022-012(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 258755.62 | BATCH 1 | 258700 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-012(Infra) | 2022-012(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501392 | Madaya Integrated School | SALVADOR | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 254502.34 | BATCH 1 | 200000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 255440.39 | BATCH 1 | 200000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 174718.76 | BATCH 1 | 150000 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501667 | Sapad Integrated School | SAPAD | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 257807.45 | BATCH 1 | 237346.32 | completed | 100% | January 17, 2023 | January 17, 2023 | 2022-011(Infra) | 2022-011(Infra) | April 12, 2022 | April 20, 2022 | July 19, 2022 | August 15, 2022 | October 11, 2022 | RAMZIE Builders & Enterprises | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 225885.3 | BATCH 1 | 225800 | completed | 100% | November 22, 2022 | November 22, 2022 | 2022-08(Infra) | 2022-08(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 228178.45 | BATCH 1 | 228000 | completed | 100% | November 22, 2022 | November 22, 2022 | 2022-08(Infra) | 2022-08(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127051 | Banisilon Central Elementary School | TANGCAL | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227930.34 | BATCH 1 | 227900 | completed | 100% | November 22, 2022 | November 22, 2022 | 2022-08(Infra) | 2022-08(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Lanao del Norte | 127051 | Banisilon Central Elementary School | TANGCAL | 2 |  | 1 | CONSTRUCTION OF WATER SYSTEM (Rainwater Collector) | 204294.87 | BATCH 1 | 204200 | completed | 100% | November 22, 2022 | November 22, 2022 | 2022-08(Infra) | 2022-08(Infra) | April 12, 2022 | April 20, 2022 | May 11, 2022 | June 9, 2022 | August 8, 2022 | MOH'D Construction | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127364 | Malvar ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 001 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501858 | New Casul Integrated School | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 002 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127372 | Upper Dioyo ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 003 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127373 | Upper Salimpono PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 004 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127363 | Guiban ES | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 005 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127369 | Pogan PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 006 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 201020 | Virayan PS | CONCEPCION | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 149300.24 | Completed | 100% | April 20, 2023 | June 21, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 007 | 019-2022 | September 4, 2022 | September 12, 2022 | September 26, 2022 | October 6, 2022 | December 14, 2022 | Kayro Construction and Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127285 | Sinian ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 148775.24 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 008 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127272 | Agapito Yap MES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 009 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127275 | Landing ES | BALIANGAO | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 010 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127282 | Punta Miray ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 011 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127283 | Punta Sulong ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 012 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127284 | Quezon ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 013 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127276 | Lipacon ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 014 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127280 | Magcamiguing ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 015 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 016 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127279 | Lusot ES | BALIANGAO | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150351.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 017 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127274 | Del Pilar ES | BALIANGAO | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150351.24 | BATCH 1 | 150349.99 | Completed | 100% | February 4, 2023 | February 10, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 018 | 014-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | September 30, 2022 | RRJ Builders and Gen. Msde. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127486 | San Juan ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 019 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127476 | Baga PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 020 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127487 | San Roque ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 021 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127480 | F.T. Paylaga MPS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 022 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127482 | Mohon ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 023 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127477 | Bangko ES | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 024 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127478 | Camanucan PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 025 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127484 | Punta PS | PANAON | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 150028.02 | Completed | 100% | February 11, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 026 | 015-2022 | June 28, 2022 | July 6, 2022 | July 18, 2022 | August 15, 2022 | October 3, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 188627.51 | BATCH 1 | 168819.73 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 027 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 | 574506.81 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 028 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127527 | Masubong PS | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 029 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127517 | Dasa ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 030 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501884 | Bitibut Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 | 574506.81 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 031 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127530 | Proceso Saldivar ES (Sepac ES) | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 032 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127532 | Salvador ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 033 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127534 | Sinaad ES | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 034 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127529 | Napilan ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 035 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 2 | 1 | 4 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 036 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127537 | Ventura ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 037 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127513 | Caluya ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 038 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127519 | Disoy ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 039 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127522 | Libertad ES | SAPANG DALAGA | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 134370.21 | Completed | 100% | February 18, 2023 | April 17, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 040 | 016-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 14, 2022 | Kayro Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF WATER AND SANITATION FACILITIES - FOUR (4) SEATER | 639390.9 | BATCH 1 | 624168.66 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 041 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 042 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127550 | San Isidro Bajo PS | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 043 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127540 | Caraghanan PS | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 044 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 045 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127542 | Colupan Bajo ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 046 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127543 | Dinas ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 047 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127544 | Estrella ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 048 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127549 | San Isidro Alto ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 049 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127551 | San Lorenzo Ruiz ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 050 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 201004 | San Vicente ES Annex | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 051 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127556 | Tipan ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 052 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Occidental | 127552 | San Vicente ES | SINACABAN | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 150350.24 | BATCH 1 | 147027.46 | Completed | 100% | February 23, 2023 | February 23, 2023 | WINS 2020 - R-X - MISAMIS OCCIDENTAL - 053 | 017-2022 | May 26, 2022 | June 3, 2022 | June 15, 2022 | July 14, 2022 | October 7, 2022 | 3R'S BUILDERS & RESOURCES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 203841.38 | BATCH 1 | 189212.41 | Completed | 100% | December 9, 2022 | January 13, 2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 205130.15 | BATCH 1 | 189212.41 | Completed | 100% | December 9, 2022 | January 18, 2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 215171.14 | BATCH 1 | 189212.41 | Completed | 100% | December 9, 2022 | January 23, 2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 203841.38 | BATCH 1 | 189212.41 | Completed | 100% | December 9, 2022 | January 23, 2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127762 | Matangad ES | GITAGUM | 2 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 2271334.41 | BATCH 1 | 1863173.82 | Completed | 100% | December 9, 2022 | January 23, 2023 | N/A | 3874972 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 28, 2022 | KL BUILDER SERVICES AND SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127763 | Pangayawan ES | GITAGUM | 2 | 1 | 8 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) 8 FAUCETS | 114530.72 | BATCH 1 | 100334.78 | Completed | 100% | December 9, 2022 | April 20.2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 304086 | Matangad NHS | GITAGUM | 2 | 1 | 16 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 1B - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 204386.38 | BATCH 1 | 179281.41 | Completed | 100% | December 9, 2022 | April 20.2023 | N/A | 3871971 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 12, 2022 | TRI FB CONST. AND GEN. MRDSE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 2 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 2265034.41 | BATCH 1 | 1802984.15 | Completed | 100% | December 9, 2022 | April 20.2023 | N/A | 3871973 | August 9, 2022 | August 16, 2022 | August 30, 2022 | September 19, 2022 | December 14, 2022 | DICACE CONST. AND SUPPLIES TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 500859 | Igangon Integrated School | SAN ISIDRO | 2 | 1 | 12 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR INTEGRATED SCHOOL (OPTION 1C - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 2 SETS OF 12 FAUCETS | 497885.97 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 315906 | Pinamuno National High School | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 254314.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 262714.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128656 | Libuton ES | SAN ISIDRO | 2 | 1 | 7 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - 1 SET OF 7 FAUCETS | 262714.72 | BATCH 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3259817.87 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3213617.87 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 128657 | Linao ES | SAN ISIDRO | 1 | 1 | 1 | REPAIR/CONVERSION OF 1 CL TO SCHOOL CLINIC | 1010630.12 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Clinic | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region XI | Davao del Norte | 500859 | Igangon Integrated School | SAN ISIDRO | 1 | 1 | 1 | CONSTRUCTION OF SCHOOL CLINIC | 3226217.87 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129374 | Badas ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129380 | Rabat-Rocamora Mati CES I | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129382 | Mayor Luisito G. Rabat MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129383 | Mayor Santiago Garcia MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 205504 | Rabat Rocamora Mati Central School SPED Center | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 500454 | Licop Integrated School | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129388 | Antonino Vicentino ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129390 | Bobon ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 218862.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129392 | Cabubuanan Elementary School | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129395 | Don Luis Rabat Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129396 | Don Salvador Lopez ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 219912.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129418 | Magum ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220437.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Abra | 305085 | Dugong National High School | BUCAY | 2 | 1 | 1 | Watsan | 580463.51 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF WATER SANITATION FACILITY | 393756.88 | BATCH 2 | 392951.29 | Completed | 100% | February 2, 2023 | March 17, 2023 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135245 | Pedro Bunot CS | CALANASAN (BAYAG) | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 896699.53 | BATCH 2 | 895527.99 | Completed | 100% | December 30, 2022 | February 10, 2023 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135249 | Sta. Filomena ES | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 260159.49 | BATCH 2 | 259798.01 | Completed | 100% | December 30, 2022 | November 25, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135250 | Tanglagan ES | CALANASAN (BAYAG) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 260159.49 | BATCH 2 | 259798.01 | Completed | 100% | December 30, 2022 | November 25, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135250 | Tanglagan ES | CALANASAN (BAYAG) | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 896227.03 | BATCH 2 | 894385.83 | Completed | 100% | December 30, 2022 | February 10, 2023 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135259 | Conner Central School | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 588941.25 | BATCH 2 | 587694.14 | Completed | 100% | January 29, 2023 | October 21, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135277 | Ripang ES | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 609128.16 | Completed | 100% | January 29, 2023 | October 21, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135277 | Ripang ES | CONNER | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787785.76 | BATCH 2 | 785937.1 | Completed | 100% | December 30, 2022 | November 25, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 588941.25 | BATCH 2 | 587694.14 | Completed | 100% | January 29, 2023 | October 21, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305112 | Conner National HS | CONNER | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 586333.57 | BATCH 2 | 584495.26 | Completed | 100% | January 29, 2023 | October 21, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135284 | San Jose ES | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 609297.46 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135284 | San Jose ES | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787169.62 | BATCH 2 | 785975.91 | Completed | 100% | January 29, 2023 | December 6, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135289 | Flora CS | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610375.18 | BATCH 2 | 608679.7 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135289 | Flora CS | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787393.27 | BATCH 2 | 785716.79 | Completed | 100% | January 29, 2023 | December 10, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135290 | Flora East CS | FLORA | 2 | 1 | 1 | PROPOSED REPAIR OF WATER SYSTEM | 382406.38 | BATCH 2 | 381960.9 | Completed | 100% | Februay 2, 2023 | December 19, 2022 | NONE | NONE | June 28, 2022 | July 5, 2022 | July 19, 2022 | July 28, 2022 | September 27, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Water System | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135290 | Flora East CS | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 786394.72 | BATCH 2 | 784641.85 | Completed | 100% | January 29, 2023 | December 7, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610375.18 | BATCH 2 | 608928.86 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 786394.72 | BATCH 2 | 784477.37 | Completed | 100% | January 29, 2023 | December 9, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 616779.37 | BATCH 2 | 615039.98 | Completed | 100% | January 29, 2023 | November 25, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135336 | Luna CS | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 610968.43 | BATCH 2 | 609481.28 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135336 | Luna CS | LUNA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 787393.27 | BATCH 2 | 785646.41 | Completed | 100% | January 29, 2023 | December 8, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135346 | Shalom PS | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 605228.76 | BATCH 2 | 603625.28 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135347 | Sta. Lina ES | LUNA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 605228.76 | BATCH 2 | 603625.28 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135353 | Dona Loreta ES | PUDTOL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 262784.49 | BATCH 2 | 261439.08 | Completed | 100% | December 30, 2022 | December 19, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135355 | Malibang ES | PUDTOL | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 584213.62 | BATCH 2 | 582748.73 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135369 | San Mariano ES | SANTA MARCELA | 2 | 1 | 2 | PROPOSED REPAIR OF EXISTING HAND WASHING FACILITY | 580457.02 | BATCH 2 | 578773.34 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Group Hand Washing | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135371 | Sta. Marcela CS | SANTA MARCELA | 2 | 1 | 1 | PROPOSED REPAIR OF WATER SYSTEM | 393756.88 | BATCH 2 | 392557.16 | Completed | 100% | Februay 2, 2023 | December 19, 2022 | NONE | NONE | June 28, 2022 | July 5, 2022 | July 19, 2022 | July 28, 2022 | September 27, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of Water System | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 135371 | Sta. Marcela CS | SANTA MARCELA | 2 |  | 3 | PROPOSED REPAIR OF COMFORT ROOMS | 785778.58 | BATCH 2 | 783880.82 | Completed | 100% | January 29, 2023 | December 5, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | CAR | Apayao | 318805 | CONSUELO NATIONAL HIGH SCHOOL | SANTA MARCELA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF HAND WASHING FACILITY | 262784.49 | BATCH 2 | 261439.08 | Completed | 100% | December 30, 2022 | December 19, 2022 | NONE | NONE | June 7, 2022 | June 13, 2022 | June 27, 2022 | July 4, 2022 | August 24, 2022 | ECV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136006 | Ipil Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 | 258459.54 | Completed | 100% | November 4, 2022 | October 28, 2024 | I-2022-116 | I-2022-116 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136009 | Magsaysay Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 | 263001.01 | Completed | 100% | November 4, 2022 | November 4, 2022 | I-2022-111 | I-2022-111 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | ARMCORE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136099 | Camp Conrado M. Balweg Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 290189 | BATCH 2 | 284709.34 | Completed | 100% | November 4, 2022 | October 25, 2024 | I-2022-112 | I-2022-112 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136111 | Sotto Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 279689 | BATCH 2 | 274209.54 | Completed | 100% | November 4, 2022 | October 25, 2024 | I-2022-110 | I-2022-110 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 136154 | Amlao Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 284939 | BATCH 2 | 278662.44 | Completed | 100% | November 4, 2022 | November 3, 2022 | I-2022-114 | I-2022-114 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | BANGYAN 3D CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 220515 | Basao Isla Elementary School | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 263939 | BATCH 2 | 263001.01 | Completed | 100% | November 4, 2022 | November 4, 2022 | I-2022-113 | I-2022-113 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | ARMCORE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) - ONE UNIT | 290189 | BATCH 2 | 284709.34 | Completed | 100% | November 4, 2022 | October 25, 2024 | I-2022-115 | I-2022-115 | August 9, 2022 | August 15, 2022 | August 15, 2022 | August 15, 2022 | October 14, 2022 | CHUMA-ASI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132166 | Cancohoy Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259943.48 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132166 | Cancohoy Elementary School | DEL CARMEN | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132167 | Dumoyog Primary School | DEL CARMEN | 2 | 1 |  | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259943.48 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132173 | Lobogon Elementary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254979.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132174 | Mabuhay Primary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 260000 | BATCH 2 | 259975.5 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-045 | BEFF-INFRA2022-045 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132177 | Quezon Primary School | DEL CARMEN | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 232510.86 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-046 | BEFF-INFRA2022-046 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132153 | La Januza Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269967.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132153 | La Januza Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Improvement of Water System (Solar Powered Pump and Stainless Steel Tank and Piping) | 550000 | BATCH 2 | 549970.83 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-047 | BEFF-INFRA2022-047 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132154 | Libertad Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132154 | Libertad Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132156 | Malinao Elementary Schol | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132160 | Suyangan Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 270000 | BATCH 2 | 269940.27 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132160 | Suyangan Elementary School | GENERAL LUNA | 2 |  | 1 | Proposed Construction of Water System (Deep Well desgn with Solar Powered Pump, Steel Overhead Tank and Drilling) | 900000 | BATCH 2 | 899881.94 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-048 | BEFF-INFRA2022-048 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Elementary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 2 | 1 | 1 | Proposed Construction of Handwashing Facility for Secondary (Option 1A -with Roofing and with counter with tile finish) | 255000 | BATCH 2 | 254918.3 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 2 |  | 1 | Proposed improvement of Water System (Steel Overhead Tank and Distribution line) | 500000 | BATCH 2 | 499786.6 | Completed | 100% | January 16, 2023 | March 20, 2023 | BEFF-INFRA2022-049 | BEFF-INFRA2022-049 | September 1, 2022 | September 7, 2022 | September 20, 2022 | October 27, 2022 | December 2, 2022 | TWO DEGREESS CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Overhead Tank)
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 702386.18 | BATCH 2 | 698595.17 | Completed | 100% | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -06 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 702386.18 | BATCH 2 | 701773.25 | Completed | 100% | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -07 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100899 | Ma. Cristina ES | BANGAR | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 696429.23 | BATCH 2 | 695810.81 | Completed | 100% | 2022-11-30 | November 21, 2022 | LU - SHF - 2022 -08 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100901 | Paratong ES | BANGAR | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 695455.43 | BATCH 2 | 695187.04 | Completed | 100% | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -09 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 501196 | Parian Este Integrated School | BAUANG | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 705700.25 | BATCH 2 | 701933.55 | Completed | 100% | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -10 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | EE MADAYAG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 100964 | Oaqui ES | LUNA | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 704226.68 | BATCH 2 | 701373.47 | Completed | 100% | 2022-11-30 | November 22, 2022 | LU - SHF - 2022 -11 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 300124 | Oanari National High School | LUNA | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 704226.68 | BATCH 2 | 701373.47 | Completed | 100% | 2022-11-30 | November 28, 2022 | LU - SHF - 2022 -12 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region I | La Union | 101075 | Urbiztondo ES | SAN JUAN | 2 | 1 | 4 | PROPSED CONSTRUCTION OF WATER AND SANITATION FACILITIES- FOUR (4) SEATER | 705484.66 | BATCH 2 | 704366.82 | Completed | 100% | 2022-11-30 | November 28, 2022 | LU - SHF - 2022 -13 | N/A | July 18, 2022 | July 27, 2022 | August 3, 2022 | August 10, 2022 | 2022-09-01 | LAV CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 104380 | Tres Reyes ES | SAGUDAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 107574.75 | BATCH 2 |  | COMPLETED | 100% | [9 empty] | FNS BUILDERS & ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region II | Quirino | 156518 | La Paz ES Extension Annex | SAGUDAY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 140213.11 | BATCH 2 |  | COMPLETED | 100% | [9 empty] | FNS BUILDERS & ENTERPRISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116090 | Alapasco Primary School | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | completed | 100% | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116091 | Banban PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-06 | 2023-06-30 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227659.27 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 180021 | Sta. Ana PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 100% | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-15 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116113 | Ngingi-an PS | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-16 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116116 | Tapacon Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116603 | Nasirum Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116763 | Ilongbukid E/S | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116767 | San Florentino ES | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 106061 | Atlu Bola ES | MABALACAT CITY | 2 | 1 | 4 | REPAIR OF COMFORT ROOMS | 310000 | BATCH 2 | 307989.66 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-006 | SBR-2022-08-007 | June 22, 2022 | June 29, 2022 | July 11, 2022 | August 15, 2022 | August 19, 2022 | Traccor Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 106087 | Sapang Biabas ES | MABALACAT CITY | 2 | 1 | 6 | REPAIR OF COMFORT ROOMS | 395000 | BATCH 2 | 393298.04 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-008 | SBR-2022-08-008 | June 22, 2022 | June 29, 2022 | july 11,2022 | August 15, 2022 | August 19, 2022 | Traccor Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 159535 | Northville 16 ES | MABALACAT CITY | 2 | 1 | 10 | REPAIR OF COMFORT ROOMS | 970000 | BATCH 2 | 967444.44 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-007 | SBR-2022-08-006 | June 22, 2022 | June 29, 2022 | July 11, 2022 | August 15, 2022 | August 19, 2022 | JFM Altitude Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 306916 | Mabalacat Comm. HS | MABALACAT CITY | 2 | 1 | 10 | REPAIR OF COMFORT ROOMS | 733000 | BATCH 2 | 730891.22 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-006 | SBR-2022-08-007 | June 22, 2022 | June 29, 2022 | July 11, 2022 | August 15, 2022 | August 19, 2022 | Traccor Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 306941 | Dr. Adelaido C. Bernardo HS | MABALACAT CITY | 2 | 1 | 2 | REPAIR OF 2 CR PLUS 1 UNIT SEPTIC VAULT | 265000 | BATCH 2 | 262444.44 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-007 | SBR-2022-08-006 | June 22, 2022 | June 29, 2022 | July 11, 2022 | August 15, 2022 | August 19, 2022 | JFM Altitude Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Mabalacat City | 500631 | Dona Asuncion Lee IS | MABALACAT CITY | 2 | 1 | 8 | REPAIR OF 8 COMFORT ROOMS OF THE 4STY BUILDING | 685900 | BATCH 2 | 682590.84 | COMPLETED | 100% | September 18, 2022 | September 16, 2022 | PB-2022-06-008 | SBR-2022-08-008 | June 22, 2022 | June 29, 2022 | July 11, 2022 | August 15, 2022 | August 19, 2022 | Traccor Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106305 | Dolores Ongsiako CES | ANAO | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 205919.89 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-001 | RR-HF 2022-001 |  |  |  |  | 2022-09-21 | MCB CONSTRUCTION AND SUPPLY | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106306 | Bantog ES | ANAO | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238662.25 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-002 | RR-HF 2022-002 |  |  |  |  | 2022-09-21 | Jayvin Construction | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106608 | Guiteb ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238662.25 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-003 | RR-HF 2022-003 |  |  |  |  | 2022-09-21 | A.R. ESBI CONSTRUCTION | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106612 | San Raymundo ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238662.25 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-004 | RR-HF 2022-004 |  |  |  |  | 2022-09-21 | A.R. ESBI CONSTRUCTION | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238662.25 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-005 | RR-HF 2022-005 |  |  |  |  | 2022-09-21 | A.R. ESBI CONSTRUCTION | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238.850.85 | COMPLETED | 100% |  | OCTOBER 20,2022 | RR-HF 2022-006 | RR-HF 2022-006 |  |  |  |  | 2022-09-20 | HIGH VISION BUILDERS CORPORATION | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 106624 | Pit-Ao ES | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 238796.34 | COMPLETED | 100% |  | October 21, 2022 | RR-HF 2022-007 | RR-HF 2022-007 |  |  |  |  | 2022-09-22 | OXCON ENTERPRISES | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 239942.94 | COMPLETED | 100% |  | OCTOBER 20,2022 | RR-HF 2022-008 | RR-HF 2022-008 |  |  |  |  | 2022-09-20 | DIANNE BUILDERS | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 2 | 1 | 1 | Construction of group handwashingfacility-for elementary(option 1A with roofing,with counter with tile finish) | 240000 | BATCH 2 | 239009.74 | COMPLETED | 100% |  | OCTOBER 20,2022 | RR-HF 2022-009 | RR-HF 2022-009 |  |  |  |  | 2022-09-20 | HIGH VISION BUILDERS CORPORATION | BAC no longer has data on this project | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108957 | SALVACION ES | AGDANGAN | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 222197.06 | Completed | 100% | 9/28/2022 | 2022-08-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | L.A PROFUGO CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108979 | APAD ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108980 | BUKAL ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108982 | CASUGURAN ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 243416 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108983 | GANGO ES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 257320.41 | BATCH 2 | 249821 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301333 | JOMALIG NHS | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 302394 | APAD JOMALIG NHS | JOMALIG | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301283 | MAGSAYSAY NHS (Formerly Ajos Ext.) | MULANAY | 2 | 1 | 1 | Construction of School Clinic | 2660554.56 | BATCH 2 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108987 | KILOGAN ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 263912 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108989 | PATNANUNGAN CENTRAL SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108990 | PATNANUNGAN NORTE ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 100% | 9/28/2022 | 9/15/2022 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108991 | SININTAN ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 100% | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108992 | TAPOL ELEMENTARY SCHOOL | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 222920 | Completed | 100% | 9/28/2022 | 2022-09-09 | 2022-02-INFRA | 2022-02-INFRA | 2022-08-02 | 2022-08-03 | 3/21/2022 | 5/20/2022 | 5/24/2022 | C.G. CABANA CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301374 | PATNANUNGAN NHS | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 175668.2 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 305524 | PAARALANG SEKUNDARYA NG PATNANUNGAN NORTE | PATNANUNGAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 246805.58 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 108999 | RIZAL-MAABOT ES | PEREZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301375 | PEREZ NHS | PEREZ | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 170540.21 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301316 | CONCEPCION NHS | PLARIDEL | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 215487.88 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109051 | Cometa ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109052 | Del Pilar ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 170540.21 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109053 | Guinhawa ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 14, 2023 | INFRA-2022-004 | INFRA-2022-004 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109054 | Gumubat ES | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | March 21, 2023 | INFRA-2022-006 | INFRA-2022-006 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301313 | EVARISTO R. MACALINTAL MNHS (Formerly Cometa NHS) | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 301314 | CESAR C. TAN MEM NHS (formerly Cometa Annex) | QUEZON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH FLAT ROOFING, WITH COUNTER WITH TILE FINISH) | 236672.71 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109122 | Don Juan Vercelos Elem. School | SAN FRANCISCO | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region IV-A | Quezon | 109149 | Rizal Elementary School | SAN NARCISO | 2 | 1 | 1 | Construction of School Clinic | 2540985.98 | BATCH 2 | 160284.24 | Completed | 100% | 2023-03-02 | 2023-03-14 | INFRA-2022-005 | INFRA-2022-005 | July 23, 2022 | August 1, 2022 | August 15, 2022 | October 6, 2022 | December 27, 2022 | VRV Construction and Trading | Paid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112759 | Bombon Central School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 309707 | Siembre High School | BOMBON | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS (Junior High) | Cabusao | 2 | 1 | 1 | Repair of Health Facilities | 569311.19 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 2 | 1 | 2 | New Handwashing Facilities | 427582 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112499 | Dugcal ES | CAMALIGAN | 2 | 1 | 1 | New Handwashing Facilities | 216359.09 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 302052 | Camaligan National High School | CAMALIGAN | 2 | 1 | 2 | New Handwashing Facilities | 427582 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Camarines Sur | 112779 | Gainza CS - Gainza | GAINZA | 2 | 1 |  | Repair of Health Facilities | 573205.47 | BATCH 2 |  | Completed | 100% | October 17, 2023 |  | 45085 | 2023-07-030 | June 14, 2023 | June 21, 2023 | July 3, 2023 | July 7, 2023 | August 18, 2023 | Riders Corners Building and Reality Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113154 | Bugao Central ES | BAGAMANOC | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113155 | Cahan Bo. Sch. | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 10, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113161 | Bagamanoc CES | BAGAMANOC | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 772808.38 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-09 |  |  | September 27, 2022 | November 3, 2022 | November 11, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113164 | Salvacion ES | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113165 | Suchan Elementary School | BAGAMANOC | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113166 | Agban Central Elementary School | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113172 | Abihao ES | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113173 | Baras CES | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 728339.24 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-11 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113175 | Macutal Elementary School | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113176 | Moning Elementary School | BARAS | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 761.991.31 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-12 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113192 | Guinobatan Elementay School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113195 | Sipi Elementary School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 715291.16 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500412 | Bote IS | BATO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 717950.84 | COMPLETED | 100% | November 21, 2022 |  | INFRA-2022-03 | 2022-12-14 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113220 | Gigmoto CES | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113221 | San Pedro ES | GIGMOTO | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302088 | Gigmoto Rural DHS | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 500033 | Sicmil Integrated School | GIGMOTO | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 795588.44 | COMPLETED | 100% | December 29, 2022 |  | INFRA-2022-03 | 2022-12-15 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | NQA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113244 | Alinawan ES | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113251 | Maculiw Comm. Sch. | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113252 | Panay Comm. Sch. | PANGANIBAN (PAYO) | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113253 | Panganiban Central Elementary School | PANGANIBAN (PAYO) | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302095 | Panganiban National High School | PANGANIBAN (PAYO) | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 700412.3 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-03 | 2022-12-16 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | MDQR CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | PANGANIBAN (PAYO) | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 771703 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-10 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113285 | Alma Elementary School | SAN MIGUEL | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 798308.53 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-18 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113287 | Caglatawan Elementary School | SAN MIGUEL | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 912371.84 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-17 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113292 | Pagsangahan Elementary School | SAN MIGUEL | 2 | 1 | 2 | Construction Of Handwashing Facilities | 247498.91 | BATCH 2 | 798308.53 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-18 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113298 | J.M.A.-Tucao ES | SAN MIGUEL | 2 | 1 | 1 | Construction Of Handwashing Facilities | 123749.45 | BATCH 2 | 912371.84 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-17 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 912371.84 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-17 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 912371.84 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-17 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 2 | 1 | 3 | Construction Of Handwashing Facilities | 371248.36 | BATCH 2 | 798308.53 | COMPLETED | 100% | January 4, 2023 |  | INFRA-2022-08 | 2022-12-18 |  |  | September 27, 2022 | November 3, 2022 | November 9, 2022 | FDS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 725356 | BATCH 2 |  | Completed | 100% | 2024-01-15 |  | INFRA 2023-09-003 | 2023-03-042 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 610169 | BATCH 2 |  | Completed | 100% | 2024-01-15 |  | INFRA 2023-09-003 | 2023-03-042 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113620 | Baras ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440032 | BATCH 2 |  | Completed | 100% | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113627 | Masbaranon ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 100% | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113634 | Tawad ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 100% | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-045 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | 3R3M CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113636 | Villa ES | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440031 | BATCH 2 |  | Completed | 100% | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-046 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | JRMG CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 302171 | Santos E. Conag National High School | Esperanza | 2 | 1 | 1 | Repair of Health Facilities | 440032 | BATCH 2 |  | Completed | 100% | 2024-01-01 |  | INFRA 2023-09-003 | 2023-11-046 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-17 | JRMG CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113863 | Buyo ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 717068 | BATCH 2 |  | Completed | 100% | 2024-01-15 | 2024-01-08 | INFRA 2023-09-003 | 2023-11-043 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113872 | P. Basas ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 780368 | BATCH 2 |  | Completed | 100% | 2024-01-15 |  | INFRA 2023-09-003 | 2023-11-043 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 758724 | BATCH 2 |  | Completed | 100% | 2024-01-15 | 2024-01-08 | INFRA 2023-09-003 | 2023-11-044 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Masbate | 113881 | Valparaiso ES | SAN FERNANDO | 2 | 1 | 1 | REPAIR OF HEALTH FACILITIES | 710556 | BATCH 2 |  | Completed | 100% | 2024-01-15 |  | INFRA 2023-09-003 | 2023-11-044 | 2023-09-28 | 2023-10-06 | 2023-10-18 | 2023-11-03 | 2023-11-16 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 113987 | Macabari Elementary School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 620000 | BATCH 2 | 409181.1 | COMPLETED | 100% | 2023-06-09 | 2023-10-11 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 600000 | BATCH 2 | 395982.07 | Completed | 100% | 2023-06-09 | 2023-08-22 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302218 | Celso F. Falcotelo National High School | BARCELONA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 428986.32 | Completed | 100% | 2023-06-09 | 2023-08-22 | 23-01-001 | 23-01-001-01 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114391 | Calao ES | PRIETO DIAZ | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 428922.22 | Completed | 100% | 2023-06-17 | 2023-08-04 | 23-01-001 | 23-01-001-02 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302223 | Manlabong National High School | PRIETO DIAZ | 2 | 1 | 1 | New Handwashing Facilities | 653305.03 | BATCH 2 | 431102.51 | Completed | 100% | 2023-06-17 | 2023-08-04 | 23-01-001 | 23-01-001-02 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114411 | Salvacion ES | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 429065.08 | Completed | 100% | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 114416 | Talaonga ES | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 580000 | BATCH 2 | 382655.47 | Completed | 100% | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | 1 | New Handwashing Facilities | 650000 | BATCH 2 | 429065.46 | Completed | 100% | 2023-06-19 | 2023-12-19 | 23-01-001 | 23-01-001-03 | 2023-01-04 | 2023-01-12 | 2023-01-24 | 2023-01-30 | 2023-02-10 | NJNY Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115849 | Constancia Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2324096.02 | BATCH 2 | 2334753.36 | Completed | 100% | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115850 | Doña Lucia C. Locsin Memorial School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2361288.64 | BATCH 2 | 2334753.36 | Completed | 100% | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 115854 | San Enrique Elementary School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2342692.33 | BATCH 2 | 2320995.12 | Completed | 100% | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2370586.79 | BATCH 2 | 2334753.36 | Completed | 100% | 2023-03-07 |  | 05-2022-lot 1 | No.-04-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | 2 | 1 | 1 | CONSTRUCTION OF CLINIC | 2351990.84 | BATCH 2 | 2320995.12 | Completed | 100% | 2023-03-07 |  | 05-2022-lot3 | No.-03-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | 2022-10-03 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116090 | Alapasco Primary School | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | completed | 100% | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116091 | Banban PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-06 | 2023-06-30 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 227659.27 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 180021 | Sta. Ana PS | BATAD | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 100% | 2023-04-06 | 2023-03-10 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L1 | 2022-06-03 | 2022-06-15 | 2022-06-27 | Aug. 08, 2022 | 2022-12-07 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116113 | Ngingi-an PS | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 573926.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-16 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116115 | Quinar-upan Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116116 | Tapacon Elementary School | BINGAWAN | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | 2023-04-14 | 2023-04-14 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L2 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-15 | WILKINSON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116601 | Janipa-an Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116603 | Nasirum Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 558176.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 563426.58 | BATCH 2 |  | Completed | 100% | 2023-04-12 | 2023-03-27 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | BEFF-2022-RVI-022-ILOILO-WATSAN-B2-L3 | 2022-06-03 | 2022-06-14 | 2022-06-27 | Aug. 08, 2022 | 2022-12-13 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116763 | Ilongbukid E/S | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VI | Iloilo | 116767 | San Florentino ES | SAN RAFAEL | 2 | 1 | 4 | Proposed Construction of Water Facilities- Four (4) Seaters | 568676.58 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 118866 | Alcantara Central ES | ALCANTARA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 439726 | BATCH 2 | 438726 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 118868 | Candabong ES | ALCANTARA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 439726 | BATCH 2 | 438726 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 187004 | Palanas ES | ALCANTARA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 | 218863 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 | 1 | 3 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 657930 | BATCH 2 | 656930 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 2 |  | 1 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2558274.37 | BATCH 2 | 2555274.37 | Completed | 100% | April 13, 2023 | June 2, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500649 | Cabadiangan Integrated School | ALCANTARA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 2A - WITH WATER CONTAINER, WITHOUT ROOFING) | 89547.33 | BATCH 2 | 88547.33 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-03 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 | 218209.49 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500650 | Pasol-Pugalo IS | ALCOY | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 | 218746.36 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119132 | Lunop ES | BOLJOON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 | 218209.49 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 302944 | Lunop NHS | BOLJOON | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 | 218183.64 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119404 | Kabatuan ES | GINATILAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 219863 | BATCH 2 | 218863 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 | 288269.18 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 | 1324497.29 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Solar Powered Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119445 | Malabuyoc Central ES | MALABUYOC | 2 | 1 | 4 | PROPOSED CONSTRUCTION OF THREE (3) UNITS GROUP HANDWASHING FACILITY OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH & ONE UNIT OPTION 1A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH | 576528.38 | BATCH 2 | 575528.38 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119446 | Mindanao ES | MALABUYOC | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 2A - WITH WATER CONTAINER, WITHOUT ROOFING) | 89547.33 | BATCH 2 | 88547.33 | COMPLETED | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | CY 2022 BEFF Health Batch 2-DepED-R7-Cebu02 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Ten twenty allied Developers |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 162952.68 | BATCH 2 | 160809.24 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119601 | Ronda Central ES | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 | 1322810.74 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Solar Powered Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 | 287135.6 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 | 1322810.74 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-04 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | M.P. Sorela Const. & Supply & Marine Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Solar Powered Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR SECONDARY (OPTION 3B - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 162432.34 | BATCH 2 | 161464.81 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF WATER SYSTEM (Installation of Overhead water tank and Cistern tank with Solar - Powered Submersible Water Pump) | 1325497.29 | BATCH 2 | 1322458.55 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | Construction of Water System (Solar Powered Water pump)
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 2 |  | 1 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2558274.37 | BATCH 2 | 2552153.71 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-05 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Tri-bairn Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 3A - ONE - SIDED, WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 289269.18 | BATCH 2 | 278375.67 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303090 | Samboan NHS | SAMBOAN | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 219310 | BATCH 2 | 217798.32 | COMPLETED | 100% | March 13, 2023 | September 27, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-01 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | GCATZ Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 119860 | Puertobello ES | TUDELA | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION A - WITH ROOFING) | 239863 | BATCH 2 | 239230.73 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 2 | 1 | 2 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION B - WITH ROOFING) | 478620 | BATCH 2 | 478096.99 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 2 |  | 2 | PROPOSED CONSTRUCTION OF SCHOOL CLINIC | 2808274.37 | BATCH 2 | 2787822.73 | Completed | 100% | April 13, 2023 | April 13, 2023 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | CY 2022 BEFF-Health Batch2-DepED-R7-Cebu-06 | October 14, 2022 | October 24, 2022 | November 7, 2022 | November 21, 2022 | January 5, 2023 | Barr steel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Clinic
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120843 | Ungale I ES | KAWAYAN | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 179667.12 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120852 | Danao ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Biliran | 120855 | Viga ES | MARIPIPI | 2 | 1 | 1 | GROUP HANDWASHING (NEWCON) | 268631.66 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122499 | San Miguel Elementary School | HERNANI | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 326150.48 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122344 | Bolusao Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122348 | Guinob-an Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122349 | Lawaan Central Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 | 1 | 1 | PROVISION OF DEEP WELL WITH SOLAR - POWERED SUBMERSIBLE WATER PUMP | 1884634.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (DeepWell)
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122350 | Maslog Elementary School | LAWAAN | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING | 216478.78 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Eastern Samar | 122536 | Bobon Elementary School | MERCEDES | 2 |  | 1 | CONSTRUCTION OF 4-SEATER COMFORT ROOM | 534750.77 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121520 | Calbasag Elementary School | Julita | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121529 | Sta. Cruz Elementary School | Julita | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121529 | Sta. Cruz Elementary School | Julita | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121533 | Villahermosa Elementary School | Julita | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 200144.06 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121533 | Villahermosa Elementary School | Julita | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 522704.42 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 200784.56 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121619 | Danao Elementary School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 522704.42 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | TRIPLE Z MC CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121621 | MacArthur Central School | MacArthur | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121621 | MacArthur Central School | MacArthur | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121716 | Calunangan Elementary School | Merida | 2 | 1 | 1 | Construction of Group Handwashing Facility | 213746.38 | BATCH 2 | 212144.19 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-07-05 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121719 | Canbantug Elementary School | Merida | 2 | 1 | 1 | Construction of Group Handwashing Facility | 214481.38 | BATCH 2 | 212354.19 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121810 | Bahay Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121810 | Bahay Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532313.63 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121813 | Canino-an Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121814 | Colawen Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 202339.31 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121814 | Colawen Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 530955.83 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121816 | Halaba Primary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 202339.31 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121816 | Halaba Primary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 530955.83 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | J. CUSTORIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121817 | Jones Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203854.76 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | F.A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121827 | Tingib Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203669.62 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121827 | Tingib Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532459.26 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121828 | Yapad Elementary School | Pastrana | 2 | 1 | 1 | Construction of Group Handwashing Facility | 204821.38 | BATCH 2 | 203669.62 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121828 | Yapad Elementary School | Pastrana | 2 |  | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 533655.5 | BATCH 2 | 532459.26 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | PYUKEI CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121868 | Badiangay Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507324.88 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121878 | San Miguelay Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507322.11 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Leyte | 121881 | Tibak Elementary School | Sta Fe | 2 | 1 | 1 | Construction of Water and Sanitation Facilities - Four (4) Seater | 509441.14 | BATCH 2 | 507324.88 | Completed | 100% |  |  |  |  | 2022-02-06 | 13/06/2022 | 27/06/2022 | 2022-05-07 |  | FOUR K BUILDERS AND CONSTRUCTION SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123587 | CASAPA ELEMENTARY SCHOOL | JIABONG | 2 | 1 | 1 | I UNIT RAIN WATER COLLECTOR | 152934.94 | BATCH 2 | 151934.94 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123598 | Malobago ES | JIABONG | 2 | 1 | 1 | 2 UNITS RAIN WATER COLLECTOR | 300733.71 | BATCH 2 | 299019.01 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Water System (RainWater Collector) | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 281506 | FLORA MABAET MABANSAG ES | JIABONG | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 593554.77 | BATCH 2 | 590821.75 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 589018 | BATCH 2 | 588508.26 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | SEGUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123609 | Canyoyo Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123613 | Logero Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123616 | Pinalangga ES | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123617 | Pinamitinan Elementary School | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193516 | Mabuhay ES | MARABUT | 2 | 1 | 1 | NEW CONSTRUCTION 1 UNIT GHW 1A | 230506.11 | BATCH 2 | 229497.56 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | KUBLAI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 193541 | Salvacion PS | MATUGINAO | 2 | 1 | 1 | I UNIT GHW 2A AND 1 UNIT RAIN WATER COLLECTOR | 316333.28 | BATCH 2 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | HAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123657 | San Luis ES | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 600635.4 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303615 | Pagsanghan National High School | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 600635.4 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires IS | PAGSANGHAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 607165.07 | BATCH 2 | 605885.4 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | PLGL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123715 | Camanhagay ES | SAN SEBASTIAN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 602628.3 | BATCH 2 | 598745.48 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2 | 1 | 1 | I UNIT GHW 2A AND 1 UNIT RAIN WATER COLLECTOR | 309345.32 | BATCH 2 | 306127.05 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123716 | Campiyak Elementary School | SAN SEBASTIAN | 2 |  | 1 | REPAIR OF 2 SEATER CR | 237308.79 | BATCH 2 | 234231.17 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GPUY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Repair of WatSan | REPAIR
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 303632 | STO NINO NHS | STO NINO | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 611701.83 | BATCH 2 |  | Completed | 100% |  |  |  |  | 2022-07-21 | 2022-07-29 | 2022-08-10 | 2022-08-15 |  | HAL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123816 | Baquiw ES | TAGAPUL-AN | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 611701.83 | BATCH 2 | 610523.12 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123820 | Luna Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123821 | Manlangit Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123825 | Pulangbato Elementary School | TAGAPUL-AN | 2 | 1 | 1 | 1 UNIT GHW 1A | 235683.06 | BATCH 2 | 234302.53 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | GG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 123977 | Pangdan ES | ZUMARRAGA | 2 | 1 | 1 | NEWCON GHW OPTION 2A AND 1 UNIT RAINWATER COLLECTOR | 314040.09 | BATCH 2 | 309614.25 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | TRIPLE Z CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Samar (Western Samar) | 313721 | San Isidro NHS | ZUMARRAGA | 2 | 1 | 1 | NEW CONSTRUCTION 4 SEATER CR | 607165.07 | BATCH 2 | 602396.72 | Completed | 100% | 2022-12-11 |  |  |  | 2022-05-25 | 2022-06-01 | 2022-06-14 | 2022-06-17 | 2022-09-05 | TRIPLE Z CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122070 | Capacuhan Elementary School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 267436.21 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 192001 | Calintaan Elementary School | ANAHAWAN | 2 | 1 | 1 | New Construction of GHW | 268227.83 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122073 | Lungsodaan Elementary School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122073 | Lungsodaan Elementary School | HINUNDAYAN | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122076 | Plaridel Elementary School | HINUNDAYAN | 2 | 1 | 1 | New Construction of GHW | 268227.83 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122078 | Gakat Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 264190.56 | BATCH 2 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122078 | Gakat Elementary School | LIBAGON | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2 |  | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 270802.89 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 |  | 4 | New Construction of WATSAN | 560850.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303465 | Limasawa National High School | LIMASAWA | 1 | 1 | 1 | New Construction of GHW | 271394.32 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303465 | Limasawa National High School | LIMASAWA | 1 |  | 4 | New Construction of WATSAN | 560850.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1 | 1 | 1 | New Construction of GHW | 264269.72 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122227 | San Juan Elementary School | PADRE BURGOS | 1 |  | 4 | New Construction of WATSAN | 540087.5 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 258710.08 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 |  | 1 | New Construction of GHW | 263723.31 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 |  | 4 | New Construction of WATSAN | 548392.55 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 192019 | Catbawan Elementary School | PINTUYAN | 2 | 1 | 1 | New Construction of GHW | 260609.97 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 2 | 1 | 1 | New Construction of GHW | 263873.91 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122098 | Habay Elementary School | SAN FRANCISCO | 2 |  | 4 | New Construction of WATSAN | 544240.05 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122250 | Garsavic Elementary School | SAN JUAN (CABALIAN) | 2 | 1 | 1 | New Construction of GHW | 266644.59 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2 | 1 | 1 | New Construction of GHW | 267436.21 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2 |  | 4 | New Construction of WATSAN | 554621.3 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 0 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122312 | Canlupao Elementary School | TOMAS OPPUS | 1 | 1 | 4 | New Construction of WATSAN | 538011.31 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of WatSan | Construction
SCHOOL HEALTH FACILITIES 2022 | Region VIII | Southern Leyte | 122319 | Maslog Elementary School | TOMAS OPPUS | 1 | 1 | 1 | New Construction of GHW | 263478.1 | BATCH 2 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4 | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-11-05 | [8 empty] | MATT GLASS ALUMINUM SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129405 | Taguibo ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129409 | Vicente Almario Sr. MS | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 214662.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction
SCHOOL HEALTH FACILITIES 2022 | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2 | 1 | 1 | CONSTRUCTION OF GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH 200MM ELEVATION) | 220962.01 | BATCH 1 |  | Completed | 100% | 2022-10-17 | [8 empty] | R. BAUDON CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  |  | 0 | 0 | 0 | 0 | 1 | Construction of Group Hand Washing | Construction