## QRF 2019-2024
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed | DUE TO | No. of Sites (original) | No. of Classrooms (original) | Project Allocation (original) | SCOPE
QRF 2019 | CAR | Abra | 134982 | Patucannay ES | BANGUED (Capital) | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 3305988.58 | 1 | 3216783.844 | Completed | 100% | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135038 | Nagaparan ES | DANGLAS | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 2405724.24 | 1 | 2323709.3407 | Completed | 100% | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135029 | Canan ES | LA PAZ | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2205051.57 | 1 | 2095607.877 | Completed | 100% | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135064 | Lacub CS | LACUB | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 6159129.62 | 1 | 5966611.555 | Completed | 100% | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135079 | Sap-al Elementary School | LACUB | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 2567862.69 | 1 | 2468916.4653 | Completed | 100% | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135065 | Lagangilang Central School | LAGANGILANG | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 5885980.58 | 1 | 5719780.1917 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135136 | Langiden CS | LANGIDEN | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3620813.95 | 1 | 3517312.7835 | Completed | 100% | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135104 | Lul-luno ES | LUBA | 0 | 1 | 3 | 1STY3CL | 11354965.53 | 1 | 11066634.1827 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-008 / CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction/HOPE EFG Builders | Just Started due to inaccessible roads | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Abra | 135112 | Tabangao ES | LUBA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2964322.57 | 1 | 2468916.4653 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-008 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135117 | Tukipa PS | LUBA | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 4434581.32 | 1 | 4337718.4494 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-008 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | TRAMS Construction | Just Started due to inaccessible roads | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 5605683.18 | 1 | 5413133.3243 | Completed | 100% | 2020-03-20 |  | CAR-ABRA-2019-007 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HGW=3 Engineering & Construction | Not Yet Started Due to Inaccessible Roads | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 134998 | Madago Primary School | MANABO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1268583.76 | 1 | 1217727.357 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135005 | San Jose ES | MANABO | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3878256.12 | 1 | 3742500.6402 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135122 | Malamsit Elementary School | PEÑARRUBIA | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3235671.95 | 1 | 3095453.7457 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135189 | Maguyepyep Elementary School | SALLAPADAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1066946.84 | 1 | 1045961.9676 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135126 | Olo ES | SAN ISIDRO | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 632182.64 | 1 | 608544.5499 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-006 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | LONNIE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 305099 | San Quintin NHS | SAN QUINTIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 4179298.38 | 1 | 4058432.9764 | Completed | 100% | 2019-11-26 |  | CAR-ABRA-2019-005 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | Baje Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135087 | Alangtin Elementary School | TUBO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 3023693.15 | 1 | 2953738.7947 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Abra | 135116 | Tubtuba ES | TUBO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 4351440.58 | 1 | 4269195.8872 | Completed | 100% | 2019-12-21 |  | CAR-ABRA-2019-009 |  | 2019-06-12 | 2019-06-18 | 2019-07-01 | 2019-07-04 | 2019-07-16 | HOPE EFG Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 305106 | Apayao National Industrial Agricultural High School | CALANASAN (BAYAG) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5241349.15 | 1 | 5088969.95 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 135286 | Bagutong ES | FLORA | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3017754.7 | 1 | 2969516.03 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 219010 | Tamalunog Elementary School | FLORA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 651052.28 | 1 | 620254.8 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 135298 | Baliwanan ES | KABUGAO (Capital) | 0 | 1 | 3 | 1STY3CL | 7034015.36 | 1 |  | Completed | 100% | [10 empty] | 2 failed biddings, 1 failed negotiated procurement, request for re-program | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Apayao | 305115 | Kabugao Agro-Ind'l. HS | KABUGAO (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 10374144.99 | 1 | 10132642.75 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 135343 | San Isidro ES | LUNA | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1315890.14 | 1 | 1295778.16 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTALS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 318801 | Tumog National Agricultural and trade High School | LUNA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5083849.15 | 1 | 4977120.33 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 305123 | Pudtol NHS | PUDTOL | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1169283.9 | 1 | 1152244.16 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | J.G. YACAS CONSTRUCTION, SUPPLY AND EQUIPMENT RENTALS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Apayao | 319009 | TAWIT NHS (MATAGUISI COMP. NHS - CACALAGAN ANNEX) | PUDTOL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3285437.2 | 1 | 8133846.45 | Completed | 100% | NOVEMBER 28,2019 |  |  |  | JUNE 11, 2019 | JUNE 20, 2019 | JULY 2, 2019 | JULY 11, 2019 | JULY 23, 2019 | EBJR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Baguio City | 136384 | Dontogan Elementary School | BAGUIO CITY | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2932636.95 | 1 | 1965559.09 | Completed | 100% | 2020-05-02 |  | 001,s.2020 | 001,s.2020 | 2019-11-20 | 2019-11-29 | 2020-12-11 | 2019-12-20 | 2020-02-17 | JJJ-A Construction and Supplier |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 4088343.48 | 1 | 4077601.49 | Completed | 100% | January 12, 2020 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Ifugao | 135808 | Amganad ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3464415.42 | 1 | 3422131.02 | Completed | 100% | January 8, 2020 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Ifugao | 135808 | Amganad ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3653335.74 | 1 | 3618631.11 | Completed | 100% | January 8, 2020 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Ifugao | 135810 | Anaba ES | BANAUE | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2222779.43 | 1 | 2220521.78 | Completed | 100% | January 8, 2020 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Kalinga | 135987 | Ag-agama Elementary School | LUBUAGAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2590760.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Kalinga | 135994 | Mabongtot Elementary School | LUBUAGAN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 478198.61 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | COMPLETED
QRF 2019 | CAR | Kalinga | 135996 | Manangol Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2407902.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Kalinga | 135996 | Manangol Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1251715.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Kalinga | 135998 | Tanglag Elementary School | LUBUAGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2222429.66 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | completed
QRF 2019 | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | 0 | 1 | 2 | 1STY2CL | 6742528.28 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | PUGONG ES | PASIL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3492885.15 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | completed
QRF 2019 | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | 0 | 1 | 2 | 1STY2CL | 5337283.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Kalinga | 136049 | Malaap Elementary School | PINUKPUK | 0 | 1 | 2 | 1STY2CL | 6770303.2 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Malagnat NHS | PINUKPUK | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 11145876.01 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Bagbag Elementary School Bulbul Annex | RIZAL (LIWAN) | 0 | 1 | 4 | 1STY2CL | 5114707.54 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | 136071 | Kinama Elementary School | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6964369.27 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6825619.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Rizal Central School Cadao Annex | RIZAL (LIWAN) | 0 | 1 | 3 | 1STY3CL | 6727105.08 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | NOT-IN-NSBI | Santor NHS | RIZAL (LIWAN) | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 10024112.37 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | 0 | 1 | 2 | 1STY2CL | 5666889.58 | 1 |  | Completed | 100% | [10 empty] | Contractor's Fault, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 44986 | 2.23 | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | 0 | 1 | 3 | 1STY3CL | 8662582.66 | 1 |  | Completed | 100% | [10 empty] | Contractor's Fault, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 44986 | 2.23 | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | 0 | 1 | 5 | 1STY3CL | 8575272.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 18074197.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Kalinga | 136143 | Ambato-Legleg Elementary School | TINGLAYAN | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 35594457.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 305235 | Barlig National High School | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 3438008.24 | 1 |  | Reverted | 0% | [10 empty] | Procurement Issues | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | TY ROSITA |  |  |  | REPAIR | Reverted
QRF 2019 | CAR | Mt. Province | 305242 | Eastern Bontoc NAVHS | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 2498721.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136187 | KALEO ELEMENTARY SCHOOL | BARLIG | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 811075.4 | 1 |  | Reverted | 0% | [10 empty] | for award;BAC problem | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% |  |  | TY ROSITA |  |  |  | REPAIR | Reverted
QRF 2019 | CAR | Mt. Province | 136196 | Ambacbac Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 765719.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136216 | Mayag Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1129781.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136221 | Otucan Elementary School | Bauko | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1113998.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136223 | Pangao Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 655852.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136226 | Sadsadan Trail Elementary School | BAUKO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1146140.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | 0 | 1 | 3 | 1STY3CL | 6702902.62 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | 0 | 1 | 3 | 1STY3CL | 8647684.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 305260 | Panabungen School of Arts, Trades & Home Industries | BESAO | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 998369.9376 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 8584999.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | 0 | 1 | 2 | 1STY2CL | 5193717.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 319216 | Banawel National High School | NATONIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 829001.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2433068.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136274 | Pangtor Primary School | NATONIN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1633100.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 319203 | Saliok National High School | NATONIN | 0 | 1 | 4 | 2 UNITS OF 1STY2CL | 8490919.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136280 | Tonglayan Elementary School | NATONIN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 1237382.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136283 | Anonat Elementary School | PARACELIS | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 705200.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2476665.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL | 6275562.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136306 | Marallag Elementary School | PARACELIS | 0 | 1 | 2 | 1STY2CL | 5193556.21 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | 0 | 1 | 3 | 1STY3CL | 7218770.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136316 | Capinitan Elementary School | SABANGAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 5170561.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 221007 | Libo Elementary School | SABANGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 421640.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136325 | Napua Elementary School | SABANGAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 521056 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2704798.65 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | 0 | 1 | 2 | 1STY2CL | 4389142.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 305264 | Sadanga National High School | SADANGA | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1742434.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | 0 | 1 | 2 | 1STY2CL | 5011790.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 305229 | Antadao National High School | SAGADA | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 3310364.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | 0 | 1 | 2 | 1STY2CL | 4972915.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 319221 | Balaoa National High School | TADIAN | 0 | 1 | 3 | 1STY3CL | 8944905.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 319223 | Lubon NHS - Mabalite Extension | TADIAN | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 1179006.55 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | 0 | 1 | 3 | 1STY3CL | 6477188.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 305251 | Masla National High School | TADIAN | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1136501.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Mt. Province | 221012 | New LubonElementary School | TADIAN | 0 | 1 | 3 | 1STY3CL | 6966736.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2700392.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 136153 | Addang Primary School | CITY OF TABUK (Capital) | 0 | 1 | 2 | 1STY2CL | 4761026.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9609694.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Tabuk City | 136093 | Calaccad Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | 6353531.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9737009.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Tabuk City | 136096 | Cudal Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 9131452.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 305203 | Cudal National High School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 11290496.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 500531 | Dilag Integrated School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 8571782.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 136171 | Lucog Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 702687.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 319117 | Naneng NHS - Mosimos Extension | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 7691889.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 220529 | San Pablo Primary School | CITY OF TABUK (Capital) | 0 | 1 | 3 | 1STY3CL | 6351404.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1101792.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | 305221 | Tabuk City National High School | CITY OF TABUK (Capital) | 0 | 1 | 44 | REPAIR OF CLASSROOMS | 12386627.0261 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 44 | 100% | 0% |  | previous yrs | TY OMPONG/TY KAREN LAWIN/TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | CAR | Tabuk City | NOT-IN-NSBI | Tabuk City National High School - BANTAY EXT. | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9579509.61 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | completed
QRF 2019 | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | 0 | 1 | 5 | 1STY5CL | 9632009.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | 5211417.5351 | 1 | 5163772.87 | Completed | 100% | [5 empty] | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | RF Varquez Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPLACEMENT | Completed
QRF 2019 | CARAGA | Surigao City | 132257 | Ouano ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 3449081.1441 | 1 | 3440000 | Completed | 100% | [5 empty] | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Windfall Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPLACEMENT | Completed
QRF 2019 | NCR | Marikina City | 305402 | Malanday NHS | CITY OF MARIKINA | 1 | 1 | 60 | REPAIR OF CLASSROOMS | 13562619.87 | 1 | 13517578.74 | Completed | 100% |  |  |  |  | 2019-06-04 | 2019-06-11 | 2019-07-01 | 2019-07-09 |  | MMEEN Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 60 | 100% | 0% |  | previous yrs | TORNADO |  |  |  | REPAIR | Completed
QRF 2019 | Region I | La Union | 101069 | Naguituban ES | San Juan | 1 | 1 | 2 | 1STY 2CL | 3607027.98 | 1 | 3583247.64 | Completed | 100% | 2019-10-20 | 2019-09-10 |  |  | 2019-06-06 | 2019-06-13 | 2019-06-28 | 2019-07-15 | 2019-07-22 | JA OLIVAR ENGINEERING DESIGN, CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | FIRE |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102366 | Carallangan ES | ALCALA | 1 | 1 | 2 | 1STY2CL | 3869401.2827 | 1 |  | Completed | 100% | [10 empty] | ONGOING/ compliance to VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1 | 1 | 3 | 1STY3CL | 5307755.7554 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102509 | Asassi ES | BAGGAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 579977.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102502 | Sta. Margarita West ES | BAGGAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 545932.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102653 | Capissayan Elementary School | GATTARAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 545932.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102664 | Tanglagan ES | GATTARAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 808067.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102898 | Casagan ES | SANTA ANA | 1 | 1 | 2 | 1STY2CL | 3821369.2801 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG/ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102899 | Casambalangan ES | SANTA ANA | 1 | 1 | 4 | 2 UNITS OF 1STY2CL | 7030500.1832 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY OMPONG/ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102902 | Kapannikian ES | SANTA ANA | 1 | 1 | 2 | 1STY2CL | 3712494.5201 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY OMPONG/ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102332 | Alinunu ES | ABULUG | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1692161.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102408 | Concepcion Elementary School | AMULUNG | 3 | 1 | 4 | 1STY4CL | 6791637.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102412 | Gabut ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102413 | GANGAUAN ES | AMULUNG | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102417 | Monte Alegre ES | AMULUNG | 3 | 1 | 5 | 1STY3CL & 1STY2CL | 8646857.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102436 | Nangalasauan ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 810920.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102441 | San Juan ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 785664.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102638 | Maddarulug Sur ES | ENRILE | 3 | 1 | 6 | 2UNITS-1STY3CL | 10147535.9354 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY OMPONG / TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102631 | Maracuru ES | ENRILE | 3 | 1 | 2 | 1STY2CL | 3672954.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102721 | Sta.Barbara Elementary School | IGUIG | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1164440.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102797 | Alitontong ES | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 825291.4 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102810 | Baliwag Elementary School | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 786475.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 155017 | Bauan E/S | PEÑABLANCA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 349536.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102812 | Bugatay ES | PEÑABLANCA | 3 | 1 | 3 | 1STY3CL | 5322410.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102801 | Lapi ES | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 739349.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102802 | Mangga ES | PEÑABLANCA | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1585443.73 | 1 |  | Completed | 100% | [10 empty] | ONGOING/ compliance to VO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 739936.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3 | 1 | 5 | 1STY5CL | 7882791.27 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102877 | Bantay ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 718499.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102871 | IRAGA ELEMENTARY SCHOOL | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1530030.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102885 | Lannig ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 742410.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102886 | Lingu ES | SOLANA | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 722670.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102873 | Malacabibi ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 798637.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102874 | Masin-San Pablo ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 699867.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102888 | Nabbotuan Elementary School | SOLANA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 805439.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 155050 | Pataya ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 688813.62 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102895 | Solana South CS | SOLANA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 362938.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102896 | Ubong ES | SOLANA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 787939.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102897 | Villa Salud ES | SOLANA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 805439.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102975 | Accusilian Elementary School | TUAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 615267.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102978 | Bagumbayan ES | TUAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 355493.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102958 | Bicok Elementary School | TUAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 784782.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102959 | Bugnay ELEMENTARY SCHOOL | TUAO | 3 | 1 | 3 | 1STY3CL | 5307755.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 44986 | 6.23 | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cagayan | 102982 | Cagumitan ES | TUAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 711424.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102960 | Culung ES | TUAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1388646.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102985 | Lallayug ES | TUAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 645557.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cagayan | 102972 | Sto. Tomas Elementary School | TUAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1067031.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 5556311.66 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cauayan City | 103209 | Amobocan ES | CITY OF CAUAYAN | 3 | 1 | 7 | 1STY3CL | 6296144.55 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cauayan City | 103180 | Andarayan-Bugallon ES | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 447616.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 103182 | Buyon ES | CITY OF CAUAYAN | 3 | 1 | 6 | 1STY3CL | 6244275.62 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cauayan City | 103184 | Casalatan ES | CITY OF CAUAYAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 952113.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 103185 | Cassap Fuera Elementary School | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 768173.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 3 | 1 | 74 | REPAIR OF CLASSROOMS | 4216845.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 74 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 323901 | Cauayan City NHS - Research Annex | CITY OF CAUAYAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 965520.72 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | YZK CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 103187 | DIPARICAO ELEMENTARY SCHOOL | CITY OF CAUAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 819485.28 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 300538 | Gappal NHS | CITY OF CAUAYAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 570773.7 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 155528 | Nagrumbuan ES - Annex | CITY OF CAUAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 466399.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 300567 | Pinoma NHS | CITY OF CAUAYAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 724294.42 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | YZK CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 103199 | Rogus ES | CITY OF CAUAYAN | 3 | 1 | 3 | 1STY3CL | 5556311.66 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Cauayan City | 103202 | Sinippil ES | CITY OF CAUAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 873835.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 300613 | Villa Concepcion HS | CITY OF CAUAYAN | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 881376.93 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | ES PUA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Cauayan City | 300614 | Villaluna NHS | CITY OF CAUAYAN | 3 | 1 | 16 | REPAIR OF CLASSROOMS | 1349321.89 | 1 |  | Completed | 100% |  |  |  |  | 2019-05-15 | 2019-05-23 | 2019-08-05 | 2019-08-08 | 2019-08-30 | GCPK CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103412 | Alibagu Elementary School | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 651366.96 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103390 | Cabeceria 24 ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 332555.57 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Camberwell Construction and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103392 | Cabeceria 27 ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Fragerr Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | City of Ilagan | 500087 | Gayong-Gayong Sur Integrated School | ILAGAN CITY (CAPITAL) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 468123.67 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 300545 | Ilagan Sports HS (INHS - Alibagu Annex) | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 638992.75 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Edpin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103424 | LULLUTAN ELEMENTARY SCHOOL | ILAGAN CITY (CAPITAL) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1685954.58 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Atlantic Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 500080 | Lupigue Integrated School (formerly Lupigue ES) | ILAGAN CITY (CAPITAL) | 1 | 1 | 26 | REPAIR OF CLASSROOMS | 3702586.81 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | Foref Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103370 | Morado ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 629880.89 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103406 | San Antonio ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 3791888.79 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | SMT Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 300583 | San Antonio Nat'l. Agro-Ind'l. & Voc'l. HS | ILAGAN CITY (CAPITAL) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 854958.12 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | City of Ilagan | 103383 | Villa Imelda ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 890751.71 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-07 | 2019-06-14 | 2019-07-09 | 2019-07-23 | 2019-08-05 | 4A's Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103146 | Candanum Elementary School | CABANGAN | 1 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103535 | Bicobian Elementary School | DIVILACAN | 1 | 1 | 3 | 1STY3CL | 6020589.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103547 | Dikaruyan Primary School | DIVILACAN | 1 | 1 | 2 | 1STY2CL | 4396305.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103554 | Divilacan Central School | DIVILACAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 517294.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103560 | Sapinit Primary School | DIVILACAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 712942.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103555 | Maconacon Central School | MACONACON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 869478.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300560 | Maconacon National High School | MACONACON | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3621461.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103558 | Reina Mercedes Elementary School | MACONACON | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 766325.08 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103534 | Alomanay ES | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1643929.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103536 | Bisag Elementary School | PALANAN | 1 | 1 | 6 | 1STY4CL | 8430539.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 155520 | Centro West Primary School | PALANAN | 1 | 1 | 6 | 1STY3CL | 7456736 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103538 | Culasi Elementary School | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1183386.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103539 | Dialawyao Elementary School | PALANAN | 1 | 1 | 4 | 1STY3CL | 6415803.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103540 | Dibewan Elementary School | PALANAN | 1 | 1 | 3 | 1STY3CL | 6020589.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103542 | Dibungko Primary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 395213.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103543 | Dibutarek Elementary School | PALANAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1653889.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103545 | Didiyan Elementary School | PALANAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1362588.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | NOT-IN-NSBI | Didiyan Elementary School Annex | PALANAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2251806.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103546 | Dikadyuan Elementary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 819901.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 155525 | Dimalicu-licu Primary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 529688.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103549 | Dimasari Elementary School | PALANAN | 1 | 1 | 7 | 1STY2CL | 6225448.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103550 | Dimatican Elementary School | PALANAN | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 395213.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103553 | Ditambali Elementary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1041574.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2521942.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103556 | Marikit Elementary School | PALANAN | 1 | 1 | 8 | 1STY4CL | 8705476.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103557 | Palanan Central School | PALANAN | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 1970292.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300564 | Palanan National High School | PALANAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1180855.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103559 | San Isidro Elementary School | PALANAN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2769537.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103561 | Taknalan Primary School | PALANAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1117478.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 342077 | Aurora Senior High School | AURORA | 2 | 1 | 30 | REPAIR OF CLASSROOMS | 469120.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300546 | Andabuen National High School | BENITO SOLIVEN | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 732000.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103526 | San Manuel Elementary School | NAGUILIAN | 2 | 1 | 3 | 1STY3CL | 5435561.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103638 | San Pedro-Villa Concepcion Elementary School | ROXAS | 2 | 1 | 3 | 1STY3CL | 5419811.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103720 | Mananao Elementary School | SAN MANUEL | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 564083.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103005 | Alicia Central School | ALICIA | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 5727263.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 659657.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 102994 | MH del Pilar Elementary School | ALICIA | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1101200.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 500023 | Sto. Niño Integrated School | ANGADANAN | 3 | 1 | 16 | REPAIR OF CLASSROOMS | 2112109.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103175 | Nueva Era Elementary School | CABATUAN | 3 | 1 | 3 | 1STY3CL | 5419811.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103487 | Luna Central School | LUNA | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 603963.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300575 | Reina Mercedes Vocational and Industrial School | REINA MERCEDES | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 949555.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 500015 | Dietban Integrated School | SAN GUILLERMO | 3 | 1 | 8 | 1STY3CL | 6376910.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103783 | Dagupan Elementary School | SAN MATEO | 3 | 1 | 3 | 1STY3CL | 5435561.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103787 | San Marcos Elementary School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1006060.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103779 | San Mateo North Central School | SAN MATEO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1006060.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300508 | Cagasat National High School | CORDON | 4 | 1 | 26 | REPAIR OF CLASSROOMS | 7047822.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103247 | Cordon South Central School-Main | CORDON | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 3657282.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300523 | Diadi Region High School | CORDON | 4 | 1 | 19 | REPAIR OF CLASSROOMS | 3975383.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300532 | Dona Josefa E. Marcos High School | CORDON | 4 | 1 | 14 | REPAIR OF CLASSROOMS | 5171378.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103250 | Gayong Elementary School | CORDON | 4 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103251 | Kakilingan Elementary School | CORDON | 4 | 1 | 6 | 2 UNITS OF 1STY3CL | 9953071.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103257 | Taringsing Elementary School | CORDON | 4 | 1 | 6 | 2 UNITS OF 1STY3CL | 9953071.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103259 | Turod Sur Elementary School | CORDON | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 2154361.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103261 | Villa Marzo Elementary School | CORDON | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1388590.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300526 | Dinapigue National High School | DINAPIGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 980047.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103306 | Arabiat Elementary School | ECHAGUE | 4 | 1 | 10 | 1STY3CL | 6568628.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103328 | Buneg Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 871754.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300529 | Don Mariano Marcos National High School | ECHAGUE | 4 | 1 | 14 | REPAIR OF CLASSROOMS | 3868697.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300533 | Dona Magdalena H. Gaffud HIgh School | ECHAGUE | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 5701423.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4 | 1 | 4 | 1STY4CL | 6686637.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 4 | 1 | 19 | REPAIR OF CLASSROOMS | 4929894.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103331 | Echague West Central School | ECHAGUE | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 2680456.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103291 | Gumbauan Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1963974.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103312 | Libertad Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 932908.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103295 | Malibago Elementary School | ECHAGUE | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2066443.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103313 | Nilumisu Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2190468.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103314 | Pangal Norte Elementary School | ECHAGUE | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1019388.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103318 | San Carlos Elementary School | ECHAGUE | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 799093.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103319 | San Felipe Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1457026.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103320 | San Juan Elementary School | ECHAGUE | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1414132.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103321 | San Manuel Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1482307.08 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103325 | Sta. Monica Elementary School | ECHAGUE | 4 | 1 | 2 | 1STY2CL | 3787305.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103323 | Sta. Ana Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1921483.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103324 | Sta. Maria Elementary School | ECHAGUE | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2476229.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103303 | Tuguegarao-Sto. Domingo Elementary School | ECHAGUE | 4 | 1 | 8 | REPAIR OF CLASSROOMS | 2072306 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300611 | Ugad High School | ECHAGUE | 4 | 1 | 30 | REPAIR OF CLASSROOMS | 5026636.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103326 | Villa Fermin Elementary School | ECHAGUE | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2376598.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103439 | A.C. Ruiz Elementary School | JONES | 4 | 1 | 5 | 1STY5CL | 8277774.82 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 103463 | Diarao Elementary School | JONES | 4 | 1 | 10 | REPAIR OF CLASSROOMS | 4573937.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1323613.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300555 | Jones Rural School - Main | JONES | 4 | 1 | 24 | REPAIR OF CLASSROOMS | 610988.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300600 | Sgt. Prospero Bello HS - Main | JONES | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 2795018.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103457 | Usol Elementary School | JONES | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1318267.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103599 | Gen. Aguinaldo ES - Main | RAMON | 4 | 1 | 3 | 1STY3CL | 5159304.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Isabela | 300572 | General Emilio Aguinaldo National High School | RAMON | 4 | 1 | 26 | REPAIR OF CLASSROOMS | 5109619.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 300574 | Raniag HIgh School | RAMON | 4 | 1 | 21 | REPAIR OF CLASSROOMS | 704142.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1253804.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 4 | 1 | 18 | 2 UNITS OF 1STY3CL | 15183576.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Nueva Vizcaya | 104187 | Abuyo ES | ALFONSO CASTAÑEDA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5259872.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 306207 | Abuyo National High School | ALFONSO CASTAÑEDA | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2880390.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 306207 | Abuyo National High School | ALFONSO CASTAÑEDA | 0 |  | 0 | REPAIR OF CLASSROOMS | 14989065.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300615 | Alfonso CastaÃ±eda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 7271745.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1145955.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 103987 | Cablahan Elementary School | AMBAGUIO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 9636832.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 103988 | DACLIG ELEMENTARY SCHOOL | AMBAGUIO | 0 | 1 | 1 | REPAIR OF CLASSROOMS | 342793.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 103914 | Canarem PS | ARITAO | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6682705.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 104021 | DIADI CENTRAL SCHOOL | DIADI | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1984210.4346 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 541074.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300625 | Carolotan High School | DUPAX DEL SUR | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6253511.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3833601.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300628 | Dupax del Sur NHS | DUPAX DEL SUR | 0 |  | 0 | REPAIR OF CLASSROOMS | 15169211.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 104078 | Biyoy ES | KASIBU | 0 | 1 | 2 | 1STY2CL | 4347951.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Nueva Vizcaya | 104100 | Paquet ES | KASIBU | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 868314.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300640 | NAPO-TUYAK HS | KAYAPA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 6206778 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 500097 | Dagupan Elementary School | QUEZON | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1058459.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 104158 | Maddiangat ES | QUEZON | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1516886.5775 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Nueva Vizcaya | 300644 | Quezon NHS | QUEZON | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1884076.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 2004722.84 | 1 | 2004202.15 | Completed | 100% | 2020-02-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-12-23 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104293 | Balagbag Elementary School | DIFFUN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1051009.85 | 1 | 920966.39 | Completed | 100% |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 300657 | Diffun HS | DIFFUN | 0 | 1 | 33 | REPAIR OF CLASSROOMS | 2744322.73 | 1 | 2439820.52 | Completed | 100% |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 500109 | Ifugao Village IS | DIFFUN | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1926593.7 | 1 | 1728766.59 | Completed | 100% |  |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-09-30 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104307 | Luttuad ES | DIFFUN | 0 | 1 | 2 | 1STY2CL | 3549295.68 | 1 | 2740548.39 | Completed | 100% | 2020-02-10 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-09-19 | 2019-11-12 | AGT Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Quirino | 500104 | San Antonio Integrated School | DIFFUN | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 1318056.95 | 1 | 1251820.47 | Completed | 100% | 2020-01-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-22 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104289 | Villa Pascua ES | DIFFUN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 930656.45 | 1 | 850056.35 | Completed | 100% | 2020-01-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-22 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 969299.97 | 1 | 800369.21 | Completed | 100% | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 365919.14 | 1 | 341435.96 | Completed | 100% | 2020-02-21 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-12-23 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104378 | Salvacion ES | SAGUDAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 621313.58 | 1 | 498503.34 | Completed | 100% | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Quirino | 104379 | Sto. Tomas ES | SAGUDAY | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 1040150.28 | 1 | 914949.61 | Completed | 100% | 2020-01-24 |  |  |  | 2019-07-25 | 2019-08-01 | 2019-08-13 | 2019-11-06 | 2019-11-25 | PROLINE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103824 | Ambalatungan ES | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 338916.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 500936 | Balintocatoc Integrated School | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 724334.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103811 | Baptista Village ES | CITY OF SANTIAGO | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 300638.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103812 | Batal ES | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 863961.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103825 | Buenavista Elementary School | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 608862.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 300505 | Cabulay High School | CITY OF SANTIAGO | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 1820821.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103837 | Calaocan ES | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 838560.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103813 | Divisoria ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 416018.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 300528 | Divisoria High School | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 209830.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 101253.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103827 | Dubinan ES | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2167256.36 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103814 | Luna ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 507769.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY2CL | 4132677.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103816 | MALINI ELEMENTARY SCHOOL | CITY OF SANTIAGO | 4 | 1 | 5 | 1STY3CL | 5742135.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103817 | Nabbuan ES | CITY OF SANTIAGO | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 415103.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103818 | Nagassican Elementary School | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 1261468.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103828 | Patul Elementary School | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1066614.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 306124 | Patul National High School | CITY OF SANTIAGO | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 804175.4 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 300578 | Rizal National High School | CITY OF SANTIAGO | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 1754766.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103838 | ROSARIO ELEMENTARY SCHOOL | CITY OF SANTIAGO | 4 | 1 | 11 | REPAIR OF CLASSROOMS | 1063138.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 325203 | ROSARIO NHS | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 181214.05 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103819 | Sagana Elementary School | CITY OF SANTIAGO | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 306395.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 325202 | Sagana National High School | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 108318.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 500937 | Salvador Integrated School | CITY OF SANTIAGO | 4 | 1 | 10 | 1STY3CL | 5912801.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103829 | San Isidro ES | CITY OF SANTIAGO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 693752.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4 | 1 | 38 | REPAIR OF CLASSROOMS | 1287298.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 395389.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103822 | Santiago East Central School | CITY OF SANTIAGO | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 809218.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 | 1 | 21 | 1STY5CL | 8969133.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL | 5229005.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 | 1 | 3 | 1STY2CL | 3940310.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4 |  | 3 | 1STY3CL | 5307755.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region II | Santiago City | 103841 | Sta. Rosa ES | CITY OF SANTIAGO | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 816028.56 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region II | Santiago City | 103833 | Villa Gonzaga ES | CITY OF SANTIAGO | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 895454.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY ROSITA |  |  |  | REPAIR | Completed
QRF 2019 | Region III | Nueva Ecija | 105656 | San Gregorio ES | RIZAL | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 3156045.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | CONSTRUCTION OF SLOPE PROTECTION |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 309402 | Bucayao National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 668442 | 1 | 658416 | Completed | 100% | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111573 | Canubing I ES | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1554987 | 1 | 1544102 | Completed | 100% | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111574 | Canubing II ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1025876 | 1 | 1015617 | Completed | 100% | 11/28/2019 | 11/28/2019 |  | 2019-06 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111560 | Gutad ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1405062 | 1 | 1394529 | Completed | 100% | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111576 | Masipit ES | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1952400 | 1 | 1941661 | Completed | 100% | 12/04/2019 | 12/04/2019 |  | 2019-05 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | CMSEL Construction & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1109501 | 1 | 1098960 | Completed | 100% | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111577 | Patas ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1511065 | 1 | 1500487 | Completed | 100% | 12/04/2019 | 12/04/2019 |  | 2019-05 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | CMSEL Construction & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Calapan City | 111569 | Sta. Cruz ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1481854 | 1 | 1471481 | Completed | 100% | 12/18/2019 | 02/01/2020 |  | 2019-07 | 07/08/2019 | 07/17/2019 | 08/06/2019 | 08/23/2019 | 08/30/2019 | Karangyan Builders & Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region IV-B | Palawan | 111003 | Funda Elementary School | CUYO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 780144.31 | 1 | 779259.89 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY SAMUEL (11.22.2018) |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112066 | Biyong Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 640582.05 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112067 | Bolo Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 608083.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 172502 | Lourdes Elementary School | TIWI | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 632989.47 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112073 | Mayong Elementary School | TIWI | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 404054.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112077 | Putsan Elementary School | TIWI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 778044.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 301880 | Tiwi Agro-Industrial School | TIWI | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 2355385.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111663 | Bongalon Elementary School | DARAGA (LOCSIN) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1344607.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 309518 | Kilicao High School | DARAGA (LOCSIN) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1832632.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111673 | Maroroy ES | DARAGA (LOCSIN) | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 455094.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 301809 | San Vicente Grande High School | DARAGA (LOCSIN) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2332171.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111704 | Villahermosa Elementary School | DARAGA (LOCSIN) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2878059.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111900 | Manumbalay Elementary School | MANITO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2712324.78 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 112041 | Nagcalsot Elementary School | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3029604.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111787 | Bonbon Elementary School | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 947712.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111791 | Caguscos Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 459045.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111762 | Libon East Central School | LIBON | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3213751.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 309504 | Rawis High School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 755548.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111802 | Sagrada Familia Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 315926.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 500155 | San Agustin Integrated School | LIBON | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1371797.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111779 | San Vicente Elementary School | LIBON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 456804.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111780 | Sta. Cruz Elementary School | LIBON | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2070117.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111782 | West Carisac Elementary School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 740098.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Albay | 111971 | Don Jose Pavia Central School | PIO DURAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 687525.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112116 | Francisco V. Aler ES | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1218019.62 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4700864.88 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309614 | Magsaysay National High School | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1780252.76 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2406465.85 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112129 | Villa Aurora ES | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 3862545.49 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112149 | Calero ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1171604.8 | 1 | 1043690.82 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112150 | Calogcog ES | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2087168.86 | 1 | 1162707.13 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112170 | Cresencia B. Enverga ES (Sta. Cruz ES) | JOSE PANGANIBAN | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3536970.92 | 1 | 1017159.47 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1465034 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309619 | Gawad Kalinga HS | JOSE PANGANIBAN | 1 |  | 3 | REPAIR OF CLASSROOMS | 1431252.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112151 | Jose Panganiban ES | JOSE PANGANIBAN | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4269793.61 | 1 | 3163194.92 | Completed | 100% | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112163 | Larap ES | JOSE PANGANIBAN | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3170013.15 | 1 | 1196211.45 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112154 | Osmena ES (Lukban ES) | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1254934.09 | 1 | 1948834.94 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112166 | San Isidro ES | JOSE PANGANIBAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1981255.73 | 1 | 1061960.82 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112158 | Segundo Aguirre (Sta Rosa Norte.) | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1392514.58 | 1 | 3525952.5 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112172 | Sta. Milagrosa ES | JOSE PANGANIBAN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1352545.62 | 1 | 967137.57 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112173 | Tawig ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1017159.47 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112199 | Bagong Silang II ES | LABO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2038285.57 | 1 | 1254750.45 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112200 | Bagong Silang III ES | LABO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2038285.57 | 1 | 1309904.74 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301893 | Daguit NHS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 5733405.76 | 1 |  | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112180 | Don Miguel Lukban ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1274608.94 | 1 | 1017159.47 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112181 | E. Obmana ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1187452.91 | 1 | 1982137.28 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112212 | Kanapawan ES | LABO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2450236.7 | 1 | 1235407.56 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 6018846.22 | 1 |  | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112190 | Malasugui ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1213812.24 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 500635 | Palali Integrated School | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2406465.85 | 1 |  | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112194 | Pampang ES | LABO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1254934.09 | 1 | 1960342.34 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112195 | Severino Francisco Elementary Sch. | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 1465034 | 1 | 1384603.19 | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN. MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 3470256.44 | 1 |  | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 5877100.25 | 1 |  | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1 |  | 4 | REPAIR OF CLASSROOMS | 1563467.03 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112246 | Dalnac ES | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1353013.75 | 1 | 1184532.47 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 2118668.86 | 1 | 1205924.25 | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1 |  | 3 | REPAIR OF CLASSROOMS | 1275934.09 | 1 | 1184406.13 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2462463.07 | 1 | 5231752.85 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GOLDEN FLEECE CONSTRUCTION AND SUPPLY INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112279 | Bulala Elementary School | SANTA ELENA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 4872710.06 | 1 | 1146074.8 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112280 | Dygico ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1208452.91 | 1 | 2277001.9 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112281 | Earth'S Bounty ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1187452.91 | 1 | 2617131.57 | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301917 | Leocadio Alejo Entienza HS | SANTA ELENA | 1 | 1 | 0 | REPAIR OF CLASSROOMS | 3491256.44 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | BULLET CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112282 | M. Hebrado ES | SANTA ELENA | 1 | 1 | 13 | REPAIR OF CLASSROOMS | 5248371.39 | 1 | 2431393.54 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173011 | Maulawin ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1622046.91 | 1 | 1196766.21 | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173007 | Patag Ilaya ES | SANTA ELENA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1759004.21 | 1 | 2280114.95 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | YAKAL CONSTRUCTION AND SUPPLY | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301913 | Rizal NATIONAL HIGH SCHOOL | SANTA ELENA | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 5293807.27 | 1 |  | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | AVZ CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112089 | Guinatungan ES | BASUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1228127.76 | 1 | 1203796.49 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112101 | Plaridel ES | BASUD | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 975804.32 | 1 | 1220029.49 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1345218.15 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2 |  | 0 | REPAIR OF CLASSROOMS | 1847862.76 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 309608 | Tuaca HS | BASUD | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 4012269.69 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112130 | A. Pabico Abordo ES | DAET (Capital) | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4148623.17 | 1 | 1290352.09 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112133 | Bagasbas ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1340014.58 | 1 | 1221587.09 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301891 | Camarines Norte National HS | DAET (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 227523.06 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112135 | Dogongan ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227594.64 | 1 | 1798122.15 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112146 | Goito Pimentel ES | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227594.64 | 1 | 1145879.22 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1942607.32 | 1 | 1180521.05 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1207426.77 | 1 | 969616.54 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112224 | F. P. Ibasco ES | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1387861.78 | 1 | 2375085.7 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112225 | Gaboc Elementary School | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1279601.61 | 1 | 812566.4 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 4269793.61 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | GREATWALL ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227101.61 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112270 | S. DELOS SANTOS ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 829119.55 | 1 | 2247907.29 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173003 | Cabanbanan ES | SAN VICENTE | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 881619.55 | 1 | 1377953.48 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112277 | V. Ricafrente ES | SAN VICENTE | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1208452.91 | 1 | 2689235.23 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 173004 | Cahabaan Elementary School | TALISAY | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 494485.89 | 1 | 1202621.87 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112290 | Gabon ES | TALISAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2268004.32 | 1 | 2235026.42 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1389994.15 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112295 | Sta. Elena Elementary School | TALISAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2709144.85 | 1 | 1716306.77 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112296 | Talisay ES | TALISAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1155952.91 | 1 | 863518.68 | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112299 | Cagbalogo ES | VINZONS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2290708.27 | 1 | 493657.3 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112300 | Calangcawan Norte ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2673117.76 | 1 | 1757608.03 | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112300 | Calangcawan Norte ES | VINZONS | 2 |  | 3 | 1STY3CL | 6390999.24 | 1 | 1618051.92 | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | FIRE DAMAGED |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Camarines Norte | 112303 | El Trino P. Zenarosa ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2486217.88 | 1 | 1515933.88 | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112312 | P. Barbin ES | VINZONS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2236866.82 | 1 | 5280653.42 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1717706.58 | 1 | 1318031.15 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | WCVC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2337557.23 | 1 |  | Completed | 100% | 2020-03-18 | [7 empty] | 2019-12-09 | RIDERSCORNER CONSTRUCTION & GEN MDSE. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112577 | Del Gallego CS | DEL GALLEGO | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 5052394.14 | 1 | 5040300 | Completed | 100% | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112580 | Mansalaya ES | DEL GALLEGO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1696694.81 | 1 | 2970300 | Completed | 100% | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112581 | Palaspas ES | DEL GALLEGO | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2978361.34 | 1 | 2645600 | Completed | 100% | 2/14/2020 |  |  | 2019-08-022 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112586 | Sinuknipan Elementary School | DEL GALLEGO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2650647.45 | 1 | 1693600 | Completed | 100% | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112587 | Sta. Rita ES | DEL GALLEGO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1716496.65 | 1 | 1714400 | Completed | 100% | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112733 | Bel-Cruz ELementary School | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2517490.74 | 1 | 2515400 | Completed | 100% | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2801981.36 | 1 | 2795343.35 | Completed | 100% | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2601739.46 | 1 | 2595644.37 | Completed | 100% | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112945 | Apad ES | RAGAY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2880755.75 | 1 | 2878700 | Completed | 100% | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112960 | Liboro Elementary School | RAGAY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2885756.65 | 1 | 2880750 | Completed | 100% | 2/14/2020 |  |  | 2019-08-023 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/17/2019 | JUKAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113051 | Alteza ES | SIPOCOT | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1197403.6 | 1 | 1197350 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113084 | Gaongan ES | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2769937.55 | 1 | 2763292.18 | Completed | 100% | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113089 | Manangle ES | SIPOCOT | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2668679.08 | 1 | 2662334.39 | Completed | 100% | 2/13/2020 |  |  | 2019-08-024 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | AVZ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3416864.94 | 1 | 3416850 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113091 | Sipocot South CS | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2795099.35 | 1 | 2795090 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302068 | Villazar National High School | SIPOCOT | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 4582486.95 | 1 | 4576555 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112775 | Cagbunga Elementary School | GAINZA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1024763.62 | 1 | 1000150 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112672 | Bahay ES | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1049769.31 | 1 | 1048300 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112677 | Fundado ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1624163.21 | 1 | 1622160 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112712 | Loba-Loba ES | LIBMANAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2534373.47 | 1 | 2532370 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301990 | Malansad Nuevo High School | LIBMANAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3709186.47 | 1 | 3707185 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112698 | Umalo ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1884869.4 | 1 | 1882870 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112785 | Milaor CS | MILAOR | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1390117.26 | 1 | 1358100 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301999 | Milaor National High School | MILAOR | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 753825.02 | 1 | 736400 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1736993.21 | 1 | 1697000 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112792 | Baliuag Nuevo ES | MINALABAC | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2246632.47 | 1 | 2194900 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112793 | Baliuag Viejo ES | MINALABAC | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 934131.39 | 1 | 912600 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301981 | Hobo National High School | MINALABAC | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2790245.88 | 1 | 2788700 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112867 | Burabod ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1724595.88 | 1 | 1723100 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112870 | Del Rosario ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1721854.62 | 1 | 1720300 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309723 | Del Rosario National HS | PAMPLONA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 484473.89 | 1 | 482900 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112876 | San Ramon ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1758810.84 | 1 | 1757300 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112877 | San Vicente ES | PAMPLONA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1049769.31 | 1 | 1048200 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112879 | Tambo ES | PAMPLONA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 693848.99 | 1 | 692300 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-027 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112880 | Tampadong ES | PAMPLONA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1785525.4 | 1 | 1784520 | Completed | 100% | Feb. 12, 2020 |  |  | 2019-08-028 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113009 | San Fernando CS | SAN FERNANDO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2773608.86 | 1 | 2679800 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113010 | San Joaquin ES | SAN FERNANDO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 765775.82 | 1 | 748100 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112759 | Bombon Central School | BOMBON | 3 | 1 | 17 | REPAIR OF CLASSROOMS | 4853831.86 | 1 | 4826563.36 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 659479.39 | 1 | 655550 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173511 | Binaliw Elem School | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 553756.04 | 1 | 543750 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112471 | Calabanga Central Division Pilot School | CALABANGA | 3 | 1 | 19 | REPAIR OF CLASSROOMS | 4399009.72 | 1 | 4372482.21 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112472 | Calabanga West Central School | CALABANGA | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1481128.28 | 1 | 1471120 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301983 | Jose De Villa NHS | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3134495.24 | 1 | 3024495 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112482 | Manguiring ES | CALABANGA | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1914348.56 | 1 | 1890350 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 3277321.56 | 1 | 3167320 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112483 | Pagatpat ES | CALABANGA | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1624296.92 | 1 | 1614290 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-029 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112490 | Sabang ES | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1241846.22 | 1 | 1235923.21 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112495 | Taculod ES | CALABANGA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1067116.17 | 1 | 1048904.2 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-030 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JANSHA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112503 | Tarosanan-San Francisco Elementary School | CAMALIGAN | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 4319050.34 | 1 | 4250000 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112506 | Canaman CS | CANAMAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2972748.71 | 1 | 2900800 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301995 | Mangayawan High School | CANAMAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1911571.91 | 1 | 1850570 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112855 | La Purisima Nuevo ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 822023.59 | 1 | 817000 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112856 | May-Ogob ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 870256.1 | 1 | 865200 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112859 | Ocampo Central School | OCAMPO | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3989414.46 | 1 | 3755200 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112861 | San Antonio ES | OCAMPO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 811415.33 | 1 | 801400 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112920 | Binanuaanan Norte ES | PILI (Capital) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 750678.78 | 1 | 745650 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1790016.53 | 1 | 1785000 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112923 | Cabocladan Elementary School | PILI (Capital) | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 428408.73 | 1 | 423400 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112932 | Pili Central School | PILI (Capital) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1091952.09 | 1 | 1086900 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302017 | Pili NHS, Pili - Gov.Mariano E. Villafuerte Annex HS | PILI (Capital) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1113508.65 | 1 | 1050510 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-031 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | ADJED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112941 | Tagbong ES | PILI (Capital) | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2367678.48 | 1 | 2321300 | Completed | 100% | 2/13/2020 |  |  | 2019-08-032 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112564 | Pili-Tabiguian Elementary School | CARAMOAN | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3046636.88 | 1 | 3044608.79 | Completed | 100% | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112568 | San Roque ES | CARAMOAN | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2514615.34 | 1 | 2511634.48 | Completed | 100% | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112571 | Tabiguian ES | CARAMOAN | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 3057822.13 | 1 | 3052798.95 | Completed | 100% | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112592 | Burabod Elementary School | GARCHITORENA | 4 | 1 | 8 | REPAIR OF CLASSROOMS | 2194961.56 | 1 | 2193960 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112593 | Cagamutan PS | GARCHITORENA | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1294057.67 | 1 | 1293050 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 500468 | Harrison Integrated School | GARCHITORENA | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2296000.78 | 1 | 2293962.25 | Completed | 100% | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112604 | Pambuhan Elementary School | GARCHITORENA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 888262.2 | 1 | 887260 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112615 | Balaynan Elementary School | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 846262.2 | 1 | 845200 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112617 | Cagaycay ES | GOA | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 527787.33 | 1 | 527700 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112619 | Digdigon ES | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 903123.65 | 1 | 903100 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112620 | Gimaga ES | GOA | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1430014.43 | 1 | 1425000 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301976 | Pinaglabanan High School | GOA | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3030198.81 | 1 | 2937400 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112634 | Tabgon ES | GOA | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 3940509.41 | 1 | 3920100 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112637 | Taytay Elementary School | GOA | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 961554.34 | 1 | 951700 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112652 | Amoguis Community School | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1405655.67 | 1 | 1404650 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112657 | Dahat Elementary School | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1050121.96 | 1 | 1048109.59 | Completed | 100% | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112639 | Del Carmen ES | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 478013.75 | 1 | 473200 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112641 | Himanag Elementary School | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 540810.98 | 1 | 535400 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112642 | Lagonoy North CS | LAGONOY | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2496027.78 | 1 | 2483800.82 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112662 | Manamoc ES | LAGONOY | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 527787.33 | 1 | 523910.69 | Completed | 100% | Feb. 13, 2020 |  |  | 2019-08-037 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | SEVEN R |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112644 | Mapid ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1531536.31 | 1 | 1514130.45 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112645 | Olas ES | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 956027.49 | 1 | 936847.28 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112646 | Paghaluban Community School | LAGONOY | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1052567.61 | 1 | 1029643.33 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112647 | Pagsimbugan Elementary School | LAGONOY | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1998437.51 | 1 | 1979093.48 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 3150426.74 | 1 | 3149420 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112666 | San Rafael-Agpo ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1231057.67 | 1 | 1230050 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112650 | Sta. Cruz ES | LAGONOY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1466625.85 | 1 | 1449530.78 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309715 | Nato National High School | SAGÑAY | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 2089578.46 | 1 | 2085500 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112993 | Turague ES | SAGÑAY | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 820156.99 | 1 | 820100 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113015 | Bahay PS | SAN JOSE | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 1055574.66 | 1 | 1045000 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-034 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173518 | Calawit Community School | SAN JOSE | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 506506.63 | 1 | 498199.2 | Completed | 100% | Feb. 11, 2020 |  |  | 2019-08-035 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113045 | Siruma Central School | SIRUMA | 4 | 1 | 1 | REPAIR OF CLASSROOMS | 472763.75 | 1 | 471763.75 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302048 | Siruma NHS | SIRUMA | 4 | 1 | 9 | REPAIR OF CLASSROOMS | 4122564.33 | 1 | 4121564.33 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173535 | Consocep E/S | TIGAON | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 1428908.1 | 1 | 1427900 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113111 | Vinagre Elementary School | TIGAON | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2115357.17 | 1 | 2110300 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-033 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | P.R. HIZO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113134 | Bagacay ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1405126.53 | 1 | 1389993.54 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113114 | Banga Elementary School | TINAMBAC | 4 | 1 | 7 | REPAIR OF CLASSROOMS | 2021827.6 | 1 | 1995484.14 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301941 | Banga HS | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1393705.56 | 1 | 1392705.56 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113116 | Bataan ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1266932.61 | 1 | 1248742.14 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113137 | Buenavista ES | TINAMBAC | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 3130697.18 | 1 | 3124697.77 | Completed | 100% | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113120 | Magsaysay ES | TINAMBAC | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 870063.95 | 1 | 869063.95 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113121 | Malibtong ES | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1233440.52 | 1 | 1213670.2 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113124 | PAG-ASA ELEMENTARY SCHOOL | TINAMBAC | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1882050.04 | 1 | 1855413.24 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113130 | San Ramon ES | TINAMBAC | 4 | 1 | 5 | REPAIR OF CLASSROOMS | 2679973.53 | 1 | 2655108.73 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-038 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | CPR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113133 | TAMBANG CENTRAL SCHOOL | TINAMBAC | 4 | 1 | 15 | REPAIR OF CLASSROOMS | 6255858.59 | 1 | 6243870.37 | Completed | 100% | Feb.28, 2020 |  |  | 2019-08-039 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113150 | Tierra Nevada Elementary School | TINAMBAC | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 2460982.63 | 1 | 2459982.63 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 113152 | Tinambac South CS II | TINAMBAC | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1319009.93 | 1 | 1318009.93 | Completed | 100% | March 5, 2020 |  |  | 2019-08-040 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1687934.67 | 1 | 1659566.02 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112318 | Antipolo Elementary School | BAAO | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1889000 | 1 | 1859467.88 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112319 | Baao Central School | BAAO | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2291158.64 | 1 | 2290000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112323 | Caranday Elementary School | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1092000 | 1 | 1090182.33 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | NOT-IN-NSBI | Caranday High School (IYAGAN Annex) | BAAO | 5 | 1 | 3 | 1STY3CL | 5753304.36 | 1 | 5742990 | completed | 100% | Jan. 12, 2020 |  |  | 2019-08-021 | 2019-08-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/14/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | completed
QRF 2019 | Region V | Camarines Sur | 301956 | Caranday HS | BAAO | 5 | 1 | 0 | REPAIR OF CLASSROOMS | 17607006.52 | 1 | 17595555 | Completed | 100% | March 19, 2020 |  |  | 2019-08-047 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112335 | San Isidro-Santa Teresita ES | BAAO | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2147336.22 | 1 | 2145400 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112342 | Tapol Elementary School | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 691505.84 | 1 | 690386.49 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112343 | Bagong Lipunan ES | BALATAN | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1387593.38 | 1 | 1386593.38 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1979737.06 | 1 | 1976488.18 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112355 | PARARAO E/S | BALATAN | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1455898.23 | 1 | 1454600 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302014 | Pararao High School | BALATAN | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 720646.28 | 1 | 719488.18 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112356 | Pulang Daga ES | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2114536.93 | 1 | 2109500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112358 | Santiago Elementary School | BALATAN | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 336440.23 | 1 | 336400 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112362 | ATIPOLO ELEM. SCHOOL | BATO | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1357511.28 | 1 | 1357000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173546 | Del Rosario PS | BATO | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 158446.28 | 1 | 158180.34 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112374 | Mangga Elementary School | BATO | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 325075.5 | 1 | 325000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112381 | Salvacion ES | BATO | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1142712.86 | 1 | 1140801.75 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 585416.76 | 1 | 584472.54 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112390 | Buhi Central School | BUHI | 5 | 1 | 15 | REPAIR OF CLASSROOMS | 4978478.38 | 1 | 4973400 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173523 | Buhi SPED CENTER | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 924784.84 | 1 | 923235.52 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 309709 | Buhi SPED Integrated School | BUHI | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 173510.42 | 1 | 172510.42 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112392 | Burocbusoc ES | BUHI | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2418082.87 | 1 | 2413100 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 173543 | Caloocan Elementary School | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 679113.59 | 1 | 679000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112398 | Ibayugan ES | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1042944.22 | 1 | 1042000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112399 | Igbac ES | BUHI | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 348926.29 | 1 | 347926.29 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112400 | Ipil Elementary School | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1150416.53 | 1 | 1149400 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112401 | Iraya lementary School | BUHI | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 1817395.3 | 1 | 1816395 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112422 | Penafrancia ES (Tawagan ES) | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1308509.3 | 1 | 1306357.83 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112415 | San Vicente Elementary School | BUHI | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2542948.39 | 1 | 2540500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112416 | Sta. Cruz Elementary School | BUHI | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1479174.58 | 1 | 1477800 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1927477.43 | 1 | 1895771.4 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112420 | Sto. Nino PS | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 316434.81 | 1 | 316400 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112421 | Tambo ES | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 671508.02 | 1 | 671500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112426 | Balaogan ES | BULA | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2862403.54 | 1 | 2861403.54 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301938 | Balaogan National High School | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1077462.97 | 1 | 1077000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112427 | Bula Central School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1569845.52 | 1 | 1568845.52 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 13 | REPAIR OF CLASSROOMS | 4127314.05 | 1 | 4057987.41 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 533882.86 | 1 | 533880 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112428 | Caorasan ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 743489.18 | 1 | 742489.18 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 953826.55 | 1 | 952251.72 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112432 | Felipe P. Panton Elementary School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1758856.29 | 1 | 1757300 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112438 | Lopez Palsong Elementary School | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 892096.25 | 1 | 891250 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112440 | Macalinao Elementary School | BULA | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2111991.24 | 1 | 2110991.24 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 470921.8 | 1 | 470144.07 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112445 | Panoypoyan ES | BULA | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 309642.87 | 1 | 309600 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112450 | San Jose Elementary School | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 679511.83 | 1 | 679500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112451 | San Ramon Elementary School | BULA | 5 | 1 | 1 | REPAIR OF CLASSROOMS | 436590.03 | 1 | 436500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112453 | Sto. Domingo Elementary School | BULA | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2453513.17 | 1 | 2450000 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112833 | Don Telesforo Llorin ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1037889.24 | 1 | 1020464.09 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1321850.92 | 1 | 1299540.35 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112836 | Madawon ES | NABUA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 727834.25 | 1 | 726834.25 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 997092.07 | 1 | 995433.56 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Camarines Sur | 112839 | Nierva ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 852697.62 | 1 | 852600 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113292 | Pagsangahan ES | SAN MIGUEL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 5065398.16 | 1 | 8176194.98 | Completed | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113294 | Paraiso B ES | SAN MIGUEL | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 1910446.83 | 1 |  | Completed | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Catanduanes | 113332 | Summit ES | VIGA | 0 | 1 | 0 | REPAIR OF CLASSROOMS | 4082974.42 | 1 |  | Completed | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114429 | Antipolo ES | IRIGA CITY | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2797256.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114418 | Don Lazaro Madara Memorial School | IRIGA CITY | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2042400.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114446 | La Anunciacion ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2398188.55 | 1 | 2773643.61 | Completed | 100% | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 302251 | Rinconada National Technical Vocational School | IRIGA CITY | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 5190953.21 | 1 | 1727402.25 | Completed | 100% | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114423 | San Francisco ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2268340.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114425 | San Jose ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2393236.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114451 | San Juan ES | IRIGA CITY | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2354069.78 | 1 | 2764042.66 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114439 | San Vicente Norte ES | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 774176.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114440 | Sta. Cruz Norte ES | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1472741.58 | 1 | 2078919.98 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114440 | Sta. Cruz Norte ES | IRIGA CITY | 5 |  | 0 | REPAIR OF CLASSROOMS | 6093347.94 | 1 | 1089542.18 | Completed | 100% | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Iriga City | 114441 | Sta. Isabel ES | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1285568.78 | 1 | 1205736.73 | Completed | 100% | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 4356804.44 | 1 | 2586399.61 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 310201 | Arimbay High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 501884.42 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114465 | Bagacay ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1285281.17 | 1 | 1360741.97 | Completed | 100% | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114486 | Bagong Abre ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 949023.4 | 1 | 1240697.63 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 653402.01 | 1 | 2880113.11 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114468 | Bariis ES | LEGAZPI CITY (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 1208542.05 | 1 | 2357636.09 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114475 | Bitano ES | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 1512240.5 | 1 | 2548007.13 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114469 | Buenavista ES | LEGAZPI CITY (Capital) | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 1508542.05 | 1 | 1508957.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114488 | Buyoan ES | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2527115.33 | 1 | 1544321.83 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114470 | Cagbacong Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1285281.17 | 1 | 638471.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1106728.09 | 1 | 1066699.08 | Completed | 100% | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 1308542.05 | 1 | 928399.95 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 832005.23 | 1 | 1228432.13 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 310202 | Legazpi City Science High School | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 435005.25 | 1 | 5290754.91 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114462 | Mabinit ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1106728.09 | 1 | 2492003.41 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 647539.29 | 1 | 698792.93 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 805145.35 | 1 | 1270935.32 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City |  | Pag-asa National High School (Main & Annex) | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2752009.27 | 1 | 5512411.59 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | St. Bernardine Construction and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 302263 | Pawa High School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 351884.42 | 1 | 3314638.49 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114493 | Rawis ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2652009.27 | 1 | 1441100.27 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1116728.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114495 | San Roque Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073399.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 260910.17 | 1 | 4045105.42 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1410203.52 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 500169 | Taysan Resettlement Integrated School | LEGAZPI CITY (Capital) | 2 |  | 0 | REPAIR OF CLASSROOMS | 1208542.05 | 1 | 6062075.37 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | A.E. Compuesto Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Legaspi City | 114484 | Victory Village Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 462396.98 | 1 | 1379386.62 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 201-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1222811.93 | 1 | 1205736.73 | Completed | 100% | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 3 | 1STY3CL | 5663811.66 | 1 | 5806283.41 | Completed | 100% | 2020-06-25 |  | 2019-INFRA-02 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-25 | J.Purisima Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3 | 1 | 2 | 1STY2CL | 3836305.68 | 1 | 3992246.74 | Completed | 100% | 2020-02-12 |  | 2019-INFRA-03 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 231003 | Batang ES, Tobgon Ext | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1374903.28 | 1 | 2492003.41 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111838 | Cabarian ES | CITY OF LIGAO | 3 | 1 | 14 | 1STY3CL | 8467935.21 | 1 | 5609871.56 | Completed | 100% | 2020-03-12 |  | 2019-INFRA-01 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Ligao City | 111842 | Francia ES | CITY OF LIGAO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2784439.41 | 1 | 2773643.61 | Completed | 100% | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231002 | Macalidong ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2512773.31 | 1 | 2586399.61 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231006 | Macalidong ES, Quiasa Ext. | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1287472.29 | 1 | 2357636.09 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111846 | Maonon ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1747067.95 | 1 | 2764042.66 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111823 | Nabonton ES | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2091230.49 | 1 | 2078919.98 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 231004 | Nabonton ES, Buga Ext. | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2385229.15 | 1 | 1360741.97 | Completed | 100% | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111849 | San Vicente ES | CITY OF LIGAO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2900461.96 | 1 | 1727402.25 | Completed | 100% | 2020-02-26 |  | 2019-INFRA-04 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | Cam Sur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111829 | Tambo ES | CITY OF LIGAO | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1104418.38 | 1 | 1089542.18 | Completed | 100% | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Ligao City | 111853 | Tula-Tula Grande ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2615795.68 | 1 | 2880113.11 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113569 | ALBASAN ELEMENTARY SCHOOL | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1535207.42 | 1 | 1508957.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 302135 | Felixberto Del Rosario, Sr. Mem. HS | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1461094.49 | 1 | 1441100.27 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 174510 | Gaway-Gaway ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1255766.83 | 1 | 1240697.63 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113579 | Imelda ES | CLAVERIA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 648194.34 | 1 | 638471.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 309935 | MABABANGBAYBAY NHS | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1030957.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113589 | Peñafrancia ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1080300.61 | 1 | 1066699.08 | Completed | 100% | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113590 | Quezon ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 942538.02 | 1 | 928399.95 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 302126 | Tito R. Espinosa Memorial National Agricultural School | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1567263.52 | 1 | 1544321.83 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113916 | Gemino Elementary School | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1243352.36 | 1 | 1228432.13 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113920 | Laurente ES | SAN PASCUAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 706565.15 | 1 | 698792.93 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113921 | Lukban ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1288035.77 | 1 | 1270935.32 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113906 | San Rafael E/S | SAN PASCUAL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2584185.74 | 1 | 2548007.13 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-022 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113936 | Sta. Cruz ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1398568.01 | 1 | 1379386.62 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 201-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113719 | Bangad Elementary School | MILAGROS | 2 | 1 | 2 | 1STY2CL | 4421535.5 | 1 | 4397888.77 | Completed | 100% | 2020-01-08 | Mar. 2020 | INFRA 2019-07-006 | 2019-09-018 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2 | 1 | 4 | 1STY4CL | 8316428.43 | 1 | 8294796.29 | Completed | 100% | 2020-03-08 | Mar. 2020 | INFRA 2019-07-007 | 2019-09-019 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 113713 | Tigbao Elementary School | MILAGROS | 2 | 1 | 2 | 1STY2CL | 4521131.29 | 1 | 4498525.63 | Completed | 100% | 2020-01-08 | Mar. 2020 | INFRA 2019-07-005 | 2019-09-017 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-08-23 | 2019-10-10 | GACT Ent. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Masbate | 113790 | Catoogan PS | PALANAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1029220.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Masbate | 113790 | Catoogan PS | PALANAS | 3 |  | 2 | 1STY2CL | 5583444.04 | 1 | 5562672.2 | Completed | 100% | 2020-03-10 |  | INFRA 2019-07-008 | 2019-09-020 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region V | Naga City | 302267 | Concepcion PequeÃ±a National High School | NAGA CITY | 3 | 1 | 30 | REPAIR OF CLASSROOMS | 7131597.33 | 1 | 5512411.59 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | St. Bernardine Construction and Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 176502 | Grand View Elementary School | NAGA CITY | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 6082736.85 | 1 | 6062075.37 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | A.E. Compuesto Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 302269 | Naga City School of Arts and Trades | NAGA CITY | 3 | 1 | 21 | REPAIR OF CLASSROOMS | 4032988.41 | 1 | 2940000 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | Sulvir Engineering and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114502 | Pacol Elementary School | NAGA CITY | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 5948684.44 | 1 | 4045105.42 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114504 | Rosario V. Maramba Elementary School | NAGA CITY | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1347298.62 | 1 | 3314638.49 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114510 | San Isidro Elementary School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3207953.55 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114511 | Tinago Central School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3477905.69 | 1 | 5290754.91 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Naga City | 114519 | Triangulo Elementary School | NAGA CITY | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1862441.93 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114109 | Milagrosa Elementary School | CASTILLA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2218783.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114134 | San Vicente ES | CASTILLA | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2424103.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302183 | Bagatao NHS | MAGALLANES | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 797212.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114278 | Dona Olimpia. De Castro Mella ES | MAGALLANES | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2146208.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 2210864.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114282 | Pili ES | MAGALLANES | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1953675.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302179 | Abucay National High School | PILAR | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 2741432.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114351 | Mabanate ES | PILAR | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2302650.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 302236 | Salvacion National High School | PILAR | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 566510.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 113998 | Abad Santos Elementary School | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2433066.74 | 1 | 2406422.68 | Completed | 100% | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114032 | Aguinaldo ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2602358.07 | 1 | 2597153.28 | Completed | 100% | 2019-12-11 | [8 empty] | VINMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114005 | C.M. Recto ES | BULAN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1059015.78 | 1 | 1056897.62 | Completed | 100% | 2019-12-11 | [8 empty] | VINMOR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114029 | San Juan Daan ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2428652.48 | 1 | 2400177.1 | Completed | 100% | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114210 | Casili ES | GUBAT | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2635721.7 | 1 | 2230402.56 | Completed | 100% | 2019-11-18 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114190 | Cogon ES | GUBAT | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1666468.49 | 1 | 1623012.24 | Completed | 100% | 2019-11-21 | [8 empty] | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114192 | Gubat North CS | GUBAT | 2 | 1 | 25 | REPAIR OF CLASSROOMS | 8351280.11 | 1 | 8319956.81 | Completed | 100% | 2020-02-05 | [8 empty] | JAYRO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 5385435.18 | 1 | 5320435.17 | Completed | 100% | 2019-12-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114212 | Manapao ES | GUBAT | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 1862599.57 | 1 | 1576170.52 | Completed | 100% | 2019-11-18 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114218 | Tabi ES | GUBAT | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 3332670.31 | 1 | 3295720.85 | Completed | 100% | 2019-11-21 | [8 empty] | 144 CUBITS BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114224 | Batang ES | IROSIN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3643825.42 | 1 | 3585486.75 | Completed | 100% | 2019-11-27 | [8 empty] | RMH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114237 | Macawayan ES | IROSIN | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3023399.54 | 1 | 2972749.04 | Completed | 100% | 2019-11-21 | [8 empty] | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114305 | Bon-ot (Big) ES | MATNOG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2182199.25 | 1 | 2162199.13 | Completed | 100% | 2019-11-17 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114318 | Lajong ES | MATNOG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1148556.64 | 1 | 1143556.13 | Completed | 100% | 2019-11-17 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 3465672.14 | 1 | 3400668.12 | Completed | 100% | 2019-11-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2 |  | 3 | REPAIR OF CLASSROOMS | 3274700.13 | 1 | 3209696.45 | Completed | 100% | 2019-11-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon | 114411 | Salvacion ES | SANTA MAGDALENA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2642110.99 | 1 | 2234045.82 | Completed | 100% | 2019-11-27 | [8 empty] | STEVEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114556 | Cabid-an Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1643638.72 | 1 | 1593635.07 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Alhadrax C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1924969.86 | 1 | 1874448.65 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | NJNY C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114572 | Gimaloto Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1047790.32 | 1 | 1026081.51 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Jayro C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114577 | Peñafrancia Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2929470.32 | 1 | 2887746.51 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 114578 | Pio Jebulan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2134339.85 | 1 | 2092352.35 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Oct. 10, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 302275 | Rawis National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3271423.54 | 1 | 3242506.78 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Oct. 3, 2019 | Duamon C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Sorsogon City | 500463 | Sto. Nino Integrated School | CITY OF SORSOGON (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3995603.48 | 1 | 3994159.12 | Completed | 100% | November |  |  |  |  | 2019-07-12 | July 24, 2019 |  | Sept. 16, 2019 | NJNY C/S |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114585 | Bantayan ES | CITY OF TABACO | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3993624.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 177501 | Basagan ES | CITY OF TABACO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 864630.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114609 | Bognabong Elementary School | CITY OF TABACO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1206622.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114586 | Bonot ES | CITY OF TABACO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1433409.36 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114612 | Cobo ES | CITY OF TABACO | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1961250.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114613 | Comon ES | CITY OF TABACO | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3174874.62 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114592 | Nagsipit ES | CITY OF TABACO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1635378.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114597 | Quinastillojan ES | CITY OF TABACO | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 809881.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114622 | San Ramon ES | CITY OF TABACO | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3466869.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region V | Tabaco City | 114601 | San Vicente ES | CITY OF TABACO | 1 | 1 | 17 | REPAIR OF CLASSROOMS | 5071568.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs | TY USMAN |  |  |  | REPAIR | Completed
QRF 2019 | Region VI | Aklan | 500171 | Lezo IS | LEZO | 0 | 1 | 5 | 1STY5CL W/ TOILET | 8794811.81 | 1 |  | Completed | 100% | 2020-05-01 |  | DEPED-REGIONVI-D1-2019QRFBATCH1-035-2019 | DEPED-REGIONVI-D1-2019QRFBATCH1-035-2019 | 2019-05-10 | 2019-05-17 | 2019-05-29 | 2019-06-14 | 2019-06-25 | First Makeen Construction | suspended Waiting for Building Permit | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | FIRE DAMAGED |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 1818952.12 | 1 | 1500393.978 | Completed | 100% | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPAIR | Completed
QRF 2019 | Region VI | Guimaras | 115845 | Tinadtaran Elementary School | BUENAVISTA | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 2017883.65 | 1 | 1426275.672 | Completed | 100% | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPAIR | Completed
QRF 2019 | Region VI | Guimaras | 115862 | Don Pedro Vasquez Memorial School | JORDAN (Capital) | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1337767.73 | 1 | 1037532.27 | Completed | 100% | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPAIR | Completed
QRF 2019 | Region VI | Guimaras | 115870 | Espinosa Elementary School | JORDAN (Capital) | 0 | 1 | 8 | 1STY2CL W/ TOILET | 5602739.08 | 1 | 4382589.37 | Completed | 100% | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs | EARTHQUAKE |  |  |  | REPLACEMENT | Completed
QRF 2019 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 | 1 | 4 | 1STY4CL | 6844288.3 | 1 | 5607979.9956 | Completed | 100% | January 18, 2020 | January 18, 2020 | QRF-2019-RP-B0 | QRF-2019-RP-B1 | May 15, 2019 | May 23, 2019 | June 10, 2019 | August 9, 2019 | August 14, 2019 | J. Custorio Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs | FIRE DAMAGED |  |  |  | REPLACEMENT | Completed
QRF 2020 | CAR | Abra | 135049 | Bangilo ES | MALIBCONG | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 15842605.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 318811 | STA. FILOMENA SCHOOL OF ARTS AND TRADE | CALANASAN (BAYAG) | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8779024.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 318808 | ALLIG NATIONAL AGRICULTURAL AND TRADE HIGH SCHOOL | FLORA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2721248.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 305113 | FLORA NATIONAL HIGH SCHOOL | FLORA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11590542.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 305107 | APAYAO SCIENCE HIGH SCHOOL | LUNA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 10629542.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 135348 | TUMOG ELEMENTARY SCHOOL | LUNA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11609930.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Apayao | 305109 | STA. MARCELA NATIONAL HIGHSCHOOL | STA. MARCELA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7034850.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Benguet | 135644 | Bedbed Elementary School | MANKAYAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1386934.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Ifugao | 305172 | Gohang NHS | BANAUE | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3678931.08 | 1 | 3122966.93 | Completed | 100% | [10 empty] | Suspended | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Kalinga | 135975 | Kabugao ES | BALBALAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Kalinga | 135983 | Sesec-An ES | BALBALAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Kalinga | 136133 | Bangad Centro- Elementary School | TINGLAYAN | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6161678.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CAR | Mt. Province | 136196 | Ambacbac Elementary School | BAUKO | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2602877.52 | 1 | 4476989.71 | Completed | 100% | [8 empty] | 2020-11-24 | BOYET CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CARAGA | Butuan City | 304765 | Anticala NHS | BUTUAN CITY (Capital) | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3820757.9 | 1 | 3781533.97 | Completed | 100% | 2021-07-15 |  |  |  |  | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Regerys Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3408125.05 | 1 | 3348273.9708 | Completed | 100% | 2021-07-15 |  |  |  |  | 2019-06-20 | 2019-07-02 | 2019-07-18 | 2019-07-22 | Two J.E. Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region II | Cagayan | 102432 | Logung ES | AMULUNG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1310550.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region II | Cauayan City | 103229 | EB Tomaneng ES | CITY OF CAUAYAN | 6 | 1 | 4 | REPAIR OF CLASSROOMS | 1094004.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301366 | Nagsinamo NHS | LUCBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 923093.16 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 108668 | Tagbacan Ibaba ES | CATANAUAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 750000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301303 | Calantas NHS | MACALELON | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1000000 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 108941 | San Pedro ES | MULANAY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 499627.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109090 | Camflora ES | SAN ANDRES | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1800000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 2271387.68 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 26 | REPAIR OF CLASSROOMS | 2790218.03 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109092 | Inanuran ES | SAN ANDRES | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1773796.62 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109094 | Pansoy ES | SAN ANDRES | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 735596.83 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109114 | Aurora ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1708681.96 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109116 | Bayog ES | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 2258578.77 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301309 | Casay National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 200000 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308044 | Huyon-Uyon National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 973487.02 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 5058311.38 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109126 | Mabuhay ES | SAN FRANCISCO (AURORA) | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 4849958.19 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 302326 | Mabunga National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2550130.07 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109128 | Madagoldol ES | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2095004.72 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco) | SAN FRANCISCO (AURORA) | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 500000 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109133 | Pugon ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1114583.22 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301379 | Pugon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 1 | REPAIR OF CLASSROOM | 699319.78 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301368 | Renato Edano ES | SAN FRANCISCO (AURORA) | 3 | 1 | 15 | REPAIR OF CLASSROOMS | 1239163.34 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109134 | Tayuman Elementary School | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1111607.26 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301411 | Tumbaga NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 1 | REPAIR OF CLASSROOM | 150000 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109146 | Nangka ES | SAN NARCISO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1392308.34 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109153 | San VIcente ES | SAN NARCISO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1760025.17 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109154 | Vigo CES | SAN NARCISO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 522381.1 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 301284 | Alabat Island National High School | ALABAT | 4 | 1 | 6 | REPAIR OF CLASSROOMS | 816036.65 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Quezon | 109228 | Tabason ES | TAGKAWAYAN | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Tanauan City | 321602 | Balele National High School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2257184.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-A | Tanauan City | 301075 | Banjo Laurel NHS | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2312048.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111555 | Biga ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1149457.96 | 1 | 1067846.44 | Completed | 100% | November 10, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 014 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111558 | Camansihan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1106478.4 | 1 | 1024709.64 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 005 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111559 | Camilmil CS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1151756.08 | 1 | 1063222.41 | Completed | 100% | October 31, 2020 |  | QRF 2020 - RIVB - CALAPAN CITY - 006 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111573 | Canubing I ES | CITY OF CALAPAN (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1096114.97 | 1 | 1015660.13 | Completed | 100% | December 9, 2020 | 11/28/2019 | QRF 2020 - R IVB - CALAPAN CITY - 023 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 301801 | Ceriaco A. Abes MNHS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1718856.97 | 1 | 1591165.03 | Completed | 100% | October 31, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 020 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 301797 | Community Voc. HS | CITY OF CALAPAN (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2131209.83 | 1 | 1973713.43 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 017 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111575 | F. Samaco MS | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2726741.15 | 1 | 2482076.21 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 009 | 2020-08 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 8 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111537 | Guinobatan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1833943.77 | 1 | 1696397.99 | Completed | 100% | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 011 | N/A | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111560 | Gutad ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1567604.19 | 1 | 1456304.3 | Completed | 100% | November 10, 2020 | 02/01/2020 | QRF 2020 - R IVB - CALAPAN CITY - 007 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111563 | M. Pesig MES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1512438.99 | 1 | 1405055.82 | Completed | 100% | November 10, 2020 |  | QRF 2020 - RIVB - CALAPAN CITY - 004 | 2020-03 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111565 | Malamig ES | CITY OF CALAPAN (Capital) | 1 | 1 | 1 | REPAIR OF CLASSROOM | 559919.5 | 1 | 520501.17 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 019 | 2020-07 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 301805 | Managpi NHS | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 2176105.41 | 1 | 2015291.22 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 018 | 2020-06 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111576 | Masipit ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1939391.94 | 1 | 1793937.55 | Completed | 100% | February 16, 2021 | 12/04/2019 | QRF 2020 - R IVB - CALAPAN CITY - 008 | N/A | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111542 | N. Aboboto MS | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2006921.61 | 1 | 1856402.49 | Completed | 100% | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 013 | N/A | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | N/A | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 6550389.71 | 1 | 6089569.8 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 003 | 2020-07 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111577 | Patas ES | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2839995 | 1 | 2631648.51 | Completed | 100% | December 9, 2020 | 12/04/2019 | QRF 2020 - R IVB - CALAPAN CITY - 010 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 301803 | Pedro V. Panaligan NHS | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 4501423.16 | 1 | 4016924.65 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 016 | 2020-08 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 8 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111546 | San Antonio ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1664056.86 | 1 | 1540616.68 | Completed | 100% | October 31, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 012 | 2020-04 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | ETVR TRADING & CONSTRUCTION | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111579 | Sta. Isabel ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1515105.36 | 1 | 1403896.63 | Completed | 100% | December 9, 2020 |  | QRF 2020 - R IVB - CALAPAN CITY - 025 | 2020-05 | April 28, 2020 | May 7, 2020 | May 20, 2020 | June 22, 2020 | June 29, 2020 | KARANGYAN BUILDERS & TRADERS | CLUSTER 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111549 | Suqui ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1656112.6 | 1 | 1531904.15 | Completed | 100% | February 20, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 002 | N/A | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Calapan City | 111581 | Tawagan ES | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 3180086.03 | 1 | 2941579.58 | Completed | 100% | February 16, 2021 |  | QRF 2020 - R IVB - CALAPAN CITY - 022 | N/A | June 23, 2020 | July 1, 2020 | July 13, 2020 | September 1, 2020 | September 7, 2020 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110079 | BALANGABONG ES | CALINTAAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 900000 | 1 | 899863.16 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110081 | CALINTAAN CS | CALINTAAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2999752.23 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110085 | IRIRON ES | CALINTAAN | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 4200000 | 1 | 4199429.32 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110092 | TANYAG ES | CALINTAAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1500000 | 1 | 1499365.5 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110116 | ALIBOG ES | MAGSAYSAY | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199818.93 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110125 | CALAWAG ES | MAGSAYSAY | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 1 | 1049150.16 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110128 | EMOK ES | MAGSAYSAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749528.51 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110130 | GARZA PS | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599083.86 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110133 | LASTE ES | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1399590.4 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110139 | PACLOLO ES | MAGSAYSAY | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1399780.26 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110140 | PURNAGA ES | MAGSAYSAY | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749465.21 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110146 | TALABA ES | MAGSAYSAY | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2450000 | 1 | 2449787.33 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110200 | MAGSIKAP ES | RIZAL | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399128.56 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110201 | MALAWAAN ES | RIZAL | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2500000 | 1 | 2498701 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110207 | SAN PEDRO ES | RIZAL | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1398913.51 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110208 | SANTO NINO ES | RIZAL | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199684.17 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110230 | BALANI MINORITY SCHOOL | SABLAYAN | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1578552.72 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110276 | AMBULONG ES ANNEX-BULWANG PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 798180.39 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110277 | AMBULONG ES ANNEX-PATAG PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799200.43 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 500153 | AMBULONG ISLAND INTEGRATED SHOOL | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399204.12 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110278 | ANSIRAY ES | SAN JOSE | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 3200000 | 1 | 3198350.41 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110249 | BAGONG SIKAT ES | SAN JOSE | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 3600000 | 1 | 3599083.88 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110279 | BANGKAL ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199113.05 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110251 | BUBOG 2 ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199294.28 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110280 | BUNLAO ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 798945.42 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110281 | BURI ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799710.45 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110283 | CATAYUNGAN ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199736.37 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110284 | CATAYUNGAN ES ANNEX-SILOM PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799200.43 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110285 | ILING ES | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2400000 | 1 | 2399778.21 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110286 | INASAKAN ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799109.03 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110287 | IPIL ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799455.44 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110288 | LABANGAN ES | SAN JOSE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199299.83 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110290 | MANGA ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599620.32 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110291 | NATANDOL ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1599927.25 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110292 | PAWICAN ES | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 | 899605.36 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110293 | PAWICAN ES ANNEX-PITOGO PS | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2700000 | 1 | 2699401.16 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110294 | PAWICAN ES ANNEX-TABAY PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799378.93 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110295 | PAWICAN ES ANNEX-TIBAGO PS | SAN JOSE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 800000 | 1 | 799225.93 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110268 | PULANG LUPA ES | SAN JOSE | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1750000 | 1 | 1749465.21 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110257 | BATO-ILI MINORITY SCHOOL | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199134.91 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110259 | DANLOG MINORITY SCHOOL | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1500000 | 1 | 1499526.59 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110302 | MABINI II ES | SAN JOSE | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 2700000 | 1 | 2699472.38 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 308901 | SAN JOSE NAT'L AGRI'L & IND'L HS | SAN JOSE | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2998443.11 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110274 | TUGTUGIN ES | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1799839.2 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110315 | YAWI-YAWI - I ES | SAN JOSE | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1199949.59 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Occidental Mindoro | 110316 | YAWI-YAWI II PS | SAN JOSE | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2000000 | 1 | 1999753.49 | Completed | 100% | 2020-10-28 |  |  |  | 2020-04-21 | 2020-04-29 | 2020-05-08 | 2020-05-14 | 2020-05-18 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110335 | LANTUYANG ES | BACO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1512842.8 | 1 | 1499204.44 | Completed | 100% | Nov. 23, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 17, 2020 | FS Sugay Const & Supplies | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110336 | LUMANGBAYAN ES | BACO | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2743732.77 | 1 | 2732012.5 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Kasanga Const and Supplies | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110337 | WATER ES | BACO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1292745.36 | 1 | 1277035.62 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Etvr Trading and Const | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110545 | B. AGUILON ES | NAUJAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1586140.76 | 1 | 1583793.21 | Completed | 100% | Dec. 17, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | Aug. 28, 2020 | Sept. 11,200 | Etvr Trading and Const | To be awarded to second lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110512 | DEL PILAR ES | NAUJAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1097794.26 | 1 | 1083472.5 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 14, 2020 | Etvr Trading and Const | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110606 | TIGUIHAN ES | POLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1144602.79 | 1 | 1136949.8 | Completed | 100% | Dec. 17, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | Aug. 28, 2020 | Sept. 11,200 | Etvr Trading and Const | To be awarded to second lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110626 | VILLAFLOR ES | PUERTO GALERA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 691275.56 | 1 | 683925.98 | Completed | 100% | Nov. 23, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-01 | 2020-07-09 | Aug. 17, 2020 | FS Sugay Const & Supplies | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110710 | VICTORIA CS | VICTORIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1745000 | 1 | 1709567.59 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110464 | CABALWA ES | MANSALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1649713.16 | 1 | 1447040.9205 | Completed | 100% |  |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 |  |  |  | For Re-Bid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110469 | M.MARCIANO MES | MANSALAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 758019.65 | 1 | 670288.584 | Completed | 100% |  |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 |  |  |  | For Re-Bid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110560 | MALAYA ES | PINAMALAYAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2243438.96 | 1 | 2218635.78 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | DK Construction | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110575 | MALIANCOG ES | PINAMALAYAN | 2 | 1 | 1 | REPAIR OF CLASSROOMS | 402870.09 | 1 | 389902.59 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Oriental Mindoro | 110565 | RANZO ES | PINAMALAYAN | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2101930.74 | 1 | 2051030.52 | Completed | 100% | Nov. 21, 2020 |  |  |  | 2020-05-12 | 2020-05-20 | 2020-06-02 | 2020-07-09 | Aug. 14, 2020 | Cmsel Const & Developer | NTP issued | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Palawan | 111001 | Cuyo Central School | CUYO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2043892.81 | 1 | 1736380.99 | Completed | 100% |  |  |  |  | 2020-05-20 | 2020-06-03 | 2020-06-16 | 2020-06-22 | UPON ISSUANCE OF SARO |  | For Mobilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111508 | Baruang ES | PUERTO PRINCESA CITY (Capital) | 2 |  | 2 | REPAIR OF CLASSROOMS | 877821.56 | 1 | 728565.44 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111508 | Baruang ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2023273.47 | 1 | 1679256 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111518 | Macarascas ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1774004.76 | 1 | 1472370.49 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111520 | Makirawa Elementary School | PUERTO PRINCESA CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 4249630.93 | 1 | 3448396.36 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2633464.68 | 1 | 2185696.32 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Puerto Princesa City | 111491 | San Pedro CS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1705643.12 | 1 | 1415632.39 | Completed | 100% |  |  |  |  | 2020-04-27 | 2020-05-04 | 2020-05-18 | 2020-05-22 | 2020-05-25 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Romblon | 111278 | CAJIDIOCAN CENTRAL ES | CAJIDIOCAN | 0 | 1 | 32 | REPAIR OF CLASSROOMS | 6548401.38 | 1 | 5608240.38 | Completed | 100% | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Romblon | 111283 | CANTAGDA ES | CAJIDIOCAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 4013870.21 | 1 | 3171845.75 | Completed | 100% | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IV-B | Romblon | 111388 | SABLAYAN ES | ROMBLON | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4655023.4 | 1 | 3913640.07 | Completed | 100% | 2020-10-14 | 2020-10-14 |  |  | 2020-05-12 | 2020-05-19 | 2020-06-02 | 2020-06-05 | 2020-06-11 | NMDC CONSTRUCTION CORPORATION | Resumption on August 27, 2020 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region IX | Zamboanga del Norte | 303711 | Don Jose Aguirre NHS | MANUKAN | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8866108.44 | 1 | 8808680.91 | Completed | 100% | 2020-12-31 | 2020-12-16 | QRF 2020-RIX-ZDN | QRF 2020-RIX-ZDN-001 | 2020-04-15 | April 24, 2020 | May 7, 2020 | May 26, 2020 | June 15, 2020 | YSL BUILDERS | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region IX | Zamboanga del Norte | 303730 | Siayan National High School | SIAYAN | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 18706024.7 | 1 | 18597394.16 | Completed | 100% | 2020-12-31 | 2020-12-16 | QRF 2020-RIX-ZDN | QRF 2020-RIX-ZDN-002 | 2020-04-15 | April 24, 2020 | May 7, 2020 | May 26, 2020 | June 15, 2020 | YSL BUILDERS | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Albay | 111584 | Bacacay East CS | Bacacay | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1265327.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111586 | Bogna ES | BACACAY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 934692.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111590 | Cajugotan ES | Bacacay | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 596674.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 301863 | Pili NHS | Bacacay | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 1752253.3 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111622 | Tambongon ES | BACACAY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 992361.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111598 | Tanagan Elementary School | BACACAY | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2422849.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172509 | Basud Elementary School | MALILIPOT | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1296144.09 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 301876 | San Isidro National High School | MALILIPOT | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1440607.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172508 | Dapdap ES | Tiwi | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 802842.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112076 | Nagas ES | Tiwi | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 786157.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112081 | Tiwi CS | Tiwi | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 1636944.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111625 | ANOLING ES | CAMALIG | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3068380.92 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111639 | Baligang ES | CAMALIG | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 6003896.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111640 | CAGUIBA ES | CAMALIG | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2267858.78 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111631 | ILULUAN ES | CAMALIG | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3907352.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111646 | MAGOGON ES | CAMALIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1326206.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111655 | TALOTO ES | CAMALIG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2053160.56 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111662 | BINITAYAN ES | DARAGA | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3094477.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 172512 | CAROLINA ES | DARAGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1576427.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111686 | GABAWAN ES | DARAGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4482826.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111687 | GAPO ES | DARAGA | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4876975.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111671 | KIWALO ES | DARAGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1307663.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 301832 | LACAG NHS | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3264205.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111674 | MATNOG ES | DARAGA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2570353.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111696 | NAMANTAO ES | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2822655.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111902 | PAWA ES | DARAGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4019599.55 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111702 | TABONTABON ES | DARAGA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3087824.1 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2020 | Region V | Albay | 111677 | TAGAS ES | DARAGA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3538992.27 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111703 | TALAHIB ES | DARAGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1759429.92 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111889 | BAMBAN ES | MANITO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1760502.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111893 | CAVIT ES | MANITO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1511291.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111894 | Cawayan Elementary School | MANITO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2444541.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111901 | NAGOTGOT ES | MANITO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3000621.21 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112017 | Bagaobawan Elementary School | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2103549.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112020 | BINOSAWAN ES | RAPU-RAPU | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2896661.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112024 | CALANAGA ES | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2968332.23 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 112029 | GALICIA ES | RAPU-RAPU | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2456754.62 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Albay | 112032 | LAGUNDI ES | RAPU-RAPU | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 3100806.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112035 | Mananao Elementary School | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3436558.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112043 | RAPU-RAPU CS | RAPU-RAPU | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3672802.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111722 | BINOGSACAN ELEMENTARY SCHOOL | GUINOBATAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1081532.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111706 | BOLOLO ELEMENTARY SCHOOL | GUINOBATAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2146032.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111710 | GUINOBATAN EAST CENTRAL SCHOOL | GUINOBATAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1081532.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111747 | LILIBDON ELEMENTARY SCHOOL | JOVELLAR | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 773801.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111753 | SAN ROQUE ELEMENTARY SCHOOL | JOVELLAR | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 843609.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111783 | ALONGONG ELEMENTARY SCHOOL | LIBON | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2338643.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111794 | J. CORTES ELEMENTARY SCHOOL | LIBON | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 3868494.3 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111764 | MABAYAWAS ELEMENTARY SCHOOL | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1159713.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111797 | MOLOSBOLOS ELEMENTARY SCHOOL | LIBON | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1250758.77 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2020 | Region V | Albay | 111775 | SAN ANTONIO ELEMENTARY SCHOOL | LIBON | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2072980.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111805 | Tagbac Elementary School | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 856248.37 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111808 | VILLA PETRONA ELEMENTARY SCHOOL | LIBON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 561699.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111905 | BADIAN ELEMENTARY SCHOOL | OAS | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 4376009.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111928 | BALOGO WEST ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2434862.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111909 | BUSAC ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2220892.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111934 | MAPORONG ELEMENTARY SCHOOL | OAS | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 2953494.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111916 | MARAMBA ELEMENTARY SCHOOL | OAS | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1243161.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111918 | NAGAS ELEMENTARY SCHOOL | OAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 841131.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111939 | SAN AGUSTIN ELEMENTARY SCHOOL | OAS | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1224294.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111941 | SAN JUAN ELEMENTARY SCHOOL | OAS | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1321939.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111943 | SAN RAMON ELEMENTARY SCHOOL | OAS | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2820151.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111955 | DR. SOFRONIO S. GARCIA ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2531819.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111961 | MALAPAY ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1955145.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111966 | MARIGONDON ELEMENTARY SCHOOL | pioDURAN | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 4151434.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111969 | ORINGON ELEMENTARY SCHOOL | PIODURAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 844869.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 112001 | APAD ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1227951.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111985 | JOSE DURAN ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 844869.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Albay | 111998 | STA. CRUZ ELEMENTARY SCHOOL | POLANGUI | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 835568.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Norte | 309610 | Victoria J. Tuacar National HS | CAPALONGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1620084.24 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Norte | 112169 | San Pedro ES | JOSE PANGANIBAN | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1453192.48 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112174 | Ulipanan ELementary School | JOSE PANGANIBAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1453192.48 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112245 | Dagang ES | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1801027.12 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112247 | Gumaus Elementary School | PARACALE | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 4297116.47 | 1 |  | COMPLETED | 100% | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 492624.59 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301910 | PARACALE NATIONAL HIGH SCHOOL | PARACALE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1488785.65 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112278 | BASIAD ELEMENTARY SCHOOL | SANTA ELENA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2357851.92 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 173008 | Don Tomas ES | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1475060.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 173010 | Kagtalaba ES | SANTA ELENA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2108214.78 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309602 | Maulawin National High School | SANTA ELENA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1803000.61 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112096 | Mocong ES | BASUD | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1915285.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 309613 | Alawihao National High School | DAET (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11511274.91 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301900 | Lalawigan National High School | MERCEDES | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1176499.84 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2833241.08 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112263 | Imelda ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3819153.72 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112267 | Manlimonsito ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1536027.33 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112273 | San Isidro ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1588527.33 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 4315111.76 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112301 | Calangcawan Sur ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4495649.17 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112302 | Don Miguel Lukban ES | VINZONS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1427546.82 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Camarines Norte | 112308 | Mangcawayan Island ES | VINZONS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3091453.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112740 | COLACLING ES | LUPI | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 4349926.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112744 | Lourdes Elementary School | LUPI | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112975 | UPPER STA. CRUZ | RAGAY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2190811.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302068 | NORTH VILLAZAR NHS | SIPOCOT | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 5087315.9 | 1 | 4576555 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302047 | SIPOCOT NHS | SIPOCOT | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 6244020.54 | 1 | 3416850 | Completed | 100% | 2/13/2020 |  |  | 2019-08-025 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112673 | Bigajo Sur Ps | LIBMANAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1897469.08 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112710 | Duang Niog ES | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1164536.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112681 | Libmanan North Cs | LIBMANAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2290243.47 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112713 | Mambulo Nuevo ES | LIBMANAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2458547.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 301994 | Mambulo Nuevo High School | LIBMANAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1658479.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 309745 | Northern Plain Hs | LIBMANAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1372186.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112772 | Bal-Flor Es | MILAOR | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1471651.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 309731 | Antipolo HS, Minalabac | MINALABAC | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3057682.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302025 | Sagrada Familia Hs | MINALABAC | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 2654590.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112812 | Timbang ES | MINALABAC | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 873260.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302066 | Villamayor Hs | MINALABAC | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1303412.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112873 | Salvacion Es | PAMPLONA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1621955.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112875 | San Isidro Es | PAMPLONA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1782776.92 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112906 | Dalupaon Es | PASACAO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3676477.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112910 | Odicon Es | PASACAO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2169670.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 113009 | San Fernando Cs | SAN FERNANDO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2110564.41 | 1 | 2679800 | Completed | 100% | 2/13/2020 |  |  | 2019-08-026 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/16/2019 | LAHDETH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 303542 | Severo High School | CALABANGA | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 1687994.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112919 | Bagong Sirang ES | PILI (Capital) | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2299792.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112928 | La Purisima ES | PILI (Capital) | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1483352.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302040 | Panagan National High School | LAGONOY | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 9218565.91 | 1 | 3149420 | Completed | 100% | Feb. 18, 2020 |  |  | 2019-08-036 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | DELPAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 302019 | Presentacion NHS (formerly:Pili NHS) | PRESENTACION (PARUBCAN) | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 13469395.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 112317 | Agdangan ES | BAAO | 5 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1405524.04 | 1 | 1659566.02 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 10377046.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Camarines Sur | 112341 | Sta. Teresa PS | BAAO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 810527.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112345 | CABANBANAN ES | BALATAN | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2265820.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112357 | San Francisco ES | BALATAN | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 3242867.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112368 | CRISTO REY ELEMENTARY SCHOOL | BATO | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1163774.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112389 | Antipolo Elementary School | BUHI | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1918784.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112395 | De La Fe Elementary School | BUHI | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 404093.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112396 | Divino Rostro ES | BUHI | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1596149.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112405 | Macaangay Elementary School | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1506085.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112409 | Sagrada ES | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 886468.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112410 | Salay Elementary School | BUHI | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 3425049.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112412 | San Isidro Elementary School | BUHI | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 4786870.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112415 | San Vicente Elementary School | BUHI | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 886468.42 | 1 | 2540500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-046 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112418 | Sta. Justina East ES | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1152912.09 | 1 | 1895771.4 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112420 | Sto. Nino PS | BUHI | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1437483.29 | 1 | 316400 | Completed | 100% | Feb. 12,2020 |  |  | 2019-08-042 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/15/2019 | ROLA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112423 | Anayan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 263373.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112425 | Bagumbayan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2402139.47 | 1 | 4057987.41 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-043 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112444 | Bula South CS (Formerly Palsong ES) | BULA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2122587.05 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 173554 | Catasan ES | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1837493.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112431 | Fabrica ES | BULA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 4885443.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112436 | La Purisima Elementary School | BULA | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1797043.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112435 | Lanipga ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 919057.47 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112440 | Macalinao Elementary School | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1693093.39 | 1 | 2110991.24 | Completed | 100% | Feb. 19, 2020 |  |  | 2019-08-041 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/22/2019 | JVM CEGUERA |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 302007 | Ombao HS | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 745090.7 | 1 | 470144.07 | Completed | 100% | Feb. 15, 2020 |  |  | 2019-08-044 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/18/2019 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112445 | Panoypoyan ES | BULA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1339019.07 | 1 | 309600 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112448 | San Agustin ES | BULA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 832549.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112451 | San Ramon Elementary School | BULA | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 1798680.88 | 1 | 436500 | Completed | 100% | Feb.18, 2020 |  |  | 2019-08-045 | 2019-01-07 | 6/17/2019 | 7/22/2019 | 8/16/2019 | 10/21/2019 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2158919.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112817 | Lourdes ES | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112837 | Malawag Elementary School | NABUA | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 926801.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112820 | Ogbon Elementary School | NABUA | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1779359.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Camarines Sur | 112822 | Paloyon ES | NABUA | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 898933.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 500167 | CRISTO REY ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1386834.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114418 | DON LAZARO MADARA MEMORIAL SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1510865.62 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114420 | IRIGA CENTRAL SCHOOL | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1086522.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114433 | NIÑO JESUS ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1617998.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 302252 | SAGRADA NATIONAL HIGH SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1068197.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114421 | SALVACION ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 3202262.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114424 | SAN ISIDRO ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1391637.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114427 | SAN NICOLAS ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2553336.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114438 | SAN RAMON ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2078200.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114439 | SAN VICENTE NORTE ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2126618.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114455 | STO. NIÑO ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 6571130.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Iriga City | 114456 | TIRIKTIRIKAN ELEMENTARY SCHOOL | IRIGA CITY | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 1510865.62 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 310201 | Arimbay High School | LEGAZPI CITY (Capital) | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 886853.76 | 1 |  | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114465 | Bagacay ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 236257.08 | 1 | 1360741.97 | Completed | 100% | 2019-12-30 |  | 2019-INFRA-06 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-24 | 3T Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114467 | Banquerohan Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2368010.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 176003 | Banquerohan Elementary school-SPED | LEGAZPI CITY (Capital) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1287834.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 420724.75 | 1 | 2880113.11 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114468 | Bariis ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 358452.9 | 1 | 2357636.09 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-08 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114487 | Bigaa Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1567235.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114459 | Bogtong ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1652348.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114469 | Buenavista ES | LEGAZPI CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3346300 | 1 | 1508957.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-025 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Legaspi City | 114476 | Buraguis ES | LEGAZPI CITY (Capital) | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 788818.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 310206 | Cagbacong High School | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1592920.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 176001 | Division SPED Center | LEGAZPI CITY (Capital) | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3012048.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114472 | Estanza ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1204513.64 | 1 | 1066699.08 | Completed | 100% | 2020-02-09 |  | 2019-07-006 | 2019-09-026 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-16 | 2019-11-11 | Sansa Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114490 | Gogon CS | LEGAZPI CITY (Capital) | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1761948.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302262 | Gogon High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1060153.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114460 | Homapon ES | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1092091.44 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Legaspi City | 302259 | Homapon High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 549247.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114479 | Ibalon Central School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 526564.89 | 1 | 1228432.13 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114461 | Imalnod ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1716632.97 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Legaspi City | 114480 | Lamba ES | LEGAZPI CITY (Capital) | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1652348.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114481 | Legazpi Port Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 454365.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114462 | Mabinit ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 356640.87 | 1 | 2492003.41 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114482 | Maslog ES | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2905821.3 | 1 | 698792.93 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302258 | Oro Site High School | LEGAZPI CITY (Capital) | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 1060153.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 302261 | Pag-asa National High School | LEGAZPI CITY (Capital) | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 986843.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114483 | Puro Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 454365.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114493 | Rawis ES | LEGAZPI CITY (Capital) | 2 | 1 | 1 | REPAIR OF CLASSROOM | 305702.32 | 1 | 1441100.27 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Legaspi City | 114473 | San Francisco ES | LEGAZPI CITY (Capital) | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3586350.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Ligao City | 111836 | Bacong ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1354097.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301838 | Bacong HS | CITY OF LIGAO | 3 | 1 | 35 | REPAIR OF CLASSROOMS | 7417286.21 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301811 | Barayong NHS | CITY OF LIGAO | 3 | 1 | 14 | REPAIR OF CLASSROOMS | 2332096.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111814 | Batang ES | CITY OF LIGAO | 3 | 1 | 22 | REPAIR OF CLASSROOMS | 5458391.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301814 | Bicol Regional Science HS | CITY OF LIGAO | 3 | 1 | 22 | REPAIR OF CLASSROOMS | 5123952.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111812 | Busay ES | CITY OF LIGAO | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 683090.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111838 | Cabarian ES | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 625351.4 | 1 | 5609871.56 | Completed | 100% | 2020-03-12 |  | 2019-INFRA-01 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-22 | GMO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301820 | Deogracias P. Princesa Memorial HS | CITY OF LIGAO | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 2650482.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111820 | Layon ES | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 580702.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | CITY OF LIGAO | 3 | 1 | 34 | REPAIR OF CLASSROOMS | 6149058.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111821 | Ligao East CS | CITY OF LIGAO | 3 | 1 | 20 | REPAIR OF CLASSROOMS | 2166909.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301837 | Ligao NHS | CITY OF LIGAO | 3 | 1 | 86 | REPAIR OF CLASSROOMS | 4542055.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 86 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111844 | Ligao West CES (Binatagan) | CITY OF LIGAO | 3 | 1 | 30 | REPAIR OF CLASSROOMS | 2725800.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111843 | Ligao West CES (P) Dunao | CITY OF LIGAO | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 4697796.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111845 | Mahaba ES | CITY OF LIGAO | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 1833094.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301858 | Oma-Oma NHS | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 704801.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111826 | Paulba ES | CITY OF LIGAO | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 4184346.37 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3 | 1 | 14 | REPAIR OF CLASSROOMS | 1646249.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111850 | Sta. Cruz ES | CITY OF LIGAO | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2371143.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 231001 | Tambac Elementary School | CITY OF LIGAO | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1007311.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111781 | Tastas ES | CITY OF LIGAO | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1471135.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111809 | Amtic ES | Ligao City | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1420798.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111811 | Barayong ES | Ligao City | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 3212280.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 301817 | Cabarian NHS | Ligao City | 3 | 1 | 19 | REPAIR OF CLASSROOMS | 2412609.3 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111818 | Don Teotimo ES | Ligao City | 3 | 1 | 1 | REPAIR OF CLASSROOM | 339237.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111819 | Herrera ES | Ligao City | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1774685.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111825 | Pandan ES | Ligao City | 3 | 1 | 10 | REPAIR OF CLASSROOMS | 4004273.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111827 | Paulog ES | Ligao City | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 869969.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111770 | Pinit ES | Ligao City | 3 | 1 | 1 | REPAIR OF CLASSROOM | 238602.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Ligao City | 111853 | Tula-Tula Grande ES | Ligao City | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1012709.16 | 1 | 2880113.11 | Completed | 100% | 2020-02-27 |  | 2019-INFRA-05 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-23 | La Abel Const & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113572 | BODEGA ES | CLAVERIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2221949.85 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113573 | BUYO ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1260093.62 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113575 | CANOMAY ES | CLAVERIA | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2226605.06 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113576 | CAWAYAN ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1665993.25 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113577 | CLAVERIA NORTH CS | CLAVERIA | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2740943.95 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113911 | CUEVA ES | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1127354.29 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113579 | IMELDA ES | CLAVERIA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 418052.49 | 1 | 638471.42 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-023 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113580 | MABABANGBAYBAY | CLAVERIA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1271354.02 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113582 | MADANILOG ES | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1594770.3 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113592 | SAN ISIDRO ES | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2097574.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302166 | SAN ISIDRO NHS | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2043225.18 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113595 | TAGUILID ES | CLAVERIA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1253150.24 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302126 | TITO R. ESPINOSA | CLAVERIA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1229257.56 | 1 | 1544321.83 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-024 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113762 | CARTORNA ES | MONREAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1352979.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174511 | Cogon ES | MONREAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 794658.3 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309923 | Cogon High School | MONREAL | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7865465.89 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113763 | Dalakit ES | MONREAL | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1574618.22 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113764 | FAMOSA ES | MONREAL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1985381.32 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113765 | FLOOR MORES ES | MONREAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1036659.1 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309930 | Gerardo C. CardiÃ±o Sr. HS | MONREAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1233628.87 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113766 | MABABOY ES (GUINHADAP EXT.) | MONREAL | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1188350.37 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113768 | MACARTHUR ES | MONREAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 4053310.14 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113771 | Morocborocan ES | MONREAL | 1 | 1 | 1 | REPAIR OF CLASSROOM | 408698.88 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113772 | REAL ES | MONREAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 4556541.63 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113774 | STO. NIÑO ES | MONREAL | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2915314.33 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113859 | Benitinan ES | SAN FERNANDO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 848149.88 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113860 | BUENASUERTE ES | SAN FERNANDO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1833056.81 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113863 | CABUG ES | SAN FERNANDO | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1780164.17 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302113 | Bagahanglad NHS | SAN JACINTO | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7616535.32 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 309928 | Emilio Lee-Llacer Sr. HS | SAN JACINTO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 786317.13 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113907 | BAYANIHAN ES | SAN PASCUAL | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2442291.49 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113913 | Donato Dela Pena ES | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 989518.53 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113920 | LAURENTE ES | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 375695.06 | 1 | 698792.93 | Completed | 100% | 2020-01-02 | Jan. 2020 | 2019-07-006 | 2019-09-021 | 2019-07-31 | 2019-08-08 | 2019-08-20 | 2019-09-13 | 2019-10-04 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113922 | LUKSOHON ES | SAN PASCUAL | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1722412.57 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113931 | RAMONA ES | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 881119.82 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate |  | Roxas Integrated School | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1256052.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate | 113934 | SAN PASCUAL CS | SAN PASCUAL | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3571113.88 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174523 | Segundina L. Rivera Elementary School | SAN PASCUAL | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 699563.14 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309937 | VICENTE D. ALBURO | SAN PASCUAL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 458132.33 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113374 | AROROY EAST CENTRAL SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1862555.28 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302111 | AROROY NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1591222.32 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113395 | AROROY WEST ELEMENTRY SCHOOL | AROROY | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2724824.58 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113398 | BONACAN ELEMETARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1673495.41 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113401 | CALANAY ELEMENTARY SCHOOL | AROROY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3068702.84 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113403 | DAYHAGAN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 1 | REPAIR OF CLASSROOM | 453625.06 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309901 | DELAVIN-RUBIA NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3426275.1 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309947 | EASTERN CAPSAY INTEGRATED SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1248941.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113377 | ELISA E. CORPUS ELMENTARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1592365.28 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113415 | GREGORIO R. DONGON ELEMENTARY SCHOOL | AROROY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2345169.62 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174517 | ISIDORO CALIMUTAN SR. ELEMENTARY SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1521081.58 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113382 | JABOYO-AN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 886833.95 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113418 | JACINTO R. RAMILO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1783524.29 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113405 | LADIAWAN PRIMARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 943219.49 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302143 | LUY-A NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 12 | REPAIR OF CLASSROOMS | 4488884.77 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113697 | MAGSALANGI ELEMENTARY SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1286243.36 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113407 | MALUBAGO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 1 | REPAIR OF CLASSROOM | 463878.84 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113408 | MARIPOSA ELEMENTARY SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1216362.56 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113411 | MATONGOG ELEMENTARY SCHOOL | AROROY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2020116.16 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302157 | PANIQUE NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1555718.45 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113412 | RUFO C. PAJES CENTRAL SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1211236.14 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113413 | SAN AGUSTIN ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 828964.41 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113414 | SAN ISIDRO ELEMENTARY SCHOOL | AROROY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 775372.85 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309909 | TERESITA C. YOUNG MEM. HIGH SCHOOL | AROROY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1250695.22 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 500163 | TIGBAO INTEGRATED SCHOOL | AROROY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2709447.3 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302174 | TINIGBAN NATIONAL HIGH SCHOOL | AROROY | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3115657.77 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2391615.9 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113420 | BALENO CENTRAL SCHOOL | BALENO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3415148.19 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113424 | CAGPANDAN ELEMENTARY SCHOOL | BALENO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1520512.17 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113431 | GABI ELEMENTARY SCHOOL | BALENO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 791737.38 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302140 | LAGTA NATIONAL HIGH SCHOOL | BALENO | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 4151248.82 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113433 | LAHONG ELEMENTARY SCHOOL | BALENO | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2589685.52 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113434 | LAHONG INTERIOIR ELEMENTARY SCHOOL | BALENO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1235447.02 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302141 | LAHONG NATIONAL HIGH SCHOOL | BALENO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1140251.4 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113437 | MAGDALENA ELEMENTARY SCHOOL | BALENO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 763016.96 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113445 | BALUD CENTRAL SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1085533.65 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302156 | BRICCIO A. ANINANG SR. MEMORIAL HIGH SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1272623.67 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501611 | CASAMONGAN INTEGRATED SCHOOL | BALUD | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1227774.72 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113451 | DANAO ELEMENTARY SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 456268.65 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174503 | PURO ELEMENTARY SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 454326.81 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501525 | UBO INTEGRATED SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 466100.62 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 501252 | ZAPATOS INTEGRATED SCHOOL | BALUD | 2 | 1 | 1 | REPAIR OF CLASSROOM | 487975.83 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302122 | BUGTONG NATIONAL HIGH SCHOOL | MANDAON | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2628111.93 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302125 | CLEOFE A. ARCE MEMORIAL HIGH SCHOOL | MANDAON | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1956066.79 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113650 | LANTANGAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 805327.01 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113656 | NANIPSAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 748410.41 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113659 | SAN JUAN ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1240221.67 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309907 | SAN PABLO NATIONAL HIGH SCHOOL | MANDAON | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1161589.43 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113664 | YANEZA LANDED ESTATE ELEMENTARY SCHOOL | MANDAON | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1673627.04 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113720 | BONBON ELEMENTARY SCHOOL | MILAGROS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 444059.68 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174521 | JOSE ANINANG SR. ES | MILAGROS | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1110806.84 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302147 | MASBATE SCHOOL OF FISHERIES | MILAGROS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1205934.91 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2555575.52 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113718 | PEDRO Y. BAUTISTA ELMENTARY SCHOOL | MILAGROS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1316623.49 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113705 | SAN ANTONIO ELEMENTARY SCHOOL | MILAGROS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 434339.27 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309941 | CRISTETA BAGANO MEMORIAL SCHOOL | MOBO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 734806.58 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113750 | MOBO CENTRAL SCHOOL | MOBO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073388.67 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113758 | Tugbo ES | MOBO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 806110.86 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113506 | BAGUMBAYAN ES | CATAINGAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 893666.08 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113511 | DIVISORIA ES | CATAINGAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1167158.69 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6750380 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 302128 | MARCELO A. ANONUEVO NHS | CATAINGAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1375552.94 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174506 | AGOHO ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 941495.17 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113530 | CABUNGAHAN ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 882768.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113533 | CAWAYAN WEST CS | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1402557.73 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113534 | CHICO ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1125335.97 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113540 | GUIOM ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 1 | REPAIR OF CLASSROOM | 410011.39 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113545 | LOOC ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 2846633.57 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113548 | MAHAYAHAY ES | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 980812.62 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113551 | NARO ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1004670.83 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113557 | PUNTA BATSAN ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 959894.69 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113562 | TABERNA ES | CAWAYAN | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1379096.6 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113563 | TALISAY ELEMENTARY SCHOOL | CAWAYAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 2439999.87 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113599 | BURACAN ELEMENTARY SCHOOL | DIMASALANG | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 485606.22 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113542 | ITOMBATO ES | DIMASALANG | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 827671.88 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113611 | MAMBOG ELEMENTARY SCHOOL | DIMASALANG | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1520205.98 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113613 | RANILE ES | DIMASALANG | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 888045.71 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113618 | FLORENCIO Y. FRANCISCO ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1315391.8 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113627 | MASBARANON ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1520205.98 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113631 | SAN ROQUE ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1492306.57 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113619 | TRANGIA-MAHUSAY ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 1 | REPAIR OF CLASSROOM | 485606.22 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113635 | TUNGA ELEMENTARY SCHOOL | ESPERANZA | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 1035173.06 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113798 | APOLINARIO ETANG ES | PALANAS | 3 | 1 | 1 | REPAIR OF CLASSROOM | 488940.54 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113778 | BUENASUERTE ES | PALANAS | 3 | 1 | 1 | REPAIR OF CLASSROOM | 489286.04 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113794 | MALATAWAN ELEMENTARY SCHOOL | PALANAS | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 854540.12 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302153 | Rondina-Atendido NHS | Palanas | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 15650725 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 302172 | TANQUE NHS | PIO V. CORPUS | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1857124.37 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 309903 | ARRIESGADO-SEVILLENO NHS | PLACER | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 927277.69 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113851 | FELIFRANCO AVENIDO SR. MES | PLACER | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 2011873.85 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113825 | GUIN-AWAYAN ELEMENTARY SCHOOL | PLACER | 3 | 1 | 1 | REPAIR OF CLASSROOM | 488749.5 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113516 | LIBTONG ES | PLACER | 3 | 1 | 1 | REPAIR OF CLASSROOM | 487404.95 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113827 | LOCSO-AN ES | PLACER | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1764259.48 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113849 | LUNA ES | PLACER | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 964006.48 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 174501 | NAGARAO ELEMENTARY SCHOOL | PLACER | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1290448.64 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113834 | SAN MARCOS ES | PLACER | 3 | 1 | 3 | REPAIR OF CLASSROOMS | 1276167.7 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302121 | Buenavista NHS | Uson | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 9756349 | 1 |  | COMPLETED | 100% | 0 | [9 empty] | Waiting for the Approval of Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 3.24 |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate | 113947 | DEL CARMEN ES | USON | 3 | 1 | 1 | REPAIR OF CLASSROOM | 495971.03 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113952 | MONGAHAY ELEMENTARY SCHOOL | USON | 3 | 1 | 1 | REPAIR OF CLASSROOMS | 485606.22 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 113972 | QUEZON ES | USON | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 955471.76 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. MHS | Uson | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 6480560 | 1 |  | COMPLETED | 100% | 2023-12-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Masbate City | 113666 | Anas ES | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1630897.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113686 | Asid ES | MASBATE CITY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 667001.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 321801 | Bolo National High School | MASBATE CITY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2239480.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113674 | Cawayan Exterioi ES | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1774402.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113683 | Electo T. Verano Elementary School | MASBATE CITY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1926092.98 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113678 | Florentino C. Versoza ES | MASBATE CITY | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 2552796.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113680 | Julian V antonio ES | MASBATE CITY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1341497.43 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 302148 | Masbate National Comprehensive HS | MASBATE CITY | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 1221576.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Masbate City | 113675 | Timoteo T. Buncaras ES | MASBATE CITY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1744568.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 176506 | Balatas Elementary School | NAGA CITY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 511595.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 114506 | Del Rosario Elementary School | NAGA CITY | 3 | 1 | 11 | REPAIR OF CLASSROOMS | 4259320.57 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 114507 | Don Manuel I. Abella Central School | NAGA CITY | 3 | 1 | 32 | REPAIR OF CLASSROOMS | 12017471.99 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1474122.93 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 7826211.16 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | COMPLETED
QRF 2020 | Region V | Naga City | 114500 | Naga Central School I | NAGA CITY | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 1933054.92 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Naga City | 114503 | Panicuason Elementary School | NAGA CITY | 3 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 3931074 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region V | Naga City | 114516 | Sabang Elementary School | NAGA CITY | 3 | 1 | 1 | REPAIR OF CLASSROOM | 498016.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114084 | Colambis Elem. School | Casiguran | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 205060.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114088 | Mabini ES | CASIGURAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 352957.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114096 | Tigbao ES | CASIGURAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 543810.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114098 | Trece Martires ES | CASIGURAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 532257.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114100 | Bagong Sirang ES | CASTILLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1454288.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114101 | Bogna ES | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1660509.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114118 | Buenavista ES | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1701487.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114119 | Burabod Elementary School | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1245750 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114120 | Caburacan ES | CASTILLA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 359910.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302201 | Cumadcad NHS | CASTILLA | 1 | 1 | 16 | REPAIR OF CLASSROOMS | 1118444.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114125 | Macalaya ES | CASTILLA | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 772005.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114111 | Oras Elementary School | CASTILLA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1007426.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302228 | Oras National High School | CASTILLA | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1762738.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114114 | San Isidro Elem. School | Castilla | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1087693.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114133 | San Roque Elem. School | Castilla | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1014119.47 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114139 | Banuang-Gurang ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2825728.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114141 | Bayawas Elem. School | Donsol | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 2095052.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302204 | Donsol NCHS | Donsol | 1 | 1 | 19 | REPAIR OF CLASSROOMS | 2800805.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114161 | Donsol West Central School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1452547.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114163 | Girawan Elementary School | DONSOL | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1025896.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114148 | Nagalon Elem. School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1957753.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114170 | Pangpang Elem School | Donsol | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 492188.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114154 | San Vicente ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1487705.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114177 | Sibago Elementary School | DONSOL | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 2957360.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114179 | Sta. Cruz ES | DONSOL | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3147231.51 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114181 | Tinanogan ES | DONSOL | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2652509.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114286 | Iluminado Carranza Elem.School | MAGALLANES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1075693.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114282 | Pili ES | MAGALLANES | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 830016.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114283 | Sta. Elena Elementary School | MAGALLANES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1692943.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114337 | Bantayan Elem. School | Pilar | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1756965.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 310006 | Bantayan National High School | PILAR | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1073917.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114341 | Calongay Elem. School | Pilar | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1414781.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114373 | Esmerada ES | PILAR | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1239931.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114347 | Inapugan ES | PILAR | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 873695.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114349 | Lumbang Elem. School | Pilar | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1784012.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114352 | Marifosque Elem. School | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 277926.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114356 | Pilar I Central School | Pilar | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 2540965.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114363 | Tingco Elementary School | PILAR | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2680017.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302248 | Tingco NHS | PILAR | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 889352.27 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113978 | Alegria Elementary School | BARCELONA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 379998.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113985 | Fabrica Elementary School | BARCELONA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 377458.3 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 113990 | Paghaluban Elementary School | BARCELONA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 743598.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302191 | Beguin HS | BULAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3637179.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302190 | Bulan National High School | Bulan | 2 | 1 | 24 | REPAIR OF CLASSROOMS | 5728979.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114011 | Danao ES | BULAN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 786667.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 310002 | J. P. Laurel HS | BULAN | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 1052678.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114021 | Namo ES | BULAN | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2315793.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114048 | Sagrada ES | BULAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2366203.27 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114059 | Bulusan CS | BULUSAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1083792.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302192 | Bulusan NHS | BULUSAN | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 5285917.65 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114064 | Porog ES | BULUSAN | 2 | 1 | 1 | REPAIR OF CLASSROOM | 369656.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114074 | San Roque ES | BULUSAN | 2 | 1 | 19 | REPAIR OF CLASSROOMS | 5103105.4 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114185 | Bagacay ES | GUBAT | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1078500 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302182 | Bagacay NHS | GUBAT | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 1800923.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114188 | Cabiguhan ES | GUBAT | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 982648.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114189 | Carriedo ES | GUBAT | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 766831.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2 | 1 | 20 | REPAIR OF CLASSROOMS | 6481932.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114211 | Gubat South CS | GUBAT | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 215687.99 | 1 | 5320435.17 | Completed | 100% | 2019-12-03 | [8 empty] | ALHADRAX CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114199 | Payawin ES | GUBAT | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1716073.31 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114230 | Cawayan ES | IROSIN | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 981036.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302212 | Gallanosa National High School | Irosin | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 2903831.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 16 | REPAIR OF CLASSROOMS | 6065708.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114240 | Patag ES | IROSIN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1842997.47 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114252 | Biriran Ele. School | Juban | 2 | 1 | 12 | REPAIR OF CLASSROOMS | 3657186.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114262 | Jagusara Elem. School | Juban | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 726345.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114272 | Tublijon Elem. School | Juban | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3166413.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114309 | Calpi Elementary School | MATNOG | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 743159.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114310 | Coron-Coron ES | MATNOG | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3248746.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114322 | Matnog CS | MATNOG | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 4174487 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114332 | Sua ES | MATNOG | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3228053.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114393 | Gogon ES | PRIETO DIAZ | 2 | 1 | 1 | REPAIR OF CLASSROOM | 369241.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 175006 | Nenita E. Oandasan Mem. Sch. | PRIETO DIAZ | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1858816.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 2404947.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114403 | San Ramon ES | PRIETO DIAZ | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1193316.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114415 | Sta. Magdalena CS | SANTA MAGDALENA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3739365.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2302784.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon | 114409 | Bilaoyon Elem. School | Sta. Magdalena | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1084051.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114520 | BACON EAST CENTRAL SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 3835469.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114534 | Bacon West Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 1 | REPAIR OF CLASSROOM | 243663.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Sorsogon City | 114547 | SAN VICENTE ELEMENTARY SCHOOL | CITY OF SORSOGON (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1574816.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114606 | Agñas Elementary School | Tabaco City | 1 | 1 | 1 | REPAIR OF CLASSROOM | 265034.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302281 | Bantayan National High School | Tabaco City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1514093.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114616 | Hacienda Elementary School | Tabaco City | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1460846.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 310503 | Hacienda High School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 1265859.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114587 | Mayon Elementary School | Tabaco City | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 4823433.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114619 | Sagurong Elementary School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2490592.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114598 | San Antonio Elementary School | Tabaco City | 1 | 1 | 19 | REPAIR OF CLASSROOMS | 12589191.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302282 | San Antonio National High School | Tabaco City | 1 | 1 | 34 | REPAIR OF CLASSROOMS | 2491420.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114620 | San Lorenzo Elementary School | Tabaco City | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 318785.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114621 | San Miguel Elementary School | Tabaco City | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 802219.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302284 | San Miguel National High School | Tabaco City | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 1416604.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114623 | San Roque Elementary School | Tabaco City | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3040431.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 302285 | Tabaco National High School | Tabaco City | 1 | 1 | 135 | REPAIR OF CLASSROOMS | 9453981.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 135 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114604 | Tabaco Northwest Central School | Tabaco City | 1 | 1 | 27 | REPAIR OF CLASSROOMS | 9061671.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114624 | Tabaco South Elementary School | Tabaco City | 1 | 1 | 18 | REPAIR OF CLASSROOMS | 6420883.78 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region V | Tabaco City | 114605 | Tabiguian Elementary School | Tabaco City | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 2206540.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 595334.53 | 1 | 489315.07 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114630 | DINA-UT ELEMENTARY SCHOOL | ALTAVAS | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 941250.66 | 1 | 931622.6 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302309 | JOSE FELICIANO MEÑEZ MEMORIAL NATIONAL HIGH SCHOOL | BALETE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1390694.68 | 1 | 1142832.61 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114654 | Guanko Elementary School | BALETE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 415787.69 | 1 | 341491.72 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 543063.6 | 1 | 539823.02 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHSNDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114671 | Muguing ES | BANGA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 1985700.94 | 1 | 1632641.53 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2790841.14 | 1 | 2758634.82 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 818121.39 | 1 | 672695.06 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302300 | Camaligan National High School | Batan | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 307071.25 | 1 | 252024.01 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302301 | Camanci National High School | BATAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1121205.42 | 1 | 1112092.14 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500640 | Ipil Integrated School | Batan | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 459203.67 | 1 | 455093.99 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114684 | CABUGAO ELEMENTARY SCHOOL | BATAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1998105.89 | 1 | 1578488.91 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114752 | NEW BUSWANG ELEMENTARY SCHOOL | KALIBO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1223802.91 | 1 | 966761.49 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500545 | BAKHAW NORTE INTEGRATED SCHOOL | KALIBO (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3881635.52 | 1 | 3872738.39 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 1064473.92 | 1 | 881275.6 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 749837.63 | 1 | 747259.43 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302313 | Linabuan NHS | KALIBO (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 275571.25 | 1 | 273750 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114759 | MOBO ELEMENTARY SCHOOL | KALIBO (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2059387.57 | 1 | 1611679.28 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114798 | ROSAL ELEMENTARY SCHOOL | LIBACAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1056440.03 | 1 | 873660.85 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114804 | BACYANG PS | MADALAG | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 843785.93 | 1 | 623594.43 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114808 | Catabana PS | MADALAG | 1 | 1 | 1 | REPAIR OF CLASSROOM | 597861.39 | 1 | 439879.86 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114816 | MADALAG ELEMENTARY SCHOOL | MADALAG | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1777256.95 | 1 | 1485251.61 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302302 | CANDELARIA NATIONAL HIGH SCHOOL | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 201102.87 | 1 | 200000 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114902 | Guinbaliwan ES | NEW WASHINGTON | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2151618.59 | 1 | 1690143.32 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 3151041.45 | 1 | 3121202.54 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302328 | Ochando National High School | NEW WASHINGTON | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 377604.5 | 1 | 373791.79 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 867507.12 | 1 | 862750 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114912 | Tambak ES | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 430472.51 | 1 | 416890.59 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114703 | BURUANGA ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3987376.05 | 1 | 3980222.31 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114704 | CABUGAO PRIMARY SCHOOL | BURUANGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1678662.91 | 1 | 1398716.73 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500182 | HABANA INTEGRATED SCHOOL | BURUANGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1304729.83 | 1 | 1291911.68 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114706 | KATIPUNAN ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 579650.18 | 1 | 482957.23 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114708 | PEPE ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2771247.16 | 1 | 2181493.99 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114709 | SANTANDER ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 878754.75 | 1 | 723074.43 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114714 | AGUTAY ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1413248.63 | 1 | 1044403.63 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114716 | AQUINO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1561562.59 | 1 | 1154056.13 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114734 | Cabugao PS | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 2123435.38 | 1 | 1669611.98 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114721 | Mabusao ES | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 2659490.62 | 1 | 2639788.53 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114723 | MALOCO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2879905.95 | 1 | 2871841.25 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302321 | NAILE NATIONAL HIGH SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1335635.25 | 1 | 1039649.38 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114724 | ONDOY ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 832619.75 | 1 |  | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114713 | AGBAGO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1055552.18 | 1 | 780085.49 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114719 | IBAJAY CENTRAL SCHOOL | IBAJAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2768795.78 | 1 | 2744654.09 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114735 | MINA-A ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1579132.27 | 1 | 1538358.4 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114737 | NAILE ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1095503.55 | 1 | 1080493.81 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114738 | NAISUD CENTRAL SCHOOL | IBAJAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1384182.93 | 1 | 1175337.5 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114742 | RIZAL ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3664360.37 | 1 | 2885839.73 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114743 | SAN ISIDRO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1235624.75 | 1 | 975978.43 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114763 | AGCAWILAN SILAKAT NONOK ELEMENTARY SCHOOL | LEZO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1124439.2 | 1 | 888059.84 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114768 | TAYHAWAN ELEMENTARY SCHOOL | LEZO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 470288.37 | 1 | 463525.22 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114832 | CABATANGA ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2278330.32 | 1 | 1887044.25 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114836 | Castillo ES | MAKATO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2364341.96 | 1 | 1958360.36 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114837 | CAYANGWAN ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3975645.21 | 1 | 3294339.15 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114842 | MANTIGUIB ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 866461.62 | 1 | 682877.77 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114845 | ARGAO ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2437500.16 | 1 | 1925461.92 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114847 | CATICLAN ELEMENTARY SCHOOL | MALAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1933938.78 | 1 | 1601796.32 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114850 | MALAY ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2179109.43 | 1 | 1804928.08 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114851 | MANOC MANOC ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1004012.2 | 1 | 831595.39 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114857 | BANAY BANAY ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2262269.17 | 1 | 1786373.21 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114864 | LILO-AN ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 820342.19 | 1 | 647054.13 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302312 | LILO-AN NATIONAL HIGH SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 488089.1 | 1 | 385349.33 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302319 | MALINAO SCHOOL FOR PHILIPPINE CRAFTSMEN | MALINAO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2505469.69 | 1 | 1979260.19 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114871 | SAN DIMAS ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1845590.17 | 1 | 1456761.06 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500643 | SAN ROQUE INTEGRATED SCHOOL | MALINAO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3007858.2 | 1 | 2930000 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114881 | GIBON ELEMENTARY SCHOOL | NABAS | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3575685.96 | 1 | 2809380.39 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114895 | Unidos Elementary School | NABAS | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 5243622.52 | 1 | 4114844.56 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | NAGAMOS BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3979019.97 | 1 | 3969473.61 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114884 | LIBERTAD ELEMENTARY SCHOOL | NABAS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1338285.52 | 1 | 1330500 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114888 | NAGUSTAN ELEMENTARY SCHOOL | NABAS | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2426859.98 | 1 | 2412000 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114891 | RIZAL ELEMENTARY SCHOOL | NABAS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2278337.19 | 1 | 2269712.29 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114892 | SOLIDO ELEMENTARY SCHOOL | NABAS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3147061.55 | 1 | 3109689.56 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302337 | TOLEDO NATIONAL HIGH SCHOOL | NABAS | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 802530.39 | 1 | 633756.4 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114896 | UNION ELEMENTARY SCHOOL | NABAS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 613868.81 | 1 | 594893.21 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114915 | BADIO ELEMENTARY SCHOOL | NUMANCIA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1677639.66 | 1 | 1670421.19 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500639 | BAYBAY ALIBAGON INTEGRATED SCHOOL | NUMANCIA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1693989.76 | 1 | 1338879.56 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500035 | NUMANCIA INTEGRATED SCHOOL | NUMANCIA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 907335.74 | 1 | 897505.98 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302327 | NUMANCIA NATIONAL SCHOOL OF FISHERIES | NUMANCIA | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 619521.73 | 1 | 489318.45 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 114933 | Sergio L. Taligatos ES | TANGALAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1826628 | 1 | 1527563.59 | Completed | 100% | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 500173 | TAMALAGON INTEGRATED SCHOOL | TANGALAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 808936.62 | 1 | 768000 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Aklan | 302336 | TANGALAN NATIONAL HIGH SCHOOL | TANGALAN | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 5052738.08 | 1 | 4977000 | Completed | 100% | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115003 | Alegria ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1169609.29 | 1 |  | Completed | 100% | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-01-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115004 | Bacong ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2244175.24 | 1 |  | Completed | 100% | 2022-09-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-01-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115005 | Banago ES | Caluya | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 4702937.78 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01D-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115006 | Bonbon ES | Caluya | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 3945027 | 1 |  | Completed | 100% | January 16, 2021 | March 12, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115007 | Caluya CS | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 6760487.52 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 302350 | Caluya NHS | Caluya | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2145761.69 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115009 | Dionela PS | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2682474.88 | 1 |  | Completed | 100% | 2022-10-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-01-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115010 | Harigue ES | Caluya | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 4089461.89 | 1 |  | Completed | 100% | 2022-09-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-01-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115011 | Hininga-an ES | Caluya | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1792265.18 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115014 | Lim ES | Caluya | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1314074.66 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115015 | Masanag ES | Caluya | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 7057906.86 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115016 | Sabang I ES | Caluya | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 726124.73 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115018 | Salamento ES | Caluya | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 624416.96 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115019 | Semirara ES | Caluya | 0 | 1 | 27 | REPAIR OF CLASSROOMS | 4395797.15 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 310705 | Semirara NHS | Caluya | 0 | 1 | 30 | REPAIR OF CLASSROOMS | 2396467.2 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115021 | Sibato ES | Caluya | 0 | 1 | 13 | REPAIR OF CLASSROOMS | 7148019.21 | 1 |  | Completed | 100% | December 27, 2020 |  |  | R6-D2-2020QRF-01D-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115022 | Sibay ES | Caluya | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 3095973.97 | 1 |  | Completed | 100% | January 16, 2021 | March 12, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 310706 | Sibay NHS | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4977373.62 | 1 |  | Completed | 100% | January 16, 2021 | March 16, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115023 | Sibolo ES | Caluya | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 4728747.3 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115025 | Tinogboc ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2997956.14 | 1 |  | Completed | 100% | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-01-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 302382 | Tinogboc NHS | Caluya | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1670487.61 | 1 |  | Completed | 100% | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-01-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115026 | Villarises ES | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 2605244.65 | 1 |  | Completed | 100% | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures, | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-01-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | 21 | REPAIR OF CLASSROOMS | 9725143.32 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115133 | Paz ES | LIBERTAD | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1478555.46 | 1 |  | Completed | 100% | January 16, 2021 | March 15, 2021 |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115137 | Taboc ES | LIBERTAD | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 755799.61 | 1 |  | Completed | 100% | January 16, 2021 | March 16, 2021 |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 420473.56 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115141 | Agripino Tambagahan MS | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 243256.8 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115146 | Buang ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2152026.97 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115147 | Cabugao ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 301687.19 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115149 | Circiaco M. Tayco MS | Pandan | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1951904.87 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115152 | Guia ES | Pandan | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 2289937.5 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 302365 | Mag-aba NHS | Pandan | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 67617.78 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115161 | Pandan CS | Pandan | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 72002.46 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115169 | Tabay ES | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 902382.95 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115170 | Talisay ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 302048.99 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115172 | Vidal Gelito ES | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 351019.46 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Antique | 115173 | Zaldivar ES | Pandan | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 363055.76 | 1 |  | Completed | 100% | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1179035.37 | 1 | 953272.0764 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115635 | Navitas ES | PANAY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 348429.7 | 1 | 281711.9063 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 500429 | AGLALANA INTEGRATED SCHOOL | Pilar | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2340265.98 | 1 | 1899238.0662 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VI | Capiz | 115692 | CABUGAO PRIMARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1332449.09 | 1 | 1009892.2482 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115670 | CARLOS V. LOPEZ ELEMENTARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1284078.81 | 1 | 1038201.6573 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 302400 | Dulangan NHS | Pilar | 1 | 1 |  | REPLACEMENT OF FENCE | 1227585.69 | 1 | 930413.987 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | OTHERS | Completed
QRF 2020 | Region VI | Capiz | 115675 | Pilar Elementary School | PILAR | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 4704973.69 | 1 | 3550572.91 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115678 | San Esteban ES | PILAR | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1136198.18 | 1 | 829362.5097 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115681 | SAN RAMON ELEMENTARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1058455.29 | 1 | 772614.4503 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115684 | STA. FE ELEMENTARY SCHOOL | Pilar | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 4288748.44 | 1 | 2895129.98 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 310811 | Yating National high School | Pilar | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 710522.61 | 1 | 538520.5947 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115688 | Agbanog ES | Pontevedra | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 802415.74 | 1 | 604471.0526 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115698 | Hipona ES | PONTEVEDRA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 489070.33 | 1 | 368423.5574 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115704 | Rizal ES | PONTEVEDRA | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3412083.95 | 1 | 2487450.02 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 310804 | Maindang National High School | CUARTERO | 2 | 1 |  | CONSTRUCTION OF RETAINING WALL | 9596206.74 | 1 | 5940052.74 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | OTHERS | Completed
QRF 2020 | Region VI | Capiz | 115464 | Sta. Rita ES | DUMALAG | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 102008.98 | 1 | 82785.176 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1178987.33 | 1 | 853021.9568 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 115579 | Atiplo Elementary School | Mambusao | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 735104.19 | 1 | 531863.2332 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Capiz | 501095 | Calixto Loyola Sr. Integrated School | SIGMA | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 532436.58 | 1 | 432097.8178 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VI | Iloilo | 116118 | Abong ES | Carles | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 913825.86 | 1 | 892785.23 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116010 | Bacolod PS | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 957041.07 | 1 | 813307.761 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116012 | Balasan CES | Balasan | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 1585598.25 | 1 | 1347497.97 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302454 | Balasan NHS | Balasan | 5 | 1 | 42 | REPAIR OF CLASSROOMS | 2841359.36 | 1 | 2045727.76 | Completed | 100% | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 42 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116013 | Batuan ES | Balasan | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 686237.07 | 1 | 582880.42 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116015 | Gimamanay ES | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 769455.5 | 1 | 653804.98 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116016 | Kinalkalan ES | Balasan | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2264359.01 | 1 | 1639543.32 | Completed | 100% | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L2 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116018 | Mamhut ES | Balasan | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2898061.78 | 1 | 2097510.66 | Completed | 100% | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L2 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 180030 | Mamhut PS | Balasan | 5 | 1 | 1 | REPAIR OF CLASSROOM | 321035.62 | 1 | 272527.2 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116020 | Pedro Bedez ES | Balasan | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1973278.4 | 1 | 1996126.5 | Completed | 100% | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L3 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116021 | Quisan ES | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 769455.5 | 1 | 653394.43 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116025 | Zaragosa ES | Balasan | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2759380.9 | 1 | 1439412.98 | Completed | 100% | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L3 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 937111.78 | 1 | 702530.625 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116095 | Jose P. Gonzaludo ES | Batad | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 380482.45 | 1 | 285081.6975 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116099 | Malico ES | Batad | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1974140.79 | 1 | 1480217.7975 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116100 | Pasayan PS | Batad | 5 | 1 | 1 | REPAIR OF CLASSROOM | 399175.07 | 1 | 298937.76 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 180021 | Sta. Ana ES | Batad | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 835117.01 | 1 | 830383.64 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 311001 | Valerio Palmares NHS | Batad | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 725529.38 | 1 | 720235.49 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116199 | Alipata ES | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1427101.42 | 1 | 1394341.17 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116200 | Asluman ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1806457.34 | 1 | 1800266.79 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116236 | Bagotao | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1048842.02 | 1 | 1017173.44 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 501492 | Barangcalan IS | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 492461.58 | 1 | 476727.2 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 180045 | Batuan IS | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1102610.65 | 1 | 1094247 | Completed | 100% | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 501493 | Binuluangan IS | Carles | 5 | 1 | 15 | REPAIR OF CLASSROOMS | 3240027.28 | 1 | 3233722.48 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116206 | Bito-on ES | Carles | 5 | 1 | 11 | REPAIR OF CLASSROOMS | 1435144.38 | 1 | 1402165.76 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116207 | Bolo ES | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 3275062.51 | 1 | 3270118.63 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L8 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 501486 | Buenavista IS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2053364.11 | 1 | 2003815.47 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L13 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116211 | Cana PS | Carles | 5 | 1 | 1 | REPAIR OF CLASSROOM | 561671.58 | 1 | 548307.84 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116213 | Cawayan ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2354426.17 | 1 | 1695466.3 | Completed | 100% | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302482 | Cawayan NHS | Carles | 5 | 1 | 13 | REPAIR OF CLASSROOMS | 1394637.96 | 1 | 1004170.48 | Completed | 100% | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | Carles | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 380482.45 | 1 | 2554599.41 | Completed | 100% | 2021-01-14 | 2021-11-12 | QRF2020-RVI-ILOILO-B1-L22 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | MBM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116217 | Granada ES | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 930705.26 | 1 | 919886.46 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302505 | Granada NHS | Carles | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1023901.19 | 1 | 1015313.69 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 311009 | Granada NHS - Ballesteros Campus | Carles | 5 | 1 | 20 | REPAIR OF CLASSROOMS | 3096850.34 | 1 | 2996800 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L20 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116219 | Lantangan ES | Carles | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 6256169.73 | 1 | 6213161.89 | Completed | 100% | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L15 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 501489 | Manlot IS | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1777067.09 | 1 | 1724299.36 | Completed | 100% | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116255 | Martin Azuelo MS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 3526759.03 | 1 | 2965893.11 | Completed | 100% | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L14 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116221 | Naborot ES | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2410394.5 | 1 | 2397198.59 | Completed | 100% | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L9 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116222 | Pantalan IS | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2721365.52 | 1 | 2695355.31 | Completed | 100% | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L9 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116223 | Piagao PS | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 482775.42 | 1 | 476106.93 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116225 | San Fernando ES | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1751891.33 | 1 | 1740873.46 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L10 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 501487 | Tabugon IS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2098301.4 | 1 | 2047784.52 | Completed | 100% |  | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L13 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 |  | RISM Builders and Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116227 | Talinting ES | Carles | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 4413345.79 | 1 | 4364729.89 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L10 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302577 | Talinting NHS | Carles | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 5020686.68 | 1 | 4994871.08 | Completed | 100% | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L11 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116228 | Tarong ES | Carles | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2733580.58 | 1 | 2312185.38 | Completed | 100% | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L14 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116229 | Tinigban IS | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 727158.47 | 1 | 722474.15 | Completed | 100% | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116230 | Toong ES | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1665686.79 | 1 | 1658730.72 | Completed | 100% | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116233 | Tupaz ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2683766.38 | 1 | 2626964.41 | Completed | 100% | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L8 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116263 | Taloto-an ES | Concepcion | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2385019.62 | 1 | 2380331.98 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116346 | Bayas ES | Estancia | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 4769183.85 | 1 | 4752274.32 | Completed | 100% | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302462 | Bayas NHS | Estancia | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 338763.96 | 1 | 329090.38 | Completed | 100% | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116347 | Botongon ES | Estancia | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1995704.07 | 1 | 1410628.26 | Completed | 100% | 2021-01-26 | 2021-12-13 | QRF2020-RVI-ILOILO-B1-L18 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116349 | Estancia CES | Estancia | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 3132916.19 | 1 | 2175718.12 | Completed | 100% | 2021-01-26 | 2021-12-13 | QRF2020-RVI-ILOILO-B1-L18 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 302500 | Estancia NHS | Estancia | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 3500000 | 1 | 227810.58 | Completed | 100% | 2021-01-15 | 2021-11-12 | QRF2020-RVI-ILOILO-B1-L22 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | MBM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116351 | Loguingot ES | Estancia | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 838104.79 | 1 | 832213.44 | Completed | 100% | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116355 | San Roques ES | Estancia | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2217169.99 | 1 | 1706805.64 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L19 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116356 | Tanza ES | Estancia | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 2789328.5 | 1 | 2146498.74 | Completed | 100% | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L19 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116675 | Amayong PS | SAN DIONISIO | 5 | 1 | 1 | REPAIR OF CLASSROOM | 434642.77 | 1 | 431061.92 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116684 | Madanlog Elementary School | SAN DIONISIO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 697640.13 | 1 | 692861.87 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Iloilo | 116685 | Malunoy ES | San Dionisio | 5 | 1 | 1 | REPAIR OF CLASSROOM | 508286.01 | 1 | 504739.84 | Completed | 100% | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Roxas City | 302756 | Balijuagan NHS | Roxas City | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 249849.27 | 1 | 230989.57 | Completed | 100% | 2021-02-13 | 2020-11-10 |  | CON-2020-016/1 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Roxas City | 117681 | Don Jose Acevedo ES | Roxas City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 267455.2 | 1 | 234618.83 | Completed | 100% | 2021-02-13 | 2020-11-17 |  | CON-2020-016/3 |  |  |  | 2020-09-13 | 2020-10-05 | NANA BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Roxas City | 117657 | Dumolog ES | Roxas City | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 649479.2 | 1 | 590706.37 | Completed | 100% | 2021-02-13 | 2020-11-23 |  | CON-2020-016/4 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VI | Roxas City | 302760 | Milibili NHS | Roxas City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 227053.34 | 1 | 204225.29 | Completed | 100% | 2021-02-13 | 2020-11-10 |  | CON-2020-016/2 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120777 | CANILLA ES | BILIRAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1323658.4 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120814 | USON ES | CAIBIRAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1798169.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120815 | Acaban Elementary School | CULABA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1057517.75 | 1 |  | Completed | 100% | [10 empty] | re-aligned to calumpang cs, naval biliran 100% completed (repair of 1 unit 1STY 2CL and 1 unit 1STY 1CL) from acaban es slope protection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VIII | Biliran | 303326 | KAWAYAN NHS | KAWAYAN | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 5657769.82 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120843 | UNGALE I ES | KAWAYAN | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4066702.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120868 | CALUMPANGES | NAVAL | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1154531.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Biliran | 120859 | LARRAZABAL ES | NAVAL | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2301989.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Borongan City | 122393 | Banuyo ES | BORONGAN CITY(Capital) | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 2698984.53 | 1 | 2697984.88 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Borongan City | 122356 | Bato ES | BORONGAN CITY(Capital) | 0 | 1 | 15 | REPAIR OF CLASSROOMS | 4641631.5 | 1 | 4630626.7 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Borongan City | 303500 | ESNCHS | BORONGAN CITY(Capital) | 0 | 1 | 20 | REPAIR OF CLASSROOMS | 7012642.3 | 1 | 7007776.7 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Borongan City | 122403 | Lalawigan CES | BORONGAN CITY(Capital) | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2107991.37 | 1 | 2095000 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124118 | Baay Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1436793.56 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124120 | Bantian Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 721753.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124081 | Cabicahan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 705939.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124131 | Cagmanipis Norte Elementary School | CALBAYOG CITY | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3184345.08 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124130 | Cagmanipis Sur Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 682674.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 123989 | Calbayog Pilot Central School | CALBAYOG CITY | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3359829.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124008 | Carmen Elementary School | CALBAYOG CITY | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2110000.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124090 | Dinabongan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 721349.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124061 | Dinagan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 351051.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 500237 | Gadgaran Integrated School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 251034.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124012 | Giragaan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 730038.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124016 | Himalandrog Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 330524.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124099 | Mag ubay Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1039080.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124137 | Malaga Central Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 704331.65 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 313811 | Malaga NHS-Peña Annex | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 687096.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 500748 | Malajog Integrated School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 323404.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124138 | Malayog Elementary School | CALBAYOG CITY | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1866042.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124125 | Malopalo Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 991009.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124126 | Manguinoo Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 720607.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124019 | Matobato Elementary School | CALBAYOG CITY | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 596122.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 123996 | Naga Elemenetary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1424000.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124041 | Navarro Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 381033.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 123998 | Obrero Elementary School | CALBAYOG CITY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1695088.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 340001.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124106 | Panoypoy Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 321659.55 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124139 | Peña I Central Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1396476.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124072 | Pilar Elementary School | CALBAYOG CITY | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3779115.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124001 | Rawis Elementary School | CALBAYOG CITY | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 1872283.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124074 | Roxas II Elementary School | CALBAYOG CITY | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1833623.2 | 1 |  | Completed | 100% | [10 empty] | 45% Accomplishment (affected by Covid-19 Pandemic) resume work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 303650 | San Joaquin National HIgh School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 324464.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124048 | San Policarpo Central Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 974798.24 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124049 | Saputan Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1051815.33 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124075 | Sigo Elementary School | CALBAYOG CITY | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1871467.51 | 1 |  | Completed | 100% | [10 empty] | 45% Accomplishment (affected by Covid-19 Pandemic) resume work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 500238 | Tabawan Integrated School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1074941.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124003 | Tapae Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 697589.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124115 | Tarabucan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 380079.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124142 | Tinaplacan Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1406301.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Calbayog City | 124051 | Trinidad Central Elementary School | CALBAYOG CITY | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3695919.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122325 | Arteche Central Elementary School | ARTECHE | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 6465046.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303495 | Balangkayan National High School | BALANGKAYAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1390426.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122614 | Cantubi Elementary School | BALANGKAYAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1188892.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122618 | Guinpoliran Elementary School | BALANGKAYAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 821101.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122623 | Maramag Elementary School | BALANGKAYAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1501905.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122631 | Talisay Elementary School | BALANGKAYAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2614013.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1183642.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122501 | Sta. Cruz Elementary School | GENERAL MACARTHUR | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 821101.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122505 | Vigan Elementary School | GENERAL MACARTHUR | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1165930.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122515 | President Roxas Elementary School | GIPORLOS | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1171201.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122555 | Baras Elementary School | GUIUAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 826351.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122524 | Guiuan East Central School | GUIUAN | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 5191517.3 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303504 | Taytay Integrated School | GUIUAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 2003527.78 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122480 | Canciledes Elementary School | HERNANI | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1537532.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122575 | Jipapad Central School | JIPAPAD | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 6398216.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3292064.76 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122355 | TAGUITE ES | LAWAAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 815851.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122587 | Barobo Elementary School | LLORENTE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 808109.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | 0 | 1 | 18 | REPAIR OF CLASSROOMS | 5526925.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | 0 | 1 | 15 | REPAIR OF CLASSROOMS | 3976649.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122598 | Naubay Elementary School | LLORENTE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1212843.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122604 | Tabok Elementary School | LLORENTE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 803410.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 313514 | Maydolong National High School | MAYDOLONG | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2463918.37 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122532 | Anuron Elementary School | MERCEDES | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1202953.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122544 | Mercedes Central School | MERCEDES | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3000004.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122550 | San Roque Primary School | MERCEDES | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1217992.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122678 | Cantinio Primary School | QUINAPONDAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 849378.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303521 | Quinapondan National High School | QUINAPONDAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 818609.64 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122718 | Matarinao Elementary School | SALCEDO | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1222290.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | 34 | REPAIR OF CLASSROOMS | 2499885.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122719 | Sta. Cruz Primary School | SALCEDO | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1188892.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 313503 | Tagbacan National High School | SALCEDO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 864999.65 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 313507 | Nena National High School (Nena School of Arts and Trades) | SAN JULIAN | 0 | 1 | 16 | REPAIR OF CLASSROOMS | 6167023.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | SAN POLICARPO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1737539.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122744 | Tabo Elementary School | SAN POLICARPO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 869878.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Eastern Samar | 122752 | San Isidro Elementary School | SULAT | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1212843.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 120963 | Binongtoan Central School | ALANGALANG | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 525011.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 120969 | Hubang Elementary School | ALANGALANG | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1728546.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313341 | Mariano Salazar National High School | ALANGALANG | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 899987.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 120951 | Mariquita Cinco Memorial Elementary School | ALANGALANG | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1178550.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313335 | Palo National High School-Pawing Annex | PALO | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 1388194.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121762 | San Fernando Elementary School | PALO | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2744087.36 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region VIII | Leyte | 303424 | San Joaquin National High School | PALO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 604571.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1 | 1 | 20 | REPAIR OF CLASSROOMS | 1869087.94 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121954 | San Roque ES | TOLOSA | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 2322519.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 667493.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte |  | Telegrafo Elementary School Annex | TOLOSA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1963099.05 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121293 | Dagami North Central School | DAGAMI | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 700000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 303432 | Sta. Mesa National High School | DAGAMI | 2 | 1 | 26 | REPAIR OF CLASSROOMS | 1832713.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 303369 | Dulag National High School | DULAG | 2 | 1 | 1 | REPAIR OF CLASSROOM | 493523.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313336 | Bienvenido Guillera Celebre National High School | JARO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 804428.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 303371 | Granja-Kalinawan National High School | JARO | 2 | 1 | 28 | REPAIR OF CLASSROOMS | 1249347.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MACARTHUR | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 948410.35 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121816 | Halaba Primary School | PASTRANA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 458685.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121820 | Lourdes Primary School | PASTRANA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 378464.8 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121821 | Macalpiay Elementary School | PASTRANA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 717883.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313330 | Manaybanay National High School | PASTRANA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 735947.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121956 | Tanghas Elementary School | TOLOSA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 811316.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121212 | Casiongan Elementary School | CALUBIAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1005286.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313317 | Felix Caneja Lafuente National High School | CALUBIAN | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 1667039.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 313340 | Rafaelito Cabanas Martinez National High School | CALUBIAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 897969.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 303390 | Leyte National High School | LEYTE | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 802071.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121885 | Don Bernardo Elementary School | TABANGO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2415570.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 303416 | Pastor Salazar National High School | TABANGO | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1084464.66 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 121555 | Tongonan Elementary School | KANANGA | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1195699.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Leyte | 305522 | Matag-ob Stand Alone Senior High School | MATAG-OB | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2900000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VIII | Leyte | 121808 | Tabunok Elementary School | PALOMPON | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 941473.26 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122777 | Allen Central Elementary School | ALLEN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2219107.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122778 | Cabacungan ES | ALLEN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1688376.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122779 | Calarayan ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 421741.27 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122782 | Guin-Arawayan ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 296314.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122783 | Jubasan ES | ALLEN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1533908.06 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122784 | Kinaguitman ES | ALLEN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1873480.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122785 | Lagundi ES | ALLEN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1679784.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122786 | Lipata ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 297649.59 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122788 | Pili ES | ALLEN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1248177.71 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122844 | Baybay ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1754819.92 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122854 | Bocsol Es | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1238329.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122835 | Daganas ES | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1264299.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122839 | Guba Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 773392.82 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122869 | Hinatad ES | CATARMAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1523186.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122871 | McKinley ES | CATARMAN (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3354089.74 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122841 | New Rizal ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1994115.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122842 | Old Rizal ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2093096.36 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122859 | Paticua Elementary School | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1828854.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122860 | Salvacion Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1259293.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122850 | Somoge ES | CATARMAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2335859.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123058 | Barobaybay ES | LAVEZARES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1405261.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123080 | Bayho ES | LOPE DE VEGA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1269833.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123089 | Henaronagan ES | LOPE DE VEGA | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 414137.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123096 | Osme¤a ES | LOPE DE VEGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 209969.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122882 | Guibuangan ES | CATUBIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1020773.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122916 | Bangon Elementary school | GAMAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1840650.82 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122948 | Talisay Elementary School | LAOANG | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1744732.01 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122997 | Lo-ok ES | LAPINIG | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 665260.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 122999 | May-igot ES | LAPINIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1212193.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123000 | Palanas elementary school | LAPINIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1202836.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Northern Samar | 123006 | Bulao ES | LAS NAVAS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1729965.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Ormoc City | 124214 | Liloan CS | Ormoc City | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1132238.19 | 1 | 1105733 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123750 | Inaraguiao ES | STA. MARGARITA | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 4310353.12 | 1 | 4256944.87 | Completed | 100% | [9 empty] | VHITS | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 630232.36 | 1 | 624852.88 | Completed | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 303637 | Valerino C. Yancha MAS | Basey | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073110.41 | 1 | 1055584.99 | Completed | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123363 | BULUAN ES | CALBIGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 911764.14 | 1 | 909613.27 | Completed | 100% | [9 empty] | GG | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123679 | PELAON ES | CALBIGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 692955.19 | 1 | 690930.18 | Completed | 100% | [9 empty] | GG | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS | DARAM | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2826478.62 | 1 | 2810915.74 | Completed | 100% | [9 empty] | MORI | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123470 | BAKHAW ES | DARAM | 2 | 1 | 1 | REPAIR OF CLASSROOM | 300756.93 | 1 | 295957.19 | Completed | 100% | [9 empty] | MORI | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 313709 | BAKHAW NHS | DARAM | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 952365.62 | 1 | 947336.71 | Completed | 100% | [9 empty] | GPUY | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 303601 | DARAM NHS | DARAM | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 918756.27 | 1 | 913734.37 | Completed | 100% | [9 empty] | GPUY | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123919 | LOKILOKON ES | PARANAS | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 4873038.89 | 1 | 4870535.54 | Completed | 100% | [9 empty] | G BUILDERS | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123931 | TULA ES | PARANAS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 442423 | 1 | 439914.46 | Completed | 100% | [9 empty] | G BUILDERS | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123668 | LAYGAYON ES | PINABACDAO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 268194.84 | 1 | 264681.12 | Completed | 100% | [9 empty] | REVCON | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 313723 | Parasanon NHS | PINABACDAO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 2992512.26 | 1 | 2988110.24 | COMPLETED | 100% | [9 empty] | REVCON | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region VIII | Samar (Western Samar) | 123715 | CANMAHAGAY ES | SAN SEBASTIAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1852565.73 | 1 | 1829569.07 | Completed | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 313716 | Anibongon IS | SANTA RITA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 400384.67 | 1 | 398187.45 | Completed | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123777 | Bugho ES | SANTA RITA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 604135.15 | 1 | 600970.01 | COMPLETED | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2020 | Region VIII | Samar (Western Samar) | 303636 | TOMINAMOS IS | STA. RITA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 806808.3 | 1 | 802189.44 | Completed | 100% | [9 empty] | JFR | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Samar (Western Samar) | 123892 | Ulayan ES | VILLAREAL | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 730541.72 | 1 | 727268.02 | Completed | 100% | [9 empty] | REVCON | for award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Southern Leyte | 192024 | Tuba-on Elementary School | SILAGO | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1727522.54 | 1 | 1705367.27 | Completed | 100% |  |  | QRF-CY2020- Slope Protection | QRF-CY2020- Slope Protection | 2020-06-03 | 2020-06-15 | 2020-06-29 | 2020-07-27 | 2020-08-11 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | SLOPE PROTECTION | Completed
QRF 2020 | Region VIII | Tacloban City | 124255 | Cabalawan ES | TACLOBAN CITY (Capital) | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 1310206.11 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | JFR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 124235 | Lucio Vivero ES | TACLOBAN CITY (Capital) | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 1532003.85 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | 63 | REPAIR OF CLASSROOMS | 5302173.26 | 1 |  | Completed | 100% | 2020-10-31 | 2020-10-31 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | RD COBACHA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 63 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | TACLOBAN CITY (Capital) | 1 | 1 | 40 | REPAIR OF CLASSROOMS | 1853041.92 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | LRD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 124248 | Salvacion Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 655281.39 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 124259 | Sta. Elena ES | TACLOBAN CITY (Capital) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 1762162.47 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | GPUY CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | 30 | REPAIR OF CLASSROOMS | 991335.76 | 1 |  | Completed | 100% | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | VHITS D.G. BUILDERS & ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2020 | Region VIII | Tacloban City | 124242 | Tagpuro Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 15 | REPAIR OF CLASSROOMS | 2097695.31 | 1 |  | Completed | 100% | 2020-10-01 | 2020-10-01 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | 4 ANGLE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | CAR | Ifugao | 220001 | Cawayan PS - Annex (Alehwagon) | ASIPULO | 0 | 1 | 1 |  | 671652.1903 | 1 | 653896.26 | completed | 100% | 2021-12-05 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Ifugao | 135840 | Namulditan ES | HINGYON | 0 | 1 | 13 |  | 6595350.19 | 1 | 6505905.81 | completed | 100% | 2022-04-27 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 136194 | Ogo-og Elementary School | BARLIG | 0 | 1 | 1 | TY ULYSSES | 778141.6583 | 1 | 763168.63 | completed | 100% | 2021-10-16 | 2021-10-15 |  | INF-2021 R-013 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-17 | Precious Gold Builders | With Time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 319214 | Abatan National High School | BAUKO | 0 | 1 | 4 | TY ULYSSES | 2684754.87 | 1 | 2236169.62 | completed | 100% | 2021-12-28 | 2022-02-15 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | JBA Construction & Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 305252 | Mt. Data National High School | BAUKO | 0 | 1 | 3 | TY ULYSSES | 3743563.8722 | 1 | 3484672.67 | completed | 100% | 2021-12-28 | 2022-02-23 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-09-29 | Litangfan Const'n Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 136227 | Salin Elementary School | BAUKO | 0 | 1 | 2 | TY ULYSSES | 2778027.4376 | 1 | 2591147.54 | completed | 100% | 2021-12-28 | 2022-01-31 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | MNJD Const'n | Contract Perfection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 136227 | Salin Elementary School | BAUKO | 0 |  | 2 | TY ULYSSES | 6215361.4961 | 1 | 6020119.44 | completed | 100% | 2022-01-03 | 2022-01-31 |  | INF-2021 QNC-022 | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-08-06 | MNJD Const'n | Contract Perfection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 305245 | Tapapan National High School | BAUKO | 0 | 1 | 2 | TY ULYSSES | 7945852.9869 | 1 | 7385512 | completed | 100% | 2022-01-10 | 2022-02-28 |  | INF-2021 QNC-023 | 2021-06-04 | 2021-06-10 | 2021-06-23 | 2021-07-22 | 2021-08-13 | Litangfan Const'n Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | completed
QRF 2021 | CAR | Mt. Province | 319215 | Banguitan National High School | BESAO | 0 | 1 | 2 | TY ULYSSES | 1957051.643 | 1 | 1595448.46 | completed | 100% | 2021-12-28 | 2022-05-24 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-09-29 | Teging Const'n | for rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 136280 | Tonglayan Elementary School | NATONIN | 0 | 1 | 2 | TY ULYSSES | 1975225.7516 | 1 | 1864198.86 | Completed | 100% | 2021-10-27 | 2021-10-20 |  | INF-2021 R-021 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-13 | Sembri Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | CAR | Mt. Province | 136345 | Balugan Elementary School | SAGADA | 0 | 1 | 8 | TY ULYSSES | 9463865.3361 | 1 | 6600466.96 | completed | 100% | 2022-04-25 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-26 | Boy-cos Const'n | for rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | 3 | TY ULYSSES | 11415841.9303 | 1 | 8159781.5 | completed | 100% | 2022-09-30 |  |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-29 | LCDC Const'n | for rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | completed
QRF 2021 | CAR | Mt. Province | 136374 | Sayapot Elementary School | TADIAN | 0 | 1 | 3 | TY ULYSSES | 2746768.1146 | 1 | 2235121.15 | Completed | 100% | 2022-02-27 | 2022-03-25 |  |  | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-11-29 | LCDC Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | CAR | Mt. Province | 305267 | Tadian School of Arts and Trades | TADIAN | 0 | 1 | 38 | TY ULYSSES | 9181784.9073 | 1 | 8892002.04 | completed | 100% | 2022-01-15 | 2022-04-20 |  | INF-2021 R-021 | 2021-06-04 | 2021-06-10 | 2021-06-25 | 2021-07-22 | 2021-08-18 | JMMAS Const'n & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | 0 | 1 | 9 | FIRE INCIDENT | 2263841.54 | 1 | 2252902.36 | completed | 100% | [10 empty] | Post Qualification | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | completed
QRF 2021 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 103 | TY ULYSSES | 26196823.18 | 1 | 26027440.46 | Completed | 100% |  |  | QRF-2021-NCR-MARIKINA CITY-001 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-05 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 103 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 48 | TY ULYSSES | 12499062.18 | 1 | 12394039.4 | Completed | 100% |  |  | QRF-2021-NCR-MARIKINA CITY-002 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 48 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2 | 1 | 51 | TY ULYSSES | 10415199.95 | 1 | 10311102.1 | Completed | 100% |  |  | QRF-2021-NCR-MARIKINA CITY-003 |  | 2021-06-17 | 2021-06-23 | 2021-07-05 | 2021-07-21 | 2021-08-04 | DREAMWORX BUILDER & TRADING INCORPORATED |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 51 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1 | 1 | 11 | TY ULYSSES | 1961193.0659 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102444 | Gaddang ES | APARRI | 1 | 1 | 12 | TY ULYSSES | 2706117.1772 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102445 | Macanaya ES | APARRI | 1 | 1 | 9 | Repair | 2141175.2013 | 1 |  | Completed | 100% | 2021-12-07 | [9 empty] | Action Taken: abondoned (Issued of notice of termination) but commited to resumed until its completion) *They Already resume on the project site and comtinue the remaining item of works hoping to finished by the end of January 2023 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-01-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102665 | Aguiguican ES | GATTARAN | 1 | 1 | 7 | TY ULYSSES | 2481050.2 | 1 |  | Completed | 100% | 2021-11-15 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102653 | Capissayan Elementary School | GATTARAN | 1 | 1 | 3 | TY ULYSSES | 1050018.12 | 1 |  | Completed | 100% | 2021-12-07 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-01-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102668 | Casicallan ES | GATTARAN | 1 | 1 | 8 | TY ULYSSES | 2900130.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102659 | Naddungan ES | GATTARAN | 1 | 1 | 7 | TY ULYSSES | 2490205.2 | 1 |  | Completed | 100% | 2021-11-15 | [9 empty] | implementation of corrective observation and variation oerder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1 | 1 | 7 | TY ULYSSES | 1969398.067 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102749 | Malanao Elementary School | LAL-LO | 1 | 1 | 7 | TY ULYSSES | 2339361.5155 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102605 | Bilibigao ES | CLAVERIA | 2 | 1 | 5 | TY ULYSSES | 1750000.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 300449 | Claveria NHS | CLAVERIA | 2 | 1 | 10 | TY ULYSSES | 4685211.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102920 | Mabnang ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 1681214.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102613 | Magdalena ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 726196.1333 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102621 | Santiago ES | CLAVERIA | 2 | 1 | 3 | TY ULYSSES | 2325142.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102755 | Aggunetan ES | LASAM | 2 | 1 | 1 | TY ULYSSES | 615737.8313 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102848 | Bangan ES | SANCHEZ-MIRA | 2 | 1 | 6 | TY ULYSSES | 2535057.7196 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 155007 | Niug Norte ES | SANTO NIÑO (FAIRE) | 2 | 1 | 4 | TY ULYSSES | 1283384.6162 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102402 | Abolo ES | AMULUNG | 3 | 1 | 6 | TY ULYSSES | 2998603.6336 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102633 | Enrile North CS | ENRILE | 3 | 1 | 20 | TY ULYSSES | 5606467.2195 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102634 | Enrile West CS | ENRILE | 3 | 1 | 12 | TY ULYSSES | 2924320.6537 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102641 | Sabino Acorda CS | ENRILE | 3 | 1 | 10 | TY ULYSSES | 2502488.1509 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102722 | Sta. Teresa ES | IGUIG | 3 | 1 | 3 | TY ULYSSES | 1050121.8 | 1 |  | Completed | 100% | 2021-12-04 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102804 | Nanguillattan E/S | PEÑABLANCA | 3 | 1 | 6 | TY ULYSSES | 1949536.599 | 1 |  | Completed | 100% | 2021-12-04 | [9 empty] | subtantially completed ( implementation of corrective observation and variation oerder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Cagayan | 102866 | Andarayan ES | SOLANA | 3 | 1 | 2 | TY ULYSSES | 832231.7522 | 1 |  | Completed | 100% | 2021-12-04 | [9 empty] | implementation of corrective observation and variation oerder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | City of Ilagan | 103367 | Marana 2nd ES | ILAGAN CITY (CAPITAL) | 1 | 1 | 2 | TY ULYSSES | 3932382.7094 | 1 |  | Completed | 100% | 2021-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Isabela | 103139 | Aggub Elementary School | CABANGAN | 1 | 1 | 4 | TY ULYSSES | 2733999.3079 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103158 | Pilig Abajo Elementary School | CABANGAN | 1 | 1 | 7 | TY ULYSSES | 1341684.8855 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103159 | Pilig Alto Elementary School | CABANGAN | 1 | 1 | 9 | TY ULYSSES | 1774795.9471 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103270 | Jimenez Multigrade School | DELFIN ALBANO (MAGSAYSAY) | 1 | 1 | 2 | TY ULYSSES | 631161.8695 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103847 | Mozzozzin Elementary School | SANTA MARIA | 1 | 1 | 11 | TY ULYSSES | 3864847.0826 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103853 | San Rafael Elementary School | SANTA MARIA | 1 | 1 | 5 | TY ULYSSES | 932853.6959 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103872 | Ammugauan Primary School | SANTO TOMAS | 1 | 1 | 2 | TY ULYSSES | 309086.169 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103867 | Malapagay Elementary School | SANTO TOMAS | 1 | 1 | 5 | TY ULYSSES | 724487.0373 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103868 | San Rafael Abajo Primary School | SANTO TOMAS | 1 | 1 | 4 | TY ULYSSES | 1045842.6512 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103876 | Fugu Abajo Elementary School | TUMAUINI | 1 | 1 | 8 | TY ULYSSES | 1091831.4829 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103877 | Fugu Elementary School | TUMAUINI | 1 | 1 | 2 | TY ULYSSES | 4169034.1674 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Isabela | 300586 | Josefina Albano National High School | TUMAUINI | 1 | 1 | 7 | TY ULYSSES | 1837727.1495 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103879 | Malamag Elementary School | TUMAUINI | 1 | 1 | 5 | TY ULYSSES | 1150062.2194 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103900 | Paragu Elementary School | TUMAUINI | 1 | 1 | 3 | TY ULYSSES | 5889429.2734 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Isabela | 103885 | San Mateo Elementary School | TUMAUINI | 1 | 1 | 6 | TY ULYSSES | 3398709.8655 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103883 | Sta. Catalina Elementary School | TUMAUINI | 1 | 1 | 3 | TY ULYSSES | 1918330.2681 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Isabela | 103904 | Tumauini West Central School | TUMAUINI | 1 | 1 | 2 | TY ULYSSES | 3839412.9575 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Isabela | 500075 | Banquero Integrated School | REINA MERCEDES | 2 | 1 | 2 | TY ULYSSES | 4169034.1674 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Isabela | 501150 | Daragutan West Integrated School | SAN MARIANO | 2 | 1 | 2 | TY ULYSSES | 3839412.9575 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Nueva Vizcaya | 300615 | Alfonso CastaÃ±eda NHS | ALFONSO CASTAÑEDA | 0 | 1 | 1 | TY ULYSSES | 1875000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | 0 | 1 | 3 | TY ULYSSES | 1650000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 103991 | Labang ES | AMBAGUIO | 0 | 1 | 4 | TY ULYSSES | 2440000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 300525 | Tiblac National High School | AMBAGUIO | 0 | 1 | 5 | TY ULYSSES | 2750000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 103966 | Abian ES | BAMBANG | 0 | 1 | 9 | TY ULYSSES | 4950000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 103951 | Aliaga ES | BAMBANG | 0 | 1 | 5 | TY ULYSSES | 2750000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 103964 | San Leonardo ES | BAMBANG | 0 | 1 | 6 | TY ULYSSES | 3000000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 103990 | Kakilingan ES | BAYOMBONG (Capital) | 0 | 1 | 2 | TY ULYSSES | 1096000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 104046 | Lamo ES | DUPAX DEL NORTE | 0 | 1 | 2 | TY ULYSSES | 5039545 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region II | Nueva Vizcaya | 306208 | Eastern Nueva Vizcaya National High School | KASIBU | 0 | 1 | 2 | TY ULYSSES | 1040000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 104100 | Paquet ES | KASIBU | 0 | 1 | 4 | TY ULYSSES | 2200000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 500097 | Dippog HS | QUEZON | 0 | 1 | 4 | TY ULYSSES | 2040000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 300649 | Santa Fe National High School | SANTA FE | 0 | 1 | 3 | TY ULYSSES | 1100000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Nueva Vizcaya | 300651 | Uddiawan National High School | SOLANO | 0 | 1 | 4 | TY ULYSSES | 1680000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 501561 | Der-an Integrated School | DIFFUN | 0 | 1 | 4 | TY ULYSSES | 1576661.54 | 1 | 1565908.07 | Completed | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 156507 | Turayok Elementary School | DIFFUN | 0 | 1 | 3 | TY ULYSSES | 502430.56 | 1 | 499757.77 | Completed | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 500105 | San Martin IS | MADDELA | 0 | 1 | 10 | TY ULYSSES | 2232025.25 | 1 |  | Completed | 100% |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  | 2021-10-11 | Proline Construction | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 104338 | San Salvador ES | MADDELA | 0 | 1 | 4 | TY ULYSSES | 1495055.32 | 1 | 1240011.28 | Completed | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-16 | Dalcon Construction | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 500626 | Villa Gracia IS | MADDELA | 0 | 1 | 6 | TY ULYSSES | 2040756.69 | 1 | 1693717.4 | Completed | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-16 | Dalcon Construction | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 501849 | Kimmabayo Integrated School | NAGTIPUNAN | 0 | 1 | 3 | TY ULYSSES | 337821.8 | 1 |  | Completed | 100% |  |  |  |  | 2021-07-28 | 2021-08-03 | 2021-08-16 |  | 2021-10-11 | Proline Construction | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region II | Quirino | 104380 | Tres Reyes ES | SAGUDAY | 0 | 1 | 7 | TY ULYSSES | 1989445.35 | 1 | 1979701.36 | Completed | 100% |  |  |  |  | 2021-06-24 | 2021-06-30 | 2021-07-12 | 2021-07-21 | 2021-08-24 | 619 Builders Const. Corp. | completed including savings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 104409 | Baler CS | BALER (Capital) | 0 | 1 | 17 | TY ULYSSES | 12208837.24 | 1 | 12145374.43 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-05 | VANMARVIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 500117 | Mariano L. Sindac IS | BALER (Capital) | 0 | 1 | 4 | TY ULYSSES | 2855188.91 | 1 | 2826418.46 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | VANMARVIL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 157513 | Butas na Bato ES | DINGALAN | 0 | 1 | 2 | TY ULYSSES | 1443287.54 | 1 | 824303.98 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | FNR Builders and Sons Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 104462 | Umiray ES | DINGALAN | 0 | 1 | 9 | TY ULYSSES | 6119107.42 | 1 | 3473983.7 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | FNR Builders and Sons Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 300695 | Umiray NHS | DINGALAN | 0 | 1 | 12 | TY ULYSSES | 14192889.5614 | 1 | 8060094.7 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | FNR Builders and Sons Supply Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 104484 | Bagtu ES | MARIA AURORA | 0 | 1 | 7 | TY ULYSSES | 4959821.7155 | 1 | 3124102.63 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | MACCO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Aurora | 104516 | Dikapinisan ES | SAN LUIS | 0 | 1 | 6 | TY ULYSSES | 4282656.05 | 1 | 2698145.03 | Completed | 100% | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | MACCO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bataan | 104577 | Jose C. Payumo Jr. ES | DINALUPIHAN | 1 | 1 | 6 | TY ULYSSES | 3696132.03 | 1 | 3675824.03 | Completed | 100% | 2021-10-20 | 2021-08-31 | QRF2021-001 | 2021-CON-00012 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-24 | T. G. OCAMPO CONSTRUCTION & SURVEYING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bataan | 104544 | Binukawan ES | BAGAC | 2 | 1 | 3 | TY ULYSSES | 1443939.49 | 1 | 1423597.95 | Completed | 100% | 2021-09-20 | 2021-07-26 | QRF2021-002 | 2021-CON-00011 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | TURQUOISE CONSTRUCTION & REALTY DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bataan | 104684 | Puting Buhangin ES | ORION | 2 | 1 | 9 | TY ULYSSES | 4132161.22 | 1 | 4111644.41 | Completed | 100% | 2021-10-20 | 2021-08-31 | QRF2021-003 | 2021-CON-00013 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | RODMAC CONSTRUCTION &TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bataan | 104685 | Sabatan ES | ORION | 2 | 1 | 5 | TY ULYSSES | 2637397.45 | 1 | 2616736.88 | Completed | 100% | 2021-10-20 | 2021-09-07 | QRF2021-004 | 2021-CON-00014 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-24 | ALTITUDE ENGINEERING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bataan | 104698 | Sta. Rosa ES | PILAR | 2 | 1 | 5 | TY ULYSSES | 3568719.22 | 1 | 3548642.04 | Completed | 100% | 2021-10-20 | 2021-09-06 | QRF2021-005 | 2021-CON-00015 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | RODMAC CONSTRUCTION &TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bulacan | 158542 | St. Martha Elementary School | BOCAUE | 2 | 1 | 16 | TY ULYSSES | 751760.04 | 1 | 697369.88 | Completed | 100% | 2021-10-22 | 2021-10-12 | PB-21-014 | PB-21--025 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-31 | DUAMON Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bulacan | 127616 | Cacarong Bata Elementary School | PANDI | 2 | 1 | 15 | TY ULYSSES | 1781937.72 | 1 | 2105320.7 | Completed | 100% | 2021-11-08 | 2021-10-27 | PB-21-013 | PB-21--024 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | EMICA Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Bulacan | 105035 | Garlang Elementary School | SAN ILDEFONSO | 3 | 1 | 0 | TY ULYSSES | 2807039.59 | 1 | 1556027.8 | Completed | 100% | 2021-11-08 | 2021-10-20 | PB-21-012 | PB-21--023 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | RHR Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | previous yrs |  |  |  |  | others | Completed
QRF 2021 | Region III | Bulacan | 306728 | Sta. Catalina Bata National High School | SAN ILDEFONSO | 3 | 1 | 4 | TY ULYSSES | 432073.49 | 1 | 358601.03 | Completed | 100% | 2021-09-24 | 2021-09-20 | PB-21-015 | PB-21--026 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | EMICA Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Gapan City | 500727 | Sto. Cristo Proper Integrated School | CITY OF GAPAN | 4 | 1 | 4 | TY ULYSSES | 573955.04 | 1 | 563657.79 | Completed | 100% | 2021-08-27 | 2021-08-01 | 2021-06-09-002-QRF | 2021-06-09-002-QRF | 2021-06-10 | 2021-06-15 | 2021-06-15 | 2021-06-18 | 2021-06-28 | Joynieltin Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Malolos City | 104867 | Caingin ES | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | TY ULYSSES | 1848240.83 | 1 | 1841861.9 | Completed | 100% | 2021-12-13 |  |  |  | 06/23-06/302021 | 2021-06-30 | 2021-07-12 | 2021-07-15 | 2021-08-16 | POWERMETAL CONSTRUCTION CO. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 159015 | Osmena ES | QUEZON | 1 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105625 | Ricardo L. Joson Elementary School | QUEZON | 1 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105634 | Tomas Joson ES | QUEZON | 1 | 1 | 3 | TY ULYSSES | 1504463.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN | 2 | 1 | 3 | TY ULYSSES | 1707160.4868 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105498 | General Ricarte ES | LLANERA | 2 | 1 | 4 | TY ULYSSES | 2043160.4652 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105655 | San Esteban ES | RIZAL | 2 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 3 | TY ULYSSES | 1436427.5123 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105195 | Ariendo ES | BONGABON | 3 | 1 | 3 | TY ULYSSES | 1690473.37 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105306 | F. Buencamino Sr. Integrated School (F. Buencamino Sr. ES) | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105313 | Tagumpay ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | TY ULYSSES | 1066073.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105757 | Pepito B. Bernardo Mem. School | SANTA ROSA | 3 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105227 | San Roque ES | CABIAO | 4 | 1 | 3 | TY ULYSSES | 1942651.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105232 | Sta. Isabel Elementary School | CABIAO | 4 | 1 | 4 | TY ULYSSES | 2177382.21 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105454 | San Vicente ES | JAEN | 4 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105681 | Calaba ES | SAN ISIDRO | 4 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105683 | Malapit East ES | SAN ISIDRO | 4 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO | 4 | 1 | 6 | TY ULYSSES | 3042657.1725 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105899 | Arenas ES | ARAYAT | 3 | 1 | 6 | TY ULYSSES | 3803405 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105903 | Cacutud ES | ARAYAT | 3 | 1 | 7 | TY ULYSSES | 4312538.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105882 | Camba ES | ARAYAT | 3 | 1 | 10 | TY ULYSSES | 3124890.21 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 300884 | Camba NHS | ARAYAT | 3 | 1 | 11 | TY ULYSSES | 3191432.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 306907 | Candating NHS | ARAYAT | 3 | 1 | 9 | TY ULYSSES | 1574153.2 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105884 | Cupang Elementary School | ARAYAT | 3 | 1 | 3 | TY ULYSSES | 1650713.65 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105891 | San Juan Bano ES | ARAYAT | 3 | 1 | 4 | TY ULYSSES | 2049694.53 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105933 | Dalayap ES | CANDABA | 4 | 1 | 3 | TY ULYSSES | 1899062.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105948 | Tenejero ES | CANDABA | 4 | 1 | 2 | TY ULYSSES | 1273776.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Pampanga | 105949 | Vizal San Pablo II ES | CANDABA | 4 | 1 | 7 | TY ULYSSES | 4723728.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Tarlac City | 106729 | Asturias ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | TY ULYSSES | 652501.55 | 1 | 650309.31 | Completed | 100% | 2021-08-31 | 2021-08-31 | [7 empty] | J.P. Aquino Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Tarlac City | 106743 | Paraiso ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | TY ULYSSES | 1093868.34 | 1 | 1040671.09 | Completed | 100% | 2021-08-31 | 2021-08-31 | [7 empty] | J.P. Aquino Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Tarlac City | 106744 | San Carlos ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | TY ULYSSES | 1062165.41 | 1 | 1059953.12 | Completed | 100% | 2021-08-26 | 2021-08-26 | [7 empty] | Boycing Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Zambales | 106974 | Almasin Elementary School | SANTA CRUZ | 2 | 1 | 13 | TY ULYSSES | 5122463.9104 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region III | Zambales | 501226 | Don Brigido Miraflor Integrated School | SANTA CRUZ | 2 | 1 | 25 | TY ULYSSES | 6794925.58 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Imus City | 301190 | Gen. Emilio Aguinaldo NHS (Imus) | IMUS | 3 | 1 | 16 | TY ULYSSES | 337822.31 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Imus City | 107974 | Imus Pilot Elementary School | IMUS | 3 | 1 | 20 | TY ULYSSES | 143612.61 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 108205 | Paciano Rizal ES | BAY | 2 | 1 | 2 | TY ULYSSES | 669527.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 108311 | Mayondon Elementary School | LOS BAÑOS | 2 | 1 | 8 | TY ULYSSES | 89932.67 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Laguna | 307927 | Dayap National Integrated High School | CALAUAN | 3 | 1 | 12 | TY ULYSSES | 256638.82 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108702 | Cablao ES | GENERAL NAKAR | 1 | 1 | 2 | TY ROLLY/QUINTA | 1666261.4847 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 302394 | Apad Jomalig National High School (Apad NHS) | JOMALIG | 1 | 1 | 9 | TY ROLLY/QUINTA | 7435608.7135 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108986 | Katakian ES | PATNANUNGAN | 1 | 1 | 3 | TY ROLLY/QUINTA | 1067248.0882 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 | 1 | 12 | TY ROLLY/QUINTA | 4632762.13 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108552 | Siain ES | BUENAVISTA | 3 | 1 | 1 | TY ROLLY/QUINTA | 471611.1288 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108553 | Villa Aurora ES | BUENAVISTA | 3 | 1 | 2 | TY ROLLY/QUINTA | 841649.8068 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108696 | San Vicente ES | GENERAL LUNA | 3 | 1 | 3 | TY ROLLY/QUINTA | 755476.4023 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108877 | Macalelon Central Elementary School | MACALELON | 3 | 1 | 3 | TY ROLLY/QUINTA | 1473519.8429 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108918 | Acaciahan ES | MULANAY | 3 | 1 | 5 | TY ROLLY/QUINTA | 1026885.1208 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108927 | Canuyep ES | MULANAY | 3 | 1 | 6 | TY ROLLY/QUINTA | 1256908.8576 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108938 | Patabog ES | MULANAY | 3 | 1 | 6 | TY ROLLY/QUINTA | 4747820.6541 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301394 | SAN ISIDRO NATIONAL HIGH SCHOOL, PADRE BURGOS | PADRE BURGOS | 3 | 1 | 13 | TY ROLLY/QUINTA | 5395013.4368 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109007 | Pitogo CS I | PITOGO | 3 | 1 | 9 | TY ROLLY/QUINTA | 2155169.6406 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109008 | Pitogo CS II | PITOGO | 3 | 1 | 11 | TY ROLLY/QUINTA | 2298863.312 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109091 | Camflora Elementary School- Annex | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2960305.1483 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2098782.202 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109093 | Mangero Elementary School | SAN ANDRES | 3 | 1 | 6 | TY ROLLY/QUINTA | 1958316.844 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109098 | Talisay ES | SAN ANDRES | 3 | 1 | 4 | TY ROLLY/QUINTA | 2214963.773 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109116 | Bayog ES | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | TY ROLLY/QUINTA | 2140731.5801 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301298 | Dr. Vivencio V. Marquez National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | TY ROLLY/QUINTA | 2950995.667 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 15 | TY ROLLY/QUINTA | 4727285.321 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109126 | Mabuhay ES | SAN FRANCISCO (AURORA) | 3 | 1 | 3 | TY ROLLY/QUINTA | 1712177.4789 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301369 | Pagsangahan NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 8 | TY ROLLY/QUINTA | 1606393.954 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301368 | Renato Edaño Vicencio NHS (Formerly Pagsangahan NHS-Don Juan Vercelos Annex) | SAN FRANCISCO (AURORA) | 3 | 1 | 12 | TY ROLLY/QUINTA | 3174436.7974 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308003 | Sto. Niño National High School (Formerly Pagsangahan NHS Ext. Sto. Niño) | SAN FRANCISCO (AURORA) | 3 | 1 | 10 | TY ROLLY/QUINTA | 2285567.4959 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109134 | Tayuman Elementary School | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | TY ROLLY/QUINTA | 1903232.7235 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109136 | Viva Antipolo ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | TY ROLLY/QUINTA | 1969455.334 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109142 | Calwit ES | SAN NARCISO | 3 | 1 | 4 | TY ROLLY/QUINTA | 3248893.3842 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 6 | TY ROLLY/QUINTA | 1526895.2989 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109149 | Rizal ES | SAN NARCISO | 3 | 1 | 3 | TY ROLLY/QUINTA | 2577000.2093 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109154 | Vigo CES | SAN NARCISO | 3 | 1 | 11 | TY ROLLY/QUINTA | 2387060.8623 | 1 |  | Completed | 100% | [10 empty] | Mobilization/ No Suspension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109302 | Punta Elementary School | UNISAN | 3 | 1 | 5 | TY ROLLY/QUINTA | 3283133.6012 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109306 | Unisan CES | UNISAN | 3 | 1 | 3 | TY ROLLY/QUINTA | 1936317.8628 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 301414 | Unisan Integrated High School (Formerly Unisan NHS) | UNISAN | 3 | 1 | 6 | TY ROLLY/QUINTA | 2969709.897 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108831 | Alat-alatin ES | LOPEZ | 4 | 1 | 6 | TY ROLLY/QUINTA | 3101919.5873 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 108846 | Jongo ES | LOPEZ | 4 | 1 | 5 | TY ROLLY/QUINTA | 1634469.166 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 109214 | Mapulot ES | TAGKAWAYAN | 4 | 1 | 5 | TY ROLLY/QUINTA | 1870352.8615 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Quezon | 308002 | Mapulot National High School | TAGKAWAYAN | 4 | 1 | 8 | TY ROLLY/QUINTA | 3894221.749 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107749 | Balele ES | CITY OF TANAUAN | 3 | 1 | 8 | TY ROLLY | 2156030 | 1 |  | Completed | 100% |  | 2023-09-11 |  |  | 2023-05-10 | 2023-05-19 | 2023-06-08 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107751 | Banjo East ES | CITY OF TANAUAN | 3 | 1 | 9 | TY ROLLY | 3599667.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107762 | Laurel ES | CITY OF TANAUAN | 3 | 1 | 4 | TY ROLLY | 2472980.59 | 1 |  | Completed | 100% | 2023-10-09 | 0 |  |  | 2023-05-10 | 2023-05-19 | 2023-05-30 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107764 | Mahabang Buhangin Elementary School | CITY OF TANAUAN | 3 | 1 | 4 | TY ROLLY | 2799853.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107767 | Maugat ES | CITY OF TANAUAN | 3 | 1 | 7 | TY ROLLY | 4029242.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107783 | Tapia ES | CITY OF TANAUAN | 3 | 1 | 6 | TY ROLLY | 1443834.22 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tanauan City | 107784 | Tinurik ES | CITY OF TANAUAN | 3 | 1 | 9 | TY ROLLY | 6116147.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS | 1 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 1309900.7 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2021 | Region IV-B | Calapan City | 111570 | Adriatico Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 4557110.36 | 1 | 4529768 | Completed | 100% | 2022-01-03 | 2021-12-29 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111552 | Batino Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 2891497.22 | 1 | 2868365.24 | Completed | 100% | 2021-11-25 | 2021-11-12 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111556 | Bucayao ES | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1038197.99 | 1 | 1033604.25 | Completed | 100% | 2021-11-20 | 2021-11-19 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 309402 | Bucayao National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 3286043.67 | 1 | 3270418.85 | Completed | 100% | 2021-11-20 | 2021-11-19 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | KARANGYAN BUILDERS & TRADERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111561 | Caguisikan Eelementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 1637143.15 | 1 | 1624046 | Completed | 100% | 2021-11-25 | 2021-11-12 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111559 | Camilmil Central School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | TY QUINTA | 3630584.59 | 1 | 3593552.88 | Completed | 100% | 2022-01-30 | 2022-12-10 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | ETVR TRADING AND CONSTRUCTION | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111537 | Guinobatan Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 5 | TY QUINTA | 2750105.37 | 1 | 2733605 | Completed | 100% | 2021-11-18 | 2021-11-10 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111560 | Gutad Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 8 | TY QUINTA | 3252320.95 | 1 | 3219147.32 | Completed | 100% | 2022-01-30 | 2022-12-10 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | ETVR TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 301805 | Managpi National High School | CITY OF CALAPAN (Capital) | 1 | 1 | 4 | TY QUINTA | 1306718.37 | 1 | 1289731.03 | Completed | 100% | 2021-09-14 | 2021-09-28 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 6 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111542 | N. Aboboto Memorial School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1528104.26 | 1 | 1518936 | Completed | 100% | 2021-11-18 | 2021-11-10 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111546 | San Antonio Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 6 | TY QUINTA | 2802699.27 | 1 | 2788699 | Completed | 100% | 2022-01-19 | 2022-01-19 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111572 | Sta. Rita Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 655485.33 | 1 | 649964.02 | Completed | 100% | 2021-09-14 | 2021-09-28 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-30 | 2021-07-06 | 2021-07-09 | CMSEL CONSTRUCTION AND DEVELOPER | CLUSTER 7 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111548 | Sto. Niño Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 7 | TY QUINTA | 3685103.64 | 1 | 3671100 | Completed | 100% | 2022-01-19 | 2022-01-19 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | F.S. SUGAY CONSTRUCTION & SUPPLIES | CLUSTER 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Calapan City | 111549 | Suqui Elementary School | CITY OF CALAPAN (Capital) | 1 | 1 | 3 | TY QUINTA | 1370698.3 | 1 | 1362474 | Completed | 100% | 2022-01-03 | 2021-12-29 | N/A | N/A | 2021-06-09 | 2021-06-17 | 2021-06-29 | 2021-07-06 | 2021-07-09 | MARC JILL CONSTRUCTION | CLUSTER 4 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109887 | Bamban Elementary School | BOAC (Capital) | 0 | 1 | 7 | TY ROLLY/QUINTA | 3597158.1006 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109870 | Don Luis Hidalgo MS | BOAC (Capital) | 0 | 1 | 2 | TY ROLLY/QUINTA | 1427222.0394 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109881 | SAWI ES | BOAC NORTH | 0 | 1 | 8 | TY ROLLY/QUINTA | 3446116.6797 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109894 | CATUBUGAN ES | BOAC SOUTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 2236369.685 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109915 | Pag-Asa ElmentarySchool | BUENAVISTA | 0 | 1 | 2 | TY ROLLY/QUINTA | 743165.8126 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109919 | YOOK ES | BUENAVISTA | 0 | 1 | 9 | TY ROLLY/QUINTA | 3419832.4691 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 169007 | Tiguion I ES | GASAN | 0 | 1 | 2 | TY ROLLY/QUINTA | 667532.217 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109951 | MENDEZ ES | MOGPOG | 0 | 1 | 5 | TY ROLLY/QUINTA | 1810247.8259 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109955 | PILI ES | MOGPOG | 0 | 1 | 1 | TY ROLLY/QUINTA | 434582.022 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-09-014 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-06 | 2021-09-30 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 110001 | LIPA ELEMENTARY | SANTA CRUZ | 0 | 1 | 3 | TY ROLLY/QUINTA | 1212028.4378 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109964 | DEVILLA ES | SANTA CRUZ EAST | 0 | 1 | 4 | TY ROLLY/QUINTA | 1371797.2861 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109965 | HAGUIMIT ES | SANTA CRUZ EAST | 0 | 1 | 7 | TY ROLLY/QUINTA | 2113979.0439 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 301549 | MAKAPUYAT NHS | SANTA CRUZ EAST | 0 | 1 | 29 | TY ROLLY/QUINTA | 8500786.1742 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109968 | MASALUKOT ES | SANTA CRUZ EAST | 0 | 1 | 6 | TY ROLLY/QUINTA | 2265397.0587 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-017 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109980 | BALIIS ES | SANTA CRUZ NORTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 1310502.0616 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109981 | BALOGO ES | SANTA CRUZ NORTH | 0 | 1 | 7 | TY ROLLY/QUINTA | 2407759.2219 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109993 | PUNONG ES | SANTA CRUZ NORTH | 0 | 1 | 8 | TY ROLLY/QUINTA | 2468258.0069 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109997 | GABALDON ES | SANTA CRUZ SOUTH | 0 | 1 | 17 | TY ROLLY/QUINTA | 5418256.7031 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 109998 | KAGANHAO ES | SANTA CRUZ SOUTH | 0 | 1 | 4 | TY ROLLY/QUINTA | 1129181.2663 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 110002 | MAKULAPNIT ES | SANTA CRUZ SOUTH | 0 | 1 | 5 | TY ROLLY/QUINTA | 1008983.8142 | 1 |  | Completed | 100% | 2022-01-28 |  | N/A | 2021-10-019 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-22 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 110015 | BONLIW ES | TORRIJOS | 0 | 1 | 13 | TY ROLLY/QUINTA | 3292252.9475 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 301533 | Bonliw National High School | TORRIJOS | 0 | 1 | 14 | TY ROLLY/QUINTA | 5697127.4403 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 110020 | Kay Duke PS | TORRIJOS | 0 | 1 | 2 | TY ROLLY/QUINTA | 1091716.3094 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 301562 | SIBUYAO NHS | TORRIJOS | 0 | 1 | 8 | TY ROLLY/QUINTA | 2997896.4227 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Marinduque | 110036 | TORRIJOS CS | TORRIJOS | 0 | 1 | 7 | TY ROLLY/QUINTA | 4575658.4189 | 1 |  | Completed | 100% | 2022-01-18 |  | N/A | 2021-09-018 | 2021-07-22 | 2021-07-30 | 2021-08-11 | 2021-09-23 | 2021-10-13 | GS MOTAR CONTRACTORS BUILDERS AND TRADING | with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110077 | Alipondo Elementary School | CALINTAAN | 0 | 1 | 3 | TY QUINTA | 1031982.4068 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110078 | BAGONG SILANG ELEMENTARY SCHOOL | CALINTAAN | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 169501 | Bagong Silang ES Cansilaw ANNEX | Calintaan | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110082 | Concepcion ES | Calintaan | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110088 | Nayong Kalikasan Elementary School | CALINTAAN | 0 | 1 | 4 | TY QUINTA | 1987269.1385 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110089 | Nilapso ES | Calintaan | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110093 | Tanyag ES Annex - (Gutad PS) | CALINTAAN | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110122 | Cabag PS | Magsaysay | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110126 | Canabang ES | Magsaysay | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110147 | Tilaga ES | Magsaysay | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110198 | Jose Lopez Elementary School | RIZAL | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 169511 | Mendigorin Elementary School | Rizal | 0 | 1 | 6 | TY QUINTA | 2942555.8703 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110203 | Pitogo Elementary School | RIZAL | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110205 | Rumbang ES | Rizal | 0 | 1 | 9 | TY QUINTA | 4375485.9679 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110279 | Bangkal ES | San Jose | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 | 1199113.05 | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110250 | Bubog 1 ES | San Jose | 0 | 1 | 7 | TY QUINTA | 3420199.2361 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110280 | Bunlao ES | San Jose | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 | 798945.42 | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110262 | Camanggahan Elementary School | San Jose | 0 | 1 | 6 | TY QUINTA | 2942555.8703 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110299 | G.E. Ramirez Memorial School | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110287 | Ipil ES | San Jose | 0 | 1 | 2 | TY QUINTA | 1031982.4068 | 1 | 799455.44 | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110252 | Labangan ES | San Jose | 0 | 1 | 9 | TY QUINTA | 4375485.9679 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110304 | MANGARIN ELEMENTARY SCHOOL | San Jose | 0 | 1 | 5 | TY QUINTA | 2576920.34 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110305 | Mapaya I ES | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110269 | San Agustin ES | San Jose | 0 | 1 | 10 | TY QUINTA | 4853129.3338 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110270 | San Agustin ES ANNEX (D-6) | San Jose | 0 | 1 | 5 | TY QUINTA | 2464912.5044 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Occidental Mindoro | 110255 | San Roque 1 ES | San Jose | 0 | 1 | 3 | TY QUINTA | 1509625.7726 | 1 |  | Completed | 100% | 2021-11-21 | 2021-12-15 | N/A | N/A | 2021-06-03 | 2021-06-11 | 2021-07-05 | 2021-07-12 | 2021-07-19 | Hawkstow Construction Development | delay due to pandemic | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 110709 | Tadyawan Minority School | Victoria | 1 | 1 | 3 | TY QUINTA | 915672.4726 | 1 | 908050.71 | Completed | 100% | Sept. 30, 2021 | Sept. 30, 2021 | QRF 2021-R IVB-Oriental Mindoro-028 | 013-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | CMSEL Const. & Developer |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 110409 | Alimawan ES | Bulalacao | 2 | 1 | 2 | TY QUINTA | 902019.9735 | 1 | 895000 | Completed | 100% | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-007 | 011-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 110411 | Balatasan ES | Bulalacao | 2 | 1 | 4 | TY QUINTA | 1571924.1544 | 1 | 1550000 | Completed | 100% | 2021-10-31 | 2021-10-01 | QRF 2021-R IVB-Oriental Mindoro-018 | 012-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 170035 | Bating ES | Bulalacao | 2 | 1 | 2 | TY QUINTA | 900193.4012 | 1 | 895000 | Completed | 100% | 2022-01-14 | 2021-12-03 | QRF 2021-R IVB-Oriental Mindoro-010 | 011-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 110414 | Bulalacao CS | Bulalacao | 2 | 1 | 14 | TY QUINTA | 4299621.5274 | 1 | 4280000 | Completed | 100% | 2022-01-14 | 2022-01-11 | QRF 2021-R IVB-Oriental Mindoro-008 | 009-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 309033 | Cabugao National High School | Bulalacao | 2 | 1 | 3 | TY QUINTA | 509380.63 | 1 | 505000 | Completed | 100% | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-005 | 010-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 110422 | Maujao ES | Bulalacao | 2 | 1 | 3 | TY QUINTA | 1392252.2753 | 1 | 1385000 | Completed | 100% | 2022-01-14 | 2021-12-13 | QRF 2021-R IVB-Oriental Mindoro-009 | 010-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | Bulalacao | 2 | 1 | 25 | TY QUINTA | 5638206.4248 | 1 | 5600000 | Completed | 100% | 2022-02-13 | 2022-02-11 | QRF 2021-R IVB-Oriental Mindoro-006 | 008-2021 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-07-06 | 2021-07-22 | ADL Constrak |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Romblon | 309205 | CARMEN NATIONAL HIGH SCHOOL | San Agustin | 0 | 1 | 4 | TISOY / ROLLY | 1758135.0613 | 1 | 1597519.23 | Completed | 100% | 2022-03-21 | 2022-02-14 | N/A | INF-SQR-2021-06 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RG FLORENTINO CONSTRUCTION AND TRADING INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Romblon | 111424 | MARIGONDON NORTE ES | San Andres | 0 | 1 | 5 | TISOY | 2598887.5998 | 1 | 2472004.64 | Completed | 100% | 2022-03-31 | 2022-06-17 | N/A | INF-SQR-2021-04 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RMR CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Romblon | 111425 | Marigondon Sur ES | San Andres | 0 | 1 | 2 | TISOY | 1108455.088 | 1 | 1177104.5 | Completed | 100% | 2022-03-31 | 2022-06-17 | N/A | INF-SQR-2021-04 | 2021-07-20 | 2021-07-27 | 2021-08-08 | 2021-12-14 | 2021-12-14 | RMR CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Romblon | 111429 | San Andres Central Elementary School | San Andres | 0 | 1 | 17 | TISOY / ROLLY | 5245186 | 1 | 4463037.89 | Completed | 100% | 2022-09-30 |  | N/A | INF-SQR-2021-05 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2022-01-28 | 2022-01-28 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IV-B | Romblon | 301771 | San Andres NHS | San Andres | 0 | 1 | 2 | TISOY | 1115165.5609 | 1 | 898845.93 | Completed | 100% | 2022-09-30 |  | N/A | INF-SQR-2021-05 | 2021-10-29 | 2021-11-04 | 2021-11-08 | 2022-01-28 | 2022-01-28 | TRIPLE PEAK MOUNTAIN CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region IX | Zamboanga del Norte | 124753 | Sipaloc ES | SIBUTAD | 1 | 1 | 2 | FIRE INCIDENT | 4553463.46 | 1 | 4541309.89 | Completed | 100% | 2021-11-07 | 2021-11-17 | QRF 2022 RIX - ZAMBOANGA DEL NORTE | QRF 2022 RIX-ZDN-01 | 2021-06-01 | 2021-06-09 | 2021-06-22 | 2021-06-28 | July 6, 2021 | July 6, 2021 | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2021 | Region V | Albay | 301818 | Cabasan National High School | Bacacay | 1 | 1 | 22 | TY QUINTA/ROLLY/ULYSSES | 6025500.14 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111878 | Balza Elementary School | Malinao | 1 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 1766953.9 | 1 |  | Completed | 100% | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111870 | Baybay Elementary School | Malinao | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1317875.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111873 | Comun Elementary School | Malinao | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1460377.93 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111875 | Jonop Elementary School | Malinao | 1 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 2559072.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111879 | Matalipni Elementary School | Malinao | 1 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 3029271.97 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111884 | Tagoytoy Elementary School | Malinao | 1 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2051881.74 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112075 | Cararayan-Naga Elementary School | TIWI | 1 | 1 | 17 | FROM REGULAR REPAIR 2021 | 5233904.42 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112073 | MAYONG ES | Tiwi | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1078621.6 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111640 | Caguiba Elementary School | CAMALIG | 2 | 1 | 11 | FROM REGULAR REPAIR 2021 | 5651432.44 | 1 |  | Completed | 100% | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 301808 | Anislag National High School | DARAGA (LOCSIN) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2340280.34 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111672 | Malobago Elementary School | DARAGA (LOCSIN) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2340461.24 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111895 | Hologan Elementary School | MANITO | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3472066.77 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112022 | Buenavista Elementary School | RAPU-RAPU | 2 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3437186.16 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112033 | Liguan Elementary School | RAPU-RAPU | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1718952.25 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112036 | Mancao Elementary School | RAPU-RAPU | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4493900.33 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 172523 | Pagcolbon Elementary School | RAPU-RAPU | 2 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1115567.37 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 112043 | Rapu-Rapu Central School | RAPU-RAPU | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3667975.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112044 | Sagrada Elementary School | RAPU-RAPU | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1710607.89 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111721 | Balite Elementary School | Guinobatan | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1249812.18 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111806 | Talin-Talin Elementary School | LIBON | 3 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1895890.79 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111978 | ALNAY ELEMENTARY SCHOOL | OAS | 3 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3631828.5682 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111927 | BALOGO EAST ELEMENTARY SCHOOL | OAS | 3 | 1 | 6 | TY NINA | 2439787.7051 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region V | Albay | 111937 | Oas South Central School | OAS | 3 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 2307639.31 | 1 |  | reverted | 0% | [10 empty] | Not included in SARo | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0% | 0% | [6 empty] | repair | reverted
QRF 2021 | Region V | Albay | 301854 | Marigondon National High School | PIODURAN | 3 | 1 | 16 | Repair | 5122870.63 | 1 |  | Completed | 100% | 2022-11-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% | 2023-02-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172525 | Anopol Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1380826.63 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112001 | Apad Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1348570.83 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111981 | Cepres Elementary School | POLANGUI | 3 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2418275.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172522 | Cotmon Elementary School | POLANGUI | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2707627.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111982 | Dalogo Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2132402.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111986 | Kinuartelan Elementary School | POLANGUI | 3 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1540957.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 301867 | La Medalla High School | POLANGUI | 3 | 1 | 10 | TY NINA | 3501355.07 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 309513 | Lanigay High School | POLANGUI | 3 | 1 | 5 | TY NINA | 2665080.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111987 | Lidong Elementary School | POLANGUI | 3 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2446556.79 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 172524 | Luisevera Matza Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 714924.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112010 | Matacon Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1739428.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111989 | Maynaga Elementary School | POLANGUI | 3 | 1 | 5 | TY NINA | 2256065.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111995 | POLANGUI NORTH CENTRAL SCHOOL | POLANGUI | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2579077.1757 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112011 | POLANGUI SOUTH CENTRAL SCHOOL | POLANGUI | 3 | 1 | 31 | TY NINA | 10330773.5192 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 31 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 112013 | San Roque Elementary School | POLANGUI | 3 | 1 | 7 | TY NINA | 2756908.16 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111998 | Sta. Cruz Elementary School | POLANGUI | 3 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1949799.25 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Albay | 111999 | Sugcad Elementary School | POLANGUI | 3 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1214077.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301896 | Gonzalo Aler National High School | CAPALONGA | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1112806.52 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112118 | Mabini ES | CAPALONGA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1716830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 305631 | San Antonio High School | CAPALONGA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1614482.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112151 | Jose Panganiban ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1685330.18 | 1 | 3163194.92 | Completed | 100% | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112162 | L. D. Bamba ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1261478.78 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112252 | MAMPUNGO ELEMENTARY SCHOOL | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1737977.1 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112167 | San Jose ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1812371.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112157 | San Rafael ES | JOSE PANGANIBAN | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1695830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 500156 | Dumagmang Integrated School | LABO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2358544.91 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112204 | F. Caudilla E/S | LABO | 1 | 1 | 6 | FROM REGULAR REPAIR 2021 | 3840116.11 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112182 | Fundado ES | LABO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3492226.81 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112211 | Kabungahan ES | LABO | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1064365.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1671318.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 501259 | Malaya Integrated School | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1716830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 513828.69 | 1 |  | Completed | 100% | 2020-04-14 | [7 empty] | 2019-12-16 | FIRST QUANTUM BUILDERS ID BUILDERS CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112242 | Batobalani Elementary School | PARACALE | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2247130.7 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 355015.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309616 | Bulala High School | SANTA ELENA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301888 | E.P. Borja High School | SANTA ELENA | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1154414.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112285 | Rizal ES | SANTA ELENA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112287 | San Pedro ES | SANTA ELENA | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 2076456.44 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112291 | M. Cacho ES | TALISAY | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 355015.96 | 1 |  | Completed | 100% | 2020-04-09 | [7 empty] | 2019-12-11 | JCO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112297 | Zantua-Abordo ES | TALISAY | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1801871.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309604 | Eugenia Morana - Quintela Memorial High School | VINZONS | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2014908.27 | 1 |  | Completed | 100% | 2023-11-01 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112305 | Gorgonio Obusan ES | VINZONS | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1801871.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112304 | Gregorio Jardin ES | VINZONS | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 586207.72 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112311 | Menandro Guinto ES | VINZONS | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2197383.97 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301914 | Sabang National High School, Vinzons | VINZONS | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2070943.41 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer High School | VINZONS | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1103792.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112092 | Mampili ES | BASUD | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1064365.29 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112103 | San Felipe ES | BASUD | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1685330.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112142 | Cobangbang Elementary School | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1074317.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112134 | Daet ES | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1135112.03 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 173001 | Don Emiliano L. Pabico ES | DAET (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1138194.28 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1621897.13 | 1 | 969616.54 | Completed | 100% | 2020-04-08 | [7 empty] | 2019-12-10 | ZKR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112232 | Manguisoc ES | MERCEDES | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3660106.17 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301902 | Manguisoc National High School | MERCEDES | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2179604.36 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 979766.86 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 524328.69 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 301918 | San Roque National High School | MERCEDES | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 672641.41 | 1 |  | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112271 | Salvacion (B) ES | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1102306.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309606 | San Isidro High School | SAN LORENZO RUIZ (IMELDA) | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 1852810.55 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 112261 | Bernardo Olis ES | SAN VICENTE | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1674830.18 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 173003 | Cabanbanan ES | SAN VICENTE | 2 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 548800.29 | 1 | 1377953.48 | Completed | 100% | [10 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Norte | 309605 | Fabrica High School | SAN VICENTE | 2 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 365515.96 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112739 | Casay ES | LUPI | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 1598693 | 1 | 1586193 | Completed | 100% | 2/17/2022 | 2/25/2022 |  | 2021-10-036 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112960 | Liboro Elementary School | RAGAY | 1 | 1 | 4 | FROM REGULAR REPAIR 2021 | 2398964.78 | 1 | 2386464.78 | Completed | 100% | 2/17/2022 | 2/25/2022 |  | 2021-10-036 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112711 | Libmanan South CS | LIBMANAN | 2 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4605609.87 | 1 | 4595600 | Completed | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-038 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112908 | Itulan ES | PASACAO | 2 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3982140.4 | 1 | 3979885.87 | Completed | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-037 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112911 | Pasacao CS | PASACAO | 2 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 6784642.24 | 1 | 6776658.43 | Completed | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-037 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 113000 | Daculang Tubig ES | SAN FERNANDO | 2 | 1 | 2 | FROM REGULAR REPAIR 2021 | 1389548.35 | 1 | 1379500 | Completed | 100% | 3/29/2022 | 2/28/2022 |  | 2021-10-038 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112491 | Salvacion-Baybay Elementary School | Calabanga | 3 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3622215.25 | 1 | 3579215 | Completed | 100% | 3/19/2022 | 3/3/2022 |  | 20221-10-041 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302034 | Magarao National High School, Magarao | Magarao | 3 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 9256238.75 | 1 | 7882421.58 | Completed | 100% | 3/19/2022 | 3/3/2022 |  | 20221-10-041 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | LDN |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302006 | Ocampo National High School | OCAMPO | 3 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 12935583.52 | 1 | 12818967.89 | Completed | 100% | 3/29/2022 |  |  | 202-10-040 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302016 | Pili National High School - Pili | PILI (Capital) | 3 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 9948815.76 | 1 | 9860886.22 | Completed | 100% | 3/24/2022 |  |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302017 | Pili NHS, Pili - Gov.Mariano E. Villafuerte Annex HS | PILI (Capital) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 818712.01 | 1 | 787372.94 | Completed | 100% | 3/24/2022 | 2/17/2022 |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302018 | V. Bagasina Sr. Memorial High School | PILI (Capital) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 2438686.94 | 1 | 2431585.83 | Completed | 100% | 3/24/2022 | 2/17/2022 |  | 2021-10-039 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 301978 | Guijalo National High School | CARAMOAN | 4 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6773474.04 | 1 | 6690990.5 | Completed | 100% | 3/19/2022 | 4/13/2022 |  | 2021-10-043 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112542 | Hanopol ES | CARAMOAN | 4 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4973566.36 | 1 | 4920220.7 | Completed | 100% | 3/19/2022 | 2/17/2022 |  | 2021-10-043 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112664 | Panicuan PS | LAGONOY | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1547411.4 | 1 | 1523299.16 | Completed | 100% | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112884 | Bantugan ES | PRESENTACION | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1624648.33 | 1 | 1619769.34 | Completed | 100% | 3/24/2022 |  |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112889 | Cagnipa ES | PRESENTACION | 4 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5965427.99 | 1 | 5962335.22 | Completed | 100% | 3/24/2022 |  |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112977 | Atulayan ES | SAGÑAY | 4 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 4203692.97 | 1 | 4201518.65 | Completed | 100% | 3/24/2022 | 4/19/2022 |  | 2021-10-042 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/24/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112979 | Bongalon ES | SAGÑAY | 4 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3164982.61 | 1 | 2973836.7 | Completed | 100% | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 300310 | Adiangao High School | SAN JOSE | 4 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1547411.4 | 1 | 1516894.16 | Completed | 100% | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 301950 | Gregorio O. Bercasio Memorial High School | TINAMBAC | 4 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6709924.31 | 1 | 6047564.99 | Completed | 100% | 3/19/2022 | 2/23/2022 |  | 2021-10-044 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | RD DAYAO |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112326 | Ikpan ES | BAAO | 5 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1981838.89 | 1 | 1975647.5 | Completed | 100% | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN | 5 | 1 | 17 | FROM REGULAR REPAIR 2021 | 4663042.91 | 1 | 4661020.07 | Completed | 100% | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112389 | Antipolo Elementary School | BUHI | 5 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1272042.58 | 1 | 1252880.5 | Completed | 100% | 3/19/2022 | 3/10/2022 |  | 2021-10-047 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112390 | Buhi Central School | BUHI | 5 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 9895239.39 | 1 | 9760990 | Completed | 100% | 3/19/2022 | 3/10/2022 |  | 2021-10-047 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112391 | Buhi North Central School | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3926646.22 | 1 | 3924092.03 | Completed | 100% | 3/29/2022 | 2/10/2022 |  | 2021-10-048 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | TGME |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112404 | Lourdes Elementary School | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4164588.85 | 1 | 4056003.77 | Completed | 100% | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112409 | Sagrada ES | BUHI | 5 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3113366.82 | 1 | 3089770.42 | Completed | 100% | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112413 | San Rafael ES | BUHI | 5 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4073945.08 | 1 | 3998732.11 | Completed | 100% | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302043 | San Vicente National High School - Buhi | BUHI | 5 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 11646335.03 | 1 | 11145550.5 | Completed | 100% | 3/19/2022 | 2022-10-03 |  | 2021-10-046 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/19/2021 | JURASSIC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112425 | Bagumbayan ES | BULA | 5 | 1 | 2 | FROM REGULAR REPAIR 2021 | 1312828.71 | 1 | 1311882.22 | Completed | 100% | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112439 | Lubgan Elementary School | BULA | 5 | 1 | 5 | FROM REGULAR REPAIR 2021 | 3360007.4 | 1 | 3338088.36 | Completed | 100% | 3/15/2022 | 2/15/2022 |  | 2021-10-049 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/15/2021 | MARAKESH |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 112816 | La Opinion ES | NABUA | 5 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4286526.56 | 1 | 4244309.38 | Completed | 100% | 3/16/2022 | 2/15/2022 |  | 2021-10-050 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/16/2021 | EA-AC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5 | 1 | 69 | TY QUINTA/ROLLY/ULYSSES | 21627436.11 | 1 | 19240337.13 | Completed | 100% | 3/19/2022 |  |  | 2021-10-045 | 7/27/2021 | 7/5/2021 | 8/16/2021 | 10/14/2021 | 11/29/2021 | JVM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 69 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113161 | Bagamanoc CES | BAGAMANOC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7057850.69 | 1 | 6987272.71 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302076 | Bugao National High School | BAGAMANOC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2458858.17 | 1 | 2434269.5 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113156 | Hinipaan Elementary School | BAGAMANOC | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6305789.86 | 1 | 6242732.07 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113172 | Abihao ES | BARAS | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1482900.42 | 1 | 1444984.54 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113166 | Agban Central Elementary School | BARAS | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 7366003.61 | 1 | 7288560.38 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302070 | Agban NHS | BARAS | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5132951.85 | 1 | 5075582.34 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113173 | Baras CES | BARAS | 0 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 7365090.31 | 1 | 7364905.82 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | 0 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 9181323.54 | 1 | 9154819.02 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113167 | Benticayan ES | BARAS | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 3681449.28 | 1 | 3680785.74 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113168 | Genitligan ES | BARAS | 0 | 1 | 3 | FROM REGULAR REPAIR 2021 | 3282775.73 | 1 | 3217259.2 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113175 | Macutal Elementary School | BARAS | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2999500.98 | 1 | 2956944.39 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113176 | Moning ES | BARAS | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1881258.93 | 1 | 1862093.54 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113177 | Paniquihan ES | BARAS | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2999500.98 | 1 | 2956944.39 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113178 | Putsan-Danao ES | BARAS | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 3120045.28 | 1 | 3108676.54 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113171 | San Miguel Elementary School | BARAS | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3430304.42 | 1 | 3404027.31 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174002 | Sta. Maria ES | BARAS | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 954338.96 | 1 | 941641.98 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113180 | Tilod ES | BARAS | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 3681449.28 | 1 | 3647471.04 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 500412 | Bote IS | BATO | 0 | 1 | 26 | TY QUINTA/ROLLY/ULYSSES | 14923145.7 | 1 |  | reverted | 0% | [10 empty] | Not included in SARo | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0% | 0% | [6 empty] | REPAIR | reverted
QRF 2021 | Region V | Catanduanes | 500032 | Cabugao IS | BATO | 0 | 1 | 9 | FROM REGULAR REPAIR 2021 | 5017810.4 | 1 | 4967632.29 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113185 | Cagraray Elementary School | BATO | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3722431.99 | 1 | 3685427.28 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113186 | Carorian ES | BATO | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3087312.68 | 1 | 3056784.9 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113192 | Guinobatan ES | BATO | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4087124.18 | 1 | 4046429.71 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113193 | Oguis ES | BATO | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3517156.85 | 1 | 3481498.82 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113189 | San Pedro ES | BATO | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5266080.48 | 1 | 5213417.95 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113190 | San Roque ES | BATO | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7662858.44 | 1 | 7586229.86 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113195 | Sipi ES | BATO | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5565154.49 | 1 | 5509502.95 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113198 | Caramoran CES | CARAMORAN | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4232110.42 | 1 | 4189789.36 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302086 | Dariao NHS | CARAMORAN | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 5523844.11 | 1 | 5468605.69 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113207 | Guiamlong ES | CARAMORAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2967697.43 | 1 | 2938020.47 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113213 | Obi ES | CARAMORAN | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2497352.94 | 1 | 2472379.51 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113202 | Panique ES | CARAMORAN | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1652978.2 | 1 | 1636448.44 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113203 | San Jose ES | CARAMORAN | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1336767.85 | 1 | 1323400.19 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113218 | Biong ES | GIGMOTO | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2232918.7976 | 1 | 2210830.19 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174010 | Dominador C. Guerrero ES | GIGMOTO | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1030728.9416 | 1 | 1020347.63 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113219 | Dororian E/S | GIGMOTO | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 2366076.9456 | 1 | 2327882.46 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | 0 | 1 | 5 | FROM REGULAR REPAIR 2021 | 3558081.73 | 1 | 3505282.07 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113220 | Gigmoto CES | GIGMOTO | 0 | 1 | 21 | TY QUINTA/ROLLY/ULYSSES | 7995483.2873 | 1 | 7917901.93 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113221 | San Pedro ES | GIGMOTO | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1074001.8 | 1 | 1063231.69 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113233 | Bagawang ES | PANDAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2540323.9924 | 1 | 2514920.74 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302103 | Leandro I.Verceles Sr. NHS | PANDAN | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2660814.2559 | 1 | 2634206.13 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113239 | Pandan CES | PANDAN | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 14557732.5287 | 1 | 14412155.36 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113253 | Panganiban Central Elementary School | PANGANIBAN | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1043616.243 | 1 | 1033137.16 | Completed | 100% | 2011-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302095 | Panganiban National High School | PANGANIBAN | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 5566236.0175 | 1 | 5510490.64 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113254 | San Miguel ES | PANGANIBAN | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2742252.8289 | 1 | 2714751.43 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113257 | Batong Paloway ES | SAN ANDRES | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 4180763.41 | 1 | 4056031.42 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113271 | Bislig ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4891107.82 | 1 | 4743976.56 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113258 | Bon-ot ES | SAN ANDRES | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2538181.56 | 1 | 2461664.86 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302078 | Cabcab NHS | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4472873.99 | 1 | 4340686.3 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113259 | Caragñag ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4746977.04 | 1 | 4598422.49 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113274 | Catagbacan ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3629135.08 | 1 | 3525577.92 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113275 | Codon ES | SAN ANDRES | 0 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6567640.64 | 1 | 6364693.43 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302085 | Codon National High School | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 5315909.49 | 1 | 5152100.72 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113260 | Comagaycay ES | SAN ANDRES | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2984527.02 | 1 | 2893461.09 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113276 | Datag Elementary School | SAN ANDRES | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1535502.92 | 1 | 1490831.68 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113277 | JMA (Asgad) Elementary School | SAN ANDRES | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3753985.49 | 1 | 3642389.87 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113261 | Jose Rizal ES | SAN ANDRES | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 4305245.93 | 1 | 4196650.16 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113278 | Manambrag ES | SAN ANDRES | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2221819.33 | 1 | 2199601 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302091 | Manambrag NHS | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2896350.78 | 1 | 2867387.26 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113279 | Maygnaway ES | SAN ANDRES | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2620312.41 | 1 | 2594109.28 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302092 | Mayngaway NHS | SAN ANDRES | 0 | 1 | 16 | TY QUINTA/ROLLY/ULYSSES | 6522895.52 | 1 | 6457666.56 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113263 | Palawig ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4816246.53 | 1 | 4665426.65 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113280 | Puting Baybay ES | SAN ANDRES | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 650503.76 | 1 | 643998.73 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113281 | San Isidro ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4351715.31 | 1 | 4308198.2 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113265 | San Jose ES | SAN ANDRES | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2166006.86 | 1 | 2101490.43 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113282 | San Vicente Elementary School | SAN ANDRES | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 309069.81 | 1 | 305979.11 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113283 | Tibang ES | SAN ANDRES | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1891622.53 | 1 | 1872706.3 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113266 | Timbaan ES | SAN ANDRES | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3790057.18 | 1 | 3672647.75 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113284 | Tominawog ES | SAN ANDRES | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 4992256.8 | 1 | 4845672.27 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113267 | Yocti ES | SAN ANDRES | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4313818.58 | 1 | 4179328.34 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113285 | Alma ES | SAN MIGUEL | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4064730.67 | 1 | 4021181.6 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113286 | Balatohan ES | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4061382.42 | 1 | 4023218.23 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174015 | Boton PS | SAN MIGUEL | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1062562.04 | 1 | 1049674.04 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113299 | Buhi Elementary School | SAN MIGUEL | 0 | 1 | 8 | FROM REGULAR REPAIR 2021 | 4696273.48 | 1 | 4663634.28 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113287 | Caglatawan Elementary School | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2119579.48 | 1 | 2098973.03 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113300 | Dayawa ES | SAN MIGUEL | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2057008.12 | 1 | 2036570.23 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113301 | Katipunan ES | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4618843.34 | 1 | 4575730.32 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113289 | Kilikilihan ES | SAN MIGUEL | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6662184.65 | 1 | 6592895.95 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | SAN MIGUEL | 0 | 1 | 20 | TY QUINTA/ROLLY/ULYSSES | 10322437.28 | 1 | 10208274.56 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113302 | Obo ES | SAN MIGUEL | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6141725.34 | 1 | 6080415.15 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113291 | Pacogon ES | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2354792.06 | 1 | 2331226.32 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113292 | Pagsangahan ES | SAN MIGUEL | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 6502317.88 | 1 | 6437771 | Completed | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113294 | Paraiso B ES | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2952877.47 | 1 | 2923291.08 | Completed | 100% | 2022-04-22 |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113293 | Paraiso-A Elementary School | SAN MIGUEL | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3961161.68 | 1 | 3921701.53 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113295 | San Marcos ES | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3156845.89 | 1 | 3125574.26 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | 0 | 1 | 17 | FROM REGULAR REPAIR 2021 | 7509797.52 | 1 | 7419023.83 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113296 | Siay Elementery School | SAN MIGUEL | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2248421.55 | 1 | 2225023.57 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113306 | Solong PS | SAN MIGUEL | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1036704.27 | 1 | 1023119.78 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Virac NRC Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113308 | Begonia ES | VIGA | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4059597.0148 | 1 | 4018966.95 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113309 | Botinagan ES | VIGA | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1351728.5127 | 1 | 1338188.83 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113321 | Mabini ES | VIGA | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1118530.6374 | 1 | 1107325.01 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113332 | Summit ES | VIGA | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 2769214.99 | 1 |  | Completed | 100% |  |  |  |  | July 5, 2019 | July 12, 2019 | July 25, 2019 | Sept. 10, 2019 | Sept. 17, 2019 | JAYRO CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113314 | Tambongon CES | VIGA | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 6411747.6466 | 1 | 6347566.72 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113315 | Tinago Elementary School | VIGA | 0 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6236755.7573 | 1 | 6174384.94 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113316 | Villa Aurora Elementary School | VIGA | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2733514.7131 | 1 | 2706154.56 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Lourbel Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113353 | Antipolo ES | VIRAC | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 10183222.12 | 1 | 10156385.26 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302071 | Antipolo NHS | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 5883749.25 | 1 | 5853134.49 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113354 | Balite Elementary School | VIRAC | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4603770.12 | 1 | 4580203.05 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113355 | Batag ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1999664.27 | 1 | 1988159.72 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113334 | Bigaa ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4496763.22 | 1 | 4474859.96 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113356 | Buenavista ES | VIRAC | 0 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 736710.36 | 1 | 733436.57 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 500031 | Buyo Integrated School | VIRAC | 0 | 1 | 29 | TY QUINTA/ROLLY/ULYSSES | 15604524.22 | 1 | 15526215.65 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 29 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113336 | Calabnigan ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1268081.07 | 1 | 1262189.91 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113357 | Calampong ES | VIRAC | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1398724.69 | 1 | 1391846.62 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113337 | Calatagan ES | VIRAC | 0 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 10513757.31 | 1 | 10461343.32 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302084 | Calatagan High School | VIRAC | 0 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 11049307.34 | 1 | 10993917.93 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174012 | Capilihan ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2754161.31 | 1 | 2740581.25 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113358 | Casoocan ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1664497.81 | 1 | 1655033.89 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302083 | Catanduanes NHS | VIRAC | 0 | 1 | 33 | TY QUINTA/ROLLY/ULYSSES | 17752951.93 | 1 | 17653201.11 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113340 | Dugui Too Elementary School | VIRAC | 0 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 5308151.36 | 1 | 5281006.12 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113341 | Dugui Wala ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3035240.3 | 1 | 3020079.95 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174013 | F. Tacorda Village ES | VIRAC | 0 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2092884.77 | 1 | 2083057.46 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-06 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113360 | Hawan ES | VIRAC | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 7326705.5 | 1 | 7290153.88 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113361 | Hawan Ilaya ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2100635.89 | 1 | 2090378.71 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302089 | Hawan National High School | VIRAC | 0 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 8179886.34 | 1 | 8139137.92 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113343 | Hicming ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 4576259.95 | 1 | 4553446.68 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113362 | Igang Elementary School | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2802622.88 | 1 | 2784412.39 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113345 | Juan M. Alberto Memorial ES | VIRAC | 0 | 1 | 25 | TY QUINTA/ROLLY/ULYSSES | 12497282.07 | 1 | 11936782.26 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113363 | Magnesia ES | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7605272.85 | 1 | 7563498.81 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113364 | Marilima ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 1913652.19 | 1 | 1903873.52 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113366 | Pajo San Isidro ES | VIRAC | 0 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 3205671.79 | 1 | 3184936.87 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113367 | Palnab ES | VIRAC | 0 | 1 | 13 | TY QUINTA/ROLLY/ULYSSES | 7364206.61 | 1 | 7322922.27 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113368 | Palta ES | VIRAC | 0 | 1 | 15 | TY QUINTA/ROLLY/ULYSSES | 9927581.75 | 1 | 9880095.92 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 302093 | Palta NHS | VIRAC | 0 | 1 | 8 | TY QUINTA/ROLLY/ULYSSES | 4285753.72 | 1 | 4253983.5 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113369 | Palta Saday ES | VIRAC | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4412135.07 | 1 | 4390345.22 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 174006 | San Isidro Village ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3413056.06 | 1 | 3386806.08 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113370 | Sto. Cristo ES | VIRAC | 0 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 4079050.32 | 1 | 4057404.09 | Completed | 100% | 2022-05-13 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113371 | Talisoy ES | VIRAC | 0 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2253749.9 | 1 | 2238142.45 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-27 | Legazpi Premium Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113351 | Taytay ES | VIRAC | 0 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 2069559.75 | 1 | 2059747.85 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113372 | Valencia ES | VIRAC | 0 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2153928.43 | 1 | 2143150.87 | Completed | 100% | 2022-06-09 | [7 empty] | 2021-11-05 | Virac Tridom Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113352 | Virac Pilot Elementary School | VIRAC | 0 | 1 | 35 | TY QUINTA/ROLLY/ULYSSES | 23451909.2 | 1 | 11929312.77 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113342 | Gogon Elementary School | VIRAC (Capital) | 0 | 1 | 10 | FROM REGULAR REPAIR 2021 | 7719792.54 | 1 | 7681550.74 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113346 | San Vicente ES | VIRAC (Capital) | 0 | 1 | 8 | FROM REGULAR REPAIR 2021 | 3733979.05 | 1 | 3733220.39 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | A.V. Laynes Trading and Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Catanduanes | 113347 | Simamla ES | VIRAC (Capital) | 0 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 6690740.87 | 1 | 6657486.64 | Completed | 100% | 2022-04-22 | [7 empty] | 2021-08-06 | Protech Construction & Development Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Iriga City | 114432 | Iriga North CS | IRIGA CITY | 5 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 7924696.19 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Iriga City | 114445 | Iriga South CS | IRIGA CITY | 5 | 1 | 19 | TY QUINTA/ROLLY/ULYSSES | 13145539.73 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114457 | Albay CS | LEGAZPI CITY (Capital) | 2 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 5525850.055 | 1 | 5288133.49 | Completed | 100% | 2020-03-04 |  | 2019-INFRA-07 | 2019-INFRA-08 | 2019-08-07 | 2019-08-15 | 2019-08-27 | 2019-10-04 | 2019-10-29 | Sunridge Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114466 | Bagumbayan CS | LEGAZPI CITY (Capital) | 2 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 8838628.945 | 1 | 8443993.01 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114467 | Banquerohan ES | LEGAZPI CITY (Capital) | 2 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 7090858.11 | 1 | 6897939.6 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 302257 | Banquerohan National High School | LEGAZPI CITY (Capital) | 2 | 1 | 14 | TY QUINTA/ROLLY/ULYSSES | 7746464.94 | 1 | 7533634.17 | Completed | 100% | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114481 | Legazpi Port Elementary School | LEGAZPI CITY (Capital) | 2 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 8337194.4 | 1 | 8114138.47 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Legaspi City | 114474 | Taysan ES | LEGAZPI CITY (Capital) | 2 | 1 | 14 | TY QUINTA/ROLLY/ULYSSES | 7485244.06 | 1 | 7269167.9 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Ligao City | 301807 | Amtic National High School | CITY OF LIGAO | 3 | 1 | 19 | TY QUINTA/ROLLY/ULYSSES | 6933571.6677 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Ligao City | 301858 | Oma-Oma National High School | CITY OF LIGAO | 3 | 1 | 18 | TY QUINTA/ROLLY/ULYSSES | 5444091.3059 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113587 | Osmena ES | CLAVERIA | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3157404.59 | 1 | 3124251.84 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113593 | San Ramon Elementary School | CLAVERIA | 1 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 2129035.65 | 1 | 2104551.74 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-064 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 501273 | Buenavista Integrated School (ES) | SAN FERNANDO | 1 | 1 | 3 | FROM REGULAR REPAIR 2021 | 1692314.15 | 1 | 1653898.62 | Completed | 100% | 2022-03-10 |  | INFRA 2021-10-037 | 2021-064 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113877 | San Fernando East ES | SAN FERNANDO | 1 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3726271.62 | 1 | 3713800.45 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-041 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | MME CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113893 | Jagna-an ES | SAN JACINTO | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2786236.98 | 1 | 2736641.96 | Completed | 100% | 2022-03-10 |  | INFRA 2021-10-036 | 2021-064 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-10 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3265362.4 | 1 | 3209851.23 | Completed | 100% | 2022-03-06 |  | INFRA 2021-10-035 | 2021-059 | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-06 | RPN CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 302137 | Halabangbaybay National High School | SAN PASCUAL | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1396189.08 | 1 | 1376358.36 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-064 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 500034 | Maximino S. Lazaro Integrated School | SAN PASCUAL | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 3441161.88 | 1 | 3400212.05 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 174520 | Patrocenio G. Dela Torre Elementary School | SAN PASCUAL | 1 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1222370.69 | 1 | 1205868.69 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113932 | Rizal Elementary School | SAN PASCUAL | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 3707609.3 | 1 | 3713800.45 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-041 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | MME CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 302168 | San Pascual National High School | SAN PASCUAL | 1 | 1 | 4 | TY QUINTA/ROLLY/ULYSSES | 2916319.7 | 1 | 2890656.09 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113937 | Sulficio Elliot ES | SAN PASCUAL | 1 | 1 | 1 | TY QUINTA/ROLLY/ULYSSES | 807654.62 | 1 | 801597.21 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 |  | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 309932 | Nabongsoran High School | AROROY | 2 | 1 | 6 | TY QUINTA/ROLLY/ULYSSES | 3234345.74 | 1 | 3183863.05 | Completed | 100% | 2022-03-09 |  | INFRA 2021-10-038 |  | 2021-11-02 | 2021-11-10 | 2021-11-22 | 2021-11-29 | 2021-12-09 | 3R3M CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113756 | Sta. Maria Elementary School | MOBO | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 1308914.87 | 1 | 1305642.58 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-046 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113630 | Rizal PS | ESPERANZA | 3 | 1 | 1 | FROM REGULAR REPAIR 2021 | 738363.65 | 1 | 736517.74 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-046 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | SANSA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate | 113818 | Tubigan Elementary School | PIO V. CORPUZ (LIMBUHAN) | 3 | 1 | 6 | FROM REGULAR REPAIR 2021 | 4181112.18 | 1 | 4170659.79 | Completed | 100% | 2022-02-24 |  | INFRA 2021-08-024 | 2021-047 | 2021-09-16 | 2021-09-24 | 2021-10-06 | 2021-11-19 | 2021-11-26 | L2A CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate City | 113673 | Biyong Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 2690340.85 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Masbate City | 130949 | Calolod Elementary School | CITY OF MASBATE (Capital) | 2 | 1 | 2 | TY QUINTA/ROLLY/ULYSSES | 591578.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114505 | Concepcion Grande ES | NAGA CITY | 3 | 1 | 9 | TY QUINTA/ROLLY/ULYSSES | 6110866.95 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114499 | Dr. Domingo G. Abcede Elementary School | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6241294.52 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6240581 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114501 | Naga Central School II | NAGA CITY | 3 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 6334316.31 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114502 | Pacol Elementary School | NAGA CITY | 3 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 6138659.81 | 1 | 4045105.42 | Completed | 100% |  |  |  |  | 2019-06-20 | 2019-06-24 | 2019-07-08 | 2019-08-16 | 2019-09-12 | DELPAR Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Naga City | 114517 | Sta.Cruz Elementary School | NAGA CITY | 3 | 1 | 22 | TY QUINTA/ROLLY/ULYSSES | 13651331.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 302241 | San Rafael High School | CASTILLA | 1 | 1 | 12 | TY QUINTA/ROLLY/ULYSSES | 2781079.77 | 1 | 1852483.39 | Completed | 100% | 2021-12-19 |  |  | 21-07-006-01 |  |  |  |  | 2021-09-06 | 144 Cubits Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 114243 | Sto. Domingo ES (Lamboon) | IROSIN | 2 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2854182.3 | 1 | 2007137.18 | Completed | 100% | 2021-12-07 |  |  | 21-07-006-02 |  |  |  |  | 2021-09-09 | Camsur Bicol Trading Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon | 114416 | Talaonga ES | SANTA MAGDALENA | 2 | 1 | 3 | TY QUINTA/ROLLY/ULYSSES | 1829435.96 | 1 | 1354285.64 | Completed | 100% | 2021-12-07 |  |  | 21-07-006-03 |  |  |  |  | 2021-09-09 | Araphil Construction and Development Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114565 | Basud Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 5 | TY QUINTA/ROLLY/ULYSSES | 2237929.79 | 1 | 1551085.73 | Completed | 100% | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC |  |  |  |  | temporarily stopped | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114554 | Bibincahan Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 17 | TY QUINTA/ROLLY/ULYSSES | 6152930.87 | 1 | 6102898.92 | Completed | 100% | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | NJNY Construction & Supply | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114527 | Gatbo Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 11 | TY QUINTA/ROLLY/ULYSSES | 3932421.1 | 1 | 2726009.16 | Completed | 100% | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 302274 | Osiao Paglingap National High School | CITY OF SORSOGON (Capital) | 1 | 1 | 10 | TY QUINTA/ROLLY/ULYSSES | 3625080.13 | 1 | 3594870.83 | Completed | 100% | July 20-August 9, 2021 | July 14, 2021 | August 9, 2021 | August 12, 2021 | August 16, 2021 | Jayro Construction & Supply | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114546 | San Roque Elementary School | CITY OF SORSOGON (Capital) | 1 | 1 | 7 | TY QUINTA/ROLLY/ULYSSES | 2907519.15 | 1 | 2165303.64 | Completed | 100% | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Sorsogon City | 114563 | Sorsogon East Central School | CITY OF SORSOGON (Capital) | 1 | 1 | 32 | TY QUINTA/ROLLY/ULYSSES | 3576898.84 | 1 | 2479334.52 | Completed | 100% | 2022-09-30 |  | August 9, 2021 | August 12, 2021 | August 16, 2021 | Camsur Bicol Trading INC | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302283 | San Lorenzo National High School | CITY OF TABACO | 1 | 1 | 35 | TY QUINTA/ROLLY/ULYSSES | 16520322.49 | 1 |  | Completed | 100% | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302284 | San Miguel National High School | CITY OF TABACO | 1 | 1 | 23 | Repair | 16946096.5 | 1 |  | Completed | 100% | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 100% | 0% | 2023-03-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 121 | Repair | 39313174.22 | 1 |  | Completed | 100% | 2022-10-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 121 | 100% | 0% | 2023-03-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2021 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 32 | TY QUINTA/ROLLY/ULYSSES | 13755640.77 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2021 | Region X | Camiguin | 303994 | Mambajao NHS | MAMBAJAO (Capital) | 0 | 1 | 5 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 1473234.1441 | 1 | 1462809.68 | COMPLETED | 100% | 2022-02-05 | 2021-12-18 | QRF 2021 - R X - Camiguin - 003 | Infra-01-02-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | JAPUZ JANSOL ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | 0 | 1 | 4 | FIRE INCIDENT | 1971512.2694 | 1 | 1960536.73 | COMPLETED | 100% | 2022-03-24 | 2022-06-04 | QRF 2021 - R X - Camiguin - 002 | Infra-01-03-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | JAPUZ JANSOL ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | COMPLETED
QRF 2021 | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | 0 |  | 2 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 4758089.7892 | 1 | 1960536.73 | COMPLETED | 100% | 2022-02-05 | 2021-12-18 | QRF 2021 - R X - Camiguin - 004 | Infra-01-02-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | Minkonstrak Eng'g. & Gen. Srvcs. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2021 | Region X | Camiguin | 126936 | Subocan ES | SAGAY | 0 | 1 | 2 | DAMAGED CLASSROOMS DUE TO TREES TOPPLED OVER IT (STRONG WINDS) | 4849009.2892 | 1 | 4838031.27 | Completed | 100% | 2022-01-21 | 2022-02-26 | QRF 2021 - R X - Camiguin - 001 | Infra-01-04-2021 | 2021-06-01 | 2022-06-09 | 2021-06-21 | 2021-07-27 | 2021-08-09 | Minkonstrak Eng'g. & Gen. Srvcs. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | previous yrs |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CAR | Abra | 135174 | Boliney CS | BOLINEY | 0 | 1 |  | Others | 7019074.5549 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 2023-04-01 | 10.23 |  |  |  |  | OTHERS | completed
QRF 2022 | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | 0 | 1 |  |  | 3314706.433 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 2023-04-01 | 12.23 |  |  |  |  | repair | Completed
QRF 2022 | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | 0 | 1 | 4 | NEW CONSTRUCTION | 17274099.21 | 1 |  | completed | 100% | 2023-05-04 | 2023-06-18 | INF-2021 QNC-001 |  | 2022-05-05 | 2022-05-13 | 2022-05-25 | 2022-06-07 | 2022-08-11 | Batakagan Construction | with 19 days time extension, 45 days LD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 4639596.2249 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | 0 | 1 | 9 | REPAIR/ REHABILITATION | 8126421.2928 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CAR | Tabuk City | 136102 | Magabbangon Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 1 | REPAIR/ REHABILITATION | 1547589 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CAR | Tabuk City | 136012 | Tabuk City Central School | CITY OF TABUK (Capital) | 0 | 1 |  | Others | 2114165.3102 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | OTHERS | Completed
QRF 2022 | CAR | Tabuk City | 136112 | Tannubong Elementary School | CITY OF TABUK (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 4639596.2249 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Agusan del Norte | 131450 | Kitcharao CES | KITCHARAO | 2 | 1 | 12 | NEW CONSTRUCTION | 26048980.31 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 2 | NEW CONSTRUCTION | 5400000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 16 | REPAIR/ REHABILITATION | 12932883.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 12 | REPAIR/ REHABILITATION | 9516868.87 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132505 | Rizal Central Elementary School | BASILISA (RIZAL) | 0 | 1 | 5 | REPAIR/ REHABILITATION | 4805281.92 | 1 | 4660850 | Completed | 100% |  |  | INFRA22 -004-08 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 305745 | Roma National High School | BASILISA (RIZAL) | 0 | 1 | 4 | NEW CONSTRUCTION | 11799061.85 | 1 |  | Completed | 100% | [10 empty] | realigned from rizal ces to roman nhs | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 11.23 |  | 1 | 4 | 11799061.85 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132510 | Tag-abaca Central Elementary School | BASILISA (RIZAL) | 0 | 1 | 13 | REPAIR/ REHABILITATION | 10440653.42 | 1 | 9151362.58 | Completed | 100% |  |  | INFRA22 -004-17 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | J-R3 CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132510 | Tag-abaca Central Elementary School | BASILISA (RIZAL) | 0 |  | 2 | NEW CONSTRUCTION | 7651642.97 | 1 | 6884671.71 | Completed | 100% |  |  | INFRA22 -004-17 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | CAPJ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 | 1 | 13 | REPAIR/ REHABILITATION | 11716714.8 | 1 | 11361134.25 | Completed | 100% |  |  | INFRA22 -004-15 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | 0 |  | 5 | NEW CONSTRUCTION | 17737420.56 | 1 | 17289156.5 | Completed | 100% |  |  | INFRA22 -004-15 |  | 2022-05-29 | 2022-06-22 | 2022-07-08 | 2022-08-10 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132364 | Longos Primary School | CAGDIANAO | 0 | 1 | 2 | NEW CONSTRUCTION | 7491972.35 | 1 |  | Completed | 100% | [10 empty] | REALIGNED from Loreto CES to Longons PS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 12.24 |  | 1 | 2 | 7491972.35 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 | 1 | 11 | REPAIR/ REHABILITATION | 6250248.57 | 1 | 6248000 | Completed | 100% |  |  | INFRA22 -004-04 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | 0 |  | 3 | NEW CONSTRUCTION | 10838276.55 | 1 | 10337426.55 | Completed | 100% |  |  | INFRA22 -004-03 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 24 | REPAIR/ REHABILITATION | 18432877.62 | 1 | 18430831.63 | Completed | 100% |  |  | INFRA22 -004-02 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | RJB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 15 | NEW CONSTRUCTION | 46467511.8 | 1 | 43182316.37 | Completed | 100% |  |  | INFRA22 -004-03 |  | 2022-05-29 | 2022-06-10 | 2022-06-23 | 2022-07-21 |  | CARTESAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% | 2023-03-01 | 11.23 |  | 1 | 15 | 46467511.8 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 8 | REPAIR/ REHABILITATION | 8560664.04 | 1 | 7726785.36 | Completed | 100% | [9 empty] | CAPJ |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 5.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | 0 |  | 4 | NEW CONSTRUCTION | 15373441.02 | 1 | 14596447.77 | Completed | 100% | [9 empty] | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 5.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 | 1 | 7 | REPAIR/ REHABILITATION | 5231820.18 | 1 | 4970229.76 | Completed | 100% |  |  | INFRA22 -004-12 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-03-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | 0 |  | 7 | NEW CONSTRUCTION | 23044703.29 | 1 | 20359995 | Completed | 100% |  |  | INFRA22 -004-13 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ALGAMON CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | 0 | 1 | 6 | NEW CONSTRUCTION | 20454827.35 | 1 | 20447120.22 | Completed | 100% |  |  | INFRA22 -004-14 |  | 2022-05-29 | 2022-06-21 | 2022-07-07 | 2022-08-10 |  | ARDRAW CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 5.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Dinagat Island | 132424 | Loreto Central Elementary School | LORETO | 0 | 1 | 18 | REPAIR/ REHABILITATION | 5797868.93 | 1 | 5792000 | Completed | 100% |  |  | INFRA22 -004-07 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132513 | Aurelio Elementary School | SAN JOSE (Capital) | 0 | 1 | 10 | REPAIR/ REHABILITATION | 10981671.28 | 1 |  | Completed | 100% | [10 empty] | realigned from cab-ilan to aurelio | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 11.23 |  | 1 | 10 | 10981671.28 | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132522 | San Jose CES-SPED Center | SAN JOSE (Capital) | 0 | 1 | 20 | REPAIR/ REHABILITATION | 10356113.41 | 1 | 9722672.08 | Completed | 100% |  |  | INFRA22 -004-09 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | AMA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | 0 | 1 | 5 | REPAIR/ REHABILITATION | 4361481.87 | 1 | 4270000 | Completed | 100% |  |  | INFRA22 -004-05 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | 0 |  | 8 | NEW CONSTRUCTION | 23418608.29 | 1 | 23390000 | Completed | 100% |  |  | INFRA22 -004-06 |  | 2022-05-29 | 2022-06-17 | 2022-06-30 | 2022-07-21 |  | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 11.23 |  | 1 | 8 | 23418608.29 | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1 | 1 | 7 | REPAIR/ REHABILITATION | 2730000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1 |  | 6 | NEW CONSTRUCTION | 16684552.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1530000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1 |  | 2 | NEW CONSTRUCTION | 6478614.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 | 1 | 11 | REPAIR/ REHABILITATION | 4965000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1 |  | 6 | NEW CONSTRUCTION | 16714552.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 13 | REPAIR/ REHABILITATION | 4412499.08 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10265937.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2445000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10250937.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1835000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 |  | 4 | NEW CONSTRUCTION | 10230937.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 | 1 | 39 | REPAIR/ REHABILITATION | 11650000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1 |  | 12 | NEW CONSTRUCTION | 33369105.5 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 | 1 | 5 | REPAIR/ REHABILITATION | 4414304.45 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1 |  | 4 | NEW CONSTRUCTION | 10310937.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 3225244.54 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1 |  | 4 | NEW CONSTRUCTION | 10230937.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2345000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1 |  | 5 | NEW CONSTRUCTION | 14966112.57 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 2 | NEW CONSTRUCTION | 6495614.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1 | 1 | 2 | NEW CONSTRUCTION | 6583614.88 | 1 |  | Completed | 100% | [10 empty] | under posqua | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 | 1 | 14 | REPAIR/ REHABILITATION | 5528191.84 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1 |  | 2 | NEW CONSTRUCTION | 6477614.88 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 | 12 | REPAIR/ REHABILITATION | 8000000 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1614929.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1 |  | 2 | NEW CONSTRUCTION | 6483614.89 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 | 1 | 7 | REPAIR/ REHABILITATION | 6492671.48 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1 |  | 3 | NEW CONSTRUCTION | 8407192.02 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 | 1 | 14 | REPAIR/ REHABILITATION | 12220934.1957 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1 |  | 6 | NEW CONSTRUCTION | 16714552.75 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2 | 1 | 35 | REPAIR/ REHABILITATION | 9865890.42 | 1 | 9850760.16 | Completed | 100% | 2023-03-14 | 2023-03-08 | QRF-REPAIR 2022- R CARAGA - SurIgao City - 224 | FY-2022-INFRA-002 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | E-JOB CONSTRUCTION & SUPPLY, OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2 |  | 4 | NEW CONSTRUCTION | 9464507.64 | 1 | 9098337.36 | Completed | 100% | 2023-03-14 | 2023-03-28 | QRF-REPAIR 2022- R CARAGA - SurIgao City - 316 | FY-2022-INFRA-007 | 2022-05-13 | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | EYT CONSTRUCTION & SUPPLY | WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132247 | Canlanipa Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 20 | REPAIR/ REHABILITATION | 10034402.06 | 1 | 10023076.22 | Completed | 100% | 2023-02-13 | 2023-02-03 | QRF-REPAIR 2022- R CARAGA - SurIgao City - 202 | FY-2022-INFRA-003 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | E-JOB CONSTRUCTION & SUPPLY, OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132299 | Mat-i Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 10 | REPAIR/ REHABILITATION | 8671265.02 | 1 | 6032737.66 | Completed | 100% | 2023-02-13 | 2023-02-03 | QRF-REPAIR 2022- R CARAGA - SurIgao City | FY-2022-INFRA-004 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-08-09 | 2022-08-17 | J-R3 CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132299 | Mat-i Central Elementary School | SURIGAO CITY (Capital) | 2 |  | 8 | NEW CONSTRUCTION | 19143244.17 | 1 | 18709118.82 | Completed | 100% | 2023-05-13 | 2023-05-09 | QRF-REPAIR 2022- R CARAGA - SurIgao City | FY-2022-INFRA-008 | 2022-05-13 | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2 | 1 | 21 | REPAIR/ REHABILITATION | 7918271.28 | 1 | 7906780.63 | Completed | 100% | 2022-12-15 | 2022-11-14 | QRF-REPAIR 2022- R CARAGA - SurIgao City - 225 | FY-2022-INFRA-005 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | P & G CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2 |  | 2 | NEW CONSTRUCTION | 6092191.78 | 1 | 5049241.83 | Completed | 100% | 2023-02-13 | 2023-02-10 | QRF-REPAIR 2022- R CARAGA - SurIgao City -314 | FY-2022-INFRA-009 | 2022-05-13 | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao City | 132287 | Surigao West Central Elementary School | SURIGAO CITY (Capital) | 2 | 1 | 32 | REPAIR/ REHABILITATION | 15985858.62 | 1 | 15971503.82 | Completed | 100% | 2023-03-14 | 2023-03-09 | QRF-REPAIR 2022- R CARAGA - SurIgao City -223 | FY-2022-INFRA-006 | 2022-05-13 | 2022-05-20 | 2022-06-03 | 2022-08-08 | 2022-08-17 | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao City | 132287 | Surigao West Central Elementary School | SURIGAO CITY (Capital) | 2 |  | 3 | NEW CONSTRUCTION | 7885468.72 | 1 | 7602801.87 | Completed | 100% | 2023-03-13 | 2023-03-23 | QRF-REPAIR 2022- R CARAGA - SurIgao City - 310 | FY-2022-INFRA- | 2022-05-13 | 2022-05-20 | 2022-06-06 | 2022-08-08 | 2022-08-17 | AMALGO CONSTRUCTION | WITH LIQUIDATED DAMAGES | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-02-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 11 | REPAIR/ REHABILITATION | 3540791.78 | 1 | 3358544.92 | Completed | 100% | 2022-11-29 |  | 003-QRF 2022-CARAGA | 018-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-27 | 2022-05-28 | JJRC CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 |  | 4 | NEW CONSTRUCTION | 9918782.27 | 1 | 8620681.42 | Completed | 100% | 2022-11-29 |  | 015-QRF 2022-CARAGA | 018-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 | 1 | 8 | REPAIR/ REHABILITATION | 5262784.16 | 1 |  | Completed | 100% |  |  | 004-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-28 | 2022-05-12 |  |  |  | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 |  | 3 | NEW CONSTRUCTION | 8170250.96 | 1 | 7756361.03 | Completed | 100% |  |  | 016-QRF 2022-CARAGA |  | 2022-06-13 | 2022-06-21 | 2022-07-04 |  |  | AMALGO CONSTRUCTION | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 | 1 | 9 | REPAIR/ REHABILITATION | 1584096.46 | 1 | 1580797.14 | Completed | 100% | 2022-12-30 |  | 007-QRF 2022-CARAGA | 021-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-06-06 | 2022-05-28 | SEGUA CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 |  | 4 | NEW CONSTRUCTION | 9884507.64 | 1 | 1580797.14 | Completed | 100% | 2022-12-30 |  | 018-QRF 2022-CARAGA | 021-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-06-06 | 2022-05-28 | SEGUA CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132407 | Gigaquit Central Elementary School | GIGAQUIT | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4493535.97 | 1 |  | Completed | 100% |  |  | 008-QRF 2022-CARAGA | [7 empty] | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132407 | Gigaquit Central Elementary School | GIGAQUIT | 2 |  | 3 | NEW CONSTRUCTION | 8170250.96 | 1 |  | Completed | 100% |  |  | 019-QRF 2022-CARAGA | [7 empty] | For Rebid | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132434 | Mainit CES | MAINIT | 2 | 1 | 15 | REPAIR/ REHABILITATION | 10718781.28 | 1 | 10670726.85 | Completed | 100% |  |  | 011-QRF 2022-CARAGA |  | 2022-04-21 | 2022-04-29 | 2022-05-13 |  |  | MICAH CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132434 | Mainit CES | MAINIT | 2 |  | 8 | NEW CONSTRUCTION | 20071355.67 | 1 | 20066581.62 | Completed | 100% |  |  | 022-QRF 2022-CARAGA |  | 2022-06-13 | 2022-06-21 | 2022-07-04 |  |  | RJB CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132437 | Matin-ao CES | MAINIT | 2 | 1 | 16 | REPAIR/ REHABILITATION | 10746950.83 | 1 |  | Completed | 100% |  |  | 012-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-29 | 2022-05-13 |  |  |  | For, reconsideration of the 2nd lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132437 | Matin-ao CES | MAINIT | 2 |  | 2 | NEW CONSTRUCTION | 6240190.85 | 1 |  | Completed | 100% |  |  | 023-QRF 2022-CARAGA |  | 2022-04-20 | 2022-04-29 | 2022-05-13 |  |  |  | For, reconsideration of the 2nd lowest bidder | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 | 1 | 4 | REPAIR/ REHABILITATION | 588886.08 | 1 | 585886.08 | Completed | 100% | 2022-10-30 |  | 009-QRF 2022-CARAGA | 022-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | DJNC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2 |  | 4 | NEW CONSTRUCTION | 9884507.64 | 1 | 9879769.75 | Completed | 100% | 2022-10-30 |  | 020-QRF 2022-CARAGA | 022-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 | 1 | 4 | REPAIR/ REHABILITATION | 550250.03 | 1 | 547043.86 | Completed | 100% | 2022-10-30 |  | 010-QRF 2022-CARAGA | 023-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | DJNC BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2 |  | 2 | NEW CONSTRUCTION | 6135190.85 | 1 | 6114918.5 | Completed | 100% | 2022-10-30 |  | 021-QRF 2022-CARAGA | 023-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | AMALGO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 21 | REPAIR/ REHABILITATION | 14288696.79 | 1 | 12572561.43 | Completed | 100% | 2023-02-24 |  | 001-QRF 2022-CARAGA | 016-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-27 | 2022-05-28 | BAMBOE CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 |  | 2 | NEW CONSTRUCTION | 6817690.85 | 1 | 6795903.07 | Completed | 100% | 2023-02-24 |  | 013-QRF 2022-CARAGA | 016-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-27 | 2022-05-28 | ROMZ BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132333 | Banbanon ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4921929.24 | 1 | 3636090.36 | Completed | 100% | 2023-01-29 |  | 002-QRF 2022-CARAGA | 017-2022 | 2022-04-20 | 2022-04-28 | 2022-05-12 | 2022-05-24 | 2022-05-28 | 3C'SL CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132333 | Banbanon ES | SAN FRANCISCO (ANAO-AON) | 2 |  | 4 | NEW CONSTRUCTION | 9412007.64 | 1 | 9402006.78 | Completed | 100% | 2023-01-29 |  | 014-QRF 2022-CARAGA | 017-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-24 | 2022-05-28 | EYT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132526 | Dakung Patag ES | SISON | 2 | 1 | 6 | REPAIR/ REHABILITATION | 4493535.97 | 1 | 3544784.88 | Completed | 100% | 2022-11-30 |  | 006-QRF 2022-CARAGA | 020-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-27 | 2022-05-28 | JR3 CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | 10 | REPAIR/ REHABILITATION | 4043914.75 | 1 | 4036000 | Completed | 100% | 2023-01-25 |  | 005-QRF 2022-CARAGA | 019-2022 | 2022-04-21 | 2022-04-29 | 2022-05-13 | 2022-05-24 | 2022-05-28 | WINDFALL CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 |  | 2 | NEW CONSTRUCTION | 6660190.85 | 1 | 5124396.34 | Completed | 100% | 2023-01-25 |  | 017-QRF 2022-CARAGA | 019-2022 | 2022-06-13 | 2022-06-21 | 2022-07-04 | 2022-05-24 | 2022-05-28 | FHD CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-03-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | NCR | Manila | 305294 | Jose P. Laurel High School | TONDO | 2 | 1 | 4 | REPAIR/ REHABILITATION | 1400000 | 1 | 1366297.64 | Completed | 100% | [9 empty] | Sherf Builders Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | Candon City | 235501 | Candon South Central School SPED Center | CITY OF CANDON | 2 | 1 | 2 | REPAIR/ REHABILITATION | 901319.11 | 1 | 895387.37 | Completed | 100% | 2022-09-16 | 2022-11-09 | N/A | N/A | 2022-05-27 | 2022-05-31 | 2022-05-31 | 2022-07-13 | 2022-07-18 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1819327.09 | 1 | 1811418.37 | Completed | 100% | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-01 | 2022- LU-01 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100875 | Balaoan CES | BALAOAN | 1 | 1 | 11 | REPAIR/ REHABILITATION | 6693187.73 | 1 | 6527091.32 | Completed | 100% | 2022-12-22 | 2022-12-21 | QRF2022-RO1-LU-02 | 2022 - LU - 02 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.M.B.M. CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | La Union | 100911 | Bauang North CS | BAUANG | 2 | 1 | 3 | REPAIR/ REHABILITATION | 1801364.18 | 1 | 1791987.88 | Completed | 100% | 2022-12-22 | 2022-12-20 | QRF2022-RO1-LU-03 | 2022 - LU - 03 | 2022-08-01 | 2022-08-10 | 2022-08-24 | 2022-09-01 | 2022-09-23 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region I | Laoag City | 153001 | Sto. Nino Elementary School | LAOAG CITY (Capital) | 1 | 1 | 3 | REPAIR/ REHABILITATION | 571180.68 | 1 | 567920.37 | Completed | 100% | Sept.18, 2022 | Sept. 15,2022 |  |  | June, 2022 | june, 2022 | 2022-07-01 | 2022-07-15 | 2022-08-04 | Elocin Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 | 1 | 7 | REPAIR/ REHABILITATION | 5231221.642 | 1 | 4700000 | Completed | 100% | [10 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | 0 |  | 18 | REPAIR/ REHABILITATION | 12917785.63 | 1 | 9900121.12 | Completed | 100% | [10 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region II | Batanes | 300411 | Batanes National Science High School | BASCO (Capital) | 0 | 1 | 12 | REPAIR/ REHABILITATION | 12975814.84 | 1 | 9450161.12 | Completed | 100% | [10 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region II | Batanes | 500063 | Raele Integrated School | Itbayat | 0 | 1 | 1 | REPAIR/ REHABILITATION | 1301588.05 | 1 | 1154807.42 | Completed | 100% | [10 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region II | Batanes | 102325 | Mahatao Elementary School | Mahatao | 0 | 1 | 2 | REPAIR/ REHABILITATION | 1731420.844 | 1 | 1506917.26 | Completed | 100% | [10 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-A | Tanauan City | 107754 | Bilogbilog Elementary School | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR/ REHABILITATION | 8175554.7148 | 1 |  | completed | 100% |  | 0 | [8 empty] | with RTA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 110749 | Araceli Central School | ARACELI | 1 | 1 | 11 | REPAIR/ REHABILITATION | 7012282.39 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 110750 | Araceli North Central School | ARACELI | 1 | 1 | 8 | REPAIR/ REHABILITATION | 5415010.46 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 110789 | Tinintinan Elementary School | ARACELI | 1 | 1 | 8 | REPAIR/ REHABILITATION | 5157828.99 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 110767 | Dumaran CS | DUMARAN | 1 | 1 | 1 | REPAIR/ REHABILITATION | 282965.41 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 111164 | Roxas North CS | ROXAS | 1 | 1 | 9 | REPAIR/ REHABILITATION | 1497092.41 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 111167 | San Dionisio Elementary School | ROXAS | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2683970.9 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 111185 | Bunuangin ES | SAN VICENTE | 1 | 1 | 3 | REPAIR/ REHABILITATION | 2033552.6384 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2234236.49 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2813770.5599 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1 |  | 2 | NEW CONSTRUCTION | 3902365.91 | 1 | 3825427.78 | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region IV-B | Palawan | 111195 | New Caruray Elementary School | SAN VICENTE | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1374418.02 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 | 1 | 6 | REPAIR/ REHABILITATION | 2276096.86 | 1 |  | Completed | 100% | [10 empty] | suspended, will resume after holyweek | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1 |  | 6 | NEW CONSTRUCTION | 16954914.25 | 1 | 16836299.29 | Completed | 100% | 2023-09-07 |  | 2022-11-006-INFRA | 2022-11-006-INFRA - LOT 3 | 2022-11-16 | 2022-11-28 | 2022-12-09 | 2022-12-19 | 2023-01-03 | EM Abin Trading and Construction | suspended, will resume after holyweek | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2706331.4978 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1 |  | 10 | NEW CONSTRUCTION | 45000000 | 1 | 44662500 | Completed | 100% | 2023-09-01 |  | 2022-11-006-INFRA | 2022-11-006-INFRA - LOT 1 | 2022-11-16 | 2022-11-28 | 2022-12-09 | 2022-12-19 | 2023-01-03 | Maryknoll Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region IV-B | Palawan | 309103 | Central Taytay NHS | TAYTAY | 1 | 1 | 16 | REPAIR/ REHABILITATION | 2996974.5083 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Palawan | 111219 | Judge Cesar L. Rodriguez ES | TAYTAY | 1 | 1 | 11 | REPAIR/ REHABILITATION | 4025753.68 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IV-B | Puerto Princesa City | 111516 | Langogan ES | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 13 | REPAIR/ REHABILITATION | 8109763.39 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Puerto Princesa City | 111528 | Salvacion CS | PUERTO PRINCESA CITY (Capital) | 2 | 1 | 6 | REPAIR/ REHABILITATION | 3408366.312 | 1 |  | completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region IV-B | Puerto Princesa City | 111528 | Salvacion CS | PUERTO PRINCESA CITY (Capital) | 2 |  | 4 | NEW CONSTRUCTION | 15811897.04 | 1 | 15007576.16 | completed | 100% | Sept. 24, 2023 |  |  | Infra 2022-11-002 | Nov. 29, 2022 | Dec. 6, 2022 | 2022-12-19 | 2022-01-11 | 2022-01-13 | GS MOTAR BUILDERS CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region IX | Zamboanga del Norte | 124541 | New Siquijor ES | MUTIA | 1 | 1 | 4 | REPAIR/ REHABILITATION | 2256282.5094 | 1 | 2251032.51 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124738 | Bagacay ES | SIBUTAD | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2846844.2811 | 1 | 2841594.28 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124740 | Calilic ES | SIBUTAD | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1661419.86 | 1 | 1659319.86 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124742 | Delapa ES | SIBUTAD | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1677169.86 | 1 | 1675069.86 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 23, 2022 | Smart Move Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124743 | Kanim ES | SIBUTAD | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2774392.3764 | 1 | 2769142.38 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4547777.0333 | 1 | 4547777.03 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124802 | Mandih CS | SINDANGAN | 2 | 1 | 6 | REPAIR/ REHABILITATION | 3444320.6957 | 1 | 3443315.59 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | MJMARI Builders and Development Corporation | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124417 | Labason CS | LABASON | 3 | 1 | 8 | REPAIR/ REHABILITATION | 4503127.9593 | 1 | 4502127.32 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | MJMARI Builders and Development Corporation | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-03-01 | 4.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region IX | Zamboanga del Norte | 124625 | Bacong CS | SALUG | 3 | 1 | 6 | REPAIR/ REHABILITATION | 3348970.27 | 1 | 3338470.27 | Completed | 100% | 2022-12-30 | 2022-12-30 | QRF 2022 - RIX - ZAMBOANGA DEL NORTE | QRF2022-R IX-ZDN-1 | 2022-05-27 | 2022-06-08 | 2022-06-17 | 2022-06-30 | Sept. 12, 2022 | YSL Builders | None | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 1 | REPAIR/ REHABILITATION | 1155849.257 | 1 | 1135148.82 | Completed | 100% | 2023-06-01 | 2023-07-05 | Bago-QRF-2022-C1 | 002-2023 | 2022-11-11 | 2022-11-18 | 2022-12-02 |  | 2023-02-02 | Sunshine Sapphire Construction and Supply, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 5 | REPAIR/ REHABILITATION | 1032901.1361 | 1 | 1031087.4 | Completed | 100% | 2023-06-01 |  | Bago-QRF-2022-C1 | 002-2023 | 2022-11-11 | 2022-11-18 | 2022-12-02 |  | 2023-02-02 | Sunshine Sapphire Construction and Supply, Inc. | Punchlisted items were not completely rectified by the contractor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 12.24 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Guimaras | 115844 | Supang Central School | BUENAVISTA | 0 | 1 | 4 | REPAIR/ REHABILITATION | 2926129.7794 | 1 | 2433541.73 | completed | 100% | 2022-12-29 | 2022-12-26 | 05-2022-lot 1 | 05-2022-lot 1 | No. 05-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | ALJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2464442.2247 | 1 | 3155555.55 | completed | 100% | 2022-12-29 | 2023-12-29 | 05-2022-lot2 | 05-2022-lot2 | No. 05-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | Early Riser Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Guimaras | 115877 | Ayangan Elementary School | SIBUNAG | 0 | 1 | 6 | REPAIR/ REHABILITATION | 3191080.3436 | 1 | 2900000 | completed | 100% | 2022-12-29 | 2022-12-28 | 05-2022-lot3 | 05-2022-lot3 | No. 05-C-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | IJOJPA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Iloilo | 116570 | Miagao Central Elementary School | MIAGAO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2089631.17 | 1 |  | completed | 100% |  | 2022-11-17 | QRF2022-RVI-022-ILOILO-L1 |  | 2022-06-03 |  | 2022-06-27 | 2022-08-08 | 2022-10-14 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-03-01 | 2.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Iloilo | 116740 | San Joaquin Central Elementary School | SAN JOAQUIN | 1 | 1 | 2 | REPAIR/ REHABILITATION | 842235.89 | 1 |  | completed | 100% |  | 2022-11-17 | QRF2022-RVI-022-ILOILO-L1 |  | 2022-06-03 |  | 2022-06-27 | 2022-08-08 | 2022-10-14 | ANJUSH BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 2.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Kabankalan City | 117833 | Bugtong ES | CITY OF KABANKALAN | 6 | 1 | 3 | NEW CONSTRUCTION | 7562127.58 | 1 |  | completed | 100% | 2023-09-20 | [8 empty] | rism builders and construction services inc |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VI | La Carlota City | 183001 | Haguimit ES II | LA CARLOTA CITY | 4 | 1 | 2 | NEW CONSTRUCTION | 5033505.33 | 1 | 4786615.62 | Completed | 100% | 2023-04-26 | 2023-10-26 | 44835 | 44835 | 2022-08-24 | 2022-09-02 | 2022-09-14 |  | 2022-10-21 | Alesca Construction Services | On -going, with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 12.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VI | Negros Occidental | 116901 | Calatrava I Central School | CALATRAVA | 1 | 1 | 1 | REPAIR/ REHABILITATION | 518534.72 | 1 | 514321.31 | Completed | 100% | 2023-03-15 | 2023-01-23 | 22-06-57 | 22-12-002 | 2022-07-09 |  | 2022-06-15 | Sept. 8, 2022 | Dec.5, 2022 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Negros Occidental | 117418 | Toboso CS | TOBOSO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 8089258.7 | 1 | 5297304.81 | Completed | 100% | 2023-04-09 |  | 22-05-20 | 22-10-003 | 2022-05-25 | 2022-06-02 | 2022-06-14 | 2022-08-09 | 2022-11-10 | TACOLOD ENTERPRISES INC. | subject for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Negros Occidental | 116945 | Candoni CES | CANDONI | 6 | 1 | 10 | REPAIR/ REHABILITATION | 5967014.47 | 1 | 3500000 | completed | 100% | 2023-05-08 |  | 22-07-24 | 22-10-004 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 18, 2022 | ############# | TACOLOD ENTERPRISES INC. | resumed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 11.24 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VI | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6 |  | 2 | NEW CONSTRUCTION | 7130281.67 | 1 | 5399595.7 | Completed | 100% | 2023-04-22 | 2023-06-14 | 22-07-05 | 22-10-005 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 15, 2022 | ############# | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VI | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6 | 1 | 10 | REPAIR/ REHABILITATION | 4031169.304 | 1 | 2768808.34 | Completed | 100% | 2023-02-22 | 2023-02-08 | 22-07-23 | 22-10-006 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 13, 2022 | 2022-11-11 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | San Carlos City | 117763 | Prosperidad ES | SAN CARLOS CITY | 1 | 1 | 11 | REPAIR/ REHABILITATION | 3925500.03 | 1 | 3904313.69 | COMPLETED | 100% | 2023-05-10 | 2023-03-13 | QRF 2022-RVI-SAN CARLOS CITY-003(BATCH1, Typoon oditte | 8652568 | 2022-05-08 | 2022-05-16 | 2022-05-30 | 2022-12-22 | 2023-01-04 | PAR Builder and Construction Supply, Corp. | realigned change physical target same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | previous yrs |  | 1 | 8 | 3925500.03 | REPAIR | COMPLETED
QRF 2022 | Region VI | Silay City | 117821 | Guimbala-on ES | SILAY CITY | 3 | 1 | 3 | REPAIR/ REHABILITATION | 1314790.08 | 1 | 1105354 | Completed | 100% |  |  | R6-D18-QRF2022-GES | R6-D18-QRF2022-GES | 2022-09-28 | 2022-10-06 | 2022-10-19 | 2022-12-05 | 2023-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VI | Silay City | 117821 | Guimbala-on ES | SILAY CITY | 3 |  | 5 | NEW CONSTRUCTION | 13240270.81 | 1 | 11131196 | Completed | 100% | 2023-11-20 |  | R6-D18-QRF2022-GES | R6-D18-QRF2022-GES | 2022-09-28 | 2022-10-06 | 2022-10-19 | 2022-12-05 | 2023-01-04 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Waiting for approval of variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VI | Sipalay City | 117367 | Binulig ES | CITY OF SIPALAY | 6 | 1 | 12 | REPAIR/ REHABILITATION | 1971461.23 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-03-01 | 2.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bais City | 120093 | Lo-oc ES | BAIS CITY | 2 | 1 | 5 | REPAIR/ REHABILITATION | 2505799.8511 | 1 | 2204740.3 | Completed | 100% | 2022-12-19 |  |  |  |  | 2022-06-15 | 2022-06-28 | 2022-08-10 | 2022-08-19 | Per Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bayawan City | 120123 | Bayawan City East Central School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 11 | REPAIR/ REHABILITATION | 4843369.1238 | 1 | 4798000 | Completed | 100% |  |  |  |  | 2022-06-10 | 2022-06-16 | 2022-06-28 | 2022-07-07 | 2022-08-09 | RISM Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 118092 | Calape Central ES | CALAPE | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2035879.1023 | 1 | 1688711.75 | Completed | 100% | 2023-06-05 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 118169 | Catigbian Central ES | CATIGBIAN | 1 | 1 | 3 | REPAIR/ REHABILITATION | 394702.3278 | 1 | 8481676.16 | Completed | 100% | 2023-05-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 118169 | Catigbian Central ES | CATIGBIAN | 1 |  | 4 | NEW CONSTRUCTION | 10000000 | 1 | one contract only | Completed | 100% | 2023-05-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VII | Bohol | 118170 | Catigbian West Central ES | CATIGBIAN | 1 | 1 | 7 | REPAIR/ REHABILITATION | 2464214.5948 | 1 | 2078987.8 | Completed | 100% | 2023-05-28 | 2023-07-13 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 118485 | Loon North Central ES | LOON | 1 | 1 | 13 | REPAIR/ REHABILITATION | 9920579.6796 | 1 | 10807364.11 | completed | 100% | 2023-07-10 | 2023-06-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118485 | Loon North Central ES | LOON | 1 |  | 2 | NEW CONSTRUCTION | 5000000 | 1 | one contract only | completed | 100% | 2023-07-10 | 2023-06-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118500 | Loon South Central ES | LOON | 1 | 1 | 13 | REPAIR/ REHABILITATION | 4011500.3828 | 1 |  | completed | 100% | 2023-06-10 | 2023-05-18 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118544 | Maribojoc Central Elementary School | MARIBOJOC | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1123979.4978 | 1 | 949762.26 | completed | 100% | 2023-06-05 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118797 | Tubigon West Central ES | TUBIGON | 1 | 1 | 36 | REPAIR/ REHABILITATION | 7865817.4963 | 1 | 7848025.48 | completed | 100% | 2023-05-26 | 373821 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | 27 | REPAIR/ REHABILITATION | 3010520.9927 | 1 | 2080522.21 | completed | 100% | 2023-07-03 | 2023-06-03 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118065 | Buenavista CES | BUENAVISTA | 2 | 1 | 7 | REPAIR/ REHABILITATION | 2690422.9533 | 1 |  | Completed | 100% | 2023-05-28 | 2023-06-05 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2 | 1 | 15 | REPAIR/ REHABILITATION | 3895366.2255 | 1 |  | Completed | 100% | 2023-05-26 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VII | Bohol | 118239 | Danao Central Elementary School | DANAO | 2 | 1 | 22 | REPAIR/ REHABILITATION | 7899199.8429 | 1 |  | completed | 100% | 2023-09-23 | 2023-09-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118239 | Danao Central Elementary School | DANAO | 2 |  | 6 | NEW CONSTRUCTION | 15000000 | 1 | one contract only | completed | 100% | 2023-09-23 | 2023-09-15 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned scope of works same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 9.23 |  | 1 | 6 | 15000000 | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118245 | Rowena Heights Elementary School | DANAO | 2 | 1 | 3 | NEW CONSTRUCTION | 7749834.84 | 1 | 7719318.54 | Completed | 100% | 2023-06-13 | 2023-06-09 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned from cansibuan ps | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 7.23 |  | 1 | 3 | 7749834.84 | REPLACEMENT | Completed
QRF 2022 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 11 | REPAIR/ REHABILITATION | 4603452.9769 | 1 | 14585019 | completed | 100% | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 4 | NEW CONSTRUCTION | 10000000 | 1 | one contract only | completed | 100% | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | realigned scope of works same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 11.23 |  | 1 | 4 | 10000000 | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118401 | Inabanga South Central Elementary School | INABANGA | 2 | 1 | 30 | REPAIR/ REHABILITATION | 9700192.5988 | 1 | 8439155.95 | completed | 100% | 2023-09-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118600 | President Carlos P. Garcia Central Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | 20 | REPAIR/ REHABILITATION | 9625173.5979 | 1 | 13325173.09 | completed | 100% | 2023-08-19 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT(WARNING FOR TERMINATION) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2023-04-01 | 6.24 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118600 | President Carlos P. Garcia Central Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2 |  | 3 | NEW CONSTRUCTION | 7500000 | 1 | one contract only | completed | 100% | 2023-08-19 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT(WARNING FOR TERMINATION) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 6.24 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118656 | San Miguel Central ES | SAN MIGUEL | 2 | 1 | 19 | REPAIR/ REHABILITATION | 6065984.0904 | 1 |  | completed | 100% | 2023-06-05 | 2023-05-24 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118656 | San Miguel Central ES | SAN MIGUEL | 2 |  | 1 | NEW CONSTRUCTION | 2500000 | 1 | 6766919.52 | completed | 100% | 2023-06-05 | 2023-05-24 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118729 | Talibon Central ES | TALIBON | 2 | 1 | 2 | REPAIR/ REHABILITATION | 633410.9605 | 1 |  | completed | 100% |  | 2023-03-28 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118743 | TALIBON II CENTRAL ES | TALIBON | 2 | 1 | 3 | REPAIR/ REHABILITATION | 959316.783 | 1 |  | completed | 100% | 2023-06-02 | 2028-03-28 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118768 | Trinidad Central Elementary School | TRINIDAD | 2 | 1 | 10 | REPAIR/ REHABILITATION | 2766141.8503 | 1 |  | completed | 100% | 2023-06-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | 26 | REPAIR/ REHABILITATION | 7670181.2855 | 1 | 6664002.04 | completed | 100% | 2023-08-02 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | FOR PUCNHLISTING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 100% | 0% | 2023-04-01 | 6.24 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118843 | Ubay Central ES | UBAY | 2 | 1 | 20 | REPAIR/ REHABILITATION | 6137354.1844 | 1 | 5187762.92 | completed | 100% | 2023-06-10 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118804 | Ubay II Central ES (Biabas CES ) | UBAY | 2 | 1 | 17 | REPAIR/ REHABILITATION | 4963731.713 | 1 |  | completed | 100% | 2023-06-10 | 2023-05-17 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 117936 | Alicia Central Elem. | ALICIA | 3 | 1 | 9 | REPAIR/ REHABILITATION | 2206602.4549 | 1 | 3765037.24 | completed | 100% | 2023-06-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 117936 | Alicia Central Elem. | ALICIA | 3 |  | 1 | NEW CONSTRUCTION | 2500000 | 1 | one contract only | completed | 100% | 2023-06-27 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 10.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 186507 | Alicia CES Annex | ALICIA | 3 | 1 | 2 | REPAIR/ REHABILITATION | 800000 | 1 | 643141.32 | completed | 100% | 2023-06-02 | 2023-07-21 |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | 19 | REPAIR/ REHABILITATION | 5594602.4759 | 1 | 23440717.89 | completed | 100% | 2023-11-13 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% | 2023-04-01 | 12.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 |  | 9 | NEW CONSTRUCTION | 22500000 | 1 | one contract only | completed | 100% | 2023-11-13 |  |  |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 9.23 |  | 1 | 9 | 22500000 | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118136 | Carmen West Central ES | CARMEN | 3 | 1 | 6 | REPAIR/ REHABILITATION | 2319764.4847 | 1 | 1869129.45 | completed | 100% | 2023-06-02 | 2023-08-04 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118291 | Duero Central ES | DUERO | 3 | 1 | 3 | REPAIR/ REHABILITATION | 1200000 | 1 | 1056904.73 | completed | 100% | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118312 | Garcia-Hernandez Central ES | GARCIA HERNANDEZ | 3 | 1 | 3 | REPAIR/ REHABILITATION | 1200000 | 1 | 1056904.73 | completed | 100% | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118437 | Lila Central ES | LILA | 3 | 1 | 4 | REPAIR/ REHABILITATION | 648384.0631 | 1 | 572086.04 | completed | 100% | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3 | 1 | 31 | REPAIR/ REHABILITATION | 3139918.14 | 1 |  | completed | 100% |  |  | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 31 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3 |  | 8 | NEW CONSTRUCTION | 20000000 | 1 | one contract only | completed | 100% | 2023-10-01 |  | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | 60 DAYS EXT | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118693 | Sierra Bullones Central ES | SIERRA BULLONES | 3 | 1 | 5 | REPAIR/ REHABILITATION | 2000000 | 1 | 7599717.51 | completed | 100% | 2023-08-02 | 2023-08-18 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Bohol | 118693 | Sierra Bullones Central ES | SIERRA BULLONES | 3 |  | 3 | NEW CONSTRUCTION | 7500000 | 1 | one contract only | completed | 100% | 2023-08-02 | 2023-08-18 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Bohol | 118864 | Valencia Central Elementary School | VALENCIA | 3 | 1 | 4 | REPAIR/ REHABILITATION | 624035.1223 | 1 | 546229.05 | completed | 100% | 2023-06-26 | 2023-07-20 | 0 |  | 2022-08-12 | 2022-08-22 | 2022-09-06 |  |  |  | ONGOING POST QUA | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Carcar City | 324904 | Tuyom National High School | CITY OF CARCAR | 1 | 1 | 20 | REPAIR/ REHABILITATION | 5641920.23 | 1 | 4296456.4 | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Cebu | 119073 | BARILI CES | BARILI | 3 | 1 | 2 | REPAIR/ REHABILITATION | 2677562.96 | 1 | 8109500.82 | COMPLETED | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-04 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 6.24 |  | 1 | 18 | 9000000 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 119073 | BARILI CES | BARILI | 3 |  | 2 | NEW CONSTRUCTION | 5462455.36 | 1 | 8109500.82 | COMPLETED | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-04 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 6.24 |  |  | 1 | 2500000 | REPLACEMENT | COMPLETED
QRF 2022 | Region VII | Cebu | 119092 | GUIBUANGAN CS | BARILI | 3 | 1 | 5 | REPAIR/ REHABILITATION | 2449646.32 | 1 | 2431144.86 | COMPLETED | 100% | 2023-11-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-05 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | AL SHER CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 6.24 |  | 1 | 28 | 14000000 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 119554 | Binabag ES | PINAMUNGAHAN | 3 | 1 | 6 | REPAIR/ REHABILITATION | 4245989.99 | 1 | 4224375.21 | COMPLETED | 100% | 2023-12-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-06 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | HERO CONSTRUCTION AND DEV. CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 6.24 |  | 0 | 0 | 0 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 | 1 | 5 | REPAIR/ REHABILITATION | 3582726.85 | 1 | 9562486.57 | Completed | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-01 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MANINGO ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 8.24 |  | 1 | 6 | 3000000 | REPAIR | Completed
QRF 2022 | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5 |  | 2 | NEW CONSTRUCTION | 6011939.84 | 1 | 9562486.57 | Completed | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-01 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MANINGO ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.24 |  |  | 2 | 5000000 | REPLACEMENT | Completed
QRF 2022 | Region VII | Cebu | 119238 | Consolacion Central ES | CONSOLACION | 6 | 1 | 24 | REPAIR/ REHABILITATION | 1942416.66 | 1 | 1934634.58 | COMPLETED | 100% | 2023-12-18 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-03 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | JY BONTILAO CONSTRUCTION AND ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% | 2023-04-01 | 6.24 |  | 1 | 24 | 4800000 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 119255 | Cordova Central ES | CORDOVA | 6 | 1 | 10 | REPAIR/ REHABILITATION | 2032057.71 | 1 | 2024217.87 | COMPLETED | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 6.24 |  | 1 | 9 | 4500000 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 302955 | Cordova NHS | CORDOVA | 6 | 1 | 20 | REPAIR/ REHABILITATION | 8932633.17 | 1 | 8856359.04 | COMPLETED | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-02 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2024 | 2023-09-11 | SB & T CONSTRUCTION OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% | 2023-04-01 | 6.24 |  | 0 | 0 |  | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu | 118866 | ALCANTARA CENTRAL ES | ALCANTARA | 7 | 1 | 6 | REPAIR/ REHABILITATION | 9144788.68 | 1 | 9127739.72 | Completed | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-08 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | RT CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 8.24 |  | 1 | 14 | 7000000 | REPAIR | Completed
QRF 2022 | Region VII | Cebu | 118994 | BADIAN CS | BADIAN | 7 | 1 | 3 | REPAIR/ REHABILITATION | 1234605.36 | 1 | 1219140.57 | completed | 100% | 2023-11-03 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-09 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | TRI BAIRN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 1.24 |  | 1 | 2 | 1000000 | REPAIR | completed
QRF 2022 | Region VII | Cebu | 119384 | BITOON CES | DUMANJUG | 7 | 1 | 19 | REPAIR/ REHABILITATION | 9583177.1 | 1 | 9533171.37 | COMPLETED | 100% | 2024-01-17 |  | CY 2022 QRF DEPED | CY 2022 QRF-DEPED-R7-CEBU-07 | JULY 19, 2023 | JULY 26, 2023 | AUGUST 07, 2023 | AUGUST 29, 2023 | 2023-09-11 | MP SORELA CONSTRUCTION AND SUPPLY AND MARINE SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% | 2023-04-01 | 6.24 |  | 1 | 13 | 6500000 | REPAIR | COMPLETED
QRF 2022 | Region VII | Cebu City | 119874 | City Central ES | CEBU CITY (Capital) | 1 | 1 | 12 | REPAIR/ REHABILITATION | 2750822 | 1 | 2116754.46 | completed | 100% | 2023-01-13 |  | DepEd CCD 2022 - 11 | DepEd CCD 2022 - 27 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 8, 2022 | JAJ & L CONST. & ENG'G sERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Cebu City | 303153 | City Central NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | 5 | REPAIR/ REHABILITATION | 668241 | 1 | 510702.36 | completed | 100% | 2022-11-14 |  | DepEd CCD 2022 - 12 | DepEd CCD 2022 - 28 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 8, 2022 | JAJ & L CONST. & ENG'G sERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Cebu City | 119882 | Mambaling ES | CEBU CITY (Capital) | 2 | 1 | 10 | REPAIR/ REHABILITATION | 3219187.68 | 1 | 2315902.45 | completed | 100% | 2023-01-25 |  | DepEd CCD 2022 - 13 | DepEd CCD 2022 - 29 | 2022-07-09 | 2022-07-18 | 2022-08-01 | 2022-08-12 | Sept. 20, 2022 | ANIELTHON CONST. & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | City of Naga, Cebu | 119516 | Cepoc Central Elementary School | CITY OF NAGA | 1 | 1 | 8 | REPAIR/ REHABILITATION | 3999819.9246 | 1 | 3992404.31 | completed | 100% | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | SB & T Construction OPC | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | City of Naga, Cebu | 119509 | Naga Central Elementary School | CITY OF NAGA | 1 | 1 | 13 | REPAIR/ REHABILITATION | 6498802.268 | 1 | 6487267.56 | completed | 100% | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | TRI BAIRN CONSTRUCTION | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | City of Naga, Cebu | 500218 | Naga Special Education Center | CITY OF NAGA | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4999370.2543 | 1 | 4990393.35 | completed | 100% | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | TRI BAIRN CONSTRUCTION | LOT 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | City of Naga, Cebu | 119512 | Tuyan Central Elementary School | CITY OF NAGA | 1 | 1 | 10 | REPAIR/ REHABILITATION | 5025620.2543 | 1 | 4979100.18 | completed | 100% | 2022-10-25 |  | cityofnaga2022-001 |  | 2022-04-12 | 2022-04-19 | 2022-05-04 | 2022-05-25 | 2022-06-20 | SB & T Construction OPC | LOT 2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Lapu-Lapu City | 119954 | Caw-oy Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 12 | REPAIR/ REHABILITATION | 4351778.22 | 1 |  | completed | 100% |  |  | 0 | [7 empty] | realigned same school change target and scope | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-04-01 | 7.23 |  | 1 | 10 | 4351778.22 | REPAIR | completed
QRF 2022 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City Central Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | 75 | REPAIR/ REHABILITATION | 36000000 | 1 |  | completed | 100% | January 26, 2023 |  | 2022-Infra-001 |  | June 22, 2022 | June 29, 2022 | July 11, 2022 | July 29, 2022 | December 29, 2022 | MANINGO ENTERPRISES | realigned same school change target and scope | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 75 | 100% | 0% | 2023-04-01 | 12.24 |  | 1 | 72 | 36000000 | REPAIR | completed
QRF 2022 | Region VII | Lapu-Lapu City | 119989 | Lapu-Lapu City Central Elementary School | LAPU-LAPU CITY (OPON) | 6 |  | 8 | REPAIR/ REHABILITATION | 27500000 | 1 |  | Completed | 100% | January 26, 2023 |  | 2022-Infra-001 |  | June 22, 2022 | June 29, 2022 | July 11, 2022 | July 29, 2022 | December 29, 2022 | MANINGO ENTERPRISES | realigned same school change target and scope | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 12.24 |  |  | 11 | 27500000 | REPAIR | Completed
QRF 2022 | Region VII | Negros Oriental | 120171 | Bindoy Central Elementary School | BINDOY (PAYABON) | 1 | 1 | 2 | REPAIR/ REHABILITATION | 6064404.0823 | 1 | 4807442.21 | completed | 100% | 2023-02-04 |  | ITB 2022-04-023 | QRF202209011 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-26 | TRIBATA CONSTRUCTION AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Negros Oriental | 120320 | La Libertad CES | LA LIBERTAD | 1 | 1 | 11 | REPAIR/ REHABILITATION | 11136631.2814 | 1 | 11129033.97 | completed | 100% | 2023-03-06 |  | ITB 2022-04-024 | QRF202209012 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Negros Oriental | 120604 | Tayasan CES | TAYASAN | 1 | 1 | 24 | REPAIR/ REHABILITATION | 9524722.2311 | 1 | 9519067.28 | completed | 100% | 2023-03-06 |  | ITB 2022-04-026 | QRF202209014 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Negros Oriental | 120366 | Mabinay Central School | MABINAY | 2 | 1 | 8 | REPAIR/ REHABILITATION | 4478136.1502 | 1 | 3627000 | completed | 100% | 2023-02-04 |  | ITB 2022-04-025 | QRF202209013 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 2.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1318876.303 | 1 | 1000473.71 | completed | 100% | 2022-11-29 |  | ITB 2022-04-021 | QRF202209009 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-29 | MDBD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Negros Oriental | 120438 | Siapo Elementary School | SAN JOSE | 2 | 1 | 5 | REPAIR/ REHABILITATION | 2429147.1364 | 1 | 1850263.91 | completed | 100% | 2023-02-07 |  | ITB 2022-04-022 | QRF202209010 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-29 | MDBD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 6.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Talisay City | 322203 | Manipis National High School | CITY OF TALISAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1926214.1136 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-03-01 | 1.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Talisay City | 119803 | Tabunoc Central School | CITY OF TALISAY | 1 | 1 | 4 | REPAIR/ REHABILITATION | 1869425.3973 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Talisay City | 119791 | Talisay City CES | CITY OF TALISAY | 1 | 1 | 38 | REPAIR/ REHABILITATION | 7433950.4127 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 38 | 100% | 0% | 2022-12-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VII | Talisay City | 119791 | Talisay City CES | CITY OF TALISAY | 1 |  | 12 | NEW CONSTRUCTION | 30000000 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-03-01 | 7.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VII | Toledo City | 120757 | South City Central ES | TOLEDO CITY | 3 | 1 | 22 | REPAIR/ REHABILITATION | 11050000 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% | 2023-03-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Eastern Samar | 122606 | Balangkayan Central Elementary School | BALANGKAYAN | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2595388.38 | 1 |  | Completed | 100% | 2023-10-05 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | 24 | REPAIR/ REHABILITATION | 7737161.07 | 1 |  | completed | 100% | 2023-08-06 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Eastern Samar | 122485 | Hernani Central Elementary School | HERNANI | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2592763.38 | 1 |  | Completed | 100% | 2023-09-29 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | 0 | 1 | 32 | REPAIR/ REHABILITATION | 6867954.14 | 1 |  | completed | 100% | 2023-11-28 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 | 1 | 6 | REPAIR/ REHABILITATION | 779227.1 | 1 | 768434.28 | Completed | 100% | 2023-10-29 |  |  |  | 2022-09-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Maasin City | 122153 | BOGO MULTIGRADE SCHOOL | CITY OF MAASIN (Capital) | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1404999.36 | 1 | 1382613.1 | COMPLETED | 100% | 2023-11-10 | 2022-09-26 | QRF-22-05-Lot 4 | QRF-22-05-Lot 4 | 2022-05-05 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Maasin City | 122125 | Cambooc MGS | CITY OF MAASIN (Capital) | 1 | 1 | 5 | REPAIR/ REHABILITATION | 3253353.731 | 1 | 3089138.14 | COMPLETED | 100% | 2023-11-10 | 2023-01-26 | QRF-22-05-Lot 3 | QRF-22-05-Lot 3 | 2022-05-05 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Maasin City | 122135 | Maasin Central School | CITY OF MAASIN (Capital) | 1 | 1 | 28 | REPAIR/ REHABILITATION | 14596082.8742 | 1 | 14455745.63 | completed | 100% | 2023-10-05 | 2023-07-12 | QRF-22-08-Lot 1 | QRF-22-08-Lot 1 | 2022-08-12 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 28 | 100% | 0% | 2023-04-01 | 12.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Maasin City | 122174 | San Rafael ES | CITY OF MAASIN (Capital) | 1 | 1 | 9 | REPAIR/ REHABILITATION | 3767359.1745 | 1 | 2899480.95 | COMPLETED | 100% | 2023-08-16 | 2023-01-03 | QRF-22-05-Lot 2 | QRF-22-05-Lot 2 | 2022-05-05 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 | 1 | 3 | REPAIR/ REHABILITATION | 2184122.06 | 1 | 2130557.53 | completed | 100% | 2023-09-30 | 2023-04-03 | QRF-2021-RVIII-Ormoc | QRF-CY2022-REPAIR | 2022-08-03 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Southern Leyte | 121996 | Bontoc Central School | BONTOC | 1 |  | 4 | REPAIR/ REHABILITATION | 7631879.2227 | 1 | 7555561.07 | COMPLETED | 100% | 2023-10-30 |  | CY2022-QRF-Gabaldon-L16 | CY2022-QRF-Gabaldon-L16 | 2022-04-27 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Southern Leyte | 121996 | Bontoc Central School | BONTOC | 1 | 1 | 34 | REPAIR/ REHABILITATION | 12766248.59 | 1 | 7555561.07 | COMPLETED | 100% | 2023-10-30 |  | CY2022-QRF-Gabaldon-L16 | CY2022-QRF-Gabaldon-L16 | 2022-04-27 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Southern Leyte | 122006 | Himakilo Primary School | BONTOC | 1 | 1 | 1 | REPAIR/ REHABILITATION | 570045.72 | 1 | 564999.05 | COMPLETED | 100% | 2023-10-29 |  | CY2022-QRF-Repair-L9 | CY2022-QRF-Repair-L9 | 2022-04-27 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Southern Leyte | 303465 | LIMASAWA NATIONAL HIGH SCHOOL | LIMASAWA | 1 | 1 | 36 | REPAIR/ REHABILITATION | 12804218.42 | 1 | 12703879.05 | Completed | 100% |  |  | CY2022-QRF-Repair-L1 | CY2022-QRF-Repair-L1 | 2022-04-27 | [5 empty] | for procurement;revised pow | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122221 | Lugsongan Elementary School | LIMASAWA | 1 | 1 | 9 | REPAIR/ REHABILITATION | 5112651.73 | 1 | 2073549.03 | Completed | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 9 | REPAIR/ REHABILITATION | 5283041.75 | 1 | 12305913.39 | COMPLETED | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-02 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | ANIELTHON CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 |  | 2 | NEW CONSTRUCTION | 5702801.39 | 1 | 693338 | COMPLETED | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | COMPLETED
QRF 2022 | Region VIII | Southern Leyte | 122225 | San Agustin Elementary School | LIMASAWA | 1 | 1 | 7 | REPAIR/ REHABILITATION | 3026805.88 | 1 | 5707088.03 | completed | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-03 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 | 1 | 6 | REPAIR/ REHABILITATION | 3261340.07 | 1 | 3560851.53 | completed | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-04 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | SB & T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 |  | 2 | NEW CONSTRUCTION | 6575848.24 | 1 | 2491050.24 | completed | 100% | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-05 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | HERO CONTRUCTION AND DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region VIII | Southern Leyte | 122189 | Macrohon Central School | MACROHON | 1 | 1 | 12 | REPAIR/ REHABILITATION | 5504070.6474 | 1 | PHP 1,472,159.77 | Completed | 100% | 2023-08-22 |  | CY 2022 QRF BATCH 2 | ITB 2023-002 | 2023-03-03 | 2023-03-10 | 2023-03-22 | 2023-04-14 | 2023-04-19 | TRIPLE JO CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122189 | Macrohon Central School | MACROHON | 1 |  | 6 | REPAIR/ REHABILITATION | 9943819.5515 | 1 | 6, 210,000.00 | Completed | 100% | 2023-12-01 |  | ITB-2023-02-018 | QRF202304018 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRIBATA Construction | With time extension. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 305533 | Malitbog National High School | MALITBOG | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4430312.8767 | 1 | 6741884.8 | Completed | 100% | 2023-12-01 |  | ITB-2023-02-025 | QRF202304021 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp. | For Post Qualification of Winning Bidders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122030 | Hinunangan East Central School | HINUNANGAN | 2 | 1 | 1 | REPAIR/ REHABILITATION | 588537.43 | 1 | 14860634.65 | completed | 100% | 2023-11-01 |  | ITB-2023-02-019 | QRF202304019 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | Micro Asia Builders Corporation | For Post Qualification of Winning Bidders | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region VIII | Southern Leyte | 122031 | Hinunangan West Central School | HINUNANGAN | 2 | 1 | 1 | REPAIR/ REHABILITATION | 628174.33 | 1 | 10996219.44 | Completed | 100% | 2023-12-31 | December 18, 2023 | ITB-2023-02-026 | QRF202304022 | February 23, 2023 | March 3, 2023 | March 15, 2023 | April 5, 2023 | April 20, 2023 | PAR Builders, Elecrical and Construction Supply Corp. | With time extension. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 3.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122031 | Hinunangan West Central School | HINUNANGAN | 2 |  | 4 | NEW CONSTRUCTION | 9930079.05 | 1 | 37483431.65 | Completed | 100% | 2024-01-10 |  | ITB-2023-02-020 | QRF202304020 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRINITYCAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2 | 1 | 12 | REPAIR/ REHABILITATION | 2527676.6584 | 1 | 16952019.97 | Completed | 100% | December 4, 2023 |  | 2023-003-Infra | CY2022-QRF-Repair-L13 | 2023-03-10 |  | 2023-03-31 | 2023-04-05 | 2023-04-20 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2 |  | 4 | NEW CONSTRUCTION | 9877536.42 | 1 | 2493388.2 | Completed | 100% | 2023-07-04 | 2023-05-25 | 2023-001-Infra | CY2022-QRF-Repair-L13 | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 | 1 | 16 | REPAIR/ REHABILITATION | 6740151.561 | 1 | 6664922.47 | Completed | 100% | 2023-07-04 | 2023-05-25 | 2023-002-Infra | CY2022-QRF-Repair-L15 | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122302 | Saint Bernard Central School | SAINT BERNARD | 2 | 1 | 35 | REPAIR/ REHABILITATION | 17360731.01 | 1 | 17187696.03 | Completed | 100% |  |  | CY2022-QRF-Repair-L8 | CY2022-QRF-Repair-L8 | 2022-04-27 | [6 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1115785.6755 | 1 | 1099486.78 | Completed | 100% |  |  | CY2022-QRF-Repair-L13 | CY2022-QRF-Repair-L13 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | VHITS D.G. BUILDERS AND ENTERPRISES | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 |  | 4 | NEW CONSTRUCTION | 9979524.06 | 1 | 9071932.33 | Completed | 100% |  |  | CY2022-QRF-NewCon-L21 | CY2022-QRF-NewCon-L21 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | BLACK NAZARENE BUILDERS AND ENTERPRISES | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 2 | 1 | 22 | REPAIR/ REHABILITATION | 11898857.161 | 1 | 11817766.38 | Completed | 100% |  |  | CY2022-QRF-Repair-L14 | CY2022-QRF-Repair-L14 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | MIGHTY A's CONSTRUCTION AND HARDWARE SUPPLY | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122059 | Silago Central School | SILAGO | 2 | 1 | 4 | REPAIR/ REHABILITATION | 1633987.3352 | 1 | 1630175.36 | Completed | 100% |  |  | CY2022-QRF-Repair-L7 | CY2022-QRF-Repair-L7 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | JUNCYNTH CONSTRUCTION & GENERAL SERVICES | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122263 | Hindangan PS | SOGOD | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1327870.84 | 1 | 1312776.25 | Completed | 100% |  |  | CY2022-QRF-Repair-L9 | CY2022-QRF-Repair-L9 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region VIII | Southern Leyte | 122280 | Sogod Central School | SOGOD | 2 | 1 | 35 | REPAIR/ REHABILITATION | 18323076.66 | 1 | 12448789.14 | Completed | 100% |  |  | CY2022-QRF-Repair-L11 | CY2022-QRF-Repair-L11 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Awarded / Perfection of Contract | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 35 | 100% | 0% | 2023-04-01 | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | 0 |  | 10 | NEW CONSTRUCTION | 19869482.89 | 1 | 19866688.44 | completed | 100% | 2023-08-30 | 2023-08-18 | QRF 2022 - R X - Camiguin - 004 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | 0 | 1 | 1 | REPAIR/ REHABILITATION | 150000 | 1 | 149472.02 | completed | 100% | 2023-08-30 | 2023-08-18 | QRF 2022 - R X - Camiguin - 043 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region X | Camiguin | 126928 | BUTAY ES | GUINSILIBAN | 0 | 1 | 2 | REPAIR/ REHABILITATION | 300000 | 1 | 296463.41 | Completed | 100% | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 033 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region X | Camiguin | 126931 | Guinsiliban CS | GUINSILIBAN | 0 | 1 | 2 | REPAIR/ REHABILITATION | 800000 | 1 | 798629.57 | completed | 100% | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 031 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | 0 | 1 | 6 | NEW CONSTRUCTION | 12667615.79 | 1 | 12662340.68 | completed | 100% | 2023-06-01 | 2023-08-05 | QRF 2022 - R X - Camiguin - 005 | QRF 2022 - R X - Camiguin - LOT 3 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 |  | 11 | NEW CONSTRUCTION | 22536171.13 | 1 | 22525933.1 | completed | 100% | 2023-09-29 | 2023-10-27 | QRF 2022 - R X - Camiguin - 003 | QRF 2022 - R X - Camiguin - LOT 1 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 | 1 | 4 | REPAIR/ REHABILITATION | 650981.29 | 1 | 644855.12 | completed | 100% | 2023-09-29 | 2023-10-27 | QRF 2022 - R X - Camiguin - 021 | QRF 2022 - R X - Camiguin - LOT 1 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% | 2023-04-01 | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 | 1 | 3 | REPAIR/ REHABILITATION | 1866506.75 | 1 | 1860652.7 | completed | 100% | 2023-09-29 |  | QRF 2022 - R X - Camiguin - 015 | QRF 2022 - R X - Camiguin - LOT 4 | 2022-07-04 | 2022-07-13 | 2021-06-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 1.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | 0 |  | 12 | NEW CONSTRUCTION | 24369730.96 | 1 | 24363319.78 | completed | 100% | 2023-09-29 |  | QRF 2022 - R X - Camiguin - 002 | QRF 2022 - R X - Camiguin - LOT 4 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | MINKONSTRAK ENG'G. & GEN. SRVCS. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2 | 1 | 2 | NEW CONSTRUCTION | 5858817.72 | 1 | 4624522.96 | Completed | 100% | 2023-07-16 | 2023-06-26 | 2022-04-0066 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | Tri FB Construction & Gen Mdse |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 10.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1301701.99 | 1 | 1105506.66 | completed | 100% | 2023-03-18 | 2023-04-25 | 2022-04-0067 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 2.23 |  |  |  |  | REPAIR | completed
QRF 2022 | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2 |  | 2 | NEW CONSTRUCTION | 6509328.44 | 1 | 5313487.54 | completed | 100% | 2023-07-16 | 2023-02-03 | 2022-04-0069 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 4.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2 | 1 | 2 | NEW CONSTRUCTION | 6836370.06 | 1 | 6270286.1 | Completed | 100% | 2023-03-18 | 2023-06-26 | 2022-04-0068 |  | 2022-04-29 | 2022-05-11 | 2022-05-23 | 2022-09-25 | 2023-09-29 | AbrahamBM Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% | 2023-04-01 | 9.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 | Region X | Gingoog City | 501023 | Civoleg Integrated School - Elem | GINGOOG CITY | 1 | 1 | 3 | REPAIR/ REHABILITATION | 1500000 | 1 |  | Completed | 100% | 2022-12-29 |  | QRF 2022 - R X - Camiguin - 004 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% | 2023-04-01 | 10.23 |  |  |  |  | REPAIR | Completed
QRF 2022 | Region X | Gingoog City | 128065 | Dona J. Pelaez Reyes CS | GINGOOG CITY | 1 | 1 | 1 | REPAIR/ REHABILITATION | 1000000 | 1 |  | Completed | 100% | 2022-12-29 |  | QRF 2022 - R X - Camiguin - 043 | QRF 2022 - R X - Camiguin - LOT 2 | 2022-07-04 | 2022-07-13 | 2022-07-25 | 2022-08-08 | 2022-09-19 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% | 2023-03-01 | previous yrs |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Abra | 134968 | Bangued East Central School | BANGUED (Capital) | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 3628003.8798 | 1 | 3612581.38 | Completed | 100% | 7/14/2023 | 7/14/2023 | CAR-ABRA-2023-02-016 | 2023-03-002 | 2/28/2023 | March 06, 2023 | March 20, 2023 | March 27, 2023 | April 6, 2023 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 1260341.25 | 1 | 1254235.11 | Completed | 100% | 7/14/2023 | 7/14/2023 | CAR-ABRA-2023-02-016 | 2023-02-002 | 2/28/2023 | March 06, 2023 | March 20, 2023 | March 27, 2023 | April 6, 2023 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | 6 | Replacement | 21534025.5 | 1 | 21511202.25 | completed | 100% | 2023-07-11 | 2023-07-11 | CAR-ABRA-2023-02-016 | 2023-03-002 | May 4, 2023 | May 11, 2023 | May 23, 2023 | June 6, 2023 | June 20, 2023 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 10178009.05 | 1 | 10159608.51 | Completed | 100% | 2023-10-11 | 2023-12-08 | CAR-ABRA-2023-02-016 | 2023-02-002 | 2/28/2023 | March 06, 2023 | March 20, 2023 | March 27, 2023 | April 6, 2023 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | 4 | Replacement | 33343514.75 | 1 | 33326978.31 | Completed | 100% | 1/16/2024 | 2024-11-08 | CAR-ABRA-2023-02-016 | 2023-02-002 | 2/28/2023 | March 06, 2023 | March 20, 2023 | March 27, 2023 | April 6, 2023 | AD MARRERO CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | CAR | Abra | 135024 | Tayum Central School | TAYUM | Lone | 1 | 19 | REPAIR OF CLASSROOMS | 4659065.19 | 1 | 4644134.26 | Completed | 100% | 2023-12-08 | 2023-12-08 | CAR-ABRA-2023-02-016 | 2023-02-002 | 2/28/2023 | March 06, 2023 | March 20, 2023 | March 27, 2023 | April 6, 2023 | SEMBRI CONSTRUCTION | N/A | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Apayao | 305123 | Pudtol Vocational High School | PUDTOL | Lone | 1 | 0 | REPAIR OF CLASSROOMS | 4805407.18 | 1 | 4801706.48 | Completed | 100% | 2023-07-11 | 11/23/2023 | QRF-2022-001 | None | 5/15/2023 | 5/22/2023 | 2023-05-06 | 6/19/2023 | 6/30/2023 | Aquila Construction Co. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Baguio City | 136388 | Elpidio R. Quirino Elementary School | BAGUIO CITY | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 999883.15 | 1 | 846915.49 | completed | 100% | 2023-05-11 | [7 empty] | 2023-07-08 | EZRAH Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1960625.84 | 1 | 821468.67 | completed | 100% | 2024-04-01 | [7 empty] | 2023-07-08 | JEKISU Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CAR | Baguio City | 305277 | Roxas National High School | BAGUIO CITY | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 976825.81 | 1 | 1548386.54 | completed | 100% | 2023-05-12 | [7 empty] | 2023-07-08 | EZRAH Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 |  | 1 | 2 | 976825.81 | REPAIR | completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 305138 | Loo National High School | BUGUIAS | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 5200000 | 1 | 4668156.03 | Completed | 100% | 2/13/2024 | 2/13/2024 | QRF-2022-01 | QRF-2022-01 | 6/13/2023 | 6/20/2023 | 2023-11-04 | 6/13/2023 | 7/18/2023 | MBW Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 135524 | Itogon Central School | ITOGON | Lone | 1 | 0 | REPAIR OF CLASSROOMS | 2500000 | 1 | 2247286.99 | Completed | 100% | 2023-08-12 | 2024-04-02 | QRF-2022-02 | QRF-2022-02 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-08-06 | 2023-11-07 | JB BANGIT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 135617 | Balili ES | LA TRINIDAD (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 1 | 1874733.11 | Completed | 100% | 2023-07-12 | 1/19/2024 | QRF-2022-03 | QRF-2022-03 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-08-06 | 2023-10-07 | PRECIOUS GOLD CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 135624 | La Trinidad CS | LA TRINIDAD (Capital) | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 9750000 | 1 | 8703674.46 | Completed | 100% | 2024-06-03 | 5/16/2024 | QRF-2022-04 | QRF-2022-04 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-08-06 | 2023-10-07 | HAIGHT'S CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 135631 | Puguis Elementary School | LA TRINIDAD (Capital) | Lone | 1 | 5 | Replacement | 12500000 | 1 | 10394095.06 | COMPLETED | 100% | 06/14/2024 | December 09, 2024 | QRF-2022-08 | QRF-2022-08 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-09-06 | 2023-10-07 | ZYMX CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 11.24 |  |  |  |  | REPLACEMENT | COMPLETED
QRF 2022 REPLENISHMENT | CAR | Benguet | 305151 | Lepanto NHS | MANKAYAN | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 1 | 3783533.19 | COMPLETED | 100% | 2024-09-01 | 5/15/2024 | QRF-2022-06 | QRF-2022-06 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-09-06 | 7/13/2023 | GEGA ENGINEERING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | CAR | Benguet | 135658 | Mankayan Central School | MANKAYAN | Lone | 1 | 18 | REPAIR OF CLASSROOMS | 11700000 | 1 | 9434950.12 | Completed | 100% | 4/23/2024 | December 12, 2024 | QRF-2022-05 | QRF-2022-05 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-09-06 | 7/18/2023 | CAIXIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Benguet | 135716 | Tuba Central School | TUBA | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 7150000 | 1 | 6344950.94 | completed | 100% | 2024-06-03 | 5/30/2024 | QRF-2022-07 | QRF-2022-07 | 2023-10-03 | 6/20/2023 | 2023-11-04 | 2023-08-06 | 2023-10-07 | HAIGHT'S CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 4 | Replacement | 4998077.29 | 1 | 4557623.77 | Completed | 100% | January 20, 2024 | November 22, 2023 | QRF 2022 - CAR - Kalinga - 001 | QRF 2022 - CAR - Kalinga - 001 | March 8, 20923 | April 24, 2023 | May 9, 2023 | July 4, 2023 | July 17, 2023 | Bangyan 3D Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136186 | Kadaclan Elementary School | BARLIG | Lone | 1 | 8 | Replacement | 47763623.8471 | 1 | 43528472.23 | Completed | 100% | 2024-05-02 | March 20, 2025 | Lot 7 QRF 2022 | INF-2023 R-006 | 2/25/2023 | 2023-03-03 | 3/21/2023 | 2023-04-11 | 2023-04-05 | HGW=3 Eng'g & Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 3.25 |  | 1 | 8 | 47763623.8471 | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136235 | Besao Central School | Besao | Lone | 1 | 1 | REPAIR OF CLASSROOM | 3979616.1247 | 1 | 3946200.79 | Completed | 100% | 2023-11-07 | August 10, 2023 | Lot 2 QRF 2022 | INF-2023 R-001 | 2/25/2023 | 2023-03-03 | 3/20/2023 | 2023-04-11 | 2023-05-05 | Archie Prince Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 305255 | Mountain Province General Comprehensive High School | BONTOC (Capital) | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 14697323.2501 | 1 | 13966159.08 | Completed | 100% | 2023-08-11 | November 7, 2023 | Lot 4 QRF 2022 | INF-2023 R-003 | 2/25/2023 | 2023-03-03 | 3/20/2023 | 2023-04-11 | 2023-05-05 | WWW.Const'n |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136310 | Paracelis Central School | PARACELIS | Lone | 1 | 4 | Replacement | 13264675.6061 | 1 | 13219562.44 | completed | 100% | 2023-06-11 | March 5, 2024 | Lot 6 QRF 2022 | INF-2023 R-005 | 2/25/2023 | 2023-03-03 | 3/21/2023 | 2023-04-11 | 2023-03-05 | MBW Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.24 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone | 1 | 8 | Replacement | 51127254.3521 | 1 | 50586443.91 | Completed | 100% | 10/26/2024 | December 10, 2024 | Lot 1 QRF 2022 | INF-2023-R-008 | 4/14/2023 | 03/03/2023, 04/24/2023 | 3-20-23 / 5-10-23/july 17, 2023 | September 11, 2023 | 9/25/2023 | GACOSCOS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 3.25 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136351 | Sagada Central School | Sagada | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 9078760.939 | 1 | 9042909.29 | Completed | 100% | 2023-09-10 | 2023-09-10 | Lot 5 QRF 2022 | INF-2023 R-004 | 2/25/2023 | 2023-03-03 | 3/21/2023 | 2023-04-11 | 2023-05-05 | FELA Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | Lone | 1 | 2 | Replacement | 6466962.0915 | 1 | 6435000 | Completed | 100% | 2023-09-09 | 2024-07-01 | Lot 3 QRF 2022 | INF-2023 R-002 | 2/25/2023 | 2023-03-03 | 3/20/2023 | 2023-04-11 | 2023-05-05 | JM-MAS Const'n & Gen. Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 2 | Replacement | 6233080.18 | 1 | 1802041.69 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 8.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 11 | REPAIR OF CLASSROOMS | 8638383.7717 | 1 | 2306105.05 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 6 | Replacement | 16825000 | 1 | 2227143.05 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 11 | REPAIR OF CLASSROOMS | 11185525 | 1 | 1287844.35 | Completed | 100% | April 18, 2025 | March 22, 2025 | CAR-ABRA-2024-08-016 | 2024-11-018 | 10/14/2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 6 | Replacement | 21971961.6669 | 1 | 879235.36 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 41 | REPAIR OF CLASSROOMS | 18420393.95 | 1 | 3059124.25 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 41 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 2 | Replacement | 6493614.88 | 1 | 1256400.58 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 7449645.76 | 1 | 8319974.87 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | 5 | Replacement | 15070000 | 1 | 855677.77 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | 14 | REPAIR OF CLASSROOMS | 4290000 | 1 | 1813060.85 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 6 | Replacement | 16910000 | 1 | 2724676.54 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 10 | REPAIR OF CLASSROOMS | 6355506.77 | 1 | 2458919.98 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132289 | B. Vasquez Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 4 | Replacement | 9464507.64 | 1 | 1737339.99 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132289 | B. Vasquez Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3871843.67 | 1 | 936445.49 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132298 | Margarita Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 8 | Replacement | 19298722.35 | 1 | 1227828.31 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132298 | Margarita Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2955303.79 | 1 | 2174074.63 | Completed | 100% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132254 | Mariano Espina Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 11 | REPAIR OF CLASSROOMS | 9832305.46 | 1 | 2198427.76 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao City | 132266 | Martinez ES | SURIGAO CITY (Capital) | 2nd | 1 | 2 | Replacement | 6092191.78 | 1 | 1451067.22 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2nd | 1 | 4 | Replacement | 10043464.8 | 1 | 2047773.77 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2nd | 1 | 2 | Replacement | 6914571.58 | 1 | 2201897.52 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2nd | 1 | 2 | Replacement | 6935571.58 | 1 | 1674306.34 | Completed | 100% | March 4, 2025 | March 04, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2nd | 1 | 3 | Replacement | 8275250.96 | 1 | 3804323.62 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 101166 | Alaminos Central School | CITY OF ALAMINOS | 1st | 1 | 17 | REPAIR OF CLASSROOMS | 28000000 | 1 | Php27,723,177.18 | completed | 100% | 12/30/2023 | 12/19/2023 | 2023-03-001 | SPF-QRF2023-04-001 | March 14,2023-April 3, 2023 | 3/22/2023 | 2023-04-04 | 4/17/2023 | 4/25/2023 | Manimeld's construction and Iron Works | with additive VO- 276,822.82, revised contract amount 28,000,000, revised Completion date DEcember 30, 2023. Revised contract amount 28,000,000.00 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300155 | Alaminos City National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 54000000 | 1 | 27852257.7 | Completed | 100% | 5/17/2024 |  | 2023-07-12 | 2023-08-29 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Aylan Construction & Trading | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 99.4% | 0.6% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Alaminos City | 300260 | Telbang National High School | CITY OF ALAMINOS | 1st | 1 | 12 | Replacement | 49200000 | 1 | 37566348.03 | Completed | 100% | 3/25/2024 |  | 2023-07-12 | 2023-08-28 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/29/2023 | T.G. Ocampo Construction and Surveying Services | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 98.74% | 1.26% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 3272296.8 | 1 | 2727538.84 | Completed | 100% | 12/19/2023 | 12/17/2023 | 23043 | 23014.2 | 4/18/2023 | 4/26/2023 | 2023-08-06 | 6/19/2023 | 6/19/2023 | Elocin Construction | Savings (Php 544,757.96) was utilized to fund the project Repair and Rehabilitation of 5 Classrooms of the same school | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 40 | Replacement | 140000000 | 1 | 50451627.8 | Completed | 100% | 5/17/2024 |  | 2023-07-12 | 2023-08-31 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | ASS Construction/ MA Tejada Construction (Joint Venture) | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 95.02% | 4.98% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 1188260.78 | 1 | 50525408.86 | Completed | 100% | 5/17/2024 |  | 2023-07-12 | 2023-08-31 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | ASS Construction/ MA Tejada Construction (Joint Venture) | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2nd | 1 | 4 | Replacement | 12000000 | 1 | 1178082.17 | Ongoing | 85.38% | 2023-05-08 | 2023-05-08 | PB-INFRA-01-2023 | N/A | 3/26/2023 | 4/18/2023 | 4/18/2023 | 2023-04-05 | 2023-08-05 | M.A. Tejada Construction |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 85.38% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 8 | REPAIR OF CLASSROOMS | 4000000 | 1 | 3990008.65 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | VIKING III BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4th | 1 | 20 | REPAIR OF CLASSROOMS | 6000000 | 1 | 5908391.57 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ZOTA TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | 24 | REPAIR OF CLASSROOMS | 6000000 | 1 | 4913922.28 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELMUEL JAY TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4th | 1 | 18 | REPAIR OF CLASSROOMS | 7000000 | 1 | 6943753.13 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | A.S.S. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 102170 | North Central Elementary School | DAGUPAN CITY | 4th | 1 | 3 | REPAIR OF CLASSROOMS | 2100000 | 1 | 2086111.66 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELMUEL JAY TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4th | 1 | 5 | REPAIR OF CLASSROOMS | 3000000 | 1 | 2971417.4 | completed | 100% | 12/13/2023 | 12/13/2023 | n/a | n/a | 2023-11-08 | 8/25/2023 | 2023-07-09 | 2023-12-09 | 9/15/2023 | ELGRAM TRADING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | 3 | Replacement | 9000000 | 1 | 7586101.37 | Completed | 100% | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/16/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 3 | Replacement | 9000000 | 1 | 7586101.37 | completed | 100% | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 | 8990670.28 | Completed | 100% | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-33 | 2023-06-07 | 7/16/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 4 | Replacement | 12000000 | 1 | 8990670.28 | completed | 100% | 5/17/2024 | 10/21/2024 | 2023-07-12 | 2023-08-33 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st |  | 10 | Replacement | 30000000 | 1 | 24413054.65 | Ongoing | 80% | 5/17/2024 |  | 2023-07-12 | 2023-08-34 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 2023-01-09 | Elocin Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 80% | 0% | [6 empty] | REPLACEMENT | ongoing
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 2764628.2477 | 1 | 2262662.78 | Completed | 100% | 10/25/2023 | 12/27/2023 | PB-03-2023-1 | PB-03-2023-1 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100152 | Marcos Central School | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1842214.5794 | 1 | 1668320.78 | Completed | 100% | 7/26/2023 | 2023-05-08 | PB-03-2023-2 | PB-03-2023-2 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3858132.46 | 1 | 3011166.41 | Completed | 100% | 11/22/2023 | 12/27/2023 | PB-03-2023-4 | PB-03-2023-4 | 2023-07-03 | 3/13/2023 | 3/27/2023 | 3/30/2023 | 4/27/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2433485.53 | 1 | 1859917.48 | Completed | 100% | 2023-01-12 | 12/27/2023 | PB-03A-2023-3 | PB-03A-2023-3 | 4/13/2023 | 4/19/2023 | 2023-02-05 | 2023-08-05 | 5/29/2023 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 100501 | Magsingal North Central School | MAGSINGAL | 1st | 1 | 12 | Replacement | 31559226.85 | 1 | 31529226.85 | Ongoing | 75% | 9/28/2024 |  | 2023-07-12 | 2023-08-35 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 75% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 1410280.53 | 1 | 1409123.18 | Completed | 100% | 8/19/2023 | 8/18/2023 | 2023-04002-PB-Works | n/a | 4/24/2023 | 2023-02-05 | 5/23/2023 | 5/31/2023 | 6/21/2023 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 1880259.3 | 1 | 1454728.12 | Completed | 100% | 8/19/2023 | 8/18/2023 | 2023-04002-PB-Works | n/a | 4/24/2023 | 2023-02-05 | 5/23/2023 | 5/31/2023 | 6/21/2023 | M.A. Tejada Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300095 | Bacnotan National High School | BACNOTAN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1690747.91 | 1 | 1688435.11 | Completed | 100% | 7/18/2023 | 2023-12-07 | QRF2022-RO1-LU-01 | 2022 - LU - 04 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3295309.0192 | 1 | 2570259.41 | Completed | 100% | 2023-06-08 | 2023-02-08 | QRF2022-RO1-LU-06 | 2022 - LU - 06 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | DPV BUILDERS AND CONSTRUCTION SUPPLY | COMPLETED INCLUDING SSAVINGS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 300114 | Dona Francisca Lacsamana de Ortega Memorial National High School | BANGAR | 1st |  | 12 | REPAIR OF CLASSROOMS | 6453979 | 1 | 4975440.38 | Completed | 100% | 2023-05-09 | 2023-01-09 | QRF2022-RO1-LU-07 | 2022-LU-07 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | DPV BUILDERS AND CONSTRUCTION SUPPLY | COMPLETED INCLUDING SSAVINGS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 100860 | Bagulin CES | BAGULIN | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1319380.58 | 1 | 1296139.72 | Completed | 100% | 7/17/2023 | 2023-12-07 | QRF2022-RO1-LU-05 | 2022-LU-05 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND SUPPLIES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 101001 | Pugo Central School | PUGO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3610020.2541 | 1 | 3599857.82 | Completed | 100% | 2023-06-08 | 2023-02-08 | QRF2022-RO1-LU-08 | 2022-LU-08 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | EE MADAYAG CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | La Union | 101096 | Damortis ES | SANTO TOMAS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 3245119.9514 | 1 | 3204773.82 | Completed | 100% | 2023-06-08 | 2023-02-06 | QRF2022-RO1-LU-09 | 2022-LU-09 | 3/14/2023 | 3/21/2023 | 2023-04-04 | 4/17/2023 | 4/27/2023 | EE MADAYAG CONSTRUCTION | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1965217.36 | 1 | 1965207.26 | Completed | 100% | June 01,2023 | August 18,2023 |  |  |  |  | 2/28/2023 | 3/15/2023 | 3/31/2023 | Elocin Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101132 | AGNO CENTRAL SCHOOL | AGNO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 927125.7 | 1 | 921100 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 8 | Replacement | 21412474.28 | 1 | 23887556.05 | Ongoing | 99.4% | 3/27/2024 |  | 2023-07-12 | 2023-08-37 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | MCB Construction & Supply | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 99.4% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2781377.1 | 1 | 2769811.29 | Completed | 100% | 10/26/2023 | 2023-11-10 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Angelina T. Dizon Construction And Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1847200 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | CLP Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 500618 | Pangascasan IS | SUAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1370306.45 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Chestinan Construction Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 8 | Replacement | 24934327.79 | 1 | 21465233.64 | completed | 100% | 2/26/2024 | 11/20/2024 | 2023-07-12 | 2023-08-36 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1854251.4 | 1 | 1824572.29 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Aldana Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 12 | Replacement | 32948933.15 | 1 | 29766091.35 | Ongoing | 60% | 9/16/2024 |  | 2023-07-12 | 2023-12-84 | 2023-06-07 | 7/13/2023 | 11/13/2023 | 12/19/2023 | 12/22/2023 | MCB Construction & Supply | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 49.36% | 10.64% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6943245.24 | Completed | 100% | 2023-08-11 | 10/18/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 2023-10-07 | 2023-12-07 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5525014.04 | Completed | 100% | 11/22/2023 | 11/21/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 7/24/2023 | 7/26/2023 | WM Salayog constructiona nd SUpply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 16 | Replacement | 40963538.51 | 1 | 34088332.04 | Ongoing | 60% | 9/16/2024 |  | 2023-07-12 | 2023-12-84 | 2023-06-07 | 7/13/2023 | 11/13/2023 | 12/19/2023 | 12/22/2023 | MCB Construction & Supply | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 50.77% | 9.23% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9210922.62 | Completed | 100% | 10/26/2023 | 10/24/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | ABC East Multi Builders And Traders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 5562754.2 | 1 | 5530867.38 | Completed | 100% | 10/26/2023 | 10/24/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Manimeld'S Construction And Iron Works |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6933376.41 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Elmuel Jay Trading And Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive NHS | CALASIAO | 3rd | 1 | 20 | REPAIR OF CLASSROOMS | 9271257 | 1 | 9231257 | Completed | 100% | 10/26/2023 | 10/26/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Jeusmack Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3rd | 1 | 15 | REPAIR OF CLASSROOMS | 6953442.75 | 1 | 6913442.43 | Completed | 100% | 10/26/2023 | 10/26/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Jeusmack Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 101546 | Malasiqui I CS | MALASIQUI | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 1390688.55 | 1 | 1384628.86 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Q&M Construction And Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui NHS | MALASIQUI | 3rd | 1 | 14 | REPAIR OF CLASSROOMS | 6489879.9 | 1 | 6461994.34 | Completed | 100% | 10/26/2023 | 10/25/2023 | 2023-05-12-INFRA | n/a | 2023-11-05 | 5/19/2023 | 5/31/2023 | 6/26/2023 | 6/29/2023 | Elgram Trading And Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 973850.07 | 1 | 917888.95 | completed | 100% | 2023-03-06 | 6/15/2023 | - | 2023-005 | 3/14/2023 | 3/22/2023 | APRIL 4,2023 | 4/14/2023 | 4/26/2023 | RGP SUCCESS VENTURES INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9983672.11 | Ongoing | 90% | 5/17/2024 |  | 2023-07-12 | 2023-08-38 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 90% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 9 | Replacement | 22500000 | 1 | 22440043.66 | Ongoing | 82% | 5/17/2024 |  | 2023-07-12 | 2023-08-39 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 80% | 2% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29857906 | Ongoing | 90% | 5/17/2024 |  | 2023-07-12 | 2023-08-39 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 87% | 3% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932498 | Ongoing | 82% | 5/17/2024 |  | 2023-07-12 | 2023-08-38 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | HG Lopez Construction | With Time Suspension/Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 80% | 2% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | REPAIR OF CLASSROOMS | 1060966.05 | 1 | 1059997.66 | completed | 100% | 8/31/2023 | 8/31/2023 | INFRA-002-2023 | INFRA-002-2023 | 3/23/2023 | 3/30/2023 | 2023-12-04 | 4/20/2023 | 4/28/2023 | JD MADRID CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 4 | Replacement | 10000000 | 1 | 9950511.25 | Ongoing | 95% | 5/17/2024 |  | 2023-07-12 | 2023-08-40 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimelds Construction and Iron Works | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 95% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 1048973.66 | 1 | 1048967.97 | completed | 100% | 8/31/2023 | 8/31/2023 | INFRA-002-2023 | INFRA-002-2023 | 3/23/2023 | 3/30/2023 | 2023-12-04 | 4/20/2023 | 4/28/2023 | JD MADRID CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 12 | Replacement | 30000000 | 1 | 29932840.74 | Ongoing | 90% | 5/17/2024 |  | 2023-07-12 | 2023-08-40 | 2023-06-07 | 7/16/2023 | 7/26/2023 | 8/18/2023 | 8/31/2023 | Manimelds Construction and Iron Works | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 90% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102269 | Badipa Elementary School | CITY OF URDANETA | 5th | 1 | 9 | REPAIR OF CLASSROOMS | 2016858.14 | 1 | 2011483.38 | completed | 100% | 8/30/2023 | 8/24/2023 | QRF REPAIR 2022-R1-URDANETA CITY-001 | 202303015 | 2023-08-03 | 4/20/2023 | 2023-03-05 | 2023-11-05 | 5/30/2023 | ELMUELJAY TARDING AND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region I | Urdaneta City | 102294 | Don Amadeo Perez, Sr. Memorial Elementary Central School - East | CITY OF URDANETA | 5th | 1 | 4 | Replacement | 15313741.51 | 1 | 15263741.51 | completed | 100% | 2/26/2024 | 2024-12-08 | 2023-07-12 | 2023-08-36 | 2023-06-07 | 7/13/2023 | 7/25/2023 | 8/18/2023 | 8/31/2023 | Manimeld’s Construction and Iron Works | With Time Suspension/Extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region I | Vigan City | 300052 | Ilocos Sur National High School | CITY OF VIGAN (Capital) | 1st | 1 |  | Replacement | 125000000 | 1 | 41140168.88 | Ongoing | 99% | 5/17/2024 |  | 2023-07-12 | 2023-08-41 | 2023-06-07 | 7/13/2023 | 7/26/2023 | 8/18/2023 | 2023-01-09 | ASS Construction | With Time Suspension/Extension; For final inspection, submition of occupancy permit and fire safety clearance | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 99.4% | -0.4% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region II | City of Ilagan | 306105 | Isabela School of Arts and Trades-Main | CITY OF ILAGAN | 1st | 1 | 0 | REPAIR OF CLASSROOMS | 2097038.4 | 1 | 1672031.73 | Completed | 100% | 2023-05-09 |  |  |  | 2/16/2023 | 2/24/2023 | 2023-08-03 | 3/24/2023 | 2023-02-05 | ARKHITEKTON BUILDERS AND CONSTRUCTION SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region II | Isabela | 103854 | Sta. Maria Central School | Sta Maria | 1st | 1 | 6 | Replacement | 9000000 | 1 | 6497594.9 | Completed | 100% |  | 11/15/2023 | Project No. 2023-03-01 | Contract ID NO 2023-04-01 |  |  | 2023-04-04 | 4/17/2023 | 2023-03-05 | FRAGERR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region II | Isabela | 103571 | Quezon Central School | Quezon | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 300000 | 1 | 2811053.13 | Completed | 100% |  | 2023-05-12 | Project No. 2023-08-05 | Contract ID NO 2023-09-01 |  |  | 2023-07-09 | 10/18/2023 | 10/29/2023 | FRAGERR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region II | Isabela | 103311 | Echague South Central School | Echague | 4th | 1 | 1 | REPAIR OF CLASSROOMS | 75000 | 1 | 66351.98 | Completed | 100% |  | 2023-02-06 | Project No. 2023-03-01 | Contract ID NO 2023-04-01 |  |  | 2023-04-04 | 4/17/2023 | 2023-03-05 | FRAGERR CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 300622 | Belance HS | DUPAX DEL NORTE | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 5350000 | 1 | 4254236.78 | Completed | 100% | September 7, 2023 | October 22, 2024 | PB 05-001 s. 2023 | PB 05-001 s. 2023 | 3/13/2023 | 3/20/2023 | 2023-03-04 | 5/15/2023 | June 9, 2023 | ZYMX CONSTRUCTION | with savings contract amount: 1,095,763.22 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 104088 | Kasibu Central School | KASIBU | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 4940000 | 1 | 3794462.33 | Completed | 100% | July 9, 2023 | May 12, 2023 | PB 05-002 s. 2023 | PB 05-002 s. 2023 | 3/13/2023 | 3/20/2023 | 2023-03-04 | 5/15/2023 | May 5, 2023 | IA Castañeda Construction | with savings contract amount: 1,145, 537.67 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region II | Nueva Vizcaya | 300623 | Bintawan NHS | VILLAVERDE | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 6500000 | 1 | 5184581.51 | Completed | 100% | August 25, 2023 | January 13, 2024 | PB 05-003 s. 2023 | PB 05-003 s. 2023 | 3/13/2023 | 3/20/2023 | 2023-03-04 | 5/15/2023 | May 22, 2023 | Mighty Construction | with savings contract amount: 1,315,418.48 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 6892000 | 1 | 3963054.24 | COMPLETED | 100% | 10/28/2023 | 9/21/2023 |  |  | 2023-07-03 | 3/15/2023 | 3/27/2023 | 4/13/2023 | 4/24/2023 | AMC CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region III | Bulacan | 306712 | Sto. Nino High School | BALIUAG | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 466271.98 | 1 | ₱386,515.13 | Completed | 100% | 5/23/2023 | 5/17/2023 | PB-23-001 | 23-03-001 | 2/22/2023 | 2023-01-03 | 3/13/2023 | 3/16/2023 | 3/31/2023 | EMICA Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Bulacan | 158529 | Cucong Elementary School | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 3064193.79 | 1 | 2514973.27 | Completed | 100% | 9/29/2023 | 2023-09-08 | PB-23-008 | 23-008 | 4/20/2023 | 2023-02-05 | 5/15/2023 | 5/16/2023 | 5/25/2023 | GELROCK BUILDERS | realigned from felizardo lipana nhs (sta rita hs) and john russel mhs (sibul nhs) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 8.23 |  | 2 | 9 | 3064193.79 | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Bulacan | 300774 | John J. Russell MHS (Sibul NHS) | SAN MIGUEL | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 425508.5126 | 1 | ₱417,671.35 | Completed | 100% | 5/23/2023 | 5/22/2023 | PB-23-003 | 23-03-003 | 2/22/2023 | 2023-01-03 | 3/13/2023 | 3/16/2023 | 3/31/2023 | EMICA Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Bulacan | 105111 | San Miguel Elementary | SAN MIGUEL | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2301524.74 | 1 | ₱1,891,657.30 | COMPLETED | 100% | 2023-06-08 | 7/28/2023 | PB-23-002 | 23-03-002 | 2/22/2023 | 2023-01-03 | 3/13/2023 | 3/16/2023 | 3/31/2023 | EMICA Builders and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4th | 1 | 22 | REPAIR OF CLASSROOMS | 7950000 | 1 | 7941961.35 | Completed | 100% | 8/17/2023 | 8/17/2023 | INFRA-NE-Emergency-22-2023 |  | 2/28/2023 |  | 2023-08-03 | 3/13/2023 | 3/17/2023 | J.V. BUAN CONSTRUCTION *T |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105368 | Gen. Tinio West Central School | GENERAL TINIO (PAPAYA) | 4th | 1 | 3 | REPAIR OF CLASSROOMS | 1650000 | 1 | 1647978.72 | Completed | 100% | 8/17/2023 |  | INFRA-NE-Emergency-23-2023 |  | 2/28/2023 |  | 2023-08-03 | 3/13/2023 | 3/17/2023 | JOYUS CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4th | 1 | 7 | REPAIR OF CLASSROOMS | 3850000 | 1 | 3846350.56 | Completed | 100% | 8/17/2023 |  | INFRA-NE-Emergency-24-2023 |  | 2/28/2023 |  | 2023-08-03 | 3/13/2023 | 3/17/2023 | IJK MAE CONSTRUCTION INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300989 | San Pedro National High School | MONCADA | 1st | 1 | 12 | Replacement | 36000000 | 1 | 35898680.53 | Ongoing | 90% | 2024-01-07 |  |  | CSCB-CY2023-002 | 7/27/2023 | 2023-04-08 | 8/17/2023 |  |  | FROMARC BUILDERS & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 90% | 0% | [6 empty] | REPLACEMENT | ongoing
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300989 | San Pedro National High School | MONCADA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 1 | 35898680.53 | Completed | 100% | 2024-01-07 |  |  | CSCB-CY2023-002 | 7/27/2023 | 2023-04-08 | 8/17/2023 |  |  | FROMARC BUILDERS & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | 16 | Replacement | 48000000 | 1 | 478945595.27 | Ongoing | 25% | 2024-01-07 |  |  | CSCB-CY2023-003 | 7/27/2023 | 2023-04-08 | 8/17/2023 |  |  | IJK MAE CONSTRUCTION, INC. | Suspended | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 25% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2022 REPLENISHMENT | Region IV-A | Batangas | 107225 | Balayan East Central School | BALAYAN | 1st | 1 | 6 | Replacement | 22500000 | 1 | 20082720.48 | COMPLETED | 100% | 2024-01-07 | 2024-09-09 | QRF 2023-BATANGAS-IVA-01 | QRF 2023-BATANGAS-IVA-01 | 2023-07-08 | 8/15/2023 | 8/23/2023 | 9/29/2023 | 10/27/2023 | AB San Lorenzo Construction and Supply Company | Delayed due to contractor's fault | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.25 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 108561 | BURDEOS CENTRAL SCHOOL | BURDEOS | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 10337287.3043 | 1 | 10323137 | COMPLETED | 100% | 2023-11-07 | 8/14/2023 | N/A | QRF 2023-QUEZON-IVA-01 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | L.A. Profugo Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301334 | BURDEOS NHS (Formerly JUDITH NHS) | BURDEOS | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 2782893.1751 | 1 | 2778600 | COMPLETED | 100% | 2023-11-07 | 2023-05-07 | N/A | QRF 2023-QUEZON-IVA-02 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | C.G. Cabana Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301361 | PSHN | GEN. NAKAR | 1st | 1 | 18 | REPAIR OF CLASSROOMS | 11175657.489 | 1 | 11155714.06 | COMPLETED | 100% | 7/17/2023 | 2023-03-07 | N/A | QRF 2023-QUEZON-IVA-03 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 3/13/2023 | 3/14/2023 | M.G. Villamin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 109045 | POLILLO CENTRAL ES | POLILLO | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 9054870.0763 | 1 | 9041896 | COMPLETED | 100% | 2023-11-07 | 8/25/2023 | QRF 2023-QUEZON-IVA-04 | QRF 2023-QUEZON-IVA-04 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 2023-06-03 | 3/14/2023 | C.G. Cabana Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region IV-A | Quezon | 301377 | POLILLO NHS | POLILLO | 1st | 1 | 43 | REPAIR OF CLASSROOMS | 12907120.9512 | 1 | 12850000 | COMPLETED | 100% | 8/16/2023 | 9/16/2023 | QRF 2023-QUEZON-IVA-05 | QRF 2023-QUEZON-IVA-05 | 2023-03-02 | 2023-10-02 | 2/22/2023 | 3/13/2023 | 3/20/2023 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 43 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1358264.3352 | 1 | PHP 1,078,677.99 | Completed | 100% | 2023-06-02 | 2023-06-02 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | 2023-02-06 | 2023-02-13 | 2023-02-27 | 2023-03-08 | 2023-03-27 | AGM SILVER CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 6.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VI | Aklan | 114786 | Libacao Central ES | LIBACAO | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1505376.28 | 1 | PHP 1,248,136.99 | COMPLETED | 100% | 2023-06-02 | 2023-06-02 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | 2023-02-06 | 2023-02-13 | 2023-02-27 | 2023-03-08 | 2023-03-27 | AGM SILVER CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 6.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VI | Guimaras | 115858 | Suclaran Central School | SAN LORENZO | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 6521637.2579 | 1 | PHP 6,471,000.00 | COMPLETED | 100% | 2023-09-05 | 2023-09-01 | 01-2023 | 01-2023 | 2023-02-02 | 2023-02-27 | 2023-03-02 | 2023-03-15 | 2023-03-27 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VII | Bohol | 117968 | Antequera Central ES | ANTEQUERA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1412793.43 | 1 | 1087521.81 | completed | 100% | 2023-08-16 | 1.8.2024 | 0 | PBI2023 - 10 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.07.2023 | HUSAIN CONST | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118171 | Causwagan ES | CATIGBIAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 212611.3412 | 1 | 164005.65 | completed | 100% | 2023-10-05 | 1.9.2024 | 0 | PBI2023-02 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.07.2023 | HUSAIN CONST | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118027 | Bien Unido Central ES | BIEN UNIDO | 2nd | 1 | 1 | Replacement | 2500000 | 1 | 1780563.39 | completed | 100% | 2023-09-30 | 1.10.2024 | 0 | PBI2023-04 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.01.2023 | SAINT JOSEPH CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118027 | Bien Unido Central ES | BIEN UNIDO | 2nd | 1 | 30 | REPAIR OF CLASSROOMS | 8892337.27 | 1 | 6383121.24 | completed | 100% | 2023-09-29 | 10.2.2023 | 0 | PBI2023-03 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.01.2023 | SAINT JOSEPH CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2nd | 1 | 2 | Replacement | 5000000 | 1 | 3579908.5 | completed | 100% | 2023-11-28 | 1.10.2024 | 0 | PBI2023-07 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.1.2023 | SAINT JOSEPH CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.23 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2nd | 1 | 18 | REPAIR OF CLASSROOMS | 7385372.54 | 1 | 5101858.68 | completed | 100% | 2023-08-06 | 9.27.2023 | 0 | PBI2023-06 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.13.2023 | ANIELTHON CONSTRUCTION AND SUPPLY | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 500209 | Inabanga North Central Integrated School (Elementary) | INABANGA | 2nd | 1 | 13 | REPAIR OF CLASSROOMS | 3501389.7546 | 1 | 2521644.09 | completed | 100% | 2023-10-30 | 9.1.2023 | 0 | PBI2023-08 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.13.2023 | ANIELTHON CONSTRUCTION AND SUPPLY | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118641 | San Isidro Central ES | SAN ISIDRO | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 3191281.8119 | 1 | 2191353.51 | completed | 100% | 2023-10-29 | 2024-01-24 | 0 | PBI2023-09 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.7.2023 | HUSAIN CONST | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 117953 | Anda Central ES | ANDA | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 336249.7955 | 1 | 330167.22 | completed | 100% | 2023-11-10 | 7.21.2023 | 0 | PBI2023 - 10 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.2.2023 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118012 | Batuan Central ES | BATUAN | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 982408.6011 | 1 | 3678836.34 | completed | 100% | 2023-11-10 | 10.2.2023 | 0 | PBI2023 - 12 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.2.2023 | SOMBRIO CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118193 | Clarin Central ES | CLARIN | 3rd | 1 | 17 | REPAIR OF CLASSROOMS | 4446904.5091 | 1 | 3335072.39 | completed | 100% | 2023-10-30 | 9.1.2023 | 0 | PBI2023-05 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.02.2023 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118520 | Mabini Central ES | MABINI | 3rd | 1 | 7 | REPAIR OF CLASSROOMS | 2450000 | 1 | 2093459.53 | completed | 100% | 2023-10-29 | 7.21.2023 | 0 | PBI2023 - 10 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.2.2023 | C. JANSENN CONSTRUCTION AND GENERAL MERCHANDISE | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Bohol | 118581 | Pilar Central ES | PILAR | 3rd | 1 | 18 | REPAIR OF CLASSROOMS | 4933014.0625 | 1 | 3678836.34 | completed | 100% | 2023-10-05 | 10.2.2023 | 0 | PBI2023 - 11 | 2023-02-15 | 2023-02-23 | 2023-03-14 | 2023-04-04 | 6.1.2023 | SAINT JOSEPH CONSTRUCTION | completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119632 | SANGAT CES | SAN FERNANDO | 1st | 1 | 15 | REPAIR OF CLASSROOMS | 7500000 | 1 |  | REVERTED | 0% | [11 empty] | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0% | 0% | [6 empty] | REPAIR | REVERTED
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119722 | Sibonga Central ES | SIBONGA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2074340.3777 | 1 | 2073549.03 | COMPLETED | 100% | 2023-07-09 | 2023-07-09 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-01-06 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2nd | 1 | 15 | REPAIR OF CLASSROOMS | 12359157.52 | 1 | 12305913.39 | COMPLETED | 100% | 2023-06-12 | 2023-09-27 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-02 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-01-06 | ANIELTHON CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119298 | DALAGUETE CENTRAL ES | DALAGUETE | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 705637.3958 | 1 | 693338 | COMPLETED | 100% | 2023-07-09 | 2023-07-09 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-01-06 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 118900 | Aloguinsan Central ES | ALOGUINSAN | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 5745235.56 | 1 | 5707088.03 | COMPLETED | 100% | 2023-07-10 | 2023-07-10 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-03 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-01-06 | GELA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119572 | Tajao Central School | PINAMUNGAHAN | 3rd | 1 | 14 | REPAIR OF CLASSROOMS | 3599380.52 | 1 | 3560851.53 | COMPLETED | 100% | 2023-07-09 | 2023-06-09 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-04 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-01-06 | SB & T CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Cebu | 119566 | PINAMUNGAJAN CES | PINAMUNGAJAN | 3rd | 1 | 9 | REPAIR OF CLASSROOMS | 2706993.5847 | 1 | 2491050.24 | COMPLETED | 100% | 2023-11-09 | 2023-11-09 | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-05 | 22/02/2023 | 2023-01-03 | 13/03/2023 | 2023-03-04 | 2023-06-06 | HERO CONSTRUCTION AND DEVELOPMENT CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Guihulngan City | 120642 | Vallehermoso Central Elementary School | VALLEHERMOSO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1477590.79 | 1 | 1472159.77 | completed | 100% | 2023-08-22 |  | CY 2022 QRF BATCH 2 | ITB 2023-002 | 2023-03-03 | 2023-03-10 | 2023-03-22 | 2023-04-14 | 2023-04-19 | TRIPLE JO CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 2.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1st | 1 | 13 | REPAIR OF CLASSROOMS | 7088958.8048 | 1 | 6, 210,000.00 | completed | 100% | 2023-12-01 | 2024-01-15 | ITB-2023-02-018 | QRF202304018 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRIBATA Construction | with approved time extension; liquidated damages | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 3 | Replacement | 6803850.4069 | 1 | 6741884.8 | completed | 100% | 2023-11-01 | 2023-10-23 | ITB-2023-02-025 | QRF202304021 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp. | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region VII | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 14977836.0543 | 1 | 14860634.65 | completed | 100% | 2023-12-01 | 2023-11-08 | ITB-2023-02-019 | QRF202304019 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | Micro Asia Builders Corporation | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 10.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Negros Oriental | 120395 | Manjuyod CES | MANJUYOD | 1st | 1 | 5 | Replacement | 11766399.6233 | 1 | 10996219.44 | completed | 100% | 2023-12-31 | 2023-12-18 | ITB-2023-02-026 | QRF202304022 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp. | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 |  |  |  |  | REPLACEMENT | completed
QRF 2022 REPLENISHMENT | Region VII | Negros Oriental | 120395 | Manjuyod CES | MANJUYOD | 1st | 1 | 40 | REPAIR OF CLASSROOMS | 40783735.5341 | 1 | 37483431.65 | completed | 100% | 2024-04-09 | 2024-04-08 | ITB-2023-02-020 | QRF202304020 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRINITYCAD Corporation | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 100% | 0% |  | 1.24 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 4 | Replacement | 17000000 | 1 | 16952019.97 | COMPLETED | 100% | 2023-09-29 | February 10, 2024 | 2023-003-Infra | 2023-003-Infra | 2023-03-10 | 2023-03-20 | 2023-03-31 | 2023-04-05 | 2023-04-20 | DOLCI Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2.24 |  |  |  |  | REPLACEMENT | COMPLETED
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 3600000 | 1 | 3587090.67 | completed | 100% | 2023-07-04 | 2023-05-25 | 2023-001-Infra | 2023-001-Infra | 2023-02-24 | 2023-03-06 | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 7.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Tagbilaran City | 233001 | Tagbilaran City Central School SPED Center | TAGBILARAN CITY (Capital) | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 900000 | 1 | 892529.27 | completed | 100% | 2023-07-04 | 2023-05-25 | 2023-002-Infra | 2023-002-Infra | 2023-02-24 | 2023-03-06 | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 5.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VII | Tanjay City | 120563 | Sta. Cruz CES | CITY OF TANJAY | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 2520000 | 1 |  | completed | 100% |  |  | 0 | [8 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.23 |  |  |  |  | REPAIR | completed
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122544 | Mercedes Central School | MERCEDES | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2600638.38 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122685 | Quinapondan Central Elementary School | QUINAPONDAN | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2158793.15 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122700 | Salcedo Central Elementary School | SALCEDO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2604913.04 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121408 | Hindang Central School | HINDANG | 5th | 1 | 5 | REPAIR OF CLASSROOMS | 1610308.64 | 1 | 1574959.81 | Completed | 100% | 6/17/2023 |  |  |  | 1/17/2023 | [5 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121688 | Cahagnaan Central School | MATALOM | 5th | 1 | 4 | Replacement | 11429257.0851 | 1 | 8518483.48 | Completed | 100% | 9/27/2023 | 12/15/2023 |  |  | 1/17/2023 | [5 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121679 | Matalom North Central School | MATALOM | 5th | 1 | 6 | REPAIR OF CLASSROOMS | 1620963.13 | 1 | 1600533.44 | Completed | 100% | 6/29/2023 |  |  |  | 1/17/2023 | [5 empty] | awarded | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 8.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4th | 1 | 4 | REPAIR OF CLASSROOMS | 2048640.94 | 1 | 1105733 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122210 | Malitbog Central School | MALITBOG | 1st | 1 | 11 | REHABILITATION OF GABALDON BUILDINGS | 11495051.46 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122210 | Malitbog Central School | MALITBOG | 1st |  | 36 | REPAIR OF CLASSROOMS | 18891179.44 | 1 |  | COMPLETED | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 36 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122224 | Padre Burgos Central School | PADRE BURGOS | 1st | 1 | 24 | REPAIR OF CLASSROOMS | 13508714.81 | 1 |  | COMPLETED | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1st | 1 | 23 | REPAIR OF CLASSROOMS | 11267143.87 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 100% | 0% |  | 2.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN | 2nd | 1 | 18 | REPAIR OF CLASSROOMS | 7337793.07 | 1 |  | COMPLETED | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 4 | Replacement | 9905392.58 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 22 | REPAIR OF CLASSROOMS | 8732039.79 | 1 |  | COMPLETED | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122080 | Libagon Central School | LIBAGON | 2nd | 1 | 25 | REPAIR OF CLASSROOMS | 11525925.34 | 1 |  | COMPLETED | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | COMPLETED
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2nd | 1 | 4 | Replacement | 9936994.3 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 2.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2nd | 1 | 13 | REPAIR OF CLASSROOMS | 6948729.04 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd | 1 | 6 | REHABILITATION OF GABALDON BUILDINGS | 8894453.9649 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 2.24 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd |  | 34 | REPAIR OF CLASSROOMS | 14172687.09 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2022 REPLENISHMENT | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 3 | Replacement | 6333807.9 | 1 | 6316664.91 | COMPLETED | 100% | 2023-10-09 | 2024-01-06 | QRF 2022 - R X - Camiguin - 010 | QRF 2022 BATCH 2 | 2023-03-14 | 2023-03-22 | 2023-03-06 | 2023-03-27 | 2023-05-08 | VINLABZ CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 |  |  |  |  | REPLACEMENT | COMPLETED
QRF 2023 | CAR | Baguio City | 305280 | Irisan National High School | Baguio City | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 2-R | 1169675.6 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | completed
QRF 2023 | CAR | Baguio City | 221501 | Kias Elementary School | Baguio City | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1000000 | 2-R | 2605810.49 | Completed | 100% | 2024-04-20 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing - With Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | completed
QRF 2023 | CAR | Ifugao | 135955 | Tinoc CS | TINOC | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 4070250.08 | 2-R | 48462000 | completed | 100% | 2024-01-14 | 2024-07-08 | QRF 2023 | 011-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | HSO | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.24 |  |  |  |  | REPAIR | completed
QRF 2023 | CAR | Mt. Province | 305249 | Bansa National High School | BAUKO | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 8128437.39 | 2-S | 544594.41 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 9.24 |  |  |  |  | SLOPE PROTECTION | completed
QRF 2023 | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 12015695 | 2-S | 3392720.89 | Completed | 100% | 2024-03-18 | 2024-03-29 | QRF 2023 | 021-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | 2023-12-13 | RJLG Construction and Supplies | Ongoing - with issued Site Instruction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 9.24 |  |  |  |  | SLOPE PROTECTION | completed
QRF 2023 | CAR | Mt. Province | 319224 | Bunga National High School | TADIAN | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 14169367.62 | 2-R | 9791374 | Completed | 100% | 2024-04-01 |  | QRF 2023 | 013-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | SGM | Ongoing - with liquidated damages ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | completed
QRF 2023 | CAR | Mt. Province | 136364 | Duagan Elementary School | TADIAN | Lone | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 11132912.72 | 2-S | 16346376.58 | Completed | 100% | 2024-03-24 |  | QRF 2023 | 014-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing-With Suspension Order due to change in foundation to suit actual field condition - Resumption on April 1, 2024 ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 9.24 |  |  |  |  | SLOPE PROTECTION | completed
QRF 2023 | CARAGA | Agusan del Norte | 131431 | Colorado ES | JABONGA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 5714123.73 | 1 | 1773076.95 | Completed | 100% | 2024-03-18 | 2024-03-26 | QRF 2023 | 022-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | October 27, 2027 | RJLG Construction and Supplies | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 70% | 30% |  |  | SHEARLINE & LPA & TY ODETTE |  |  |  | REPAIR | Ongoing
QRF 2023 | CARAGA | Butuan City | 132034 | Imelda ES | BUTUAN CITY (Capital) | 1 | 1 | 0 | SLOPE PROTECTION | 3526609.12 | 1 | 23861999.87 | Completed | 100% | 2024-04-21 |  | QRF 2023 | 015-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | Mindanao Rock | Ongoing - with liquidated damages ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10% | 90% |  |  | SOIL EROSION/LANDSLIDE |  |  |  | SLOPE PROTECTION | Ongoing
QRF 2023 | CARAGA | Butuan City | 137019 | Sinaka IPED Elementary School | BUTUAN CITY (Capital) | 1st | 1 | 4 | 1STY4CL | 12000000 | 2- NC | 758014.3 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 3% | 97% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | CARAGA | Surigao del Norte | 132344 | Cabugao ES | BACUAG | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 3191536.58 | 1 | 2151115.2 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132352 | Payapag Elementary School | BACUAG | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 3393326.28 | 1 | 39598320.79 | Completed | 100% | September 30, 2024 |  | QRF 2023 | PB Const2023-002 | June 3,2023 | June 13,2023 | June 27,2023 | July 27,2023 | October 27, 2023 | Junjing Construction and Gen Mer. | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304826 | Gigaquit National School of Home Industries | GIGAQUIT | 2 | 1 | 14 | REPAIR OF CLASSROOMS | 8340458.83 | 1 | 835775.02 | Completed | 100% | March 1,2024 | February 25, 2024 | QRF 2023 | G2PB Repair 2023-001 | October 10,2023 | Oct 23,2023 | Nov 6,2023 | Nov 22, 2023 | Dec.19, 2023 | Tri - FB | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 8.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132412 | Poniente Elementary School | GIGAQUIT | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4022170.9 | 1 | 21907012.66 | completed | 100% | 17‎ ‎July‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-1 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-07-10 | 2023-07-14 | G-Baron Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132435 | Mansayao ES | MAINIT | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 4518379.12 | 1 | 16036677.23 | Completed | 100% | ‎29‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-3 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | Completed - Subject for turn-over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio Memorial National High School (Sta. Cruz National School) | PLACER | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3278625.08 | 1 | 18973207.53 | Completed | 100% | ‎13‎ ‎January‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-2 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 304838 | Lakandula National High School | PLACER | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 910185.26 | 1 | 3817916.63 | Completed | 100% | ‎14‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-4 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1410767.81 | 1 | 5741696.19 | Completed | 100% | Revised date March 16, 2025 |  | PB-02-07-2024-011 | 045-2024 | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-08-14 | 2024-09-16 | IM and M Construction | with approved extension No's 1&2 and variation order no.1. Impose Liquidation damage (LD) during progress billing. Tentative date completion July 31, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | CARAGA | Tandag City | 132964 | Engr. Nestor Ty Memorial Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL (WITH COMMON TOILET) | 10525907.02 | 1 | 8629785.3 | Completed | 100% | January 8, 2024 | February 2, 2024 | QRF 2023-001 | [5 empty] | July 4, 2023 | Melroshean Construction Corporation | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 10% | 90% |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL (WITH COMMON TOILET) | 10520708.47 | 1 | 8233512 | Completed | 100% | January 8, 2024 | February 4, 2024 | QRF 2023-002 | [5 empty] | July 4, 2023 | 3'CSL Construction and Supply | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 10% | 90% |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1834811.6 | Completed | 100% | 9/28/2024 | 2024-07-08 | PB-19-2023-1 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100013 | Bangsirit ES | BACARRA | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 4925877 | 2-R | 4401231.88 | completed | 100% | 9/28/2024 | 2024-11-07 | PB-19-2023-2 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 634587.67 | completed | 100% | 9/28/2024 | 2024-03-05 | PB-19-2023-2 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100007 | Pasiocan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784970.3 | completed | 100% | 9/28/2024 | 2024-07-08 | PB-19-2023-1 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1784635.64 | completed | 100% | 9/28/2024 | 2024-07-08 | PB-19-2023-1 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 320801 | BANBAN NHS | BANGUI | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1365141.42 | Completed | 100% | 2024-01-10 | 9/20/2024 | PB-19B-2023-7 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 895425.54 | Completed | 100% | 2024-01-10 | 9/20/2024 | PB-19B-2023-7 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100107 | Paayas ES | BURGOS | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2572715.41 | Completed | 100% | 2024-01-10 | 9/30/2024 | PB-19B-2023-6 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100167 | Dampig ES | PAGUDPUD | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1895646.18 | completed | 100% | 8/29/2024 | 2024-07-08 | PB-19-2023-8 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 3016937.09 | Completed | 100% | 8/29/2024 | 2024-07-08 | PB-19-2023-8 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100199 | Davila ES | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2506581.45 | Completed | 100% | 2024-04-11 | 2024-08-05 | PB-19B-2023-15 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-08-05 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 2788000 | 2-R | 2314877.57 | Completed | 100% | 2024-04-11 | 2024-08-05 | PB-19B-2023-15 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-08-05 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1622920.46 | Completed | 100% | 2024-01-10 | 2024-11-08 | PB-19B-2023-16 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 3742897.43 | Completed | 100% | 8/29/2024 | 7/18/2024 | PB-19-2023-17 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 636101.98 | completed | 100% | 8/29/2024 | 7/18/2024 | PB-19-2023-17 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | DPV Builders and Construction Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100213 | Surong PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 1012229.86 | Completed | 100% | 2024-01-10 | 2024-11-08 | PB-19B-2023-16 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100218 | Boyboy ES | PIDDIG | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 343985.21 | Completed | 100% | 11/24/2024 | 11/20/2024 | PB-19-2023-18 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 345057.91 | Completed | 100% | 11/24/2024 | 11/20/2024 | PB-19-2023-18 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 632610.25 | Completed | 100% | 11/24/2024 | 11/20/2024 | PB-19-2023-18 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100311 | Dasar ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1794270.16 | completed | 100% | 8/29/2024 | 8/27/2024 | PB-19A-2023-19 | n/a | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 633380 | 2-R | 454449.33 | Completed | 100% | 8/29/2024 | 8/29/2024 | PB-19A-2023-19 | n/a | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 3304000 | 2-R | 3296745.93 | Completed | 100% | 11/24/2024 | 11/20/2024 | PB-19-2023-18 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100324 | Tungel ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1480782.92 | completed | 100% | 8/29/2024 | 8/27/2024 | PB-19A-2023-19 | n/a | 12/20/2023 | 12/27/2023 | 2024-08-01 | 2/20/2024 | 2024-01-04 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3750206 | 2-R | 2814383.65 | Completed | 100% | 2024-09-12 | 12/27/2024 | PB-19-2023-20 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100041 | Turod ES | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1187200 | 2-R | 831704.72 | Completed | 100% | 12/28/2024 | 11/30/2024 | PB-19-2023-3 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100060 | Barbarangay ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1628202.96 | Completed | 100% | 11/30/2024 | 2024-11-08 | PB-19B-2023-9 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100063 | Caestebanan ES | BANNA (ESPIRITU) | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3020855 | 2-R | 2520165.06 | Completed | 100% | 11/30/2024 | 11/19/2024 | PB-19B-2023-9 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4187330 | 2-R | 2857524.12 | Completed | 100% | 12/28/2024 | 11/30/2024 | PB-19-2023-3 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 320808 | Bamasesamar National High School | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1298980 | 2-R | 1160009.34 | completed | 100% | 9/13/2024 | 5/25/2024 | PB-19-2023-12 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1000219 | 2-R | 920129.09 | Completed | 100% | 2024-01-10 | 6/27/2024 | PB-19-2023-11 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100130 | Dingras West CES | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 2-R | 3334927.64 | Completed | 100% | 10/31/2024 | 2024-05-10 | PB-01-2024 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 2024-03-06 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100134 | Peralta ES | DINGRAS | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8600094.07 | Completed | 100% | 9/14/2024 | 8/24/2024 | PB-15-2023-1 | n/a | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region I | Ilocos Norte | 100124 | Saludares-Cali ES | DINGRAS | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2498555 | 2-R | 2487632.44 | Completed | 100% | 2024-01-10 | 6/27/2024 | PB-19-2023-11 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100135 | San Esteban ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1828801.76 | completed | 100% | 9/13/2024 | 5/25/2024 | PB-19-2023-12 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100138 | Suyo ES | DINGRAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1815871.21 | completed | 100% | 2024-01-10 | 6/27/2024 | PB-19-2023-11 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100151 | Mabuti ES | MARCOS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1899820 | 2-R | 1584474 | terminated | 0% |  |  | PB-19B-2023-9 |  | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction | Terminated, building to be repaired was replaced by the DPWH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | [6 empty] | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6265349.89 | Completed | 100% | 2024-06-11 | 12/27/2024 | PB-15-2023-2 | n/a | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Abeian Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 481818.73 | Completed | 100% | 2024-09-12 | 12/27/2024 | PB-19-2023-13 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100185 | Nagbacalan ES | PAOAY | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 4565891 | 2-R | 3621685.56 | Completed | 100% | 2024-09-12 | 12/27/2024 | PB-19-2023-13 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2576846.3 | Completed | 100% | 2024-09-12 | 12/27/2024 | PB-19-2023-14 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 1595900 | 2-R | 1114477.47 | Completed | 100% | 2024-09-12 | 12/27/2024 | PB-19-2023-14 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3211861 | 2-R | 2743455.85 | Completed | 100% | 10/31/2024 | 2024-10-10 | PB-19B-2023-4 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100236 | Bicbica PS | PINILI | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 2- NC | 8598431.5 | Completed | 100% | 10/31/2024 | 11/20/2024 | PB-15-2023-3 | n/a | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | KRB Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 639120.75 | 2-R | 545285.46 | Completed | 100% | 10/31/2024 | 2024-11-08 | PB-19B-2023-4 | n/a | 2024-04-03 | 2024-08-03 | 3/25/2024 | 4/15/2024 | 5/29/2024 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 2- NC | 6258355.82 | Completed | 100% | 2024-08-09 | 2024-05-10 | PB-15-2023-4 | n/a | 2023-09-11 | 11/14/2023 | 11/28/2023 | 12/28/2023 | 2/26/2024 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd |  | 3 | REPAIR OF CLASSROOMS | 2449998.96 | 2-R | 2440022.86 | Completed | 100% | 2024-10-10 | 11/30/2024 | PB-19-2023-5 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 348290 | 2-R | 341366.87 | Completed | 100% | 2024-10-10 | 11/30/2024 | PB-19-2023-5 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-04-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region I | Ilocos Norte | 100276 | Barcelona ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 2-R | 1946864.79 | completed | 100% | 11/24/2024 | 2024-08-07 | PB-19-2023-10 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 100284 | Santiago ES | SOLSONA | 2nd | 1 | 1 | REPAIR OF CLASSROOM | 950000 | 2-R | 948168.99 | completed | 100% | 11/24/2024 | 2024-08-07 | PB-19-2023-10 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 7.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1050000 | 2-R | 1045358.69 | Completed | 100% | 11/24/2024 | 11/22/2024 | PB-19-2023-10 | n/a | 11/20/2023 | 11/29/2023 | 2023-11-12 | 2/20/2024 | 2024-01-04 | Elocin Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 |  |  |  |  | REPAIR | Ongoing
QRF 2023 | Region II | Nueva Vizcaya | 103980 | Ambaguio CS | AMBAGUIO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 6249523.32 | 2-R | 4415902.41 | Ongoing | 99% | May 30, 2024 | - | PB12-001-QRF-Lot 1 | PB12-001-QRF-Lot 1 | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 2, 2024 | IA Castañeda Construction | with savings contract amount: 4,415,902.41 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 98% | 1% | [6 empty] | REPAIR | Ongoing
QRF 2023 | Region II | Nueva Vizcaya | 306202 | Bonfa National High School | BAYOMBONG (Capital) | Lone | 1 | 1 | REPAIR OF CLASSROOMS | 600000 | 2-R | 562547.02 | Completed | 100% | April 16, 2024 | April 15, 2024 | PB12-001-QRF-Lot 3 | PB12-001-QRF-Lot 3 | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 16, 2024 | Mighty Construction | with additional works amount: 37,452.98 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region II | Nueva Vizcaya | 104223 | Villaverde Central School | VILLAVERDE | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1350000 | 2-R | 952179.1 | completed | 100% | April 2, 2024 | November 6, 2024 | PB12-001-QRF-Lot 2 | PB12-001-QRF-Lot 2 | December 1, 2023 | December 11, 2023 | December 27, 2023 | January 24, 2024 | February 2, 2024 | IA Castañeda Construction | with savings contract amount: 397,820.9 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.25 |  |  |  |  | REPAIR | completed
QRF 2023 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1st | 1 | 8 | 2STY8CL | 22950000 | 2- NC | 15742082.99 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | ongoing
QRF 2023 | Region IV-A | Dasmarinas City | 107908 | Paliparan III ES | CITY OF DASMARIÑAS | 4th | 1 | 6 | REPAIR OF CLASSROOMS | 2637865.5 | 2-R | 1822725.3 | Completed | 100% | 9/30/2024 | 2024-10-09 | CY2023 QRF Batch 2 RRC | CY2023 QRF Batch 2 RRC | March 13, 2024- | 3/21/2024 | 2024-03-04 | 2024-03-05 | 2024-03-06 | Open Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.24 |  |  |  |  | REPAIR | completed
QRF 2023 | Region IV-A | Tanauan City | 107749 | Balele ES | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1423774.38 | Completed | 100% | 10/28/2023 | 2023-11-09 | N/A | N/A | 2023-10-05 | 5/19/2023 | 2023-08-06 | 2023-07-07 | 7/21/2023 | open builders corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107753 | Bernardo Lirio Memorial Central School | CITY OF TANAUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 800000 | 1 | 790492.18 | Completed | 100% | 10/28/2023 | 8/30/2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 4 | REPAIR OF CLASSROOMS | 800000 | 1 | 790298.94 | Completed | 100% | 10/28/2023 | 9/14/2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 391219.74 | Completed | 100% | 10/28/2023 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107762 | Laurel ES | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1186282.19 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301113 | Luyos National High School | CITY OF TANAUAN | 3 | 1 | 9 | REPAIR OF CLASSROOMS | 1800000 | 1 | 1782547.48 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107765 | Malaking Pulo ES | CITY OF TANAUAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1583362.61 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301119 | Malaking Pulo National High School | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 390711.09 | Completed | 100% | 10/28/2023 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107770 | Pagaspas ES | CITY OF TANAUAN | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 400000 | 1 | 391587.77 | Completed | 100% | 10/28/2023 | 8/20/2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301138 | Pres. Jose P. Laurel National High School | CITY OF TANAUAN | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 1400000 | 1 | 1387885.25 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107779 | Suplang Elementary School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1180052.23 | Completed | 100% | 10/28/2023 | 9/18/2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 301159 | Tinurik National High School | CITY OF TANAUAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1600000 | 1 | 1584414.37 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 500867 | Ulango Integrated School | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1189951.19 | Completed | 100% | 2023-09-10 | October 19,2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | MG VILLAMIN CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 107787 | Wawa ES | CITY OF TANAUAN | 3 | 1 | 6 | REPAIR OF CLASSROOMS | 1200000 | 1 | 1188805.92 | Completed | 100% | 10/28/2023 | 9/20/2023 | N/A | N/A | 2023-10-05 | 5/19/2023 | 5/30/2023 | 2023-07-07 | 7/21/2023 | gs motar builders construction and trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.23 | TY PAENG |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF DASMARIÑAS | 3rd | 1 | 6 | REPAIR OF CLASSROOMS | 8500000 | 2-R | 8483174.9 | Completed | 100% | 5/16/2024 | 5/19/2024 | N/A | N/A | 2023-10-05 | 11/30/2023 | 12/13/2023 | 2024-05-01 | 1/19/2024 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 12.23 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region IV-B | Oriental Mindoro | 301623 | Bulbugan NHS | GLORIA | 2nd | 1 | 6 | 2STY6CL | 30160867 | 2- NC | 29050000 | completed | 100% | 2024-11-22 | 2024-11-20 | QRF 2023-MIMAROPA-ORIENTAL MINDORO-002 | 018-2023 | 2023-11-08 | 2023-11-16 | 2023-11-29 | 2023-12-07 | 2023-12-18 | ADL Constrak OPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 1.25 |  |  |  |  | REPLACEMENT | completed
QRF 2023 | Region IX | Dapitan City | 125916 | Ilaya Elementary School | DAPITAN CITY | 1st | 1 | 10 | 2STY10CL | 32421818.5311 | 2- NC | 32327913.17 | Ongoing | 79% | 2024-01-08 |  | SDODAP-INFRA-2023-003 | SDODAP-INFRA-2023-003 | 14/11/2023 | 21/11/2023 | 2023-07-12 | 22/12/2023 | 2024-03-01 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 79% | 0% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region IX | Dapitan City | 125919 | Oyan Elementary School | DAPITAN CITY | 1st | 1 | 4 | 1STY4CL | 21233503.4667 | 2- NC | 21363407.93 | Completed | 100% | 2024-01-07 |  | SDODAP-INFRA-2023-002 | SDODAP-INFRA-2023-002 | 14/11/2023 | 21/11/2023 | 2023-07-12 | 22/12/2023 | 2024-03-01 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.24 |  |  |  |  | REPLACEMENT | completed
QRF 2023 | Region IX | Dapitan City | 125919 | Oyan Elementary School | DAPITAN CITY | 1st |  | 3 | REPAIR OF CLASSROOMS | 2524721.336 | 2-R | 2488604.93 | Completed | 100% | 20/03/2024 | 18/03/2024 | SDODAP-INFRA-2023-001 | SDODAP-INFRA-2023-001 | 14/11/2023 | 21/11/2023 | 2023-07-12 | 22/12/2023 | 2024-03-01 | MORTE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Camarines Norte | 112161 | Dahican Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8750694 | 1 | 8248310.41 | Completed | 100% | 2023-11-08 | 2023-12-19 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | Meltri Construction Services | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8481294 | 1 | 6932320.69 | Completed | 100% | 2023-12-02 | 2023-12-24 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | MBC Builders and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 4 | 1STY4CL | 11095757.25 | 1 | 9077808.62 | Completed | 100% | 2023-12-02 | 2023-12-24 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | MBC Builders and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 0 | SLOPE PROTECTION | 20215246.12 | 1 | 20149399.76 | Completed | 100% | 2023-11-24 | 2023-12-24 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-30 | 2023-06-06 | 2023-06-29 | 2022-07-18 | 2023-07-27 | JAEJR Electrical, Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Camarines Norte | 112155 | Parang Elementary School | JOSE PANGANIBAN | 1st | 1 | 2 | 1STY2CL | 6034952.59 | 1 | 3713765.02 | Completed | 100% | 2023-10-01 | 2023-12-27 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-03 | Century Glass Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112152 | Regino A. Yet Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8720694 | 1 | 7379093.56 | Completed | 100% | 2023-11-15 | 2023-12-12 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-22 | 2023-07-03 | Meltri Construction Services | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112156 | San Mauricio Elementary School | JOSE PANGANIBAN | 1st | 1 | 3 | 1STY3CL | 8720694 | 1 | 6019892.2 | Completed | 100% | 2023-11-12 | 2024-03-12 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-30 | EPL General Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112206 | Daguit Elementary School | LABO | 1st | 1 | 3 | 1STY3CL | 8481294 | 1 | 6743528.22 | Completed | 100% | 2023-11-11 | 2024-03-13 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-29 | Araphil Construction and Development Corp. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112208 | Felix Asis Elementary School | LABO | 1st | 1 | 2 | 1STY2CL | 6034952.59 | 1 | 5099972.96 | Completed | 100% | 2023-10-01 | 2023-10-16 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-22 | 2023-07-03 | Meltri Construction Services | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | 2 | 1STY2CL | 6586051.82 | 1 | 8685821.38 | Completed | 100% | 2023-11-23 | 2023-12-22 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-06-30 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | LA ABEL CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | 2 | 1STY2CL | 6586051.82 | 1 | 5498272.77 | Completed | 100% | 2023-11-23 | 2023-12-22 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | LA ABEL CONSTRUCTION AND SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112213 | Macogon Elementary School | LABO | 1st | 1 | 3 | 1STY3CL | 8876595.59 | 1 | 6146720.44 | Completed | 100% | 2023-11-12 | 2024-03-12 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-30 | EPL General Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112247 | Gumaus Elementary School | PARACALE | 1st | 1 | 2 | 1STY2CL | 6009036.68 | 1 | 5498272.77 | Completed | 100% | 2023-09-27 | 2023-10-16 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-13 | 2023-06-29 | Meltri Construction Services | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112083 | Balce Elementary School | BASUD | 2nd | 1 | 0 | SLOPE PROTECTION | 8000000 | 1 | 7941528.03 | Completed | 100% | 2023-11-23 | 2023-11-20 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-30 | 2023-06-06 | 2023-06-29 | 2023-07-18 | 2023-07-26 | NEB Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Camarines Norte | 112224 | F. P. Ibasco Elementary School | MERCEDES | 2nd | 1 | 3 | 1STY3CL | 8720694 | 1 | 8631104.39 | Completed | 100% | 2023-12-21 | 2024-05-09 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-13 | 2023-08-08 | EPL General Construction and Supply | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8683413.32 | 1 | 6251672.23 | Completed | 100% | 2023-11-11 | 2024-03-01 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8683413.32 | 1 | 4525434.65 | Completed | 100% | 2023-11-11 | 2024-03-01 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-29 | RidersCorner Construction & Gen. Mdse. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 309604 | Eugenia Morana - Quintela Memorial High School | VINZONS | 2nd | 1 | 2 | 1STY2CL | 6274352.59 | 1 | 4525434.65 | Completed | 100% | 2023-10-03 | 2023-12-27 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-07-05 | RidersCorner Construction & Gen. Mdse. | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Camarines Norte | 502249 | Pinagtigasan Calaguas Island Integrated School | VINZONS | 2nd | 1 | 3 | 1STY3CL | 8720694 | 1 | 8685821.38 | Completed | 100% | 2023-11-08 | 2023-12-10 | INFRA01-05-2023CN | INFRA01-05-2023CN | 2023-05-08 | 2023-05-15 | May 29-30, 2023 | 2023-06-14 | 2023-06-26 | O.L. De Leon Construction | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 5978075.08 | 1 | 5972113.34 | Completed | 100% | 2024-02-13 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-004 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 70% | 30% |  |  | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Ongoing
QRF 2023 | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st |  | 3 | 1STY3CL | 8571900.92 | 1 | 8561119.62 | Completed | 100% | 2024-02-13 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-004 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 85% | 15% |  |  | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1st | 1 | 2 | 1STY2CL | 6093809.88 | 1 | 6083147.5 | Completed | 100% | 2024-01-08 | 2023-12-06 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 5326059.93 | 1 | 5322804.23 | Completed | 100% | 2024-01-02 | 2024-06-07 | INFRA 2023-05-001 | 2023-07-008 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st |  | 4 | 1STY4CL | 11104764.36 | 1 | 11100536.54 | Completed | 100% | 2024-01-02 | 2024-06-07 | INFRA 2023-05-001 | 2023-07-008 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3362054.88 | 1 | 8610317.09 | Ongoing | 95% | 2024-01-06 |  | INFRA 2023-05-001 | 2023-07-009 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 95% | 0% |  |  | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Ongoing
QRF 2023 | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st |  | 3 | 1STY3CL | 8615718.84 | 1 | 8610317.09 | Ongoing | 95% | 2024-01-06 |  | INFRA 2023-05-001 | 2023-07-009 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 95% | 0% |  |  | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region V | Masbate | 113486 | Panisihan ES | BATUAN | 1st | 1 | 3 | 1STY3CL | 8626673.32 | 1 | 8621271.56 | Completed | 100% | 2024-01-06 |  | INFRA 2023-05-001 | 2023-07-009 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113488 | Royroy Elementary School | BATUAN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2054044.78 | 1 | 2051603.85 | Completed | 100% | 2024-01-02 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-008 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113489 | Sawang ES | BATUAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1400039.73 | 1 | 1397914.08 | Completed | 100% | 2024-01-01 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-010 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113489 | Sawang ES | BATUAN | 1st |  | 2 | 1STY2CL | 6138577.25 | 1 | 6133044.97 | Completed | 100% | 2024-01-01 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-010 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113578 | Dapdap ES | CLAVERIA | 1st | 1 | 0 | SLOPE PROTECTION | 6513275.3 | 1 | 6504278.01 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-005 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113585 | Nabasagan ES | CLAVERIA | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 4676034.68 | 1 | 4670322.97 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-005 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113587 | Osmena ES | CLAVERIA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1574858.78 | 1 | 1570734.39 | Completed | 100% | 2024-01-08 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-005 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113589 | Peñafrancia ES | CLAVERIA | 1st | 1 | 3 | 1STY3CL | 8962800.23 | 1 | 8957445.08 | Completed | 100% | 2024-01-08 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-005 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113767 | Lapu-Lapu ES | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2057029.63 | 1 | 2053560.04 | Completed | 100% | 2024-01-06 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-004 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113769 | Maglambong Elementary School | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2058024.58 | 1 | 2054323.53 | Completed | 100% | 2024-01-08 | 2024-02-23 | INFRA 2023-05-001 | 2023-07-014 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 501537 | Rizal Integrated School | MONREAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2059019.53 | 1 | 2057265.74 | Completed | 100% | 2024-01-02 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-015 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 501537 | Rizal Integrated School | MONREAL | 1st |  | 3 | 1STY3CL | 8662380.08 | 1 | 8660210.74 | Completed | 100% | 2024-01-02 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-015 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st | 1 | 10 | REPAIR OF CLASSROOMS | 6645014.53 | 1 | 6636888.36 | Completed | 100% | 2024-01-09 | 2024-02-16 | INFRA 2023-05-001 | 2023-07-003 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st |  | 5 | 1STY5CL | 13663334.56 | 1 | 13646287.9 | Completed | 100% | 2024-01-09 | 2024-02-16 | INFRA 2023-05-001 | 2023-07-003 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113860 | Buenasuerte ES | SAN FERNANDO | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4026009.43 | 1 | 4021037.97 | Completed | 100% | 2024-01-08 | 2024-02-23 | INFRA 2023-05-001 | 2023-07-012 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2717004.38 | 1 | 2714524.44 | Completed | 100% | 2024-01-01 | 2024-02-28 | INFRA 2023-05-001 | 2023- | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st |  | 2 | 1STY2CL | 6175238.49 | 1 | 6170487 | Completed | 100% | 2024-01-01 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-011 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302127 | Buyo National High School | SAN FERNANDO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3372999.33 | 1 | 3370355.28 | Completed | 100% | 2024-01-01 | 2024-02-16 | INFRA 2023-05-001 | 2023-07-011 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302127 | Buyo National High School | SAN FERNANDO | 1st |  | 2 | 1STY2CL | 6186192.97 | 1 | 6182233.4 | Completed | 100% | 2024-01-01 | 2024-06-05 | INFRA 2023-05-001 | 2023-07-011 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 7.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113867 | Ipil ES | SAN FERNANDO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1408994.28 | 1 | 1407184.38 | Completed | 100% | 2024-01-02 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-015 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113867 | Ipil ES | SAN FERNANDO | 1st |  | 3 | 1STY3CL | 8697147.45 | 1 | 8693893.44 | Completed | 100% | 2024-01-02 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-015 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113871 | Minio ES | SAN FERNANDO | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1409989.23 | 1 | 1403329.55 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-012 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113871 | Minio ES | SAN FERNANDO | 1st |  | 5 | 1STY5CL | 13708101.93 | 1 | 13697873.93 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-012 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2065984.18 | 1 | 2063497.58 | Completed | 100% | 2024-01-01 | 2023-12-06 | INFRA 2023-05-001 | 2023-07-006 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st |  | 4 | 1STY4CL | 11219056.41 | 1 | 11212085.67 | Completed | 100% | 2024-01-01 | 2023-12-06 | INFRA 2023-05-001 | 2023-07-006 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113880 | Talisay ES | SAN FERNANDO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2066979.13 | 1 | 2064517.93 | Completed | 100% | 2024-01-02 | 2024-02-13 | INFRA 2023-05-001 | 2023-07-008 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302113 | Bagahanglad National High School | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2722974.12 | 1 | 2714529.01 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-012 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113891 | Guiwanon ES | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2723969.03 | 1 | 2721512.73 | Completed | 100% | 2024-01-01 | 2024-06-20 | INFRA 2023-05-001 | 2023-07-011 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1st | 1 | 3 | 1STY3CL | 8732859.24 | 1 | 8721989.66 | Completed | 100% | 2024-01-01 | 2023-12-06 | INFRA 2023-05-001 | 2023-07-006 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | C.L. CARANDANG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3380958.93 | 1 | 3376882.32 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-014 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st |  | 6 | 1STY6CL | 16243813.72 | 1 | 16232937.05 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-014 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302167 | San Jacinto National High School | SAN JACINTO | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2726953.88 | 1 | 2723654.7 | Completed | 100% | 2024-01-06 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-004 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2072948.83 | 1 | 2070439.95 | Completed | 100% | 2024-01-08 | 2023-12-05 | INFRA 2023-05-001 | 2023-07-013 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1st |  | 3 | 1STY3CL | 8755717.65 | 1 | 8744878.07 | Completed | 100% | 2024-01-08 | 2023-12-05 | INFRA 2023-05-001 | 2023-07-013 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113902 | Tutuban Elementary School | SAN JACINTO | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3383943.78 | 1 | 3379814.1 | Completed | 100% | 2024-01-06 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-004 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | VAEMAR CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113903 | Washington Elementary School | SAN JACINTO | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2074938.73 | 1 | 2064458.82 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-013 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113903 | Washington Elementary School | SAN JACINTO | 1st |  | 3 | 1STY3CL | 8767621.58 | 1 | 8756740.87 | Completed | 100% | 2024-01-08 | 2023-12-08 | INFRA 2023-05-001 | 2023-07-013 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113905 | Acacia Elementary School | SAN PASCUAL | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1420933.68 | 1 | 1418574.15 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113908 | Boca Chica ES | SAN PASCUAL | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2076928.63 | 1 | 2074389.9 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113915 | Florentino D. Peñalosa Elementary School | SAN PASCUAL | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4042923.58 | 1 | 4040487.9 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113917 | Halabangbaybay ES | SAN PASCUAL | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2733918.53 | 1 | 2730785.75 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113930 | Quintina Elementary School | SAN PASCUAL | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 5354913.48 | 1 | 5351640.43 | Completed | 100% | 2024-01-08 | 2023-12-20 | INFRA 2023-05-001 | 2023-07-007 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CAMSUR BICOL TRADING INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1478686.89 | 1 | 1474072.41 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2nd |  | 2 | 1STY2CL | 7153545.65 | 1 | 7152603.62 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 764352.22 | 1 | 758553.45 | Completed | 100% | 2024-01-09 | 2024-01-08 | INFRA 2023-05-001 | 2023-07-017 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2nd |  | 2 | 1STY2CL | 7110437.12 | 1 | 7107419.51 | Completed | 100% | 2024-01-09 | 2024-01-08 | INFRA 2023-05-001 | 2023-07-017 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 309925 | Damaso R. Rubia Memorial High School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1545684.33 | 1 | 1544464.61 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309925 | Damaso R. Rubia Memorial High School | AROROY | 2nd |  | 2 | 1STY2CL | 7561464.35 | 1 | 7558586.69 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113403 | Dayhagan Elementary School | AROROY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2199354.33 | 1 | 2196406.8 | Completed | 100% | 2024-01-09 | 2024-01-08 | INFRA 2023-05-001 | 2023-07-017 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113403 | Dayhagan Elementary School | AROROY | 2nd |  | 0 | 1STY 3CL | 10598933.77 | 1 | 10596079.91 | Completed | 100% | 2024-01-09 | 2024-01-08 | INFRA 2023-05-001 | 2023-07-017 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | MARABE GEN. CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1465255.55 | 1 | 1459341.09 | Completed | 100% | 2024-01-09 | 2024-03-01 | INFRA 2023-05-001 | 2023-07-016 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd |  | 0 | SLOPE PROTECTION | 8384656.58 | 1 | 8381317.59 | Completed | 100% | 2024-01-09 | 2024-03-01 | INFRA 2023-05-001 | 2023-07-016 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd |  | 2 | 1STY2CL | 7123598.56 | 1 | 7120440.61 | Completed | 100% | 2024-01-09 | 2024-03-01 | INFRA 2023-05-001 | 2023-07-016 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113385 | Malubi Elementary School | AROROY | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4968352.45 | 1 | 4965459.87 | Completed | 100% | 2024-01-09 | 2024-03-01 | INFRA 2023-05-001 | 2023-07-016 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 502253 | Manamoc Upland Integrated School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1506872.36 | 1 | 1504691.41 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 500162 | Mataba Integrated School | AROROY | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1548336.45 | 1 | 1544789.32 | Completed | 100% | 2024-01-08 | 2024-04-03 | INFRA 2023-05-001 | 2023-07-019 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 500162 | Mataba Integrated School | AROROY | 2nd |  | 2 | 1STY2CL | 7691464.35 | 1 | 7688416.42 | Completed | 100% | 2024-01-08 | 2024-04-03 | INFRA 2023-05-001 | 2023-07-019 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113416 | Talib Elementary School | AROROY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3587688.56 | 1 | 3584914.73 | Completed | 100% | 2024-01-09 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-018 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | SQUARE N CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113420 | Baleno Central School | BALENO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2146833.66 | 1 | 2144247.71 | Completed | 100% | 2024-01-08 | 2024-04-03 | INFRA 2023-05-001 | 2023-07-019 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302144 | Magdalena National High School | BALENO | 2nd | 1 | 2 | 1STY2CL | 7477683.45 | 1 | 7477115.36 | Completed | 100% | 2024-01-08 | 2024-04-03 | INFRA 2023-05-001 | 2023-07-019 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302144 | Magdalena National High School | BALENO | 2nd |  | 0 | SLOPE PROTECTION | 2535466.48 | 1 | 2535760.25 | Completed | 100% | 2024-01-08 | 2024-04-03 | INFRA 2023-05-001 | 2023-07-019 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | COLINA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113447 | Andronico A. Maybay ES | BALUD | 2nd | 1 | 5 | 1STY5CL | 13582855.4 | 1 |  | Completed | 100% | 2023-01-12 |  |  |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 2023-05-07 | 2023-12-07 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113445 | Balud Central School | BALUD | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1468896.56 | 1 | 1466691.99 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-021 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302116 | Balud National High School | BALUD | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1459595.45 | 1 | 1457079.06 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-021 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113454 | Ilaya ES | BALUD | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2847655.12 | 1 | 2845114.84 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113464 | Pulanduta ES | BALUD | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 4286453.44 | 1 | 4284248.03 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113649 | Jose Z. Meza Sr MES | MANDAON | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3566788.77 | 1 | 3564016.95 | Completed | 100% | 2024-01-02 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-020 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113649 | Jose Z. Meza Sr MES | MANDAON | 2nd |  | 2 | 1STY2CL | 7138225.65 | 1 | 7136111.36 | Completed | 100% | 2024-01-02 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-020 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113664 | Yaneza Landed Estate Elementary School | MANDAON | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 786872.11 | 1 | 784887.04 | Completed | 100% | 2024-01-02 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-020 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2165358.33 | 1 | 2163946.88 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-09-2024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2nd |  | 2 | 1STY2CL | 7346487.45 | 1 | 7344657.05 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-09-2024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113700 | Milagros East CS | MILAGROS | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 8578595.23 | 1 | 8577416.37 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-09-2024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113703 | Punta Tigbao ES | MILAGROS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 812356.15 | 1 | 810340.71 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-09-2024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113710 | Sawmill ES | MILAGROS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 854634.32 | 1 | 852482.65 | Completed | 100% | 2024-01-09 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-021 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1478998.55 | 1 | 1475471.78 | Completed | 100% | 2024-01-02 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-020 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2nd |  | 2 | 1STY2CL | 7136143.12 | 1 | 7133842.74 | Completed | 100% | 2024-01-02 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-020 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | GINA'S CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 6.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113736 | Bagacay ES | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1435968.54 | 1 | 1430915.29 | Completed | 100% | 2024-01-01 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-023 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113736 | Bagacay ES | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21233516.44 | 1 | 21222162.48 | Completed | 100% | 2024-01-01 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-023 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2153668.54 | 1 | 2148112.16 | Completed | 100% | 2024-01-02 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21235356.44 | 1 | 21225753.08 | Completed | 100% | 2024-01-02 | 2024-02-15 | INFRA 2023-05-001 | 2023-07-024 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 309922 | Floro L. Medina Memorial High School | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1499646.15 | 1 | 1497506.25 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309922 | Floro L. Medina Memorial High School | MOBO | 2nd |  | 0 | SLOPE PROTECTION | 6945352.45 | 1 | 6942449.08 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 174502 | Jose B. Gamora ES | MOBO | 2nd | 1 | 0 | SLOPE PROTECTION | 2174766.56 | 1 | 2172269.41 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113745 | Luyong Catungan ES | MOBO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 2168684.56 | 1 | 2166490.98 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-025 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | CB CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1436844.14 | 1 | 1434626.73 | Completed | 100% | 2024-01-01 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-022 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd |  | 0 | SLOPE PROTECTION | 2384654.15 | 1 | 2380660.73 | Completed | 100% | 2024-01-01 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-022 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd |  | 6 | 2-UNITS 1STY3CL | 21138396.9 | 1 | 21130527.89 | Completed | 100% | 2024-01-01 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-022 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302129 | Cataingan National High School | CATAINGAN | 3rd | 1 | 40 | REPAIR OF CLASSROOMS | 26809782.4 | 1 | 26794782 | Completed | 100% | 2024-01-03 | 2024-01-01 | INFRA 2023-05-001 | 2023-07-034 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | HKP CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113510 | Curvada ES | CATAINGAN | 3rd | 1 | 5 | 1STY3CL & 1STY2CL | 18303107.51 | 1 | 18294569.66 | Completed | 100% | 2024-01-01 | 2024-01-29 | INFRA 2023-05-001 | 2023-07-032 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113513 | Emilio S. Boro Sr. Central School | CATAINGAN | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2701390.6 | 1 | 2699492.06 | Completed | 100% | 2024-01-02 | 2023-12-28 | INFRA 2023-05-001 | 2023-07-031 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113514 | Estampar ES | CATAINGAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1380490.6 | 1 | 1377395.38 | Completed | 100% | 2024-01-01 | 2024-01-29 | INFRA 2023-05-001 | 2023-07-032 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3rd | 1 | 12 | 2STY6CL & 2-UNITS 1STY3CL | 40527006.23 | 1 | 40476902.44 | Completed | 100% | 2024-01-02 | 2024-01-03 | INFRA 2023-05-001 | 2023-07-033 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302142 | Liong National High School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2076928.63 | 1 | 2072316.7 | Completed | 100% | 2024-01-01 | 2024-01-29 | INFRA 2023-05-001 | 2023-07-032 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113495 | Malobago Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2053497.6 | Completed | 100% | 2024-01-02 | 2023-12-28 | INFRA 2023-05-001 | 2023-07-031 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113495 | Malobago Elementary School | CATAINGAN | 3rd |  | 2 | 1STY2CL | 7695433.27 | 1 | 7688589.12 | Completed | 100% | 2024-01-02 | 2023-12-28 | INFRA 2023-05-001 | 2023-07-031 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113496 | Matayum Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2053708.99 | Completed | 100% | 2024-01-02 | 2023-12-28 | INFRA 2023-05-001 | 2023-07-031 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113496 | Matayum Elementary School | CATAINGAN | 3rd |  | 2 | 1STY2CL | 7695433.27 | 1 | 7693566.23 | Completed | 100% | 2024-01-02 | 2023-12-28 | INFRA 2023-05-001 | 2023-07-031 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113520 | Matubinao Elementary School | CATAINGAN | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2055798.45 | 1 | 2052910.78 | Completed | 100% | 2024-01-01 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-030 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113522 | Osmeña Elementary School | CATAINGAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 674427.94 | Completed | 100% | 2024-01-01 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-030 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113524 | Quezon ES | CATAINGAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1310556.7 | 1 | 1308753.98 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-036 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113531 | Calapayan Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1382445.47 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113548 | Mahayahay Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1361487.04 | 1 | 1360606.57 | Completed | 100% | 2023-01-12 |  |  |  | 2023-11-05 | 5/19/2023 | 5/31/2023 | 2023-05-07 | 2023-12-07 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113550 | Malbug Elementary School | CAWAYAN | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1384380.03 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113562 | Taberna Elementary School | CAWAYAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 675007.87 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309914 | Tomas V. Rivera National High School | CAWAYAN | 3rd | 1 | 9 | REPAIR OF CLASSROOMS | 5897505.15 | 1 | 5894875.58 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 309914 | Tomas V. Rivera National High School | CAWAYAN | 3rd |  | 0 | SLOPE PROTECTION | 9570000 | 1 | 9555635.43 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region V | Masbate | 302177 | Villahermosa National High School | CAWAYAN | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685266.15 | 1 | 684436.3 | Completed | 100% | 2024-01-07 | 2024-01-05 | INFRA 2023-05-001 | 2023-07-037 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113599 | Buracan ES | DIMASALANG | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 692309.5433 | 1 | 691376.41 | Completed | 100% | 2024-01-03 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-029 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113600 | Cabanuyoan Elementary School | DIMASALANG | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2720935 | 1 | 2713867.85 | Completed | 100% | 2024-01-03 | 2024-01-02 | INFRA 2023-05-001 | 2023-07-028 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113600 | Cabanuyoan Elementary School | DIMASALANG | 3rd |  | 5 | 1STY3CL & 1STY2CL | 18303107.51 | 1 | 18295174.66 | Completed | 100% | 2024-01-03 | 2024-01-02 | INFRA 2023-05-001 | 2023-07-028 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | NJNY CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3rd | 1 | 5 | REPAIR OF CLASSROOMS | 3376738.25 | 1 | 3374660.19 | Completed | 100% | 2024-01-03 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-029 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3rd |  | 2 | 1STY2CL | 7530785.98 | 1 | 7525833.58 | Completed | 100% | 2024-01-03 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-029 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113609 | Gregorio Alino Elementary School | DIMASALANG | 3rd | 1 | 2 | 1STY2CL | 7730974.41 | 1 | 7724358.85 | Completed | 100% | 2024-01-03 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-029 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113611 | Mambog Elementary School | DIMASALANG | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685266.15 | 1 | 684344.98 | Completed | 100% | 2024-01-03 | 2024-02-14 | INFRA 2023-05-001 | 2023-07-029 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | JOHNCB CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113620 | Baras ES | ESPERANZA | 3rd | 1 | 4 | 2-UNITS 1STY2CL | 15461948.82 | 1 | 15449947.7 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-036 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113778 | Buenasuerte Elementary School | PALANAS | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1375350.76 | 1 | 1372050.87 | Completed | 100% | 2024-01-01 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-030 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113781 | Palanas North CS | PALANAS | 3rd | 1 | 3 | REPAIR OF CLASSROOMS | 2026042.95 | 1 | 2023200.04 | Completed | 100% | 2024-01-01 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-030 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113783 | San Antonio ES | PALANAS | 3rd | 1 | 4 | 2-UNITS 1STY2CL | 15461948.82 | 1 | 15456890.38 | Completed | 100% | 2024-01-01 | 2024-02-12 | INFRA 2023-05-001 | 2023-07-030 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113808 | Gregorio M. Bolitres Elementary School | PIO V. CORPUZ (LIMBUHAN) | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 680743.52 | 1 | 680536.53 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-036 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113841 | Camayabsan Elementary School | PLACER | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 685254.25 | 1 | 684264.79 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-036 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113845 | Daraga ES | PLACER | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2741064.6 | 1 | 2737171.5 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-035 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113845 | Daraga ES | PLACER | 3rd |  | 6 | 3-UNITS 1STY2CL | 21144266.2 | 1 | 21133158.49 | Completed | 100% | 2024-01-02 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-035 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | RED DIAMOND CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113851 | Felifranco R. Avenido Sr. Mem. ES | PLACER | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1384619.0867 | 1 | 1383369.11 | Completed | 100% | 2024-01-01 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-027 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113850 | M & R Lecciones ES | PLACER | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 680233.75 | 1 | 679314.9 | Completed | 100% | 2024-01-01 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-027 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113854 | San Pero ES | PLACER | 3rd | 1 | 2 | 1STY2CL | 7730974.41 | 1 | 7724147.32 | Completed | 100% | 2024-01-01 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-027 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113940 | Arado Elementary School | USON | 3rd | 1 | 2 | 1STY2CL | 7682455.25 | 1 | 7677740.1 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 1.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 302121 | Buenavista National High School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 675347.65 | 1 | 674383 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113946 | Crossing ES | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 655278.35 | 1 | 654395.38 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113948 | Del Rosario ES | USON | 3rd | 1 | 2 | 1STY2CL | 7570420.7 | 1 | 7563561.43 | Completed | 100% | 2024-01-01 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-027 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 3.24 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113965 | Felix S. Merioles Elementary School | USON | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1340489.12 | 1 | 1337942.47 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113965 | Felix S. Merioles Elementary School | USON | 3rd |  | 2 | 1STY2CL | 7570420.7 | 1 | 7566448.93 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 11.23 | MASBATE (EARTHQUAKE) |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region V | Masbate | 113949 | Mabini ES | USON | 3rd | 1 | 2 | REPAIR OF CLASSROOMS | 1370532.3 | 1 | 1369941.47 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 113971 | Panisijan Elementary School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 655278.35 | 1 | 654746.15 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302170 | San Ramon National High School | USON | 3rd | 1 | 1 | REPAIR OF CLASSROOMS | 670244.56 | 1 | 668979.51 | Completed | 100% | 2024-01-02 | 2023-11-27 | INFRA 2023-05-001 | 2023-07-026 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | 3R3M CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | REPAIR | Completed
QRF 2023 | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3rd | 1 | 0 | SLOPE PROTECTION | 4730000 | 1 | 4724144.75 | Completed | 100% | 2024-01-01 | 2023-12-29 | INFRA 2023-05-001 | 2023-07-027 | 2023-05-11 | 2023-05-19 | 2023-05-31 | 2023-07-05 | 2023-07-12 | EJ CANTORIA CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 10.23 | MASBATE (EARTHQUAKE) |  |  |  | SLOPE PROTECTION | Completed
QRF 2023 | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 1655029.6 | 2-R | 1638294.04 | Completed | 100% | 2024-03-18 | 2024-03-18 | 2023INFRA-QRF-01 | CY 2023 QRF-REPAIR/REHAB-01 | 2023-12-25 | 2023-11-07 | 2023-11-20 | 2023-12-15 | 2023-12-28 | MB ANG Construction & Supply | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 4.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122369 | Ando Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1614713.4117 | 1 | 1604230.65 | Completed | 100% | 2023-09-23 |  | CY 2023-QRF-B1-R-BOR –C5 | CY 2023-QRF-B1-R-BOR –C5 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122357 | Calico-an Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2140685.7011 | 1 | 2138680.89 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR–C1 | CY 2023-QRF-B1-R-BOR–C1 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122398 | Camada Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2409150.2189 | 1 | 2398211.66 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C2 | CY 2023-QRF-B1-R-BOR –C2 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122361 | Eugenio S. Daza Pilot Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2522036.6047 | 1 | 2510073.16 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR–C6 | CY 2023-QRF-B1-R-BOR–C6 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 8.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122403 | Lalawigan Central Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 5721759.0761 | 1 | 5711677.58 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C12 | CY 2023-QRF-B1-R-BOR –C12 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 100% | 0% |  | 11.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 502290 | Sabang Integrated School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2404559.8182 | 1 | 2394398.63 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C3 | CY 2023-QRF-B1-R-BOR –C3 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122362 | San Gabriel Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 4841848.0755 | 1 | 4839848 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C4 | CY 2023-QRF-B1-R-BOR –C4 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122363 | San Jose Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 3138856.835 | 1 | 3136846.32 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C7 | CY 2023-QRF-B1-R-BOR –C7 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122387 | San Saturnino Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1598425.2174 | 1 | 1588037.65 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C8 | CY 2023-QRF-B1-R-BOR –C8 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Tubigan Builders | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122364 | Siha Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 2 | 1STY2CL | 6828901.78 | 1 | 6798868.48 | Completed | 100% | 2024-01-15 |  | CY 2023-QRF-B1-NEWCON-BOR -14 | CY 2023-QRF-B1-NEWCON-BOR -14 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Galacan Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region VIII | Borongan City | 122388 | Sta. Fe Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1601069.0943 | 1 | 1590568.94 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C9 | CY 2023-QRF-B1-R-BOR –C9 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | Lexbuild Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 303525 | Sta. Fe National High School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 4990026.13 | 1 | 4988023.25 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C13 | CY 2023-QRF-B1-R-BOR –C13 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122389 | Surok Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 3149287.661 | 1 | 3147286.89 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C10 | CY 2023-QRF-B1-R-BOR –C10 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Borongan City | 122390 | Tabunan Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 3536422.7091 | 1 | 3533823.23 | Completed | 100% | 2023-09-04 |  | CY 2023-QRF-B1-R-BOR –C11 | CY 2023-QRF-B1-R-BOR –C11 | 2023-04-14 | 2023-04-21 | 2023-05-04 | 2023-05-22 | 2023-05-26 | VHITS D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 8.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122347 | Guinmaayohan Elementary School | BALANGIGA | Lone | 1 | 9 | REPAIR OF CLASSROOMS | 4658658.32 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 192519 | San Juan Elementary School | GUIUAN | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 4049092.3203 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122554 | Tubabao Elementary School | GUIUAN | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1972578.1556 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 501932 | Cagpile Integrated School | ORAS | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2606947.213 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122664 | Gamot Primary School | ORAS | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1429380.0865 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122668 | Oras West Central Elementary School | ORAS | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 7768905.12 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122674 | Buenavista Elementary School | QUINAPONDAN | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 4229092.3203 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122681 | Naga Elementary School | QUINAPONDAN | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 4221755.4143 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122686 | San Pedro Elementary School | QUINAPONDAN | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1792578.1556 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122690 | Abejao Elementary School | SALCEDO | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1404404.1132 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 3106437.0164 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 5890643.09 | 1 |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI | 2 | 1 | 3 | 1STY3CL | 8343500.28 | 1 | 8320904.13 | Completed | 100% | 2024-01-11 | 2024-03-04 | 2023-QRF B1-(RVIII)-LOT-7 | 2023-QRF B1-(RVIII)-LOT-7 | 2023-07-17 | N/A | 2023-07-25 | 2023-08-29 | 2023-09-06 | NV & CONSTRUCTION & GENERAL SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 6.24 | FIRE INCIDENT |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1st | 1 | 11 | REPAIR OF CLASSROOMS | 6650571.4861 | 1 | 5308214.02 | Completed | 100% | 2023-12-31 | 2023-12-10 | CY2023-QRF-Repair-L4 | CY2023-QRF-Repair-L4 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | QCC CONSTRUCTION AND SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 100% | 0% |  | 2.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122081 | Magkasag Elementary School | LIBAGON | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2599910.7911 | 1 | 1507907.14 | Completed | 100% | 2023-11-01 | 2023-10-26 | CY2023-QRF-Repair-L1 | CY2023-QRF-Repair-L1 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | VHITS D.G. BUILDERS AND ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 4997420.14 | 1 | 2898506.01 | Completed | 100% | 2023-12-16 | 2023-11-17 | CY2023-QRF-Repair-L2 | CY2023-QRF-Repair-L2 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | VHITS D.G. BUILDERS AND ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122237 | Manglit Elementary School | PINTUYAN | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 7224374.6487 | 1 | 4891833.89 | Completed | 100% | 2023-12-31 | 2023-11-17 | CY2023-QRF-Repair-L5 | CY2023-QRF-Repair-L5 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | HD GOLDEN BUILDERS AND SUPPLY INC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122238 | Nueva Estrella Elementary School | PINTUYAN | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 6130124.6202 | 1 | 4238888.02 | Completed | 100% | 2023-12-31 | 2023-12-18 | CY2023-QRF-Repair-L6 | CY2023-QRF-Repair-L6 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | ST. JOSEPH CONSTRUCTION | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122245 | Son-Ok Elementary School | PINTUYAN | 2nd | 1 | 14 | REPAIR OF CLASSROOMS | 8314713.815 | 1 | 5550596.43 | Completed | 100% | 2024-01-25 | 2023-11-17 | CY2023-QRF-Repair-L7 | CY2023-QRF-Repair-L7 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | HD GOLDEN BUILDERS AND SUPPLY INC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 122104 | Marayag Elementary School | SAN FRANCISCO | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 5713718.537 | 1 | 3921423.18 | Completed | 100% | 2023-12-16 | 2023-11-17 | CY2023-QRF-Repair-L3 | CY2023-QRF-Repair-L3 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | HD GOLDEN BUILDERS AND SUPPLY INC. | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 2nd | 1 | 34 | REPAIR OF CLASSROOMS | 11438604.33 | 1 | 6634826.57 | Completed | 100% | 2024-01-30 | 2023-12-18 | CY2023-QRF-Repair-L9 | CY2023-QRF-Repair-L9 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | VHITS D.G. BUILDERS AND ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 34 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | 2nd | 1 | 25 | REPAIR OF CLASSROOMS | 7915072.1224 | 1 | 4591179.53 | Completed | 100% | 2024-01-15 | 2023-12-18 | CY2023-QRF-Repair-L8 | CY2023-QRF-Repair-L8 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | VHITS D.G. BUILDERS AND ENTERPRISES | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 25 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 4988712.6263 | 1 | 4034890.9094 | Completed | 100% | 2023-12-16 | 2023-11-16 | CY2023-QRF-Repair-L10 | CY2023-QRF-Repair-L10 | 2023-04-15 | 2023-04-24 | 2023-05-08 | 2023-07-17 | 2023-08-03 | MIGHTY A's CONSTRUCTION AND HARDWARE SUPPLY | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 12.23 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 127244 | Aloran Central School | ALORAN | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1181156.34 | 1 | 1169675.6 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 304024 | Aloran Trade HS | ALORAN | 1st | 1 | 14 | REPAIR OF CLASSROOMS | 2631921.7 | 1 | 2605810.49 | Completed | 100% | 2024-04-20 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing - With Variation Order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 12 | 2UNITS 2STY6CL | 49200000 | 1 | 48462000 | completed | 100% | 2024-01-14 | 2024-07-08 | QRF 2023 | 011-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | HSO | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 11.24 | SHEARLINE & LPA |  |  |  | REPLACEMENT | completed
QRF 2023 | Region X | Misamis Occidental | 201016 | Palayan PS | ALORAN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 550000 | 1 | 544594.41 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 010-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 127507 | Usocan Elementary School | PLARIDEL | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 3415705.95 | 1 | 3392720.89 | Completed | 100% | 2024-03-18 | 2024-03-29 | QRF 2023 | 021-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | 2023-12-13 | RJLG Construction and Supplies | Ongoing - with issued Site Instruction | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 7.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 127334 | Bitoon Elementary School | CLARIN | 2nd | 1 | 4 | 1STY4CL | 10094200 | 1 | 9791374 | Ongoing | 80% | 2024-04-01 |  | QRF 2023 | 013-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | SGM | Ongoing - with liquidated damages ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 73% | 7% |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region X | Misamis Occidental | 127538 | Cagay-Anon ES | SINACABAN | 2nd | 1 | 4 | 2STY4CL | 16800000 | 1 | 16346376.58 | Ongoing | 85% | 2024-03-24 |  | QRF 2023 | 014-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing-With Suspension Order due to change in foundation to suit actual field condition - Resumption on April 1, 2024 ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 75% | 10% |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region X | Misamis Occidental | 127552 | San Vicente ES | SINACABAN | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1786838.15 | 1 | 1773076.95 | Completed | 100% | 2024-03-18 | 2024-03-26 | QRF 2023 | 022-2023 | 2023-09-09 | 2023-08-10 | 2023-08-25 | 2023-10-12 | October 27, 2027 | RJLG Construction and Supplies | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 127575 | Ozamiz Elementary School | TUDELA | 2nd | 1 | 6 | 2STY6CL | 24600000 | 1 | 23861999.87 | Ongoing | 83% | 2024-04-21 |  | QRF 2023 | 015-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-17 | Mindanao Rock | Ongoing - with liquidated damages ; already conducted coordination meeting with the concerned contractor, committed to finish the project before the opening of classes before June 16, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 82% | 1% |  |  | SHEARLINE & LPA |  |  |  | REPLACEMENT | Ongoing
QRF 2023 | Region X | Misamis Occidental | 127582 | Tudela Central School | TUDELA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 766473.74 | 1 | 758014.3 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Occidental | 304058 | Tudela National Comprehensive High School | TUDELA | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2173436.49 | 1 | 2151115.2 | Completed | 100% | 2024-01-14 | 2024-01-31 | QRF 2023 | 018-2023 | 2023-08-02 | 2023-08-10 | 2023-08-25 | 2023-09-06 | 2023-10-09 | 3R'S | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 5.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | 15 | 3STY15CL | 45000000 | 1 | 39598320.79 | Completed | 100% | September 30, 2024 |  | QRF 2023 | PB Const2023-002 | June 3,2023 | June 13,2023 | June 27,2023 | July 27,2023 | October 27, 2023 | Junjing Construction and Gen Mer. | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 100% | 0% |  | 1.25 | SHEARLINE & LPA |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region X | Misamis Oriental | 304081 | Lourdes Alubijid NHS | ALUBIJID | 2nd | 1 | 0 | Structural Assessment & Repair of 1CL TVL Bldg. | 1000000 | 1 | 835775.02 | Completed | 100% | March 1,2024 | February 25, 2024 | QRF 2023 | G2PB Repair 2023-001 | October 10,2023 | Oct 23,2023 | Nov 6,2023 | Nov 22, 2023 | Dec.19, 2023 | Tri - FB | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 8 | 2STY8CL | 24871003.7 | 1 | 21907012.66 | completed | 100% | 17‎ ‎July‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-1 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-07-10 | 2023-07-14 | G-Baron Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 11.24 | SHEARLINE & LPA |  |  |  | REPLACEMENT | completed
QRF 2023 | Region X | Oroquieta City | 304049 | Rizal NHS | OROQUIETA CITY (Capital) | 1st | 1 | 6 | 2STY6CL | 18906773.84 | 1 | 16036677.23 | Completed | 100% | ‎29‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-3 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | Completed - Subject for turn-over | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 3.24 | SHEARLINE & LPA |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st | 1 | 6 | 2STY6CL | 21824913.64 | 1 | 18973207.53 | Completed | 100% | ‎13‎ ‎January‎ ‎2024 |  | INFRA-2023-DEPEDOROQ-2 |  | 2023-04-27 | 2023-05-10 | 2023-05-22 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 8.24 | SHEARLINE & LPA |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st |  | 3 | REPAIR OF CLASSROOMS | 4793783.14 | 1 | 3817916.63 | Completed | 100% | ‎14‎ ‎December‎ ‎2023 |  | INFRA-2023-DEPEDOROQ-4 |  | 2023-04-27 | 2023-05-10 | 2023-05-23 | 2023-06-26 | 2023-07-17 | RJLG Construction | variance is subject for utilization | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 8.24 | SHEARLINE & LPA |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao City | 129652 | Alejandra L. Navarro Central Elementary School | DAVAO CITY | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 2722196.51 | 2-R | 2252300.56 | Completed | 100% | June 19, 2024 | May 14, 2024 | QRF-001-2023 | 1s2024 | Oct.27, 2023-November 16,2023 | Nov.3, 2023 | November 16, 2023 | January 16, 204 | February 20, 2024 | Panabo General Contractor & Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 100% | 0% |  | 3.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 315819 | Bango NHS | COMPOSTELA | 1st | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 6 | 18564153.25 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128267 | Mangayon ES | COMPOSTELA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2809299.4999 | 2-R | 2121007.86 | Completed | 100% | 2024-07-23 | July 23, 2024 | SDDO-017-2023-LOT1 | SDDO-017-2023-LOT1 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128270 | New Alegria ES | COMPOSTELA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 4108204.8708 | 2-R | 2755999.53 | Completed | 100% | 2024-07-23 | July 23, 2024 | SDDO-017-2023-LOT1 | SDDO-017-2023-LOT1 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128378 | Bagong Silang ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 2073961.6626 | 2-R | 1435695.91 | Completed | 100% | 2024-07-24 | July 24, 2024 | SDDO-017-2023-LOT3 | SDDO-017-2023-LOT3 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128380 | Cambagang ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 5915104.5493 | 2-R | 4071586.69 | Completed | 100% | 2024-07-24 | July 24, 2024 | SDDO-017-2023-LOT3 | SDDO-017-2023-LOT3 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128387 | Mabugnao ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 4 | 13005556.2 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128390 | Mauswagon ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 4 | 1STY4CL | 13960812.88 | 2- NC | 13939582.97 | Ongoing | 85% | April 15, 2025 | April 15, 2025 | SDDO-015-2024 | SDDO-015-2024 | June 8, 2024 | January 31, 2024 | February 12, 2024 | September 13, 2024 | October 23, 2024 | TWO DEGREES CONSTRUCTION & SUPPLY | COMPLETED | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 85% | 0% | [6 empty] | REPLACEMENT | ongoing
QRF 2023 | Region XI | Davao De Oro | 128393 | New Manay ES | MARAGUSAN (SAN MARIANO) | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 2079599.3422 | 2-R | 1462881.36 | Completed | 100% | 2024-07-24 | 2024-07-24 | SDDO-017-2023-LOT3 | SDDO-017-2023-LOT3 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 204009 | Sapawan ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 3 | 9707668.78 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128403 | Tuburan ES | MARAGUSAN (SAN MARIANO) | 1st | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 3 | 9707668.78 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128431 | Casoon ES | MONKAYO | 1st | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 3 | 10971940.01 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 304199 | Monkayo NHS | MONKAYO | 1st | 1 | 16 | REPAIR OF CLASSROOMS | 3921702.2494 | 2-R | 2761931.82 | Completed | 100% | 2024-07-26 | July 26, 2024 | SDDO-017-2023-LOT9 | SDDO-017-2023-LOT9 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 500455 | Olaycon Integrated School | MONKAYO | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 2193563.3169 | 2-R | 1590036.59 | Completed | 100% | 2024-07-23 | July 23, 2024 | SDDO-017-2023-LOT2 | SDDO-017-2023-LOT2 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 315808 | ULIP NATIONAL HIGH SCHOOL | MONKAYO | 1st | 1 | 3 | 1STY3CL | 9707668.78 | 2- NC | 9686709.35 | Completed | 100% | 2025-04-15 | April 15, 2025 | SDDO-015-2024 | SDDO-015-2024 | 2024-06-08 | 08/18/2024 | 2024-09-09 | September 13, 2024 | October 23, 2024 | TWO DEGREES CONSTRUCTION & SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | ongoing
QRF 2023 | Region XI | Davao De Oro | 315808 | ULIP NATIONAL HIGH SCHOOL | MONKAYO | 1st |  | 12 | REPAIR OF CLASSROOMS | 3289402.9498 | 2-R | 2333984.98 | Completed | 100% | 2024-07-26 | July 26, 2024 | SDDO-017-2023-LOT9 | SDDO-017-2023-LOT9 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 'January 16, 2024 | March 25, 2024 | R. FABALE CONSTRUCTION CORP | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 304202 | Montevista NHS | MONTEVISTA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 1553352.2934 | 2-R | 1149366.41 | Completed | 100% | 2024-07-23 | July 23, 2024 | SDDO-017-2023-LOT2 | SDDO-017-2023-LOT2 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128477 | Sambayon ES | MONTEVISTA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2916790.98 | 2-R | 1980451.57 | Completed | 100% | 2024-07-23 | July 23, 2024 | SDDO-017-2023-LOT2 | SDDO-017-2023-LOT2 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-25 | R. FABALE CONSTRUCTION CORP |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 304206 | New Bataan NHS | NEW BATAAN | 1st | 1 | 42 | REPAIR OF CLASSROOMS | 16725290.86 | 2-R | 10972099.93 | Completed | 100% | 2024-07-26 | September 9, 2024 | SDDO-017-2023-LOT8 | SDDO-017-2023-LOT8 | November 16, 2023 | December 04, 2023 | December 18, 2023 | 2024-01-16 | 2024-03-27 | TWO DEGREES CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 42 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 304173 | Anibongan NHS | MACO | 2nd | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 12 | 4707111.8978 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 304193 | Atty. Orlando S. Rimando NHS | MACO | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 6257681.1187 | 2-R |  | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 100% | -100% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 128345 | Bucana ES | MACO | 2nd | [6 empty] | Not yet started | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 2 | 6848897.56 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128349 | Gubatan ES | MACO | 2nd | 1 | 9 | 3-UNITS 1STY3CL | 31978668.37 | 2- NC | 31969553.96 | Completed | 100% | 2024-11-16 |  |  |  |  | January 31, 2024 | February 12, 2024 | 2024-03-22 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 12.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2023 | Region XI | Davao De Oro | 315811 | New Leyte NHS | MACO | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 1614972.4355 | 2-R | 1137605.79 | Completed | 100% | 2024-07-18 |  | SDDO-017-2023-LOT6 |  |  | December 04, 2023 | December 18, 2023 | 2024-03-11 | 2024-03-15 | DQMB CONST. & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 301526 | Pangi NHS | MACO | 2nd | [6 empty] | Not yet started | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 4 | 3095069.0163 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128362 | Taglawig ES | MACO | 2nd | 1 | 2 | 1STY2CL | 6848897.56 | 2- NC | 6827397.19 | Completed | 100% | 2025-02-19 | April 15, 2025 | SDDO-015-2024 | SDDO-015-2024 | 2024-06-08 | 08/18/2024 | September 9, 2024 | September 13, 2024 | October 23, 2024 | TWO DEGREES CONSTRUCTION & SUPPLY | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 |  |  |  |  | REPLACEMENT | ongoing
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  | 1 | 3 | 9707668.78 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  |  | 2 | 5000000 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  |  | 5 | 17524161.43 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | Not yet started | [6 empty] | January 31, 2024 | February 12, 2024 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  |  | 3 | 9707668.78 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 128484 | Bukal ES | NABUNTURAN (Capital) | 2nd | [6 empty] | Not yet started | [6 empty] | December 04, 2023 | December 18, 2023 |  |  |  | REALIGNED; Waiting for BAC Decision due to MGB findings | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% |  |  |  |  | 4 | 3892007.3359 |  | REALIGNED
QRF 2023 | Region XI | Davao De Oro | 304203 | Monkayo CES | MONKAYO WEST | 1st |  | 10 | 2STY10CL | 37496099.9 | 2-NC |  | Ongoing | 55% | July 30, 2025 |  | SDDO-029-2024-LOT4 | SDDO-029-2024-LOT4 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | ATR CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 45% | 10% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region XI | Davao De Oro | 304203 | Montevista Stand alone SHS | MONTEVISTA | 1st |  | 4 | 2STY4CL | 13964796.33 | 2-NC | 36321048.61 | Ongoing | 65% | June 30, 2025 |  | SDDO-029-2024-LOT3 | SDDO-029-2024-LOT3 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | LLM UNIFIED BUILDERS & TRADING CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 60% | 5% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region XI | Davao De Oro | 128389 | Maragusan CES | MARAGUSAN (SAN MARIANO) | 1st |  | 15 | Repair of Classrooms | 16326906.57 | 2-R | 12770470.1697 | Ongoing | 85% | May 31, 2025 |  | SDDO-029-2024-LOT1 | SDDO-029-2024-LOT1 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | DQMB CONSTRUCTION & SUPPLY CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 70% | 15% | [6 empty] | REPAIR | Ongoing
QRF 2023 | Region XI | Davao De Oro | 128439 | Pangi ES | MACO NORTH | 2nd |  | 3 | 1STY3CL | 9547895.27 | 2-NC | 14939717.0549 | Ongoing | 75% | June 30, 2025 |  | SDDO-029-2024-LOT3 | SDDO-029-2024-LOT3 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | LLM UNIFIED BUILDERS & TRADING CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 69% | 6% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region XI | Davao De Oro | 128358 | Nabunturan Comprehensive High School | NABUNTURAN WEST | 2nd |  | 10 | 2STY10CL | 36668264.18 | 2-NC | 8730320.7764 | Ongoing | 55% | July 30, 2025 |  | SDDO-029-2024-LOT2 | SDDO-029-2024-LOT2 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | ATR CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 48% | 7% | [6 empty] | REPLACEMENT | Ongoing
QRF 2023 | Region XI | Davao De Oro | 301526 | PANGI NHS | MACO NORTH | 2nd |  | 4 | Repair of Classrooms | 4807238.72 | 2-R | 4398828.6801 | Ongoing | 85% | May 31, 2025 | May 31, 2025 | SDDO-029-2024-LOT1 | SDDO-029-2024-LOT1 | November 26, 2024 | December 4, 2024 | December 16, 2024 | December 26, 2024 | January 2, 2025 | DQMB CONSTRUCTION & SUPPLY CORP. |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 76% | 9% | [6 empty] | REPAIR | Ongoing
QRF 2023 | Region XI | Davao De Oro | 502373 | Antequera Integrated School | NABUNTURAN (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3628369.14 | 2-R | 3319284.1556 | Completed | 100% | May 31, 2025 | May 31, 2025 | SDDO-017-2023-LOT9 | SDDO-029-2024-LOT1 | November 26, 2024 | December 04, 2023 | December 16, 2024 | December 26, 2024 | January 2, 2025 | DQMB CONSTRUCTION & SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2nd | 1 | 20 | REPAIR OF CLASSROOMS | 5641678.2049 | 2-R | 3893058.15 | Completed | 100% | 2024-11-01 | November 11, 2024 | SDDO-017-2023-LOT7 | SDDO-017-2023-LOT7 | November 16, 2023 | December 04, 2023 | December 18, 2023 | March 22, 2024 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY | Ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XI | Davao De Oro | 304195 | Manat NHS | NABUNTURAN (Capital) | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 4107035.1455 | 2-R | 2744050.32 | Completed | 100% | 2024-11-01 | November 11, 2024 | SDDO-017-2023-LOT7 | SDDO-017-2023-LOT7 | SDDO-017-2023-LOT7 | December 04, 2023 | December 18, 2023 | 2024-03-22 | 2024-05-16 | TWO DEGREES CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 100% | 0% |  | 12.24 |  |  |  |  | REPAIR | Completed
QRF 2023 | Region XII | North Cotabato | 130297 | Pigcawayan CES | PIGKAWAYAN | 1st | 1 | 6 | 1STY6CL | 16500000 | 2- NC | 13497000 | Completed | 100% | 2024-09-19 | 2024-09-19 | 122-2023 | 122-2023 | 2023-11-09 | 2023-11-15 | 2023-12-01 | 2024-01-25 | 2024-02-19 | CABS CONSTRUCTION | Completed subject for final inspection | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 100% | 0% |  | 9.24 |  |  |  |  | REPLACEMENT | Completed
QRF 2024 | CAR | Abra | 130933 | Talaytay Primary School | SAN QUINTIN | Lone | 1 | 1 | Repair of Classrooms | 1812258.92 | 1- R | 7659742.46 | Ongoing | 80% | 2025-06-18 |  | ITB W-12-2025 | 2024-020 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-03 | December 20, 2024 | MJTP CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 80% | 0% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 134974 | Sappaac ES | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2314415.38 | 1- R | 2015230.12 | Completed | 100% | 04/20/2025 | 04/16/2025 | infra-001-10-2024 | 001-10-2024 | 10/15/2024 | 10/21/2024 | 2024-04-11 | 2025-12-02 | December 20, 2024 | KCK Builders Corp | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 134977 | Bañacao ES | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2234552.56 | 1- R | 1571884 | Completed | 100% | 2025-10-04 | 2025-11-04 | infra-001-10-2024 | 001-10-2024 | 10/15/2024 | 10/21/2024 | 2024-04-11 | 2025-12-02 | December 20, 2024 | KCK Builders Corp | Completed with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 134982 | Patucannay ES | BANGUED (Capital) | Lone | 1 | 1 | Repair of Classrooms | 1303489 | 1- R | 1287844.35 | Completed | 100% | April 18, 2025 | March 22, 2025 | CAR-ABRA-2024-08-016 | 2024-11-018 | 10/14/2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 134988 | Bangcagan PS | BUCAY | Lone | 1 | 1 | Repair of Classrooms | 885896.4 | 1- R | 879235.36 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135001 | Pagala East PS | BUCAY | Lone | 1 | 2 | Repair of Classrooms | 3070581.61 | 1- R | 3059124.25 | Ongoing | 95% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 80% | 15% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | Lone | 1 | 1 | Repair of Classrooms | 1266246.45 | 1- R | 1256400.58 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135028 | Bulbulala ES | LA PAZ | Lone | 1 | 13 | Repair of Classrooms | 8335019.94 | 1- R | 8319974.87 | Ongoing | 85% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 80% | 5% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135036 | Manganip ES | DANGLAS | Lone | 1 | 1 | Repair of Classrooms | 865024.79 | 1- R | 855677.77 | Ongoing | 85% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 80% | 5% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 305075 | Abra HS | BANGUED (Capital) | Lone | 1 | 4 | Repair of Classrooms | 2013234.97 | 1- R | 1813060.85 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) | 1 | 9 | 7597113.07 | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | Lone | 1 | 3 | Repair of Classrooms | 2924888.53 | 1- R | 2724676.54 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135025 | Velasco ES | TAYUM | Lone | 1 | 3 | Repair of Classrooms | 2658989.57 | 1- R | 2458919.98 | Completed | 100% | May 28, 2025 |  | CAR-ABRA-2025-01-001 | 2025-02-007 | January 6, 2025 | January 15, 2025 | January 27, 2025 | February 5, 2025 | February 19, 2025 | SEMBRI CONSTRUCTION | toon es realigned to abra hs, bangued west and velazco es | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135057 | Caridad Azares ES | LAGANGILANG | Lone | 1 | 2 | Repair of Classrooms | 1747040.5 | 1- R | 1737339.99 | Ongoing | 86% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 80% | 6% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135113 | Tiempo ES | TUBO | Lone | 1 | 1 | Repair of Classrooms | 937054.79 | 1- R | 936445.49 | Ongoing | 85% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 80% | 5% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135121 | Lusuac ES | PEÑARRUBIA | Lone | 1 | 1 | Repair of Classrooms | 1234154.53 | 1- R | 1227828.31 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135128 | San Isidro CS | SAN ISIDRO | Lone | 1 | 3 | Repair of Classrooms | 2180649.37 | 1- R | 2174074.63 | Ongoing | 90% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 80% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135134 | Casilagan ES | PIDIGAN | Lone | 1 | 2 | Repair of Classrooms | 2204410.31 | 1- R | 2198427.76 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135139 | Nagdaingan ES | PIDIGAN | Lone | 1 | 2 | Repair of Classrooms | 1451566.94 | 1- R | 1451067.22 | Completed | 100% | March 4, 2025 | March 4, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135146 | Suyo Pilot ES | PIDIGAN | Lone | 1 | 3 | Repair of Classrooms | 2054760.88 | 1- R | 2047773.77 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135149 | Bolbolo ES | PILAR | Lone | 1 | 3 | Repair of Classrooms | 2207723.45 | 1- R | 2201897.52 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135175 | Bucloc CS | BUCLOC | Lone | 1 | 1 | Repair of Classrooms | 1682247.92 | 1- R | 1674306.34 | Completed | 100% | March 4, 2025 | March 04, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 77% | 23% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135183 | Dumagas ES | BOLINEY | Lone | 1 | 2 | Repair of Classrooms | 3818698.03 | 1- R | 3804323.62 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 135218 | Nangobongan PS | SAN JUAN | Lone | 1 | 1 | Repair of Classrooms | 1079165.92 | 1- R | 1069553.26 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 305085 | Dugong National High School | BUCAY | Lone | 1 | 2 | Repair of Classrooms | 1234154.53 | 1- R | 1225110.04 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 305086 | Gaddani NHS | TAYUM | Lone | 1 | 2 | Repair of Classrooms | 1787642.05 | 1- R | 1776279.96 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 305088 | Lul-luno NHS | LUBA | Lone | 1 | 1 | Repair of Classrooms | 852509.45 | 1- R | 847595 | Ongoing | 86% | March 4, 2025 |  | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 76% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | 2 | Repair of Classrooms | 3812923.03 | 1- R | 3807992.12 | Completed | 100% | April 18, 2025 | March 29, 2025 | CAR-ABRA-2024-10-016 | 2024-11-018 | October 14, 2024 | October 21, 2024 | November 04, 2024 | November 13, 2024 | November 27, 2024 | SEMBRI CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 90% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | CARAGA | Agusan del Norte | 131453 | San Isidro ES | KITCHARAO | 2nd | 1 | 7 | Repair of Classrooms | 14561894.93 | 1- R |  | Under Procurement | 0% | [10 empty] | tagbuaya es realigned to san isidro es | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) | 1 | 7 | 14561894.93 | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1st | 1 | 4 | Repair of Classrooms | 8314893.17 | 1- R |  | Ongoing | 90% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0% | 90% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131445 | Bliss Elementary School | KITCHARAO | 2nd | 1 | 5 | Repair of Classrooms | 9832308.28 | 1- R |  | Under Procurement | 0% | [10 empty] | E. G. Montilla ES realigned to bliss es | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) | 1 | 5 | 9832308.28 | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131477 | Sagbuco ES | LAS NIEVES | 1st | 1 | 3 | Repair of Classrooms | 3609571.17 | 1- R |  | Ongoing | 60% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 60% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131480 | Tinucoran ES | LAS NIEVES | 1st | 1 | 3 | Repair of Classrooms | 3608521.17 | 1- R | 2686874.46 | Ongoing | 85% |  |  | QRF REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 007 | QRF REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 007 |  |  | November 8, 2024 | November 13, 2024 | December 18, 2024 | RJB Construction and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 85% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131541 | La Paz ES | SANTIAGO | 2nd | 1 | 1 | Repair of Classrooms | 1517415.11 | 1- R | 1236244.6 | Ongoing | 78% | May 14, 2025 |  | QRF REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 004 | QRF REPAIR 2024 - R XIII - AGUSAN DEL NORTE - 004 |  |  |  | February 18, 2025 | February 28, 2025 | LGTD Company OPC |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 78% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 131549 | Bagang ES | BUENAVISTA | 2nd | 1 | 3 | Repair of Classrooms | 8457296.24 | 1- R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 304683 | Guinabsan National High School - Simbalan National High School Annex | BUENAVISTA | 2nd | 1 | 2 | Repair of Classrooms | 2834759.63 | 1- R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Agusan del Norte | 317301 | Guinabsan National High School - Sangay National High School Annex | BUENAVISTA | 2nd | 1 | 4 | Repair of Classrooms | 9345844.95 | 1- R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bayugan City | 131598 | Gethsemane ES | CITY OF BAYUGAN | 1st | 1 | 3 | Repair of Classrooms | 3609571.17 | 1- R | 3609571.17 | Ongoing | 80% | June 30, 2025 | - | QRF-REPAIR 2024-RXIII-BAYUGAN CITY-009 | QRF-REPAIR 2024-RXIII-BAYUGAN CITY-009 | December 2, 2024 | December 3, 2024 | December 23, 2024 | December 26, 2024 | January 8, 2025 | ALCT CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 80% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132608 | Bebiano Alba Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 443180.99 | 1- R | 441862.82 | COMPLETED | 100% | November 4, 2025 | 2025-03-28 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 215612.47 | 1- R | 214859.6 | COMPLETED | 100% | 2025-05-31 | 2025-05-28 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 72% | 28% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132610 | Bucto Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 7644763.4 | 1- R | 442038.54 | COMPLETED | 100% | November 4, 2025 | 2025-03-28 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132611 | Burboanan Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 655408.84 | 1- R | 654212.19 | COMPLETED | 100% | 2025-05-31 | 2025-05-27 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 59% | 41% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132612 | Caguyao Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 7333326.75 | 1- R | 223314.49 | COMPLETED | 100% | November 4, 2025 | 2025-03-28 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 65% | 35% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132613 | Coleto Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 428772.05 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 84% | 16% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132615 | F. C. Pedraverde-Lindo Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435444.72 | 1- R | 434413.83 | COMPLETED | 100% | 2025-05-31 | 2025-05-30 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132616 | Maharlika Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 427087.11 | COMPLETED | 100% | November 4, 2025 | July 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132617 | Gerardo D. Verano Jr. Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 234381.7 | 1- R | 232280.97 | COMPLETED | 100% | January 5, 2025 | 2025-04-23 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 71% | 29% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132618 | Isabelo Landeta Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 436939.23 | 1- R | 436084.86 | COMPLETED | 100% | 2025-05-31 | 2025-05-28 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 59% | 41% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132619 | Mabog Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 447840.33 | 1- R | 446745.08 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132622 | Mantuyom Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 874669.67 | 1- R | 872863.55 | COMPLETED | 100% | November 4, 2025 | July 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 85% | 15% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132623 | Ser-Fel Mone Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 653123.13 | 1- R | 652420.61 | COMPLETED | 100% | 2025-05-31 | 2025-05-30 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 57% | 43% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132624 | Olayvar Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 437554.61 | 1- R | 435387.95 | COMPLETED | 100% | January 5, 2025 | 2025-04-25 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 81% | 19% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132627 | Puerto Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 438257.91 | 1- R | 429282.38 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132628 | R. Castillo Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 433334.83 | 1- R | 432366.6 | COMPLETED | 100% | 2025-05-31 | 2025-05-27 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 90% | 10% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132631 | San Fernando Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 431664.5 | 1- R | 430982.92 | COMPLETED | 100% | 2025-05-31 | 2025-05-28 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 61% | 39% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132632 | San Isidro Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 651013.24 | 1- R | 650478.66 | COMPLETED | 100% | 2025-05-31 | 2025-05-28 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 62% | 38% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132633 | Gaspar Serrano Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 448279.89 | 1- R | 445531.5 | COMPLETED | 100% | January 5, 2025 | 2025-04-25 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 75% | 25% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 434917.25 | 1- R | 429020.2 | COMPLETED | 100% | November 4, 2025 | July 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132638 | SIMON EDGAR A. GARAY ES | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 648903.35 | 1- R | 647637 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132639 | Sote Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 660156.1 | 1- R | 659585.76 | COMPLETED | 100% | 2025-05-31 | 2025-05-27 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 90% | 10% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132833 | Mangagoy Central Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435708.46 | 1- R | 435198.86 | COMPLETED | 100% | 2025-05-31 | 2025-05-30 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 66% | 34% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132834 | Mangagoy East Elementary School | CITY OF BISLIG | 2nd | 1 | 5 | Repair of Classrooms | 1081271.15 | 1- R | 1079250.33 | COMPLETED | 100% | 2025-05-31 | 2025-05-27 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 61% | 39% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132837 | Mangagoy South Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 435972.19 | 1- R | 435171.51 | COMPLETED | 100% | 2025-05-31 | 2025-05-28 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 57% | 43% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132839 | Espiritu Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 438961.2 | 1- R | 436266.85 | COMPLETED | 100% | January 5, 2025 | 2025-04-29 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 75% | 25% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132840 | Labisma Elementary School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 875900.44 | 1- R | 873565.55 | COMPLETED | 100% | January 5, 2025 | 2025-04-25 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132841 | Lawigan Elementary School | CITY OF BISLIG | 2nd | 1 | 3 | Repair of Classrooms | 666573.68 | 1- R | 664525.12 | COMPLETED | 100% | January 5, 2025 | 2025-04-29 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132842 | Paler Lumayog Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 437202.96 | 1- R | 435176.18 | COMPLETED | 100% | January 5, 2025 | 2025-04-23 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132843 | Plaza Central Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 221458.62 | 1- R | 219440.92 | COMPLETED | 100% | January 5, 2025 | 2025-04-23 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 132844 | Requina Elementary School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 436851.31 | 1- R | 434665.95 | COMPLETED | 100% | January 5, 2025 | 2025-04-29 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 235001 | P. M. Clar Elementary School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 233063.02 | 1- R | 230609.86 | COMPLETED | 100% | January 5, 2025 | 2025-04-29 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 77% | 23% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 235004 | New Jerusalem Elementary School | CITY OF BISLIG | 2nd | 1 | 6 | Repair of Classrooms | 1302273 | 1- R | 1300032.87 | COMPLETED | 100% | January 5, 2025 | 2025-04-23 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 75% | 25% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 304865 | Bislig City National High School | CITY OF BISLIG | 2nd | 1 | 8 | Repair of Classrooms | 1721031.65 | 1- R | 1717351.44 | COMPLETED | 100% | 2025-05-31 | 2025-05-30 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 61% | 39% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 304867 | Mone National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 224008.07 | 1- R | 223292.71 | COMPLETED | 100% | 2025-05-31 | 2025-05-27 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 90% | 10% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 304868 | San Vicente National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 440104.06 | 1- R | 436695.71 | COMPLETED | 100% | November 4, 2025 | July 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 304918 | Danipas National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 439049.12 | 1- R | 436873.59 | COMPLETED | 100% | January 5, 2025 | 2025-04-25 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322501 | San Jose National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 233766.31 | 1- R | 231654.35 | COMPLETED | 100% | January 5, 2025 | 2025-04-29 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 74% | 26% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322502 | Tumanan National High School | CITY OF BISLIG | 2nd | 1 | 2 | Repair of Classrooms | 446873.29 | 1- R | 435368.52 | COMPLETED | 100% | November 4, 2025 | 2025-03-28 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322504 | San Isidro National High School | CITY OF BISLIG | 2nd | 1 | 4 | Repair of Classrooms | 866318.02 | 1- R | 865392.85 | COMPLETED | 100% | 2025-05-31 | 2025-05-30 | INFRA_2024_005 | INFRA_2024_005 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | MCLA Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 60% | 40% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 232711.37 | 1- R | 230109.14 | COMPLETED | 100% | November 4, 2025 | July 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322506 | Coleto National High School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 220491.59 | 1- R | 209688.01 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322507 | Labisma National High School | CITY OF BISLIG | 2nd | 1 | 5 | Repair of Classrooms | 1086944.78 | 1- R | 1084170.22 | COMPLETED | 100% | January 5, 2025 | 2025-04-23 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 76% | 24% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 322508 | San Fernando Integrated School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 216975.11 | 1- R | 207536.83 | COMPLETED | 100% | November 4, 2025 | February 4, 2025 | INFRA_2024_007 | INFRA_2024_007 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | SVTS Builders & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 85% | 15% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Bislig City | 501292 | Pamaypayan Integrated School | CITY OF BISLIG | 2nd | 1 | 1 | Repair of Classrooms | 241502.58 | 1- R | 239179.57 | COMPLETED | 100% | January 5, 2025 | 2025-04-25 | INFRA_2024_006 | INFRA_2024_006 | 2024-11-25 | February 12, 2024 | 2024-12-16 | 2024-12-20 | 2024-12-23 | AACAD Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 70% | 30% |  |  | TD KABAYAN |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Dinagat Island | 132515 | Cuarenta Elementary School | SAN JOSE (Capital) | Lone | 1 | 2 | 1STY2CL WITH COMMON TOILET | 8801976.29 | 1- NC | 6679436.19 | Ongoing | 82% |  | - | INFRA2024-002 | INFRA2024-002 | August 8, 2024 | August 20, 2w024 | September 4, 2024 | October 19, 2023 | October 28, 2024 | ARDRAW |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 82% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Dinagat Island | 304836 | Melgar NHS | BASILISA (RIZAL) | Lone | 1 | 2 | Repair of Classrooms | 2455106.77 | 1- R | 1841257.65 | completed | 100% | January 25, 2025 | December 5, 2024 | INFRA2024-004 | INFRA2024-004 | August 8, 2024 | August 20, 2w024 | September 4, 2024 | October 19, 2023 | October 28, 2024 | WINDAFALL |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 | Fire |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Siargao | 132148 | Consuelo Elementary School | GENERAL LUNA | 1st | 1 | 6 | Repair of Classrooms | 18279803.53 | 1- R | 2229412.01 | Ongoing | 95% | December 17, 2024 | - | BEFF-INFRA2024-007 | BEFF-INFRA2024-007 | September 5, 2024 | September 19, 2025 | September 23, 2025 | October 10, 2024 | October 18, 2024 | RBEP CONSTRUCTION | for punch listing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 95% | 0% |  |  | SHEARLINE |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Siargao | 132174 | Mabuhay Primary School | DEL CARMEN | 1st | 1 | 6 | Repair of Classrooms | 10467818.59 | 1- R | 8005027.61 | Ongoing | 95% | January 16, 2025 | - | BEFF-INFRA2024-006 | BEFF-INFRA2024-006 | September 5, 2024 | September 19, 2025 | September 23, 2025 | October 10, 2024 | October 18, 2024 | RBEP CONSTRUCTION | for punch listing | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 95% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Surigao del Sur | 132644 | Bacolod Elementary School | CAGWAIT | 1st | 1 | 4 | 2-UNITS 1STY2CL | 12710324.73 | 1- NC | 6,336,697.28 | Ongoing | 74.83% | May 26, 2025 | - | QRF 2024 - R XIII - SURIGAO DEL SUR - 001 and 002 | 001 - 2025 | October 18, 2024 | October 25, 2024 | November 7, 2024 | November 20, 2024 | January 20, 2025 | TRIDENT ENGINEERING SERVICES; CYL CONSTRUCTION & SUPPLY | Requested for Contract Time Extension due to Unfavorable Weather Condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 40% | 34.83% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Surigao del Sur | 132644 | Bacolod Elementary School | CAGWAIT | [6 empty] | 6335565.88 | Ongoing | 85.03% | June 02, 2025 |  |  | 002 - 2025 |  |  |  |  | January 27, 2025 | [12 empty] | 40%
QRF 2024 | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2nd | 1 | 8 | 2-UNITS 1STY2CL | 19938649.56 | 1- NC | 9,689,479.13 | Ongoing | 25% | June 25, 2025 | - | QRF 2024 - R XIII - SURIGAO DEL SUR - 003 and 004 | 003 - 2025 | October 18, 2024 | October 25, 2024 | November 7, 2024 | November 20, 2024 | January 20, 2025 | ETP BUILDERS; J-R3 CONSTRUCTION & SUPPLY | Requested for Contract Time Extension due to Unfavorable Weather Condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 16% | 9% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | [6 empty] | 9714500.55 | Ongoing | 30.17% | July 02, 2025 |  |  | 004 - 2025 |  |  |  |  | January 27, 2025 | [12 empty] | 16%
QRF 2024 | CARAGA | Surigao del Sur | 500584 | Sta. Maria Integrated School | TAGBINA | 2nd | 1 | 4 | 1STY4CL | 9956134.23 | 1- NC | 9872544.27 | Ongoing | 40.32% | June 25, 2025 | - | QRF 2024 - R XIII - SURIGAO DEL SUR - 005 | 005 - 2025 | October 18, 2024 | October 25, 2024 | November 7, 2024 | November 20, 2024 | January 20, 2025 | ILMAR CONSTRUCTION AND SUPPLY | Requested for Contract Time Extension due to Unfavorable Weather Condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 19% | 21.32% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132957 | Awasian Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 11289692.93 | 1- NC |  | Under Procurement | 0% | [10 empty] | ONGOING PROCUREMENT | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132977 | San Jose Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 11289692.93 | 1- NC |  | Under Procurement | 0% | [10 empty] | for realignment san jose to quintos (awaiting approval) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 10656067.46 | 1- NC | 10122191.88 | Ongoing | 60% | July 25, 2025 | NA | QRF2024-001 | QRF2024-001 | November 6, 2024 | November 18, 2024 | December 2, 2024 | December 18, 2024 | January 22, 2025 | Trident Engineering Services |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 60% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1st | 1 | 2 | Repair of Classrooms | 2794585.69 | 1- R | 1927574.12 | Ongoing | 60% | April 26, 2025 | NA | QRF2024-005 | QRF2024-005 | November 6, 2024 | November 14, 2024 | November 28, 2024 | December 12, 2024 | January 22, 2025 | Melroshean Construction Corporation | with approved time extension due to weather condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 60% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Tandag City | 501274 | Meliton M. Ajos Memorial Integrated School | CITY OF TANDAG (Capital) | 1st | 1 | 3 | 1STY3CL WITH COMMON TOILET | 10821883.46 | 1- NC | 7704691.29 | Ongoing | 30% | July 25, 2025 | NA | QRF2024-002 | QRF2024-002 | November 6, 2024 | November 18, 2024 | December 2, 2024 | December 18, 2024 | January 22, 2025 | CYL Construction and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 30% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | CARAGA | Tandag City | 132971 | Quezon Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | Repair of Classrooms | 9445989.04 | 1- R | 1927574.12 | Ongoing | 60% | April 26, 2025 | NA | QRF2024-006 | QRF2024-006 | November 6, 2024 | November 14, 2024 | November 28, 2024 | December 12, 2024 | January 22, 2025 | Melroshean Construction Corporation | with approved time extension due to weather condition | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 60% | 0% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | CARAGA | Tandag City | 502042 | Rosario Integrated School | CITY OF TANDAG (Capital) | 1st | 1 | 4 | Repair of Classrooms | 7882447.55 | 1- R | 5222226.46 | Completed | 100% | May 26, 2025 | NA | QRF2024-003 | QRF2024-003 | November 6, 2024 | November 18, 2024 | December 2, 2024 | December 18, 2024 | January 22, 2025 | Trident Engineering Services | with approved time extension due to weather condition | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.25 | EARTHQUAKE (Hinatuan) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 100079 | Magnuang ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 565554.92 | 1- R | 565543.22 | Completed | 100% | 2025-10-04 | 2/18/2025 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 100081 | Naguirangan-Capacuan ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4571722.38 | Ongoing | 90% | 6/19/2025 |  | 2024-002 | 24010 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,716,826.42) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Deped Building 2 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 75% | 15% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100085 | Quiling Elementary School | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4571722.38 | Ongoing | 90% | 6/19/2025 |  | 2024-002 | 24009 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,716,826.42) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Bagong Lipunan School Building - 3 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 75% | 15% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100086 | Sumader ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 261960.82 | 1- R | 261825.01 | Completed | 100% | 2025-10-04 | 1/28/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 100087 | Tabug ES | CITY OF BATAC | 2nd | 1 | 2 | 1STY2CL | 6288548.8 | 1- NC | 4681175.28 | Ongoing | 90% | 6/19/2025 |  | 2024-002 | 24008 | August 30, 2024 | Sept. 12, 2024 | Sept. 24, 2024 | Oct. 14, 2024 | Oct. 28, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 1,607,373.52) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of Marcos Pre-Fab School Building 2 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 75% | 15% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100089 | Baay ES | CITY OF BATAC | 2nd | 1 | 3 | 1STY3CL | 8630843.3 | 1- NC | 6084631.32 | Ongoing | 50% | 8/18/2025 |  | 2024-003 | 24013 | Oct. 07, 2024 | Oct. 16, 2024 | Oct. 28, 2024 | Dec. 18, 2024 | Dec. 26, 2024 | VCD Construction | Time Suspension and Extension was given due to the processing of the building permit and variation order, Savings (Php 2,546,211.98) from the project was requested and approved on March 26, 2025, to fund the project, Repair and Rehabilitation of 12 Classrooms of the same school which is now currently ongoing. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 40% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Batac City | 100091 | Baoa ES | CITY OF BATAC | 2nd | 1 | 1 | Repair of Classrooms | 220610.27 | 1- R | 220610.27 | Completed | 100% | 2025-10-04 | 1/28/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Batac City | 100093 | Biningan ES | CITY OF BATAC | 2nd | 1 | 3 | Repair of Classrooms | 800478.7 | 1- R | 800457.18 | Completed | 100% | 2025-10-04 | 3/18/2025 | 2024-006 | 24015 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | ADG Builders, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Batac City | 300005 | Batac National High School | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 362703.34 | 1- R | 362701.66 | Completed | 100% | 2025-10-04 | 2025-09-05 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 90% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2nd | 1 | 2 | Repair of Classrooms | 674429.08 | 1- R | 673921.61 | Completed | 100% | 2025-10-04 | 2025-09-05 | 2024-006 | 24014 | Nov. 28, 2024 | Dec. 06, 2024 | Dec. 18, 2024 | Dec. 23, 2024 | Dec. 26, 2024 | Martin Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 90% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region I | Ilocos Norte | 100053 | Nagbalagan ES | BANGUI | 1st | 1 | 4 | 2-UNITS 1STY2CL | 11671993.99 | 1- NC | 8642482.64 | Ongoing | 65% | 7/16/2025 |  | PB-07-2024-Lot 1 | PB-07-2024-Lot 1 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | Caixia Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 65% | 0% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100062 | Bugasi ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC | 6468375.49 | Ongoing | 90% | 4/17/2025 |  | PB-07-2024-Lot 2 | PB-07-2024-Lot 2 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | LAV Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 80% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 2 | Repair of Classrooms | 485255.7 | 1- R | 480277.72 | Completed | 100% | 3/30/2025 | 2025-01-04 | PB-14-2024-1 | PB-14-2024-1 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0% | 100% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | reverted
QRF 2024 | Region I | Ilocos Norte | 100074 | VALDEZ ELEMENTARY SCHOOL | BANNA (ESPIRITU) | 2nd | 1 | 3 | 1STY3CL | 8575310.14 | 1- NC | 6558696.85 | Ongoing | 90% | 4/17/2025 |  | PB-07-2024-Lot 3 | PB-07-2024-Lot 3 | 2024-04-09 | 2024-10-09 | 9/23/2024 | 10/28/2024 | 11/18/2024 | Caixia Construction | With request for time extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 70% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | Repair of Classrooms | 443145.15 | 1- R | 438234.61 | completed | 100% | 3/30/2025 | 3/28/2025 | PB-14-2024-2 | PB-14-2024-2 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 2 | Repair of Classrooms | 637304.27 | 1- R | 632134.73 | completed | 100% | 3/30/2025 | 3/28/2025 | PB-14-2024-2 | PB-14-2024-2 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1st | 1 | 5 | Repair of Classrooms | 859025.56 | 1- R | 853025.56 | Completed | 100% | 2025-10-03 | 2025-01-04 | PB-14-2024-3 | PB-14-2024-3 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 80% | 20% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2nd | 1 | 4 | Repair of Classrooms | 632738.78 | 1- R | 627346.34 | Completed | 100% | 3/30/2025 | 2025-01-04 | PB-14-2024-1 | PB-14-2024-1 | 11/29/2024 | 2024-05-12 | 12/18/2024 | 1/20/2025 | 1/29/2025 | LAV Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 100% | 0% |  | 4.25 | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1st | 1 | 4 | Repair of Classrooms | 839105.83 | 1- R |  | Not yet started | 0% | [10 empty] | Deffered due to the issuance of Notice of Prohibited Use by the LGU | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region I | Laoag City | 500742 | San Mateo Integrated School | LAOAG CITY (Capital) | 1st | 1 | 6 | Repair of Classrooms | 1234766.65 | 1- R | 1202187.77 | Completed | 100% | MAr.03,2025 | April 15,2025 | 2024-PB1-002 | 2024-pb1-002 | Oct.04,2024 | Oct.11,2024 | Oct.28,2024 | Nov.25,2025 | Dec.03,2024 | Elocin Construction | Punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 90% | 10% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region II | Cagayan | 300438 | Cabatacan National High School | LASAM | 2nd | 1 | 21 | Repair of Classrooms | 9077261.28 | 1- R | 5702445.94 | Ongoing | 95% | June 25,2025 |  | Repair/Rehabilitation of school building | INFRA2024-090 | August 30,2024 | September 9,2024 | September 23,2024 | OCTOBER 14,2024 | OCTOBER 22,2024 | GCPK CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 90% | 5% |  |  | EARTHQUAKE (Ilocos Norte) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region IX | Zamboanga Del Norte | 124575 | Lingasad ES | POLANCO | 1st | 1 | 6 | 2STY6CL with PWD ramp with handrails, parapet all on concrete gutter and complete with Electrical works, Sanitary/plumbing works, Ventilation, Water pumping and Fire protection systems | 24877957.84 | 1- NC | 24837942.65 | Ongoing | 75% | 2025-05-10 | - | 2024-049-CBZN | CB-2024-043 | 2024-07-24 | Aug. 01, 2024 | Aug. 14, 2024 | Sept. 5, 2024 | Sept. 10, 2024 | YSL BUILDERS | With Approved Time Extension | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 70% | 5% |  |  | Fire |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | Region VI | Iloilo | 116055 | Salihid ES | BAROTAC NUEVO | 4th | 1 | 2 | 1STY2CL | 9475815.29 | 1- NC | 6702484.43 | Ongoing | 87% | 2025-08-06 |  | QRF2024-RVI-022-ILOILO-L1 | QRF2024-RVI-022-ILOILO-L1 | 2024-08-08 | 2024-08-14 | 2024-08-30 | 2024-09-11 | 2024-12-06 | EARLY RISER CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 83% | 4% |  |  | Fire |  |  |  | REPLACEMENT | ongoing
QRF 2024 | Region VII | Negros Oriental | 120356 | Dahile ES | MABINAY | 2nd | 1 | 8 | 2-UNITS 1STY4CL with Common Toilet | 26312604.57 | 1- NC | 24508091.67 | Ongoing | 45% | 2026-02-15 |  | ITB2024-07-143 | QRF202409029 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-19 | 2024-10-11 | TRINITYCAD Corporation | None | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 40% | 5% |  |  | Fire |  |  |  | REPLACEMENT | ONGOING
QRF 2024 | Region VII | Negros Oriental | 120474 | Palayuhan ES | SIATON | 3rd | 1 | 7 | Repair of Classrooms | 1801517.91 | 1- R | 1329769.5 | Completed | 100% | 2025-01-10 | 2025-01-10 | ITB2024-07-144 | QRF202409030 | 2024-08-08 | 2024-08-16 | 2024-08-28 | 2024-09-19 | 2024-10-11 | MCS-9 Construction | with approved time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 100% | 0% |  | 1.25 | TD KABAYAN |  |  |  | REPAIR | Completed
QRF 2024 | Region VIII | Calbayog City | 502375 | Himalandrog Seven-Hills Integrated School | CALBAYOG CITY | 1st | 1 | 8 | 2-UNITS 1STY4CL WITH COMMON TOILET, PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM & SITE DEVELOPMENT | 43063753.9 | 1- NC | 43050034.22 | Ongoing | 30% | 2025-12-07 | ONGOING | 2024(RVIII-CALB)-QRF | 2024-024 | 2024-08-07 | 2024-08-15 | 2024-08-27 | 2024-09-16 | 2024-11-15 | JFR Construction Inc. | On going Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 30% | 0% |  |  | Fire |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region VIII | Southern Leyte | 122194 | San Joaquin Elementary School | MACROHON | 1st | 1 | 9 | Repair of Classrooms | 5624065.38 | 1- R | 4442556.41 | Completed | 100% | 2025-04-26 | 2025-04-04 | CY2024-QRF-Repair -B1-L1 | CY2024-QRF-Repair -B1-L1 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 100% | 0% |  | 4.25 | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122198 | Villa Jacinta Elementary School | MACROHON | 1st | 1 | 12 | Repair of Classrooms | 7349218.58 | 1- R | 6088992.84 | Completed | 100% | 2025-05-11 | 2025-04-11 | CY2024-QRF-Repair -B1-L2 | CY2024-QRF-Repair -B1-L2 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 90% | 10% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122216 | Tigbawan Elementary School | MALITBOG | 1st | 1 | 5 | Repair of Classrooms | 3118839.65 | 1- R | 2463791.18 | Completed | 100% | 2025-03-12 | 2025-03-12 | CY2024-QRF-Repair -B1-L3 | CY2024-QRF-Repair -B1-L3 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 100% | 0% |  | 4.25 | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122236 | Kinachawa Elementary School | SAN RICARDO | 2nd | 1 | 8 | Repair of Classrooms | 5001198.13 | 1- R | 3946273.17 | Completed | 100% | 2025-04-26 | 2025-04-11 | CY2024-QRF-Repair -B1-L4 | CY2024-QRF-Repair -B1-L4 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 95% | 5% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122240 | Pinut-an Elementary School | SAN RICARDO | 2nd | 1 | 15 | Repair of Classrooms | 9003187.23 | 1- R | 5697169.02 | Completed | 100% | 2025-05-26 | 2025-05-15 | CY2024-QRF-Repair -B1-L5 | CY2024-QRF-Repair -B1-L5 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 80% | 20% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122270 | Mac Elementary School | SOGOD | 2nd | 1 | 13 | Repair of Classrooms | 7761485.49 | 1- R | 6438909.96 | Completed | 100% | 2025-05-11 | 2025-04-10 | CY2024-QRF-Repair -B1-L6 | CY2024-QRF-Repair -B1-L6 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 95% | 5% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122271 | Magatas Elementary School | SOGOD | 2nd | 1 | 7 | Repair of Classrooms | 4199183.59 | 1- R | 3490366.11 | Completed | 100% | 2025-03-27 | 2025-03-21 | CY2024-QRF-Repair -B1-L7 | CY2024-QRF-Repair -B1-L7 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Bench Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 95% | 5% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2nd | 1 | 9 | Repair of Classrooms | 5721707.02 | 1- R | 5700717.97 | Completed | 100% | 2025-04-26 | 2025-05-16 | CY2024-QRF-Repair -B1-L8 | CY2024-QRF-Repair -B1-L8 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Bench Construction | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 80% | 20% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 303478 | Pinut-an National High School | SAN RICARDO | 2nd | 1 | 16 | Repair of Classrooms | 9707352.08 | 1- R | 6111355.94 | Completed | 100% | 2025-05-26 | 2025-05-15 | CY2024-QRF-Repair -B1-L9 | CY2024-QRF-Repair -B1-L9 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 80% | 20% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO | 2nd | 1 | 14 | Repair of Classrooms | 8399226.38 | 1- R | 5625583.19 | Completed | 100% | 2025-05-21 | 2025-05-15 | CY2024-QRF-Repair -B1-L10 | CY2024-QRF-Repair -B1-L10 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 95% | 5% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 303449 | Consolacion National High School | SOGOD | 2nd | 1 | 8 | Repair of Classrooms | 4879554.1 | 1- R | 3442383.46 | Completed | 100% | 2025-03-27 | 2025-03-21 | CY2024-QRF-Repair -B1-L11 | CY2024-QRF-Repair -B1-L11 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 98% | 2% |  |  | SHEARLINE |  |  |  | REPAIR | Ongoing
QRF 2024 | Region X | Bukidnon | 126484 | Sagasaan ES | KITAOTAO | 3rd | 1 | 2 | 1STY2CL | 6599650.8 | 1- NC | 5741696.19 | Ongoing | 75% | Revised date March 16, 2025 |  | PB-02-07-2024-011 | 045-2024 | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-08-14 | 2024-09-16 | IM and M Construction | with approved extension No's 1&2 and variation order no.1. Impose Liquidation damage (LD) during progress billing. Tentative date completion July 31, 2025 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 50% | 25% |  |  | EARTHQUAKE (Hinatuan) |  |  |  | REPLACEMENT | ongoing
QRF 2024 | Region XI | Davao Occidental | 129064 | Mangahos PS | SARANGANI | Lone | 1 | 2 | 1STY2CL | 5650766.5 | 1- NC | 5649035.38 | Ongoing | 70% | 2025-06-18 |  | ITB W-13-2025 | 2024-021 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-03 | December 20, 2024 | MJTP CONSTRUCTION | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 30% | 40% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | Region XI | Davao Occidental | 304283 | Kalbay National High School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 3 | 1STY3CL | 7661049.91 | 1- NC | 7659742.46 | Ongoing | 75% | 2025-06-18 |  | ITB W-12-2025 | 2024-020 | 2025-11-11 | 2025-11-18 | 2025-11-25 | 2025-12-03 | December 20, 2024 | MJTP CONSTRUCTION |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 45% | 30% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | Region XI | Island Garden City of Samal | 128690 | Kaputian Central Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 3 | Repair of Classrooms | 3769336.35 | 1- R | 2015230.12 | Completed | 100% | 04/20/2025 | 04/16/2025 | infra-001-10-2024 | 001-10-2024 | 10/15/2024 | 10/21/2024 | 2024-04-11 | 2025-12-02 | December 20, 2024 | KCK Builders Corp | On-Going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region XI | Island Garden City of Samal | 128733 | Limao Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd |  | 3 | Repair of Classrooms | 2223978.46 | 1- R | 1571884 | Completed | 100% | 2025-10-04 | 2025-11-04 | infra-001-10-2024 | 001-10-2024 | 10/15/2024 | 10/21/2024 | 2024-04-11 | 2025-12-02 | December 20, 2024 | KCK Builders Corp | Completed with time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 100% | 0% |  | 4.25 | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region XII | General Santos City | 131278 | Labangal Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 4 | 1STY4CL | 11239295.18 | 1- NC | 11239295.18 | Ongoing | 20% | 150CD |  | 003-2025 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-02-24 | LEIGHCHEEN CONSTRUCTION CORPORATION | On-Going Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 20% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | Region XII | General Santos City | 131314 | Pedro Acharon Sr. Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 1 | Repair of Classrooms | 348546.5 | 1- R | 348546.5 | Ongoing | 75% | 50CD |  | 004-2025- Lot 1 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-03-26 | BEBCON BUILDERS AND SUPPLY | On-Going Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 75% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region XII | General Santos City | 304637 | Datu Andiam Manza National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 20 | Repair of Classrooms | 190230.76 | 1- R | 190230.76 | Ongoing | 85% | 45CD |  | 004-2025- Lot 2 |  | 2025-01-08 | 2025-01-08 | 2025-01-21 | 2025-02-04 | 2025-03-26 | BEBCON BUILDERS AND SUPPLY | On-Going Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 85% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Ongoing
QRF 2024 | Region XII | North Cotabato | 130197 | DILANGALEN CENTRAL ELEMENTARY SCHOOL | MIDSAYAP | 1st | 1 | 3 | 1STY3CL | 11342818.56 | 1- NC | 8847398.47 | Ongoing | 55% | 2025-01-08 |  | 2024074 | 2024074 | 2024-09-13 | 2024-09-23 | 2024-10-07 | 2024-11-11 | 2024-11-29 | CLA Construction Incorporated | On-Going Construction | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 45% | 10% |  |  | SHEARLINE |  |  |  | REPLACEMENT | Ongoing
QRF 2024 | Region XII | Sarangani | 130443 | Baliton Elementary School | GLAN | Lone | 1 | 2 | 1STY2CL | 4892845.52 | 1- NC |  | Ongoing | 1.08% |  |  |  |  | 2024-12-13 |  | January 28,2025 |  |  |  | CONTRACT TO BE AWARDED AFTER LIFTING ELECTION BAN | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 1.08% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 130450 | Calatungan ES | GLAN | Lone | 1 | 5 | Repair of Classrooms | 6875408.92 | 1- R |  | Ongoing | 2.26% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | CONTRACT TO BE AWARDED AFTER LIFTING ELECTION BAN | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 1.08% | 1.18% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 130467 | Macatimbol ES | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1015687.2 | 1- R |  | Ongoing | 2.03% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | CONTRACT TO BE AWARDED AFTER LIFTING ELECTION BAN | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 2.03% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 130474 | Pangyan Central ES | GLAN | Lone | 1 | 5 | Repair of Classrooms | 5671478.61 | 1- R |  | Ongoing | 2.27% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | CONTRACT TO BE AWARDED AFTER LIFTING ELECTION BAN | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 2.26% | 0.01% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 130487 | Bocay- Il ES | KIAMBA | Lone | 1 | 2 | 1STY2CL | 4916342.86 | 1- NC |  | Not yet started | 21.82% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 21.82% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 130560 | Lun Padidu Central Elementary School | MALAPATAN | Lone | 1 | 6 | 2-UNITS 1STY3CL | 15224946.67 | 1- NC |  | Not yet started | 60% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0% | 60% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 130563 | Mama Nawa Elementary School | MALAPATAN | Lone | 1 | 10 | Repair of Classrooms | 13605574.34 | 1- R |  | Not yet started | [7 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 130582 | Talus ES | MALUNGON | Lone | 1 | 9 | Repair of Classrooms | 14907576.67 | 1- R |  | Not yet started | [7 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 304541 | Pangyan National High School | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1188056.38 | 1- R |  | Not yet started | 0% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 316604 | Amado M. Quirit Sr National High School | MALAPATAN | Lone | 1 | 7 | Repair of Classrooms | 1475383.74 | 1- R |  | Not yet started | 0% |  |  |  |  | 2025-04-15 | [5 empty] | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 500260 | Lumigo Integrated School | GLAN | Lone | 1 | 9 | 3-UNITS 1STY3CL | 27304958.65 | 1- NC |  | Not yet started | 2.03% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 2.03% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 500261 | Roque Adarna Integrated School | GLAN | Lone | 1 | 6 | 2-UNITS 1STY3CL | 15224946.67 | 1- NC |  | Ongoing | [5 empty] | 2025-02-05 |  | February 25,2025 |  |  |  | BID EVALUATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 500267 | Mangelen IS | MAASIM | Lone | 1 | 4 | Repair of Classrooms | 5121274.06 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-08 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 500285 | Tagaytay Integrated School | ALABEL (Capital) | Lone | 1 | 2 | Repair of Classrooms | 621384.02 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 500288 | Kinabalan Integrated School | MALUNGON | Lone | 1 | 2 | Repair of Classrooms | 684829.83 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 500707 | Tonga Lim Siao Sr. Integrated School | GLAN | Lone | 1 | 6 | Repair of Classrooms | 6696299.07 | 1- R |  | Ongoing | 2.27% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | BID EVALUATION | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 2.27% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 500829 | Panambalan Integrated School | GLAN | Lone | 1 | 7 | Repair of Classrooms | 13029145.87 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-08 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 501281 | Prudencio Mariano Sr. Integrated School | GLAN | Lone | 1 | 5 | 1STY3CL 1STY2CL | 12309649.43 | 1- NC |  | Ongoing | 21.82% |  |  |  |  | 2025-02-05 |  | February 25,2025 |  |  |  | CONTRACT TO BE AWARDED AFTER LIFTING ELECTION BAN | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 21.82% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sarangani | 502228 | CALONKAMBING INTEGRATED SCHOOL | GLAN | Lone | 1 | 2 | Repair of Classrooms | 1010642.25 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | Lone | 1 | 16 | Repair of Classrooms | 437548.03 | 1- R |  | Not yet started | 0% | [6 empty] | 2025-04-15 |  |  |  | BID EVALUATION | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | South Cotabato | 130693 | Ubo Elementary School | LAKE SEBU | 2nd | 1 | 4 | 2-UNITS 1STY2CL | 11873019.44 | 1- NC | 1739342.82 | Completed | 100% | 2025-04-14 | 2025-03-24 | 24-11-028 | 24-11-028 | 2024-11-12 | 2024-11-20 | 2024-12-02 | 2024-12-10 | 2024-12-27 | JV Constech | For Turnover | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0% | 100% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | South Cotabato | 130860 | Lampitak Elementary School | TAMPAKAN | 1st | 1 | 4 | Repair of Classrooms | 2964223.54 | 1- R | 2103002.51 | Not yet started | 0% | 2025-04-08 | N/A | DSC-24-12-286 | 2025-028 | 2024-12-18 | 2025-01-07 | 2025-01-21 | 2025-02-24 | 2025-03-20 | PHSMB Construction & Supply | ON-GOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region XII | South Cotabato | 130869 | Eleonor D. Belotindos Elementary School | TANTANGAN | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 1739342.82 | Completed | 100% | 2025-04-14 | 2025-03-24 | 24-11-028 | 24-11-028 | 2024-11-12 | 2024-11-20 | 2024-12-02 | 2024-12-10 | 2024-12-27 | JV Constech | For Turnover | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0% | 100% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 | 9 | 1STY3CL AND 2STY6CL | 26103951.7 | 1- NC | 23232517 | Ongoing | 6% | 11/27/2025 | N/A | DSC-24-12-287 | 2025-033 | 2024-12-18 | 2025-01-07 | 2025-01-21 | 2025-02-24 | 2025-03-24 | Dedase Construction Services | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0% | 6% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | South Cotabato | 501991 | Dumadalig Integrated School | TANTANGAN | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 5114680.91 | Ongoing | 2% | 08/23/2025 | N/A | DSC-24-12-287 | 2025-034 | 2024-12-18 | 2025-01-07 | 2025-01-21 | 2025-02-24 | 2025-03-06 | H-Royal Construction | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 2% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | South Cotabato | 502376 | Cinco Integrated School | BANGA | 2nd | 1 | 2 | 1STY2CL | 5805259.72 | 1- NC | 4329799.25 | Ongoing | 5% | 2025-05-09 | N/A | DSC-24-12-287 | 2025-035 | 2024-12-18 | 2025-01-07 | 2025-01-21 | 2025-02-24 | 2025-03-07 | River-Stone Consutruction Services | ON-GOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 5% |  |  | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPLACEMENT | Under Procurement
QRF 2024 | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2nd | 1 | 24 | Repair of Classrooms | 1794219.49 | 1- R | 1739342.82 | Completed | 100% | 2025-04-14 | 2025-03-24 | 24-11-028 | 24-11-028 | 2024-11-12 | 2024-11-20 | 2024-12-02 | 2024-12-10 | 2024-12-27 | JV Constech | For Turnover | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 100% | 0% |  | 4.25 | EARTHQUAKE (Mw 6.8 Sarangani, Davao Occidental) |  |  |  | REPAIR | Under Procurement
QRF 2024 | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1st | 1 | 37 | Repair of Classrooms | 40000000 | 2-R | 39926190.8 | Ongoing | 35% | May 20, 2025 |  | 2024-11-521 | 2025-01-014 | December 04, 2024 | December 06, 2024 | December 06, 2024 | December 13, 2025 | January 16, 2025 | A. De Guia Construction and Development Corporation | The project was procurred thru Negotiated Procurement inorder to immediately address the need, however, implementation was hampered by extreme and unpredictable weather disturbace and the inavailabity of special-cut lumber in the local market, a total extension of 60 CD has been granted to complete the project | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 37 | 0 | 20% | 15% |  |  | TY MARCE/HURRICANE |  |  |  | REPAIR | ONGOING
QRF 2024 | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2nd | 1 | 39 | REPAIR OF CLASSROOMS | 19648076.16 | 3-R | 1944750 | Ongoing | 70% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 39 | 0 | 0% | 70% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100002 | Bacarra CES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.77 | Ongoing | 70% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 20% | 50% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100006 | Nambaran ES | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597811.08 | Not yet started | 0% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647983.8 | Not yet started | 0% | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100010 | SPECIAL EDUCATION CENTER | BACARRA | 1st | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3845845.18 | Ongoing | 50% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 50% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100011 | Santo Cristo Elementary School | BACARRA | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649206.51 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1946780.33 | Ongoing | 98% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 98% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100019 | Paninaan Elementary School | BACARRA | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2598258.05 | Ongoing | 95% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 45% | 50% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100022 | San Agustin ES | BACARRA | 1st | 1 | 9 | REPAIR OF CLASSROOMS | 5850000 | 3-R | 5832130.29 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 60% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100038 | Pasuc-Parang ES | BADOC | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2594696.51 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100066 | Crispina ES | BANNA (ESPIRITU) | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 639079.29 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100072 | Sinamar ES | BANNA (ESPIRITU) | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948623.74 | Ongoing | 40% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 30% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100106 | Nagsurot Elementary School | BURGOS | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945868.82 | Ongoing | 70% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 70% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100113 | Langayan ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 70% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 45% | 25% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100114 | Maglaoi ES | CURRIMAO | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646034.75 | Ongoing | 35% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 35% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100117 | Pias-Gaang ES | CURRIMAO | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1945863.08 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 45% | 15% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100122 | Francisco ES | DINGRAS | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1285260.05 | Ongoing | 40% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 10% | 30% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100128 | Bacsil ES | DINGRAS | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 50% | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 50% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100156 | Santiago ES | MARCOS | 2nd | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4547749.73 | Ongoing | 60% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 30% | 30% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100164 | Burayoc ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645894.62 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100165 | Caparispisan ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646009.29 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100177 | Subec ES | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 645471.97 | Ongoing | 10% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100179 | Tarrag PS | PAGUDPUD | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Ongoing | 95% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 90% | 5% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100180 | Bacsil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 649461.85 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100184 | Mumulaan ES | PAOAY | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247141.13 | Ongoing | 95% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 50% | 45% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100188 | Paoay CES | PAOAY | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 6500000 | 3-R | 6494750 | Ongoing | 80% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 30% | 50% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100189 | Paoay East Central ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 90% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 15% | 75% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100190 | Pasil ES | PAOAY | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 636301.85 | Ongoing | 20% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 20% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100194 | Binsang ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 95% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 35% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100197 | Carusikis ES | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2596663.73 | Ongoing | 80% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 |  | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 65% | 15% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100198 | Dadaeman Elementary School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 10% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 3 | 1STY3CL | 9000000 | 3- NC | 8994759.45 | Ongoing | 35% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 15% | 20% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100200 | Dilanis ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1293700 | Ongoing | 60% | 9/30/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100203 | Madalayap Elementary School | PASUQUIN | 1st | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2587210.91 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 40% | 20% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100205 | Naglicuan ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291108.21 | Ongoing | 50% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 40% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100207 | Pangil ES | PASUQUIN | 1st | 1 | 4 | 2STY4CL | 12000000 | 3- NC | 11997232.68 | Ongoing | 25% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 20% | 5% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 646523.89 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100209 | Puyupuyan ES | PASUQUIN | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 626526.64 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100211 | Sta. Catalina ES | PASUQUIN | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 3235817.47 | Ongoing | 60% | 9/30/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 40% | 20% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100214 | Tabungao ES | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295629.05 | Ongoing | 70% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 40% | 30% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100226 | Maruaya PS | PIDDIG | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 70% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 70% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100234 | Badio ES | PINILI | 2nd | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3235817.47 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100240 | Darat ES | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947230.77 | Ongoing | 80% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 20% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100242 | Gulpeng PS | PINILI | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 643005.08 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100244 | Nagtrigoan ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1261742.73 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100245 | Pugaoan-Bungro ES | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296958.76 | Ongoing | 80% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 80% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100247 | Puzol Elementary School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2595871.43 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100252 | Barabar ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100254 | Bugnay ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647084.86 | Completed | 100% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 40% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 1 | REPAIR OF CLASSROOMS | 1400000 | 3-R | 1397903.98 | Completed | 100% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 90% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100257 | Filipinas East ES | SAN NICOLAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3894750.31 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1948932.75 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100262 | Cabuloan Elementary School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644722.89 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100267 | Ruiz ES | SARRAT | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 70% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 70% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100271 | Sarrat Central School | SARRAT | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750.01 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100282 | Nagpatpatan ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 10% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100287 | Talugtog ES | SOLSONA | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1944750 | Ongoing | 10% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100288 | Alsem ES | VINTAR | 1st | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1932612.08 | Ongoing | 60% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 40% | 20% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100296 | Esperanza ES | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1283338.55 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100306 | Visaya Elementary School | VINTAR | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1294750 | Ongoing | 95% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 90% | 5% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 100314 | Lipay ES | VINTAR | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3247441.15 | Ongoing | 15% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 15% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150003 | Nagbacalan West ES | PAOAY | 2nd | 1 | 3 | REPAIR OF CLASSROOMS | 1950000 | 3-R | 1947773.07 | Completed | 100% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 40% | 60% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150008 | San Isidro PS | PASUQUIN | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1288248.77 | Ongoing | 30% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 30% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 150023 | Casilian Primary School - Taguipuro Annex | BACARRA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1296398.12 | Ongoing | 70% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0% | 70% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300015 | Dingras NHS | DINGRAS | 2nd | 1 | 6 | REPAIR OF CLASSROOMS | 3900000 | 3-R | 3895135.72 | Ongoing | 95% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 65% | 30% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3244750 | Ongoing | 10% | 8/31/2025 | ONGOING |  | 2025-02-23 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | Manimeld's Construction & Iron Works | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 300023 | Pagsanahan NHS | BADOC | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1291769.55 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 644793.38 | Not yet started | 0% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500592 | Pandan Integrated School | SARRAT | 1st | 1 | 7 | REPAIR OF CLASSROOMS | 4550000 | 3-R | 4522791.92 | Not yet started | 0% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 500593 | Sacritan Integrated School | PINILI | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2600000 | 3-R | 2597889.56 | Not yet started | 0% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502581 | Balaoi Integrated School | PAGUDPUD | 1st | 1 | 1 | REPAIR OF CLASSROOMS | 650000 | 3-R | 647045.27 | Ongoing | 10% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0% | 10% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502711 | Tubburan Integrated School | BACARRA | 1st | 1 | 5 | REPAIR OF CLASSROOMS | 3250000 | 3-R | 3228809.88 | Ongoing | 50% | 8/31/2025 | ONGOING |  | 2025-02-21 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ELOCIN Construction | ONGOING | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0% | 50% | [7 empty] | Under Procurement
QRF 2024 | Region I | Ilocos Norte | 502750 | Sto. Tomas Integrated School | PINILI | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 3-R | 1295964.13 | Not yet started | 0% | 9/30/2025 | ONGOING |  | 2025-02-22 | 2025-07-03 | 3/15/2025 | 3/27/2025 | 2025-12-03 | 2025-04-03 | ASS Construction | ONGOING | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0% | 0% | [7 empty] | Under Procurement
QRF 2024 | Region II | Batanes | 102314 | Tukon Elementary School | BASCO (Capital) | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 597975.19 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 102311 | Basco Central School | BASCO (Capital) | Lone | 1 | 18 | REPAIR OF CLASSROOMS | 2212337.67 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 102324 | Uyugan Elementary School | UYUGAN | Lone | 1 | 1 | REPAIR OF CLASSROOMS | 1570530.77 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 102325 | Mahatao Elementary School | MAHATAO | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 774860.41 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 921614.29 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 867866.43 | 3-R |  | Not yet started | 0% | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | Lone | 1 | 4 | REPAIR OF CLASSROOMS | 1026956.74 | 3-R |  | Ongoing | 20% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 20% | 0% | [7 empty] | ONGOING
QRF 2024 | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 933117.02 | 3-R |  | Ongoing | 50% | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 50% | 0% | [7 empty] | ONGOING
Formulas:
Target Completion Date = [Issuance of Notice to Proceed]+135
Target Completion Date = [Target Completion Date, row above]
Issuance of Notice to Proceed = [Issuance of Notice to Proceed, row above]
Issuance of Invitation to Bid = '[10]QRF 2019-2024'!$T680
Pre-Submission Conference = '[10]QRF 2019-2024'!$U680
Bid Opening = '[10]QRF 2019-2024'!$V680
Issuance of Resolution to Award = '[10]QRF 2019-2024'!$W680