## SF List of Schools
Category | Region | Division | School ID | School Name | Municipality | LD | No. of Sites | Elem. Individual Learner Table & Chair Set | JHS Individual Learner Table & Chair Set | SHS Individual Learner Table & Chair Set | Total Individual Learner Table & Chair Set | Teacher's Table & Chair Set | Science Laboratory Table & Stool Set | Working Table & Stool Set | Approved Budget for Contract | Implementing Unit | Legend | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Supplier | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of Sites Terminated | No. of Sets Reverted | No. of Sets Not yet started | No. of Sets Under Procurement | No. of Sets On Going | No. of Sets Completed | No. of Sets Terminated | PREVIOUS ACCOMPLISHMENT | DIFFERENCE | Projected Date of Completion | Month Completed
CY 2024 SF | CAR | Apayao | 501756 | CADACLAN INTEGRATED SCHOOL | CALANASAN (BAYAG) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135669 | Taneg ES | MANKAYAN | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 502168 | Mogao Integrated School | MANKAYAN | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135693 | Indaoac ES | TUBA | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 318904 | Tuba Central NHS | TUBA | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 305164 | Tublay National Trade High School | TUBLAY | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135940 | Tulaed ES | MAYOYAO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305186 | Tulaed NHS | MAYOYAO | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135945 | Danggo ES | TINOC | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135947 | Gumhang Elementary School | TINOC | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135949 | Impugong ES | TINOC | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305192 | Tinoc NHS | TINOC | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 305227 | Western Kalinga National High School | BALBALAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 135993 | Mabilong Elementary School | LUBUAGAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 305202 | Cawagayan National High School | PINUKPUK | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136186 | Kadaclan Elementary School | BARLIG | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136233 | Ambagiw ES | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136233 | Ambagiw ES | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 221006 | Mountain Province SPED Center | BONTOC (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 305924 | Mainit National High School | BONTOC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136267 | Apapawan Elementary School | NATONIN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 305258 | Natonin National High School | NATONIN | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319203 | Saliok National High School | NATONIN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136289 | Butigue Elementary School | PARACELIS | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136306 | Marallag Elementary School | PARACELIS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136307 | Mulliang Elementary School | PARACELIS | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136310 | Paracelis Central School | PARACELIS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 305231 | Paracelis Technical & Vocational High School | PARACELIS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319202 | San Rafael National High School | PARACELIS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319220 | Anonat National Agricultural and Vocational High School | PARACELIS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136328 | Sabangan Central School | Sabangan | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 305257 | Namatec National High School | Sabangan | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136372 | Masla Elementary School | TADIAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 136376 | Tadian Central School | TADIAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 221012 | New LubonElementary School | TADIAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Mt. Province | 319221 | Balaoa National High School | TADIAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136093 | Calaccad Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136153 | Addang Primary School | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136158 | Balawag Elementary School | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 136183 | Western Tabuk CS | CITY OF TABUK (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 220529 | San Pablo Primary School | CITY OF TABUK (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 220531 | Bulanao East Annex - Greenhills PS | CITY OF TABUK (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 305200 | Calaccad National High School | CITY OF TABUK (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 319101 | Bulo National High School | CITY OF TABUK (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 501889 | Toppan Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 501889 | Toppan Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 501890 | MALEDDA INTEGRATED SCHOOL | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 501971 | Lacnog Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 502123 | Guilayon Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | 502380 | Appas Integrated School | CITY OF TABUK (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Tabuk City | NOT-IN-NSBI | Tabuk City National High School - BANTAY EXT. | CITY OF TABUK (Capital) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304841 | Rizal National High School | BASILISA (RIZAL) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304842 | Puerto Princesa National High School | BASILISA (RIZAL) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304844 | Sering National High School | BASILISA (RIZAL) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304851 | Tag-abaca National High School | BASILISA (RIZAL) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 324404 | New Nazareth National High School | BASILISA (RIZAL) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132356 | Boa Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132357 | Borja Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132359 | Cabungaan Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132361 | Del Pilar Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132362 | Lahi Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132367 | Nueva Estrella Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132368 | R.E. Ecleo Sr. Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132371 | Sto Nino Elementary School | CAGDIANAO | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132522 | San Jose CES-SPED Center | SAN JOSE (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132217 | Burgos Central Elementary School | BURGOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132129 | Don Enrique Navarro Memorial School | DAPA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132133 | Sta Felomina Elementary School | DAPA | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132134 | Union Elementary School | DAPA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132137 | Cambas-ac Elementary School | DAPA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132165 | Cabugao ES | Del Carmen | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132167 | Dumoyog ES | Del Carmen | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132180 | Tuboran ES | Del Carmen | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132158 | Sta. Cruz ES | Gen. Luna | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132155 | Magsaysay ES | GENERAL LUNA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 317603 | Gen. Luna NHS - Consuelo NHS Annex | GENERAL LUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao |  | Gen Luna National High School - Annex | GENERAL LUNA | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132189 | Mabuhay ES | Pilar | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132230 | San Benito Central Elementary School | SAN BENITO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132198 | Roxas ES | San Isidro | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132199 | San Isidro Central Elementary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132204 | Tigasao ES | San Isidro | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | , | Del Pilar ES | San Isidro | 1st | 1 | 80 | - | - | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132208 | Garcia Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132209 | Libertad ES | SANTA MONICA (SAPAO) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132213 | Sapao Central Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132224 | Socorro Central Elementary School and SPED Center | SOCORRO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132257 | Ouano ES | SURIGAO CITY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132266 | Martinez ES | SURIGAO CITY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132284 | Libuac Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132287 | Surigao West Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132289 | B. Vasquez Memorial Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132298 | Margarita Mem. CES | SURIGAO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132299 | Mat-i Central Elementary School | SURIGAO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132301 | Punta Bilar ES | SURIGAO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 130665 | Don Epifanio Cedro Elementary School | ALEGRIA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132329 | San Pedro ES | ALEGRIA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 304811 | Alegria National High School | ALEGRIA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 304813 | Bacuag National Agro-Industrial School | BACUAG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132407 | Gigaquit Central Elementary School | GIGAQUIT | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132434 | Mainit CES | MAINIT | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132437 | Matin-ao CES | MAINIT | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132451 | Binocaran ES | MALIMONO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132460 | Malimono Central Elementary School | MALIMONO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 304818 | Cantapoy National High School | MALIMONO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132467 | Amoslog ES | PLACER | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132469 | Bad-as ES | PLACER | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132478 | Placer Central Elementary School | PLACER | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132479 | Placer West CES | PLACER | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132528 | Gacepan ES | SISON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132529 | Hinapayaw ES | SISON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132549 | Talavera ES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 305953 | Himama-ug National High School | TAGANA-AN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 501680 | Hinatuan Integrated School | TAGANA-AN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132560 | Calang-Custodio ES | TUBOD | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132561 | Capayahan ES | TUBOD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132562 | Marciano Dapar ES (Cawilan ES) | TUBOD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132567 | Timamana ES | TUBOD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132600 | Amag Elementary School | BAYABAS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132687 | San Vicente Elementary School | CARMEN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 214548 | Tabinas Indigenous Community Elementary School | CARMEN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 305747 | Gacub Atad S. Iligan Tribal National High School | CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132771 | Diatagon Barangay Elementary School | LIANGA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 214546 | Sangay Elementary School of Living Tradition | SAN MIGUEL | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 502151 | Balbuena Integrated School | HINATUAN | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 501293 | Pamian Integrated School | LINGIG | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao del Sur | 132919 | Sta Fe Elementary School | TAGBINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Tandag City | 132964 | Engr. Nestor Ty Memorial Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305319 | Eulogio Rodriguez Vocational High School | CITY OF MANILA | 6th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136481 | J. Zamora Elementary School | PANDACAN | 6th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305317 | Elpidio Quirino High School | SAMPALOC | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305315 | Victoriano Mapa High School | SAN MIGUEL | 6th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305314 | Gen. E. Aguinaldo Integrated School | SANTA ANA | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6th | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136671 | Barangka ES | CITY OF MARIKINA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136676 | Marikina ES | CITY OF MARIKINA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 305399 | TaÃ±ong HS | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 305401 | Marikina Science HS | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 319904 | Kalumpang National High School | CITY OF MARIKINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136681 | Fortune ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136682 | H. Bautista ES | CITY OF MARIKINA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2nd | 1 | 1440 | - | - | 1440 | 32 | - | - | 4928000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 150052 | Concepcion Integrated School | CITY OF MARIKINA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 305398 | Marikina HS | CITY OF MARIKINA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA | 2nd | 1 | - | 1350 | - | 1350 | 30 | - | - | 4620000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 319902 | Fortune High School | CITY OF MARIKINA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Marikina City | 500052 | Concepcion Integrated School | CITY OF MARIKINA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 136870 | Wawa Elementary School | CITY OF NAVOTAS | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Pasay City | 136599 | Marcela Marcelo ES | PASAY CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Pasig City | 305422 | Rizal Experimental Station And Pilot School for Cottage Industries (RESPSCI) | CITY OF PASIG | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 340694 | Lucresia Kasilag Senior High School (SHS within E. Abada ES) | QUEZON CITY | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305337 | Justice Cecilia Muñoz Palma High School | QUEZON CITY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305352 | Juan Sumulong High School | QUEZON CITY | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305338 | Maligaya HS | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305341 | San Bartolome HS | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305635 | West Fairview High School | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 360867 | Leandro Locsin Integrated School | QUEZON CITY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Quezon City | 305344 | Sauyo HS | QUEZON CITY | 6th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Taguig | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 136797 | Malinta Elementary School | CITY OF VALENZUELA | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 136812 | Roberta de Jesus ES | CITY OF VALENZUELA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305436 | Polo National High School | CITY OF VALENZUELA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305437 | Dalandanan National High School | CITY OF VALENZUELA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 320404 | Bignay National High School | CITY OF VALENZUELA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305441 | Valenzuela NHS | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305443 | Gen. T. de Leon NHS | CITY OF VALENZUELA | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305444 | Maysan National High School | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100067 | Imelda ES | BANNA (ESPIRITU) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100110 | Bimmanga ES | CURRIMAO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100130 | Dingras West CES | DINGRAS | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 320807 | San Marcelino National High School | DINGRAS | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 500594 | Uguis Integrated School | NUEVA ERA | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100192 | Sideg Elementary School | PAOAY | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100247 | Puzol Elementary School | PINILI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300027 | Pinili NHS | PINILI | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 320815 | Bingao National High School | SAN NICOLAS | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100285 | Solsona Central ES | SOLSONA | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300056 | Lussoc National High School | SANTO DOMINGO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300049 | Dili NHS | SANTA CRUZ | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300032 | Ag-agrao NHS | SANTA MARIA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300078 | Santiago NHS | SANTIAGO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300143 | SINAPANGAN NATIONAL HIGH SCHOOL | BALAOAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 340825 | San Gabriel Senior High School | SAN GABRIEL | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300140 | Santol Vocational High School | SANTOL | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300125 | Old Sudipen National High School | SUDIPEN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 500563 | San Julian Integrated School | AGOO | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300112 | Don Eulogio De Guzman Memorial NHS | BAUANG | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300102 | Burgos National High School | BURGOS | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300104 | Caba National High School | CABA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 500495 | Casilagan Elementary School | NAGUILIAN | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300131 | Pugo Central National High School | PUGO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 500361 | Cabaruan Integrated School | SANTO TOMAS | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300152 | Tubao National High School | TUBAO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Laoag City | 102199 | Eulalio. F. Siazon Memorial Elementary School | LAOAG CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Laoag City | 300373 | Ilocos Norte College of Arts and Trades | LAOAG CITY (Capital) | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500371 | Awag Integrated School | ANDA | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500606 | Anda Integrated School | ANDA | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte National High School | BANI | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300245 | Ranao National High School | BANI | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101657 | Baybay Elementary School | SUAL | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 151513 | Modesto V. Ferrer ES | SUAL | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | SUAL | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300185 | Camaley NHS | BINMALEY | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101386 | Bolaoen ES | BUGALLON | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300209 | Labrador NHS | LABRADOR | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500369 | Ramon Magsaysay Integrated School | LABRADOR | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101489 | Tonton Elementary School | LINGAYEN (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101491 | Baay ES | LINGAYEN (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101496 | Domalandan East ES | LINGAYEN (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101499 | Malimpuec ES | LINGAYEN (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101582 | Caturay Elementary School | MANGATAREM | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 151514 | Cabayugan Elementary School | MANGATAREM | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300174 | Bogtong NHS | MANGATAREM | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101672 | Angatel ES | URBIZTONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101689 | Don Pio B. Palisoc ES | URBIZTONDO | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300160 | Balangay NHS | URBIZTONDO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101280 | Tamaro-Tambac Elementary School | BAYAMBANG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101561 | Don Pedro ES | MALASIQUI | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 151515 | Pacuan ES | MALASIQUI | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 151520 | Ican Elementary School | MALASIQUI | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300213 | Lokeb Sur National High School | MALASIQUI | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui NHS | MALASIQUI | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300257 | Talospatang NHS | MALASIQUI | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101625 | Primicias Elementary School | MAPANDAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300265 | Torres NHS | MAPANDAN | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101637 | STA. BARBARA CENTRAL SCHOOL | SANTA BARBARA | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300266 | Tuliao NHS | SANTA BARBARA | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 300277 | Ariston-Bantog NHS | ASINGAN | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | ASINGAN | 6th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101738 | San Aurelio 3rd ES | BALUNGAO | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101847 | San Narciso Sur ES | NATIVIDAD | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101895 | Rizal Elementary School | ROSALES | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Carlos City | 102258 | Caoayan-Kiling Elementary School | SAN CARLOS CITY | 3rd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Carlos City | 153507 | Jose Macam Paningbatan Sr. Elementary School | SAN CARLOS CITY | 3rd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101028 | Mameltac Elementary School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101031 | Pao ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101034 | Santiago ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101044 | San Agustin (Poro) Elementary School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500530 | Nagyubuyuban Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500983 | San Fernando City SPED Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102278 | Palina East Elementary School | CITY OF URDANETA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102287 | Cabuloan Elementary School | CITY OF URDANETA | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102297 | Labit East Elementary School | CITY OF URDANETA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102301 | Manan Elementary School | CITY OF URDANETA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102303 | Nancalobasaan Elementary School | CITY OF URDANETA | 5th | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102306 | San Jose Elementary School | CITY OF URDANETA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 300408 | Palina West National High School | CITY OF URDANETA | 5th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Vigan City | 100783 | Ayusan-Paoa Elementary School | CITY OF VIGAN (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Vigan City | 100786 | Burgos Memorial School West | CITY OF VIGAN (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Vigan City | 300088 | Vigan East National High School | CITY OF VIGAN (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Batanes | 300416 | Mahatao NHS | MAHATAO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300422 | BAYBAYOG NATIONAL HIGH SCHOOL | ALCALA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102912 | Sta. Ana CS | SANTA ANA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300473 | Libertad National High School | ABULUG | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102789 | Masi Primary School | PAMPLONA | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102953 | Sto. Nino Central Elementary School | SANTO NIÑO (FAIRE) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102634 | Enrile West CS | ENRILE | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102716 | Iguig CS | IGUIG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102796 | Abucay ES | PEÑABLANCA | 3rd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 103209 | Amobocan ES | CITY OF CAUAYAN | 3rd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 103227 | Alinam ES | CITY OF CAUAYAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 103228 | Cauayan South CS | CITY OF CAUAYAN | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 501622 | San Luis Integrated School | CITY OF CAUAYAN | 3rd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | City of Ilagan | 103392 | Cabeceria 27 ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | City of Ilagan | 103420 | Camunatan ES | ILAGAN CITY (CAPITAL) | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | City of Ilagan | 501548 | Dappat Integrated School | ILAGAN CITY (CAPITAL) | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103145 | Cabagan Science Elementary School | CABAGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 501434 | Cubag Integrated School | CABAGAN | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103146 | Candanum Elementary School | CABANGAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 501434 | Cubag Integrated School | CABANGAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103271 | Maui Elementary School | DELFIN ALBANO (MAGSAYSAY) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103535 | Bicobian Elementary School | DIVILACAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103547 | Dikaruyan Primary School | DIVILACAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 501311 | Reina Mercedes Integrated School | MACONACON | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103536 | Bisag Elementary School | PALANAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103539 | Dialawyao Elementary School | PALANAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103540 | Dibewan Elementary School | PALANAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103549 | Dimasari Elementary School | PALANAN | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103556 | Marikit Elementary School | PALANAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 155520 | Centro West Primary School | PALANAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103797 | Ballacayu Elementary School | SAN PABLO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103854 | Sta. Maria Central School | SANTA MARIA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103862 | Barumbung Elementary School | SANTO TOMAS | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103854 | Sta. Maria Central School | Sta Maria | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 305942 | Tumauini Stand-Alone Senior High Schol | TUMAUINI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103526 | San Manuel Elementary School | NAGUILIAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 500467 | Sto. Tomas Integrated School | NAGUILIAN | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103620 | Dangan Elementary School | REINA MERCEDES | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103627 | Santor Elementary School | REINA MERCEDES | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103638 | San Pedro-Villa Concepcion Elementary School | ROXAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 500070 | San Jose Integrated School | SAN MARIANO | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 500095 | San Mariano II Central Integrated School | SAN MARIANO | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 300500 | Alicia National High School | ALICIA | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 300502 | Villa Domingo National High School | ANGADANAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 500020 | Lomboy Integrated School | ANGADANAN | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103175 | Nueva Era Elementary School | CABATUAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103608 | Raniag Elementary School | RAMON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 500015 | Dietban Integrated School | SAN GUILLERMO | 3rd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103783 | Dagupan Elementary School | SAN MATEO | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103793 | Villa Fuerte Elementary School | SAN MATEO | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103245 | Camarao Elementary School | CORDON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103246 | Capirpiriwan Elementary School | CORDON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103502 | San Jose Norte Elementary School | MALLIG | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103815 | Mabini ES | CITY OF SANTIAGO | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103816 | MALINI ELEMENTARY SCHOOL | CITY OF SANTIAGO | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4th | 1 | 945 | - | - | 945 | 21 | - | - | 3234000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103830 | Santiago North CS SpEd Center | CITY OF SANTIAGO | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 103840 | Santiago South CS | CITY OF SANTIAGO | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 306124 | Patul National High School | CITY OF SANTIAGO | 4th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 500937 | Salvador Integrated School | CITY OF SANTIAGO | 4th | 1 | - | - | 400 | 400 | 10 | - | - | 1375000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 500938 | Sinili Integrated School | CITY OF SANTIAGO | 4th | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Santiago City | 501147 | San Jose Integrated School | CITY OF SANTIAGO | 4th | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Tuguegarao City | 104395 | Bagay Elementary School | TUGUEGARAO CITY(Capital) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 107061 | Sto. Rosario Elementary School | ANGELES CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 500132 | Malabanias IS | ANGELES CITY | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 104492 | Detailen ES | MARIA AURORA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 104496 | Dimanpudso ES | MARIA AURORA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 300696 | Wenceslao NHS | MARIA AURORA | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 302766 | Suguit NHS | MARIA AURORA | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 104608 | Casupanan ES | HERMOSA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 300705 | Hermosa NHS | HERMOSA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 104654 | Morong ES | MORONG | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 104637 | Balon ES | MARIVELES | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 104688 | Alauli ES | PILAR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104777 | Matungao Elementary School | BULACAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104812 | Meysulao ES | CALUMPIT | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104849 | Hagonoy West Central School | HAGONOY | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 501660 | Inaon Integrated School | PULILAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104731 | Dalig Elementary School | BALAGTAS (BIGAA) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104757 | Sta. Barbara ES | BALIUAG | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 306717 | Teodoro Evangelista Mem. HS | BALIUAG | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105012 | Sipat Elementary | PLARIDEL | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300727 | Dr. Felipe de Jesus High School | PLARIDEL | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104714 | Camachile Elementary School | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104722 | Pulong Sampaloc ES | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 158525 | Durumugan ES | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104957 | San Mateo Elementary School | NORZAGARAY | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104959 | T.P. Policarpio ES (Minuyan ES) | NORZAGARAY | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105034 | Calawitan Elementary School | SAN ILDEFONSO | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105036 | Lapnit Elementary School | SAN ILDEFONSO | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105043 | Sta. Catalina Bata Elementary School | SAN ILDEFONSO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105055 | Malipampang ES | SAN ILDEFONSO | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 306728 | Sta. Catalina Bata National High School | SAN ILDEFONSO | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105069 | Bulualto ES | SAN MIGUEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105083 | Pinambaran ES | SAN MIGUEL | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105087 | Sibul Elementary School | SAN MIGUEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105090 | Tartaro ES | SAN MIGUEL | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105099 | Dr. Juan F. Pascual MS (formerly Silangan ES) | SAN MIGUEL | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105111 | San Miguel Elementary | SAN MIGUEL | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105115 | Caingin ES | SAN RAFAEL | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105116 | Capihan Elementary School | SAN RAFAEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105120 | Maguinao Elementary School | SAN RAFAEL | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105125 | Pasong Callos ES | SAN RAFAEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105132 | San Agustin ES | SAN RAFAEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105137 | Tambubong ES | SAN RAFAEL | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104907 | Loma de Gato Elementary School | MARILAO | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300763 | Obando NHS | OBANDO | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105147 | Cay Pombo ES | SANTA MARIA | 4th | 1 | 675 | - | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105150 | Garden Village ES | SANTA MARIA | 4th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105160 | Pila Elementary School | SANTA MARIA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300767 | Pulong Buhangin NHS | SANTA MARIA | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104764 | Bunducan ES | BOCAUE | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104765 | Bunlo Elementary School | BOCAUE | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104978 | Malibong Matanda ES | PANDI | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 105152 | Jose Juan Serapio ES (Catmon ES) | SANTA MARIA | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300765 | Parada NHS | SANTA MARIA | 6th | 1 | - | 810 | - | 810 | 18 | - | - | 2772000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 107153 | Daniel A. Avena Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 107155 | Gaya-Gaya Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 107164 | Sta. Cruz (BBD) Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 301059 | Paradise Farms National High School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 305697 | Mulawin National High School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 305698 | San Rafael National High School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 307510 | Kaypian National High School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 502220 | Bagong Buhay F Integrated School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Gapan City | 105339 | San Nicolas Central School | CITY OF GAPAN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Gapan City | 300851 | San Roque NHS | CITY OF GAPAN | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Mabalacat City | 159505 | Marcos Village ES | MABALACAT CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104871 | Longos Elementary School | CITY OF MALOLOS (Capital) | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104874 | Lugam Annex ES | CITY OF MALOLOS (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104876 | San Pablo ES | CITY OF MALOLOS (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104878 | Sta. Isabel ES | CITY OF MALOLOS (Capital) | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104897 | Panasahan ES | CITY OF MALOLOS (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 137148 | Mojon Elementary School | CITY OF MALOLOS (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 500404 | CITY OF MALOLOS INTEGRATED SCHOOL - ATLAG | CITY OF MALOLOS (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Meycauayan City | 104928 | Perez Elementary School | CITY OF MEYCAUAYAN | 4th | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Meycauayan City | 104932 | Calvario Elementary School | CITY OF MEYCAUAYAN | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Meycauayan City | 137210 | Bagong Pag-asa Elementary School | CITY OF MEYCAUAYAN | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Munoz Science City | 105555 | Pandalla ES | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Munoz Science City | 105558 | San Andres ES | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105193 | Umangan ES | ALIAGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105273 | Dr. A. Ongsiako Sr. ES | CUYAPO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105375 | Bantug ES | GUIMBA | 1st | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105410 | Calem Elementary | GUIMBA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 501658 | Maybubon Integrated School | GUIMBA | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105804 | Sicsican Matanda ES | TALAVERA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105829 | San Miguel Na Munti ES | TALAVERA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105502 | Llanera CS | LLANERA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 500122 | Sta. Barbara Integrated School(Elementary) | LLANERA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105519 | Burgos ES | LUPAO | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300841 | Rizal National High School | RIZAL | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 502146 | Fronda Integrated School | TALUGTUG | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300862 | Gen. Mamerto Natividad National HS | GENERAL MAMERTO NATIVIDAD | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300811 | Jorge M. Padilla National High School | LAUR | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105593 | Sapang Buho ES | PALAYAN CITY (Capital) | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105764 | Esing T. Angeles E/S | SANTA ROSA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300846 | Juan Basangan National High School (Formerly San Francisco NHS) | SAN ANTONIO | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 107124 | Olongapo City ES | OLONGAPO CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 107137 | Asinan ES | OLONGAPO CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 107139 | Kalalake ES | OLONGAPO CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 107139 | Kalalake ES | OLONGAPO CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 500027 | James L. Gordon IS | OLONGAPO CITY | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Olongapo City | 500134 | Sergia Soriano Esteban IS SPED Center (Kalaklan ES) | OLONGAPO CITY | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Antipolo City | 109328 | Kaila ES | CITY OF ANTIPOLO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Antipolo City | 230001 | Tanza ES | CITY OF ANTIPOLO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Antipolo City | 500391 | Apia IS | CITY OF ANTIPOLO | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107202 | Agoncillo Central School | AGONCILLO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107203 | Pamiga Elementary School | AGONCILLO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 301122 | Malvar School of Arts and Trade | MALVAR | 3rd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 301083 | Bayorbor National High School | MATAASNAKAHOY | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 301071 | Balas Buco Sta. Maria National High School | TALISAY | 3rd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107594 | Padre Imo Luna Memorial Elementary School | SAN JOSE | 4th | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107608 | Paaralang Elementarya ng Calubcub 1 | SAN JUAN | 4th | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Binan City | 108218 | Dela Paz West ES | CITY OF BIÑAN | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Binan City | 108227 | Platero ES | CITY OF BIÑAN | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Binan City | 301254 | Nereo R. Joaquin National High School | CITY OF BIÑAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Binan City | 307932 | Mamplasan NHS (Jacobo Annex) | CITY OF BIÑAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cabuyao City | 301229 | Bigaa Integrated National High School | CABUYAO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cabuyao City | 301234 | Cabuyao Integrated National High School | CABUYAO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Calamba City | 109825 | Tiyani Elementary School | CITY OF CALAMBA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Calamba City | 109864 | Barandal Elementary School | CITY OF CALAMBA | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Calamba City | 301515 | Calamba Integrated School | CITY OF CALAMBA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 301174 | Binakayan National High School | KAWIT | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108093 | Tejeros Convention Elementary School | ROSARIO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107895 | Lantic Elementary School | CARMONA | 5th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107863 | Pangil Elementary School | AMADEO | 7th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108168 | Maximino V. Pangilinan Elementary School | TANZA | 7th | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108186 | Palawit Elementary School | TRECE MARTIRES CITY (Capital) | 7th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107840 | Amuyong Elementary School | ALFONSO | 8th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107853 | Sinaliw Elementary School | ALFONSO | 8th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108036 | Urdaneta Elementary School | MAGALLANES | 8th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108046 | Pinagsanhan Elementary School | MARAGONDON | 8th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 301169 | Constancio E. Aure Sr. National High School | MENDEZ (MENDEZ-NUÑEZ) | 8th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 305620 | Mendez-Nuñez National High School | MENDEZ (MENDEZ-NUÑEZ) | 8th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 103570 | Villa Apolonia Elementary School | NAIC | 8th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 301206 | Naic Coastal Integrated National High School | NAIC | 8th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108148 | Mendez Crossing Elementary School | TAGAYTAY CITY | 8th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite City | 109628 | Garita ES | CAVITE CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite City | 301485 | Sangley Point NHS | CAVITE CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Gen. Trias City | 301223 | Tropical Village National High School | CITY OF GENERAL TRIAS | 6th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Imus City | 107969 | Anabu II Elementary School | IMUS | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Imus City | 107972 | Buhay na Tubig Elementary School | IMUS | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Imus City | 107981 | Alapan II Elementary School | IMUS | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 301269 | Sta. Maria NHS | SANTA MARIA | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 108492 | Magsaysay ES | SINILOAN | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 108493 | Palanas ES (Llavac) | SINILOAN | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 301273 | Siniloan Integrated National High School | SINILOAN | 4th | 1 | - | 500 | - | 500 | 11 | - | - | 1710500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lipa City | 301496 | Pinagkawitan Integrated National Hgh School | LIPA CITY | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lucena City | 109732 | Lucena South II Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lucena City | 109733 | Mayao Castillo Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lucena City | 167501 | Hermana Fausta Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lucena City | 308508 | Lucena City National High School - Mayao Crossing Extension | LUCENA CITY (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 501452 | Carlagan Integrated School | BURDEOS | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 501453 | Calutcot Integrated School | BURDEOS | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108725 | Umiray ES | GENERAL NAKAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108787 | Infanta CS | INFANTA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 302394 | Apad Jomalig National High School (Apad NHS) | JOMALIG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108911 | Mauban South CES I (SPED) | MAUBAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 109034 | Libo ES | PANUKULAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108984 | Guinaygayan ES | PATNANUNGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108617 | Kinatihan I ES | CANDELARIA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 305598 | SARIAYA NATIONAL HIGH SCHOOL | SARIAYA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108652 | Don Abadilla ES | CATANAUAN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 301302 | Caigdal National High School | UNISAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 301400 | San Rafael NHS | ATIMONAN | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon |  | Matanag NHS | ATIMONAN | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108738 | Guinayangan ES | GUINAYANGAN | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 108847 | Lopez West Elementary School Bldg. I | LOPEZ | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 301375 | Perez National High School | PEREZ | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Quezon | 301375 | Perez National High School | PEREZ | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 109312 | Doña Susana Madrigal Elementary School | BINANGONAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 301468 | Tuna-Balibago National High School | CARDONA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 109446 | Bayugo Elementary School | JALA-JALA | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 109516 | Doña Paz Sumulong Tanjuatco Elementary School | TANAY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 109493 | Pintong Bukawe Elementary School | SAN MATEO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal |  | Banaba High School | SAN MATEO | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School (SPED) | CITY OF TAYABAS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301741 | Sibaltan National High School | EL NIDO (BACUIT) | 1st | 1 |  | 135 | 90 | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301737 | San Miguel National High School (Gaudencio Abordo NHS) | LINAPACAN | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111046 | Lacaren Elementary School | MAGSAYSAY | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111047 | Los Angeles Elementary School | MAGSAYSAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111049 | Magsaysay Central School | MAGSAYSAY | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111136 | Andres Soriano Memorial Elementary School | ROXAS | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111167 | San Dionisio Elementary School | ROXAS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170540 | Pedro Baquiao Memorial Elementary School | ROXAS | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301705 | Magara School for Philippine Craftsmen | ROXAS | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301731 | Roxas National Comprehensive High School | ROXAS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111190 | Irawan Elementary School | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111190 | Irawan Elementary School | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111195 | New Caruray Elementary School | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111232 | Liminangcong Central School | TAYTAY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111246 | Sandoval Elementary School | Taytay | 1st | 1 | 90 |  |  | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170558 | Taytay West Elementary School | TAYTAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301712 | New Guinlo National High School | TAYTAY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 309103 | Central Taytay National High Shool | TAYTAY | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110725 | Isaub Elementary School | ABORLAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110808 | Mangsee Elementary School | BALABAC | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110826 | Bono-Bono Elementary School | BATARAZA | 2nd | 1 | 180 |  |  | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110832 | Igang-Igang Elementary School | BATARAZA | 2nd | 1 | 90 |  |  | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110845 | Rio Tuba Central School | BATARAZA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301730 | Rio Tuba National High School | BATARAZA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110866 | Brooke's Point Central School SPED Center | BROOKE'S POINT | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301671 | Brooke's Point National High School - Pangobilian NHS | BROOKE'S POINT | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301704 | Maasin National High School (Bernas NHS) | BROOKE'S POINT | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111072 | Narra Pilot School | NARRA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111076 | San Isidro Elementary School | NARRA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301710 | Narra National High School | NARRA | 2nd | 1 | 450 | 275 | - | 725 | 16 | - | - | 2480500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301724 | Princess Urduja National High School | NARRA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111120 | Quezon Central School | QUEZON | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301726 | Quezon National High School | QUEZON | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110322 | Imbo Elementary School | RIZAL (MARCOS) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110657 | Calupisan Elementary School | RIZAL (MARCOS) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111119 | Rizal Central School | RIZAL (MARCOS) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170545 | Tulapos Elementary School | RIZAL (MARCOS) | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170567 | Rancho II Elementary School | RIZAL (MARCOS) | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110905 | Labog Elementary School | SOFRONIO ESPAÑOLA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301725 | Pulot National High School | SOFRONIO ESPAÑOLA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111467 | East Central School | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111477 | FRANCISCO UBAY MEMORIAL ELEM SCHOOL | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111491 | San Pedro CS | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111492 | Sicsican Elementary School | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111495 | Sta. Monica ES | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111497 | Tagburos ES | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111503 | Wescom ES | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 111528 | Salvacion CS | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 301782 | Inagawan Integrated HS | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 301793 | San Jose NHS | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 301796 | Sicsican NHS | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 309301 | PALAWAN NATIONAL SCHOOL | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Puerto Princesa City | 330506 | Sta. Monica High School | PUERTO PRINCESA CITY (Capital) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301747 | Alcantara National High School | ALCANTARA | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 302080 | Melodias Imperial, Sr. National High School | ALCANTARA | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301752 | Cajidiocan National High School | CAJIDIOCAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301758 | Danao National High School | CAJIDIOCAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 306045 | Victorio Sixon Balogo National High School | CALATRAVA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 309201 | Calatrava National High School | CALATRAVA | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 309210 | Mauricio F. Fabito National High School | CORCUERA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301765 | LOOC NATIONAL HIGH SCHOOL | LOOC | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301768 | Magdiwang NHS | MAGDIWANG | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301769 | Odiongan National High School | ODIONGAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 111387 | Romblon West CS | ROMBLON (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301770 | Romblon NHS, Romblon | ROMBLON (Capital) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 309204 | EDUARDO M. MORENO NATIONAL HIGH SCHOOL | SAN AGUSTIN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301771 | San Andres NHS | SAN ANDRES | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301759 | Don Carlos M. Mejias Memorial NHS | SAN FERNANDO | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 305694 | Armin Rios-Marin National High School | SAN FERNANDO | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 301763 | Sta. Fe NHS | SANTA FE | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Romblon | 309212 | Tranquilino Cawaling Sr. National High School | SANTA FE | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Dapitan City | 125916 | Ilaya Elementary School | DAPITAN CITY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Dapitan City | 125919 | Oyan Elementary School | DAPITAN CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Dapitan City | 125946 | Dampalan Elementary School | DAPITAN CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Dapitan City | 125952 | Sigayan Elementary School | DAPITAN CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Dapitan City | 125955 | Larayan ES | DAPITAN CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Isabela City | 126025 | Panigayan Elementary School | CITY OF ISABELA (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Isabela City | 502129 | Badjao Floating Integrated School | CITY OF ISABELA (Capital) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 687500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 126060 | Bulatok Integrated School | PAGADIAN CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 126083 | Balintawak Elementary School | PAGADIAN CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 303909 | Tawagan Sur NHS | PAGADIAN CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 303913 | ZAMBOANGA DEL SUR SCHOOL OF ARTS AND TRADES | PAGADIAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 314703 | Tulawas IS | PAGADIAN CITY (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 502125 | La Suerte Integrated School | PAGADIAN CITY (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126150 | Talisayan ES | ZAMBOANGA CITY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126208 | Mariki ES | ZAMBOANGA CITY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 314804 | Capisan NHS | ZAMBOANGA CITY | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126193 | Talabaan ES | ZAMBOANGA CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126248 | Tagpangi ES | ZAMBOANGA CITY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125520 | Kawayan Elementary School | ALICIA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 196521 | Buug Central SPED Center | BUUG | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125570 | Guinoman Elementary School | DIPLAHAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 303835 | Natan National High School | DIPLAHAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125599 | Lalat Elementary School | IMELDA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125694 | La Dicha Elementary School | MALANGAS | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 196520 | Malangas Central SPED Center | MALANGAS | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125733 | Buhangin Mahaba Elementary School | OLUTANGA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125763 | Kima Elementary School | PAYAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125609 | Bangkerohan Elementary School | IPIL | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125622 | Luis Ruiz Sr. Elementary School | IPIL | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125635 | Buayan Elementary School | KABASALAN | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125710 | Baga Elementary School | NAGA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125711 | Baluno Elementary School | NAGA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125786 | Guinabucan Elementary School | ROSELLER LIM | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125804 | Surabay Central Elementary School | ROSELLER LIM | 2nd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 303872 | Titay National High School | TITAY | 2nd | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 303874 | Tungawan National High School | TUNGAWAN | 2nd | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112584 | San Juan ES | DEL GALLEGO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 173534 | San Rafael Norte ES | LUPI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112672 | Bahay ES | LIBMANAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112681 | Libmanan North CS | LIBMANAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 302037 | San Juan National High School | LIBMANAN | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112789 | Antipolo ES | MINALABAC | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112797 | Hamoraon ES | MINALABAC | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112798 | Hobo ES | MINALABAC | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 302021 | Ramon B. Felipe Sr. NHS (frmerly: San Vicente HS) | PAMPLONA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 309769 | Pasacao National High School | PASACAO | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112766 | San Antonio ES | BOMBON | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 302052 | Camaligan National High School (formerly: Santo Tomas NHS) | CAMALIGAN | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112537 | Gata ES | CARAMOAN | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112629 | Napawon ES | GOA | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 501283 | Lip-Ac Integrated School | GOA | 4th | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 305911 | Mabca National High School | SAGÑAY | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 309766 | Cabalinadan High School | TIGAON | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | NOT-IN-NSBI | Caranday High School (IYAGAN Annex) | BAAO | 5th | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112344 | Balatan CS | BALATAN | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112354 | Nacacale ES | BALATAN | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 112427 | Bula Central School | BULA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 113173 | Baras CES | BARAS | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 113181 | Batalay ES | BATO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 500412 | Bote IS | Bato | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 500414 | Palumbanes Integrated School | CARAMORAN | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 302094 | Pandan SAT | PANDAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 113305 | San Miguel CES | SAN MIGUEL | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 302089 | Hawan National High School | VIRAC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Catanduanes | 302090 | Magnesia National High School | VIRAC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Legaspi City | 302261 | Legazpi City National High School | LEGAZPI CITY (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Ligao City | 111837 | Balanac ES | CITY OF LIGAO | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Ligao City | 111838 | Cabarian ES | CITY OF LIGAO | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Ligao City | 111843 | Ligao West Central Elementary School (Poblacion) | CITY OF LIGAO | 3rd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Ligao City | 301837 | Ligao National High School | CITY OF LIGAO | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113477 | Batuan CS | BATUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113486 | Panisihan ES | BATUAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113489 | Sawang ES | BATUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 500164 | Costa Rica Integrated School | BATUAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113589 | Peñafrancia ES | CLAVERIA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113775 | Togoron ES | MONREAL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 501537 | Rizal Integrated School | MONREAL | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113863 | Buyo ES | SAN FERNANDO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113867 | Ipil ES | SAN FERNANDO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113871 | Minio ES | SAN FERNANDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113873 | Progreso ES | SAN FERNANDO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302127 | Buyo National High School | SAN FERNANDO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113894 | Leonardo Barrun ES | SAN JACINTO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113900 | San Jacinto CS | SAN JACINTO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113901 | Tacdugan ES | SAN JACINTO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113903 | Washington Elementary School | SAN JACINTO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113935 | San Pedro ES | SAN PASCUAL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 501527 | Roxas Integrated High School | SAN PASCUAL | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113374 | Aroroy East CS | AROROY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113393 | Amoroy ES | AROROY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302143 | Luy-a National High School | AROROY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 309925 | Damaso R. Rubia Memorial High School | AROROY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 500162 | Mataba Integrated School | AROROY | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302144 | Magdalena National High School | BALENO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113447 | Andronico A. Maybay ES | BALUD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113649 | Jose Z. Meza Sr MES | MANDAON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113694 | Jamorawon ES | MILAGROS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113713 | Tigbao Elementary School | MILAGROS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113714 | Tinaclipan ES | MILAGROS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113719 | Bangad Elementary School | MILAGROS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113736 | Bagacay ES | MOBO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113749 | Fabian R. De Mesa Elementary School | MOBO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113752 | PINAMARBUHAN ES | MOBO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113495 | Malobago Elementary School | CATAINGAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113496 | Matayum Elementary School | CATAINGAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113510 | Curvada ES | CATAINGAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 309921 | Feliciano S. Samonte Memorial High School | CATAINGAN | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113600 | Cabanuyoan Elementary School | DIMASALANG | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113606 | Dimasalang CS | DIMASALANG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113609 | Gregorio Alino Elementary School | DIMASALANG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113620 | Baras ES | ESPERANZA | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113620 | Baras ES | ESPERANZA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113621 | Prudencio Martinez ES | ESPERANZA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113626 | Magsaysay Elementary School | ESPERANZA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113627 | Masbaranon ES | ESPERANZA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113628 | Pablo .M. Conag CS | ESPERANZA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113783 | San Antonio ES | PALANAS | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113790 | Catoogan PS | PALANAS | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113845 | Daraga ES | PLACER | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113854 | San Pero ES | PLACER | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113940 | Arado Elementary School | USON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113948 | Del Rosario ES | USON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 113965 | Felix S. Merioles Elementary School | USON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302131 | Del Carmen National High School | USON | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 302175 | Uson National High School | USON | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate | 309950 | SIMAWA NATIONAL HIGH SCHOOL | USON | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Masbate City | 113665 | Amancio Aguilar Elementary School | CITY OF MASBATE (Capital) | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Naga City | 114514 | Jose Rizal Elementary School | NAGA CITY | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114079 | Boton ES | CASIGURAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114087 | Inlagadian ES | CASIGURAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302240 | San Juan NHS | CASIGURAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302201 | Cumadcad National High School | CASTILLA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114145 | Gogon ES | DONSOL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114161 | Donsol West CS | DONSOL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302205 | Donsol National Comprehensive HS - Banuang Gurang Extension HS | DONSOL | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114285 | Tagas ES | MAGALLANES | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114274 | Behia Elementary School | MAGALLANES (34 BRGYS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114280 | Bartolome G. Lee, Sr. ES | MAGALLANES (34 BRGYS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302222 | Magallanes National High School | MAGALLANES (34 BRGYS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114352 | Marifosque ES | PILAR | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114376 | Leona ES | PILAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114382 | Naspi Elementary School | PILAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302230 | Pilar National Comprehensive High School | PILAR | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 113978 | Alegria Elementary School | BARCELONA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 113982 | Barcelona Central School | BARCELONA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2nd | 1 | - | 945 | - | 945 | 21 | - | - | 3234000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 310009 | San Antonio National High School | BARCELONA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114262 | Jagusara ES | JUBAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 114396 | Prieto Diaz CS | PRIETO DIAZ | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Sorsogon | 302223 | Manlabong National High School | PRIETO DIAZ | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Tabaco City | 114594 | Oson ES | CITY OF TABACO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Tabaco City | 114618 | Rawis ES | CITY OF TABACO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Tabaco City | 302282 | San Antonio NHS, Tabaco | CITY OF TABACO | 1st | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 310601 | LUPO NATIONAL HIGH SCHOOL | ALTAVAS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 501791 | Don Edecio S. Venturanza Integrated School | BANGA | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500642 | Palay Integrated School | BATAN | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 302320 | Maloco NHS | IBAJAY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500639 | Baybay-Alibagon Integrated School | MAKATO | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115066 | Calacja II ES | HAMTIC | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115120 | Paningayan Primary School | LAUA-AN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115148 | Bonifacio Gella Candari Elementary School | PANDAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115196 | Igbarawan-Mabasa Elementary School | PATNONGON | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115259 | Bulan-Bulan ES | SAN REMIGIO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115345 | Martinez ES | TIBIAO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115374 | Igdurarog PS | TOBIAS FORNIER (DAO) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115389 | Bakiang ES | VALDERRAMA | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117455 | Bata Elementary School - I | BACOLOD CITY (Capital) | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117471 | Handumanan ES-1 | BACOLOD CITY (Capital) | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117488 | Don I. Nessia Sr. Elementary School | BACOLOD CITY (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 181005 | Handumanan Elementary School II | BACOLOD CITY (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bago City | 117526 | R & S Abindan ES | BAGO CITY | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117548 | Don Ricardo Jesena Sr. ES | CADIZ CITY | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117550 | F.M. Cabras ES | CADIZ CITY | 2nd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117551 | Floro L. Reboton ES | CADIZ CITY | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117574 | Gen. A. Lacson ES | CADIZ CITY | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 311402 | Caduha-an NHS - Tagbanon Ext. HS | CADIZ CITY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501437 | Tapulang Integrated School | MA-AYON | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501093 | Celestino D. Diaz Integrated School | PANITAN | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501100 | Guise Integrated School | PILAR | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 115696 | Feliciano Consing ES | PONTEVEDRA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 310804 | Maindang National High School | CUARTERO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 500429 | Aglalana Integrated School | DUMARAO | 2nd | 1 | - | - | 560 | 560 | 14 | - | - | 1925000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501096 | Manuel Ganzon Advincula Integrated School | JAMINDAN | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 115725 | Agkaningay PS | SAPI-AN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 501095 | Calixto Loyola Sr. Integrated School | SIGMA | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 115769 | Abangay ES | TAPAZ | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Escalante City | 501108 | Paitan Integrated School | CITY OF ESCALANTE | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115857 | Silvestra Galarpe Melgar Memorial School | SAN LORENZO | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115886 | Paaralan ng Buhay ng Naoway | SIBUNAG | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Himamaylan City | 302587 | Aguisan NHS | CITY OF HIMAMAYLAN | 5th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Himamaylan City | 302610 | Carabalan NHS | CITY OF HIMAMAYLAN | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Himamaylan City | 501798 | Tugas Integrated School | CITY OF HIMAMAYLAN | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117024 | Don H. Maravilla MS | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302622 | Enrique B. Magalona NHS - Consing Ext. | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302609 | Cansilayan Farm School | MURCIA | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117423 | Ayungon ES | VALLADOLID | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 116866 | Binalbagan ES | BINALBAGAN | 5th | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117119 | Tagda ES | HINIGARAN | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302673 | Pahilanga National High School | HINIGARAN | 5th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117185 | Bulad ES | ISABELA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302655 | Isabela National High School-Sikatuna Extension | ISABELA | 5th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117213 | Don Generoso M. Villanueva ES | LA CASTELLANA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117222 | Mansalanao ES | LA CASTELLANA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6th | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 116966 | Isio ES | CAUAYAN | 6th | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117157 | Paz Vda. de Escamilla ES | HINOBA-AN (ASIA) | 6th | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117159 | San Rafael ES | HINOBA-AN (ASIA) | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117160 | Talacagay ES | HINOBA-AN (ASIA) | 6th | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6th | 1 | - | 2205 | - | 2205 | 49 | - | - | 7546000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302614 | Culipapa National High School | HINOBA-AN (ASIA) | 6th | 1 | - | 1260 | - | 1260 | 28 | - | - | 4312000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302688 | Tabu NHS | ILOG | 6th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302689 | Tabu NHS - Canlamay Extension | ILOG | 6th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Passi City | 117904 | Maasin Elementary School | CITY OF PASSI | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Passi City | 302805 | Passi National High School | CITY OF PASSI | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Passi City | 312203 | Agdahon Farm School | CITY OF PASSI | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 117666 | Banica Elementary School | ROXAS CITY (Capital) | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 117670 | Mongpong ES | ROXAS CITY (Capital) | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 302758 | Culasi NHS | ROXAS CITY (Capital) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 500193 | Marcos Fuentes IS | ROXAS CITY (Capital) | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 500194 | Inzo Arnaldo Village Integrated School | ROXAS CITY (Capital) | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Roxas City | 501073 | Lawa-an Integrated School | ROXAS CITY (Capital) | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sagay City | 117695 | Buenaventura Rodriguez Elementary School | SAGAY CITY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sagay City | 311801 | Old Sagay National High School | SAGAY CITY | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sagay City | 311801 | Old Sagay National High School | SAGAY CITY | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 117776 | Iliranan IS | SAN CARLOS CITY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 117790 | Mabato ES | SAN CARLOS CITY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 117794 | Lina dela Viña Valmayor ES | SAN CARLOS CITY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 502281 | Iliranan Integrated School | SAN CARLOS CITY | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 502282 | Lamesa Integrated School | SAN CARLOS CITY | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | San Carlos City | 502285 | Talave Integrated School | SAN CARLOS CITY | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Silay City | 117814 | Eustaquio Lopez Elementary School | SILAY CITY | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Silay City | 117821 | Guimbala-on ES | SILAY CITY | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sipalay City | 117365 | Barasbarasan Elementary School - Indangawan Annex | CITY OF SIPALAY | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sipalay City | 117376 | Macarandan ES | CITY OF SIPALAY | 6th | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Sipalay City | 302636 | Gil Montilla NHS - Camindangan Ext. | CITY OF SIPALAY | 6th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Victorias City | 117436 | Alejandro Acuña Yap Quiña ES | CITY OF VICTORIAS | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Victorias City | 117442 | P. A. Cuaycong ES | CITY OF VICTORIAS | 3rd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Victorias City | 302698 | Victorias NHS - Gaston Ext. | CITY OF VICTORIAS | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bais City | 120076 | Dansulan ES | BAIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bais City | 120083 | Basak Elementary School | BAIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bais City | 120095 | Mabunao Elementary School | BAIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bais City | 120104 | San Vicente Elementary School | BAIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 120107 | Basay Central School | BASAY | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 303217 | Basay National High School | BASAY | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 120135 | Omod Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 120138 | Senator Lorenzo G. Teves Memorial Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 321911 | Abundio Agarpao, Sr. Memorial High School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bogo City | 119107 | Bogo Central School 111 | CITY OF BOGO | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bogo City | 302931 | Binabag NHS | CITY OF BOGO | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bogo City | 302932 | Cayang NHS | CITY OF BOGO | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4th | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302872 | Lourdes NHS | PANGLAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118033 | Mandawa ES | BIEN UNIDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118112 | Cambane ES | CANDIJAY | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118157 | Tuan Elementary School | CARMEN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118302 | Taytay Elementary School | DUERO | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118354 | Cansiwang ES | GUINDULMAN | 3rd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118429 | Mayana ES | JAGNA | 3rd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118450 | Tambangan ES | LOAY | 3rd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118459 | Buenavista ES | LOBOC | 3rd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118515 | Bulawan Elementary School | MABINI | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118585 | San Vicente ES | PILAR | 3rd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118851 | Botong ES | VALENCIA | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City | 120197 | Aquino Elementary School | CANLAON CITY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City | 120210 | Manggapa Elementary School | CANLAON CITY | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City |  | Carmen Elementary School | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City |  | Ninoy Aquino HS | CANLAON CITY | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City |  | Bucalan HS | CANLAON CITY | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City |  | Everlasting ES | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 137085 | San Miguel Primary School | CORDOVA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119477 | Minglanilla Central ES | MINGLANILLA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119722 | Sibonga Central ES | SIBONGA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119378 | Kabalaasnan ES | DUMANJUG | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119285 | Pantao ES | DAANBANTAYAN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119421 | Tayud Elementary School | LILOAN | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119239 | Danglag Elementary School | CONSOLACION | 6th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA | 6th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119892 | Camp Lapu-Lapu ES | CEBU CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119868 | Punta Princesa ES | CEBU CITY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119880 | Guadalupe ES | CEBU CITY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119885 | Labangon Bliss ES | CEBU CITY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119916 | Sawang Calero ES | CEBU CITY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 500229 | Cantipla IS | CEBU CITY (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 500231 | Sibugay ES | CEBU CITY (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | City of Naga, Cebu | 119524 | Uling Elementary School | CITY OF NAGA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Danao City | 119357 | Severo Duterte Memo. ES | DANAO CITY | 5th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Danao City | 500041 | Eduardo Gorre Memo. Integrated School | DANAO CITY | 5th | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Danao City | 500447 | BINALIW INTEGRATED SCHOOL | DANAO CITY | 5th | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 136947 | Puti-an Elementary School | VALLEHERMOSO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119960 | Talima Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119969 | Punta Engaño Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119973 | Agus Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119974 | Bagong Silang Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119975 | Basak Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119984 | Sudtonggan Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119985 | Babag I Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119987 | Canjulao Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119990 | Look Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 303180 | Marigondon National High School | LAPU-LAPU CITY (OPON) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Mandaue City | 120001 | Opao ES | MANDAUE CITY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Mandaue City | 120002 | Paknaan ES | MANDAUE CITY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Mandaue City | 120018 | Don Calixto C. Yongco, Sr. ES (Tawason ES) | MANDAUE CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120032 | Awa-an ES | AYUNGON | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120178 | Canluto ES | BINDOY (PAYABON) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120309 | Yli Elementary School | JIMALALUD | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120323 | Mandapaton ES | LA LIBERTAD | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 303258 | Pacuan National High School | LA LIBERTAD | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120393 | Managba ES | MANJUYOD | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120406 | Tupas ES | MANJUYOD | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 312957 | Amlan NHS-Jugno Campus | AMLAN (AYUQUITAN) | 2nd | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120359 | Hagtu Elementary School | MABINAY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120368 | Manlingay Elementary School | MABINAY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120483 | Balugo Elementary School | SIBULAN | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120609 | Bong-ao Elementary School | VALENCIA (LUZURRIAGA) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 501427 | Larena Integrated School | LARENA | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120668 | Campalanas Elementary School | LAZI | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120708 | Tag-ibo Elementary School | SAN JUAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120689 | Banban Elementary School | SIQUIJOR (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 303360 | Caridad National High School | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 303420 | Pomponan National High School | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 121079 | Baybay I CS (Baybay North CS) | CITY OF BAYBAY | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 121102 | Baybay II Central School | CITY OF BAYBAY | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 500672 | Gabas Integrated School | CITY OF BAYBAY | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 500746 | Mapgap Integrated School | CITY OF BAYBAY | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 303500 | E. Samar NCHS | CITY OF BORONGAN (Capital) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 303500 | Eastern Samar National Comprehensive High School | CITY OF BORONGAN (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 123986 | Caballero Elementary School | CALBAYOG CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 124008 | Carmen Elementary School | CALBAYOG CITY | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 124141 | San Joaquin Central Elementary School | CALBAYOG CITY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 313801 | Calbayog City National High School | CALBAYOG CITY | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Catbalogan City | 123424 | Cinco Elementary School | CITY OF CATBALOGAN (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational High School | DOLORES | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122606 | Balangkayan Central Elementary School | BALANGKAYAN | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122413 | Can-avid Central Elementary School | CAN-AVID | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122484 | Gen. MacArthur Central Elementary School | GENERAL MACARTHUR | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303503 | Guiuan National High School | GUIUAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial National High School | HERNANI | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122575 | Jipapad Central School | JIPAPAD | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122625 | Maydolong Central Elementary School | MAYDOLONG | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122668 | Oras West Central Elementary School | ORAS | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122700 | Salcedo Central Elementary School | SALCEDO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122731 | San Julian Central Elementary School | SAN JULIAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303336 | Alangalang National High School | ALANGALANG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 122171 | Pinascohan MGS | CITY OF MAASIN (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 303457 | Guadalupe National High School | CITY OF MAASIN (Capital) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 323101 | Ibarra National High School | CITY OF MAASIN (Capital) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 500399 | Asuncion Integrated School | CITY OF MAASIN (Capital) | 1st | 1 | - | 120 |  | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 303454 | Dongon National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 303469 | Manhilo National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 313401 | Maasin City National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Maasin City | 501052 | Canyuom Integrated School | CITY OF MAASIN (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122820 | Capul I CS | CAPUL | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122826 | Oson ES | CAPUL | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122853 | Washington ES | CATARMAN (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122873 | Polangi ES | CATARMAN (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 303545 | Rosario Lim Uy National High School | CATARMAN (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 303587 | Washington NHS | CATARMAN (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 500236 | Cawayan Integrated School | CATARMAN (Capital) | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123058 | Barobaybay ES | LAVEZARES | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123066 | Libertad ES | LAVEZARES | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 305818 | Ruperto S. Sampayan National High School | SAN ISIDRO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123228 | P. Tingzon ES | SAN JOSE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123249 | Sila ES | SAN VICENTE | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123250 | Tarnate ES | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122898 | Hibubullao CS | CATUBIG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 303553 | Bangon NHS | GAMAY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 303557 | Laoang NHS | LAOANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 313613 | La Perla NHS | LAOANG | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 313624 | Oleras NHS | LAOANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 122998 | Mabini ES | LAPINIG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123147 | Campedico ES | PALAPAG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123150 | Dona PC Gorgonia ES | PALAPAG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123163 | Pangpang IS | PALAPAG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 123185 | Nagbobtac ES | PALAPAG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Northern Samar | 313612 | Malobago - Pagsang-an NHS | SAN ROQUE | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124150 | Dolores ES | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124158 | Liberty IS | ORMOC CITY | 4th | 1 |  | 40 |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124161 | San Antonio IS | ORMOC CITY | 4th | 1 |  | 230 |  | 230 | 6 | - | - | 792000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124162 | Magaswe IS | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124173 | Cabaonaon ES | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124186 | Monterico IS | ORMOC CITY | 4th | 1 |  | 40 |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124190 | San Jose Central School | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124202 | Cabintan ES | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124215 | Margen ES | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124218 | Salvacion ES | ORMOC CITY | 4th | 1 | 40 |  |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124219 | San Isidro Integrated School | ORMOC CITY | 4th | 1 |  | 480 |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 124223 | Sto Nino ES | ORMOC CITY | 4th | 1 | 60 |  |  | 60 | 2 | - | - | 209000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 303656 | Linao NHS | ORMOC CITY | 4th | 1 |  | 80 |  | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 303658 | NOCNHS | ORMOC CITY | 4th | 1 |  | 80 |  | 80 | 1 | - | - | 269500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 303662 | Valencia National High School | ORMOC CITY | 4th | 1 |  | 90 |  | 90 | 1 | - | - | 302500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 305904 | Salvacion NHS | ORMOC CITY | 4th | 1 |  | 40 |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 330523 | Ormoc City Senior High School | ORMOC CITY | 4th | 1 |  |  | 90 | 90 | 1 | - | - | 302500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 501363 | Mas-in IS | ORMOC CITY | 4th | 1 |  | 80 |  | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 501364 | Gaas IS | ORMOC CITY | 4th | 1 |  | 80 |  | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Ormoc City | 502293 | Lao IS | ORMOC CITY | 4th | 1 |  | 40 |  | 40 | 1 | - | - | 137500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123285 | Almagro Central Elementary School | ALMAGRO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 303600 | Costa Rica National High School | ALMAGRO | 1st | 1 |  | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 501934 | Kerikite Integrated School | ALMAGRO | 1st | 1 |  | 90 |  | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 303612 | Matuguinao National High School | MATUGUINAO | 1st | 1 |  | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123651 | Buenos Aires Integrated School | PAGSANGHAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 313714 | Buenos Aires Integrated School | PAGSANGHAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123812 | Sto. Niño Central Elementary School | SANTO NIÑO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123819 | Labangbaybay Elementary School | TAGAPUL-AN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123358 | Barobaybay Elementary School | CALBIGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123365 | Calbiga Central Elementary School | CALBIGA | 2nd | 1 | 90 |  |  | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123584 | Camarubo-an Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123585 | Candayao Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123586 | Cantongtong Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123593 | Jiabong Central Elementary School | JIABONG | 2nd | 1 | 45 |  |  | 45 | 1 | - | - | 154000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123597 | Malino Elementary School | JIABONG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123601 | Parina Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123607 | Victory Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 313711 | Casapa National High School | JIABONG | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123713 | Bontod Elementary School | SAN SEBASTIAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123721 | San Sebastian Central Elementary School | SAN SEBASTIAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 501372 | Tatabunan Integrated School | TALALORA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123973 | Maputi Elementary School | ZUMARRAGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 123984 | Zumarraga Central Elementary School | ZUMARRAGA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Samar (Western Samar) | 313707 | Bioso Integrated School | ZUMARRAGA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122029 | Catublian Elementary School | HINUNANGAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122031 | Hinunangan West Central School | HINUNANGAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 305496 | Sto. Niño National High School | HINUNANGAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303472 | Rito Monte de Ramos Sr. MHS (Nahaong NHS) | LIBAGON | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303459 | Himay-angan NHS | LILOAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122232 | Buenavista Elementary School | PINTUYAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122288 | Himbangan ES | SAINT BERNARD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122307 | Tambis II Multi-Grade Elementary School | SAINT BERNARD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 313407 | New Guinsaugon National High School | SAINT BERNARD | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122108 | Pinamudlan Elementary School | SAN FRANCISCO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 192021 | Anislagon Primary School | SAN FRANCISCO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122250 | Garsavic Elementary School | SAN JUAN (CABALIAN) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 305494 | San Isidro National High School | SOGOD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 501047 | Kahupian Integrated School | SOGOD | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303462 | Ichon National High School | MACROHON | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 192030 | Mahika Elementary School | SAINT BERNARD | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303490 | Tambis NHS | SAINT BERNARD | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 313407 | New Guinsaugon National High School | SAINT BERNARD | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122090 | Bongbong Elementary School | SAN FRANCISCO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122104 | Marayag Elementary School | SAN FRANCISCO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 122235 | Esperanza Elementary School | SAN RICARDO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Southern Leyte | 303449 | Consolacion National High School | SOGOD | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 102307 | New Hope Elementary School | TACLOBAN CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 124225 | Judge Antonio R. Montilla, Sr. Elementary School | TACLOBAN CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 124260 | Sto. Nino SPED Center | TACLOBAN CITY (Capital) | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 303663 | Leyte National High School | TACLOBAN CITY (Capital) | 1st | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 500490 | Kapuso Village Integrated School | TACLOBAN CITY (Capital) | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City | 500891 | North Hill Arbours Integrated School | TACLOBAN CITY (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City |  | Saint Francis Integrated School | TACLOBAN CITY (Capital) | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Tacloban City |  | Anibong Dreamville Elementary School | TACLOBAN CITY (Capital) | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126265 | Danatag ES | BAUNGON | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126519 | Dona Pilar ES | LIBONA | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126643 | San Miguel ES | MANOLO FORTICH | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 500676 | DAGUMBAAN INTEGRATED SCHOOL | TALAKAG | 1st | 1 | - | - | 560 | 560 | 14 | - | - | 1925000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126504 | Cawayan ES | LANTAPAN | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126512 | Valbueco ES | LANTAPAN | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126756 | Kalagangan CES | SAN FERNANDO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126764 | Mahayag ES | SAN FERNANDO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126436 | Gutapol ES | KIBAWE | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126475 | Kitaotao CES | KITAOTAO | 3rd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127959 | Bayabas Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127972 | Bayanga Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127977 | Lumbia Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127987 | Upper Tignapoloan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 128003 | Iponan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 306046 | Pigsag-an National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 502012 | Balongkot Integrated School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127942 | East City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127943 | FS Catanico Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127944 | Gusa Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127954 | Tablon Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127964 | Camaman-an Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127965 | Indahag Elementary School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 304116 | Indahag National High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 500684 | Bugang Integrated School | SAGAY | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127667 | Amoros ES | CITY OF EL SALVADOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127668 | Bolisong ES | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127671 | El Salvador City CS | CITY OF EL SALVADOR | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127681 | Ulaliman Elementary School | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 500799 | Pigsalohan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 500800 | Dukdokaan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2nd | 1 |  | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126548 | Mapulo Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126557 | Aglayan Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126558 | Bangcud Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126572 | San Roque Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126582 | Kalasungay Central School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501188 | Kibalabag Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501189 | Capitan Angel Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501190 | Magsaysay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501581 | Tuburan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501582 | Simaya Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501852 | Mabuhay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 501236 | MANSABAY ALTO IS | LOPEZ JAENA | 1ST | 1 | - | - | 180 | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127527 | Masubong Primary School | SAPANG DALAGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127602 | Balingasag CS | BALINGASAG | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127603 | Baliwagan CS | BALINGASAG | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127741 | C.Gadrinab ES | LAGONGLONG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127743 | Gaston ES | LAGONGLONG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127744 | Kabulawan ES | LAGONGLONG | 1st | 1 | - | 118 | - | 118 | 3 | - | - | 405900 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127750 | Tabok ES | LAGONGLONG | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 380 | - | 380 | 8 | - | - | 1298000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127783 | Kibungsod CS | MAGSAYSAY (LINUGOS) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127823 | Medina CS | MEDINA | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127855 | Inobulan ES | SALAY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127715 | Ampianga ES | SUGBONGCOGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127724 | Kaulayanan ES | SUGBONGCOGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127874 | Babanlagan ES | TALISAYAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304091 | Misamis Oriental General Comprehensive High School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 3080000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127712 | San Nicolas ES | JASAAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127926 | Lugait CS | LUGAIT | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127805 | Manticao CS | MANTICAO | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127935 | Naawan CS | NAAWAN | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127835 | Barra ES | OPOL | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 501747 | Malanang Integrated School | OPOL | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127872 | Sta. Cruz ES | TAGOLOAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 127437 | Oroquieta City CES | OROQUIETA CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 127474 | Vicente Flores MES | OROQUIETA CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 304047 | Oroquieta City NHS - Villaflor Campus | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 304049 | Rizal NHS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Oroquieta City | 500402 | Dullan IS | OROQUIETA CITY (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Ozamis City | 128181 | Felipe Carreon Central School | OZAMIS CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Tangub City | 128219 | Banglay Elementary School | TANGUB CITY | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Tangub City | 128238 | Aquino ES | TANGUB CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Tangub City | 128240 | Balatacan ES | TANGUB CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Tangub City | 501029 | Bintana Integrated School | TANGUB CITY | 2nd | 1 | - | - | 440 | 440 | 11 | - | - | 1512500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 126839 | Dabongdabong ES | CITY OF VALENCIA | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 126873 | Laligan Central School | CITY OF VALENCIA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 126874 | Lumbayao ES | CITY OF VALENCIA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 314909 | Guinuyoran National High School | CITY OF VALENCIA | 4th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 500703 | Dagat-Kidavao IS | CITY OF VALENCIA | 4th | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 501120 | Batangan Integrated School | CITY OF VALENCIA | 4th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Valencia City | 501122 | Lumbo Integrated School | CITY OF VALENCIA | 4th | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 304240 | Linao National High School | SAN ISIDRO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128818 | New Clarin Elementary School | BANSALAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128835 | Vicente Duterte Elementary School | BANSALAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 305510 | Zosimo S. Magdadaro National High School | KIBLAWAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128936 | Magsaysay Central Elementary School | MAGSAYSAY | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 305779 | Bolton National High School | MALALAG | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 129018 | New Katipunan Elementary School | MATANAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 129049 | Padada Central Elementary School | PADADA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 129076 | Astorga Central Elementary School | SANTA CRUZ | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 129099 | Santa Cruz Central Elementary School | SANTA CRUZ | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 304297 | Sulop National High School | SULOP | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 501416 | Aldo Pagagao Integrated School | JOSE ABAD SANTOS (TRINIDAD) | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 304276 | Heracleo Casco Memorial National High School | SANTA MARIA | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 205028 | Kibatang ES | DON MARCELINO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 501080 | Tingolo Integrated School | MALITA | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 304316 | Dr. Beato C. Macayra National High School | BAGANGA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 304304 | Boston National High School | BOSTON | 1st | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 304307 | Caraga National High School | CARAGA | 1st | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 304334 | Sangab National High School | CARAGA | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 501419 | Bantay Integrated School | CARAGA | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 501958 | Baugo Integrated School | CARAGA | 1st | 1 | - | - | 440 | 440 | 11 | - | - | 1512500 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 304310 | San Antonio National High School | CATEEL | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 501608 | Modesto T. Veroy, Sr. Integrated School | CATEEL | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129348 | Anastacio P. Mamada Elementary School | MANAY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129426 | Dugmanon Elementary School | SAN ISIDRO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Island Garden City of Samal | 128606 | Mambago-B Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Island Garden City of Samal | 128608 | San Antonio Elementary School | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 102164 | Talucanga Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129380 | Rabat-Rocamora Mati CES I | CITY OF MATI (Capital) | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129395 | Don Luis Rabat Sr. MS | CITY OF MATI (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129399 | Don Enrique Lopez ES | CITY OF MATI (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129404 | Tagbinonga ES | CITY OF MATI (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129408 | Fausta Salazar Como MS | CITY OF MATI (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129408 | Fausta Salazar Como MS | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 304303 | Bobon NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 304318 | Libudon NHS (Sanghay Campus) | CITY OF MATI (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | CITY OF MATI (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 325105 | Macambol NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 500454 | Licop Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 400 | 400 | 10 | - | - | 1375000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 501085 | Cabuaya Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 501085 | Cabuaya Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 501087 | Luban Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 501087 | Luban Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 501424 | Culian Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 400 | 400 | 10 | - | - | 1375000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129781 | Cabili ES | CITY OF PANABO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129783 | Gredu ES | CITY OF PANABO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129784 | Panabo Central Elementary School SPED Center | CITY OF PANABO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129787 | San Pedro ES | CITY OF PANABO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129789 | A.O. Floirendo Elementary School | CITY OF PANABO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129812 | Little Panay ES | CITY OF PANABO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129814 | Malativas ES | CITY OF PANABO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 129819 | Sta. Cruz ES | CITY OF PANABO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Panabo City | 207003 | Antonio O. Floirendo Elementary School II | CITY OF PANABO | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131296 | H.N. Cahilsot Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131297 | Romana C. Acharon Central Elemetary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131321 | NASA Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131323 | Upper Tambler I Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 210012 | Jose R. Lansang Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 304636 | Antonino G. Busano, Sr. High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 304653 | Lagao National High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131326 | Kidapawan City Pilot Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131328 | Suerte MES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131344 | Lanao Central Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131358 | Paco Central Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 304667 | Onica National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 500309 | Binoligan Integrated School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 131391 | Magsaysay ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 131395 | Marbel 6 ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 317201 | Bacongco NHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 317205 | Esperanza National High School – Annex, San Jose Campus | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129828 | Marabuhay ES | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129833 | AMATAC ELEMENTARY SCHOOL | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129852 | Tawas-Abaga Elementary School | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129853 | Teren-Teren Elementary School | ALAMADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304412 | ALAMADA HIGH SCHOOL | ALAMADA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129955 | Wadya ES | BANISILAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304453 | Kibudtungan National High School | CARMEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130005 | Kabacan Pilot Central School | KABACAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130027 | Kapayawi ES | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130029 | Kitubod ES | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130038 | C. V. Cocal Annex Elementary School | LIBUNGAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130192 | VILLARICA ELEMENTARY SCHOOL | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130195 | CENTRAL BULANAN ES | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 207508 | San Pedro Elementary School | MIDSAYAP | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130267 | Lampaki ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130269 | Gallego ES (Malu-ao ES) | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130279 | Rogonan ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130286 | Cabpangi ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130287 | Capayuran ES | PIGKAWAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130330 | Pikit Central Elementary School | PIKIT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130698 | Maganod Elementary School | PIKIT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304509 | Sultan Memorial HS | PIKIT | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130051 | Datu Mantawil ES | MAGPET | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130077 | Inac ES | MAGPET | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130094 | Biangan Elementary School | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130095 | Buena Vida ES | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130101 | Luayon ES (Garing) | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130104 | Rodero ES | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130108 | Bato Elementary School | MAKILALA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304482 | New Caridad NVTHS | TULUNAN | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 2nd | 1 | - | 1530 | - | 1530 | 34 | - | - | 5236000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129938 | Kiaring ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129944 | Pantar ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129950 | Sabang ES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129951 | Salama CES | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129952 | Thailand Elementary School | BANISILAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130255 | BAGONTAPAY CENTRAL ELEMENTARY SCHOOL | M'LANG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130405 | F. Cajelo ES | TULUNAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 55% Allocation for Regular Supplier |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 501757 | Lam-ayan Integrated School | BUGUIAS | Lone | 1 | - | - | 560 | 560 | 14 | - | - | 1925000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135517 | Balatoc Elementary School | ITOGON | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 305126 | Ampucao National High School | ITOGON | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 305539 | AMBIONG NATIONAL HIGH SCHOOL | LA TRINIDAD (Capital) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135741 | Awayan ES | AGUINALDO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135819 | Cambulo ES - Mattao Annex | BANAUE | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135845 | Umalbong ES | HINGYON | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135879 | Banga ES | LAGAWE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135888 | Luta PS | LAGAWE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135922 | Buninan PS | MAYOYAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135936 | Nattum PS (Abagong) | MAYOYAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 135970 | Bullalayao Primary School | BALBALAN | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 306053 | Eastern Balbalan National High School | BALBALAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 319116 | Balbalan National High school | BALBALAN | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 319116 | Balbalan National High school | BALBALAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 135989 | Dangoy Elementary School | LUBUAGAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136014 | Bagtayan Elementary School | PASIL | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136049 | Malaap Elementary School | PINUKPUK | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 305210 | Limos National High School - Dao-angan Extension | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 305542 | Malagnat National High School-Taggay Extension | PINUKPUK | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School-Pinococ Extension | PINUKPUK | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 319107 | Camalog National High School | PINUKPUK | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Malagnat NHS | PINUKPUK | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136071 | Kinama Elementary School | RIZAL (LIWAN) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136076 | Rizal Central School | RIZAL (LIWAN) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 305218 | Macutay Palao National High School | RIZAL (LIWAN) | Lone | 1 | - | 675 | - | 675 | 15 | - | - | 2310000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Bagbag Elementary School Bulbul Annex | RIZAL (LIWAN) | Lone | 1 | 160 | - | - | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Rizal Central School Cadao Annex | RIZAL (LIWAN) | Lone | 1 | 120 | - | - | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | NOT-IN-NSBI | Santor NHS | RIZAL (LIWAN) | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136123 | Dacalan Elementary School | TANUDAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136126 | Lubo Elementary School | TANUDAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Kalinga | 136143 | Ambato-Legleg Elementary School | TINGLAYAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131474 | Mat-i CES | LAS NIEVES | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131417 | Carmen CES | CARMEN | 2nd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131418 | Cervantina ES | CARMEN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131419 | Dona Josefa Antillon ES | CARMEN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131424 | San Agustin ES | CARMEN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131426 | Tagcatong Elementary School | CARMEN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131433 | Jabonga Central Elementary School | JABONGA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131481 | Buhang ES | MAGALLANES | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131500 | Nasipit CES | NASIPIT | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131581 | Beto ES | TUBAY | 2nd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 132619 | Mabog Elementary School | CITY OF BISLIG | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 132838 | Caramcam Elementary School | CITY OF BISLIG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 132842 | Paler Lumayog Elementary School | CITY OF BISLIG | 2nd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 305746 | Francisco C. Jongko National High School | CITY OF CABADBARAN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 317312 | La Union National High School | CITY OF CABADBARAN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 501724 | Chief Justice Ramon Avancena Integrated School | CITY OF CABADBARAN | 2nd | 1 | - | - | 520 | 520 | 13 | - | - | 1787500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 502134 | Alfonso B. Dagani ES | CITY OF CABADBARAN | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136431 | T. Paez Integrated School (Elem.) | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136432 | J. P. Rizal Elementary School | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136434 | Gen. Vicente Lim Elementary School | TONDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136440 | J. C. de Jesus Elementary School | TONDO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136441 | R. Almario Elementary School | TONDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305288 | Dr. Juan G. Nolasco High School | TONDO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305289 | T. Paez Integrated School | TONDO | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305290 | Gregorio Perfecto High School | TONDO | 1st | 1 | - | 169 | - | 169 | 4 | - | - | 579700 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305292 | Antonio J. Villegas Vocational High School | TONDO | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136419 | Barrio Obrero Elementary School | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136420 | F. G. Calderon Elementary School | TONDO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136426 | Francisco Benitez Elementary School | TONDO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136427 | Lakan Dula Elementary School | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136429 | Librada Avelino ES | TONDO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136444 | Gen. Maximo Hizon Elementary School | TONDO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3rd | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305303 | Raja Soliman Science and Technology High School | SAN NICOLAS | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305312 | Manila Science High School | ERMITA | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305311 | Manila High School | INTRAMUROS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136477 | Aurora A. Quezon Elementary School | MALATE | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136478 | H.J. Atienza Elementary School | MALATE | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136473 | Justo Lukban Elementary School | PACO | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 319401 | Pres. Corazon C. Aquino High School/Manila HS Annex | PORT AREA | 5th | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 101166 | Alaminos Central School | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 101191 | Popantay ES | CITY OF ALAMINOS | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 101196 | San Vicente ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 101200 | Telbang ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 300157 | Alos National High School | CITY OF ALAMINOS | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 300260 | Telbang National High School | CITY OF ALAMINOS | 1st | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 500564 | Pangapisan Integrated School | CITY OF ALAMINOS | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Batac City | 340748 | Ferdinand E. Marcos SHS | CITY OF BATAC | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100427 | Ayudante Elementary School | CITY OF CANDON | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100444 | Parioc Elementary School | CITY OF CANDON | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 102163 | Bolosan ES | DAGUPAN CITY | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 102165 | Bonuan Buquig ES | DAGUPAN CITY | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 102170 | North Central Elementary School | DAGUPAN CITY | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 102175 | Carael ES | DAGUPAN CITY | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 500054 | Federico N. Ceralde Integrated School | DAGUPAN CITY | 4th | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 500055 | Pugaro Integrated School | DAGUPAN CITY | 4th | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100017 | Calioet ES | BACARRA | 1st | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100018 | Casilian ES | BACARRA | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100049 | Dadaor ES | BANGUI | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100052 | Masikil ES | BANGUI | 1st | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100103 | BLISS ELEMENTARY SCHOOL | BURGOS | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100109 | Tanap ES | BURGOS | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100172 | Pagudpud South CES | PAGUDPUD | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100179 | Tarrag PS | PAGUDPUD | 1st | 1 | 495 | - | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100212 | Sulbec PS | PASUQUIN | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100214 | Tabungao ES | PASUQUIN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100270 | San Bernabe ES | SARRAT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 150015 | San Andres Elementary School | SARRAT | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100296 | Esperanza ES | VINTAR | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100298 | Gubang ES | VINTAR | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 150014 | Mabanbanag PS | VINTAR | 1st | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100031 | Lasien School | BADOC | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103573 | Turod Elementary School | QUEZON | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103587 | Santiago Elementary School | QUIRINO | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103635 | Matusalem Elementary School | ROXAS | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 300612 | Echague National High School | ECHAGUE | 6th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 103999 | Tiblac ES | AMBAGUIO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 300525 | Tiblac National High School | AMBAGUIO | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 501901 | Dulli Integrated School | AMBAGUIO | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 502194 | Balong IS | AMBAGUIO | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 300620 | Bambang NHS | BAMBANG | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 501941 | Sto. Domingo IS | BAMBANG | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Nueva Vizcaya | 104078 | Biyoy ES | KASIBU | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 501566 | Eden Integrated School | CABARROGUIS (Capital) | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 104307 | Luttuad ES | DIFFUN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 156507 | Turayok Elementary School | DIFFUN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 500104 | San Antonio Integrated School | DIFFUN | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 501560 | Gulac Integrated School | DIFFUN | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 300654 | Balligui HS | MADDELA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Quirino | 500103 | Divisoria Sur IS | MADDELA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 306908 | Diosdado Macapagal HS | MEXICO | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300874 | Bahay Pare NHS | CANDABA | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 306920 | Macabebe High School | MACABEBE | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300935 | Sta. Maria NHS, Minalin | MINALIN | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300936 | Sto. Rosario NHS | MINALIN | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 306918 | San Simon High School | SAN SIMON | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300924 | San Matias NHS | SANTO TOMAS | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 107168 | Camp Olivas Elementary School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 107194 | Mansgold Elementary School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 107200 | Sto. Nino Elementary School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 500139 | St. Vincent of Quebiawan Integrated School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 500142 | San Nicolas Integrated School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 137170 | SAMPUGU Elementary School | SAN JOSE CITY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 300833 | Porais National High School | SAN JOSE CITY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 300868 | Tondod National High School | SAN JOSE CITY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 306076 | Tayabo High School | SAN JOSE CITY | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 306077 | Kita-Kita High School | SAN JOSE CITY | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 306817 | Caanawan National High School | SAN JOSE CITY | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 501238 | San Agustin Integrated School | SAN JOSE CITY | 2nd | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Science City of Muñoz | 105548 | Maligaya ES | SCIENCE CITY OF MUÑOZ | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Science City of Muñoz | 500395 | Gabaldon IS | SCIENCE CITY OF MUÑOZ | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1100000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Science City of Muñoz | 500398 | Palusapis IS | SCIENCE CITY OF MUÑOZ | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300973 | Birbira High School | CAMILING | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300969 | Mababanaba High School | SAN JOSE | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300967 | La Paz NHS | LA PAZ | 3rd | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 106702 | Maliwalo CES | CITY OF TARLAC (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 106714 | Baras Baras ES | CITY OF TARLAC (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 106774 | Felicidad Magday ES | CITY OF TARLAC (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 500390 | Armenia IS | CITY OF TARLAC (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 500555 | Batangbatang IS | CITY OF TARLAC (Capital) | 2nd | 1 | - | - | 40 | 40 | 1 | - | - | 137500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 500556 | Burot Integrated School | CITY OF TARLAC (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106953 | Rabanes Elementary School | SAN MARCELINO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 501183 | Laoag Integrated School | SAN MARCELINO | 1st | 1 | - | - | 246 | 246 | 6 | - | - | 844800 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106830 | Laoag Elementary School | CABANGAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106849 | San Roque Elementary School | CANDELARIA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 500127 | Pamibian IS | CANDELARIA | 2nd | 1 | - | 90 | 240 | 330 | 6 | - | - | 1122000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106871 | Dampay Elementary School | IBA (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106873 | Iba Elementary School | IBA (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 160502 | ADBSA Elementary School | IBA (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 501606 | Sta Barbara Integrated School | IBA (Capital) | 2nd | 1 | - | 90 | 320 | 410 | 8 | - | - | 1397000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106986 | Sta. Cruz North Central School | SANTA CRUZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106999 | Sta. Cruz South Central School | SANTA CRUZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 301014 | Guisguis National High School | SANTA CRUZ | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Rizal | 308135 | Southville 8C National High School | RODRIGUEZ (MONTALBAN) | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 109771 | San Marcos Elementary School | SAN PABLO CITY | 3rd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 109785 | Sta. Monica Elementary School | SAN PABLO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 109786 | Sta. Veronica Elementary School | SAN PABLO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 109791 | SAN PABLO CENTRAL SCHOOL | SAN PABLO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 301507 | Dolores National High School | SAN PABLO CITY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pablo City | 301510 | Sto. Angel National High School | SAN PABLO CITY | 3rd | 1 | - | 500 | - | 500 | 11 | - | - | 1710500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pedro City | 108420 | Cuyab Elementary School | SAN PEDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pedro City | 108422 | Laguna Resettlement Community School | SAN PEDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | San Pedro City | 301256 | Pacita Complex NHS | SAN PEDRO | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Sta. Rosa City | 307902 | Santa Rosa Science & Technology High School | CITY OF SANTA ROSA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Sto.Tomas City | 107718 | Sta. Maria Elementary School | SANTO TOMAS | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tanauan City | 107748 | Bagumbayan ES | CITY OF TANAUAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tanauan City | 107749 | Balele ES | CITY OF TANAUAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tanauan City | 107766 | Maria Paz ES | CITY OF TANAUAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tanauan City | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tayabas City | 137190 | Mayuwi Community School | CITY OF TAYABAS | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tayabas City | 301381 | Rosario Quesada Integrated National High School | CITY OF TAYABAS | 1st | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Tayabas City | 301416 | West Palale National High School | CITY OF TAYABAS | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Calapan City | 111536 | Calapan Central School | CITY OF CALAPAN (Capital) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 301535 | Buenavista NHS | BUENAVISTA | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 301531 | Bangbang National High School | GASAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 301557 | Mogpog National Comprehensive High School | MOGPOG | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110084 | Filomeno Jimenez ES | CALINTAAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110088 | Nayong Kalikasan Elementary School | CALINTAAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110254 | San Roque 2 ES | SAN JOSE | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301600 | Central NHS | SAN JOSE | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 308901 | San Jose National Agricultural and Industrial High School | SAN JOSE | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301603 | Santa Cruz NHS | SANTA CRUZ | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 110320 | Benito Villar MS | BACO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301616 | Baco NHS | BACO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro |  | Baco National High School Tabon-tabon Annex | BACO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301614 | Aurora NHS | NAUJAN | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301645 | Naujan Municipal High School | NAUJAN | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301648 | Porfirio Comia MNHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 309010 | Laguna NHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 309004 | Puerto Galera NHS | PUERTO GALERA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301653 | San Teodoro NHS | SAN TEODORO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 110683 | Socorro CS | SOCORRO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301634 | Leuteboro NHS | SOCORRO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301610 | Alcadesma NHS | BANSUD | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 309019 | Pag-asa NHS | BANSUD | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301695 | Gaudencio E. Abordo Mem. National High School | AGUTAYA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110981 | Claudio Sandoval Elementary School | CORON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110989 | Marcilla Elementary School | CORON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301684 | Coron School of Fisheries | CORON | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301685 | Borac National High School | CORON | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 301687 | Culion Sanitarium Special National High School | CULION | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110765 | Dalmacio Sadio Elementary School | Dumaran | 1st | 1 | 45 |  |  | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110784 | Sta. Teresita Elementary School | Dumaran | 1st | 1 | 80 |  |  | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 170582 | Malague Elementary School | Dumaran | 1st | 1 | 90 |  |  | 90 | 1 | - | - | 302500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 111023 | El Nido Central School | EL NIDO (BACUIT) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 502203 | Pag-asa Integrated School | KALAYAAN | 1st | 1 | - | - | 90 | 90 | 4 | - | - | 319000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 303936 | Tictapul NHS | ZAMBOANGA CITY | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 305994 | Lamisahan National High School | ZAMBOANGA CITY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 305995 | Tigtabon National High School | ZAMBOANGA CITY | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124753 | Sipaloc ES | SIBUTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 303694 | Kanim NHS | SIBUTAD | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 314118 | Saluyong NHS | MANUKAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124482 | Minang ES | PRES. MANUEL A. ROXAS | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 303682 | Dohinob NHS | PRES. MANUEL A. ROXAS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 303731 | Diongan NHS | SIAYAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124763 | Fatima ES | SINDANGAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124318 | Sas Integrated School | GUTALAC | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124453 | Goin Elementary School | LILOY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 501730 | Lintangan Integrated School | SIBUCO | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124843 | Piacan ES | SIRAWAI | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125083 | Lower Bagong Tudela IPS | JOSEFINA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125388 | Pictoran ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 196032 | Sominot CES-SPED | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303818 | Subanen Agricultural NHS | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 124941 | Dimataling CES | DIMATALING | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 314206 | Diosdado Macapagal Memorial NHS | LAKEWOOD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125162 | Mala-Tiguha ES | LAPUYAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125348 | San Miguel CES & SPED Center | SAN MIGUEL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125415 | Tabina CES | TABINA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125450 | Busol ES | TIGBAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125461 | Nangan-nangan ES | TIGBAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | TIGBAO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125495 | Biu-os ES | VINCENZO A. SAGUN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125563 | Villacastor ES | BUUG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125566 | Diplahan CES | DIPLAHAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125581 | Pilar ES | DIPLAHAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125596 | Imelda CES | IMELDA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125743 | Olutanga CES | OLUTANGA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125774 | Payao CES | PAYAO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125852 | Sagay Elementay School | Talusan | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125800 | San Jose ES | ROSELLER LIM | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125803 | Sto. Rosario ES | ROSELLER LIM | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 125805 | Taruc ES | ROSELLER LIM | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 196526 | Gutayan ES | ROSELLER LIM | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 314319 | Sto. Rosario National High School | ROSELLER LIM | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga Sibugay | 501386 | Silingan Integrated School | ROSELLER LIM | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111601 | Banao ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111604 | Cagbulacao ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111607 | Damacan ES | BACACAY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111611 | Mapulang Daga ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111612 | Mataas ES | BACACAY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111614 | Nahapunan ES | BACACAY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111616 | Namantao ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111620 | Sula ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111622 | Tambongon ES | BACACAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111856 | Calbayog ES | Malilipot | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111859 | Salvacion ES | Malilipot | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111860 | San Antonio ES | Malilipot | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111874 | Estancia Elementary School | MALINAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111875 | Jonop Elementary School | Malinao | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 112064 | Baybay Elementary School | TIWI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 112072 | Maynonong Elementary School | TIWI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 112080 | Sugod Elementary School | TIWI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111651 | TAGAYTAY ELEMENTARY SCHOOL | CAMALIG | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111651 | TAGAYTAY ELEMENTARY SCHOOL | CAMALIG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111748 | Mamlad ES | JOVELLAR | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111751 | Salvacion ES | JOVELLAR | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111757 | Tinaldukan ES | JOVELLAR | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111763 | Linao Elementary School | LIBON | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111766 | Malabiga Elementary School | LIBON | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111783 | Alongong ES | LIBON | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111807 | Tambo ES | LIBON | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111905 | Badian ES | OAS | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111911 | Cagmanaba ES | OAS | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111925 | Tapel ES | OAS | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 111925 | Tapel ES | OAS | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Albay | 112005 | La Medalla ES | POLANGUI | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112151 | Jose Panganiban Elementary School | JOSE PANGANIBAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112152 | Regino A. Yet Elementary School | JOSE PANGANIBAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112155 | Parang Elementary School | JOSE PANGANIBAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112156 | San Mauricio Elementary School | JOSE PANGANIBAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112159 | Roman V. Heraldo ES | JOSE PANGANIBAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112161 | Dahican Elementary School | JOSE PANGANIBAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112197 | Agapito Racelis ES | LABO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112206 | Daguit Elementary School | LABO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112208 | Felix Asis Elementary School | LABO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112213 | Macogon Elementary School | LABO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112247 | Gumaus Elementary School | PARACALE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112260 | Tugos ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301890 | Batobalani National High School | PARACALE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301890 | Batobalani NHS | PARACALE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301912 | Tabas National High School | PARACALE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309621 | MAXIMO MANARANG HIGH SCHOOL | PARACALE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 173005 | Guitol ES | SANTA ELENA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301913 | Rizal NATIONAL HIGH SCHOOL | SANTA ELENA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309602 | Maulawin National High School | SANTA ELENA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309618 | San Pedro-Domingo Llarena HS | SANTA ELENA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112094 | Mangcamagong Elem. School | BASUD | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301889 | Basud National High School | BASUD | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112298 | Banocboc Elementary School | VINZONS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112300 | Calangcawan Norte ES | VINZONS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112308 | Mangcawayan Island ES | VINZONS | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112313 | Pinagtigasan ES | VINZONS | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112314 | Sto. Domingo ES | VINZONS | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112316 | Vinzons Pilot ES | VINZONS | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301892 | D. Q. Liwag NHS | VINZONS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301904 | MATANGO NATIONAL HIGH SCHOOL | VINZONS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301914 | Sabang NHS | VINZONS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301925 | Vinzons Pilot High School | VINZONS | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309604 | Eugenia M. Quintela Memorial High School | VINZONS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309620 | Sarah Jane Ferrer HS | VINZONS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 502249 | Pinagtigasan Calaguas Island Integrated School | VINZONS | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | CABUSAO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302536 | Nalundan NHS | GUIMBAL | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 501443 | Cabasi-Sta. Rosa Integrated School | GUIMBAL | 1st | 1 | - | - | 90 | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302542 | Oton National High School | OTON | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 115950 | Bancal ES | ALIMODIAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302540 | New Lucena National High School | NEW LUCENA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302468 | Buayahon-Bantay NHS | SANTA BARBARA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116111 | Maganhop PS | BINGAWAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | BINGAWAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116117 | Tubod PS | BINGAWAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302481 | CARVASANA NHS | CALINOG | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302501 | Esteban S. Javellana MHS | CALINOG | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 311019 | Binolusan Pequeño National High School | CALINOG | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116394 | Janiuay Pilot ES | JANIUAY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302478 | Calmay NHS | JANIUAY | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302478 | Calmay NHS | JANIUAY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116546 | Maasin CES | MAASIN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 311029 | Dagami National High School | MAASIN | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116594 | Abat Elementary School | MINA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116602 | Mina Central School | MINA | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 311015 | Calicuang NHS | DINGLE | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 501478 | Taminla Integrated School | DUEÑAS | 4th | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116323 | Dumangas CES | DUMANGAS | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116325 | Lacturan ES | DUMANGAS | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116332 | Alyag PS | DUMANGAS | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116343 | Paloc Sool ES | DUMANGAS | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302483 | Cayos NHS | DUMANGAS | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116066 | Del Pilar PS | BAROTAC VIEJO | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116067 | Gen. Luna ES | BAROTAC VIEJO | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5th | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116100 | Pasayan PS | BATAD | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 501483 | Bulak Integrated School | BATAD | 5th | 1 | - | - | 90 | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo City | 117588 | Iloilo Central ES | ILOILO CITY (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo City | 117602 | Sambag ES | ILOILO CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo City | 117619 | Baluarte ES | ILOILO CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo City | 117621 | I. Arroyo ES | ILOILO CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 117833 | Bugtong ES | CITY OF KABANKALAN | 6th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 117840 | Esteban R. Abada Memorial School - West SPED | CITY OF KABANKALAN | 6th | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 302795 | Locotan National High School | CITY OF KABANKALAN | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 117630 | Ayungon ES | LA CARLOTA CITY | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 117637 | Roberto Salas Benedicto ES | LA CARLOTA CITY | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 117640 | La Carlota North ES | LA CARLOTA CITY | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 117646 | Haguimit ES | LA CARLOTA CITY | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | La Carlota City | 183001 | Haguimit ES II | LA CARLOTA CITY | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 116901 | Calatrava I Central School | CALATRAVA | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 116914 | San Isidro ES | CALATRAVA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117327 | Bagong Silang ES | SALVADOR BENEDICTO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS | SALVADOR BENEDICTO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 501440 | Ecogan Integrated School | CALATRAVA | 2nd | 1 | - | - | 400 | 400 | 10 | - | - | 1375000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302618 | Don Simplicio Lizares Memorial High School | CITY OF TALISAY | 3rd | 1 | - | 585 | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3rd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117431 | Estado ES | CITY OF VICTORIAS | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118241 | Hibale ES | DANAO | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118321 | Alumar ES | GETAFE | 2nd | 1 | 585 | - | - | 585 | 13 | - | - | 2002000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 305721 | Canmaya Diot High School | SAGBAYAN (BORJA) | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118719 | Garcia Park ES | TALIBON | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118746 | Bongbong ES | TRINIDAD | 2nd | 1 | 630 | - | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118820 | Humayhumay ES | UBAY | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 117960 | Linawan ES | ANDA | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City | 312964 | Jose B. Cardenas Memorial High School - Bayog Ext. | CANLAON CITY | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Carcar City | 324901 | LIBURON NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303093 | Sangat NHS | SAN FERNANDO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 305753 | South Poblacion NHS - Math & Science School | SAN FERNANDO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303000 | Mantalongon NHS | DALAGUETE | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 312404 | Jose Chona Jo Memorial National High School | BALAMBAN | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 303160 | Pit-os National High School | CEBU CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | City of Naga, Cebu | 303065 | Naga National High School | CITY OF NAGA | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Danao City | 322002 | Guinsay National High School | DANAO CITY | 5th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 324803 | Buenavista National High School | CITY OF GUIHULNGAN | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1694000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 305592 | Dr. Ernesto A. Uy Sr. National High School | MABINAY | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120693 | Cang-agong Elementary School | SIQUIJOR (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Talisay City | 119791 | Talisay City CES | CITY OF TALISAY | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Talisay City | 119802 | San Isidro Elementary School | CITY OF TALISAY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Tanjay City | 303282 | Tanjay NHS (Polo) | CITY OF TANJAY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Toledo City | 120740 | Talavera ES | TOLEDO CITY | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Toledo City | 303312 | Magdugo National High School | TOLEDO CITY | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay | 121097 | Biasong Elementary School | Baybay | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 121126 | Pomponan Elementary School | CITY OF BAYBAY | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 313316 | Baybay City National Night High School | CITY OF BAYBAY | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 344593 | Baybay City Senior High School | CITY OF BAYBAY | 5th | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120860 | Naval CS | NAVAL (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120862 | Sabang ES | NAVAL (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 122394 | Baras ES | CITY OF BORONGAN (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 313515 | Supt. Fidel E. Anacta, Sr. MHS | CITY OF BORONGAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Catbalogan City | 123415 | Majaba Elementary School | CITY OF CATBALOGAN (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303494 | Arteche National High School | ARTECHE | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122415 | Cansangaya Elementary School | CAN-AVID | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122431 | Del Pilar Elementary School | DOLORES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | Lone | 1 | - | 91 | - | 91 | 2 | - | - | 311300 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303499 | Dolores National High School | DOLORES | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121737 | Caloogan Elementary School | PALO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303426 | San Miguel National High School | SAN MIGUEL | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303430 | Sta. Fe National High School | SANTA FE | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303388 | Tanauan Sch. Of Craftsmanship & Home Industries (LIT-Tanauan Campus)Campus | TANAUAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303391 | Daniel Z. Romualdez State Comprehensive School of Fisheries | TOLOSA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303353 | Burauen Comprehensive National High School | BARAUEN | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313307 | Jugaban National High School | CARIGARA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121317 | BENITA B. MARAY ELEMENTARY SCHOOL | DAGAMI | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121344 | Dulag Central School | DULAG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121456 | Buenavista Elementary School | JARO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121558 | Bagacay West Elementary School | LA PAZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121559 | Bongtod Primary School | LA PAZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121566 | Canbanez Primary School | LA PAZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121626 | San Antonio Elementary School | MACARTHUR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 191565 | San Pedro Elementary School | MACARTHUR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121703 | Camansi Primary School | MAYORGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121704 | Gen. A. Luna Primary School | MAYORGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121711 | Talisay Elementary School | MAYORGA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121712 | Union Elementary School | MAYORGA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121817 | Jones Elementary School | PASTRANA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313343 | Macalpi-ay National High School | PASTRANA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121223 | Calubian South Central School | CALUBIAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121226 | Igang Elementary School | CALUBIAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303358 | Calubian National High School (Calubian Nat'l. Voc'l. School) | CALUBIAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313340 | Rafaelito Cabanas Martinez National High School | CALUBIAN | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121837 | Hugpa Elementary School | SAN ISIDRO | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 154000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121845 | Sangabon Elementary School | SAN ISIDRO | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303411 | Muertegui National High School | SAN ISIDRO | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303423 | San Isidro National High School | SAN ISIDRO | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303434 | Tabango National High School | TABANGO | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313309 | Gibacungan National High School | TABANGO | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121968 | Hinabuyan Central School | VILLABA | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303389 | Villaba National High School (LNCAST) | VILLABA | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303442 | Villaba National Comprehensive High School | VILLABA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121438 | Binog Elementary School | ISABEL | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303406 | Matlang National High School | ISABEL | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303406 | Matlang National High School | ISABEL | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 305522 | Matag-ob Stand Alone Senior High School | MATAG-OB | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 305522 | Matag-ob Stand Alone Senior High School | MATAG-OB | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303410 | Puerto Bello National High School | MERIDA | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121777 | San Miguel Elementary School | PALOMPON | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 120922 | Burubud-an Elementary School | ABUYOG | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte |  | Canmarating Senior High School | ABUYOG | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121070 | Marcelo Elementary School | BATO | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303346 | Bato National High School | BATO | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121383 | Hampangan Elementary School | HILONGOS | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 770000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 305646 | Talisay National High School | HILONGOS | 5th | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121423 | Guadalupe Elementary School | INOPACAN | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121513 | Sta. Cruz Elementary School | JAVIER (BUGHO) | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121639 | Mahaplag Central School | MAHAPLAG | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121688 | Cahagnaan Central School | MATALOM | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303356 | Cahagnaan National High School | MATALOM | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 500801 | Bantaawan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 240 | - |  | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 501025 | Sulpicio Lugod Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 501436 | Kamanikan Integrated School - Elem | GINGOOG CITY | 1st | 1 | 480 | - |  | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128082 | Luinab Elementary School | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128095 | Sta. Filomena Central School | ILIGAN CITY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128107 | Dona Matrona Actub Yanez MES (Bunawan ES) | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128110 | Kalubihon ES | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128137 | Cabili Village ES | ILIGAN CITY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501369 | Bacolod Central Integrated School | BACOLOD | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127039 | Cayontor PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127049 | Tingintingin PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 200529 | Upper Tugar PS | KAUSWAGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1237500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127093 | Bosque Elementary School | LINAMON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1650000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127126 | Batal ES | MATUNGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 200508 | Bubong Radapan P S | MATUNGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127159 | Bowi PS | PANTAR | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127161 | Cabasaran ES | PANTAR | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan ES | PANTAR | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127211 | CABASARAN PS | TAGOLOAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 210 | 210 | 6 | - | - | 726000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 500689 | Lala Proper ES | LALA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127104 | Abucay -Cancamo ES (Olango ES) | MAGSAYSAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 501378 | Shiek Omar Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 550000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127174 | Barandia PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127188 | Sudlon ES | SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 137089 | Pangantapan Primary School | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 200505 | Pansur PS | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 127210 | SAPAD ELEMENTARY SCHOOL | SAPAD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 412500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 136949 | SULTAN LINDONGAN PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 136950 | BAYABAO PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao City | 305667 | GSIS Heights National High School | DAVAO CITY | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128270 | New Alegria ES | COMPOSTELA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 501775 | Tigbao Integrated School | MARAGUSAN (SAN MARIANO) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 825000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128510 | Andap ES | NEW BATAAN | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128313 | Mabuhay ES | LAAK (SAN VICENTE) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128335 | Mabini CES | MABINI (DOÑA ALICIA) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1540000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 305637 | Teresa National High School | MACO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128413 | Mawab Central Elementary School SPED Center | MAWAB | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 304194 | Mainit NHS | NABUNTURAN (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128542 | Doroteo De Castro ES | PANTUKAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 315807 | Magnaga NHS | PANTUKAN | 2nd | 1 | - | 630 | - | 630 | 14 | - | - | 2156000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129404 | Tagbinonga ES | CITY OF MATI (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130479 | Nicomedes Tolentino ES | GLAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 1078000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130535 | Malalag CES-SPED Center | MAITUM | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 304534 | Malalag National High School | MAITUM | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 500281 | Wali Integrated School | MAITUM | Lone | 1 | - | - | 280 | 280 | 7 | - | - | 962500 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130611 | Malandag CES Sped Center | MALUNGON | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130646 | Banga Central Elementary School | BANGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130651 | Lamkot ES | Banga | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 316718 | San Vicente National High School | BANGA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 501270 | Lambukay Integrated School | BANGA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 275000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1386000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130699 | El Kuda ES | NORALA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 316909 | Fabiola Villa-Gasis NHS - San Miguel NHS Annex | NORALA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130767 | Colongulo Elementary School | SURALLAH | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130771 | Lambusong ES | SURALLAH | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130782 | Shri- Visaya Elementary School | SURALLAH | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130783 | Surallah CES | SURALLAH | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130868 | Bukay Pait Elementary School | TANTANGAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130870 | Dumadalig Integrated School | TANTANGAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130879 | New Iloilo ES | TANTANGAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130884 | Tantangan Central Elementary School | TANTANGAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 316911 | New Lambunao IS | TANTANGAN | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130808 | Datal Nabong ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130813 | Edwards ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130818 | Laconon IS | T'BOLI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1232000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130825 | Lamsine ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130829 | Lugan CES | T'BOLI | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1848000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130844 | Talambong ES | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130846 | Talufo IS | T'BOLI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130847 | Tboli ES | T'BOLI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 616000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 130968 | Aguil Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 308000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304616 | KALIBUHAN NATIONAL HIGH SCHOOL | PALIMBANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 462000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Tacurong City | 131219 | Amado Fernandez Sr. CES | CITY OF TACURONG | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 924000 | Central Office Implementation | 20% Allocation for E-Bamboo |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 134994 | Dugong ES | BUCAY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 135027 | Benben Elementary School | LA PAZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra |  | El Bernos Elementary School | LA PAZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 135104 | Lul-luno ES | LUBA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305077 | Bolbolo NHS | PILAR | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305093 | Pilar Rural High School | PILAR | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Abra | 500518 | An-anaao Integrated School | TAYUM | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 135229 | Ayayao ES | CALANASAN (BAYAG) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 135280 | Talifugo ES | CONNER | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 305111 | Conner Central NHS Main | CONNER | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 135285 | Atok Elementary School | FLORA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 502117 | San Jose Integrated School | FLORA | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 135298 | Baliwanan ES | KABUGAO (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 135347 | Sta. Lina ES | LUNA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Apayao | 219004 | Luyon ES | LUNA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Baguio City | 136380 | Adiwang Elementary School | BAGUIO CITY | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Baguio City | 136382 | Baguio Central school | BAGUIO CITY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 305158 | Sinipsip National High School | BUGUIAS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135562 | Balakbak ES | KAPANGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135631 | Puguis Elementary School | LA TRINIDAD (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Benguet | 135724 | Langbis PS | TUBLAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131567 | Sangay ES | BUENAVISTA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131450 | Kitcharao CES | KITCHARAO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Sur | 131809 | Sta Irene Central ES | PROSPERIDAD (Capital) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Agusan del Sur | 131844 | San Francisco Pilot CES | SAN FRANCISCO | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 131516 | Caasinan ES | CITY OF CABADBARAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Cabadbaran City | 131575 | Calibunan ES | CITY OF CABADBARAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132498 | Montag Elementary School | BASILISA (RIZAL) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132499 | Navarro Elementary School | BASILISA (RIZAL) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132505 | Rizal Central Elementary School | BASILISA (RIZAL) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132510 | Tag-abaca Central Elementary School | BASILISA (RIZAL) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 305745 | Roma National High School | BASILISA (RIZAL) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132357 | Borja Elementary School | CAGDIANAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132369 | San Jose Elementary School | CAGDIANAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132396 | Dinagat Central Elementary School | DINAGAT | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | Lone | 1 | - | 630 | - | 630 | 14 | - | - | 1895600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132308 | Bolodbolod Central Elementary School | LIBJO (ALBOR) | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132313 | Magsaysay Elementary School | LIBJO (ALBOR) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132424 | Loreto Central Elementary School | LORETO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132426 | Panamaon Elementary School | LORETO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132513 | Aurelio Elementary School | SAN JOSE (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132517 | Jacquez Primary School | SAN JOSE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132521 | Matingbe Elementary School | SAN JOSE (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132554 | Malinao Elementary School | TUBAJON | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Surigao City | 132265 | Capalayan ES | SURIGAO CITY (Capital) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN | Lone | 1 | 1260 | - | - | 1260 | 28 | - | - | 3791200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | City of San Juan | 136750 | Nicanor C. Ibuna ES | CITY OF SAN JUAN | Lone | 1 | 720 | - | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Las Piñas City | 136777 | Las Piñas Elementary School Central | CITY OF LAS PIÑAS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Las Piñas City | 340548 | Las Piñas City National Senior High School - Manuyo Campus | CITY OF LAS PIÑAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136690 | Makati ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136703 | Hen. Pio del Pilar ES Main | CITY OF MAKATI | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136707 | Maximo Estrella ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136714 | La Paz ES | CITY OF MAKATI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 305407 | San Isidro NHS | CITY OF MAKATI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 305409 | Gen. Pio del Pilar NHS | CITY OF MAKATI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136692 | Comembo ES | CITY OF MAKATI | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136693 | East Rembo ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136694 | Fort Bonifacio ES | CITY OF MAKATI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136695 | Pembo ES | CITY OF MAKATI | 2nd | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136696 | Rizal ES | CITY OF MAKATI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136710 | Nemesio I. Yabut ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 136711 | Pitogo ES | CITY OF MAKATI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 305411 | Fort Bonifacio HS | CITY OF MAKATI | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 305412 | Benigno "Ninoy" S. Aquino HS | CITY OF MAKATI | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Makati City | 320001 | Pitogo HS | CITY OF MAKATI | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 101170 | Balangobong ES | CITY OF ALAMINOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 300155 | Alaminos City National High School | CITY OF ALAMINOS | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Alaminos City | 300260 | Telbang National High School | CITY OF ALAMINOS | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Batac City | 100079 | Magnuang ES | CITY OF BATAC | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100428 | Bagani Elementary School | CITY OF CANDON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100430 | Bagar Elementary School | CITY OF CANDON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100435 | Candon North Central School | CITY OF CANDON | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 100437 | Caterman Elementary School | CITY OF CANDON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2nd | 1 | - | 1800 | - | 1800 | 40 | - | - | 5416000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100199 | Davila ES | PASUQUIN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100202 | Gabaldon ES | PASUQUIN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100305 | Vintar CES | VINTAR | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100035 | Nagrebcan ES | BADOC | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 500000 | Caraitan Integrated School | BADOC | 2nd | 1 | - | 90 | 80 | 170 | 2 | - | - | 502800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100148 | Fortuna ES | MARCOS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 150004 | Upon ES | PINILI | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300087 | Tay-ac National High School | BANTAY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 100501 | Magsingal North Central School | MAGSINGAL | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 300035 | San Juan National High School | SAN JUAN (LAPOG) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 502103 | Pangada-Cabaroan Integrated School | SANTA CATALINA | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 501578 | Comillas North Integrated School | CERVANTES | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Ilocos Sur | 100579 | Pagangpang Elementary School | GALIMUYOD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 100854 | Quirino Elementary School | BACNOTAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 100857 | Zaragosa Elementary School | BACNOTAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300124 | Oanari National High School | LUNA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 101069 | Naguituban ES | San Juan | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 101071 | San Juan CES | SAN JUAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300147 | San Juan National High School | SAN JUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 100811 | San Manuel Sur ES | AGOO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 500359 | Capas Integrated School | AGOO | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300149 | Suyo National High School | BAGULIN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300108 | Cuenca National High School | PUGO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300119 | Leones National High School | TUBAO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | La Union | 300152 | Tubao National High School | TUBAO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Laoag City | 305601 | Caaoacan High School | LAOAG CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Laoag City |  | MMSU Laboratory Elementary School | LAOAG CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500606 | Anda Integrated School | ANDA | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101339 | Balingasay ES | BOLINAO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101355 | Lucero Elementary School | BOLINAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500441 | Dasol Integrated School | DASOL | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500907 | Pita Integrated School | INFANTA | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102366 | Carallangan ES | ALCALA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102378 | Tupang ES | ALCALA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102450 | San Antonio ES | APARRI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102485 | C. Verzosa ES | BAGGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102504 | Taguntungan ES | BAGGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102533 | Tueg ES | BAGGAO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102681 | Tasica ES | GATTARAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102898 | Casagan ES | SANTA ANA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102899 | Casambalangan ES | SANTA ANA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102902 | Kapannikian ES | SANTA ANA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102340 | Guiddam ES | ABULUG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102352 | Sta. Rosa Elementary School | ABULUG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300419 | Abulug SOF | ABULUG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102607 | Capannikian Elementary School | CLAVERIA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102609 | Claveria East CS | CLAVERIA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102835 | Duyun ES | RIZAL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102836 | Gaddangao ES | RIZAL | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102838 | Illuru ES | RIZAL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102842 | Mauanan Elementary School | RIZAL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300478 | Mauanan NHS | RIZAL | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102408 | Concepcion Elementary School | AMULUNG | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102412 | Gabut ES | AMULUNG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102413 | GANGAUAN ES | AMULUNG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102417 | Monte Alegre ES | AMULUNG | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102631 | Maracuru ES | ENRILE | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102638 | Maddarulug Sur ES | ENRILE | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102716 | Iguig CS | IGUIG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102812 | Bugatay ES | PEÑABLANCA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 300445 | Penablanca National High School | PEÑABLANCA | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 502307 | Bangag Integrated School (102867-Banagag ES) | SOLANA | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cagayan | 102959 | Bugnay ELEMENTARY SCHOOL | TUAO | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 103182 | Buyon ES | CITY OF CAUAYAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Cauayan City | 103199 | Rogus ES | CITY OF CAUAYAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 107030 | Mining Elementary School | ANGELES CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 300677 | Baler NHS | BALER (Capital) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 104431 | Camilo Osias ES | DILASAG | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 104464 | Borlongan ES | DIPACULAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 300691 | Maria Aurora NHS | MARIA AURORA | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Aurora | 300694 | Mayor Cesario A. Pimentel NHS | SAN LUIS | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Balanga City | 305944 | Bataan National High School - Senior High School | CITY OF BALANGA (Capital) | 2nd | 1 | - | - | 270 | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Balanga City | 502032 | Tuyo Integrated School | CITY OF BALANGA (Capital) | 2nd | 1 | - | 320 | - | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 306608 | Orani NHS - Pagasa | ORANI | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 300698 | Bagac NHS-Parang | BAGAC | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 306612 | Roosevelt National High School | DINALUPIHAN | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 306615 | Mariveles NHS Pob. Annex-Sisiman | MARIVELES | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bataan | 501331 | Sampaloc Integrated School | MORONG | 3rd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104825 | Malis ES | GUIGUINTO | 2nd | 1 | 900 | - | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104950 | Matictic Elementary School | NORZAGARAY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 3rd | 1 | 900 | - | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Cabanatuan City | 107084 | Obrero ES | CABANATUAN CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Cabanatuan City | 107088 | Samon ES | CABANATUAN CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Cabanatuan City | 107089 | Sapang ES | CABANATUAN CITY | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Cabanatuan City | 107114 | Pagas Elementary School | CABANATUAN CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 107163 | San Rafael (BBH) Elementary School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | City of San Jose Del Monte | 307514 | San Manuel National High School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Gapan City | 105315 | Balante ES | CITY OF GAPAN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Gapan City | 501200 | Marelo Integrated School | CITY OF GAPAN | 4th | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Malolos City | 104873 | Look 1st ES | CITY OF MALOLOS (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Nueva Ecija | 300798 | Capintalan NHS | CARRANGLAN | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Antipolo City | 109321 | Bagong Nayon IV ES | CITY OF ANTIPOLO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Antipolo City | 109322 | Libis ES | CITY OF ANTIPOLO | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Bacoor City | 107877 | Aniban Central School | BACOOR | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107225 | Balayan East Central School | BALAYAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107239 | Lanatan-Muntingtubig Elementary School | BALAYAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107320 | Carlosa Elementary School | CALATAGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107320 | Carlosa Elementary School | CALATAGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107403 | Dayapan Elementary School | LEMERY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107497 | Bulihan Elementary School | NASUGBU | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107279 | San Teodoro Elementary School | BAUAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 501538 | As-Is Integrated School | BAUAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107431 | Bignay Primary School | LOBO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107437 | Mabilog Na Bundok Elementary School | LOBO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107446 | San Nicolas Elementary School | LOBO | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107462 | San Juan-Sto. Niño Elementary School | MABINI | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107653 | San Luis Central School | SAN LUIS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107813 | Pisa Elementary School | TINGLOY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 301095 | Coral na Munti National High School | AGONCILLO | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107349 | San Felipe Elementary School | CUENCA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107373 | Gulod Elementary School | LAUREL | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 501541 | Sampa-Pacifico Integrated School | SANTA TERESITA | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107576 | San Ignacio Elementary School | ROSARIO | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107589 | Benigna Dimatatac Memorial Elementary School | SAN JOSE | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107592 | Galamay-Amo Elementary School | SAN JOSE | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107598 | Taysan Elementary School | SAN JOSE | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 107607 | Calabasahan Elementary School | SAN JUAN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas | 305560 | Mahanadiong National High School | TAYSAN | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Batangas City | 109605 | Haligue Silangan ES | BATANGAS CITY (Capital) | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Binan City | 108221 | Langkiwa ES | CITY OF BIÑAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Calamba City | 109845 | Kay Anlog ES | CITY OF CALAMBA | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Calapan City | 301803 | Pedro V. Panaligan Memorial National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Calapan City |  | Personas National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 109870 | Don Luis Hidalgo MS | BOAC (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 301554 | Marinduque NHS | BOAC (Capital) | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 169011 | Aurora Sevilla Sotto Libtangin Elementary School | GASAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 169001 | Ino ES | MOGPOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 169009 | Malayak Elementary School | MOGPOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 109960 | Alobo ES | SANTA CRUZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 110003 | Maniwaya Elementary School | SANTA CRUZ | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 110027 | Matuyatuya ES | TORRIJOS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 110036 | Torrijos CS | TORRIJOS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301588 | Magsaysay National High School | MAGSAYSAY | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110169 | Mamburao CS | MAMBURAO (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301593 | Occidental Mindoro NHS | MAMBURAO (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301595 | RIZAL NATIONAL HIGH SCHOOL | RIZAL | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301596 | Sablayan NATIONAL COMPREHENSIVE HIGH SCHOOL | SABLAYAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110253 | San Jose Pilot ES | SAN JOSE | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110282 | Caminawit CS | SAN JOSE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301592 | Pedro T. Mendiola Sr. Memorial National High School | SAN JOSE | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 301599 | San Jose NHS | SAN JOSE | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 126071 | Dumagoc ES | PAGADIAN CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 314706 | Bulatok Integrated School | PAGADIAN CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Pagadian City | 501979 | Kalasan Integrated School | PAGADIAN CITY (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126098 | Baluno ES | ZAMBOANGA CITY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126137 | Camp Susana ES | ZAMBOANGA CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126138 | Datu Panguluhan ES | ZAMBOANGA CITY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 305996 | Mampang National High School | ZAMBOANGA CITY | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 345869 | Baliwasan SHS - Stand Alone | ZAMBOANGA CITY | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126178 | Buenakapok ES | ZAMBOANGA CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126195 | Tolosa ES | ZAMBOANGA CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126201 | Lumbangan ES | ZAMBOANGA CITY | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126207 | Don Gregorio Evangelista MS | ZAMBOANGA CITY | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga City | 126225 | Guiwan ES | ZAMBOANGA CITY | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301896 | Gonzalo Aler NHS | CAPALONGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301897 | Delia Diezmo National High School | CAPALONGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112172 | Sta. Milagrosa ES | JOSE PANGANIBAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301898 | Jose Panganiban NHS | JOSE PANGANIBAN | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301901 | Larap NHS with Annex (CNCEA) | JOSE PANGANIBAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301920 | Sta. Cruz NHS | JOSE PANGANIBAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301920 | Sta. Cruz NHS | JOSE PANGANIBAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112151 | Jose Panganiban ES | Jose Panganiban East | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112179 | Bulhao ES | LABO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112186 | Labo Elementary school | LABO | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112196 | Tulay Na Lupa ES | LABO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112208 | Felix Asis ES | LABO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301886 | Bagong Silang I HS | LABO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301887 | Bagong Silang II NHS | LABO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301894 | Labo Science and Tech. HS | LABO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301899 | Labo National High School | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301921 | Tigbinan NHS | LABO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301922 | Tulay Na Lupa National High School | LABO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301923 | Talobatib HS | LABO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 500156 | Dumagmang IS | LABO | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 500909 | Kabatuhan Integrated School | LABO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112202 | Calabasa ES | Labo West | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112242 | Batobalani Elementary School | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112244 | Capacuan ES | PARACALE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112246 | Dalnac ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112247 | Gumaus ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112251 | Ignacio Español ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112254 | Paracale Central School | PARACALE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112255 | Pedro V. Moreno (Malaguit) ES | PARACALE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112257 | S. Basilio ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112259 | Tawig ES | PARACALE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 114660 | Banga ES | BANGA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad Sr. IS | BANGA | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 362700 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 114713 | Agbago ES | IBAJAY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 114894 | Toledo Elementary School | NABAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 114936 | Tangalan ES | TANGALAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500171 | Lezo IS | LEZO | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 604500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Aklan | 500171 | Lezo IS | LEZO | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115218 | Delegate Angel Salazar Jr. MS | SAN JOSE (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Antique | 115367 | Igbalogo Elementary School | TOBIAS FORNIER (DAO) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117465 | Alberto D. Arceo Sr. ES | BACOLOD CITY (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117472 | Jose Gonzaga ES | BACOLOD CITY (Capital) | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117474 | Vista Alegre ES | BACOLOD CITY (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117478 | Dona E.J. Garcia ES | BACOLOD CITY (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 117484 | Estefania ES | BACOLOD CITY (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 302699 | ABKASA NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 302704 | Romanito P. Maravilla, Sr. National High School | BACOLOD CITY (Capital) | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City | 302718 | Teofilo Gensoli,Sr. National High School | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bacolod City |  | Bacolod City NHS - Extension | BACOLOD CITY (Capital) | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bago City | 117519 | Cristeta A. Dormido ES | BAGO CITY | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bago City | 117522 | Louisiana Elementary School | BAGO CITY | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Bago City | 117528 | Don Salvador Benedicto Memorial School | BAGO CITY | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Cadiz City | 117542 | Villacin ES | CADIZ CITY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 302405 | Jose Diva Avelino Jr. NHS | PONTEVEDRA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 302409 | Jamindan National High School | JAMINDAN | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 115590 | Ilawod ES (mambusao east) | MAMBUSAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Capiz | 115816 | San Nicolas ES | TAPAZ | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115870 | Espinosa Elementary School | JORDAN (Capital) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115901 | Paaralan ng Buhay ng La Orca | NUEVA VALENCIA | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115906 | Guiwanon Elementary School | NUEVA VALENCIA | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 115859 | Tangaw Primary School | SAN LORENZO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Guimaras | 305930 | Catalino G. Nava Farm School | SAN LORENZO | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Iloilo | 116513 | Pepe-Lonoc Elementary School | LEON | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 302789 | Kabankalan NHS | CITY OF KABANKALAN | 6th | 1 | - | 765 | - | 765 | 17 | - | - | 2301800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Kabankalan City | 302791 | Talubangi NHS | CITY OF KABANKALAN | 6th | 1 | - | 630 | - | 630 | 14 | - | - | 1895600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117237 | Nato Soliguen ES | LA CASTELLANA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 116985 | Tibak PS | CAUAYAN | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118004 | Dorol ES | BALILIHAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 500211 | San Roque Integrated School | BALILIHAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118169 | Catigbian Central ES | CATIGBIAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 186510 | Pandol Primary School | CORELLA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 305722 | De La Paz High School | CORTES | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118485 | Loon North Central ES | LOON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118027 | Bien Unido Central ES | BIEN UNIDO | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118063 | Bato Elementary School | BUENAVISTA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 500217 | Danahaw IS | CLARIN | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118231 | Sta. Cruz ES | DAGOHOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118239 | Danao Central Elementary School | DANAO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118245 | Rowena Heights Elementary School | DANAO | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118600 | President Carlos P. Garcia Central Elementary School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 305721 | Canmaya Diot High School | SAGBAYAN (BORJA) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118635 | Cambansag Elementary | SAN ISIDRO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118640 | Masonoy PS | SAN ISIDRO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118656 | San Miguel Central ES | SAN MIGUEL | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118801 | Achila Elementary School | UBAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 117936 | Alicia Central Elem. | ALICIA | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302809 | Alicia Technical Vocational HS | ALICIA | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 312314 | Quezon HS | BATUAN | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 312314 | Quezon HS | BATUAN | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118308 | Candulao ES | GARCIA HERNANDEZ | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118466 | Loboc Central Elementary School | LOBOC | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302837 | Concepcion NHS | MABINI | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 118693 | Sierra Bullones Central ES | SIERRA BULLONES | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Canlaon City | 120215 | Pula ES | CANLAON CITY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 118917 | Argao I Central ES | ARGAO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 118947 | Colawin ES | ARGAO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 302944 | LUNOP NATIONAL HIGH SCHOOL | BOLJOON | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303164 | Dumalan NHS | DALAGUETE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119040 | Cornelio C. Melgar Elementary School | BALAMBAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119073 | BARILI CES | BARILI | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 302928 | Balao NHS | BARILI | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303068 | Patupat NHS | BARILI | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 305595 | Lusong National High School | TUBURAN | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 500660 | Gibitngil Integrated School | MEDELLIN | 4th | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 500666 | Calambua Integrated School | SAN REMIGIO | 4th | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119771 | Kanlim-ao ES | TABUELAN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119216 | Catmondaan ES | CATMON | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 502211 | Basak Integrated School | COMPOSTELA | 5th | 1 | - | - | 120 | 120 | 3 | - | - | 362700 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119413 | Lataban ES | LILOAN | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119414 | Liloan Central ES | LILOAN | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119417 | Simeon Ayuda ES | LILOAN | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 501916 | Catarman Integrated School | LILOAN | 5th | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 502121 | Campo Integrated School | SAN FRANCISCO | 5th | 1 | - | - | 120 | 120 | 3 | - | - | 362700 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 500498 | Pansoy Integrated School | SOGOD | 5th | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 136962 | Tilhaong Primary School | CONSOLACION | 6th | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 137084 | Pitogo Primary School | CONSOLACION | 6th | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 187025 | Catarman Elementary School | CORDOVA | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 118869 | Lawaan ES | ALCANTARA | 7th | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119008 | Matutinao ES | BADIAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119405 | Kagsing ES | GINATILAN | 7th | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119596 | Cansalonoy ES | RONDA | 7th | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 121093 | Sta. Cruz Elementary School | CITY OF BAYBAY | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 305817 | Maganhan National High School | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City |  | Punta National High School | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120763 | Lo-ok ES | ALMERIA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303332 | Tabunan National High School | ALMERIA | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120782 | Pinangomhan ES | BILIRAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120798 | Asug ES | CAIBIRAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120801 | Cabibihan ES | CAIBIRAN | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120809 | Manlabang ES | CAIBIRAN | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303321 | Bool NHS | CULABA | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2708000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120844 | Ungale II Elementary School | KAWAYAN | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120846 | Agutay ES | MARIPIPI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120864 | Talustusan ES | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120872 | Eden Elementary School | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120875 | Libtong Daku ES | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120876 | Libtong Gamay Elementary School | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120878 | Lucsoon ES | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120882 | VILLACANEJA ELEMENTARY SCHOOL | NAVAL (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 303330 | Naval National High School | NAVAL (Capital) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Borongan City | 122364 | Siha Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Calbayog City | 194001 | Calbayog City SPED Center | CALBAYOG CITY | 1st | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Catbalogan City | 123427 | Rama Elementary School | CITY OF CATBALOGAN (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122329 | Buenavista Elementary School | ARTECHE | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122341 | Balangiga Central Elementary School | BALANGIGA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122618 | Guinpoliran Elementary School | BALANGKAYAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 313501 | Can-avid National High School | CAN-AVID | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122451 | Dapdap Central Elementary School | DOLORES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 192512 | Darahoway Elementary School | DOLORES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 192517 | Caybane Primary School | DOLORES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303499 | Dolores National High School | DOLORES | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122478 | Calutan Primary School | GENERAL MACARTHUR | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 305563 | Vigan National High School | GENERAL MACARTHUR | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122560 | Cantahay Elementary School | GUIUAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122492 | Padang Elementary School | HERNANI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | LAWAAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303497 | Bolusao National High School | LAWAAN | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 313514 | Maydolong National High School | MAYDOLONG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122649 | Saurong Elementary School | ORAS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 122728 | Pagbabangnan Elementary School | SAN JULIAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 191561 | Hinapolon Primary School | ALANGALANG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313331 | Alangalang Night High School | ALANGALANG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303413 | Pagsulhugon National High School | BABATNGON | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303421 | Emeterio-Federica Gerez National High School | BABATNGON | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121761 | San Antonio Elementary School | PALO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 191518 | Tacuranga Elementary School | PALO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 313335 | Palo National High School-Pawing Annex | PALO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303426 | San Miguel National High School | SAN MIGUEL | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303429 | Sta. Cruz National High School | SAN MIGUEL | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121870 | Catoogan Elementary School | SANTA FE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303430 | Sta. Fe National High School | SANTA FE | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121918 | Amanluran Elementary School | TANAUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121936 | Guindag-an Elementary School | TANAUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte |  | San Isidro National High School | TANAUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121950 | Daniel Z. Romualdez Memorial Elementary School | TOLOSA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303354 | Burauen National High School | BARAUEN | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303363 | Celestino De Guzman Memorial National High School | BARUGO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte |  | Visares NHS | CAPOOCAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121254 | Alberto T. Aguja Mem. Central School | CARIGARA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121455 | Batug Elementary School | JARO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 121462 | Montejo Mendiola Memorial Elementary School | JARO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126279 | San Miguel ELEMENTARY SCHOOL | BAUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126280 | SAN VICENTE ES | BAUNGON | 1st | 1 | 90 |  |  | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126622 | Camp 1 ES | MANOLO FORTICH | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126815 | Megbadiang ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126336 | Osmena Elementary School | DANGCAGAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126447 | Natulongan CS | KIBAWE | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126662 | Kuya ES | MARAMAG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Bukidnon | 126675 | Tubigon ES | MARAMAG | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 128001 | Canitoan Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 127967 | South City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Cagayan de Oro City | 304114 | Gusa Regional Science High School-X | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126884 | Bura Elementary School | CATARMAN | Lone | 1 | 131 | - | - | 131 | 3 | - | - | 394600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126885 | Catarman CS | CATARMAN | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126889 | Mainit ES | CATARMAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126890 | Manduao ES | CATARMAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126929 | Cabuan es | GUINSILIBAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126933 | Maac Elementary School | GUINSILIBAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126897 | Mahinog Central School | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126901 | Pontod Elementary School | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 303993 | Sixto A. Abao NHS | MAHINOG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | Lone | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126916 | Naasag ES | MAMBAJAO (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126918 | Quiboro ES | MAMBAJAO (Capital) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126921 | Tupsan ES | MAMBAJAO (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127670 | Cogon ES | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127677 | Pedro Sa. Baculio ES (Bolobolo) | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | El Salvador | 127678 | Sambulawan Elementary School | CITY OF EL SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Gingoog City | 500811 | Pedro Maligmat Integrated School - Elem | GINGOOG CITY | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128086 | Miguel Obach MES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Iligan City | 128146 | Tipanoy ES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1088100 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Lanao del Norte | 502082 | Sultan Dimasangcay Mananggolo Integrated School | KAUSWAGAN | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 604500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126590 | Patpat Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 501195 | Candiisan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127395 | Malibacsan ELementary School | JIMENEZ | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 501871 | Panalsalan Integrated School | PLARIDEL | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao City | 304349 | Binowang National High School | DAVAO CITY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao City | 305890 | Norberto G. Bacaro Sr. National High School | DAVAO CITY | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128277 | T.H. Valderrama ES | COMPOSTELA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128383 | Katipunan Elementary School | MARAGUSAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128426 | Bagong Taas ES | MONKAYO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 204011 | Paco ES | MONKAYO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128468 | Magtaya ES | MONTEVISTA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 300640 | Camansi National High School | MONTEVISTA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128519 | Magangit Elementary School | NEW BATAAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 501366 | Pongpong Integrated School | NEW BATAAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128338 | Masicareg ES | MABINI (DOÑA ALICIA) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 128364 | Calabcab ES | MACO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 305772 | New Visayas National High School | MACO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao De Oro | 300588 | Boringot National High School | PANTUKAN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 500846 | Rizal Integrated School | ASUNCION (SAUG) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 128648 | Dacudao ES | SAN ISIDRO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 304222 | Carmen NHS | CARMEN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Norte | 304254 | Sto Tomas NHS | SANTO TOMAS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128827 | Darapuay Elementary School | BANSALAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128829 | Eman Elementary School | BANSALAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128830 | Kinuskusan Elementary School | BANSALAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 305883 | Manual National High School | KIBLAWAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 205046 | Asbang-Elok Elementary School | MAGSAYSAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 128946 | Baybay Elementary School | MALALAG | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 129038 | La Suerte Elementary School | MATANAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao del Sur | 304288 | Matanao National High School | MATANAO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 109395 | Datu Tawang Elementary School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 129068 | Quiapo Elementary School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 304287 | Mariano Peralta National High School | MALITA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 305674 | Buhangin National High School | MALITA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 109429 | Leonila Limboran Elementary School | SANTA MARIA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 129102 | Babak PS | SANTA MARIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 501911 | Buca Integrated School | SANTA MARIA | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 604500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Occidental | 129063 | Mabila CES | SARANGANI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 136928 | Francisco D. Minghi Elementary School | BAGANGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 136958 | Limot Elementary School | BAGANGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 136960 | Mantapay Elementary School | BAGANGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129342 | Capasnan ES | MANAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131267 | A. Biscayda Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131279 | Lanton Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 131282 | Arizala Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131334 | Manongol CES | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Kidapawan City | 131341 | Lapan Elementary School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 131407 | Koronadal Central II ES | CITY OF KORONADAL (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Koronadal City | 304672 | Marbel 7 National High School | CITY OF KORONADAL (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129843 | Mirasol ES | ALAMADA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129849 | Rangayen ES | ALAMADA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130031 | Nicaan Central Elementary School | LIBUNGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130175 | Miguel Intes (Katingawan) ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130178 | Salunayan ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130204 | Sta. Cruz ES | MIDSAYAP | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130058 | Kisandal ES | MAGPET | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 304706 | Inac High School | MAGPET | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 100922 | Braulio G. Dano Elementary School | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130088 | Makilala Central Elementary School | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130094 | Biangan Elementary School | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130095 | Buena Vida ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130096 | Buhay ES | MAKILALA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130105 | San Isidro ES | MAKILALA | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 135400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130116 | Leboce ES | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130125 | Villaflores ES | MAKILALA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 207566 | Lower Saguing ES | MAKILALA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 316539 | Malungon High School | MAKILALA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 129992 | Tonganon ES | CARMEN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130391 | Bituan ES | Tulunan | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | North Cotabato | 130394 | Nabundasan ES | TULUNAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130469 | Margus Elementary School | GLAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130507 | Salakit Elementary School | KIAMBA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 130521 | Maasim CES | MAASIM | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 501198 | Polomolok Creek Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 501847 | LR Morandante Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 502160 | Silway 7 Integrated School | POLOMOLOK | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 208527 | Tampakan SPED Center | TAMPAKAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130891 | Lote Elementary School | TUPI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 304575 | Tupi National High School | TUPI | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 501664 | Lunen Integrated School | TUPI | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 502385 | Juan-Loreto Tamayo Integrated School | TUPI | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | South Cotabato | 130671 | Lake Sebu CES | LAKE SEBU | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305182 | Kiangan NHS | KIANGAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135880 | Boliwong ES | LAGAWE (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135884 | Cudog ES | LAGAWE (Capital) | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 220020 | Ifugao SPED Center | LAGAWE (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305169 | Caba National High School | LAGAWE (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 319004 | Lagawe NHS | LAGAWE (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 135898 | Dunuan ES | LAMUT | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305176 | Hapid NHS | LAMUT | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 500882 | Alupapan Integrated School | LAMUT | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CAR | Ifugao | 305185 | Mayoyao NHS | MAYOYAO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 132844 | Requina Elementary School | CITY OF BISLIG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Bislig City | 322507 | Labisma National High School | CITY OF BISLIG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132024 | Bading ES | BUTUAN CITY (Capital) | 1st | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132028 | Anticala ES | BUTUAN CITY (Capital) | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132039 | Taguibo Elementary School | BUTUAN CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132046 | Los Angeles ES | BUTUAN CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132052 | Pedro D. Duncano ES (Tiniwisan ES) | BUTUAN CITY (Capital) | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132062 | Basag ES | BUTUAN CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 132067 | Camayahan ES | BUTUAN CITY (Capital) | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 304759 | BANZA NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 304766 | Lumbocan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 304772 | TUNGAO NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 317504 | MAHAY IS | BUTUAN CITY (Capital) | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 317511 | AMPAYON NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | CARAGA | Butuan City | 317513 | BAGONG SILANG NATIONAL HIGH SCHOOL | BUTUAN CITY (Capital) | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305300 | Cayetano Arellano High School | SANTA CRUZ | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305304 | Esteban Abada High School | SAMPALOC | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305306 | Ramon Magsaysay High School | SAMPALOC | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC | 4th | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136467 | P. Burgos ES | TONDO | 4th | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5th | 1 | - | 495 | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 500605 | Aguilar Integrated School | AGUILAR | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 151524 | Alejandro V. Frias Elementary School | BASISTA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300235 | Parayao National High School | BINMALEY | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101475 | Kadampat ES | LABRADOR | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan School of Arts and Trades | LINGAYEN (Capital) | 2nd | 1 | - | 720 | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan I, Lingayen | 101533 | Asin Este ES | MALASIQUI | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101935 | Labney ES | SAN JACINTO | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101937 | Macayug ES | SAN JACINTO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 101771 | Binalonan South Central School | BINALONAN | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 102057 | Doña Aurea ES | SANTO TOMAS | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6th | 1 | - | 720 | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 300283 | Baracbac NHS | UMINGAN | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Pangasinan II, Binalonan | 501898 | San Vicente Integrated School | UMINGAN | 6th | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Carlos City | 102255 | Bolosan-Caingal Elementary School | SAN CARLOS CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Carlos City | 300391 | Turac National High School | SAN CARLOS CITY | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101021 | Bangbangolan ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500482 | Lingsat Integrated School | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1450800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | San Fernando City | 500602 | San Fernando South Central Integrated School (South CIS) | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1450800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102294 | Don Amadeo Perez, Sr. Memorial Elementary Central School - East | CITY OF URDANETA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region I | Urdaneta City | 102298 | Labit West Elementary School | CITY OF URDANETA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103249 | Dallao Elementary School | CORDON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103250 | Gayong Elementary School | CORDON | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103251 | Kakilingan Elementary School | CORDON | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103257 | Taringsing Elementary School | CORDON | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103290 | Echague East Central School | ECHAGUE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103306 | Arabiat Elementary School | ECHAGUE | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103325 | Sta. Monica Elementary School | ECHAGUE | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103439 | A.C. Ruiz Elementary School | JONES | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103470 | Jones West Central School-C2 | JONES | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103599 | Gen. Aguinaldo ES - Main | RAMON | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103653 | Dabubu Elementary School | SAN AGUSTIN | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103669 | Sinaoangan Sur Elementary School | SAN AGUSTIN | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103707 | San Isidro West Central School | SAN ISIDRO | 4th | 1 | 810 | - | - | 810 | 18 | - | - | 2437200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 103130 | Cullalabo Elementary School | BURGOS | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 159520 | Balik Barangay (Manibaug Pasig) ES | PORAC | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 159537 | Diaz ES | PORAC | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300906 | Pasig NHS | CANDABA | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 106252 | Sto. Nino ES | SAN LUIS | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Pampanga | 106259 | San Miguel ES | SAN SIMON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 500145 | Maimpis IS | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Fernando City | 500149 | San Agustin IS | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | San Jose City | 105731 | Sto. Tomas Elementary School | SAN JOSE CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 306089 | Camiling Science High School | CAMILING | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300989 | San Pedro National High School | MONCADA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106559 | Apulid ES | PANIQUI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2166400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106618 | Daldalayap ES | SAN CLEMENTE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106619 | Doclong 1st ES | SAN CLEMENTE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 502183 | Amacalan Integrated School | GERONA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 502180 | Maamot Integrated School | SAN JOSE | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 307014 | Calibungan HS | VICTORIA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 307021 | Balayang HS | VICTORIA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106408 | Parang ES | CONCEPCION | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac | 106442 | Sto. Nino ES | CONCEPCION | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Tarlac City | 500390 | Armenia Integrated School | CITY OF TARLAC (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 501225 | Looc Integrated School | CASTILLEJOS | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 107019 | Sto. Tomas Elementary School | SUBIC | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 501169 | Porac Integrated School | BOTOLAN | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 160502 | ADBSA Aeta School (Jesmag Iba) | IBA (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 301037 | Zambales National High School | IBA (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 106928 | San Nicolas Elementary School | SAN ANTONIO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 307123 | Angel C. Manglicmot High School | SAN ANTONIO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region III | Zambales | 301034 | Lipay High School | SANTA CRUZ | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 164013 | Bagbag II Elementary School | ROSARIO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108131 | Pooc Elementary School | SILANG | 5th | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107928 | Dao Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 107934 | Narvaez Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Cavite | 108147 | Maitim II Elementary School | TAGAYTAY CITY | 8th | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Dasmarinas City |  | Mabuhay ES | CITY OF DASMARIÑAS | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Imus City |  | Imus Integrated School | IMUS | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 108358 | Kabubuhayan ES | NAGCARLAN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 307929 | Nanhaya NHS (San Francisco NHS - Nanhaya Ext.) | VICTORIA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 108287 | Mayatba ES | FAMY | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Laguna | 108444 | Patimbao ES | SANTA CRUZ (Capital) | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lipa City | 109692 | Cipriano M. Andal MES (Halang ES) | LIPA CITY | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-A | Lipa City | 109692 | Cipriano M. Andal MES (Halang ES) | LIPA CITY | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 301532 | Bognuyan NHS | GASAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Marinduque | 109973 | Santa Cruz East Central School | SANTA CRUZ | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 110082 | Concepcion ES | CALINTAAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Occidental Mindoro | 169521 | Tamisan Minority School | CALINTAAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 300448 | Bongabong Technical and Vocational High School | BONGABONG | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301632 | Formon NHS | BONGABONG | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 309005 | Labasan National High School | BONGABONG | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301620 | Bulalacao NHS | BULALACAO (SAN PEDRO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 305922 | Bagong Sikat High School | BULALACAO (SAN PEDRO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 309002 | President Diosdado Macapagal MNHS | GLORIA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301617 | Balugo NHS | MANSALAY | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 110562 | Papandayan ES | PINAMALAYAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301649 | Quinabigan NHS | PINAMALAYAN | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational High School | ROXAS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301640 | Dangay NHS | ROXAS | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Oriental Mindoro | 301652 | San Mariano NHS | ROXAS | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IV-B | Palawan | 110747 | Villa Sol Elementary School | AGUTAYA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 314119 | Mutia National High School Extension - Alvenda | MUTIA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124604 | Mapang ES II | RIZAL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124605 | Nangca ES | RIZAL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 303726 | Sebaca NHS | RIZAL | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Norte | 124844 | Sirawai CS | SIRAWAI | 3rd | 1 | 1125 | - | - | 1125 | 25 | - | - | 3385000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 125022 | Dumingag CES | DUMINGAG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region IX | Zamboanga del Sur | 303788 | Lapuyan NHS | LAPUYAN | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301915 | San Felipe NHS | BASUD | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309611 | Dominador Narido High School | BASUD | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112138 | Pandan Elementary School | DAET (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112141 | Calasgasan ES | DAET (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112148 | ZURBANO ELEMENTARY SCHOOL | DAET (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301924 | Vicente L. Basit Memorial High School | DAET (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309612 | Porfirio R. Ponayo HS | DAET (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309622 | Camarines Norte NHS-Annex | DAET (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112223 | Colasi ES | MERCEDES | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112224 | F. P. Ibasco Elementary School | MERCEDES | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112232 | Manguisoc ES | Mercedes | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112235 | Mercedes Elementary School | MERCEDES | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112239 | Tagongtong ES | MERCEDES | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301902 | Manguisoc NHS | MERCEDES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301905 | Mercedes HS | MERCEDES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301907 | Pablo S. Villafuerte HS | MERCEDES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301909 | Pambuhan National High School | MERCEDES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309603 | Caringo High School | MERCEDES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112271 | Salvacion (B) ES | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112273 | San Isidro ES | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309606 | San Isidro HS (Alcantara) | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301919 | Froilan D. Lopez HS | SAN VICENTE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 309605 | Fabrica HS | SAN VICENTE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112289 | F. David ES | TALISAY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112292 | Ramon Magsaysay ES | TALISAY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 112293 | San Isidro ES | TALISAY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region V | Camarines Norte | 301916 | San Francisco National High School | TALISAY | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 305809 | Jose N. Villanueva National High School | CAUAYAN | 6th | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 501793 | Baclao Integrated School | CAUAYAN | 6th | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 501793 | Baclao Integrated School | CAUAYAN | 6th | 1 | - | - | 440 | 440 | 11 | - | - | 1329900 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117141 | Bato ES | HINOBA-AN (ASIA) | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117142 | Bilbao-Watkins ES | HINOBA-AN (ASIA) | 6th | 1 | 1170 | - | - | 1170 | 26 | - | - | 3520400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117144 | C.L. Hodges ES | HINOBA-AN (ASIA) | 6th | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117147 | Culipapa ES | HINOBA-AN (ASIA) | 6th | 1 | 1350 | - | - | 1350 | 30 | - | - | 4062000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117148 | Damutan ES | HINOBA-AN (ASIA) | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VI | Negros Occidental | 117150 | Don E. Bilbao ES | HINOBA-AN (ASIA) | 6th | 1 | 990 | - | - | 990 | 22 | - | - | 2978800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303103 | Juan Pamplona NHS | TABUELAN | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 500656 | Gilutongan Integrated School | CORDOVA | 6th | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 119447 | Montañeza ES | MALABUYOC | 7th | 1 | 675 | - | - | 675 | 15 | - | - | 2031000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu | 303033 | Langin NHS | RONDA | 7th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119901 | Mabolo ES | CEBU CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 967200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 119883 | Napo ES | CEBU CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 305713 | Balogo National High School | CITY OF GUIHULNGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 305915 | Calamba National High School | CITY OF GUIHULNGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 324801 | Magsaysay National High School | CITY OF GUIHULNGAN | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Guihulngan City | 120642 | Vallehermoso Central Elementary School | VALLEHERMOSO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Lapu-Lapu City | 119957 | Sabang Elementary School | LAPU-LAPU CITY (OPON) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Mandaue City | 120013 | Maguikay ES | MANDAUE CITY | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Mandaue City | 303196 | Pagsabungan NHS | MANDAUE CITY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120031 | Anibong Elementary School | AYUNGON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120327 | Martilo ES | LA LIBERTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120334 | Solonggon ES | LA LIBERTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120395 | Manjuyod CES | MANJUYOD | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 677000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 305592 | Dr. Ernesto A. Uy Sr. National High School | MABINAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120430 | Basak Primary School | SAN JOSE | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120489 | Libertad Ong Calderon MES (Ajong Elementary S) | SIBULAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120067 | San Miguel Elementary School | BACONG | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Negros Oriental | 120610 | Bongbong ES | VALENCIA (LUZURRIAGA) | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120675 | Kimba Elementary School | LAZI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120676 | Kinamandagan Elementary School | LAZI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120680 | Logucan Elementary School | MARIA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 120683 | Pisong A Elementary School | MARIA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VII | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 483600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 303348 | Baybay National High School | CITY OF BAYBAY | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 303349 | Bitanhuan National High School | CITY OF BAYBAY | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Baybay City | 327501 | Banahao National High School | CITY OF BAYBAY | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120780 | Hugpa ES | BILIRAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120781 | Julita ES | BILIRAN | Lone | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120790 | Casiawan ES | CABUCGAYAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120792 | LANGGAO ES | CABUCGAYAN | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120799 | Bariis ES | CAIBIRAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120805 | Kaulangohan ES | CAIBIRAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120812 | Tomalistis ES | CAIBIRAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120814 | Uson ES | CAIBIRAN | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120830 | Bulalacao ES | KAWAYAN | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 947800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120837 | Mapuyo ES | KAWAYAN | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120842 | Tucdao ES | KAWAYAN | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120856 | Agpangi ES | NAVAL (Capital) | Lone | 1 | 585 | - | - | 585 | 13 | - | - | 1760200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120857 | Atipolo ES | NAVAL (Capital) | Lone | 1 | 630 | - | - | 630 | 14 | - | - | 1895600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region VIII | Biliran | 120858 | Cornelio P. Limpiado ES | NAVAL (Capital) | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126561 | Cabangahan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 126566 | Macote Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 303973 | Managok National High School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Malaybalay City | 314914 | Casisang National High School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127252 | Lobogon ES | ALORAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127284 | Quezon ES | BALIANGAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 304025 | Baliangao SOF | BALIANGAO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127533 | Sapang Dalaga Central Elementary School | SAPANG DALAGA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127334 | Bitoon Elementary School | CLARIN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127339 | Dela Paz Elementary School | CLARIN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127538 | Cagay-Anon ES | SINACABAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127541 | Colupan Alto ES | SINACABAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127550 | San Isidro Bajo Primary School | SINACABAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 406200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Occidental | 127575 | Ozamiz Elementary School | TUDELA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1st | 1 | 157 | - | - | 157 | 4 | - | - | 474900 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 500522 | Kabulakan IS | BALINGOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 725400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region X | Misamis Oriental | 127733 | Mosangot ES | BINUANGAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129358 | Pedro Masanguid ES | MANAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 137186 | Mandabon Elementary School | MANAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 501962 | Jose Bitac Integrated School | MANAY | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 502246 | Francisco E. Lahora Sr. Integrated School | MANAY | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129462 | Tarragona Central Elementary School | TARRAGONA | 1st | 1 | 630 | - | - | 630 | 14 | - | - | 1895600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129181 | Dinagsaan Elementary School | BANAYBANAY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1083200 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129187 | Pintatagan Elementary School | BANAYBANAY | 2nd | 1 | 495 | - | - | 495 | 11 | - | - | 1489400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129285 | Manuel Roxas Elementary School | GOVERNOR GENEROSO | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 305515 | Magdug National High School | GOVERNOR GENEROSO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 305963 | Tamban National High School | GOVERNOR GENEROSO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 305963 | Tamban National High School | GOVERNOR GENEROSO | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129302 | Calapagan Elementary School | LUPON | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1624800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129319 | Tagboa ES | LUPON | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 316106 | Don Mariano Marcos National High School | LUPON | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 129441 | La Union ES | SAN ISIDRO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Davao Oriental | 305517 | Talisay National High School | SAN ISIDRO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XI | Mati City | 129393 | Cangusan ES | CITY OF MATI (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 130970 | Lam-alis Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 209032 | Balnate Elementary School | COLUMBIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 500761 | Upper Bunawan Integrated School | COLUMBIO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 316801 | Sultan Ali Akbar Sinenggayan National High School | ISULAN (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131085 | Pinguiaman Elementary School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 500762 | Palumbe Integrated School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 500434 | Palavilla Integrated School | LUTAYAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | LUTAYAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 241800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131206 | Bannawag Elementary School | PRESIDENT QUIRINO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 270800 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 130920 | Biwang Central School | BAGUMBAYAN | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1218600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131003 | Salabaca Elementary School | ESPERANZA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 812400 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131032 | DATU GUIABAR PILOT SCHOOL | KALAMANSIG | 2nd | 1 | 675 | - | - | 675 | 15 | - | - | 2031000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131044 | Pag-asa Elementary School | KALAMANSIG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131046 | Ricardo Cabaluna Memorial Elementary School | KALAMANSIG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 541600 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2nd | 1 | - | 448 | - | 448 | 9 | - | - | 1343300 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 |  | 0%
CY 2024 SF | Region XII | Sultan Kudarat | 131129 | Salangsang Elementary School | LEBAK | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1354000 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Under procurement | [12 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 |  | 0%
CY 2023 SF | CAR | Abra | 500743 | La Paz Integrated School | LA PAZ | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 530400 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 135058 | Cayapa ES | LAGANGILANG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 501729 | TABANGAO IS (ES) | LUBA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 328400 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 166300 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 135140 | Palang PS | SAN QUINTIN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 61100 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 305104 | Tineg National High School | TINEG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Abra | 135093 | Batayan PS | TUBO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [11 empty] | Missing in CAR updates under CY 2023 SF, found in CY 2022 instead | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | CAR | Apayao | 135361 | Barocboc ES | SANTA MARCELA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 269400 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CAR | Apayao | 135362 | Consuelo Elementary School | SANTA MARCELA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 269400 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 305275 | Mil-an National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1392800 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 305278 | San Vicente National High School (Integrated Senior High School) | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 826700 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 305279 | Sto. Tomas National High School | BAGUIO CITY | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1632600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 305280 | Irisan National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1493800 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 305284 | Joaquin Smith National High School | BAGUIO CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 698400 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Baguio City | 340055 | Baguio City National Science High School (Senior High School-Stand Alone) | BAGUIO CITY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1508500 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305135 | Bokod NHS-Main | BOKOD | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 890100 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305163 | Tublay School of Home Industries - Annex (Ambuklao) | BOKOD | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 494500 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 318901 | Bokod NHS Annex - Daklan | BOKOD | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 677600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 135510 | Midas Elementary School | ITOGON | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 435700 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305125 | Alejo M. Pacalso Memorial National High School | ITOGON | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | Lone | 1 | - | 135 | - | 135 | 3 | - | 21 | 672750 | Regional Office Implementation | 55% Allocation for Regular Supplier | 763500 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305142 | Laurencio Fianza NHS - Main | ITOGON | Lone |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | CAR | Benguet | 501809 | Palidan Integrated School | BAKUN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 324200 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 502174 | Abucot Integrated School | KABAYAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 501301 | Cayapas Integrated School | BUGUIAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 501203 | Datakan Integrated School | KAPANGAN | Lone | 1 | - | - | 800 | 800 | 20 | - | - | 2586000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 795600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 501759 | Bad-ayan Integrated School | BUGUIAS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305162 | Tublay School of Home Industries | TUBLAY | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2835800 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 502170 | Boneng Integrated School | ATOK | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 449700 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 501761 | Sagpat Integrated School | KIBUNGAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305149 | Kibungan National High School | KIBUNGAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 395600 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 502171 | Lubo Integrated School | KIBUNGAN | Lone | 1 |  | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 376700 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 305133 | Benguet National High School | LA TRINIDAD (Capital) | Lone | 1 | - | 585 | - | 585 | 13 | - | - | 1882400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1285700 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 502168 | Mogao Integrated School | MANKAYAN | Lone | 1 |  | 200 | - | 200 | 5 | - | - | 646500 | Regional Office Implementation | 55% Allocation for Regular Supplier | 442000 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 501810 | Tacadang Integrated School | KIBUNGAN | Lone | 1 | - | 70 |  | 70 | 1 | - | - | 222300 | Regional Office Implementation | 55% Allocation for Regular Supplier | 151400 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | CAR | Benguet | 135735 | Ciriaco Magno ES | TUBLAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 197800 | Completed | 100% | 2025-05-13 | 2025-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135748 | Damag ES Annex (Damag Proper) | AGUINALDO | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 380900 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 252600 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao |  | Asipulo National High School Annex | ASIPULO | Lone | 1 |  | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135813 | Banaue CS | BANAUE | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1502400 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135824 | Gohang ES | BANAUE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135825 | Kinakin ES | BANAUE | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135826 | Patilong ES | BANAUE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135827 | Poitan ES | BANAUE | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao | 135868 | Duit ES | KIANGAN | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CAR | Ifugao |  | Lagawe NHS Annex | LAGAWE (Capital) | Lone | 1 |  | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Kalinga | 135992 | Lubuagan Central School | LUBUAGAN | Lone |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Kalinga | 340131 | SHS in Lubuagan, Kalinga | LUBUAGAN | Lone | 1 | - | - | - | - | - | - | 14 | 158900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 126000 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 63200 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Mt. Province | 305233 | Banao National High School | BAUKO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 460900 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CAR | Mt. Province | 136236 | Besao Elementary School | BESAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 164200 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CAR | Mt. Province | 305256 | Tocucan National High School | BONTOC (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 90500 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | CAR | Mt. Province | 221004 | Cabunagan Primary School | TADIAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 141100 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CAR | Tabuk City | 136086 | Bulanao Central School | CITY OF TABUK (Capital) | Lone | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1978000 | Completed | 100% | 2024-05-13 | 2024-05-14 | [7 empty] | ASIAPRIME COMMODITIES CORP.- WILLIE MART JV |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 131469 | Lawan Lawan ES | LAS NIEVES | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1st |  | - | 270 | - | 270 | 6 | - | 42 | 1345500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 317310 | E. G. Montilla NHS (Mat-I NHS Annex) | LAS NIEVES | 1st | 1 | - | 180 | - | 180 | 4 | 28 | - | 911560 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 500048 | Lawan-Lawan NHS | LAS NIEVES | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 927752 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 131550 | F.S. OMAYANA ES | BUENAVISTA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 649345 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 317317 | Rizal NHS (Guinabsan NHS Annex) | BUENAVISTA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 131426 | Tagcatong Elementary School | CARMEN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Norte | 131581 | Beto ES | TUBAY | 2nd | 1 | 630 | - | - | 630 | 14 | - | - | 2027200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 131791 | AZPETIA ES | PROSPERIDAD | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304718 | Libertad NHS | BUNAWAN | 2nd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 131759 | BATAAN ES | LA PAZ | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304719 | Loreto NHS | LORETO | 2nd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2nd | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2nd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304717 | Lapinigan National High School | SAN FRANCISCO | 2nd | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2nd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 317419 | Sayon NHS | SANTA JOSEFA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 131930 | SAN VICENTE ES | STA. JOSEFA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 317409 | Kapatungan National High School | TRENTO | 2nd | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 317412 | Pulang Lupa NHS | TRENTO | 2nd | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Agusan del Sur | 304733 | Sampaguita National High Schools | VERUELA | 2nd | 1 | - | 360 | - | 360 | 8 | 14 | 28 | 1642380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Bayugan City | 304707 | BAYUGAN NCHS | BAYUGAN CITY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 132118 | Libertad CES | BUTUAN CITY (Capital) | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS (Main) | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 7 | 14 | 821190 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS (Pagatpatan Campus) | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | 56 | 1794000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades - Annex | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 7 | 14 | 821190 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | 56 | 1794000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304764 | Los Angeles National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304765 | Anticala NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304766 | Lumbocan NHS | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304766 | Lumbocan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | 56 | 1794000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | 42 | 1345500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1st |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317502 | Aupagan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317505 | Maibu National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317506 | La Trinidad Integrated Secondary School | BUTUAN CITY (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1st |  |  | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317508 | Pinamanculan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317508 | Pinamanculan National High School | BUTUAN CITY (Capital) | 1st |  |  | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1st | 1 |  | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317511 | Ampayon National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317513 | Bagong Silang National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317515 | Pareja ISS | BUTUAN CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317517 | Alviola ISS | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317520 | Pedro D. Duncano National HS | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 317521 | Pigdaulan National High School | BUTUAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 500317 | La Soledad NHS | BUTUAN CITY (Capital) | 1st | 1 | - | - | 160 | 160 | 4 | 14 | - | 683380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 500319 | Manila de Bugabos National High School | BUTUAN CITY (Capital) | 1st | 1 | - | - | 160 | 160 | 4 | 14 | - | 683380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Butuan City | 501201 | La Trinidad Integrated Secondary School | BUTUAN CITY (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | 14 | 14 | 1100880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Cabadbaran City | 304699 | Cabadbaran City NHS | CITY OF CABADBARAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2nd |  | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 304841 | Rizal National High School | BASILISA (RIZAL) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 304842 | Puerto Princesa National High School | BASILISA (RIZAL) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 304844 | Sering National High School | BASILISA (RIZAL) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 304851 | Tag-abaca National High School | BASILISA (RIZAL) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 324404 | New Nazareth National High School | BASILISA (RIZAL) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132356 | Boa Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132357 | Borja Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132359 | Cabungaan Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132360 | Cagdianao Central Elementary School | CAGDIANAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132361 | Del Pilar Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132362 | Lahi Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132367 | Nueva Estrella Elementary School | CAGDIANAO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132368 | R.E. Ecleo Sr. Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132371 | Sto Nino Elementary School | CAGDIANAO | Lone | 1 | 315 | - | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132372 | Tigbao Elementary School | CAGDIANAO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132374 | Valencia Elementary School | CAGDIANAO | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132305 | Albor Central Elementary School | LIBJO (ALBOR) | Lone | 1 | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | CARAGA | Dinagat Island | 132306 | Arellano Elementary School | LIBJO (ALBOR) | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132215 | Baybay Elementary School | BURGOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132126 | Consolacion Elementary School | DAPA | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132129 | Don Enrique Navarro Memorial School | DAPA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132132 | Osmena Elementary School | DAPA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132134 | Union Elementary School | DAPA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132137 | Cambas-ac Elementary School | DAPA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132139 | Dapa Central Elementary School & SPED Center | DAPA | 1st | 1 | 1215 | - | - | 1215 | 27 | - | - | 3909600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 27 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132143 | San Miguel Elementary School | DAPA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304774 | Dapa National High School | DAPA | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 909083 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304775 | Consolacion National High School | DAPA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304791 | Union National High School | DAPA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304775 | Consolacion National High School | DAPA | 1st | 1 |  | - | - | - | - | 7 | - | 83090 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317606 | Dapa National High School-Annex | DAPA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132168 | Esperanza Elementary School | DEL CARMEN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1st | 1 | 810 | - | - | 810 | 18 | - | - | 2606400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132179 | Sayak Elementary School | DEL CARMEN | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132180 | Tuboran Elementary School | DEL CARMEN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1st | 1 |  | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | - | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1st | 1 | - | - | - | - | - | 14 | 14 | 325080 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317605 | Oguing Navarro Memorial National High School | DEL CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132148 | Consuelo Elementary School | GENERAL LUNA | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132152 | General Luna CES | GENERAL LUNA | 1st | 1 | 990 | - | - | 990 | 22 | - | - | 3185600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132154 | Libertad Elementary School | GENERAL LUNA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132158 | Sta. Cruz Elementary School | GENERAL LUNA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | - | - | - | - | - | 14 | 21 | 404530 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | - | - | - | - | - | - | - | 0 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1st | 1 | - | - | - | - | - | 7 | - | 83090 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317603 | Gen. Luna NHS - Consuelo NHS Annex | GENERAL LUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132181 | Caridad Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132188 | Mabini Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132192 | San Roque Elementary School | PILAR | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st | 1 | - | - | - | - | - | 14 | 14 | 325080 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st |  | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304780 | Caridad National High School | PILAR | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1st | 1 | - | - | - | - | - | 7 | 7 | 162540 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 132198 | Roxas Elementary School | SAN ISIDRO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1st | 1 | - | - | - | - | - | 14 | 7 | 245630 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304784 | Roxas National High School | SAN ISIDRO | 1st | 1 | - | 135 | - | 135 | 3 | 7 | 7 | 596940 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | 315 | - | 315 | 7 | 14 | 21 | 1418130 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304786 | Libertad National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | 225 | - | 225 | 5 | 14 | 7 | 969630 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317607 | Alegria National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | - | - | - | - | 7 | - | 83090 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1st | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1st | 1 | - | 135 | - | 135 | 3 | 7 | 7 | 596940 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 304790 | Pamosaingan National High School | SOCORRO | 1st | 1 | - | 225 | - | 225 | 5 | 14 | 7 | 969630 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Siargao | 317602 | Atoyay National High School | SOCORRO | 1st | 1 | - | 225 | - | 225 | 5 | 14 | 7 | 969630 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304924 | Unidad NHS | CAGWAIT | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 500575 | Isla General IS | CANTILAN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304886 | Felisberto Verano NHS | CORTES | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 317912 | Davisol NHS | LIANGA | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago NHS | MARIHATAG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 500573 | Gata IS | SAN AGUSTIN | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304905 | San Miguel National Comprehensive HS | SAN MIGUEL | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304907 | San Miguel National Comprehensive HS-Sagbayan Annex | SAN MIGUEL | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304908 | San Miguel NHS | SAN MIGUEL | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Caraga | Surigao del Sur | 132942 | Falcon Memorial ES | Tago | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 317903 | Badong NHS | TAGO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 500322 | Bangsud Integrated School | TAGO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304861 | Barobo NHS | BAROBO | 2nd | 1 | - | 135 | - | 135 | 3 | - | 21 | 672750 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 304861 | Barobo NHS | BAROBO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-10-11 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1st |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-10-11 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136630 | Sta. Quiteria ES | KALOOKAN CITY | 1st | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1640000 | Completed | 100% | 2025-02-16 | 2024-10-02 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136640 | Sto. Niño Elementary School | KALOOKAN CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-10-04 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 319701 | Cielito Zamora Senior High School | KALOOKAN CITY | 1st | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 | 2024-10-05 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136623 | Barrio San Jose ES | KALOOKAN CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 | 2024-09-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Las Piñas City | 136779 | Pulanlupa ES | CITY OF LAS PIÑAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Las Piñas City | 305430 | Las Piñas National High School | CITY OF LAS PIÑAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Technical Vocational HS | City Of Las Piñas | Lone | 1 | 0 | 0 | 640 | 640 | 16 | 0 | 0 | 2068800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1464000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Las Piñas City | NEWLY-ESTABLISHED SCHOOL | Golden Acres ES - 8CL Golden Acres SHS - 24CL | Las Piñas City | Lone | 1 | 0 | 0 | 1280 | 1280 | 32 | 0 | 0 | 4137600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2928000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 32 | 0 |  | 100%
CY 2023 SF | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-11-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-11-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Mandaluyong City | 502026 | Senate President Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 | 2025-03-07 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 4054400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2996000 | Completed | 100% | 2025-02-16 | 2025-04-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1st |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 100% | 2025-02-16 | 2025-04-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136423 | Mariano Ponce Elementary School | TONDO | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 100% | 2025-02-16 | 2025-05-02 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 100% | 2025-02-16 | 2025-05-05 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2nd | 1 | 0 | 0 | 480 | 480 | 12 | 0 | 0 | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1146000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3rd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 | 2025-05-06 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3rd | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3rd | 1 | 900 | 0 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 100% | 2025-02-16 | 2025-04-16 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4th | 1 | 900 | 0 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 100% | 2025-02-16 | 2025-04-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5th | 1 | 990 | 0 | 0 | 990 | 22 | 0 | 0 | 3185600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2354000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5th | 1 | 1080 | 0 | 0 | 1080 | 24 | 0 | 0 | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2568000 | Completed | 100% | 2025-02-16 | 2025-05-09 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6th | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 100% | 2025-02-16 | 2025-04-15 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6th | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 4054400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2996000 | Completed | 100% | 2025-02-16 | 2025-05-03 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 100%
CY 2023 SF | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2025-04-29 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Muntinlupa City | 281541 | Poblacion ES | Muntinlupa | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | Lone | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Navotas | 305453 | Navotas NHS | CITY OF NAVOTAS | Lone | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Paranaque City | 136763 | F. Serrano Sr. ES - Don Bosco | CITY OF PARAÑAQUE | 2nd | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Pasig City | 136743 | San Miguel Elementary School | CITY OF PASIG | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Pasig City | 136731 | Oranbo ES | Pasig City | Lone | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Pasig City | 136727 | Kalawaan ES | Pasig City | Lone | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Pasig City | 340654 | SHS in Buting, Pasig City | Pasig City | Lone | 1 | 0 | 720 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2025-03-05 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1st | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 305328 | Pugad Lawin HS | QUEZON CITY | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2nd | 1 | 1260 | 0 | 0 | 1260 | 28 | 0 | 0 | 3636332 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5th | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5th | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136519 | Lucas R. Pascual Mem. ES | QUEZON CITY | 6th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6th | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | City of San Juan | 305609 | San Juan City Technical-Vocational and Livelihood -Senior High School | CITY OF SAN JUAN | Lone | 1 | 0 | 1080 | 0 | 1080 | 24 | 0 | 0 | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2460000 | Completed | 100% | 2025-02-16 | 2025-03-13 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1st | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Pateros | 1st | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1712000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1st | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1st | 1 | 0 | 360 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 856000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 228002 | Gat. Andres Bonifacio Elmentary School | TAGUIG CITY | 2nd | 1 | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1284000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2nd | 1 | 0 | 900 | 0 | 900 | 20 | 0 | 0 | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2140000 | Completed | 100% | 2025-02-16 |  | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-22 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-11-27 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Valenzuela City |  | Veinte Reales HS | CITY OF VALENZUELA | 1st | 1 | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-11-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd | 1 | 720 | 0 | 0 | 720 | 16 | 0 | 0 | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1640000 | Completed | 100% | 2025-02-16 | 2024-11-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd |  | 540 | 0 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 | 2024-11-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2nd |  | 360 | 0 | 0 | 360 | 8 | 0 | 0 | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 820000 | Completed | 100% | 2025-02-16 | 2024-11-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101196 | SAN VICENTE ES | ALAMINOS CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101166 | Alaminos City Central School | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101167 | Alos ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101168 | Amandiego ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101169 | Amangbangan ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101170 | Amangbangan ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101171 | Balayang ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101172 | Baleyadaan ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101173 | Bisocol ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101174 | Bolaney ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101175 | Bued ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101176 | Cabatuan ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101177 | Cayucay ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101178 | Dulacac ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101180 | Landoc ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101182 | Maawi ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101183 | Magsaysay ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101185 | Mona ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101186 | Palamis ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101189 | Pogo ES | CITY OF ALAMINOS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101191 | Popantay ES | CITY OF ALAMINOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101192 | Quibuar ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101198 | Tangcarang ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 101199 | Tawintawin ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 236001 | Linmansangan ES | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City |  | LONGOS ELEMENTARY SCHOOL | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Alaminos City |  | LONGOS ELEMENTARY SCHOOL | CITY OF ALAMINOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Batac City | 305491 | CITY OF BATAC NHS RAYURAY | Batac City | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Candon City | 322601 | CANDON INFORMATION TECHNOLOGY NHS | Candon City | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | DAGUPAN CITY | 500054 | FEDERICO N. CERALDE IS | DAGUPAN CITY | 4th | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100046 | Banban Elementary School | BANGUI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100054 | Paddagan ES | BANGUI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100100 | Ablan Community School | BURGOS | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100108 | Saoit ES | BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100220 | Carasi ES | CARASI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100050 | Dumalneg ES | DUMALNEG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300019 | Luzong NHS | Pagudpud | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100037 | Paltit ES | BADOC | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300015 | Dingras NHS | Dingras | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100158 | Tabucbuc Elementary School | MARCOS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300020 | Marcos NHS | Marcos | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300022 | Nueva Era NHS | Nueva Era | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300027 | Pinili NHS | Pinili | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 701200 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 100252 | Barabar ES | SAN NICOLAS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 300028 | San Nicolas NHS | San Nicolas | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Norte | 320817 | Bagbag Solsona NHS | Solsona | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100402 | Cabugao North Central School | CABUGAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 300068 | Puro NHS, Caoayan | CAOAYAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100737 | SAGSAGAT ELEMENTARY SCHOOL | SAN ILDEFONSO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 150522 | Mindoro Primary School | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100660 | Calawaan Elementary School | SANTA CATALINA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100564 | Bussot Priimary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 300054 | Lidlidda National High School | LIDLIDDA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 350600 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100552 | Tadao Elementary School | NAGBUKEL | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100386 | Ansad ES | SAN ESTEBAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100624 | Nagpanaoan Community School | SANTA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100627 | Santa CS | SANTA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 701200 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100587 | Sto. Rosario ES | SIGAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Ilocos Sur | 100331 | Banga Elementary School | SUGPON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300103 | Butubut National High School | BALAOAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300114 | DOÑA FRANCISCA LACSAMANA DE ORTEGA MEMORIAL NATIONAL HIGH SCHOOL | BANGAR | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 101078 | Corrooy ES | SANTOL | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300117 | Duplas NHS | SUDIPEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300129 | Pres. Elpidio. Quirino NHS | AGOO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 321007 | Manga National HS | ARINGAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 100861 | Cambaly Elementary School | BAGULIN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300112 | Don Eulogio De Guzman MNHS | BAUANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300112 | Don Eulogio De Guzman MNHS | BAUANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300128 | Paringao National High School | BAUANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300104 | Caba NHS | CABA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300123 | Northern Naguilian National High School | NAGUILIAN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 100997 | Ambangonan ES | PUGO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | La Union | 300131 | Pugo Central NHS | PUGO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Laoag City | 102209 | Gabaldon ES | LAOAG CITY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 262950 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101144 | Patar ES | AGNO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300154 | Agno NHS | AGNO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 866560.1015 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101218 | San Jose ES | ANDA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101234 | Centro Toma ES | BANI | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101359 | Patar ES | BOLINAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300159 | Arnedo NHS | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300172 | Binabalian NHS | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300194 | Dewey National High School | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300214 | Luciente II NHS | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300238 | Pilar NHS | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300249 | Sampaloc National High School | BOLINAO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 321108 | Tupa Integrated School | BOLINAO | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 72213.3418 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 321109 | Liwa Liwa Integrated School | BOLINAO | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 72213.3418 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 129090.6521 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500611 | Catubig Integrated School (High School) | BOLINAO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 129090.6521 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500615 | Liwa Liwa Integrated School | BOLINAO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 129090.6521 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500621 | Tupa Integrated School | BOLINAO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 129090.6521 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101404 | Concordia ES | BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101456 | Uli ES | DASOL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101457 | Viga ES | DASOL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1st | 1 | - | - | 480 | 480 | 12 | - | - | 1391628 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101671 | Sual CS | SUAL | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101164 | Sipitan ES | AGUILAR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300202 | Enrico T. Prado NHS | AGUILAR | 2nd | 1 | - | 45 | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101325 | Basing Elementary School | BINMALEY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101330 | Gayaman ES | BINMALEY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101333 | Nagpalangan ES | BINMALEY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101336 | Sta. Rosa ES | BINMALEY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101485 | Matalava ES | LINGAYEN (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101576 | Talospatang ES | MALASIQUI | 3rd | 1 | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1083200.1269 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 500365 | Mabulitec Integrated School | MALASIQUI | 3rd | 1 | - | - | 320 | 320 | 8 | - | - | 1034400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 516362.6083 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300242 | Primicias NHS | MAPANDAN | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101638 | Tuliao ES | SANTA BARBARA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 101648 | Maticmatic ES II | SANTA BARBARA | 3rd | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 649920.0761 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan I, Lingayen | 300176 | Botao NHS | STA. BARBARA | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-12 | 2024-02-03 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101799 | Lipit Elementary School | MANAOAG | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 300280 | Baguinay NHS | MANAOAG | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 500388 | Gueguesangen IS | MANGALDAN | 4th | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 258181.3041 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101829 | Talogtog ES | MANGALDAN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101910 | Mabilao ES | SAN FABIAN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101912 | Pangulong Marcos ES | SAN FABIAN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101694 | Alcala CS | ALCALA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101700 | Laoac ES | ALCALA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101703 | Pindangan West ES | ALCALA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101756 | Biinalonan North CS SPED Center (Binalonan North Central Elementary School) | BINALONAN | 5th | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1444266.8358 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101781 | Cabu-Cala ES | LAOAC | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101869 | Imbalbalatong ES | POZORRUBIO | 5th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 722133.4179 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101874 | Sugcong ES | POZORRUBIO | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | REGION I | Pangasinan Ii, Binalonan | 500375 | Sison Central Is | Sison | 5th | 1 | - | - | 640 | 640 | 16 | - | - | 2068800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1032725.2166 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzales ES | Sto Tomas | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102122 | Maburac ES | VILLASIS | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102125 | Puelay ES | VILLASIS | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102126 | Villasis I Central School SPED Center | VILLASIS | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102145 | San Blas ES | VILLASIS | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 101961 | San Juan ES | SAN MANUEL | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION I | Pangasinan Ii, Binalonan | 500379 | San Felipe Is | San Nicolas | 6th | 1 | - | - | 360 | 360 | 9 | - | - | 1163700 | Regional Office Implementation | 55% Allocation for Regular Supplier | 580907.9343 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102011 | San Quintin Central School | SAN QUINTIN | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102093 | Umingan Central School | UMINGAN | 6th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 866560.1015 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region I | Pangasinan II, Binalonan | 102118 | San Vicente Integrated School | UMINGAN | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-02-21 | 2024-02-15 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | San Carlos City | 102254 | Balite Sur Elementary School | San Carlos City | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 433280.0507 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | San Fernando City | 321001 | La Union NHS - Sacyud Annex | CITY OF SAN FERNANDO (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | San Fernando City | 500480 | Pagudpud IS | San Fernando City (Capital) | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 258181.3041 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 288853.3672 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 577706.7343 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | REGION I | Urdaneta City | 500060 | San Jose Leet Is | Urdaneta City | 5th | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 258181.3041 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | REGION I | Urdaneta City | 500061 | Don Alipio Fernandez ,Sr. Is | Urdaneta City | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 387271.9562 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 43430110 | Completed | 100% | 2024-04-03 | 2023-07-10 | 2023-09-463 | 2024-01-001 | sEPT. 22, 2023 | Sept. 29, 2023 | Oct. 16, 2023 | Jan. ii, 2024 | Jan. 15, 2024 | BASE WOOD PRODUCTS | CONTRACT LOT 2 (BATANES, CAGAYAN, TUGUEGARAO CITY); WITH ADDIONAL 90 CD EXTENSION DUE TO GEOGRAPHICAL LOCATIONS OF RECIPIENT SCHOOLS | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Batanes | 500063 | Raele Integrated School | ITBAYAT | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Batanes | 300415 | Ivana NHS | IVANA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Batanes | 300417 | Sabtang National School of Fisheries | SABTANG | Lone | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300420 | Afusing NHS | ALCALA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300421 | ALCALA RURAL SCHOOL | ALCALA | 1st |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102443 | Dodan ES | APARRI | 1st |  | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300437 | Bukig National Agricultural and Technical School | APARRI | 1st |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300471 | Aparri East National High School | APARRI | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102507 | Adaoag ES | BAGGAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102516 | Callao Elementary School | BAGGAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | CAGAYAN | 300429 | Baggao National Agricultural School | BAGGAO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | CAGAYAN | 300429 | Baggao National Agricultural School | BAGGAO | 1st |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300430 | Baggao National School of Arts & Trades | BAGGAO | 1st | 1 | - | 270 | - | 270 | 6 | - | 42 | 1345500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300431 | Baggao NHS | BAGGAO | 1st |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306002 | Baggao NAS - Sta. Margarita Annex | BAGGAO | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306020 | AGAMAN NATIONAL HIGH SCHOOL | BAGGAO | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300474 | Licerio Antiporda Sr. NHS | BUGUEY | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300480 | Pattao NHS | BUGUEY | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306011 | Licerio Antiporda Sr. NHS - Dalaya Ext. | BUGUEY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306012 | Pattao NHS - Maddalero Ext. | BUGUEY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102568 | Paddaya Elementary School | CAMALANIUGAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102569 | Paddaya Este Elementary School | CAMALANIUGAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300444 | Camalaniugan NHS | CAMALANIUGAN | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306426 | Camalaniugan National High School- Catotoran Annex | CAMALANIUGAN | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300440 | Calaoagan Dackel National High School | GATTARAN | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300455 | Don Mariano Marcos NHS | GATTARAN | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300462 | Gattaran National Trade School | GATTARAN | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306422 | Calaoagan Dackel National High School-Capissayan Annex | GATTARAN | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102702 | Rebecca Elementary School | GONZAGA | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300435 | Baua HS | GONZAGA | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300465 | Ipil National High School | GONZAGA | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300482 | Rebecca NHS | GONZAGA | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300483 | Gonzaga National High School | GONZAGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1st |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306423 | Cabiraoan National High School | GONZAGA | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300475 | Logac National High School | LAL-LO | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306003 | Lal-lo NHS - Cabayabasan Annex | LAL-LO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300447 | Casambalangan NHS | SANTA ANA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300488 | Sta. Ana Fishery National High School | SANTA ANA | 1st |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306013 | Luga National High School | SANTA TERESITA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102331 | Abulug CES (Bldg 1) | ABULUG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102334 | Banguian ES | ABULUG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102337 | Canayun ES (Bldg 1) | ABULUG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102338 | Dana-ili ES | ABULUG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102340 | Guiddam ES | ABULUG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102343 | Macugay ES | ABULUG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102390 | Kapanickian Norte ES | ALLACAPAN | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300423 | Alig Valley National High School | ALLACAPAN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 500009 | Utan Integrated School | ALLACAPAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102543 | Fugu ES | BALLESTEROS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300449 | Claveria NHS | CLAVERIA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300450 | Claveria RVS | CLAVERIA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300439 | Nabannagan National High School | LASAM | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300443 | Callao National High School | LASAM | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300436 | Bidduang National High School | PAMPLONA | 2nd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102826 | Minanga ES | PIAT | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102829 | Sto. Domingo ES | PIAT | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300464 | Illuru NHS | RIZAL | 2nd | 1 | - | - | - | - | - | 7 | - | 83090 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 501586 | San Juan IS | RIZAL | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300485 | Sanchez Mira NHS | SANCHEZ-MIRA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102916 | Cadongdongan ES | SANTA PRAXEDES | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306006 | Abariongan National High School | SANTO NIÑO (FAIRE) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306425 | Namuccayan Integrated School | SANTO NIÑO (FAIRE) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300425 | AMULUNG NATIONAL HIGH SCHOOL | AMULUNG | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300452 | Cordova National High Sschool | AMULUNG | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306009 | Bayabat NHS - La Suerte Ext. | AMULUNG | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306010 | PACAC GRANDE NAT'L. HIGH SCHOOL | AMULUNG | 3rd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102625 | Alibago ES | ENRILE | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102629 | Lemu Elementary School | ENRILE | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300458 | Enrile Vocational High School | ENRILE | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300472 | Lemu NHS | ENRILE | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102718 | Manaoag ES | IGUIG | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300463 | Vicente D. Trinidad High School | IGUIG | 3rd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 306001 | Gammad National High School | IGUIG | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300457 | Penablanca East NHS | PEÑABLANCA | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 102870 | Dassun ES | SOLANA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300426 | Andarayan NHS | SOLANA | 3rd | 1 | - | 810 | - | 810 | 18 | - | - | 2606400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300484 | Sampaguita NHS | SOLANA | 3rd | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300487 | Solana Fresh Water Fishery School | SOLANA | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300466 | Itawes Nat'l. Agr'l. & Tech'l. School | TUAO | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300468 | Itawes Nat'l.l Agr'l. & Tech'l. School - Bagumbayan Annex | TUAO | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cagayan | 300494 | Tuao Voc'l. and Tech'l. School - Pata Annex | TUAO | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 103186 | Cauayan East CS - Main | CITY OF CAUAYAN | 6th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 103211 | Cauayan North CS | CITY OF CAUAYAN | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Cauayan City | 300516 | Cauayan City NHS | CITY OF CAUAYAN | 6th | 1 | - | 45 | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region II | City of Ilagan | 103432 | San Felipe ES | ILAGAN (CAPITAL) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION II | City Of Ilagan | 500087 | Gayong-Gayong Sur Is | Ilagan (Capital) | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 22984966 | Completed | 100% | Aug. 19, 2024 | Oct. 19, 2024 | 2023-09-463 | 2024-04-009 | Feb. 08, 2024 | Feb. 19, 2024 | 2024-03-04 | 2024-04-16 | 2024-05-17 | BASE WOOD PRODUCTS/LV YOUNG EDUCATION TECHNOLOGY CORPORATION | Contract Lot 1 (Isabela and City of Ilagan), with time extension due to geographical locations of recipient schools | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103147 | Cansan ES | Cabagan | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103161 | San Juan ES | Cabagan | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300587 | Ragan Sur National High School | DELFIN ALBANO (MAGSAYSAY) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300560 | Maconacon National High School | MACONACON | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300554 | Isabela School of Fisheries | PALANAN | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306132 | Simanu National High School | SAN PABLO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300603 | Santa Maria High School | SANTA MARIA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103888 | Antagan 1st ES - Sitio Magoli Annex | TUMAUINI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300503 | BENITO SOLIVEN NATIONAL HIGH SCHOOL | BENITO SOLIVEN | 2nd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300546 | Andabuen National High School | BENITO SOLIVEN | 2nd | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300537 | Gamu Rural School-Main | GAMU | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300563 | Naguillian National High School | NAGUILIAN | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306157 | Cabaruan Integrated School | NAGUILIAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103648 | Sinamar Elementary School | ROXAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300562 | Munoz High School | ROXAS | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300592 | San Mariano National High School - Main | SAN MARIANO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300593 | Alibadbad National High School | SAN MARIANO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300595 | Ueg National High School | SAN MARIANO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306137 | Daragutan East National High School | SAN MARIANO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 102990 | Burgos Elementary School | ALICIA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300550 | La Suerte HS | ANGADANAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300571 | Ramon National High School | RAMON | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300571 | Ramon National High School | RAMON | 3rd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300571 | Ramon National High School | RAMON | 3rd |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103770 | Daramuangan Norte Elem. School | San Mateo | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103770 | Daramuangan Norte Elem. School | San Mateo | 3rd |  | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | ISABELA | 103248 | Cordon South CS Annex | CORDON | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300523 | Diadi Region High School | CORDON | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103443 | Dicamay I Elementary School | JONES | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103456 | Sto. Domingo ES - Annex (LSB) | JONES | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300524 | Dibuluan National High School | JONES | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300572 | General Emilio Aguinaldo National High School | RAMON | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300574 | Raniag HIgh School | RAMON | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103671 | Virgonesa Elementary School | SAN AGUSTIN | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300518 | Dabubu High School - Main | SAN AGUSTIN | 4th | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300518 | Dabubu High School - Main | SAN AGUSTIN | 4th |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103073 | Bagnos Elementary School | AURORA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300509 | Burgos National High School | BURGOS | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300511 | San Antonino National High School | BURGOS | 5th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103484 | Bustamante Elementary School | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103486 | Lalog Elementary School | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103487 | Luna Central School | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103488 | Mambabanga Elementary School | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103490 | Pulay-Union Kalinga Elementary School | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103491 | Puroc-Concepcion ES | LUNA | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | - | - | - | - | - | - | 14 | 158900 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 500970 | Sto. Domingo-San Isidro Integrated School | LUNA | 5th | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300561 | Mallig National High School-Main | MALLIG | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306110 | San Jose National High School | MALLIG | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 500077 | Bimonton Integrated School | MALLIG | 5th | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300568 | Quezon National High School | QUEZON | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300568 | Quezon National High School | QUEZON | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 500082 | Sto. Domingo Integrated School | QUIRINO | 5th | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103633 | Lucban Masigun Elementary School | ROXAS | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103637 | San Jose Elementary School | ROXAS | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103638 | San Pedro-Villa Concepcion Elementary School | ROXAS | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306111 | Monico Rarama National High School | ROXAS | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 306135 | Matusalem National High School | ROXAS | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 500094 | Simimbaan Integrated School | ROXAS | 5th | 1 | - | - | 80 | 80 | 2 | 7 | 7 | 421140 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300512 | Callang National High School - Main | SAN MANUEL | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300513 | Malalinta National High School | SAN MANUEL | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300514 | Sandiat National High School | SAN MANUEL | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 300611 | Ugad High School | ECHAGUE | 6th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103701 | Gud Elementary School | SAN ISIDRO | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103702 | Nagbukel Elementary School | SAN ISIDRO | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103703 | Patanad Elementary School | SAN ISIDRO | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103705 | Ramos Elementary School | SAN ISIDRO | 6th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103706 | San Isidro East Central School | SAN ISIDRO | 6th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 103709 | Villaflor Elementary School | SAN ISIDRO | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Isabela | 155510 | Ramos West Elementary School | SAN ISIDRO | 6th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 104188 | Alfonso Castañeda Central School | ALFONSO CASTAÑEDA | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 21061894 | Completed | 100% | Aug. 19, 2024 | Oct. 19, 2024 | 2023-09-463 | 2024-04-010 | Feb. 08, 2024 | Feb. 19, 2024 | 2024-03-04 | 2024-04-16 | 2024-05-17 | BASE WOOD PRODUCTS/LV YOUNG EDUCATION TECHNOLOGY CORPORATION | Contract Lot 3 (Nueva Vizcaya, Quirino, Ang Santiago City), with time extension due to geographical locations of recipient schools | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 137028 | Bagingey ES | AMBAGUIO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300618 | Aritao National High School | ARITAO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300647 | Sta. Clara HS | ARITAO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300627 | Diadi NHS | DIADI | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300622 | Belance HS | DUPAX DEL NORTE | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300635 | LAMO NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300637 | Munguia NHS | DUPAX DEL NORTE | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 306206 | DUPAX DEL NORTE NATIONAL HIGH SCHOOL | DUPAX DEL NORTE | Lone | 1 | - | 315 | - | 315 | 7 | - | 7 | 1093050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300625 | Carolotan High School | DUPAX DEL SUR | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300629 | Ganao National HS | DUPAX DEL SUR | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300636 | Malabing Valley NHS-INTEGRATED SENIOR HIGH SCHOOL | KASIBU | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300633 | Martinez Cuyangan National High School | KAYAPA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300639 | Nansiakan NHS | KAYAPA | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 300648 | Sta. Cruz Pingkian High School | KAYAPA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 500024 | Napo-Tuyak National High School | KAYAPA | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 500096 | Binalian Integrated National High School | KAYAPA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 306205 | Canabuan National High School | SANTA FE | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Nueva Vizcaya | 104215 | Ernesto "Lapan" Pale ES | VILLAVERDE | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 104238 | Aglipay East CS | Aglipay | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 300652 | Aglipay NHS | AGLIPAY | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 300656 | Cabarroguis NSAT | CABARROGUIS (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 104364 | San Pugo Elementary School (New Site) | NAGTIPUNAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region II | Quirino | 501562 | Salvacion Integrated School | SAGUDAY | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Santiago City | 300599 | Santiago City National High School | CITY OF SANTIAGO | 4th |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Santiago City | 325201 | Santiago City National High School - Sinsayon | CITY OF SANTIAGO | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Santiago City | 325204 | Divisoria High School - Naggasican Extension | CITY OF SANTIAGO | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Santiago City | 500936 | Balintocatoc Integrated School | CITY OF SANTIAGO | 4th | 1 | - | - | 280 | 280 | 7 | - | - | 905100 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 104388 | Libag Elementary School | TUGUEGARAO CITY(Capital) | 3rd |  | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | 2024-04-03 | 2024-07-20 | 2023-09-463 | 2024-01-001 |  |  |  |  | Jan. 15, 2024 | BASE WOOD PRODUCTS | Included in Contract Lot 2 (Batanes, Cagayan and Tuguegarao City) | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 300668 | Cagayan National High Sschool | TUGUEGARAO CITY(Capital) | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 300670 | Linao National High School | TUGUEGARAO CITY(Capital) | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 300671 | Gosi National High School | TUGUEGARAO CITY(Capital) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region II | Tuguegarao City | 306401 | Tuguegarao City Science High School | TUGUEGARAO CITY(Capital) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region III | Angeles City | 107041 | Gueco Balibago ES | Angeles City | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1st | 1 | 1080 | - | - | 1080 | 24 | - | - | 3116856 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2023 SF | Region III | Aurora | 104419 | Agues ES | CASIGURAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region III | Aurora | 300695 | Umiray NHS | DINGALAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Aurora | 104511 | Villa Aurora ES | Maria Aurora | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | REGION III | Aurora | 104515 | Dibut ES | SAN LUIS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region III | BALANGA CITY | 104552 | Balanga Elementary School | Balanga City | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region III | Balanga City | 305619 | Balanga City National Science High School | CITY OF BALANGA (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104537 | P. Rubiano ES | ABUCAY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104539 | T. Pinpin MES | ABUCAY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st |  | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1st |  | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104571 | Bayan-Bayanan ES | DINALUPIHAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104579 | Layac ES | DINALUPIHAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300714 | Nagbalayong NHS | MORONG | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104668 | Paraiso ES | ORANI | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2nd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 300712 | Mariveles NHS Malaya | MARIVELES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 361011 | Mariveles SHS - Sitio Mabuhay | MARIVELES | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104674 | Bantan ES | ORION | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104675 | Bilolo ES | ORION | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104678 | Capunitan ES | ORION | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 104685 | Sabatan ES | ORION | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bataan | 305899 | Bataan HS for the Arts | BAGAC | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | REGION III | Bulacan | 104804 | F. Mendoza Memorial ES | CALUMPIT | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104813 | Meyto Elementary School | CALUMPIT | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 306723 | San Miguel-Meysulao HS | Calumpit | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104945 | Cabayunan Elementary School | DOÑA REMEDIOS TRINIDAD | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 306713 | Bajet-Castillo HS | Pulilan | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104730 | Borol 2nd Elementary School | BALAGTAS (BIGAA) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104762 | Batia ES | BOCAUE | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104768 | Lolomboy ES | BOCAUE | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104823 | Guiguinto Central School | GUIGUINTO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104980 | Mapulang lupa ES | PANDI | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3rd |  | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104727 | A. S. De Guzman ES (Taboc ES) | ANGAT | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105072 | Camachin ES | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104939 | Apugan ES | NORZAGARAY | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104947 | FVR Phase 3 Elementary School | NORZAGARAY | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 306716 | Upig High School | SAN ILDEFONSO | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105068 | Buliran ES | SAN MIGUEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105080 | Maligaya ES | SAN MIGUEL | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105122 | Paco Elementary School | SAN RAFAEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105133 | San Rafael Cs | SAN RAFAEL | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 104914 | Tabing Ilog ES | MARILAO | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | CABANATUAN CITY | 500561 | Daan Sarile Integrated School | CABANATUAN CITY | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | San Fernando City | 501141 | Malino Integrated School | City of San Fernando | 3rd | 1 | - | - | 240 | 240 | 6 | - | - | 695814 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 300813 | Sta. Cruz NHS | CITY OF GAPAN | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 300829 | Pambuan HS | CITY OF GAPAN | 4th |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4th |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Gapan City | 105330 | Sta. Cruz ES | Gapan City | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Malolos City | 104866 | Bungahan Elementary School | CITY OF MALOLOS (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Malolos City | 104871 | Longos ES | CITY OF MALOLOS (Capital) | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Malolos City | 104882 | Tikay ES | CITY OF MALOLOS (Capital) | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Malolos City | 323601 | Bulihan NHS | CITY OF MALOLOS (Capital) | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Malolos City | 323605 | Pres. Corazon Cojuangco-Aquino MNHS | CITY OF MALOLOS (Capital) | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | Science City of Munoz | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Munoz Science City | 500397 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105173 | Bibiclat ES | ALIAGA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105175 | Don Emiliano Soriano ES | ALIAGA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105183 | San Eustacio Elementary School | ALIAGA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 300783 | Aliaga National NHS | ALIAGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105256 | Bambanaba ES | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105259 | Bonifacio ES | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105260 | Bued PS | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105269 | Cuyapo CS | CUYAPO | 1st | 1 | 675 | - | - | 675 | 15 | - | - | 1948035 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105272 | Doroteo R. Jose Elementary School | CUYAPO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 128367 | Cacapasan Elementary School | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija |  | Brgy. Tutuloy ES | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija |  | Cacapasan ES | CUYAPO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105378 | Cabaruan ES | GUIMBA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105408 | Banitan ES | GUIMBA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105415 | Guimba West CS | GUIMBA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105487 | Tabing Ilog Elemetary School | LICAB | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105566 | Alzate Village ES | NAMPICUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105568 | Maeling Elementary School | NAMPICUAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. HS | QUEZON | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105768 | Baloc ES | SANTO DOMINGO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105774 | Concepcion ES | SANTO DOMINGO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 159006 | Pulong Buli ES | SANTO DOMINGO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105799 | Matingkis ES | TALAVERA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105810 | Bantug ES | TALAVERA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105811 | Bantug Hacienda ES | TALAVERA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105814 | Caputican ES | TALAVERA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105815 | Collado ES | TALAVERA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION III | Nueva Ecija | 105817 | Dimasalang Sur ES | TALAVERA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105820 | Homestead I ES | TALAVERA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105825 | Mamandil PS | TALAVERA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105826 | Minabuyok ES | TALAVERA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 501822 | San Pascual Integrated School | TALAVERA | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105853 | Batitang ES | ZARAGOZA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105866 | Zaragoza CS | ZARAGOZA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105240 | Camanggahan ES | CARRANGLAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105513 | Agupalo Weste ES | LUPAO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105526 | Salvacion 2nd ES | LUPAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105302 | Bugnan ES | GABALDON (BITULOK & SABANI) | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 501168 | Virginia D. Dulay Integrated School | GEN. MAMERTO NATIVIDAD | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija |  | Cabiao National Senior High School | CABIAO | 4th | 1 |  | 1305 | - | 1305 | 29 | - | - | 4199200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 29 | 0 |  | 100%
CY 2023 SF | REGION III | Nueva Ecija | 105588 | Sabangan Es To Palale Es | General Tinio (Papaya) | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105438 | Jaen West Elementary School | JAEN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105457 | Sto. Tomas North ES | JAEN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105689 | Sto. Cristo ES | SAN ISIDRO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105740 | San Anton ES | SAN LEONARDO | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105744 | Tambo North E/S | SAN LEONARDO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300875 | Balitucan National High School | MAGALANG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300876 | Andres M. Luciano HS | MAGALANG | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300920 | San Jose High School | FLORIDABLANCA | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 305740 | San Juan Bano High School | ARAYAT | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 301065 | Potrero NHS | BACOLOR | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106198 | Sta. Maria ES | MEXICO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 105878 | Sto. Rosario ES | APALIT | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 105940 | MAPANIQUI ELEMENTARY | CANDABA | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 105951 | Vizal Sto. Cristo ES | CANDABA | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106091 | Caduang Tete ES | MACABEBE | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106093 | Macabebe Central ES | MACABEBE | 4th | 1 | 1080 | - | - | 1080 | 24 | - | - | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106094 | San Gabriel ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106096 | San Roque ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106097 | San Vicente Ferrer ES | MACABEBE | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106098 | San Vicente San Francisco ES | MACABEBE | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106099 | Saplad David ES | MACABEBE | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106101 | Tacasan ES | MACABEBE | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106102 | Telacsan Elementary | MACABEBE | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106103 | Castuli ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106104 | Concuelo ES | MACABEBE | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106107 | Lolu ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106112 | Sapang Malalam ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106113 | Sta. Lutgarda ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106114 | Sta. Maria CS | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 159519 | Sitio Mindanao ES | MACABEBE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300883 | Caduang Tete HS | Macabebe | 4th | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300915 | San Esteban HS | Macabebe | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300930 | San Vicente-San Francisco NHS | MACABEBE | 4th | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300934 | Sta. Maria NHS, Macabebe | MACABEBE | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300941 | Telacsan NHS | MACABEBE | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306937 | Dalayap HS | Macabebe | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga |  | Consuelo HS | MACABEBE | 4th | 1 |  | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106143 | Alauli ES | MASANTOL | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106144 | Bagang ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106145 | Balibago ES | MASANTOL | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106146 | Bebe Anac ES | MASANTOL | 4th | 1 | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106147 | Bebe Matua ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106149 | Caingin ES | MASANTOL | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106151 | Malauli ES | MASANTOL | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106152 | Masantol Central ES | MASANTOL | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106153 | Nigui ES | MASANTOL | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106154 | Palimpe ES | MASANTOL | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106155 | Puti ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106156 | San Isidro Matua ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106158 | Sapang Kawayan ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106160 | Sta. Lucia Matua ES | MASANTOL | 4th | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106161 | Sua ES | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 159530 | Sta. Cruz E/S (Annex) | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 159531 | Sagrada Familia ES | MASANTOL | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 159541 | San Pedro PS | MASANTOL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306906 | Sagrada HS (Tarik Suliman HS) | Masantol | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306923 | Sapang Kawayan High School | MASANTOL | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306926 | Malauli HS | Masantol | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106202 | Lourdes ES | MINALIN | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106204 | Sto. Rosario ES (MINALIN ES) | MINALIN | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106205 | San Francisco ES | MINALIN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106206 | San Isidro ES | MINALIN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106207 | San Pedro ES | MINALIN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106209 | Sta. Maria ES | MINALIN | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106211 | Sto. Domingo ES | MINALIN | 4th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300935 | Sta. Maria HS | Minalin | 4th | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300936 | Sto. Rosarion HS | Minalin | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306939 | Bulac HS | Minalin | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 306946 | Conrado P. Mapinlac Sr. HS | Minalin | 4th | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106263 | San Simon Elementary School | SAN SIMON | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106300 | San Matias ES | SANTO TOMAS | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106302 | Sapa ES | SANTO TOMAS | 4th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 106303 | Sto. Rosarion Pau ES | SANTO TOMAS | 4th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga | 300924 | San Matias NHS | SANTO TOMAS | 4th | 1 | - | 1350 | - | 1350 | 30 | - | - | 4344000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga |  | Poblacion ES | SANTO TOMAS | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Pampanga |  | Poblacion HS | SANTO TOMAS | 4th | 1 |  | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | City of San Jose Del Monte | 107150 | Paradise Farms Community School | CITY OF SAN JOSE DEL MONTE | Lone | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106306 | Bantog ES | ANAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106309 | San Jose ES | ANAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106347 | Marawi ES | Camiling | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 300952 | Bilad High School | CAMILING | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 300997 | Tarlac National High School - Annex | CITY OF TARLAC (Capital) | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106548 | CAMPOSANTO ES | MONCADA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 307011 | Moncada National High School | MONCADA | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106576 | Burgos ES | PANIQUI | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | PANIQUI | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106610 | Ramos CS | RAMOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106665 | Sta. Maria ES | SAN MANUEL | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106443 | Abagon ES | GERONA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106445 | Buenlag ES | GERONA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106452 | Magaspac ES | Gerona | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106455 | Quezon ES | GERONA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106475 | Padapada PS | GERONA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106485 | Villa Paz ES | GERONA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 501833 | Calayaan Integrated School | GERONA | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106730 | Sulipa ES | Gerona | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106640 | Moriones ES | SAN JOSE | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2nd |  | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3rd |  | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3rd |  | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 300956 | Calangitan HS (Resettlement School) | CAPAS | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106404 | Concepcion North CES | Concepcion | 3rd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | CONCEPCION | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac | 106498 | Caut ES | LA PAZ | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac City | 106767 | San Vicente ES Main | CITY OF TARLAC (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Tarlac City | 321402 | Baras Baras HS | CITY OF TARLAC (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Zambales | 106856 | Castillejos Elementary School | CASTILLEJOS | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region III | Zambales | 106857 | Del Pilar Elementary School | CASTILLEJOS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Zambales | 160513 | Josephine F. Khonghun Special Education Center | SUBIC | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region III | Zambales | 106813 | Bangan -Capayawan Elementary School | BOTOLAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Antipolo City | 109339 | San Isidro ES | CITY OF ANTIPOLO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Antipolo City | 321505 | Dela Paz NHS | CITY OF ANTIPOLO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region IV-A | Antipolo City | 109347 | Binayoyo ES (Binayoyo Integrated HS) | CITY OF ANTIPOLO | 2nd | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | REGION IV-A | Antipolo City | 301420 | Dalig Nhs To Cupang Nhs | City Of Antipolo | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Bacoor City | 107873 | Mambog ES | BACOOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Bacoor City | 107875 | Salinas ES | BACOOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Bacoor City | 107879 | Gawaran ES | BACOOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Bacoor City | 107887 | Niog Elementary School | BACOOR | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | REGION IV-A | Bacoor City | 107890 | Talaba Elementary School | BACOOR | 2nd | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | Bacoor City | 301171 | Bacoor NHS - Molino Main | BACOOR | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 342209 | Balayan Senior High School | BALAYAN | 1st | 1 | - | 1080 | - | 1080 | 24 | - | - | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 342209 | Balayan Senior High School | BALAYAN | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 301070 | Ananias C. Hernandez Memorial National High School | LEMERY | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 163505 | Antonio Bonsol Elementary School | TAAL | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107427 | Balatbat Elementary School | LOBO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107428 | Balibago Elementary School | LOBO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107642 | Boboy Elementary School | SAN LUIS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 301148 | Santa Monica NHS | SAN LUIS | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107818 | Talahib Elementary School | TINGLOY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107342 | Dalipit Elementary School | CUENCA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107471 | Malvar Central School | MALVAR | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 342219 | SHS in Sto. Tomas | SANTO TOMAS | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107560 | Marilag Elementary School | ROSARIO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107563 | Mayuro ES | ROSARIO | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 107584 | Aya Elementary School | SAN JOSE | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas |  | San Juan Senior High School | San Juan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas |  | San Juan Senior High School | San Juan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 301098 | Dagatan NHS | Taysan | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas |  | Taysan SHS | Taysan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas |  | Taysan SHS | Taysan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas City | 109548 | Dumantay ES | BATANGAS CITY (Capital) | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-A | Biñan City | 307932 | Mamplasan NHS | CITY OF BIÑAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 107895 | Lantic ES | CARMONA | 5th | 1 | 720 | - | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 107941 | San Gabriel II ES | GEN. MARIANO ALVAREZ | 5th | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108111 | Silang West ES | SILANG | 5th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108118 | Carmen ES | SILANG | 5th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108130 | Pasong Langka ES | SILANG | 5th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108013 | Mahabang Kahoy Cerca ES | INDANG | 7th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108027 | Baliwag ES | MAGALLANES | 8th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 108036 | Urdaneta ES | MAGALLANES | 8th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Cavite | 301216 | Tagaytay City NHS Annex (Senior HS) | TAGAYTAY CITY | 8th | 1 | - | 2880 | - | 2880 | 64 | - | - | 9267200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 64 | 0 |  | 100%
CY 2023 SF | Region IV-A | Dasmarinas City | 107905 | Malinta Elementary School | CITY OF DASMARIÑAS | 4th | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | General Trias City | 107948 | Ipilan Barrio School | GEN. TRIAS CITY | 6th | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Imus City | 107981 | Alapan II Elementary School | IMUS | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108305 | B.N. Calara ES | BAY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3rd | 1 | 720 | - | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108365 | San Francisco ES | NAGCARLAN | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108497 | Masapang ES | VICTORIA | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108329 | Maytalang I ES | LUMBAN | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108392 | Casa Real ES | PAKIL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108401 | Pakil ES | PAKIL | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108442 | Pagsawitan ES | SANTA CRUZ (Capital) | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Laguna | 108451 | Sto. Angel Norte E/S | SANTA CRUZ (Capital) | 4th | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | REGION IV-A | Laguna | 307940 | Sta. Maria NHS - Calangay Annex | SANTA MARIA | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lipa City | 109665 | San Lucas ES | LIPA CITY | 4th | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lipa City | 301499 | San Celestino Integrated National High School | LIPA CITY | 4th | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6th | 1 | - | - | 800 | 800 | 20 | - | - | 2319380 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6th | 1 | - | - | 480 | 480 | 12 | - | - | 1391628 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6th |  | - | - | 320 | 320 | 8 | - | - | 1034400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Lucena City | 109716 | Camp Nakar ES | Lucena City | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109084 | Caldong Resettlement ES | SAMPALOC | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108617 | Kinatihan I ES | CANDELARIA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 308016 | Dolores Macasaet National High School | CANDELARIA | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108680 | Don Severo Filismino ES | DOLORES | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 301305 | Callejon NHS | San Antonio | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109179 | Emiliano Gala Memorial ES | SARIAYA | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109187 | Manggalang I ES | Sariaya | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109290 | Tiaong East ES | TIAONG | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108948 | DAYAP ES | AGDANGAN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108949 | E. LICUP ES | AGDANGAN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 165001 | Bagong Silang ES | Buenavista | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108933 | Malibago ES | Mulanay | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109124 | Loawan ES | San Francisco | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108509 | Atimonan CES | Atimonan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108514 | Caridad Ibaba ES | Atimonan | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108595 | Binutas ES | CALAUAG | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108599 | Dona Aurora ES | Calauag | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 108754 | Biga-Labnig ES | GUMACA | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Quezon | 109228 | Tabason ES | Tagkawayan | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 109372 | Tatala ES | BINANGONAN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 301436 | Don Jose M. Ynares,Sr. Memorial National High School | BINANGONAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 109535 | Taytay ES | Taytay | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 109459 | Quisao ES | Pililla | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 109477 | San Isidro ES | Rodriguez | 2nd | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region IV-A | Rizal | 109502 | Cayabu ES | Tanay | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | San Pablo City | 109806 | Guerilla Elementary School | San Pablo City | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region IV-A | Sta. Rosa City | 307902 | Santa Rosa Science and Technology High School | CITY OF SANTA ROSA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-A | Tanauan City | 230501 | Dayapan Elementary School | CITY OF TANAUAN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-A | Tayabas City | 500496 | Dapdap Integrated School | CITY OF TAYABAS | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION IV-A | Tayabas City | 109258 | Potol ES | CITY OF TAYABAS | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region IV-B | Calapan City | 301798 | Canubing National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1st |  | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Calapan City | 301800 | Oriental Mindoro National High School | CITY OF CALAPAN (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Calapan City | 301802 | Nag-iba National High School | CITY OF CALAPAN (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Marinduque | 109918 | Tungib ES | BUENAVISTA | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region IV-B | Marinduque | 301553 | Maranlig National High School | TORRIJOS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Marinduque | 308801 | Poctoy NHS (Bonliw NHS-Poctoy Annex) | TORRIJOS | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | REGION IV-B | Marinduque | Newly-Established School | Tigwi Nhs To Tigwi Shs | Torrijos | Lone | 1 | - | - | 480 | 480 | 12 | - | - | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-B | Occidental Mindoro | 110094 | Agkawayan ES | LOOC | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Occidental Mindoro | 110126 | Canabang ES | MAGSAYSAY | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Occidental Mindoro | 110306 | Mapaya II ES | SAN JOSE | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301616 | Baco NHS | BACO | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | BACO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309008 | Anastacio Dela Chica High School | BACO | 1st |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301611 | Apitong NHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301614 | Aurora NHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301630 | Doroteo S. Mendoza Sr. MNHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301651 | San Agustin NHS | NAUJAN | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301651 | San Agustin NHS | NAUJAN | 1st |  | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309001 | Inarawan NHS | NAUJAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309001 | Inarawan NHS | NAUJAN | 1st |  | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301627 | Domingo Yu Chu NHS | POLA | 1st |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301628 | Araceli B. Pantilanan - Bacawan High School | POLA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301629 | Matulatula High School | POLA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301629 | Matulatula High School | POLA | 1st |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309025 | Leandro Panganiban Sr. - Tagumpay High School | POLA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 110613 | Isidoro Suzara Memorial School | PUERTO GALERA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301635 | Fortuna NHS | SOCORRO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1st | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301613 | Aurelio Arago MNHS | VICTORIA | 1st |  | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301655 | Villapagasa NHS | BANSUD | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 309027 | Felimon M. Salcedo Sr. MNHS | BANSUD | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301621 | Maujao NHS | BULALACAO (SAN PEDRO) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Oriental Mindoro | 301639 | Marcelo I. Cabrera Vocational HS | ROXAS | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 110747 | Villasol ES | Agutaya | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301734 | Salvacion National High School | BUSUANGA | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309167 | Concepcion National High School | BUSUANGA | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309167 | Concepcion National High School | BUSUANGA | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309167 | Concepcion National High School | BUSUANGA | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 110971 | Talaga ES | Cagayancillo | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301677 | Cagayancillo National High School | CAGAYANCILLO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region III | Bulacan | 105082 | Partida Elementary | SAN MIGUEL | 3rd |  | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 303817 | Sominot National High School | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 2896000 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 |  | 0%
CY 2023 SF | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309168 | Decalachao National High School | CORON | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301688 | Cuyo National High School | CUYO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301708 | Manamoc National High School | CUYO | 1st | 1 | - | 180 | - | 180 | 4 | - | 21 | 817550 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 305744 | Pical NHS | Linapacan | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 111041 | Balaguen ES | Magsaysay | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301745 | Tumarbong National High School | ROXAS | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | REGION IV-B | Palawan | 111176 | Tinitian Elementary School | ROXAS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 111197 | Pagdanan ES | San Vicente | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | REGION IV-B | Palawan | 111143 | Casian Nhs To Caramay Es | Taytay | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301722 | Plaridel NHS | ABORLAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309127 | Sibaring National High School | BALABAC | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309129 | Southern Bataraza National High School | BATARAZA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 110866 | Brooke's Point Central School SPED Center | BROOKE'S POINT | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301690 | Dumangeña National High School | NARRA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301727 | Quezon-Aramaywan National High School | QUEZON | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301729 | Quinlogan National High School | QUEZON | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301743 | Tagusao National High School | QUEZON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301680 | Candawaga National High School | RIZAL (MARCOS) | 2nd |  | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301702 | Jose P. Rizal National High School | RIZAL (MARCOS) | 2nd |  | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 309149 | Taburi National High School | RIZAL (MARCOS) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 301661 | Apurawan NHS | ABORLAN | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Puerto Princesa City | 301779 | Bacungan NHS | Puerto Princesa City | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region IV-B | Puerto Princesa City | 301780 | Bahile NHS | Puerto Princesa City | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region IV-B | Puerto Princesa City | 301788 | Luzviminda NHS | Puerto Princesa City | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region IV-B | Puerto Princesa City | 111485 | Mateo Jagmis MES | PUERTO PRINCESA CITY (Capital) | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111259 | Camili ES | ALCANTARA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 301778 | TUNGONAN NATIONAL HIGH SCHOOL | BANTON | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111404 | Fetalvero-Mingoa MS | CALATRAVA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111307 | Alegria ES | CORCUERA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111350 | Bunsoran ES | FERROL | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111295 | Silum ES | MAGDIWANG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111385 | Palje PS | ROMBLON (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IV-B | Romblon | 111402 | Concepcion Sur ES | SANTA MARIA (IMELDA) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Dapitan City | 303884 | Sulangon NHS- Aliguay Ext. | Dapitan City | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Isabela City | 126002 | ISABELA CENTRAL PILOT ES | ISABELA CITY(Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 868800 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Pagadian City | 303913 | ZAMBOANGA DEL SUR SCHOOL OF ARTS AND TRADES | PAGADIAN CITY (Capital) | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1592800 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga City | 126114 | Southern Support Command ES | ZAMBOANGA CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 868800 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION IX | Zamboanga City | 126104 | Sinunuc ES | ZAMBOANGA CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga City | 126201 | Lumbangan ES | ZAMBOANGA CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga City | 126225 | Guiwan ES | ZAMBOANGA CITY | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1158400 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1st |  | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 434400 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1158400 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124750 | SAWANG ES | SIBUTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1st | 1 | - | - | - | - | - | - | 42 | 476700 | Regional Office Implementation | 55% Allocation for Regular Supplier | 476700 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124374 | Mias ES | KATIPUNAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 724000 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124495 | Dohinob CS | PRES. MANUEL A. ROXAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 434400 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 868800 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3rd |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 124309 | Canupong ES | GUTALAC | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Norte | 303743 | Dacon National High School (Sirawai NHS - Guban Annex) | SIRAWAI | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303786 | Lantungan NHS | AURORA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 196022 | Dumingag SPED Center | DUMINGAG | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 868800 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 125087 | NOPULAN ELEMENTARY SCHOOL | JOSEFINA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | RAMON MAGSAYSAY (LIARGO) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 125394 | EASTERN SOMINOT ELEMENTARY SCHOOL | SOMINOT | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 125451 | CALUMA ELEMENTARY SCHOOL | TIGBAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 124965 | Guinicolalay ES | DINAS | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 125008 | Rebokon ES | DUMALINAO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 314217 | Bibilik NHS | DUMALINAO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region IX | Zamboanga del Sur | 125156 | Karpok Elementary School | LAPUYAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga del Sur | 125502 | LUNIB ELEMENTARY SCHOOL | VINCENZO A. SAGUN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 579200 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 289600 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region IX | Zamboanga Sibugay | 125849 | Laparay ES | Talusan | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 434400 | On-going |  |  |  | 10361188 | 2023-08-226 | 2023-11-25 | 2023-12-05 | 2023-12-18 | 2024-01-19 | 2024-01-25 | Canlubang Techno-Industrial Corp. | Final Demand Letter for receipt of the supplier. | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 111610 | Lower Bonga Elementary School | BACACAY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 112053 | Calayucay Elementary School | SANTO DOMINGO (LIBOG) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 111650 | Solong Elementary School | CAMALIG | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301823 | Ilawod National High School | CAMALIG | 2nd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 111657 | Alcala ES | DARAGA (LOCSIN) | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 111890 | Buyo Elementary School | MANITO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 111720 | Travesia ES | GUINOBATAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301842 | Malipo National High School | GUINOBATAN | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301844 | Mauraro High School | GUINOBATAN | 3rd | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301849 | Marcial O. Rañola Memorial School | GUINOBATAN | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301850 | Lower Binogsacan National High School | GUINOBATAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301850 | Lower Binogsacan National High School | GUINOBATAN | 3rd |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301851 | Masarawag National High School | GUINOBATAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301851 | Masarawag National High School | GUINOBATAN | 3rd |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301836 | San Pascual National High School | LIBON | 3rd | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301860 | Pantao National High School | LIBON | 3rd | 1 | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301870 | Saban National High School | OAS | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301839 | Malapay High School | PIO DURAN | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301828 | Itaran National High School | POLANGUI | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301829 | Maysua High School | POLANGUI | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3rd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3rd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301840 | Magpanambo NHS | POLANGUI | 3rd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301852 | Matacon National High School | POLANGUI | 3rd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Albay | 301868 | Ponso National HS | POLANGUI | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Norte | 112123 | PORTUGAL CHAVEZ ES | CAPALONGA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112154 | OSMENA ES | JOSE PANGANIBAN | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112160 | D. ALBONIA ES | JOSE PANGANIBAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112163 | LARAP ES | JOSE PANGANIBAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112164 | NAKALAYA ES | JOSE PANGANIBAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112193 | NAPAOD ES | LABO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112200 | BAGONG SILANG III | LABO WEST | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112204 | F. CAUDILLA ES | LABO WEST | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112207 | DUMAGMANG I.S. | LABO WEST | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 173020 | PALANAS ES | PARACALE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112282 | M. Hebrado ES | SANTA ELENA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 173008 | DON TOMAS ES | STA. ELENA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 173009 | JUAN A. AMPARO ES | STA. ELENA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112266 | Mampurog ES | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 112275 | San Vicente CS | SAN VICENTE | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 309607 | Lazaro Cabezudo HS | TALISAY | 2nd | 1 | - | 45 | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Norte | 309607 | Lazaro Cabezudo HS | TALISAY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 302051 | Sta. Lutgarda HS (Senior High) | Cabusao | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112577 | Del Gallego CS | DEL GALLEGO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 301961 | Colacling National High School | LUPI | 1st | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301979 | Haluban NHS | LUPI | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301929 | Simeon Tycangco Memorial High School | RAGAY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301977 | Godofredo Reyes Sr. National HS | RAGAY | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302020 | Ragay National Agricultural and Fisheries School (RNAFS) | RAGAY | 1st | 1 | - | 135 | - | 135 | 3 | - | 21 | 672750 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302047 | Sipocot NHS | SIPOCOT | 1st | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 112779 | Gainza CS - Gainza | GAINZA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112688 | Mantalisay Elementary School | LIBMANAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112698 | Umalo ES | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112700 | Bagamelon ES | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112705 | Caima Elementary School | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112714 | Odoc ES | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112717 | Salvacion ES | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112724 | Villa Socorro ES | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 173508 | Tinanquihan Primary School | LIBMANAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 302037 | San Juan National HS | LIBMANAN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur |  | Bagadion High School (Mambulo Nuevo HS Annex) | LIBMANAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112801 | Malitbog ES | MINALABAC | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112869 | Calawat PS/Elementary School | PAMPLONA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112876 | San Ramon ES | PAMPLONA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 302012 | Pamplona NHS | PAMPLONA | 2nd |  | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112907 | Hubo ES | PASACAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112915 | Tilnac Elementary School | PASACAO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 500158 | Antipolo Heights Integrated School | PASACAO | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112994 | Alianza ES | SAN FERNANDO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112996 | BICAL ELEMENTARY SCHOOL | SAN FERNANDO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112998 | Calascagas PS | SAN FERNANDO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 113001 | Gñaran ES | SAN FERNANDO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 113011 | Sta. Cruz ES | SAN FERNANDO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 302013 | PAMUKID NATIONAL HIGH SCHOOL | SAN FERNANDO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 309705 | Pinamasagan National High School | SAN FERNANDO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112771 | Sto. Domingo Elementary School | BOMBON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 301998 | Medroso-Mendoza NHS | CALABANGA | 3rd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112498 | Camaligan Central School | CAMALIGAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 112762 | Magarao Central School | Magarao | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 309749 | BINOBONG HIGH SCHOOL | PILI (Capital) | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 137076 | Sitio Lipata ES | CARAMOAN | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 300496 | New Partido HS | Goa | 4th | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 305545 | Goa Science NHS | Goa | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region V | Camarines Sur | 309753 | SALOGON HS | San Jose | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301926 | Agdangan National High School | BAAO | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301933 | Eusebia Paz Arroyo Mem. NHS | BAAO | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301960 | Coguit HS | BALATAN | 5th | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302014 | Pararao High School | BALATAN | 5th | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302059 | Tapayas High School | BALATAN | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309725 | Laganac High School | BALATAN | 5th | 1 | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309759 | Pulang Daga High School | BALATAN | 5th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 112383 | San Miguel ES | BATO | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301997 | Masoli High School | BATO | 5th | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302026 | Salvacion HS, Bato | BATO | 5th | 1 | - | 270 | - | 270 | 6 | 14 | 14 | 1193880 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302027 | San Roque High School | BATO | 5th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302044 | Bato National High School | BATO | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302044 | Bato National High School | BATO | 5th |  | - | 135 | - | 135 | 3 | 7 | 7 | 596940 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302043 | San Vicente NHS | BUHI | 5th | 1 | - | 135 | - | 135 | 3 | 7 | 7 | 596940 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 305484 | Iraya High School | BUHI | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301947 | Bula NHS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301948 | Bula NHS - Caorasan Annex HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301959 | Casugad High School | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5th | 1 | - | 135 | - | 135 | 3 | - | 7 | 513850 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301971 | Fabrica HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301982 | Inoyonan National HS | BULA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301982 | Inoyonan National HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302010 | Palsong NHS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302041 | San Ramon HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 309760 | Fabrica HS - La Victoria Annex HS | BULA | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301985 | La Purisima National High School | NABUA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 301991 | Malawag National High School | NABUA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302001 | Nabua National High School | NABUA | 5th | 1 | - | 675 | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Camarines Sur | 302002 | Lourdes PHS | NABUA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302076 | Bugao NHS | Bagamanoc | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 113173 | Baras CES | BARAS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302070 | Agban NHS | Baras | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302073 | Baras RDHS | Baras | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302073 | Baras RDHS | Baras | Lone |  | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302075 | Bote Integrated School | BATO | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 500032 | Cabugao IS | Bato | Lone |  | - | - | - | - | - | 14 | - | 166180 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302081 | Caramoran RDHS | Caramoran | Lone | 1 | - | 270 | - | 270 | 6 | - | 42 | 1345500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302081 | Caramoran RDHS | Caramoran | Lone |  | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302082 | Caramoran SF | Caramoran | Lone | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302082 | Caramoran SF | Caramoran | Lone |  | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302088 | Gigmoto RDHS | Gigmoto | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 500033 | Sicmil IS | Gigmoto | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302103 | Leandro I. Verceles Sr. NHS | Pandan | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302103 | Leandro I. Verceles Sr. NHS | Pandan | Lone |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 500159 | Cobo IS | Pandan | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 309801 | Panganiban NHS (CAIC Compound) | Panganiban (Payo) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302078 | Cabcab NHS | San Andres (Calolbon) | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302091 | Manambrag NHS | San Andres (Calolbon) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302098 | San Miguel Rural DHS | SAN MIGUEL | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302099 | Mabato NHS (SMRDHS Annex) | San Miguel | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302105 | Tinago NHS | Viga | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302107 | Viga RDHS | Viga | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302071 | Antipolo NHS | Virac (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 302084 | Calatagan High School | Virac (Capital) | Lone | 1 | - | 765 | - | 765 | 17 | - | - | 2461600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Catanduanes | 500031 | Buyo IS | Virac (Capital) | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION V | Iriga City | 500168 | Santiago Integrated School | IRIGA CITY | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Legaspi City | 100182 | Banquerohan Resettlement Elementary School | Legazpi City | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION V | Legaspi City | 114475 | Bitano ES | LEGAZPI CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Legaspi City | 114496 | Tamaoyan ES | LEGAZPI CITY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Ligao City | 301817 | Cabarian NHS | CITY OF LIGAO | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Ligao City | 301862 | Paulba NHS | CITY OF LIGAO | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Ligao City | 321701 | Ligao City National Technical -Vocational High School | CITY OF LIGAO | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Ligao City | 231004 | Nabonton ES, Buga Ext. | Ligao City | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113477 | Batuan CS | BATUAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 174511 | Cogon ES | MONREAL | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302152 | Monreal National High School | MONREAL | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 501273 | Buenavista Integrated School | SAN FERNANDO | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309901 | Delavin-Rubia National High School | AROROY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309951 | AMOTAG NATIONAL HIGH SCHOOL | AROROY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113440 | Potoson ES | BALENO | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302115 | Baleno National High School | BALENO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302140 | Lagta National High School | BALENO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309931 | Amador-Bello HS | BALENO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302156 | Briccio A. Aninang Sr. Mem. HS | BALUD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302156 | Briccio A. Aninang Sr. Mem. HS | BALUD | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302160 | Salvador Arollado, Sr. MHS | BALUD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302160 | Salvador Arollado, Sr. MHS | BALUD | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302161 | Liberato P. Tacurda Sr. HS | BALUD | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302164 | Quinayangan National High School | BALUD | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302164 | Quinayangan National High School | BALUD | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302122 | Bugtong National High School | MANDAON | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302122 | Bugtong National High School | MANDAON | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302125 | Cleofe A. Arce Memorial High School | MANDAON | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302145 | Federico A. Estipona Memorial High School | MANDAON | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302150 | Milagros National High School | MILAGROS | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309906 | Serafin C. Rosero Memorial High School | MILAGROS | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309906 | Serafin C. Rosero Memorial High School | MILAGROS | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309908 | Mary Perpetua E. Brioso Memorial High School | MILAGROS | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302146 | Marintoc National High School | MOBO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302146 | Marintoc National High School | MOBO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302151 | Mobo National High School | MOBO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309922 | Floro L. Medina MHS | MOBO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309922 | Floro L. Medina MHS | MOBO | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113505 | Abaca ES | CATAINGAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113506 | Bagumbayan ES | CATAINGAN | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113509 | Chimenea ES | CATAINGAN | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113525 | San Isidro Elementary School | CATAINGAN | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113543 | Dalipe ES | CAWAYAN | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113603 | Calabad ES | DIMASALANG | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113612 | N.B. Cabrera ES | DIMASALANG | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113633 | Sorosimbahan ES | ESPERANZA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113782 | Pedro A. Basas ES | PALANAS | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3rd | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309911 | Miabas National High School | PALANAS | 3rd |  | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 113823 | Calumpang ES | PLACER | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302118 | G. Bangalisan National High School | PLACER | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302136 | Matagangtang National High School | PLACER | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302165 | Rodolfo Z. Titong National High School | PLACER | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302176 | Verdida-Sabrido NHS | PLACER | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302178 | Vivencio P. Casas Sr. Memorial High School | PLACER | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 309903 | Arriesgado-Sevilleno National High School | PLACER | 3rd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302110 | Temistocles A. Merioles, Sr. Memorial High School | USON | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate | 302175 | Uson National High School | USON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Masbate City | 113702 | Nursery Elementary School | CITY OF MASBATE (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Naga City | 302268 | Naga City Science High School | NAGA CITY | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Naga City | 310302 | Leon Q. Mercado HS (Formerly CSNHS-Pacol Annex) | NAGA CITY | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302240 | San Juan NHS | Casiguran | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 114106 | La Union ES | Castilla | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302226 | Mayon NHS | Castilla | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302231 | PILI NATIONAL HIGH SCHOOL | MAGALLANES | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 310008 | San Rafael NHS | PILAR | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 114006 | Cadandanan ES | Bulan | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 114192 | Gubat North CS | GUBAT | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 114200 | San Ignacio Elementary School | GUBAT | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302214 | Gubat National High School | GUBAT | 2nd |  | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302225 | Matnog NHS | MATNOG | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 302196 | Calao National High School | PRIETO DIAZ | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon | 114415 | Sta. Magdalena CS | SANTA MAGDALENA | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 114561 | Ambrosio J. Labrador Elementary School | CITY OF SORSOGON (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 114568 | Buenavista Elementary School (Sorsogon West) | CITY OF SORSOGON (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302271 | Buenavista National High School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302272 | Celestino G. Tabuena Memorial NHS | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302273 | Gatbo National High School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302278 | Sawanga National High School | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 302280 | Lydia D. Martinez Memorial High School | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 310401 | Buhatan National High School | CITY OF SORSOGON (Capital) | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 310405 | Bogña Integrated School | CITY OF SORSOGON (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500462 | Bogña Integrated School | CITY OF SORSOGON (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500463 | Sto. Niño Integrated School | CITY OF SORSOGON (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | 14 | 417500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500464 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | 14 | 417500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500464 | Buhatan Integrated National School | CITY OF SORSOGON (Capital) | 1st |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500465 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | - | 14 | 417500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Sorsogon City | 500465 | Pamurayan Integrated School | CITY OF SORSOGON (Capital) | 1st |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Tabaco City | 114604 | Tabaco Northwest Central School | CITY OF TABACO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region V | Tabaco City | 302283 | San Lorenzo NHS | CITY OF TABACO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1st |  | - | 225 | - | 225 | 5 | - | - | 649345 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 500170 | Aguinaldo T. Repiedad, Sr. IS | BANGA | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114901 | Tomas SM Bautista Elementary School | NEW WASHINGTON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114912 | Tambak Elementary School | New Washington | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 302297 | Buruanga Vocational School | BURUANGA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114713 | Agbago ES | IBAJAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 500171 | Lezo Integrated School | LEZO | 2nd |  | - | - | - | - | - | - | - | 0 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 500171 | Lezo IS | LEZO | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114842 | Mantiguib ES | MAKATO | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2nd |  | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2nd |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114846 | Balabag ES | MALAY | 2nd |  | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 649345 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2nd |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2nd |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114851 | Manocmanoc ES | MALAY | 2nd |  | 315 | - | - | 315 | 7 | - | - | 909083 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2nd |  | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 302295 | Boracay NHS-Main | MALAY | 2nd |  | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 302295 | Boracay NHS | MALAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2nd |  | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 310603 | LAMBERTO H. TIROL NATIONAL HIGH SCHOOL | MALAY | 2nd |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114887 | Nabas ES | NABAS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 114917 | Bulwang Elementary School | Numancia | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Aklan | 501181 | Vivo Integrated School | TANGALAN | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 114942 | Iba ES | ANINI-Y | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 114973 | Belison CS | BELISON | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 302347 | Belison NS | BELISON | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 114991 | Jinalinan-Paliwan ES | BUGASONG | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 500515 | Kawit Integrated School | CULASI | Lone | 1 | - | - | 480 | 480 | 12 | - | - | 1391628 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115085 | Alberto Siasat ES (Casalngan ES) | HAMTIC | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 310704 | Gen. Leandro Fullon NS | HAMTIC | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115102 | Capnayan PS | LAUA-AN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115117 | Maybunga PS | LAUA-AN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115139 | Tinindugan Primary School | LIBERTAD | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 302359 | Igburi National High School | PATNONGON | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115260 | Cabunga-an-ES | SAN REMIGIO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115287 | Apong Elementary School | SIBALOM | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115353 | Tigbaboy PS | TIBIAO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 115376 | Lawigan ES | TOBIAS FORNIER (DAO) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Antique | 302345 | Barasanan National High School | TOBIAS FORNIER (DAO) | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 181002 | Fr. Gratian Murray, AFCS IS | BACOLOD CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | Bacolod City (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | Lone |  | - | 360 | - | 360 | 8 | - | 56 | 1794000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | Lone |  | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | Lone |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | Lone |  | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302702 | Barangay Singcang-Airport NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302703 | Bata NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | Lone |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | Lone |  | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | Lone |  | - | 270 | - | 270 | 6 | - | 14 | 1027700 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | Lone |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 311201 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 500189 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 500190 | Fr. Gratian Murray, AFCS IS | BACOLOD CITY (Capital) | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 500190 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | Lone | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 500190 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | Lone |  | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Bacolod City | 500190 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | Lone |  | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Cadiz City | 302736 | Jerusalem National High School (yee-on Ext.) | Cadiz City | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | CAPIZ | 115578 | West Villaflores ES | MA-AYON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 310812 | Pawa National High School | PANAY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 302418 | Panitan NHS | PANITAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 302392 | Casanayan National High School | PILAR | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 115698 | Hipona ES | PONTEVEDRA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 302391 | Capiz National High School | ROXAS CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | CAPIZ | 115415 | Vicente Fabuna ES | CUARTERO | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 115420 | Mahabang Sapa PS | Cuartero | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2nd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Capiz | 115819 | Tapaz CES | TAPAZ | 2nd |  | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 302626 | Old Poblacion NHS | CITY OF ESCALANTE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 302627 | Tamlang NHS | CITY OF ESCALANTE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Escalante City | 501108 | Paitan IS | Escalante | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 115873 | San Miguel Central School | Jordan | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302432 | Jordan NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302438 | Trinidad V. Canja-Sta. Teresa NHS | JORDAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 115901 | Paaralan ng Buhay ng La Orca | NUEVA VALENCIA | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302433 | Simeon J. Jabasa National High School | NUEVA VALENCIA | Lone |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 302435 | Calaya National High School | NUEVA VALENCIA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VI | Guimaras | 115847 | Aguilar Elementary School | SAN LORENZO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VI | Iloilo | 116360 | Guimbal CES | GUIMBAL | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region VI | Iloilo | 302506 | Guimbal NHS | GUIMBAL | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302507 | Igbaras NHS | IGBARAS | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | ILOILO | 302531 | MIAG-AO NATIONAL HIGH SCHOOL | MIAG-AO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302495 | Don Felix Serra NHS | SAN JOAQUIN | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302578 | Tigbauan NHS | TIGBAUAN | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 115945 | Alimodian CES | ALIMODIAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116861 | Sigangao ES | ZARRAGA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | ILOILO | 302492 | Don Benjamin Jalandoni Sr. MNHS | ZARRAGA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302452 | Badiangan NHS | BADIANGAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302442 | Acao NHS | CABATUAN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302447 | Ambrosio Maido MNHS | CABATUAN | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116156 | Aglibacao ES | CALINOG | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116193 | Maspasan Elementary School | CALINOG | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302444 | Alcarde Gustilo Mem. National High School | CALINOG | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302453 | Badlan NHS | CALINOG | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302477 | Calinog NCHS | CALINOG | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302481 | CARVASANA NHS | CALINOG | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302526 | Malitbog National High School | CALINOG | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 311018 | Fernandez Perez MNHS | CALINOG | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302560 | Quipot National High School | JANIUAY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116428 | Don Eugenio Ladrido MES | LAMBUNAO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302517 | Lambunao National High School | LAMBUNAO | 3rd | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 311003 | Jayobo NHS | LAMBUNAO | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 311020 | Caninguan NHS | LAMBUNAO | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | ILOILO | 116465 | Pughanan Integrated School | Lambunao West | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302524 | Maasin National Comprehensive High School | MAASIN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302559 | Leon Mediana NHS | MAASIN | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302533 | Mina NHS | MINA | 3rd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302514 | Jose Facultad Memorial National High School | POTOTAN | 3rd | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4th | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302455 | Banate NHS | BANATE | 4th |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302489 | De La Paz National High School | BANATE | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302491 | Dominador Abang MNHS | SAN ENRIQUE | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302461 | Bay-ang NHS | AJUY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | ILOILO | 302523 | Luca NHS | AJUY | 5th | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302454 | Balasan NHS | BALASAN | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116067 | Gen. Luna ES | BAROTAC VIEJO | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116072 | Nueva Invencion ES | BAROTAC VIEJO | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302458 | Barotac Viejo National High School | BAROTAC VIEJO | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302502 | GEN. LUNA NHS | BAROTAC VIEJO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 116091 | Banban PS | BATAD | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5th | 1 | - | - | - | - | - | - | 7 | 79450 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | CARLES | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302484 | Roberto H. Tirol High School | CONCEPCION | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5th |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302500 | Estancia National High School | ESTANCIA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302532 | Milan NHS | LEMERY | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302493 | Carlos Lopez NHS | SAN DIONISIO | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo | 302570 | Sara NHS | SARA | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo City | 117617 | Mandurriao ES | Iloilo City | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo City | 302737 | Fort San Pedro National High School | Iloilo City | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | REGION VI | Iloilo City | 117606 | La Paz ES I | ILOILO CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Iloilo City | 117625 | Taal ES | ILOILO CITY (Capital) | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6th |  | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302789 | Kabankalan NHS | CITY OF KABANKALAN | 6th | 1 | - | 765 | - | 765 | 17 | - | - | 2461600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302791 | Talubangi NHS | CITY OF KABANKALAN | 6th | 1 | - | 630 | - | 630 | 14 | - | - | 2027200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Kabankalan City | 302794 | Inapoy NHS | Kabankalan City | 6th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 180511 | Hipolito Mahilum ES | CALATRAVA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302658 | Labilabi NHS | TOBOSO | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302662 | Manapla National High School | MANAPLA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302663 | Manapla NHS - Purisima Extension | MANAPLA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117028 | Jose M. Consing Memorial School | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302621 | Enrique B. Magalona NHS | ENRIQUE B. MAGALONA (SARAVIA) | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION VI | Negros Occidental | 117275 | Alegria ES | MURCIA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 300683 | San Enrique NHS (Sibucao Ext.) | SAN ENRIQUE | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302692 | Tinongan NHS | ISABELA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117218 | Cabacungan ES | LA CASTELLANA | 5th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VI | Negros Occidental | 117232 | Don Felix Robles ES | LA CASTELLANA | 5th | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 116955 | Abaca ES | CAUAYAN | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 116966 | Isio ES | CAUAYAN | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 116975 | Man-uling ES | CAUAYAN | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 116989 | Tuyom ES | CAUAYAN | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6th |  | - | 270 | - | 270 | 6 | - | 42 | 1345500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 305809 | Jose N. Villanueva National High School | CAUAYAN | 6th | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 501793 | Baclao Integrated School | CAUAYAN | 6th | 1 | - | - | 440 | 440 | 11 | - | - | 1422300 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302634 | Gil Montilla NHS - Binulig Ext. | CITY OF SIPALAY | 6th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302639 | Gil Montilla NHS - Crossing Tanduay Ext. | CITY OF SIPALAY | 6th | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6th |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6th |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302665 | Nabulao NHS - Cayhagan Extension | CITY OF SIPALAY | 6th | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117141 | Bato ES | HINOBA-AN (ASIA) | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117142 | Bilbao-Watkins ES | HINOBA-AN (ASIA) | 6th | 1 | 1170 | - | - | 1170 | 26 | - | - | 3764800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117144 | C.L. Hodges ES | HINOBA-AN (ASIA) | 6th | 1 | 495 | - | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117147 | Culipapa ES | HINOBA-AN (ASIA) | 6th | 1 | 1350 | - | - | 1350 | 30 | - | - | 4344000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117148 | Damutan ES | HINOBA-AN (ASIA) | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117150 | Don E. Bilbao ES | HINOBA-AN (ASIA) | 6th | 1 | 990 | - | - | 990 | 22 | - | - | 3185600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117153 | JM.Reliquias ES | HINOBA-AN (ASIA) | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6th | 1 | 1305 | - | - | 1305 | 29 | - | - | 4199200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117157 | Paz Vda. de Escamilla ES | HINOBA-AN (ASIA) | 6th | 1 | 495 | - | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117159 | San Rafael ES | HINOBA-AN (ASIA) | 6th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117160 | Talacagay ES | HINOBA-AN (ASIA) | 6th | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6th | 1 | - | 2205 | - | 2205 | 49 | - | - | 7095200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302614 | Culipapa National High School | HINOBA-AN (ASIA) | 6th | 1 | - | 1260 | - | 1260 | 28 | - | - | 4054400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 117173 | Tabu ES | ILOG | 6th | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302661 | Juan Gequillana NHS (Manalad NHS) | ILOG | 6th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302688 | Tabu NHS | ILOG | 6th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Negros Occidental | 302688 | Tabu NHS | ILOG | 6th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Passi City | 101052 | Ayuyan Elementary School | CITY OF PASSI | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | ROXAS CITY | 117675 | Tanza ES | ROXAS CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Roxas City | 302757 | Cong. Ramon A. Arnaldo HS | ROXAS CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | 14 | - | 745380 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Roxas City | 302759 | Dumolog NHS | ROXAS CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Roxas City | 311704 | Don Ynocencio A. Del Rosario National High School formerly Tanque NHS-Dayao Extension | ROXAS CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | San Carlos City | 117790 | Mabato ES | SAN CARLOS CITY | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | San Carlos City | 302775 | Julio Ledesma NHS | San Carlos City | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Sipalay City | 302635 | Gil Montilla NHS - Cabadiangan Ext. | CITY OF SIPALAY | 6th | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Sipalay City | 302636 | Gil Montilla NHS - Camindangan Ext. | CITY OF SIPALAY | 6th | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0%
CY 2023 SF | Region VI | Sipalay City | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bais City | 120077 | Olympia Elementary School | BAIS CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303214 | Dodong Escaño Memorial High School | BAIS CITY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 303216 | Bais City National Science High School | BAIS CITY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 323004 | Cambagahan National HS | BAIS CITY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 323007 | Mansangaban National High School | BAIS CITY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bayawan City | 120118 | Olandao Elementary School | BASAY | 3rd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bayawan City | 303219 | Bal-os National High School | BASAY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bayawan City | 303220 | Maglinao National High School | BASAY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bayawan City | 303227 | Dawis National High School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 117934 | Tagbuane ES | ALBURQUERQUE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302883 | Calape National High School | CALAPE | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302877 | Mantacida National High School | CATIGBIAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 111201 | San Vicente CS | SAN VICENTE | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 170530 | Casoyan ES | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 305722 | De La Paz High School | CORTES | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302881 | Pagnitoan National High School | MARIBOJOC | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312360 | Ponciano L. Padin National High School | BIEN UNIDO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118070 | Cambus-oc ES | BUENAVISTA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118072 | Cantores PS | BUENAVISTA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118082 | Overland ES | BUENAVISTA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2nd |  | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312312 | Panghagban HS | BUENAVISTA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302836 | Clarin National School of Fisheries | CLARIN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region IV-B | Palawan | 111211 | Bato CS | TAYTAY | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 118227 | Mahayag Elementary School | DAGOHOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302843 | Francisco Dagohoy Memorial High School | DANAO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302859 | Southern Inabanga HS | INABANGA | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302827 | Campao Oriental High School | JETAFE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302828 | Handumon NHS | JETAFE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312324 | Bonbonon High School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 312325 | Gaus High School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 312335 | Basiao High School | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312353 | Campamanog HS | PRES. CARLOS P. GARCIA (PITOGO) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312309 | JAPeR Memorial High School | SAGBAYAN (BORJA) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118723 | San Agustin Elementary School | TALIBON | 2nd |  | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302814 | Zosimo A. Gulle Memorial National High School | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2nd |  | - | 405 | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2nd |  | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2nd |  | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302896 | Sikatuna Nat'l Agricultural HS | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 312313 | Mayor Catalino Y. Casoyla MHS | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 312331 | Ponciana E. Leoligao HS | TALIBON | 2nd | 1 | - | 135 | - | 135 | 3 | - | 21 | 672750 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Bohol | 312350 | San Isidro High School | TALIBON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118745 | Banlasan ES | TRINIDAD | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118749 | Guinobatan ES | TRINIDAD | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118759 | Mahagbu ES | TRINIDAD | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118768 | Trinidad Central Elementary School | TRINIDAD | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302858 | Hinlayagan NHS | TRINIDAD | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 500216 | Soom IS | TRINIDAD | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 695814 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 303130 | Erico B. Aumentado High School | UBAY | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 117954 | Bacong ES | ANDA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118019 | Garcia ES | BATUAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3rd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Bohol | 118671 | Magsaysay ES | SEVILLA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 119477 | Minglanilla Central ES | MINGLANILLA | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 312472 | Badian NHS - Sanlagan Ext. | BADIAN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 119305 | Mantalongon ES | DALAGUETE | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 500487 | Minolos IS | BARILI | 3rd | 1 | - | - | 480 | 480 | 12 | - | - | 1391628 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 119266 | Daanbantayan Central ES | DAANBANTAYAN | 4th | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region VII | Cebu | 302961 | Calape NHS | DAANBANTAYAN | 4th | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 303047 | Madridejos NHS | MADRIDEJOS | 4th | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 119453 | Bomedco ES | MEDELLIN | 4th | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 303087 | San Remegio NHS | SAN REMIGIO | 4th | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 501669 | Hagnaya IS | SAN REMIGIO | 4th | 1 | - | - | 480 | 480 | 12 | - | - | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Cebu | 119196 | Luyang ES | CARMEN | 5th | 1 | 1800 | - | - | 1800 | 40 | - | - | 5792000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5th | 1 | 1800 | - | - | 1800 | 40 | - | - | 5792000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 500655 | Bagalnga Integrated School | COMPOSTELA | 5th | 1 | - | - | 480 | 480 | 12 | - | - | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Cebu | 119419 | Liloan Nhs To Suba Es | Liloan | 5th | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5th | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 303008 | Luciano B. Rama Sr. MNHS | PORO | 5th | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 119257 | Gabi ES | CORDOBA | 6th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Cebu | 118998 | Basiao PS | BADIAN | 7th |  | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Guihulngan City | 120249 | Laos ES | City of Guihulngan | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Guihulngan City | 120280 | Pitogo PS | CITY OF GUIHULNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Guihulngan City | 303233 | Guihulngan NHS - Hilaitan | CITY OF GUIHULNGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Guihulngan City | 120634 | Malangsa ES | Vallehermoso | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Guihulngan City | 312904 | Guba High School | VALLEHERMOSO | 1st | 1 | - | 45 | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120032 | Awa-an ES | AYUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120052 | Nabhang ES | AYUNGON | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120059 | Tiguib ES | AYUNGON | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120184 | Manseje Elementary School | BINDOY (PAYABON) | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120199 | Binalbagan Elementary School | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120210 | Manggapa Elementary School | CANLAON CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120218 | Upper Lumapao ES | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120303 | MONGPONG PRIMARY SCHOOL | JIMALALUD | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120389 | Lamogong ES | MANJUYOD | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120398 | Sacsac ES | MANJUYOD | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120404 | Tanglad Elementary School | MANJUYOD | 1st | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120580 | Cambaye Elementary School | TAYASAN | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120599 | Suquib Elementary School | TAYASAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 312965 | Jose B. Cardenas MHS - Pula Ext. | CANLAON CITY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 312966 | Panciao High School | MANJUYOD | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120198 | Bayog Elementary School | CANLAON CITY | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312916 | Jose B. Cardenas MHS - Uptown Annex | CANLAON CITY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312954 | Malaiba HS | CANLAON CITY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312955 | Masulog HS | CANLAON CITY | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental |  | Carmen ES | CANLAON CITY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental |  | Pasto ES | CANLAON CITY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312922 | Jimalalud NHS - Tamao Ext. | JIMALALUD | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120310 | Agbobolo ES (Aya ES) | LA LIBERTAD | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303258 | Pacuan National High School | LA LIBERTAD | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120587 | Lutay ES | Tayasan | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303289 | Tayasan National High School (Main) | TAYASAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303207 | Amlan National High School | AMLAN (AYUQUITAN) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303209 | Silab Community High School Annex | AMLAN (AYUQUITAN) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312957 | Amlan NHS-Jugno Campus | AMLAN (AYUQUITAN) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120368 | Manlingay Elementary School | MABINAY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303234 | Inapoy High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312924 | Campanun-an Senior High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120435 | Alicia C. Calumpang Elementary School | SAN JOSE | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Dumaguete City | 303168 | Dumaguete City National High School | DUMAGUETE CITY (Capital) | 2nd | 1 | - | 1620 | - | 1620 | 36 | - | - | 5212800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120485 | Calabnugan Elementary School | Sibulan | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120488 | Escaguit Elementary School | SIBULAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Negros Oriental | 120490 | Lo-oc ES | Sibulan | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312918 | Buntod High School | BACONG | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120226 | Maayongtubig ES | DAUIN | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 120507 | Cawitan Elementary School | SANTA CATALINA | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312931 | Nagbinlod High School | SANTA CATALINA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3rd |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303269 | Lorenza P. Palarpalar MHS (Bonbonon PCHS) | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312968 | Palayuhan High School | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312970 | Caticugan HS | SIATON | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Negros Oriental | 312956 | Gregorio Elmaga MHS | ZAMBOANGUITA | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Siquijor | 500232 | Cabulihan Integrated School | LARENA | Lone | 1 |  | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VII | Siquijor | 303299 | Ponong High School | LARENA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Siquijor | 501427 | Larena Integrated School | LARENA | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Siquijor | 501430 | San Juan Integrated School | SAN JUAN | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | 1080 | - | - | 1080 | 24 | - | - | 3475200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st |  | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tagbilaran City | 302874 | Manga National High School | TAGBILARAN CITY (Capital) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Talisay City | 119803 | Tabunoc Central Elem. School | CITY OF TALISAY | 1st | 1 | 720 | - | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303283 | Tanjay City Science HS | CITY OF TANJAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303284 | Lourdes Ledesma Del Prado MNHS | CITY OF TANJAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2nd |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VII | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Baybay City | 121079 | Lintaon Es To Baybay I Cs | City Of Baybay | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Baybay City | 121126 | Pomponan Elementary School | CITY OF BAYBAY | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | REGION VIII | Baybay City | 121145 | Mahayahay Es To Marcos Es | City Of Baybay | 5th | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region VIII | Baybay City | 303360 | Caridad National High School | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Baybay City | 303420 | Pomponan NHS | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5th | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Baybay City | 313316 | Baybay City National Night HS | CITY OF BAYBAY | 5th |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5th | 1 | - | 180 | - | 180 | 4 | - | 28 | 897000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Baybay City | 313323 | Ciabu NHS | CITY OF BAYBAY | 5th |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 120777 | Canila ES | BILIRAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 120797 | Alegria ES | CAIBIRAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 500410 | Union Integrated School | CAIBIRAN | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 120819 | Calipayan ES | CULABA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 500411 | Inasuyan Integrated School | KAWAYAN | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Biliran | 303334 | Viga National High School | MARIPIPI | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | REGION VIII | Borongan City | 122364 | Suhotan Ps To Siha Es | City Of Borongan (Capital) | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region VIII | Borongan City | 122368 | Amantacop ES | CITY OF BORONGAN (Capital) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Borongan City | 303525 | Sta. Fe NHS | CITY OF BORONGAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Borongan City | 313515 | E. Samar NCHS - Supt. Fidel E. Anacta, Sr. MHS Annex | CITY OF BORONGAN (Capital) | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Calbayog City | 123991 | Carayman Elementary School | Calbayog City | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region VIII | Catbalogan City | 123409 | Catbalogan II Central Elementary School | Catbalogan City (Capital) | 2nd | 1 | 900 | - | - | 900 | 20 | - | - | 2597380 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | REGION VIII | Eastern Samar | 122325 | Sulangan Central Elementary School To Arteche Ces | Arteche | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 779214 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 313501 | Can-avid NHS | CAN-AVID | Lone | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122454 | Lupok Central Elementary School To Hinolaso Es | Dolores | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational HS | DOLORES | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 313521 | Dapdap National Technical Vocational HS | DOLORES | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | Lone | 1 | - | - | - | - | - | - | 7 | 79450 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122509 | Huknan Elementary School To Gigoso Es | Giporlos | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 122517 | San Miguel Elementary School | GIPORLOS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 303508 | Homonhon NHS | GUIUAN | Lone | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 122477 | Cacatmonan Primary School | HERNANI | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 122572 | Cagmanaba Elementary School | JIPAPAD | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | REGION VIII | Eastern Samar | 122575 | Oras West Central Elementary School To Jipapad Ces | Jipapad | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 303510 | Jipapad NHS | JIPAPAD | Lone | 1 | - | - | - | - | - | - | 7 | 79450 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122343 | Layog Primary School To Beta-Og Es | Lawaan | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 129869 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | LAWAAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 303513 | Llorente NHS | LLORENTE | Lone |  | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 122462 | Maputi Elementary School | MASLOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 303515 | Maslog NHS | MASLOG | Lone | 1 | - | - | - | - | - | - | 14 | 158900 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 122538 | Busay Primary School | MERCEDES | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 303518 | Mercedes NHS | MERCEDES | Lone | 1 | - | - | - | - | - | - | 14 | 158900 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 122634 | Bantayan Elementary School | ORAS | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | REGION VIII | Eastern Samar | 122649 | Oras East District Sped Center To Saurong Es | Oras | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Eastern Samar | 122658 | Binalayan Elementary School | ORAS | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | REGION VIII | Eastern Samar | 303522 | Quinapondan National High School To Salcedo National High School | Quinapondan | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122720 | Capanoypoyan Primary School To Taclaon Es | Salcedo | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Eastern Samar | 122735 | Bangon Elementary School | SAN POLICARPO | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122761 | Pangabutan Primary School To Binaloan Es | Taft | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122768 | Lupok Central Elementary School To Malinao Es | Taft | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | REGION VIII | Eastern Samar | 122771 | Danao Elementary School To Polangi Es | Taft | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 120972 | Lukay Elementary School | ALANGALANG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 120973 | Montano Elementary School | ALANGALANG | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121005 | Babatngon Central School | BABATNGON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121764 | San Jose Elementary School | PALO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121882 | Victoria Elementary School | SANTA FE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121940 | Maribi Elementary School | TANAUAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121946 | Burak Elementary School | TOLOSA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121242 | Guinadiongan Elementary School | CAPOOCAN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121521 | Caridad Elementary School | Julita | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121560 | Buracan Elementary School | La Paz | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121621 | MacArthur Central School | Mac Arthur | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121711 | Talisay Elementary School | Mayorga | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121809 | Aringit Primary School | Pastrana | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121907 | Amandangay Elementary School | Tabontabon | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121961 | Tunga Central School | Tunga | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121209 | Bunacan Elementary School | CALUBIAN | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121975 | Tabunoc Elementary School | VILLABA | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 120992 | Soob Elementary School | ALBUERA | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121541 | Libongao Elementary School | KANANGA | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121551 | San Ignacio Elementary School | KANANGA | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121658 | Cambadbad Elementary School | MATAG-OB | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121667 | Naulayan Elementary School | MATAG-OB | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 121726 | Macario Elementary School | Merida | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 121770 | Lomonon Elementary School | PALOMPON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 121788 | Cangcosme Elementary School | PALOMPON | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303385 | Kikilo National High School | ABUYOG | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303338 | Anahawan National High School | BATO | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 191544 | Magnangoy Primary School | HILONGOS | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th |  | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 121410 | Ma-asin Elementary School | Hindang | 5th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303370 | Esperanza National High School | MATALOM | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122783 | Jubasan Elementary School | ALLEN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122794 | Langub-Langub Elementary School | BIRI | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122825 | Landusan Elementary School | CAPUL | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122836 | GENEROSO R. FRIGILLANA MS | CATARMAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303543 | Galutan NHS | CATARMAN (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303561 | Basilio B. Chan Mem. Agricultural and Industrial Sch. | LAVEZARES | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 313623 | GUILLERMO C. ADRIATICO, SR. NATIONAL HIGH SCHOOL | LAVEZARES | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303563 | Lope De Vega NHS | LOPE DE VEGA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123117 | Cahicsan Elementary School | MONDRAGON | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303550 | Francisca Dominice NHS | MONDRAGON | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303568 | Nenita National High School | MONDRAGON | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 313605 | Leonardo M. Amigo High School | MONDRAGON | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123192 | Jamo-og Elementary School | ROSARIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303573 | Rosario National High School | ROSARIO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123204 | San Nicolas Elementary School | SAN ANTONIO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123219 | VERIATO ES | SAN ISIDRO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123222 | Bonglas Primary School | SAN JOSE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123247 | San Vicente Central School | SAN VICENTE | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123278 | Lungib Elementary School | VICTORIA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303552 | Gamay National High School | GAMAY | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122943 | Laoang I CS | LAOANG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122973 | Burabud ES | LAOANG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122985 | Rawis CS | LAOANG | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 122987 | SIMORA ES | LAOANG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 304914 | E.J. Dulay National High School | LAOANG | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123001 | Pio Del Pilar Elementary School | LAPINIG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123104 | Burgos Elementary School | MAPANAS | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 123149 | CAPACUJAN ES | PALAPAG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303539 | Capacujan NHS | PALAPAG | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High School | PAMBUJAN | 2nd | 1 | - | 90 | - | 90 | 2 | 14 | - | 455780 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 303581 | San Roque-Pambujan Vocational High School | PAMBUJAN | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Northern Samar | 313618 | Balnasan National High School | SAN ROQUE | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Ormoc City | 124204 | Curva Elementary School | ORMOC CITY | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Ormoc City | 194501 | Ormoc City Central School | ORMOC CITY | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Ormoc City |  | Lilo-an National High School (ANNEX) | ORMOC CITY | 4th | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123297 | San Isidro PS | ALMAGRO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123549 | Matuguinao CES | MATUGUINAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123652 | Calanyugan ES | PAGSANGHAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123750 | Inoraguiao ES | SANTA MARGARITA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123807 | Ilijan ES | SANTO NIÑO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123826 | San Vicente Elementary school | TAGAPUL-AN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123831 | Bahay ES | TARANGNAN | 1st |  | 45 | - | - | 45 | 1 | - | - | 144800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 281506 | Flora Mabaet Mabansag Elementary School | JIABONG | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123620 | Tinabanan ES | MARABUT | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 313736 | Pequit IS | PARANAS (WRIGHT) | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123899 | Navatas Guti Elementary School | TALALORA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Samar (Western Samar) | 123974 | Marapilit ES | ZUMARRAGA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122180 | Asuncion Multigrade ES | MACROHON | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303487 | Sogod NHS | SOGOD | Lone | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122218 | Bunga Elementary Multi-Grade School | PADRE BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122321 | San Isidro Elementary School | TOMAS OPPUS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region VIII | Tacloban City | 124233 | Bayanihan ES | Tacloban City (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126280 | San Vicente ES | BAUNGON | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126603 | LARAPAN ES | MALITBOG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126631 | KITAM-IS ES | MANOLO FORTICH | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126781 | KILABONG ES | SUMILAO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126814 | MASIMAG ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126817 | MIGPAIT ES | TALAKAG | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 500890 | Iba Integrated School | CABANGLASAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 314923 | Impasugong NHS-Kapitan Bayong Annex | IMPASUG-ONG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126405 | Malinao ES | KADINGILAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 649345 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126706 | Busco ES | QUEZON | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126716 | Miluya ES | QUEZON | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126717 | Minsalirac ES | QUEZON | 3rd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 500677 | Dilapa Integrated School | QUEZON | 3rd | 1 | - | - | 120 | 120 | 3 | - | - | 347907 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Bukidnon | 126418 | FORCHACU III ES | KALILANGAN | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 127961 | Bongbongon Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 127972 | Bayanga Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 304117 | Iponan National High School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 127942 | East City Central School | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 127956 | Macabalan ES | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | 675 | - | - | 675 | 15 | - | - | 1948035 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region X | Cagayan de Oro City | 304115 | Gusa NHS-Cugman Annex | CAGAYAN DE ORO CITY (Capital) | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 100% | March 7, 2024 | March 4 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Camiguin | 126884 | Bura ES | CATARMAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 322600 | Completed | 100% | April 11, 2024 | 2025-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Camiguin | 126929 | Cabuan es | GUINSILIBAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 100% | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Camiguin | 126901 | Pontod ES | MAHINOG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Camiguin | 129936 | Sagay CS | SAGAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | El Salvador | 127674 | Kalabaylabay ES | CITY OF EL SALVADOR | 2nd | 1 | 405 | - | - | 405 | 9 | - | - | 1168821 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Gingoog City | 501024 | Sangalan Integrated School | Ginggoog City | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 695814 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Gingoog City | 128045 | Talisay Elementary School | GINGOOG CITY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Gingoog City | 304132 | Kalipay National High School | GINGOOG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Gingoog City | 315501 | EUREKA NATIONAL HIGH SCHOOL | GINGOOG CITY | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 128093 | Echavez ES | ILIGAN CITY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 128156 | SUAREZ CENTRAL SCHOOL | ILIGAN CITY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 304140 | Don Jose F. Yañez MHS (Bunawan NHS) | ILIGAN CITY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 304150 | Iligan City NSOF | ILIGAN CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 304152 | Maria Cristina National High School | ILIGAN CITY | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 304160 | Tubaran NHS - Digkilaan Annex | ILIGAN CITY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Iligan City | 500698 | Del Carmen Integrated School | ILIGAN CITY | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier | 322600 | Completed | 100% | April 11, 2024 | 2025-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 100% | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 303998 | Baloi National High School | BALOI | 1st |  | - | 90 | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative | 568800 | Completed | 100% | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304013 | Diego H. Patigayon NHS (Mukas NHS) | KOLAMBUGAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 100% | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 100% | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 127136 | Sultan Macalpang Permites CS (Matungao CES) | MATUNGAO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 100% | April 11, 2024 | 2026-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 127166 | Pantar CES | PANTAR | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 100% | April 11, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304019 | Pantar NHS | PANTAR | 1st |  | - | 180 | - | 180 | 4 | - | 14 | 738100 | Regional Office Implementation | 55% Allocation for Regular Supplier | 512200 | Completed | 100% | April 11, 2024 | 2001-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 11, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304021 | Tagoloan NHS | TAGOLOAN | 1st |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 11, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 127239 | Pigcarangan Integrated School | TUBOD (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 100% | April 11, 2024 | 2009-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 500249 | Carusa Integrated School | KAPATAGAN | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 508800 | Completed | 100% | April 16, 2024 | 2022-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 758400 | Completed | 100% | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304004 | Lala NHS | LALA | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2029-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304009 | Magsaysay NHS | MAGSAYSAY | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2027-03-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 100% | April 16, 2024 | 2004-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304014 | Munai NHS | MUNAI | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2011-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 304018 | Pantao Ragat Agro-Ind. HS | PANTAO RAGAT | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 16, 2024 | 2010-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 160 | 160 | 4 | - | 14 | 676100 | Regional Office Implementation | 55% Allocation for Regular Supplier | 472200 | Completed | 100% | April 16, 2024 | 2011-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 100% | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 500690 | Sultan Ali Dimaporo Memorial IS | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 100% | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 501240 | Calube Integrated School | SULTAN NAGA DIMAPORO (KAROMATAN) | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 339200 | Completed | 100% | April 16, 2024 | 2012-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 100% | April 16, 2024 | 2015-04-01 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 126591 | San Jose ES | CITY MALAYBALAY (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 100% | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 314916 | Malaybalay City NHS | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote NHS | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/25 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 103610 | Damitan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 103647 | Pigpamulahan Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 103677 | Incalbog Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/27 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 126576 | BCT Elementary School | CITY MALAYBALAY (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote National HIgh School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 284400 | Completed | 100% | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 325505 | Apo Macote National HIgh School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 501190 | Magsaysay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 6, 2024 | 3/29 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 501579 | Kilap-agan Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 100% | April 6, 2024 | 4/1 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 501580 | Casisang Central Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City | 501852 | Mabuhay Integrated School | CITY MALAYBALAY (Capital) | 2nd | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 169600 | Completed | 100% | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Malaybalay City |  | Malaybalay City ALS Center | CITY MALAYBALAY (Capital) | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 758400 | Completed | 100% | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127527 | Masubong Primary School | SAPANG DALAGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 11, 2024 | 3/18 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127290 | Bonifacio CS | BONIFACIO | 2nd | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 948000 | Completed | 100% | April 11, 2024 | 3/8 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127342 | Lupagan Elementary School | CLARIN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 100% | April 11, 2024 | 3/8 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127344 | Pan-ay ES | CLARIN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 568800 | Completed | 100% | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127346 | Segatic Sur Es To Segatic Norte Ps | Clarin | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127355 | Ozamiz ES | CLARIN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 189600 | Completed | 100% | April 11, 2024 | 3/20 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd |  | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Occidental | 127562 | Camating ES | TUDELA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 284400 | Completed | 100% | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 127604 | Binitinan ES | BALINGASAG | 1st | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1137600 | Completed | 100% | March 7, 2024 | March 1 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 500251 | Lantad IS | BALINGASAG | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 339200 | Completed | 100% | March 7, 2024 | March 4 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 127875 | Balingoan CS | BALINGOAN | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 100% | July 30, 2024 | 6/3 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 304062 | Binuangan NHS | BINUANGAN | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 853200 | Completed | 100% | July 30, 2024 | 6/3 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 304077 | Kinoguitan Nat'l Agricultural HS | KINOGUITAN | 1st | 1 | - | 526 | - | 526 | 12 | - | - | 1694200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1109600 | Completed | 100% | July 30, 2024 | 6/7 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 127744 | Kabulawan ES | LAGONGLONG | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 100% | July 30, 2024 | 6/7 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | - | - | - | - | - | - | - | 0 | Regional Office Implementation | 20% Allocation for E-Bamboo |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 | 0 |  | 0%
CY 2023 SF | Region X | Misamis Oriental | 304066 | Consuelo NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 100% | July 30, 2024 | 6/13 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 304076 | Kibungsod NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1896000 | Completed | 100% | July 30, 2024 | 6/13 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 315322 | Damayuhan NHS | MAGSAYSAY (LINUGOS) | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 20% Allocation for E-Bamboo | 189600 | Completed | 100% | July 30, 2024 | 6/17 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 304089 | Medina NCHS | MEDINA | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1896000 | Completed | 100% | July 30, 2024 | 6/17 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 304095 | Portulin NHS | MEDINA | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 20% Allocation for E-Bamboo | 1137600 | Completed | 100% | July 30, 2024 | 6/21 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 100% | July 30, 2024 | 6/27 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 500250 | Alipuaton IS | SALAY | 1st |  | - | - | 240 | 240 | 6 | - | - | 775800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 508800 | Completed | 100% | July 30, 2024 | 6/27 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 127738 | Sugbongcogon CS | SUGBONGCOGON | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 100% | March 17, 2024 | 6/28 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 501161 | Luna Integrated School | CLAVERIA | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 100% | March 17, 2024 | 2/9 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 379200 | Completed | 100% | March 17, 2024 | 2/9 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 501158 | Tuod Integrated School | MANTICAO | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 100% | March 17, 2024 | 2/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Misamis Oriental | 501038 | Maribojoc Integrated School | TAGOLOAN | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 517200 | Regional Office Implementation | 20% Allocation for E-Bamboo | 339200 | Completed | 100% | March 17, 2024 | 2/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Oroquieta City | 127458 | Poblacion 2 ES | OROQUIETA CITY (Capital) | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 100% | March 17, 2024 | 3/8 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Oroquieta City | 304044 | Misamis Occidental Science & Tech. HS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 100% | March 17, 2024 | 3/8 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Oroquieta City | 304057 | Talairon NHS | OROQUIETA CITY (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 20% Allocation for E-Bamboo | 568800 | Completed | 100% | March 17, 2024 | 3/12 | SF2023_EB_19M | 23-12-B23 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region X | Oroquieta City | 500401 | Mobod IS | OROQUIETA CITY (Capital) | 1st | 1 | - | - | 80 | 80 | 2 | 7 | - | 341690 | Regional Office Implementation | 55% Allocation for Regular Supplier | 229100 | Completed | 100% | April 11, 2024 | 3/26 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region X | Ozamis City | 128192 | Cruz Lanzado Saligan Elementary School | OZAMIS CITY | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 379200 | Completed | 100% | April 11, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region X | Ozamis City | 500701 | Misamis Annex Integrated School | OZAMIS CITY | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1163700 | Regional Office Implementation | 55% Allocation for Regular Supplier | 763200 | Completed | 100% | April 11, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region X | Valencia City | 126875 | Mabuhay Elementary School | CITY OF VALENCIA | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 14400 | Completed | 100% | April 6, 2024 | 4/3 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Valencia City | 500703 | Dagat-Kidavao IS | CITY OF VALENCIA | 4th | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region X | Valencia City | 500705 | Mt. Nebo ES | CITY OF VALENCIA | 4th | 1 | - | - | 120 | 120 | 3 | - | - | 387900 | Regional Office Implementation | 55% Allocation for Regular Supplier | 254400 | Completed | 100% | April 6, 2024 | 4/5 | SF2023_32M | 23-12-B22 | Sept. 20, 2023 | Sept. 27, 2023 | Oct. 13, 2023 | Dec. 11, 2023 | Jan. 12, 2024 | Willie Mart |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 315815 | New Albay NHS | MARAGUSAN (SAN MARIANO) | 1st | 1 | - | 90 | - | 90 | 2 | - | 7 | 369050 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128439 | Moncayo CES | MONKAYO | 1st | 1 | 450 | - | - | 450 | 10 | - | - | 1298690 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 304214 | Union NHS | MONKAYO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128471 | Montevista CES | MONTEVISTA | 1st | 1 | 675 | - | - | 675 | 15 | - | - | 1948035 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128477 | Sambayon ES | MONTEVISTA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 501055 | Canidkid Integrated School | MONTEVISTA | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 231938 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 301358 | Mabuhay NHS | LAAK (SAN VICENTE) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro |  | Mansinaon ES | LAAK (SAN VICENTE) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128535 | Bon-Temple ES | PANTUKAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128539 | Bongbong ES | PANTUKAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128542 | Doroteo De Castro ES | PANTUKAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128544 | Kingking CES | PANTUKAN | 2nd | 1 | 720 | - | - | 720 | 16 | - | - | 2077904 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128551 | Nagas ES | PANTUKAN | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 128555 | Pantukan ES | PANTUKAN | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region XI | Davao De Oro | 304211 | Tambongon NHS | PANTUKAN | 2nd | 1 | - | 406 | - | 406 | 9 | - | - | 1171601 | Central Office Implementation | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129561 | Wireless ES | DAVAO CITY | 1st | 1 | 900 | - | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129695 | Elpidio Quirino ES | DAVAO CITY | 1st | 1 | 945 | - | - | 945 | 21 | - | - | 3040800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 21 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129713 | Baliok ES | DAVAO CITY | 1st | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1st | 1 | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1st |  | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129715 | Catalunan Grande ES | DAVAO CITY | 1st |  | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129717 | Davao City Special School | DAVAO CITY | 1st | 1 | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129717 | Davao City Special School | DAVAO CITY | 1st |  | 675 | - | - | 675 | 15 | - | - | 2172000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 300557 | Vicenta C. Nograles National High School | DAVAO CITY | 1st | 1 | - | 720 | - | 720 | 16 | - | - | 2316800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129243 | Congressman Manuel M. Garcia Elementary School | DAVAO CITY | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129506 | Buhangin CES SPED CENTER | DAVAO CITY | 2nd | 1 | 540 | - | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 316211 | Paradise Embac National High School | DAVAO CITY | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 316213 | MAHAYAG NATIONAL HIGH SCHOOL | DAVAO CITY | 2nd | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129469 | Malagos ES SPED Center | DAVAO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129474 | Tawantawan ES | DAVAO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129502 | Tagurano ES | DAVAO CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129503 | Tibuloy ES | DAVAO CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129533 | Dalagdag ES | DAVAO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129535 | Lacson ES | DAVAO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129564 | Darila ES | DAVAO CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129569 | Lamanan ES | DAVAO CITY | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 129629 | SALAYSAY ELEMENTARY SCHOOL | DAVAO CITY | 3rd | 1 | 180 | - | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 301748 | Catigan National High School | Davao City | 3rd | 1 | - | 540 | - | 540 | 12 | - | - | 1558428 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 304355 | Wangan National High School | DAVAO CITY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 304387 | Angalan NHS | DAVAO CITY | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 519476 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao City | 501072 | Baracayo Integrated School | DAVAO CITY | 3rd | 1 | - | - | 160 | 160 | 4 | - | - | 463876 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 304218 | Sagayen NHS | ASUNCION (SAUG) | 1st | 1 | - | 90 | - | 90 | 2 | - | 14 | 448500 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 500789 | Sampao IS | KAPALONG | 1st | 1 | - | - | 120 | 120 | 3 | - | - | 347907 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 204502 | Mangguangan ES | NEW CORELLA | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 128667 | Pinamuno ES - Mamaon Ext. | SAN ISIDRO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 259738 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 128618 | Dujali Central Elementary School | BRAULIO E. DUJALI | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1038952 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Norte | 204537 | Maguintalunan Elementary School | SANTO TOMAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Davao del Sur | 305509 | Lapulabao National High School | HAGONOY | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Occidental |  | Jose Abad Santos NHS (Mangili Extension) | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Occidental | 128991 | Ismael Yahya ES | MALITA | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Occidental | 129108 | Cumasi ES | SANTA MARIA | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 205512 | Nursery ES | BAGANGA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 205512 | Nursery ES | BAGANGA | 1st |  | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 129241 | Mercedes Elementary School | CARAGA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 304333 | San Luis NHS | CARAGA | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 304334 | Sangab National High School | CARAGA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 500457 | Maylaya IS | CATEEL | 1st | 1 | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 500457 | Maylaya IS | CATEEL | 1st |  | - | - | 80 | 80 | 2 | - | - | 258600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 316102 | Del Pilar NHS | MANAY | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Davao Oriental | 129444 | Baisan ES | TARRAGONA | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Digos City | 129773 | Apolandia ES | CITY OF DIGOS (Capital) | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Island Garden City of Samal | 304223 | Cogon National High School | ISLAND GARDEN CITY OF SAMAL | 2nd |  | - | 90 | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Island Garden City of Samal | 304223 | Cogon National High School | ISLAND GARDEN CITY OF SAMAL | 2nd |  | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Island Garden City of Samal | 341526 | SHS in Penaplata | ISLAND GARDEN CITY OF SAMAL | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2nd | 1 | - | - | - | - | - | 7 | 7 | 162540 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 129398 | Gov. Leopoldo Lopez Sr. MS | CITY OF MATI (Capital) | 2nd |  | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2nd | 1 | - | - | - | - | - | 21 | 21 | 487620 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 129403 | Tagabakid ES | CITY OF MATI (Capital) | 2nd |  | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 304318 | Libudon NHS (Sanghay Campus) | CITY OF MATI (Capital) | 2nd | 1 | - | - | - | - | - | 7 | 7 | 162540 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | - | 0 |  | 100%
CY 2023 SF | Region XI | Mati City | 325105 | Macambol NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | 7 | 7 | 1320940 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | REGION XI | Mati City | Newly-Stablished School | Macangao Agri. Vhs To Tagboa Agri-Vocational Hs | Lupon | 2nd | 1 | - | - | 480 | 480 | 12 | - | - | 1551600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region XI | Panabo City | 129802 | Consolacion ES | CITY OF PANABO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XI | Panabo City | 129805 | J.P. Laurel ES | City of Panabo | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XI | Tagum City | 305519 | Magdum National High School | CITY OF TAGUM (Capital) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | COTABATO CITY | 131264 | Don E. Sero Elementary School | COTABATO CITY | 1st | 1 | 180 | 0 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Cotabato City | 316903 | CCNHS - ANNEX ( Bubong Site) | COTABATO CITY | 1st | 1 | 0 | 450 | 0 | 450 | 10 |  |  | 1448000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1317680 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 675 | 0 | 0 | 675 | 15 |  |  | 2172000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1976520 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | General Santos City | 317005 | Dadiangas North High School | GENERAL SANTOS CITY (DADIANGAS) | 1st | 1 | 0 | 270 | 0 | 270 | 6 |  |  | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304658 | Ginatilan National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304659 | Manongol National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 1080 | 0 | 1080 | 24 |  |  | 3475200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 3162432 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304666 | Spottswood NHS | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 304668 | Paco NHS | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 84 | 2691000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2490096 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2nd |  | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 131394 | Marbel 1 CES | CITY OF KORONADAL (Capital) | 2nd | 1 | 360 | 0 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Koronadal City | 317205 | Esperanza National High School – Annex, San Jose Campus | CITY OF KORONADAL (Capital) | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 303624 | Cesar C. Cabaya Sr. HS | Libungan | 1st | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 130174 | Midsayap Pilot ES | Midsayap | 1st | 1 | 450 | 0 | 0 | 450 | 10 |  |  | 1448000 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1317680 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304415 | ANTIPAS NHS | ANTIPAS | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304416 | Antipas NHS - Malire Annex | ANTIPAS | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304470 | Malatab HS | ANTIPAS | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304439 | Marciano Dahan HS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 | 14 | 0 | 745380 | Regional Office Implementation | 75% Allocation for Regular Supplier | 671272 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304442 | F. A. Andolana Mem. NHS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  | 0 | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304460 | Lanao Kuran NVTHS | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  | 0 | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304471 | MALIBATUAN HIGH SCHOOL | ARAKAN | 2nd | 1 | 0 | 180 | 0 | 180 | 4 | 14 | 0 | 745380 | Regional Office Implementation | 75% Allocation for Regular Supplier | 671272 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316534 | Meocan High School | ARAKAN | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304422 | Basak NHS | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304463 | Magpet National High School | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304464 | Mahongkog High School | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304465 | Temporan National High School | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304490 | Pangao-an NHS | MAGPET | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316501 | Manumba National HS | MAGPET | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 500460 | Sallab High School | MAGPET | 2nd | 1 | 0 | 0 | 80 | 80 | 2 |  |  | 258600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 235326 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304423 | Bulakanon High School | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304457 | Ricardo L. Ipong NHS | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304466 | Makilala National High School | MAKILALA | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2nd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2nd | 1 | 0 | 720 | 0 | 720 | 16 |  |  | 2316800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 2108288 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304498 | Ilustre HS | PRESIDENT ROXAS | 2nd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 129948 | Rancho ES | Banisilan | 3rd | 1 | 180 | 0 | 0 | 180 | 4 |  |  | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304431 | Dalapitan HS | MATALAM | 3rd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304477 | New Alimodian HS | MATALAM | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | MATALAM | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304462 | Lika NHS | M'LANG | 3rd | 1 | 0 | 540 | 0 | 540 | 12 |  |  | 1737600 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1581216 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304488 | Nueva Vida National High School | M'LANG | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304510 | New Rizal HS | M'LANG | 3rd | 1 | 0 | 360 | 0 | 360 | 8 |  |  | 1158400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 1054144 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | North Cotabato | 304504 | Sibsib High School | TULUNAN | 3rd | 1 | 0 | 135 | 0 | 360 | 3 | 0 | 21 | 672750 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | North Cotabato | 316514 | Minapan High School | TULUNAN | 3rd | 1 | 0 | 270 | 0 | 540 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | Lone | 1 | 0 | 135 | 0 | 720 | 3 |  |  | 434400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | Sarangani | 500265 | Datu Molod IS | MAASIM | Lone | 1 | 0 | 270 | 0 | 485 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | Sarangani | 500711 | Francisco A. Cagang Sr. Integrated School | MALAPATAN | Lone | 1 | 0 | 0 | 200 | 320 | 5 |  |  | 646500 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 130721 | Dole Cannery CES | POLOMOLOK | 1st | 1 | 0 | 135 | 0 | 180 | 3 |  |  | 434400 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 316704 | Lamba NHS - Banga NHS Annex | BANGA | 2nd | 1 | 0 | 270 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 316714 | Malaya NHS - Banga NHS Annex | BANGA | 2nd | 1 | 0 | 135 | 0 | 135 | 3 |  | 21 | 672750 | Regional Office Implementation | 75% Allocation for Regular Supplier | 622524 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2nd | 1 | 270 | 0 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2nd | 1 | 270 | 0 | 0 | 180 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 100777 | Datal Ligaw Elementary School | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 130658 | Bakdulong Elementary School | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 180 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 281569 | Datu Kahar Macasayon ES | LAKE SEBU | 2nd | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2nd | 1 | 0 | 180 | 0 | 135 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | South Cotabato | 130848 | T'bolok Elementary School | T'BOLI | 2nd | 1 | 0 | 180 | 0 | 135 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304588 | Columbio National High School | COLUMBIO | 1st | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1st | 1 | 0 | 270 | 0 | 270 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304596 | Laguilayan National High School | ISULAN (Capital) | 1st | 1 | 0 | 180 | 0 | 270 | 4 |  |  | 579200 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304614 | New Pangasinan National High School | ISULAN (Capital) | 1st | 1 | 0 | 270 | 0 | 135 | 6 |  |  | 868800 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304598 | Pimbalayan National High School - Lambayong Annex | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304607 | Madanding National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 389607 | Central Office Implementation | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region XII | Sultan Kudarat | 304608 | Maligaya National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304609 | Mamali National High School | LAMBAYONG (MARIANO MARCOS) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | LUTAYAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | Lutayan | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 646500 | Regional Office Implementation | 75% Allocation for Regular Supplier | 588315 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304594 | Kalanawe II National High School | PRESIDENT QUIRINO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304618 | Central Mangilala High School - President Quirino Annex | PRESIDENT QUIRINO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 75% Allocation for Regular Supplier | 395304 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 130910 | Bagumbayan Central Elementary School | BAGUMBAYAN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 131124 | Keytodac Central School | LEBAK | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304619 | Purikay National High School | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304626 | Tran National High School | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304579 | Apolinario S. Bernardo National High School | CITY OF TACURONG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304620 | Rajah Muda NHS | CITY OF TACURONG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 75% Allocation for Regular Supplier | 527072 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region XII | Tacurong City | 304627 | Virginia F. Griño National High School | CITY OF TACURONG | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 75% Allocation for Regular Supplier | 790608 | Completed | 100% | 2025-02-02 | 2025-02-01 | 2023-09-486.1 | 2023-09-486.1 | August 20,2024 | 2024-08-12 | 2024-09-10 | 2024-10-14 | 2024-10-25 | Hauwei Builders and Development Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100% | 2025-02-02 | 2025-02-01
CY 2023 SF | Region VIII | Southern Leyte | 122302 | Saint Bernard Central School | SAINT BERNARD | Lone | 1 | 450 | - | - | 450 | 10 | - | - | 1448000 | Regional Office Implementation | 55% Allocation for Regular Supplier | 790608 | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 192030 | Mahika Elementary School | SAINT BERNARD | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303490 | Tambis NHS | SAINT BERNARD | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 313407 | New Guinsaugon National High School | SAINT BERNARD | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122090 | Bongbong Elementary School | SAN FRANCISCO | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122104 | Marayag Elementary School | SAN FRANCISCO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | Lone | 1 | 405 | - | - | 405 | 9 | - | - | 1303200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122235 | Esperanza Elementary School | SAN RICARDO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 868800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | Region VIII | Maasin City | 303454 | Dongon National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | Region VIII | Maasin City | 303469 | Manhilo National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 630 | - | 630 | 14 | - | - | 2027200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2023 SF | Region VIII | Maasin City | 303474 | Nonok Norte National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1592800 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | Region VIII | Maasin City | 313401 | Maasin City National High School | CITY OF MAASIN (Capital) | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Maasin City | 500399 | Asuncion Integrated School | CITY OF MAASIN (Capital) | Lone | 1 | - | - | 440 | 440 | 11 | - | - | 1422300 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 192005 | Guinsangaan MG Elementary School | BONTOC | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303475 | Paku NHS | BONTOC | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 501531 | Beniton Integrated School | BONTOC | Lone | 1 | - | - | 148 | 148 | 4 | - | - | 480000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122046 | San Pablo Elementary School | HINUNANGAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303447 | Hinunangan National High School | HINUNANGAN | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303368 | Dr. Geronimo B. Zaldivar Memorial School of Fisheries | ALBUERA | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Leyte | 303374 | Hilongos National Vocational School | HILONGOS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303456 | Estela National High School | LILOAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 579200 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 303459 | Himay-angan NHS | LILOAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region VIII | Southern Leyte | 122210 | Malitbog Central School | MALITBOG | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 434400 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2023 SF | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 701200 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1158400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 701200 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2023 SF | Region I | Laoag City |  | Farinas High School formerly Laoag City Science HS | LAOAG CITY (Capital) | 1st | 1 |  | 1980 | - | 1980 | 44 | - | - | 6371200 | Regional Office Implementation | 55% Allocation for Regular Supplier | 3856600 | Completed | 100% | 2024-01-31 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-09 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 44 | 0 |  | 100%
CY 2023 SF | Region V | Albay | 301865 | Polangui General Comprehensive High School | POLANGUI | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2896000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | On-going | [12 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 |  | 0%
CY 2023 SF | Region VIII | Leyte | 121736 | Anahaway Elementary School | PALO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region III | San Jose City |  | Sampugu Integrated School | SAN JOSE CITY | 2nd | 1 | - | 225 |  | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region III | San Jose City |  | San Agustin High School | SAN JOSE CITY | 2nd | 1 | - | 225 |  | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region III | San Jose City |  | Kaliwanagan High School | SAN JOSE CITY | 2nd | 1 | - | 225 |  | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region III | San Jose City |  | San Raymundo Elementary School | SAN JOSE CITY | 2nd | 1 | 225 | - |  | 225 | 5 | - | - | 724000 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2023 SF | Region IV-A | Batangas | 307730 | Rosario Technical High School | ROSARIO | 4th | 1 | - | 540 | - | 540 | 12 | - | - | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region I | Urdaneta City | 300401 | Cayambanan National High School | CITY OF URDANETA | 5th | 1 | - | 315 | - | 315 | 7 | - | - | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 505493.3925 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | Region I | Urdaneta City | 102298 | Labit West Elementary School | CITY OF URDANETA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | Region I | Urdaneta City | 102301 | Manan Elementary School | CITY OF URDANETA | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 144426.6836 | Completed | 100% | 2024-01-31 | 2024-01-26 |  |  | 2023-10-06 | 2023-10-13 | 2023-10-09 | 2023-11-30 | 2023-12-12 | JTC Pallete Packaging System, Inc. | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY | 1st | 1 | 0 | 260 | 0 | 260 | 6 | 0 | 0 | 837800 | Regional Office Implementation | 55% Allocation for Regular Supplier | 593000 | Completed | 100% | 2025-02-16 | 2024-10-02 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY | 2nd | 1 | 0 | 90 | 0 | 90 | 2 | 0 | 0 | 289600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 205000 | Completed | 100% | 2025-02-16 | 2024-09-09 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2nd | 1 | 585 | 0 | 0 | 585 | 13 | 0 | 0 | 1882400 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1332500 | Completed | 100% | 2025-02-16 | 2024-09-25 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 136609 | Kaunlaran ES | KALOOKAN CITY | 2nd | 1 | 315 | 0 | 0 | 315 | 7 | 0 | 0 | 1013600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 717500 | Completed | 100% | 2025-02-16 | 2024-09-26 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2023 SF | NCR | Caloocan City | 305391 | M. B. Asistio, Sr. HS | KALOOKAN CITY | 2nd | 1 | 0 | 540 | 0 | 540 | 12 | 0 | 0 | 1737600 | Regional Office Implementation | 55% Allocation for Regular Supplier | 1230000 | Completed | 100% | 2025-02-16 | 2024-09-09 | N/A | PB ESSD-2024-008 | Aug. 08, 2023 | Sept. 13, 2024 | Sept. 27, 2023 | 2024-03-07 | 2024-04-16 | Empresa Prestine Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2023 SF | Region III | Nueva Ecija | 105381 | Cawayang Bugtong ES | GUIMBA | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 870876 | Regional Office Implementation | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305082 | Cristina B. Gonzales MHS | BUCAY | Lone | 1 | - | 720 | - | 720 | 16 | - | - | 2262240 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305085 | Dugong NHS | Bucay | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305092 | Pangtod NHS | BUCAY | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135192 | Pikek PS | DAGUIOMAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305096 | Rosalio Eduarte NHS | DOLORES | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 318701 | MARC YSRAEL B. BERNOS MEMORIAL NATIONAL HIGH SCHOOL | LA PAZ | Lone | 1 | - | 810 | - | 810 | 18 | - | - | 2545020 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305102 | Tagodtod National High School | LAGANGILANG | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135202 | Baybayatin PS | LAGAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135142 | Quillat ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305087 | Langiden NHS | LANGIDEN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 500590 | Peñarrubia Integrated School | PEÑARRUBIA | Lone | 1 | - | - | 360 | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 305162 | Tublay School of Home Industries-Main | TUBLAY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 305167 | Asipulo National High School | ASIPULO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135842 | Pitawan ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 305213 | Pasil National High School | PASIL | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 305214 | Central Pasil National High School | PASIL | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305237 | Besao National High School | BESAO | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136329 | Sabangan Elementary School | SABANGAN | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305262 | Pingad National High School | SABANGAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305264 | Sadanga National Technical Vocational and Skills Training High School | SADANGA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305266 | Ankileng National High School | SAGADA | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132317 | Plaridel Elementary School | LIBJO (ALBOR) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132554 | Malinao Elementary School | TUBAJON | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132175 | Mahayahay Elementary School | DEL CARMEN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132327 | Ombong ES | ALEGRIA | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132459 | Karihatag ES | MALIMONO | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304833 | Malimono National High School | MALIMONO | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1696680 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Norte | 100100 | Ablan Community School | BURGOS | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 500348 | San Vicente IS | SAN VICENTE | 1st | 1 | - | - | 540 | 540 | 12 | - | - | 1696680 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 300042 | Cabittaogan National High School | SANTA CATALINA | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300150 | Tagudtud National High School | BAGULIN | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2nd | 1 | - | - | 135 | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100998 | Cuenca ES | PUGO | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzales ES | Sto Tomas | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 500063 | Raele Integrated School | ITBAYAT | Lone | 1 | - | - | 90 | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 300464 | Illuru NHS | RIZAL | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region II | Isabela | 300558 | Luna National High School | LUNA | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 300623 | Bintawan NHS | VILLAVERDE | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region II | Quirino | 300665 | Saguday NHS | SAGUDAY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region III | Nueva Ecija | 105567 | Cabawangan ES | NAMPICUAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region III | Tarlac | 106617 | Cat-Nag ES | SAN CLEMENTE | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107253 | Cesar Orona ES | BALETE | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 307713 | San Nicolas Integrated High School | SAN NICOLAS | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 301191 | Gen. Emilio Aguinaldo National High School | GENERAL EMILIO AGUINALDO | 8th | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 301240 | Famy National Integrated High School | FAMY | 4th | 1 | - | 495 | - | 495 | 11 | - | - | 1555290 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108945 | Binagbag ES | Agdangan | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301284 | Alabat Island National High School | ALABAT | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109243 | Tayabas East CS I | CITY OF TAYABAS | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 301416 | West Palale National High School | CITY OF TAYABAS | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301584 | Looc NHS | LOOC | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301588 | Magsaysay National High School | MAGSAYSAY | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110968 | Mampio Elementary School | CAGAYANCILLO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110970 | Sta. Cruz Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301737 | San Miguel National High School (Gaudencio Abordo NHS) | LINAPACAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301738 | San Vicente National High School | SAN VICENTE | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 309108 | New Canipo National High School | SAN VICENTE | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301747 | Alcantara National High School | ALCANTARA | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% | 706375 | Completed | 100% | 2022-06-28 | 2022-06-20 | 2022-002CBZN | 2022-002CBZN | 2022-03-03 | 2022-03-14 | 2022-03-25 | 2022-04-13 | 2022-04-29 | TOP ASIA FURNITURE PRODUCERS COOPERATIVE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% | 450680 | Completed | 100% | 2022-09-07 |  | ZDS-22-SF-01 | ZDS-22-SF-01 | 2022-02-24 | 2022-03-04 | 2022-03-17 | 2022-03-23 | 2022-06-09 | HAPPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | TIGBAO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% | 676020 | Completed | 100% | 2022-09-07 |  | ZDS-22-SF-01 | ZDS-22-SF-01 | 2022-02-24 | 2022-03-04 | 2022-03-17 | 2022-03-23 | 2022-06-09 | HAPPC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 303870 | Talusan NHS | TALUSAN | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% | 728580 | Completed | 100% | 2022-06-03 | 2022-06-03 |  | 2022-0303 | 2022-03-01 | 2022-03-01 | 2022-03-04 |  |  | Top Asia Furniture Producers Cooperative |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Norte | 301903 | San Lorenzo Ruiz National High School | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Sur | 301942 | Barcelonita Fisheries School | CABUSAO | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 500412 | Bote IS | BATO | Lone | 1 | - | - | 540 | 540 | 12 | - | - | 1696680 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302095 | Panganiban National High School | PANGANIBAN (PAYO) | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 302134 | F. Alindogan National High School | BATUAN | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113636 | VILLA ELEMENTARY SCHOOL | ESPERANZA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302223 | Manlabong NHS | PRIETO DIAZ | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 500171 | Lezo IS | LEZO | 2nd | 1 | - | - | 180 | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 500183 | Jawili Integrated School | TANGALAN | 2nd | 1 | - | - | 135 | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 302347 | Belison NS | BELISON | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VI | Guimaras | 302439 | Remedios E. Vilches-San Lorenzo National High School | SAN LORENZO | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VI | Iloilo | 311001 | Valerio P. Palmares NHS | BATAD | 5th | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302900 | San Roque National High School | ALBURQUERQUE | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118192 | Cantoyoc PS | CLARIN | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303073 | Pilar NHS | PILAR | 5th | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119862 | Secante Bag-o PS | TUDELA | 5th | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 500894 | Ginatilan Integrated School | GINATILAN | 7th | 1 | - | - | 360 | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119602 | Sta. Cruz ES | RONDA | 7th | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 500232 | Cabulihan Integrated School | LARENA | Lone | 1 | - | - | 180 | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120784 | Villa Enage Elemenetary School | BILIRAN | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303320 | Biliran National Agricultural High School | BILIRAN | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303323 | Cabucgayan NHS | CABUCGAYAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 305563 | Vigan National High School | GENERAL MACARTHUR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 501925 | San Roque Integrated School | JIPAPAD | Lone | 1 | - | - | 225 | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 313512 | Quinapundan National High School- Anislag Annex | QUINAPONDAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121520 | Calbasag Elementary School | JULITA | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303381 | Julita National High School | JULITA | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303342 | Atty. Roque A. Marcos Memorial School (La Paz NHS) | LA PAZ | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1413900 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303397 | Macarthur National High School | MACARTHUR | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303414 | Palale National High School | MACARTHUR | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121732 | Puerto Bello Elementary School | MERIDA | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 282780 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121412 | Mahilum Elementary School | HINDANG | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5th | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303540 | Capul Agro-Industrial School | CAPUL | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303536 | Buenavista NHS | ROSARIO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303582 | San Vicente School of Fisheries | SAN VICENTE | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 344947 | Victoria SHS (Stand Alone) | VICTORIA | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123113 | SILJAGON ES | MAPANAS | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303564 | Mapanas Agro-Industrial High School | MAPANAS | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1131120 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 313607 | SILJAGON NHS | MAPANAS | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 424170 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123296 | Marasbaras PS | ALMAGRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303600 | Costa Rica National High School | ALMAGRO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 501934 | Kerikite Integrated School | ALMAGRO | 1st | 1 | - | - | 270 | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303609 | Jiabong National High School | JIABONG | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1413900 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303466 | Lungsodaan National High School | HINUNDAYAN | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1413900 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 302079 | Padre Burgos National Technical Vocational High School | PADRE BURGOS | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 989730 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 315003 | Mahinog National High School II | MAHINOG | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 126935 | Sagay Central School | SAGAY | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 304787 | El Salvador City National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304011 | Marcela T. Mabanta NHS | KAUSWAGAN | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1413900 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304008 | Linamon NHS | LINAMON | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501557 | Matampay Integrated School | MATUNGAO | 1st |  | - | - | 180 | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 500431 | Tambacon Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 225 | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304023 | Salvador NHS (Salvador Trade HS) | SALVADOR | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127370 | San Francisco ES | CONCEPCION | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501880 | Sapang Ama Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 405 | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127554 | Sinacaban CS | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501875 | Libertad Bajo Integrated School | SINACABAN | 2nd | 1 | - | - | 225 | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 341233 | Kinoguitan SHS | KINOGUITAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 315304 | Lumbo NHS | LAGONGLONG | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1272510 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128646 | Agman ES | SAN ISIDRO | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 565560 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 315906 | Pinamuno National High School | SAN ISIDRO | 1st | 1 | - | 230 | - | 230 | 5 | - | - | 724640 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129407 | Tamisan Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 848340 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129413 | Dawan Central ES | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304325 | Mati National Comprehensive High School | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 706950 | DIVISION OFFICE IMPLEMENTATION | DLI - 10% |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 101016 | Abra Special Education Center | BANGUED (Capital) | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134981 | Dangdangla Elementary School | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134983 | Sagap Elementary School | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134984 | San Antonio ES | BANGUED (Capital) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 318704 | Abra High School - Calot Extension | BANGUED (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134987 | Bangbangcag PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134988 | Bangcagan PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134990 | Bucay North ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134991 | Bugbog ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134992 | Calao ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134997 | Lublubnac PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134999 | Madalipay ES | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135001 | Pagala East PS | BUCAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501342 | Layugan Integrated School | BUCAY | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305080 | Capitan NHS | DAGUIOMAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135026 | Abaquid ES | DANGLAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135039 | Padangitan ES | DANGLAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135016 | Cardona Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135019 | Don Rosalio Eduarte ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135021 | Mudiit ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135022 | Pacac ES | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135023 | Taping Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218501 | Libtec Elementary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218521 | Lourdes Zapata Primary School | DOLORES | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135028 | Bulbulala ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135031 | Gongonot Elementary School | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135032 | Isit Elementary School | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135035 | Malabbaga ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135040 | Pidipid ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135042 | Sidongan PS | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135043 | Toon ES | LA PAZ | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135047 | Bacag ES | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135055 | Buneg PS | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135064 | Lacub CS | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135067 | Lan-ag ES | LACUB | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 318703 | Alfredo D. Bersamina NHS | LACUB | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135085 | Villa San Isidro ES | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218503 | Willy Castillo PS | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218514 | Taping Primary School | LAGANGILANG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305081 | Cayapa NHS | LAGANGILANG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305094 | Pulot National High School | LAGAYAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501341 | Ba-i Integrated School | LAGAYAN | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135136 | Langiden CS | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135137 | Mabungtot ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135138 | Malapaao ES | LANGIDEN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135053 | Bonglo Elementary School | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135054 | Bulbulala PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135056 | Caoayan PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135060 | Diangay PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135063 | Kileng PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135068 | Lenneng ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135075 | Nalbuan ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135080 | Subagan PS | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135081 | Sucao ES | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218502 | Agat Primary School | LICUAN-BAAY (LICUAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305076 | Baay National High School | LICUAN-BAAY (LICUAN) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501115 | LICUAN INTEGRATED SCHOOL | LICUAN-BAAY (LICUAN) | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135086 | Agumanay ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135088 | Ampalioc PS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135092 | Barit ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135094 | Botot ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135099 | Gayaman ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135102 | Lipting PS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135103 | Luba CS | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135104 | Lul-luno ES | LUBA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501729 | TABANGAO IS | LUBA | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135049 | Bangilo ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135051 | Bayabas Elementary School | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135052 | Binasaran PS | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135061 | Dulao ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135070 | Liwang ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135071 | Malibcong CS | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135072 | Mataragan ES | MALIBCONG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305090 | Mataragan NAS | MALIBCONG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134993 | Catacdegan ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134996 | Liagan PS | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 134998 | Madago Elementary School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135000 | Manabo Pilot ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135005 | San Jose ES | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135007 | Sapdaan Elementary School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135009 | Sto. Tomas Barrio School | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218520 | Casakgudan PS | MANABO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305098 | Manabo NHS (San Jose Catacdegan NHS) | MANABO | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135120 | Dumayco Primary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135122 | Malamsit Elementary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135130 | Sta. Rosa Elementary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218519 | Tattawa Primary School | PEÑARRUBIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135134 | Casilagan PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135139 | Nagdaingan ES | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135145 | Sulbec PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218510 | Pangtud PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218512 | Poblacion West PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 218517 | Banay PS | PIDIGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305101 | Suyo National High School | PIDIGAN | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135149 | Bolbolo ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135152 | Dalit ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135153 | Dintan ES | PILAR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305077 | Bolbolo NHS | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305083 | Dalit National High School | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305093 | Pilar Rural High School | PILAR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135168 | Abas ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135170 | Bantay Primary School | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135172 | Bazar ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135173 | Bilabila ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135177 | Callaban PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135184 | Gangal Elementary School | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135186 | Lam-aoan PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135190 | Naguilian ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135191 | Nangas-Asan PS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135193 | Sallapadan Bo. ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135194 | Sal-lapadan CS | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135195 | Ud-udiao ES | SALLAPADAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305074 | Abas NHS | SALLAPADAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501343 | Maguyepyep Integrated School | SALLAPADAN | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135119 | Dalimag ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135123 | Manayday ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135124 | Maoay PS | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135126 | Olo ES | SAN ISIDRO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305097 | San Isidro NHS | SAN ISIDRO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135197 | Alimosgan ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135201 | Baug PS | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135204 | Cabcaburao ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135209 | Daoidao ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135213 | Lam-Ag ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135218 | Nangobongan PS | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135221 | Quidaoen ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135224 | Silet ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135225 | Supiil ES | SAN JUAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305091 | Northern Abra NHS | SAN JUAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305095 | Quidaoen NHS | SAN JUAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135012 | Bagalay Elementary School | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135013 | Basbasa ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135014 | Bumagcat ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135018 | Don Marcos Rosales ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135025 | Velasco ES | TAYUM | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305086 | Gaddani NHS | TAYUM | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 500518 | Ananaao Integrated School | TAYUM | Lone | 1 | - | - | 120 | 120 | 3 | - | - | 393807.4303 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135087 | Alangtin Elementary School | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135089 | Amtuagan ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135093 | Batayan PS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135095 | Caocaoayan PS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135115 | Tubo CS | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135116 | Tubtuba ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 135118 | Wayangan ES | TUBO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305084 | Dilong National High School | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305100 | Supo NHS | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 305103 | Tiempo NHS | TUBO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Abra | 501105 | LUMABA INTEGRATED SCHOOL | VILLAVICIOSA | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135672 | Omas Ampaguey ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135673 | Bayabas ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135675 | Ebbes ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135676 | Jose Gonzales ES | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135684 | Yabyabuan MG School | SABLAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 219527 | Amsalsal PS | SABLAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 305157 | Sablan NHS | SABLAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 318915 | Sablan NHS Extension-Balluay | SABLAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135720 | Baayan ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135722 | Balangabang ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135724 | Langbis PS | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135725 | Dorencio ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135729 | Mamuyod ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135730 | Moran ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135732 | Pangablan Elementary School | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Benguet | 135735 | Ciriaco Magno ES | TUBLAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135789 | Bukig Elementary School | ASIPULO | Lone | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135792 | Duli Elementary School | ASIPULO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135801 | Nanlahyan PS | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135805 | Pula ES | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135806 | Pulpog PS | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 220001 | Cawayan PS - Annex (Alehwagon) | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 220006 | Asipulo CS - Annex | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 220021 | Duli ES Extension | ASIPULO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 305174 | Natcak NHS | ASIPULO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 305175 | Camandag NHS | ASIPULO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135832 | Anao ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135834 | Bitu ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135835 | Cababuyan ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135837 | Humalophop ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135838 | Kayang PS | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135844 | Ubuag PS | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 135845 | Umalbong ES | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 220002 | Northern Cababuyan Elementary School - Annex | HINGYON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Ifugao | 340118 | SHS within Namulditan ES | HINGYON | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136016 | Batong Buhay Elementary School | PASIL | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136017 | Balinciagao Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136022 | Colayo Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136023 | Dalupa Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136024 | Dangtalan Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136025 | Galdang Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136026 | Magsilay Elementary School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136027 | Pasil Central School | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136028 | Pasil CS (Guinaang Annex ) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136029 | Pasil CS (Malucsad Annex) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 136030 | Pasil CS ( Pugong Annex) | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 220513 | Balinciagao ES - Limood Annex | PASIL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Kalinga | 305215 | Batong Buhay National High School | PASIL | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136188 | Latang Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136189 | Lias Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136190 | Lingoy Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136191 | Lingoy-Chatol Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136192 | Lunas Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136193 | Mog-ao Primary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136194 | Ogo-og Elementary School | BARLIG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305236 | Lias National High School | BARLIG | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305242 | Eastern Bontoc National Agricultural Vocational High School | BARLIG | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136237 | Bunga Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136238 | Catengan Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136240 | Gueday Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136241 | Lacmaan Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136243 | Masameyeo Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136244 | Panabungen Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136245 | Pangweo Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136246 | Payeo Elementary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136247 | Suquib Primary School | BESAO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 319225 | Agawa National High School | BESAO | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136317 | Data Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136319 | Gayang Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136320 | Labbay Primary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136322 | Legleg Primary School | SABANGAN | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136323 | Madepdeppas Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136325 | Napua Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136326 | Camatagan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136327 | Pingad-Bao-angan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136330 | Supang Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136331 | Tambingan Elementary School | SABANGAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305257 | Namatec National High School | SABANGAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 319206 | Data National High School | SABANGAN | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136332 | Anabel Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136333 | Bekigan Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136334 | Belwang Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136335 | Betwagan Elementary School | SADANGA | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136336 | Demang Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136338 | Sacasacan Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136339 | Saclit Elementary School | SADANGA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305238 | Betwagan National High School | SADANGA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 319204 | Belwang National High School | SADANGA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 319219 | Saclit National High School | SADANGA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136341 | Aguid Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136345 | Balugan Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136346 | Bangaan Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136348 | Kilong Primary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136349 | Nacagang Primary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 136350 | Payag-eo Elementary School | SAGADA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305234 | Bangaan National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 305265 | Sagada National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CAR | Mt. Province | 319222 | Balugan National High School | SAGADA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 131530 | Balangbalang ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 131531 | Humilog ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 131532 | Luis B. Azura Sr. Memorial ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 131533 | Panaytayon ES | REMEDIOS T. ROMUALDEZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Agusan del Norte | 304673 | Agay National High School | REMEDIOS T. ROMUALDEZ | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132391 | A. Ecleo Elementary School | DINAGAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132393 | Cabayawan Elementary School | DINAGAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132394 | Cab-ilan Elementary School | DINAGAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132398 | Justiniana Elementary School | DINAGAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132401 | Tagbuyakhao Elementary School | DINAGAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 304823 | Cab-ilan National High School | DINAGAT | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132310 | Garcia Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132311 | Kanihaan Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132313 | Magsaysay Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132314 | Maytubig Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132318 | Quezon Elementary School | LIBJO (ALBOR) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 317801 | Rosita National High School | LIBJO (ALBOR) | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 324401 | Llamera National High School | LIBJO (ALBOR) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132551 | Babangnan Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132552 | Imelda Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132556 | Navarro Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132557 | Roxas Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132558 | Sta Cruz Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 132559 | Tubajon Central Elementary School | TUBAJON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 304854 | Tubajon National High School | TUBAJON | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Dinagat Island | 324407 | Malinao National High School | TUBAJON | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132216 | Bitaug Elementary School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132218 | Matin-ao Elementary School | BURGOS | 1st | 1 | 196 | - | - | 196 | 4 | - | - | 572544.633 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132162 | Antipolo Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132163 | Bagacay Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132164 | Bitoon Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132165 | Cabugao Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132167 | Dumoyog Primary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132169 | Halian Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132171 | Katipunan Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132172 | Lasala Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132174 | Mabuhay Primary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132177 | Quezon Primary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132178 | San Fernando Elementary School | DEL CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 317605 | Oguing Navarro Memorial National High School | DEL CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132149 | Corazon Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132150 | Daku Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132151 | Dao Primary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132153 | La Januza Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132155 | Magsaysay Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132157 | Mam-on Primary school | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132160 | Suyangan Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132161 | Tawin-Tawin Elementary School | GENERAL LUNA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2940103.9395 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 317603 | Gen. Luna NHS - Consuelo NHS Annex | GENERAL LUNA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132182 | Consolacion Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132184 | Dayaohay Primary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132185 | Jaboy Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132186 | Katipunan Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132188 | Mabini Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132189 | Mabuhay Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132225 | Bongdo Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132226 | Maribojoc Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132196 | Pacifico Primary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132197 | Pelaez Elementary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132200 | San Miguel Primary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132201 | Sta. Paz Elementary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132202 | Sto. Nino Elementary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132203 | Tambacan Elementary School | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132207 | Bailan Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132211 | Magsaysay Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 132214 | Tangbo Elementary School | SANTA MONICA (SAPAO) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Siargao | 317607 | Alegria National High School | SANTA MONICA (SAPAO) | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 136967 | Simfrosa P. Dantes Elementary School | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA | 2nd | 1 | 360 | - | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132325 | Ferlda ES | ALEGRIA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304811 | Alegria National High School | ALEGRIA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132348 | Hinatigan ES | BACUAG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132349 | Little Baguio ES | BACUAG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132350 | Lo-oc PS | BACUAG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132353 | Pongtud Elementary school | BACUAG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132354 | Sto. Rosario ES | BACUAG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304817 | Campo National High School | BACUAG | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132451 | Binocaran ES | MALIMONO | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132463 | Sohoton ES | MALIMONO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132465 | Villa Riza ES | MALIMONO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304818 | Cantapoy National High School | MALIMONO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304819 | Pili National High School | MALIMONO | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304832 | Bunyasan National High School | MALIMONO | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304856 | Villa Riza National High School | MALIMONO | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304843 | San Francisco National High School | SAN FRANCISCO (ANAO-AON) | 2nd | 1 | - | 675 | - | 675 | 15 | - | - | 2205077.9546 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132528 | Gacepan ES | SISON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132536 | Tinogpahan ES | SISON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 214002 | E. Siscon PS | SISON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 214003 | Upper Patag Elementary School | SISON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. Memorial National High School | SISON | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 317808 | Dakung Patag National High School | SISON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132540 | Fabio ES | TAGANA-AN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132543 | Laurel ES | TAGANA-AN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132547 | SALVACION ES | TAGANA-AN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132549 | Talavera ES | TAGANA-AN | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 132550 | Upper Libas ES | TAGANA-AN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304812 | Tagana-an National High School (ASA NHS) | TAGANA-AN | 2nd | 1 | - | 585 | - | 585 | 13 | - | - | 1911067.5607 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 317810 | Cawilan National High School | TAGANA-AN | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 501680 | Hinatuan Integrated School | TAGANA-AN | 2nd | 1 | - | - | 360 | 360 | 9 | - | - | 1181422.2909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1617057.1667 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD | 2nd | 1 | - | 585 | - | 585 | 13 | - | - | 1911067.5607 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 132679 | Antonio Borda Memorial Elementary School | CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 132685 | Gacub Elementary School | CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 214548 | Tabinas Indigenous Community Elementary School | CARMEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 304875 | Carmen National Agricultural High School | CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 305747 | Gacub Atad S. Iligan Tribal National High School | CARMEN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN | 1st | 1 | - | - | 400 | 400 | 10 | - | - | 1312691.4343 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | CARAGA | Surigao del Sur | 304903 | Purisima National High School | TAGO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Norte | 100163 | Bucarot PS | ADAMS | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Norte | 150007 | MALAGGAO PS | ADAMS | 1st | 1 | 315 | - | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100540 | Mapisi Primary School | NAGBUKEL | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 300040 | Belen NHS | SAN ILDEFONSO | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 262950 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 330511 | PHI SCIENCE HIGH SCHOOL - ILOCOS REGION CAMPUS | SAN ILDEFONSO | 1st | 1 | - | 1080 | - | 1080 | 24 | - | - | 3164323.4131 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 150522 | Mindoro Primary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 320909 | San Sebastian NHS | SAN VICENTE | 1st | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 262950 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100331 | Banga Elementary School | SUGPON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100334 | Caoayan Elementary School | SUGPON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100341 | Nagawa Elem. School | SUGPON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100345 | Tangilig ES | SUGPON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100555 | Alfonso Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100564 | Bussot Priimary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100565 | Butarag PS | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100567 | Concepcion Elementary School | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100570 | G. del Pilar Central | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 395540.4266 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 300048 | G. DEL PILAR NHS | GREGORIO DEL PILAR (CONCEPCION) | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 395540.4266 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100350 | Bequi-Walin Elementary School | LIDLIDDA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100367 | Tay-ac Elementary School | LIDLIDDA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 300054 | Lidlidda National High School | LIDLIDDA | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100533 | Bandril PS | NAGBUKEL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100535 | Cadacad Elementary School | NAGBUKEL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100539 | Lapting ES | NAGBUKEL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100553 | Taleb ES | NAGBUKEL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 501026 | Bantugo-Mission Integrated School | NAGBUKEL | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 392000 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100333 | Calipayan Elementary School | SUGPON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100337 | DANAC ELEMENTARY SCHOOL | SUGPON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Ilocos Sur | 100340 | Licungan Elementary School | SUGPON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100858 | Alibangsay ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100861 | Cambaly Elementary School | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100862 | Cardiz ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100864 | Libbo ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100865 | Papayo ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100867 | Sinabugan Elementary School | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100869 | Tio-angan ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100871 | Upper Wallayan ES | BAGULIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100935 | Delles ES | BURGOS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100937 | Linuan ES | BURGOS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 100938 | Tumapoc ES | BURGOS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300102 | Burgos National High School | BURGOS | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 101002 | San Luis ES | PUGO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300108 | Cuenca National High School | PUGO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300121 | Maoasoas National High School | PUGO | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 262950 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300131 | Pugo Central National High School | PUGO | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 300138 | San Luis National High School | PUGO | 2nd | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | La Union | 500601 | Saytan Integrated School | PUGO | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 313600 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region I | Pangasinan II, Binalonan | 102059 | Salvacion ES | SANTO TOMAS | 5th | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 175300 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region I | Pangasinan II, Binalonan | 321203 | San Antonio NHS | SANTO TOMAS | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 438250 | Completed | 100% | 2024-02-12 | 2024-01-25 |  |  | 2023-10-06 | 2023-10-09 | 2023-10-25 | 2023-11-14 | 2023-11-29 | Willie Mart | Delivery completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 300411 | Batanes Nat"l Science High School | BASCO (Capital) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 501736 | Valugan Integrated School | BASCO (Capital) | Lone | 1 | - | - | 270 | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 102317 | Mayan Elementary School | ITBAYAT | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 102319 | Yawran Barrio School | ITBAYAT | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Batanes | 300414 | Itbayat National Agricultural HS | ITBAYAT | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 102834 | Dungan Elementary School | RIZAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 102840 | Liuan ES | RIZAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 102841 | Masi Elementary School | RIZAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 102846 | Sinicking ES | RIZAL | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 501586 | San Juan ES | RIZAL | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 501587 | Bural Integrated School | RIZAL | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 102916 | Cadongdongan ES | SANTA PRAXEDES | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Cagayan | 300489 | Sta. Praxedes High School | SANTA PRAXEDES | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Isabela | 103487 | Luna Central School | LUNA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Isabela | 155507 | Macugay Elementary School | LUNA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Isabela | 300591 | San Isidro National High School | SAN ISIDRO | 6th | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Isabela | 306123 | Manuel L. Quezon National High School | SAN ISIDRO | 6th | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 103988 | Daclig ES | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 103992 | Laylaya PS | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 13592550 | Completed | 100% | 2024-04-02 | 2024-04-02 | 2023-08-453 | 2023-12-006 | Nov. 11, 2023 | Nov. 30, 2023 | Dec. 12, 2023 | DEc. 19, 2023 | DEc. 27, 2023 | BASE WOOD PRODUCTS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 103995 | Napo Elementary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 103996 | Pacdal ES | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 103998 | Salingsingan ES | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 137027 | Pihipi Elementary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 137028 | Bagingey Elementary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 137029 | Hiket Elementary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 156003 | Hamhamaan Elementary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 156012 | Lihlit PS | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 281559 | Hukhukyung Primary School | AMBAGUIO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 300525 | Tiblac National High School | AMBAGUIO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 300617 | Ambaguio High School | AMBAGUIO | Lone | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region II | Nueva Vizcaya | 501901 | Dulli Integrated School | AMBAGUIO | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Quirino | 104375 | La Paz ES | SAGUDAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Quirino | 104377 | SAGUDAY CENTRAL SCHOOL | SAGUDAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region II | Quirino | 156518 | La Paz ES Extension Annex | SAGUDAY | Lone | 1 | 360 | - | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region II | Quirino | 501562 | Salvacion Integrated School | SAGUDAY | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region III | Nueva Ecija | 300838 | Nampicuan NHS | NAMPICUAN | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region III | Bulacan | 501659 | Dulong Malabon Integrated School | PULILAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region III | Tarlac | 160004 | Dagundon ES | ANAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region III | Tarlac | 106309 | San Jose ES | ANAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region III | Tarlac | 106611 | San Juan ES | RAMOS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region III | Tarlac | 106612 | San Raymundo ES | RAMOS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106613 | Serrano PS | RAMOS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106618 | Daldalayap ES | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106619 | Doclong 1st ES | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106621 | Dueg Resettlement ES | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 106623 | Casipo PS | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region III | Tarlac | 300950 | Bamban NHS | SAN CLEMENTE | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Reverted | [11 empty] | Fund Lapsed due to Failed Bidding | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 |  | 0%
CY 2022 SF | Region IV-A | Batangas | 107808 | Corona Elementary School | TINGLOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107812 | Papaya Elementary School | TINGLOY | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107813 | Pisa Elementary School | TINGLOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107814 | San Jose Elementary School | TINGLOY | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107816 | San Pedro Elementary School | TINGLOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107818 | Talahib Elementary School | TINGLOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107819 | Bago Primary School | TINGLOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107820 | Tingloy Central School | TINGLOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 301134 | Papaya National High School | TINGLOY | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 301158 | Tingloy National High School | TINGLOY | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 395540.4266 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 342199 | Tingloy Senior High School | TINGLOY | 2nd | 1 | - | 720 | - | 720 | 16 | - | - | 2109548.9421 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 163512 | Calawit Elementary School | BALETE | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 301073 | Balete National High School | BALETE | 3rd | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 342201 | Primitivo Kalaw Senior High School | BALETE | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107658 | Abelo Elementary School | SAN NICOLAS | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107660 | Bancoro Elementary School | SAN NICOLAS | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107662 | Calangay Elementary School | SAN NICOLAS | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107663 | Hipit Elementary School | SAN NICOLAS | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107666 | San Nicolas Central School | SAN NICOLAS | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107667 | Sinturisan Elementary School | SAN NICOLAS | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107687 | Burol Elementary School | SANTA TERESITA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107689 | Jorge M. Atienza Elementary School | SANTA TERESITA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 107695 | Tambo Elementary School | SANTA TERESITA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Batangas | 301149 | Sta. Teresita National High School | SANTA TERESITA | 3rd | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 107928 | Dao Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 107930 | Kabulusan Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 360 | - | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 107932 | Kaypaaba Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 107934 | Narvaez Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 315 | - | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region IV-A | Cavite | 107935 | Tabora Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 315 | - | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108353 | Antipolo Sulsuguin ES | RIZAL | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3rd | 1 | 900 | - | - | 900 | 20 | - | - | 2636936.1776 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Memorial National High School | RIZAL | 3rd | 1 | - | 900 | - | 900 | 20 | - | - | 2636936.1776 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108284 | Famy Elementary School | FAMY | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108287 | Mayatba ES | FAMY | 4th | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108291 | Paagahan ES | MABITAC | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108293 | Eugenia Games Olarte Reyes Elem. Sch. | MABITAC | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4th | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 301255 | Paagahan Integrated National High School | MABITAC | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 307928 | Matalatala Integrated National High School | MABITAC | 4th | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108394 | Cornelio C. Dalena ES | PAKIL | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108398 | Kabulusan ES | PAKIL | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108401 | Pakil ES | PAKIL | 4th | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 108403 | Saray ES | PAKIL | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 301243 | Kabulusan Integrated National High School | PAKIL | 4th | 1 | - | 765 | - | 765 | 17 | - | - | 2241395.751 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 |  | 100%
CY 2022 SF | Region IV-A | Laguna | 342344 | PAKIL SENIOR HIGH SCHOOL (Stand Alone SHS No. 2 Pakil) | PAKIL | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108979 | Apad ES | JOMALIG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108980 | Bukal ES | JOMALIG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108982 | Casuguran ES | JOMALIG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108983 | Gango ES | JOMALIG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301333 | Jomalig NHS | JOMALIG | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 302394 | Apad Jomalig National High School (Apad NHS) | JOMALIG | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108978 | Amaga ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108981 | Busdak ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108984 | Guinaygayan ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108986 | Katakian ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108987 | Kilogan ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108990 | Patnanungan Norte ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108991 | Sinintan ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108992 | Tapol ES | PATNANUNGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 305524 | PAARALANG SEKUNDARYA NG PATNANUNGAN NORTE | PATNANUNGAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 308028 | Busdak NHS (Formerly Busdak NHS - Patnanungan NHS Annex) | PATNANUNGAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 109079 | Alupay ES | SAMPALOC | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 109080 | Apasan Elementary School | SAMPALOC | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 109084 | Caldong Resettlement ES | SAMPALOC | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108948 | Dayap ES | AGDANGAN | 3rd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301321 | Elias A. Salvador NHS | AGDANGAN | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301316 | Concepcion National High School | PLARIDEL | 4th | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 109052 | Del Pilar Elementary School | QUEZON | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Quezon | 301365 | JOEL B. ARQUIZA NHS | QUEZON | 4th | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109231 | Alsam ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109232 | Busal ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109241 | Pandakake ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109246 | Valencia ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109247 | Wakas ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109249 | Eugenio Francia Elementary School | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109257 | Malao-A / Calantas ES | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109259 | Tayabas West CS I | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109260 | Tayabas West CS II | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109261 | Tayabas West CS III | CITY OF TAYABAS | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 109262 | Tayabas West CS IV | CITY OF TAYABAS | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS | 1st | 1 | - | 900 | - | 900 | 20 | - | - | 2940103.9395 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 342576 | Buenaventura Alandy National High School | CITY OF TAYABAS | 1st | 1 | - | 1080 | - | 1080 | 24 | - | - | 3528124.7274 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2022 SF | Region IV-A | Tayabas City | 500496 | Dapdap Integrated School | CITY OF TAYABAS | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110094 | Agkawayan ES | LOOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110095 | Tabao ES (Ambil ES-Tabao Site) | LOOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110096 | Tambo ES (Ambl ES-Tambo Site) | LOOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110100 | Looc CS | LOOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301583 | Looc National School Of Fisheries | LOOC | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301584 | Looc NHS | LOOC | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110116 | Alibog ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110117 | Bagong Silang ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110118 | Bamban ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110119 | Bambanay ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110121 | Buriraoan ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110124 | Calachuchi ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110126 | Canabang ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110128 | Emok ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110130 | Garza ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110132 | Hinango ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110135 | Magarang Elementary School | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110137 | Nalwak ES | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 110147 | Tilaga ES | MAGSAYSAY | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 169506 | Banga PS | MAGSAYSAY | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301590 | Magsaysay NHS - Purnaga Annex | MAGSAYSAY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 301605 | Sta. Teresa NHS | MAGSAYSAY | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1617057.1667 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 305529 | Paclolo National High School | MAGSAYSAY | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Occidental Mindoro | 308906 | Magsaysay NHS - Alibog Annex | MAGSAYSAY | Lone | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110741 | Algeciras Elementry School | AGUTAYA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110743 | Diit Elementary School | AGUTAYA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110744 | Maracañao Elementary School | AGUTAYA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110745 | Matarawis Elementary School | AGUTAYA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 309120 | Concepcion National High School | AGUTAYA | 1st | 1 | - | 675 | - | 675 | 15 | - | - | 2205077.9546 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110964 | Cagayancillo Central School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110965 | Calusa Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110966 | Cawili Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110967 | Magsaysay Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110969 | Nusa Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110971 | Talaga Elementary School | CAGAYANCILLO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301677 | Cagayancillo National High School | CAGAYANCILLO | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110925 | Barangonan Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110931 | Cabunlawan Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110938 | Decabaitot Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110949 | Nangalao Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110953 | Old Barangonan Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 110960 | San Miguel Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 170538 | Binalabag Elementary School | LINAPACAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 305744 | Pical National High School | LINAPACAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 309128 | Bulawit National High School (Gaudencio Abordo NHS R.A.6992) | LINAPACAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 309165 | Nangalao National High School | LINAPACAN | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111040 | Alcoba Elementary School | MAGSAYSAY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111042 | Canipo Elementary School | MAGSAYSAY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111043 | Cocoro Elementary School | MAGSAYSAY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111047 | Los Angeles Elementary School | MAGSAYSAY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111049 | Magsaysay Central School | MAGSAYSAY | 1st | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111050 | Rizal Elementary School | MAGSAYSAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111051 | Rizal North Elementary School | MAGSAYSAY | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301689 | Danawan National High School | MAGSAYSAY | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan |  | Danawan NHS - Cocoro Extension | MAGSAYSAY | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111179 | Albaguen Elementary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111202 | Santa Cruz Elementary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111203 | Santo Niño Elementary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 111204 | T.D.C. Elementary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 170530 | Casoyan Elementary School | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301660 | Alimanguan National High School | SAN VICENTE | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301681 | Caruray National High School | SAN VICENTE | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Palawan | 301723 | Port Barton National High School | SAN VICENTE | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 111254 | Agbay-Ang ES | ALCANTARA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301777 | Tugdan NHS | ALCANTARA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 302080 | Melodias Imperial, Sr. National High School | ALCANTARA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301750 | Banton NHS | BANTON | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 111397 | Calatrava Elementary School | CALATRAVA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 111412 | Josefina Fetalino Malayo ES | CALATRAVA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 171003 | Cabibihan ES | CALATRAVA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 309201 | Calatrava National High School | CALATRAVA | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 309213 | Pascual Catajay Linao National High School | CALATRAVA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301757 | Corcuera National High School | CORCUERA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301766 | Mabini NHS | CORCUERA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 309210 | Mauricio F. Fabito National High School | CORCUERA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301761 | Ferrol National High School | FERROL | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 111295 | Silum ES | MAGDIWANG | Lone | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301768 | Magdiwang NHS | MAGDIWANG | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 111415 | Talamban Elementary School | SANTA MARIA (IMELDA) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 301774 | Santa Maria NHS | SANTA MARIA (IMELDA) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IV-B | Romblon | 309211 | Sto Nino National High School | SANTA MARIA (IMELDA) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 124538 | Head Tipan ES | MUTIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 833600 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 314119 | Mutia National High School Extension - Alvenda | MUTIA | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 124739 | Bolicon PS | SIBUTAD | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 124742 | Delapa ES | SIBUTAD | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 1250400 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125083 | Lower Bag-ong Tudela IPS | JOSEFINA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125086 | INIGO G. MERCADO PS | JOSEFINA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125089 | Tagaytay Hill IPS | JOSEFINA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125382 | Datagan ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125387 | New Oroquieta ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125390 | San Miguel ES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125393 | Sominot CES | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303817 | Sominot National High School | SOMINOT (DON MARIANO MARCOS) | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 729400 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 125465 | Timolan ES | TIGBAO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 625200 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303800 | Nilo NHS | TIGBAO | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 625200 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303765 | Cogon National High School | VINCENZO A. SAGUN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 625200 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 303782 | Kabatan National High School | VINCENZO A. SAGUN | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1617057.1667 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 1146200 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga del Sur | 314208 | Sagucan NHS | VINCENZO A. SAGUN | 2nd | 1 | - | 630 | - | 630 | 14 | - | - | 2058072.7576 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 1458800 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125843 | Baganipay ES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125850 | Mahayahay ES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125851 | Moalboal ES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125853 | Samonte ES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 125855 | Tuburan ES | TALUSAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 303871 | Kasigpitan NHS | TALUSAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 521000 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN | 1st | 1 | - | 495 | - | 495 | 11 | - | - | 1617057.1667 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier | 1146200 | Completed | 100% |  |  | 10110837 | 2023-08-227 | 2023-09-08 | 2023-09-19 | 2023-10-03 | 2023-11-13 | 2023-12-05 | Canlubang Techno-Industrial Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Norte | 112269 | Resettlement ES | SAN LORENZO RUIZ (IMELDA) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Norte | 112277 | V. Ricafrente ES | SAN VICENTE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Norte | 301919 | Froilan D. Lopez High School | SAN VICENTE | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Norte | 309605 | Fabrica High School | SAN VICENTE | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Sur | 302051 | Sta. Lutgarda National High School | CABUSAO | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2058072.7576 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Sur | 301973 | Gainza National High School | GAINZA | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Sur | 112499 | Dugcal ES | CAMALIGAN | 3rd | 1 | 540 | - | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region V | Camarines Sur | 112770 | Sta. Lucia ES | MAGARAO | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113155 | Cahan Bo. Sch. | BAGAMANOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113160 | Bacak Elementary School | BAGAMANOC | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302072 | Bagamanoc Rural DHS | BAGAMANOC | Lone | 1 | - | 495 | - | 495 | 11 | - | - | 1450314.8977 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302100 | San Vicente National High School | BAGAMANOC | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113169 | Guinsaanan Elementary School | BARAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113170 | Puraran Elementary School | BARAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113171 | San Miguel Elementary School | BARAS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302073 | Baras Rural DHS | BARAS | Lone | 1 | - | 990 | - | 990 | 22 | - | - | 2900629.7954 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 174003 | Bagumbayan ES | BATO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 174016 | Pananaogan Elementary School | BATO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302074 | Bato Rural Development High School | BATO | Lone | 1 | - | 675 | - | 675 | 15 | - | - | 2205077.9546 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 500032 | Cabugao IS | BATO | Lone | 1 | - | - | 480 | 480 | 12 | - | - | 1575229.7212 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113223 | Sioron ES | GIGMOTO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 174010 | Dominador C. Guerrero ES | GIGMOTO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 302087 | Dororian NHS | GIGMOTO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113246 | Bayhan PS | PANGANIBAN (PAYO) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113250 | Mabini ES | PANGANIBAN (PAYO) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113252 | Panay Comm. Sch. | PANGANIBAN (PAYO) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 309801 | Panganiban National High School, CAIC Compound (Panganiban) | PANGANIBAN (PAYO) | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113287 | Caglatawan Elementary School | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113294 | Paraiso B ES | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113295 | San Marcos ES | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113296 | Siay Elementery School | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113297 | Tobrehon ES | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 113306 | Solong PS | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 174007 | Pangilao ES | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Catanduanes | 174015 | Boton PS | SAN MIGUEL | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113478 | Burgos Elementary School | BATUAN | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113483 | Mabuhay Elementary School | BATUAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113484 | Matabao ES | BATUAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 302124 | Burgos National High School | BATUAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 500164 | Costa Rica Integrated School | BATUAN | 1st | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 500165 | Antonio Lee Llacer Sr. Integrated School | BATUAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113862 | Buenos Aires ES | SAN FERNANDO | 1st | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113865 | Canelas ES | SAN FERNANDO | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113869 | Lumbia PS | SAN FERNANDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 174512 | Corbada Elementary School | SAN FERNANDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 174513 | Magkaipit Elementary School | SAN FERNANDO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 302109 | Andres Clemente Jr.National High School | SAN FERNANDO | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 501273 | Buenavista Integrated School | SAN FERNANDO | 1st | 1 | - | - | 320 | 320 | 8 | - | - | 1050153.1474 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113619 | Trangia-Mahusay Elemenatary School | ESPERANZA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113622 | Guadalupe Elementary School | ESPERANZA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113625 | Libertad Primary School | ESPERANZA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 113630 | Rizal PS | ESPERANZA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 302171 | Santos E. Conag National High School | ESPERANZA | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 309902 | Allanaraiz-Marfil High School | ESPERANZA | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region V | Masbate | 501841 | Villa Integrated School | ESPERANZA | 3rd | 1 | - | - | 400 | 400 | 10 | - | - | 1312691.4343 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 113981 | Bangate Elementary School | BARCELONA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 113984 | Cagang Elementary School | BARCELONA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302184 | Barcelona National Comprehensive High School | BARCELONA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302218 | Celso F. Falcotelo National High School | BARCELONA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 310009 | San Antonio National High School | BARCELONA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 114405 | Sto. Domingo ES | PRIETO DIAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302196 | Calao National High School | PRIETO DIAZ | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302232 | Prieto Diaz National High School | PRIETO DIAZ | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 114408 | Alig-igan ES | SANTA MAGDALENA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 114410 | MANANGKAS ELEMENTARY SCHOOL | SANTA MAGDALENA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302245 | Sta. Magdalena National High School | SANTA MAGDALENA | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region V | Sorsogon | 302247 | Talaonga National High School | SANTA MAGDALENA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 114701 | Bagongbayan Elementary School | BURUANGA | 2nd | 1 | 45 | - | - | 45 | 1 | - | - | 147005.197 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0%
CY 2022 SF | Region VI | Aklan | 114710 | Tabungyan Elementary School | BURUANGA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Aklan | 302318 | BURUANGA NATIONAL HIGH SCHOOL | BURUANGA | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 |  | 0%
CY 2022 SF | Region VI | Aklan | 500182 | Habana Integrated School | BURUANGA | 2nd | 1 | - | - | 280 | 280 | 7 | - | - | 918884.004 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 |  | 0%
CY 2022 SF | Region VI | Aklan | 302304 | Catalino M. Prado NHS | LEZO | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 114931 | Lanipga-Napatag PS | TANGALAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 302331 | Panayakan National High School | TANGALAN | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 302336 | Tangalan National High School | TANGALAN | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 500173 | Tamalagon Integrated School | TANGALAN | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 941880.9772 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VI | Aklan | 501181 | Vivo Integrated School | TANGALAN | 2nd | 1 | - | - | 208 | 208 | 5 | - | - | 611254.3095 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 114975 | Buenavista ES | BELISON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 114978 | Mojon ES | BELISON | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Antique | 115126 | Alejo S. Dionela PS | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Antique | 115128 | Codiong PS | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 115129 | Igcagay PS | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 115132 | Pedro C. Rufon Sr. MPS | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 115134 | Pucio ES | LIBERTAD | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VI | Antique | 115135 | San Juan PS | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Antique | 115138 | Tinigbas ES | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Antique | 115139 | Tinindugan Primary School | LIBERTAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Antique | 302383 | Union NHS | LIBERTAD | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VI | Guimaras | 115847 | Aguilar Elementary School | SAN LORENZO | Lone | 1 | 45 | - | - | 45 | 1 | - | - | 147005.197 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0%
CY 2022 SF | Region VI | Guimaras | 115853 | Miagos Primary School | SAN LORENZO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 |  | 0%
CY 2022 SF | Region VI | Guimaras | 115859 | Tangaw Primary School | SAN LORENZO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 |  | 0%
CY 2022 SF | Region VI | Guimaras | 302437 | Dr. Catalino Gallego Nava Memorial High School | SAN LORENZO | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116107 | Cairohan PS | BINGAWAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116111 | Maganhop PS | BINGAWAN | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 147005.197 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116112 | Malitbog Ilawod PS | BINGAWAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116117 | Tubod PS | BINGAWAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 302465 | Bingawan NHS | BINGAWAN | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 |  | 0%
CY 2022 SF | Region VI | Iloilo | 311025 | Jovita Alfaras Rivera National High School | BINGAWAN | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116594 | Abat Elementary School | MINA | 3rd | 1 | 45 | - | - | 45 | 1 | - | - | 147005.197 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0%
CY 2022 SF | Region VI | Iloilo | 137024 | Yugot Elementary School | MINA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116096 | Calangag PS | BATAD | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116097 | Caw-i Primary School | BATAD | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116099 | Malico PS | BATAD | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 116100 | Pasayan PS | BATAD | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 |  | 0%
CY 2022 SF | Region VI | Iloilo | 180021 | Sta. Ana PS | BATAD | 5th | 1 | 45 | - | - | 45 | 1 | - | - | 147005.197 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 0%
CY 2022 SF | Region VI | Iloilo | 302460 | Batad National High School | BATAD | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 |  | 0%
CY 2022 SF | Region VI | Iloilo | 302510 | Ilongbukid NHS | SAN RAFAEL | 5th | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Terminated | [11 empty] | Contract Terminated | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 |  | 0%
CY 2022 SF | Region VI | Iloilo | 302569 | San Rafael NHS (San Rafael) | SAN RAFAEL | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 395540.4266 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VI | Iloilo | 501483 | Bulak Integrated School | BATAD | 5th | 1 | - | - | 160 | 160 | 4 | - | - | 470940.4886 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117931 | Canlimpong PS | ALBURQUERQUE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117932 | Cantiguib PS | ALBURQUERQUE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 186510 | Pandol Primary School | CORELLA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118212 | Monserrat Elementary School | CORTES | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 312355 | Lourdes High School | CORTES | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118199 | Tubod PS | CLARIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 186503 | Villaflor ES | CLARIN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 500217 | Danahaw IS | CLARIN | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302840 | Dagohoy NHS | DAGOHOY | 2nd | 1 | - | 630 | - | 630 | 14 | - | - | 1845855.3243 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118637 | Cansague Norte PS | SAN ISIDRO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118640 | Masonoy PS | SAN ISIDRO | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302890 | San Isidro National High School | SAN ISIDRO | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 305580 | Cambansag High School | SAN ISIDRO | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 312327 | Candungao High School | SAN ISIDRO | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117951 | Abihid ES | ANDA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117952 | Almaria ES | ANDA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117956 | Buenasuerte E/S | ANDA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117957 | Candabong ES | ANDA | 3rd | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 117965 | Tanod ES | ANDA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3rd | 1 | - | 844 | - | 844 | 19 | - | - | 2474043.6579 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118014 | Behind The Clouds PS | BATUAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118019 | Garcia ES | BATUAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118023 | Quirino PS | BATUAN | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302815 | Batuan NHS | BATUAN | 3rd | 1 | - | 450 | - | 450 | 10 | - | - | 1318468.0888 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 312314 | Quezon HS - Batuan NHS Annex | BATUAN | 3rd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118661 | Cabancalan PS | SEVILLA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118664 | Calinginan Sur PS | SEVILLA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 118666 | Ewon Elementary School | SEVILLA | 3rd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA | 3rd | 1 | - | 405 | - | 405 | 9 | - | - | 1186621.2799 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VII | Bohol | 312310 | Bayawahan National High School | SEVILLA | 3rd | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 118873 | Bulalacao ES | ALCOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 118874 | Caidiocan PS | ALCOY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302918 | Nug-as NHS | ALCOY | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 500650 | Pasol-Pugalo IS | ALCOY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 470940.4886 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119126 | Baclayan ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119127 | Becerril ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119129 | Caipilan Elementary School | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119130 | El Pardo ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119131 | Granada ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119133 | Nangka ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119134 | Pondohan ES | BOLJOON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302943 | El Pardo NHS | BOLJOON | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302944 | LUNOP NATIONAL HIGH SCHOOL | BOLJOON | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119604 | Basak Elementary School | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119606 | Cañorong ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119607 | Dalahikan ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119608 | Jumangpas ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119609 | Kalatagan ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119610 | Kamburoy ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119611 | Manuel L. Quezon ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119612 | Monteverde ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119614 | San Sebastian ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119615 | Suba ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119616 | Tangbo ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 187024 | Colase ES | SAMBOAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 312425 | Pedro B. Uy Calderon Memorial National High School | SAMBOAN | 2nd | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 500662 | Bulangsuran Integrated School | SAMBOAN | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119549 | Pilar Central School | PILAR | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119550 | San Isidro ES | PILAR | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119551 | San Juan ES | PILAR | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303032 | Dapdap NHS | PILAR | 5th | 1 | - | 90 | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303074 | Don Filomeno M. Torres MNHS | PILAR | 5th | 1 | - | 135 | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119857 | General PS | TUDELA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119858 | Maslog PS | TUDELA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119860 | Puertobello ES | TUDELA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119861 | Santander PS | TUDELA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119864 | VILLAHERMOSA ES | TUDELA | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303080 | Puertobello NHS | TUDELA | 5th | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303081 | Puertobello NHS - Pob. Ext. | TUDELA | 5th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 7th | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119398 | Anao ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119399 | Cambagte ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119400 | Campisong ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119401 | Canorong ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119403 | Guiwanon Elementary School | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119404 | Kabatuan ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119408 | Salamanca ES | GINATILAN | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 7th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 500921 | Mangaco Integrated School | GINATILAN | 7th | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119439 | Calipay PS | MALABUYOC | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119441 | Labrador ES | MALABUYOC | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119449 | Salmeron ES | MALABUYOC | 7th | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 302982 | CerdeÃ±a NHS | MALABUYOC | 7th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303057 | MontaÃ±eza NHS | MALABUYOC | 7th | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303058 | Sorsogon NHS | MALABUYOC | 7th | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 312462 | Mahanlud NHS | MALABUYOC | 7th | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119599 | Liboo ES | RONDA | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119600 | Madanglog ES | RONDA | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 119603 | Tupas ES | RONDA | 7th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303033 | Langin NHS | RONDA | 7th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Cebu | 303034 | Ronda NHS- Langin NHS Ext. | RONDA | 7th | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120430 | Basak Primary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120431 | Jose R. Remollo ES (Cambaloctot ES) | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120432 | Cancawas Primary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120433 | Janayjanay Elementary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120435 | Alicia C. Calumpang Elementary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120437 | San Roque Primary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120438 | Siapo Elementary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 120439 | Sra. Ascion Elementary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 303278 | Crisostomo O. Retes National High School | SAN JOSE | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VII | Negros Oriental | 312928 | Siapo HS | SAN JOSE | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 120662 | New Corregidor Elementary School | LARENA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 501427 | Larena Integrated School | LARENA | Lone | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 120680 | Logucan Elementary School | MARIA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 303300 | Tambisan National High School | SAN JUAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 303305 | Catulayan National High School | SAN JUAN | Lone | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VII | Siquijor | 501430 | San Juan Integrated School | SAN JUAN | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120763 | Lo-ok ES | ALMERIA | Lone | 1 | 190 | - | - | 190 | 4 | - | - | 555610.609 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120765 | Palayan ES | ALMERIA | Lone | 1 | 235 | - | - | 235 | 5 | - | - | 687457.4178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303319 | Almeria NHS | ALMERIA | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 313201 | Western Biliran High School for the Arts and Culture | ALMERIA | Lone | 1 | - | 90 | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120777 | Canila ES | BILIRAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120790 | Casiawan ES | CABUCGAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120791 | J.D. Garcia ES | CABUCGAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120795 | Salawad Elementary School | CABUCGAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303322 | Cabucgayan National School of Arts and Trade | CABUCGAYAN | Lone | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120804 | Katipunan ES | CAIBIRAN | Lone | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120814 | Uson ES | CAIBIRAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303328 | Caibiran National High School | CAIBIRAN | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2636936.1776 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2940103.9395 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120823 | Patag PS | CULABA | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303321 | Bool NHS | CULABA | Lone | 1 | - | 720 | - | 720 | 16 | - | - | 2352083.1516 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303324 | Culaba NVS | CULABA | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 501046 | Pinamihagan Integrated School | CULABA | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120835 | L. Atillo ES | KAWAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120844 | Ungale II Elementary School | KAWAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303326 | Kawayan National High School | KAWAYAN | Lone | 1 | - | 137 | - | 137 | 3 | - | - | 447310.0123 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 303333 | Tucdao National High School | KAWAYAN | Lone | 1 | - | 450 | - | 450 | 10 | - | - | 1318468.0888 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120850 | Canduhao ES | MARIPIPI | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120851 | Casibang ES | MARIPIPI | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Biliran | 120852 | Danao ES | MARIPIPI | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122610 | Caisawan Elementary School | BALANGKAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122616 | General Malvar Elementary School | BALANGKAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122621 | Magsaysay Elementary School | BALANGKAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303495 | Balangkayan National High School | BALANGKAYAN | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122474 | Alang-Alang Primary School | GENERAL MACARTHUR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122495 | Quirino Primary School | GENERAL MACARTHUR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122496 | Roxas Primary School | GENERAL MACARTHUR | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122515 | President Roxas Elementary School | GIPORLOS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122516 | Salvacion Elementary School | GIPORLOS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122498 | San Isidro Elementary School | HERNANI | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303505 | Pedro E. Candido Memorial National High School | HERNANI | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122577 | Mabuhay Elementary School | JIPAPAD | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122352 | San Isidro Primary School | LAWAAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122466 | San Miguel Elementary School | MASLOG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122467 | San Roque Elementary School | MASLOG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122470 | Tangbo Elementary School | MASLOG | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303515 | Maslog National High School | MASLOG | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303518 | Mercedes National High School | MERCEDES | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122678 | Cantinio Elementary School | QUINAPONDAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122680 | Mabini Elementary School | QUINAPONDAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 192503 | San Isidro Elementary School | QUINAPONDAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303521 | Quinapondan National High School | QUINAPONDAN | Lone | 1 | - | 675 | - | 675 | 15 | - | - | 1977702.1332 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122694 | Iberan Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122696 | Lusod Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122701 | Seguinon Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122704 | Alog Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122709 | Bugay Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122715 | Guba Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122716 | Jagnaya Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122719 | Sta. Cruz Elementary School | SALCEDO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122729 | Putong Elementary School | SAN JULIAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 122745 | Tanauan Elementary School | SAN POLICARPO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School of Agriculture | SAN POLICARPO | Lone | 1 | - | 585 | - | 585 | 13 | - | - | 1911067.5607 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121878 | San Miguelay Elementary School | SANTA FE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121948 | Cantariwis Elementary School | TOLOSA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303391 | Daniel Z. Romualdez State Comprehensive School of Fisheries | TOLOSA | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303440 | Tolosa National High School | TOLOSA | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121518 | Balante Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121521 | Caridad Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121524 | Gitabla Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121526 | Inawangan Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121531 | Tagkip Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191514 | Bugho Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191538 | Bonifacio Primary School | JULITA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121559 | Bongtod Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121561 | Caabangan Elementary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121563 | Cacao Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121565 | Caltayan Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121566 | Canbanez Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121567 | Cogon Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121569 | Gimiranat East Elementary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121570 | Gimiranat West Elementary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121571 | Jacinta Vivero Memorial Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121575 | Miguel Gernale Memorial Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121577 | Moroboro Elementary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121578 | Nicasio Vivero Memorial Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121579 | Pansud Elementary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121581 | Piliway Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121585 | Tarugan Primary School | LA PAZ | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 313332 | Buracan National High School | LA PAZ | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121618 | Causwagan Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191529 | Gen. Luna Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191530 | Lanauan Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191539 | Quezon Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191556 | Burabod Primary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191564 | Kiling Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191565 | San Pedro Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191568 | Prisco A. Pille Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191575 | Salvacion Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191577 | San Vicente Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191581 | Oguisan Elementary School | MACARTHUR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121702 | Calipayan Elementary School | MAYORGA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121703 | Camansi Primary School | MAYORGA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303407 | Mayorga National High School | MAYORGA | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121809 | Aringit Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121811 | Cabaohan Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121815 | Dumarag Elementary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121816 | Halaba Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121818 | Lanauan Elementary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121819 | Lima Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121820 | Lourdes Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191511 | Cancaraja Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191555 | Capilla Primary School | PASTRANA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303380 | Juan Villablanca Memorial High School | PASTRANA | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 313343 | Macalpi-ay National High School | PASTRANA | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121909 | Balingasag Primary School | TABONTABON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121910 | Belisong Primary School | TABONTABON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121913 | Jabong Elementary School | TABONTABON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121915 | Mohon Primary School | TABONTABON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 191540 | Mering Primary School | TABONTABON | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303382 | Justimbaste-Remandaban National High School | TABONTABON | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303441 | Gregorio C. Catenza NHS (Tunga NHS) | TUNGA | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121728 | Mahayag Primary School | MERIDA | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121729 | Mat-e Primary School | MERIDA | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121734 | San Jose Elementary School | MERIDA | 4th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121735 | Tubod Primary School | MERIDA | 4th | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 303410 | Puerto Bello National High School | MERIDA | 4th | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 313301 | Minesite National High School | MERIDA | 4th | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121399 | Baldoza Elementary School | HINDANG | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121407 | Himokilan Elementary School | HINDANG | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Leyte | 121409 | Katipunan Elementary School | HINDANG | 5th | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122776 | Alejandro Primary School | ALLEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122780 | Caputian PS | ALLEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122789 | Sta. Rita Elementary School | ALLEN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122790 | Bagong Silang ES | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122793 | CAWAYAN ES | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122794 | Langub-Langub ES | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122795 | MACARET ELEMENTARY SCHOOL | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122797 | SALVACION ELEMENTARY SCHOOL | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122800 | Tampipi Elementary School | BIRI | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303534 | BIRI NATIONAL HIGH SCHOOL | BIRI | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303576 | San Antonio NHS | BIRI | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122819 | Aguin ES | CAPUL | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122822 | Dalaquit Elem School | CAPUL | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123250 | Tarnate ES | SAN VICENTE | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303567 | Mongolbongol NHS | SAN VICENTE | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123270 | Acedillo Elementary School | VICTORIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123271 | Buenasuerte ES | VICTORIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123275 | Gonzaga Elementary School | VICTORIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123281 | San Lazaro ES | VICTORIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123283 | San Roman Elementary School | VICTORIA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 303585 | Victoria NHS | VICTORIA | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 330502 | Maxvilla National High School | VICTORIA | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122991 | Bagacay Elementary School | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122992 | Cahagwayan ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122994 | Can-omanio ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122995 | Imelda ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122997 | Lo-ok ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122998 | Mabini ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 122999 | May-igot ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123000 | Palanas elementary school | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123001 | Pio Del Pilar ES | LAPINIG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123106 | Magsaysay ES | MAPANAS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123109 | Naparasan ES | MAPANAS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123110 | Pangudtan PS | MAPANAS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 123111 | Quezon ES | MAPANAS | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Northern Samar | 313622 | Magtaon NHS | MAPANAS | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123293 | Lunang II ES | ALMAGRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123294 | Magsaysay ES | ALMAGRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123299 | Tonga-Tonga ES | ALMAGRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123540 | De-It ES | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123549 | Matuguinao CES | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123550 | Nagpapacao ES | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123557 | San Isidro ES | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193503 | LIbertad PS | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193504 | Rizal PS 2 | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193536 | Inubod ES | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193541 | Salvacion PS | MATUGUINAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123812 | Sto. Nino CS | SANTO NIÑO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303591 | Baras National High School | SANTO NIÑO | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303632 | Sto. Niño National High School | SANTO NIÑO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303638 | Villahermosa National High School | SANTO NIÑO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 313703 | Cabunga-an Integrated School | SANTO NIÑO | 1st | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 501924 | Sevilla Integrated School | SANTO NIÑO | 1st | 1 | - | - | 360 | 360 | 9 | - | - | 1181422.2909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123819 | Labangbaybay ES | TAGAPUL-AN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123824 | Pantalan Elementary School | TAGAPUL-AN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123826 | San Vicente Elementary school | TAGAPUL-AN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123828 | Trinidad Elementary School | TAGAPUL-AN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303590 | Baquiw National High School | TAGAPUL-AN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 313724 | Balocawe Integrated School | TAGAPUL-AN | 1st | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123583 | Bugho ES | JIABONG | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123588 | Catalina ES | JIABONG | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123589 | Cristina Elementary School | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123590 | Dogongan Elementary School | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123591 | Garcia ES | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123594 | Jidanao Elementary School | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123600 | Nagbac Elementary School | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123603 | San Andres ES | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123605 | San Miguel ES | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193545 | Hinaga ES | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 281506 | Flora Mabaet Mabansag Elementary School | JIABONG | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 193516 | Mabuhay ES | MARABUT | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303611 | Marabut National High School | MARABUT | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303614 | Osmeña National High School | MARABUT | 2nd | 1 | - | 1080 | - | 1080 | 24 | - | - | 3528124.7274 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123714 | Cabaywa ES | SAN SEBASTIAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303627 | San Sebastian National High School | SAN SEBASTIAN | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 501374 | Inobongan Integrated School | SAN SEBASTIAN | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123899 | Navatas Guti Elementary School | TALALORA | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303608 | Independencia National High School | TALALORA | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 501372 | Tatabunan Integrated School | TALALORA | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123967 | Botaera ES | ZUMARRAGA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 123974 | Marapilit ES | ZUMARRAGA | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303602 | Mualbual National High School | ZUMARRAGA | 2nd | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 303643 | Zumarraga National High School | ZUMARRAGA | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 313707 | Bioso Integrated School | ZUMARRAGA | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 313721 | San Isidro National High School | ZUMARRAGA | 2nd | 1 | - | 495 | - | 495 | 11 | - | - | 1617057.1667 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region VIII | Samar (Western Samar) | 501931 | Camayse Integrated School | ZUMARRAGA | 2nd | 1 | - | - | 320 | 320 | 8 | - | - | 1050153.1474 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303444 | Anahawan National Vocational High Schoolchool | ANAHAWAN | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122062 | Amaga Elementary School | HINUNDAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122069 | Cabulisan Multi-Grade Elem.School | HINUNDAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 192031 | Cat-iwing MG Elem School | HINUNDAYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 313411 | Libagon National High School | LIBAGON | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303465 | LIMASAWA NATIONAL HIGH SCHOOL | LIMASAWA | Lone | 1 | - | 900 | - | 900 | 20 | - | - | 2940103.9395 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122241 | Punod Primary School | PINTUYAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303477 | Pintuyan National Vocational High School | PINTUYAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | Lone | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 192021 | Anislagon Primary School | SAN FRANCISCO | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | Lone | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122254 | Sta. Filomena Elementary School | SAN JUAN (CABALIAN) | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303481 | San Juan NHS | SAN JUAN (CABALIAN) | Lone | 1 | - | 765 | - | 765 | 17 | - | - | 2499088.3486 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 17 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303478 | Pinut-an National High School | SAN RICARDO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | Lone | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 122313 | Carnaga Elementary School | TOMAS OPPUS | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303479 | RIZAL NATIONAL HIGH SCHOOL | TOMAS OPPUS | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region VIII | Southern Leyte | 303480 | San Isidro NHS | TOMAS OPPUS | Lone | 1 | - | 270 | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 126889 | Mainit ES | CATARMAN | Lone | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 303989 | Bonbon NHS | CATARMAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 303990 | Camiguin NHS | CATARMAN | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 500686 | Sto. Niño Integrated School | CATARMAN | Lone | 1 | - | - | 320 | 320 | 8 | - | - | 941880.9772 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 303991 | Guinsiliban National High School | GUINSILIBAN | Lone | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 303995 | Eulalio U. Pabillore National High Sschool | SAGAY | Lone | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 500683 | Alangilan Integrated School | SAGAY | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 706410.7329 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Camiguin | 500962 | Bacnit Integrated School | SAGAY | Lone | 1 | - | - | 240 | 240 | 6 | - | - | 706410.7329 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 325701 | SAN FRANCISCO DE ASIS NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 127681 | Ulaliman ES | CITY OF EL SALVADOR | 2nd | 1 | 135 | - | - | 135 | 3 | - | - | 441015.5909 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 304065 | Cogon National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 304768 | Himaya National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 304797 | Sinaloc National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 315 | - | 315 | 7 | - | - | 922927.6622 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 305683 | Sambulawan National High School | CITY OF EL SALVADOR | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 315305 | MOLUGAN NATIONAL HIGH SCHOOL | CITY OF EL SALVADOR | 2nd | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region X | El Salvador | 501927 | Kalabaylabay Integrated School | CITY OF EL SALVADOR | 2nd | 1 | - | - | 411 | 411 | 10 | - | - | 1208396.9323 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200529 | Upper Tugar PS | KAUSWAGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 315106 | Sultan Dimasangcay Mananggolo IS (Delabayan ES) | KAUSWAGAN | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501807 | Baraason Integrated School | KAUSWAGAN | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Inudaran PS | KAUSWAGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501030 | Samburon Integrated School | LINAMON | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127139 | Pangi Elementary School | MATUNGAO | 1st | 1 | 270 | - | - | 270 | 6 | - | - | 791080.8533 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200508 | Bubong Radapan P S | MATUNGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304012 | MATUNGAO NATIONAL HIGH SCHOOL | MATUNGAO | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1582161.7066 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127165 | Lower Kalanganan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127167 | Pantar West Primary School | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127168 | Pendulonan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127170 | Punod ES | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127171 | Sigayan Adil PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127172 | Tambo-Cadayonan ES | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127173 | Tawanan PS | PANTAR | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304019 | Pantar National High School | PANTAR | 1st | 1 | - | 180 | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127213 | Gadongan PS | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200543 | Malimbato Primary School | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501394 | Tagoloan Integrated School | TAGOLOAN | 1st | 1 | - | - | 459 | 459 | 11 | - | - | 1503757.5812 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501395 | Kiasar Integrated School | TAGOLOAN | 1st | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501433 | Tumple Integrated School | TAGOLOAN | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Payong Dalamas ES | TAGOLOAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127101 | Durianon Primary School | MAGSAYSAY | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 315110 | SERGIO P. CERUJALES, JR. NHS | MAGSAYSAY | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501378 | Shiek Omar Integrated School | MAGSAYSAY | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127174 | Barandia PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127175 | Bulacon PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127176 | Buntong ES | SALVADOR | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127180 | Daligdigan PS | SALVADOR | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127183 | Mabatao ELEMENTARY SCHOOL | SALVADOR | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127188 | Sudlon ES | SALVADOR | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200505 | Pansur PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Pangantapan PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Inasagan PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Inudaran PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Mindalano PS | SALVADOR | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127190 | Baning Elem. School | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127192 | Carcum Prim. School | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 127193 | Dansalan PS | SAPAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 304017 | Panoloon NHS | SAPAD | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 136948 | SULTAN MIMBISA LOMABAO PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 136949 | SULTAN LINDONGAN PRIMARY SCHOOL | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200533 | Beruar Elementary School | TANGCAL | 2nd | 1 | 270 | - | - | 270 | 6 | - | - | 882031.1818 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 200534 | Tangkal Proper IPS | TANGCAL | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 315103 | Tangcal NHS (Annex Magsaysay NHS) | TANGCAL | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1323046.7728 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501599 | Big Banisilon Integrated School | TANGCAL | 2nd | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte | 501602 | Pelingkingan Integrated School | TANGCAL | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Brgy. Bayabao PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Lamaosa PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Lanao del Norte |  | Lingco-an PS | TANGCAL | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127276 | Lipacon ES | BALIANGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127281 | Naburos ES | BALIANGAO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127360 | Balongkot ES | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127362 | Debaloy ES | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127365 | Mantukoy PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127366 | Marugang Elementary School | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127367 | Migubay PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127373 | Upper Salimpono PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 201020 | Virayan PS | CONCEPCION | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501858 | New Casul Integrated School | CONCEPCION | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127476 | Baga PS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127477 | Bangko ES | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127478 | Camanucan Elementary School | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127479 | De La Paz Primary School | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127480 | F.T. Paylaga MPS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127481 | Map-An PS | PANAON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127512 | Boundary Primary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127517 | Dasa Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 20% Allocation for E-Bamboo |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127518 | Dioyo Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127519 | Disoy ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127520 | El Paraiso Primary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127521 | Feliciano Baguio PS | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127522 | Libertad Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127525 | Manalac ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127529 | Napilan Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127531 | Salimpono Elemntary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127532 | Salvador ES | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127536 | Upper Bautista PS | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127537 | Ventura Elementary School | SAPANG DALAGA | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501873 | Locus Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501874 | Manla Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 280 | 280 | 7 | - | - | 824145.8551 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 501884 | Bitibut Integrated School | SAPANG DALAGA | 1st | 1 | - | - | 400 | 400 | 10 | - | - | 1177351.2215 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127543 | Dinas Elementary School | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127544 | Estrella ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127545 | Katipunan ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127546 | Libertad Alto ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127549 | San Isidro Alto ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127550 | San Isidro Bajo Primary School | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Occidental | 127551 | San Lorenzo Ruiz ES | SINACABAN | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 304085 | Mantangale NHS | BALINGOAN | 1st | 1 | - | 90 | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 341228 | Mantangale SHS | BALINGOAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127722 | Dampias E.A. Rañises ES | BINUANGAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127719 | Buko ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127726 | Kinoguitan CS | KINOGUITAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127735 | Panabol ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127737 | Suarez ES | KINOGUITAN | 1st | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 201506 | Kalitian ES | KINOGUITAN | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 304070 | Esperanza NHS | KINOGUITAN | 1st | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 360848 | Esperanza Senior High School | KINOGUITAN | 1st | 1 | - | 360 | - | 360 | 8 | - | - | 1176041.5758 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 500253 | Calubo IS | KINOGUITAN | 1st | 1 | - | - | 116 | 116 | 3 | - | - | 381218.5875 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127745 | Kamansi ES | LAGONGLONG | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 304068 | Dampil NHS | LAGONGLONG | 1st | 1 | - | 315 | - | 315 | 7 | - | - | 1029036.3788 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 341234 | Lagonglong SHS | LAGONGLONG | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2058072.7576 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127724 | Kaulayanan ES | SUGBONGCOGON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127731 | Mangga ES | SUGBONGCOGON | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 304101 | Sugbongcogon NHS | SUGBONGCOGON | 1st | 1 | - | 540 | - | 540 | 12 | - | - | 1764062.3637 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 500999 | G. Pelaez IS | GITAGUM | 2nd | 1 | - | - | 240 | 240 | 6 | - | - | 787614.8606 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 127760 | Libertad CS | LIBERTAD | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 304079 | Libertad NHS | LIBERTAD | 2nd | 1 | - | 855 | - | 855 | 19 | - | - | 2793098.7425 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 19 | 0 |  | 100%
CY 2022 SF | Region X | Misamis Oriental | 501321 | Lubluban IS | LIBERTAD | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128576 | Kipalili ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128581 | Mamangan ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128590 | Sabangan ES | SAN ISIDRO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128595 | Sawata Ernandcor Central Elem. School | SAN ISIDRO | 1st | 1 | 360 | - | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128648 | Dacudao ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128652 | Gov. Dujali ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128657 | Linao ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 128667 | Pinamuno ES | SAN ISIDRO | 1st | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 304240 | Linao National High School | SAN ISIDRO | 1st | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 304251 | Sawata NHS | SAN ISIDRO | 1st | 1 | - | 630 | - | 630 | 14 | - | - | 2058072.7576 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 |  | 100%
CY 2022 SF | Region XI | Davao del Norte | 500859 | Igangon Integrated School | SAN ISIDRO | 1st | 1 | - | - | 440 | 440 | 11 | - | - | 1443960.5777 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 11 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 101813 | Bugakan Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 102157 | Catmonan Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 102164 | Talucanga Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129381 | Rabat-Rocamora Mati CES II | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129385 | Tagawisan ES | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 263693.6178 | CENTRAL OFFICE IMPLEMENTATION | 15% Allocation for Regular Cooperative |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129389 | Benito G. Rabat Exec. ES | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129393 | Cangusan ES | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129394 | Serafin Vizconde Sr. Elementary School | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129402 | Sta. Cruz ES | CITY OF MATI (Capital) | 2nd | 1 | 225 | - | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129404 | Tagbinonga ES | CITY OF MATI (Capital) | 2nd | 1 | 180 | - | - | 180 | 4 | - | - | 527387.2355 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129408 | Fausta Salazar Como MS | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129414 | Francisco Hinayon ES | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 129418 | Magum ES | CITY OF MATI (Capital) | 2nd | 1 | 222 | - | - | 222 | 5 | - | - | 650767.0324 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 205504 | Rabat Rocamora Mati Central School SPED Center | CITY OF MATI (Capital) | 2nd | 1 | 90 | - | - | 90 | 2 | - | - | 294010.3939 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304303 | Bobon NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 659234.0444 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304305 | Buso National High School | CITY OF MATI (Capital) | 2nd | 1 | - | 180 | - | 180 | 4 | - | - | 588020.7879 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304313 | Dawan NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 405 | - | 405 | 9 | - | - | 1186621.2799 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304314 | Don Enrique Lopez NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304318 | Libudon NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 585 | - | 585 | 13 | - | - | 1911067.5607 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 13 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304327 | Matiao NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1470051.9697 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304328 | Davao Oriental Regional Science High School | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 304338 | Taguibo Agri. Voc. High School | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 325104 | Badas NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 450 | - | 450 | 10 | - | - | 1318468.0888 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 325105 | Macambol NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 225 | - | 225 | 5 | - | - | 735025.9849 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 325106 | Mayo NHS | CITY OF MATI (Capital) | 2nd | 1 | - | 360 | - | 360 | 8 | - | - | 1054774.471 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 500454 | Licop Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 501085 | Cabuaya Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 588675.6108 | CENTRAL OFFICE IMPLEMENTATION | 10% Allocation for Cooperative of PWDs |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 501086 | Lanca Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 501087 | Luban Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 200 | 200 | 5 | - | - | 656345.7172 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 100%
CY 2022 SF | Region XI | Mati City | 501424 | Culian Integrated School | CITY OF MATI (Capital) | 2nd | 1 | - | - | 160 | 160 | 4 | - | - | 525076.5737 | REGIONAL OFFICE IMPLEMENTATION | 55% Allocation for Regular Supplier |  | Completed | 100% | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 100%
5385503690.0001