## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 211505 | Bokbokon ES | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-16 | 130114S00064 | 15ND0025 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-08-06 | 2015-08-26 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131458 | Bonifacio ES | LAS NIEVES | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2883574.43 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-24 | 130114S00022 | 14ND0039 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-17 | 2014-08-05 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-10-31 | 130114S00017 | 14ND0037 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-20 | 2014-09-03 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131478 | San Roque ES | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-14 | 130114S00021 | 14ND0038 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-20 | 2014-09-03 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131479 | Subait ES | LAS NIEVES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110129.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 130114S00018 | 14ND0036 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-17 | 2014-08-05 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131549 | Bagang ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 130114S00068 | 15NA0012 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 317319 | Bangonay NHS | JABONGA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 |  | 2014-11-03 | 130114S00009 | 14NA0018 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131581 | Beto ES | TUBAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00010 | 14NA0016 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 211503 | Cabayugan ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 130114S00066 | 15NA0012 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131544 | Cadahondahonan ES | SANTIAGO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 130114S00069 | 15NA0012 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131482 | Caloc-an ES | MAGALLANES | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6317156.7656 |  |  | COMPLETED | 1 | 2015-04-29 | 2015-04-29 | 130114S00057 | 14NA0033 | 2014-11-03 | 2014-11-05 | 2014-11-17 | 2014-11-20 | 2014-11-27 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131493 | Camagong ES | NASIPIT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00015 | 14NA0011 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131495 | Culit ES | NASIPIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 130114S00067 | 15NA0012 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131420 | Elpedio Salas Sr. ES | CARMEN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2881574.43 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00056 | 14NA0011 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 500314 | Hinandayan NHS (Nasipit National Vocational School Annex) | NASIPIT | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2913574.43 |  |  | COMPLETED | 1 |  | 2014-11-03 | 130114S00004 | 14NA0011 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 |  | 2014-11-03 | 130114S00003 | 14NA0018 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131539 | Jose L. Ong Oh Jr. ES | SANTIAGO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00014 | 14NA0017 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131552 | Kabalalahan ES | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00055 | 14NA0012 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131586 | La Fraternidad ES | TUBAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00007 | 14NA0016 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131576 | La Union ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1984017.57 |  |  | REVERTED | 0 | 2014-11-03 | 2014-11-03 | 130114S00011 | 14NA0015 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131554 | Lekda ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2933574.43 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00054 | 14NA0012 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131484 | Magallanes North ES | MAGALLANES | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00008 | 14NA0015 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131437 | Maraiging ES | JABONGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-10-31 | 130114S00065 | 15NA0012 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-17 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131499 | Minbahandi ES | NASIPIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2016017.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00023 | 14NA0011 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 500312 | NORCACES ISS (Evening Opportunity HS) | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1984017.57 |  |  | REVERTED | 0 | 2014-11-03 | 2014-11-03 | 130114S00006 | 14NA0015 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131564 | Olave ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986017.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00053 | 14NA0012 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 211510 | Poblacion Doz PS | REMEDIOS T. ROMUALDEZ | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986017.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00002 | 14NA0015 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 211507 | San Juan PS | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00051 | 14NA0012 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131546 | Santiago CES | SANTIAGO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2883574.43 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00013 | 14NA0017 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131443 | Sto. Nino ES | JABONGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112929.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00016 | 14NA0018 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 211501 | Tabon PS | NASIPIT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00001 | 14NA0011 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131571 | Tapnigue ES | BUENAVISTA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110129.12 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00052 | 14NA0012 | 2014-05-21 | 2014-05-22 | 2014-06-03 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986017.57 |  |  | COMPLETED | 1 |  | 2014-11-03 | 130114S00005 | 14NA0016 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Norte | 131547 | Villa Serrano ES | SANTIAGO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1984017.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 130114S00012 | 14NA0017 | 2014-05-28 | 2014-05-29 | 2014-06-10 | 2014-06-24 | 2014-07-02 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131862 | Anahawan ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2632943.5115 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 130214S00106 | 14NB0070 | 2014-10-31 | 2014-11-04 | 2014-11-18 | 2014-12-10 | 2014-12-16 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131668 | Balobo ES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1135129.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00066 | 14NB0022 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-21 | 2014-09-24 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304707 | Bayugan NCHS | CITY OF BAYUGAN | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18953879.7656 |  |  | COMPLETED | 1 |  | 2015-12-29 | 130214S00098 | 14NB0098 | 2014-12-10 | 2014-12-12 | 2015-01-23 | 2015-02-14 | 2015-03-02 | JV: GIOVANNI CONSTRUCTION/DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317420 | Bayugan NCHS - Magkiangkang Annex | CITY OF BAYUGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 130214S00050 | 14NB0021 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131669 | Bentahon ES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00067 | 14NB0023 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-21 | 2014-09-24 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131970 | Buena Gracia ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00039 | 14NB0037 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131670 | Bunaguit ES | ESPERANZA | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3802005.49 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00068 | 14NB0058 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131618 | Cagbas ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986017.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 130214S00029 | 14NB0033 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131699 | Catmonon ES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2015-12-10 | 2014-12-10 | 130214S00072 | 14NB0030 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-21 | 2014-09-24 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131971 | Causwagan ES | TALACOGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00044 | 14NB0031 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131940 | Cecilia ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00021 | 14NB0039 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-22 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131942 | Culi ES | SAN LUIS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 130214S00035 | 14NB0028 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131976 | Culi-Ram ES | TALACOGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-15 | 130214S00117 | 15NB0028 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-26 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131866 | Dandanon ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2898574.43 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 130214S00034 | 14NB0042 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-21 | 2014-09-24 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131943 | Datu Bandahan ES | SAN LUIS | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-14 |  | 130214S00139 | 15NB0026 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131937 | DOP BALIT IP SCHOOL (IPA) | SAN LUIS | 1 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 2 | 4321625.4513 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 130214S00079 | 14NB0050 | 2014-08-01 | 2014-08-05 | 2014-08-27 | 2014-09-21 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212074 | DOP BINATUNAN IP SCHOOL (IPA) | SAN LUIS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00136 | 15NB0024 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212072 | DOP KIBUKAY IP SCHOOL (IPA) | ESPERANZA | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 4B | 2826789.8282 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00115 | 15NB0022 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212073 | DOP SAN ANDRES IP School (IPA) | SAN LUIS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00142 | 15NB0023 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-26 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131775 | East Prosperidad CES | PROSPERIDAD (Capital) | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  | 2016-04-24 | 130214S00116 | 15NB0072 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-28 | 2015-10-27 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131775 | East Prosperidad CES | PROSPERIDAD (Capital) | 1 |  | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  | 2016-04-24 | 130214S00127 | 15NB0073 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-29 | 2015-10-27 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304712 | Esperanza NHS | ESPERANZA | 1 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 1 | 5777148.86 |  |  | COMPLETED | 1 |  | 2014-12-28 | 130214S00076 | 14NB0045 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-21 | 2014-09-24 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317440 | Esperanza NHS - Catmonon HS Annex | ESPERANZA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2893574.43 |  |  | COMPLETED | 1 |  | 2014-12-23 | 130214S00065 | 14NB0046 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-21 | 2014-09-24 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131621 | Gamao ES | CITY OF BAYUGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 130214S00028 | 14NB0018 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-25 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317424 | Guadalupe NHS - Duangan HS Ext. | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006017.57 |  |  | COMPLETED | 1 |  | 2014-12-24 | 130214S00077 | 14NB0035 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-21 | 2014-09-24 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131674 | Guibonon PS | ESPERANZA | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1 | 2016-02-14 |  | 130214S00111 | 15NB0020 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131676 | Imelda ES | ESPERANZA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 | 2015-11-15 | 130214S00154 | 15NB0025 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212051 | Jose T. Cuyos, Sr. I PS | ROSARIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1024373.101 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-10 | 130214S00078 | 14NC0029 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-14 | 2014-08-29 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131871 | Keoya ES | SIBAGAT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00037 | 14NB0052 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-29 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131679 | Kubo ES | ESPERANZA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2893574.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00069 | 14NB0051 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-21 | 2014-10-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131983 | La Flora ES | TALACOGON | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-01-27 | 130214S00049 | 14NB0057 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-29 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131796 | La Purisima Elementary Schhol | PROSPERIDAD (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 |  | 2015-12-29 | 130214S00145 | 15NB0032 | 2015-07-16 | 2015-07-30 | 2015-08-02 | 2015-08-26 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131796 | La Purisima Elementary Schhol | PROSPERIDAD (Capital) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 |  | 2015-12-26 | 130214S00146 | 15NB0033 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212002 | La Suerte ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2893574.43 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 130214S00048 | 14NB0047 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-21 | 2014-09-24 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131680 | Langag ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006017.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00070 | 14NB0034 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-21 | 2014-09-24 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131779 | Lucena ES | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8269859.2031 |  |  | COMPLETED | 1 | 2015-08-22 | 2015-08-22 | 130214S00093 | 14NB0096 | 2014-12-10 | 2014-12-12 | 2015-01-23 | 2015-02-18 | 2015-03-02 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317428 | Lucena NHS - West Prosperidad Annex | PROSPERIDAD (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6327206.7656 |  |  | COMPLETED | 1 |  | 2015-08-11 | 130214S00100 | 14NB0094 | 2014-12-10 | 2014-12-12 | 2014-12-29 | 2015-01-26 | 2015-02-12 | J-R3 CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131780 | Mapaga ES | PROSPERIDAD (Capital) | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-01-25 | 2015-12-15 | 130214S00137 | 15NB0029 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131801 | Mikit ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1991017.57 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00026 | 14NB0040 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304724 | Mount Olive National High School | CITY OF BAYUGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 |  | 2014-12-28 | 130214S00046 | 14NB0019 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131802 | New Maasin ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-26 | 130214S00148 | 15NB0034 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131878 | New Tubigon ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2913574.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00024 | 14NB0055 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-29 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304728 | Noli NHS | CITY OF BAYUGAN | 1 | 1 | 10 | 2STY8CL & 1STY2CL | 2014 K10 BATCH 3 | 13145077.9578 |  |  | COMPLETED | 1 |  | 2015-10-21 | 130214S00092 | 14NB0097 | 2014-12-10 | 2014-12-12 | 2014-12-29 | 2015-02-14 | 2015-03-02 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304729 | Noli NHS - Calaitan NHS Annex | CITY OF BAYUGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 |  | 2014-12-28 | 130214S00045 | 14NB0020 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131708 | OdiongES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 130214S00073 | 14NB0025 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131959 | Olangoan ES | SAN LUIS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1155129.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00020 | 14NB0054 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-29 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131782 | Pakwan ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 |  | 2015-12-26 | 130214S00149 | 15NB0030 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-08-28 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131782 | Pakwan ES | PROSPERIDAD (Capital) | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 |  | 2015-12-06 | 130214S00151 | 15NB0031 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-08-28 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131609 | Panaytay ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986017.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 130214S00032 | 14NB0032 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-21 | 2014-09-24 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131881 | Perez ES | SIBAGAT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1145129.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-27 | 130214S00027 | 14NB0053 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-29 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131960 | Policarpo ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 130214S00019 | 14NB0038 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-22 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131806 | Salvacion ES | PROSPERIDAD (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6327206.7656 |  |  | COMPLETED | 1 | 2015-09-27 | 2015-09-27 | 130214S00096 | 14NB0093 | 2014-12-10 | 2014-12-12 | 2014-12-29 | 2015-01-26 | 2015-02-12 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131783 | San Agustin ES | PROSPERIDAD (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1046201.9548 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 130214S00094 | 14NB0077 | 2014-11-11 | 2014-11-12 | 2014-11-25 | 2014-12-13 | 2014-12-16 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131611 | San Isidro Elementary School | CITY OF BAYUGAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2883574.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-01-27 | 130214S00031 | 14NB0048 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-26 | 2014-09-29 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131882 | San Isidro I ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 130214S00023 | 14NB0059 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131883 | San Isidro II ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00134 | 15NB0037 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212059 | San Isidro PS | TALACOGON | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-26 | 130214S00144 | 15NB0038 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131962 | San Luis CES | SAN LUIS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 |  | 130214S00135 | 15NB0036 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131963 | San Mariano ES | SAN LUIS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130214S00025 | 14NB0029 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131787 | San Roque ES | PROSPERIDAD (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6337256.7656 |  |  | COMPLETED | 1 | 2015-08-26 | 2015-08-26 | 130214S00095 | 14NB0095 | 2014-12-10 | 2014-12-12 | 2014-12-29 | 2015-01-26 | 2015-02-12 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212060 | San Roque PS | TALACOGON | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-26 | 130214S00125 | 15NB0027 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-25 | 2015-08-28 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131886 | Senai ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 130214S00022 | 14NB0043 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-21 | 2014-09-24 | J-R3 CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317442 | Sibagat NHSHI - Afga Annex | SIBAGAT | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3674691.1656 |  |  | COMPLETED | 1 |  | 2015-03-16 | 130214S00101 | 14NB0071 | 2014-10-31 | 2014-11-04 | 2014-11-18 | 2014-12-05 | 2014-12-16 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131692 | Skyline ES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-24 | 130214S00071 | 14NB0024 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131810 | Sta. Maria ES | PROSPERIDAD (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-11-30 | 130214S00147 | 15NB0035 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131695 | Tagbalili ES | ESPERANZA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00112 | 15NB0021 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131713 | Tahina ES | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 130214S00074 | 14NB0026 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-22 | 2014-09-25 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317432 | Talacogon National High School - Labnig Annex | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006017.57 |  |  | COMPLETED | 1 |  | 2014-12-15 | 130214S00043 | 14NB0036 | 2014-07-11 | 2014-07-15 | 2014-08-19 | 2014-09-22 | 2014-09-25 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131714 | Tandang Sora Elementary School | ESPERANZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125129.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 130214S00075 | 14NB0027 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-21 | 2014-09-24 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212062 | Tumalog ES | TALACOGON | 1 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 1 | 5807148.86 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 130214S00047 | 14NB0056 | 2014-09-23 | 2014-09-24 | 2014-10-07 | 2014-10-20 | 2014-10-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131645 | Verdu ES | CITY OF BAYUGAN | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3792005.49 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 130214S00018 | 14NB0049 | 2014-08-01 | 2014-08-05 | 2014-08-19 | 2014-09-22 | 2014-09-25 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131613 | Villa Ondayon ES | CITY OF BAYUGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110129.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 130214S00030 | 14NB0017 | 2014-07-04 | 2014-07-08 | 2014-08-19 | 2014-09-26 | 2014-09-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131892 | Villangit ES | SIBAGAT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 130214S00001 | 14NB0044 | 2014-08-01 | 2014-09-12 | 2014-10-10 | 2014-10-20 | 2014-10-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131893 | Alma ES | VERUELA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903574.43 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-11-16 | 130214S00010 | 14NC0018 | 2014-06-19 | 2014-07-01 | 2014-07-22 | 2014-07-30 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131924 | Aurora ES | SANTA JOSEFA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 |  | 2016-01-25 | 130214S00124 | 15NC0043 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-16 | 2015-09-28 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131924 | Aurora ES | SANTA JOSEFA | 2 |  | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 |  | 2016-02-13 | 130214S00133 | 15NC0053 | 2015-08-24 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131896 | Bacay ES | VERUELA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2016017.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-11-07 | 130214S00011 | 14NC0017 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-18 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131834 | Bitan-agan ES | SAN FRANCISCO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-21 |  | 130214S00123 | 15NC0042 | 2015-08-12 | 2015-08-14 | 2015-08-27 | 2015-09-15 | 2015-09-24 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131814 | Bonifacio CES | ROSARIO | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 4B | 5281656.248 |  |  | COMPLETED | 1 | 2016-03-29 |  | 130214S00113 | 15NC0059 | 2015-08-21 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131835 | Borbon ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-05 | 130214S00056 | 14NC0008 | 2014-06-18 | 2014-06-21 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131816 | Cabantao ES | ROSARIO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-11-14 | 130214S00061 | 14NC0010 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131997 | Cahian ES | TRENTO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-01-23 | 130214S00007 | 14NC0014 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131998 | Cebolin ES | TRENTO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006017.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-25 | 130214S00013 | 14NC0016 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317448 | Cebolin Hs Annex | TRENTO | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-13 |  | 130214S00130 | 15NC0055 | 2015-08-24 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131750 | Comota ES | LA PAZ | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1028915.9548 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-02 | 130214S00102 | 14NC0045 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212032 | Dao PS | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1836461.2636 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-05 | 130214S00085 | 14NC0024 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-12 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131751 | Dona Adela CES | LA PAZ | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 |  | 2016-02-11 | 130214S00121 | 15NC0050 | 2015-08-19 | 2015-08-21 | 2015-09-03 | 2015-09-17 | 2015-09-28 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131751 | Dona Adela CES | LA PAZ | 2 |  | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 |  | 2016-02-13 | 130214S00122 | 15NC0056 | 2015-08-24 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212069 | DOP MANGUICAO IP SCHOOL (IPA) | LA PAZ | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00120 | 15NC0047 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-16 | 2015-09-28 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131852 | Ebro ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-20 | 130214S00062 | 14NC0009 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-13 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131819 | Garsuta ES | ROSARIO | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 130214S00150 | 15NC0129 | 2015-10-30 | 2015-11-12 | 2015-11-27 | 2015-12-19
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 132000 | Gasa ES | TRENTO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1822861.2636 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 130214S00080 | 14NC0025 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-14 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131653 | Hagnaya ES | BUNAWAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-02-05 | 130214S00042 | 14NC0022 | 2014-07-07 | 2014-07-11 | 2014-07-22 | 2014-08-06 | 2014-08-11 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131654 | Hubang ES | BUNAWAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1135129.12 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-21 | 130214S00041 | 14NC0013 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131722 | Ilang-Ilang ES | LORETO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00143 | 15NC0045 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-16 | 2015-09-28 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131655 | Imelda ES | BUNAWAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3792005.49 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-06 | 130214S00040 | 14NC0014 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 132001 | Isdaon ES | TRENTO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 130214S00014 | 14NC0015 | 2014-06-17 | 2014-06-20 | 2014-07-22 | 2014-08-28 | 2014-09-08 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131723 | Jandayugong ES | LORETO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110129.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-11-20 | 130214S00038 | 14NC0018 | 2014-06-19 | 2014-07-01 | 2014-07-22 | 2014-07-30 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212054 | Jose T. Cuyos, Sr.II PS | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-02-23 | 130214S00064 | 14NC0011 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131656 | Kalingayan ES | BUNAWAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-06 | 130214S00033 | 14NC0012 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131753 | Kasapa II ES | LA PAZ | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2700149.5699 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-20 | 130214S00103 | 14NC0045 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131727 | Kauswagan ES | LORETO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2913574.43 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-11-22 | 130214S00002 | 14NC0019 | 2014-06-19 | 2014-07-01 | 2014-07-03 | 2014-07-14 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131754 | Kimondo ES | LA PAZ | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1028915.9548 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-20 | 130214S00104 | 14NC0045 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131839 | Ladgadan ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-04 | 130214S00055 | 14NC0008 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131757 | Langasian ES | LA PAZ | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-11 |  | 130214S00129 | 15NC0051 | 2015-08-19 | 2015-08-21 | 2015-09-03 | 2015-09-17 | 2015-09-30 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131759 | Lope Cortes ES | LA PAZ | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3688761.1656 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-04-14 | 130214S00105 | 14NC0047 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | THEARIS BUILDERS & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131840 | Lucac ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-05 | 130214S00051 | 14NC0008 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131760 | Lydia ES | LA PAZ | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1029373.101 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-06 | 130214S00088 | 14NC0023 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-20 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131732 | Magaud ES | LORETO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00153 | 15NC0046 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-16 | 2015-09-28 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131911 | Magsaysay ES | VERUELA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125129.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-11-07 | 130214S00017 | 14NC0017 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-18 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131912 | Mahayahay ES | VERUELA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00128 | 15NC0044 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-15 | 2015-09-28 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131763 | Maitom ES | LA PAZ | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2661533.6991 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-17 | 130214S00082 | 14NC0023 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-20 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131824 | Masabong PS | ROSARIO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-11-14 | 130214S00060 | 14NC0010 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131764 | Min-angkig Elementary School | LA PAZ | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-11 |  | 130214S00132 | 15NC0048 | 2015-08-19 | 2015-08-21 | 2015-09-03 | 2015-09-17 | 2015-09-30 | DDS BUILDERS | CONTRACTOR WORKING ON LIQUIDATED DAMAGE
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212008 | New Israel ES | TRENTO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1061573.101 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 130214S00087 | 14NC0025 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-14 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131856 | New Visayas ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-20 | 130214S00053 | 14NC0009 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131825 | Novele ES | ROSARIO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2898574.43 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-21 | 130214S00059 | 14NC0013 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131659 | Nueva Era ES | BUNAWAN | 2 | 1 | 6 | 2STY6CL (open ground) | 2014 K10 BATCH 4C | 150000 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131913 | Nueva Era ES | VERUELA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-13 | 2015-12-21 | 130214S00126 | 15NC0054 | 2015-08-24 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131857 | Ormaca ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1836861.2636 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-03-16 | 130214S00083 | 14NC0025 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-14 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131926 | Pag-asa ES | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1846461.2636 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 130214S00090 | 14NC0024 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-12 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131858 | Pasta ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-16 | 130214S00052 | 14NC0009 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131842 | Pudlosan ES | SAN FRANCISCO | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-02-11 |  | 130214S00141 | 15NC0052 | 2015-08-19 | 2015-08-21 | 2015-09-03 | 2015-09-17 | 2015-09-30 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131827 | Rosario CES | ROSARIO | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2016-02-13 |  | 130214S00114 | 15NC0058 | 2015-08-21 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131766 | Sabang Adgawan Elementary School | LA PAZ | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-03-18 |  | 130214S00119 | 15NC0049 | 2015-08-19 | 2015-08-21 | 2015-10-27 | 2015-11-11 | 2015-11-20 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131915 | San Gabriel ES | VERUELA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125129.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-11-07 | 130214S00012 | 14NC0017 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-18 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131740 | San Isidro ES | LORETO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2913574.43 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-03-20 | 130214S00006 | 14NC0020 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-18 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 132013 | San Juan ES | TRENTO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996017.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-25 | 130214S00015 | 14NC0016 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-15 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131742 | San Miguel PS | LORETO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-11-20 | 130214S00008 | 14NC0019 | 2014-06-19 | 2014-07-01 | 2014-07-03 | 2014-07-16 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131768 | San Patricio ES | LA PAZ | 2 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4437031.6745 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-04 | 130214S00091 | 14NC0048 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131917 | Sawagan ES | VERUELA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2680049.5699 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-01-26 | 130214S00099 | 14NC0046 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131932 | Simeon S. Castor ES | SANTA JOSEFA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1044373.101 |  |  | COMPLETED | 1 | 2015-02-09 | 2015-02-09 | 130214S00086 | 14NC0024 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-06 | 2014-08-29 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131743 | Sta Teresa ES | LORETO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2036017.57 |  |  | COMPLETED | 1 | 2015-01-16 | 2015-01-16 | 130214S00005 | 14NC0021 | 2014-06-19 | 2014-07-01 | 2014-07-03 | 2014-07-24 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131845 | Sta. Ana ES | SAN FRANCISCO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103129.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-01-14 | 130214S00054 | 14NC0008 | 2014-06-18 | 2014-06-21 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1105129.12 |  |  | COMPLETED | 1 |  | 2014-12-24 | 130214S00063 | 14NC0010 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317429 | Sta. Cruz NHS - Novele Annex | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1867495.5828 |  |  | COMPLETED | 1 |  | 2015-05-22 | 130214S00097 | 14NC0046 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-18 | 2014-11-24 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131921 | Sta. Emelia ES | VERUELA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1846461.2636 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 130214S00084 | 14NC0026 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-14 | 2014-08-29 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131934 | Sta. Josefa CES | SANTA JOSEFA | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 4B | 4455568.2979 |  |  | COMPLETED | 1 | 2016-03-29 |  | 130214S00110 | 15NC0057 | 2015-08-21 | 2015-08-28 | 2015-09-08 | 2015-09-22 | 2015-10-02 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131830 | Sta. Rosa ES | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1991017.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-02-18 | 130214S00058 | 14NC0011 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131744 | Sto Nino ES | LORETO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2016017.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-11-25 | 130214S00004 | 14NC0021 | 2014-06-19 | 2014-07-01 | 2014-07-03 | 2014-07-24 | 2014-08-04 | J & S ESCUADRA CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131663 | Tagbayangbang ES | BUNAWAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888574.43 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-18 | 130214S00036 | 14NC0012 | 2014-06-12 | 2014-06-24 | 2014-06-26 | 2014-09-16 | 2014-09-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 212022 | Upper Consuelo II ES | BUNAWAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3792005.49 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 130214S00016 | 14NC0015 | 2014-06-17 | 2014-06-20 | 2014-07-22 | 2014-08-28 | 2014-09-08 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131831 | Valentina PS | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1991017.57 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-01-19 | 130214S00057 | 14NC0022 | 2014-07-07 | 2014-07-11 | 2014-07-22 | 2014-08-06 | 2014-08-11 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 317445 | Veruela NHS Annex - Nueva Era HS | VERUELA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1870861.2636 |  |  | COMPLETED | 1 |  | 2015-01-10 | 130214S00089 | 14NC0026 | 2014-07-13 | 2014-07-18 | 2014-07-22 | 2014-08-19 | 2014-08-29 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Agusan del Sur | 131747 | Waloe ES | LORETO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115129.12 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-03-10 | 130214S00003 | 14NC0020 | 2014-07-08 | 2014-07-17 | 2014-07-22 | 2014-08-06 | 2014-08-18 | DDS BUILDERS
NC 2014 | K10 (2014) | CARAGA | Bayugan City | 131598 | Gethsemane ES | CITY OF BAYUGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00131 | 15NB0039 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-08-28 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | CARAGA | Bayugan City | 131603 | Magkiangkang ES | CITY OF BAYUGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-26 | 130214S00140 | 15NB0040 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-08-28 | DATREBIL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Bayugan City | 131622 | New Bohol Elementary School | CITY OF BAYUGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-25 |  | 130214S00138 | 15NB0041 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-23 | 2015-08-28 | ABADA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132608 | Bebiano Alba ES | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-28 | 130514S00032 | 14NI0027 | 2014-09-09 | 2014-09-11 | 2014-09-22 | 2014-09-26 | 2014-10-02 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132612 | Caguyao ES | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-30 | 130514S00039 | 14NI0028 | 2014-08-12 | 2014-08-14 | 2014-08-26 | 2014-09-02 | 2014-09-10 | BISLIG VENTURE CONSTRUCTION & DEVT. INC.
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132617 | Gerardo Verano ES | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1089935.8563 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-01 | 130514S00004 | 14NI0024 | 2014-08-12 | 2014-08-14 | 2014-08-26 | 2014-09-02 | 2014-09-10 | BISLIG VENTURE CONSTRUCTION & DEVT. INC.
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132620 | Mamparasan ES | CITY OF BISLIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-05 |  | 130514S00094 | 15NI0025 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132833 | Mangagoy CES | CITY OF BISLIG | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  | 2016-05-26 | 130514S00095 | 15NI0066 | 2015-11-30 | 2015-12-04 | 2015-12-14 | 2015-12-23 | 2015-12-28 | O. G. SANTOS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132833 | Mangagoy CES | CITY OF BISLIG | 2 |  | 8 | 2STY8CL | 2014 K10 BATCH 4C | 10877342.5917 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132833 | Mangagoy CES | CITY OF BISLIG | 2 |  | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | CARAGA | Bislig City | 235003 | New Bonga Primary School | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1060275 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-07-03 | 130514S00060 | 14NI0069 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Bislig City | 235004 | New Jerusalem Primary School | CITY OF BISLIG | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3631065 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-13 | 130514S00061 | 14NI0070 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132641 | Pablo B. Duray ES | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1069935.8563 |  |  | COMPLETED | 1 | 2014-12-31 | 2015-01-15 | 130514S00030 | 14NI0025 | 2014-09-09 | 2014-09-11 | 2014-09-22 | 2014-09-26 | 2014-10-02 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132625 | Pamanlinan ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1854207.6235 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-04-01 | 130514S00062 | 14NI0071 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132628 | R. Castillo ES | CITY OF BISLIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-02-04 |  | 130514S00086 | 15NI0024 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132630 | San Antonio ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1871821.3447 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-05 | 130514S00031 | 14NI0023 | 2014-08-12 | 2014-08-14 | 2014-08-26 | 2014-09-02 | 2014-09-10 | BISLIG VENTURE CONSTRUCTION & DEVT. INC.
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132639 | Sote PS | CITY OF BISLIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-05 | 2015-12-28 | 130514S00085 | 15NI0023 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | MAG CORPORATION
NC 2014 | K10 (2014) | CARAGA | Bislig City | 132640 | Sta. Cruz ES | CITY OF BISLIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-30 | 130514S00009 | 14NI0026 | 2014-08-12 | 2014-08-14 | 2014-08-26 | 2014-09-02 | 2014-09-10 | BISLIG VENTURE CONSTRUCTION & DEVT. INC.
NC 2014 | K10 (2014) | CARAGA | Butuan City | 304756 | Agusan NHS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 |  | 2015-05-13 | 130114S00058 | 14ND0076 | 2014-11-27 | 2014-11-28 | 2014-12-10 | 2014-12-19 | 2014-12-29 | JOSELLE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 |  | 2014-11-17 | 130114S00031 | 14ND0012 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-18 | 2014-09-03 | 3C SL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132028 | Anticala ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-02-20 | 130114S00050 | 14ND0056 | 2014-11-05 | 2014-11-06 | 2014-11-18 | 2014-12-09 | 2014-12-19 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132105 | Bit-os ES | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-17 |  | 130114S00072 | 15ND0050 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | GIOVANNI CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132030 | Bugsukan ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-20 | 2014-10-20 | 130114S00030 | 14ND0013 | 2014-06-04 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-08 | JOSELLE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 317518 | Bugsukan ISS | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-20 | 2014-10-20 | 130114S00026 | 14ND0014 | 2014-06-04 | 2014-06-04 | 2014-06-17 | 2014-06-27 | 2014-07-08 | JOSELLE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132065 | Buhangin ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2027417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-01 | 130114S00028 | 14ND0029 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-17 | 2014-08-05 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 |  | 2014-10-29 | 130114S00024 | 14ND0015 | 2014-06-04 | 2014-06-04 | 2014-06-17 | 2014-06-30 | 2014-07-17 | ADSE ENTERPRISES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 500316 | Cabcabon ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-14 | 130114S00038 | 14ND0016 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-14 | 2014-09-03 | ETP BUILDERS
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132068 | Datu Ecleo Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-17 |  | 130114S00071 | 15ND0042 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-10-20 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132069 | Don Francisco ES | BUTUAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-01 | 130114S00044 | 14ND0040 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-17 | 2014-08-05 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132056 | Doongan Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3885805.49 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 130114S00045 | 14ND0042 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-21 | 2014-08-05 | RAMISES CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 317501 | Florida NHS | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-29 | 130114S00049 | 14ND0017 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-06-30 | 2014-07-17 | ADSE ENTERPRISES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 212503 | Francisco T. Magno ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2027417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-10-31 | 130114S00032 | 14ND0031 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-08-05 | REYROSE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132116 | Kinamlutan ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2077417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-28 | 130114S00037 | 14ND0032 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-18 | 2014-09-03 | 3C SL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 500317 | La Soledad ISS | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 |  | 2014-11-16 | 130114S00027 | 14ND0018 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-20 | 2014-09-03 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132117 | La Trinidad ES | BUTUAN CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3910805.49 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 130114S00062 | 14ND0058 | 2014-11-05 | 2014-11-06 | 2014-11-18 | 2014-12-09 | 2014-12-22 | RAMISES CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132118 | Libertad CES | BUTUAN CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-17 | 130114S00036 | 14ND0043 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-22 | 2014-08-05 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 304764 | Los Angeles NHS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2027417.57 |  |  | COMPLETED | 1 |  | 2014-11-02 | 130114S00029 | 14ND0033 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-08-05 | REYROSE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132058 | Lumbocan ES | BUTUAN CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 |  |  | 130114S00073 | 15ND0083 | 2015-12-15 | 2015-12-15 | 2015-12-28 | 2015-12-29
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132076 | Mahay ES | BUTUAN CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3910805.49 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 130114S00061 | 14ND0059 | 2014-11-05 | 2014-11-06 | 2014-11-18 | 2014-12-09 | 2014-12-19 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132035 | Mahayahay ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2057417.57 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-21 | 130114S00048 | 14ND0034 | 2014-06-13 | 2014-06-13 | 2014-06-26 | 2014-07-15 | 2014-08-05 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132077 | Maibu ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-11-24 | 2014-11-24 | 130114S00020 | 14ND0019 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-09-02 | 2014-09-11 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132106 | Mandacpan ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2027417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 130114S00041 | 14ND0035 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-14 | 2014-09-03 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132096 | Mandamo ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 130114S00042 | 14ND0020 | 2014-07-16 | 2014-07-17 | 2014-08-05 | 2014-08-18 | 2014-09-03 | 3C SL CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132107 | Maon ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4379334.6094 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-03-31 | 130114S00059 | 14ND0073 | 2014-11-27 | 2014-11-28 | 2014-12-10 | 2014-12-18 | 2014-12-29 | KELVIN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132120 | Masao ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1130329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 130114S00035 | 14ND0021 | 2014-07-16 | 2014-07-17 | 2014-10-07 | 2014-10-20 | 2014-11-01 | REY ROSE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132121 | Matin-ao ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-20 | 2014-10-20 | 130114S00034 | 14ND0022 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-06-30 | 2014-07-08 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132025 | Obrero ES | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2UNIT 2STY4CL | 2014 K10 BATCH 3 | 12848579.5312 |  |  | COMPLETED | 1 | 2015-05-29 | 2015-05-28 | 130114S00060 | 14ND0077 | 2014-11-27 | 2014-11-28 | 2014-12-10 | 2014-12-19 | 2015-01-14 | C ZARLES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132036 | Pianing ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-29 | 130114S00047 | 14ND0023 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-07-07 | 2014-07-17 | TWO ACES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132079 | Pigdaulan ES | BUTUAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-03 | 130114S00043 | 14ND0041 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-21 | 2014-08-06 | JOSELLE CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132123 | Pinamanculan ES | BUTUAN CITY (Capital) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3867805.49 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-01 | 130114S00033 | 14ND0044 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-21 | 2014-08-05 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132108 | San Roque ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1130329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-29 | 130114S00040 | 14ND0024 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-07-08 | 2014-07-17 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132109 | San Vicente ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 130114S00039 | 14ND0025 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-07-15 | 2014-07-24 | TWO ACES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Butuan City | 132049 | Sidlakan ES | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-29 | 2014-10-29 | 130114S00046 | 14ND0026 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-07-08 | 2014-07-17 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Butuan City | 317522 | Tagkiling Tribal ISS | BUTUAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 |  | 2014-10-22 | 130114S00025 | 14ND0027 | 2014-06-06 | 2014-06-06 | 2014-06-19 | 2014-07-07 | 2014-07-17 | TWO ACES CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 304808 | Albor NHS | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2172417.57 |  |  | COMPLETED | 1 |  | 2015-01-06 | 130814S00003 | 14NE0013 | 2014-08-04 | 2014-08-07 | 2014-08-18 | 2014-09-02 | 2014-10-02 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132419 | Cambinliw ES | LORETO | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1144329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-04-10 | 130814S00005 | 1308-14-S-00005 | 2014-11-05 | 2014-11-11 | 2014-11-13 | 2014-11-25 | 2015-01-09 | By Administration
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132489 | Diegas ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2172417.57 |  |  | COMPLETED | 1 | 2014-11-25 | 2015-08-28 | 130814S00002 | 14NE0009 | 2014-06-18 | 2014-06-19 | 2014-07-02 | 2014-08-04 | 2014-08-28 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132491 | Edera ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130814S00007 | 15NE0022 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132421 | Esperanza ES | LORETO | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-13 |  | 130814S00011 | 15NE0055 | 2015-10-01 | 2015-10-05 | 2015-10-16 | 2015-10-30 | 2015-11-13 | WERR CORPORATION INTERNATIONAL | No Remarks
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132495 | GEOTINA ELEMENTARY SCHOOL | BASILISA (RIZAL) | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 |  |  | 130814S00009 | 15NE0032 | 2015-11-25 | 2015-11-26 | 2015-12-09
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132499 | Navarro ES | BASILISA (RIZAL) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | REVERTED | 0 |  |  | 130814S00008 | 15NE0054 | 2015-10-01 | 2015-10-05
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132426 | Panamaon ES | LORETO | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1792087.7106 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1144329.12 |  |  | COMPLETED | 1 |  | 2014-12-27 | 130814S00001 | 14NE0015 | 2014-08-14 | 2014-08-15 | 2014-08-28 | 2014-09-23 | 2014-10-13 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132506 | Roxas Elementary School | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1964740.174 |  |  | COMPLETED | 1 | 2016-02-10 |  | 130814S00010 | 15NE0023 | 2015-09-08 | 2015-09-09 | 2015-09-21 | 2015-09-29 | 2015-10-13 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Dinagat Island | 132509 | Sto. Nino ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2172417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2015-05-24 | 130814S00004 | 14NE0012 | 2014-08-04 | 2014-08-07 | 2014-08-18 | 2014-09-02 | 2014-09-16 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | CARAGA | Siargao | 317607 | Alegria National High School - Annex | SANTA MONICA (SAPAO) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1176329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-24 | 130714S00009 | 14NG005 | 2014-06-27 | 2014-06-27 | 2014-07-10 | 2014-07-15 | 2014-07-31 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Siargao | 132220 | Bay-ang Comm. ES | SOCORRO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3141174.43 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 130714S00003 | 14NG006 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | R.M. MONDARES CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132126 | Consolacion ES | DAPA | 1 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 4A | 3673171.0629 |  |  | COMPLETED | 1 | 2015-11-28 |  | 130714S00080 | 15NG0007 | 2015-08-26 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-09-30 | JGS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132127 | Corregidor ES | DAPA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2290417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-02-27 | 130714S00014 | 14NG004 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Siargao | 132183 | Datu ES | PILAR | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2260417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 130714S00066 | 14NG004 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Siargao | 132130 | Don Paulino Elementary School | DAPA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1020615.4086 |  |  | COMPLETED | 1 | 2015-11-28 |  | 130714S00079 | 15NG0007 | 2015-08-26 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-09-30 | JGS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132168 | Esperanza ES | DEL CARMEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3602592.44 |  |  | COMPLETED | 1 |  | 2015-11-19 | 130714S00085 | 15NG0010 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | JGS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132168 | Esperanza ES | DEL CARMEN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 |  | 2015-11-19 | 130714S00087 | 15NG0010 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | JGS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132172 | Lasala ES | DEL CARMEN | 1 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 4A | 2041230.8172 |  |  | COMPLETED | 1 |  |  | 130714S00076 | 1307-14-S-00076 | 2015-12-01 | 2015-12-03 | 2015-12-15 |  |  | By Administration
NC 2014 | K10 (2014) | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2220417.57 |  |  | COMPLETED | 1 |  | 2014-11-18 | 130714S00017 | 14NG006 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | R.M. MONDARES CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 317605 | Oguing Navarro Mem. NHS - Annex | DEL CARMEN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1234329.12 |  |  | COMPLETED | 1 |  | 2014-11-27 | 130714S00010 | 14NG005 | 2014-06-27 | 2014-06-27 | 2014-07-10 | 2014-07-15 | 2014-07-31 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Siargao | 132132 | Osmena ES | DAPA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1020615.4086 |  |  | COMPLETED | 1 | 2015-11-28 |  | 130714S00077 | 15NG0007 | 2015-08-26 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-09-30 | JGS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132198 | Roxas ES | SAN ISIDRO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 1020615.4086 |  |  | COMPLETED | 1 |  |  | 130714S00081 | 1307-14-S-00081 | 2015-12-01 | 2015-12-03 | 2015-12-15 |  |  | By Administration
NC 2014 | K10 (2014) | CARAGA | Siargao | 304784 | Roxas NHS | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2310417.57 |  |  | COMPLETED | 1 |  | 2014-11-27 | 130714S00065 | 14NG005 | 2014-06-27 | 2014-06-27 | 2014-07-10 | 2014-07-15 | 2014-07-31 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Siargao | 132219 | San Mateo ES | BURGOS | 1 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 4A | 2041230.8172 |  |  | COMPLETED | 1 |  |  | 130714S00078 | 1307-14-S-00078 | 2015-12-01 | 2015-12-03 | 2015-12-15 |  |  | By Administration
NC 2014 | K10 (2014) | CARAGA | Siargao | 132192 | San Roque ES | PILAR | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3041174.43 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-03 | 130714S00067 | 14NG004 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Siargao | 132213 | Sapao CES | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2190417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-24 | 130714S00013 | 14NG005 | 2014-06-27 | 2014-06-27 | 2014-07-10 | 2014-07-15 | 2014-07-31 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Siargao | 304788 | Socorro National HS | SOCORRO | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 1 | 4380835.14 |  |  | COMPLETED | 1 |  | 2014-11-18 | 130714S00012 | 14NG006 | 2014-07-21 | 2014-08-15 | 2014-08-26 | 2014-09-01 | 2014-09-05 | R.M. MONDARES CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132144 | Sta. Fe ES | DAPA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2588606.04 |  |  | COMPLETED | 1 |  | 2015-11-19 | 130714S00086 | 15NG0011 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 132144 | Sta. Fe ES | DAPA | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 |  | 2015-11-19 | 130714S00088 | 15NG0011 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Siargao | 304778 | Sta. Fe NHS | GENERAL LUNA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6819337.6381 |  |  | COMPLETED | 1 |  |  | 130714S00089 | 15NG0036 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132274 | Alegria ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 130714S00015 | 14NF0050 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 304800 | Anomar NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 |  | 2014-11-14 | 130714S00051 | 14NF0020 | 2014-06-26 | 2014-06-26 | 2014-07-28 | 2014-08-26 | 2014-09-12 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132244 | Bitaugan ES | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3020174.43 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-03-28 | 130714S00007 | 14NF0078 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-01 | 2014-12-29 | KENT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132279 | Buenavista ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 130714S00043 | 14NF0031 | 2014-07-28 | 2014-07-29 | 2014-07-31 | 2014-08-08 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132290 | C.V. Diez Mem. CES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-07 | 130714S00046 | 14NF0022 | 2014-06-26 | 2014-06-26 | 2014-07-10 | 2014-07-15 | 2014-07-28 | JMT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132247 | Canlanipa ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 130714S00006 | 14NF0021 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 304802 | Capalayan NHS | SURIGAO CITY (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3785805.49 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-02-12 | 130714S00064 | 14nf0059 | 2014-08-07 | 2014-08-18 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132281 | Danawan ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-24 | 2014-11-23 | 130714S00044 | 14NF0051 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 304803 | Day-asan NHS | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2888174.43 |  |  | COMPLETED | 1 |  | 2014-12-08 | 130714S00053 | 14NF0066 | 2014-08-15 | 2014-08-20 | 2014-08-28 | 2014-09-15 | 2014-10-07 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132250 | Hanigad ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-18 | 2014-12-07 | 130714S00005 | 14NF0053 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-15 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132293 | Ipil ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4592048.49 |  |  | COMPLETED | 1 | 2016-03-17 |  | 130714S00084 | 15NF0061 | 2015-10-07 | 2015-10-08 | 2015-10-22 | 2015-11-03 | 2015-11-12 | R.F. VARQUEZ CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132300 | J. R. Clavero MES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-08 | 130714S00048 | 14NF0024 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132296 | Lipata ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-10-28 | 130714S00047 | 14NF0028 | 2014-06-26 | 2014-06-26 | 2014-07-18 | 2014-07-30 | 2014-08-12 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 317704 | Lipata National High School - Annex | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 |  | 2014-12-28 | 130714S00054 | 14NF0026 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 317705 | Mabini NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 130714S00055 | 14NF0038 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-08-27 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132267 | Nabago ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 130714S00016 | 14NF0025 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 304804 | Nonoc NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 |  | 2014-12-17 | 130714S00042 | 14NF0048 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-15 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132301 | Punta Bilar ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986417.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-06 | 130714S00049 | 14NF0046 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-09-16 | GICAR CONSTRUCTION, INC.
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132304 | Sabang ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 1 | 2190658.24 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 130714S00050 | 14NF0062 | 2014-08-04 | 2014-08-12 | 2014-08-28 | 2014-09-15 | 2014-09-25 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132259 | San Jose ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 130714S00004 | 14NF0052 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-15 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132264 | Sarvida Yuipco MES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 130714S00019 | 14NF0027 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-27 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132271 | Surigao City CES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4297929.6094 |  |  | COMPLETED | 1 | 2015-10-05 |  | 130714S00069 | 15NF0011 | 2015-01-27 | 2015-01-27 | 2015-02-09 | 2014-02-17 | 2015-02-28 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 317701 | Taft NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 |  | 2016-01-12 | 130714S00068 | 15NF0010 | 2015-01-27 | 2015-01-27 | 2015-02-09 | 2015-03-09 | 2015-03-27 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132288 | Tugonan ES | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-10 | 130714S00045 | 14NF0018 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-23 | 2014-07-25 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 132243 | Vicente Cabilao Mem. ES (Balibayon ES) | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-12-10 | 130714S00008 | 14NF0019 | 2014-06-26 | 2014-06-26 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao City | 317707 | Wilfredo D. Rafols Mem. NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1988417.57 |  |  | COMPLETED | 1 |  | 2014-11-25 | 130714S00056 | 14NF0042 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-08-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132450 | Alvarez ES | MALIMONO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 |  | 2014-10-07 | 130714S00023 | 14NF0023 | 2014-06-26 | 2014-06-26 | 2014-07-10 | 2014-07-15 | 2014-07-23 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  | 2014-11-20 | 130714S00038 | 14NF0047 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-08-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-28 | 130714S00057 | 14NF0036 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-09-16 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 130714S00032 | 14NF0034 | 2014-07-28 | 2014-07-29 | 2014-07-31 | 2014-08-08 | 2014-08-26 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132451 | Binocaran PS | MALIMONO | 2 | 2 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1977917.57 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 130714S00070 | 14NF0073 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-01 | 2014-12-17 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132471 | Bugas-Bugas ES | PLACER | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-11-11 | 130714S00026 | 14NF0032 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-08-26 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132405 | Camboayon ES | GIGAQUIT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 130714S00063 | 14NF0035 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132345 | Cambuayon ES | BACUAG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 130714S00058 | 14NF0033 | 2014-07-16 | 2014-07-18 | 2014-07-31 | 2014-08-08 | 2014-09-16 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 317810 | Cawilan NHS-Annex | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 |  | 2014-12-27 | 130714S00011 | 14NF0067 | 2014-08-14 | 2014-08-20 | 2014-08-28 | 2014-09-15 | 2014-09-26 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1978417.57 |  |  | COMPLETED | 1 |  | 2014-12-28 | 130714S00036 | 14NF0070 | 2014-07-17 | 2014-07-21 | 2014-07-31 | 2014-08-14 | 2014-09-26 | CEBU HAYDTER CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132379 | Daywan ES | CLAVER | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-16 | 130714S00059 | 14NF0060 | 2014-07-27 | 2014-07-18 | 2014-08-28 | 2014-09-15 | 2014-09-26 | CEBU HAYDTER CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132527 | De Castro ES | SISON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-28 | 2014-11-28 | 130714S00029 | 14NF0056 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-16 | JMT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132457 | Dumanig ES | MALIMONO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1977917.57 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 130714S00071 | 14NF0074 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-01 | 2014-12-17 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132407 | Gigaquit CES | GIGAQUIT | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2873174.43 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 130714S00030 | 14NF0061 | 2014-08-15 | 2014-08-19 | 2014-08-28 | 2014-09-15 | 2014-09-26 | CEBU HAYDTER CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132382 | Lapinigan ES | CLAVER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 130714S00060 | 14NF0068 | 2014-08-15 | 2014-08-18 | 2014-08-28 | 2014-09-15 | 2014-10-07 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132531 | Mabuhay ES | SISON | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-28 | 130714S00018 | 14NF0055 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-16 | JMT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132383 | Magallanes ES | CLAVER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-06 | 130714S00061 | 14NF0064 | 2014-08-04 | 2014-08-08 | 2014-08-28 | 2014-09-15 | 2014-10-07 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 |  | 2014-11-28 | 130714S00039 | 14NF0065 | 2014-08-15 | 2014-08-20 | 2014-08-28 | 2014-09-15 | 2014-09-26 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132545 | Opong ES | TAGANA-AN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 130714S00033 | 14NF0030 | 2014-07-28 | 2014-07-29 | 2014-07-31 | 2014-08-08 | 2014-09-16 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132439 | Paco ES | MAINIT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-28 | 130714S00052 | 14NF0054 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-15 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3810805.49 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-29 | 130714S00041 | 14NF0058 | 2014-08-15 | 2014-08-22 | 2014-08-28 | 2014-09-15 | 2014-09-26 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132478 | Placer CES | PLACER | 2 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 1 | 2244658.24 |  |  | COMPLETED | 1 | 2015-03-01 | 2015-03-01 | 130714S00027 | 14NF0075 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-01 | 2014-12-23 | ALGAMON CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 214007 | Punta Naga ES | CLAVER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-16 | 130714S00083 | 15NF0027 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-30 | 2015-08-21 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132440 | Quezon ES | MAINIT | 2 | 1 | 2 | 2UNIT 1STY1CL | 2014 K10 BATCH 1 | 2189658.24 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-09 | 130714S00020 | 14NF0063 | 2014-08-04 | 2014-08-12 | 2014-08-28 | 2014-09-15 | 2014-10-07 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132442 | San Francisco ES | MAINIT | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 130714S00021 | 14NF0039 | 2014-07-28 | 2014-07-29 | 2014-07-31 | 2014-08-12 | 2014-08-26 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 |  | 2014-11-10 | 130714S00037 | 14NF0044 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132414 | San Isidro ES | GIGAQUIT | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-08 | 130714S00028 | 14NF0045 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132386 | Sapa ES | CLAVER | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-09 | 2014-12-08 | 130714S00062 | 14NF0043 | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-08 | 2014-09-08 | ASJ BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 |  | 2015-02-04 | 130714S00022 | 14NF0076 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-01 | 2014-12-19 | KENT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 |  | 2015-02-12 | 130714S00034 | 130714S00034 | 2014-11-10 | 2014-11-22 | 2014-11-24 | 2014-12-03 | 2014-12-15 | MYMS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 132535 | Tagbayani ES | SISON | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-12-15 | 130714S00031 | 14NF0049 | 2014-07-28 | 2014-07-29 | 2014-08-11 | 2014-08-14 | 2014-09-16 | JMT CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Norte | 317809 | Talavera NHS - Annex (Tagana-an NHS) | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 |  | 2014-10-28 | 130714S00040 | 14NF0041 | 2014-07-21 | 2014-07-23 | 2014-08-04 | 2014-08-08 | 2014-08-27 | CARTESIAN BUILDERS
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132931 | Anahao Daan ES | TAGO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1031544.3213 |  |  | COMPLETED | 1 | 2015-11-12 | 2015-12-01 | 130514S00068 | 14NH0046 | 2015-04-28 | 2015-06-04 | 2015-06-15 | 2015-06-23 | 2015-07-16 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132768 | Anibongan ES | LIANGA | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130514S00092 | 15NH0115 | 2015-11-26 | 2015-11-27 | 2015-12-10 | 2015-12-28
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132847 | Arorogan ES | MARIHATAG | 1 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 2 | 3743642.6894 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 130514S00037 | 14NH0026 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-13 | 2014-10-23 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132705 | Balibadon ES | CORTES | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891821.3447 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 130514S00005 | 14NH0024 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132769 | Ban-as ES | LIANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1051644.3213 |  |  | COMPLETED | 1 |  | 2015-06-02 | 130514S00059 | 14NH0050 | 2015-01-13 | 2015-01-14 | 2015-01-26 | 2015-02-23 | 2015-03-05 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 500322 | Bangsud ISS | TAGO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1054935.8563 |  |  | COMPLETED | 1 |  | 2015-02-13 | 130514S00023 | 14NH0019 | 2014-08-29 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132959 | Bioto ES | CITY OF TANDAG (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-12 | 130514S00010 | 14NH0025 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132960 | Bongtud ES | CITY OF TANDAG (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-03-20 | 130514S00011 | 14NH0025 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132858 | Britania ES | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1871821.3447 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 130514S00029 | 14NH0020 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-13 | 2014-10-23 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132859 | Buhisan ES | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1871821.3447 |  |  | COMPLETED | 1 | 2015-01-14 | 2015-01-23 | 130514S00015 | 14NH0021 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304877 | Carrascal NHS | CARRASCAL | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891821.3447 |  |  | COMPLETED | 1 |  | 2015-02-14 | 130514S00006 | 14NH0018 | 2014-08-28 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132939 | Claudia P. Pimentel MES | TAGO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1059935.8563 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-11 | 130514S00008 | 14NH0019 | 2014-08-28 | 2014-08-29 | 2014-09-11 | 2014-10-07 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 214510 | Eusebio Josol PS | CORTES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1069935.8563 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 130514S00026 | 14NH0024 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304889 | Gamut NHS (Tago) | TAGO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2717370.3558 |  |  | COMPLETED | 1 |  | 2015-02-14 | 130514S00018 | 14NH0019 | 2014-08-28 | 2014-08-29 | 2014-09-11 | 2014-10-07 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132773 | Ganayon ES | LIANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1026519.3213 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-09-30 | 130514S00066 | 14NH0048 | 2015-01-13 | 2015-01-14 | 2015-01-26 | 2015-02-23 | 2015-03-05 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132861 | GATA ELEMENATRY SCHOOL | SAN AGUSTIN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2015-02-05 | 2015-01-31 | 130514S00007 | 14NH0020 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-13 | 2014-10-23 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132762 | Habag PS | LANUZA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1059935.8563 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 130514S00003 | 14NH0024 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 214511 | Ibuan Elementary School | LANUZA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1906821.3447 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132862 | Janipaan ES | SAN AGUSTIN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2662605.6543 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-10-15 | 130514S00071 | 14NH0048 | 2015-01-13 | 2015-01-14 | 2015-01-26 | 2015-02-23 | 2015-03-05 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304925 | Jose Sanvictores Sr. National School Annex | CAGWAIT | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3510318.8429 |  |  | COMPLETED | 1 |  | 2015-11-12 | 130514S00065 | 14NH0046 | 2015-04-28 | 2015-06-04 | 2015-06-15 | 2015-06-23 | 2015-07-16 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132945 | Jubang ES | TAGO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1054935.8563 |  |  | COMPLETED | 1 | 2015-03-28 | 2015-08-05 | 130514S00028 | 14NH00300 | 2014-12-26 | 2014-12-03 | 2014-12-15 | 2015-01-15 | 2015-01-27 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132775 | La Union ES | LIANGA | 1 | 1 | 5 | 1STY3CL & 1STY2CL | 2014 K10 BATCH 3 | 4500897.1833 |  |  | COMPLETED | 1 | 2015-05-26 | 2015-07-15 | 130514S00067 | 14NH0049 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-15 | 2015-01-27 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132880 | Libas Gua ES | SAN MIGUEL | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-02-26 |  | 130514S00083 | 15NH0063 | 2015-08-17 | 2015-08-29 | 2015-09-02 | 2015-09-08 | 2015-09-30 | RJ CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132966 | Mabuhay ES | CITY OF TANDAG (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891821.3447 |  |  | COMPLETED | 1 | 2015-03-15 | 2015-04-30 | 130514S00012 | 14NH0025 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132778 | Neptune ES | LIANGA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-03-29 |  | 130514S00099 | 15NH0062 | 2015-10-12 | 2015-10-13 | 2015-10-26 | 2015-11-23 | 2015-12-01 | DIGOS CONSTRAK CORPORATION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132766 | Pakwan ES | LANUZA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1891821.3447 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 130514S00002 | 14NH0024 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-01 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132677 | Palasao ES | CANTILAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-27 | 130514S00001 | 14NH0018 | 2014-08-28 | 2014-08-29 | 2014-09-11 | 2014-09-24 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132779 | Payasan ES | LIANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1834107.6235 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-07-15 | 130514S00072 | 14NH0049 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-15 | 2015-01-27 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132865 | Pong-on ES | SAN AGUSTIN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1074935.8563 |  |  | COMPLETED | 1 | 2015-02-04 | 2015-02-04 | 130514S00017 | 14NH0020 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-13 | 2014-10-23 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132972 | Quintos ES | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2747370.3558 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-27 | 130514S00013 | 14NH0025 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132780 | R. Moreno ES | LIANGA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2652555.6543 |  |  | COMPLETED | 1 | 2015-07-02 | 2015-09-30 | 130514S00069 | 14NH0048 | 2015-01-13 | 2015-01-14 | 2015-01-26 | 2015-02-23 | 2015-03-05 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan ISS | LINGIG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2690828.124 |  |  | COMPLETED | 1 |  | 2016-01-05 | 130514S00084 | 15NI0032 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132973 | Rosario ES | CITY OF TANDAG (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1059935.8563 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-12 | 130514S00014 | 14NH0025 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132867 | San Agustin CES | SAN AGUSTIN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130514S00093 | 15NH0113 | 2015-11-26 | 2015-11-27 | 2015-12-10 | 2015-12-28
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132867 | San Agustin CES | SAN AGUSTIN | 1 |  | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130514S00098 | 15NH0114 | 2015-11-26 | 2015-11-27 | 2015-12-10 | 2015-12-28
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132977 | San Jose ES | CITY OF TANDAG (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1031544.3213 |  |  | COMPLETED | 1 | 2015-11-12 | 2015-11-11 | 130514S00074 | 14NH0046 | 2015-04-28 | 2015-06-04 | 2015-06-15 | 2015-06-23 | 2015-07-16 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304905 | San Miguel NCHS | SAN MIGUEL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1069935.8563 |  |  | COMPLETED | 1 |  | 2015-02-14 | 130514S00019 | 14NH0021 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 317913 | San Miguel NCHS - San Roque NHS Annex | SAN MIGUEL | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1074935.8563 |  |  | COMPLETED | 1 |  | 2015-03-15 | 130514S00022 | 14NH0021 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132782 | San Pedro ES | LIANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1026519.3213 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-07-14 | 130514S00070 | 14NH0049 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-15 | 2015-01-27 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132855 | San Pedro ES | MARIHATAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881821.3447 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 130514S00038 | 14NH0026 | 2014-09-09 | 2014-09-11 | 2014-09-23 | 2014-10-13 | 2014-10-23 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132830 | San Vicente ES | MADRID | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2732370.3558 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-23 | 130514S00036 | 14NH0018 | 2014-08-28 | 2014-08-29 | 2014-09-11 | 2014-10-07 | 2014-10-17 | WERR CORPORATION INTERNATIONAL
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132783 | St. Christine ES | LIANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1871821.3447 |  |  | COMPLETED | 1 | 2015-04-26 | 2015-05-16 | 130514S00025 | 14NH0047 | 2014-12-01 | 2014-12-03 | 2014-12-15 | 2015-01-15 | 2015-01-27 | ROWIEs CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304916 | Sto. Niño NHS | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1881821.3447 |  |  | COMPLETED | 1 |  | 2015-01-05 | 130514S00020 | 14NH0020 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-13 | 2014-10-23 | TABADA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132605 | Tabing Dagat ES | BAYABAS | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1041594.3213 |  |  | COMPLETED | 1 |  | 2015-11-12 | 130514S00073 | 14NH0046 | 2015-04-28 | 2015-06-04 | 2015-06-15 | 2015-06-23 | 2015-07-16 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132718 | Uba ES | CORTES | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1041594.3213 |  |  | COMPLETED | 1 | 2015-11-12 | 2015-11-11 | 130514S00064 | 14NH0046 | 2015-04-28 | 2015-06-04 | 2015-06-15 | 2015-06-23 | 2015-07-16 | JOAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304924 | Unidad NHS | CAGWAIT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 2 | 2747370.3558 |  |  | COMPLETED | 1 |  | 2015-02-14 | 130514S00021 | 14NH0021 | 2014-09-02 | 2014-09-03 | 2014-09-19 | 2014-10-07 | 2014-10-17 | CHU CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132573 | Barobo Townsite ES | BAROBO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2727089.5598 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-16 | 130514S00048 | 14NI0049 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132893 | Batunan Elementary School | TAGBINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-27 | 130514S00034 | 14NI0033 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-02 | 2014-09-10 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132574 | Cabacungan ES | BAROBO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1874307.6235 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-17 | 130514S00042 | 14NI0050 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132575 | Campbagang ES | BAROBO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1834107.6235 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-05-12 | 130514S00050 | 14NI0051 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132581 | Guinhalinan ES | BAROBO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1046619.3213 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-12 | 130514S00043 | 14NI0052 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132896 | Hinagdanan ES | TAGBINA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2672655.6543 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-05-22 | 130514S00041 | 14NI0066 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132794 | Hinipaan ES | LINGIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1036569.3213 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-06 | 130514S00045 | 14NI0061 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132582 | Javier ES | BAROBO | 2 | 1 | 6 | 2UNIT 1STY3CL | 2014 K10 BATCH 3 | 5343629.1195 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-06 | 130514S00055 | 14NI0053 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132583 | Kinayan ES | BAROBO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1046619.3213 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-03-18 | 130514S00040 | 14NI0054 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132901 | Lago ES | TAGBINA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-05 |  | 130514S00091 | 15NI0027 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132796 | Lingig CES | LINGIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1036569.3213 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-07 | 130514S00046 | 14NI0062 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132797 | Mahabo ES | LINGIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1036569.3213 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-02-06 | 130514S00047 | 14NI0063 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132586 | Malindog ES | BAROBO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1859232.6235 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-03-17 | 130514S00054 | 14NI0055 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132908 | Manambia ES | TAGBINA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-05 |  | 130514S00090 | 15NI0028 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132807 | Pedro Redondo ES | LINGIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1159935.8563 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 130514S00035 | 14NI0031 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-02 | 2014-09-10 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 214514 | Quary II Soriano ES | TAGBINA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-01-05 |  | 130514S00087 | 15NI0031 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132914 | Quezon Integrated School | TAGBINA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3668215.2471 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-18 | 130514S00051 | 14NI0067 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 317941 | Rizal National High School - Annex | BAROBO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1896821.3447 |  |  | COMPLETED | 1 |  | 2014-12-09 | 130514S00027 | 14NI0030 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-02 | 2014-09-10 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132590 | San Jose ES | BAROBO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1854207.6235 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-05-04 | 130514S00056 | 14NI0056 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132810 | San Roque ES | LINGIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1854207.6235 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-17 | 130514S00058 | 14NI0064 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132749 | Sasa ES | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1834107.6235 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-06-16 | 130514S00044 | 14NI0060 | 2014-10-23 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 317935 | Sta. Maria ISS | TAGBINA | 2 | 1 | 4 | 2UNIT 1STY2CL | 2014 K10 BATCH 3 | 3688315.2471 |  |  | COMPLETED | 1 |  | 2015-03-19 | 130514S00052 | 14NI0068 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132594 | Sua ES | BAROBO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1026519.3213 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-02 | 130514S00053 | 14NI0057 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132750 | Tabok ES | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1921821.3447 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-23 | 130514S00024 | 14NI0029 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-02 | 2014-09-10 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132925 | Tagongon ES | TAGBINA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-05 |  | 130514S00089 | 15NI0029 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | MAG CORPORATION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132596 | Talisay Seaside ES | BAROBO | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 3 | 3505293.8429 |  |  | COMPLETED | 1 | 2015-05-18 | 2015-07-11 | 130514S00057 | 14NI0058 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | AEP CONSTRUCTION AND SERVICES, INC.
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1049935.8563 |  |  | COMPLETED | 1 |  | 2014-11-09 | 130514S00033 | 14NI0032 | 2014-08-14 | 2014-08-14 | 2014-08-27 | 2014-09-02 | 2014-09-10 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132926 | Trinidad ES | TAGBINA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-01-06 |  | 130514S00088 | 15NI0030 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-08-31 | 2015-09-07 | MAG CORPORATION
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132598 | Unidad ES | BAROBO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2692755.6543 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-03-16 | 130514S00063 | 14NI0059 | 2014-10-22 | 2014-10-24 | 2014-11-04 | 2014-11-14 | 2014-11-19 | TWINA BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | CARAGA | Surigao del Sur | 132818 | Union ES | LINGIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2652555.6543 |  |  | COMPLETED | 1 | 2015-04-18 | 2015-04-15 | 130514S00049 | 14NI0065 | 2014-10-23 | 2014-10-24 | 2014-11-06 | 2014-11-14 | 2014-11-19 | MN BAYALAS CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131459 | Casiklan ES | LAS NIEVES | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4573636.82 |  |  | COMPLETED | 1 |  |  | 130115S00092 | 15ND0076 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304680 | Casiklan NHS- Durian NHS Annex | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00025 | 15ND0018 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-27 | 2015-07-30 | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304679 | Durian NHS | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00023 | 15ND0019 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-31 | 2015-08-07 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317310 | E. G. Montilla NHS (Mat-I NHS Annex) | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00031 | 15ND0020 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-31 | 2015-09-10 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131463 | Fatima ES | LAS NIEVES | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 130115S00091 | 15ND0070 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-08 | 2015-09-28 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131466 | Katipunan ES | LAS NIEVES | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2832592.44 |  |  | COMPLETED | 1 |  |  | 130115S00090 | 15ND0041 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-24 | 2015-09-10 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130115S00024 | 15ND0049 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-10-28 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 500048 | Lawan-Lawan NHS (Durian NHS Annex) | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00027 | 15ND0021 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-27 | 2015-07-30 | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304690 | LINGAYAO NATIONAL HIGH SCHOOL | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00033 | 15ND0022 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-31 | 2015-08-07 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304693 | Maningalao NHS | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00034 | 15ND0023 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-31 | 2015-09-03 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304694 | Marcos Calo NHS | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00035 | 15ND0024 | 2015-07-03 | 2015-07-03 | 2015-07-16 | 2015-07-31 | 2015-08-26 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304695 | Mat-i NHS | LAS NIEVES | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6489337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00030 | 15ND0047 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-10-28 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 317314 | Abilan NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6344338 |  |  | COMPLETED | 1 |  |  | 130115S00106 | 15NA0059 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-11-19 | 2015-11-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304673 | Agay NHS | REMEDIOS T. ROMUALDEZ | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 |  |  | 130115S00005 | 15NA0045 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-12-28 |  | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317315 | Agong-ong NHS (Buenavista NHS Annex | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00044 | 15NA0015 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-12 | 2015-08-21 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317311 | Balangbalang NHS (Agay NHS Annex) | REMEDIOS T. ROMUALDEZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6529337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00019 | 15NA0021 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-10-20 | 2015-10-26 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317319 | Bangonay NHS | JABONGA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00020 | 15NA0016 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-13 | 2015-08-24 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10727342.5917 |  |  | COMPLETED | 1 |  |  | 130115S00093 | 15NA0060 | 2015-09-22 | 2015-09-23 | 2015-10-05 | 2015-12-14 | 2015-12-18 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131508 | Buenavista CES | BUENAVISTA | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 130115S00094 | 15NA0056 | 2015-09-15 | 2015-09-16 | 2015-09-28 | 2015-11-19 | 2015-11-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8344965.051 |  |  | COMPLETED | 1 |  |  | 130115S00051 | 15NA0031 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-10-20 | 2015-10-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 500047 | Buenavista Special Education HS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00050 | 15NA0015 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-12 | 2015-08-21 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317304 | Cahayagan NHS (Carmen NHS Annex) | CARMEN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00076 | 15NA0013 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-10 | 2015-08-19 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131417 | Carmen CES | CARMEN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 130115S00105 | 15NA0043 | 2015-09-03 | 2015-09-04 | 2015-09-29 | 2015-10-07 | 2015-10-15 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317308 | Culit NHS (Nasipit National Vocational School Annex) | NASIPIT | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00004 | 15NA0014 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-11 | 2015-08-20 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304678 | Cuyago NHS | JABONGA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00018 | 15NA0054 | 2015-09-15 | 2015-09-16 | 2015-09-28 | 2015-12-28 |  | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 211506 | Datu Saldong Domino ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | REVERTED | 0 |  |  | 130115S00102 | 15NA0044
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2472377.5407 |  |  | COMPLETED | 1 |  |  | 130115S00111 | 15NA0066 | 2015-10-08 | 2015-10-09 | 2015-10-21 | 2015-10-26 | 2015-11-06 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 130115S00014 | 15NA0055 | 2015-09-15 | 2015-09-16 | 2015-09-28 | 2015-10-20 | 2015-10-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131585 | DOÑA TELESFORA ELEMENTARY SCHOOL | TUBAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 130115S00101 | 15NA0046 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-06 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131537 | Dona Telesfora ES | SANTIAGO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 130115S00097 | 15NA0046 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-06 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 500313 | F. S. Omayana NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00049 | 15NA0015 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-12 | 2015-08-21 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304682 | Guinabsan National High School | BUENAVISTA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 130115S00048 | 15NA0032 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-10-01 | 2015-10-07 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 500314 | Hinandayan ES | NASIPIT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2013606.04 |  |  | COMPLETED | 1 |  |  | 130115S00103 | 15NA0043 | 2015-09-03 | 2015-09-04 | 2015-09-29 | 2015-10-07 | 2015-10-15 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 500314 | Hinandayan NHS (Nasipit NHS Annex)) | NASIPIT | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00013 | 15NA0014 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-11 | 2015-08-20 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131447 | Hinimbangan ES | KITCHARAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2043606.04 |  |  | COMPLETED | 1 |  |  | 130115S00086 | 15NA0047 | 2015-09-03 | 2015-09-04 | 2015-09-29 | 2015-10-07 | 2015-10-15 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130115S00032 | 15NA0035 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-29 | 2015-10-05 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 130115S00047 | 15NA0033 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-29 | 2015-10-05 | JOSELLE CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304687 | Jaliobong NHS | KITCHARAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 130115S00006 | 15NA0042 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-29 | 2015-10-05 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131540 | Kauswagan de Oro ES | SANTIAGO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 130115S00089 | 15NA0046 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-06 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304688 | Kitcharao NHS | KITCHARAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 |  |  | 130115S00017 | 15NA0041 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-29 | 2015-10-05 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 317305 | Lekda NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2068606 |  |  | COMPLETED | 1 |  |  | 130115S00110 | 15NA0058 | 2015-09-16 | 2015-09-16 | 2015-09-29 | 2015-10-07 | 2015-10-15 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131555 | Linao-Linao ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2907592.44 |  |  | REVERTED | 0 |  |  | 130115S00099 | 15NA0050
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131557 | Lower Olave ES | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2043606.04 |  |  | COMPLETED | 1 |  |  | 130115S00100 | 15NA0044 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-06 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304691 | Magallanes NHS | MAGALLANES | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 130115S00046 | 15NA0037 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-21 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304692 | Magdagooc NHS | JABONGA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00016 | 15NA0016 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-13 | 2015-08-24 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 500049 | Manapa II ISS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 |  |  | 130115S00095 | 15NA0044 | 2015-09-03 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-06 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 500311 | Manoligao National High School | CARMEN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00075 | 15NA0013 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-10 | 2015-08-19 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1 |  |  | 130115S00015 | 15NA0030 | 2015-08-25 | 2015-08-26 | 2015-09-07 | 2015-09-28 | 2015-10-02 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317302 | Nasipit NHS | NASIPIT | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6459337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00022 | 15NA0022 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-20 | 2015-10-26 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 317317 | Rizal NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2832592 |  |  | COMPLETED | 1 |  |  | 130115S00107 | 15NA0058 | 2015-09-16 | 2015-09-16 | 2015-09-29 | 2015-10-07 | 2015-10-15 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | K10 (2015) | CARAGA | Agusan del Norte | 131440 | San Jose ES | JABONGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2043606.04 |  |  | COMPLETED | 1 |  |  | 130115S00087 | 15NA0047 | 2015-09-03 | 2015-09-04 | 2015-09-29 | 2015-10-07 | 2015-10-15 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317303 | San Vicente ISS | JABONGA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00029 | 15NA0016 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-13 | 2015-08-24 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 317301 | Sangay NHS-Guinabsan NHS Annex | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00043 | 15NA0015 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-12 | 2015-08-21 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304698 | Santiago NHS | SANTIAGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130115S00045 | 15NA0034 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-29 | 2015-10-05 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte |  | SHS in Carmen, Agusan Del Norte | CARMEN | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 13796560 |  |  | COMPLETED | 1 |  |  | 130115S00077 | 15NA0074 | 2015-12-02 | 2015-12-03
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304683 | Simbalan NHS - Guinabsan NHS Annex | BUENAVISTA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00052 | 15NA0020 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-11-09 | 2015-11-13 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304700 | Tinigbasan NHS | TUBAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00028 | 15NA0016 | 2015-07-21 | 2015-07-23 | 2015-08-03 | 2015-08-13 | 2015-08-24 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 130115S00026 | 15NA0048 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-10-20 | 2015-10-26 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Norte | 304702 | Vinapor NHS | CARMEN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00074 | 15NA0019 | 2015-08-06 | 2015-08-07 | 2015-08-19 | 2015-11-09 | 2015-11-13 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317442 | Afga Nhs | SIBAGAT | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00035 | 15NB0092 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | BAICAMAR CONSTRUCTION AND SUPPLIES, INC.
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304704 | Agusan del Sur National Science HS | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00036 | 15NB0045 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-06 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304737 | Anislagan NHS | SAN LUIS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00074 | 15NB0069 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317444 | Aurora Nhs | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00037 | 15NB0046 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317405 | Azpetia NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8584965.051 |  |  | COMPLETED | 1 |  |  | 130215S00040 | 15NB0080 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-22 | 2015-11-26 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131667 | Bakingking ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2113606.04 |  |  | COMPLETED | 1 |  |  | 130215S00137 | 15NB0117 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317418 | Balit HS | SAN LUIS | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00073 | 15NB0047 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317433 | Buena Gracia Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00033 | 15NB0048 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317440 | Catmonon Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00060 | 15NB0049 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317416 | Causwagan NHS | TALACOGON | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6514337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00032 | 15NB0070 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-22 | 2015-11-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304738 | Cecilia NHS | SAN LUIS | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00071 | 15NB0050 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131973 | Concillo ES | TALACOGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00107 | 15NB0112 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317422 | Corpuz Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00031 | 15NB0051 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131706 | Datu Mankumbate ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00111 | 15NB0114 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304710 | Del Monte NHS | TALACOGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 130215S00030 | 15NB0081 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317411 | Desamparados Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00019 | 15NB0052 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317424 | Duangan Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00075 | 15NB0053 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304712 | Esperanza NHS | ESPERANZA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 130215S00069 | 15NB0082 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304713 | Guadalupe NHS | ESPERANZA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8474965.051 |  |  | COMPLETED | 1 |  |  | 130215S00068 | 15NB0083 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317414 | Hawilian National High School | ESPERANZA | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2680828.124 |  |  | COMPLETED | 1 |  |  | 130215S00067 | 15NB0054 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317432 | Labnig NHS | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00028 | 15NB0055 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304739 | Laminga NHS | SAN LUIS | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3880828.124 |  |  | COMPLETED | 1 |  |  | 130215S00066 | 15NB0096 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-10-31 | 2015-11-17 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304739 | Laminga NHS | SAN LUIS | 1 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3880828.124 |  |  | COMPLETED | 1 |  |  | 130215S00061 | 15NB0097 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-10-31 | 2015-11-17 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304720 | Los Arcos NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9279965.051 |  |  | COMPLETED | 1 |  |  | 130215S00038 | 15NB0084 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-22 | 2015-11-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304722 | Lucena NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8584965.051 |  |  | COMPLETED | 1 |  |  | 130215S00026 | 15NB0085 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304721 | Mabuhay Nhs | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00025 | 15NB0058 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317435 | Maharlika Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00024 | 15NB0063 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | BAICAMAR CONSTRUCTION AND SUPPLIES, INC.
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131987 | Marbon ES | TALACOGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00106 | 15NB0111 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317434 | Marbon Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00023 | 15NB0060 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317423 | Nato Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00065 | 15NB0061 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304726 | New Tubigon National High School of Home Industries | SIBAGAT | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1834740.174 |  |  | COMPLETED | 1 |  |  | 130215S00020 | 15NB0065 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304726 | New Tubigon National High School of Home Industries | SIBAGAT | 1 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1834740.174 |  |  | COMPLETED | 1 |  |  | 130215S00021 | 15NB0066 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317425 | Oro Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00064 | 15NB0062 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-06 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304730 | Patin-ay HS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 130215S00048 | 15NB0086 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304731 | Prosperidad NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5836910.09 |  |  | COMPLETED | 1 |  |  | 130215S00050 | 15NB0095 | 2015-09-04 | 2015-09-08 | 2015-09-22 | 2015-11-11 | 2015-11-16 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 500315 | Sabang Gibong Nhs | TALACOGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00029 | 15NB0064 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | BAICAMAR CONSTRUCTION AND SUPPLIES, INC.
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131687 | Salug ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00139 | 15NB0118 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | ABADA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317441 | Salug Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00063 | 15NB0067 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317430 | San Jose Nhs | PROSPERIDAD (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6549337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00057 | 15NB0071 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304736 | San Luis NHS | SAN LUIS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9699965.051 |  |  | COMPLETED | 1 |  |  | 130215S00098 | 15NB0078 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | MIGO CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131711 | San Toribio ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00109 | 15NB0113 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-18 | 2015-11-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317415 | San Toribio NHS | ESPERANZA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9215965.051 |  |  | COMPLETED | 1 |  |  | 130215S00097 | 15NB0079 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-10-20 | 2015-10-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317404 | San Vicente NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 130215S00056 | 15NB0087 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304740 | SIBAGAT NATIONAL HIGH SCHOOL OF HOME INDUSTRIES | SIBAGAT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 130215S00055 | 15NB0088 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317439 | Sta. Fe Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00062 | 15NB0059 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304749 | Sta. Irene NHS | PROSPERIDAD (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 130215S00054 | 15NB0089 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131889 | Sta. Maria ES | SIBAGAT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00118 | 15NB0116 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-20 | 2015-11-26 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9478965.051 |  |  | COMPLETED | 1 |  |  | 130215S00053 | 15NB0090 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-10-10 | 2015-10-27 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317428 | West Prosperidad Nhs | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00052 | 15NB0057 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304755 | Zillovia NHS | TALACOGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 130215S00039 | 15NB0091 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-10-05 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 130215S00078 | 15NC0118 | 2015-11-23 | 2015-11-27 | 2015-12-08
NC 2015 | TECHVOC (2015) | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4979098.54 |  |  | COMPLETED | 1 |  |  | 130215S00142 | 15NC0069 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131833 | Alegria ES | SAN FRANCISCO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6194337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00119 | 15NC0130 | 2015-10-30 | 2015-11-16 | 2015-11-27 | 2015-12-09
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317413 | Aurora NHS | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00049 | 15NC0021 | 2015-07-30 | 2015-08-12 | 2015-08-18 | 2015-09-01 | 2015-09-10 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00070 | 15NC0022 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 130215S00072 | 15NC0158 | 2015-12-14 | 2015-12-17 | 2015-12-28
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304708 | Binucayan NHS | LORETO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 130215S00047 | 15NC0115 | 2015-12-14 | 2015-12-26 | 2015-12-29
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131813 | Blocking Elementary School | ROSARIO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00124 | 15NC0085 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131815 | Brodecs PS | ROSARIO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00125 | 15NC0084 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131650 | BROOKSIDE ELEMENTARY SCHOOL | BUNAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00105 | 15NC0083 | 2015-09-24 | 2015-10-02 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317426 | Buena Suerte NHS | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00079 | 15NC0023 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304709 | Bunawan National High School | BUNAWAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130215S00046 | 15NC0116 | 2015-12-09 | 2015-12-11 | 2015-12-23
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131836 | Das-agan ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00129 | 15NC0087 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3280828.124 |  |  | COMPLETED | 1 |  |  | 130215S00087 | 15NC0038 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-15 | 2015-09-24 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3280828.124 |  |  | COMPLETED | 1 |  |  | 130215S00088 | 15NC0039 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-15 | 2015-09-24 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 212057 | DATU MADAGNAS PS | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00116 | 15NC0086 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131902 | Del Monte ES | VERUELA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00130 | 15NC0078 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304711 | Democrito O. Plaza MHS | SAN FRANCISCO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6639337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00086 | 15NC0149 | 2015-11-23 | 2015-11-27 | 2015-12-08
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131720 | Don Flaviano I ES | LORETO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00108 | 15NC0098 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 212014 | J.A. Morales ES | ROSARIO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00114 | 15NC0079 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317421 | Johnson Nhs | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00045 | 15NC0024 | 2015-07-30 | 2015-08-12 | 2015-08-18 | 2015-09-01 | 2015-09-10 | AGUERO CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131795 | Jose U. Cortes ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00123 | 15NC0080 | 2015-10-30 | 2015-11-16
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131821 | Jugo Chua Sr. ES | ROSARIO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6194337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00136 | 15NC0150 | 2015-11-20 | 2015-11-27
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317409 | Kapatungan NHS | TRENTO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00042 | 15NC0025 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304714 | Kasapa NHS | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00041 | 15NC0026 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317447 | KAUSWAGAN NHS | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00058 | 15NC0027 | 2015-07-30 | 2015-08-06 | 2015-08-12 | 2015-09-01 | 2015-09-10 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317406 | La Fortuna NHS | VERUELA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130215S00027 | 15NC0110
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304716 | La Paz NHS | LA PAZ | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3030828.124 |  |  | COMPLETED | 1 |  |  |  | 130215S00084 |  | 2015-08-06 | 2015-08-14 | 2015-08-27 | 2015-09-15 | 42271
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304716 | La Paz NHS | LA PAZ | 2 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 3030828.124 |  |  | COMPLETED | 1 |  |  |  | 130215S00085 |  | 2015-08-06 | 2015-08-14 | 2015-08-27 | 2015-09-15 | 42271
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 132003 | Langkila-an ES | TRENTO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00133 | 15NC0081 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304717 | Lapinigan NHS | SAN FRANCISCO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 130215S00083 | 15NC0111 | 2015-12-14 | 2015-12-22 | 2015-12-23
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317403 | Lapinigan NHS - New Visayas Ext. | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00082 | 15NC0028 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304718 | Libertad NHS | BUNAWAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 130215S00051
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131758 | Log Pond 3 PS | LA PAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2263606.04 |  |  | COMPLETED | 1 |  |  | 130215S00120 | 15NC0090 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304719 | Loreto NHS | LORETO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1 |  |  | 130215S00022 | 15NC0112 | 2015-12-03 | 2015-12-11 | 2015-12-23
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317431 | Magaud Nhs | LORETO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6429337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00059
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131762 | Magboya ES | LA PAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00121 | 15NC0082 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304741 | Magsaysay Nhs | SIBAGAT | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00017 | 15NB0056 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131822 | Maligaya ES | ROSARIO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00127 | 15NC0073 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131925 | Malipayon ES | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00132 | 15NC0074 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 212024 | Mambagongon PS | LA PAZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2263606.04 |  |  | COMPLETED | 1 |  |  | 130215S00138 | 15NC0089 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 132005 | Manat ES | TRENTO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6194337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00134 | 15NC0159 | 2015-12-14 | 2015-12-17 | 2015-12-28
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317407 | Manat NHS | TRENTO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00016 | 15NC0148 | 2015-11-23 | 2015-11-27 | 2015-12-08
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131733 | Manawe ES | LORETO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00100 | 15NC0097 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304748 | Marfil NHS | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00081 | 15NC0029 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 212067 | MAXIMO MAGADAN MEMORIAL PS | LORETO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00128 | 15NC0075 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 132006 | Melfreda ES | TRENTO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00135 | 15NC0076 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131735 | Moto ES | LORETO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00110 | 15NC0077 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317429 | Novele Nhs | ROSARIO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00076 | 15NC0030 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-01 | 2015-09-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131737 | Nueva Gracia ES | LORETO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00101 | 15NC0096 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317427 | Nueva Gracia Nhs | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00009 | 15NC0031 | 2015-07-30 | 2015-08-06 | 2015-08-18 | 2015-09-03 | 2015-09-14 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304743 | Padiay Nhs | SIBAGAT | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00008 | 15NB0068 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | ABADA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317401 | Panagangan NHS | LA PAZ | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 130215S00080 | 15NC0113
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 132007 | Pangyan ES | TRENTO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00112 | 15NC0071 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131765 | Pinamoyanan elementary School | LA PAZ | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00122 | 15NC0095 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317412 | Pulang Lupa NHS | TRENTO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00096 | 15NC0157 | 2015-12-14 | 2015-12-28 | 2015-12-29
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317437 | Salvacion Nhs | TRENTO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00007 | 15NC0032 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304733 | Sampaguita NHS | VERUELA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130215S00006
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304734 | San Isidro NHS | LORETO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8339965.051 |  |  | COMPLETED | 1 |  |  | 130215S00005 | 15NC00114
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317443 | San Isidro Nhs | TRENTO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00034 | 15NC0033 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131661 | San Marcos ES | BUNAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00104 | 15NC0092 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131741 | San Mariano ES | LORETO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00115 | 15NC0072 | 2015-09-28 | 2015-10-02 | 2015-10-13 | 2015-10-27 | 2015-11-05 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317438 | San Roque Nhs | TRENTO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00003 | 15NC0034 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317446 | San Vicente Nhs | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00001 | 15NC0035 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317419 | Sayon Nhs | SANTA JOSEFA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6499337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00002 | 15NC0162
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 212013 | Singanan ES | BUNAWAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00113 | 15NC0094 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317408 | Sinobong NHS | VERUELA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130215S00004
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131920 | Sta. Cruz ES | VERUELA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2827592.44 |  |  | COMPLETED | 1 |  |  | 130215S00131 | 15NC0093 | 2015-09-30 | 2015-10-09 | 2015-10-20 | 2015-11-04 | 2015-11-16 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 130215S00089 | 15NC0146 | 2015-11-23 | 2015-11-27 | 2015-12-08
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304750 | Sta. Josefa NHS | SANTA JOSEFA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 130215S00010 | 15NC0117
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304705 | Sta. Maria NHS | TRENTO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 130215S00018 | 15NC0147 | 2015-11-23 | 2015-11-27 | 2015-12-08
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304751 | Sto. Tomas NHS | LORETO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 130215S00011 | 15NC0109 | 2015-12-15 | 2015-12-18 | 2015-12-29
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130215S00012
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131664 | Upper Consuelo I ES | BUNAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2013606.04 |  |  | COMPLETED | 1 |  |  | 130215S00103 | 15NC0091 | 2015-09-30 | 2015-10-02 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304754 | Veruela NHS | VERUELA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130215S00013
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 317445 | Veruela NHS Annex - Nueva Era HS | VERUELA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00014 | 15NC0036 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Agusan del Sur | 304715 | Waloe NHS | LORETO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130215S00015 | 15NC0037 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-09-03 | 2015-09-14 | AGUERO CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Agusan del Sur | 131665 | West Bunawan CES | BUNAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1 |  |  | 130215S00126 | 15NC0088 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-29 | 2015-11-10 | DDS BUILDERS
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304707 | Bayugan NCHS | CITY OF BAYUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 130215S00095 | 15NB0042 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-02 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304729 | Calaitan NHS | CITY OF BAYUGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 3212592.44 |  |  | COMPLETED | 1 |  |  | 130215S00090 | 15NB0043 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304723 | Marcelina NHS | CITY OF BAYUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 130215S00094 | 15NB0074 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-10-20 | 2015-10-27 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304724 | Mount Olive National High School | CITY OF BAYUGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 7239337.6381 |  |  | COMPLETED | 1 |  |  | 130215S00099 | 15NB0075 | 2015-08-19 | 2015-08-20 | 2015-10-07 | 2015-11-18 | 2015-11-26 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304728 | Noli National High School | CITY OF BAYUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 130215S00093 | 15NB0044 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-09-05 | 2015-09-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Bayugan City | 131624 | Salvacion CES | CITY OF BAYUGAN | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12621310.093 |  |  | COMPLETED | 1 |  |  | 130215S00102 | 15NB0110 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304732 | Salvacion NHS | CITY OF BAYUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8864965.051 |  |  | COMPLETED | 1 |  |  | 130215S00092 | 15NB0076 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-15 | DATREBIL CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Bayugan City | 131639 | San Agustin ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130215S00117 | 15NB0115 | 2015-09-23 | 2015-09-24 | 2015-10-07 | 2015-11-21 | 2015-11-26 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City | 304735 | SAN JUAN NATIONAL HIGH SCHOOL | CITY OF BAYUGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9564965.051 |  |  | COMPLETED | 1 |  |  | 130215S00091 | 15NB0077 | 2015-08-19 | 2015-08-20 | 2015-09-02 | 2015-09-30 | 2015-10-27 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bayugan City |  | SHS in Bayugan City | CITY OF BAYUGAN | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 130215S00140 | 15NB0132 | 2015-12-04 | 2015-12-07 | 2015-12-21
NC 2015 | SHS (2015) | CARAGA | Bayugan City |  | SHS in Bayugan City | CITY OF BAYUGAN | 1 |  | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 130215S00141 | 15NB0133 | 2015-11-28 | 2015-12-07 | 2015-12-21
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00023 | 15NI0073 | 2015-12-01 | 2015-12-13 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00022 | 15NI0040 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | TWINA BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Bislig City | 132614 | DELOT ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00129
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00019 | 15NI0049 | 2015-10-08 | 2015-10-09 | 2015-10-21 | 2015-10-28 | 2015-11-02 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Bislig City | 322505 | Mabog NHS | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00021 | 15NI0022 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 |  |  | 130515S00018 | 15NI0072 | 2015-11-30 | 2015-12-13 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304919 | Mangagoy NHS | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 9356615.051 |  |  | COMPLETED | 1 |  |  | 130515S00025 | 15NI0042 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | O. G. SANTOS CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Bislig City | 132621 | Mantaban ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00135
NC 2015 | K10 (2015) | CARAGA | Bislig City | 132622 | Mantuyom ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00126
NC 2015 | SHS (2015) | CARAGA | Bislig City |  | Proposed Stand-Alone SHS 1 | CITY OF BISLIG | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 5 | 13396954 |  |  | COMPLETED | 1 |  |  | 130515S00102
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304869 | Sikahoy NHS | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2766106 |  |  | COMPLETED | 1 |  |  | 130515S00103 | 15NI0037 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-13 | 2015-10-16 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Bislig City | 304917 | TABON M. ESTRELLA NATIONAL HIGH SCHOOL | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 130515S00020 | 15NI0041 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304756 | Agusan NHS | BUTUAN CITY (Capital) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15371327.92 |  |  | COMPLETED | 1 |  |  | 130115S00068 | 15ND0084 | 2015-10-16 | 2015-10-16 | 2015-10-29 | 2015-11-09 | 2015-11-20 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304756 | Agusan NHS | BUTUAN CITY (Capital) | 1 |  | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21703013.45 |  |  | COMPLETED | 1 |  |  | 130115S00072 | 15ND0085 | 2015-10-30 | 2015-10-30 | 2015-11-11 | 2015-11-24 | 2015-12-21 | C ZARLES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130115S00067 | 15ND0054 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-23 | 2015-10-20 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317517 | Alviola ISS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00061 | 15ND0043 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-09-02 | 2015-10-20 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8474965.051 |  |  | COMPLETED | 1 |  |  | 130115S00057 | 15ND0061 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | JOSELLE CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317511 | Ampayon Integrated Secondary School | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130115S00070 | 15ND0059 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | REY ROSE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304765 | Anticala NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8484965.051 |  |  | COMPLETED | 1 |  |  | 130115S00064 | 15ND0062 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-23 | 2015-10-20 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317502 | Aupagan ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00041 | 15ND0032 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-10 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317513 | Bagong Silang ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00036 | 15ND0026 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-26 | REYROSE CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 130115S00065 | 15ND0051 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-21 | 2015-10-20 | JOAN CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Butuan City | 317503 | Basag Integrated Secondary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 130115S00108 | 15ND0063 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-10-19 | 2015-11-17 | KELVIN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8384965.051 |  |  | COMPLETED | 1 |  |  | 130115S00060 | 15ND0056 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-21 | 2015-10-20 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 130115S00053 | 15ND0052 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | TWINA BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132113 | Consuelo ES | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 130115S00078 | 15ND0048 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-11-02 | JOSELLE CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317507 | Consuelo ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00037 | 15ND0027 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-26 | JOSELLE CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132031 | Daan Taligaman Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00104 | 15ND0064 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132087 | Danapa ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00081 | 15ND0069 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-09-08 | 2015-09-28 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132071 | Dona Josefa Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00085 | 15ND0067 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | C & R CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317510 | Kinamlutan ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00040 | 15ND0033 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-07 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 500317 | La Soledad ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00042 | 15ND0034 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-28 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317506 | La Trinidad ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00012 | 15ND0035 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-08-26 | JOSELLE CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304763 | Libertad NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 130115S00056 | 15ND0053 | 2015-08-12 | 2015-08-12 | 2015-08-25 | 2015-09-14 | 2015-10-20 | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304764 | Los Angeles NHS | BUTUAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2922592.44 |  |  | COMPLETED | 1 |  |  | 130115S00071 | 15ND0039 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-08 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304764 | Los Angeles NHS | BUTUAN CITY (Capital) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2922592.44 |  |  | COMPLETED | 1 |  |  | 130115S00069 | 15ND0039 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-09 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304766 | Lumbocan NHS | BUTUAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2832592.44 |  |  | COMPLETED | 1 |  |  | 130115S00073 | 15ND0038 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-12 | 2015-09-10 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304766 | Lumbocan NHS | BUTUAN CITY (Capital) | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2832592.44 |  |  | COMPLETED | 1 |  |  | 130115S00058 | 15ND0038 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-11 | 2015-09-10 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304767 | Maguinda NHS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6599337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00054 | 15ND0045 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-10-20 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317505 | Maibu ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00010 | 15ND0028 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-09-10 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 500319 | Manila de Bugabos ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00011 | 15ND0029 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-26 | ROIM BUILDERS & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132078 | Masago Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00079 | 15ND0068 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317515 | Pareja ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00021 | 15ND0036 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-03 | KELVIN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317520 | Pedro D. Duncano ISS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00055 | 15ND0046 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-10-20 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132059 | Pedro-Victorina Calo Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00098 | 15ND0065 | 2015-08-14 | 2015-08-14 | 2015-08-27 | 2015-09-08 | 2015-09-28 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317521 | Pigdaulan NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8384965.051 |  |  | COMPLETED | 1 |  |  | 130115S00066 | 15ND0057 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | GIOVANNI CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317508 | Pinamanculan ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00038 | 15ND0037 | 2015-07-15 | 2015-07-15 | 2015-07-28 | 2015-08-07 | 2015-09-09 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304769 | San Vicente NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130115S00059 | 15ND0060 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-23 | 2015-10-20 | L.C. TING CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132050 | Silad-Mahogany Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00096 | 15ND0044 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-11-02 | BAICAMAR CONSTRUCTION AND SUPPLIES, INC.
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304770 | Sumile NHS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00039 | 15ND0030 | 2015-08-05 | 2015-08-06 | 2015-08-18 | 2015-08-25 | 2015-09-28 | KELVIN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Butuan City | 317522 | Tagkiling Tribal ISS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130115S00003 | 15ND0031 | 2015-07-10 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-09-10 | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | K10 (2015) | CARAGA | Butuan City | 132082 | Tagpulangi ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00080 | 15ND0066 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130115S00063 | 15ND0055 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-21 | 2015-10-20 | JOAN CONSTRUCTION
NC 2015 | TECHVOC (2015) | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1 |  |  | 130115S00112 | 15ND0077 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-30 | 2015-10-27 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 130115S00062 | 15ND0058 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-14 | 2015-10-20 | FLORIANE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Cabadbaran City | 131577 | Alfonso B. Dagani ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00088 | 15NA0049 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-28 | 2015-10-14 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | CITY OF CABADBARAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 130115S00007 | 15NA0038 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-20 | 2015-10-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 130115S00008 | 15NA0039 | 2015-08-27 | 2015-08-28 | 2015-09-18 | 2015-10-20 | 2015-10-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | SHS (2015) | CARAGA | Cabadbaran City | 317307 | Del Pilar NHS (Calamba NHS Annex) | CITY OF CABADBARAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1 |  |  | 130115S00009 | 15NA0023 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-10-20 | 2015-10-26 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Cabadbaran City | 317312 | La Union NHS (Calamba NHS Annex) | CITY OF CABADBARAN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8739965 |  |  | COMPLETED | 1 |  |  | 130115S00109 | 15NA0061 | 2015-09-22 | 2015-09-23 | 2015-10-05 | 2015-12-28 |  | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2015 | K10 (2015) | CARAGA | Cabadbaran City | 131524 | Mahaba ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00082 | 15NA0049 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-28 | 2015-10-14 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Cabadbaran City | 131527 | Pirada ES | CITY OF CABADBARAN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 130115S00083 | 15NA0057 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-12-18 | 2015-12-23 | TWO ACES CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Cabadbaran City | 131529 | Tolosa Central Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130115S00084 | 15NA0049 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-28 | 2015-10-14 | 3C SL CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304808 | Albor NHS | LIBJO (ALBOR) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 |  |  | 130815S00007 | 15NE0045 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304809 | Albor NHS - Osmena NHS Annex | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00016 | 1308-15-S-00016 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304823 | Cab-ilan NHS | DINAGAT | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00009 | 15NE0037 | 2015-09-09 | 2015-09-11
NC 2015 | SHS (2015) | CARAGA | Dinagat Island |  | Cagdianao NHS | CAGDIANAO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130815S00006 | 15NE0033 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS | SLOW ACCOMPLISHMENTS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2800828.124 |  |  | COMPLETED | 1 |  |  | 130815S00027 | 15NE0040 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304816 | Del Pilar NHS | CAGDIANAO | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 130815S00005 | 1308-15-S-00005 | 2015-11-19 | 2015-11-20 | 2015-12-02 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2765828.124 |  |  | COMPLETED | 1 |  |  | 130815S00010 | 15NE0038 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2765828.124 |  |  | COMPLETED | 1 |  |  | 130815S00004 | 15NE0039 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 130815S00028 | 15NE0028 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-08-28 | 2015-09-23 | WERR CORPORATION INTERNATIONAL
NC 2015 | TECHVOC (2015) | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5379098.54 |  |  | COMPLETED | 1 |  |  | 130815S00033 | 15NE0066 | 2015-10-29 | 2015-11-03 | 2015-11-13 | 2015-12-02 |  | CARTESIAN BUILDERS
NC 2015 | K10 (2015) | CARAGA | Dinagat Island | 132490 | Dona Helen ES | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130815S00032 | 15NE0061 | 2015-09-17 | 2015-09-18 | 2015-09-30 | 2015-10-19 | 2015-11-10 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324403 | Edera NHS | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00017 | 1308-15-S-00017 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304827 | Liberty NHS | LORETO | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00035 | 1308-15-S-00035 | 2015-11-26 | 2015-11-27 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00018 | 1308-15-S-00018 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324407 | Malinao NHS | TUBAJON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 130815S00029 | 15NE0064 | 2015-11-17 | 2015-11-20 | 2015-12-01 | 2015-12-22
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304836 | Melgar NHS | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00019 | 1308-15-S-00019 | 2015-11-26 | 2015-11-27 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324404 | New Nazareth NHS Annex | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00020 | 1308-15-S-00020 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324405 | Panamaon NHS Annex | LORETO | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00034 | 1308-15-S-00034 | 2015-11-26 | 2015-11-27 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304839 | Plaridel NHS | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1939740.174 |  |  | COMPLETED | 1 |  |  | 130815S00002 | 1308-15-S-00002 | 2015-11-26 | 2015-11-27 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304839 | Plaridel NHS | LIBJO (ALBOR) | 0 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1939740.174 |  |  | COMPLETED | 1 |  |  | 130815S00003 | 1308-15-S-00003 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00021 | 15NE0035 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304840 | R. E. Ecleo, Sr. NHS | CAGDIANAO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 130815S00008 | 15NE0027 | 2015-09-08 | 2015-09-09 | 2015-09-30 | 2015-10-19 | 2015-11-10 | JTA BUILDERS | ABANDONED BY THE SUBCONTRACTOR FOR ALMOST 2 YEARS, YET NO TERMINATION OF THE CONTRACT
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304841 | Rizal NHS | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6489337.6381 |  |  | COMPLETED | 1 |  |  | 130815S00011 | 15NE0036 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-28 | 2015-09-23 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304842 | Rizal NHS - Puerto Princesa - Moleta NHS Annex | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00022 | 1308-15-S-00022 | 2015-11-25 | 2015-11-26 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 317801 | Rosita National High School | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130815S00023 | 15NE0043 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304810 | San Jose NHS | LIBJO (ALBOR) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 |  |  | 130815S00012 | 15NE0044 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-10-08 | 2015-10-27 | JTA BUILDERS | ABANDONED BY THE SUBCONTRACTOR FOR ALMOST 2 YEARS, YET NO TERMINATION OF THE CONTRACT
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304844 | Sering NHS | BASILISA (RIZAL) | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2820828.124 |  |  | COMPLETED | 1 |  |  | 130815S00024 | 1308-15-S-00024 | 2015-11-26 | 2015-11-27 |  |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island |  | SHS in Loreto, Dinagat Island | LORETO | 0 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 5 | 12888675 |  |  | COMPLETED | 1 |  |  | 130815S00030 | 15NE0063 | 2015-10-15 | 2015-10-19 | 2015-10-30 | 2015-11-18
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1 |  |  | 130815S00013 | 15NE0031 | 2015-08-03 | 2015-08-04 | 2015-08-17 | 2015-08-28 | 2015-09-23 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304852 | Tag-abaca NHS - Rita-Glenda NHS Annex | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 130815S00026 | 15NE0034 | 2015-08-05 | 2015-08-17 | 2015-08-18 | 2015-08-28 | 2015-09-23 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 |  |  | 130815S00014 | 1308-15-S-00014 | 2015-11-25 | 2015-12-04 | 2015-12-14 |  |  | By Administration
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 317805 | Tubajon NHS - Mabini NHS Annex | TUBAJON | 0 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3684886.575 |  |  | COMPLETED | 1 |  |  | 130815S00015 | 15NE0053 | 2015-10-01 | 2015-10-05 | 2015-10-16 | 2015-10-30 | 2015-11-13 | WERR CORPORATION INTERNATIONAL
NC 2015 | SHS (2015) | CARAGA | Dinagat Island | 317802 | Valencia NHS | CAGDIANAO | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6609337.6381 |  |  | COMPLETED | 1 |  |  | 130815S00025 | 1308-15-S-00025 | 2015-11-19 | 2015-11-20 | 2015-12-02 |  |  | By Administration
NC 2015 | K10 (2015) | CARAGA | Dinagat Island | 132512 | Villa Ecleo ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130815S00031 | 15NE0060 | 2015-10-20 | 2015-10-23
NC 2015 | K10 (2015) | CARAGA | Siargao | 132145 | Anajawan Elementary School | GENERAL LUNA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2288606.04 |  |  | COMPLETED | 1 |  |  | 130715S00087 | 15NG0035 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | K10 (2015) | CARAGA | Siargao | 213001 | Atoyay ES | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 130715S00078 | 15NG0027 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | K10 (2015) | CARAGA | Siargao | 132216 | Bitaug PS | BURGOS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 130715S00079 | 15NG0028 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304773 | Burgos NHS | BURGOS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00052 | 1307-15-S-00052
NC 2015 | K10 (2015) | CARAGA | Siargao | 132166 | Cancohoy ES | DEL CARMEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 6805184.88 |  |  | COMPLETED | 1 |  |  | 130715S00084 | 1307-15-S-00084
NC 2015 | K10 (2015) | CARAGA | Siargao | 132231 | Cancohoy ES | SOCORRO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 6805184.88 |  |  | COMPLETED | 1 |  |  | 130715S00085 | 1307-15-S-00085
NC 2015 | SHS (2015) | CARAGA | Siargao | 304780 | Caridad NHS | PILAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6819338 |  |  | COMPLETED | 1 |  |  | 130715S00075 | 1307-15-S-00075
NC 2015 | SHS (2015) | CARAGA | Siargao | 304775 | Consolacion NHS | DAPA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 130715S00051 | 15NG0012 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | JGS CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Siargao | 317606 | Dagohoy National High School-Annex | DAPA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2238606 |  |  | COMPLETED | 1 |  |  | 130715S00095 | 15NG0034 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304774 | Dapa NHS | DAPA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 130715S00050 | 1307-15-S-00050
NC 2015 | SHS (2015) | CARAGA | Siargao | 304783 | Del Carmen NHS | DEL CARMEN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 130715S00048 | 1307-15-S-00048
NC 2015 | K10 (2015) | CARAGA | Siargao | 132221 | Don. Albino Taruc Memorial ES | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 130715S00091 | 15NG0026 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304777 | Gen Luna NHS | GENERAL LUNA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 130715S00047 | 1307-15-S-00047 | [6 empty] | Rectification
NC 2015 | SHS (2015) | CARAGA | Siargao | 317601 | Gen. Luna NHS - Suyangan NHS Annex | GENERAL LUNA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00004 | 15NG0009 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304786 | Libertad NHS | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 130715S00055 | 15NG0013 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Siargao | 132211 | Magsaysay ES | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2338606.04 |  |  | COMPLETED | 1 |  |  | 130715S00083 | 15NG0029 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304776 | Mariano Matugas MNHS | DEL CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2178606.04 |  |  | COMPLETED | 1 |  |  | 130715S00046 | 15NG0013 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | DT&C CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Siargao | 132234 | Nueva Estrella CES | SOCORRO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8964965.051 |  |  | COMPLETED | 1 |  |  | 130715S00090 | 1307-15-S-00090
NC 2015 | SHS (2015) | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2158606.04 |  |  | COMPLETED | 1 |  |  | 130715S00045 | 15NG0014 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 317605 | Oguing Navarro Mem. NHS - Annex | DEL CARMEN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6489337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00049 | 1307-15-S-00049
NC 2015 | SHS (2015) | CARAGA | Siargao | 304790 | Pamosaingan NHS | SOCORRO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00053 | 1307-15-S-00053
NC 2015 | SHS (2015) | CARAGA | Siargao | 304779 | Pilar NHS | PILAR | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8814965.051 |  |  | COMPLETED | 1 |  |  | 130715S00057 | 1307-15-S-00057
NC 2015 | K10 (2015) | CARAGA | Siargao | 132212 | Rizal ES | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 130715S00082 | 15NG0030 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304784 | Roxas NHS | SAN ISIDRO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6559337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00064 | 1307-15-S-00064
NC 2015 | K10 (2015) | CARAGA | Siargao | 132230 | San Benito CES | SAN BENITO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8814965.051 |  |  | REVERTED | 0 |  |  | 130715S00086 | 1307-15-S-00086
NC 2015 | K10 (2015) | CARAGA | Siargao | 132230 | San Benito CES | SAN BENITO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3252592.44 |  |  | COMPLETED | 1 |  |  | 130715S00094 | 15NG0025 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304781 | San Benito NHS | SAN BENITO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00063 | 1307-15-S-00063 | [6 empty] | Rectification
NC 2015 | K10 (2015) | CARAGA | Siargao | 132142 | San Carlos ES | DAPA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2338606.04 |  |  | COMPLETED | 1 |  |  | 130715S00088 | 15NG0031 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304782 | San Isidro NHS | SAN ISIDRO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 |  |  | 130715S00038 | 1307-15-S-00038 | [6 empty] | Slow paced construction. Lack of manpower and materials resources.
NC 2015 | K10 (2015) | CARAGA | Siargao | 132238 | San Roque Community ES | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 130715S00089 | 15NG0033 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 130715S00062 | 1307-15-S-00062
NC 2015 | SHS (2015) | CARAGA | Siargao | 317604 | Siargao Nat'l. Science HS | DAPA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00013 | 1307-15-S-00013
NC 2015 | SHS (2015) | CARAGA | Siargao | 304788 | Socorro National HS | SOCORRO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8634965.051 |  |  | Terminated | 0 |  |  | 130715S00058 | 1307-15-S-00058 | [6 empty] | The project was terminated. However, the project was continued thru change of creditor and was completed last March 4, 2021.
NC 2015 | SHS (2015) | CARAGA | Siargao | 317602 | Socorro NHS - Atoyay NHS Annex | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2178606.04 |  |  | COMPLETED | 1 |  |  | 130715S00061 | 15NG0014 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304788 | Sta. Fe NHS | SOCORRO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6949338 |  |  | COMPLETED | 1 |  |  | 130715S00074 | 1307-15-S-00074
NC 2015 | K10 (2015) | CARAGA | Siargao | 132241 | Sudlon ES | SOCORRO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 130715S00092 | 15NG0032 | 2015-12-01 | 2015-12-03 | 2015-12-15
NC 2015 | SHS (2015) | CARAGA | Siargao | 304791 | Union NHS | DAPA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 130715S00054 | 15NG0012 | 2015-08-10 | 2015-08-14 | 2015-08-25 | 2015-09-14 | 2015-09-21 | JGS CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00016 | 15NF0044 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-14 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304800 | Anomar NHS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 130715S00012 | 130715S00012 | 2015-11-15 | 2015-11-19 | 2015-12-02 | 2015-12-08
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317702 | Cantiasay NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2368606 |  |  | COMPLETED | 1 |  |  | 130715S00071 | 15NF0070 | 2015-10-20 | 2015-10-30 | 2015-11-04 | 2015-11-10 | 2015-12-01 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304794 | Caraga Regional Science HS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00011 | 15NF0060 | 2015-10-07 | 2015-10-08 | 2015-10-22 | 2015-11-11 | 2015-12-14 | AMA CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304803 | Day-asan NHS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 |  |  | 130715S00010 | 15NF0058 | 2015-10-07 | 2015-10-08 | 2015-10-22 | 2015-11-03 | 2015-11-19 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00009 | 15NF0059 | 2015-10-07 | 2015-10-08 | 2015-10-22 | 2015-11-03 | 2015-11-12 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304792 | Juan P. Cedro, Sr. MHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2118606 |  |  | COMPLETED | 1 |  |  | 130715S00073 | 15NF0082 | 2015-10-29 | 2015-10-30 | 2015-11-11 | 2015-11-20 | 2015-12-11 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317703 | Libuac NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2278606 |  |  | COMPLETED | 1 |  |  | 130715S00069 | 15NF0069 | 2015-10-20 | 2015-10-30 | 2015-11-04 | 2015-11-10 | 2015-12-01 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317704 | Lipata National High School - Annex | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 9714965 |  |  | COMPLETED | 1 |  |  | 130715S00070 | 130715S00070
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317706 | Manjagao NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2318606 |  |  | COMPLETED | 1 |  |  | 130715S00068 | 15NF0084 | 2015-10-29 | 2015-10-30 | 2015-11-11 | 2015-11-18 | 2015-12-08 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304799 | Mat-i NHS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130715S00008 | 130715S00008 | 2015-11-19 | 2015-11-20 | 2015-12-02 | 2015-12-08
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304804 | Nonoc NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 2364740.174 |  |  | COMPLETED | 1 |  |  | 130715S00006 | 130715S00006 | 2015-07-29 | 2015-07-30 | 2015-08-11
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304804 | Nonoc NHS - Annex | SURIGAO CITY (Capital) | 2 |  | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00007 | 130715S00007 | 2015-07-29 | 2015-07-30 | 2015-08-11
NC 2015 | K10 (2015) | CARAGA | Surigao City | 132270 | Roxas ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 130715S00093 | 15NF0054 | 2015-10-05 | 2015-10-07 | 2015-10-23 | 2015-11-03 | 2015-11-19 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304807 | San Jose NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00003 | 15NF0045 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-14 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2442377.5407 |  |  | COMPLETED | 1 |  |  | 130715S00096 | 130715S00096 | 2015-11-19 | 2015-11-20 | 2015-12-02 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 |  |  | 130715S00005 | 130715S00005 | 2015-11-19 | 2015-11-20 | 2015-12-02 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317701 | Taft NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 130715S00015 | 130715S00015 | 2015-11-23 | 2015-11-25 | 2015-12-08 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304805 | Talisay NHS - Annex | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2118606 |  |  | COMPLETED | 1 |  |  | 130715S00072 | 15NF0071 | 2015-10-20 | 2015-10-30 | 2015-11-04 | 2015-11-10 | 2015-12-01 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 317707 | Wilfredo D. Rafols Mem. NHS | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1 |  |  | 130715S00022 | 15NF0030 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-10-07 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao City | 304806 | Zaragoza NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2178606 |  |  | COMPLETED | 1 |  |  | 130715S00077 | 15NF0083 | 2015-10-29 | 2015-10-30 | 2015-11-11 | 2015-11-20 | 2015-12-08 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00043 | 15NF0072 | 2015-10-20 | 2015-10-22 | 2015-11-04 | 2015-11-11 | 2015-12-01 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 130715S00032 | 130715S00032 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-10
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00034 | 15NF0038 | 2015-07-19 | 2015-07-23 | 2015-08-03 | 2015-09-09 | 2015-09-28 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Surigao del Norte | 214005 | Baliw ES | BACUAG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130715S00080 | 15NF0055 | 2015-10-05 | 2015-10-07 | 2015-10-22 | 2015-11-03 | 2015-12-01 | JMT CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304832 | Bunyasan NHS | MALIMONO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00037 | 15NF0064 | 2015-10-12 | 2015-10-14 | 2015-10-30 | 2015-11-03 | 2015-11-17 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00036 | 15NF0081 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-18 | 2015-12-18 | ASJ BUILDERS
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304818 | Cantapoy NHS | MALIMONO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00027 | 15NF0035 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-08-24 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317810 | Cawilan NHS-Annex | TAGANA-AN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6919338 |  |  | COMPLETED | 1 |  |  | 130715S00066 | 15NF0106 | 2015-11-23 | 2015-12-05 | 2015-12-08 | 2015-12-14 |  | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 130715S00031 | 15NF0068 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-12-01 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS - Annex (TS PSMHS) | SISON | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00030 | 15NF0037 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-12 | 2015-08-28 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 130715S00020 | 15NF0066 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-09 | 2015-12-07 | AMA CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317804 | GNSHI - Lasicam-Perral NHS-Annex | GIGAQUIT | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00029 | 15NF0010(G) | 2015-07-22 | 2015-07-23 | 2015-10-22 | 2015-10-28 | 2015-10-30 | By Administration
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304838 | Lakandula NHS | PLACER | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00014 | 15NF0039 | 2015-07-22 | 2015-07-23 | 2015-08-04 | 2015-08-12 | 2015-09-04 | JMT CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00060 | 15NF0062 | 2015-10-12 | 2015-10-14 | 2015-10-30 | 2015-11-18 | 2015-12-01 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130715S00033 | 15NF0065 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-12-11 | GICAR CONSTRUCTION, INC.
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304833 | Malimono NHS | MALIMONO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00026 | 15NFF0034 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-08-24 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304831 | Masgad NHS | MALIMONO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00025 | 15NF0033 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-08-24 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304834 | Matin-ao NHS | MAINIT | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00024 | 15NF0075 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-09 | 2015-12-01 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304835 | Matin-ao NHS - Hacienda NHS Annex | MAINIT | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00018 | 15NF0079 | 2015-10-28 | 2015-10-30 | 2015-11-10 | 2015-11-16 | 2015-12-01 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304830 | Paco NHS | MAINIT | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00056 | 15NF0063 | 2015-10-12 | 2015-10-14 | 2015-10-30 | 2015-11-10 | 2015-12-01 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317807 | Pananay-an NHS - Annex (Placer NHS) | PLACER | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6619338 |  |  | COMPLETED | 1 |  |  | 130715S00067 | 15NF0107 | 2015-11-23 | 2015-12-05 | 2015-12-08 | 2015-12-14 |  | CARTESIAN BUILDERS
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317806 | Payapag NHS - Annex (Campo NHS) | BACUAG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6499337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00059 | 15NF080 | 2015-10-28 | 2015-10-30 | 2015-11-10 | 2015-11-18 | 2015-12-14 | JMT CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304819 | Pili National High School | MALIMONO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00019 | 15NF0032 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-08-24 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 130715S00042 | 15NF0077 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-10 | 2015-12-01 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00021 | 15NF0074 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-10 | 2015-12-07 | CARTESIAN BUILDERS
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte |  | SHS in Alegria, Surigao del Norte | ALEGRIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 9844965 |  |  | COMPLETED | 1 |  |  | 130715S00076 | 130715S00076
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10917342.5917 |  |  | COMPLETED | 1 |  |  | 130715S00035 | 15NF0057 | 2015-10-05 | 2015-10-08 | 2015-10-22 | 2015-11-03 | 2015-12-01 | AMA CONSTRUCTION
NC 2015 | TECHVOC (2015) | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | Construction of 1UNIT Standard Technical and Vocational Building | 2015 TVL | 2469549.27 |  |  | COMPLETED | 1 |  |  | 130715S00097 | 15NF0085 | 2015-10-28 | 2015-10-30 | 2015-11-11 | 2015-11-20 | 2015-12-01 | R.F. VARQUEZ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304849 | T.S Pantilo, Sr. MNHS | SISON | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00041 | 130715S00041 | 2015-10-28 | 2015-10-30 | 2015-11-10 | 2015-11-18
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304850 | T.S Pantilo, Sr. MNHS - Mayag NHS Annex | SISON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 130715S00065 | 15NF0042 | 2015-07-29 | 2015-07-30 | 2015-08-11 | 2015-08-19 | 2015-09-14 | JMT CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00023 | 130715S00023 | 2015-11-15 | 2015-11-19
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304821 | Taganito NHS | CLAVER | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130715S00017 | 130715S00017 | 2015-11-15 | 2015-11-19 | 2015-12-01 | 2015-12-08
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 317809 | Talavera NHS - Annex (Tagana-an NHS) | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130715S00028 | 15NF0031 | 2015-07-19 | 2015-07-22 | 2015-08-03 | 2015-08-11 | 2015-08-24 | MYMS CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Surigao del Norte | 132448 | Tapian ES | MAINIT | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130715S00081 | 15NF0056 | 2015-10-05 | 2015-10-07 | 2015-10-23 | 2015-11-03 | 2015-11-17 | ASJ BUILDERS
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304853 | Timamana NHS | TUBOD | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130715S00040 | 15NF0076 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-10 | 2015-12-17 | ASJ BUILDERS
NC 2015 | SHS (2015) | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 130715S00039 | 15NF0073 | 2015-10-20 | 2015-10-22 | 2015-11-04 | 2015-11-11 | 2015-12-01 | ALGAMON CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304857 | Adlay NHS | CARRASCAL | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 130515S00090 | 15NH0064 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-28 | 2015-09-09 | RJ CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317925 | Agsam ISS | LANUZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00003 | 15NH0056 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304858 | Anibongan NHS | LIANGA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6809837.6381 |  |  | COMPLETED | 1 |  |  | 130515S00097
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304899 | Antipolo NHS | MARIHATAG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00014 | 15NH0052 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317903 | Badong National High School | TAGO | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00024 | 15NH0047 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132869 | Bagyang ES | SAN MIGUEL | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00119
NC 2015 | SHS (2015) | CARAGA | Surigao Del Sur | 132769 | Ban-as ES | LIANGA | 1 | 1 | 2 | Completion of 1STY2CL | 2015 COMPLETION BATCH 4 | 868355.68 |  |  | COMPLETED | 1 |  |  | 130515S00136 | 15NH0093 | 2015-10-22 | 2015-10-23 | 2015-11-04 | 2015-11-23 | 2015-12-01 | RJ CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 500322 | Bangsud ES | TAGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00117 | 15NH0081 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500322 | Bangsud ISS | TAGO | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00026 | 15NH0048 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304861 | BAROBO NHS | BAROBO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8629965.051 |  |  | COMPLETED | 1 |  |  | 130515S00070 | 15NI0052 | 2015-11-10 | 2015-11-12 | 2015-11-23 | 2015-12-02 | 2015-12-04 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500323 | Bitaugan ISS | CAGWAIT | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00012 | 15NH0051 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | J & A PIMENTEL CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304906 | BOLHOON NATIONAL HIGH SCHOOL | SAN MIGUEL | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3917968.78 |  |  | COMPLETED | 1 |  |  | 130515S00093 | 15NH0072 | 2015-07-29 | 2015-08-11 | 2015-08-11 | 2015-09-01 | 2015-09-10 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304871 | Buenavista NHS | CITY OF TANDAG (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 130515S00017 | 1305-15-S-00017
NC 2015 | TECHVOC (2015) | CARAGA | Surigao del Sur | 304871 | Buenavista NHS | CITY OF TANDAG (Capital) | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4899098.54 |  |  | COMPLETED | 1 |  |  | 130515S00138 | 15NH0097 | 2015-09-24 | 2015-09-25 | 2015-10-07 | 2015-11-16 | 2015-11-24 | VIRGILIO ANUTA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304872 | Burgos NHS | CORTES | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00091
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317915 | Cabangahan ISS | CANTILAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2098606 |  |  | COMPLETED | 1 |  |  | 130515S00105
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132936 | Cagdapao Elementary School | TAGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00111 | 15NH0076 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 214502 | Cagpangi ES | TAGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00107 | 15NH0080 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132874 | Calatngan ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00112 | 1305-15-S-00112 | 2015-08-06 | 2015-08-18
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304873 | Cantilan NHS | CANTILAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130515S00083
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317928 | Cantilan NHS - Consuelo Annex | CANTILAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00011 | 15NH0043 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304875 | Carmen Nat'l. Agr'l. HS | CARMEN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00082
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304877 | Carrascal NHS | CARRASCAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130515S00079
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132875 | Carromata ES | SAN MIGUEL | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00114
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132877 | Catabadan ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00125 | 1305-15-S-00125 | 2015-08-06 | 2015-08-18
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago Nat'l HS | MARIHATAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8948965.051 |  |  | COMPLETED | 1 |  |  | 130515S00077
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500050 | Esperanza ISS (Carmen Nat'l. Agr'l. HS - Esperanza NHS Annex) | CARMEN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00101 | 15NH0045 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304886 | Felisberto Verano National high school | CORTES | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00076
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304885 | Florita Herrera-Irizari NHS | LANUZA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00084
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304888 | Gamut NHS (Barobo) | BAROBO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8876565.051 |  |  | COMPLETED | 1 |  |  | 130515S00071 | 15NI0069 | 2015-11-30 | 2015-12-04 | 2015-12-14 | 2015-12-21 | 2015-12-24 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304889 | Gamut NHS (Tago) | TAGO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00072
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317914 | Gata ISS | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00054 | 15NH0054 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 214528 | Himatagan PS | LANUZA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00128 | 15NH0078 | 2015-10-12 | 2015-10-13 | 2015-10-26 | 2015-11-23 | 2015-12-01 | RJ CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132944 | Himat-e ES | TAGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00110 | 15NH0074 | 2015-10-12 | 2015-10-13 | 2015-10-26 | 2015-11-23 | 2015-12-01 | DIGOS CONSTRAK CORPORATION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317916 | Isla General ISS | CANTILAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00010 | 15NH0060 | 2015-07-21 | 2015-07-23
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304925 | Jose Sanvictores Sr. National School Annex | CAGWAIT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00073
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132863 | Lamela ES | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00120 | 15NH0087 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | TABADA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317919 | Libas Sud ISS | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00053 | 15NH0049 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132948 | Lindoy ES | TAGO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00109 | 1305-15-S-00109 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | JOAN CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304895 | Lingig NHS | LINGIG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8924965.051 |  |  | COMPLETED | 1 |  |  | 130515S00074 | 15NI0068 | 2015-11-30 | 2015-12-04 | 2015-12-14 | 2015-12-21 | 2015-12-28 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 214524 | Lower Bagyang Elementary School | SAN MIGUEL | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00106
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304897 | Madrid NHS | MADRID | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1 |  |  | 130515S00075
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317904 | Madrid NHS - Union NHS Annex | MADRID | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00032 | 15NH0044 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132884 | Mahayag ES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00123 | 15NH0084 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | JOAN CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132649 | Mam-on ES | CAGWAIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0 |  |  | 130515S00118 | 1305-15-S-00118 | 2015-08-05
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132826 | Manga Elementary School | MADRID | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00121 | 1305-15-S-00121 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | J & A PIMENTEL CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304898 | Marihatag Nat'l. Agr'l. HS | MARIHATAG | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00009 | 15NH0053 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317905 | Marihatag Nat'l. Agr'l. HS - Mararag Annex | MARIHATAG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6626037.6381 |  |  | COMPLETED | 1 |  |  | 130515S00099
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500321 | Matho ISS | CORTES | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00081 | 15NN0070 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-09-01 | 2015-09-10 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500321 | Matho ISS | CORTES | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00098 | 15NH0069 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-09-01 | 2015-09-10 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500320 | Nurcia ISS | LANUZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00015 | 15NH0046 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317902 | Pakwan ISS (F.H. Irizari Memorial NHS - Pakwan NHS Annex) | LANUZA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 |  |  | 130515S00008 | 15NH0061 | 2015-07-21 | 2015-07-23
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304874 | Palasao Integrated School | CANTILAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00007 | 15NH0042 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132606 | Panaosawon ES | BAYABAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00116 | 15NH0085 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | JOAN CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132969 | Pandanon ES | CITY OF TANDAG (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00108 | 15NH0073 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304900 | Panikian NHS | CARRASCAL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00096
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304901 | Parang NHS | CANTILAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 130515S00095
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304903 | Purisima NHS | TAGO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 130515S00094
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304904 | Salvacion NHS | SAN AGUSTIN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00085
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132781 | San Isidro ES | LIANGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00122 | 15NH0088 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-09-21 | 2015-09-30 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304905 | San Miguel NCHS | SAN MIGUEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130515S00092
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304907 | San Miguel NCHS - Sagbayan Annex | SAN MIGUEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130515S00100
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317913 | San Miguel NCHS - San Roque NHS Annex | SAN MIGUEL | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3967968.78 |  |  | COMPLETED | 1 |  |  | 130515S00063 | 15NH0071 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-13 | 2015-09-10 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304908 | San Miguel NCHS Poblacion Annex | SAN MIGUEL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 130515S00089
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317908 | SMNCHS-Mahayag Annex | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00056 | 15NH0050 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada NHS | BAYABAS | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5442651.88 |  |  | COMPLETED | 1 |  |  | 130515S00078 | 15NH0065 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-08-11 | 2015-09-10 | SQUARE CUBE CONSTRUCTION(FORMERLY SQUARE CUBE TRAD
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304915 | St. Christine NHS | LIANGA | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5622651.88 |  |  | COMPLETED | 1 |  |  | 130515S00087 | 15NH0066 | 2015-07-23 | 2015-08-04 | 2015-08-05 | 2015-09-01 | 2015-09-10 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317912 | St. Christine NHS - Davisol NHS Annex | LIANGA | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00006 | 15NH0055 | 2015-06-16 | 2015-06-18 | 2015-06-30 | 2015-07-07 | 2015-07-30 | ROWIEs CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304916 | Sto. Niño NHS | SAN AGUSTIN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9044965.051 |  |  | COMPLETED | 1 |  |  | 130515S00086
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317907 | Sumo-sumo NHS Annex | TAGO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 130515S00080
NC 2015 | SHS (2015) | CARAGA | Surigao Del Sur | 132605 | Tabing Dagat ES | BAYABAS | 1 | 1 | 2 | Completion of 1STY2CL | 2015 COMPLETION BATCH 4 | 807588.3 |  |  | COMPLETED | 1 |  |  | 130515S00137 | 15NH0094 | 2015-09-20 | 2015-09-23 | 2015-10-05 | 2015-10-20 | 2015-10-29 | ROWIEs CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132715 | Tag-anungan ES | CORTES | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00115 | 15NH0079 | 2015-10-12 | 2015-10-13 | 2015-10-26 | 2015-11-23 | 2015-12-01 | RJ CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304922 | Tandag Nat'l. Sci HS | CITY OF TANDAG (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 |  |  | 130515S00016 | 1305-15-S-00016
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304887 | Tigao National High School | CORTES | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00058
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304924 | Unidad NHS | CAGWAIT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8834965.051 |  |  | COMPLETED | 1 |  |  | 130515S00059
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132784 | Anibongan ES | LINGIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00132 | 15NI0034 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317930 | Anibongan ISS | LINGIG | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00005 | 15NI0020 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-29 | 2015-07-31 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317924 | Baculin ISS | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00004 | 15NI0015 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-29 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132723 | Balbuena ES | HINATUAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00133 | 15NI0033 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304860 | Barcelona NHS | LINGIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 9234965.051 |  |  | COMPLETED | 1 |  |  | 130515S00060
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317921 | BAROBO NHS-WAKAT NHS ANNEX | BAROBO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6706337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00061 | 15NI0048 | 2015-10-08 | 2015-10-09 | 2015-10-21 | 2015-10-28 | 2015-11-02 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317909 | Bingcongan IS | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00013 | 15NI0017 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304862 | Cabacungan NHS | BAROBO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00034 | 15NI0009 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500326 | Carpenito ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00043 | 15NI0010 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi NHS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00050 | 15NI0014 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132578 | Dinuyan ES | BAROBO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 130515S00134 | 15NI0075 | 2015-11-30 | 2015-12-04 | 2015-12-14 | 2015-12-21 | 2015-12-28 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304878 | Doña Carmen NHS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00044 | 15NI0013 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | DINGO BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6709337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00069 | 15NI0039 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317940 | Hinatuan NCHS - Cambatong NHS Annex | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00040 | 15NI0016 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317939 | Hinatuan NCHS - Roxas NHS Annex | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00045 | 15NI0016 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | O. G. SANTOS CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304890 | Hinatuan NHS | HINATUAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8494965.051 |  |  | COMPLETED | 1 |  |  | 130515S00062 | 15NI0070 | 2015-12-01 | 2015-12-13 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304863 | Javier NHS | BAROBO | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3757968.78 |  |  | COMPLETED | 1 |  |  | 130515S00057 | 15NI0026 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-07 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317938 | Jobar Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00046 | 15NI0014 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304880 | Kahayagan NHS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00047 | 15NI0010 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132900 | Kinagbangan ES | TAGBINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00130 | 15NI0035 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | AMAZING FIND BUILDERS CORPORATION (FORMERLY: SKILLED CONTRACTORS & LABORERS EMPOWERMENT COOPERATIVE)
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304859 | Lianga NCHS | LIANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 130515S00064
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304896 | M.K.Yusingco NHS | LINGIG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6719338 |  |  | COMPLETED | 1 |  |  | 130515S00104
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500324 | Maglambing ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00048 | 15NI0019 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304881 | Maglatab NHS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00049 | 15NI0021 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132906 | Magsaysay ES | TAGBINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00113 | 15NI0035 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | AMAZING FIND BUILDERS CORPORATION (FORMERLY: SKILLED CONTRACTORS & LABORERS EMPOWERMENT COOPERATIVE)
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317932 | Malixi ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00042 | 15NI0019 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317936 | Manambia ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00039 | 15ni0012 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 214522 | New Canaan PS | LINGIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00127 | 15NI0034 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317927 | Osmena ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00038 | 15NI0011 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | DINGO BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy NHS | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00037 | 15NI0015 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500325 | Quary 1 Integrated School | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00036 | 15NI0011 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | DINGO BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317934 | Quezon ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00035 | 15ni0012 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | OLIN DEVELOPMENT ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan ISS | LINGIG | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00027 | 15NI0020 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317941 | Rizal National High School - Annex | BAROBO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00033 | 15NI0009 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | AGUERO CONSTRUCTION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304882 | San Vicente II NHS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00041 | 15NI0021 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 132918 | Soriano ES | TAGBINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00131 | 15NI0036 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | AMAZING FIND BUILDERS CORPORATION (FORMERLY: SKILLED CONTRACTORS & LABORERS EMPOWERMENT COOPERATIVE)
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304883 | Sta. Juana NHS | TAGBINA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6809337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00065
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317935 | Sta. Maria ISS | TAGBINA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00031 | 15NI0013 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | DINGO BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | CARAGA | Surigao del Sur | 214506 | Sto. Nino PS | HINATUAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 130515S00124 | 15NI0033 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304920 | Tagasaka NHS | HINATUAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 130515S00066 | 15NI0038 | 2015-09-09 | 2015-09-11 | 2015-09-22 | 2015-09-29 | 2015-10-02 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304921 | Tagasaka NHS - Bigaan NHS Annex | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00030 | 15NI0017 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | MAG CORPORATION
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317910 | Tagasaka NHS - Loyola NHS Annex | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00029 | 15NI0018 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304884 | Tagbina NHS | TAGBINA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 130515S00068 | 15NI0047 | 2015-10-08 | 2015-10-09 | 2015-10-21 | 2015-10-28 | 2015-11-02 | TWINA BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8374965.051 |  |  | COMPLETED | 1 |  |  | 130515S00088 | 15NI0071 | 2015-12-01 | 2015-12-13 | 2015-12-14
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 317926 | Tarusan ISS | HINATUAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 130515S00028 | 15NI0018 | 2015-07-09 | 2015-07-20 | 2015-07-23 | 2015-07-28 | 2015-07-31 | R. SEMILLA CONSTRUCTION & MARKETING
NC 2015 | SHS (2015) | CARAGA | Surigao del Sur | 304923 | Tidman NHS | HINATUAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6633037.6381 |  |  | COMPLETED | 1 |  |  | 130515S00067
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304680 | Casiklan Nhs- Durian Nhs Annex | Las Nieves | 1 | 1 | 6 | 1STY6CL | BATCH 9 CL | 6094219.0144 |  |  | Completed | 1 |  |  |  | 16ND0073 |  | 2016-06-30 | 2016-07-12
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304680 | Casiklan Nhs- Durian Nhs Annex | Las Nieves | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1 |  |  |  | 16ND0063 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304679 | Durian Nhs | Las Nieves | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9803720.3461 |  |  | Completed | 1 |  |  |  | 16ND0068 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304679 | Durian Nhs | Las Nieves | 1 |  | 8 | 2STY8CL | BATCH 9 CL | 13021544.3309 |  |  | Completed | 1 |  |  |  | 16ND0070 |  | 2016-08-12 | 2016-08-25
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317310 | E. G. Montilla Nhs (Mat-I Nhs Annex) | Las Nieves | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 17612910.72 |  |  | Completed | 1 |  |  |  | 16ND0071 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304689 | Las Nieves Nhs | Las Nieves | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 21655925.759 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304689 | Las Nieves Nhs | Las Nieves | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 7481259.6019 |  |  | Completed | 1 |  |  |  | 16ND0066 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304689 | Las Nieves Nhs | Las Nieves | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 3159520.2264 |  |  | Completed | 1 |  |  |  | 16ND0064 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304681 | Lawan-Lawan Nhs (Durian Nhs Annex) | Las Nieves | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 4192512.7558 |  |  | Completed | 1 |  |  |  | 16ND0065 |  | 2016-08-12 | 2016-08-25
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304690 | Lingayao National High School | Las Nieves | 1 | 1 | 6 | 1STY6CL | BATCH 9 CL | 5897039.644 |  |  | Completed | 1 |  |  |  | 16ND0072 |  | 2016-06-30 | 2016-07-12 | 2016-08-08
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304693 | Maningalao Nhs | Las Nieves | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1 |  |  |  | 16ND0086 |  | 2016-07-29 | 2016-08-11
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304694 | Marcos Calo Nhs | Las Nieves | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9908607.7117 |  |  | Completed | 1 |  |  |  | 16ND0069 |  | 2016-08-12 | 2016-08-25
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304694 | Marcos Calo Nhs | Las Nieves | 1 |  | 4 | 1STY2CL | BATCH 9 CL | 3738381.212 |  |  | Completed | 1 |  |  |  | 16ND0085 |  | 2016-07-29 | 2016-08-11
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304695 | Mat-I Nhs | Las Nieves | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9636093.4561 |  |  | Completed | 1 |  |  |  | 16ND0067 |  | 2016-06-24 | 2016-07-07
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304695 | Mat-I Nhs | Las Nieves | 1 |  | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1 |  |  |  | 16ND0087 |  | 2016-07-29 | 2016-08-11
NC 2016 | TECHVOC | CARAGA | Agusan Del Norte | 304673 | Agay Nhs | Remedios T. Romualdez | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304673 | Agay Nhs | Remedios T. Romualdez | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317315 | Agong-Ong Nhs (Buenavista Nhs Annex | Buenavista | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072678MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317315 | Agong-Ong Nhs (Buenavista Nhs Annex | Buenavista | 2 |  | 3 | 1STY3CL | BATCH 9 CL | 2802592.44 |  |  | Completed | 1 |  |  | P00072679MN | 16NA0018 | 2016-06-01 | 2016-06-09 | 2016-06-20 | 2016-07-01 | 2016-07-16 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317315 | Agong-Ong Nhs (Buenavista Nhs Annex | Buenavista | 2 |  | 4 | 1STY4CL | BATCH 9 CL | 3667968.78 |  |  | Completed | 1 |  |  | P00072680MN | 16NA0024 | 2016-06-07 | 2016-06-14 | 2016-06-29 | 2016-07-08 | 2016-07-30 | BN Builders Const & Supplies
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317311 | Balangbalang Nhs (Agay Nhs Annex) | Remedios T. Romualdez | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072716MN | 16NA0033 | 2016-06-11 | 2016-06-21 | 2016-07-05 | 2016-07-15 | 2016-07-28 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317319 | Bangonay Nhs | Jabonga | 2 | 1 | 6 | 1STY2CL | BATCH 9 CL | 5234233.308 |  |  | Completed | 1 |  |  | P00072689MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304674 | Buenavista Nhs | Buenavista | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12838675.28 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304675 | Buenavista Special Education Hs | Buenavista | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072681MN | 16NA0031 | 2016-06-09 | 2016-06-21 | 2016-07-05 | 2016-07-15 | 2016-07-28 | BN Builders Const & Supplies
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317304 | Cahayagan Nhs (Carmen Nhs Annex) | Carmen | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3916000 |  |  | Completed | 1 |  |  | P00072685MN | 16NA0014 | 2016-05-19 | 2016-05-26 | 2016-06-13 | 2016-06-13 | 2016-06-13 | BBC Construction
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317308 | Culit Nhs (Nasipit National Vocational School Annex) | Nasipit | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00072711MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304678 | Cuyago Nhs | Jabonga | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3489488.872 |  |  | Completed | 1 |  |  | P00072690MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317309 | Dona Rosario Nhs - Tubay Nhs Annex | Tubay | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 14816937.0918 |  |  | Completed | 1 |  |  | P00072719MN
NC 2016 | K10 | CARAGA | Agusan Del Norte | 304682 | Guinabsan Nhs | Buenavista | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072682MN | 16NA0027 | 2016-06-07 | 2016-06-14 | 2016-06-29 | 2016-07-06 | 2016-07-19 | BN Builders Const & Supplies
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317318 | Hinandayan Nhs (Nasipit Nhs Annex)) | Nasipit | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8264965.05 |  |  | Completed | 1 |  |  | P00072712MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304688 | Kitcharao Nhs | Kitcharao | 2 | 1 | 6 | 1STY6CL | BATCH 9 CL | 5285441.89 |  |  | Completed | 1 |  |  | P00072693MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304688 | Kitcharao Nhs | Kitcharao | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00072694MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304688 | Kitcharao Nhs | Kitcharao | 2 |  | 8 | 2STY4CL | BATCH 9 CL | 11404807.7485 |  |  | Completed | 1 |  |  | P00072695MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304691 | Magallanes Nhs | Magallanes | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15689000 |  |  | Completed | 1 |  |  | P00071719MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304691 | Magallanes Nhs | Magallanes | 2 |  | 16 | 2STY8CL | BATCH 7 CL | 22554685.18 |  |  | Completed | 1 |  |  | P00071720MN | 16NA0042 | 2016-06-23 | 2016-07-01 | 2016-07-12
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304691 | Magallanes Nhs | Magallanes | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6619337.64 |  |  | Completed | 1 |  |  | P00071721MN | 16NA0037 | 2016-06-15 | 2016-06-22 | 2016-07-04
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304692 | Magdagooc Nhs | Jabonga | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072691MN
NC 2016 | K10 | CARAGA | Agusan Del Norte | 317306 | Manoligao Nhs(Carmen National High School Annex) | Carmen | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3916000 |  |  | Reverted | 0 |  |  | P00072686MN | 16NA0015 | 2016-06-09 | 2016-06-21
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304696 | Nasipit National Vocational School | Nasipit | 2 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16429930.1 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304696 | Nasipit National Vocational School | Nasipit | 2 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317302 | Nasipit Nhs | Nasipit | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2851000 |  |  | Completed | 1 |  |  | P00072713MN | 16NA0017 | 2016-06-01 | 2016-06-09 | 2016-06-20 | 2016-07-01 | 2016-07-16 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317302 | Nasipit Nhs | Nasipit | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072714MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317302 | Nasipit Nhs | Nasipit | 2 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | P00072715MN | 16NA0017 | 2016-06-01 | 2016-06-09 | 2016-06-20 | 2016-07-01 | 2016-07-16 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317303 | San Vicente Nhs | Jabonga | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6419337.64 |  |  | Completed | 1 |  |  | P00072692MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 317301 | Sangay Nhs | Buenavista | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6419337.64 |  |  | Completed | 1 |  |  | P00072683MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304698 | Santiago Nhs | Santiago | 2 | 1 | 12 | 2STY12CL | BATCH 9 CL | 14579217.18 |  |  | Completed | 1 |  |  | P00072717MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304698 | Santiago Nhs | Santiago | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072718MN | 16NA0030 | 2016-06-09 | 2016-06-21 | 2016-07-05 | 2016-07-15 | 2016-07-28 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte |  | Shs In Carmen, Agusan Del Norte | Carmen | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072687MN | 16NA0034 | 2016-06-11 | 2016-06-21 | 2016-07-05 | 2016-07-15 | 2016-07-28 | Rudhil Const. & Ent, Inc.
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304683 | Simbalan Nhs - Guinabsan Nhs Annex | Buenavista | 2 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16429930.1 |  |  | Completed | 1 |  |  | P00072684MN | 16NA0028 | 2016-06-07 | 2016-06-14 | 2016-06-29 | 2016-07-11 | 2016-07-21 | Reyrose Const. & Supply
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304700 | Tinigbasan Nhs | Tubay | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6627804.52 |  |  | Completed | 1 |  |  | P00072720MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304701 | Tubay Nhs | Tubay | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 19609216.6651 |  |  | Completed | 1 |  |  | P00072721MN
NC 2016 | SHS | CARAGA | Agusan Del Norte | 304702 | Vinapor Nhs | Carmen | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072688MN | 16NA0040 | 2016-06-23 | 2016-07-01
NC 2016 | SHS | CARAGA | Agusan Del Sur | 317442 | Afga Nhs | Sibagat | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6883125 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317444 | Aurora Nhs | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317433 | Buena Gracia National High School | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 131670 | Bunaguit Es | Esperanza | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2164100 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 131670 | Bunaguit Es | Esperanza | 1 |  | 4 | 1STY4CL | BATCH 13 CL | 4084765.658 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317416 | Causwagan National High School | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304738 | Cecilia Nhs | San Luis | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9101461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317422 | Corpuz Nhs | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304710 | Del Monte Nhs | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317411 | Desamparados Nhs | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304712 | Esperanza National High School | Esperanza | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304712 | Esperanza National High School | Esperanza | 1 |  | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304712 | Esperanza National High School | Esperanza | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304713 | Guadalupe Nhs | Esperanza | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2924570 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317414 | Hawilian National High School | Esperanza | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 131679 | Kubo Es | Esperanza | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9061461.555 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304720 | Los Arcos Nhs | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317434 | Marbon Nhs | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304726 | New Tubigon High School Of Home Industries | Sibagat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 131959 | Olangoan Es | San Luis | 1 | 1 | 6 | 1STY2CL | BATCH 13 CL | 5915818.12 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304730 | Patin-Ay National High School | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304731 | Prosperidad Nhs | Prosperidad (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304736 | San Luis Nhs | San Luis | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304736 | San Luis Nhs | San Luis | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 12010076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317415 | San Toribio Nhs | Esperanza | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317404 | San Vicente Nhs | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304740 | Sibagat National High School Of Home Industries | Sibagat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304749 | Sta. Irene National High School | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 317428 | West Prosperidad Nhs | Prosperidad (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304755 | Zillovia Nhs | Talacogon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304703 | Agusan Del Sur National High School | San Francisco | 2 | 1 | 18 | 3STY6CL | BATCH 3 CL | 28340250 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304703 | Agusan Del Sur National High School | San Francisco | 2 |  | 18 | 3STY6CL | BATCH 3 CL | 28340250 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304703 | Agusan Del Sur National High School | San Francisco | 2 |  | 18 | 3STY6CL | BATCH 3 CL | 28340250 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304709 | Bunawan National High School | Bunawan | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 19069427.2852 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304709 | Bunawan National High School | Bunawan | 2 |  | 6 | 3STY6CL | BATCH 11 CL | 10987851.3782 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304709 | Bunawan National High School | Bunawan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2669334.8 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 131659 | Nueva Era Es | Bunawan | 2 | 1 | 6 | 2STY6CL | BATCH 11 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 304750 | Sta. Josefa National High School | Santa Josefa | 2 | 1 | 18 | 3STY6CL | BATCH 9 CL | 28340250 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Agusan Del Sur | 304750 | Sta. Josefa National High School | Santa Josefa | 2 |  | 18 | 2STY6CL | BATCH 9 CL | 27124384.6683 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304750 | Sta. Josefa National High School | Santa Josefa | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2510000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304750 | Sta. Josefa National High School | Santa Josefa | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2510000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Agusan Del Sur | 304753 | Trento Nhs | Trento | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20065250 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304753 | Trento Nhs | Trento | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2510000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Agusan Del Sur | 304753 | Trento Nhs | Trento | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2510000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Bayugan City | 304707 | Bayugan Nchs | City Of Bayugan | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Bayugan City | 304707 | Bayugan Nchs | City Of Bayugan | 1 |  | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Bayugan City | 304728 | Noli National High School | City Of Bayugan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Bayugan City |  | Stand Alone Shs | City Of Bayugan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Bayugan City |  | Stand Alone Shs | City Of Bayugan | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Bayugan City |  | Stand Alone Shs | City Of Bayugan | 1 |  | 40 | 2STY8CL | BATCH 9 CL | 49023041.6626 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Bayugan City |  | Stand Alone Shs | City Of Bayugan | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7976100 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Bislig City | 132612 | Caguyao Es | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1874740.17 |  |  | Completed | 1 |  |  | 16NI0012 | 16NI0012 | 2016-06-05 | 2016-06-17 | 2016-06-29 | 2016-07-07 | 2016-07-13 | MAG CORPORATION
NC 2016 | SHS | CARAGA | Bislig City | 304866 | Maharlika Nhs | City Of Bislig | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8254965.05 |  |  | Completed | 1 |  |  | 16NI0016 | 16NI0016 | 2016-06-02 | 2016-06-14 | 2016-06-26 | 2016-08-02 | 2016-08-09 | MARK ANTHONY CONST. & SUPPLY
NC 2016 | SHS | CARAGA | Bislig City | 304919 | Mangagoy Nhs | City Of Bislig | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8384965.05 |  |  | Completed | 1 |  |  | 16NI0015 | 16NI0015 | 2016-06-02 | 2016-06-14 | 2016-06-26 | 2016-08-02 | 2016-08-09 | R. SEMILLA CONST. & MKTG.
NC 2016 | K10 | CARAGA | Bislig City | 235003 | New Bongga Ps | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1894740.17 |  |  | Completed | 1 |  |  | 16NI0025 | 16NI0025 | 2016-11-05 | 2016-11-17 | 2016-11-29 | 2016-12-12 | 2016-12-19 | JIMBERNS BUILDERS & CONST. SUPPLY
NC 2016 | K10 | CARAGA | Bislig City | 235004 | New Jerusalem Es | City Of Bislig | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6349337.64 |  |  | Completed | 1 |  |  | 16NI0017 | 16NI0017 | 2016-06-02 | 2016-06-14 | 2016-06-26 | 2016-08-02 | 2016-08-09 | JIMBERNS BUILDERS & CONST. SUPPLY
NC 2016 | K10 | CARAGA | Bislig City | 132625 | Pamanlinan Es | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1849740.17 |  |  | Completed | 1 |  |  | 16NI0013 | 16NI0013 | 2016-06-05 | 2016-06-17 | 2016-06-29 | 2016-07-07 | 2016-07-13 | MN BAYALAS CONST.
NC 2016 | SHS | CARAGA | Bislig City | 304869 | Sikahoy Nhs | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1894740.17 |  |  | Completed | 1 |  |  | 16NI0011 | 16NI0011 | 2016-06-05 | 2016-06-17 | 2016-06-29 | 2016-07-07 | 2016-07-13 | R. SEMILLA CONST. & MKTG.
NC 2016 | K10 | CARAGA | Bislig City | 132639 | Sote Es | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1844740.17 |  |  | Completed | 1 |  |  | 16NI0014 | 16NI0014 | 2016-06-05 | 2016-06-17 | 2016-06-29 | 2016-07-07 | 2016-07-13 | MAG CORPORATION
NC 2016 | K10 | CARAGA | Bislig City | 304917 | Tabon M. Estrella National High School | City Of Bislig | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6349337.64 |  |  | Completed | 1 |  |  | 17NI0042 | 17NI0042 | 2017-03-26 | 2017-04-08 | 2017-04-20 | 2017-04-25 | 2017-07-31 | MAG CORPORATION
NC 2016 | K10 | CARAGA | Bislig City | 322508 | Tabon M. Estrella National High School To San Fernando Is | City Of Bislig | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1968606.04 |  |  | Completed | 1 |  |  | 17NI0052 | 17NI0052 | 2017-05-25 | 2017-06-07 | 2017-06-19 | 2017-06-23 | 2017-06-29 | MAG CORPORATION
NC 2016 | K10 | CARAGA | Butuan City | 132041 | A.J. Mejia Es | Butuan City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958748.1825 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | Butuan City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | Butuan City (Capital) | 1 |  | 60 | 4STY20CL | BATCH 11 CL | 93308670.81 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304757 | Agusan Pequeno Nhs | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2569478.8327 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 304757 | Agusan Pequeno Nhs (Main Campus) | Butuan City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8366763.66 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 304757 | Agusan Pequeno Nhs (Pagatpatan Campus) | Butuan City (Capital) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8485390.73 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 317517 | Alviola Iss | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6430186.52 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304758 | Amparo Nhs | Butuan City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8422512.62 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304758 | Amparo Nhs | Butuan City (Capital) | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6487553.7 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317511 | Ampayon National High School | Butuan City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8385346.65 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304765 | Anticala Nhs | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6620270.77 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317502 | Aupagan National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6501425.08 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304759 | Banza Nhs | Butuan City (Capital) | 1 | 1 | 16 | 2STY8CL | BATCH 3 CL | 22268945.06 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 132023 | Butuan Central Elementary School | Butuan City (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15254543.55 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304761 | Butuan City Comprehensive Hs | Butuan City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1972863.494 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304761 | Butuan City Comprehensive Hs | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2629904.23 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304762 | Butuan City Sch. Of Arts & Trades | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304762 | Butuan City Sch. Of Arts & Trades | Butuan City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8463155.68 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304762 | Butuan City Sch. Of Arts & Trades | Butuan City (Capital) | 1 |  | 6 | 2STY6CL | BATCH 13 CL | 8463155.68 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304762 | Butuan City Sch. Of Arts & Trades | Butuan City (Capital) | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 6476176.52 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317507 | Consuelo National High School | Butuan City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8403929.63 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 132057 | Jose T. Domingo, Sr. Ces | Butuan City (Capital) | 1 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16696361.36 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317510 | Kinamlutan National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6559362.17 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 317510 | Kinamlutan National High School | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2591036.7837 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317514 | La Soledad Nhs | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6562650.56 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 317506 | La Trinidad Iss | Butuan City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11572726.67 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304763 | Libertad National High School | Butuan City (Capital) | 1 | 1 | 24 | 2STY6CL | BATCH 3 CL | 33392722.72 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 304764 | Los Angeles National High School | Butuan City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11564282.39 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304764 | Los Angeles National High School | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2606409.797 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304766 | Lumbocan Nhs | Butuan City (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2031770.2394 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304767 | Maguinda Nhs | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6804191.44 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317505 | Maibu National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6817414.98 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 317505 | Maibu National High School | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2744041.0818 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317519 | Manila De Bugabos National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6645313.44 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 132025 | Obrero Es | Butuan City (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15254543.55 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 132025 | Obrero Es | Butuan City (Capital) | 1 |  | 8 | 2STY8CL | BATCH 3 CL | 11088482.53 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 317515 | Pareja Iss | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6568673.37 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317520 | Pedro D. Duncano National Hs | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6487553.7 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 317520 | Pedro D. Duncano National Hs | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2589620.6306 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317521 | Pigdaulan National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6544877.9 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 317508 | Pinamanculan National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6473211.9 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 317508 | Pinamanculan National High School | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2609762.4286 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304769 | San Vicente Nhs | Butuan City (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11088482.53 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304769 | San Vicente Nhs | Butuan City (Capital) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8348180.68 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304769 | San Vicente Nhs | Butuan City (Capital) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5125529.8 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City |  | Stand Alone No. 1 | Butuan City (Capital) | 1 | 1 | 80 | 4STY20CL | BATCH 11 CL | 128013689.523 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City |  | Stand Alone No. 1 | Butuan City (Capital) | 1 |  | 15 | 3STY15CL | BATCH 11 CL | 22346059.7931 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City |  | Stand Alone No. 1 | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2623185 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Butuan City | 304770 | Sumile National High School | Butuan City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6874782.16 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304771 | Taligaman Nhs | Butuan City (Capital) | 1 | 1 | 16 | 2STY8CL | BATCH 3 CL | 22715537.725 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304771 | Taligaman Nhs | Butuan City (Capital) | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6461889.6359 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Butuan City | 304772 | Tungao Nhs | Butuan City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2710471.4185 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Butuan City | 304772 | Tungao Nhs | Butuan City (Capital) | 1 | 1 | 12 | 2STY12CL | BATCH 13 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | City Of Cabadbaran | 2 | 1 | 30 | 3STY15CL | BATCH 1 CL | 44513260.54 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Cabadbaran City | 304699 | Cabadbaran City National High School | City Of Cabadbaran | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2231281.98 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Cabadbaran City | 304676 | Calamba Nhs | City Of Cabadbaran | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Cabadbaran City | 317307 | Del Pilar Nhs (Calamba Nhs Annex) | City Of Cabadbaran | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Cabadbaran City |  | La Union Shs (Stand Alone) | City Of Cabadbaran | 2 | 1 | 10 | 2STY10CL | BATCH 1 CL | 14556573.203 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Cabadbaran City |  | La Union Shs (Stand Alone) | City Of Cabadbaran | 2 |  |  | FENCE (400m) | BATCH 1 CL | 2400000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Cabadbaran City |  | La Union Shs (Stand Alone) | City Of Cabadbaran | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2374393.09 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Cabadbaran City | 131523 | Lusong Elementary School | City Of Cabadbaran | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1198449.69 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132417 | Acoje Es | Loreto | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304808 | Albor Nhs | Libjo (Albor) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132306 | Arellano Es | Libjo (Albor) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304815 | Cagdianao Nhs | Cagdianao | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304825 | Cuarenta Nhs | San Jose (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132420 | Dahican Es | Loreto | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | Cagdianao | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304822 | Dinagat School Of Fisheries | Dinagat | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. Mnhs | San Jose (Capital) | 0 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14172542.8037 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132491 | Edera Es | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 324403 | Edera Nhs | Basilisa (Rizal) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132492 | F. S. Matugas Es | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132422 | Ferdinand Es | Loreto | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132494 | Galanida Es | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132397 | Gomez Es | Dinagat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132311 | Kanihaan Es | Libjo (Albor) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304827 | Liberty National High School | Loreto | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 324401 | Llamera Nhs | Libjo (Albor) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304828 | Loreto Nhs | Loreto | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9421461.5561 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 324407 | Malinao National High School | Tubajon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304836 | Melgar Nhs | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 214004 | Melody-Curada Es | Libjo (Albor) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 324404 | New Nazareth Nhs | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132315 | Oliverio Elementary School | Libjo (Albor) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132501 | Omay-Edradan E/S | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304809 | Osmeña-Sto. Niño National High School | Libjo (Albor) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132426 | Panamaon Es | Loreto | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304839 | Plaridel National High School | Libjo (Albor) | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6620280.9375 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | Dinagat | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. Nhs | Cagdianao | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | Basilisa (Rizal) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304842 | Rizal Nhs - Puerto Princesa - Moleta Nhs Annex | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 317801 | Rosita National High School | Libjo (Albor) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304844 | Sering Nhs | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132371 | Sto Nino Es | Cagdianao | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132509 | Sto. Nino Es | Basilisa (Rizal) | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 304851 | Tag-Abaca Nhs | Basilisa (Rizal) | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana Nhs | Tubajon | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Dinagat Island | 304854 | Tubajon Nhs | Tubajon | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 317802 | Valencia National High School | Cagdianao | 0 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Dinagat Island | 132375 | Villa Alcaria Ps | Cagdianao | 0 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3190000 |  |  | Reverted | 0
NC 2016 | K10 | CARAGA | Siargao | 317607 | Alegria National High School | Santa Monica (Sapao) | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6975000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Siargao | 317607 | Alegria National High School | Santa Monica (Sapao) | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9471461.5561 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Siargao | 317602 | Atoyay National High School | Socorro | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2954910.9364 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Siargao | 317602 | Atoyay National High School | Socorro | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 9908607.7117 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304780 | Caridad Nhs | Pilar | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304775 | Consolacion Nhs | Dapa | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304775 | Consolacion Nhs | Dapa | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304774 | Dapa Nhs | Dapa | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 36142729.297 |  |  | Completed | 1 | [10 empty] | Termination approved, for Advertisement
NC 2016 | SHS | CARAGA | Siargao | 304774 | Dapa Nhs | Dapa | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 25727777.982 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304774 | Dapa Nhs | Dapa | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2816200 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304783 | Del Carmen Nhs | Del Carmen | 1 | 1 | 12 | 2STY6CL | BATCH 9 CL | 19817215.4234 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304783 | Del Carmen Nhs | Del Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304777 | Gen Luna Nhs | General Luna | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 25841946.2745 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304777 | Gen Luna Nhs | General Luna | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 317601 | Gen. Luna Nhs - Suyangan Nhs Annex | General Luna | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Reverted | 0 | [10 empty] | Termination approved, for Advertisement
NC 2016 | SHS | CARAGA | Siargao | 304786 | Libertad Nhs | Santa Monica (Sapao) | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9908607.7117 |  |  | Reverted | 0
NC 2016 | TECHVOC | CARAGA | Siargao | 304786 | Libertad Nhs | Santa Monica (Sapao) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | Del Carmen | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304789 | Nueva Estrella Nhs | Socorro | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 17430000 |  |  | Reverted | 0
NC 2016 | SHS | CARAGA | Siargao | 317605 | Oguing Navarro Mem. Nhs - Annex | Del Carmen | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304790 | Pamosaingan Nhs | Socorro | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304790 | Pamosaingan Nhs | Socorro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304779 | Pilar Nhs | Pilar | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14340000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304784 | Roxas Nhs | San Isidro | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 17430000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304784 | Roxas Nhs | San Isidro | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5849140 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304781 | San Benito Nhs | San Benito | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 17430000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304781 | San Benito Nhs | San Benito | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304782 | San Isidro Nhs | San Isidro | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9908607.7117 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Siargao | 304782 | San Isidro Nhs | San Isidro | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2924570 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 317604 | Siargao Nat'L. Science Hs | Dapa | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304788 | Socorro National Hs | Socorro | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 17430000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304788 | Socorro National Hs | Socorro | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 17430000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304778 | Sta. Fe National High School | General Luna | 1 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Siargao | 304791 | Union Nhs | Dapa | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7300000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132273 | Alang-Alang Es | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29
NC 2016 | SHS | CARAGA | Surigao City | 304793 | Alegria Nhs | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao City | 304793 | Alegria Nhs | Surigao City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2849741.75 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27 |  |  | Algamon Costruction
NC 2016 | SHS | CARAGA | Surigao City | 304800 | Anomar Nhs | Surigao City (Capital) | 2 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13338675.28 |  |  | Completed | 1 | [9 empty] | Algamon Costruction
NC 2016 | TECHVOC | CARAGA | Surigao City | 304800 | Anomar Nhs | Surigao City (Capital) | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5299483.5 |  |  | Completed | 1 | [5 empty] | 2016-03-11 | 2016-03-23 |  |  | Cartesian Builders
NC 2016 | K10 | CARAGA | Surigao City | 132277 | Bay-Bay Es | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29
NC 2016 | K10 | CARAGA | Surigao City | 132244 | Bitaugan Es | Surigao City (Capital) | 2 | 1 | 4 | 1STY2CL | BATCH 9 CL | 3739488.872 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. Ces | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132290 | C.V. Diez Mem. Ces | Surigao City (Capital) | 2 |  | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132246 | Cagutsan Elementary School | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29
NC 2016 | SHS | CARAGA | Surigao City | 317702 | Cantiasay Nhs | Surigao City (Capital) | 2 | 1 | 6 | 1STY2CL | BATCH 9 CL | 5724213.155 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 304802 | Capalayan Nhs | Surigao City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 304794 | Caraga Regional Science Hs | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6669337.64 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132280 | Catadman Es | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29 |  |  | C.V. Construction
NC 2016 | SHS | CARAGA | Surigao City | 304803 | Day-Asan Nhs | Surigao City (Capital) | 2 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2226509.2394 |  |  | Completed | 1 | [5 empty] | 2016-06-15 | 2016-06-27
NC 2016 | SHS | CARAGA | Surigao City | 304795 | Ipil Nhs | Surigao City (Capital) | 2 | 1 | 10 | 2STY10CL | BATCH 3 CL | 14018754.96 |  |  | Completed | 1 | [9 empty] | Algamon Costruction
NC 2016 | K10 | CARAGA | Surigao City | 304792 | Juan P. Cedro, Sr. Mem. Nhs | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132251 | Lagundi Elementary School | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29
NC 2016 | SHS | CARAGA | Surigao City | 317704 | Lipata National High School | Surigao City (Capital) | 2 | 1 | 12 | 2STY6CL | BATCH 3 CL | 16997849.62 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 317705 | Mabini National High School | Surigao City (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2083470.02 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 317706 | Manjagao Nhs | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 304799 | Mat-I National High School | Surigao City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8498924.81 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao City | 304799 | Mat-I National High School | Surigao City (Capital) | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5299483.5 |  |  | Completed | 1 | [5 empty] | 2016-03-11 | 2016-03-23 |  |  | Migo Construction
NC 2016 | SHS | CARAGA | Surigao City | 304804 | Nonoc Nhs - Annex | Surigao City (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9333817.291 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao City | 304804 | Nonoc Nhs - Annex | Surigao City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2899741.75 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City | 132259 | San Jose Elementary School | Surigao City (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2183970.02 |  |  | Completed | 1 | [9 empty] | A.T. Dumlao
NC 2016 | K10 | CARAGA | Surigao City | 132303 | Sumilom Ps | Surigao City (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 | [5 empty] | 2016-06-17 | 2016-06-29
NC 2016 | TECHVOC | CARAGA | Surigao City | 304801 | Surigao City Nhs | Surigao City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 304801 | Surigao City Nhs | Surigao City (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao City |  | Surigao City Stand Alone | Surigao City (Capital) | 2 | 1 | 16 | 2STY8CL | BATCH 1 CL | 23842674.84 |  |  | Completed | 1 | [9 empty] | Gicar Construction
NC 2016 | K10 | CARAGA | Surigao City | 317701 | Taft Nhs - Annex | Surigao City (Capital) | 2 | 1 | 24 | 2STY8CL | BATCH 5 CL | 34489012.26 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 304805 | Talisay Nhs - Annex | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao City | 304806 | Zaragoza Nhs | Surigao City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1 | [9 empty] | ASJ Builders
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304845 | Amando A. Fabio Mnhs | Placer | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | Bacuag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | Bacuag | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304814 | Balite Nhs | San Francisco (Anao-Aon) | 2 | 1 | 8 | 2STY4CL | BATCH 5 CL | 13338675.28 |  |  | Completed | 1 |  |  | P00071264MN | 16NF0050 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | CV CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132428 | Bobonaon Primary School | Mainit | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072832MN | 16NF0028 | 2016-02-26 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-07-04 | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132404 | Camam-Onan Es | Gigaquit | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2182367.022 |  |  | Completed | 1 |  |  | P00072831MN | 16NF0022 | 2016-02-26 | 2016-03-04 | 2016-05-25 | 2016-06-01 | 2016-06-27 | AMA CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304817 | Campo Nhs | Bacuag | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8498924.81 |  |  | Completed | 1 |  |  | P00070260MN | 16NF0057 | 2016-05-23 | 2016-06-01 | 2016-06-13 |  |  | ALGAMON CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304817 | Campo Nhs | Bacuag | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5299483.5 |  |  | Completed | 1 |  |  | P00070734MN | 16NF0035 | 2016-03-03 | 2016-03-11 | 2016-03-23 | 2016-05-13 | 2016-06-06 | ASJ BUILDERS
NC 2016 | SHS | CARAGA | Surigao Del Norte | 317810 | Cawilan Nhs-Annex | Tagana-An | 2 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2182367 |  |  | Completed | 1 |  |  | P00072836MN | 16NF0081 | 2016-06-09 | 2016-06-17 | 2016-06-29 |  |  | MYMS CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304820 | Claver Nhs | Claver | 2 | 1 | 30 | 2STY10CL | BATCH 3 CL | 41816264.88 |  |  | Completed | 1 |  |  | P00070259MN
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304820 | Claver Nhs | Claver | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00070733MN | 16NF0039 | 2016-03-03 | 2016-03-11 | 2016-03-29 | 2016-05-16 | 2016-06-13 | CARTESIAN BUILDERS
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 317808 | Dakung Patag Nhs | Sison | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132325 | Ferlda Es | Alegria | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072826MN | 16NF0025 | 2016-02-26 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-07-04 | AMA CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304826 | Gigaquit Nat'L. Sch. Of Home Industries | Gigaquit | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Norte | 304835 | Hacienda Nhs | Mainit | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8498924.81 |  |  | Completed | 1 |  |  | P00070263MN | 16NF0059 | 2016-05-28 | 2016-06-03 | 2016-06-16 |  |  | MYMS CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304835 | Hacienda Nhs | Mainit | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00070735MN | 16NF0038 | 2016-03-03 | 2016-03-11 | 2016-03-23 | 2016-05-13 | 2016-06-06 | MYMS CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304838 | Lakandula Nhs | Placer | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7321271.404 |  |  | Completed | 1 |  |  | P00072835MN | 16NF0070 | 2016-06-03 | 2016-06-10
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132382 | Lapinigan Es | Claver | 2 | 1 | 2 | 1STY1CL | BATCH 9 CL | 2426509.2394 |  |  | Completed | 1 |  |  | P00072828MN | 16NF0043 | 2016-03-03 | 2016-03-11 | 2016-06-03 | 2016-06-13 | 2016-07-04 | AMA CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 317804 | Lasicam - Perral National High School | Gigaquit | 2 | 1 | 4 | 1STY2CL | BATCH 3 CL | 4167940.04 |  |  | Completed | 1 |  |  | P00070262MN | 16NF0036 | 2016-02-22 | 2016-03-11 | 2016-03-23 | 2016-05-13 | 2016-06-06 | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132349 | Little Baguio Es | Bacuag | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072827MN | 16NF0030 | 2016-07-01 | 2016-07-08 | 2016-07-21 |  |  | AMA CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 317803 | Magpayang Nhs | Mainit | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304829 | Mainit Nhs | Mainit | 2 | 1 | 16 | 2STY8CL | BATCH 3 CL | 22992674.84 |  |  | Completed | 1 |  |  | P00070264MN | 16NF0078 | 2016-05-28 | 2016-06-15
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304829 | Mainit Nhs | Mainit | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00070736MN | 16NF0041 | 2016-02-22 | 2016-03-11 | 2016-03-23 | 2016-05-16 | 2016-06-06 | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132436 | Marayag Ps | Mainit | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072833MN | 16NF0027 | 2016-02-22 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-07-04 | MYMS CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304831 | Masgad Nhs | Malimono | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 7069337.64 |  |  | Completed | 1 |  |  | P00071267MN | 16NF0072 | 2016-06-03 | 2016-06-10
NC 2016 | K10 | CARAGA | Surigao Del Norte | 304834 | Matin-Ao National High School | Mainit | 2 | 1 | 12 | 2STY12CL | BATCH 7 CL | 15896662.05 |  |  | Completed | 1 |  |  | P00071781MN | 16NF0047 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | CV CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304834 | Matin-Ao National High School | Mainit | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5299483.5 |  |  | Completed | 1 |  |  | P00072557MN | 16NF0048 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | CV CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 304850 | Mayag National High School | Sison | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6869337.64 |  |  | Completed | 1 |  |  | P00071269MN | 16NF0052 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | AMA CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304830 | Paco Nhs | Mainit | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2083970.02 |  |  | Completed | 1 |  |  | P00071266MN | 16NF0024 | 2016-02-26 | 2016-03-04 | 2016-06-27 | 2016-07-12 |  | MYMS CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 317807 | Pananay-An Nhs - Annex (Placer Nhs) | Placer | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6669337.64 |  |  | Completed | 1 |  |  | P00071270MN | 16NF0051 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | RF VARQUEZ CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132546 | Patiño Es | Tagana-An | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072837MN | 16NF0029 | 2016-02-22 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-07-04 | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 317806 | Payapag Nhs | Bacuag | 2 | 1 | 12 | 2STY6CL | BATCH 3 CL | 16997849.62 |  |  | Completed | 1 |  |  | P00070261MN | 16NF0053 | 2016-05-23 | 2016-06-01 | 2016-06-13 |  |  | ALGAMON CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304819 | Pili National High School | Malimono | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8798924.81 |  |  | Completed | 1 |  |  | P00071265MN | 16NF0073 | 2016-06-03 | 2016-06-10 | 2016-06-23 | 2016-07-01 | 2016-07-18 | MIGO CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304837 | Placer Nhs | Placer | 2 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16997849.62 |  |  | Completed | 1 |  |  | P00071268MN | 16NF0049 | 2016-05-20 | 2016-05-27 | 2016-06-09 | 2016-06-17 | 2016-07-08 | ALGAMON CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304837 | Placer Nhs | Placer | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00071708MN | 16NF0064 | 2016-05-27 | 2016-06-03 | 2016-06-16 | 2016-06-27 | 2016-07-08 | ALGAMON CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 214007 | Punta Naga Elementary School | Claver | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1213254.6197 |  |  | Completed | 1 |  |  | P00072829MN | 16NF0031 | 2016-02-22 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-07-04 | MYMS CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304843 | San Francisco Nhs | San Francisco (Anao-Aon) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2649741.75 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132444 | San Jose Es | Mainit | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2083970.02 |  |  | Completed | 1 |  |  | P00071263MN | 16NF0023 | 2016-02-22 | 2016-03-04 | 2016-03-17 | 2016-05-11 | 2016-06-24 | AT DUMLAO CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132463 | Sohoton Es | Malimono | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1224580.0817 |  |  | Completed | 1 |  |  | P00072834MN | 16NF0026 | 2016-02-22 | 2016-03-04 | 2016-06-03 | 2016-06-13 | 2016-06-29 | MIGO CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte |  | Stand Alone 1 | Alegria | 2 | 1 | 20 | 2STY10CL | BATCH 3 CL | 27877509.92 |  |  | Completed | 1 |  |  | P00070258MN | 16NF0056 | 2016-05-23 | 2016-06-01 | 2016-06-13 | 2016-06-24 |  | FH GOPITEO CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte |  | Stand Alone 1 | Alegria | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00070732MN | 16NF0037 | 2016-03-03 | 2016-03-11 | 2016-03-23 | 2016-05-16 | 2016-05-30 | MIGO CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304847 | Surigao Del Norte Nhs | Surigao City (Capital) | 2 | 1 | 48 | 4STY12CL | BATCH 11 CL | 89409374.48 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304812 | Tagana-An Nhs (Asa Nhs) | Tagana-An | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304821 | Taganito Nhs | Claver | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Norte | 317809 | Talavera National High School | Tagana-An | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7049337.64 |  |  | Completed | 1 |  |  | P00072838MN | 16NF0075 | 2016-06-09 | 2016-06-15 | 2016-06-27 |  |  | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 317809 | Talavera National High School | Tagana-An | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 9068924.81 |  |  | Completed | 1 |  |  | P00072839MN | 16NF0077 | 2016-06-09 | 2016-06-15 | 2016-06-27 |  |  | MYMS CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 132388 | Tayawod Es | Claver | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1113254.6197 |  |  | Completed | 1 |  |  | P00072830MN | 16NF0046 | 2016-03-03 | 2016-03-11 | 2016-06-03 | 2016-06-13 | 2016-07-04 | AMA CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 304849 | Toledo S. Pantilo Sr. Mnhs | Sison | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8274965.051 |  |  | Completed | 1 |  |  | P00070189MN | 16NF0018 | 2016-02-15 | 2016-02-24 | 2016-03-07 | 2016-05-10 | 2016-06-01 | MIGO CONSTRUCTION
NC 2016 | K10 | CARAGA | Surigao Del Norte | 304849 | Toledo S. Pantilo Sr. Mnhs | Sison | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6379337.6381 |  |  | Completed | 1 |  |  | P00070180MN | 16NF0019 | 2016-02-15 | 2016-02-24 | 2016-03-07 | 2016-05-10 | 2016-06-01 | CARTESIAN BUILDERS
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304849 | Toledo S. Pantilo Sr. Mnhs | Sison | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2669741.75 |  |  | Completed | 1 |  |  | P00070189MN | 16NF0020 | 2016-02-15 | 2016-02-24 | 2016-03-07 | 2016-05-10 | 2016-06-01 | MIGO CONSTRUCTION
NC 2016 | SHS | CARAGA | Surigao Del Norte | 304855 | Tubod Nhs | Tubod | 2 | 1 | 12 | 2STY6CL | BATCH 3 CL | 16997849.62 |  |  | Completed | 1 |  |  | P00070265MN | 16NF0060 | 2016-05-28 | 2016-06-03 | 2016-06-29 | 2016-06-28 |  | ALGAMON CONSTRUCTION
NC 2016 | TECHVOC | CARAGA | Surigao Del Norte | 304855 | Tubod Nhs | Tubod | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2649741.75 |  |  | Completed | 1 |  |  | P00070737MN | 16NF0040 | 2016-03-03 | 2016-03-11 | 2016-03-23 | 2016-05-18 | 2016-05-31 | ASJ BUILDERS
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304861 | Barobo National High School | Barobo | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21413013.45 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304889 | Gamut National High School (Tago) | Tago | 1 | 1 | 12 | 2STY12CL | BATCH 5 CL | 15205996.11 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304889 | Gamut National High School (Tago) | Tago | 1 |  | 8 | 2STY8CL | BATCH 5 CL | 11371397.03 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304895 | Lingig National High School | Lingig | 1 | 1 | 18 | 3STY18CL | BATCH 1 CL | 25298250 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304897 | Madrid National High School | Madrid | 1 | 1 | 20 | 2STY10CL | BATCH 1 CL | 27942620 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304897 | Madrid National High School | Madrid | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304860 | Barcelona National High School | Lingig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 317909 | Bingcongan Integrated Secondary School | Hinatuan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304862 | Cabacungan National High School | Barobo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304879 | Dante Luib Osano Maputi National High School | Tagbina | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2603250 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304888 | Gamut National School (Barobo) | Barobo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Surigao Del Sur | 304890 | Hinatuan National Comprehensive High School | Hinatuan | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 317940 | Hinatuan National Comprehensive High School - (Cambatong Nhs Annex) | Hinatuan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304863 | Javier National High School | Barobo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 317910 | Loyola National High School | Hinatuan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 317932 | Malixi Integrated School | Tagbina | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304882 | San Vicente Ii National High School | Tagbina | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 304884 | Tagbina National High School | Tagbina | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | CARAGA | Surigao Del Sur | 317921 | Wakat National High School | Barobo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Tandag City | 304871 | Buenavista Nhs | City Of Tandag (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 1 CL | 12771310.093 |  |  | Completed | 1
NC 2016 | SHS | CARAGA | Tandag City | 304871 | Buenavista Nhs | City Of Tandag (Capital) | 1 |  | 12 | 2STY6CL | BATCH 1 CL | 16429930.102 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Tandag City | 304922 | Tandag Nat'L. Sci Hs | City Of Tandag (Capital) | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13241664.54 |  |  | Completed | 1
NC 2016 | K10 | CARAGA | Tandag City | 304922 | Tandag Nat'L. Sci Hs | City Of Tandag (Capital) | 1 |  | 16 | 2STY8CL | BATCH 5 CL | 22675101.06 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131507 | Agong-ong ES | BUENAVISTA | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 4038819.26 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131553 | Labong Elementary School | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 4369110.57 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131421 | Gosoon ES | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2796941.14 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131433 | Jabonga CES | JABONGA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2823456.3 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131435 | Juan L. Subrastas ES | JABONGA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2967295.66 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131455 | Zapanta Valley PS | KITCHARAO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2930336.14 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131490 | Aclan ES | NASIPIT | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2930336.14 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131495 | Culit ES | NASIPIT | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3946147.97 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131500 | Nasipit CES | NASIPIT | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 5492814.7 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131502 | Sta. Ana ES | NASIPIT | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 4167180.38 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131505 | Triangulo ES | NASIPIT | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2910451.77 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131535 | San Antonio ES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2940670.13 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131542 | Monte De Oro Elementary School | SANTIAGO | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 4529846.55 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131547 | Villa Serrano ES | SANTIAGO | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2827979.19 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131585 | DOÑA TELESFORA ES | TUBAY | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3977695.19 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 3108915 |  |  | Completed | 1 |  |  |  | 17NI0053 | 2017-12-05 | 2017-12-12 | 2017-09-11 | 2017-09-14 | 2017-09-22 | Mark Anthony Const. & Supply
NC 2017 | K10 | CARAGA | Bislig City | 132629 | R. Castillo ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 3086039 |  |  | Completed | 1 |  |  |  | 17NI0055 | 2017-12-05 | 2017-12-12 | 2017-09-11 | 2017-09-14 | 2017-09-22 | MN Bayalas Const.
NC 2017 | K10 | CARAGA | Bislig City | 322508 | San Fernando Integrated School | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 3086039 |  |  | Completed | 1 |  |  |  | 17NI0054 | 2017-12-05 | 2017-12-12 | 2017-09-11 | 2017-09-14 | 2017-09-22 | Mark Anthony Const. & Supply
NC 2017 | K10 | CARAGA | Butuan City | 132084 | Bagong Silang ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2796947.86 |  |  | Completed | 1 |  |  | P00170523MN-CW1 | 17ND0068 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2017 | K10 | CARAGA | Butuan City | 132064 | Bugabus Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2865792.15 |  |  | Completed | 1 |  |  | P00170524MN-CW1 | 17ND0069 | 2017-07-27 | 2017-03-08 | 2017-08-22 |  | 2017-12-21 | LBL TRAFFIC CONTROL & CONSTRUCTION SERVICES
NC 2017 | K10 | CARAGA | Butuan City | 212505 | Datu Man-Oloy Tribal ES | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2767996.09 |  |  | Completed | 1 |  |  | P00170525MN-CW1 | 17ND0074 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2017 | K10 | CARAGA | Butuan City | 132071 | Dona Josefa Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2846464.76 |  |  | Completed | 1 |  |  | P00170526MN_CW1 | 17ND0070 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2017 | K10 | CARAGA | Butuan City | 132056 | Doongan Elementary School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2846464.76 |  |  | Completed | 1 |  |  | P00170527MN-CW1 | 17ND0071 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-12-07 | 2017-12-21 | RAMISES CONSTRUCTION
NC 2017 | K10 | CARAGA | Butuan City | 132033 | Dugyaman ES | BUTUAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4181659.68 |  |  | Completed | 1 |  |  | P00170528MN-CW1 | 17ND0075 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | JOAN CONSTRUCTION
NC 2017 | K10 | CARAGA | Butuan City | 132074 | F.R. Sibayan Central Elem. School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2673373.48 |  |  | Completed | 1 |  |  | P00170529MN_CW1 | 17ND0072 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | JOAN CONSTRUCTION
NC 2017 | K10 | CARAGA | Butuan City | 132094 | Lamosig E/S | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2920517.81 |  |  | Completed | 1 |  |  | P00170530MN-CW1 | 17ND0073 | 2017-07-27 | 2017-03-08 | 2017-08-22 | 2017-09-18 | 2017-10-04 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2017 | K10 | CARAGA | Dinagat Island | 132308 | Bolodbolod Central ES | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2615000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132521 | Matingbe Elementary School | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2615000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132558 | Sta Cruz ES | TUBAJON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 3150000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132217 | Burgos CES | BURGOS | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 5900000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Siargao | 304773 | Burgos NHS | BURGOS | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4500000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Siargao | 304774 | Dapa NHS | DAPA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132143 | San Miguel ES | DAPA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132134 | Union ES | DAPA | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 5900000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132148 | Consuelo ES | GENERAL LUNA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132181 | Caridad ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132190 | Pilar CES | PILAR | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4500000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132190 | Pilar CES | PILAR | 1 |  | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132230 | San Benito CES | SAN BENITO | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 5900000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132198 | Roxas ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132201 | Sta. Paz ES | SAN ISIDRO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132206 | Alegria ES | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132235 | Pamosaingan ES | SOCORRO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3200000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132224 | Socorro CES | SOCORRO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4500000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Norte | 132324 | Camp Edward ES | ALEGRIA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2715410.85 |  |  | Completed | 1 |  |  | 17NF0029 |  |  | 2017-07-14 | 2017-07-27
NC 2017 | K10 | CARAGA | Surigao del Norte | 214009 | Landing ES | GIGAQUIT | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2768670.25 |  |  | Completed | 1 |  |  | 17NF0028 |  |  | 2017-07-14 | 2017-07-27
NC 2017 | SHS | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2743181.72 |  |  | Completed | 1 |  |  | 17NF0024 |  |  | 2017-07-14 | 2017-07-27 |  |  | R.F. Varquez Construction
NC 2017 | SHS | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2662080.95 |  |  | Completed | 1 |  |  | 17NF0030 |  |  | 2017-07-14 | 2017-07-27 |  |  | R.F. Varquez Construction
NC 2017 | K10 | CARAGA | Surigao del Sur | 132647 | Cempron ES | CAGWAIT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132658 | Cabangahan Elementary School | CANTILAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3192590 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 317915 | Cabangahan Integrated Secondary School | CANTILAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3192590 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304873 | Cantilan National High School | CANTILAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132661 | Cantilan Pilot ES | CANTILAN | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 6188100 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132663 | Magasang Elementary School | CANTILAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304857 | Adlay National High School | CARRASCAL | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4410025 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304857 | Adlay National High School | CARRASCAL | 1 |  | 3 | 1STY3CL | BATCH 2 | 4410025 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Tandag City | 132978 | Tandag CES | CITY OF TANDAG (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4811950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Tandag City | 132978 | Tandag CES | CITY OF TANDAG (Capital) | 1 |  | 3 | 1STY3CL | BATCH 2 | 4811950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132707 | Burgos ES | CORTES | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4611950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132709 | Cortes CES | CORTES | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4811950 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304887 | Tigao National High School | CORTES | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3124420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132763 | Lanuza CES | LANUZA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132765 | Nurcia ES | LANUZA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 317901 | Nurcia ISS | LANUZA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132771 | Diatagon Barangay ES | LIANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4811950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132776 | Lianga CES | LIANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4811950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132777 | Manyayay MG Demo School | LIANGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3274420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132852 | Marihatag CES | MARIHATAG | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 214529 | Hamburger Elementary School | SAN AGUSTIN | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4661950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132866 | Salvacion Elementary School | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2122600 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132868 | Sto. Nino ES | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 214539 | Carromata Elementary School of Living Tradition | SAN MIGUEL | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4661950 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 214541 | Kiskis Elementary School of Living Tradition | SAN MIGUEL | 1 | 1 | 5 | 1STY5CL | BATCH 2 | 8062330 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132887 | San Miguel CES | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304908 | San Miguel National High School | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3274420 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 214517 | Tambonon Elementary School | SAN MIGUEL | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3219420 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304889 | Gamut NHS (Tago) | TAGO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3324420 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4060000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 500313 | F. S. Omayana NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8080000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304685 | Jabonga NHS | JABONGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 4100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3545896.685 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3545896.685 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Norte | 131475 | New Cana-an ES | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3196958.1 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 | 1 | 2 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 8080000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304673 | Agay National High School | REMEDIOS T. ROMUALDEZ | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8132000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 4 | 4100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 317309 | Dona Rosario NHS - Tubay NHS Annex | TUBAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4040000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Sur | 131650 | BROOKSIDE ELEMENTARY SCHOOL | BUNAWAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3463080.32 |  |  | Completed | 1 |  |  | 17NC0096 | 17NC0096 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131658 | Mambalili ES | BUNAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3036167.99 |  |  | Completed | 1 |  |  | 17NC0091 | 17NC0091 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131664 | Upper Consuelo I ES | BUNAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2893662.17 |  |  | Completed | 1 |  |  | 17NC0079 | 17NC0079 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131665 | West Bunawan CES | BUNAWAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4450314.25 |  |  | Completed | 1 |  |  | 17NC0099 | 17NC0099 | [5 empty] | MRS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 317427 | Nueva Gracia Nhs | LORETO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3067375.11 |  |  | Completed | 1 |  |  | 17NC0108 | 17NC0108 | [5 empty] | DAVE CONSTRUCTION
NC 2017 | SHS | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3433900.25 |  |  | Completed | 1 |  |  | 17NC0101 | 17NC0101 | [5 empty] | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131814 | Bonifacio CES | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2850257.2 |  |  | Completed | 1 |  |  | 17NC0077 | 17NC0077 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131814 | Bonifacio CES | ROSARIO | 2 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4306754.23 |  |  | Completed | 1 |  |  | 17NC0102 | 17NC0102 | [5 empty] | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131814 | Bonifacio CES | ROSARIO | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3433900.25 |  |  | Completed | 1 |  |  | 17NC0097 | 17NC0097 | [5 empty] | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131816 | Cabantao ES | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2784571.17 |  |  | Completed | 1 |  |  | 17NC0087 | 17NC0087 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131817 | Cabawan ES | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2953873.65 |  |  | Completed | 1 |  |  | 17NC0088 | 17NC0088 | [5 empty] | DDS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3783880.16 |  |  | Completed | 1 | [9 empty] | ROIM BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3783880.16 |  |  | Completed | 1 | [9 empty] | ROIM BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 212014 | J.A. Morales ES | ROSARIO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3433900.25 |  |  | Completed | 1 |  |  | 17NC0095 | 17NC0095 | [5 empty] | MAIR CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131822 | Maligaya ES | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2784571.17 |  |  | Completed | 1 |  |  | 17NC0082 | 17NC0082 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | AGUERRO CONSTRUCTION
NC 2017 | SHS | CARAGA | Agusan del Sur | 317429 | Novele National High School | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3073125.72 |  |  | Completed | 1 |  |  | 17NC0090 | 17NC0090 | [5 empty] | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131832 | Wasian ES | ROSARIO | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4253768.49 |  |  | Completed | 1 |  |  | 17NC0100 | 17NC0100 | [5 empty] | LM CONSTRUCTION
NC 2017 | TVL | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3047375.11 |  |  | Completed | 1 |  |  | 17NC0111 | 17NC0111 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131849 | Buena Suerte ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2953873.65 |  |  | Completed | 1 |  |  | 17NC0085 | 17NC0085 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | DDS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131851 | Caimpugan ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2953873.65 |  |  | Completed | 1 |  |  | 17NC0086 | 17NC0086 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | MRS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 304711 | Democrito O. Plaza MHS | SAN FRANCISCO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3057375.11 |  |  | Completed | 1 |  |  | 17NC0103 | 17NC0103 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131838 | Karaos ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3401076.04 |  |  | Completed | 1 |  |  | 17NC0098 | 17NC0098 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131839 | Ladgadan ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2989742.68 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Sur | 131853 | Lapinigan CES with SPED Program | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2989742.68 |  |  | Completed | 1 |  |  | 17NC0093 | 17NC0093 | [5 empty] | DDS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 212032 | Dao Elementary School | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2758777.01 |  |  | Completed | 1 |  |  | 17NC0070 | 17NC0070 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | MRS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 317419 | Sayon NHS | SANTA JOSEFA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3067375.11 |  |  | Completed | 1 |  |  | 17NC0105 | 17NC0105 | [5 empty] | DAVE CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131932 | Simeon S. Castor ES | SANTA JOSEFA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2803374.53 |  |  | Completed | 1 |  |  | 17NC0094 | 17NC0094 | [5 empty] | MAIR CONSTRUCTION
NC 2017 | TVL | CARAGA | Agusan del Sur | 304750 | Sta. Josefa National High School | SANTA JOSEFA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3067375 |  |  | Completed | 1 |  |  | 17NC0106 | 17NC0106 | [5 empty] | SMB
NC 2017 | TVL | CARAGA | Agusan del Sur | 304750 | Sta. Josefa National High School | SANTA JOSEFA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3067375 |  |  | Completed | 1 |  |  | 17NC0107 | 17NC0107 | [5 empty] | ASCOF
NC 2017 | K10 | CARAGA | Agusan del Sur | 131996 | Basa ES | TRENTO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4189677.17 |  |  | Completed | 1 |  |  | 17NC0084 | 17NC0084 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 212030 | Cogonon ES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2758777.01 |  |  | Completed | 1 |  |  | 17NC0072 | 17NC0072 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131999 | Cuevas ES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2758777.01 |  |  | Completed | 1 |  |  | 17NC0069 | 17NC0069 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 132003 | Langkila-an ES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2758777.01 |  |  | Completed | 1 |  |  | 17NC0071 | 17NC0071 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | LM CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 132005 | Manat ES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2758777.01 |  |  | Completed | 1 |  |  | 17NC0073 | 17NC0073 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | MAIR CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 132008 | Pulanglupa ES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2770303.94 |  |  | Completed | 1 |  |  | 17NC0089 | 17NC0089 | [5 empty] | LM CONSTRUCTION
NC 2017 | TVL | CARAGA | Agusan del Sur | 317437 | Salvacion NHS | TRENTO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3067375.11 |  |  | Completed | 1 |  |  | 17NC0104 | 17NC0104 | [5 empty] | MRS BUILDERS
NC 2017 | SHS | CARAGA | Agusan del Sur | 317443 | San Isidro National High School | TRENTO | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5039357.91 |  |  | Completed | 1 |  |  | 17NC0083 | 17NC0083 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | ROIM BUILDERS
NC 2017 | SHS | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2835153.14 |  |  | Completed | 1 |  |  | 17NC0080 | 17NC0080 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | MRS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3047375.11 |  |  | Completed | 1 |  |  | 17NC0109 | 17NC0109 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 132019 | Trento West CES | TRENTO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2835153.14 |  |  | Completed | 1 |  |  | 17NC0081 | 17NC0081 | 2017-09-15 | 2017-09-22 | 2017-05-10 |  |  | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131898 | Baubo ES | VERUELA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2832729.15 |  |  | Completed | 1 |  |  | 17NC0078 | 17NC0078 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | DDS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131903 | Don Mateo ES | VERUELA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2778327.08 |  |  | Completed | 1 |  |  | 17NC0074 | 17NC0074 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | DDS BUILDERS
NC 2017 | SHS | CARAGA | Agusan del Sur | 317406 | La Fortuna NHS | VERUELA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2778327.08 |  |  | Completed | 1 |  |  | 17NC0075 | 17NC0075 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | AGUERRO CONSTRUCTION
NC 2017 | K10 | CARAGA | Agusan del Sur | 131910 | Logum ES | VERUELA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2778327.08 |  |  | Completed | 1 |  |  | 17NC0076 | 17NC0076 | 2017-08-09 | 2017-09-15 | 2017-09-28 |  |  | DDS BUILDERS
NC 2017 | TVL | CARAGA | Agusan del Sur | 304754 | Veruela NHS | VERUELA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3124750 |  |  | Completed | 1 |  |  | 17NC0110 | 17NC0110 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Bayugan City | 212012 | Datu Hugmakan ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2893330 |  |  | Completed | 1 |  |  | P00172436MN-CW1 | 17NB0175 | 2017-11-24 | 2017-12-01 | 2017-12-13 | 2017-12-22 | 2018-01-09 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 131599 | Hamogaway ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3197070 |  |  | Completed | 1 |  |  | P00172428MN-CW1 | 17NB0167 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 131604 | Mt Carmel ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3036130 |  |  | Completed | 1 |  |  | P00172429MN-CW1 | 17NB0168 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | LM CONSTRUCTION & GENERAL MARKETING
NC 2017 | K10 | CARAGA | Bayugan City | 131605 | Mt. Olive ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3010085 |  |  | Completed | 1 |  |  | P00172430MN-CW1 | 17NB0169 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 212003 | New Katipunan ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3368650 |  |  | Completed | 1 |  |  | P00172435MN-CW1 | 17NB0174 | 2017-11-24 | 2017-12-01 | 2017-12-13 | 2017-12-22 | 2018-01-09 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2017 | SHS | CARAGA | Bayugan City | 304728 | Noli National High School | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3197070 |  |  | Completed | 1 |  |  | P00172437MN-CW1 | 17NB0176 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 131610 | Pinagala-an ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3010085 |  |  | Completed | 1 |  |  | P00172431MN-CW1 | 17NB0170 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | ABADA CONSTRUCTION
NC 2017 | K10 | CARAGA | Bayugan City | 131640 | San Juan ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3236750 |  |  | Completed | 1 |  |  | P00172432MN-CW1 | 17NB0171 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 131640 | San Juan ES | CITY OF BAYUGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 3236750 |  |  | Completed | 1 |  |  | P00172433MN-CW1 | 17NB0172 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Bayugan City | 131640 | San Juan ES | CITY OF BAYUGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 3236750 |  |  | Completed | 1 |  |  | P00172434MN-CW1 | 17NB0173 | 2017-09-27 | 2017-10-05 | 2017-10-17 | 2017-11-13 | 2017-11-29 | DATREBIL CONSTRUCTION & SUPPLY
NC 2017 | TVL | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2913585.87 |  |  | Completed | 1 |  |  | P00172440MN-CW1 | 17ND0090 | 2017-09-28 | 2017-05-10 | 2017-10-19 | 2017-11-21 | 2017-12-01 | ABADA CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Butuan City | 132060 | Alviola CES | BUTUAN CITY (Capital) | 1 | 1 | 5 | 1STY5CL | BATCH 4 | 6276899.43 |  |  | Completed | 1 |  |  | P00172438MN-CW1 | 17ND0084 | 2017-09-21 | 2017-09-28 | 2017-10-10 |  | 2017-12-21 | HMARI CONSTRUCTION SERVICES
NC 2017 | K10 | CARAGA | Butuan City | 132060 | Alviola CES | BUTUAN CITY (Capital) | 1 |  | 3 | 1STY3CL | BATCH 4 | 4078881.99 |  |  | Completed | 1 |  |  | P00172439MN_CW1 | 17ND0083 | 2017-09-21 | 2017-09-28 | 2017-10-10 | 2017-10-23 | 2017-11-21 | KELVIN CONSTRUCTION
NC 2017 | TVL | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3033103.4 |  |  | Completed | 1 |  |  | P00172441MN-CW1 | 17ND0096 | 2017-10-04 | 2017-11-10 | 2017-10-23 | 2017-11-21 | 2017-12-01 | J-R3 CONSTRUCTION AND SUPPLY
NC 2017 | TVL | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2939018.48 |  |  | Completed | 1 |  |  | P00172442MN-CW1 | 17ND0091 | 2017-09-28 | 2017-05-10 | 2017-10-19 | 2017-11-21 | 2017-12-01 | ETP BUILDERS
NC 2017 | TVL | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3051814.4 |  |  | Completed | 1 |  |  | P00172448MN_CW1 | 17ND0093 | 2017-09-28 | 2017-05-10 | 2017-10-19 | 2017-11-21 | 2017-12-12 | J-R3 CONSTRUCTION AND SUPPLY
NC 2017 | TVL | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3033103.4 |  |  | Completed | 1 |  |  | P00172450MN-CW1 | 17ND0097 | 2017-10-04 | 2017-11-10 | 2017-10-23 | 2017-11-21 | 2017-12-01 | J-R3 CONSTRUCTION AND SUPPLY
NC 2017 | TVL | CARAGA | Butuan City | 304764 | Los Angeles National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3181384.85 |  |  | Completed | 1 |  |  | P00172443MN-CW1 | 17ND0099 | 2017-10-04 | 2017-11-10 | 2017-10-23 | 2017-11-21 | 2017-12-01 | TWO ACES CONSTRUCTION AND SUPPLY
NC 2017 | TVL | CARAGA | Butuan City | 317505 | Maibu National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3814154.38 |  |  | Completed | 1 |  |  | P00172446MN-CW1 | 17ND0101 | 2017-10-04 | 2017-11-10 | 2017-10-23 | 2017-11-21 | 2017-12-12 | JOSELLE CONSTRUCTION
NC 2017 | TVL | CARAGA | Butuan City | 317505 | Maibu National High School | BUTUAN CITY (Capital) | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2965125.46 |  |  | Completed | 1 |  |  | P00172447MN-CW1 | 17ND0092 | 2017-09-28 | 2017-05-10 | 2017-10-19 | 2017-11-21 | 2017-12-01 | BN BUILDERS & CONSTRUCTION SUPPLIES
NC 2017 | TVL | CARAGA | Butuan City | 317520 | Pedro D. Duncano National HS | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 2894856.11 |  |  | Completed | 1 |  |  | P00172451MN-CW1 | 17ND0089 | 2017-09-28 | 2017-05-10 | 2017-10-19 | 2017-11-21 | 2017-12-01 | WILLTORR CONSTRUCTION
NC 2017 | TVL | CARAGA | Butuan City | 317508 | Pinamanculan National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3156738.63 |  |  | Completed | 1 |  |  | P00172449MN-CW1 | 17ND0098 | 2017-10-04 | 2017-11-10 | 2017-10-23 | 2017-11-21 | 2017-12-01 | WILLTORR CONSTRUCTION
NC 2017 | TVL | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3804113.49 |  |  | Completed | 1 |  |  | P00172444MN-CW1 | 17ND0100 | 2017-10-04 | 2017-11-10 | 2017-10-23 |  | 2017-12-21 | ME3 CONSTRUCTION
NC 2017 | TVL | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 | 1 | 1 | WORKSHOP BLDG. (7X18) | BATCH 4 | 4077015.85 |  |  | Completed | 1 |  |  | P00172445MN_CW1 | 17ND0102 | 2017-10-04 | 2017-11-10 | 2017-10-23 |  | 2017-12-01 | ABADA CONSTRUCTION & SUPPLY
NC 2017 | K10 | CARAGA | Cabadbaran City | 281003 | Dagnasay Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2875798.88 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304895 | Lingig NHS | LINGIG | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3278900.55 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3548156.82 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 4 | 10115330 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304881 | Maglatab National High School | TAGBINA | 2 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 4 | 9925532 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Agusan del Norte | 304687 | Jaliobong NHS | KITCHARAO | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 5 | 4100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 131528 | Puting Bato Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | BATCH 5 | 2851942.44 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304696 | Nasipit National Vocational School | NASIPIT | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2817728.37 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Agusan del Sur | 131696 | Anolingan ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0223 | 17NB0223 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131698 | Casanaag ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0224 | 17NB0224 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131701 | Concordia ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2851355 |  |  | Completed | 1 |  |  | 17NB0225 | 17NB0225 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 212072 | DOP KIBUKAY IP SCHOOL (IPA) | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2831745 |  |  | Completed | 1 |  |  | 17NB0234 | 17NB0234 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131673 | ESPERANZA CENTRAL ELEMENTARY SCHOOL | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0201 | 17NB0201 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131675 | Hawilian ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3022455 |  |  | Completed | 1 |  |  | 17NB0202 | 17NB0202 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131681 | Maasin ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0231 | 17NB0231 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131682 | Milagros ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0203 | 17NB0203 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | SHS | CARAGA | Agusan del Sur | 317423 | Nato National High School | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0230 | 17NB0230 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131708 | Odiong Elementary School | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2798360 |  |  | Completed | 1 |  |  | 17NB0226 | 17NB0226 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131709 | Oro ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2865125 |  |  | Completed | 1 |  |  | 17NB0227 | 17NB0227 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131686 | Remedios ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2785840 |  |  | Completed | 1 |  |  | 17NB0204 | 17NB0204 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131687 | Salug ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0222 | 17NB0222 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131693 | Sta Fe ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0205 | 17NB0205 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 212007 | Valentina ES | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0228 | 17NB0228 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131771 | Asuncion ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0182 | 17NB0182 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | SHS | CARAGA | Agusan del Sur | 317444 | Aurora Nhs | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3197070 |  |  | Completed | 1 |  |  | 17NB0181 | 17NB0181 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131774 | Cordova ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3217185 |  |  | Completed | 1 |  |  | 17NB0206 | 17NB0206 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131775 | East Prosperidad Central Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2942935 |  |  | Completed | 1 |  |  | 17NB0183 | 17NB0183 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131777 | La Fortuna Eementary School | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2864340 |  |  | Completed | 1 |  |  | 17NB0207 | 17NB0207 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131778 | Las Navas ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3217185 |  |  | Completed | 1 |  |  | 17NB0184 | 17NB0184 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131780 | Mapaga Elementary School | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2969815 |  |  | Completed | 1 |  |  | 17NB0185 | 17NB0185 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131805 | Salimbogaon ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0208 | 17NB0208 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131783 | San Agustin ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0186 | 17NB0186 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131783 | San Agustin ES | PROSPERIDAD (Capital) | 1 |  | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0187 | 17NB0187 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131784 | San Jose ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB018 | 17NB0188 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131784 | San Jose ES | PROSPERIDAD (Capital) | 1 |  | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0189 | 17NB0189 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | SHS | CARAGA | Agusan del Sur | 304749 | Sta. Irene National High School | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0180 | 17NB0180 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131810 | Sta. Maria ES | PROSPERIDAD (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0179 | 17NB0179 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131941 | Coalicion ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3010085 |  |  | Completed | 1 |  |  | 17NB0209 | 17NB0209 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131942 | Culi Elementary School | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0210 | 17NB0210 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131943 | Datu Bandahan ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2798365 |  |  | Completed | 1 |  |  | 17NB0211 | 17NB0211 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131944 | Datu Sandigan ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0212 | 17NB0212 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131945 | Dimasalang ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0198 | 17NB0198 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131956 | Mahayahay ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2865125 |  |  | Completed | 1 |  |  | 17NB0213 | 17NB0213 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131958 | Nuevo Trabajo ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0199 | 17NB0199 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131961 | San Jose ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0200 | 17NB0200 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131872 | Kolambugan ES | SIBAGAT | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2712245 |  |  | Completed | 1 |  |  | 17NB0214 | 17NB0214 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131878 | New Tubigon ES | SIBAGAT | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2737790 |  |  | Completed | 1 |  |  | 17NB0215 | 17NB0215 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131971 | Causwagan ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0192 | 17NB0192 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131972 | Cebuna ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2686695 |  |  | Completed | 1 |  |  | 17NB0216 | 17NB0216 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131973 | Concillo ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0217 | 17NB0217 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | SHS | CARAGA | Agusan del Sur | 317422 | Corpuz NHS | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2672940 |  |  | Completed | 1 |  |  | 17NB0221 | 17NB0221 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131978 | Desamparados ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0193 | 17NB0193 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131979 | Don Flaviano ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2983265 |  |  | Completed | 1 |  |  | 17NB0190 | 17NB0190 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131980 | F.E. Lopez ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2942945 |  |  | Completed | 1 |  |  | 17NB0191 | 17NB0191 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131981 | Kabakahan ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3236750 |  |  | Completed | 1 |  |  | 17NB0218 | 17NB0218 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131982 | Kasilayan Elementary School | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2686695 |  |  | Completed | 1 |  |  | 17NB0219 | 17NB0219 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131984 | Labnig ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2627740 |  |  | Completed | 1 |  |  | 17NB0194 | 17NB0194 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | SHS | CARAGA | Agusan del Sur | 317432 | Labnig NHS | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2758715 |  |  | Completed | 1 |  |  | 17NB0197 | 17NB0197 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 131987 | Marbon ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0195 | 17NB0195 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Agusan del Sur | 212059 | San Isidro Elementary School | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2969825 |  |  | Completed | 1 |  |  | 17NB0220 | 17NB0220 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131994 | Zamora ES | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2647390 |  |  | Completed | 1 |  |  | 17NB0196 | 17NB0196 | 2017-10-23 | 2017-10-30 | 2017-11-23 | 2017-05-12 | 2017-12-28
NC 2017 | K10 | CARAGA | Bislig City | 132607 | Balingan ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 11633277 |  |  | Completed | 1 |  |  |  | 17NI0081 | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-21 | 2017-12-29 | Aguero Construction
NC 2017 | K10 | CARAGA | Bislig City | 235002 | BCD SPED Center | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 13755287 |  |  | Completed | 1 |  |  |  | 17NI0078 | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-21 | 2017-12-29 | Thearis Builders & Supply
NC 2017 | K10 | CARAGA | Bislig City | 132837 | Mangagoy South ES | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 14224755 |  |  | Completed | 1 |  |  |  | 17NI0185 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Thearis Builders & Supply
NC 2017 | K10 | CARAGA | Bislig City | 132627 | Puerto PS | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9856496 |  |  | Completed | 1 |  |  |  | 17NI0085 | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-21 | 2017-12-29 | Mark Anthony Const. & Supply
NC 2017 | SHS | CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 14418044 |  |  | Completed | 1 |  |  |  | 17NI0077 | 2017-11-27 | 2017-12-05 | 2017-12-18 | 2017-12-21 | 2017-12-29 | MN Bayalas Const.
NC 2017 | K10 | CARAGA | Cabadbaran City | 131528 | Puting Bato Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2851942.44 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132357 | Borja ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132358 | Cabiton-an PS | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132362 | Lahi ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132363 | Legaspi ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132365 | Maatas ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132372 | Tigbao ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132374 | Valencia ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132392 | Bagumbayan ES | DINAGAT | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132395 | Cayetano ES | DINAGAT | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132399 | Magsaysay ES | DINAGAT | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132402 | Wadas ES | DINAGAT | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132424 | Loreto CES | LORETO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 324405 | Panamaon NHS Annex | LORETO | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132518 | Justiniana Edera ES | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132552 | Imelda ES | TUBAJON | 0 | 1 | 2 | 1STY2CL | BATCH 7 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132556 | Navarro ES | TUBAJON | 0 | 1 | 3 | 1STY3CL | BATCH 7 | 3900000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304793 | Alegria NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3410083.73 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304794 | Caraga Regional Science HS | SURIGAO CITY (Capital) | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 19987981.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304795 | Ipil NHS | SURIGAO CITY (Capital) | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 18875527.74 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304792 | Juan P. Cedro Sr. Memorial High Schoo | SURIGAO CITY (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 10240491.93 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 317703 | Libuac NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3285755.21 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 317704 | Lipata National High School | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3092430.44 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 317704 | Lipata National High School | SURIGAO CITY (Capital) | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 18995527.74 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304799 | Mat-i National High School | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3059844.71 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304799 | Mat-i National High School | SURIGAO CITY (Capital) | 2 |  | 4 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 20021611.61 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984987.56 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304801 | Surigao City NHS | SURIGAO CITY (Capital) | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 19987981.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 304806 | Zaragoza National High School | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3385755.21 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Norte | 304811 | Alegria NHS | ALEGRIA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9840491.93 |  |  | Completed | 1 |  |  | 17NF0097 | [6 empty] | MIGO Construction
NC 2017 | SHS | CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 | 1 | 10 | 2STY10CL | BATCH 7 | 21958249.37 |  |  | Completed | 1 |  |  | 17FN0152 | [6 empty] | FH GOPITEO Construction and Supply
NC 2017 | TVL | CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 19017455.97 |  |  | Completed | 1 |  |  | 17FN0144 | [6 empty] | FH GOPITEO Construction and Supply
NC 2017 | TVL | CARAGA | Surigao del Norte | 317806 | Payapag NHS | BACUAG | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 18925527.74 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304821 | Taganito NHS | CLAVER | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 20147981.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3426275.38 |  |  | Completed | 1 |  |  | 17NF0113 | [6 empty] | JMT Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0138 | [6 empty] | AMA Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0137 | [6 empty] | ASJ Builders
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0136 | [6 empty] | CG Builders
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0135 | [6 empty] | CG Builders
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0134 | [6 empty] | AMA Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0133 | [6 empty] | AMA Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0132 | [6 empty] | AMA Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0131 | [6 empty] | JMT Consruction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0130 | [6 empty] | JMT Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3176613.07 |  |  | Completed | 1 |  |  | 17NF0129 | [6 empty] | JMT Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304835 | Hacienda NHS | MAINIT | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3028778.9 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304835 | Hacienda NHS | MAINIT | 2 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9887534.75 |  |  | Completed | 1 |  |  | 17NF0163 |  |  |  | 2017-12-28
NC 2017 | TVL | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3009316.08 |  |  | Completed | 1 | [9 empty] | MYMS Construction and Supply
NC 2017 | TVL | CARAGA | Surigao del Norte | 317803 | Magpayang NHS | MAINIT | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 19159384.2 |  |  | Completed | 1 |  |  | 17NF0148 | [6 empty] | C.V. Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3171169.89 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3171169.89 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304829 | Mainit NHS | MAINIT | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 20271838.37 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304834 | Matin-ao National High School | MAINIT | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 18989070.32 |  |  | Completed | 1 | [9 empty] | ALGAMON Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304830 | Paco NHS | MAINIT | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 7 | 9925648.87 |  |  | Completed | 1 |  |  | 17NF0164 |  |  |  | 2017-12-28
NC 2017 | TVL | CARAGA | Surigao del Norte | 304832 | Bunyasan NHS | MALIMONO | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3185204.26 |  |  | Completed | 1 | [9 empty] | MIGO Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3118287.97 |  |  | Completed | 1 |  |  | 17NF0122 | [6 empty] | MIGO Construction
NC 2017 | K10 | CARAGA | Surigao del Norte | 132476 | Pananay-an ES | PLACER | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10010805.81 |  |  | Completed | 1 |  |  | 17NF0099 | [6 empty] | MIGO Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 317807 | Pananay-an NHS - Annex (Placer NHS) | PLACER | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3051637.76 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Norte | 132478 | Placer CES | PLACER | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10010805.81 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3051637.76 |  |  | Completed | 1 | [9 empty] | R.F. Varquez Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3178120.19 |  |  | Completed | 1 | [9 empty] | ALGAMON Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1 |  |  | 17NF0112 | [6 empty] | Cartesian Builders
NC 2017 | TVL | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1 |  |  | 17NF0111 | [6 empty] | Cartesian Builders
NC 2017 | TVL | CARAGA | Surigao del Norte | 304814 | Balite NHS | SAN FRANCISCO (ANAO-AON) | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 19980983.86 |  |  | Completed | 1 |  |  | 17NF0143 | [6 empty] | C.V. Construction and Development
NC 2017 | SHS | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9840491.93 |  |  | Completed | 1 |  |  | 17NF0096 | [6 empty] | J.M.T. Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1 |  |  | 17NF0154 |  |  | 2017-12-14 | 2017-12-28 |  |  | J.M.T. Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3003233.95 |  |  | Completed | 1 |  |  | 17NF0155 |  |  | 2017-12-14 | 2017-12-28
NC 2017 | TVL | CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS | SISON | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3192721.44 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. MNHS | SISON | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3118287.97 |  |  | Completed | 1 |  |  | 17NF0156 |  |  | 2017-12-14 | 2017-12-28
NC 2017 | TVL | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3031000.565 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3031000.565 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3031000.565 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304847 | Surigao Del Norte NHS | SURIGAO CITY (Capital) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3031000.565 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 13191784.82 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3021480.34 |  |  | Completed | 1 |  |  | 17NF0118 | [6 empty] | A.T.C.D.I.
NC 2017 | TVL | CARAGA | Surigao del Norte | 304853 | Timamana National High School | TUBOD | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 7 | 18875527.74 |  |  | Completed | 1 |  |  | 17NF0142
NC 2017 | TVL | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3604736.195 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3604736.195 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132569 | Amaga ES | BAROBO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3139514.47 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132571 | Bahi ES | BAROBO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4301434.93 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132580 | Gamut ES | BAROBO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3139514.47 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132597 | Tambis CES | BAROBO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3139514.47 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132599 | Wakat Elementary School | BAROBO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3139514.47 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 317924 | Baculin Integrated Secondary School | HINATUAN | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10027280 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 317940 | Cambatong National High School | HINATUAN | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10027280 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 317940 | Cambatong National High School | HINATUAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 3067657.61 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 11580291 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 |  | 8 | 2STY8CL | BATCH 7 | 20196043 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132735 | Hinatuan South CES | HINATUAN | 2 | 1 | 10 | 2STY10CL | BATCH 7 | 22476654 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy National High School | HINATUAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2992307.41 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132755 | Tidman ES | HINATUAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3184448.57 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132785 | Antonio A. Orozco Elem. School | LINGIG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3169438.89 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132786 | Barcelona CES | LINGIG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 11635906 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132799 | Mandus ES | LINGIG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3187253.58 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132898 | Kahayagan ES | TAGBINA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3139514.47 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 317932 | Malixi Integrated School | TAGBINA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4267368.21 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132922 | Sta. Maria ES | TAGBINA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3105543.61 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 317935 | Sta. Maria Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3056753.99 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao del Sur | 132924 | Tagbina CES | TAGBINA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9912111 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4267368.21 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10016081 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 317315 | Agong-ong NHS (Buenavista NHS Annex | BUENAVISTA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 3048896.86 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 3048896.86 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 500313 | F. S. Omayana NHS (Buenavista NHS Annex) | BUENAVISTA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 2855000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304682 | Guinabsan NHS | BUENAVISTA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 2892534.79 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304702 | Vinapor NHS | CARMEN | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 3028689.4 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304687 | Jaliobong NHS | KITCHARAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 2895000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Norte | 304701 | Tubay NHS | TUBAY | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 3330000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 | 1 | 3 | 1STY3CL | BATCH 8 | 6701734.18 |  |  | Completed | 1 |  |  | 18NC0035 | 18NC0035 | [5 empty] | LM CONSTRUCTION
NC 2017 | SHS | CARAGA | Agusan del Sur | 304747 | Datu Lipus Makapandong National High School | ROSARIO | 2 |  | 4 | 1STY4CL | BATCH 8 | 8721271.81 |  |  | Completed | 1 |  |  | 18NC0036 | 18NC0036 | [5 empty] | MRS BUILDERS
NC 2017 | K10 | CARAGA | Agusan del Sur | 131899 | Binongan ES | VERUELA | 2 | 1 | 2 | 1STY2CL | BATCH 8 | 4631040.27 |  |  | Completed | 1 |  |  | 18NC0034 | 18NC0034 | [5 empty] | MRS BUILDERS
NC 2017 | SHS | CARAGA | Butuan City | 317511 | Ampayon National High School | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2757924.36 |  |  | Completed | 1 |  |  | P00177740MN_CW1 | 17ND0109 | 2017-11-09 | 2017-11-16 | 2017-12-07 | 2017-12-15 | 2017-12-21 | OLIN DEV'T. ENGINEERING & CONSTRUCTION
NC 2017 | SHS | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2846464.57 |  |  | Completed | 1 |  |  | P00177739MN_CW1 | 17ND0110 | 2017-11-09 | 2017-11-16 | 2017-12-07 | 2017-12-15 | 2017-12-21 | QUADCON BUILDERS AND DESIGN
NC 2017 | K10 | CARAGA | Agusan del Sur | 212072 | DOP KIBUKAY IP SCHOOL (IPA) | ESPERANZA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2831745 |  |  | Completed | 1 |  |  | 17NB0229 | 17NB0229 | 2017-11-14 | 2017-11-23 | 2017-05-12 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131969 | Wegguam ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2686695 |  |  | Completed | 1 |  |  | 17NB0235 | 17NB0235 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131969 | Wegguam ES | SAN LUIS | 1 |  | 2 | 1STY2CL | BATCH 10 | 2686695 |  |  | Completed | 1 |  |  | 17NB0236 | 17NB0236 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131887 | Sibagat CES | SIBAGAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2608090 |  |  | Completed | 1 |  |  | 17NB0237 | 17NB0237 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 131887 | Sibagat CES | SIBAGAT | 1 |  | 2 | 1STY2CL | BATCH 10 | 2608090 |  |  | Completed | 1 |  |  | 17NB0237 | 17NB0237 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 212060 | San Roque Elementary School | TALACOGON | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2647390 |  |  | Completed | 1 |  |  | 17NB0239 | 17NB0239 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Agusan del Sur | 212060 | San Roque Elementary School | TALACOGON | 1 |  | 2 | 1STY2CL | BATCH 10 | 2647390 |  |  | Completed | 1 |  |  | 17NB0240 | 17NB0240 | 2017-11-28 |  | 2017-12-13 | 2017-12-22
NC 2017 | K10 | CARAGA | Bislig City | 132608 | Bebiano Alba ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3342112 |  |  | Completed | 1 |  |  |  | 17NI0166 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | MN Bayalas Const.
NC 2017 | K10 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 11776630 |  |  | Completed | 1 |  |  |  | 17NI0187 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | RDF Const. & Supply
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3331423.365 |  |  | Completed | 1 |  |  |  | 17NI0183 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3331423.365 |  |  | Completed | 1 |  |  |  | 17NI0183 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3339057.595 |  |  | Completed | 1 |  |  |  | 17NI0182 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3339057.595 |  |  | Completed | 1 |  |  |  | 17NI0182 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 2 | REGULAR WORKSHOP BLDG. | BATCH 10 | 7066687.26 |  |  | Completed | 1 |  |  |  | 17NI0181 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304865 | Bislig City NHS | CITY OF BISLIG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3988444.94 |  |  | Completed | 1 |  |  |  | 17NI0156 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | JM Lacorte Construction
NC 2017 | K10 | CARAGA | Bislig City | 322506 | Bislig City NHS Coleto Annex | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3484107 |  |  | Completed | 1 |  |  |  | 17NI0163 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Aguero Construction
NC 2017 | TVL | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 | 1 | 2 | ICT LABORATORY | BATCH 10 | 6491214.91 |  |  | Completed | 1 |  |  |  | 17NI0191 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Abada Construction & Supply
NC 2017 | TVL | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 |  | 2 | SCIENCE LABORATORY | BATCH 10 | 6459919.79 |  |  | Completed | 1 |  |  |  | 17NI0192 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Aguero Construction
NC 2017 | TVL | CARAGA | Bislig City | 322503 | Bucto NHS | CITY OF BISLIG | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 7845294.11 |  |  | Completed | 1 |  |  |  | 17NI0155 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Abada Construction & Supply
NC 2017 | K10 | CARAGA | Bislig City | 132611 | Burboanan ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3602676 |  |  | Completed | 1 |  |  |  | 17NI0164 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Mag Corporation
NC 2017 | K10 | CARAGA | Bislig City | 132614 | DELOT ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3563546 |  |  | Completed | 1 |  |  |  | 17NI0162 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | MN Bayalas Const.
NC 2017 | K10 | CARAGA | Bislig City | 132633 | Gaspar-Serrano ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3342112 |  |  | Completed | 1 |  |  |  | 17NI0165 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3385261.16 |  |  | Completed | 1 |  |  |  | 17NI0207 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | RNH Bentulan Construction
NC 2017 | TVL | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 |  | 2 | SCIENCE LABORATORY | BATCH 10 | 6578205.53 |  |  | Completed | 1 |  |  |  | 17NI0190 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | RNH Bentulan Construction
NC 2017 | TVL | CARAGA | Bislig City | 304894 | Lawigan NHS | CITY OF BISLIG | 2 |  | 3 | REGULAR WORKSHOP BLDG. | BATCH 10 | 10821193.02 |  |  | Completed | 1 |  |  |  | 17NI0170 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | RNH Bentulan Construction
NC 2017 | TVL | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 | 1 | 2 | ICT LABORATORY | BATCH 10 | 6632915.62 |  |  | Completed | 1 |  |  |  | 17NI0184 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Two Degrees Const. & Supply
NC 2017 | TVL | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3278173.21 |  |  | Completed | 1 |  |  |  | 17NI0208 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | MN Bayalas Const.
NC 2017 | TVL | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3592503.36 |  |  | Completed | 1 |  |  |  | 17NI0197 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | MN Bayalas Const.
NC 2017 | TVL | CARAGA | Bislig City | 322505 | Mabog National High School | CITY OF BISLIG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3911981.58 |  |  | Completed | 1 |  |  |  | 17NI0157 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | MN Bayalas Const.
NC 2017 | TVL | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9840629 |  |  | Completed | 1 |  |  |  | 17NI0178 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Jimberns Builders & Consruction Supply
NC 2017 | TVL | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9865209 |  |  | Completed | 1 |  |  |  | 17NI0107 | 2017-11-29 | 2017-12-07 | 2017-12-20 | 2017-12-23 | 2017-12-31 | Jimberns Builders & Consruction Supply
NC 2017 | TVL | CARAGA | Bislig City | 304866 | Maharlika NHS | CITY OF BISLIG | 2 |  | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 9804959 |  |  | Completed | 1 |  |  |  | 17NI0133 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Jimberns Builders & Consruction Supply
NC 2017 | TVL | CARAGA | Bislig City | 304919 | Mangagoy NHS | CITY OF BISLIG | 2 | 1 | 3 | 3STY WORKSHOP BLDG (7X18) | BATCH 10 | 15553979 |  |  | Completed | 1 |  |  |  | 17NI0101 | 2017-11-29 | 2017-12-07 | 2017-12-20 | 2017-12-23 | 2017-12-31 | LM Construction
NC 2017 | K10 | CARAGA | Bislig City | 235003 | New Bongga Elementary School | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3751193 |  |  | Completed | 1 |  |  |  | 17NI0159 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Jimberns Builders & Consruction Supply
NC 2017 | K10 | CARAGA | Bislig City | 132626 | Pamaypayan ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3833779 |  |  | Completed | 1 |  |  |  | 17NI0158 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | RNH Bentulan Construction
NC 2017 | K10 | CARAGA | Bislig City | 132628 | R. Castillo ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3739459 |  |  | Completed | 1 |  |  |  | 17NI0160 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | JM Lacorte Construction
NC 2017 | K10 | CARAGA | Bislig City | 132634 | San Nicolas ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3583298 |  |  | Completed | 1 |  |  |  | 17NI0161 | 2017-11-30 | 2017-12-08 | 2017-12-21 | 2017-12-24 | 2018-01-02 | Mag Corporation
NC 2017 | TVL | CARAGA | Bislig City | 304869 | Sikahoy NHS | CITY OF BISLIG | 2 | 1 | 2 | SCIENCE LABORATORY | BATCH 10 | 3464800.63 |  |  | Completed | 1 |  |  |  | 17NI0203 | 2017-12-01 | 2017-12-09 | 2017-12-22 | 2017-12-27 | 2018-01-03 | Jimberns Builders & Consruction Supply
NC 2017 | TVL | CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 7995495.48 |  |  | Completed | 1 |  |  |  | 17NI0127 | 2017-11-29 | 2017-12-07 | 2017-12-20 | 2017-12-23 | 2017-12-31 | MN Bayalas Const.
NC 2017 | TVL | CARAGA | Bislig City | 340306 | Stand Alone SHS | CITY OF BISLIG | 2 |  | 3 | 3STY WORKSHOP BLDG (7X18) | BATCH 10 | 17072090 |  |  | Completed | 1 |  |  |  | 17NI0097 | 2017-11-29 | 2017-12-07 | 2017-12-20 | 2017-12-23 | 2017-12-31 | Legacy Construction Corporation
NC 2017 | K10 | CARAGA | Cabadbaran City | 281004 | Ansili Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3292957.45 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2710424.51 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 281002 | Masundong Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3986922.23 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 281001 | Palidan Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3986922.23 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 131527 | Pirada ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2851942.44 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 131528 | Puting Bato Elementary School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2851942.44 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132485 | Capasanan ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132503 | Puerto Princesa ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132503 | Puerto Princesa ES | BASILISA (RIZAL) | 0 |  | 5 | 1STY2CL & 1STY3CL | BATCH 10 | 7260000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304852 | Rita-Glenda National High School | BASILISA (RIZAL) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304842 | Rizal NHS - Puerto Princesa - Moleta NHS Annex | BASILISA (RIZAL) | 0 | 1 | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304842 | Rizal NHS - Puerto Princesa - Moleta NHS Annex | BASILISA (RIZAL) | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304842 | Rizal NHS - Puerto Princesa - Moleta NHS Annex | BASILISA (RIZAL) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2850000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304842 | Rizal NHS - Puerto Princesa - Moleta NHS Annex | BASILISA (RIZAL) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2850000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132507 | Sering ES | BASILISA (RIZAL) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132507 | Sering ES | BASILISA (RIZAL) | 0 |  | 5 | 1STY2CL & 1STY3CL | BATCH 10 | 7260000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 | 1 | 3 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 13104000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 |  | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304851 | Tag-abaca NHS | BASILISA (RIZAL) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | CAGDIANAO | 0 | 1 | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | CAGDIANAO | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | CAGDIANAO | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | CAGDIANAO | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3300000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304816 | Del Pilar National High School | CAGDIANAO | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3300000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 | 1 | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304840 | R. E. Ecleo Sr. NHS | CAGDIANAO | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132368 | R.E. Ecleo Sr. ES | CAGDIANAO | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3900000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132371 | Sto Nino ES | CAGDIANAO | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3900000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 | 1 | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324406 | Primitivo J. Ebol Memorial National High School | DINAGAT | 0 |  | 2 | WORKSHOP BLDG. (7X18) | BATCH 10 | 6200000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132305 | Albor Central ES | LIBJO | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4700000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132305 | Albor CES | LIBJO (ALBOR) | 0 |  | 3 | 1STY3CL | BATCH 10 | 4700000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 10277661.6 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 | 1 | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324401 | Llamera NHS | LIBJO (ALBOR) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132318 | Quezon ES | LIBJO (ALBOR) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 | 1 | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132422 | Ferdinand ES | LORETO | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 3360000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132426 | Panamaon ES | LORETO | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3900000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 | 1 | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2900000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2900000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304825 | Cuarenta NHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | 10 | 2STY10CL | BATCH 10 | 26493078.14 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2800000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3000000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132517 | Jacquez Primary School | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 10 | 9540000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132522 | San Jose CES-SPED Center | SAN JOSE (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 10 | 12300000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132523 | San Juan Elementary School | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 10 | 9540000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 | 1 | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 |  | 1 | 1STY UNIQUE WORKSHOP BLDG. | BATCH 10 | 5138830.8 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317805 | Trinidad Mapa-Gupana NHS | TUBAJON | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 | 1 | 4 | 2STY ICT LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 10 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 |  | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304854 | Tubajon NHS | TUBAJON | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132219 | San Mateo Elementary School | BURGOS | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132132 | Osmeña ES | DAPA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132187 | Maasin ES | PILAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132227 | Nuevo Campo Elementary Schoool | SAN BENITO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132228 | Pitogo Elementary School | SAN BENITO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Siargao | 132222 | Lanit-ag PS | SOCORRO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Surigao City | 132272 | Surigao City Pilot Sch. | SURIGAO CITY (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 41549450.51 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 340383 | Surigao City Stand Alone | SURIGAO CITY (Capital) | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 19987981.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao City | 317707 | Wilfredo D. Rafols Mem. NHS | SURIGAO CITY (Capital) | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 10067557.1 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 340416 | Alegria Stand Alone Senior High School | ALEGRIA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3224895.9 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3051637.76 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3051637.76 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304813 | Bacuag Nat'L Agro-Indust'L Sch. | BACUAG | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36411885.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3378301.26 |  |  | Completed | 1 |  |  | 17NF0076 | [6 empty] | MIGO Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3051637.76 |  |  | Completed | 1 |  |  | 17NF0075 | [6 empty] | MIGO Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3051637.76 |  |  | Completed | 1 |  |  | 17NF0048 | [6 empty] | MIGO Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304817 | Campo NHS | BACUAG | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36371885.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 317806 | Payapag NHS | BACUAG | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3193287.97 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3273805.11 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3273805.11 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3273805.11 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3273805.11 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3273805.11 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304820 | Claver NHS | CLAVER | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36776885.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304821 | Taganito NHS | CLAVER | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3212721.44 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304821 | Taganito NHS | CLAVER | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3212721.44 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3426275.38 |  |  | Completed | 1 |  |  | 17NF0078 | [6 empty] | C.V. Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304826 | Gigaquit Nat'l. Sch. of Home Industries | GIGAQUIT | 2 |  | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36541885.91 |  |  | Completed | 1 |  |  | 17NF0080 | [6 empty] | Charlz Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 317804 | Lasicam - Perral National High School | GIGAQUIT | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 13271784.82 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304845 | Amando A. Fabio MNHS | PLACER | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 34864768.69 |  |  | Completed | 1 |  |  | 17NF0084 | [6 empty] | ALGAMON Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 304837 | Placer NHS | PLACER | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36411885.91 |  |  | Completed | 1 |  |  | 17NF0149 | [6 empty] | BLIMEX Construction and Supply
NC 2017 | TVL | CARAGA | Surigao del Norte | 304843 | San Francisco NHS | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 19680983.86 |  |  | Completed | 1 |  |  | 17NF0087 | [6 empty] | ALGAMON Construction
NC 2017 | TVL | CARAGA | Surigao del Norte | 317808 | Dakung Patag NHS | SISON | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 10 | 36261885.91 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304850 | Mayag National High School | SISON | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 26013569.64 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304849 | Toledo S. Pantilo Sr. MNHS | SISON | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 13006784.82 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Norte | 304855 | Tubod NHS | TUBOD | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 10 | 20603975.79 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304862 | Cabacungan National High School | BAROBO | 2 | 1 | 6 | 3STY WORKSHOP BLDG (7X18) | BATCH 10 | 30181341 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304863 | Javier National High School | BAROBO | 2 | 1 | 2 | 2STY SCIENCE BLDG. | BATCH 10 | 10206306 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304863 | Javier National High School | BAROBO | 2 |  | 2 | 2STY ICT LAB BLDG. | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317941 | Rizal National High School | BAROBO | 2 | 1 | 6 | 2UNITS 3STY BLDG. REGULAR WORKSHOP, SCIENCE LAB & ICT LAB | BATCH 10 | 30378714 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304864 | Tambis National High School | BAROBO | 2 | 1 | 6 | 2UNITS 3STY BLDG. REGULAR WORKSHOP, SCIENCE LAB & ICT LAB | BATCH 10 | 34393228 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317921 | WAKAT NATIONAL HIGH SCHOOL | BAROBO | 2 | 1 | 2 | 1UNIT 2STY BLDG. (REGULAR WORKSHOP & SCIENCE LAB) | BATCH 10 | 9926276 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317921 | WAKAT NATIONAL HIGH SCHOOL | BAROBO | 2 |  | 3 | 1UNIT 3STY BLDG. REGULAR WORKSHOP, SCIENCE LAB & ICT LAB | BATCH 10 | 15378598 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317924 | Baculin Integrated Secondary School | HINATUAN | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3476783.7 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317924 | Baculin Integrated Secondary School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317924 | Baculin Integrated Secondary School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 10130362 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304921 | Bigaan National High School | HINATUAN | 2 | 1 | 3 | 2UNITS 3STY BLDG. (REGULAR WORKSHOP, SCIENCE & ICT LAB) | BATCH 10 | 29295150 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317909 | Bingcongan Integrated Secondary School | HINATUAN | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3506980.02 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317909 | Bingcongan Integrated Secondary School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317909 | Bingcongan Integrated Secondary School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 9860347 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317909 | Bingcongan Integrated Secondary School | HINATUAN | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 10 | 3939745.27 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317940 | Cambatong National High School | HINATUAN | 2 | 1 | 2 | 1UNIT 2STY BLDG. (REGULAR WORKSHOP & SCIENCE LAB) | BATCH 10 | 9832311 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317940 | Cambatong National High School | HINATUAN | 2 |  | 3 | 1UNIT 3STY BLDG. (SCIENCE LAB & ICT LAB) | BATCH 10 | 15217520 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 | 1 | 2 | 1UNIT 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 9840629 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304891 | Dugmanon National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 | 1 | 3 | 1UNIT 3STY REGULAR WORKSHOP BLDG. | BATCH 10 | 16357006 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 10232473 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304890 | Hinatuan National Comprehensive High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 11730041 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317939 | Hinatuan National Comprehensive High School - Roxas National High School Annex | HINATUAN | 2 | 1 | 3 | 2UNITS 3STY BLDG. (REGULAR WORKSHOP, SCIENCE & ICT LAB) | BATCH 10 | 29332138 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317910 | Loyola National High School | HINATUAN | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3393556.76 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317910 | Loyola National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317910 | Loyola National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304902 | Portlamon Pastor Uy National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 11511692 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304920 | Tagasaka National High School | HINATUAN | 2 | 1 | 2 | 1UNIT 2STY SCIENCE LABORATORY BLDG. | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304920 | Tagasaka National High School | HINATUAN | 2 |  | 2 | 1UNIT 2STY ICT LABORATORY BLDG. | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317926 | Tarusan Integrated Secondary School | HINATUAN | 2 | 1 | 6 | 2UNITS 3STY BLDG. (REGULAR WORKSHOP, SCIENCE & ICT LAB) | BATCH 10 | 30322486 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304923 | Tidman National High School | HINATUAN | 2 | 1 | 2 | 1UNIT 2STY BLDG. (REGULAR WORKSHOP & SCIENCE LAB) | BATCH 10 | 11545017 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304923 | Tidman National High School | HINATUAN | 2 |  | 3 | 1UNIT 3STY BDLG. (SCIENCE & ICT LAB.) | BATCH 10 | 17253042 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317930 | Anibongan Integrated Secondary School | LINGIG | 2 | 1 | 2 | 1UNIT 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 10024471 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317930 | Anibongan Integrated Secondary School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 10137190 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317930 | Anibongan Integrated Secondary School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9966272 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304860 | Barcelona National High School | LINGIG | 2 | 1 | 2 | REGULAR WORKSHOP BLDG. | BATCH 10 | 7126693.92 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304860 | Barcelona National High School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 11865619 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304860 | Barcelona National High School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 11673005 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304895 | Lingig National High School | LINGIG | 2 | 1 | 3 | 1UNIT 3STY REGULAR WORKSHOP BLDG. | BATCH 10 | 17018655 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304896 | M.K.Yusingco National High School | LINGIG | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 11504217 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304896 | M.K.Yusingco National High School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 11378926 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated Secondary School | LINGIG | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3511621.02 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated Secondary School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 10163781 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500327 | Rajah Cabungsuan Integrated Secondary School | LINGIG | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 11511692 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated Secondary School | TAGBINA | 2 | 1 | 3 | 1UNIT 3STY REGULAR WORKSHOP BLDG. | BATCH 10 | 15251359 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500326 | Carpenito Integrated Secondary School | TAGBINA | 2 |  | 1 | TVL UNIQUE WORKSHOP BLDG. | BATCH 10 | 3977801.62 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4018863.62 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 |  | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3727107.48 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 10115330 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304879 | Dante Luib Osano Maputi National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 10088493 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304878 | Doña Carmen National High School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304878 | Doña Carmen National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317938 | Jobar Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 10289215 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317938 | Jobar Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 10055901 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3434734.56 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304880 | Kahayagan National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 10169974 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500324 | Maglambing Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500324 | Maglambing Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317932 | Malixi Integrated School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (REGULAR WORKSHOP & SCIENCE LAB) | BATCH 10 | 11545017 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317932 | Malixi Integrated School | TAGBINA | 2 |  | 3 | 1UNIT 3STY BLDG. (SCIENCE LAB & ICT LAB) | BATCH 10 | 17245246 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317936 | Manambia Integrated Secondary School | TAGBINA | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3589333.62 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317936 | Manambia Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317936 | Manambia Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317927 | Osmeña Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317927 | Osmeña Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500325 | Quary 1 Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 2UNITS 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 20180050 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500325 | Quary 1 Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 500325 | Quary 1 Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317934 | Quezon Integrated Secondary School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317934 | Quezon Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304882 | San Vicente II National High School | TAGBINA | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3505869.12 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304882 | San Vicente II National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304882 | San Vicente II National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 | 1 | 2 | 1UNIT 2STY REGULAR WORKSHOP BLDG. | BATCH 10 | 9840629 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 10206305 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304883 | Sta. Juana National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 10007012 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317935 | Sta. Maria Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 317935 | Sta. Maria Integrated Secondary School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 | 1 | 1 | REGULAR WORKSHOP BLDG. | BATCH 10 | 3434734.56 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (SCIENCE LAB) | BATCH 10 | 9865209 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Surigao del Sur | 304884 | Tagbina National High School | TAGBINA | 2 |  | 2 | 1UNIT 2STY BLDG. (ICT LAB) | BATCH 10 | 9804959 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City |  | Dagsanay ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2845798.88 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 330102 | Lusong National High School | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3139827.56 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304836 | Melgar National High School | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304836 | Melgar National High School | BASILISA (RIZAL) | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324404 | New Nazareth NHS | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324404 | New Nazareth NHS | BASILISA (RIZAL) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324404 | New Nazareth NHS | BASILISA (RIZAL) | 0 |  | 1 | 1STY REGULAR WORKSHOP BLDG. | BATCH 13 | 4368000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304841 | Rizal NHS | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304844 | Sering NHS | BASILISA (RIZAL) | 0 | 1 | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | 0 | 1 | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 317802 | Valencia National High School | CAGDIANAO | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304809 | Osmeña-Sto. Niño National High School | LIBJO (ALBOR) | 0 | 1 | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304809 | Osmeña-Sto. Niño National High School | LIBJO (ALBOR) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) | 0 | 1 | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Dinagat Island | 340528 | LORETO NHS | LORETO | 0 | 1 | 8 | 2STY8CL | BATCH 13 | 24718416.09 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 340528 | LORETO NHS | LORETO | 0 |  | 2 | 2STY REGULAR WORKSHOP BLDG. | BATCH 13 | 35244000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 132513 | Aurelio ES | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 13 | 9540000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Dinagat Island | 324402 | Jade B. Ecleo- Aurelio National High School | SAN JOSE (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 13 | 13555185 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324407 | Malinao National High School | TUBAJON | 0 | 1 | 4 | 2STY REGULAR WORKSHOP BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324407 | Malinao National High School | TUBAJON | 0 |  | 4 | 2STY SCIENCE LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | TVL | CARAGA | Dinagat Island | 324407 | Malinao National High School | TUBAJON | 0 |  | 4 | 2STY ICT LABORATORY BLDG. | BATCH 13 | 17622000 |  |  | Completed | 1
NC 2017 | K10 | CARAGA | Cabadbaran City | 131527 | Pirada ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 287885.12 |  |  | Completed | 1
NC 2017 | SHS | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 295734.33 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131472 | Maningalao ES | LAS NIEVES | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2939718.45 |  |  | Completed | 1 |  |  | P00270107MN-CW1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131480 | Tinucoran ES | LAS NIEVES | 1 | 1 | 4 | 1STY4CL | BATCH 1 | 7325610.83 |  |  | Completed | 1 |  |  | P00270108MN-CW1
NC 2018 | TVL | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 | 1 | 8 | 2STY8CL (2 SCILAB & 2 ICT LAB) | BATCH 1 | 17484082.27 |  |  | Completed | 1 |  |  | P00270109MN-CW1
NC 2018 | TVL | CARAGA | Agusan del Norte | 304689 | Las Nieves NHS | LAS NIEVES | 1 |  | 6 | 3STY6CL (3 REG. WORKSHOP) | BATCH 1 | 16274692.55 |  |  | Completed | 1 |  |  | P00270110MN-CW1
NC 2018 | TVL | CARAGA | Agusan del Norte | 317310 | E. G. Montilla NHS (Mat-I NHS Annex) | LAS NIEVES | 1 | 1 | 4 | 2STY4CL (2 SCI. LAB) | BATCH 1 | 9991536.59 |  |  | Completed | 1 |  |  | P00270111MN-CW1
NC 2018 | TVL | CARAGA | Agusan del Norte | 500048 | Lawan-Lawan NHS | LAS NIEVES | 1 | 1 | 8 | 2STY8CL (2 SCILAB & 2 ICT LAB) | BATCH 1 | 18103944.4 |  |  | Completed | 1 |  |  | P00270112MN-CW1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131423 | Rojales ES | CARMEN | 2 | 1 | 4 | 2STY4Cl with handwashing facility | Batch 3 | 11056394.94 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131429 | BANGONAY CES | JABONGA | 2 | 1 | 6 | 2STY6CL with handwashing facility | Batch 3 | 15085277.9 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131485 | Magallanes CES | MAGALLANES | 2 | 1 | 10 | 2STY10CL with handwashing facility | Batch 3 | 26731061.66 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131493 | Camagong ES | NASIPIT | 2 | 1 | 6 | 2STY6CL with handwashing facility | Batch 3 | 15086777.9 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131512 | Matabao ES | BUENAVISTA | 2 | 1 | 6 | 2-UNITS 1STY3CL with Toilet Attached with handwashing facility | Batch 3 | 10632543.748 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131534 | RT Romualdez CES | REMEDIOS T. ROMUALDEZ | 2 | 1 | 10 | 2-UNITS 1STY5CL with Toilet Attached with handwashing facility | Batch 3 | 14445758.98 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131558 | Macalang ES | BUENAVISTA | 2 | 1 | 6 | 2-UNITS 1STY3CL with Toilet Attached with handwashing facility | Batch 3 | 8760130.68 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Agusan del Norte | 131565 | RIZAL CES | BUENAVISTA | 2 | 1 | 8 | 2STY8CL with handwashing facility | Batch 3 | 26787648.2 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Agusan del Norte | 304674 | Buenavista NHS | BUENAVISTA | 2 | 1 | 9 | 3STY9CL with handwashing facility | Batch 3 | 29619981.24 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Agusan del Norte | 304686 | Jagupit NHS | SANTIAGO | 2 | 1 | 16 | 4STY16CL with handwashing facility | Batch 3 | 56043304.33 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Agusan del Norte | 317317 | Rizal NHS (Guinabsan NHS Annex) | BUENAVISTA | 2 | 1 | 6 | 2STY6CL with handwashing facility | Batch 3 | 15125702.9 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Agusan del Norte | 500047 | Buenavista SPED IS | BUENAVISTA | 2 | 1 | 4 | 2STY4CL with handwashing facility | Batch 3 | 11198394.94 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Agusan del Norte | 500047 | Buenavista SPED ES | BUENAVISTA | 2 |  | 8 | 2STY8CL with handwashing facility | Batch 3 | 23451648.2 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Agusan del Sur | 304717 | Lapinigan National High School | SAN FRANCISCO | 2 | 1 | 12 | 2 SCIENCE/LAB, 2 ICT, 2 REGULAR WORKSHOP (9.50MX64.00M) | BATCH 1 | 28576799.17 |  |  | Completed | 1 |  |  |  | 18NC0089 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-08-20 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 304718 | Libertad NHS | BUNAWAN | 2 | 1 | 8 | 2 SCIENCE/LAB, 2 ICT (9.50MX46.00M) | BATCH 1 | 22708240.95 |  |  | Completed | 1 |  |  |  | 18NC0096 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-08-20 | ROIM BUILDERS/LM CONTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 304719 | Loreto NHS | LORETO | 2 | 1 | 8 | 2 SCIENCE/LAB, 2 ICT (9.50MX46.00M) | BATCH 1 | 20173585.63 |  |  | Completed | 1 |  |  |  | 18NC0098 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 304733 | Sampaguita National High Schools | VERUELA | 2 | 1 | 16 | 2 SCIENCE/LAB, 2 ICT, 4 REGULAR WORKSHOP (9.50MX46.00M) | BATCH 1 | 40166738.95 |  |  | Completed | 1 |  |  |  | 18NC0099 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-08-20 | LEGACY CONSTRUCTION CORP.
NC 2018 | TVL | CARAGA | Agusan del Sur | 304744 | Sta. Cruz NHS | ROSARIO | 2 | 1 | 12 | 2 SCIENCE/LAB, 2 ICT, 2 REGULAR WORKSHOP (9.50MX64.00M) | BATCH 1 | 28576799.17 |  |  | Completed | 1 |  |  |  | 18NC0090 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 304745 | Bayugan III NHS | ROSARIO | 2 | 1 | 8 | 2 SCIENCE/LAB, 2 ICT (9.50MX46.00M) | BATCH 1 | 22013903.99 |  |  | Completed | 1 |  |  |  | 18NC0094 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-08-20 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 304753 | Trento NHS | TRENTO | 2 | 1 | 12 | 2 SCIENCE/LAB, 2 ICT , 2 REGULAR WORKSHOP (9.50MX46.00M) | BATCH 1 | 28231241.75 |  |  | Completed | 1 |  |  |  | 18NC0093 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-08-20 | LEGACY CONSTRUCTION CORP.
NC 2018 | TVL | CARAGA | Agusan del Sur | 317402 | Bayugan II National High School | SAN FRANCISCO | 2 | 1 | 8 | 2 SCIENCE/LAB, 2 ICT (9.50MX46.00M) | BATCH 1 | 22013903.99 |  |  | Completed | 1 |  |  |  | 18NC0095 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 317409 | Kapatungan National High School | TRENTO | 2 | 1 | 12 | 2 SCIENCE/LAB, 2 ICT, 2 REGULAR WORKSHOP (9.50MX64.00M) | BATCH 1 | 28231241.75 |  |  | Completed | 1 |  |  |  | 18NC0091 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 317412 | Pulang Lupa NHS | TRENTO | 2 | 1 | 12 | 2 SCIENCE/LAB, 2 ICT, 2 REGULAR WORKSHOP (9.50MX64.00M) | BATCH 1 | 28231241.75 |  |  | Completed | 1 |  |  |  | 18NC0092 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | LM CONSTRUCTION & GENERAL MERCHANDISE
NC 2018 | TVL | CARAGA | Agusan del Sur | 317419 | Sayon NHS | SANTA JOSEFA | 2 | 1 | 8 | 2 SCIENCE/LAB, 2 ICT (9.50MX46.00M) | BATCH 1 | 20173585.63 |  |  | Completed | 1 |  |  |  | 18NC0097 | 2018-06-05 | 2018-06-14 | 2018-06-26 | 2018-07-10 | 2018-09-04 | THEARIS BUILDERS & SUPPLY
NC 2018 | SHS | CARAGA | Agusan del Sur | 304710 | Del Monte NHS | TALACOGON | 1 | 1 | 4 | 2STY8CL | Batch 3 | 24000000 |  |  | Completed | 1 |  |  | P00273450MN-CW1 | 18NB0087 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | REGERYS CONSTRUCTION
NC 2018 | SHS | CARAGA | Agusan del Sur | 304730 | Patin-ay NHS | PROSPERIDAD (Capital) | 1 | 1 | 9 | 3STY18CL | Batch 3 | 56000000 |  |  | Completed | 1 |  |  | P00273451MN-CW1 | 18NB0083 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL CONSTRUCTION
NC 2018 | SHS | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 | 1 | 6 | 3STY12CL | Batch 3 | 42000000 |  |  | Completed | 1 |  |  | P00273452MN-CW1 | 18NB0091 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL CONSTRUCTION
NC 2018 | SHS | CARAGA | Agusan del Sur | 304752 | Talacogon NHS | TALACOGON | 1 |  | 8 | 2UNITS 2STY4CL | Batch 3 | 32000000 |  |  | Completed | 1 |  |  | P00273453MN-CW1 | 18NB0090 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL CONSTRUCTION
NC 2018 | SHS | CARAGA | Agusan del Sur | 304755 | Zillovia NHS | TALACOGON | 1 | 1 | 4 | 2STY8CL | Batch 3 | 24000000 |  |  | Completed | 1 |  |  | P00273454MN-CW1 | 18NB0088 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL CONSTRUCTION
NC 2018 | SHS | CARAGA | Agusan del Sur | 317442 | Afga Nhs | SIBAGAT | 1 | 1 | 4 | 2UNITS 2STY4CL | Batch 3 | 28000000 |  |  | Completed | 1 |  |  | P00273455MN-CW1 | 18NB0084 | 2018-07-13 | 2018-03-12 | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL CONSTRUCTION
NC 2018 | K10 | CARAGA | Bayugan City | 131602 | Lapana ES | CITY OF BAYUGAN | 1 | 1 | 8 | 2STY8CL | Batch 3 | 24000000 |  |  | Completed | 1 |  |  |  |  | 2018-07-13 |  | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL Construction & Supply
NC 2018 | K10 | CARAGA | Bayugan City | 131616 | Bayugan Central Elem. School SPED Center | CITY OF BAYUGAN | 1 | 1 | 10 | 2STY10CL | Batch 3 | 26000000 |  |  | Completed | 1 |  |  |  |  | 2018-07-13 |  | 2018-12-12 | 2018-12-20 | 2018-12-28 | REGERYS Construction & Supply
NC 2018 | K10 | CARAGA | Bayugan City | 131616 | Bayugan Central Elem. School SPED Center | CITY OF BAYUGAN | 1 |  | 8 | 2STY8CL | Batch 3 | 24000000 |  |  | Completed | 1 |  |  |  |  | 2018-07-13 |  | 2018-12-12 | 2018-12-20 | 2018-12-28 | DATREBIL Construction & Supply
NC 2018 | K10 | CARAGA | Bislig City | 132631 | San Fernando ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 16060391.6 |  |  | Completed | 1 |  |  | P00273459MN - CW1 | 18NI0065 | 2018-10-31 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-18 | CJEP BUILDERS AND ENGINEERING SERVICES
NC 2018 | K10 | CARAGA | Bislig City | 132637 | Sanyata ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL WITH TOILET | Batch 3 | 5174938.97 |  |  | Completed | 1 |  |  | P00273460MN - CW1 | 18NI0072 | 2018-10-31 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-18 | SVTS BUILDERS AND SUPPLY
NC 2018 | K10 | CARAGA | Bislig City | 132641 | Pablo B. Duray - Tumanan ES | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL WITH TOILET | Batch 3 | 5125292.82 |  |  | Completed | 1 |  |  | P00273461MN - CW1 | 18NI0073 | 2018-10-31 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-18 | EGCG BUILDERS AND SUPPLY
NC 2018 | K10 | CARAGA | Bislig City | 132841 | Lawigan ES | CITY OF BISLIG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14285815.91 |  |  | Completed | 1 |  |  | P00273462MN - CW1 | 18NI0070 | 2018-10-31 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-18 | CJEP BUILDERS AND ENGINEERING SERVICES
NC 2018 | K10 | CARAGA | Bislig City | 235001 | P. M. Clar Primary School | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL WITH TOILET | Batch 3 | 5009711.28 |  |  | Completed | 1 |  |  | P00273463MN - CW1 | 18NI0074 | 2018-10-31 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-18 | EGCG BUILDERS AND SUPPLY
NC 2018 | K10 | CARAGA | Butuan City | 132046 | Los Angeles ES | BUTUAN CITY (Capital) | 1 | 1 | 12 | 2UNITS 2STY6CL | BATCH 1 | 27953241.52 |  |  | Completed | 1 |  |  | p00270124mn-cw1 | 18ND0143 |  |  | 2018-08-20 | 2018-09-07 | 2018-09-26 | Reyrose Construction and Supply
NC 2018 | K10 | CARAGA | Butuan City | 132107 | Maon ES | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17141302.37 |  |  | Completed | 1 |  |  | p00270125mn-cw1 | 18ND0098 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | Aguero Construction
NC 2018 | K10 | CARAGA | Butuan City | 132109 | San Vicente ES | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 18404967.13 |  |  | Completed | 1 |  |  | p00270126mn-cw1 | 18ND0116 |  |  | 2018-06-13 | 2018-07-23 | 2018-08-01 | Two Aces Construction & Supplies
NC 2018 | K10 | CARAGA | Butuan City | 132120 | Masao ES | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 19955424.48 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0104 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | LVRO Construction & Supply
NC 2018 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17675820.7 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0112 |  |  | 2018-06-13 | 2018-07-12 | 2018-07-26 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2018 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 |  | 6 | 3STY6CL | BATCH 1 | 17393659.28 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0120 |  |  | 2018-07-24 | 2018-08-16 | 2018-09-05 | ROIM BUILDERS AND CONSTRUCTION SUPPLY
NC 2018 | TVL | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17518458.72 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0111 |  |  | 2018-06-13 | 2018-07-12 | 2018-08-01 | AGUERO CONSTRUCTION
NC 2018 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL | BATCH 1 | 17783006.58 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0113 |  |  | 2018-06-13 | 2018-07-05 | 2018-07-25 | REYROSE CONSTRUCTION AND SUPPLY DEVELOPMENT CORP./JOSELLE CONSTRUCTION (JV)
NC 2018 | TVL | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS (Main) | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 REGULAR WORKSHOP, 1 SCIENCE & ICT LAB | BATCH 1 | 17522427.27 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0101 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 304757 | Agusan Pequeno NHS (Pagatpatan Campus) | BUTUAN CITY (Capital) | 1 |  | 4 | 2STY4CL - SCIENCE & ICT LAB (9.5MX23M) | BATCH 1 | 11003245.63 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0140 |  |  | 2018-08-01 | 2018-08-16 | 2018-09-05 | Abada Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 304758 | Amparo NHS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18022540.21 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0091 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | Aguero Construction
NC 2018 | TVL | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 4 REGULAR WORKSHOP (9.5MX46M) | BATCH 1 | 19105982.23 |  |  | Completed | 1 |  |  | P00270127MN-CW1 | 18ND0103 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 304759 | Banza NHS | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 19118164.43 |  |  | Completed | 1 |  |  | 18ND0122 | 18ND0122 |  |  | 2018-06-26 | 2018-07-12 | 2018-08-01 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 304761 | Butuan City Comprehensive HS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18963180.23 |  |  | Completed | 1 |  |  | 18ND0123 | 18ND0123 |  |  | 2018-06-26 | 2018-07-12 | 2018-08-01 | DATRIBEL Construction & Supply
NC 2018 | SHS | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 21945915.76 |  |  | Completed | 1 |  |  | 18ND0117 | 18ND0117 |  |  | 2018-06-13 | 2018-07-05 | 2018-07-25 | JMT Construction
NC 2018 | SHS | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades | BUTUAN CITY (Capital) | 1 |  | 16 | 4STY16CL | BATCH 1 | 44148058.74 |  |  | Completed | 1 |  |  | 18ND0118 | 18ND0118 |  |  | 2018-06-13 | 2018-07-05 | 2018-07-25 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 304762 | Butuan City Sch. of Arts & Trades - Annex | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL (2 REGULAR WORKSHOP, 1 SCIENCE & 1 ICT LAB) - 9.5MX46M | BATCH 1 | 17104494.34 |  |  | Completed | 1 |  |  | 18ND0097 | 18ND0097 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | BN Builders and Construction Supplies
NC 2018 | TVL | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 4 REGULAR WORKSHOP (9.5MX46M) | BATCH 1 | 16923822.58 |  |  | Completed | 1 |  |  | 18ND0096 | 18ND0096 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | BN Builders and Construction Supplies
NC 2018 | TVL | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16792771.79 |  |  | Completed | 1 |  |  | 18ND0095 | 18ND0095 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | Two Aces Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 304764 | Los Angeles National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 19508518.53 |  |  | Completed | 1 |  |  | 18ND0124 | 18ND0124 |  |  | 2018-08-20 | 2018-09-25 |  | Ebuilders Construction & Development Corp.
NC 2018 | TVL | CARAGA | Butuan City | 304765 | Anticala NHS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16492863.19 |  |  | Completed | 1 |  |  | 18ND0084 | 18ND0084 |  |  | 2018-07-24 | 2018-08-06 | 2018-08-23 | Two Aces Construction & Supply/RAC Construction & Supplies (JV)
NC 2018 | SHS | CARAGA | Butuan City | 304766 | Lumbocan NHS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10695484.26 |  |  | Completed | 1 |  |  | 18ND0139 | 18ND0139 |  |  | 2018-08-01 | 2018-08-16 | 2018-09-05 | Abada Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 304766 | Lumbocan NHS | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 19441418.28 |  |  | Completed | 1 |  |  | 18ND0093 | 18ND0093 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 4 REGULAR WORKSHOP (9.5MX46M) | BATCH 1 | 18231334.86 |  |  | Completed | 1 |  |  | 18ND0114 | 18ND0114 |  |  | 2018-06-13 | 2018-07-12 | 2018-08-01 | Hexaminds Corporation
NC 2018 | TVL | CARAGA | Butuan City | 304769 | San Vicente National High School | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18243517.05 |  |  | Completed | 1 |  |  | 18ND0115 | 18ND0115 |  |  | 2018-06-13 | 2018-07-12 | 2018-08-01 | LM CONSTRUCTION AND GENERAL MARKETING
NC 2018 | TVL | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 | 1 | 12 | 2STY12CL - 6 REGULAR WORKSHOP (9.5MX64M) | BATCH 1 | 22302706.79 |  |  | Completed | 1 |  |  | 18ND0141 | 18ND0141 |  |  | 2018-08-01 | 2018-08-23 | 2018-09-12 | Olin Development Engineering and Construction
NC 2018 | TVL | CARAGA | Butuan City | 304771 | Taligaman NHS | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16928978.81 |  |  | Completed | 1 |  |  | 18ND0110 | 18ND0110 |  |  | 2018-06-13 | 2018-07-05 | 2018-07-25 | DATRIBEL Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL - 2 REGULAR WORKSHOP (9.5MX23M) | BATCH 1 | 9711538.42 |  |  | Completed | 1 |  |  | 18ND0137 | 18ND0137 |  |  | 2018-08-01 | 2018-08-17 | 2018-09-05 | BN Builders and Construction Supplies
NC 2018 | TVL | CARAGA | Butuan City | 304772 | Tungao NHS | BUTUAN CITY (Capital) | 1 |  | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17361577.15 |  |  | Completed | 1 |  |  | 18ND0127 | 18ND0127 |  |  | 2018-07-03 | 2018-07-17 | 2018-08-07 | BN Builders and Construction Supplies
NC 2018 | TVL | CARAGA | Butuan City | 317502 | Aupagan National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18372605.99 |  |  | Completed | 1 |  |  | 18ND0121 | 18ND0121 |  |  | 2018-06-26 | 2018-07-12 | 2018-08-01 | Thearis Builders and Supply
NC 2018 | TVL | CARAGA | Butuan City | 317505 | Maibu National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18073706.72 |  |  | Completed | 1 |  |  | 18ND0125 | 18ND0125 |  |  | 2018-06-26 | 2018-07-12 | 2018-08-01 | BN Builders and Construction Supplies
NC 2018 | TVL | CARAGA | Butuan City | 317506 | La Trinidad Integrated Secondary School | BUTUAN CITY (Capital) | 1 | 1 | 12 | 2STY12CL - 2 SCIENCE & 2 ICT LAB & 2 REGULAR WORKSHOPS | BATCH 1 | 26186491.19 |  |  | Completed | 1 |  |  | 18ND0142 | 18ND0142 |  |  | 2018-08-01 | 2018-09-17 | 2018-10-08 | LVRO Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 317507 | Consuelo National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16718676.65 |  |  | Completed | 1 |  |  | 18ND0086 | 18ND0086 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 317508 | Pinamanculan National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17712859.92 |  |  | Completed | 1 |  |  | 18ND0090 | 18ND0090 |  |  | 2018-07-24 | 2018-08-06 | 2018-08-23 | ROIM BUILDERS AND CONSTRUCTION SUPPLY
NC 2018 | TVL | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL - 2 SCIENCE LAB (9.5MX23M) | BATCH 1 | 9454079.71 |  |  | Completed | 1 |  |  | 18ND0135 | 18ND0135 |  |  | 2018-08-01 | 2018-08-17 | 2018-09-05 | Olin Development Engineering and Construction
NC 2018 | TVL | CARAGA | Butuan City | 317510 | Kinamlutan National High School | BUTUAN CITY (Capital) | 1 |  | 4 | 2STY4CL - 2 ICT LAB (9.5MX23M) | BATCH 1 | 9478518.62 |  |  | Completed | 1 |  |  | 18ND0136 | 18ND0136 |  |  | 2018-09-26 | 2018-10-10 |  | Poliran Builders Corporation
NC 2018 | TVL | CARAGA | Butuan City | 317511 | Ampayon National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18873723.26 |  |  | Completed | 1 |  |  | 18ND0119 | 18ND0119 |  |  | 2018-07-24 | 2018-08-06 | 2018-08-23 | FGM Builders Resources & Development Corporation/Quadcom Builders and Design (JV)
NC 2018 | TVL | CARAGA | Butuan City | 317513 | Bagong Silang National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17585460.4 |  |  | Completed | 1 |  |  | 18ND0089 | 18ND0089 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | Aguero Construction
NC 2018 | TVL | CARAGA | Butuan City | 317515 | Pareja ISS | BUTUAN CITY (Capital) | 1 | 1 | 6 | 3STY6CL - 1 SCIENCE & 2 ICT LAB (7MX23M) | BATCH 1 | 17654770.95 |  |  | Completed | 1 |  |  | 18ND0126 | 18ND0126 |  |  | 2018-06-26 | 2018-07-12 | 2018-08-01 | LVRO Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 317517 | Alviola ISS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 18857702.2 |  |  | Completed | 1 |  |  | 18ND0102 | 18ND0102 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-30 | F.H. Gopiteo Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 317520 | Pedro D. Duncano National HS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17199059 |  |  | Completed | 1 |  |  | 18ND0100 | 18ND0100 |  |  | 2018-07-24 | 2018-08-06 | 2018-08-23 | BN Builders and Construction Supplies/Willtorr Construction (JV)
NC 2018 | TVL | CARAGA | Butuan City | 317521 | Pigdaulan National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 17183268.2 |  |  | Completed | 1 |  |  | 18ND0099 | 18ND0099 |  |  | 2018-05-22 | 2018-07-09 | 2018-07-18 | LVRO Construction & Supply
NC 2018 | TVL | CARAGA | Butuan City | 500317 | La Soledad NHS | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16641792.93 |  |  | Completed | 1 |  |  | 18ND0085 | 18ND0085 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | REYROSE CONSTRUCTION AND SUPPLY DEV’T. CORP.
NC 2018 | TVL | CARAGA | Butuan City | 500319 | Manila de Bugabos National High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M) | BATCH 1 | 16875227.88 |  |  | Completed | 1 |  |  | 18ND0087 | 18ND0087 |  |  | 2018-05-09 | 2018-06-27 | 2018-07-18 | Aguero Construction
NC 2018 | K10 | CARAGA | Cabadbaran City | 131517 | Cabinet ES | CITY OF CABADBARAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10225289.58 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Cabadbaran City | 131572 | Antonio Luna ES | CITY OF CABADBARAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9630006.78 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 10 | 2STY10CL | Batch 3 | 24157088.02 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Cabadbaran City | 304676 | Calamba NHS | CITY OF CABADBARAN | 2 | 1 | 1 | TVL WORKSHOP | Batch 3 | 4065000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Cabadbaran City | 304699 | Cabadbaran City NHS | CITY OF CABADBARAN | 2 | 1 | 2 | 2-units TVL Workshop | Batch 3 | 8250000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Cabadbaran City | 340341 | La Union SHS (Stand Alone) | CITY OF CABADBARAN | 2 | 1 | 1 | TVL WORKSHOP | Batch 3 | 4250000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132359 | Cabungaan ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3850000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132391 | A. Ecleo Elementary School | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3850000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132393 | Cabayawan Elementary School | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3850000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132396 | DINAGAT CENTRAL ELEMENTARY SCHOOL | DINAGAT | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5200000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132398 | Justiniana ES | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132400 | New Mabuhay ES | DINAGAT | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5200000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132401 | Tagbuyakhao Elementary School | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132497 | Melgar ES | BASILISA (RIZAL) | 0 | 1 | 6 | 2-UNITS 1STY3CL | Batch 3 | 9650000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132504 | Ritaglenda Elementary School | BASILISA (RIZAL) | 0 | 1 | 6 | 2-UNITS 1STY3CL | Batch 3 | 9650000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132516 | Don Ruben Elementary School | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3950000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132519 | Luna ES | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3850000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132554 | MALINAO ES | TUBAJON | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5150000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 132559 | TUBAJON CENTRAL ELEMENTARY SCHOOL | TUBAJON | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5150000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 300544 | General Aguinaldo National High School | LIBJO (ALBOR) | 0 | 1 | 6 | 2-UNITS 1STY3CL | Batch 3 | 9650000 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Dinagat Island | 304822 | Dinagat School of Fisheries | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3850000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 304823 | Cab-ilan NHS | DINAGAT | 0 | 1 | 2 | 1STY2CL | Batch 3 | 4100000 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Dinagat Island | 304824 | Don Ruben E. Ecleo Sr. MNHS | SAN JOSE (Capital) | 0 | 1 | 2 | 1STY2CL | Batch 3 | 3950000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 305482 | DONA HELENE NHS | BASILISA (RIZAL) | 0 | 1 | 6 | 2-UNITS 1STY3CL | Batch 3 | 9700000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Dinagat Island | 324402 | Jade B. Ecleo- Aurelio National High School | SAN JOSE (Capital) | 0 | 1 | 4 | 2STY4CL | Batch 3 | 11540000 |  |  | Completed | 1
NC 2018 | SHS | CARAGA | Dinagat Island | 324403 | Edera NHS | BASILISA (RIZAL) | 0 | 1 | 3 | 1STY3CL | Batch 3 | 5150000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1 | 1 | 5 | 1STY5CL | BATCH 1 | 7300000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Siargao | 132176 | Numancia Central Elementary School | DEL CARMEN | 1 |  | 5 | 1STY5CL | BATCH 1 | 7300000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Siargao | 132220 | Bay-ang Elementary School | SOCORRO | 1 | 1 | 3 | 1STY3CL | BATCH 1 | 4500000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 4 | 1STY 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 17200000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304774 | Dapa National High School | DAPA | 1 | 1 | 7 | 3UNITS REGULAR WORKSHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 30100000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304775 | Consolacion National High School | DAPA | 1 | 1 | 2 | 1STY 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 8600000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1 | 1 | 4 | 1STY 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 17200000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1 | 1 | 7 | 1STY 3UNITS REGULAR WORKSHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 30100000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1 | 1 | 4 | 1STY 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 17200000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1 | 1 | 6 | 1STY 2UNITS REGULAR WORKSHOP, 2UNITS SCIENCE ALB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 25800000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304780 | Caridad National High School | PILAR | 1 | 1 | 3 | 1STY 1UNIT SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 12900000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 | 3 | 1STY 1UNIT REGULAR WORKSHOP, 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 12900000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1 | 1 | 5 | 1STY 1UNIT REGULAR WORKSHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 21500000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1 | 1 | 6 | 1STY 2UNITS REGULAR WORKSHOP, 2UNITS SCIENCE ALB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 25800000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304784 | Roxas National High School | SAN ISIDRO | 1 | 1 | 3 | 1STY 1UNIT REGULAR WORKSHOP, 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 12900000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 | 1 | 7 | 1STY 3UNITS REGULAR WORKSHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 30100000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304786 | Libertad National High School | SANTA MONICA (SAPAO) | 1 | 1 | 5 | 1STY 1UNIT REGULAR WORKHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 21500000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304788 | SOCORRO NATIONAL HIGH SCHOOL | SOCORRO | 1 | 1 | 6 | 1STY 2UNITS REGULAR WORKSHOP, 2UNITS SCIENCE ALB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 25800000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304789 | Nueva Estrella NHS | SOCORRO | 1 | 1 | 3 | 1STY 1UNIT REGULAR WORKHOP, 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 12900000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 304790 | Pamosaingan National High School | SOCORRO | 1 | 1 | 5 | 1STY 1UNIT REGULAR WORKHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 21500000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 317601 | Suyangan National High School | GENERAL LUNA | 1 | 1 | 2 | 1STY 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 8600000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 317602 | Atoyay National High School | SOCORRO | 1 | 1 | 5 | 1STY 1UNIT REGULAR WORKSHOP, 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 21500000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 317604 | Siargao National Science High School | DAPA | 1 | 1 | 4 | 1STY 2UNITS SCIENCE LAB & 2UNITS ICT (7MX18M PER UNIT) | BATCH 1 | 17200000 |  |  | Completed | 1
NC 2018 | TVL | CARAGA | Siargao | 317607 | Alegria National High School | SANTA MONICA (SAPAO) | 1 | 1 | 2 | 1STY 1UNIT SCIENCE LAB & 1UNIT ICT (7MX18M PER UNIT) | BATCH 1 | 8600000 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132248 | Cantiasay ES | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16488386.03 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132249 | Day-asan ES | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5495299.74 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132252 | Lisondra ES | SURIGAO CITY (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16478386.03 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132261 | Talisay ES | SURIGAO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12762017.1 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132262 | Zaragoza ES | SURIGAO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12732017.1 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132275 | Anomar ES | SURIGAO CITY (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11303013.97 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132278 | Bilabid ES | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5475299.74 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132281 | Danawan ES | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3833354.61 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao City | 132336 | Lope R. Ruiz Memo. ES (Japson ES) | SURIGAO CITY (Capital) | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5655089.36 |  |  | Completed | 1
NC 2018 | K10 | CARAGA | Surigao del Norte | 132328 | Pongtud ES | ALEGRIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3301637.17 |  |  | Completed | 1 |  |  | 18NF0102 | [5 empty] | 2019-01-20 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132329 | San Pedro ES | ALEGRIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3241637.17 |  |  | Completed | 1 |  |  | 18NF0107 | [5 empty] | 2019-01-20 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132329 | San Pedro ES | ALEGRIA | 2 |  | 2 | 1STY2CL | Batch 3 | 3241637.17 |  |  | Completed | 1 |  |  | 18NF0108 | [5 empty] | 2019-01-20 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132334 | Diaz ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3256637.17 |  |  | Completed | 1 |  |  | 18NF0101 | [5 empty] | 2019-01-21 | AJP BUILDERS AND SUPPLIES
NC 2018 | K10 | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11727711.7 |  |  | Completed | 1 |  |  | 18NF0122 | [5 empty] | 2019-01-24 | CV CONSTRUCTION AND DEVELOPMENT | Slow accomplishment due to lack of manpower and financial capability
NC 2018 | K10 | CARAGA | Surigao del Norte | 132341 | Oslao ES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11496528.21 |  |  | Completed | 1 |  |  | 18NF0123 | [5 empty] | 2019-01-24 | RCDG CONSTRUCTION/AT DUMLAO CONST., INC.
NC 2018 | K10 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3291637.17 |  |  | Completed | 1 |  |  | 18NF0106 | [5 empty] | 2019-01-20 | L.V.R.O. CONSTRUCTION AND SUPPPLY
NC 2018 | K10 | CARAGA | Surigao del Norte | 132342 | Bacuag CES | BACUAG | 2 |  | 6 | 2STY6CL | Batch 3 | 14337525.26 |  |  | Completed | 1 |  |  | 18NF0116 | [5 empty] | 2019-01-21 | CV CONSTRUCTION AND DEVELOPMENT | Slow accomplishment due to lack of manpower and financial capability
NC 2018 | K10 | CARAGA | Surigao del Norte | 132346 | Campo ES | BACUAG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11115457.89 |  |  | Completed | 1 |  |  | 18NF0125 | [5 empty] | 2019-01-24 | AMALGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132347 | Dugsangon ES | BACUAG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3251637.17 |  |  | Completed | 1 |  |  | 18NF0105 | [5 empty] | 2019-01-20 | ASJ BUILDERS
NC 2018 | K10 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3271637.17 |  |  | Completed | 1 |  |  | 18NF0099 | [5 empty] | 2019-01-17 | L.V.R.O. CONSTRUCTION AND SUPPPLY
NC 2018 | K10 | CARAGA | Surigao del Norte | 132351 | Pautao ES | BACUAG | 2 |  | 2 | 1STY2CL | Batch 3 | 3271637.17 |  |  | Completed | 1 |  |  | 18NF0100 | [5 empty] | 2019-01-17 | L.V.R.O. CONSTRUCTION AND SUPPPLY
NC 2018 | K10 | CARAGA | Surigao del Norte | 132433 | Magpayang ES | MAINIT | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3251637.17 |  |  | Completed | 1 |  |  | 18NF0109 | [5 empty] | 2019-01-20 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132449 | Tolingon ES | MAINIT | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3271637.17 |  |  | Completed | 1 |  |  | 18NF0098 | [5 empty] | 2019-01-17 | C.V. CONSTRUCTION AND DEVELOPMENT
NC 2018 | K10 | CARAGA | Surigao del Norte | 132467 | Amoslog ES | PLACER | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14375060.6 |  |  | Completed | 1 |  |  | 18NF0115 | [5 empty] | 2019-01-21 | MYMS CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132469 | Badas ES | PLACER | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14427525.26 |  |  | Completed | 1 |  |  | 18NF0114 | [5 empty] | 2019-01-22 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132471 | Bugas-Bugas ES | PLACER | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3258637.17 |  |  | Completed | 1 |  |  | 18NF0110 | [5 empty] | 2019-01-20 | GEVANS CONSTRUCTION AND SUPPLY
NC 2018 | K10 | CARAGA | Surigao del Norte | 132472 | Ellaperral ES | PLACER | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12850125.7 |  |  | Completed | 1 |  |  | 18NF0119 | [5 empty] | 2019-01-24 | C.V. CONSTRUCTION AND DEVELOPMENT
NC 2018 | K10 | CARAGA | Surigao del Norte | 132531 | Mabuhay ES | SISON | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3251637.17 |  |  | Completed | 1 |  |  | 18NF0104 | [5 empty] | 2019-01-21 | GC BUILDERS
NC 2018 | K10 | CARAGA | Surigao del Norte | 132534 | Sison CES | SISON | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14322076.09 |  |  | Completed | 1 |  |  | 18NF0117 | [5 empty] | 2019-01-21 | MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132542 | Hinatuan ES | TAGANA-AN | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3803354.61 |  |  | Completed | 1 |  |  | 18NF0097 | [5 empty] | 2019-01-17 | ROMZ BUILDERS
NC 2018 | K10 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14697975.52 |  |  | Completed | 1 |  |  | 18NF0113 | [5 empty] | 2019-01-22 | ROMZ BUILDERS
NC 2018 | K10 | CARAGA | Surigao del Norte | 132561 | Capayahan ES | TUBOD | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3246637.17 |  |  | Completed | 1 |  |  | 18NF0103 | [5 empty] | 2019-01-20 | MYMS CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Norte | 132568 | Tubod CES | TUBOD | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14193660.05 |  |  | Completed | 1 |  |  | 18NF0118 | [5 empty] | 2019-01-21 | MYMS CONSTRUCTION
NC 2018 | TVL | CARAGA | Surigao del Norte | 304812 | Tagana-an NHS (ASA NHS) | TAGANA-AN | 2 | 1 | 2 | 2STY Workshop Bldg. | Batch 3 | 14837075.52 |  |  | Completed | 1 |  |  | 18NF0127 | [5 empty] | 2019-01-24 | ROMZ BUILDERS
NC 2018 | TVL | CARAGA | Surigao del Norte | 304833 | Malimono NHS | MALIMONO | 2 | 1 | 12 | 4STY12CL (1CL + 1LAB. PER FLOOR) | Batch 3 | 37599950.19 |  |  | Completed | 1 |  |  | 18NF0126 | [5 empty] | 2019-01-24 | F.H. GOPITEO CONSTRUCTION AND SUPPLY/MIGO CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Sur | 132643 | Aras- Asan Es | CAGWAIT | 1 | 1 | 4 | 2STY4CL | Batch 3 | 15791766.93 |  |  | Completed | 1 |  |  |  | 18FN0118 |  |  |  |  | 2019-01-21 | MYMS Construction
NC 2018 | K10 | CARAGA | Surigao del Sur | 132716 | Tigao ES | CORTES | 1 | 1 | 12 | 2-UNITS 2STY6CL | Batch 3 | 34749583.48 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | FFJJ CONSTRUCTION
NC 2018 | SHS | CARAGA | Surigao del Sur | 304873 | Cantilan NHS | CANTILAN | 1 | 1 | 6 | 2STY6CL (SHS) | Batch 3 | 19734874.35 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | ASJ BUILDERS
NC 2018 | TVL | CARAGA | Surigao del Sur | 304886 | Felisberto Verano NHS | CORTES | 1 | 1 | 1 | 2STY REGULAR WORKSHOP | Batch 3 | 17030000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | MARK ANTHONY CONSTRUCTION & SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 304905 | San Miguel National Comprehensive HS | SAN MIGUEL | 1 | 1 | 1 | 2STY REGULAR WORKSHOP | Batch 3 | 17030000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | DDS BUILDERS
NC 2018 | TVL | CARAGA | Surigao del Sur | 304907 | San Miguel National Comprehensive HS-Sagbayan Annex | SAN MIGUEL | 1 | 1 | 1 | 2STY REGULAR WORKSHOP | Batch 3 | 17030000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | ACQ SOLOMONIC BUILDERS DEVELOPMENT CORP.
NC 2018 | TVL | CARAGA | Surigao del Sur | 304908 | San Miguel NHS | SAN MIGUEL | 1 | 1 | 1 | 2STY SCIENCE LAB | Batch 3 | 17150000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | DDS BUILDERS
NC 2018 | TVL | CARAGA | Surigao del Sur | 304924 | Unidad NHS | CAGWAIT | 1 | 1 | 1 | 2STY REGULAR WORKSHOP | Batch 3 | 17030000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | ROWIES CONSTRUCTION
NC 2018 | TVL | CARAGA | Surigao del Sur | 317903 | Badong NHS | TAGO | 1 | 1 | 1 | 2STY ICT LAB | Batch 3 | 16900000 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | MOLROW CONSTRUCTION & SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago NHS | MARIHATAG | 1 | 1 | 1 | 2STY ICT LAB | Batch 3 | 16900000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | JIMBERNS BUILDERS & CONSTRUCTION SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 317912 | Davisol NHS | LIANGA | 1 | 1 | 1 | 2STY REGULAR WORKSHOP | Batch 3 | 17030000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | ACQ SOLOMONIC BUILDERS DEVELOPMENT CORP.
NC 2018 | TVL | CARAGA | Surigao del Sur | 500322 | Bangsud Integrated School | TAGO | 1 | 1 | 1 | 2STY ICT LAB | Batch 3 | 16900000 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | NEWCON BUILDERS CONST. & SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 500573 | Gata IS | SAN AGUSTIN | 1 | 1 | 1 | 2STY SCIENCE LAB | Batch 3 | 17150000 |  |  | Completed | 1 | [8 empty] | 2019-01-10 | ACQ SOLOMONIC BUILDERS DEVELOPMENT CORP.
NC 2018 | TVL | CARAGA | Surigao del Sur | 500575 | Isla General IS | CANTILAN | 1 | 1 | 1 | 2STY ICT LAB | Batch 3 | 17900000 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | LISCAL CONSTRUCTION SERVICES
NC 2018 | K10 | CARAGA | Surigao del Sur | 132572 | Barobo Central ES | BAROBO | 2 | 1 | 12 | 3STY12CL | Batch 3 | 35287064.49 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | GIOVANNI CONSTRUCTION
NC 2018 | K10 | CARAGA | Surigao del Sur | 132573 | Barobo Townsite ES | BAROBO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14285815.91 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | JB CIANO CONST.
NC 2018 | K10 | CARAGA | Surigao del Sur | 132596 | Talisay Seaside ES | BAROBO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 17253791.76 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | RDF CONST & SUPPLY
NC 2018 | K10 | CARAGA | Surigao del Sur | 132599 | Wakat ES | BAROBO | 2 | 1 | 8 | 2UNITS 2STY4CL | Batch 3 | 29443253.9467 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | MRS BUILDERS & SUPPLY
NC 2018 | K10 | CARAGA | Surigao del Sur | 132742 | Pocto ES | HINATUAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 15896503.07 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | TWO DEGREES CONST. & SUPPLY
NC 2018 | K10 | CARAGA | Surigao del Sur | 132743 | Portlamon ES | HINATUAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 15917506.06 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | MRS BUILDERS & SUPPLY
NC 2018 | K10 | CARAGA | Surigao del Sur | 132925 | Tagongon ES | TAGBINA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 16068447.89 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | SUTS BUILDERS & SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 304861 | Barobo NHS | BAROBO | 2 | 1 | 3 | 3STY REGULAR WORKSHOP | Batch 3 | 20099503.85 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | THEARIS BUILDERS & SUPPLY
NC 2018 | TVL | CARAGA | Surigao del Sur | 304861 | Barobo NHS | BAROBO | 2 |  | 2 | 2STY ICT LAB. | Batch 3 | 14277430.56 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | THEARIS BUILDERS & SUPPLY
NC 2018 | SHS | CARAGA | Surigao del Sur | 304921 | Bigaan NHS | HINATUAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14285815.91 |  |  | Completed | 1 | [8 empty] | 2018-12-20 | MRS BUILDERS & SUPPLY
NC 2018 | K10 | CARAGA | Tandag City | 304892 | Jacinto P. Elpa NHS | CITY OF TANDAG (Capital) | 1 | 1 | 20 | 4STY20CL | Batch 3 | 46208409.74 |  |  | Completed | 1
NC 2019 | SHS | CARAGA | Agusan del Norte | 304679 | Bokbokon NHS (Durian NHS Annex) | LAS NIEVES | 1 | 1 | 2 | 1STY2CL |  | 4803882.3164 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Norte | 211511 | Calayagon ES | BUENAVISTA | 2 | 1 | 2 | 1-UNIT 1STY2CL with Toilet Attached and Handwashing Facility |  | 3190116.7935 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Norte | 131494 | Cubi-Cubi ES | NASIPIT | 2 | 1 | 3 | 1STY3CL with Attached Toilet & Handwashing Facility |  | 3965955.5033 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Norte | 131587 | Lawigan ES | TUBAY | 2 | 1 | 3 | 1STY3CL with Attached Toilet & Handwashing Facility |  | 6254112.7712 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 | 1 | 3 | 1-UNIT 1STY3CL with Toilet Attached and Handwashing Facility |  | 4488870.8817 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Norte | 317320 | Pupotsan NHS (Magallanes NHS Annex) | MAGALLANES | 2 |  | 6 | 3UNITS 1STY2CL |  | 11389844.8632 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | CARAGA | Agusan del Sur | 304710 | Del Monte NHS | TALACOGON | 1 | 1 | 4 | 2STY4CL |  | 13674100 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Sur | 131703 | Guadalupe CES | ESPERANZA | 1 | 1 | 2 | 1STY2CL (w/ toilet at each classroom) |  | 5619012.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Sur | 131788 | San Vicente ES | PROSPERIDAD (Capital) | 1 | 1 | 10 | 2STY10CL |  | 27323137.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Sur | 131714 | Tandang Sora Elementary School | Esperanza | 1 | 1 | 6 | 2STY6CL |  | 20526187.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | CARAGA | Agusan del Sur | 317426 | Buenasuerte National High School | SAN FRANCISCO | 2 | 1 | 4 | 1STY4CL W/ TOILET |  | 9546086.4619 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Agusan del Sur | 132009 | Quimayong ES | TRENTO | 2 | 1 | 3 | 1STY3CL W/ TOILET |  | 6937294.5163 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Bayugan City | 131609 | Panaytay ES | CITY OF BAYUGAN | 1 | 1 | 2 | 1STY2CL (w/ toilet at each classroom) |  | 5603975 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Bislig City | 132635 | San Roque Central Elementary School | CITY OF BISLIG | 2 | 1 | 2 | 1STY2CL (with Toilet Attached) |  | 4991723.1675 |  | Completed | 1 |  |  |  | 19NI0061 | 8/1/2019 | 2019-08-08 | 2019-08-20 | 2019-08-27 | 2019-08-30 |  |  | 0
NC 2019 | SHS | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 | 1 | 8 | 2UNITS 2STY4CL |  | 20877643.1079 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | CARAGA | Cabadbaran City | 330101 | Puting Bato National High School | CITY OF CABADBARAN | 2 |  | 6 | 1STY6CL |  | 8428891.3993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Dinagat Island | 132399 | Magsaysay ES | DINAGAT | 0 | 1 | 3 | 1STY3CL |  | 5213000 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Dinagat Island | 132370 | Sta Rita ES | CAGDIANAO | 0 | 1 | 2 | 1STY2CL |  | 3909750 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao City | 132272 | Surigao City Pilot Sch. | SURIGAO CITY (Capital) | 2 | 1 | 16 | 4STY16CL |  | 46402225.1422 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao City | 132243 | Vicente Cabilao Mem. ES (Balibayon ES) | SURIGAO CITY (Capital) | 2 | 1 | 2 | 1STY2CL |  | 4874764.1691 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao del Norte | 132331 | Anao-aon CES | SAN FRANCISCO (ANAO-AON) | 2 | 1 | 6 | 2STY6CL |  | 16998458.5409 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao del Norte | 132378 | Claver Central Elementary School | CLAVER | 2 | 1 | 12 | 3STY12CL |  | 43451263.9166 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao del Sur | 132858 | Britania Elementary School | SAN AGUSTIN | 1 | 1 | 2 | 1STY2CL (Grade 1-10 CL) |  | 4117215.4101 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | CARAGA | Surigao del Sur | 317906 | Cresencio S. Lago National High School | MARIHATAG | 1 | 1 | 2 | 1STY2CL |  | 4117215.4101 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | CARAGA | Surigao del Sur | 304898 | Marihatag National Agricultural High School | MARIHATAG | 1 | 1 | 2 | 1STY2CL |  | 4117215.4101 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao del Sur | 214516 | Mahogany Elementary School | LINGIG | 2 | 1 | 4 | 2STY4CL |  | 13873357.9727 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Surigao del Sur | 214518 | Pinanapatan Elementary School | LINGIG | 2 | 1 | 2 | 1STY2CL (with Toilet Attached) |  | 5670381.2015 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | CARAGA | Tandag City | 132968 | Meliton M. Ajos Memorial Elementary School | CITY OF TANDAG (Capital) | 1 | 1 | 2 | 1STY2CL (Grade 1-10 CL) |  | 4117215.4101 |  | Completed | 1 | [11 empty] | 0
NC 2020 | SHS | CARAGA | Agusan del Norte | 131469 | Lawan Lawan ES | LAS NIEVES | 1 | 1 | 4 | 2UNITS 1STY2CL w/ toilet attached and handwashing facility at both endwalls |  | 10587407.4 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Agusan del Norte | 131550 | F.S. OMAYANA ES | BUENAVISTA | 2 | 1 | 5 | 1STY5CL with toilet attached and Handwashing Facility at both endwalls |  | 9944462.39 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Agusan del Norte | 131594 | Victory ES | TUBAY | 2 | 1 | 4 | 1STY4CL with Handwashing Facility at both endwalls |  | 8250820.23 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131791 | AZPETIA ES | PROSPERIDAD | 1 | 1 | 3 | 1STY3CL |  | 7578900 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131862 | ANAHAWAN ES | SIBAGAT | 1 | 1 | 2 | 1STY2CL |  | 5052600 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131951 | KALILID ES | SAN LUIS | 1 | 1 | 2 | 1STY2CL |  | 5032550 |  |  | COMPLETED | 1
NC 2020 | SHS | CARAGA | Agusan del Sur | 317441 | Salug Nhs | ESPERANZA | 1 | 1 | 2 | 1STY2CL with toilet each CL |  | 6049085 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131649 | BABADAN ES | BUNAWAN | 2 | 1 | 2 | 1STY2CL |  | 7735605.14 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131759 | BATAAN ES | LA PAZ | 2 | 1 | 2 | 1STY2CL |  | 5312789.37 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131841 | PISAAN ES | SAN FRANCISCO | 2 | 1 | 2 | 1STY2CL |  | 4932767.44 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 131930 | SAN VICENTE ES | STA. JOSEFA | 2 | 1 | 2 | 1STY2CL |  | 5037870.24 |  |  | COMPLETED | 1
NC 2020 | SHS | CARAGA | Agusan del Sur | 317431 | MAGAUD NHS | LORETO | 2 | 1 | 2 | 1STY2CL |  | 5090019.72 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Agusan del Sur | 317448 | CEBOLIN NHS | TRENTO | 2 | 1 | 2 | 1STY2CL |  | 5037870.24 |  |  | COMPLETED | 1
NC 2020 | TVL | CARAGA | Bayugan City | 304707 | BAYUGAN NCHS | BAYUGAN CITY | 1 | 1 | 4 | 2STY4-CL(2 SCI.LAB) |  | 13197912.5 |  |  | Completed | 1
NC 2020 | SHS | CARAGA | Bislig City | 304868 | San Vicente NHS | City of Bislig | 2 | 1 | 4 | 2STY4CL |  | 15809921.24 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Butuan City | 132118 | Libertad CES | BUTUAN CITY (Capital) | 1 | 1 | 10 | 2STY10CL |  | 28792843.61 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Cabadbaran City | 131522 | Francisco C. Jongko Elementary School | CITY OF CABADBARAN | 2 | 1 | 3 | 1STY3CL |  | 6249401.38 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Siargao | 132139 | Dapa Central Elementary School and SPED Center | Dapa | 1 | 1 | 2 | 1STY2CL |  | 5012500 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Siargao | 132146 | Cabitoonan Elementary School | GENERAL LUNA | 1 | 1 | 6 | 1STY6CL |  | 21052500 |  |  | Reverted | 0 | [10 empty] | No Buildable Space
NC 2020 | K10 | CARAGA | Siargao | 132175 | Mahayahay Elementary School | DEL CARMEN | 1 | 1 | 6 | 1STY6CL |  | 21052500 |  |  | Completed | 1
NC 2020 | SHS | CARAGA | Siargao | 304791 | Union National High School | Dapa | 1 | 1 | 3 | 1STY3CL |  | 7218000 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Surigao City | 132269 | Quezon ES | Surigao City | 2 | 1 | 4 | 2STY4CL |  | 14508128.72 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Surigao del Norte | 132327 | Ombong ES | ALEGRIA | 2 | 1 | 6 | 2STY6CL |  | 17531255.35 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Surigao del Norte | 132459 | Karihatag ES | MALIMONO | 2 | 1 | 3 | 1STY3CL |  | 6992838.53 |  |  | COMPLETED | 1
NC 2020 | K10 | CARAGA | Surigao del Sur | 132942 | Falcon Memorial ES | Tago | 1 | 1 | 20 | 4STY20CL |  | 46323930.76 |  |  | Completed | 1 | [10 empty] | Notice to Proceed dated on August 20, 2020
NC 2020 | K10 | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2 | 1 | 6 | 2STY6CL |  | 17430827.4 |  |  | Completed | 1 | [10 empty] | Waiting for the Released of SARO
NC 2020 | K10 | CARAGA | Tandag City | 132959 | Bioto Elementary School | Tandag City | 1 | 1 | 2 | 1STY2CL |  | 4117215.41 |  |  | Completed | 1
NC 2020 | K10 | CARAGA | Tandag City | 132975 | San Antonio Elementary School | Tandag City | 1 | 1 | 2 | 1STY2CL |  | 4117215.41 |  |  | Completed | 1
NC 2021 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 148085.2098 | 147715.92 |  | Reverted | 0 | [10 empty] | Not procured
NC 2021 | SHS | CARAGA | Butuan City | 304763 | Libertad Integrated Senior High School | BUTUAN CITY (Capital) | 1 | 1 | 8 | Construction/Completion (2STY8CL - 2 SCIENCE & 2 ICT LAB (9.5MX46M)) |  | 120545.7729 | 120245.16 |  | Reverted | 0 | [10 empty] | Not procured
NC 2022 | SHS | CARAGA | Siargao | 304773 | Burgos National High School | BURGOS | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1 |  | 2023-03-29
NC 2022 | SHS | CARAGA | Siargao | 304783 | Del Carmen National High School | DEL CARMEN | 1 | 1 | 6 | COMPLETION OF 2STY6CL | 2 |  | 4010000 |  | Completed | 1 |  | 2023-03-27
NC 2022 | SHS | CARAGA | Siargao | 304776 | Mariano Matugas Memorial National High School | DEL CARMEN | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 2506250 |  | Completed | 1 |  | 2023-03-27
NC 2022 | SHS | CARAGA | Siargao | 317605 | Oguing Navarro Memorial National High School | DEL CARMEN | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 3007500 |  | Completed | 1 |  | 2023-03-27
NC 2022 | SHS | CARAGA | Siargao | 304777 | Gen Luna National High School | GENERAL LUNA | 1 | 1 | 6 | COMPLETION OF 2STY6CL | 2 |  | 4010000 |  | Completed | 1 |  | 2023-04-20
NC 2022 | SHS | CARAGA | Siargao | 304778 | Sta. Fe National High School | GENERAL LUNA | 1 | 1 | 8 | COMPLETION OF 2-UNITS 2STY4CL | 2 |  | 4110250 |  | Completed | 1 |  | 2023-03-23
NC 2022 | SHS | CARAGA | Siargao | 304780 | Caridad National High School | PILAR | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 2105250 |  | Completed | 1 |  | 2023-03-23
NC 2022 | SHS | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1 | 1 | 8 | COMPLETION OF 2-UNITS 2STY4CL | 2 |  | 3508750 |  | Completed | 1 |  | 2023-03-23
NC 2022 | SHS | CARAGA | Siargao | 304779 | Pilar National High School | PILAR | 1 |  | 6 | COMPLETION OF 2STY6CL | 2 |  | 2506250 |  | Completed | 1 |  | 2023-03-22
NC 2022 | SHS | CARAGA | Siargao | 304781 | San Benito National High School | SAN BENITO | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1 |  | 2023-04-24
NC 2022 | SHS | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO | 1 | 1 | 6 | COMPLETION OF 2STY6CL | 2 |  | 3508750 |  | Completed | 1 |  | 2023-04-13
NC 2022 | SHS | CARAGA | Siargao | 304785 | Sapao National High School | SANTA MONICA (SAPAO) | 1 | 1 | 6 | COMPLETION OF 2STY6CL | 2 |  | 2105250 |  | Completed | 1 |  | 2023-03-29
NC 2022 | SHS | CARAGA | Surigao del Sur | 304909 | Solomon P. Lozada National High School | BAYABAS | 1 | 1 | 6 | 2STY6CL | 2 |  | 17613925 |  | Completed | 1 | 2023-09-01
NC 2023 | K10 | CARAGA | Agusan del Norte | 131567 | Sangay ES | BUENAVISTA |  | 1 | 0 |  | Batch 1 | 20175000 | 20000000 |  | Completed | 1
NC 2023 | K10 | CARAGA | Agusan del Sur | 131809 | Sta Irene Central ES | PROSPERIDAD (Capital) |  | 1 | 10 |  | Batch 1 | 30262500 | 30000000 | 25400000 | Completed | 1 | 2024-05-12 | 2024-05-12 | P00775196MN | 23NB0049 | 2023-05-23 | 2023-05-30 | 2023-06-13 | 2023-07-28 | 2023-08-11 | MIGO CONSTRUCTION
NC 2023 | K10 | CARAGA | Agusan del Sur | 131844 | San Francisco Pilot CES | SAN FRANCISCO |  | 1 | 10 |  | Batch 1 | 30262500 | 30000000 | 29687172.64 | Ongoing | 0.15 | 2024-03-28 |  | P00775197MN | 23NC0070 | 2023-07-26 | 2023-08-02 | 2023-08-15 | 2023-08-25 | 2023-09-26 | BJ CONSTRUCTION & SUPPLY
NC 2023 | K10 | CARAGA | Bislig City | 132609 | Bislig Central Elementary School | CITY OF BISLIG |  | 1 | 8 |  | Batch 3 | 34448983 | 33243268.59 |  | Reverted | [11 empty] | NO ALLOCATION
NC 2023 | SHS | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) |  | 1 | 12 |  | Batch 1 | 33711931.83 | 33419511.11 | 33394675.42 | Completed | 1 | 2024-05-10 | 2024-08-06 | P00775198MN-CW1 | 23ND0084 | 2023-08-04 | 2024-08-11 | 2023-08-23 | 2023-09-25 | 2023-10-05 | REYROSE CONST. AND SUPPLY DEV'T. CORP.
NC 2023 | K10 | CARAGA | Cabadbaran City | 131516 | Caasinan ES | CITY OF CABADBARAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | CARAGA | Cabadbaran City | 131575 | Calibunan ES | CITY OF CABADBARAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | CARAGA | Dinagat Island | 132316 | Osmeña Elementary School | LIBJO (ALBOR) | 0 | 1 | 3 |  | Batch 1 | 9949710.6 | 9863405.8 | 9540733.84 | reverted | 1 | 2024-04-29 | 2024-06-10 | P00775201MN | 23NE0104 | 2023-07-24 | 2023-08-10 | 2023-08-22 | 2023-09-13 | 2023-09-27 | Heavy John Engineering consultancy | cancel/transfer requested to manoligao es
NC 2023 | K10 | CARAGA | Dinagat Island | 132426 | Panamaon Elementary School | LORETO | 0 | 1 | 2 |  | Batch 1 | 8099009.45 | 8028757.82 | 7787500 | Completed | 1 | 2024-03-30 | 2024-03-30 | P00775202MN | 23NE0105 | 2023-09-13 | 2023-08-10 | 2023-08-22 | 2023-09-13 | 2023-09-27 | GHS construction and Development Services
NC 2023 | K10 | CARAGA | Dinagat Island | 132498 | Montag Elementary School | BASILISA (RIZAL) |  | 1 | 3 |  | Batch 1 | 9980427.04 | 9893855.8 | 9517757.79 | reverted | 1 | 2024-10-05 | 2024-10-05 | P00775203MN | 23NE0137 | 2023-11-24 | 2023-12-01 | 2023-12-14 | 2023-12-20 | 2024-01-09 | HEAVY JOHN ENGINEERING CONSULTANCY | cancel/transfer requested
NC 2023 | K10 | CARAGA | Dinagat Island | 132499 | Navarro Elementary School | BASILISA (RIZAL) |  | 1 | 3 |  | Batch 1 | 10409744.46 | 10319449.28 | 10237852.03 | Completed | 1 | 2024-01-20 | 2024-03-17 | P00775204MN | 23NE0038 | 2022-12-01 | 2022-12-08 | 2022-12-20 | 2023-06-08 | 2023-07-18 | RADIAN CONSTRUCTION AND SUPPLY
NC 2023 | K10 | CARAGA | Dinagat Island | 305745 | Roma National High School | BASILISA (RIZAL) |  | 1 | 4 |  | Batch 1 | 12595082.77 | 12485831.74 | 12111256.35 | Completed | 1 | 2024-04-29 | 2024-04-29 | P00775205MN | 23NE0099 | 2023-07-31 | 2023-08-10 | 2023-08-22 | 2023-09-13 | 2023-09-27 | Anavan Innovative Builders
NC 2023 | K10 | CARAGA | Dinagat Island | 132357 | Borja Elementary School | CAGDIANAO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4602809.97 | Completed | 1 | 2024-03-30 | 2024-04-14 | P00775206MN | 23NE0097 | 2023-07-17 | 2023-08-10 | 2023-08-22 | 2023-09-13 | 2023-09-27 | P&G construction and Supply
NC 2023 | K10 | CARAGA | Dinagat Island | 132369 | San Jose Elementary School | CAGDIANAO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4614095.3 | Completed | 1 | 2024-01-30 | 2024-03-30 | P00775207MN | 23NE0101 | 2023-07-17 | 2023-08-10 | 2023-08-22 | 2023-09-11 | 2023-09-27 | JMT construction
NC 2023 | SHS | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) |  | 1 | 6 |  | Batch 1 | 22848649.61 | 22650458.1 | 22526355.34 | Completed | 1 | 2024-03-25 | 2024-05-24 | P00775209MN | 23NE0037 | 2023-03-10 | 2023-03-17 | 2023-03-30 | 2023-06-08 | 2023-07-18 | ATJ BUILDERS
NC 2023 | K10 | CARAGA | Dinagat Island | 132313 | Magsaysay Elementary School | LIBJO (ALBOR) |  | 1 | 4 |  | Batch 1 | 12624977.81 | 12515467.47 | 12106973.69 | Completed | 1 | 2024-04-29 | 2024-06-03 | P00775208MN | 23NE0103 | 2023-07-17 | 2023-08-10 | 2023-08-22 | 2023-09-13 | 2023-09-27 | Heavy John Engineering consultancy
NC 2023 | K10 | CARAGA | Dinagat Island | 132513 | Aurelio Elementary School | SAN JOSE (Capital) |  | 1 | 6 |  | Batch 1 | 22848649.61 | 22650458.1 | 22507205.81 | Ongoing | 0.98 | 2024-03-30 | 2024-11-28 | P00775210MN | 23NE0040 | 2022-12-01 | 2022-12-08 | 2022-12-20 | 2023-06-08 | 2023-07-18 | RADIAN CONSTRUCTION AND SUPPLY
NC 2023 | K10 | CARAGA | Dinagat Island | 132517 | Jacquez Primary School | SAN JOSE (Capital) |  | 1 | 1 |  | Batch 1 | 2284642.52 | 2264825.3 | 2201752.21 | reverted | 1 | 2024-02-14 | 2024-03-18 | P00775211MN | 23NE0102 | 2023-07-17 | 2023-08-10 | 2023-08-22 | 2023-10-03 | 2023-10-17 | P&G construction and Supply | transfered to paniog es
NC 2023 | K10 | CARAGA | Dinagat Island | 132521 | Matingbe Elementary School | SAN JOSE (Capital) |  | 1 | 2 |  | Batch 1 | 8067233.83 | 7997257.82 | 7764749.9 | Completed | 1 | 2024-02-29 | 2024-06-02 | P00775212MN | 23NE0100 | 2023-07-17 | 2023-08-10 | 2023-08-22 | 2023-09-11 | 2023-09-18 | C.V. construction & Development
NC 2023 | K10 | CARAGA | Dinagat Island | 132554 | Malinao Elementary School | TUBAJON |  | 1 | 7 |  | Batch 1 | 24049302.62 | 23840696.52 | 23702845.66 | Completed | 1 | 2024-04-19 | 2024-06-18 | P00775213MN | 23NE0039 | 2022-12-01 | 2022-12-08 | 2022-12-20 | 2023-06-08 | 2023-07-18 | CARTESIAN BUILDERS CORPORATION
NC 2023 | K10 | CARAGA | Siargao | 132137 | Cambas-ac Elementary School | DAPA |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4744032.05 | Completed | 1 | 2024-01-14 | 2023-12-17 | P00775216MN | 23NF0088 | 2023-08-02 | 2023-08-09 | 2023-08-29 | 2023-08-30 | 2023-09-11 | RADIAN CONST. & SUPPLY
NC 2023 | K10 | CARAGA | Siargao | 132129 | Don Enrique Navarro Memorial School | DAPA |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4740035.62 | Completed | 1 | 2023-11-27 | 2023-11-20 | P00775214MN | 23NF0074 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | RADIAN CONST. & SUPPLY
NC 2023 | K10 | CARAGA | Siargao | 132133 | Sta Felomina Elementary School | DAPA |  | 1 | 1 |  | Batch 1 | 2017500 | 2000000 | 1998470.62 | Completed | 1 | 2023-12-15 | 2023-12-10 | P00775215MN | 23NF0094 | 2023-08-02 | 2023-08-09 | 2023-08-29 | 2023-08-30 | 2023-09-11 | RADIAN CONST. & SUPPLY
NC 2023 | K10 | CARAGA | Siargao | 132165 | Cabugao ES | Del Carmen |  | 1 | 3 |  | Batch 1 | 10440562.5 | 10350000 | 10344981.88 | Completed | 1 | 2024-02-25 | 2024-02-22 | P00775217MN | 23NF0084 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | SEVERS CONSTRUCTION
NC 2023 | K10 | CARAGA | Siargao | 132167 | Dumoyog ES | Del Carmen |  | 1 | 2 |  | Batch 1 | 8019562.5 | 7950000 | 7939909.43 | Completed | 1 | 2024-07-01 | 2024-07-14 | P00775218MN | 23NF0107 | 2023-08-02 | 2023-08-09 | 2023-08-22 | 2023-12-21 | 2023-12-29 | SEVERS CONSTRUCTION
NC 2023 | K10 | CARAGA | Siargao | 132180 | Tuboran ES | Del Carmen |  | 1 | 4 |  | Batch 1 | 13012875 | 12900000 | 12894933.33 | Completed | 1 | 2024-03-26 | 2024-03-23 | P00775219MN | 23NF0082 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | SEVERS CONSTRUCTION
NC 2023 | K10 | CARAGA | Siargao | 132158 | Sta. Cruz ES | Gen. Luna |  | 1 | 4 |  | Batch 1 | 12458062.5 | 10350000 | 12342917.67 | Completed | 1 | 2024-02-25 | 2024-02-22 | P00775220MN | 23NF0087 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | JZL BUILDERS ENTERPRISES
NC 2023 | SHS | CARAGA | Siargao |  | Gen Luna National High School - Annex | GENERAL LUNA |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 | 29994954.82 | Completed | 1 | 2024-07-24 | 2024-07-24 | P00775224MN | 23NF0077 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 317603 | Gen. Luna NHS - Consuelo NHS Annex | GENERAL LUNA |  | 1 | 6 |  | Batch 1 | 17163881.25 | 17015000 | 17004900.08 | Completed | 1 | 2024-03-26 | 2024-03-23 | P00775223MN | 23NF0081 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132155 | Magsaysay ES | GENERAL LUNA |  | 1 | 2 |  | Batch 1 | 8019562.5 | 7950000 | 7939935.86 | Completed | 1 | 2024-01-26 | 2024-01-25 | P00775221MN | 23NF0078 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132189 | Mabuhay ES | Pilar |  | 1 | 4 |  | Batch 1 | 13012875 | 12900000 | 12894917.29 | Completed | 1 | 2024-03-26 | 2024-03-26 | P00775225MN | 23NF0083 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132190 | Pilar Central Elementary School | PILAR |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4739937.77 | Completed | 1 | 2023-11-27 | 2023-11-20 | P00775226MN | 23NF0076 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | RADIAN CONST. & SUPPLY
NC 2023 | K10 | CARAGA | Siargao | 132229 | San Juan Elementary School | SAN BENITO |  | 1 | 2 |  | Batch 1 | 8019562.5 | 7950000 | 7944962 | Completed | 1 | 2024-01-26 | 2024-01-25 | P00775227MN | 23NF0079 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | SEVERS CONSTRUCTION
NC 2023 | K10 | CARAGA | Siargao |  | Del Pilar ES | San Isidro |  | 1 | 2 |  | Batch 1 | 8019562.5 | 7950000 | 7950000 | Completed | 1 | 2024-01-26 | 2024-01-25 | P00775231MN | 23NF0075 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132198 | Roxas ES | San Isidro |  | 1 | 3 |  | Batch 1 | 10440562.5 | 10350000 | 10344930.07 | Completed | 1 | 2024-02-25 | 2024-02-24 | P00775228MN | 23NF0085 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | JZL BUILDERS ENTERPRISES
NC 2023 | SHS | CARAGA | Siargao | 304782 | San Isidro National High School | SAN ISIDRO |  | 1 | 5 |  | Batch 1 | 17915400 | 17760000 | 17750048.41 | Completed | 1 | 2024-08-30 | 2024-08-30 | P00775230MN | 23NF0108 | 2023-08-02 | 2023-08-22 | 2023-08-22 | 2023-12-21 | 2023-12-29 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132204 | Tigasao ES | San Isidro |  | 1 | 2 |  | Batch 1 | 8019562.5 | 7950000 | 7944856.16 | Completed | 1 | 2024-01-26 | 2024-01-25 | P00775229MN | 23NF0080 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132208 | Garcia Elementary School | SANTA MONICA (SAPAO) |  | 1 | 3 |  | Batch 1 | 10440562.5 | 10350000 | 10344911.47 | Completed | 1 | 2024-01-26 | 2024-01-26 | P00775232MN | 23NF0073 | 2023-07-04 | 2023-07-11 | 2023-07-25 | 2023-07-28 | 2023-07-31 | JZL BUILDERS ENTERPRISES
NC 2023 | K10 | CARAGA | Siargao | 132209 | Libertad ES | SANTA MONICA (SAPAO) |  | 1 | 3 |  | Batch 1 | 10440562.5 | 10350000 | 10344993.07 | Completed | 1 | 2024-02-25 | 2024-02-25 | P00775233MN | 23NF0086 | 2023-07-18 | 2023-07-26 | 2023-08-08 | 2023-08-15 | 2023-08-25 | SEVERS CONSTRUCTION
NC 2023 | K10 | CARAGA | Surigao City | 132284 | Libuac Elementary School | SURIGAO CITY (Capital) |  | 1 | 4 |  | Batch 1 | 10329528.65 | 10239929.27 | 10227813.11 | Completed | 1 | 2024-05-05 | 2024-05-05 | 23NG0082 | 23NG0082 | 2023-08-09 | 2023-08-17 | 2023-08-29 | 2023-09-06 | 2023-09-26 | AJP Builders and Supplies
NC 2023 | K10 | CARAGA | Surigao City | 132301 | Punta Bilar ES | SURIGAO CITY (Capital) |  | 1 | 4 |  | Batch 2 | 9713930.61 | 9385440.2 | 6703291.76 | Completed | 1 | 2024-11-25 | 2024-11-25 | 23NG0165 | 23NG0165 | 2024-02-29 | 2024-03-08 | 2024-03-20 | 2024-04-16 | 2024-04-30 | 417 Construction Corporation | With Project Modification; from 4CL to 3CL
NC 2023 | K10 | CARAGA | Surigao del Norte | 132321 | Alegria CES | ALEGRIA |  | 1 | 6 |  | Batch 1 | 18864871.16 | 18701235.35 | 18701204.49 | Completed | 1 | 2024-07-03 | 2024-11-16 | 23NG0077 | 23NG0077 | 2023-07-25 | 2023-08-02 | 2023-08-14 | 2023-08-22 | 2023-09-05 | RJB CONSTRUCTION & SUPPLY
NC 2023 | K10 | CARAGA | Surigao del Norte | 304811 | Alegria National High School | ALEGRIA |  | 1 | 6 |  | Batch 1 | 19016183.66 | 18851235.35 | 18822166.82 | Completed | 1 | 2024-06-16 | 2024-10-10 | 23NG0075 | 23NG0075 | 2023-07-25 | 2023-08-02 | 2023-08-14 | 2023-08-22 | 2023-09-05 | ROMZ BUILDERS
NC 2023 | K10 | CARAGA | Surigao del Norte | 130665 | Don Epifanio Cedro Elementary School | ALEGRIA |  | 1 | 2 |  | Batch 1 | 7913541.31 | 7844898.45 | 7841435.78 | Completed | 1 | 2024-05-11 | 2024-05-11 | 23NG0066 | 23NG0066 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | P & G CONSTRUCTION & SUPPLY
NC 2023 | SHS | CARAGA | Surigao del Norte | 304813 | Bacuag National Agro-Industrial School | BACUAG |  | 1 | 6 |  | Batch 1 | 18985941.34 | 18821255.35 | 18791778.69 | Ongoing | 0.92 | 2024-07-02 |  | 23NG0076 | 23NG0076 | 2023-07-25 | 2023-08-02 | 2023-08-14 | 2023-08-22 | 2023-09-05 | C.V. CONSTRUCTION AND DEVELOPMENT | WITH WORK SUSPENSION ORDERS, UNDER LIQUIDATED DAMAGES
NC 2023 | K10 | CARAGA | Surigao del Norte | 132451 | Binocaran ES | MALIMONO |  | 1 | 2 |  | Batch 1 | 7782403.81 | 7714898.45 | 7714857.15 | Completed | 1 | 2024-05-16 | 2024-05-16 | 23NG0067(RE-AD) | 23NG0067(RE-AD) | 2023-08-22 | 2023-08-30 | 2023-09-11 | 2023-09-14 | 2023-09-27 | P & G CONSTRUCTION & SUPPLY
NC 2023 | SHS | CARAGA | Surigao del Norte | 304818 | Cantapoy National High School | MALIMONO |  | 1 | 2 |  | Batch 1 | 7883278.81 | 7814898.45 | 7799898.46 | Completed | 1 | 2024-07-24 | 2024-07-24 | 23NG0087 | 23NG0087 | 2023-09-12 | 2023-09-20 | 2023-10-02 | 2023-10-09 | 2023-11-21 | GEVANS CONSTRUCTION & SUPPLY
NC 2023 | K10 | CARAGA | Surigao del Norte | 132458 | Hanagdong Elementary School | MALIMONO |  | 1 | 4 |  | Batch 1 | 15885924.85 | 15748128.72 | 15677243.39 | Completed | 1 | 2024-06-04 | 2024-06-04 | 23NG0084 | 23NG0084 | 2023-08-22 | 2023-08-30 | 2023-09-11 | 2023-09-14 | 2023-09-27 | ALGAMON CONSTRUCTION
NC 2023 | K10 | CARAGA | Surigao del Norte | 132340 | Magtangale ES | SAN FRANCISCO (ANAO-AON) |  | 1 | 4 |  | Batch 1 | 16128024.85 | 15988128.72 | 15974041.94 | Completed | 1 | 2024-04-05 | 2024-04-05 | 23NG0069 | 23NG0069 | 2023-08-09 | 2023-08-17 | 2023-08-29 | 2023-09-06 | 2023-09-26 | AJP BUILDERS AND SUPPLIES
NC 2023 | K10 | CARAGA | Surigao del Norte | 132528 | Gacepan ES | SISON |  | 1 | 2 |  | Batch 1 | 8004328.81 | 7934898.45 |  | REVERTED | [11 empty] | REVERTED BECAUSE THE BUILDABLE SPACE LEFT WAS OCCUPIED BY THE LAST MILE SCHOOL BUILDING PROGRAM
NC 2023 | K10 | CARAGA | Surigao del Norte | 132529 | Hinapayaw ES | SISON |  | 1 | 2 |  | Batch 1 | 7565625 | 7500000 | 7499706.08 | Completed | 1 | 2024-04-20 | 2024-04-19 | 23NG0069 | 23NG0069 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | C.V. CONSTRUCTION AND DEVELOPMENT
NC 2023 | K10 | CARAGA | Surigao del Norte | 132538 | Banban ES | TAGANA-AN |  | 1 | 2 |  | Batch 1 | 8064853.81 | 7994898.45 | 7994822.36 | Completed | 1 | 2024-04-08 | 2024-04-08 | 23NG0073 | 23NG0073 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | C.V. CONSTRUCTION AND DEVELOPMENT
NC 2023 | K10 | CARAGA | Surigao del Norte | 305953 | Himama-ug National High School | TAGANA-AN |  | 1 | 4 |  | Batch 1 | 15795137.35 | 15658128.72 | 15607514.71 | Completed | 1 | 2024-04-08 | 2025-05-15 | 23NG0086 | 23NG0086 | 2023-09-12 | 2023-09-20 | 2023-10-02 | 2023-10-09 | 2023-11-21 | ROMZ BUILDERS
NC 2023 | K10 | CARAGA | Surigao del Norte | 501680 | Hinatuan Integrated School | TAGANA-AN |  | 1 | 4 |  | Batch 1 | 16309599.85 | 16168128.72 | 16037588.61 | Completed | 1 | 2024-04-28 | 2024-12-28 | 23NG0078 | 23NG0078 | 2023-08-09 | 2023-08-17 | 2023-08-29 | 2023-09-06 | 2023-09-26 | ROMZ BUILDERS
NC 2023 | K10 | CARAGA | Surigao del Norte | 132548 | Tagana-an CES | TAGANA-AN |  | 1 | 2 |  | Batch 1 | 7666500 | 7600000 | 7600000 | Completed | 1 | 2024-03-20 | 2024-03-18 | 23NG0068 | 23NG0068 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | AMALGO CONSTRUCTION
NC 2023 | K10 | CARAGA | Surigao del Norte | 132549 | Talavera ES | TAGANA-AN |  | 1 | 2 |  | Batch 1 | 8155641.31 | 8084898.45 | 8082810 | Completed | 1 | 2024-04-11 | 2024-04-11 | 23NG0072 | 23NG0072 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | AMALGO CONSTRUCTION
NC 2023 | K10 | CARAGA | Surigao del Norte | 132560 | Calang-Custodio ES | TUBOD |  | 1 | 4 |  | Batch 1 | 16047324.85 | 15908128.72 | 15904066.41 | Completed | 1 | 2024-05-28 | 2024-08-09 | 23NG0080 | 23NG0080 | 2023-08-09 | 2023-08-17 | 2023-08-29 | 2023-09-11 | 2023-09-26 | LVRO CONSTRUCTION & SUPPLY | UNDER LIQUIDATED DAMAGES
NC 2023 | K10 | CARAGA | Surigao del Norte | 132562 | Marciano Dapar ES (Cawilan ES) | TUBOD |  | 1 | 2 |  | Batch 1 | 7515187.5 | 7450000 | 7437768.88 | Completed | 1 | 2024-04-11 | 2024-04-11 | 23NG0071 | 23NG0071 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | ALGAMON CONSTRUCTION
NC 2023 | K10 | CARAGA | Surigao del Norte | 132567 | Timamana ES | TUBOD |  | 1 | 2 |  | Batch 1 | 7515187.5 | 7450000 | 7419541.5 | Completed | 1 | 2024-02-11 | 2024-02-10 | 23NG0070 | 23NG0070 | 2023-07-18 | 2023-07-26 | 2023-08-07 | 2023-08-14 | 2023-08-30 | AMALGO CONSTRUCTION
NC 2023 | SHS | CARAGA | Surigao del Norte | 304855 | Tubod National High School | TUBOD |  | 1 | 12 |  | Batch 1 | 42583627.23 | 15668128.72 | 13510173.53 | Completed | 1 | 2024-06-22 | 2025-02-15 | 23NG0081 | 23NG0081 | 2023-08-09 | 2023-08-17 | 2023-08-29 | 2023-09-06 | 2023-09-26 | MIGO CONSTRUCTION | UNDER LIQUIDATED DAMAGES
NC 2023 | K10 | CARAGA | Surigao del Sur | 132600 | Amag Elementary School | BAYABAS |  | 1 | 2 |  | Batch 1 | 4766132.35 | 4724790.43 | 4720442.22 | Completed | 1 | 2023-12-01 | 2024-02-28 | P00775256MN | P00775256MN | 2023-06-16 | 2023-06-29 | 2023-07-17 | 2023-07-26 | 2023-07-31 | CYL CONSTRUCTION AND SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 501275 | Panaosawon Integrated School | BAYABAS |  | 1 | 2 |  | Batch 1 | 4766132.35 | 4724790.43 | 4683576.2 | Completed | 1 | 2023-12-01 | 2023-12-01 | P00775257MN | P00775257MN | 2023-06-16 | 2023-06-29 | 2023-07-17 | 2023-07-26 | 2023-07-31 | CYL CONSTRUCTION AND SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 132682 | Carmen Central Elementary School | CARMEN |  | 1 | 12 |  | Batch 1 | 37727250 | 18700000 | 18,590,563.21 18,499,278.00 | Completed | 1 | 2024-04-02 |  | P00775258MN; P00775259MN | P00775258MN; P00775259MN | 2023-07-03 | 2023-07-03 | 2023-07-17 | 2023-07-28 | 2023-08-02 | TRIDENT ENGINEERING SERVICES and RJ CONSTRUCTION & SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 500050 | Esperanza Integrated School | CARMEN |  | 1 | 10 |  | Batch 1 | 26813592.21 | 18700000 | 7,860,844.11 18,484,265.65 | Completed | 1 |  |  | P00775263MN; P00775264MN | P00775263MN; P00775264MN | [5 empty] | RJ CONSTRUCTION & SUPPLY; LICSAL CONST. CORPORATION | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 305747 | Gacub Atad S. Iligan Tribal National High School | CARMEN |  | 1 | 4 |  | Batch 1 | 7949967.21 | 7881008.39 | 7856655.3 | Completed | 1 | 2024-04-17 | 2024-09-05 | P00775262MN | P00775262MN | 2023-07-11 | 2023-07-18 | 2023-07-31 | 2023-08-08 | 2023-08-15 | ROWIE'S CONSTRUCTION | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 132687 | San Vicente Elementary School | CARMEN |  | 1 | 2 |  | Batch 1 | 4766132.35 | 4724790.43 | 4702137.51 | Completed | 1 | 2023-12-19 | 2023-12-19 | P00775260MN | P00775260MN | 2023-07-11 | 2023-07-18 | 2023-07-31 | 2023-08-08 | 2023-08-15 | ROWIE'S CONSTRUCTION | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 214548 | Tabinas Indigenous Community Elementary School | CARMEN |  | 1 | 2 |  | Batch 1 | 4766132.35 | 4724790.43 | 4704773.28 | Completed | 1 | 2023-12-11 | 2024-08-28 | P00775261MN | P00775261MN | 2023-06-16 | 2023-06-29 | 2023-07-11 | 2023-07-26 | 2023-08-03 | RJ CONSTRUCTION AND SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 132771 | Diatagon Barangay Elementary School | LIANGA |  | 1 | 6 |  | Batch 1 | 18863625 | 18700000 | 18218116.54 | Completed | 1 | 2024-04-02 | 2025-01-16 | P00775265MN | P00775265MN | 2023-06-26 | 2023-07-03 | 2023-07-17 | 2023-07-28 | 2023-08-02 | RJ CONSTRUCTION AND SUPPLY | Completed
NC 2023 | SHS | CARAGA | Surigao del Sur | 304915 | St. Christine National High School | LIANGA |  | 1 | 6 |  | Batch 3 | 19990000 | 19290350 |  | Ongoing | 0 | [10 empty] | Under Procurement
NC 2023 | K10 | CARAGA | Surigao del Sur | 214546 | Sangay Elementary School of Living Tradition | SAN MIGUEL |  | 1 | 6 |  | Batch 1 | 18863625 | 18700000 | 18499355.41 | Completed | 1 | 2024-04-03 | 2024-08-07 | P00775266MN | P00775266MN | 2023-06-30 | 2023-07-07 | 2023-07-19 | 2023-07-31 | 2023-08-04 | RJ CONSTRUCTION AND SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 502151 | Balbuena Integrated School | HINATUAN |  | 1 | 5 |  | Batch 1 | 10087500 | 10000000 | 9952940.25 | Completed | 1 | 2024-02-03 | 2024-04-04 | P00775267MN | P00775267MN | 2023-06-02 | 2023-06-09 | 2023-06-22 | 2023-07-11 | 2023-07-19 | SVTS BUILDERS AND SUPPLY | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 501293 | Pamian Integrated School | LINGIG |  | 1 | 5 |  | Batch 1 | 10087500 | 10000000 | 9999966.61 | Completed | 1 | 2023-12-26 | 2024-04-07 | P00775268MN | P00775268MN | 2023-06-02 | 2023-06-09 | 2023-06-22 | 2023-07-11 | 2023-07-20 | ROCK DIWATA BUILDERS, INC. | Completed
NC 2023 | K10 | CARAGA | Surigao del Sur | 132919 | Sta Fe Elementary School | TAGBINA |  | 1 | 5 |  | Batch 1 | 10087500 | 10000000 | 9999374.87 | Completed | 1 | 2023-12-26 | 2024-03-02 | P00775269MN | P00775269MN | 2023-06-02 | 2023-06-09 | 2023-06-22 | 2023-07-11 | 2023-07-21 | SVTS BUILDERS AND SUPPLY | Completed
NC 2023 | SHS | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) |  | 1 | 20 |  | Batch 1 | 30262500 | 30000000 | 29797557.85 | Completed | 1 | 2024-08-04 | 2025-05-05 | P00775272MN |  | 2023-06-26 | 2023-07-07 | 2023-07-19 | 2023-07-31 | 2023-08-04 | Rowies Construction
NC 2023 | K10 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) |  | 1 | 3 |  | Batch 1 | 6272288.54 | 6217882.07 | 6197214.35 | Completed | 1 | 2023-08-15 | 2023-09-25 | P00775270MN |  | 2023-07-11 | 2023-07-18 | 2023-07-31 | 2023-08-08 | 2023-08-15 | Licsal Construction Corporation
NC 2023 | K10 | CARAGA | Tandag City | 132980 | Telaje Elementary School | CITY OF TANDAG (Capital) |  | 1 | 2 |  | Batch 1 | 4766132.35 | 4724790.43 | 4694737.86 | Completed | 1 | 2023-08-04 | 2023-09-20 | P00775271MN |  | 2023-06-30 | 2023-07-07 | 2023-07-19 | 2023-07-31 | 2023-08-04 | Rowies Construction
NC 2024 |  | CARAGA | Agusan del Norte | 131478 | San Roque ES | LAS NIEVES |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  |  | Ongoing | 0.3
NC 2024 |  | CARAGA | Agusan del Norte | 131479 | Subait Elementary School | LAS NIEVES |  | 1 | 2 | 1STY2CL | BATCH 1 | 8838999.14 |  |  | Ongoing | 0.65
NC 2024 |  | CARAGA | Agusan del Norte | 131555 | Linao-Linao ES | BUENAVISTA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | CARAGA | Agusan del Norte | 131502 | Sta. Ana ES | NASIPIT |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0.8
NC 2024 |  | CARAGA | Agusan del Sur | 317441 | Salug Nhs | ESPERANZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969333.47 | Completed | 1 | 2025-02-09 |  | P00875282MN-CW1 | 24NB0078 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-28 | 2024-09-09 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE | COMPLETED AND INSPECTED WITH COMPLIED PUNCHLIST
NC 2024 |  | CARAGA | Agusan del Sur | 131692 | Skyline Elementary School | ESPERANZA |  | 1 | 2 | 1STY2CL | BATCH 1 | 5414000 |  | 5385037.35 | Ongoing | 0.98 | 2025-02-09 |  |  | 24NB0086 | 2024-08-16 | 2024-08-27 | 2024-09-09 | 2024-09-15 | 2024-10-07 | JB CIANO CONSTRUCTION | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 131693 | Sta Fe Elementary School | ESPERANZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973713.09 | Completed | 1 | 2025-02-09 |  | P00875283MN-CW1 | 24NB0079 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-28 | 2024-09-09 | MAIR CONSTRUCTION AND GENERAL MERCHANDISE | COMPLETED AND INSPECTED WITH COMPLIED PUNCHLIST
NC 2024 |  | CARAGA | Agusan del Sur | 131809 | Sta Irene Central ES | PROSPERIDAD (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4465576.37 | Ongoing | 0.98 | 2025-02-12 |  | P00875284MN-CW1 | 24NB0080 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-29 | 2024-09-10 | MIGO CONSTRUCTION | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 131958 | Nuevo Trabajo ES | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968524.66 | Ongoing | 0.98 | 2025-02-09 |  | P008875285MN-CW1 | 24NB0081 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-28 | 2024-09-09 | MJS CONSTRUCTION AND SUPPLY | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 304736 | San Luis NHS | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4464326.87 | Ongoing | 0.98 | 2025-02-12 |  | P008875286MN-CW1 | 24NB0082 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-29 | 2024-09-10 | MIGO CONSTRUCTION | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 304726 | New Tubigon High School of Home Industries | SIBAGAT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972204.87 | Ongoing | 0.8 | 2025-03-14 |  | P008875287MN-CW1 | 24NB0083 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-29 | 2024-09-10 | JB CIANO CONSTRUCTION
NC 2024 |  | CARAGA | Agusan del Sur | 304710 | Del Monte National High School | TALACOGON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970822.01 | Completed | 1 | 2025-02-09 |  | P008875288MN-CW1 | 24NB0084 | 2024-07-09 | 2024-07-19 | 2024-08-01 | 2024-08-28 | 2024-09-09 | JB CIANO CONSTRUCTION | COMPLETED AND INSPECTED WITH COMPLIED PUNCHLIST
NC 2024 |  | CARAGA | Agusan del Sur | 131665 | West Bunawan Central Elementary School | BUNAWAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925780.32 | Completed | 1 | 2024-11-19 |  | P00875290MN | 24NC0071 | 2024-07-16 | 2024-07-23 | 2024-08-05 | 2024-08-14 | 2024-08-27 | K-PRIME CONSTRUCTION | COMPLETED AND INSPECTED WITH COMPLIED PUNCHLIST
NC 2024 |  | CARAGA | Agusan del Sur | 304716 | La Paz NHS | LA PAZ |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4935051.69 | Ongoing | 0.72 | 2024-11-19 |  | P00875291MN | 24NC0072 | 2024-07-16 | 2024-07-23 | 2024-08-05 | 2024-08-14 | 2024-08-27 | L.M. CONSTRUCTION & GENERAL MARKETING
NC 2024 |  | CARAGA | Agusan del Sur | 131727 | Kauswagan ES | LORETO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4936113.8 | Ongoing | 0.98 | 2024-11-20 |  | P00875292MN | 24NC0073 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-08-15 | 2024-08-28 | DAVE CONSTRUCTION | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 501727 | Jose T. Cuyos Sr. II Integrated School | ROSARIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4939687.17 | Ongoing | 0.98 | 2024-11-20 |  | P00875293MN | 24NC0074 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-08-15 | 2024-08-28 | DDS BUILDERS | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 304703 | Agusan del Sur National High School | SAN FRANCISCO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4933726.54 | Ongoing | 0.55 | 2025-02-04 |  | P00875294MN | 24NC0077 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-11-18 | 2024-11-27 | HANDDEL CONSTRUCTION\
NC 2024 |  | CARAGA | Agusan del Sur | 500798 | Patrocinio Integrated School | SANTA JOSEFA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4939133.64 | Ongoing | 0.98 | 2025-02-04 |  | P00875295MN | 24NC0078 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-11-18 | 2024-11-24 | DDS BUILDERS | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 304741 | Magsaysay Nhs | SIBAGAT |  | 1 | 4 | 1STY4CL | BATCH 1 | 10243593 |  |  | Ongoing | 0.62 |  |  |  | 24NB0091 | 2024-08-16 | 2024-08-27 | 2024-09-09 | 2024-09-15 | 2024-10-07
NC 2024 |  | CARAGA | Agusan del Sur | 500952 | Singapore Integrated School | TRENTO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4935046.92 | Ongoing | 0.98 | 2024-11-20 |  | P00875296MN | 24NC0075 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-08-15 | 2024-08-28 | MAORIN BUILDERS & SUPPLY | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Agusan del Sur | 131900 | Caigangan Elementary School | VERUELA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949460.48 | Ongoing | 0.98 | 2024-11-20 |  | P00875297MN | 24NC0076 | 2024-07-17 | 2024-07-24 | 2024-08-06 | 2024-08-15 | 2024-08-28 | JICLAM BUILDERS & ENTERPRISES | PARTIALLY COMPLETED / CONTRACTOR OF DPWH NOT REQUESTING FOR FINAL INSPECTION IN DEP-ED
NC 2024 |  | CARAGA | Bayugan City | 317420 | Magkiangkang National High School | CITY OF BAYUGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969326.53 | Completed | 1 | 2025-12-02 | 2025-09-02 | 24NB0085 | [5 empty] | 2024-09-16 | MAIR CONSTRUCTION & GENERAL MERCHANDISE
NC 2024 |  | CARAGA | Bislig City | 132835 | Mangagoy Hilltop Elementary School | CITY OF BISLIG |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9655574.71 | Completed | 1 | 2024-10-31 | 2024-11-13 | 24NI0074 | 24NI0074 | 2024-04-16 | 2024-04-23 | 2024-04-30 | 2024-05-06 | 2024-05-13 | MCLA Construction
NC 2024 |  | CARAGA | Butuan City | 304756 | Agusan National High School | BUTUAN CITY (Capital) |  | 1 | 20 | 4STY20CL | GAA 17B | 40000000 |  |  | Under Procurement | 0 |  |  | 25ND0148 |  | 2025-07-03 | 2025-03-14 | 2025-03-26
NC 2024 |  | CARAGA | Butuan City | 501522 | Baobaoan Integrated School | BUTUAN CITY (Capital) |  | 1 | 4 | 1STY4CL | BATCH 2 | 13595606.49 |  |  | Under Procurement | 0 |  |  | 24ND0164 |  | 2025-07-03 | 2025-03-14 | 2025-03-26
NC 2024 |  | CARAGA | Butuan City | 501522 | Baobaoan Integrated School* | BUTUAN CITY (Capital) |  | 1 | 16 | 2-UNITS 2STY8CL | BATCH 2 | 84000000 |  |  | Under Procurement | 0 |  |  | 24ND0167 |  | 2025-07-03 | 2025-03-14 | 2025-03-26
NC 2024 |  | CARAGA | Butuan City | 317520 | Pedro D. Duncano National HS* | BUTUAN CITY (Capital) |  | 1 | 9 | 3STY9CL | BATCH 2 | 48000000 |  |  | Under Procurement | 0 |  |  | 24ND0168 |  | 2025-07-03 | 2025-03-14 | 2025-03-26
NC 2024 |  | CARAGA | Butuan City | 317520 | Pedro D. Duncano National HS* | BUTUAN CITY (Capital) |  | 1 | 4 | 2STY4CL | BATCH 2 | 21000000 |  |  | Under Procurement | 0 |  |  | 24ND0165 |  | 2025-07-03 | 2025-03-14 | 2025-03-26
NC 2024 |  | CARAGA | Butuan City | 132039 | Taguibo Elementary School | BUTUAN CITY (Capital) |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  |  | Under Procurement | 0 |  |  | 24ND0169 |  | 2025-03-27 | 2025-03-04 | 2025-05-05
NC 2024 |  | CARAGA | Butuan City | 212504 | Tud-ol ES | BUTUAN CITY (Capital) |  | 1 | 4 | 1STY4CL | BATCH 1 | 12727872.51 |  | 12587488.67 | Completed | 1 | 2024-12-07 | 2024-11-20 | 24ND0106 | 24ND0107 | 2024-04-18 | 2024-04-25 | 2024-07-05 |  | 2024-10-06 | Olin Construction
NC 2024 |  | CARAGA | Cabadbaran City | 304676 | Calamba National High School | CITY OF CABADBARAN |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0.6
NC 2024 |  | CARAGA | Cabadbaran City | 501724 | Chief Justice Ramon Avancena Integrated School | CITY OF CABADBARAN |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0.7
NC 2024 |  | CARAGA | Cabadbaran City | 305746 | Francisco C. Jongko National High School | CITY OF CABADBARAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.95
NC 2024 |  | CARAGA | Dinagat Island | 304815 | Cagdianao National High School | CAGDIANAO |  | 1 | 3 | 1STY3CL | BATCH 1 | 9089219.58 |  | 8902406.64 | Completed | 1 | 2024-03-12 | 2024-03-12 | P00875395MN |  |  | 2023-07-12 | 2023-12-19 | 2024-03-25 | 2024-03-25 | Heavy John Engineering Consultancy
NC 2024 |  | CARAGA | Dinagat Island | 132370 | Sta Rita Elementary School | CAGDIANAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4910324.91 | Ongoing | 0.3 | 2025-07-31 |  | P00875298MN |  |  | 2024-03-10 | 2024-10-15 | 2024-05-11 | 2024-05-11 | Radian Construction and Supply | late start due to modification request
NC 2024 |  | CARAGA | Dinagat Island | 132374 | Valencia Elementary School | CAGDIANAO |  | 1 | 6 | 2UNITS 1STY3CL | BATCH 1 | 21306138.55 |  | 20913362.17 | Ongoing | 0.95 | 2025-03-03 |  | P00875394MN |  |  | 2023-07-12 | 2023-12-19 | 2024-03-25 | 2024-03-25 | Radian Construction and Supply | late start due to modification request
NC 2024 |  | CARAGA | Dinagat Island | 132399 | Magsaysay Elementary School | DINAGAT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4910324.91 | Ongoing | 0.1 | 2025-07-31 |  | P00875299MN |  |  | 2024-03-10 | 2024-10-15 | 2024-05-11 | 2024-05-11 | Radian Construction and Supply | late start due to modification request
NC 2024 |  | CARAGA | Dinagat Island | 304808 | Albor National High School | LIBJO (ALBOR) |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2025-10-10 |  | P00875303MN |  |  | 2024-03-10 | 2024-10-15 | 2024-05-11 | 2024-05-11 | Radian Construction and Supply | late start due to modification request; April - 100%, May - 10%
NC 2024 |  | CARAGA | Dinagat Island | 304839 | Plaridel National High School | LIBJO (ALBOR) |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  |  | Ongoing | 0.3 |  |  | P00875301MN |  |  | 2024-03-10 | 2024-10-15 |  |  | LAV CONSTRUCTION | CHANGE LOCATION TO BOA ES-30% ON GOING; late start due to modificationwaiting for SAA
NC 2024 |  | CARAGA | Dinagat Island | 132319 | Rosita Elementary School | LIBJO (ALBOR) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Ongoing | 0.1 | 2025-11-08 |  | P00875300MN |  |  | 2024-03-10 | 2024-10-15 | 2025-05-11 | 2025-05-11 | Radian Construction and Supply | late start due to modification request
NC 2024 |  | CARAGA | Dinagat Island | 304810 | San Jose National High School | LIBJO (ALBOR) |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  |  | Ongoing | 0.3 | [9 empty] | LAV CONSTRUCTION | CHANGE LOCATION TO BOA ES-30% ON GOING; late start due to modificationwaiting for SAA
NC 2024 |  | CARAGA | Siargao | 132130 | Don Paulino Elementary School | DAPA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972950 | Completed | 1 | 2024-04-10 | 2024-02-10 | P00875305MN | 24NF0059 | 2024-04-24 | 2024-02-05 | 2024-05-17 | 2024-05-28 | 2024-05-06 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132132 | Osmena Elementary School | DAPA |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7958000 | Completed | 1 | 2024-11-26 | 2024-11-26 | P00875313MN | 24NF0058 | 2024-04-24 | 2024-02-05 | 2024-05-17 | 2024-05-24 | 2024-05-30 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132143 | San Miguel Elementary School | DAPA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972999.63 | Completed | 1 | 2024-10-23 | 2024-10-23 | P00875308MN | 24NF0072 | 2024-07-05 | 2024-05-14 | 2024-05-28 | 2024-11-06 | 2024-06-21 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132164 | Bitoon Elementary School | DEL CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973000 | Completed | 1 | 2024-09-27 | 2024-09-27 | P00875306MN | 24NF0061 | 2024-04-24 | 2024-02-05 | 2024-05-17 | 2024-05-24 | 2024-05-30 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132177 | Quezon Primary School | DEL CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7957974.17 | Completed | 1 | 2024-09-12 | 2024-09-12 | P00875314MN | 24NF0060 | 2024-04-24 | 2024-02-05 | 2024-05-17 | 2024-05-30 | 2024-07-06 | JZL BUILDERS AND ENTERPRISES
NC 2024 |  | CARAGA | Siargao | 132191 | Salvacion Elementary School | PILAR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972990 | Completed | 1 | 2024-09-27 | 2024-09-27 | P00875309MN | 24NF0069 | 2024-04-30 | 2024-07-05 | 2024-05-21 | 2024-05-24 | 2024-05-30 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132210 | Mabini Elementary School | SANTA MONICA (SAPAO) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972993.65 | Completed | 1 | 2024-09-27 | 2024-09-27 | P00875307MN | 24NF0068 | 2024-04-30 | 2024-07-05 | 2024-05-21 | 2024-05-24 | 2025-05-30 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132221 | Don. Albino Taruc Memorial ES | SOCORRO |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954408.38 | Completed | 1 | 2024-12-22 | 2024-12-18 | P00875315MN | 24NF0071 | 2024-07-05 | 2024-05-14 | 2024-05-28 | 2024-11-06 | 2024-06-21 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132232 | Honrado Community Elementary School | SOCORRO |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954887.52 | Completed | 1 | 2024-03-12 | 2024-11-30 | P00875316MN | 24NF0062 | 2024-04-24 | 2024-02-05 | 2024-05-17 | 2024-05-28 | 2024-05-06 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Siargao | 132234 | Nueva Estrella Central Elementary School | SOCORRO |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954408.38 | Completed | 1 | 2024-12-22 | 2024-12-18 | P00875317MN | 24NF0074 | 2024-05-17 | 2024-05-23 | 2024-07-06 | 2024-11-06 | 2024-06-21 | RADIAN CONSTRUCTION & SUPPLY
NC 2024 |  | CARAGA | Surigao City | 132242 | Aurora Elementary School | SURIGAO CITY (Capital) |  | 1 | 4 | 1STY4CL | BATCH 1 | 11071704.07 |  | 11013330.36 | Completed | 1 | 2025-04-22 | 2025-04-22 | 24NG0060 | 24NG0060 | 2024-05-21 | 2024-05-29 | 2024-06-10 | 2024-07-16 | 2024-07-30 | AJP Builder and Supply | with time extension
NC 2024 |  | CARAGA | Surigao City | 132263 | Bonifacio ES | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954780.91 | Completed | 1 | 2025-01-06 | 2025-04-02 | 24NG0055 | 24NG0055 | 2024-04-16 | 2024-04-24 | 2024-05-06 | 2024-06-06 | 2024-06-14 | AJP Builder and Supply | Under Liquidated damages
NC 2024 |  | CARAGA | Surigao City | 132247 | Canlanipa Central Elementary School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | funds reverted; no buildable space
NC 2024 |  | CARAGA | Surigao City | 132265 | Capalayan ES | SURIGAO CITY (Capital) |  | 1 | 3 | Construction of One (1) Storey - Three (3) Classrooms School Building (with Common Toilet) with Provision of Rainwater Collector | BATCH 1 | 9648364.53 |  | 9575713.34 | Ongoing | 0.6442 | 2025-08-25 |  | 24NG0071 | 24NG0071 | 2024-06-18 | 2024-06-26 | 2024-11-29 | 2024-12-16 | 2025-01-03 | ROMZ Builders | W/ WORK SUSPENSION due to obstruction
NC 2024 |  | CARAGA | Surigao City | 304795 | Ipil National High School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7894589.75 | Completed | 1 | 2025-02-07 | 2025-04-02 | 24NG0056 | 24NG0056 | 2024-04-16 | 2024-04-24 | 2024-05-06 | 2024-06-06 | 2024-06-14 | AJP Builder and Supply | Under Liquidated damages
NC 2024 |  | CARAGA | Surigao City | 132300 | J. R. Clavero Memorial Elementary School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7954620.99 | Completed | 1 | 2025-01-15 | 2025-04-02 | 24NG0057 | 24NG0058 | 2024-04-16 | 2024-04-24 | 2024-05-06 | 2024-06-06 | 2024-06-14 | AJP Builder and Supply | Under Liquidated damages
NC 2024 |  | CARAGA | Surigao City | 132297 | Mabua ES | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7894554.1 | Completed | 1 | 2025-02-07 | 2025-04-02 | 24NG0058 | 24NG0058 | 2024-04-16 | 2024-04-24 | 2024-05-06 | 2024-06-06 | 2024-06-14 | AJP Builder and Supply | Under Liquidated damages
NC 2024 |  | CARAGA | Surigao City | 317706 | Manjagao National High School | SURIGAO CITY (Capital) |  | 1 | 4 | 2STY4CL | BATCH 1 | 21362750.48 |  | 21200658.33 | Ongoing | 0.6256 | 2025-08-03 |  | 24NG0068 | 24NG0068 | 2024-06-18 | 2024-06-26 | 2024-09-24 | 2024-10-08 | 2024-10-22 | Amalgo Construction | WITH SUSPENSION ORDER DUE TO ABSENCE OF PERMIT
NC 2024 |  | CARAGA | Surigao City | 132256 | Orok Elementary School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7958692 | Completed | 1 | 2025-02-05 | 2025-02-05 | 24NG0061 | 24NG0061 | 2024-05-21 | 2024-05-29 | 2024-06-10 | 2024-08-09 | 2024-08-26 | AJP Builder and Supply
NC 2024 |  | CARAGA | Surigao City | 317705 | Patricio A. Bernaldez Memorial National High School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7959732.55 | Completed | 1 | 2024-12-24 | 2024-12-24 | 24NG0059 | 24NG0059 | 2024-04-16 | 2024-04-24 | 2024-05-06 | 2024-06-06 | 2024-06-14 | AJP Builder and Supply
NC 2024 |  | CARAGA | Surigao City | 317701 | Taft National High School | SURIGAO CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7837283.65 | Completed | 1 | 2025-03-12 | 2025-04-25 | 24NG0063 | 24NG0063 | 2024-05-21 | 2024-05-29 | 2024-06-10 | 2024-07-16 | 2024-07-30 | 417 CONSTRUCTION CORP. | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao City | 132243 | Vicente C. Cabilao Memorial Elementary School | SURIGAO CITY (Capital) |  | 1 | 6 | 2STY6CL | BATCH 1 | 22064483.27 |  | 21554077 | Ongoing | 0.9345 | 2025-04-11 |  | 24NG0065 | 24NG0065 | 2024-05-24 | 2024-05-31 | 2024-06-13 | 2024-07-16 | 2024-07-30 | 417 CONSTRUCTION CORP. | WITH WORK SUSPENSION ORDERS; under liquidated damages
NC 2024 |  | CARAGA | Surigao del Norte | 132343 | Bitaog ES | BACUAG |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  | 9940507.74 | Ongoing | 0.25 | 2025-05-06 |  | 24NG0083 | 24NG0083 | 2024-09-26 | 2024-04-10 | 2024-10-24 | 2024-11-18 | 2024-12-18 | P&G CONSTRUCTION AND SUPPLY
NC 2024 |  | CARAGA | Surigao del Norte | 132440 | Quezon ES | MAINIT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944524.64 | Ongoing | 0.37 | 2025-01-06 |  | 24NG0079 | 24NG0079 | 2024-09-18 | 2024-09-26 | 2024-08-10 | 2024-10-16 | 2024-04-11 | ALLYDE CONSTRUCTION | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao del Norte | 132448 | Tapian ES | MAINIT |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944708.53 | Ongoing | 0.57 | 2025-04-17 |  | 24NG0078 | 24NG0078 | 2024-09-18 | 2024-09-26 | 2024-08-10 | 2024-10-16 | 2024-04-11 | ALLYDE CONSTRUCTION | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao del Norte | 132330 | Amontay ES | SAN FRANCISCO (ANAO-AON) |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7838517.62 | Ongoing | 0.64 | 2025-11-01 |  | 24NG0062 | 24NG0062 | 2024-05-21 | 2024-05-29 | 2024-10-06 | 2024-07-16 | 2024-05-08 | 417 CONSTRUCTION CORP. | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao del Norte | 502154 | Jubgan Integrated School | SAN FRANCISCO (ANAO-AON) |  | 1 | 4 | 2-UNITS 1STY2CL | GAA 17B | 16000000 |  | 15564603.36 | Ongoing | 0.59 | 2025-08-04 |  | 24NG0069 | 24NG0069 | 2024-06-18 | 2024-06-26 | 2024-08-07 | 2024-07-26 | 2024-12-08 | 417 CONSTRUCTION CORP. | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao del Norte | 502154 | Jubgan Integrated School | SAN FRANCISCO (ANAO-AON) |  |  | 4 | 2-UNITS 1STY2CL | GAA 17B | 10000000 |  | 9783184.81 | Ongoing | 0.35 | 2025-05-17 |  | 24NG0070 | 24NG0070 | 2024-06-18 | 2024-06-26 | 2024-08-07 | 2024-09-08 | 2024-11-29 | 417 CONSTRUCTION CORP.
NC 2024 |  | CARAGA | Surigao del Norte | 132529 | Hinapayaw ES | SISON |  | 1 | 2 | 1STY2CL | BATCH 1 | 7310516.14 |  | 7175726.31 | Ongoing | 0.88 | 2025-02-03 |  | 24NG0064 | 24NG0064 | 2024-05-21 | 2024-05-29 | 2024-10-06 | 2024-07-16 | 2024-05-08 | 417 CONSTRUCTION CORP. | WITH WORK SUSPENSION ORDERS
NC 2024 |  | CARAGA | Surigao del Sur | 500321 | Matho Integrated School | CORTES |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 3452342.65 | Completed | 1 | 2024-09-04 | 2024-09-04 | P00875341MN | P00875341MN | 2024-04-05 | 2024-04-21 | 2024-04-24 | 2024-05-08 | 2024-05-21 | LICSAL CONSTRUCTION CORPORATION | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 214546 | Sangay Elementary School of Living Tradition | SAN MIGUEL |  | 1 | 3 | 1STY3CL | GAA 17B | 5000000 |  | 4923980.54 | Completed | 1 | 2024-09-24 | 2024-09-24 | P00875331MN | P00875331MN | 2024-04-05 | 2024-04-12 | 2024-04-24 | 2024-05-08 | 2024-05-21 | LICSAL CONSTRUCTION CORPORATION | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 132569 | Amaga Elementary School | BAROBO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9930171.7 | Completed | 1 | 2024-11-04 | 2024-11-04 | P00875333MN | P00875333MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | Dave Construction | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 132570 | Anunang Elementary School | BAROBO |  | 1 | 1 | 1STY3CL | GAA 17B | 10000000 |  | 9949879.19 | Completed | 1 | 2024-12-02 | 2024-11-29 | P00875339MN | P00875339MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | SVTS Builders and Supply | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 132580 | Gamut Elementary School | BAROBO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9943429.33 | Completed | 1 | 2024-11-08 | 2024-11-05 | P00875334MN | P00875334MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | SVTS Builders and Supply | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 132581 | Guinhalinan Elementary School | BAROBO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9946467.65 | Completed | 1 | 2024-10-03 | 2024-09-27 | P00875332MN | P00875332MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | Dave Construction | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 132583 | Kinayan Elementary School | BAROBO |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9949966.65 | Completed | 1 | 2024-11-15 | 2024-11-15 | P00875337MN | P00875337MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | White Torch Builders Corporation | Project Completed
NC 2024 |  | CARAGA | Surigao del Sur | 214506 | Sto. Nino Elementary School | HINATUAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9748288.86 | Ongoing | 0.67 | 2025-03-13 |  | P00875336MN | P00875336MN | 2024-08-09 | 2024-08-16 | 2024-08-29 | 2024-09-12 | 2024-09-25 | ROWIES CONSTRUCTION | 6.51% Slippage
NC 2024 |  | CARAGA | Surigao del Sur | 500583 | Quezon Integrated School | TAGBINA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9913773.35 | Completed | 1 | 2025-01-16 | 2025-01-15 | P00875335MN | P00875335MN | 2024-04-02 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-05-20 | MN Bayalas Construction | Project Completed
NC 2024 |  | CARAGA | Tandag City | 304892 | Jacinto P. Elpa National High School | CITY OF TANDAG (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 25000000 |  | 24603184.34 | Ongoing | 0.85 | 2024-08-05 |  | P00875328MN |  | 2024-03-27 | 2024-03-04 | 2024-04-15 | 2024-04-26 | 2024-08-05 | ROWIES CONSTRUCTION
NC 2024 |  | CARAGA | Tandag City | 502041 | Mabuhay Integrated School | CITY OF TANDAG (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | 2024-06-11 | 2024-11-21 | P00875330MN |  | 2024-05-16 | 2024-05-23 | 2024-04-06
NC 2024 |  | CARAGA | Tandag City | 132970 | Pangi Elementary School | CITY OF TANDAG (Capital) |  | 1 | 4 | 1STY4CL | BATCH 1 | 10400000 |  | 10337789.83 | Completed | 1 | 2024-11-19 | 2024-12-17 | P00875401MN |  | 2023-02-11 | 2023-09-11 | 2024-09-05 | 2024-04-19 | 2024-04-30 | RJ CONSTRUCTION AND SUPPLY
NC 2024 |  | CARAGA | Tandag City | 502042 | Rosario Integrated School | CITY OF TANDAG (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4923387.8 | Completed | 1 | 2024-09-24 | 2024-09-24 | P00875329MN |  | 2024-05-04 | 2024-12-04 | 2024-04-24 | 2024-08-05 | 2024-05-21 | LICSAL CONSTRUCTION CORP.
NC 2024 |  | CARAGA | Tandag City | 132977 | San Jose Elementary School | CITY OF TANDAG (Capital) |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 3444309.22 | Completed | 1 | 2024-10-09 | 2024-08-10 | P00875342MN |  | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-14 | 2024-05-24 | RJ CONSTRUCTION AND SUPPLY
NC 2024 |  | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 3373734.87 | Completed | 1 | 2024-09-09 | 2024-09-09 | P00875340MN |  | 2024-12-04 | 2024-04-19 | 2024-02-05 | 2024-05-14 | 2024-05-24 | RJ CONSTRUCTION AND SUPPLY

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.