## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | NCR | Caloocan City | 305384 | Baesa HS | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | NC0214S00072 | 14OD0076 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Caloocan City | 136651 | Bagumbong ES | Caloocan City | 1 | 1 | 18 | 3STY 18CL | 2014 K10 BATCH 3 | 27120494.0625 |  |  | COMPLETED | 1 |  |  | NC0214S00061
NC 2014 | K10 (2014) | NCR | Caloocan City | 223501 | Caloocan North ES | Caloocan City | 1 | 1 | 48 | 4STY28CL & 4STY20CL | 2014 K10 BATCH 4B | 71170836.41 |  |  | COMPLETED | 1 |  |  | NC0214S00114
NC 2014 | K10 (2014) | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | NC0214S00059 | 14OD0073 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Caloocan City | 136640 | Sto. Nino ES | Caloocan City | 1 | 1 | 8 | 4STY 8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-23 | NC0214S00060 | 14OD0074 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 36 | 4STY20CL & 4STY16CL | 2014 K10 BATCH 4B | 57805359.69 |  |  | COMPLETED | 1 |  |  | NC0214S00113
NC 2014 | K10 (2014) | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-07-25 | NC0214S00065 | 14OD0075 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-16 | 2015-02-27 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Caloocan City | 136608 | Kasarinlan ES | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | COMPLETED | 1 |  |  | NC0214S00097 | 15OD0070 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-14 | 2015-09-04 | J. SIMEON CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 6 | 4STY6CL (Open Ground) | 2014 K10 BATCH 4A | 15035522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 | 12 | Completion of 4STY/12CL(remaining 4CL), 4STY/8CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 30789912.22 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 40 | 2 UNITS 4STY20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 | 9 | 3STY/9CL and installation of remaining bored piles | 2014 K10 BATCH 4B | 16565073.8707 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 136613 | Maypajo ES | Caloocan City | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00108 | [7 empty] | termination of contract on process
NC 2014 | K10 (2014) | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | [10 empty] | ongoing; rebidded
NC 2014 | K10 (2014) | NCR | Las Piñas City | 136773 | CAA ES | CITY OF LAS PIÑAS | 0 | 1 | 32 | 2 Units 4STY 16CL | 2014 K10 BATCH 3 | 55078781.25 |  |  | COMPLETED | 1 | 2016-08-10 |  | NC0214S00066 | 15OI0047 | 2015-04-13 | 2015-04-15 | 2015-05-04 | 2015-06-03 | 2015-06-18 | PRECIOUS CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Las Piñas City | 305432 | Golden Acres NHS | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00123 |  | 2015-07-17 |  | 2015-08-05 |  | 2015-09-02 | RGDG CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00100 | 15OI0140 | 2015-07-23 | 2015-07-24 | 2015-11-23 |  |  | DAVHEZ TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30
NC 2014 | K10 (2014) | NCR | Malabon City | 500337 | Catmon IS | CITY OF MALABON | 0 | 1 | 24 | 3STY15CL (1CL open) & 3STY9CL | 2014 K10 BATCH 4B | 36184341.37 |  |  | COMPLETED | 1 |  |  | NC0214S00101 | 016OA0017 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03
NC 2014 | K10 (2014) | NCR | Malabon City | 136828 | Dampalit ES | CITY OF MALABON | 0 | 1 | 2 | Completion of 2STY/4CL(construction of remaining 2CL) | 2014 K10 BATCH 4B | 5078460.2437 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Malabon City | 136854 | Epifanio de los Santos ES | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4B | 21383013.45 |  |  | COMPLETED | 1 |  |  | NC0214S00102 | 016OA0019 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03
NC 2014 | K10 (2014) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30
NC 2014 | K10 (2014) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 | 7 | Completion of 2STY/10CL(construction of remaining 7CL) | 2014 K10 BATCH 4B | 7383047.4188 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Malabon City | 305447 | Malabon NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Malabon City | 136844 | Muzon ES | CITY OF MALABON | 0 | 1 | 5 | Completion of 2STY/6CL(construction of remaining 5CL) | 2014 K10 BATCH 4B | 8023252.8469 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30
NC 2014 | K10 (2014) | NCR | Malabon City | 136832 | Panghulo ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | COMPLETED | 1 | 2016-05-05 |  | NC0214S00069 | 015OA0079 | 2015-07-29 | 2015-08-07 | 2015-08-19 | 2015-08-27 | 2015-09-09 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 19220118.3984 |  |  | COMPLETED | 1 | [8 empty] | 2015-10-30
NC 2014 | SHS (2014) | NCR | Malabon City | 305449 | Potrero NHS | Malabon City | 0 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | NC0214S00136 | 016OA0016 | 2015-12-09 | 2015-12-17 | 2015-12-29 |  | 2016-02-03
NC 2014 | K10 (2014) | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-29 |  | NC0214S00103 | 015OA0095 | 2015-10-22 | 2015-11-11 | 2015-11-11 | 2015-11-23 | 2015-12-03 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NCR | Malabon City | 320504 | Tinajeros NHS - Acacia Annex | CITY OF MALABON | 0 | 1 | 0 | Completion of 3STY/9CL | 2014 K10 BATCH 4B | 1505105.4375 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | NC0214S00105 | 015OA0062 | 2015-06-10 | 2015-06-18 | 2015-06-29 | 2015-07-08 | 2015-07-24 | DREAMWORX BUILDER & TRADING, INC.
NC 2014 | K10 (2014) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6303 |  |  | COMPLETED | 1 | [8 empty] | 2015-09-09
NC 2014 | K10 (2014) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 | 3 | Completion of 3STY/9CL(construction of remaining 3CL) | 2014 K10 BATCH 4B | 3995299.9594 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Mandaluyong City | 319803 | Eulogio Rodriguez Integ. Sch. | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-03-01 |  | NC0214S00135 | 0150B0159 | 2015-06-30 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-09-30 | TRACSOM BUILDERS, INC.
NC 2014 | K10 (2014) | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 20 | 4STY20CL w/ provision for micropiles @ 250mm, 15m depth (Replacement of Burned Bldg.) | 2014 K10 BATCH 3 | 46161534.375 |  |  | COMPLETED | 1 | [9 empty] | ORANI BUILDERS
NC 2014 | K10 (2014) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [9 empty] | M.V CALDO CONST. ENGINEERING & SUPPLY
NC 2014 | SHS (2014) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | Manila | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | [9 empty] | SUPREME ABF CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 28544390.625 |  |  | COMPLETED | 1 | [9 empty] | PRECIOUS CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Manila | 305299 | Dona Teodora Alonzo HS | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0114S00027 | 15-OE0091 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | HEXAMINDZ CORPORATION
NC 2014 | SHS (2014) | NCR | Manila | 305303 | Raja Soliman Science and Technology High School | Manila | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | reverted | 0 |  |  | NC0114S00021
NC 2014 | SHS (2014) | NCR | Manila | 305307 | Claro M. Recto High School | Manila | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0114S00026 | 15-OE0090 | 2015-07-02 | 2015-07-02 | 2015-07-14 |  |  | SUPREME ABF CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Manila | 305312 | Manila Science High School | Manila | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | reverted | 0 |  |  | NC0114S00030
NC 2014 | K10 (2014) | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | [9 empty] | TRIPLE 8 CONST. & SUPPLY
NC 2014 | K10 (2014) | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 | 16 | 4STY 16CL(proposed for SHS) | 2014 K10 BATCH 3 | 27539390.625 |  |  | reverted | 0
NC 2014 | K10 (2014) | NCR | Marikina City | 136671 | Barangka ES | Marikina City | 1 | 1 | 10 | 3STY 30CL (phase 2) | 2014 K10 BATCH 4A | 12864000 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-03 | NC0214S00090 | 0140B0258 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | NVF CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.3984 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 319907 | Jesus dela Pena NHS | Marikina City | 1 | 1 | 16 | 4STY 16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-01-06 |  | NC0214S00084 | 0150B0290 | 2014-12-10 | 2014-12-11 | 2015-03-30 | 2015-04-28 | 2015-05-12 | FIRMABUILT CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 319904 | Kalumpang National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4A | 31900584.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Marikina City | 305402 | Malanday NHS | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-07-01 |  | NC0214S00133 | 0150B0295 | 2015-10-01 | 2015-10-02 | 2015-10-15 | 2015-10-21 | 2015-11-04 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4A | 19861783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City |  | San Roque National High School | Marikina City | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136687 | Sto. Nino ES | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-02-05 |  | NC0214S00082 | 0140B0238 | 2014-12-04 | 2014-12-11 | 2015-03-30 | 2015-04-30 | 2015-05-08 | JEMN BUILDERS
NC 2014 | SHS (2014) | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 319906 | Sto. Nino National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136679 | Concepcion Integrated School | Marikina City | 2 | 1 | 3 | Completion of 4STY12CL (Construction of remaining 3CL) | 2014 K10 BATCH 4B | 5625000 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-04 | NC0214S00219 | 0150B0127 | 2015-05-13 | 2015-05-15 | 2015-05-26 | 2015-06-16 | 2015-08-14 | LTDL BUILDERS
NC 2014 | K10 (2014) | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 | 32 | 2 UNITS 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 55209089.5312 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 | 0 | Construction of remaining 1 bay of stairs for both buildings (4STY20CL & 3STY9CL) and connecting bridge | 2014 K10 BATCH 4B | 4968750 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 24 | 2UNITS 4STY12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 | 24 | 2 units of 4STY/12CL | 2014 K10 BATCH 3 | 40023567.1875 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136900 | F. de Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-10-30 | NC0214S00086 | 150I0005 | 2015-01-26 | 2015-01-26 | 2015-02-09 | 2015-02-20 | 2015-03-05 | MRRM TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0214S00145 | 15OI0161 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | CHIARA CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136902 | Lakeview ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15205622.3438 |  |  | COMPLETED | 1 | 2015-09-30 |  | NC0214S00077 | 15OI0004 | 2015-01-26 | 2015-01-28 | 2015-02-09 | 2014-02-16 | 2015-03-05 | VICVERA BUILDERS,INC.
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 60 | 3 UNITS 4STY20CL | 2014 K10 BATCH 3 | 96181903.125 |  |  | COMPLETED | 1 |  |  | NC0214S00142
NC 2014 | SHS (2014) | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22692343.62 |  |  | COMPLETED | 1 | 2016-06-18 |  | NC0214S00131 | 15OI0107 | 2015-08-25 | 2015-08-19 | 2015-09-07 | 2015-09-15 | 2015-10-21 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-08 | 2015-09-08 | NC0214S00051 | 140I0099 | 2015-01-04 | 2015-01-07 | 2015-01-20 | 2015-02-06 | 2015-02-26 | REDCAR TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Muntinlupa City | 136906 | Tunasan ES | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2UNITS 4STY8CL | 2014 K10 BATCH 4B | 29795037.68 |  |  | reverted | 0 |  |  | NC0214S00144 | 15OI0164 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-15 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Navotas |  | Bangkulasi NHS | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY 12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 136858 | Dagat-dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | COMPLETED | 1 | 2015-05-08 | 2015-05-08 | NC0214S00095 | 014OA0051 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 6 | Micropiles | 2014 K10 BATCH 4A | 7543437.8817 |  |  | COMPLETED | 1 | 2015-05-08 | 2015-05-08 | NC0214S00092 | 014OA0047 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 4 | cement grouting at 10 meter depth | 2014 K10 BATCH 4A | 1593230.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 0 | cement grouting at 13.5 meter depth | 2014 K10 BATCH 4A | 1433787.4509 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-07 | NC0214S00096 | 014OA0050 | 2014-12-04 | 2014-12-05 | 2014-12-09 | 2014-12-24 | 2015-01-09 | FEL-GENE CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 22937518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 |  | 3STY12CL | 2014 K10 BATCH 3 | 23904509.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 28929509.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 27397518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | NC0214S00129 | 015OA0093 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-15 | 2015-10-27 | J. SIMEON CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 19897518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 3 | cement grouting | 2014 K10 BATCH 4A | 3242509.8498 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 | 32 | 4STY32CL | 2014 K10 BATCH 3 | 51340935 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 136757 | Paranaque Elementary School Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 | 36 | 4STY24CL & 4STY/12CL | 2014 K10 BATCH 3 | 58442484.8438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 19205522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 136765 | Sto. Niño ES | CITY OF PARAÑAQUE | 1 | 1 | 12 | 4STY12CL only since a 3STY3CL bldg was already constructed at the proposed site | 2014 K10 BATCH 4B | 22152343.62 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City |  | Don Bosco ES (El Dorado) | CITY OF PARAÑAQUE | 2 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 16 | 4STY16CL(open 4CL @ GF) | 2014 K10 BATCH 3 | 20768199.0547 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Parañaque City | 136758 | Sampaloc Site II ES | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Pasay City | 305367 | Pasay City East HS | Pasay City | 0 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-01 |  | NC0114S00023 | 15OH0074 | 2015-07-15 | 2015-07-27 | 2015-08-27 | 2015-08-30 | 2015-09-10 | HERBANA BUILDERS AND SUPPLY
NC 2014 | SHS (2014) | NCR | Pasay City | 319602 | Philippine National School for the Blind | Pasay City | 0 |  |  | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 | 9 | 4STY9CL (using 4STY12CL open GF) | 2014 K10 BATCH 3 | 19107283.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32050584.375 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-23 |  | NC0214S00119 | 0150B0167 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-08-27 | L.P.O. ENTERPRISES
NC 2014 | K10 (2014) | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-06 | 2015-10-06 | NC0314S00021 | 14OF0130 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-07 | 2015-10-07 | NC0314S00022 | 14OF0131 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | NC0314S00061 | 15OF0111 | 2015-07-15 | 2015-07-24 | 2015-08-05 | 2015-08-24 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305321 | Judge Juan Luna HS | Quezon City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0314S00067 | 15OF0123 | 2015-08-12 | 2015-08-13 | 2015-08-25 |  |  | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION
NC 2014 | K10 (2014) | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/8CL(Ramp, plumbing, sanitary & tile works(incl masonry for toilet cubicles), security grilles, railings) | 2014 K10 BATCH 4B | 364687.5 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00046 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305329 | Quezon City Science HS | Quezon City | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-05-23 |  | NC0314S00065 | 15OF0112 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | JYBL CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | 2016-05-23 |  | NC0314S00044 | 15OF0103 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | AYLAN CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Quezon City | 305327 | San Francisco HS | Quezon City | 1 | 1 | 16 | 4STY16CL | 2014 SHS BATCH 1 | 26702469.42 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Quezon City | 305324 | Sergio Osmena, Sr. HS to BALINGASA HS | Quezon City | 1 | 1 |  | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-10-12 |  | NC0314S00052 | 15OF0136 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-09 | 2015-10-13 | AYLAN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works, blackboards) | 2014 K10 BATCH 4B | 279375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136539 | Bagong Silangan ES | QUEZON CITY | 2 | 1 | 0 | Completion of 4STY/8CL(Plumbing (incl. septic tank), sanitary & tile works, security grilles) | 2014 K10 BATCH 4B | 414375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15105522.3438 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Quezon City | 305331 | Commonwealth HS | Quezon City | 2 | 1 | 20 | 4STY20CL | 2014 SHS BATCH 1 | 31102890.27 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-11-30 | NC0314S00026 | 14OF0133 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-12 | JAMARI CONSTRUCTION (FORMERLY FRAE CONSTRUCTION)
NC 2014 | K10 (2014) | NCR | Quezon City | 319505 | Judge Feliciano Belmonte, Sr. HS | QUEZON CITY | 2 | 1 | 24 | 4STY16CL & 4STY8CL | 2014 K10 BATCH 3 | 42564912.9688 |  |  | COMPLETED | 1 | 2016-08-01 |  | NC0314S00034 | 15OF0062 | 2014-12-04 | 2015-03-13 | 2015-06-03 | 2015-06-11 | 2015-06-25 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION
NC 2014 | K10 (2014) | NCR | Quezon City |  | New Holy Spirit HS (Annex) | Quezon City | 2 | 1 | 40 | 2 UNITS OF 4STY 20CL | 2014 K10 BATCH 3 | 64101168.75 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136548 | Payatas B ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-11-08 | 2015-10-07 | NC0314S00024 | 14OF0127 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Quezon City | 136540 | Pres. Corazon C. Aquino ES (Batasan Hills ES) | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1 | 2016-03-06 |  | NC0314S00020 | 14OF0126 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 305347 | Carlos P. Garcia HS | QUEZON CITY | 3 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Quezon City | 305347 | Carlos P. Garcia HS | Quezon City | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136557 | Cubao ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-05-13 |  | NC0314S00048 | 15OG0088 | 2015-08-05 | 2015-08-20 | 2015-08-24 | 2015-09-01 | 2015-09-17 | RCDG CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | NCR | Quezon City | 305352 | Juan Sumulong HS | Quezon City | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-17 |  | NC0314S00060 | 15OG0093 | 2015-08-05 | 2015-08-15 | 2015-08-24 | 2015-09-10 | 2015-09-21 | GREENWALL CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Quezon City | 136565 | Teodora Alonzo ES | QUEZON CITY | 3 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | NC0314S00019 | 14og00088 | 2014-11-07 | 2014-11-20 | 2014-11-25 | 2014-12-16 | 2014-12-19 | METRICS CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305355 | Carlos L. Albert HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-24 |  | NC0314S00058 | 15OG0100 | 2015-08-20 | 2015-09-01 | 2015-09-07 | 2015-09-22 | 2015-09-28 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS
NC 2014 | SHS (2014) | NCR | Quezon City | 305361 | Manuel Roxas HS | Quezon City | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-06 |  | NC0314S00057 | 15-OG084 | 2015-07-28 | 2015-08-07 | 2015-10-20 | 2015-11-02 | 2015-11-06 | ST. GERRARD CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Quezon City | 305356 | Ponciano Bernardo HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-19 |  | NC0314S00056 | 15-OG083 | 2015-07-27 | 2015-08-10 | 2015-08-10 | 2015-08-29 | 2015-09-01 | GRAIA CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | NCR | Quezon City | 305359 | Quezon City HS | Quezon City | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-02 |  | NC0314S00053 | 15OG-0085 | 2015-07-22 | 2015-08-08 | 2015-08-10 | 2015-09-01 | 2015-09-04 | E.A. RAMIREZ CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NCR | Quezon City | 136527 | Dona Rosario Elementary School | Quezon City | 5 | 1 | 0 | Completion of 4STY/8CL(2 units toilets, catch basins, electric fans, security grilles) | 2014 K10 BATCH 4B | 398437.5 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00039 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 319504 | Dona Rosario HS | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-08 | 2015-10-08 | NC0314S00032 | 14OF0125 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | JYBL CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 136534 | Lagro ES | Quezon City | 5 | 1 | 3 | Completion of 3STY 9CL: 3CL at 3rd Floor (masongry, carpentry. Electrical, painting), roofing and steel works, plumbing and sanitary works. Security grilles for the whole building | 2014 K10 BATCH 4A | 3718500 |  |  | COMPLETED | 1 | 2015-04-11 | 2015-05-11 | NC0314S00035 | 14OF0047 | 2014-11-28 | 2014-11-29 | 2014-12-04 | 2014-12-28 | 2015-01-06 | AYLAN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 305336 | Lagro HS | Quezon City | 5 | 1 | 0 | Completion of 4STY/16CL (Finishing work, plumbing, sanitary, tile works, cubicles, septic tank, security grills) | 2014 K10 BATCH 4B | 564375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136535 | Maligaya ES | Quezon City | 5 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-06-28 |  | NC0314S00040 | 15OF0106 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | R.D. MANDANAS CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Quezon City | 136537 | North Fairview ES | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-17 |  | NC0314S00049 | 15OF0108 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | E.A. RAMIREZ CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NCR | Quezon City | 136523 | Odelco ES | Quezon City | 5 | 1 | 4 | 4STY4CL | 2014 K10 BATCH 3 | 10205307.6562 |  |  | COMPLETED | 1 | 2015-07-10 | 2015-09-07 | NC0314S00030 | 14OF0123 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | TAPNIO AND TAN CONSTRUCTION AND DEVT. CORPORATION
NC 2014 | K10 (2014) | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | Quezon City | 5 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4B | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-27 |  | NC0314S00047 | 15OF0107 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY
NC 2014 | K10 (2014) | NCR | Quezon City | 136538 | San Agustin ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1 | 2015-11-07 | 2015-11-05 | NC0314S00031 | 14OF0124 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI
NC 2014 | K10 (2014) | NCR | Quezon City | 136529 | San Gabriel ES | Quezon City | 5 | 1 | 0 | Completion of 4STY/12CL(Plumbing, sanitary & tile works (incl masonry for cubicles), septic tank, security grilles) | 2014 K10 BATCH 4B | 564375 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-25 | NC0314S00041 | 15OF0120 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-21 | AYLAN CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | NCR | Quezon City | 305342 | Sta. Lucia HS | Quezon City | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-10-22 |  | NC0314S00055 | 15OF0143 | 2015-08-18 | 2015-09-04 | 2015-09-29 | 2015-10-06 | 2015-10-22 | JYBL CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | NCR | Quezon City | 222501 | West Fairview Elementary School | Quezon City | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-29 |  | NC0314S00042 | 15OF0109 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | MPJR BUILDERS COMPANY
NC 2014 | SHS (2014) | NCR | Quezon City | 305335 | Ismael Mathay, Sr. HS | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-30 |  | NC0314S00054 | 15OF0114 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-25 | M O M ENTERPRISES
NC 2014 | K10 (2014) | NCR | Quezon City | 136522 | Leopoldo B. Santos ES | Quezon City | 6 | 1 | 8 | 4STY/8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-10-08 | 2015-10-08 | NC0314S00033 | 14OF0122 | 2014-12-04 | 2014-12-08 | 2014-12-19 | 2014-12-29 | 2015-01-06 | HONEYVILLE CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Quezon City | 136524 | Placido del Mundo ES | Quezon City | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-30 |  | NC0314S00037 | 15OF0110 | 2015-07-24 | 2015-07-24 | 2015-08-05 | 2015-08-06 | 2015-08-28 | MPJR BUILDERS COMPANY
NC 2014 | SHS (2014) | NCR | Taguig City & Pateros | 320607 | Agripino Manalo National HS | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | Reverted | 0 |  |  | NC0214S00120
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Pateros | 1 | 1 | 12 | 4STY 12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27539390.625 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Taguig City & Pateros | 305467 | Maria Concepcion Cruz HS | Taguig City & Pateros | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0214S00121 | 0150B0164 | 2015-07-05 | 2015-07-06 | 2015-07-16 | 2015-07-31 |  | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 3 | 38430701.25 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1 | 2015-09-12 |  | NC0214S00048 | 0140B0253 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-16 | 2015-02-14 | E.R. VENZON CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Taguig City & Pateros | 305460 | Taguig National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-05 |  | NC0214S00122 | 0150B0271 | 2015-08-13 | 2015-08-17 | 2015-08-27 | 2015-09-18 | 2015-10-07 | R.T. MORABE CONSTRUCTION
NC 2014 | SHS (2014) | NCR | Taguig City & Pateros | 305464 | Tipas National High School | Taguig City & Pateros | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-13 |  | NC0214S00124 | 0150B0303 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-10 | 2015-11-16 | R.S. MESA CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros |  | DepED Property | Taguig- Pateros | 2 | 1 | 24 | 2 Units 4STY 12CL(elevated @ 1.5m) | 2014 K10 BATCH 3 | 44137296.8717 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Taguig City & Pateros | 320602 | Maria Asuncion Rodriguez Tiñga High School | Taguig City & Pateros | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | Reverted | 0 | 2016-03-05 |  | NC0214S00125 | 015B0164 | 2015-07-01 | 2015-07-03 | 2015-07-14 | 2015-08-04 | 2015-09-07
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20011783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Taguig City & Pateros | 305465 | Western Bicutan NHS | TAGUIG CITY | 2 | 1 | 7 | 4STY7CL (with 1 stair open below 1cl) | 2014 K10 BATCH 3 | 15064922.3438 |  |  | COMPLETED | 1 | 2016-03-12 |  | NC0214S00034 | 0140B0254 | 2014-12-10 | 2014-12-11 | 2014-12-23 | 2015-01-06 | 2015-01-07 | HONY TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1363279.6969 |  |  | COMPLETED | 1 | 2015-10-18 |  |  |  | 2015-07-22 |  | 2015-08-18 |  |  | C.B. Tampengco Const. & Supply
NC 2014 | SHS (2014) | NCR | Valenzuela City | 320404 | Bignay NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15185522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Valenzuela City | 305440 | Lawang Bato NHS | CITY OF VALENZUELA | 1 | 1 | 3 | 3STY3CL | 2014 K10 BATCH 3 | 7323603.6328 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-10 | NC0214S00040 | 14OD0077 | 2014-12-09 | 2014-12-19 | 2014-12-22 | 2015-01-25 | 2015-02-27 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136797 | Malinta ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL (incl. finishing works, toilets, roofing, carpentry) | 2014 K10 BATCH 4B | 4523437.5 |  |  | COMPLETED | 1 | 2015-12-02 |  | NC0214S00111 | 15OD0065 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2014 | SHS (2014) | NCR | Valenzuela City | 305438 | Malinta NHS | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00138 | 15OD0101 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO.
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14195118.4009 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Completion of 3STY12CL(construction of remaining 8CL) | 2014 K10 BATCH 4B | 5533060.275 |  |  | COMPLETED | 1 | 2016-01-01 |  | NC0214S00110 | 15OD0071 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-09-04 | LARSEN-DUTCHER CONSTRACTOR
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136812 | Roberta de Jesus ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-17 |  | NC0214S00116 | 15OD0074 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-09-04 | 2015-09-21 | CARDRIAN BUILDERS CO.
NC 2014 | K10 (2014) | NCR | Valenzuela City | 320402 | Vicente Trinidad NHS (Punturin NHS) | CITY OF VALENZUELA | 1 | 1 | 0 | Completion of 4STY8CL | 2014 K10 BATCH 4B | 1382887.575 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-10-16 | NC0214S00118 | 15OD0067 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-16 | 2015-09-04 | J. SIMEON CONSTRUCTION
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10817093.5547 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NCR | Valenzuela City | 320407 | Wawangpulo National High School | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14907518.84 |  |  | COMPLETED | 1 |  |  | NC0214S00127
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 2 | Completion of 3STY/6CL | 2014 K10 BATCH 4B | 2863237.8662 |  |  | COMPLETED | 1 | 2015-11-17 |  | NC0214S00115 | 15OD0064 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-18 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NCR | Valenzuela City | 136825 | Marulas Central ES | CITY OF VALENZUELA | 2 | 1 | 0 | Completion of 4STY/8CL & 3STY/9CL | 2014 K10 BATCH 4B | 1274735.0159 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-11-02 | NC0214S00109 | 15OD0066 | 2015-07-29 | 2015-08-10 | 2015-08-11 | 2015-08-17 | 2015-09-04 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | NCR | Caloocan City | 136650 | Bagbaguin ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00138 | 15OD0094 | 2015-09-18 | 2015-10-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | VICTORIA DEVELOPMENT AND CONSTRUCTION SUPPLY CORP.
NC 2015 | K10 (2015) | NCR | Caloocan City | 136641 | Kalayaan ES | Caloocan City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Caloocan City | 319705 | Maypajo HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00154 | [6 empty] | PRISMOIDIAL CONST. CORP.
NC 2015 | K10 (2015) | NCR | Caloocan City | 136629 | Morning Breeze ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00092 | 15OD0089 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-29 | 2015-10-23 | TM ABAD CONSTRUCTION
NC 2015 | K10 (2015) | NCR | Caloocan City | 136646 | NHC ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00140 | 15OD0102 | 2015-10-07 | 2015-10-16 | 2015-10-20 | 2015-10-26 | 2015-11-17 | CARDRIAN BUILDERS CO.
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 1 (Caloocan City Business High School) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | ORIENTECH CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 11 (Caloocan National Science & Technology High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | H.T.L. CONS'T
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 2 (Cielito Zamora High School) | Caloocan City | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-04 | 2015-09-22 | 2015-09-24 | 2015-09-29 | 2015-11-05 | T.M. ABAD CONS'T
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 4 (NHC HS) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | CARDRIAN BUILDERS CO.
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 6 (Bagong Barrio NHS - Annex) | Caloocan City | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | SUPREME ABF CONST. & CONST. SUPPLY CO. INC.
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 7 (AHS-Horacio Dela Costa Annex) | Caloocan City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-26 |  |  |  |  | GENETIAN BUILDERS
NC 2015 | SHS (2015) | NCR | Caloocan City |  | Proposed Stand Alone 9 (Bagumbong High School) | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-11 | 2015-09-29 | 2015-10-01 | 2015-10-05 | 2015-11-05 | VICTORIA DEV'T & CONS'T CORP.
NC 2015 | K10 (2015) | NCR | Caloocan City | 136649 | Tala ES | Caloocan City | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00143
NC 2015 | K10 (2015) | NCR | Caloocan City | 136631 | Talipapa ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00082 | 15OD0095 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-06 | 2015-11-05 | CARDRIAN BUILDERS CO.
NC 2015 | K10 (2015) | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00150 |  | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-09 | 2015-11-05
NC 2015 | K10 (2015) | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Caloocan City | 136638 | Urduja ES | Caloocan City | 1 |  | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | Caloocan City | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00137 | 15OD0096 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-10-01 | 2015-10-23 | CARDRIAN BUILDERS CO.
NC 2015 | K10 (2015) | NCR | Caloocan City | 136609 | Kaunlaran ES | Caloocan City | 2 | 1 |  | Completion of 4STY6CL (Open Ground) | 2015 COMPLETION BATCH 4 | 843004.5563 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Caloocan City | 305392 | M. B. Asistio Sr. HS Unit 1 | Caloocan City | 2 | 1 |  | Completion of 2 UNITSof 4STY20CL | 2015 COMPLETION BATCH 4 | 4993346.46 |  |  |  | 0
NC 2015 | K10 (2015) | NCR | Caloocan City | 305390 | Maria Clara HS | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00083 | 15OD0092 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM
NC 2015 | SHS (2015) | NCR | Caloocan City | 305392 | Proposed Stand Alone 3 (M. B. Asistio Sr. HS Unit 1) | Caloocan City | 2 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 8 | 53404938.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  |  |  | 2015-11-05 |  |  |  |  | EDISON DEV'T CONST. | ongoing; rebidded
NC 2015 | SHS (2015) | NCR | Caloocan City | 500330 | Proposed Stand Alone 5 (Tandang Sora IS) | Caloocan City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [9 empty] | C.B. TAMPENGCO CONST. & SUPPLY
NC 2015 | K10 (2015) | NCR | Caloocan City | 136614 | Sampalukan ES | Caloocan City | 2 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2088779.1753 |  |  |  | 1
NC 2015 | K10 (2015) | NCR | Caloocan City | 500330 | Tandang Sora IS | Caloocan City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  |  | 0 |  |  | NC0215S00165 | 15OD0088 | 2015-09-11 | 2015-09-23 | 2015-09-24 | 2015-09-30 | 2015-10-23 | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM | Contract Terminated
NC 2015 | SHS (2015) | NCR | City of San Juan |  | Proposed Stand Alone SHS 1 (Tech-Voc) (Pinaglabanan ES) | City of San Juan | 0 | 1 | 9 | 4STY12CL (open 3 cl @ ground) | 2015 SHS BATCH 5 | 21192344 |  |  | reverted | 0
NC 2015 | SHS (2015) | NCR | City of San Juan | 305423 | San Juan National HS (Academic) | City of San Juan | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | reverted | 0 |  |  | NC0215S00128
NC 2015 | SHS (2015) | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 |  | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Las Piñas City | 320304 | Las Pinas City National Science High School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 2UNITS 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 21280072.63 |  |  | COMPLETED | 1 |  |  | NC0215S00075 |  | 2015-08-17 |  | 2015-09-07 |  | 2016-03-01 | DAVHEZ TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00068 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | NCR | Las Piñas City | 305430 | Las Piñas National HIgh School | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00069 |  | 2015-12-17 |  | 2016-01-05 |  | 2016-03-23 | ORANI BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | NCR | Las Piñas City | 136778 | Manuyo Elementary School | CITY OF LAS PIÑAS | 0 | 1 | 3 | 3STY3CL | 2015 K10 BATCH 6 | 6653472.88 |  |  | COMPLETED | 1 |  |  | NC0215S00136 | 15OI0154 | 2015-12-03 |  | 2015-12-22 |  | 2016-01-15 | MRJR CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | NCR | Las Piñas City |  | Proposed Stand Alone SHS 1 (Las Pinas CES) | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  |  |  | 2015-10-28 |  | 2015-11-23 |  | 2015-12-22 | ORANI BUILDERS AND SUPPLY
NC 2015 | K10 (2015) | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Malabon City | 136830 | Malabon ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 15 | 3sty15cl | 2015 ADDITIONAL FUND BATCH 9 | 6111685.53 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Malabon City | 320502 | Malabon NHS - Concepcion Voc-Tech Annex | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 7 | 10417132 |  |  | COMPLETED | 1 |  |  | NC0215S00153 | [5 empty] | 2016-03-18
NC 2015 | K10 (2015) | NCR | Malabon City | 136831 | Panghulo ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 |  | Completion of Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 1718800.4616 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 1 (TNHS-Acacia Annex) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 | [8 empty] | 2016-01-11
NC 2015 | SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 2 (Dampalit ES) | CITY OF MALABON | 0 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 5 | 18222269 |  |  | COMPLETED | 1 | [8 empty] | 2016-07-19
NC 2015 | SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | COMPLETED | 1 | [8 empty] | 2016-06-07
NC 2015 | SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 4 (Imelda ES) | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 | [8 empty] | 2016-01-25
NC 2015 | SHS (2015) | NCR | Malabon City |  | Proposed Stand Alone SHS 6 (Santiago Syjuco Memorial School) | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 5 | 21383013 |  |  | COMPLETED | 1 | [8 empty] | 2016-04-11
NC 2015 | K10 (2015) | NCR | Malabon City | 500339 | Tanong IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | COMPLETED | 1 |  |  | NC0215S00152 | [5 empty] | 2016-03-18
NC 2015 | K10 (2015) | NCR | Malabon City | 136839 | Tonsuya ES | CITY OF MALABON | 0 | 1 |  | Completion of 3STY3CL | 2015 COMPLETION BATCH 4 | 612128.4262 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 319802 | Highway Hills Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 30152344 |  |  | COMPLETED | 1 |  |  | NC0215S00116 | 0150B0301 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-04 | 2015-11-16 | TRACSOM BUILDERS, INC.
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 500331 | Isaac Lopez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00070
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | reverted | 0 |  |  | NC0215S00073 | 0150B300 | 2015-10-08 | 2015-10-09 | 2015-10-22 | 2015-11-12 |  | TRACSOM BUILDERS, INC.
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 305393 | Mandaluyong High School | CITY OF MANDALUYONG | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 37202469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00067 | 0150B0299 | 2015-10-09 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-05 | TRACSOM BUILDERS, INC.
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 38002890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 26252344 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0115S00021 | 15-OE0159 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | R.D. TALENS CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 142465.625 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Manila | 305291 | Tondo High School | TONDO | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0115S00016
NC 2015 | K10 (2015) | NCR | Manila | 305296 | Pres. Sergio Osmena, Sr. High School | TONDO | 2 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 7694435.2484 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 10909209.6668 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | reverted | 0 |  |  | NC0115S00015
NC 2015 | K10 (2015) | NCR | Manila | 136464 | Moises Salvador Elementary School | Manila | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0115S00017 | 15-OE0158 | 2015-11-20 | 2015-11-20 | 2015-12-03 |  |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | NCR | Manila | 305308 | Valeriano E. Fugoso Memorial High School | MANILA | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0115S00020
NC 2015 | SHS (2015) | NCR | Manila | 305309 | M.Araullo High School | ERMITA | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0115S00014 | 15OH0097 | 2015-10-11 | 2015-10-26 | 2015-10-27 |  |  | WERR CONSTRUCTION INTERNATIONAL
NC 2015 | K10 (2015) | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 5577284.5063 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Manila | 305314 | Gen. Emilio Aguinaldo IS- Annex | Manila | 6 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 9983526.165 |  |  |  | 0
NC 2015 | SHS (2015) | NCR | Manila |  | Proposed Stand Alone SHS 6 (Bacood ES) | SAMPALOC | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [9 empty] | HEXAMINDZ CORPORATION
NC 2015 | K10 (2015) | NCR | Marikina City | 136672 | Industrial Valley ES | Marikina City | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 5999172.5916 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136675 | Malanday ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 2239374.87 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136676 | Marikina ES | Marikina City | 1 |  |  | Completion of 4STY12CL (Batch 4A) | 2015 COMPLETION BATCH 4 | 7462337.94 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Marikina City | 319905 | San Roque National High School | Marikina City | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136680 | Concepcion ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00085 | 0150B0293 | 2015-09-23 | 2015-10-05 | 2015-10-06 | 2015-10-29 | 2015-11-06 | ORANI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | NCR | Marikina City | 305403 | Concepcion Integrated School | Marikina City | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00115 | 0150B0292 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-27 | 2015-11-23 | C.B. GARAY PHILWIDE BUILDERS
NC 2015 | K10 (2015) | NCR | Marikina City | 136682 | H. Bautista ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 305398 | Marikina HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL & Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 15730030.3788 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136677 | Nangka ES | Marikina City | 2 | 1 |  | Completion 4STY12CL | 2015 COMPLETION BATCH 4 | 7213523.0963 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136684 | Parang ES | Marikina City | 2 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00086 | 0150B0285 | 2015-09-23 | 2015-09-25 | 2015-10-06 | 2015-10-22 | 2015-12-01 | ORANI BUILDERS & SUPPLY
NC 2015 | K10 (2015) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 |  | Completion of 2 Units 4STY12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Marikina City | 305404 | Parang HS | Marikina City | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136685 | SSS Village ES | Marikina City | 2 | 1 |  | Completion of 2 units of 4STY/12CL | 2015 COMPLETION BATCH 4 | 13266387.7325 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Marikina City | 136686 | St. Mary ES | Marikina City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00087 | 15OI0109 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-25 | 2015-10-20 | PRECIOUS CONSTRUCTION
NC 2015 | K10 (2015) | NCR | Muntinlupa City | 320702 | Muntinlupa Business High School - Sucat Annex | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00088 | 15OI0159 | 2015-12-14 | 2015-12-16 | 2015-12-28 | 2016-12-29 | 2016-01-19 | LMG CONSTRUCTION
NC 2015 | SHS (2015) | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 |  | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 1 (Muntinlupa NHS) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Muntinlupa City |  | Proposed Stand Alone SHS 2 (Cupang SHS) | CITY OF MUNTINLUPA | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Muntinlupa City | 136904 | Putatan ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00139 | 15OI0143 | 2015-11-12 | 2015-11-13 | 2015-11-25 | 2015-12-11 | 2015-12-23 | ORANI BUILDERS & SUPPLY
NC 2015 | K10 (2015) | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | NC0215S00145
NC 2015 | K10 (2015) | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 20 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY20CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 13422977.41 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Navotas | 340628 | Lisan SHS Stand Alone | CITY OF NAVOTAS | 0 | 1 | 17 | 2 units 3STY9CL(1 unit with 1 cl open at the ground floor; 1.5m addl elevation) | 2015 SHS BATCH 5 | 31836524 |  |  | reverted | 0
NC 2015 | K10 (2015) | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00144
NC 2015 | SHS (2015) | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 19897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00080 | 015OA0091 | 2015-09-18 | 2015-09-28 | 2015-10-08 | 2015-10-16 | 2015-10-27 | VRV CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00089 | 015OA0097 | 2015-11-02 | 2015-11-19 | 2015-11-27 |  |  | STRUKTURA TEKNIKA SERVICES CO.
NC 2015 | K10 (2015) | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | Completion of 3STY12CL. (Upgrading of 3STY12CL to 4STY12CL INCLUDING COST for soil improvement and additional 1m elevation | 2015 COMPLETION BATCH 4 | 4379706.6847 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Parañaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00146 | 15OC0075 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION
NC 2015 | K10 (2015) | NCR | Parañaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00141 | 15OC0069 | 2015-08-17 | 2015-08-20 | 2015-09-01 | 2015-09-08 | 2015-09-18 | MPJR BUILDERS COMPANY
NC 2015 | K10 (2015) | NCR | Parañaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 6 | 30952890.27 |  |  | COMPLETED | 1 |  |  | NC0215S00149 | 15OC0076 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-07 | 2015-09-18 | PRECIOUS CONSTRUCTION
NC 2015 | K10 (2015) | NCR | Parañaque City | 136754 | La Huerta ES | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY32CL | 2015 COMPLETION BATCH 4 | 5228199.416 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Parañaque City | 136756 | Paranaque ES Central | CITY OF PARAÑAQUE | 1 | 1 |  | Completion of 4STY24CL & 4STY/12CL | 2015 COMPLETION BATCH 4 | 14094676.5723 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Parañaque City | 305426 | Paranaque National High School - Baclaran | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 18 | 4STY20CL (2cl open at ground floor) | 2015 SHS BATCH 5 | 29822890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Parañaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Parañaque City |  | Proposed Stand Alone SHS 3 (PNHS-Sto. Nino) | CITY OF PARAÑAQUE | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Parañaque City |  | Proposed Stand Alone SHS 4 (PNHS-Don Bosco) | CITY OF PARAÑAQUE | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Pasay City | 319602 | Philippine HS for the Blind | PASAY CITY | 0 | 1 | 4 | 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 4354597.47 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Pasay City | 136595 | Rivera Village ES | Pasay City | 0 | 1 |  | 4STY9CL (Completion of 4STY12CL open GF) | 2015 COMPLETION BATCH 4 | 3192828.2063 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Pasay City | 136601 | Timoteo Paez ES | Pasay City | 0 | 1 |  | Completion of 4STY20CL | 2015 COMPLETION BATCH 4 | 6454915.895 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Pasig City |  | Porposed Stand Alone SHS 2 (Ugong Pasig City National) | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL (L-Shape) | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Pasig City |  | Proposed Stand Alone SHS 3 (RHS) | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 ADDITIONAL FUND BATCH 9 | 13293913.52 |  |  | COMPLETED | 1 |  |  | NC0315S00043 | 15OF0127 | 2015-08-12 | 2015-08-13 | 2015-12-15 | 2015-12-22 |  | AYLAN CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 4330387.33 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 319506 | National Orthopedic Hospital School for Crippled Children | QUEZON CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | NC0315S00033 | 15OF0102 | 2015-07-23 | 2015-07-10 | 2015-08-05 | 2015-08-06 | 2015-08-28 | SUMMIT MERIDIEN CONSTRUCTION GROUP INC.
NC 2015 | SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 1 (Balingasa HS; from Masambong HS & San Jose HS) | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 4 (Toro Hills; from Pugad Lawin & E Rod HS) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 5 (E. Abada; from SFHS) | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City |  | Proposed Stand Alone SHS 6 (Bagong Pag-asa ES) | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Quezon City | 136505 | San Antonio ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Quezon City | 136498 | San Francisco ES | Quezon City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 305330 | Batasan Hills National HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00032 | 15OF0122 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | RCDG CONSTRUCTION CORPORATION
NC 2015 | SHS (2015) | NCR | Quezon City | 305345 | Balara HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00031 | 15OG0099 | 2015-08-20 | 2015-09-04 | 2015-09-07 | 2015-09-22 | 2015-09-30 | MPJR BUILDERS COMPANY
NC 2015 | SHS (2015) | NCR | Quezon City | 305346 | Camp Gen. E. Aguinaldo HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00030 | 15OG0090 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | NCR | Quezon City | 136558 | Eulogio Rodriguez, Sr. ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00044 | 15OG0103 | 2015-10-02 | 2015-10-18 | 2015-10-20 | 2015-11-04 | 2015-11-05 | R.E. ORLINA CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | NCR | Quezon City | 136559 | Quirino ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00045 | 15OG-0104 | 2015-10-01 | 2015-10-15 | 2015-10-20 | 2015-11-04 | 2015-11-05 | METRICS CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 |  | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 16 | additional 2 units 4STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 29795037.68 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00026 | 15OG0089 | 2015-08-11 | 2015-08-22 | 2015-08-24 | 2015-08-28 | 2015-09-01 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS
NC 2015 | K10 (2015) | NCR | Quezon City | 136576 | Pedro Tuason ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00046 | 15OG-0111 | 2015-10-16 | 2015-10-27 | 2015-11-04 | 2015-11-20 | 2015-11-23 | MRB11 CONSTRUCTION CORPORATION (FORMERLY:MRB CONS
NC 2015 | SHS (2015) | NCR | Quezon City | 136580 | Proposed Stand Alone SHS10 (Kamuning A&D ES; for Media Arts students from all over QC) | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Quezon City | 136581 | Proposed Stand AloneSHS 9 (MH del Pilar; from R Magsaysay) | QUEZON CITY | 4 | 1 | 16 | 4STY8CL | 2015 SHS BATCH 5 | 29795038 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Quezon City | 136533 | Kaligayahan ES | Quezon City | 5 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | COMPLETED | 1 |  |  | NC0315S00035 | 15OF0130 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-23 | LMG CONSTRUCTION
NC 2015 | SHS (2015) | NCR | Quezon City | 305336 | Lagro HS | QUEZON CITY | 5 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Quezon City | 305338 | Maligaya HS | Quezon City | 5 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 3780074.83 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | NC0315S00047 | 15OF0132 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-23 | PRISMODIAL CONSTRUCTION CORPORATION (FOR. PRISMODI
NC 2015 | SHS (2015) | NCR | Quezon City | 305333 | Culiat HS | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0315S00034 | 15OF0133 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | NEWBIG FOUR J CONSTRUCTION INC., (FORMERLY FOUR J
NC 2015 | K10 (2015) | NCR | Quezon City | 136519 | Lucas R. Pascual ES | Quezon City | 6 | 1 | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1 |  |  | NC0315S00036 | 15OF0134 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-28 | 2015-09-14 | MPJR BUILDERS COMPANY
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136894 | Capt. H. Francisco ES Annex | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136893 | Capt. Hipolito Francisco Elementary School - Main | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136883 | Cipriano P. Sta. Teresa Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 5222963.07 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136871 | Ciriaco P. Tiñga Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY16CL | 2015 COMPLETION BATCH 4 | 6383621.53 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136874 | Napindan Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY24CL | 2015 COMPLETION BATCH 4 | 9285267.68 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Taguig City | 1 | 1 |  | Completion of 4STY8CL | 2015 COMPLETION BATCH 4 | 3481975.38 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 2 (Taguig ES) | TAGUIG CITY | 1 | 1 | 24 | 4STY12CL | 2015 SHS BATCH 5 | 44304687 |  |  | COMPLETED | 1 | [10 empty] | CONTRACT TO BE TERMINATED
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 3 (DANES) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros |  | Proposed Stand Alone SHS 4 (Brgy. Fort Bonifacio SHS) | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136876 | Taguig Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | NC0215S00147 | 0150B0352 | 2015-11-19 | 2015-11-23 | 2015-12-03 | 2015-12-23 |  | VERZONTAL BUILDERS, INC. (FORMERLY VERZONTAL BUILD
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  | NC0215S00107
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros |  | DepED Property | Taguig City | 2 | 1 |  | Completion of 2 units 4STY12CL(elevated @ 1.5m) | 2015 COMPLETION BATCH 4 | 602647.6184 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros | 320606 | Pres. Diosdado Macapagal HS - Signal VNHS Annex | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | Reverted | 0 |  |  | NC0215S00081
NC 2015 | K10 (2015) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | Taguig City | 2 | 1 |  | Completion of 4STY12CL | 2015 COMPLETION BATCH 4 | 1990560.0263 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NCR | Taguig City & Pateros | 305463 | Signal Village NHS | TAGUIG CITY | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Valenzuela City | 136800 | A. Deato ES | Valenzuela City | 1 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 3 | 14897518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00090
NC 2015 | K10 (2015) | NCR | Valenzuela City | 136802 | Coloong ES | CITY OF VALENZUELA | 1 | 1 |  | Completion 4STY8CL | 2015 COMPLETION BATCH 4 | 3043971.8762 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY9CL | 2015 COMPLETION BATCH 4 | 776209.5191 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 |  | Completion of 3STY6CL | 2015 COMPLETION BATCH 4 | 2932013.3353 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NCR | Valenzuela City | 305445 | Caruhatan NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22152344 |  |  | COMPLETED | 1 |  |  | NC0215S00151
NC 2015 | K10 (2015) | NCR | Valenzuela City | 320408 | DALANDANAN NHS- Bagbaguin Annex | Valenzuela City | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 3 | 26702469.42 |  |  | COMPLETED | 1 |  |  | NC0215S00091 | 15OD0104 | 2015-10-07 | 2015-10-16 | 2015-10-19 | 2015-10-22 | 2015-11-17 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00148 | 15OD0099 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-15 | 2015-11-05 | C.B. TAMPENGCO CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15082518.84 |  |  | COMPLETED | 1 |  |  | NC0215S00071 | 15OD0103 | 2015-10-07 | 2015-10-19 | 2015-10-20 | 2015-10-26 | 2015-11-17 | JAGONBUILD CONSTRUCTION CORP. (FOR. JAGON BUILDERS
NC 2016 | K10 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22153000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 305376 | Amparo High School | Caloocan City | 1 |  | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Reverted | 0
NC 2016 | K10 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10567131.51 |  |  | Completed | 1 |  |  | P00074635LZ | 16OD0069 |  |  | 2016-09-06 |  |  | J. Simeon Construction
NC 2016 | K10 | NCR | Caloocan City | 136639 | Bagong Silang Es | Caloocan City | 1 | 1 | 2 | Completion of 4STY8CL | BATCH 11 CL | 2000000 |  |  | Completed | 1 |  |  | P00074644LZ P00171687LZ | 17OD0121 |  |  | 2017-07-20 |  |  | Aylan Const. & Trading
NC 2016 | SHS | NCR | Caloocan City | 319707 | Caloocan City Business High School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074645LZ | 16OD0072 |  |  | 2016-09-13 |  |  | Prismodial Const. Corp.
NC 2016 | K10 | NCR | Caloocan City | 340539 | Caloocan North Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074639LZ P00181048LZ | 16OD0117 |  |  | 2017-09-04 |  |  | C.B. Tampengco Const. and Supply
NC 2016 | K10 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074642LZ | 16OD0073 |  |  | 2016-09-15 |  |  | Victoria Dev't. & Const. Supply Corp.
NC 2016 | K10 | NCR | Caloocan City | 305374 | Camarin Hs | Caloocan City | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 |  |  | P00074643LZ | 16OD0074 |  |  | 2016-09-15 |  |  | Aylan Const. & Trading
NC 2016 | K10 | NCR | Caloocan City |  | Camarin Shs (Brixton) | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 136652 | Caybiga Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 319701 | Cielito Zamora High School (Bonifacio Campus) | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 136636 | Congress Es | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14898000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 305387 | Llano Hs | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074647LZ | 16OD0078 |  |  | 2016-09-27 |  |  | Prismodial Const. Corp.
NC 2016 | K10 | NCR | Caloocan City |  | Samalla Tala Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074650LZ | 16OD0076 |  |  | 2016-09-22 |  |  | St. Gerrard Construction
NC 2016 | K10 | NCR | Caloocan City |  | Sampaguita Shs | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074649LZ | 16OD0075 |  |  | 2016-09-22 |  |  | Prismodial Const. Corp. | TO VERIFY APPROPRIATION FROM DPWH REPORT: 14,897,518.84
NC 2016 | K10 | NCR | Caloocan City | 305380 | Tala Hs | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074648LZ | 16OD0083 |  |  | 2016-10-25 |  |  | Aylan Const. & Trading
NC 2016 | K10 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31103000 |  |  | Completed | 1 |  |  | P00072840LZ | 16OD0059 |  |  | 2016-08-02 |  |  | St. Gerrard Construction
NC 2016 | K10 | NCR | Caloocan City | 136615 | Andres Bonifacio Es | Caloocan City | 2 |  | 16 | 4STY16CL | BATCH 9 CL | 26703000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 136606 | Grace Park Es (Main) | Caloocan City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Caloocan City | 319706 | Kasarinlan Hs | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1 |  |  | P00074638LZ | 17OD0119 |  |  | 2017-07-20 |  |  | St. Timothy Const. Corp.
NC 2016 | K10 | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs (Main) | Caloocan City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074636LZ P00171689LZ | 17OD0120 |  |  | 2017-07-20 |  |  | Omicron Const.
NC 2016 | SHS | NCR | Caloocan City | 305391 | M. B. Asistio Sr. Hs Unit 1 To M. B. Asistio, Sr. Hs | Caloocan City | 2 |  | 32 | 4STY32CL | BATCH 13 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | K10 | NCR | Las Piñas City | 136773 | Caa Elementary School Main | City Of Las Piñas | 0 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62205780.54 |  |  | Completed | 1 |  |  | P00075393LZ | 17OI0077 | 2017-06-13 | 2017-06-21 | 2017-07-04 | 2017-07-19 | 2017-10-16 | REDCAR TRADING AND CONSTRUCTION
NC 2016 | K10 | NCR | Las Piñas City | 136790 | Daniel Fajardo Es To Talon Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 17OI0123 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | DAVHEZ CONSTRUCTION
NC 2016 | K10 | NCR | Las Piñas City | 136784 | Dona Manuela Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075394LZ | 17OI0051 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-04-24 | 2017-10-16 | DAVHEZ CONSTRUCTION
NC 2016 | K10 | NCR | Las Piñas City | 136775 | Gatchalian Es | City Of Las Piñas | 0 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 |  |  | P0007031LZ | 16OI0027 | 2017-02-23 | 2017-03-02 | 2017-03-14 | 2017-03-21 | 2017-06-06 | MRRM Trading and Construction
NC 2016 | K10 | NCR | Las Piñas City |  | Moonwalk Es To Realign To Repsci Las Pinas | City Of Las Piñas | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070312LZ | 16OI0095 | 2017-09-29 | 2017-10-06 | 2017-10-13 | 2017-10-28 | 2017-11-22 | DAVHEZ CONSTRUCTION
NC 2016 | K10 | NCR | Las Piñas City |  | Shs In Martinville, Las Piñas City/ Realign To Golden Acres Las Pinas | Las Piñas City | 0 | 1 | 32 | 4STY32CL | BATCH 3 CL | 44532220.04 |  |  | Completed | 1 |  |  | P00070310LZ | 17OI0098 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-10-06 | 2017-12-15 | DAVHEZ CONSTRUCTION
NC 2016 | K10 | NCR | Las Piñas City | 136791 | Zapote Es | City Of Las Piñas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00075395LZ | 17OI0052 | 2017-03-17 | 2017-03-24 | 2017-04-05 | 2017-12-24 | 2017-12-15 | LMG CONSTRUCTION
NC 2016 | K10 | NCR | Malabon City | 136834 | Imelda Es | City Of Malabon | 0 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 | [8 empty] | 2016-10-27 | edison devt & const
NC 2016 | K10 | NCR | Malabon City |  | Ninoy Aquino Es | City Of Malabon | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 | [8 empty] | 2017-08-08 | hexamindz corp
NC 2016 | K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 2016-05-12 | LTM builders
NC 2016 | K10 | NCR | Malabon City | 136838 | Tañong Es I | City Of Malabon | 0 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1 | [8 empty] | 2016-11-15 | victoria devt
NC 2016 | K10 | NCR | Malabon City | 136850 | Tinajeros Es | City Of Malabon | 0 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1 | [8 empty] | 2017-10-16 | alpha & omega general contractor
NC 2016 | K10 | NCR | Malabon City | 320504 | Tinajeros Nhs - Acacia Annex | City Of Malabon | 0 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 | [8 empty] | 2016-10-12 | framecon builders
NC 2016 | K10 | NCR | Mandaluyong City | 500051 | Andres Bonifacio Is | Mandaluyong City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 33300000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Mandaluyong City | 136657 | Filemon Javier Es | Mandaluyong City | 0 | 1 | 12 | 4STY12CL (INCL. SITE DEV & DEMOLITION) WITH COVERED HIGH COLUMN SUPPORT FOR MULTI-PURPOSE HALL/ROOF DECK | BATCH 11 CL | 35300000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Mandaluyong City | 136831 | Hulo Integrated School | Mandaluyong City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 52300000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Mandaluyong City | 500335 | Ilaya Barangka Is | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 35450000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Mandaluyong City | 319804 | Jose Fabella Memorial School | City Of Mandaluyong | 0 | 1 | 16 | 4STY16CL | BATCH 3 CL | 32150000 |  |  | Completed | 1
NC 2016 | SHS | NCR | Mandaluyong City | 305394 | Mataas Na Paaralang Neptali A. Gonzales | City Of Mandaluyong | 0 | 1 | 48 | 4STY48CL | BATCH 13 CL | 100950000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Manila | 136488 | Gen. Emilio Aguinaldo Is | Manila | 6 | 1 | 12 | 4STY12CL | BATCH 11 CL | 24352577.982 |  |  | Completed | 1
NC 2016 | K10 | NCR | Marikina City | 136681 | Fortune Es | Marikina City | 2 | 1 | 4 | Completion of 3STY9CL | BATCH 11 CL | 5959577.43 |  |  | Completed | 1
NC 2016 | K10 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Marikina City | 136685 | Sss Village Es | City Of Marikina | 2 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 | 1 | 32 | 4STY16CL | BATCH 7 CL | 53404938.84 |  |  | Completed | 1 |  |  |  | 16OI0049 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136908 | Alabang Es (Main) | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0043 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | RV Rieta Trading & Gen Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136910 | Bayanan Elementary School Unit I | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0050 | 2016-03-02 | 2016-03-09 | 2016-03-21 |  |  | R. V. Rieta Trading & Gen. Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136912 | Cupang Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0042 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Redcar Trading & Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136900 | F. De Mesa Es | City Of Muntinlupa | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 29795837.68 |  |  | Completed | 1 |  |  |  | 16OI0053 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0054 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | MRRM Trading & Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16OI0051 | 2016-03-02 | 2016-03-09 | 2016-03-21
NC 2016 | K10 | NCR | Muntinlupa City | 136903 | Muntinlupa Es | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0057 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Orani Builders Supply
NC 2016 | K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897918.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | NCR | Muntinlupa City | 305468 | Muntinlupa Nhs | City Of Muntinlupa | 0 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16OI0055 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Orani Builders Supply
NC 2016 | K10 | NCR | Muntinlupa City | 305470 | Pedro E. Diaz High School | City Of Muntinlupa | 0 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0052 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-13 | Precious Const.
NC 2016 | K10 | NCR | Muntinlupa City | 136905 | Soldiers' Hills Es | City Of Muntinlupa | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16OI0056 | 2016-03-02 | 2016-03-09 | 2016-03-21 | 2016-03-31 | 2016-06-07 | E. M. Paule Const. & Trading
NC 2016 | K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | City Of Muntinlupa | 0 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16OI0068 | 2016-04-22 | 2016-03-09 | 2016-05-11 | 2016-05-19 | 2016-07-03 | Orani Builders Supply
NC 2016 | K10 | NCR | Navotas City | 136858 | Dagat-Dagatan Elementary School | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | NCR | Navotas City | 305454 | San Rafael Technological High School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Navotas City | 136867 | Tangos Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | NCR | Navotas City | 305457 | Tangos National High School | City Of Navotas | 0 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Navotas City | 305453 | Navotas National High School | Navotas City | 0 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26852469.42 |  |  | Completed | 1
NC 2016 | K10 | NCR | Navotas City |  | Navotas Science High School | Navotas City | 0 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Navotas City | 136863 | North Bay Boulevard North Elementary School | City Of Navotas | 0 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | NCR | Navotas City | 340628 | Shs In Lisan, Navotas City | City Of Navotas | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 0 |  | 56 | 4STY28CL | BATCH 11 CL | 80135892.28 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading
NC 2016 | K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Triple 8 Construction & Supply Inc.
NC 2016 | K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Reverted | 0 | [9 empty] | Flordes Construction & Trading | Mutual termination; cancelled effective December 23, 2021
NC 2016 | K10 | NCR | Paranaque City | 136757 | Paranaque Elementary School Unit Ii | City Of Parañaque | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [9 empty] | Flordes Construction & Trading
NC 2016 | K10 | NCR | Paranaque City | 136756 | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 13 CL | 29795037.68 |  |  | Completed | 1
NC 2016 | K10 | NCR | Paranaque City |  | Paranaque Es Central | City Of Parañaque | 1 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 | [9 empty] | Redcar Trading and Construction
NC 2016 | SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 | 1 | 28 | 4STY28CL | BATCH 3 CL | 40067946.14 |  |  | Completed | 1 | [9 empty] | MRRM Trading and Construction
NC 2016 | SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp
NC 2016 | SHS | NCR | Paranaque City | 305426 | Paranaque National High School - Baclaran | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp
NC 2016 | SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | City Of Parañaque | 1 | 1 | 24 | 4STY12CL | BATCH 11 CL | 44304687.24 |  |  | Completed | 1 | [9 empty] | Hexamindz Corporation
NC 2016 | K10 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | Omicron Construction
NC 2016 | K10 | NCR | Paranaque City | 305427 | Paranaque Nhs - Don Galo Annex | City Of Parañaque | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | Henscha Philippines Inc.
NC 2016 | K10 | NCR | Paranaque City |  | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [9 empty] | R.E. Orlina Construction Corp
NC 2016 | K10 | NCR | Paranaque City | 136765 | Sto. Nino Es | City Of Parañaque | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Paranaque City | 136766 | Tambo Es | City Of Parañaque | 1 | 1 | 32 | 4STY32CL | BATCH 7 CL | 44532220.04 |  |  | Completed | 1 | [9 empty] | Precious Construction
NC 2016 | K10 | NCR | Pasay City | 136593 | Kalayaan Es | Pasay City | 0 | 1 | 9 | 4STY 9CL | BATCH 9 CL | 21170000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Pasay City | 136599 | Marcela Marcelo Es | Pasay City | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | NCR | Pasay City | 319602 | Philippine National School For The Blind | Pasay City | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.051 |  |  | Completed | 1
NC 2016 | K10 | NCR | Pasay City | 136601 | Timoteo Paez Es | Pasay City | 0 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot Sci (Respsci) | City Of Pasig | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31602890.27 |  |  | Completed | 1 |  |  | P00171699 LZ_CW1 | 0170B0120 | 2016-12-29 | 2017-01-06 | 2017-01-19 |  | 2017-10-24 | LPO Enterprises & R'CEL Gen. Con & Gen. Merchendise (J.V.)
NC 2016 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136501 | Esteban Abada Es | Quezon City | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City |  | Shs In Kaligayahan | Quezon City | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 27709000 |  |  | Terminated | 1 | [10 empty] | DPWH REPORT: For Termination The contractor failed to resume to work; for mutual termination as per DPWH
NC 2016 | K10 | NCR | Quezon City |  | Shs In Pasong Tamo | Quezon City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City |  | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136506 | Toro Hills Es | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | NCR | Quezon City | 305331 | Commonwealth Hs | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136542 | Dona Juana Es | Quezon City | 2 | 1 | 3 | Completion of 4STY14CL | BATCH 9 CL | 4754642.66 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 319501 | Shs In Batasan Hills (Ext. Of Batasan Hills Nhs) To Holy Spirit Nhs | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City |  | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890.27 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs
NC 2016 | K10 | NCR | Quezon City |  | Shs In Harmony Hills (Accibal Property) | Quezon City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23018000 |  |  | Terminated | 0 | [10 empty] | DPWH REPORT: FOR TERMINATION / WITH ISFs
NC 2016 | K10 | NCR | Quezon City | 136564 | Pura V. Kalaw Es | Quezon City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.02 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136534 | Lagro Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136536 | Nagkaisang Nayon Es | Quezon City | 5 | 1 | 16 | 4STY16CL (L-Shape) | BATCH 11 CL | 26852469.42 |  |  | Terminated | 1 | [10 empty] | For Termination;The contractor failed to resume to work; No movement at all
NC 2016 | K10 | NCR | Quezon City | 136538 | San Agustin Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22177343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26739923.9661 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136529 | San Gabriel Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | San Juan City |  | San Juan Es To San Juan City Tech-Voc And Livelihood Shs | San Juan City | 0 | 1 | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Reverted | 0
NC 2016 | K10 | NCR | Taguig | 136892 | Aguho Es | Taguig | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Taguig | 136874 | Napindan Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Terminated | 0 | [10 empty] | The project was terminated due to long period of suspension of the project due to pending demolition of the remaining existing structure by Dep-ed affecting the two grid line. - With request for funding which was received by Dep-Ed Central Office dated March 15, 2023 for the construction and completion of the building amounting Php62,500,00.00.
NC 2016 | K10 | NCR | Taguig | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | SHS | NCR | Taguig | 305466 | Pateros National High School | Pateros | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Taguig | 320611 | Taguig Integrated School | Taguig City | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22302343.52 |  |  | Completed | 1
NC 2016 | SHS | NCR | Taguig | 305460 | Taguig National High School | Taguig City | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | SHS | NCR | Taguig | 305464 | Tipas National High School | Taguig City | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Taguig | 136890 | Maharlika Elementary School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22302343.52 |  |  | Completed | 1
NC 2016 | SHS | NCR | Taguig | 305463 | Signal Village National High School | Taguig City | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Taguig | 136887 | Upper Bicutan Es | Taguig City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 136801 | A. Fernando Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 305438 | Malinta National High School | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.8364 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City |  | Shs In Arkong Bato, Valenzuela | City Of Valenzuela | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City |  | Shs In Paso De Blas, Valenzuela | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.8364 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City |  | Shs In Punturin, Valenzuela | City Of Valenzuela | 1 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 136810 | Tugatog Es | City Of Valenzuela | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.8364 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City |  | Shs In Ugong | Valenzuela City | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. Nhs | City Of Valenzuela | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | NCR | Valenzuela City | 305441 | Valenzuela Nhs | Valenzuela City | 2 | 1 | 8 | Completion of 4STY32CL | BATCH 11 CL | 14747518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136492 | Ramon Magsaysay Es | Quezon City | 1 | 1 | 20 | 4STY20CL | BATCH 14 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 305322 | Eulogio Rodriguez, Jr. Hs | Quezon City | 1 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136525 | San Bartolome Es | Quezon City | 5 | 1 | 8 | 4STY8CL | BATCH 14 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City | 136533 | Kaligayahan Es | Quezon City | 5 | 1 | 12 | 4STY12CL | BATCH 14 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | NCR | Quezon City |  | Atty. Alfredo D. Vargas, Sr. Memorial High School | Quezon City | 5 | 1 | 20 | 4STY20CL L- Type Building (included elevation of 0.80 -1.20m high) | BATCH 14 CL | 42150000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Marikina City | 136680 | Concepcion ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P00172458LZ-CW1 | 0170B0387 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 | 2017-11-14 | GR FEVEDAL CONSTRUCTION DEVELOPERS CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 4 | 37165805.23 |  |  | Completed | 1 |  |  | P00172459LZ-CW1 | 0170B0385 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-14 | BELL CONSTRUCTION
NC 2017 | K10 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 37767415.24 |  |  | Completed | 1 |  |  | P00172460LZ-CW1 | 0170B0383 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-14 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136687 | Sto. Nino ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 4 | 35423184.21 |  |  | Completed | 1 |  |  | P00172457LZ-CW1 | 0170B0386 | 2017-09-26 | 2017-10-06 | 2017-10-10 | 2017-11-02 |  | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION
NC 2017 | K10 | NCR | Pasig City | 136729 | Bagong Ilog ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | BATCH 4 | 42574742.6 |  |  | Completed | 1 |  |  | P0072462 LZ_CW1 | 0170B0384 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | Henscita Phils., Inc.
NC 2017 | K10 | NCR | Pasig City | 136725 | Buting ES | CITY OF PASIG | 0 | 1 | 9 | 4STY9CL | BATCH 4 | 32371949.57 |  |  | Completed | 1 |  |  | P0072461 LZ_CW1 | 0170B0388 | 2017-09-26 | 2017-10-06 | 2017-10-17 | 2017-11-02 | 2017-11-20 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION
NC 2017 | TVL | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 16 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 72278943.25 |  |  | Completed | 1 |  |  | P0072463 LZ_CW1 | 0170B0421 | 2017-10-30 | 2017-11-10 | 2017-11-21 | 2017-12-01 | 2017-12-19 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION
NC 2017 | SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 28 | 4STY28CL | BATCH 4 | 62945715.06 |  |  | Completed | 1 |  |  | P0072464 LZ_CW1 | 0170B0422 | 2017-10-30 | 2017-11-10 | 2017-12-12 | 2017-12-14 | 2017-12-28 | ALPHA & OMEGA CONTRACTOR & DEVELOPMENT CORPORATION
NC 2017 | K10 | NCR | Malabon City | 136835 | Longos ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 20705296.99 |  | 19961055.45 | Completed | 1 | [8 empty] | 2017-12-13 | ISH Const. Inc
NC 2017 | K10 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 23053022.14 |  | 22249624.04 | Completed | 1 | [8 empty] | 2017-12-13 | T.M. Abad Const.
NC 2017 | K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 20 | 4STY20CL | BATCH 7 | 60000000 |  | 57848516.92 | Completed | 1 | [8 empty] | 2018-01-10 | St. Timothy Const. Corp.
NC 2017 | SHS | NCR | Malabon City | 305452 | Tinajeros NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 19744516.77 |  | 19032845.4 | Completed | 1 | [8 empty] | 2017-12-13 | JTC Cruz Const. co. inc.
NC 2017 | K10 | NCR | Malabon City | 136839 | Tonsuya Elementary School | CITY OF MALABON | 0 | 1 | 15 | 3STY15CL | BATCH 7 | 46106889.97 |  | 45478773.82 | Completed | 1 | [8 empty] | 2017-12-13 | Edison Devt. Const.
NC 2017 | K10 | NCR | Marikina City |  | Industrial Valley NHS | CITY OF MARIKINA | 1 | 1 | 36 | 4STY36CL | BATCH 7 | 109453944.7 |  |  | Completed | 1 |  |  | P00174788LZ-CW1 | 0170B0459 | 2017-12-06 | 2017-12-13 | 2017-10-22 | 2018-01-03 | 2018-01-04 | EDISON DEVELOPMENT CORPORATION
NC 2017 | TVL | NCR | Navotas | 136856 | Bagumbayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 3 | 3STY3CL | BATCH 7 | 10417126.08 |  |  | Completed | 1
NC 2017 | K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Navotas | 136861 | Navotas I Elementary School | CITY OF NAVOTAS | 0 | 1 | 15 | 4STY16CL | BATCH 7 | 55558005.76 |  |  | Completed | 1 | [10 empty] | - Termination of Original Contract (17OA0097) - New Contract for Project Completion (17OA0106) - New Contract for Project Completion (17OA0106)
NC 2017 | SHS | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1
NC 2017 | K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL | BATCH 7 | 27636000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Navotas | 305455 | Tanza National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 7 | 42036997.81 |  |  | Completed | 1
NC 2017 | SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | BATCH 7 | 68651344.94 |  |  | Terminated | 0 |  |  |  | 17OC0088 |  |  |  |  | 2017-12-27 | SPRING STAR Const. & Supply | Terminated; Suspended as of December 27, 2017 due to pending demolition of existing building since it is still being utilized by the students. The newly built 2 Units 12 CL is not sufficient to cater the number of students using the old building; Awaiting for the completion of the ongoing construction of 2 Units 28CL. (For Termination)
NC 2017 | K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 18812000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136512 | GSIS VILLAGE ELEMENTARY | QUEZON CITY | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 34234000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 7 | 34175000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 39783000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 45561000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City |  | Sta. Lucia ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 7 | 18921000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Caloocan City | 305389 | Caloocan City City Science HS | Caloocan City | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1 |  |  | P00178672LZ | 17OD0170 |  |  | 2017-12-19 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178650LZ | 17OD0146 |  |  | 2017-11-28 |  |  | Aylan Construction and Trading
NC 2017 | K10 | NCR | Caloocan City | 136632 | Amparo ES | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178651LZ | 17OD0130 |  |  | 2017-11-23 |  |  | Aylan Construction and Trading
NC 2017 | K10 | NCR | Caloocan City | 136625 | Baesa ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178649LZ | 17OD0131 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136650 | Bagbaguin ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178656LZ | 17OD0159 |  |  | 2017-12-19 |  |  | C.B. Tampengco Const. & Supply
NC 2017 | SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178669LZ | 17OD0179 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading
NC 2017 | SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178670LZ | 17OD0180 |  |  | 2017-12-12 |  |  | C.T. Leoncio Const. & Trading
NC 2017 | K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178653LZ | 17OD0147 |  |  | 2017-11-28 |  |  | E.A. Ramirez Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp.
NC 2017 | K10 | NCR | Caloocan City | 305381 | Bagong Silang HS | Caloocan City | 1 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1 |  |  | P00178667LZ | 17OD0157 |  |  | 2017-11-29 |  |  | Alpha & Omega Gen. Contractor & Dev't. Corp.
NC 2017 | K10 | NCR | Caloocan City | 136651 | Bagumbong ES | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178657LZ | 17OD0132 |  |  | 2017-11-23 |  |  | T.M. Abad Construction
NC 2017 | K10 | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | Caloocan City | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178675LZ | 17OD0148 |  |  | 2017-11-28 |  |  | C.B. Tampengco Const. & Supply
NC 2017 | K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178652LZ | 17OD0181 |  |  | 2017-12-12 |  |  | Aylan Construction and Trading
NC 2017 | K10 | NCR | Caloocan City | 305374 | Camarin High School | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178663LZ | 17OD0133 |  |  | 2017-11-23 |  |  | T.M. Abad Construction
NC 2017 | K10 | NCR | Caloocan City | 136652 | Caybiga ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178658LZ | 17OD0160 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp.
NC 2017 | K10 | NCR | Caloocan City | 305385 | Caybiga HS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178671LZ | 17OD0134 |  |  | 2017-11-23 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136620 | Cecilio Apostol ES | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178648LZ | 17OD0135 |  |  | 2017-11-23 |  |  | Larsen-Dutcher Constractor
NC 2017 | SHS | NCR | Caloocan City | 305375 | Ceilito Zamora SHS | Caloocan City | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178664LZ | 17OD0136 |  |  | 2017-11-23 |  |  | Jagonbuild Construction Corp.
NC 2017 | K10 | NCR | Caloocan City | 136653 | Deparo ES | Caloocan City | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178659LZ | 17OD0161 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp.
NC 2017 | K10 | NCR | Caloocan City | 136641 | Kalayaan ES | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00178654LZ | 17OD0162 |  |  | 2017-12-01 |  |  | Steven Construction and Supply
NC 2017 | K10 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178660LZ | 17OD0151 |  |  | 2017-11-29 |  |  | C.B. Tampengco Const. & Supply
NC 2017 | K10 | NCR | Caloocan City | 305379 | Manuel L. Quezon HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1 |  |  | P00178665LZ | 17OD0137 |  |  | 2017-11-23 |  |  | RCDG Construction Corporation
NC 2017 | K10 | NCR | Caloocan City | 136655 | Sampaguita Elem. School | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178661LZ | 17OD0156 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178655LZ | 17OD0152 |  |  | 2017-12-13 |  |  | Aylan Construction and Trading
NC 2017 | K10 | NCR | Caloocan City | 305380 | Tala High School | CALOOCAN CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1 |  |  | P00171688LZ | 17OD0126 |  |  | 2017-10-24 |  |  | Aylan Construction and Trading
NC 2017 | K10 | NCR | Caloocan City | 305371 | Talipapa HS | Caloocan City | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178662LZ | 17OD0153 |  |  | 2017-12-19 |  |  | First R + J Builders Phils. Corp.
NC 2017 | K10 | NCR | Caloocan City | 136622 | Eulogio Rodriguez Elementary School | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1 |  |  | P00178676LZ | 17OD0149 |  |  | 2017-11-29 |  |  | Alcel Construction
NC 2017 | K10 | NCR | Caloocan City | 136608 | Kasarinlan ES | KALOOKAN CITY | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Caloocan City | 136609 | Kaunlaran ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1 |  |  | P00178674LZ | 17OD0177 |  |  | 2017-12-07 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Malabon City | 136840 | Amang Rodriguez ES | CITY OF MALABON | 0 | 1 | 6 | 3STY6CL | BATCH 10 | 20834252.16 |  | 20730027.02 | Completed | 1 | [8 empty] | 2018-01-10 | Square Meter Trading & Const. Corp.
NC 2017 | K10 | NCR | Malabon City | 136853 | Catmon IS | CITY OF MALABON | 0 | 1 | 9 | 3STY9CL | BATCH 10 | 27000000 |  | 25520958.51 | Completed | 1 | [8 empty] | 2018-01-10 | ISH Const. Inc
NC 2017 | K10 | NCR | Malabon City | 136849 | Potrero ES I | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 31649789.72 |  | 31455124.21 | Completed | 1 | [8 empty] | 2017-12-21 | Square Meter Trading & Const. Corp.
NC 2017 | K10 | NCR | Malabon City | 136846 | Santiago Syjuco Memorial School | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 36000000 |  | 35469792.21 | Completed | 1 | [8 empty] | 2017-12-21 | Steven Const. & Supply
NC 2017 | K10 | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 64141000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136471 | Bacood Elementary School | SAMPALOC | 6 | 1 | 16 | 4STY16CL | BATCH 10 | 45350000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136482 | Bagong Diwa Elementary School | PANDACAN | 6 | 1 | 24 | 4STY24CL | BATCH 13 | 59785600 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305299 | Dona Teodora Alonzo HS | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 47600000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 305317 | Elpidio Quirino High School | SANTA ANA | 6 | 1 | 12 | 4STY12CL | BATCH 10 | 53105000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 25185000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1 |  | 6 | 2STY6CL | BATCH 10 | 17127000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305302 | Jose Abad Santos High School | SANTA CRUZ | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 78400000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 24 | 4STY24CL | BATCH 10 | 84650000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136461 | Legarda Elementary School | SAMPALOC | 4 | 1 | 16 | 4STY16CL | BATCH 10 | 46570000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98747000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305312 | Manila Science High School | ERMITA | 5 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305318 | Manuel A. Roxas High School | PACO | 5 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 19025000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Manila | 305316 | Mariano Marcos Memorial High School | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40760000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136467 | P. Burgos ES | TONDO | 4 | 1 | 24 | 4STY24CL | BATCH 10 | 60956000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Marikina City | 136679 | Concepcion Integrated School | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33137151.39 |  |  | Completed | 1 |  |  | P00178703LZ-CW1 | 0170B0432 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNELL_BELVOIR CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136673 | Kalumpang ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63685374.28 |  |  | Completed | 1 |  |  | P00178698LZ-CW1 | 0170B0454 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136674 | L. Victorino ES | CITY OF MARIKINA | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57582992.4 |  |  | Completed | 1 |  |  | P00178699LZ-CW1 | 0170B0462 | 2017-12-06 | 2017-12-13 | 2017-12-26 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136675 | Malanday ES | CITY OF MARIKINA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1 |  |  | P00178700LZ-CW1 | 0170B0433 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-28 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136677 | Nangka ES | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 44030854.92 |  |  | Completed | 1 |  |  | P00178702LZ-CW1 | 0170B0428 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION
NC 2017 | SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 37845984.62 |  |  | Completed | 1 |  |  | P00178704LZ-CW1 | 0170B0431 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNEL-BELVOIR CORPORATION
NC 2017 | SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 |  | 8 | 4STY8CL | BATCH 10 | 18094817.33 |  |  | Completed | 1 |  |  | P00178705LZ-CW1 | 0170B0436 | 2017-11-21 | 2017-12-01 | 2017-12-12 | 2017-12-14 | 2017-12-22 | VINNELL_BELVOIR CORPORATION
NC 2017 | K10 | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA | 1 | 1 | 28 | 4STY28CL | BATCH 10 | 63865374.28 |  |  | Completed | 1 |  |  | P00178701LZ-CW1 | 0170B0455 | 2017-12-02 | 2017-12-08 | 2017-12-22 | 2018-01-03 | 2018-01-04 | GR FEVIDAL CONSTRUCTION DEVELOPERS CORPORATION
NC 2017 | K10 | NCR | Paranaque City | 136753 | Fourth Estate ES | CITY OF PARAÑAQUE | 2 | 1 | 48 | 4STY48CL | BATCH 10 | 117688019.9 |  |  | Completed | 1 |  |  | P00178706LZ | 17OC0121 | 2017-11-28 |  | 2017-11-28 | 2017-12-12 | 2017-12-27 | New Big Four J Construction, Inc.
NC 2017 | K10 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY | 0 |  | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 319601 | Kalayaan NHS | PASAY CITY | 0 | 1 | 9 | 4STY9CL | BATCH 10 | 21403800 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 305367 | Pasay City East HS | PASAY CITY | 0 | 1 | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 305370 | Pasay City South HIgh School | PASAY CITY | 0 |  | 12 | 4STY12CL | BATCH 10 | 34970000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 500328 | Philippine National School for the Blind | PASAY CITY | 0 | 1 | 6 | 2STY6CL | BATCH 10 | 9525000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Pasay City | 500329 | Philippine School for the Deaf | PASAY CITY | 0 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136567 | Aguinaldo ES | QUEZON CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 40139000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 46046000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa ES | QUEZON CITY | 1 |  | 12 | 4STY12CL | BATCH 10 | 35238000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136552 | Bagumbayan ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34586000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136553 | Balara ES | QUEZON CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 34600000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | COMpleted | 1 | [10 empty] | REDESIGNING OF THE PLAN & SPECS
NC 2017 | TVL | NCR | Quezon City | 305360 | Don Alejandro Roces, Sr. Sci. & Tech. HS | QUEZON CITY | 4 | 1 | 27 | 4STY TVL | BATCH 10 | 95436000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136542 | Dona Juana ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 35741000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 20495000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136563 | Project 3 ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17628000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 47045000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305329 | Quezon City Science HS | QUEZON CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 18980000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 45936000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305327 | San Francisco HS | QUEZON CITY | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 80870000 |  |  | COMpleted | 1
NC 2017 | K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 49052000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136510 | Sto. Cristo ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34144000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136506 | Toro Hills ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 19984000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 305467 | Maria Concepcion Cruz HS | PATEROS | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 20667628.92 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136896 | Pateros Elementary School | PATEROS | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49027051.57 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136895 | Paulina Manalo ES | PATEROS | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41546562.56 |  |  | Completed | 1
NC 2017 | SHS | NCR | Taguig | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 7 | 4STY7CL | BATCH 10 | 17159570.67 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136883 | Cipriano P. Sta. Teresa Elementary School | TAGUIG CITY | 1 | 1 | 24 | 4STY24CL | BATCH 10 | 57497969.97 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136871 | Ciriaco P. Tiñga Elementary School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32244946.68 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136886 | Kapitan Jose Cardones Memorial ES | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | BATCH 10 | 55961256.52 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 500342 | Napindan Integrated School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23410308.71 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 21279843.93 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136877 | Tipas Elementary School -Main | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34509193.16 |  |  | Completed | 1
NC 2017 | SHS | NCR | Taguig | 320605 | Upper Bicutan National High School | TAGUIG CITY | 2 | 1 | 6 | 4STY6CL | BATCH 10 | 10756889.78 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig | 136879 | Ususan Elementary School | TAGUIG CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55693407.06 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45550000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136820 | Bitik ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 40760000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Valenzuela City | 305437 | Dalandanan NHS | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 55760000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136815 | Lawang Bato Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 34820000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136797 | Malinta Elementary School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL | BATCH 10 | 33600000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45700000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136798 | Maysan ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL | BATCH 10 | 19025600 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 41930000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136806 | Pasolo ES | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL | BATCH 10 | 23670000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 49265000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136819 | Silvestre Lazaro Elementary School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 18875600 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23520000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181221LZ | 17OD0145 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp.
NC 2017 | K10 | NCR | Caloocan City | 136615 | Andres Bonifacio ES | CALOOCAN CITY | 2 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181222LZ | 17OD0142 |  |  | 2017-11-28 |  |  | St. Timothy Const. Corp.
NC 2017 | K10 | NCR | Caloocan City | 136637 | Horacio dela Costa ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181224LZ | 17OD0150 |  |  | 2017-11-29 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181225LZ | 17OD0154 |  |  | 2017-11-29 |  |  | Orani Builders Supply
NC 2017 | K10 | NCR | Caloocan City | 136646 | NHC ES | CALOOCAN CITY | 1 |  | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181226LZ | 17OD0143 |  |  | 2017-11-28 |  |  | Orani Builders Supply
NC 2017 | K10 | NCR | Caloocan City | 305373 | Sampaguita HS | CALOOCAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 12 | 19025600 |  |  | Completed | 1 |  |  | P00181227LZ | 17OD0144 |  |  | 2017-11-28 |  |  | Accelerated Metal Technology and Const. Inc.
NC 2017 | K10 | NCR | Caloocan City | 136623 | San Jose ES | CALOOCAN CITY | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 34970000 |  |  | Completed | 1 |  |  | P00181223LZ | 17OD0155 |  |  | 2017-11-29 |  |  | Alcel Construction
NC 2017 | K10 | NCR | Las Piñas City | 136775 | Gatchalian ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 16355000 |  |  | Completed | 1 |  |  | P00181228 | 17OI0099 | 2017-09-06 | 2017-09-14 | 2017-09-26 | 2017-11-09 | 2017-12-05 | GF ROVERO MERCHANDISING
NC 2017 | K10 | NCR | Las Piñas City | 305434 | Las Pinas East National High School | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 41780000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0126 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION
NC 2017 | K10 | NCR | Las Piñas City | 136777 | Las Pinas ES Central | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31800000 |  |  | Completed | 1 |  |  | P00181229 | 17OI0124 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | LMG CONSTRUCTION
NC 2017 | K10 | NCR | Las Piñas City | 136788 | Pamplona ES I | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17455000 |  |  | Completed | 1 |  |  | P00181230 | 17OI0116 | 2017-10-16 | 2017-10-26 | 2017-11-07 | 2017-04-24 | 2017-09-06 | FRAMECON BUILDERS
NC 2017 | K10 | NCR | Las Piñas City | 136789 | Pilar Village ES | CITY OF LAS PIÑAS | 0 | 1 | 16 | 4STY16CL | BATCH 12 | 37200000 |  |  | Completed | 1 |  |  | P00181232 | 17OI0125 | 2017-11-02 | 2017-11-10 | 2017-11-23 | 2017-11-29 | 2017-12-15 | DAVHEZ CONSTRUCTION
NC 2017 | SHS | NCR | Mandaluyong City | 500051 | Andres Bonifacio Integrated School | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG | 0 | 1 | 24 | 4STY24CL | BATCH 12 | 54000000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Mandaluyong City |  | Sen. Neptali Gonzales Integrated School | Mandaluyong City | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 32000000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 60895000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136452 | P. Gomez ES | SANTA CRUZ | 3 |  | 16 | 4STY16CL | BATCH 10 | 54256000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136472 | Pio del Pilar Elementary School | SAMPALOC | 6 | 1 | 20 | 4STY20CL | BATCH 10 | 58070000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136485 | Sta. Ana ES | SANTA ANA | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | BATCH 12 | 47990000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 |  | 20 | 4STY20CL | BATCH 12 | 43840000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Muntinlupa City | 320704 | Muntinlupa NHS -Tunasan Annex | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10120 | 17O10120 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Redcar Trading & Const
NC 2017 | SHS | NCR | Muntinlupa City | 305469 | Muntinlupa Science High School | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | BATCH 12 | 31904360.14 |  |  | Completed | 1 |  |  | 17O10121 | 17O10121 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Redcar Trading & Const/RDGD Const. (JV)
NC 2017 | K10 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10117 | 17O10117 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Framecon Builders
NC 2017 | K10 | NCR | Muntinlupa City | 136914 | Sucat Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10119 | 17O10119 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | Vicvera Bldrs Inc
NC 2017 | K10 | NCR | Muntinlupa City | 136907 | Victoria Homes ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL | BATCH 12 | 17429616.04 |  |  | Completed | 1 |  |  | 17O10118 | 17O10118 |  | 2017-10-26 | 2017-11-07 | 2017-11-21 | 2017-12-05 | RV Rieta Trading & Gen. Const.
NC 2017 | K10 | NCR | Quezon City |  | Harmony Hills NHS | QUEZON CITY | 2 | 1 | 32 | 4STY32CL | BATCH 12 | 79376000 |  |  | Terminated | 0 | [10 empty] | For Terminations with ISF's; WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS
NC 2017 | K10 | NCR | Valenzuela City |  | Lingunan HS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 12 | 40760000 |  |  | Completed | 1
NC 2017 | K10 | NCR | City of San Juan | 136745 | Salapan ES | CITY OF SAN JUAN | 0 | 1 | 7 | 4STY7CL | BATCH 13 | 21350000 |  |  | Completed | 1 |  |  | 017OB0450 | P00182445LZ_CW1 | 2017-11-28 | 2017-12-08 | 2017-12-19 | 2017-12-22 | 2018-01-04 | B.BERNARDO CONSTRUCTION
NC 2017 | K10 | NCR | City of San Juan | 136746 | San Juan ES | City of San Juan | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 63798000 |  |  | Completed | 1 |  |  | 017OB0460 | P00182446LZ_CW1 | 2017-12-05 | 2107-12-26 | 2017-12-26 | 2018-01-03 | 2018-01-04 | ST. TIMOTHY CONSTRUCTION CORP.
NC 2017 | SHS | NCR | City of San Juan | 305423 | San Juan National High School | CITY OF SAN JUAN | 0 | 1 | 28 | 4STY28CL | BATCH 13 | 61000000 |  |  | Completed | 1 |  |  | 017OB0461 | P00182448LZ_CW1 | 2017-12-05 | 2107-12-26 | 2017-12-26 | 2018-01-03 | 2018-01-04 | GR FEVIDAL CONST. AND DEV. CORP.
NC 2017 | K10 | NCR | City of San Juan | 136747 | San Perfecto ES | CITY OF SAN JUAN | 0 | 1 | 36 | 4STY36CL | BATCH 13 | 70000000 |  |  | Completed | 1 |  |  | 017OB0445 | P00182447LZ_CW1 | 2017-11-28 | 2017-12-19 | 2017-12-19 | 2017-12-22 | 2018-01-04 | HENSCHA PHIL.INC.
NC 2017 | K10 | NCR | Manila | 305289 | T. Paez Integrated School | TONDO | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 39143000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136431 | T. Paez Integrated School (Elem.) | TONDO | 1 | 1 | 32 | 4STY32CL | BATCH 10 | 98072000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 12 | 4STY12CL | BATCH 10 | 31808000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Taguig |  | Gat Andres Bonifacio HS | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 41440293.15 |  |  | Completed | 1
NC 2017 | SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 41668504.32 |  | 41460161.8 | Completed | 1 | [8 empty] | 2018-01-10 | Alpha & Omega Gen. Contractor & Dev't. Corp.
NC 2017 | K10 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | BATCH 14 | 55558005.76 |  | 53360915.48 | Completed | 1 | [8 empty] | 2018-01-10 | Hexamindz Corp.
NC 2017 | SHS | NCR | Navotas | 305457 | Tangos National High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 42036997.81 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136500 | Bungad ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34535000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305320 | Balingasa HS | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34234000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; WAITING FOR THE PUMP TO BE INSTALLED
NC 2017 | K10 | NCR | Quezon City |  | Bagong Silangan Annex HS | QUEZON CITY | 2 | 1 | 20 | 4STY20CL | BATCH 14 | 46046000 |  |  | Completed | 1 | [10 empty] | NO MOVEMENT, based on dpwh completed as per program
NC 2017 | K10 | NCR | Quezon City | 136571 | Cruz na Ligas ES | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1
NC 2017 | TVL | NCR | Quezon City | 305359 | Quezon City High School | QUEZON CITY | 4 | 1 | 3 | 3STY3CL | BATCH 14 | 10000000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Quezon City | 305361 | Manuel A. Roxas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 35000000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL | BATCH 14 | 35238000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136537 | North Fairview ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Quezon City | 136538 | San Agustin ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | BATCH 14 | 19984000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; With Approved Buffer Funds 2018; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS
NC 2017 | K10 | NCR | Quezon City | 136513 | New Era ES | QUEZON CITY | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 40633000 |  |  | Completed | 1 | [10 empty] | COMPLETED AS PER DPWH; NO MOVEMENT AT ALL, WAITING FOR THE RESPONSE OF DPWH RE: COPY OF PERTINENT DOCUMENTS
NC 2017 | K10 | NCR | Valenzuela City | 136818 | Punturin ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 305439 | Canumay West NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | BATCH 14 | 40760000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136817 | Paso de Blas ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136822 | Caruhatan West ES | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 34970000 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1
NC 2017 | SHS | NCR | Valenzuela City | 305443 | Gen. T. de Leon NHS | CITY OF VALENZUELA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 38130000 |  |  | Completed | 1
NC 2017 | SHS | NCR | Valenzuela City | 305446 | Sitero Francisco Mem. NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1
NC 2017 | K10 | NCR | Valenzuela City |  | Bagbaguin NHS | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19025600 |  |  | Completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136627 | Bagong Barrio ES | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49570000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136629 | Morning Breeze Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136630 | Sta. Quiteria ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136631 | Talipapa ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136633 | Camarin D ES | KALOOKAN CITY | 1 |  | 20 | 4STY20CL | Batch 3 | 49050000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1 | [10 empty] | awaiting additional fund
NC 2018 | K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136642 | Silanganan ES (Star ES) | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 38270000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136643 | A. Mabini Elementary School | KALOOKAN CITY | 1 | 1 | 24 | 2 Units 4STY12CL | Batch 3 | 79200000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136649 | Tala ES | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 44050000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136655 | Sampaguita Elementary School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39770000 |  |  | COMpleted | 1 | [10 empty] | Delayed Implementation
NC 2018 | K10 | NCR | Caloocan City | 223501 | Caloocan North ES | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 305372 | Bagumbong High School | KALOOKAN CITY | 1 | 1 | 16 | 2 units 4STY8CL | Batch 3 | 44500000 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; 1 Unit partially completed (for installation of fire pro), 1 unit at 70% status though continous ongoing of works; Contractor committed to turn-over the buildings by April 30, 2023 Last Inspection: April 3 with UED, AM Nhey and Division Engrs
NC 2018 | K10 | NCR | Caloocan City | 305374 | Camarin High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 49330000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Caloocan City | 305376 | Amparo High School | KALOOKAN CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 46050000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Caloocan City | 305386 | Deparo High School | KALOOKAN CITY | 1 |  | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Caloocan City |  | CIELITO ZAMORA HS- BONIFACIO CAMPUS | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22450000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22250000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City |  | Bagong Silang Resettlement Project | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40850000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Caloocan City |  | Camarin Brixton Senior High School | KALOOKAN CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 51150000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136614 | Sampalukan ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51730000 |  |  | completed | 1
NC 2018 | K10 | NCR | Caloocan City | 136618 | Gregoria de Jesus ES | KALOOKAN CITY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 51650000 |  |  | completed | 1
NC 2018 | K10 | NCR | Las Piñas City | 136784 | Dona Manuela ES | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL | Batch 3 | 18655000 |  |  | COMpleted | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection
NC 2018 | K10 | NCR | Las Piñas City | 136785 | Moonwalk ES | CITY OF LAS PIÑAS | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45780000 |  |  | COMpleted | 1 | [10 empty] | On-going construction, target completion in December 2020. Pump installed. For joint final inspection
NC 2018 | SHS | NCR | Makati City | 305406 | Makati High School | CITY OF MAKATI | 1 | 1 | 12 | 6STY12CL | Batch 3 | 51691232.21 |  | 50402601.87 | COMpleted | 1 | [8 empty] | 2018-12-27 | C.B. GARAY PHILWIDE BUILDERS
NC 2018 | K10 | NCR | Makati City | 136697 | Tibagan ES | CITY OF MAKATI | 2 | 1 | 24 | 6STY24CL | Batch 3 | 82782166.63 |  | 80720496.68 | COMpleted | 1 | [8 empty] | 2019-01-08 | DUMDUMA CONSTRUCTION AND TRADING CORPORATION / STUDIO 26 CONSTRUCTION INC.
NC 2018 | K10 | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 81600000 |  | 78707083.61 | Completed | 1 | 2019-09-04 |  |  | 18OA0118 | [5 empty] | Cardrian Builders Inc.
NC 2018 | K10 | NCR | Malabon City | 136852 | Acacia ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 38530451.32 | Completed | 1 | 2019-05-24 |  |  | 18OA0115 | [5 empty] | C.B. Tampengco Const. & Supply
NC 2018 | SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 40800000 |  | 39336781.16 | Completed | 1 | 2019-05-23 |  |  | 18OA0105 | [5 empty] | Hexamindz Corp.
NC 2018 | K10 | NCR | Malabon City | 136834 | Imelda ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 30800000 |  | 29694849.81 | Completed | 1 | 2019-07-20 |  |  | 18OA0124 | [5 empty] | 124 Triumph Builders & Steel Inc.
NC 2018 | K10 | NCR | Malabon City | 136838 | Tañong ES I | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 38240000 |  | 36901685.25 | Completed | 1 | 2019-09-29 |  |  | 18OA0122 | [5 empty] | M.G. Salazar Const
NC 2018 | K10 | NCR | Malabon City | 136845 | Niugan ES | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL | Batch 3 | 76480000 |  | 76085502.37 | Completed | 1 | 2019-12-06 |  |  | 18OA0123 | [5 empty] | NEW BIG FOURJ CONST
NC 2018 | K10 | NCR | Malabon City | 136848 | Potrero ES | CITY OF MALABON | 0 | 1 | 12 | 4STY12CL | Batch 3 | 46200000 |  | 44579287.17 | Completed | 1 | 2019-10-24 |  |  | 18OA0121 | [5 empty] | St. Timothy Const. Corp.
NC 2018 | K10 | NCR | Malabon City | 136855 | Maysilo ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL | Batch 3 | 35840000 |  | 34696920.83 | Completed | 1 | 2019-08-27 |  |  | 18OA0125 | [5 empty] | Steven Const. & Supply
NC 2018 | SHS | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 | 1 | 4 | 4STY4CL | Batch 3 | 14364000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Mandaluyong City | 305395 | City of Mandaluyong Science HS | CITY OF MANDALUYONG | 0 |  | 24 | 4STY24CL | Batch 3 | 60000000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 50000000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1
NC 2018 | SHS | NCR | Mandaluyong City | 500333 | Eulogio Rodriguez Integrated School | CITY OF MANDALUYONG | 0 |  | 4 | 4STY4CL | Batch 3 | 10000000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 | 1 | 32 | 4STY32CL | Batch 3 | 80000000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Mandaluyong City |  | Sen. Neptali A. Gonzales Integrated School | CITY OF MANDALUYONG | 0 |  | 12 | 4STY12CL | Batch 3 | 32572215.9469 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO | 1 | 1 | 16 | 4STY16CL | Batch 3 | 57300000 |  |  | COMpleted | 1
NC 2018 | K10 | NCR | Manila | 136449 | Juan Sumulong Elementary School | SANTA CRUZ | 3 | 1 | 12 | 4STY12CL | Batch 3 | 50000000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Manila | 340599 | SHS within A.Maceda Intg. Sch.-(HS) | CITY OF MANILA | 4 | 1 | 4 | 4STY4CL (SPECIAL DESIGN) | Batch 3 | 23600000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 40 | 4STY40CL | Batch 3 | 116010000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 24 | 4STY24CL | Batch 3 | 81902000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 | 1 | 28 | 4STY28CL | Batch 5 | 229660358.78 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136453 | A. Mabini Elementary School | QUIAPO | 1 |  | 8 | 4STY8CL | Batch 5 | 49276374.28 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136443 | Gen. Gregorio del Pilar ES | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 90600000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 80300000 |  |  | COMpleted | 1
NC 2018 | K10 | NCR | Manila | 305295 | Lakan Dula High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 65000000 |  |  | COMpleted | 1
NC 2018 | K10 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 | 1 | 16 | 4STY16CL | Batch 5 | 81200000 |  |  | COMpleted | 1
NC 2018 | K10 | NCR | Manila | 305298 | Florentino Torres High School | TONDO | 2 |  | 12 | 4STY12CL | Batch 5 | 70200000 |  |  | COMpleted | 1
NC 2018 | K10 | NCR | Manila | 136466 | V. E. Fugoso Memorial School | SAMPALOC | 4 | 1 | 20 | 4STY20CL | Batch 5 | 54300000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136476 | E. delos Santos Elementary School | CITY OF MANILA | 5 | 1 | 22 | 4STY22CL | Batch 5 | 67588702.95 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136479 | Rafael Palma Elementary School | CITY OF MANILA | 5 | 1 | 24 | 4STY24CL | Batch 5 | 78327248.76 |  |  | Completed | 1
NC 2018 | K10 | NCR | Manila | 136489 | Tomas Earnshaw Elementary School | SANTA ANA | 6 | 1 | 28 | 4STY28CL | Batch 5 | 86806728.08 |  |  | Completed | 1
NC 2018 | K10 | NCR | Marikina City | 136685 | SSS Village ES | CITY OF MARIKINA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 60851765.74 |  |  | Completed | 1 | [9 empty] | Alpha-Omega Gen Con & Dep't. Corp
NC 2018 | SHS | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA | 2 | 1 | 24 | 4STY24CL | Batch 3 | 67546019.91 |  |  | Completed | 1 | [8 empty] | 2019-01-14 | Vinnel-Belvoir Corporation
NC 2018 | K10 | NCR | Muntinlupa City | 136900 | F. De Mesa ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45992000 |  |  | Completed | 1 |  |  |  | 18OI0180 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | MRRM Trading & Const.
NC 2018 | K10 | NCR | Muntinlupa City | 136901 | Itaas Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45427500 |  |  | Completed | 1 |  |  |  | 18OI0179 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | ORANI BUILDERS SUPLY
NC 2018 | K10 | NCR | Muntinlupa City | 136903 | Muntinlupa ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34313000 |  |  | Completed | 1 |  |  |  | 18OI0183 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | G. F. ROVERO MERCHANDISING
NC 2018 | K10 | NCR | Muntinlupa City | 136904 | Putatan Elementary School | CITY OF MUNTINLUPA | 0 | 1 | 16 | 2 UNITS 4STY8CL | Batch 3 | 37800000 |  |  | Completed | 1 |  |  |  | 18OI0184 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply
NC 2018 | K10 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 12 | 4STY12CL | Batch 3 | 34492000 |  |  | Completed | 1 |  |  |  | 18OI0186 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | ORANI BUILDERS SUPPLY
NC 2018 | K10 | NCR | Muntinlupa City | 136912 | Cupang ES | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL | Batch 3 | 46166000 |  |  | Completed | 1 |  |  |  | 18OI0181 |  | 2018-11-29 | 2018-12-11 |  | 2018-12-28 | REDCAR TRADING & CONST.
NC 2018 | SHS | NCR | Muntinlupa City | 305468 | Muntinlupa NHS | CITY OF MUNTINLUPA | 0 | 1 | 16 | 4STY16CL | Batch 3 | 40515000 |  |  | Completed | 1 |  |  |  | 18OI0185 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | MRRM Trading & Const.
NC 2018 | K10 | NCR | Muntinlupa City | 305470 | PEDRO E. DIAZ HIGH SCHOOL | CITY OF MUNTINLUPA | 0 | 1 | 32 | 2 UNITS 4STY16CL | Batch 3 | 79620000 |  |  | Completed | 1 |  |  |  | 18OI0186 |  | 2018-12-05 | 2018-12-17 |  | 2018-12-28 | C. T. LEONCIO Const. & Trading/KP Gonzales Const. & Supply
NC 2018 | K10 | NCR | Navotas | 136857 | Bangkulasi Elementary School | CITY OF NAVOTAS | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 55410000 |  |  | COMpleted | 1 | [9 empty] | Dungan Contractor's & Trading Corp./ Jojalie Const. (JV) | For Punchlisting and Final Inspection
NC 2018 | K10 | NCR | Navotas | 136859 | Kapitbahayan Elementary School | CITY OF NAVOTAS | 0 | 1 | 24 | 4STY24CL | BATCH 1 | 82750000 |  |  | Completed | 1 | [9 empty] | MRBll Const. Corp
NC 2018 | K10 | NCR | Navotas | 136860 | Navotas Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41190000 |  |  | Completed | 1 | [9 empty] | Orientech Const. & Devt. Corp.
NC 2018 | K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41140000 |  |  | Completed | 1 | [9 empty] | C.T. Leoncio Const. & Trading
NC 2018 | SHS | NCR | Navotas | 305454 | San Rafael Technological High School | CITY OF NAVOTAS | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 41410000 |  |  | Completed | 1 | [9 empty] | St. Timothy Const. Corp.
NC 2018 | K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE | 1 | 1 | 16 | 4STY16CL | Batch 3 | 35522115.63 |  |  | Completed | 1
NC 2018 | K10 | NCR | Paranaque City | 136762 | Don Galo ES | CITY OF PARAÑAQUE | 1 | 1 | 4 | 4STY4CL | Batch 3 | 6825497.26 |  |  | Completed | 1
NC 2018 | K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 22432790.46 |  |  | Completed | 1
NC 2018 | K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 |  | 20 | 4STY20CL | Batch 3 | 51169448.43 |  |  | Completed | 1
NC 2018 | SHS | NCR | Paranaque City | 305424 | Paranaque National High School Main | CITY OF PARAÑAQUE | 1 | 1 | 28 | 4STY28CL | Batch 3 | 73737963.15 |  |  | Completed | 1
NC 2018 | SHS | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL | Batch 3 | 24747640.87 |  |  | Completed | 1
NC 2018 | K10 | NCR | Paranaque City | 136755 | Masville ES | CITY OF PARAÑAQUE | 2 | 1 | 12 | 4STY12CL (9mX7m) or 4STY16CL (Modified 8mX7m) | Batch 3 | 30851669.06 |  |  | Completed | 1
NC 2018 | K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL (9mX7m) or 4STY12CL (Modified 8mX7m) | Batch 3 | 20617779.37 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished
NC 2018 | K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 |  | 24 | 4STY24CL (9mX7m) or 4STY36CL (Modified 8mX7m) | Batch 3 | 61553338.11 |  |  | Completed | 1 | [10 empty] | Suspended 1/10/2019, Still finding a new site that will serve as temporary learning shelter for the displaced students that will be affected since the entire builing will be demolished
NC 2018 | K10 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59975000 |  | 54427594.9 | Completed | 1 | 2019-09-12 |  |  | 18OH0174 |  |  | 2018-11-06 | 2018-11-21 | 2018-12-10 | St. Timothy Const. Corporation
NC 2018 | K10 | NCR | Pasay City | 136604 | Jose Rizal ES | PASAY CITY | 0 |  | 24 | 4STY24CL | Batch 3 | 68891000 |  | 63466057.96 | Completed | 1 | 2019-10-12 |  |  | 18OH0173 |  |  | 2018-11-06 | 2018-11-21 | 2018-12-10 | Alpha & Omega Gen. Contractor & Dev't Corp. | Punchlist items still for acceptance. Ceiling is damaged by Typhoon Fabian, to be rectified by Contractor.
NC 2018 | K10 | NCR | Pasig City | 136728 | San Joaquin ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 59295681.69 |  |  | Completed | 1
NC 2018 | K10 | NCR | Pasig City | 136732 | Pineda ES | CITY OF PASIG | 0 | 1 | 20 | 4STY20CL | Batch 3 | 56669465.54 |  |  | Completed | 1
NC 2018 | K10 | NCR | Pasig City | 136742 | Maybunga ES | CITY OF PASIG | 0 | 1 | 12 | 4STY12CL | Batch 3 | 41690415.08 |  |  | Completed | 1
NC 2018 | SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG | 0 | 1 | 24 | 4STY24CL | Batch 3 | 68269701.05 |  |  | Completed | 1
NC 2018 | SHS | NCR | Pasig City | 305422 | Rizal Exp. Sta. And Pilot SCI (RESPSCI) | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL | Batch 3 | 26218158.47 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136565 | Teodora Alonzo Elementary School | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18100000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY12CL & 4STY8CL | Batch 3 | 61450000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136508 | Mines Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 305323 | San Jose HS | QUEZON CITY | 1 | 1 | 24 | 4STY24CL | Batch 3 | 62600000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 305332 | Bagong Silangan HS | QUEZON CITY | 2 | 1 | 16 | 4STY16CL | Batch 3 | 46860000 |  |  | Completed | 1 | [10 empty] | With Additional Funds intended for Connecting Bridge
NC 2018 | SHS | NCR | Quezon City | 319501 | Holy Spirit SHS | QUEZON CITY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 22610000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Quezon City | 305350 | Quirino HS | QUEZON CITY | 3 | 1 | 8 | 4STY8CL | Batch 3 | 30555000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136573 | Pinyahan ES | QUEZON CITY | 4 | 1 | 16 | 4STY16CL | Batch 3 | 47500000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136579 | General Roxas Elementary School | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28195000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136583 | Aurora A. Quezon ES | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28120000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY | 4 | 1 | 8 | 4STY8CL | Batch 3 | 28150000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Quezon City | 305355 | Carlos L. Albert HS | QUEZON CITY | 4 | 1 | 20 | 4STY20CL | Batch 3 | 61650000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136531 | Damong Maliit ES | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23010000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City |  | ATTY. ALFRED VARGAS SR. HS | QUEZON CITY | 5 | 1 | 8 | 4STY8CL | Batch 3 | 23945000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City |  | G.B. FRANCISCO | QUEZON CITY | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54570000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 20 | 4STY20CL | Batch 3 | 54050000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 22810000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 136505 | San Antonio ES | QUEZON CITY | 1 | 1 | 12 | 4STY12CL | Batch 5 | 39510000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Quezon City | 305328 | Pugad Lawin HS | QUEZON CITY | 1 | 1 | 8 | 4STY8CL | Batch 5 | 23410000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Taguig | 136875 | Ricardo P. Cruz, Sr. Elementary School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 27075203.01 |  | 25,932,552,52 | Completed | 1 | 2020-08-29 | 2020-12-15 | P00273636LZ_CW1 | 018OB0464 | 2018-10-29 | 2018-11-07 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hyper J Construction & Supply
NC 2018 | K10 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25907137.3 |  | 24822894.92 | Completed | 1 | 2020-02-13 | 2020-12-15 | P00273637LZ_CW1 | 018OB0466 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hyper J Construction & Supply
NC 2018 | K10 | NCR | Taguig | 136897 | Sta. Ana Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 37565830.5 |  | 36066487.7 | Completed | 1 | 2021-04-27 |  | P00273638LZ_CW1 | 018OB0462 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Hony Trading and Construction
NC 2018 | K10 | NCR | Taguig | 136898 | Sto. Rosario Elementary School | PATEROS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 33116745.66 |  | 31758084.98 | Completed | 1 | 2020-02-07 | 2020-03-13 | P00273639LZ_CW1 | 018OB0463 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | Dahl Construction Corporation
NC 2018 | K10 | NCR | Taguig | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 24 | 4STY24CL | Batch 3 | 62326754.78 |  | 60009167.37 | Completed | 1 | 2019-09-27 | 2020-01-02 | P00273640LZ_CW1 | 018OB0456 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | MRBII Construction Corporation
NC 2018 | K10 | NCR | Taguig | 136887 | Upper Bicutan ES | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL | Batch 3 | 39012528.26 |  | 37461040.68 | Completed | 1 | 2020-01-31 | 2020-03-13 | P00273641LZ_CW1 | 018OB0461 | 2018-10-25 | 2018-11-05 | 2018-11-16 | 2018-11-27 | 2018-12-12 | MRBII Construction Corporation
NC 2018 | K10 | NCR | Valenzuela City | 136794 | Dalandanan Elementary School | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39400000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City | 136806 | Pasolo Elementary School | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55800000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City |  | Disiplina Village ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 39050000 |  | 37836609.18 | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL | Batch 3 | 21150000 |  | 21043537.2 | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 46600000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City |  | Malanday NHS | CITY OF VALENZUELA | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55400000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City | 136796 | Sitio Sto. Rosario ES (Malabo ES) | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL | Batch 3 | 47150000 |  |  | Completed | 1
NC 2018 | K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21470000 |  |  | Completed | 1
NC 2018 | SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21100000 |  |  | Completed | 1
NC 2019 | K10 | NCR | Caloocan City | 305373 | Sampaguita HS | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Caloocan City | 305386 | Deparo High School | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | exiting bldg - for demolition | 0
NC 2019 | K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Caloocan City | 136633 | Camarin D ES | Caloocan City | 1 |  | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Caloocan City | 136639 | Bagong Silang ES | Caloocan City | 1 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 47418250 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Caloocan City | 136606 | Grace Park ES (Main) | Caloocan City | 2 | 1 | 20 | 4STY20CL |  | 50947050 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | SHS | NCR | Caloocan City | 305388 | Caloocan HS | Caloocan City | 2 | 1 | 8 | 4STY8CL |  | 24060000 |  | completed | 1 | [10 empty] | Awaiting on the Approved Authority to Demolished to be issued by the LGU | 0
NC 2019 | K10 | NCR | Malabon City | 136850 | Tinajeros ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 30877000 | 28446060 | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Malabon City | 305450 | Panghulo NHS | CITY OF MALABON | 0 | 1 | 16 | 4STY16CL |  | 76671200 | 68593280 | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Manila | 500566 | T. Paez Integrated School (Elem.) | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  | completed | 1 | [10 empty] | DPWH Terminated the Contract under this project. | 0
NC 2019 | K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 | 1 | 20 | 4STY20CL |  | 68370500 |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0
NC 2019 | K10 | NCR | Manila | 136437 | Manuel L. Quezon Elementary School | CITY OF MANILA | 1 |  | 24 | 2UNITS 4STY12CL |  | 99448000 |  | Terminated | 0.82 | [10 empty] | DPWH Terminated the Contract under this project; Completion of the school building already funded under GAA 2023 | 0
NC 2019 | K10 | NCR | Manila | 136439 | I. Delos Reyes ES | CITY OF MANILA | 1 | 1 | 32 | 4STY16CL |  | 57443250 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136456 | P. Guevara Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 42907000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136452 | P. Gomez ES | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 52337464.7685 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Manila | 305302 | Jose Abad Santos High School | CITY OF MANILA | 3 | 1 | 16 | 4STY16CL |  | 83876040.8241 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 305300 | Cayetano Arellano High School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 66203184.4932 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | CITY OF MANILA | 3 | 1 | 12 | 4STY12CL |  | 54417594.5245 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136460 | G. Lopez Jaena Elementary School | CITY OF MANILA | 4 | 1 | 20 | 4STY20CL (SPECIAL DESIGN) |  | 56541000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136472 | Pio del Pilar Elementary School | CITY OF MANILA | 5 | 1 | 8 | 4STY8CL |  | 29573750 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Manila | 136482 | Bagong Diwa Elementary School | CITY OF MANILA | 6 | 1 | 24 | 4STY24CL |  | 49724000 |  | Completed | 1 | [10 empty] | awaiting for the approval of central office for modification of plans and quantity of CLs | 0
NC 2019 | K10 | NCR | Manila | 136471 | Bacood Elementary School | CITY OF MANILA | 5 | 1 | 16 | 4STY16CL |  | 50726500 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Muntinlupa City | 136911 | Buli ES | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 28070000 |  | Completed | 1 |  |  |  | 19OI0140 | 8/1/2019 | 2019-08-07 | 2019-09-03 | 2019-09-12 | 2019-09-27 |  |  | 0
NC 2019 | K10 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 20 | 4STY20CL |  | 49122500 |  | Completed | 1 |  |  |  | 19OI0141 | 8/1/2019 | 2019-08-07 | 2019-08-19 | 2019-08-28 | 2019-09-09 |  |  | 0
NC 2019 | K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL |  | 38335600 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 | 1 | 24 | 4STY24CL |  | 62756500 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136492 | Ramon Magsaysay ES | QUEZON CITY | 1 |  | 20 | 4STY20CL |  | 54185125 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22516150 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 | 1 | 20 | 4STY20CL |  | 54185125 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136507 | Bagong Pag-Asa Elementary School | QUEZON CITY | 1 |  | 16 | 4STY16CL |  | 46611237.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136509 | Project 6 ES | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22666525 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 | 1 | 8 | 4STY8CL |  | 30375750 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136569 | Dona Josefa E. Marcos ES | QUEZON CITY | 3 |  | 12 | 4STY12CL |  | 38095000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Quezon City | 305353 | Krus na Ligas HS | QUEZON CITY | 4 | 1 | 12 | 4STY12CL |  | 40100000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 24004862.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Taguig | 305464 | Tipas National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL w/ ROOFDECK |  | 56381109.0094 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Valenzuela City | 320407 | Wawangpulo National High School | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 16040000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 12 | 4STY12CL |  | 48440800 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 20 | 4STY20CL |  | 51648489.1147 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 16 | 4STY16CL |  | 45893588.7322 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 |  | 8 | 4STY8CL |  | 22502549.9446 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Valenzuela City | 320406 | Canumay East National High School | CITY OF VALENZUELA | 1 | 1 | 16 | 2UNITS 4STY8CL |  | 45120136.644 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | 4STY8CL |  | 22697871.3705 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | 4STY20CL |  | 47655164.2386 |  | Completed | 1 | [11 empty] | 0
NC 2020 | K10 | NCR | Caloocan City | 136640 | Sto. Niño Elementary School | KALOOKAN CITY | 1 | 1 | 8 | 4STY8CL |  | 24761750 |  |  | Completed | 1
NC 2020 | K10 | NCR | Caloocan City | 319701 | Cielito Zamora Senior High School | KALOOKAN CITY | 1 | 1 | 12 | 4STY12CL |  | 41904500 |  |  | Completed | 1
NC 2020 | K10 | NCR | Caloocan City | 136623 | Barrio San Jose ES | KALOOKAN CITY | 2 | 1 | 12 | 4STY12CL |  | 41603750 |  |  | Completed | 1
NC 2020 | K10 | NCR | Las Piñas City | 136779 | Pulanlupa ES | CITY OF LAS PIÑAS | 0 | 1 | 12 | 4STY12CL |  | 38596250 |  | 37576003.99 | Completed | 1 |  |  |  | 20OI0090 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | RR Encado Constructors Inc./Rocksteel Const. & Dev`t Corp (Joint Venture) | Completed as per DPWH; very slow moving of the work accomplishment due to minimal delivery of constraction materials on site
NC 2020 | SHS | NCR | Las Piñas City | 305430 | Las Piñas National High School | CITY OF LAS PIÑAS | 0 | 1 | 8 | 4STY8CL |  | 26967250 |  | 26335101.13 | completed | 1 |  | 2021-08-03 |  | 20OI0089 | 2020-01-08 | 2020-01-15 | 2020-01-29 | 2020-01-29 | 2020-08-18 | Metrics Construction and Trading | Turned-over
NC 2020 | K10 | NCR | Malabon City | 136833 | Santulan ES | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | COMpleted | 1 | 2020-05-02 |  |  | 20OA0075 |  |  | 2020-07-20 |  |  | solenko construction
NC 2020 | SHS | NCR | Malabon City | 305447 | Malabon NHS | CITY OF MALABON | 0 | 1 | 8 | 4STY8CL |  | 38596250 |  |  | COMpleted | 1 | 2020-05-02 |  |  | 20OA0074 |  |  | 2020-07-20 |  |  | newbig four J construction inc
NC 2020 | K10 | NCR | Mandaluyong City |  | Senate President Neptali A. Gonzales IS | CITY OF MANDALUYONG | 0 | 1 | 12 | 4STY12CL |  | 27067500 |  |  | Completed | 1
NC 2020 | K10 | NCR | Manila | 136423 | Mariano Ponce Elementary School | TONDO | 2 | 1 | 16 | 4STY16CL |  | 90773235.11 |  |  | Completed | 1 | [10 empty] | on-going concreting works at 1st floor
NC 2020 | K10 | NCR | Manila | 500567 | F. G. Calderon Elementary School | TONDO | 2 | 1 | 12 | 4STY12CL |  | 69077262.5 |  |  | Completed | 1 | [10 empty] | Completed as per DPWH; Ongoing concreting at ground floor
NC 2020 | K10 | NCR | Manila | 136446 | Andres Bonifacio Elementary School | SANTA CRUZ | 3 | 1 | 8 | 4STY8CL (COMPLETION) |  | 10075125 |  |  | Completed | 1 | [10 empty] | Completed
NC 2020 | K10 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ | 3 | 1 | 20 | 4STY20CL |  | 97267562.5 |  |  | COMpleted | 1 | [10 empty] | Ongoing concreting at ground floor
NC 2020 | K10 | NCR | Manila | 136456 | P. Guevara Elementary School | SAN NICOLAS | 3 | 1 | 12 | 4STY12CL |  | 33040842.6 |  |  | COMpleted | 1 | [10 empty] | Ongoing concreting at ground floor
NC 2020 | K10 | NCR | Manila | 136458 | Laong Laan ES | SAMPALOC | 4 | 1 | 12 | 4STY12CL |  | 62255250 |  |  | COMpleted | 1 | [10 empty] | on-going foundation works
NC 2020 | K10 | NCR | Manila | 136480 | Bagong Barangay Elementary School | PANDACAN | 6 | 1 | 8 | 4STY8CL |  | 27067500 |  |  | COMpleted | 1 | [10 empty] | on-going foundation works
NC 2020 | SHS | NCR | Marikina City | 319906 | Sto. Nino National High School | CITY OF MARIKINA | 1 | 1 | 8 | 4STY8CL with Mat Foundation |  | 34887000 |  |  | Completed | 1 | 2021-04-03 | 2021-04-03 |  | 20OB0421 | 2020-05-26 | 2020-06-03 | 2020-06-16 |  | 2020-08-07 | MRBII Construction Corporation
NC 2020 | K10 | NCR | Muntinlupa City | 136908 | Alabang ES (Main) | CITY OF MUNTINLUPA | 0 | 1 | 8 | 4STY8CL |  | 19548750 |  | 19051420.15 | Completed | 1 | 2021-03-21 | 2021-09-30 | P00470027LZ-CW1 | 20OI0092 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | RGDG Construction | Due to pandemic
NC 2020 | K10 | NCR | Muntinlupa City | 281541 | Poblacion ES | Muntinlupa | 0 | 1 | 8 | 4STY8CL |  | 24761750 |  | 24391249.6 | Completed | 1 |  |  | P00470028LZ-CW1 | 20OI0093 | 2020-01-03 | 2020-01-15 | 2020-01-29 | 2020-02-20 | 2020-08-18 | GREAT PACIFIC Builders and Gen. Contractor Inc. | due to pandemic and demoliion of NAWASA elevated tank
NC 2020 | SHS | NCR | Navotas City | 305453 | Navotas NHS | CITY OF NAVOTAS | 0 | 1 | 8 | 4STY8CL (7X8) |  | 38596250 |  |  | Completed | 1 | 2021-05-05 | [8 empty] | MRBll Construction Corporation
NC 2020 | K10 | NCR | Paranaque City | 136768 | Baclaran ES Unit I | CITY OF PARAÑAQUE | 1 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 23944652.12 | Completed | 1 | 2021-09-13 |  | P00470030LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | J.A. Evangelista Construction
NC 2020 | K10 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES - Don Bosco | CITY OF PARAÑAQUE | 2 | 1 | 8 | 4STY8CL with ROOFDECK |  | 24747486.2 |  | 24191889.08 | COMpleted | 1 | 2021-09-13 |  | P00470031LZ-CWI |  |  |  | 2020-09-09 | 2020-09-15 | 2020-09-18 | GREAT PACIFIC Builders and Gen. Contractor Inc.
NC 2020 | K10 | NCR | Pasig City | 136727 | Kalawaan ES | Pasig City | 0 | 1 | 8 | 4STY8CL |  | 40049665.93 |  |  | Completed | 1
NC 2020 | K10 | NCR | Pasig City | 136731 | Oranbo ES | Pasig City | 0 | 1 | 16 | 4STY16CL |  | 59962819.77 |  |  | Completed | 1
NC 2020 | K10 | NCR | Pasig City | 136743 | San Miguel Elementary School | CITY OF PASIG | 0 | 1 | 8 | 4STY8CL |  | 30032092.31 |  |  | Completed | 1
NC 2020 | SHS | NCR | Pasig City | 340654 | SHS in Buting, Pasig City | Pasig City | 0 | 1 | 16 | 4STY16CL WITH ROOF DECK |  | 87205470 |  |  | Completed | 1
NC 2020 | K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | COMPLETED | 1
NC 2020 | K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | 4STY28CL |  | 87718750 |  |  | COMPLETED | 1 | [10 empty] | Completed as of DPWH; DEMOLITION COMPLETED
NC 2020 | K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 | 1 | 12 | 4STY12CL |  | 40902000 |  |  | Completed | 1
NC 2020 | K10 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | 4STY16CL |  | 52130000 |  |  | COMPLETED | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED
NC 2020 | K10 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | Completed | 1 | [10 empty] | Mobilized
NC 2020 | K10 | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY | 5 | 1 |  | CONSTRUCTION OF RETAINING WALL |  | 13964825 |  |  | COMPLETED | 1
NC 2020 | K10 | NCR | Quezon City | 136519 | Lucas R. Pascual Mem. ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 44957112.5 |  |  | COMPLETED | 1
NC 2020 | K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | 4STY12CL |  | 40250375 |  |  | COMPLETED | 1 | [10 empty] | 100 %, DEMOLITION COMPLETED
NC 2020 | K10 | NCR | Taguig City & Pateros | 136892 | Aguho Elementary School | PATEROS | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 47151585 |  | 45551188.88 | Completed | 1 | 2021-07-21 |  | P00470044LZ | 20OB0433 |  |  | 2020-07-15 |  |  | Newbig Four J Construction Inc.
NC 2020 | K10 | NCR | Taguig City & Pateros | 136896 | Pateros Elementary School | Pateros | 1 | 1 | 16 | 4STY16CL |  | 71177500 |  | 68609100.51 | Completed | 1 | 2021-06-06 |  | P00470045LZ | 20OB0423 |  |  | 2020-06-16 |  |  | MRBII Construction Corp.
NC 2020 | SHS | NCR | Taguig City & Pateros | 305459 | Bagumbayan National High School | TAGUIG CITY | 1 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 46917000 |  | 45190402.5 | Completed | 1 | 2021-07-21 |  | P00470046LZ | 20OB0424 |  |  | 2020-06-16 |  |  | Flordes Construction and Trading Corp.
NC 2020 | SHS | NCR | Taguig City & Pateros | 320601 | Taguig Science High School | TAGUIG CITY | 1 | 1 | 8 | 4STY8CL with roofdeck (With Provision for 4sty12Cl) |  | 35087500 |  | 33833315.44 | Completed | 1 | 2021-05-07 |  | P00470050LZ | 20OB0422 |  |  | 2019-12-19 |  |  | Hony Trading & Construction
NC 2020 | K10 | NCR | Taguig City & Pateros | 136885 | Enlisted Men's Signal Village Elementary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL |  | 35262937.5 |  | 34566172.31 | Completed | 1 | 2021-07-29 |  | P00470048LZ | 20OBD0171 |  |  | 2020-08-18 |  |  | St. Timothy Construction Corp.
NC 2020 | K10 | NCR | Taguig City & Pateros | 228002 | Gat. Andres Bonifacio Elmentary School | TAGUIG CITY | 2 | 1 | 12 | 4STY12CL WITH ROOF DECK |  | 50125000 |  | 4441598251 | Completed | 1 | 2021-05-22 |  | P00470049LZ | 20OB0172 |  |  | 2019-12-19 |  |  | MRBII Construction Corp.
NC 2020 | SHS | NCR | Taguig City & Pateros | 305463 | Signal Village National High School | TAGUIG CITY | 2 | 1 | 20 | 4STY20CL |  | 64861750 |  | 62521178.4 | Completed | 1 |  |  | P00470050LZ | 20OB0422 |  |  | 2020-06-16 |  |  | Orani Builders and Supply
NC 2020 | K10 | NCR | Valenzuela City | 136795 | Lingunan ES | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24360750 |  |  | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470051LZ | 20OD0103 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc.
NC 2020 | K10 | NCR | Valenzuela City |  | Veinte Reales HS | CITY OF VALENZUELA | 1 | 1 | 8 | 4STY8CL |  | 24482553.75 |  | 23853462.32 | Completed | 1 | 2021-04-13 | 2021-07-06 | P00470052LZ | 20OD0104 |  |  |  |  | 2020-08-17 | Toughbuilt Const. & Trading Inc.
NC 2020 | K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 | 1 | 16 | 4STY16CL |  | 47167625 |  | 45850285.22 | Completed | 1 | 2021-07-12 |  | P00470053LZ | 20OD0193 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF
NC 2020 | K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 12 | 4STY12CL |  | 41653875 |  | 40530029.26 | Completed | 1 | 2021-06-12 |  | P00470054LZ | 20OD0192 |  |  |  |  | 2020-08-17 | DJB Const. Services | Suspended due to presence of ISF
NC 2020 | K10 | NCR | Valenzuela City | 136821 | Caruhatan East ES | CITY OF VALENZUELA | 2 |  | 8 | 4STY8CL |  | 24711625 |  | 24081305.36 | COMpleted | 1 | 2021-04-13 |  | P00470055LZ | 20OD0194 |  |  |  |  | 2020-08-17 | DJB Const. Services | On Going
NC 2021 | K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1002500 | 1000000 | 996110.17 | completed | 1 | 2021-10-27 |  | P00575461LZ | 21OD0197 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading
NC 2021 | K10 | NCR | Caloocan City | 136634 | Camarin Elementary School | KALOOKAN CITY | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 2005000 | 2000000 | 1994008.08 | completed | 1 | 2021-11-26 |  | P00575462LZ | 21OD0200 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading
NC 2021 | K10 | NCR | Caloocan City | 136654 | Llano ES | CALOOCAN CITY | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1494229.88 | completed | 1 | 2021-10-27 |  | P00575463LZ | 21OD0195 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | C.B. Tampengco Construction & Supply
NC 2021 | K10 | NCR | Caloocan City | 305374 | Camarin HS | CALOOCAN CITY | 1 | 1 | 16 | Construction/Completion (2-4STY8CL) |  | 2005000 | 2000000 | 1996667.41 | completed | 1 | 2021-12-26 |  | P00575464LZ | 21OD0196 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Aylan Const. & Trading
NC 2021 | SHS | NCR | Caloocan City | 305380 | Tala High School | KALOOKAN CITY | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 4010000 | 4000000 | 3989457.54 | completed | 1 | 2021-12-26 |  | P00575465LZ | 21OD0224 | 2021-08-04 | 2021-08-11 | 2021-08-23 | 2021-09-13 | 2021-09-27 | Aylan Const. & Trading
NC 2021 | SHS | NCR | Caloocan City | 305381 | Bagong Silang HS | KALOOKAN CITY | 1 | 1 | 6 | Construction/Completion (3STY6CL) (construction of 1CL at 2nd Floor, Staircase, CR with Septic Tank & repair/refurbishment of 5CL)) |  | 4010000 | 4000000 | 3986234.57 | completed | 1 | 2021-12-26 |  | P00575466LZ | 21OD0206 | 2021-07-16 | 2021-07-23 | 2021-08-04 | 2021-08-23 | 2021-09-27 | AGH Const. Corp.
NC 2021 | SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 1495444.36 | completed | 1 | 2021-10-27 |  | P00575467LZ | 21OD0199 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp.
NC 2021 | SHS | NCR | Caloocan City | 305383 | Bagong Barrio NHS | Caloocan City | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1495444.36 | completed | 1 | 2021-10-27 |  | P00575468LZ | 21OD0198 | 2021-07-09 | 2021-07-16 | 2021-07-28 | 2021-08-18 | 2021-09-27 | Probuilds & Works Construction Corp.
NC 2021 | K10 | NCR | Paranaque City | 136769 | Baclaran ES Unit II | CITY OF PARAÑAQUE | 1 | 1 | 2 | Construction/Completion (4STY2CL) |  | 5012500 | 5000000 | 4849479.06 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Jalenz Construction and Supply
NC 2021 | SHS | NCR | Paranaque City | 320201 | Paranaque Science HS | CITY OF PARAÑAQUE | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 20050000 | 20000000 | 19500585.67 | COMPLETED | 1 | 2022-04-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | YPR General Contractor and Construction Supply Inc.
NC 2021 | K10 | NCR | Paranaque City | 136761 | Col. E. De Leon Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 32 | Construction/Completion (4STY32CL) |  | 10025000 | 10000000 | 9698075.4 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Golden 3T Construction Corp,
NC 2021 | K10 | NCR | Paranaque City | 136763 | F. Serrano Sr. ES | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 8020000 | 8000000 | 7757714.6 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction
NC 2021 | K10 | NCR | Paranaque City | 226001 | Sun Valley ES | CITY OF PARAÑAQUE | 2 | 1 | 3 | Construction/Completion (3STY3CL) |  | 7518750 | 7500000 | 7274965.25 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction
NC 2021 | SHS | NCR | Paranaque City | 305428 | Dr. Arcadio Santos NHS - Main | CITY OF PARAÑAQUE | 2 | 1 | 8 | Construction/Completion (4-STOREY) |  | 6015000 | 6000000 | 5819939.36 | COMPLETED | 1 | 2022-02-10 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | GMO Construction
NC 2021 | SHS | NCR | Paranaque City | 320203 | Moonwalk National High School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4STY4CL) |  | 2506250 | 2500000 | 2424970.58 | COMPLETED | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction
NC 2021 | K10 | NCR | Paranaque City |  | Marcelo Green HS | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (4-STOREY) |  | 2005000 | 2000000 | 1939135.79 | COMPLETED | 1 | 2022-01-11 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | RGDG Construction
NC 2021 | K10 | NCR | Paranaque City |  | Silverio Annex Elementary School | CITY OF PARAÑAQUE | 2 | 1 | 1 | Construction/Completion (Four (4) Storey & Three (3) Storey) |  | 1002500 | 1000000 | 979905.88 | COMPLETED | 1 | 2021-12-12 |  |  |  | 2021-08-09 |  | 2021-09-29 | 2021-10-06 | 2021-10-14 | Lizvil Construction and Supply
NC 2021 | K10 | NCR | Quezon City | 136491 | Demetrio Tuazon ES | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completion Works
NC 2021 | K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4522277.5 | 4511000 |  | Completed | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completion Works
NC 2021 | K10 | NCR | Quezon City | 136498 | San Francisco ES | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (4STY32CL) |  | 13032500 | 13000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 |  | no movement
NC 2021 | SHS | NCR | Quezon City | 305327 | San Francisco High School | QUEZON CITY | 1 | 1 | 32 | Construction/Completion (2 units 4STY16CL) |  | 13032500 | 13000000 |  | Completed | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completion Works
NC 2021 | K10 | NCR | Quezon City | 136546 | Manuel L. Quezon ES | QUEZON CITY | 2 | 1 | 28 | Construction/Completion (4STY28CL) |  | 6015000 | 6000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1
NC 2021 | K10 | NCR | Quezon City | 136549 | Payatas B Annex ES | QUEZON CITY | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1002500 | 1000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | Completed based on DPWH; No movement yet
NC 2021 | SHS | NCR | Quezon City | 305331 | Commonwealth HS | QUEZON CITY | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | AYLAN CONSTRUCTION & TRADING | Completed based on DPWH; no movement
NC 2021 | K10 | NCR | Quezon City | 136527 | Dona Rosario Elementary School | QUEZON CITY | 5 |  | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | COMpleted | 1 | [8 empty] | 2021-11-09 | JYBL CONSTRUCTION & TRADING | no movement
NC 2021 | K10 | NCR | Quezon City | 136528 | Rosa L. Susano - Novaliches ES | QUEZON CITY | 5 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | J. SIMEON CONSTRUCTION | Completed based on DPWH; No movement yet, ongoing phase 1
NC 2021 | K10 | NCR | Quezon City | 136529 | San Gabriel ES | QUEZON CITY | 5 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4736812.5 | 4725000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | TAPNIO AND TAN CONSTRUCTION AND DEVELOPMENT CORPORATION | no movement
NC 2021 | K10 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 | 1 | 12 | Construction/Completion (4STY12CL) |  | 7017500 | 7000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | RAMALLA CONSTRUCTION & TRADING | Completed based on DPWH;; only 1 bldg constructed 4sty16cl needs to be removed in this list
NC 2021 | K10 | NCR | Quezon City | 136530 | Villa Verde Elementary School | QUEZON CITY | 5 |  | 16 | Construction/Completion (4STY16CL) |  | 3007500 | 3000000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 |  | no movement
NC 2021 | K10 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 4957362.5 | 4945000 |  | COMPLETED | 1 | [8 empty] | 2021-11-09 | E.I. VILLACORTE CONSTRUCTION | Completed based on DPWH;; no movement
NC 2021 | K10 | NCR | Valenzuela City | 136807 | Pio Valenzuela ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1473340.67 | completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0207 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction
NC 2021 | K10 | NCR | Valenzuela City | 136811 | WawangPulo ES | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1503750 | 1500000 | 1472681.08 | completed | 1 | 2021-11-25 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Toughbulit Const & Trading Inc
NC 2021 | SHS | NCR | Valenzuela City | 305436 | Polo NHS | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1956107.88 | completed | 1 | 2021-11-25 |  | P00575493LZ | 21OD0209 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction
NC 2021 | SHS | NCR | Valenzuela City | 305440 | Lawang Bato National High School | CITY OF VALENZUELA | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 711229.8305 | 709456.19 | 696652.75 | completed | 1 | 2021-10-26 |  | P00575494LZ | 21OD0203 |  |  | 2021-07-28 |  | 2021-09-27 | C.L. Morales Const & Trading
NC 2021 | SHS | NCR | Valenzuela City |  | SHS IN ARKONG BATO, VALENZUELA | CITY OF VALENZUELA | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2005000 | 2000000 | 1961127.65 | completed | 1 | 2021-11-25 |  | P00575495LZ | 21OD0208 |  |  | 2021-08-04 |  | 2021-09-27 | J. Simeon Construction
NC 2021 | K10 | NCR | Valenzuela City | 136823 | Constantino ES | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 781950 | 780000 | 768429.01 | completed | 1 | 2021-10-26 |  | P00575496LZ | 21OD0205 |  |  | 2021-08-04 |  | 2021-09-27 | Carry On Const
NC 2021 | K10 | NCR | Valenzuela City | 136825 | Marulas Central School | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 516396.7123 | 515108.94 | 504747.74 | completed | 1 | 2021-10-26 |  | P00575492LZ | 21OD0225 |  |  | 2021-08-23 |  | 2021-09-27 | Flordes Const & Trading
NC 2021 | SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 | 1 | 20 | Construction/Completion (4STY20CL) |  | 3483802.3564 | 3475114.57 | 3935191.55 | completed | 1 | 2022-01-24 |  | P00575498LZ | 21OD0223 |  |  | 2021-08-23 |  | 2021-09-27 | DJB Const
NC 2021 | SHS | NCR | Valenzuela City | 305445 | Caruhatan National High School | CITY OF VALENZUELA | 2 |  | 8 | Construction/Completion (4STY8CL) |  | 1152875 | 1150000 | 1127121.68 | completed | 1 | 2021-10-26 |  | P00575499LZ | 21OD0202 |  |  | 2021-07-28 |  | 2021-09-27 | Carry On Const
NC 2021 | K10 | NCR | Valenzuela City |  | Disiplina Village NHS | CITY OF VALENZUELA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1102750 | 1100000 | 1080261.59 | completed | 1 | 2021-10-26 |  | P00575400LZ | 21OD0201 |  |  | 2021-07-28 |  | 2021-09-27 | Miles Trading & Const
NC 2022 | K10 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of March 16, 2023
NC 2022 | K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 00:00:00 | [9 empty] | - ongoing embankment; - remaining activities, left side stairs and septic vault
NC 2022 | K10 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-08-05 | [9 empty] | Issued Suspension Order No. 1 (60 C.D.) with Contract Time Extension No. 1 (60 C.D.) due to the pending completion of demolition works implemented by the Navotas City DepED
NC 2022 | K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-25 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (93C.D.) due to pending demolition of existing structure by DepEd Issued Time Extension No. 2 (15C.D.) due to limited access to project site
NC 2022 | K10 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | [10 empty] | Completed as of April 01, 2023
NC 2022 | K10 | NCR | Navotas | 136867 | Tangos Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-06-06 | [9 empty] | Ongoing installation of second floor RSB
NC 2022 | K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS | 0 | 1 | 12 | Construction of School Building | 1 |  | 30450937.5 |  | Completed | 1 | 2023-06-06 | [9 empty] | - on going chb laying - 15 columns at grids 1-5 to be poured by Tuesday
NC 2022 | SHS | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-02-06 | [9 empty] | Completed as of January 24, 2023
NC 2022 | SHS | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS | 0 | 1 | 8 | Construction of School Building | 1 |  | 20300625 |  | Completed | 1 | 2023-05-22 | [9 empty] | Issued Suspension Order/Time Extension No. 1 (60 C.D.) to give way to the construction of temporary acess points for entrance and exit of the adjacent school building Issued Suspension Order/Time Extension No. 2 (45 C.D.) due to suspended/unworkable days brought by inclement weather condition
NC 2023 | K10 | NCR | Caloocan City | 223502 | Gabriela Silang ES (Bagong Silang ES - Annex) | KALOOKAN CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29387423.33 | Completed | 1 | 2024-12-07 | 2024-10-01 | P00775063LZ | 23OD0237 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | Dreamworx Builder & Trading Inc.
NC 2023 | K10 | NCR | Caloocan City | 136613 | Maypajo ES | KALOOKAN CITY |  | 1 | 8 |  | Batch 1 | 35457562.5 | 35150000 | 34423890.25 | Ongoing | 0.8 | 2024-10-11 |  | P00775064LZ | 23OD0238 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | Dreamworx Builder & Trading Inc.
NC 2023 | K10 | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY |  | 1 | 8 |  | Batch 1 | 29808562.5 | 29550000 | 28912136.52 | Completed | 1 | 2024-12-06 | 2024-12-11 | P00775065LZ | 23OD0236 | 2023-06-22 |  | 2023-07-11 |  | 2023-08-18 | DSA Prime Builders Corporation
NC 2023 | K10 | NCR | City of San Juan | 136750 | Nicanor C. Ibuna ES | CITY OF SAN JUAN |  | 1 | 16 |  | Batch 1 | 8070000 | 8000000 | 7716515.22 | Completed | 1 | 2023-12-03 | 2024-01-02 | P00775067LZ | 23OB0454 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Aylan Consrtruction & Trading
NC 2023 | K10 | NCR | City of San Juan | 136751 | Pinaglabanan ES | CITY OF SAN JUAN |  | 1 | 4 |  | Batch 1 | 11096250 | 11000000 | 10614195.75 | Completed | 1 | 2024-01-02 | 2024-05-17 | P00775068LZ | 23OB0455 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Sto. Cristo Construction & Trading Inc.
NC 2023 | K10 | NCR | City of San Juan | 136746 | San Juan ES | CITY OF SAN JUAN |  | 1 | 28 |  | Batch 1 | 11096250 | 11000000 | 10615395.14 | Completed | 1 | 2023-12-03 | 2023-11-22 | P00775066LZ | 23OB0456 | 2023-05-29 | 2023-05-26 | 2023-06-20 | 2023-06-27 | 2023-07-06 | Magnificus Builders Inc.
NC 2023 | SHS | NCR | Las Piñas City | 340548 | Las Piñas City National Senior High School - Manuyo Campus | CITY OF LAS PIÑAS |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14549997.85 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775070LZ-CW1 | 23OI0110 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024
NC 2023 | K10 | NCR | Las Piñas City | 136777 | Las Piñas Elementary School Central | CITY OF LAS PIÑAS |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14549991.09 | Completed | 1 | 2024-03-03 | 2024-07-12 | P00775069LZ-CW1 | 23OI0111 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-19 | Dahvez Construction | turn-over on July 12, 2024
NC 2023 | K10 | NCR | Malabon City | 305451 | Tugatog NHS | CITY OF MALABON |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 29384529.47 | Completed | 1 | 2024-06-26 | 2024-07-26 | P00775071-LG-CW1 | 230A0100 | 2023-06-28 | 2023-07-06 | 2023-07-18 |  | 2023-07-31 | AL-REM KONSTRUCT INC. | phase 1 only, Division Engineer will follow up on the documents/data from DPWH.
NC 2023 | SHS | NCR | Mandaluyong City | 305394 | Mataas na Paaralang Neptali A. Gonzales | CITY OF MANDALUYONG |  | 1 | 6 |  | Batch 1 | 33711931.83 | 33419511.11 |  | Not Yet Started | [11 empty] | FOR REALIGNMENT
NC 2023 | K10 | NCR | Manila | 136439 | I. Delos Reyes ES | TONDO |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29096416.08 | Completed | 1 | 2025-02-20 | 2024-09-20 | P00775073LZ | 23OE0231 | 2023-06-13 | 2023-06-22 | 2023-07-13 |  | 2023-07-25 | ROAD EDGE TRADING & DEV'T SERVICES | COMPLETED BUT NOT YET TURN OVER
NC 2023 | K10 | NCR | Manila | 136429 | Librada Avelino ES | TONDO |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29011653.71 | Completed | 1 | 2024-04-19 | 2024-04-19 | P00775074LZ | 23OE0230 | 2023-06-13 | 2023-06-22 | 2023-07-03 | 2023-07-11 | 2023-07-14 | El-Jake Builders | COMPLETED BUT NOT YET TURN OVER
NC 2023 | K10 | NCR | Manila | 136451 | Francisco Balagtas ES | SANTA CRUZ |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29092137.75 | Completed | 1 | 2024-10-15 | 2024-10-15 | P00775075LZ | 23OE232 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | TRILEX BUILDERS AND CONSTRICTION SUPPLY, INC. | COMPLETED BUT NOT YET TURN OVER
NC 2023 | K10 | NCR | Manila | 305304 | Esteban Abada High School | SAMPALOC |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29086575.68 | Completed | 1 | 2024-06-24 | 2024-06-23 | P00775076LZ | 23OE228 | 2023-06-13 | 2024-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | I & E Construction Corp. | COMPLETED
NC 2023 | SHS | NCR | Manila | 305309 | M.Araullo High School | ERMITA |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 | 29415864.41 | Ongoing | 0.67 | 2024-07-23 | 2024-07-23 | 23OH0081 | 23OH0081 | 2023-08-02 |  |  |  |  | RDBT CONST. CORP. | Requested to revise to 6-classroom school building instead of 9-classroom since the allocation is just enough for 6-classroom
NC 2023 | K10 | NCR | Manila | 305317 | Elpidio Quirino High School | SAMPALOC |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29052919.5 | Ongoing | 0.95 | 2025-01-02 | 2024-12-16 | P00775078LZ | 23OE229 | 2023-06-13 | 2023-06-22 | 2023-07-04 | 2023-07-11 | 2023-07-14 | Flordes Construction & Trading Corp. | COMPLETED BUT NOT YET TURN OVER
NC 2023 | SHS | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 28926115.59 | Completed | 1 | 2024-04-03 | 2024-06-28 | P00775079LZ | 23OB0457 | 2023-05-29 | 2023-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Streamline Builders Corp.
NC 2023 | K10 | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA |  | 1 | 32 |  | Batch 1 | 30262500 | 30000000 | 28850946.22 | Not Yet Started | 0 |  |  | P00775080LZ | 23OB0458 | 2023-05-29 | 2323-06-07 | 2023-07-21 | 2023-07-26 | 2023-08-08 | Kai Construction | Work suspended; Application of demolition permit
NC 2023 | K10 | NCR | Muntinlupa City | 228501 | Poblacion Elementary School | CITY OF MUNTINLUPA |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29999999.06 | Completed | 1 | 2024-04-02 | 2024-06-08 | P00775081LZ-CW1 | 230I0112 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-18 | 2023-10-05 | Greenwall Construction | with approved additional 30CD
NC 2023 | K10 | NCR | Navotas | 136865 | Daanghari Elementary School | CITY OF NAVOTAS |  | 1 | 8 |  | Batch 1 | 2017500 | 2000000 | 1958779.07 | Completed | 1 | 2023-09-25 | 2023-12-15 | P00775082LZ | 23OA0090 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation
NC 2023 | K10 | NCR | Navotas | 136858 | Dagat-Dagatan Elementary School | CITY OF NAVOTAS |  | 1 | 12 |  | Batch 1 | 3026250 | 3000000 | 2935041.11 | Completed | 1 | 2023-10-28 | 2023-10-28 | P00775083LZ | 23OA0089 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | C.B. Tampengco Const. & Supply
NC 2023 | SHS | NCR | Navotas | 305456 | Kaunlaran High School | CITY OF NAVOTAS |  | 1 | 8 |  | Batch 1 | 4035000 | 4000000 | 3919257.43 | Completed | 1 | 2023-10-28 | 2024-02-20 | P00775084LZ | 23OA0092 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-31 | Two Dimension Construction | Suspended due to On-Going Construction of Phase 2 Project
NC 2023 | SHS | NCR | Navotas | 305453 | Navotas National High School | CITY OF NAVOTAS |  | 1 | 8 |  | Batch 1 | 1008750 | 1000000 | 982185.24 | Completed | 1 | 2023-08-26 | 2024-07-27 | P00775085LZ | 23OA0091 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation | Suspended due to On-Going Construction of Phase 2 Project
NC 2023 | K10 | NCR | Navotas | 136862 | North Bay Boulevard Elementary School | CITY OF NAVOTAS |  | 1 | 12 |  | Batch 1 | 13113750 | 13000000 | 12727742.97 | Completed | 1 | 2023-12-22 | 2024-02-20 | P00775086LZ | 23OA0097 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-26 | Erish Builders& Supply
NC 2023 | K10 | NCR | Navotas | 136864 | San Rafael Vill. Elementary School | CITY OF NAVOTAS |  | 1 | 8 |  | Batch 1 | 22192500 | 22000000 | 21543817.73 | Completed | 1 | 2024-02-25 | 2024-03-26 | P00775087LZ | 23OA0096 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-31 | MRBll Construction Corporation
NC 2023 | K10 | NCR | Navotas | 136866 | San Roque Elementary School | CITY OF NAVOTAS |  | 1 | 8 |  | Batch 1 | 22192500 | 22000000 | 21509297.96 | Completed | 1 | 2024-02-22 | 2024-02-22 | P00775088LZ | 23OA0095 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-07-28 | T.M. Abad Const. Corporation
NC 2023 | K10 | NCR | Navotas | 136868 | Tangos I Elementary School | CITY OF NAVOTAS |  | 1 | 12 |  | Batch 1 | 13113750 | 13000000 | 12727513.81 | Ongoing | 0.95 | 2023-12-23 | 2024-07-27 | P00775089LZ | 23OA0093 | 2023-06-21 | 2023-06-21 | 2023-06-29 | 2023-07-25 | 2023-08-27 | Justbilt Builders | Suspended due to On-Going Construction of Phase 2 Project
NC 2023 | K10 | NCR | Navotas | 136869 | Tanza Elementary School | CITY OF NAVOTAS |  | 1 | 12 |  | Batch 1 | 33288750 | 33000000 | 32319015.9 | Completed | 1 | 2024-03-26 | 2024-03-26 | P00775090LZ | 23OA0094 | 2023-06-29 | 2023-06-21 | 2023-07-19 | 2023-07-25 | 2023-07-31 | B. Bernardo Construction Inc.
NC 2023 | K10 | NCR | Navotas | 136870 | Wawa Elementary School | CITY OF NAVOTAS |  | 1 | 20 |  | Batch 1 | 30262500 | 30000000 | 29385432.95 | Completed | 1 | 2024-07-27 | 2024-07-27 | P00775091LZ | 23OA0101 | 2023-06-21 | 2023-06-28 | 2023-06-29 | 2023-07-28 | 2023-07-26 | P7 Builders Inc.
NC 2023 | K10 | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9798127.34 | Completed | 1 | 2024-04-15 | 2024-04-15 | P00775092LZ | 23OC0119 | 2023-10-05 | 2023-10-13 | 2023-10-25 |  | 2023-12-18 | J.S. Rabano Construction and Supply Inc. | Suspended December 29, 2023 due to revision of plan
NC 2023 | K10 | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE |  | 1 | 4 |  | Batch 1 | 20175000 | 20000000 | 19600930.96 | Completed | 1 | 2024-05-15 | 2024-05-15 | P00775093LZ | 23OC0120 | 2023-10-06 | 2023-10-14 | 2023-10-26 |  | 2023-12-18 | AARCON Builders | Suspended dated December 29, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building
NC 2023 | K10 | NCR | Paranaque City | 136759 | San Antonio Elementary School | CITY OF PARAÑAQUE |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 29400545.83 | Ongoing | 0.95 | 2024-07-14 | 2024-07-14 | P00775094LZ | 23OC0121 | 2023-10-07 | 2023-10-15 | 2023-10-27 |  | 2023-12-18 | GRAC-TA Builders | Suspended December 18, 2023 due to pending issuance of demolition and building permit from the Local Government of Parañaque City and ongoing coordination with the DepEd regarding the demolition of existing building.
NC 2023 | K10 | NCR | Pasay City | 136599 | Marcela Marcelo ES | PASAY CITY |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29370451.32 | Completed | 1 |  | 2024-06-30 | 230H0084 | 230H0084 | 2023-07-24 | 2023-08-03 | 2023-08-15 |  |  | ST. GABRIEL BUILDERS / LCRUZ CONSTRUCTION (JV) | complete
NC 2023 | SHS | NCR | Pasig City | 305422 | Rizal Experimental Station And Pilot School for Cottage Industries (RESPSCI) | CITY OF PASIG |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29999743.52 | Completed | 1 | 2024-04-15 | 2024-05-24 | P00775096LZ | 23OB0460 | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-14 | Magnificus Builders Inc.
NC 2023 | SHS | NCR | Pasig City | 305413 | Rizal High School | CITY OF PASIG |  | 1 | 28 |  | Batch 3 | 175000000 | 168875000 | 168875000 | Ongoing | 0.35 | 2025-10-22 |  |  | 23OB0498 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | Prudent Diamond Square Construction Co.
NC 2023 | K10 | NCR | Quezon City | 136490 | Balingasa Elementary School | QUEZON CITY |  | 1 | 12 |  | Batch 1 | 33711931.83 | 33419511.11 | 33054465.68 | Not Yet Started |  |  |  | P00775097LZ-CW1 | 23OF0149 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION (JOINT VENTURE) | Waiting for the issuance of Demolition Permit for the existing school building and the approval from QC-LGU to demolish the buildig (Brgy. Day Care) located at the frontage of the school / waiting for the data from DPWH / Construction of 4STY 8CL
NC 2023 | SHS | NCR | Quezon City | 340694 | Lucresia Kasilag Senior High School (SHS within E. Abada ES) | QUEZON CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29802912.39 | Completed | 1 | 2024-08-30 | 2024-08-30 | P00775099LZ-CW1 | 23OF0151 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | AYANA CONSTRUCTION AND TRADING | waiting for the data from DPWH
NC 2023 | K10 | NCR | Quezon City | 136493 | San Jose Elementary School | QUEZON CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29803158.14 | Completed | 1 | 2024-11-15 | 2024-11-15 | P00775098LW-CW1 | 23OF0150 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | WAY MAKER GENERAL CONTRACTOR OPC. | waiting for the data from DPWH
NC 2023 | K10 | NCR | Quezon City | 305337 | Justice Cecilia Muñoz Palma High School | QUEZON CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29851396.56 | Completed | 0.9 | 2024-12-12 |  | P00775100LW-CW1 | 23OF0152 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | R. ROSE CONSTRUCTION SERVICES | waiting for the data from DPWH
NC 2023 | SHS | NCR | Quezon City | 305352 | Juan Sumulong High School | QUEZON CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29549992.78 | Ongoing | 0.75 | 2025-01-21 |  |  | 23-OG-0112 | 2023-12-02 |  |  |  |  | WAY MAKER GENERAL CONTRACTOR OPC. | 4 Sty 4 Cl with Repair/Rehab of 2 Sty Imelda BLDG & Site Dev, Division Engineer will follow up on the documents/data from DPWH.
NC 2023 | K10 | NCR | Quezon City | 136585 | Diosdado P. Macapagal ES (Tatalon ES) | QUEZON CITY |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29909975.54 | Completed | 1 | 2025-01-03 |  |  | 23-OG-0110 | 2023-12-02 |  |  |  |  | FRAMECON BUILDERS | Phase 1 - 3Sty 6Cl (6 Cl completed), Division Engineer will follow up on the documents/data from DPWH.
NC 2023 | SHS | NCR | Quezon City | 360867 | Leandro Locsin Integrated School | QUEZON CITY |  | 1 | 0 |  | Batch 1 | 10087500 | 10000000 | 9910245.7 | Not Yet Started |  |  |  |  | 23OF0156 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | 10 BUILDERS AND DEVELOPMENT CORPORATION | Proposed 4Storey 4 Classrooms. waiting to commence once the 4sty-16cl is completed, Division Engineer will follow up on the documents/data from DPWH.
NC 2023 | K10 | NCR | Quezon City | 305338 | Maligaya HS | QUEZON CITY |  | 1 | 0 |  | Batch 1 | 5043750 | 5000000 |  | Not Yet Started |  |  |  |  | 23OF0153 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | FRAMECON BUILDERS | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building
NC 2023 | SHS | NCR | Quezon City | 305341 | San Bartolome HS | QUEZON CITY |  | 1 | 0 |  | Batch 1 | 10087500 | 10000000 |  | Not Yet Started |  |  |  |  | 23OF0154 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | CG GENERAL CONSTRUCTION & DEVELOPMENT CORPORATION | UNIMPLEMENTABLE. For Reversion of Fund for Rehabilitation/Repair of School Building
NC 2023 | K10 | NCR | Quezon City | 305635 | West Fairview High School | QUEZON CITY |  | 1 | 0 |  | Batch 1 | 5043750 | 5000000 | 4975914 | Completed | 1 | 2024-02-22 | 2024-02-22 | P00775105LW-CW1 | 23OF0155 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION | Construction of 3STY 2CL, waiting for the data from DPWH
NC 2023 | K10 | NCR | Quezon City | 305344 | Sauyo HS | QUEZON CITY |  | 1 | 10 |  | Batch 1 | 30262500 | 30000000 | 29849908.6 | Ongoing | 0.4 | 2024-09-18 |  |  | 23OF0163 | 2023-06-07 | 2023-06-15 | 2023-06-27 | 2023-06-30 | 2024-07-06 | MILES TRADING AND CONSTRUCTION | Division Engineer will follow up on the documents/data from DPWH.
NC 2023 | K10 | NCR | Taguig | 136893 | Capt. Hipolito Francisco Elementary School - Main | PATEROS |  | 1 | 8 |  | Batch 1 | 10087500 | 10000000 | 9886489.56 | Completed | 1 | 2024-04-10 | 2024-04-18 | P00775108LZ | 23OB0484 | 2023-12-07 | 2023-12-15 | 2023-12-28 | 2023-12-29 | 2024-01-12 | B. Valencerina Trading and Construction | completed
NC 2023 | SHS | NCR | Taguig | 320601 | Taguig Science High School | TAGUIG CITY |  | 1 | 12 |  | Batch 1 | 20175000 | 20000000 | 18996358.85 | Ongoing | 0.95 | 2024-01-18 |  | P00775109LZ | 23OB0461 | 2023-07-10 | 2023-07-19 | 2023-08-01 | 2023-08-08 | 2023-08-15 | TWENTYSIX CONSTRUCTION INC. | DPWH Issued contract time extension and imposed liquidated damages.
NC 2023 | K10 | NCR | Taguig | 502057 | Bagong Tanyag Integrated School | TAGUIG CITY |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 | 29644438.12 | Ongoing | 0.95 | 2024-08-05 |  | P00775110LZ | 23OB0468 | 2023-12-08 | 2023-12-08 | 2023-12-29 | 2023-12-29 | 2024-01-09 | B. Bernardo Construction Inc. | For punchlist
NC 2023 | K10 | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 | 12 |  | Batch 1 | 32280000 | 32000000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Phase 1 only, for final inspection of DepEd
NC 2023 | K10 | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA |  | 1 | 8 |  | Batch 1 | 29657250 | 29400000 | 28782907.95 | Completed | 1 | 2024-04-11 |  | P00775112LZ | 23OD0235 | 2023-06-22 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-08-16 | Rworkmate Construction | Turn Over to School
NC 2024 |  | NCR | Caloocan City | 136625 | Baesa ES | KALOOKAN CITY |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19738193.69 | Ongoing | 0.32 | 2025-01-25 |  | P00875001LZ | 24OD0292 | 2024-06-20 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-07-29 | FRAMECON BUILDERS
NC 2024 |  | NCR | Caloocan City | 319707 | Caloocan City Business High School | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39398654.98 | Ongoing | 0.57 | 2025-05-25 |  | P00875002LZ | 24OD0291 | 2024-06-20 | 2024-06-28 | 2024-07-10 | 2024-07-22 | 2024-07-29 | WAWAO BUILDERS
NC 2024 |  | NCR | Caloocan City | 319705 | Maypajo High School | KALOOKAN CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39167469.39 | Ongoing | 0.2 | 2025-04-16 |  | P00875003LZ | 24OD0295 | 2024-07-11 | 2024-07-18 | 2024-08-01 | 2024-08-13 | 2024-08-19 | ED1SON DEVELOPMENT & CONSTRUCTION INC./TWENTYSIX CONSTRUCTION INC.
NC 2024 |  | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY |  | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 2500000 |  | 2447832.87 | Ongoing | 0.96 | 2024-10-27 |  | P00875789LZ | 24OD0285 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | TM ABAD CONSTRUCTION CORP.
NC 2024 |  | NCR | Caloocan City | 136632 | Amparo ES | KALOOKAN CITY |  |  | 8 | Completion of 4STY8CL | BATCH 1 | 2500000 |  | 2460814.81 | Ongoing | 0.96 | 2024-10-27 |  | P00875790LZ | 24OD0289 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | TM ABAD CONSTRUCTION CORP.
NC 2024 |  | NCR | Caloocan City | 136617 | Caloocan Central Elementary School | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44106806.77 | Ongoing | 0.22 | 2025-07-14 |  | P00875788LZ | 24OD0297 | 2024-08-17 | 2024-08-27 | 2024-09-05 | 2024-09-11 | 2024-09-17 | STRUKTURA TEKNIKA SERVICES CO.
NC 2024 |  | NCR | Caloocan City | 500330 | Tandang Sora IS | KALOOKAN CITY |  | 1 | 12 | Completion of 4STY12CL | BATCH 1 | 19998569.25 |  | 19595766.82 | Ongoing | 0.5 | 2025-01-25 |  | P00875791LZ | 24OD0288 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | AYLAN CONSTRUCTION & TRADING
NC 2024 |  | NCR | Caloocan City | 136637 | Horacio dela Costa ES | KALOOKAN CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38954849.56 | Not Yet Started | 0 | 2025-03-26 |  | P00875004LZ | 24OD0286 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-07-22 | 2024-07-29 | MILES TRADING AND CONSTRUCTION/OSCORD BUILDERS CORPORATION | Permit to Demolish on Process
NC 2024 |  | NCR | Caloocan City | 136644 | Manuel L. Quezon ES | KALOOKAN CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 45050000 |  | 44083387.04 | Ongoing | 0.4 | 2025-07-14 |  | P00875792LZ | 24OD0298 | 2024-08-17 | 2024-08-27 | 2024-09-05 | 2024-09-11 | 2024-09-17 | DIADEMA CONSTRUCTION AND ENTERPRISES INC.
NC 2024 |  | NCR | Las Piñas City | 136774 | Daniel Fajardo Elementary School | CITY OF LAS PIÑAS |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | FOR REVERSION | Not Yet Started | [11 empty] | cancelled, limited right of way
NC 2024 |  | NCR | Las Piñas City | 136776 | Ilaya Elementary School | CITY OF LAS PIÑAS |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19502329.68 | Not Yet Started | 0 | 2025-07-23 |  | P00875008LZ-CW1 | 24OI0160 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls
NC 2024 |  | NCR | Las Piñas City | 320304 | Las Piñas City National Science High School | CITY OF LAS PIÑAS |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19500175.61 | Not Yet Started | 0 | 2025-07-23 |  | P00875007LZ-CW1 | 24OI0159 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls
NC 2024 |  | NCR | Las Piñas City | 136779 | Pulanlupa Elementary School | CITY OF LAS PIÑAS |  | 1 | 4 | 4STY4CL | GAA 17B | 20000000 |  | 19501674.69 | Not Yet Started | 0 | 2025-07-23 |  | P00875006LZ-CW1 | 24OI0161 | 2024-12-26 |  | 2025-08-01 | 2025-12-02 | 2025-02-21 | Dahvez Construction | Awarded (waiting for approval of building permit), Approved modification of the project from 3stry6cls to 4stry4cls
NC 2024 |  | NCR | Malabon City | 302387 | Malabon City Techvoc and Entrepreneurship Senior High School (CMPI Campus) | CITY OF MALABON |  | 1 | 8 | 4STY8CL (Phase 1) | GAA 17B | 40000000 |  | 38991692.17 | Ongoing | 0.58 | 2025-06-21 |  |  | 24OA0091 | 2024-09-21 | 2024-09-21 | 2024-10-11 | 2024-10-15 | 2024-10-25 | Rotaflex Construction and Development Corp.
NC 2024 |  | NCR | Malabon City | 136836 | Ninoy Aquino ES | CITY OF MALABON |  | 1 | 8 | 4STY8CL | BATCH 1 | 44000000 |  | 29384529.47 | Not Yet Started | 0 | 2025-01-13 |  | P00875793LZ | 24OA0086 | 2024-03-27 |  | 2025-04-16 |  | 2024-05-07 | C.B. Tampengco Construction and Supply | Waiting for demolition permit
NC 2024 |  | NCR | Mandaluyong City | 500335 | Ilaya Barangka Integrated School | CITY OF MANDALUYONG |  | 1 |  | Multi-Storey School Building (Phase 2) | GAA 17B | 40000000 |  | 39800000 | Ongoing | 0.5 | 2026-01-06 |  |  | 24OB0495 | 2024-03-26 |  | 2024-04-17 | 2024-04-24 | 2024-08-05 |  | part of phase 1 construction of 7 storey 28 classrooms
NC 2024 |  | NCR | Manila | 136436 | A. V. Hernandez Elementary School | TONDO |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38971545.94 | Ongoing | 0.65 |  |  | P00875011LZ | 24OE0186 | 2024-03-08 | 2024-03-01 | 2024-04-30 | 2024-05-07 | 2024-05-09
NC 2024 |  | NCR | Manila | 305295 | Lakan Dula High School | TONDO |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38935353.14 | Ongoing | 0.8 | 2025-03-25 | 2025-03-25 | P00875012LZ | 24OE0185 | 2024-03-08 | 2024-03-01 | 2024-04-16 | 2024-04-22 | 2024-04-25
NC 2024 |  | NCR | Manila | 136450 | Antonio Regidor Elementary School | SANTA CRUZ |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38956893.27 | Ongoing | 0.45 |  |  | P00875013LZ | 24OE0187 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17
NC 2024 |  | NCR | Manila | 305307 | Claro M. Recto High School | SAMPALOC |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38953493.53 | Ongoing | 0.95 | 2025-03-24 | 2025-03-14 | P00875014LZ | 24OE0183 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17 |  | for final inspection and punchlisting
NC 2024 |  | NCR | Manila | 136473 | Justo Lukban Elementary School | PACO |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  | 39345960.41 | Ongoing | 0.2 | 2025-11-26 |  | 24OH0148 | 24OH0148 | 2024-11-29 | 2025-12-12 | 2024-12-19 | 2024-12-31 | 2025-01-28
NC 2024 |  | NCR | Manila | 136454 | Geronimo Santiago Elementary School | SAN MIGUEL |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  | 38976244.56 | Ongoing | 0.3 |  |  | P00875016LZ | 24OE0184 | 2024-03-08 | 2024-03-01 | 2024-04-02 | 2024-04-11 | 2024-04-17
NC 2024 |  | NCR | Marikina City | 305402 | Malanday National High School | CITY OF MARIKINA |  | 1 | 8 | Completion of 4STY8CL with covered roof deck | GAA 17B | 30000000 |  |  | Ongoing | 0.6 |  |  | 24OB0531 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going
NC 2024 |  | NCR | Marikina City | 136678 | San Roque ES | CITY OF MARIKINA |  | 1 | 2 | 2STY2CL | GAA 17B | 10000000 |  |  | Ongoing | 0 |  |  | 24OB0529 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | For Mobilization
NC 2024 |  | NCR | Marikina City | 319905 | San Roque National High School | CITY OF MARIKINA |  | 1 | 6 | 3STY6CL | GAA 17B | 40000000 |  |  | Ongoing | 0.05 |  |  | 24OB0530 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going
NC 2024 |  | NCR | Marikina City | 305399 | Tañong HS | CITY OF MARIKINA |  | 1 | 16 | 3STY6CL | GAA 17B | 40000000 |  |  | Ongoing | 0.05 |  |  | 24OB0534 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going
NC 2024 |  | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA |  | 1 |  | Completion of 5STY30CL | GAA 17B | 75000000 |  |  | Ongoing | 0.05 |  |  | 24OB0535 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going
NC 2024 |  | NCR | Marikina City | 319901 | Nangka HS | CITY OF MARIKINA |  |  | 12 | 4STY12CL | GAA 17B | 80000000 |  |  | Ongoing | 0.1 |  |  | 24OB0533 |  |  |  | 2025-01-14 | 2025-11-03 | 2025-03-17 |  | On-going
NC 2024 |  | NCR | Marikina City | 136684 | Parang ES | CITY OF MARIKINA |  | 1 | 32 | 4STY32CL | GAA 17B | 150000000 |  |  | Ongoing | 0 |  |  | 24OB0500 |  |  |  | 2024-08-22 | 2024-08-30 | 2024-10-09 |  | Pending certificate of condemnation
NC 2024 |  | NCR | Marikina City | 305404 | Parang HS | CITY OF MARIKINA |  | 1 | 24 | 4STY24CL with Roofdeck | GAA 17B | 30000000 |  |  | Completed | 1 | 2025-10-04 | 2025-01-04 | 24OB0496 |  |  |  | 2024-04-17 | 2024-05-24 | 2024-04-06
NC 2024 |  | NCR | Muntinlupa City | 305469 | Muntinlupa Science HS | CITY OF MUNTINLUPA |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39001215.57 | Ongoing | 0.95 | 2025-10-06 |  | P00875025LZ-CW1 | 24OI0153 | 2024-05-28 | 2024-05-07 | 2024-07-18 | 2024-02-08 | 2024-12-08 | REDCAR TRADING AND CONSTRUCTION
NC 2024 |  | NCR | Navotas | 305458 | San Roque National High School | CITY OF NAVOTAS |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38984013.3 | Ongoing | 0.31 | 2025-10-24 |  | 24OA0092 | 24OA0092 | 2024-09-21 | 2024-09-27 | 2024-11-10 | 2024-10-18 | 2024-10-25 | STRUKTURA TEKNIKA SERVICES CO. | On-going
NC 2024 |  | NCR | Paranaque City | 136767 | Baclaran Elementary School Central | CITY OF PARAÑAQUE |  | 1 |  | 3-Storey School Building | GAA 17B | 20000000 |  | 9850892.19 | Ongoing | 0.15 | 2025-01-06 |  | P00875027LZ-CW1 | 240CO141 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01
NC 2024 |  | NCR | Paranaque City | 136754 | La Huerta Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4-Storey School Building (Phase 2) | GAA 17B | 10000000 |  | 9799081.22 | Ongoing | 0.6 | 2025-01-06 |  | P00875028LZ-CW1 | 240CO14 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01
NC 2024 |  | NCR | Paranaque City | 136765 | Sto. Niño Elementary School | CITY OF PARAÑAQUE |  | 1 |  | 4-Storey School Building with Ancillary (Phase 2) | GAA 17B | 10000000 |  | 19600545.56 | Ongoing | 0.4 | 2025-10-09 |  | P00875029LZ-CW1 | 240CO139 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01
NC 2024 |  | NCR | Paranaque City | 137129 | Don Bosco Elementary School | CITY OF PARAÑAQUE |  | 1 | 12 | 4STY12CL with Roofdeck | GAA 17B | 40000000 |  | 39400750.05 | Ongoing | 0.4 | 2025-09-29 |  | P00875030LZ-CW1 | 240CO140 | 2024-11-26 | 2024-03-12 | 2024-12-16 | 2024-12-26 | 2025-02-01
NC 2024 |  | NCR | Pasay City | 136590 | Apelo Cruz ES | PASAY CITY |  | 1 | 6 | 4STY6CL | GAA 17B | 40000000 |  | 39171336.73 | Ongoing | 0.22 | 2025-11-16 |  | Project ID No. 240H0122 | Contract ID No. 240H0122 | 2024-11-10 | 2024-10-31 | 2024-10-31 | 2024-12-31 | 2025-04-02 | ALE BUILDERS CONST. & DEVT. CORP
NC 2024 |  | NCR | Pasig City | 305420 | Sta. Lucia High School | CITY OF PASIG |  | 1 | 3 | 4STY8CL (Phase 1 3STY3CL) | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | [10 empty] | re-scheduled procurement activities
NC 2024 |  | NCR | Quezon City | 305321 | Judge Juan Luna HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39517388.5 | Ongoing | 0.5 |  |  |  | 24OF0168 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-23 | 2024-04-29 | FRAMECON BUILDERS | Demolition Ongoing
NC 2024 |  | NCR | Quezon City | 319501 | Holy Spirit National High School | QUEZON CITY |  | 1 | 12 | Completion of 4STY8CL | BATCH 1 | 3000000 |  | 2995001.99 | Completed | 1 | 2024-10-16 |  |  | 24OF0203 | 2024-05-17 | 2024-05-24 | 2024-05-06 | 2024-06-13 | 2024-06-19 | ALTIUS CONSTRUCTION AND TRADING
NC 2024 |  | NCR | Quezon City | 136549 | Raymundo Punongbayan ES | QUEZON CITY |  | 1 | 10 | 2STY10CL | GAA 17B | 40000000 |  |  | Ongoing | 0.15 | [10 empty] | Demolition Ongoing
NC 2024 |  | NCR | Quezon City | 136566 | 15th Avenue Elementary School | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39787695.03 | Ongoing | 0.25 | 2025-08-27 |  |  | 24-OG-0107 |  |  | 2024-03-04 |  | 2024-04-26
NC 2024 |  | NCR | Quezon City | 305362 | Dr. Josefa Jara Martinez HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 39680323.22 | Ongoing | 0.9 | 2025-12-04 |  |  | 24-OG-0106 |  |  | 2024-03-20 |  | 2024-04-26 | FRAMECON BUILDERS
NC 2024 |  | NCR | Quezon City | 319504 | Dona Rosario HS | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | [10 empty] | Ongoing Redesigning of Structural Foundation
NC 2024 |  | NCR | Quezon City | 136533 | Kaligayahan ES | QUEZON CITY |  | 1 |  | 2-Storey School Building | GAA 17B | 10000000 |  | 9868853.6 | Ongoing | 0.85 |  |  |  | 24OF0150 | 2024-03-27 | 2024-04-04 | 2024-04-24 | 2024-04-22 | 2024-04-29 | FRAMECON BUILDERS
NC 2024 |  | NCR | Quezon City | 360867 | Leandro Locsin Integrated School (SHS in Kaligayahan) | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 72000000 |  | 71538358.5 | Ongoing | 0.5 | 2025-05-15 |  |  | 24OF0176 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | RD8 BUILDERS CORPORATION
NC 2024 |  | NCR | Quezon City | 136536 | Nagkaisang Nayon ES | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 12000000 |  | 11820501.49 | Completed | 1 | 2024-11-16 |  |  | 24OF0173 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | R. ROSE CONSTRUCTION SERVICES
NC 2024 |  | NCR | Quezon City | 136525 | San Bartolome ES | QUEZON CITY |  | 1 | 16 | Completion of 4STY16CL | BATCH 1 | 5000000 |  | 4925150.5 | Completed | 1 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2024 |  | NCR | Quezon City | 136514 | Pasong Tamo ES | QUEZON CITY |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0 | 2024-11-15 |  |  | 24OF0175 | 2024-04-17 | 2024-04-25 | 2024-07-05 | 2024-05-15 | 2024-05-21 | JOJEAN CONSTRUCTION AND DEVELOPMENT CORPORATION | With approved modification and Certificate of Coordination, waiting for approved demolition and revised plan
NC 2024 |  | NCR | Taguig City and Pateros | 500342 | Napindan Integrated School | TAGUIG CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 40000000 |  | 38586354.32 | Ongoing | 0.25 | 2025-07-09 |  | P00875040LZ | 240B0520 | 2024-12-16 | 2024-12-26 | 2025-07-01 | 2025-03-03 | 2025-03-17 | GERCEL CONSTRUCTION & DEVELOPMENT | Phase 1 (2sty 6cl provision for 4sty 12cl)
NC 2024 |  | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 | 12 | 4STY12CL (Phase 2) | GAA 17B | 20000000 |  | 19898880 | Ongoing | 1 | 2025-02-23 |  |  | 24OD0290 | 2024-10-07 | 2024-06-20 | 2024-10-07 | 2024-08-15 | 2024-07-29 | Nova Ventus Construction Inc. | Phase 2
NC 2024 |  | NCR | Valenzuela City |  | Pasolo National High School | CITY OF VALENZUELA |  | 1 | 2 | 1STY2CL Phase 1 of 4STY12CL | GAA 17B | 20000000 |  | 19590117.48 | Ongoing | 0.15 | 2025-05-21 |  |  | 24OD0326 | 2024-12-18 | 2024-11-27 | 2024-12-18 | 2025-01-13 | 2024-12-23 | Nova Ventus Construction Inc. | Phase 1 (1st 2cl)
NC 2024 |  | NCR | Valenzuela City | 136812 | Roberta de Jesus Elementary School | CITY OF VALENZUELA |  | 1 | 8 | 4STY8CL | BATCH 1 | 29550000 |  | 29476125 | Ongoing | 0.45 | 2025-06-15 |  |  | 24OD0287 | 2024-04-06 | 2024-05-15 | 2024-04-06 | 2024-11-07 | 2024-07-29 | Diadema Construction and Enterprises Inc.
NC 2024 |  | NCR | Valenzuela City | 136816 | Apolonia F. Rafael Elementary School | CITY OF VALENZUELA |  | 1 | 16 | 3STY12CL Phase 1 of 4STY16CL | BATCH 1 | 53050000 |  | 52783817.37 | Ongoing | 0.45 | 2025-07-13 |  |  | 24OD0296 | 2024-05-09 | 2024-08-16 | 2024-05-09 | 2024-11-10 | 2024-09-17 | Diadema Construction And Enterprises Inc. | Phase 1
NC 2024 |  | NCR | Valenzuela City | 136827 | Serrano Elementary School | CITY OF VALENZUELA |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39796807.51 | Ongoing | 0.45 | 2025-06-15 |  |  | 24OD0294 | 2024-01-08 | 2024-10-07 | 2024-01-08 | 2024-06-09 | 2024-08-20 | Larsen-Dutcher Constractor Corporation

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.