## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 11, 2025
ELECTRIFICATION 2017 | NIR | Cadiz City | 117569 | Aluyan ES | CADIZ CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1101216.52 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117831 | Ballo ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 327426.32 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117878 | Camandaan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 103109.53 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 185501 | Cara-an ES | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 575339.29 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117883 | Ilan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 375014.12 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 185502 | Mambaog PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 258222.93 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117888 | Mamig Elementary School | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 233902.03 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117866 | Piliopiliohan PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 377135.42 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117891 | Sagumayon PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 77360.33 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Kabankalan City | 117868 | Sampac PS | CITY OF KABANKALAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 201772.03 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180505 | Tugas ES | CITY OF HIMAMAYLAN | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1116889.07 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117202 | Canlupa PS | ISABELA | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263400 | 265174.3 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117258 | Binata-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 536631.35 | 698921.58 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117262 | E. Basa PS | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 699806.92 | 535718.22 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116971 | Macapula ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 629037.28 | 628377.12 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 669838 | 667903.43 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116977 | Payong PS | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 758672.56 | 757285.55 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116979 | Sibucao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 896856.69 | 896003.99 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116983 | Talimagao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349163.74 | 348928.02 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117014 | Taya-o ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 549601.5 | 548807.25 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180518 | Aguinaldo Primary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 723035.78 | 922663.56 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 923210.17 | 722527.62 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117145 | Cabanbanan PS | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835486.41 | 834624.64 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117146 | Cemeco ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 970538.94 | 969541.76 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180508 | MAATOP ELEMENTARY SCHOOL | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 958158.87 | 956847.73 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117155 | Manlawa-an Elementary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 786342.28 | 784935.17 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Sagay City | 117731 | Hamticon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 572834.21 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Sagay City | 117732 | Laon ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 504099.64 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Sagay City | 117701 | Onofre Dela Paz ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 841603.67 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Sagay City | 117702 | Pedro R.Katalbas, Sr. II ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 433936.72 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Sagay City | 184001 | Uychiat ES | SAGAY CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 570050.58 |  | COMPLETED | 1 | 2018-01-18 | 2018-01-25 | 2017-06-01 | 2017-07-01 | October 27-November 20, 2017 | 2017-11-06 | 2017-11-20 | 2017-12-07 | 2017-12-12 | RiSM Builders & Construction Services, Inc. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Bais City | 120084 | Biso PS | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 248776.32 |  | REVERTED | 0 | [11 empty] | FAILED BIDDING NO TAKER | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Bais City | 237501 | Cambayungon ES | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 505185.69 |  | REVERTED | 0 | [11 empty] | FAILED BIDDING NO TAKER | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 487551.32 |  | REVERTED | 0 | [11 empty] | FAILED BIDDING NO TAKER | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Guihulngan City | 120266 | Dadiangao PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 831989.92 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1340772.59 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Guihulngan City | 120255 | Panagtugas PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1355741.1 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Guihulngan City | 120286 | Tominhao PS | CITY OF GUIHULNGAN | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1360645.41 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 189530 | Alagasihan PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 39782.2 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120342 | Barang-barang PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 41069.35 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120350 | Campo-aling ES | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 184157.53 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120523 | Sto. Tomas ES | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 71674.73 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 189521 | Tubod PS | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 52592.75 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Siquijor | 190008 | Cantugbas PS | MARIA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 75845.97 | 75742.97 | COMPLETED | 1 | Dec. 30, 2017 |  |  |  | Oct. 31, 2017 |  | Nov. 6, 2017 | Nov. 9, 2017 | Dec. 15, 2017 | Vanzdarryl Construction Design & Consultancy |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Tanjay City | 234005 | Bulo Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 532231.32 |  | REVERTED | 0 | [11 empty] | contract terminated | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Tanjay City | 120545 | Camuyogan ES | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 481609.38 |  | REVERTED | 0 | [11 empty] | contract terminated | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Tanjay City | 120546 | Canghatap Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349670.02 |  | REVERTED | 0 | [11 empty] | contract terminated | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Tanjay City | 120558 | Mato-Bato Elementary School | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 447814.41 |  | REVERTED | 0 | [11 empty] | contract terminated | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Tanjay City | 322306 | Namonbon HS | CITY OF TANJAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 597036.67 |  | REVERTED | 0 | [11 empty] | contract terminated | ENERGIZATION
ELECTRIFICATION 2018 | NIR | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1243711.98 |  | REVERTED | 0 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | NIR | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1198382.95 |  | REVERTED | 0 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | NIR | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 1183857.74 |  | REVERTED | 0 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1102366.73 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1200557.89 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1043874.29 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | UPGRADING | 1 | 699622.42 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 1099930.86 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 | 1 | UPGRADING | 1 | 684142.75 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | UPGRADING | 1 | 817515.25 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1457684.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1529330.44 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 | 1 | UPGRADING | 2 | 1457684.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | UPGRADING | 1 | 1433253.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | SOLAR PANEL | 1 | 1476567.94 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | UPGRADING | 1 | 1141365.67 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1242920.54 | 1233763.67 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1289994.35 | 1279684.23 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1079432.83 | 1070675.04 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117877 | Calabasahan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 524506.15 | 518045.22 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 735237.11 | 729079.2 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1062593.61 | 1053919.59 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1189719.39 | 1179653.73 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1121839.62 | 1111632.05 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1470360.01 | 1459657.31 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1235574.22 | 1222832.52 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117860 | Inapoy ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1118972.87 | 1107188.35 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117862 | Linao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 610781.59 | 602926.46 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1524238.54 | 1510168.12 | COMPLETED | 1 | September 13,2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1674056.79 | 1661209.91 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117864 | Matama ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 886082.7 | 874897.42 | COMPLETED | 1 | October 23,2018 |  | 2018-018 | 2018-018 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 739363.37 | 730730.71 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117890 | Pacao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 823203.85 | 812381.19 | COMPLETED | 1 | October 23,2018 |  | 2018-016 | 2018-016 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 18,2018 | Double MM Builders |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117867 | Pinaguinpinan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1405408.16 | 1393914.58 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1178458.45 | 1169522.29 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1211309.76 | 1203264.7 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 777804.47 | 771434.8 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 2 | 1125610.39 | 1113766.43 | COMPLETED | 1 | October 30,2018 |  | 2018-017 | 2018-017 | March 21,2018 | March 28,2018 | April 13,2018 | May 15,2018 | June 25,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117894 | Talubangi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1294087.86 | 1283512.02 | COMPLETED | 1 | September 13,2018 |  |  | 2018-012 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 9,2018 | Micro-asia Builders Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1066144.14 | 1058821.3 | COMPLETED | 1 | September 8,2018 |  |  | 2018-010 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1015085.74 | 1006648.06 | COMPLETED | 1 | September 8,2018 |  |  | 2018-009 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 2109898.02 | 2090797.87 | COMPLETED | 1 | September 13, 2018 |  |  | 2018-014 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 8,2018 | Micro-asia Builders Corporation |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 302801 | Tapi NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 1141365.67 | 1132714.04 | COMPLETED | 1 | September 8,2018 |  |  | 2018-011 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Kabankalan City | 117872 | Yanog ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | 1 | 477986.55 | 471075.51 | COMPLETED | 1 | September 8,2018 |  |  | 2018-013 | February 20,2018 | February 28,2018 | March 12,2018 | March 21,2018 | May 4,2018 | Rism Builders and Construction Services Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 5285721.3 | 4974653.02 | COMPLETED | 1 |  |  | 5460136 | 18-09-013 | July 3, 2018 | July 11, 2018 | August 20, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3764775.05 | 3721032.46 | COMPLETED | 1 |  |  | 5460154 | 18-09-014 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3817604.51 | 3788330.6 | COMPLETED | 1 |  |  | 5605695 | 18-10-015 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 | 1 | UPGRADING | 1 | 5241938.17 | 5205258.47 | COMPLETED | 1 |  |  | 5605347 | 18-10-014 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | UPGRADING | 1 | 1274910.45 | 1249959.61 | COMPLETED | 1 |  |  | 5463534 | 18-09-017 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | UPGRADING | 1 | 3382586.69 | 3346741.14 | COMPLETED | 1 |  |  | 5460097 | 18-09-012 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | UPGRADING | 1 | 3817604.51 | 3780045.51 | COMPLETED | 1 |  |  | 5463520 | 18-09-016 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 473564.08 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 | 1 | SOLAR PANEL | 1 | 614377.15 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | UPGRADING | 1 | 5608104.57 | 5180471.84 | COMPLETED | 1 |  |  | 5460162 | 18-09-015 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | UPGRADING | 1 | 3745342.73 | 3461829.73 | COMPLETED | 1 |  |  | 5460063 | 18-09-011 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | UPGRADING | 1 | 2814054.98 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 612976.08 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 180521 | Dung-I ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | UPGRADING | 1 | 4406315.1 | 4372766.4 | COMPLETED | 1 |  |  | 5605736 | 18-10-016 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 875895.2 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1491653.57 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1191398.82 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 302764 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 302766 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1495260.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1496882.15 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 311803 | Sagay NHS-Lopez Jaena Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1170095.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 311802 | Sagay NHS-Rizal Ext. | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1271236.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 | 1 | UPGRADING | 1 | 1225112.25 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | San Carlos City | 117759 | Gigalaman ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1793278.34 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2019 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | San Carlos City | 117761 | Handalago ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1144542.09 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2020 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | San Carlos City | 117778 | Lagha Elementary School - Extension | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 917691.67 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2021 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | San Carlos City | 117797 | Pagbatangan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 3955732.52 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2022 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | San Carlos City | 117798 | Paniagan ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 928296.67 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2023 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | SOLAR PANEL | 1 | 1577032.92 |  | COMPLETED | 1 |  |  | 5294450-2018-BEFF-Electification | 5294450-2018-BEFF-Electification | April 17, 2018 | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-06-04 | ALI Construstion & Supply |  | N | SOLAR
ELECTRIFICATION 2018 | NIR | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1678512.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1226572.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 | 1 | UPGRADING | 1 | 1223049.33 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | UPGRADING | 2 | 4612008.25 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | UPGRADING | 1 | 4097269.85 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bais City | 303216 | Bais City Science NHS | BAIS CITY | 2 | 1 | UPGRADING | 1 | 1627597.61 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | UPGRADING | 1 | 2638984.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | UPGRADING | 1 | 1435064.97 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1877651.65 | 1863296.59 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1499669.73 | 1487208.28 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | UPGRADING | 1 | 2410027.97 | 2393026.79 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120111 | Cabigti-an ES | BASAY | 3 | 1 | UPGRADING | 1 | 1813292.52 | 1768728.41 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | UPGRADING | 1 | 1379975.04 | 1368108.92 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321911 | Abundio Agarpao, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1936621.59 | 1926822.56 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321908 | Antonio M. Lacson, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1725381.18 | 1716527.19 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321907 | Atilano B. Cabangal MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1286681.59 | 1275279.59 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321901 | Banaybanay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2306773.75 | 2290297.1 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321902 | Bayawan City Science HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1428522.8 | 1413910.11 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 4287728.97 | 4258888.02 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303238 | Bugay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2286399.4 | 2267516.46 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120146 | Canabuan PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1572433.82 | 1520756.68 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2168858.4 | 2157882.93 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303227 | Dawis NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2208937.86 | 2190447.83 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120150 | Guintana-an ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1216320.41 | 988325.04 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120153 | Hag-um PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 642505.31 | 435345.98 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2682519.69 | 2639904.02 | COMPLETED | 1 |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303237 | Kalumboyan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1920492.43 | 1905937.13 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120158 | Kangkawit PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1379061.37 | 1369638.42 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120131 | Kasla ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 767286.51 | 670969.06 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321905 | Lapay High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1992340.81 | 1974928.47 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 120159 | Lunoy Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1254280.16 | 1162458.67 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2560876.57 | 2514873.29 | COMPLETED | 1 |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303240 | Manduaw NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2623847.79 | 2582259.02 | COMPLETED | 1 |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321903 | Minaba HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1941999.9 | 1924840.35 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 232003 | Napo ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1260825.01 | 1109689.97 | COMPLETED | 1 |  |  |  |  | 3/13/18 | 3/21/18 | 2018-02-04 | 4/20/18 | 4/26/18 | GC TECH |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303254 | Narra HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1881799.15 | 1872104.64 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303256 | Omod National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1559432.94 | 1551470.34 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321910 | Pagatban HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1892234.94 | 1877816.51 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321906 | San Jose HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1431785.89 | 1417162.97 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303241 | Tabuan PCHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2814862.39 | 2795857.65 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 303242 | Tayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 2662911.37 | 2642161.1 | COMPLETED | 1 |  |  |  |  | 4/18/18 | 4/26/18 | 2018-08-05 | 5/25/18 | 2018-07-06 | SM AND MST CONST'N |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Bayawan City | 321904 | Villasol HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING | 1 | 1464300.14 | 1455818.07 | COMPLETED | 1 |  |  |  |  | 2018-07-06 | 6/15/18 | 6/27/18 | 2018-05-07 | 2018-11-07 | MS CONSTN & MKTG |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Dumaguete City | 303168 | Dumaguete City HS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 1552683.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Dumaguete City | 303169 | RTPM - Dumaguete Science HS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 821230.26 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 1 | 836109.56 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Guihulngan City | 120239 | Busay Elementary School | CITY OF GUIHULNGAN | 1 | 1 | SOLAR PANEL | 1 | 938136.67 |  | REVERTED | 0 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 1657858.69 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 1382422.08 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | 1 | 2259021.5 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Guihulngan City | 120258 | Trinidad ES | CITY OF GUIHULNGAN | 1 | 1 | SOLAR PANEL | 1 | 1866055.02 |  | REVERTED | 0 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | UPGRADING | 1 | 586439.48 | 580894.29 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312949 | Ayungon Science High School | AYUNGON | 1 | 1 | UPGRADING | 1 | 484435.16 | 479852.65 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | UPGRADING | 1 | 627304.52 | 621371.36 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303276 | Tambo National High School | AYUNGON | 1 | 1 | UPGRADING | 2 | 590808.68 | 587371.98 | terminated | 0.32 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 616259.07 | 610118.41 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303229 | Demetrio Alviola NHS - Nalundan Annex | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 457294.38 | 452742 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 2 | 1125370.28 | 1119476.6 | terminated | 0.34 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303251 | Manjuyod National High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 1027398.05 | 1009106.87 | COMPLETED | 1 | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312961 | Manjuyod Science High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 466436.24 | 461791.5 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 | 1 | UPGRADING | 1 | 596480.44 | 588081.49 | COMPLETED | 1 | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303255 | Negros Oriental High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 2 | 643928.75 | 634357.53 | terminated | 0.45 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659054.43 | 652943.57 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 577903.93 | 571012.457 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2 | 1 | UPGRADING | 2 | 637792.52 | 640485.86 | terminated | 0.47 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312924 | Campanun-an Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 576820.9 | 570934.14 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312923 | Canggohob HS | MABINAY | 2 | 1 | UPGRADING | 1 | 479603.42 | 475162.71 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | UPGRADING | 1 | 605633.91 | 599603.8 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312951 | Mabinay Science High School | MABINAY | 2 | 1 | UPGRADING | 1 | 623832.57 | 616712.597 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2 | 1 | UPGRADING | 1 | 471654.73 | 466289.46 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 631634.17 | 624474.947 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 | 1 | UPGRADING | 1 | 663993.05 | 657672.6 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659889.99 | 653772.57 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303278 | Crisostomo O. Retes NHS (Tampi NHS) | SAN JOSE | 2 | 1 | UPGRADING | 1 | 769006.9 | 759164.24 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | UPGRADING | 1 | 566903.28 | 560064.537 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303266 | San Miguel NHS | BACONG | 3 | 1 | UPGRADING | 1 | 778525.78 | 768635.76 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental |  | Antonio B. Alejado MHS (Campus II) | DAUIN | 3 | 1 | UPGRADING | 2 | 516957.6 | 514088.84 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 | 1 | UPGRADING | 2 | 502304.6 | 499512.55 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303224 | Apolinar B. Macias MHS (Casile NHS) | DAUIN | 3 | 1 | UPGRADING | 1 | 674191.81 | 666821.297 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303225 | Dauin NHS | DAUIN | 3 | 1 | UPGRADING | 1 | 694285.21 | 686814.167 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312921 | Froilan A. Alanano MHS | DAUIN | 3 | 1 | UPGRADING | 1 | 541118.53 | 534418.067 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 | 1 | UPGRADING | 1 | 618741.84 | 611657.187 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303206 | Avocado Community High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 549572.35 | 544576 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303250 | Casiano Z. Napigkit NHS (Manalongon NHS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 755011.31 | 745225.04 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 633408.36 | 599043.49 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312932 | Eligio T. Monte De Ramos HS (Milagrosa HS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 642188.83 | 638347.21 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312933 | Kakha High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 569707.8 | 566218.9 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 661279.82 | 655171.5 | terminated | 0.27 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 685131.65 | 675674.96 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312935 | Sta. Catalina Science High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 682615.65 | 678509.1 | terminated | 0.35 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School (Cabangahan HS) | SIATON | 3 | 1 | UPGRADING | 2 | 563035.84 | 559881.45 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | UPGRADING | 2 | 698194.63 | 693171.23 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 | 1 | UPGRADING | 1 | 748699.97 | 740620.75 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | UPGRADING | 1 | 664886.16 | 657899.52 | terminated | 0.92 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312908 | Balugo National High School | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 773368.09 | 763493.11 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 891964.53 | 881506.89 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | 2 | 855825.17 | 850910.43 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 | 1 | UPGRADING | 1 | 651972.91 | 644724.747 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | 1 | 2787612.5 | 2338366.12 | terminated | 0.55 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303303 | Basac National High School | LARENA | 0 | 1 | UPGRADING | 1 | 5937774.35 | 5314986.57 | terminated | 0.45 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303293 | Campalanas National High School | LAZI | 0 | 1 | UPGRADING | 1 | 2636170.21 | 2467591.87 | terminated | 0.75 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 | 1 | UPGRADING | 1 | 3700754.43 | 3399753.16 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303295 | Leon Parami High School | LAZI | 0 | 1 | UPGRADING | 1 | 5722840.8 | 5216947.16 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 120669 | Candaping Elementary School | MARIA | 0 | 1 | UPGRADING | 1 | 2800298.26 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303305 | Catulayan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 2955591.79 | 2788223.92 | terminated | 0.65 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 3067762.82 | 2795296.97 | terminated | 0.8 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 2657032.83 | 2608113.44 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 120694 | Cang-alwang Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 | 1352254.37 | REVERTED | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303298 | San Antonio National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 8550699.35 | 8162560.7 | terminated | 0.8 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1606427.72 | 1353112.32 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 120541 | Alangilan PS | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1170923.34 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Tanjay City | 120543 | Ballacag ES | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1306144.33 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1361578.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 234004 | Mandalamon Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1157207.78 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1848529.77 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1499917.3 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Tanjay City | 303279 | Tanjay Legislated HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 960052.61 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 1463896.74 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 303283 | Tanjay Science HS | CITY OF TANJAY | 2 | 1 | UPGRADING | 1 | 835379.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 120565 | Toyupan Elementary School | CITY OF TANJAY | 2 | 1 | SOLAR PANEL | 2 | 1870833.45 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 665880.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 312911 | Hunop Community High School | PAMPLONA | 2 | 1 | UPGRADING | 1 | 674059.51 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | UPGRADING | 1 | 883293.56 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Tanjay City | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | UPGRADING | 1 | 1027752.07 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 662718.06 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 534638.1 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117498 | J.L. Araneta Elementary School | BAGO CITY | 4 | 1 | UPGRADING | Batch 3 | 500013.26 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117508 | L. De La Rama ES | BAGO CITY | 4 | 1 | UPGRADING |  | 216001.52 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117509 | Lag-asan ES | BAGO CITY | 4 | 1 | UPGRADING |  | 672967.88 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 755636.55 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4 | 1 | UPGRADING |  | 279050.04 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | UPGRADING |  | 332856.69 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3176131.35 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311406 | Burgos National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1402643.61 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1524721.65 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311401 | Caduha-an NHS - Luna Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1409045.19 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311402 | Caduha-an NHS - Tagbanon Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1602136.72 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311404 | Dr. Vicente F. Gustilo Memorial NHS - Daga Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1805687.43 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 4631699.05 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 311407 | V NHS-Sewahon Extension High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 3 | 1610170.12 |  | COMPLETED | 1 | [10 empty] | Energized already | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Cadiz City | 302735 | Villacin National High School | CADIZ CITY | 2 | 1 | UPGRADING | Batch 1 | 3560415.93 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Escalante City | 302595 | Buenavista National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1708168.21 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1484496.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Escalante City | 302627 | Tamlang National High School | CITY OF ESCALANTE | 1 | 1 | UPGRADING |  | 1335649.91 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117832 | Basak ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 628605.53 | 550460.45 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 262470.43 | 260100 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117879 | Candiacap ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 407822.33 | 331508.3 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117882 | Dr. Pablo Torre PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 446008.26 | 370031.25 | COMPLETED | 1 | [9 empty] | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 302794 | Inapoy NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 289754.27 | 287300 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117861 | Kabanyohan Elementary School | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 256850.37 | 253800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 365146.42 | 362300 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117843 | Lorenzo Zayco ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 760560.62 | 665681.84 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117846 | NOAC ELEMENTARY SCHOOL | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 329604.62 | 237776.08 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117889 | Nursery PS | CITY OF KABANKALAN | 6 | 1 | UPGRADING | Batch 3 | 405171.76 | 311542.08 | COMPLETED | 1 | [9 empty] | PAR Builders,Electrical and Construction Supply Corp. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 346562.59 | 343800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 878730.89 | 872600 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117852 | Tagukon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 412868.5 | 409800 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117871 | Tampalon ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 728041.35 | 722700 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | UPGRADING |  | 427403.76 | 424200 | COMPLETED | 1 | November 17, 2019 | [6 empty] | December 18, 2018 | August 13, 2019 | Rism Builders and Construction Services Inc. |  | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | UPGRADING | Batch 1 | 2150211.82 | 1731414 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 2 | 1 | UPGRADING | Batch 1 | 1780753.92 | 2370390.96 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | UPGRADING | Batch 1 | 1708168.21 | 1697812.15 | COMPLETED | 1 | 2019-12-27 | [6 empty] | 2019-08-19 | 2019-08-19 | TMTC Construction and Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | UPGRADING | Batch 1 | 2535306.24 | 1432540 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117690 | Alfredo E. Marañon Sr. ES | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 785518.36 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117724 | Bato Central Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117693 | Bulanon Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 596388.8 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117716 | Gil Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 1436339.2 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117696 | Jose B. Puey Sr. Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2632677.65 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 826799.26 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117721 | Maria Lopez Elementary School | SAGAY CITY | 2 | 1 | UPGRADING |  | 2121705.88 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117700 | Old Sagay Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 2436633.67 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117704 | Raymundo Tupas Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 823050.06 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 343922 | Sagay City Senior High School (Stand Alone) | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 |  |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 311801 | Sagay National High School - Old Sagay Ext. | SAGAY CITY | 2 | 1 | UPGRADING |  | 864251.93 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2 | 1 | UPGRADING | Batch 3 | 767526.91 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 117811 | Bongol ES | SILAY CITY | 3 | 1 | UPGRADING |  | 229262.85 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1105925.8 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3 | 1 | UPGRADING | Batch 3 | 1295636.98 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 117807 | Gov. Emilio Gaston Memorial ES | SILAY CITY | 3 | 1 | UPGRADING |  | 1653365.49 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 117817 | Mambag-id ES | SILAY CITY | 3 | 1 | UPGRADING |  | 404044.74 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3 | 1 | UPGRADING |  | 663530.47 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 120083 | Basak ES | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 626888.75 |  | ONGOING | 0.95 | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 303214 | Dodong Escaño Memorial High School | BAIS CITY | 2 | 1 | UPGRADING |  | 669552.47 |  | ONGOING | 0.95 | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | UPGRADING |  | 702562.43 |  | ONGOING | 0.95 | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | UPGRADING |  | 576229.83 |  | ONGOING | 0.95 | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 323010 | LUCILA C. YARED NATIONAL HIGH SCHOOL | BAIS CITY | 2 | 1 | UPGRADING |  | 587257.24 |  | ONGOING | 0.95 | 2019-11-30 |  | Electrification System Upgrade | BCD-2018-087 | 2018-06-11 | 2018-11-14 | 2018-11-26 | 2019-12-08 | 2019-08-18 | R.R. GADINGAN | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 323012 | Mayor Praxedes P. Villanueva II Memorial High School | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 711104.26 |  | ONGOING | 0.95 | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bais City | 323008 | OKIOT NATIONAL HIGH SCHOOL | BAIS CITY | 2 | 1 | UPGRADING | Batch 3 | 578323.59 |  | ONGOING | 0.95 | 2020-03-05 |  | Electrification System Upgrade | BCD-2020-001 | 2020-01-16 | 2020-01-24 | 2020-05-02 | 2020-02-13 | 2020-12-03 | Double MM Builders | Done inspection of NORECO 1, waiting for their recommendation |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Bayawan City | 120129 | Dita Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1329213.33 | 1321567.26 | COMPLETED | 1 |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Bayawan City | 120160 | Mandu-aw Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1528962.97 | 1519355.67 | COMPLETED | 1 |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Bayawan City | 120161 | Minaba Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | UPGRADING |  | 1417540.05 | 1408664.46 | COMPLETED | 1 |  |  |  | 2019-BEFF-E-001 | 2019-10-24 | 2019-11-05 | 2019-11-16 | 2019-11-21 | 2019-08-09 | H.I.T. Contractors |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Dumaguete City | 303166 | Camanjac National High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 777148.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Dumaguete City | 303170 | Hermenegilda F. Gloria Memorial High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 773014.4 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Dumaguete City | 119939 | West City Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | Batch 1 | 843322.77 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 1031892.17 |  | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 938636.74 |  | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | UPGRADING | Batch 2 | 1156419.11 |  | COMPLETED | 1 | [9 empty] | PAR BUILDERS |  |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 |  | UPGRADING | Batch 3 | 922397.2 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 | 1 | UPGRADING |  | 3988592.91 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303243 | La Libertad Technical-Vocational School | LA LIBERTAD | 1 | 1 | UPGRADING |  | 1863791.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303289 | Tayasan National High School (Main) | TAYASAN | 1 | 1 | UPGRADING | Batch 3 | 694554.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1 |  | UPGRADING | Batch 3 | 604060.01 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303208 | Jantianon National High School | AMLAN (AYUQUITAN) | 2 |  | UPGRADING | Batch 3 | 627950.94 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303234 | Inapoy High School | MABINAY | 2 |  | UPGRADING | Batch 3 | 675652.01 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | UPGRADING | Batch 3 | 910437.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 |  | UPGRADING | Batch 3 | 577473.63 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312901 | Maningcao National High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 551832.88 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312944 | Sibulan Science High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 406268.6 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312918 | Buntod High School | BACONG | 3 |  | UPGRADING | Batch 3 | 639294.81 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312920 | Dauin Science High School | DAUIN | 3 |  | UPGRADING | Batch 3 | 628569.22 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | UPGRADING |  | 1728758.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303264 | Obat High School | SANTA CATALINA | 3 |  | UPGRADING | Batch 3 | 606756.89 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303265 | Sta. Catalina National High School | SANTA CATALINA | 3 | 1 | UPGRADING | Batch 3 | 900675.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 |  | UPGRADING | Batch 3 | 693170.34 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312970 | Caticugan HS | SIATON | 3 |  | UPGRADING | Batch 3 | 597167.29 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312941 | Giligaon High School | SIATON | 3 |  | UPGRADING | Batch 3 | 622658.35 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 |  | UPGRADING | Batch 3 | 608533.6 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | UPGRADING | Batch 3 | 712287.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303268 | Siaton NHS | SIATON | 3 | 1 | UPGRADING |  | 1923841.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312914 | Siaton Science HS | SIATON | 3 |  | UPGRADING | Batch 3 | 558999.52 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303236 | Jose Marie Locsin MHS (Mayabon HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | Batch 3 | 666385.77 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120658 | Enrique Villanueva Central Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | Batch 3 | 291882.27 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 500232 | Cabulihan Integrated School ( Junior & Senior HS) | LARENA | 0 | 1 | UPGRADING |  | 142341.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120659 | Larena Central Elementary School | LARENA | 0 | 1 | UPGRADING |  | 422610.72 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120675 | Kimba Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 228294.34 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120676 | Kinamandagan Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 286904.23 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303294 | Kinamandagan High School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 250257.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120677 | Lazi Central School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 372866.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | UPGRADING |  | 2389150.46 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120705 | San Juan Central School | SAN JUAN | 0 | 1 | UPGRADING |  | 532602.64 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120703 | Ponong Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 224400.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303299 | Ponong High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 234567.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120706 | Siquijor Central Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING |  | 268142.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303281 | Azagra High School | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 813570.41 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1133550.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1194551.99 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | UPGRADING |  | 1478797.42 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 312915 | Inawasan PCHS | PAMPLONA | 2 | 1 | UPGRADING |  | 568874.04 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 | 1 | UPGRADING |  | 690777.83 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | UPGRADING |  | 619053.78 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | UPGRADING |  | 1402437.97 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | UPGRADING |  | 949301.95 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Kabankalan City | 117829 | Badiangay ES | CITY OF KABANKALAN | 6 | 1 |  |  | 996308.04 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 | 1 |  |  | 2918681.94 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Kabankalan City | 117856 | Camansi ES | CITY OF KABANKALAN | 6 | 1 |  |  | 1640793.7 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Kabankalan City | 117849 | Pitgong ES | CITY OF KABANKALAN | 6 | 1 |  |  | 479345.9 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-KABANKALANCITY-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302603 | Calatrava NHS | CALATRAVA | 1 | 1 |  |  | 5349237.01 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302624 | ENRIQUETA MONTILLA DE ESTEBAN MEMORIAL HIGH SCHOOL | PULUPANDAN | 4 | 1 |  |  | 6176278.18 | 6140194.07 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-006 | 20-09-007 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 | 1 |  |  | 4601842.13 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302600 | Bilbao-Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 |  |  | 8670357.39 | 3296807.84 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-004 | 20-09-006 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply | Energized already on OCT |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Sagay City | 117691 | Alfredo E. Maranon Sr. ES- School of the Future | Sagay City | 2 | 1 |  |  | 1193711.9 | 893000 | COMPLETED | 1 | September 16, 2021 | August 21, 2021 | ELEC2020-RVI-SAGAYCITY-001 | 43831 | February 25- March 16, 2020 | 2020-03-03 | 2020-03-16 | 2021-05-31 | 2021-07-16 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Sagay City | 117695 | Buenaventura Rodriguez Elem School | Sagay City | 2 | 1 |  |  | 946032.78 | 793222.9845 | COMPLETED | 1 | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-002 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Sagay City | 117739 | Rufino T. Halipa Sr. Elem School | Sagay City | 2 | 1 |  |  | 662421.31 | 555335.4289 | COMPLETED | 1 | Decemeber 2, 2020 | Decemeber 2, 2020 | ELEC2020-RVI-SAGAYCITY-003 | 43709 | Novmber 21-December 11, 2019 | 2019-11-29 | 2019-12-12 | 2020-09-11 | 2020-10-06 | RISM BUILDERS & CONSTRUCTION SERVICES, INC. |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Silay City | 302780 | Doña Montserrat Lopez Memorial National High School (JHS) | SILAY CITY | 3 | 1 |  |  | 2028763.71 |  | COMPLETED | 1 |  |  | ELEC2020-RVI-SILAYCITY-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Silay City | 117804 | Silay South ES | SILAY CITY | 3 | 1 |  |  | 2266185.32 |  | ONGOING | 0.95 |  |  | ELEC2020-RVI-SILAYCITY-001 | [7 empty] | transformer requirements. As per PO, 100kva single phase Max allowed by COOP for a single phase is only 50kva...for VO as end of January |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Bayawan City | 120107 | Basay Central School | BASAY | 3 | 1 |  |  | 1349567.05 |  | COMPLETED | 1 |  |  | Elec2020-RVII-BAYAWAN-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Bayawan City | 120123 | Bayawan City East Central School | CITY OF BAYAWAN (TULONG) | 3 | 1 |  |  | 4632554.88 |  | COMPLETED | 1 |  |  | Elec2020-RVII-BAYAWAN-001 |  | 2/13/2020 | 2/21/2020 | 2020-04-03 | 2020-11-03 | 2020-11-12 | H.I.T. CPNTRACTORS |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Bayawan City | 120165 | Tayawan Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 |  |  | 1536168.85 |  | COMPLETED | 1 |  |  | Elec2020-RVII-BAYAWAN-004 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Dumaguete City | 119934 | Batinguel Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 774652.63 | 774152.62 | COMPLETED | 1 | 2021-10-29 |  | Elec2020-RVII-DUMAGUETE-005 | Elec2020-RVII-DUMAGUETE-005 | 2020-03-05 | 2020-03-20 | 2020-04-01 | 2020-04-23 | 2021-06-24 | PINS CONSTRUCTION | Energized already but still for final inspection; waiting for the availability of the contractor. |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Dumaguete City | 303167 | Junob National High School | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 831614.36 |  | COMPLETED | 1 |  |  | Elec2020-RVII-DUMAGUETE-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 |  |  | 779998.96 |  | COMPLETED | 1 |  |  | Elec2020-RVII-DUMAGUETE-002 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 | 1 |  |  | 3171684.86 |  | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-024 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 | 1 |  |  | 721415.76 |  | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-017 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 | 1 |  |  | 850816.56 | 764758.06 | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-013 | [5 empty] | 2021-09-02 | Tribata Construction and Development |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Bacolod City | 181005 | Handumanan Elementary School II | BACOLOD CITY (Capital) | Lone | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2179424.96 |  | Under Procurement | 0 | [10 empty] | no subaro yet; issue with the compliance of local cooperative; fund insufficient |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Bago City | 117504 | Bago City Elementary School | BAGO CITY | 4th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3809119.24 |  | Under Procurement | 0 | [10 empty] | no subaro yet; CO awaiting submission of RTA from division office to download subaro |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2nd | 1 | Installation of primary Poles and Service Lines with Transformers and Complete Accessories | 1 | 4175702.24 | 4127265.51 | COMPLETED | 1 | 2025-02-20 |  |  |  | 2024-06-27 | 2024-07-05 | 2024-07-24 | 2024-07-31 | 2024-09-16 | PAR BUILDERS ELECTRICAL AND CONST. SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Escalante City | 117043 | Escalante Central Elementary School | CITY OF ESCALANTE | 1st | 1 | Upgrading of Electrical System | 1 | 3692973.81 | 3508000 | ONGOING | 0.95 | 2025-03-09 |  | Project 02-2024 | Project 02-2024 | 2024-06-29 | 2024-07-08 | 2024-07-19 |  | 2024-10-09 | PAR BUILDERS | Waiting for the Cooperative schedule to energize |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 20047981.78 |  | not yet started | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3233807.07 | 3223059.63 | COMPLETED | 1 | 2025-02-02 | 2025-04-17 | 23-11-33 | 24-09-002 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3416277.7 | 3394508.88 | COMPLETED | 1 | 2025-02-02 | 2025-04-02 | 23-11-30 | 24-08-001 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Sagay City | 302767 | Sagay National High School | SAGAY CITY | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3575492.35 | 2789804.67 | COMPLETED | 1 |  |  | 45352 | 45352 | 2024-07-23 | 2024-07-30 | 2024-08-12 | 2024-09-28 | 2025-01-06 | CAPRICORN GENERAL MERCHANDISING & SERVICES | already downloaded subaro |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1st | 1 | Upgrading of Electrical System | 1 | 2426232.73 | 2370639.42 | ONGOING | 0.98 | 2024-09-12 |  | 2023-10-0094 | 10389058-2023-10-0094 | 2023-12-03 | 2023-12-18 | Decemebr 27, 2023 | 2024-01-18 | 2024-06-07 | 2023 BEFF Upgrading of Electrical System ( Overhead System) | waiting of electric cooperative to energized |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Silay City | 302781 | Brgy. E. Lopez NHS (SHS) | SILAY CITY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3024557.77 | 2975811 | Completed | 1 | 2025-05-06 |  | 2024-07-ELNHS-002 | 2024-C-005 | 2024-06-29 | 2024-07-07 | 2024-07-30 | 2024-08-05 | 2025-01-06 |  |  |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Sipalay City | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3546699.83 |  | Under Procurement | 0 | [10 empty] | CO awaiting submission of RTA from division office to download subaro |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Victorias City | 117447 | Victorias North ES | CITY OF VICTORIAS | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3479568.81 | 2999675.4 | ONGOING | 0.98 | 2025-03-31 |  | SDOVC-INFRA2024-001 | SDOVC-INFRA2024-001 | 2024-07-11 | 2024-07-19 | 2024-07-31 | 2024-08-22 | 2024-08-27 | Nem Construction Supplies and Services | On-going project |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Bayawan City | 120108 | Bongalonan Elementary School | BASAY | 3rd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2362253.92 | 2138763.97 | COMPLETED | 1 | 2024-08-30 |  | 2024-BEFF-ELEC-001 | 2024-BEFF-ELEC-001 | 2023-11-27 | 2024-12-04 | 2024-12-18 | 2024-01-09 | 2024-05-31 | Global Power Equipment Marketing Corporation |  |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Dumaguete City | 119937 | Magsaysay MES | DUMAGUETE CITY (Capital) | 2nd | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 3000000 | 2339992.66 | COMPLETED | 1 | 2024-10-16 |  | 2024-001 | 2024-001 | 2024-03-13 | 2024-04-01 | 2024-04-11 | 2024-04-22 | 2024-07-11 | Global Power Equipment Marketing Corporation | awaiting schedule with the electric cooperative for energization of the transformer |  | ENERGIZATION
ELECTRIFICATION 2024 | NIR | Guihulngan City | 120236 | Bonbon ES | Guihulngan City | 1st | 1 | Off-grid (Solar PV Energy System) | 1 | 7595594.13 |  | not yet started | 0 | [10 empty] | waiting for the lifting of election ban |  | SOLAR
ELECTRIFICATION 2024 | NIR | Siquijor | 120655 | Basac ES | Larena | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2497039.92 | 2068253.96 | COMPLETED | 1 | 2024-08-21 |  | 10336674 | 2023-90 | 2023-11-20 | 2023-11-28 | 2023-12-11 | 2023-12-12 | 2024-05-21 | Global Power Equipment Marketing Corporation | for approval from local cooperative |  | UPGRADING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%