## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | SHS (2014) | NIR | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1 | 2015-12-23 |  | 060614S00239 | 15GC0046 | 2015-07-13 | 2015-07-10 | 2015-07-27 | 2015-08-14 | 2015-08-20 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE
NC 2014 | SHS (2014) | NIR | Bacolod City | 302702 | Barangay Singcang-Airport NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | REVERTED | 0 |  |  | 060614S00200 | 15GC0064 | 2015-09-01 | 2015-09-02 | 2015-09-10 | 2015-09-22 | 2015-09-30
NC 2014 | SHS (2014) | NIR | Bacolod City | 302703 | Bata NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00201 | 15GC0070 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | NIR | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00202 | 15GC0071 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | NIR | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-02-03 |  | 060614S00203 | 15GC0073 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 060614S00205 | 15GC0036 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-03 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00206 | 15GC0068 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00197 | 15GC0072 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | NIR | Bacolod City | 500189 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8439965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00208 | 15GC0065 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2224658.24 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-04 |  | 060614S00221 | 15GC0069 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | JAIME B. CHING ENTERPRISES
NC 2014 | SHS (2014) | NIR | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-03 |  | 060614S00210 | 15GC0074 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 060614S00199 | 15GC0035 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-06 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Bacolod City | 302718 | Teofilo Gensoli, Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-10-01 | 060614S00213 | 15GC0037 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-08-10 | 2015-08-12 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Bais City | 323004 | Cambagahan National HS | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-17 | 070314S00118 | 14HK0020 | 2014-08-07 | 2014-08-22 | 2014-11-17 | 2014-12-09 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 120089 | Cambaguio ES | BAIS CITY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-19 | 070314S00137 | 14HK0018 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 120075 | Cansanag ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-17 | 070314S00124 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 120092 | Lonoy Elementary School | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-15 | 070314S00113 | 14HK0020 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-15 | 2014-12-17 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Bais City | 120095 | Mabunao ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-18 | 070314S00114 | 14HK0018 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Bais City | 120077 | Olympia ES | BAIS CITY | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4593399.6094 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-05-20 | 070314S00197 | 14HK0050 | 2014-12-14 | 2014-12-23 | 2014-12-29 | 2014-12-29 | 2014-12-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | NIR | Bais City | 120103 | Sab-ahan ES | BAIS CITY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-04-16 | 070314S00115 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-16 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bais City | 237502 | Talungon Elementary School | BAIS CITY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 070314S00116 | 14HK0019 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-01 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Bayawan City | 120167 | Uban-uban PS | Bayawan City | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 2 | 1751222.0788 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00189 | 14HL0032 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Bayawan City | 232001 | Baican PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-06-03 | 2015-06-03 | 070314S00112 | 14HL0020 | 2014-11-26 | 2014-12-05 | 2014-12-09 | 2014-12-17 | 2014-12-29 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 990387.4407 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Bayawan City | 120158 | Kangkawit PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 070314S00120 | 14HL0022 | 2014-11-26 | 2014-12-05 | 2014-12-09 | 2014-12-17 | 2014-12-29 | ASCENTIA CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6313739.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Bayawan City | 232003 | Napo ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00126 | 14HL0021 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Bayawan City | 321904 | Villasol NHS | Bayawan City | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 976682.6705 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | REVERTED | 0 |  |  | 060614S00215 | 15GK0107 | 2015-09-09 | 2015-09-11
NC 2014 | SHS (2014) | NIR | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2660828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00216 | 15KG0065 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00217 | 15GK0094 | 2015-08-25 | 2015-08-25 | 2015-09-08 | 2015-09-15 | 2015-09-24 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | NIR | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00218 | 15KG0065 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Cadiz City | 311401 | Caduha-an NHS - Luna Ext. HS | CADIZ CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00171 | 15GK0085 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10927342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1122049.6543 |  |  | COMPLETED | 1 | 2015-12-18 | 2015-12-18 | 060614S00174 | 15GK0085 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | NIR | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2710828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00220
NC 2014 | SHS (2014) | NIR | Cadiz City | 302727 | Sicaba NHS | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2720828.124 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 060614S00196 | 15KG0065 | 2015-07-03 | 2015-07-23 | 2015-07-24 | 2015-08-07 | 2015-08-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00184
NC 2014 | SHS (2014) | NIR | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00185 | 15GK0095 | 2015-08-25 | 2015-08-25 | 2015-09-08 | 2015-09-15 | 2015-09-24 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2690828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Cadiz City | 302735 | Villacin NHS | CADIZ CITY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | REVERTED | 0 |  |  | 060614S00183
NC 2014 | K10 (2014) | NIR | Dumaguete City | 303166 | Camanjac NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 5 | 1STY 2CL & 1STY 3CL | 2014 K10 BATCH 1 | 4965592 |  |  | COMPLETED | 1 | 2015-11-03 |  | 070314S00129 | 15HK0077 | 2014-08-07 | 2014-08-22 | 2014-11-19 | 2014-09-11 | 2014-09-18 | C. LARA CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Dumaguete City | 119945 | Cantil-e ES | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-13 | 070314S00127 | 14HK0012 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Dumaguete City | 119948 | Junob ES | DUMAGUETE CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-01-14 | 070314S00128 | 14HK0012 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-09-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Dumaguete City | 312601 | PIAPI HIGH SCHOOL | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 060614S00224 | 15GK0089 | 2015-08-18 | 2015-08-18 | 2015-09-01 | 2015-09-08 | 2015-09-17 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Escalante City | 325602 | Buenavista NHS - Langub Ext. | CITY OF ESCALANTE | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 060614S00109 | 14GK040 | 2014-09-05 | 2014-10-17 | 2014-12-11 | 2014-12-17 | 2014-12-22 | By Administration
NC 2014 | SHS (2014) | NIR | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 060614S00225 | 15GK0090 | 2015-08-18 | 2015-08-18 | 2015-09-01 | 2015-09-08 | 2015-09-17 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | NIR | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120233 | Antibalas ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | REVERTED | 0 |  |  | 070314S00131 | 070314S00131 | 2014-09-27 | 2014-10-09 | 2014-10-14 | 2014-11-04 | 2014-11-14
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120263 | Balogo ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-08-30 | 2015-08-30 | 070314S00217 | 070314S00217 | 2014-11-28 | 2014-12-19 | 2014-12-22 | 2015-01-22 | 2015-01-27 | GLUBROS DEVELOPMENT INC.
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120236 | Bonbon ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | REVERTED | 0 |  |  | 070314S00132 | 070314S00132 | 2014-09-27 | 2014-10-09 | 2014-10-14 | 2014-11-05 | 2014-11-14 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120240 | Cabal-asan PS | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | REVERTED | 0 |  |  | 070314S00133 | 070314S00133 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | REVERTED | 0 |  |  | 070314S00134 | 070314S00134 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120250 | Lip-o ES | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | REVERTED | 0 |  |  | 070314S00135 | 070314S00135 | 2014-10-30 | 2014-11-06 | 2014-11-12 | 2014-12-02 | 2014-12-18 |  | RECOMMENDATION FOR CONTRACT TERMINATION SUBMITTED TO DPWH REGIONAL OFFICE
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120254 | Matu-og ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4372299.6094 |  |  | COMPLETED | 1 | 2016-03-07 |  | 070314S00210 | 070314S00210 | 2015-07-24 | 2015-08-06 | 2015-08-11 | 2015-09-02 | 2015-09-23 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120281 | Plagatasanon ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2016-05-20 |  | 070314S00216 | 15HJ0167 | 2015-03-23 | 2015-05-19 | 2015-11-03 | 2015-11-20 | 2015-12-01 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2014 | K10 (2014) | NIR | Guihulngan City | 120257 | Sandayao ES | CITY OF GUIHULNGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | REVERTED | 0 |  |  | 070314S00100 | 14HJ0006 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | LAB GENERAL ENGINEERING
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117830 | Balisong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3165174.43 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-02 | 060614S00110 | 14GM0013 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117831 | Ballo PS | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-03 | 060614S00111 | 14GM0014 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302785 | Bantayan NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00238 | 15GM0052 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11177342.5917 |  |  | COMPLETED | 1 |  |  | 060614S00237 | 0606-14-S-00237 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-10
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117833 | Bugtong PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00112 | 14GM0015 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117836 | Carol-an ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3055174.43 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-11-19 | 060614S00123 | 14GM0016 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117839 | D.C.Gurrucharri MS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00114 | 14GM0017 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117881 | Dacongcogon ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00113 | 14GM0027 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117882 | Dr. Pablo Torre PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00090 | 14GM0028 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | By Administration
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00236 | 15GM0053 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117859 | Hilamonan ES | CITY OF KABANKALAN | 6 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4020835.14 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00115 | 14GM0026 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117842 | Hinapunan ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00106 | 14GM0018 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117842 | Hinapunan Integrated School | CITY OF KABANKALAN | 6 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4673392.2448 |  |  | COMPLETED | 1 | 2016-01-04 |  | 060614S00180 | 15GM0044 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Kabankalan City | 302794 | Inapoy NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-02 | 060614S00133 | 14GM0033 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117886 | Lowag ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-10-26 | 2014-10-26 | 060614S00091 | 14GM0029 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | By Administration
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117844 | Mansumbil PS | CITY OF KABANKALAN | 6 | 1 | 2 | 2UNITS 1STY 1CL | 2014 K10 BATCH 1 | 2274658.24 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00116 | 14GM0019 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117846 | NOAC ES | CITY OF KABANKALAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00117 | 14GM0020 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3880805.49 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00118 | 14GM0021 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117848 | Orong ES | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3820805.49 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00119 | 14GM0022 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 3UNITS 1STY 1CL | 2014 K10 BATCH 1 | 3356987.36 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117850 | President Osmena Elementary School | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3222746.69 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00120 | 14GM0023 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117892 | Salong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 060614S00092 | 14GM0030 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ETHAN PROPERTY DEVELOPER
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-05-26 |  | 060614S00235 | 15GM0151 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-23 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117893 | San Jose ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-10-12 | 060614S00093 | 14GM0031 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117851 | SONEDCO ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00121 | 14GM0024 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | 10 | 2STY10CL | 2014 K10 BATCH 4B | 13371310.093 |  |  | COMPLETED | 1 | 2016-04-24 |  | 060614S00170 | 15GM0054 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 | 2016-05-26 |  | 060614S00234 | 15GM0152 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-23 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6539337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 060614S00233 | 15GM0055 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | AQUA DRAGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-20 | 060614S00098 | 14GM0025 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-27 | 2014-07-09 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | NIR | Kabankalan City | 312101 | TAN-AWAN NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-05 |  | 060614S00222 | 15GM0040 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Kabankalan City | 302801 | Tapi National NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 060614S00231 | 15GM0056 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | NIR | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117328 | Bayongbonganan ES | SALVADOR BENEDICTO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-07-18 | 2015-07-31 | 060614S00141 | 14GK028 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302597 | Bug-ang NHS | TOBOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116919 | Cambayobo ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-02 | 2015-05-02 | 060614S00101 | 14GK036 | 2014-09-05 | 2014-10-17 | 2014-12-11 | 2014-12-17 | 2014-12-22 | By Administration
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35596257.14 |  |  | REVERTED | 0 |  |  | 060614S00229 | 15GK0177 | 2015-12-15 | 2015-12-18 | 2015-12-29 | 2015-12-29 |  |  | Reverted, confirm to the DE/DPE
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116902 | Cruz ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-09 | 2015-07-09 | 060614S00122 | 14GK032 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116903 | De La Rosa PS | CALATRAVA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 060614S00097 | 14GK0021 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116904 | Dolis ES | CALATRAVA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 060614S00089 | 14GK0022 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116920 | Ecogan ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 060614S00102 | 14GK031 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180511 | Hipolito Mahilum ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 060614S00107 | 14GK0035 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117332 | Kinabong ES | SALVADOR BENEDICTO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 060614S00064 | 14GK030 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116905 | Laga-an ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-15 | 2015-07-15 | 060614S00099 | 14GK035 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116927 | Malatas ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 060614S00103 | 14GK0027 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116931 | Pantao ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-03 | 2015-07-03 | 060614S00104 | 14GK034 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116913 | San Benito ES | CALATRAVA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 060614S00100 | 14GK0024 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116935 | Sanchez ES | CALATRAVA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 060614S00096 | 14GK0029 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302682 | SOFRONIO CARMONA NHS | SALVADOR BENEDICTO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-08 |  | 060614S00228 | 15GK0077 | 2015-07-16 | 2015-07-21 | 2015-08-04 | 2015-08-14 | 2015-08-26 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116936 | Spur-2 ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 060614S00131 | 14GK037 | 2014-09-05 | 2014-10-17 | 2014-12-11 | 2014-12-17 | 2014-12-22 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117415 | Stop Aguinaldo ES | TOBOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-05-01 | 2015-05-01 | 060614S00144 | 14GK038 | 2014-09-05 | 2014-10-17 | 2014-12-11 | 2014-12-17 | 2014-12-22 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302691 | Tigbao NHS | CALATRAVA | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302691 | TIGBAO NHS | CALATRAVA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116939 | Winaswasan ES | CALATRAVA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 060614S00150 | 14GK033 | 2014-12-12 | 2014-12-17 | 2014-12-23 | 2014-12-23 | 2015-01-15 | By Administration
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302662 | MANAPLA NHS | MANAPLA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-10-31 | 060614S00223 | 15GK0078 | 2015-07-16 | 2015-07-21 | 2015-08-04 | 2015-08-13 | 2015-08-26 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. (FORMERLY RISM DESIGNERs & GEN. MDSE. & ENGG.)
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117287 | Amayco ES | MURCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 060614S00147 | 14GK0043 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117288 | Antawan E/S | MURCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-03 | 2015-05-03 | 060614S00146 | 14GK0044 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180524 | Balasyang Elementary School | MURCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 060614S00125 | 14GK0047 | 2014-09-05 | 2014-10-17 | 2014-10-31 | 2014-11-11 | 2014-11-18 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117289 | Barandiaran ES | MURCIA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-26 | 060614S00142 | 14GK0045 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302697 | Barangay Estado NHS | CITY OF VICTORIAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-01 | 2015-03-01 | 060614S00128 | 14GK0050 | 2014-09-05 | 2014-10-17 | 2014-10-31 | 2014-11-11 | 2014-11-18 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117392 | Cabatangan ES | CITY OF TALISAY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-25 |  | 060614S00173 | 15GK0087 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | J. LEE CONSTRUCTION CORPORATION (FORMERLY: J. LEE
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117021 | Canlusong ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-22 | 2015-03-22 | 060614S00148 | 14GK0041 | 2014-09-05 | 2014-10-17 | 2014-10-31 | 2014-11-11 | 2014-11-18 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00251 | 15GK0096 | 2015-08-25 | 2015-08-25 | 2015-09-08 | 2015-09-15 | 2015-09-24 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117380 | Catabla Baybay Elementary School | CITY OF TALISAY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | REVERTED | 0 |  |  | 060614S00169
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117432 | Gawahon ES | CITY OF VICTORIAS | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 060614S00130 | 14GK0046 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180526 | Hda. Puyas ES | MURCIA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 060614S00126 | 14GK0048 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117282 | Marañon PS | MURCIA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-26 | 060614S00149 | 14GK0042 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 311102 | Minoyan National High School | MURCIA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2014740.174 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 060614S00168 | 15GK0084 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | J. LEE CONSTRUCTION CORPORATION (FORMERLY: J. LEE
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302670 | Murcia NHS | MURCIA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302667 | Negros Occ National Science HS | CITY OF VICTORIAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 060614S00232 | 15GK0099 | 2015-09-01 | 2015-09-01 | 2015-09-15 | 2015-09-22 | 2015-10-01 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117384 | P. Lacson Mora ES | CITY OF TALISAY | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2016-01-25 |  | 060614S00164 | 15GK0087 | 2015-08-10 | 2015-08-13 | 2015-08-27 | 2015-09-07 | 2015-09-15 | J. LEE CONSTRUCTION CORPORATION (FORMERLY: J. LEE
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302611 | CATALINO SOLIGUEN NHS | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-12-07 | 060614S00278 | 15GN0064 | 2015-07-26 | 2015-07-28 | 2015-08-10 | 2015-08-18 | 2015-09-01 | JAIME B. CHING ENTERPRISES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180515 | Gomez PS | PONTEVEDRA | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-12-02 | 060614S00274 | 15GN0063 | 2015-07-26 | 2015-07-28 | 2015-08-10 | 2015-08-19 | 2015-08-28 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117314 | Mabini ES | PONTEVEDRA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-29 | 2014-09-29 | 060614S00275 | 14GN0040 | 2014-07-02 | 2014-07-04 | 2014-07-17 | 2014-07-23 | 2014-07-31 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302685 | San Isidro NHS (Pontevedra) | PONTEVEDRA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-05 |  | 060614S00276 | 15GN0080 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-26 | 2015-09-04 | JAIME B. CHING ENTERPRISES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302686 | Tabao NHS | VALLADOLID | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 060614S00039 | 1GL008M | 2014-08-22 | 2014-08-20 | 2014-09-03 | 2014-09-08 | 2014-09-16 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117066 | Balatogan ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY 1CL & 1STY 2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-20 | 060614S00136 | 14GL049 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302592 | Biao NHS | BINALBAGAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 060614S00124 | 14GL005M | 2014-08-31 | 2014-08-20 | 2014-09-03 | 2014-09-08 | 2014-09-16 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117258 | Binata-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00038 | 14GL035 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-17 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117090 | Bulod ES | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00065 | 14GL027 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117218 | Cabacungan ES | LA CASTELLANA | 5 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-20 | 060614S00010 | 14GL048 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302602 | Cabacungan NHS | LA CASTELLANA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302602 | Cabacungan NHS | LA CASTELLANA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 311103 | Cabacungan NHS - Masulog Ext. | LA CASTELLANA | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117230 | Cabadiangan ES | LA CASTELLANA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 060614S00012 | 14GL007M | 2014-08-22 | 2014-08-20 | 2014-09-03 | 2014-09-08 | 2014-09-16 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117093 | Campayas ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-22 | 060614S00009 | 14GL042 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117070 | Cantupa ES | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-20 | 2014-10-19 | 060614S00137 | 14GL028 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302610 | CARABALAN NHS | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | 060614S00260 | 15GL0069 | 2015-06-22 | 2015-06-24 | 2015-07-07 | 2015-07-13 | 2015-07-20 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117095 | Carmen ES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 060614S00004 | 14GL018 | 2014-06-19 | 2014-06-20 | 2014-07-02 | 2014-08-06 | 2014-08-08 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117071 | Catingib Elementary School | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | 060614S00163 | 15GL0072 | 2015-06-26 | 2015-07-01 | 2015-07-14 | 2015-07-20 | 2015-07-27 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1067049.6543 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | 060614S00172 | 15GL0073 | 2015-07-03 | 2015-07-08 | 2015-07-20 | 2015-07-27 | 2015-08-04 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117232 | Don Felix Robles ES | LA CASTELLANA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00043 | 14GL019 | 2014-06-19 | 2014-06-20 | 2014-07-02 | 2014-07-11 | 2014-07-18 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302674 | Esteban Jalandoni Mem. NHS (Baga-as NHS) | HINIGARAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302674 | Esteban Jalandoni Mem. NHS (Baga-as NHS) | HINIGARAN | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117263 | Guinpana-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-23 | 060614S00166 | 15GL0071 | 2015-06-26 | 2015-07-01 | 2015-07-14 | 2015-07-20 | 2015-07-27 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302647 | Guinpana-an NHS - Mamballo Ext. | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-20 | 060614S00034 | 14GL036 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-16 | 2014-07-22 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302655 | Isabela NHS - Sikatuna Ext. | ISABELA | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00024 | 14GL041 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117234 | Jose Soriano ES | LA CASTELLANA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00042 | 14GL034 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-16 | 2014-07-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-24 | 2015-09-24 | 060614S00167 | 15GL0070 | 2015-06-26 | 2015-07-01 | 2015-07-14 | 2015-07-20 | 2015-07-27 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 311111 | Libacao National High School | CITY OF HIMAMAYLAN | 5 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-09-21 | 2014-09-20 | 060614S00006 | 14GL045 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | SBK CONSTRUCTION SUPPLIES AND SERVICES
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302654 | Libas NHS | ISABELA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-08 |  | 060614S00230 | 15GL0089 | 2015-09-04 | 2015-09-04 | 2015-09-17 | 2015-09-25 | 2015-10-06 | AQUA DRAGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117265 | Macagahay ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00037 | 14GL037 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-17 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117266 | Magallon Cadre ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-22 | 060614S00036 | 14GL038 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-16 | 2014-07-22 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302680 | Mahalang NHS | CITY OF HIMAMAYLAN | 5 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00027 | 14GL047 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116886 | Mangahoycahoy ES | BINALBAGAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00134 | 14GL024 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117236 | Manghanoy Elementary School | LA CASTELLANA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00040 | 14GL020 | 2014-06-19 | 2014-06-20 | 2014-07-02 | 2014-07-11 | 2014-07-18 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117269 | Montilla ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00035 | 14GL039 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-16 | 2014-07-22 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-14 | 060614S00132 | 14GL006M | 2014-08-22 | 2014-08-20 | 2014-09-03 | 2014-09-08 | 2014-09-16 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-20 | 060614S00023 | 14GL044 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116888 | Nasanagan ES | BINALBAGAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00135 | 14GL025 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117082 | Paloypoy ES | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-20 | 2014-09-19 | 060614S00138 | 14GL029 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-10 | 2014-07-17 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 311110 | Paloypoy Integrated School | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 117082 | PALOYPOY INTEGRATED SCHOOL | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302676 | Payao NHS - Namulo Ext. | BINALBAGAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-19 | 2014-09-18 | 060614S00026 | 14GL026 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117135 | Quiwi ES | HINIGARAN | 5 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-09-22 | 2014-09-21 | 060614S00032 | 14GL046 | 2014-06-24 | 2014-06-24 | 2014-07-10 | 2014-07-18 | 2014-07-23 | SBK CONSTRUCTION SUPPLIES AND SERVICES
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302679 | RAYMUNDO T. TONGSON MHS | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-20 | 2015-09-19 | 060614S00258 | 15GL0068 | 2015-06-18 | 2015-06-19 | 2015-07-02 | 2015-07-09 | 2015-07-16 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117273 | Salapid PS | MOISES PADILLA (MAGALLON) | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-22 | 060614S00044 | 14GL040 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-17 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117086 | Sibucao ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2960828.124 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 060614S00165 | 15GL074 | 2015-07-03 | 2015-07-08 | 2015-07-20 | 2015-07-27 | 2015-08-04 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117106 | Sig-ang ES | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-19 | 2014-09-18 | 060614S00003 | 14GL031 | 2014-06-20 | 2014-06-20 | 2014-07-03 | 2014-07-11 | 2014-07-18 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-10-21 | 060614S00095 | 14GL032 | 2014-06-23 | 2014-06-23 | 2014-07-08 | 2014-07-17 | 2014-07-23 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117138 | Arcadio L. Vergara ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-11-12 | 060614S00046 | 14GM0052 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116992 | Baclao ES (Upper Main) | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116941 | Bali ES | CANDONI | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-03 | 2015-08-03 | 060614S00007 | 14GM0085 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117350 | Barangay V ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 060614S00055 | 14GM0055 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116959 | Baslay ES | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00008 | 14GM0072 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180506 | Binotusan PS | CITY OF SIPALAY | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00048 | 14GM0062 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116995 | Bonbon ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00073 | 14GM0044 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-14 | 2015-01-14 | 060614S00080 | 14GM0086 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302601 | Bulwangan NHS - Talacagay Ext. | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117144 | C.L. Hodges ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-12-10 | 060614S00031 | 14GM0087 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117351 | Cabadiangan ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 060614S00066 | 14GM0056 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117145 | Cabanbanan PS | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 060614S00081 | 14GM0088 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117352 | Calangcang ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 060614S00053 | 14GM0057 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117370 | Cambogui-ot ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 060614S00051 | 14GM0059 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116962 | Camindangan ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00022 | 14GM0073 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117354 | Cantaca ES | CITY OF SIPALAY | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 060614S00052 | 14GM0058 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116963 | Cauayan CES | CAUAYAN | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00011 | 14GM0074 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117146 | Cemeco ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-26 | 060614S00082 | 14GM0089 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302614 | Culipapa NHS | HINOBA-AN (ASIA) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117148 | Damutan ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-08 |  | 060614S00083 | 14GM0090 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117151 | Don. M. Vasquez Estate ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00084 | 14GM0091 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180521 | Dung-i ES | CITY OF SIPALAY | 6 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-10-11 | 2015-12-03 | 060614S00047 | 14GM0063 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | AKN CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302634 | Gil Montilla NHS - Binulig Ext. | CITY OF SIPALAY | 6 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | 2016-01-04 |  | 060614S00249 | 15GM0038 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | AJM PROVIDENCE BUILDERS & TRADING INC.
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302636 | Gil Montilla NHS - Camindangan Ext. | CITY OF SIPALAY | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 060614S00248 | 15GM0057 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302638 | Gil Montilla NHS - Cartagena Ext. | CITY OF SIPALAY | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-26 |  | 060614S00247 | 15GM0153 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-23 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302639 | GIL MONTILLA NHS - CROSSING TANDUAY EXT | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-12 |  | 060614S00262 | 15GM0039 | 2015-08-19 | 2015-08-25 | 2015-09-07 | 2015-09-22 | 2015-10-08 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302640 | Gil Montilla NHS - Manlucahoc Ext. | CITY OF SIPALAY | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 060614S00246 | 15GM0058 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116965 | Guiljungan ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00002 | 14GM0075 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | ADP CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302644 | Guiljungan NHS - Talacdan Ext. | CAUAYAN | 6 | 1 | 6 | 1STY6CL | 2014 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 | 2016-01-04 |  | 060614S00245 | 15GM0042 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117177 | Gusnit ES | ILOG | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-12 | 2015-08-12 | 060614S00057 | 14GM0035 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117004 | Langoni ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00074 | 14GM0045 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116969 | Lumbia ES | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00013 | 14GM0076 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116970 | M. Ledesma PS | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060614S00014 | 14GM0077 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180508 | MAATOP ELEMENTARY SCHOOL | HINOBA-AN (ASIA) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1287049.6543 |  |  | REVERTED | 0 |  |  | 060614S00175 | 15GM0043 | 2015-11-29 | 2015-08-25 | 2015-12-01
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116971 | Macapula PS | CAUAYAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00015 | 14GM0078 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117376 | Macarandan ES | CITY OF SIPALAY | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00050 | 14GM0060 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117168 | Magka ES | ILOG | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060614S00062 | 14GM0067 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117169 | Magsaysay ES | ILOG | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00061 | 14GM0068 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116972 | Ma-init PS | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00016 | 14GM0079 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116973 | Maloy-a PS | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00017 | 14GM0080 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117170 | Mambusao ES | ILOG | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-12-20 | 060614S00060 | 14GM0069 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116975 | Man-uling ES | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00018 | 14GM0081 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117006 | Masaling ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00075 | 14GM0046 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-22 | 2014-07-31 | GALENO CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116976 | Molobolo ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060614S00019 | 14GM0082 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 180522 | Omas ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 060614S00076 | 14GM0064 | 2014-06-26 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 060614S00049 | 14GM0061 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | GIMP CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117156 | Payab-on ES | HINOBA-AN (ASIA) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-08-04 | 2015-08-04 | 060614S00085 | 14GM0092 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 060614S00088 | 14GM0047 | 2014-06-27 | 2014-06-27 | 2014-08-05 | 2014-08-15 | 2014-08-27 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 060614S00243 | 15GM0059 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117172 | San Jose Villa ES | ILOG | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060614S00059 | 14GM0070 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117159 | San Rafael ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-03 | 060614S00079 | 14GM0093 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | CELCOR BUILDERS AND EQUIPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116979 | Sibucao ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00020 | 14GM0083 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | SHS (2014) | NIR | Negros Occidental | 302633 | Sipalay CIty National High School | CITY OF SIPALAY | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-24 |  | 060614S00261 | 15GM0060 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117173 | Tabu ES | ILOG | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 060614S00058 | 14GM0071 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117160 | Talacagay PS | HINOBA-AN (ASIA) | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 060614S00063 | 14GM0094 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116981 | Talacdan ES | CAUAYAN | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-12-30 | 060614S00021 | 14GM0084 | 2014-07-08 | 2014-07-08 | 2014-07-23 | 2014-08-01 | 2014-08-08 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116982 | Talangnan PS | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-10 | 060614S00033 | 14GM0037 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116984 | Tambad ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00078 | 14GM0038 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117012 | Tambo E/S | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 060614S00077 | 14GM0048 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | ADP CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117014 | Taya-o ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-28 | 060614S00067 | 14GM0049 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116987 | Tomina ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-06-02 | 2015-06-02 | 060614S00068 | 14GM0039 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116988 | Tumalawas ES | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 060614S00069 | 14GM0040 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116989 | Tuyom ES | CAUAYAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00070 | 14GM0041 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-07-01 | 2014-07-14 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2014 | K10 (2014) | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Occidental | 116990 | Villa Luciana PS | CAUAYAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 060614S00071 | 14GM0042 | 2014-08-22 | 2014-08-20 | 2014-08-26 | 2014-09-02 | 2014-09-08 | By Administration
NC 2014 | K10 (2014) | NIR | Negros Occidental | 117184 | Vista Alegre ES | ILOG | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 060614S00045 | 14GM0036 | 2014-05-28 | 2014-05-28 | 2014-06-11 | 2014-06-30 | 2014-07-09 | VMD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120288 | Aglahug ES | JIMALALUD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00185 | 14HJ0046 | 2015-07-24 | 2015-08-06 | 2015-08-11 | 2015-09-02 | 2015-09-23
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120030 | Amdus ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2016-12-15 | 2015-12-15 | 070314S00125 | 14HJ0040 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-09-04 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120289 | Apanangon ES | JIMALALUD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 |  |  | 070314S00167 | 14HJ0041 | [6 empty] | Recommended for Termination
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120169 | Atotes ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00154 | 14HJ0014 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-08 | 2014-08-20 | GIMP CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2016-01-20 |  | 070314S00123 | 15HJ0071 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-08-26 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303210 | Ayungon National High School | AYUNGON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120578 | Bago ES | TAYASAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 070314S00187 | 14HJ0013 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-27 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120381 | Balaas ES | MANJUYOD | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 070314S00186 | 14HJ0016 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120579 | Banga ES | TAYASAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 |  |  | 070314S00184 | 14HJ0011 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-09-25 | B.C. CUERPO CONSTRUCTION CORPORATION | Included to 2021 Completion/New Construction
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120292 | Banog ES | JIMALALUD | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2634590.4049 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120170 | Batangan ES | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-10-23 | 070314S00111 | 14HJ0039 | 2015-03-29 | 2015-04-23 | 2015-04-29 | 2015-05-25 | 2015-06-26
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120382 | Bolisong ES | MANJUYOD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2820417.57 |  |  | COMPLETED | 1 | 2015-12-22 | 2015-11-27 | 070314S00179 | 15HJ0051 | 2015-03-29 | 2015-04-24 | 2015-04-29 | 2015-05-25 | 2015-06-26 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120201 | Budlasan ES | CANLAON CITY | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3055174.43 |  |  | COMPLETED | 1 | 2016-06-01 |  | 070314S00098 | 15HJ0161 | 2015-06-26 | 2015-07-02 | 2015-11-03 | 2015-11-20 | 2015-12-04 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120172 | Bulod ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00136 | 14HJ0040 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120294 | Cabang ES | JIMALALUD | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2584340.4049 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120173 | Cabcaban ES | BINDOY (PAYABON) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3045174.43 |  |  | COMPLETED | 1 | 2016-02-23 |  | 070314S00099 | 15HJ0073 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-08-26 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120295 | Camandayon ES | JIMALALUD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2130417.57 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-10-23 | 070314S00169 | 15HJ0036 | 2015-03-29 | 2015-04-24 | 2015-04-29 | 2015-05-25 | 2015-06-26 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120176 | Campulay ES | BINDOY (PAYABON) | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2995174.43 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00103 | 14HJ0014 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | GIMP CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120316 | Cangabo ES | LA LIBERTAD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | REVERTED | 0 |  |  | 070314S00172 | 14HJ0010 | [5 empty] | B.C. CUERPO CONSTRUCTION CORPORATION | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120386 | Concepcion ES | MANJUYOD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 |  |  | 070314S00180 | 14HJ0036
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120581 | DALAUPON ELEMENTARY SCHOOL | TAYASAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | REVERTED | 0 |  |  | 070314S00168 | 14HJ0011 | [5 empty] | B.C. CUERPO CONSTRUCTION CORPORATION | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120180 | Danao ES | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2016-01-11 |  | 070314S00104 | 14HJ0034 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06 |  | Recommended for termination to the Regional Office
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120628 | Don Julian dela Vina Villegas Memorial ES | VALLEHERMOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-26 |  | 070314S00151 | 14HJ0009 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-08 | 2014-08-20 | LAB GENERAL ENGINEERING | with 2021 completion
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120625 | Don Vicente Lopez, Sr. MS (Bagawines ES) | VALLEHERMOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-02-26 |  | 070314S00143 | 14HJ0007 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-09-25 | LAB GENERAL ENGINEERING | with 2021 completion
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120040 | Duli-Duli ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00088 | 14HJ0038 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120631 | Guba Elementary School | VALLEHERMOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | REVERTED | 0 |  |  | 070314S00145 | 14HJ0007 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-09-25 | LAB GENERAL ENGINEERING
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312904 | Guba HS | VALLEHERMOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120204 | Guibawan PS | CANLAON CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2016-01-13 |  | 070314S00152 | 14HJ0048 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120318 | Guihob ES | LA LIBERTAD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 |  |  | 070314S00173 | 14HJ0047 | [6 empty] | Included to 2021 Completion/New Construction
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120042 | Inacban PS | AYUNGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-14 | 070314S00089 | 14HJ0013 | 2014-06-18 | 2014-07-18 | 2014-07-25 | 2014-08-14 | 2014-08-27 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120297 | Irene ES | JIMALALUD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00170 | 14HJ0049 | 2015-07-24 | 2015-08-07 | 2015-08-11 | 2015-09-08 | 2015-09-23
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120044 | Jandalamanon ES | AYUNGON | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00090 | 14HJ0037 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312922 | Jimalalud NHS - Tamao Ext. | JIMALALUD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303223 | Jose B. Cardenas MHS (Canlaon City NHS) | CANLAON CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | REVERTED | 0 |  |  | 070314S00158 | 14HJ0048 | 2015-07-31
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120045 | Kilaban ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2016-12-15 | 2015-12-15 | 070314S00091 | 14HJ0041 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-09-08 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120046 | Lamigan ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  |  | 070314S00092 | 14HJ0012 | [5 empty] | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120206 | Linothangan ES | CANLAON CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 |  |  | 070314S00164 | 14HJ0008 | [5 empty] | LAB GENERAL ENGINEERING | Included to 2021 Completion/New Construction
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120391 | LOCAY E/S | MANJUYOD | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 070314S00181 | 14HJ0016 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120048 | Maaslum ES | AYUNGON | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 970287.4407 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120202 | MACARIO ESPAÑOLA MEMORIAL SCHOOL | CANLAON CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1715997.9432 |  |  | COMPLETED | 1 |  |  | 070314S00200 | 070314S00200 | [5 empty] | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120589 | Maglihe ES | TAYASAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | REVERTED | 0 |  |  | 070314S00149 | 14HJ0044 | [6 empty] | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120300 | Mahanlod ES | JIMALALUD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-11-22 | 070314S00171 | 15HJ0035 | 2015-03-29 | 2015-04-24 | 2015-04-29 | 2015-05-25 | 2015-06-26 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120634 | Malangsa ES | VALLEHERMOSO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | Terminated | 0.08 | 2016-06-01 |  | 070314S00147 | 15HJ0165 | 2015-06-26 | 2015-07-02 | 2015-11-03 | 2015-11-20 | 2015-12-01 | ST. RAYMUND CONSTRUCTION, INC. | Recommended for termination to the Regional Office
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312961 | Manjuyod Science HS | MANJUYOD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2016-02-02 |  | 070314S00061 | 14HJ0038 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-24
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120325 | Manluminsag ES | LA LIBERTAD | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2483840.4049 |  |  | COMPLETED | 1 | 2015-07-31 | 2015-07-31 | 070314S00205 | 070314S00205 | 2014-11-28 | 2014-12-19 | 2014-12-23 | 2015-01-16 | 2015-01-27 | GLUBROS DEVELOPMENT INC.
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120050 | Manogtong ES | AYUNGON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2016-01-26 |  | 070314S00093 | 14HJ0039 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120185 | Mantahaw ES | BINDOY (PAYABON) | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3950805.49 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-12-13 | 070314S00105 | 14HJ0051 | 2015-03-29 | 2015-06-04 | 2015-06-09 | 2015-06-24 | 2015-07-03
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120186 | Matobato ES | BINDOY (PAYABON) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2483840.4049 |  |  | COMPLETED | 1 | 2015-09-04 | 2015-08-15 | 070314S00192 | 14HJ00118 | 2014-11-28 | 2015-01-30 | 2015-02-04 | 2015-02-19 | 2015-03-02 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120591 | Matuog ES | TAYASAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1715997.9432 |  |  | COMPLETED | 1 | 2015-07-06 | 2015-07-06 | 070314S00206 | 14HJ0126 | 2014-11-28 | 2015-01-30 | 2015-02-04 | 2015-02-19 | 2015-03-02 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120051 | Nabalian ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 |  |  | 070314S00094 | 15HJ0159 | [5 empty] | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120592 | Nabilog ES | TAYASAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | REVERTED | 0.02 |  |  | 070314S00139 | 14HJ0011 | [5 empty] | B.C. CUERPO CONSTRUCTION CORPORATION | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120187 | Nagcasunog ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 |  |  | 070314S00106 | 14HJ0032
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303257 | Owacan Provincial Comm. HS | JIMALALUD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0.02 | [10 empty] | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120305 | Pacuan ES | JIMALALUD | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 3 | 2544140.4049 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120329 | Pacuan ES | LA LIBERTAD | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 |  |  | 070314S00174 | 14HJ0046
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303258 | Pacuan National High School | LA LIBERTAD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | REVERTED | 0.02 | [10 empty] | TERMINATED; NO UPDATES FROM DPWH IF THE FUND WAS REVERTED
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 |  |  | 070314S00107 | 14HJ0015 | [5 empty] | B.C. CUERPO CONSTRUCTION CORPORATION | Included to 2021 Completion/New Construction
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120636 | Paliran Elementary School | VALLEHERMOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2016-01-13 |  | 070314S00148 | 14HJ0047 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120213 | Panubigan ES | CANLAON CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 980337.4407 |  |  | COMPLETED | 1 | 2015-08-04 | 2015-09-30 | 070314S00201 | 070314S00201 | 2014-11-28 | 2015-03-24 | 2015-04-07 | 2015-04-24 | 2015-05-08 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120191 | Peñahan ES | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2016-01-11 |  | 070314S00108 | 14HJ0034 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303261 | Pinalubngan NHS | TAYASAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120595 | Pindahan ES | TAYASAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1866747.9432 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120637 | Pinucauan ES | VALLEHERMOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2016-02-05 |  | 070314S00162 | 15HJ0166 | 2015-06-26 | 2015-07-02 | 2015-11-03 | 2015-11-20 | 2015-12-01 | ST. RAYMUND CONSTRUCTION, INC.
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120215 | Pula ES | CANLAON CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 |  |  | 070314S00165 | 14HJ0008 | [5 empty] | LAB GENERAL ENGINEERING | Included to 2021 Completion/New Construction
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120597 | Sacsac ES | TAYASAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 |  |  | 070314S00140 | 14HJ0043 | 2015-07-31
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120192 | Salong ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | REVERTED | 0 |  |  | 070314S00109 | 14HJ0015 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | B.C. CUERPO CONSTRUCTION CORPORATION | Recommended for termination to the Regional Office
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120400 | Salvacion ES | MANJUYOD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-11-22 | 2015-11-22 | 070314S00182 | 15HJ0031 | 2015-03-29 | 2015-04-24 | 2015-04-29 | 2015-05-25 | 2015-06-26 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120402 | San Isidro ES | MANJUYOD | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-11-03 | 2015-10-12 | 070314S00183 | 14HJ0033 | 2015-03-29 | 2015-06-04 | 2015-06-09 | 2015-06-24 | 2015-07-03
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120216 | Tabalogo ES | CANLAON CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | REVERTED | 0 |  |  | 070314S00166 | 14HJ0008 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | LAB GENERAL ENGINEERING | Recommended for termination to the Regional Office
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120638 | Tabon Elementary School | VALLEHERMOSO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-02-26 |  | 070314S00150 | 14HJ0006 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-09-25 | LAB GENERAL ENGINEERING | with 2021 completion
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120600 | Tabunan ES | TAYASAN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | REVERTED | 0 | 2016-01-26 |  | 070314S00141 | 14HJ0043 | 2015-07-24 | 2015-08-05 | 2015-08-11 | 2015-08-29 | 2015-09-23
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120193 | Tagaytay ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 |  |  | 070314S00110 | 14HJ0015 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-08-20 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120055 | Talanyog ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2016-02-16 |  | 070314S00095 | 15HJ0160 | 2015-07-10 | 2015-07-16 | 2015-11-03 | 2015-12-03 | 2015-12-19 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120194 | Talaptapan ES | BINDOY (PAYABON) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 965262.4407 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189515 | Tamao ES | TAYASAN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2016-06-01 |  | 070314S00144 | 15HJ0164 | 2015-07-31 | 2015-10-21 | 2015-11-03 | 2015-11-20 | 2015-12-01 | MAI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303276 | Tambo National High School | AYUNGON | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120602 | Tambulan ES | TAYASAN | 1 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 |  |  | 070314S00142 | 14HJ0050 | 2015-07-10 | 2015-11-24 | 2015-12-08
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120058 | Tibyawan ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2016-12-15 | 2015-12-15 | 070314S00096 | 14HJ0041 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-09-04 | 2015-09-15
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120060 | Tumampon ES | AYUNGON | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-26 |  | 070314S00097 | 14HJ0012 | 2014-06-18 | 2014-07-15 | 2014-07-25 | 2014-08-12 | 2014-08-20 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120406 | Tupas ES | MANJUYOD | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2016-01-20 |  | 070314S00175 | 15HJ0077 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-08-24 | ETHAN PROPERTY DEVELOPER
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120641 | Ulay Elementary School | VALLEHERMOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | Terminated | 0.15 | 2015-02-26 |  | 070314S00138 | 14HJ0006 | 2014-06-18 | 2014-07-16 | 2014-07-25 | 2014-08-12 | 2014-09-25 | LAB GENERAL ENGINEERING | Terminated
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303292 | Vallehermoso PCHS | VALLEHERMOSO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189530 | Alagasihan PS | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-10 | 070314S00040 | 14HK0016 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312957 | Amlan NHS-Jugno Campus | AMLAN (AYUQUITAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120343 | Barras ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-04-10 | 070314S00121 | 14HK0027 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120430 | Basak PS | SAN JOSE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-13 | 070314S00035 | 14HK0015 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-23 | C. LARA CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120346 | Binantangan ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-07-10 | 070314S00176 | 14HK0031 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312943 | Bolocboloc HS | SIBULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 070314S00012 | 14HK0022 | 2014-08-07 | 2014-08-22 | 2014-09-03 | 2014-09-12 | 2014-09-23 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120349 | Bulwang ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-20 | 070314S00163 | 14HK0028 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312927 | Cambaloctot HS | SAN JOSE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120350 | Campo-aling ES | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-13 | 070314S00122 | 14HK0030 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120351 | Canggohob ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-07-07 | 070314S00062 | 14HK0028 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120352 | Cansal-ing ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-20 | 070314S00013 | 14HK0030 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120023 | Cantalina ES | AMLAN (AYUQUITAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-22 | 070314S00177 | 14HK0021 | 2014-08-07 | 2014-08-22 | 2014-09-03 | 2014-09-12 | 2014-09-23 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120353 | Cantombol ES | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-07-14 | 070314S00027 | 14HK0028 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120357 | Danawan ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120488 | Escaguit ES | SIBULAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1736097.9432 |  |  | REVERTED | 0 |  |  | 070314S00218 | 14HK0049 | 2014-12-14 | 2014-12-23 | 2014-12-29 | 2014-12-29 | 2014-12-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120361 | Inapoy ES | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-04-16 | 070314S00025 | 14HK0029 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189523 | Lanot PS | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-04-21 | 070314S00039 | 14HK0031 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120363 | Lapong ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-13 | 070314S00021 | 14HK0016 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189510 | Lower Capanun-an ES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-04-21 | 070314S00029 | 14HK0027 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120366 | Mabinay CES | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-08-14 | 070314S00022 | 14HK0030 | 2014-08-07 | 2014-08-22 | 2014-12-11 | 2014-12-22 | 2014-12-29 | STARS & STRIPES CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120492 | Magsaysay MES | SIBULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-23 | 070314S00037 | 14HK0022 | 2014-08-07 | 2014-08-22 | 2014-09-03 | 2014-09-12 | 2014-09-23 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120367 | Mampalasan ES | MABINAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-06-09 | 070314S00023 | 14HK0032 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120493 | Maningcao ES | SIBULAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 965262.4407 |  |  | REVERTED | 0 |  |  | 070314S00209 | 14HK0048 | 2014-12-14 | 2014-12-23 | 2014-12-29 | 2014-12-29 | 2014-12-29 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312959 | Mayaposi CHS | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120370 | Namangka ES | MABINAY | 2 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-08-21 | 070314S00024 | 14HK0017 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-22 | DT&C CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303255 | Negros Oriental NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303247 | Paniabonan HS | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120375 | Samac ES | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-04-17 | 070314S00038 | 14HK0027 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312928 | Siapo HS | SAN JOSE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312945 | Sibulan NHS - Balugo Ext. | SIBULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312907 | Sibulan NHS - Enrique Villanueva HS Ext. | SIBULAN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312953 | Sibulan Night High School | SIBULAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303209 | Silab Comm. HS Annex | AMLAN (AYUQUITAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120439 | Sra. Ascion ES | SAN JOSE | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-06 | 070314S00036 | 14HK0015 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-23 | C. LARA CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120441 | Tapon Norte Elementary School | SAN JOSE | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-20 | 070314S00016 | 14HK0024 | 2014-08-07 | 2014-08-22 | 2014-09-03 | 2014-09-11 | 2014-09-22 | C. LARA CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120378 | Tara ES | MABINAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-08-13 | 070314S00030 | 14HK0017 | 2014-08-07 | 2014-08-22 | 2014-09-02 | 2014-09-11 | 2014-09-22 | DT&C CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303218 | Actin National High School | BASAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120444 | Apoloy ES | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00067 | 14HL0012 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120502 | Aw-a ES | SANTA CATALINA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 070314S00077 | 14HL0019 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120111 | Cabigti-an ES | MAGLINAO | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312940 | Cambonbon National High School | SIATON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120452 | Canaway ES | SIATON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2220417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00068 | 14HL0026 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120454 | Casalaan ES | SIATON | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-15 | 070314S00069 | 14HL0025 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120455 | Caticugan ES | SIATON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-15 | 070314S00070 | 14HL0027 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120507 | Cawitan ES | SANTA CATALINA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-02-01 | 070314S00078 | 14HL0029 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | VESA ENGINEERING AND CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312929 | Cawitan HS | SANTA CATALINA | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120459 | Felipe Tayko MCES | SIATON | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 3970835.14 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120459 | Felipe Tayko MCES | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120459 | Felipe Tayko MCES | SIATON | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4010835.14 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120460 | Giligaon ES | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-01-28 | 070314S00073 | 14HL0028 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION &
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312956 | Gregorio Elmaga MHS | ZAMBOANGUITA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1715997.9432 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189525 | Hagikhik PS | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189508 | Jagna ES | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00074 | 14HL0017 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189529 | Kabangkalan PS | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120510 | Kakha ES | SANTA CATALINA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00079 | 14HL0024 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120115 | Linantayan ES | BASAY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-04-09 | 2015-02-28 | 070314S00065 | 14HL0023 | 2014-10-29 | 2014-11-07 | 2014-11-11 | 2014-11-26 | 2014-12-04 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303259 | Lorenza P. Palarpalar MHS | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312919 | Malongcay Dacu High School | DAUIN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 960237.4407 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312939 | Mantiquil Masaligan HS | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312939 | Mantiquil Masaligan HS | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120529 | Marcelino E. Elligan-Banlas ES | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1736097.9432 |  |  | COMPLETED | 1 | 2015-05-04 | 2015-05-04 | 070314S00199 | 14HL0048 | 2014-11-26 | 2014-12-05 | 2014-12-09 | 2014-12-17 | 2014-12-29 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312932 | Milagrosa HS | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6338864.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120514 | Nagbinlod ES | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-04-16 | 2015-04-16 | 070314S00044 | 14HL0035 | 2014-11-05 | 2014-11-13 | 2014-11-18 | 2014-11-28 | 2014-12-11 | L.C. CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120470 | Nasipit ES | SIATON | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 070314S00064 | 14HL0014 | 2014-09-17 | 2014-09-09 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120618 | Nasuji PS | VALENCIA (LUZURRIAGA) | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00084 | 14HL0011 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | NALE CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303264 | Obat High School | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120516 | Omol Elementary School | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00081 | 14HL0024 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312912 | Pedro R. Abul MHS | SANTA CATALINA | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4317024.6094 |  |  | COMPLETED | 1 | [10 empty] | Inaccessible road and far flung, Abandoned
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120464 | Ramon Ponce De Leon MES (Malabuhan ES) | SIATON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00086 | 14HL0026 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120653 | Salngan ES | ZAMBOANGUITA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 070314S00053 | 14HL0026 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2014 | K10 (2014) | NIR | Negros Oriental | 303265 | Sta. Catalina NHS | SANTA CATALINA | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4442649.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189520 | Sta. Catalina Science HS | SANTA CATALINA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-04-16 | 2015-04-16 | 070314S00085 | 14HL0041 | 2014-11-05 | 2014-11-14 | 2014-11-18 | 2014-11-28 | 2014-12-11 | BIGFOOT CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312935 | Sta. Catalina Science HS | SANTA CATALINA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120525 | Tamlang ES | SANTA CATALINA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-02-01 | 070314S00082 | 14HL0024 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | VIRLO CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312930 | Tamlang HS | SANTA CATALINA | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1030587.4407 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Negros Oriental | 120480 | Tayak ES | SIATON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2100417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-15 | 070314S00028 | 14HL0013 | 2014-07-18 | 2014-07-29 | 2014-07-31 | 2014-08-13 | 2014-08-22 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Negros Oriental | 189521 | Tubod PS | SANTA CATALINA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 070314S00043 | 14HL0018 | 2014-09-17 | 2014-09-28 | 2014-09-30 | 2014-10-09 | 2014-10-22 | CRIZEL CONSTRUCTION & CONCRETE PRODUCTS
NC 2014 | K10 (2014) | NIR | Negros Oriental | 312958 | Valencia NHS-Dobdob Ext. | VALENCIA (LUZURRIAGA) | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1786347.9432 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060614S00195 | 15GK0102 | 2015-09-01 | 2015-09-02
NC 2014 | SHS (2014) | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | REVERTED | 0 |  |  | 060614S00194 | 15GK0101 | 2015-09-01 | 2015-09-02
NC 2014 | K10 (2014) | NIR | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Sagay City | 117721 | Maria Lopez ES | Sagay City | 2 | 1 | 5 | 1STY1CL, 1STY4CL | 2014 K10 BATCH 2 | 4374000 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-03-07 | 060614S00152 | 14GK0053 | 2014-09-19 | 2014-09-25 | 2014-10-07 | 2014-10-20 | 2014-10-29 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | NIR | Sagay City | 302767 | Sagay NHS | Sagay City | 2 | 1 | 9 | 2U-1STY3CL, 1STY2CL, 1STY1CL | 2014 K10 BATCH 2 | 7919000 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Sagay City | 117707 | Talusan ES | Sagay City | 2 | 1 | 4 | 2U-1STY2CL | 2014 K10 BATCH 2 | 3562000 |  |  | COMPLETED | 1 | 2015-02-25 | 2015-02-25 | 060614S00153 | 14GK0052 | 2014-09-19 | 2014-09-25 | 2014-10-07 | 2014-10-20 | 2014-10-29 | GKMM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | NIR | Sagay City | 302771 | Vito NHS | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 060614S00192 | 15GK0104 | 2015-09-01 | 2015-09-02 | 2015-09-15 | 2015-09-22 | 2015-10-01 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | REVERTED | 0 |  |  | 060614S00191 | 15GK0092 | 2015-08-18 | 2015-08-19
NC 2014 | SHS (2014) | NIR | San Carlos City | 302775 | Julio Ledesma NHS | SAN CARLOS CITY | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-08 |  | 060614S00190 | 15GK0117 | 2015-10-08 | 2015-10-08 | 2015-10-22 | 2015-10-30 | 2015-11-09 | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE
NC 2014 | SHS (2014) | NIR | San Carlos City | 302776 | Quezon NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8344965.051 |  |  | REVERTED | 0 |  |  | 060614S00189 | 15GK0093 | 2015-08-18 | 2015-08-19 | 2015-09-01
NC 2014 | SHS (2014) | NIR | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3619886.575 |  |  | COMPLETED | 1 | 2016-02-02 |  | 060614S00181 | 15GK0076 | 2015-07-16 | 2015-07-31 | 2015-08-04 | 2015-08-24 | 2015-08-26 | OPELL CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | NIR | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-02 |  | 060614S00187 | 15GK0098 | 2015-09-01 | 2015-09-01 | 2015-09-08 | 2015-09-15 | 2015-09-24 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10437131.51 |  |  | COMPLETED | 1 | 2016-03-12 |  | 060614S00186 | 15GK0106 | 2015-09-09 | 2015-09-11 | 2015-09-24 | 2015-10-02 | 2015-10-12 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | NIR | Silay City | 302779 | Don Felix T. Lacson NHS (Brgy. Capitan Ramon) | SILAY CITY | 3 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3491886.575 |  |  | COMPLETED | 1 | 2016-01-17 |  | 060614S00211 | 15GK0063 | 2015-07-03 | 2015-07-10 | 2015-07-24 | 2015-08-07 | 2015-08-18 | KENBE CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | NIR | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15221327.92 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | NIR | Silay City | 500202 | Sibato Integrated School | SILAY CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2370417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-03-16 | 060614S00041 | 14GK0051 | 2014-09-05 | 2014-09-16 | 2014-10-01 | 2014-10-14 | 2014-10-22 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Tanjay City | 322301 | Graciano Banogon HS | CITY OF TANJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-11 | 070314S00059 | 14HK0026 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-15 | 2014-09-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | NIR | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | NIR | Tanjay City | 322305 | Luca HS | CITY OF TANJAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2080417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-05 | 070314S00060 | 14HK0026 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-15 | 2014-09-29 | RICHFIELD BUILDERS
NC 2014 | K10 (2014) | NIR | Tanjay City | 234003 | Lugta Elementary School | CITY OF TANJAY | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-10 | 070314S00056 | 14HK0025 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-12 | 2014-09-29 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Tanjay City | 303282 | Tanjay NHS (Polo) | CITY OF TANJAY | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-09 | 070314S00057 | 14HK0025 | 2014-08-07 | 2014-08-22 | 2014-09-04 | 2014-09-12 | 2014-09-29 | R.E. SINGSON CONSTRUCTION
NC 2014 | K10 (2014) | NIR | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-08 | 2015-02-16 | 070414S00001 | 14HM-0023 | 2014-06-27 | 2014-07-25 | 2014-08-05 | 2014-09-26 | 2014-10-03 | QM BUILDERS
NC 2014 | K10 (2014) | NIR | Siquijor | 190005 | Candigum ES | LARENA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 2 | 1004283.8736 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 070414S00002 | 14HM-0024 | 2014-06-30 | 2014-07-25 | 2014-08-05 | 2014-09-26 | 2014-10-03 | QM BUILDERS
NC 2015 | K10 (2015) | NIR | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 060615S00126 | 15GC0084 | 2015-09-27 | 2015-09-28 | 2015-10-12 | 2015-10-19 | 2015-10-26 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bacolod City | 302701 | Bacolod City National High School | BACOLOD CITY (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 63005781 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Bacolod City | 117478 | DoÃ±a E.J. Garcia ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00055 | 15GC0050 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-27 | 2015-09-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31942890 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Bacolod City | 117488 | Don I. Nessia Sr. ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00125 | 15GC0063 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-14 | 2015-09-21 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Bacolod City | 117482 | Educ.& Training Center Sch. II | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | NIR | Bacolod City | 181005 | Handumanan ES II | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060615S00057 | 15GC0075 | 2015-09-01 | 2015-09-02 | 2015-09-14 | 2015-09-24 | 2015-09-30 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | K10 (2015) | NIR | Bacolod City | 117471 | Handumanan ES-1 | BACOLOD CITY (Capital) | 0 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 6 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 060615S00124 | 15GC089 | 2015-10-19 | 2015-10-20 | 2015-11-03 | 2015-11-06 | 2015-11-10 | JAIME B. CHING ENTERPRISES
NC 2015 | TECHVOC (2015) | NIR | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2629549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8184965.051 |  |  | COMPLETED | 1 |  |  | 060615S00121 | 15GC0083 | 2015-09-27 | 2015-09-28 | 2015-10-12 | 2015-10-19 | 2015-10-26 | LEGACY CONSTRUCTION | w/ defects and non conformance to standard plans. Inspected w/ local School Board and letter sent to DPWH
NC 2015 | K10 (2015) | NIR | Bago City | 117525 | Najaba ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1993606.04 |  |  | COMPLETED | 1 |  |  | 060615S00127 | 060615S00127 | 2015-10-26 | 2015-10-27 | 2015-11-10 | 2015-11-23 | 2015-12-02 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 060615S00036 | 15GN0077 | 2015-08-06 | 2015-08-07 | 2015-08-20 | 2015-08-26 | 2015-09-04 | MICRO ASIA BUILDERS CORPORATION
NC 2015 | TECHVOC (2015) | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Bago City | 302722 | RAMON TORRES MALINGIN NATIONAL HIGH SCHOOL | BAGO CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11207342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8494965 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bago City | 302723 | Ramon Torres Sagasa NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00035 | 060615S00035 | 2015-11-25 | 2015-11-26 | 2015-12-08
NC 2015 | SHS (2015) | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 060615S00034 | 15GN0078 | 2015-08-06 | 2015-08-14 | 2015-08-20 | 2015-08-26 | 2015-09-04 | FOUR SG ENTERPRISES
NC 2015 | K10 (2015) | NIR | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 060615S00054 | 15GN0084 | 2015-08-09 | 2015-08-11 | 2015-08-24 | 2015-08-27 | 2015-09-08 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bais City | 303216 | Bais City Science NHS | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070315S00161 | 0703-15-S-00161 | 2015-09-15 | 2015-09-21 | 2015-09-25 | 2015-10-08 | 2015-10-19 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | K10 (2015) | NIR | Bais City | 120076 | Dansulan ES | BAIS CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 070315S00205 | 0703-15-S-00205 | 2015-11-06 | 2015-11-20 | 2015-11-23 | 2015-12-03 | 2015-12-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2015 | SHS (2015) | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10767131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bais City | 323007 | Mansangaban National HS | BAIS CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 11167131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bais City | 323008 | Okiot National High School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00035 | 15HK0068 | 2015-10-16 | 2015-11-11 | 2015-11-18 | 2015-12-03 | 2015-12-11 | GIMP VENTURES
NC 2015 | K10 (2015) | NIR | Bais City | 323006 | Sto. Thomas National High School | BAIS CITY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00164 | 15HK0089 | 2015-08-18 | 2015-08-31 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.R. GADINGAN CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 321911 | Abundio Agarpao, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00036 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Bayawan City | 321908 | Antonio M. Lacson, Sr. MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00037 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Bayawan City | 321907 | Atilano B. Cabangal MHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00038 | 15HL0050 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Bayawan City | 321901 | Banaybanay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00039 | 15HL0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Bayawan City | 303217 | Basay NHS | BASAY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14952518.84 |  |  | COMPLETED | 1 |  |  | 070315S00146 | 15HL0072 | 2015-12-16 | 2015-12-17 | 2015-12-24
NC 2015 | SHS (2015) | NIR | Bayawan City | 321902 | Bayawan City Science HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00040 | 15HL0051 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | TECHVOC (2015) | NIR | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bayawan City | 303221 | Bayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Bayawan City | 120125 | Bugay ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00204 | 15HL0093 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Bayawan City | 303238 | Bugay NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00028 | 15HL0051 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | K10 (2015) | NIR | Bayawan City | 120126 | Cadal-ugan E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00220 | 15HL0094 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | K10 (2015) | NIR | Bayawan City | 120147 | Cansig-id PS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00208 | 15HL0096 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00027 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303227 | Dawis NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00049 | 15HL0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303239 | Kalamtukan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bayawan City | 303237 | Kalumboyan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 |  |  | 070315S00034 | 15HL0052 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Bayawan City | 321905 | Lapay High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00057 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 321909 | Malabugas HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Bayawan City | 303240 | Manduaw NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00055 | 15HL0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | ADROIT CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Bayawan City | 120134 | Matunoy ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6264337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00219 | 15HL0095 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Bayawan City | 321903 | Minaba HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00054 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303254 | Narra HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00009 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303256 | Omod National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8222965.051 |  |  | COMPLETED | 1 |  |  | 070315S00053 | 15HL0055 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 321910 | Pagatban HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00026 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 321906 | San Jose HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00052 | 15HL0056 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | ADROIT CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303241 | Tabuan PCHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00042 | 15HL0053 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303242 | Tayawan NHS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00050 | 15HL0054 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | PINS CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Bayawan City | 120168 | Villasol ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00217 | 15HL0097 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | CTG CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Bayawan City | 321904 | Villasol HS | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4829098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Cadiz City | 302736 | Jerusalem National High School (Villacin NHS - Jerusalem Ext. HS) | CADIZ CITY | 2 | 1 | 2 | ADDITIONAL 1STY2CL | 2015 ADDITIONAL FUND BATCH 9 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 | 1 | 1 | ADDITIONAL 1STY1CL | 2015 ADDITIONAL FUND BATCH 9 | 1012049.6543 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Dumaguete City | 119936 | Candau-ay ES | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00166 | 15HK0079 | 2015-08-07 | 2015-08-21 | 2015-08-25 | 2015-08-28 | 2015-09-08 | VESA ENGINEERING & CONST(FOR DELETION)
NC 2015 | SHS (2015) | NIR | Dumaguete City | 303168 | Dumaguete City HS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070315S00015 | 15HK0044 | 2015-07-14 | 2015-08-12 | 2015-08-14 | 2015-08-20 | 2015-08-28 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | SHS (2015) | NIR | Dumaguete City | 303169 | RTPM - Dumaguete Science HS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00008 | 15HK0045 | 2015-08-10 | 2015-08-13 | 2015-08-14 | 2015-08-21 | 2015-08-28 | C. LARA CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00024 | 15HK0046 | 2015-07-14 | 2015-08-19 | 2015-08-25 | 2015-08-28 | 2015-09-11 | MONTPHIL CONSTRUCTION CORPORATION
NC 2015 | TECHVOC (2015) | NIR | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120234 | Basak ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2048606.04 |  |  | COMPLETED | 1 |  |  | 070315S00214 | 070315S00214 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120239 | Busay Elementary School | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2118606.04 |  |  | REVERTED | 0 |  |  | 070315S00228 | 070315S00228 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120266 | Dadiangao PS | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6519337.6381 |  |  | REVERTED | 0 |  |  | 070315S00212 | 070315S00212 | 2015-11-16
NC 2015 | SHS (2015) | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00051 | 070315S00051 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06 | ST. RAYMUND CONSTRUCTION, INC. | see 2021 completion UPDATE THE CONTRACTOR TO CMPLETE THE PROJECT ON TIME
NC 2015 | K10 (2015) | NIR | Guihulngan City | 324803 | Guihulngan National High School - Buenavista Extension | CITY OF GUIHULNGAN | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070315S00183 | 070315S00183 | 2015-09-30 | 2015-10-15 | 2015-10-20 | 2015-11-05 | 2015-11-23 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00043 | 070315S00043 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-06 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | SHS (2015) | NIR | Guihulngan City | 303233 | Guihulngan NHS - Hilaitan | CITY OF GUIHULNGAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14967518.84 |  |  | REVERTED | 0 |  |  | 070315S00160
NC 2015 | K10 (2015) | NIR | Guihulngan City | 324802 | Guihulngan NHS - P. Zamora Extension | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00184 | 070315S00184 | 2015-09-30 | 2015-10-29
NC 2015 | SHS (2015) | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 070315S00044 | 070315S00044 | 2015-06-15 | 2015-08-18 | 2015-08-25 | 2015-09-17 | 2015-09-28 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Guihulngan City | 303232 | Guihulngan NHS - Sandayao Annex | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00047 | 070315S00047 | 2015-07-20 | 2015-10-27 | 2015-11-03 | 2015-11-20 | 2015-12-01 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE | Slow progress
NC 2015 | SHS (2015) | NIR | Guihulngan City | 312910 | Guihulngan NHS, Hilaitan - Trinidad Annex | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 070315S00048 | 070315S00048 | 2015-07-20 | 2015-08-11 | 2015-08-18 | 2015-09-15 | 2015-09-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120268 | Hinakpan Elementary School | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 070315S00209 | 070315S00209 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120259 | Jacinto Baquilta ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | REVERTED | 0 |  |  | 070315S00215 | 070315S00215 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | REVERTED | 0 |  |  | 070315S00227 | 070315S00227 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120249 | Laos ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070315S00185 | 070315S00185 | 2015-09-30 | 2015-10-29 | 2015-12-08
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120277 | Mckinley ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00213 | 070315S00213 | 2015-11-16 | 2015-12-08 | 2015-12-15
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120282 | Planas ES | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070315S00210 | 070315S00210 | 2015-11-16
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120283 | Taloto ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00216 | 070315S00216 | 2015-11-23 | 2015-12-08 | 2015-12-15
NC 2015 | K10 (2015) | NIR | Guihulngan City | 120258 | Trinidad ES | CITY OF GUIHULNGAN | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 15121327.92 |  |  | REVERTED | 0 |  |  | 070315S00211 | 070315S00211
NC 2015 | K10 (2015) | NIR | Kabankalan City | 117841 | Bino ES | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00053 | 15GM0064 | 2015-10-03 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-06 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8304965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2118606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Kabankalan City | 302788 | DAAN BANUA NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 060615S00136 | 15GM0089 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | NIR | Kabankalan City | 117883 | Ilan PS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 060615S00128 | 0606-15-S-00128 | 2015-10-20 | 2015-10-22
NC 2015 | K10 (2015) | NIR | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2088606 |  |  | COMPLETED | 1 |  |  | 060615S00140 | 15GM0090 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Kabankalan City | 117888 | Mamig ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00052 | 15GM0046 | 2015-09-08 | 2015-09-11 | 2015-09-23 | 2015-10-05 | 2015-10-22 | ADROIT CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Kabankalan City | 302798 | PINAGUINPINAN NHS | CITY OF KABANKALAN | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8334965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Kabankalan City | 117849 | Pitgong ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00043 | 15GM0045 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | TECHVOC (2015) | NIR | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2489549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 30 | 3STY15CL | 2015 SHS BATCH 5 | 43126027 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15241328 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | 48 | 4STY16CL | 2015 SHS BATCH 5 | 80707408 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302586 | Agpangi NHS | CALATRAVA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00027 | 15GK0111 | 2015-09-09 | 2015-09-09 | 2015-09-24 | 2015-10-02 | 2015-10-12 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302597 | Bug-ang NHS | TOBOSO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2892592 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8444965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116912 | Patun-an ES | CALATRAVA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060615S00044 | 15GK0113 | 2015-10-01
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1 |  |  | 060615S00094 | 15GK0135 | 2015-10-26 | 2015-10-27 | 2015-11-10 | 2015-11-18 | 2015-11-27 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117421 | Vergara ES | TOBOSO | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00045 | 15GK0110 | 2015-09-09 | 2015-09-09 | 2015-09-24
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117251 | Patlagan Elementary School | MANAPLA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00129 | 15GK0128 | 2015-10-20 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-11-20 | HUMMING BIRD CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117275 | Alegria ES | MURCIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00130 | 15GK0126 | 2015-10-20 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-11-20 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117025 | E. B. Magalona ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00050 | 15GK0112 | 2015-09-09 | 2015-09-09 | 2015-09-24 | 2015-10-02 | 2015-10-12 | REDSON CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302621 | Enrique B. Magalona NHS | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 5 | 5472652 |  |  | COMPLETED | 1 |  |  | 060615S00080 | 15GK0157 | 2015-11-05 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-18 | SILVERROCK CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 12788675 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117028 | Jose M. Consing Memorial School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00048 | 15GK0112 | 2015-09-09 | 2015-09-09 | 2015-09-24 | 2015-10-02 | 2015-10-12 | REDSON CONSTRUCTION AND SUPPLIES
NC 2015 | K10 (2015) | NIR | Negros Occidental | 302659 | Lopez Jaena NHS | MURCIA | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8464965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302659 | Lopez Jaena NHS | MURCIA | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 11117343 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302659 | Lopez Jaena NHS | MURCIA | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117388 | Maria-Eustaquia Lizares ES | CITY OF TALISAY | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00046 | 15GK0088 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-08 | 2015-09-17 | TANON CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | NIR | Negros Occidental |  | Proposed Stand Alone SHS 4 (Victorias NHS) | Victorias | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12921310 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | 12 | 2STY12CL | 2015 SHS BATCH 5 | 14729217 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 180509 | San Antonio ES | CITY OF TALISAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060615S00131 | 15GK0126 | 2015-10-20 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-11-20 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 180516 | Smile Village ES | MURCIA | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 060615S00132 | 15GK0136 | 2015-10-26 | 2015-10-27 | 2015-11-10 | 2015-11-18 | 2015-11-27 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 | 1 | 24 | 2STY12CL | 2015 SHS BATCH 5 | 29158434 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | K10 (2015) | NIR | Negros Occidental | 302696 | Victorias NHS - Alfonso Sta. Ana MHS Ext. (Cuaycong Ext.) | CITY OF VICTORIAS | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1 |  |  | 060615S00137 | 15GK0156 | 2015-11-05 | 2015-11-13 | 2015-11-26 | 2015-12-08 | 2015-12-18 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Negros Occidental | 302591 | ANTIPOLO NATIONAL HIGH SCHOOL | PONTEVEDRA | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8364965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302591 | Antipolo NHS | PONTEVEDRA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302624 | Enriqueta Montilla De Esteban MHS | PULUPANDAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1 |  |  | 060615S00083 | 060615S00083 | 2015-11-25 | 2015-11-26 | 2015-12-08 |  |  |  | No Remarks
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302683 | San Enrique HS | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1998606 |  |  | COMPLETED | 1 |  |  | 060615S00084 | 15GN0090 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-10-19 | 2015-10-27 | JAIME B. CHING ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302686 | Tabao NHS | VALLADOLID | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3787969 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302587 | Aguisan NHS | CITY OF HIMAMAYLAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1 |  |  | 060615S00086 | 15GL0095 | 2015-09-18 | 2015-09-18 | 2015-10-01 | 2015-10-09 | 2015-10-21 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302592 | Biao NHS | BINALBAGAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8234965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 311101 | Binalbagan NHS - NOSOF Ext. | BINALBAGAN | 5 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | COMPLETED | 1 |  |  | 060615S00090 | 15GL0100 | 2015-10-02 | 2015-10-02 | 2015-10-15 | 2015-10-23 | 2015-11-06 | AQUA DRAGON CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302671 | Binalbagan NHS (Paglaum NHS) | BINALBAGAN | 5 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | COMPLETED | 1 |  |  | 060615S00089 | 15GL0105 | 2015-10-13 | 2015-10-16 | 2015-10-28 | 2015-11-06 | 2015-11-18 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 311103 | Cabacungan NHS - Masulog Ext. | LA CASTELLANA | 5 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3667969 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117213 | Don Generoso M. Villanueva ES | LA CASTELLANA | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 060615S00042 | 15GL0076 | 2015-07-15 | 2015-07-07 | 2015-07-29 | 2015-08-06 | 2015-08-12 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117074 | Doña Gregoria Ramos Memorial School | CITY OF HIMAMAYLAN | 5 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00056 | 15GL0080 | 2015-08-05 | 2015-08-07 | 2015-08-20 | 2015-08-28 | 2015-09-09 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117262 | E. Basa PS | MOISES PADILLA (MAGALLON) | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00119 | 15GL0093 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-07 | 2015-10-19 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302646 | Guinpana-an NHS | MOISES PADILLA (MAGALLON) | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 060615S00088 | 15GL0098 | 2015-09-23 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-26 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5029098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 62805781 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117220 | La Castellana ES | LA CASTELLANA | 5 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117220 | La Castellana ES | LA CASTELLANA | 5 |  | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116873 | Mabunga Primary School | BINALBAGAN | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060615S00133 | 15GL0094 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-07 | 2015-10-19 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | 4 | Construction of 4 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 9478197.08 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302675 | Payao National High School | BINALBAGAN | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 060615S00065 | 15GL0096 | 2015-09-18 | 2015-09-18 | 2015-10-01 | 2015-10-09 | 2015-10-21 | BIG JOEs ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental |  | Proposed Stand Alone SHS 3 (Hinigaran NHS) | Hinigaran | 5 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 62955781 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117210 | Sebucauan ES | ISABELA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060615S00123 | 15GL0091 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-07 | 2015-10-19 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117229 | Velez Malaga Elementary School | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00120 | 15GL0092 | 2015-09-16 | 2015-09-17 | 2015-09-29 | 2015-10-07 | 2015-10-19 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 060615S00107 | 15GM0080 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117139 | Asia ES | HINOBA-AN (ASIA) | 6 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 060615S00122 | 15GM0099 | 2015-10-19 | 2015-10-21 | 2015-11-03 | 2015-11-13 | 2015-12-01 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116957 | Baluarte PS | CAUAYAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2088606.04 |  |  | COMPLETED | 1 |  |  | 060615S00118 | 0606-15-S-00118 | 2015-10-19 | 2015-10-21
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 5 | 5322652 |  |  | COMPLETED | 1 |  |  | 060615S00093 | 15GM0091 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SILVERGRACES CONSTRUCTION AND CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 060615S00079 | 15GM0081 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302598 | Bulata NHS | CAUAYAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2862592 |  |  | COMPLETED | 1 |  |  | 060615S00064 | 15GM0084 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302599 | Bulwangan NHS | HINOBA-AN (ASIA) | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302599 | Bulwangan NHS | HINOBA-AN (ASIA) | 6 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302605 | Camalanda-an NHS | CAUAYAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 5875818 |  |  | COMPLETED | 1 |  |  | 060615S00096 | 15GM0082 | 2015-10-12 | 2015-10-07 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116961 | Camalarang ES | CAUAYAN | 6 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4873636.82 |  |  | COMPLETED | 1 |  |  | 060615S00117 | 15GM0101 | 2015-10-19 | 2015-10-21 | 2015-11-03 | 2015-11-13 | 2015-12-01 | ZPM GENERAL MERCHANDISE
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6349338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1 |  |  | 060615S00098 | 15GM0075 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302612 | Cauayan NHS | CAUAYAN | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6439338 |  |  | COMPLETED | 1 |  |  | 060615S00099 | 15GM0071 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302614 | Culipapa NHS | HINOBA-AN (ASIA) | 6 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 SHS BATCH 5 | 4723637 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8394965 |  |  | COMPLETED | 1 |  |  | 060615S00101 | 15GM0076 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302630 | Florentina F. Caña Recto NHS | CAUAYAN | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1 |  |  | 060615S00102 | 15GM0072 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | GKMM CONSTRUCTION & SUPPLIES
NC 2015 | TECHVOC (2015) | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 302635 | Gil Montilla NHS - Cabadiangan Ext. | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 060615S00139 | 15GM0088 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302641 | Guiljungan NHS | Cauayan | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6439338 |  |  | COMPLETED | 1 |  |  | 060615S00104 | 15GM0073 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | GKMM CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302642 | Guiljungan NHS - Abaca Ext. | CAUAYAN | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1 |  |  | 060615S00105 | 15GM0074 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117153 | J.M. Reliquias Elementary School | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00113 | 15GM0095 | 2015-10-19 | 2015-10-21 | 2015-11-03 | 2015-11-13 | 2015-12-01 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2832592 |  |  | COMPLETED | 1 |  |  | 060615S00103 | 15GM0085 | 2015-10-12 | 2015-10-14 | 2015-10-26 | 2015-11-06 | 2015-11-20 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 060615S00116 | 15GM0093 | 2015-10-19 | 2015-11-03
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302661 | Juan Gequillana NHS (Manalad NHS) | ILOG | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00030 | 15GM0154 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-11 | 2015-12-23 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | NIR | Negros Occidental | 117155 | Manlawa-an Elementary School | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 060615S00112 | 15GM0096 | 2015-10-19 | 2015-10-21
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00037 | 15GM0155 | 2015-11-10 | 2015-11-13 | 2015-11-26 | 2015-12-11 | 2015-12-23 | H.L.J CONSTRUCTION & ENTERPRISES
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302665 | Nabulao NHS - Cayhagan Ext. | CITY OF SIPALAY | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 060615S00028 | 15GM0063 | 2015-09-11 | 2015-09-14 | 2015-09-28 | 2015-10-06 | 2015-10-22 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302666 | Nabulao NHS - Maricalum Ext. | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 060615S00029 | 15GM0041 | 2015-07-23 | 2015-07-27 | 2015-08-10 | 2015-08-18 | 2015-09-03 | EMR BUILDERS
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116977 | Payong PS | CAUAYAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 060615S00115 | 15GM0094 | 2015-10-20 | 2015-10-22 | 2015-11-04
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116978 | R. Garcia PS | CAUAYAN | 6 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4723636.82 |  |  | COMPLETED | 1 |  |  | 060615S00109 | 15GM0102 | 2015-10-19 | 2015-10-21 | 2015-11-03 | 2015-11-13 | 2015-12-01 | ZPM GENERAL MERCHANDISE
NC 2015 | K10 (2015) | NIR | Negros Occidental | 116980 | Sura ES | CAUAYAN | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2902592.44 |  |  | COMPLETED | 1 |  |  | 060615S00114 | 15GM0103 | 2015-10-19 | 2015-10-21 | 2015-11-03 | 2015-11-13 | 2015-12-01 | ZPM GENERAL MERCHANDISE
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302688 | Tabu NHS | ILOG | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6329338 |  |  | COMPLETED | 1 |  |  | 060615S00060 | 15GM0069 | 2015-10-04 | 2015-10-07 | 2015-10-20 | 2015-10-30 | 2015-11-16 | GIMP CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | NIR | Negros Occidental | 180502 | Tagaytay ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060615S00111 | 0606-15-S-00111 | 2015-10-19 | 2015-10-21
NC 2015 | SHS (2015) | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Occidental | 180523 | Upper Cawas PS | ILOG | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 060615S00110 | 15GM0098 | 2015-10-19 | 2015-10-21
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120031 | Anibong Elementary School | AYUNGON | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | REVERTED | 0 |  |  | 070315S00189 | 070315S00189 | 2015-11-23
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00079 | 070315S00079 | 2015-07-17 | 2015-07-28 | 2015-08-04 | 2015-09-02 | 2015-09-28 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312949 | Ayungon Science High School | AYUNGON | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00069 | 070315S00069 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-28 | JOSHUA ENGINEERING
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120528 | Baknit Elementary School | SANTA CATALINA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303222 | Budlasan HS | CANLAON CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070315S00059 | 070315S00059 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-28 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120037 | Candana-ay ES | AYUNGON | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2048606.04 |  |  | COMPLETED | 1 |  |  | 070315S00225 | 070315S00225 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120181 | Danawan Elementary School | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2058606.04 |  |  | REVERTED | 0 |  |  | 070314S00026 | 14HK0029 | 2014-08-07 | 2014-08-22 | 2014-11-14 | 2014-11-28 | 2014-12-22 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303229 | Demetrio Alviola NHS - Nalundan Annex | BINDOY (PAYABON) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00075 | 070315S00075 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-12 | ETHAN PROPERTY DEVELOPER
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8249965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120630 | Don Esperidion Villegas ES | VALLEHERMOSO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2288606.04 |  |  | COMPLETED | 1 |  |  | 070315S00196 | 070315S00196 | 2015-11-23
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312904 | Guba HS | VALLEHERMOSO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | Terminated | 0 | [10 empty] | Recommended for termination to the Regional Office
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120582 | Guincalaban Elementary School | TAYASAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00177 | 070315S00177 | 2015-09-30 | 2015-10-15 | 2015-10-20 | 2015-11-05 | 2015-11-23 | ST. RAYMUND CONSTRUCTION, INC. | Included to 2021 Completion/New Construction
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120583 | Ilaya-Tayasan Elementary School | TAYASAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6309337.6381 |  |  | Terminated | 0 |  |  | 070315S00222 | 070315S00222 | 2015-11-16 | 2015-12-08 | 2015-12-15 |  |  |  | TERMINATED; Included to the letter from DPWH 1st to Usec Ablan dated October 7, 2022.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303235 | Jimalalud NHS | JIMALALUD | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14932518.84 |  |  | COMPLETED | 1 |  |  | 070315S00162
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312922 | Jimalalud NHS - Tamao Ext. | JIMALALUD | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 312964 | Jose B. Cardenas Memorial High School - Bayog Ext. | CANLAON CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00181 | 070315S00181 | 2015-09-30 | 2015-10-29 | 2015-11-03 | 2015-11-20 | 2015-12-01 | ST. RAYMUND CONSTRUCTION, INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312963 | Jose B. Cardenas MHS - Tabalogo Ext. | CANLAON CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00083 | 070315S00083 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-12 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312916 | Jose B. Cardenas MHS - Uptown Annex | CANLAON CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 070315S00084 | 070315S00084 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-28 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312903 | Kauswagan HS | MANJUYOD | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00094 | 070315S00094 | 2015-07-17 | 2015-07-28 | 2015-08-04 | 2015-09-03 | 2015-09-14 | GIMP VENTURES
NC 2015 | K10 (2015) | NIR | Negros Oriental | 303243 | La Libertad Technical-Vocational School | LA LIBERTAD | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | cOMPLETED | 1 |  |  | 070315S00180 | 070315S00180 | 2015-09-30 | 2015-10-29 | 2015-12-08
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120390 | Libjo ES | MANJUYOD | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00179 | 15HJ0185 | 2015-09-30 | 2015-10-29 | 2015-11-03 | 2015-12-01 | 2015-12-23 | MAI CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070315S00116 | 070315S00116 | 2015-06-26 | 2015-07-02 | 2015-07-09 | 2015-08-24 | 2015-09-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120324 | Manghulyawon ES | LA LIBERTAD | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00182 | 070315S00182 | 2015-09-30 | 2015-10-15 | 2015-10-20 | 2015-11-05 | 2015-11-23 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION
NC 2015 | TECHVOC (2015) | NIR | Negros Oriental | 303251 | Manjuyod National High School | MANJUYOD | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303251 | Manjuyod NHS | MANJUYOD | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14932518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312966 | Manjuyod NHS - Panciao Ext. | MANJUYOD | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00011 | 070315S00011 | 2015-07-24 | 2015-08-03 | 2015-08-04 | 2015-08-24 | 2015-09-28 | PERFORMANCE BUILDERS & DEVELOPERS CORPORATION | SOME PUNCHLISTED ITEMS NOT YET RECTIFIED; With letter to DPWH 1st
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312955 | Masulog HS | CANLAON CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1 |  |  | 070315S00023 | 070315S00023 | 2015-06-26 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-28 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120396 | Matambok ES | MANJUYOD | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | REVERTED | 0 |  |  | 070315S00178
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120328 | Nasunggan ES | LA LIBERTAD | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6279337.6381 |  |  | Terminated | 0 |  |  | 070315S00195 | 070315S00195 | 2015-11-16 | [5 empty] | TERMINATED; with letter communication to dpwh.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 189519 | Naula-an Elementary School | BINDOY (PAYABON) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6309337.6381 |  |  | REVERTED | 0 |  |  | 070315S00223 | 070315S00223 | 2015-11-23 | 2015-12-08 | 2015-12-15
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120593 | Numnum Elementary School | TAYASAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00193 | 070315S00193 | 2015-11-16
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303257 | Owacan Provincial Comm. HS | JIMALALUD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303258 | Pacuan NHS | LA LIBERTAD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | cOMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303261 | Pinalubngan NHS | TAYASAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312960 | Pinucauan HS | VALLEHERMOSO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6409337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00018 | 070315S00018 | 2015-06-19 | 2015-07-02 | 2015-07-07 | 2015-07-22 | 2015-09-11 | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120331 | Pisong ES | LA LIBERTAD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 070315S00206 | 070315S00206 | 2015-11-23
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120332 | Pitogo ES | LA LIBERTAD | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | REVERTED | 0 |  |  | 070315S00163 | 070315S00163 | 2015-09-30
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00021 | 070315S00021 | 2015-07-17 | 2015-07-28 | 2015-08-04 | 2015-09-08 | 2015-09-15 | GIMP VENTURES
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120307 | Talamban ES | JIMALALUD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 070315S00218 | 070315S00218 | 2015-11-23
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303276 | Tambo NHS | AYUNGON | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120603 | Tanlad ES | TAYASAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 4067212.08 |  |  | REVERTED | 0 |  |  | 070315S00221 | 070315S00221 | 2015-11-23
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312950 | Tayasan National Science HS | TAYASAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00019 | 070315S00019 | 2015-07-10 | 2015-07-16 | 2015-07-21 | 2015-08-24 | 2015-09-06 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303290 | Tayasan NHS - Bago Campus | TAYASAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 070315S00073 | 070315S00073 | 2015-07-10 | 2015-07-16 | 2015-07-21 | 2015-08-24 | 2015-09-07 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303289 | Tayasan NHS (Main) | TAYASAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1 |  |  | 070315S00045 | 070315S00045 | 2015-07-10 | 2015-07-16 | 2015-07-21 | 2015-08-24 | 2015-09-07 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303292 | Vallehermoso NHS | VALLEHERMOSO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8259965.051 |  |  | COMPLETED | 1 | [10 empty] | With pending request for additional funds
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303271 | Ajong HS | SIBULAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6354337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00060 | 15HK0060 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | C. LARA CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303207 | Amlan NHS | AMLAN (AYUQUITAN) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14957518.84 |  |  | COMPLETED | 1 |  |  | 070315S00156 | 0703-15-S-00156 | 2015-09-15 | 2015-09-21 | 2015-09-25 | 2015-10-08 | 2015-10-19 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312957 | Amlan NHS-Jugno Campus | AMLAN (AYUQUITAN) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303211 | Bagtic NHS | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00085 | 15HK0070 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303245 | Barras Annex NHS | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6424337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00086 | 15HK0071 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | AJM PROVIDENCE BUILDERS & TRADING INC.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120486 | Calinawan ES | SIBULAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00174 | 15HK0092 | 2015-08-18 | 2015-08-31 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312927 | Cambaloctot HS | SAN JOSE | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312924 | Campanun-an PCHS | MABINAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00087 | 15HK0043 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-18 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312923 | Canggohob HS | MABINAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00088 | 15HK0042 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-20 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312925 | Cansal-ing Prov'l. Comm. HS | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6404337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00100 | 15HK0072 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312907 | Enrique Villanueva HS | SIBULAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303234 | Inapoy HS | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00092 | 15HK0073 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303208 | Jantianon NHS | AMLAN (AYUQUITAN) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6359338 |  |  | COMPLETED | 1 |  |  | 070315S00187 | 15HK0115 | 2015-10-26 | 2015-11-02 | 2015-11-04 | 2015-11-10 | 2015-11-13 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120362 | Lamdas Elementary School | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00165 | 15HK0080 | 2015-08-07 | 2015-08-21 | 2015-08-25 | 2015-08-28 | 2015-09-11 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8259965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7173647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312967 | Mabinay NHS-Manlingay Annex | MABINAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00095 | 15HK0042 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-20 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312951 | Mabinay Science High School | MABINAY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00096 | 15HK0043 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-18 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312901 | Maningcao NHS | SIBULAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00097 | 15HK0062 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312959 | Mayaposi Community HS | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303255 | Negros Oriental NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22187343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303255 | Negros Oriental NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22187343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Negros Oriental | 303255 | Negros Oriental NHS | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 189511 | New Namangka Elementary School | MABINAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00176 | 0703-15-S-00176 | 2015-08-04 | 2015-08-25 | 2015-08-27 | 2015-09-03 | 2015-09-14 | MONTPHIL CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120372 | Pandanon Elementary School | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6209337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00192 | 0703-15-S-00192 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-04 | 2015-11-11 | GIMP CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303247 | Paniabonan HS | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8279965.051 |  |  | COMPLETED | 1 |  |  | 070315S00070 | 15HK0055 | 2015-07-14 | 2015-08-10 | 2015-08-14 | 2015-08-19 | 2015-08-28 | LEGACY CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Negros Oriental | 189518 | Pinayon-an Elementary School | MABINAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00175 | 15HK0091 | 2015-08-18 | 2015-08-28 | 2015-09-04 | 2015-09-11 | 2015-09-18 | GIMP VENTURES
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303272 | San Antonio NHS | SIBULAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00068 | 15HK0061 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-19 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 |  |  | 070315S00139 | 0703-15-S-00139 | 2015-09-15 | 2015-09-21 | 2015-09-29 | 2015-10-09 | 2015-10-19 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312928 | Siapo HS | SAN JOSE | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6374337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312945 | Sibulan NHS - Balugo Ext. | SIBULAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312946 | Sibulan NHS - Maslog Ext. | SIBULAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6364337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00061 | 15HK0058 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | G. UYMATIAO JR. CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312953 | Sibulan Night HS | SIBULAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312944 | Sibulan Science HS | SIBULAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00063 | 15HK0039 | 2015-07-14 | 2015-07-22 | 2015-07-28 | 2015-08-11 | 2015-08-18 | L.C. CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303209 | Silab Comm. HS Annex | AMLAN (AYUQUITAN) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120376 | Tadlong Elementary School | MABINAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6199337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00191 | 0703-15-S-00191 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-04 | 2015-11-11 | GIMP CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120440 | Tampi Elementary School | SAN JOSE | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6194337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00194 | 0703-15-S-00194 | 2015-11-13 | 2015-11-20 | 2015-11-23 | 2015-12-03 | 2015-12-11 | JOSHUA ENGINEERING
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303278 | Tampi NHS | SAN JOSE | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070315S00135 | 15HK0047 | 2015-07-14 | 2015-08-10 | 2015-08-14 | 2015-08-21 | 2015-08-28 | C. LARA CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303248 | Tara PCHS | MABINAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8309965.051 |  |  | COMPLETED | 1 |  |  | 070315S00065 | 15HK0056 | 2015-07-14 | 2015-08-10 | 2015-08-14 | 2015-08-20 | 2015-08-28 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312948 | Tubigon HS | SIBULAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00033 | 15HK0038 | 2015-07-14 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Bayawan City | 303218 | Actin NHS | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303205 | Amio NHS | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6374337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00074 | 15HL0041 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303226 | Antonio B. Alejado MNHS (Mag-aso HS) | DAUIN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00077 | 15HL0045 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312909 | Apo Island HS | DAUIN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00078 | 15HL0046 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303224 | Apolinar B. Macias MHS (Casile NHS) | DAUIN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00104 | 15HL0045 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial HS (Cabangahan HS) | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303206 | Avocado CHS | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00091 | 15HL0049 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120606 | Balabag Elementary School | VALENCIA (LUZURRIAGA) | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00170 | 15HL0061 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-07-31 | BIGFOOT CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | NIR | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1 |  |  | 070315S00119 | 15HL0028 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312908 | Balugo NHS | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1 |  |  | 070315S00120 | 15HL0026 | 2015-07-15 | 2015-07-16 | 2015-07-27 | 2015-07-29 | 2015-07-31 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312918 | Buntod HS | BACONG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00121 | 15HL0035 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | GLUBROS DEVELOPMENT INC.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120448 | Cabangahan Elementary School | SIATON | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00172 | 15HL0059 | 2015-07-08 | 2015-07-09 | 2015-07-21 | 2015-07-25 | 2015-07-31 | ZION CONSTRUCTION(FORMERLY MASTERPIECE CONST. & SU
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120111 | Cabigti-an ES | BASAY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312940 | Cambonbon NHS | SIATON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1968606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00123 | 15HL0043 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303250 | Casiano Z. Napigkit NHS (Manalongon NHS) | SANTA CATALINA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15002518.84 |  |  | COMPLETED | 1 |  |  | 070315S00147 | 15HL0071 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-18 | 2015-11-24 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312970 | Caticugan High School | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00118 | 15HL0042 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312929 | Cawitan HS | SANTA CATALINA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120508 | Danao Elementary School | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00224 | 15HL0085 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | R.R. GADINGAN CONSTRUCTION | due to peace in order and harassment of workers
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303225 | Dauin NHS | DAUIN | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14937518.84 |  |  | COMPLETED | 1 |  |  | 070315S00148 | 15HL0065 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-18 | 2015-11-24 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312920 | Dauin Science HS | DAUIN | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00126 | 15HL0048 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120531 | Elias R. Macias Memorial Elementary School | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6269337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00202 | 15HL0090 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | R.R. GADINGAN CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312921 | Froilan A. Alanano MHS | DAUIN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00128 | 15HL0046 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312941 | Giligaon HS | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00129 | 15HL0043 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312956 | Gregorio Elmaga MHS | ZAMBOANGUITA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 189525 | Hagikhik PS | SIATON | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303236 | Jose Marie Locsin MHS (Mayabon HS) | ZAMBOANGUITA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070315S00131 | 15HL0027 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Negros Oriental | 189529 | Kabangkalan ES | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312933 | Kakha HS | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00132 | 15HL0032 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120447 | Lindy Pajunar MES (Bondo ES) | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6199337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00207 | 15HL0087 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | BIGFOOT CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303269 | Lorenza P. Palarpalar MHS (Bonbonon PCHS) | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070314S00071 | 14HL0039 | 2014-11-05 | 2014-11-14 | 2014-11-18 | 2014-11-28 | 2014-12-11 | BIGFOOT CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | NIR | Bayawan City | 303220 | Maglinao NHS | BASAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 |  |  | 070315S00133 | 15HL0029 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312969 | Mainit High School | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00124 | 15HL0031 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070315S00108 | 15HL0031 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312939 | Mantiquil Masaligan HS | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303252 | Maria Macahig NHS | SIATON | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14947518.84 |  |  | COMPLETED | 1 |  |  | 070315S00153 | 15HL0066 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312932 | Milagrosa HS | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | [10 empty] | abandoned
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312931 | Nagbinlod HS | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00106 | 15HL0034 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-27 | 2015-07-07 | UY CONDEV CORPORATION (FORMERLY:UY CONSTRUCTION &
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303264 | Obat HS | SANTA CATALINA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14967518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8259965.051 |  |  | COMPLETED | 1 |  |  | 070315S00107 | 15HL0036 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00117 | 15HL0042 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120473 | Pagang Elemetary School | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00200 | 15HL0088 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | TRINITY CONSTRUCTION AND DEVELOPMENT
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312968 | Palayuhan High School | SIATON | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00109 | 15HL0044 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312912 | Pedro R. Abul MHS | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Negros Oriental | 303262 | Pulangbato National High School | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120066 | Sacsac ES | BACONG | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00198 | 15HL0092 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | CTG CONSTRUCTION & ENTERPRISES
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120539 | San Isidro Elementary School | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6299337.6381 |  |  | REVERTED | 0 |  |  | 070315S00203 | 15HL0091 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | ZPM GENERAL MERCHANDISE | abandoned; inaccessible road
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312934 | San Miguel HS | SANTA CATALINA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6404337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00111 | 15HL0049 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303266 | San Miguel NHS | BACONG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 070315S00112 | 15HL0037 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 |  |  | 070315S00113 | 15HL0038 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303268 | Siaton NHS | SIATON | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14937518.84 |  |  | COMPLETED | 1 |  |  | 070315S00149 | 15HL0067 | 2015-10-28 | 2015-10-29 | 2015-11-10 | 2015-11-18 | 2015-11-24 | PHILSOUTH BUILDERS (FORMERLY: LOTIFF CONSTRUCTION)
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312914 | Siaton Science HS | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00114 | 15HL0040 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | C.S. RAYOS CONSTRUCTION & GENERAL SERICES, INC.
NC 2015 | TECHVOC (2015) | NIR | Negros Oriental | 303265 | Sta. Catalina National High School | SANTA CATALINA | 3 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303265 | Sta. Catalina NHS | SANTA CATALINA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14932518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312935 | Sta. Catalina Science HS | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14937518.84 |  |  | COMPLETED | 1 |  |  | 070315S00150 | 15HL0068 | 2015-12-16 | 2015-12-17 | 2015-12-24
NC 2015 | K10 (2015) | NIR | Negros Oriental | 120479 | Talaptap Elementary School | SIATON | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6419337.6381 |  |  | REVERTED | 0 |  |  | 070315S00201 | 15HL0089 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-11-04 | 2015-11-11 | ZPM GENERAL MERCHANDISE | abandoned; hinterland project/manual hauling of materials
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312930 | Tamlang HS | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 303291 | Valencia NHS (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10452131.51 |  |  | COMPLETED | 1 |  |  | 070315S00041 | 15HL0030 | 2015-06-10 | 2015-06-11 | 2015-06-23 | 2015-06-27 | 2015-07-07 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312958 | Valencia NHS-Dobdob Ext. | VALENCIA (LUZURRIAGA) | 3 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00006 | 15HL0047 | 2015-05-27 | 2015-05-28 | 2015-06-09 | 2015-06-27 | 2015-07-07 | VVER CONSTRUCTION
NC 2015 | TECHVOC (2015) | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Sagay City | 117712 | Cesar Gamboa ES | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 060615S00049 | 15GK0108 | 2015-09-09 | 2015-09-09
NC 2015 | TECHVOC (2015) | NIR | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2449549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Sagay City | 500039 | Serafin V. Aguilar Integrated School | SAGAY CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2058606 |  |  | COMPLETED | 1 |  |  | 060615S00138 | 15GK0127 | 2015-10-20 | 2015-10-21 | 2015-11-04 | 2015-11-11 | 2015-11-20 | A.F.G CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2015 | SHS (2015) | NIR | Sagay City |  | SNHS-Brgy. Lopez Jaena Ext. | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Sagay City |  | SNHS-Brgy. Rizal Ext. | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | NIR | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4879098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00144 | 15HK0041 | 2015-07-14 | 2015-08-10 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Tanjay City | 120547 | Cangkue Elementary School | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070315S00167 | 15HK0081 | 2015-08-18 | 2015-08-31 | 2015-09-04 | 2015-09-11 | 2015-09-18 | RICHFIELD BUILDERS
NC 2015 | K10 (2015) | NIR | Tanjay City | 120550 | Doña Loreto Ledesma Mapa (Nagsala ES) | CITY OF TANJAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 070315S00168 | 15HK0093 | 2015-08-04 | 2015-08-25 | 2015-08-27 | 2015-09-03 | 2015-09-14 | TSD BUILDERS CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | NIR | Tanjay City | 312911 | Hunop HS | PAMPLONA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6424337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Tanjay City | 312915 | Inawasan PCHS | PAMPLONA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070315S00137 | 15HK0041 | 2015-08-06 | 2015-09-01 | 2015-09-04 | 2015-09-11 | 2015-09-18 | R.E. SINGSON CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Tanjay City | 303274 | Isidoro Salma MHS (Balayong ) | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | NIR | Tanjay City | 234008 | Julian Calibo Memorial School | CITY OF TANJAY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4672048.49 |  |  | COMPLETED | 1 |  |  | 070315S00199 | 0703-15-S-00199 | 2015-09-29 | 2015-10-12 | 2015-10-21 | 2015-11-04 | 2015-11-11 | SILLIMAN AVENUE CONST & SUPPLY (FORMERLY OVERDRIVE
NC 2015 | SHS (2015) | NIR | Tanjay City | 303284 | Lourdes L. del Prado MNHS | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Tanjay City | 303285 | Lourdes L. del Prado MNHS ( Bahian) | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6719337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00013 | 15HK0065 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10817131.51 |  |  | COMPLETED | 1 |  |  | 070315S00152 | 0703-15-S-00152 | 2015-09-22 | 2015-10-13 | 2015-10-21 | 2015-11-03 | 2015-11-11 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Ni¤o) | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00012 | 15HK006 | 2015-07-14 | 2015-08-10 | 2015-08-11 | 2015-08-20 | 2015-08-28 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Tanjay City | 303286 | Novallas High School | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10487131.51 |  |  | REVERTED | 0 |  |  | 070315S00010 | 0703-15-S-00010
NC 2015 | SHS (2015) | NIR | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14957518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Tanjay City | 303273 | Sta. Agueda NHS | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | NIR | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 070315S00142 | 15HK0050 | 2015-07-14 | 2015-08-10 | 2015-08-14 | 2015-08-21 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Tanjay City | 303279 | Tanjay Legislated HS | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 070315S00002 | 15HK0067 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | RICHFIELD BUILDERS
NC 2015 | SHS (2015) | NIR | Tanjay City | 303280 | Tanjay NHS (Opao) | CITY OF TANJAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 070315S00003 | 15HK0049 | 2015-07-14 | 2015-08-10 | 2015-08-12 | 2015-08-20 | 2015-08-28 | L.C. CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Tanjay City | 303283 | Tanjay Science HS | CITY OF TANJAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 070315S00004 | 0703-15-S-00004 | 2015-08-26 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-19 | VESA ENGINEERING AND CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303303 | Basac National High School | LARENA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6329337.6381 |  |  | COMPLETED | 1 |  |  | 070415S00003 | 15HM-0053 | 2015-06-17 | 2015-06-26 | 2015-09-29 | 2015-10-12 | 2015-10-15 | NALE CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Siquijor | 120691 | Caipilan Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070415S00013 | 15HM-0065 | 2015-07-24 | 2015-07-31 | 2015-08-11 | 2015-09-01 | 2015-09-04 | TEKNIBUILD CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303293 | Campalanas National High School | LAZI | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 2827592 |  |  | COMPLETED | 1 |  |  | 070415S00014 | 15HM-0070 | 2015-08-17 | 2015-08-20 | 2015-09-01 | 2015-10-12 | 2015-10-15 | BRB2 CONSTRUCTION & SUPPLY, CO.
NC 2015 | SHS (2015) | NIR | Siquijor | 303304 | Candaping High School | MARIA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1 |  |  | 070415S00004 | 15HM-0054 | 2015-06-17 | 2015-06-19 | 2015-08-03 | 2015-08-11 | 2015-08-14 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00005 | 15HM-0055 | 2015-06-17 | 2015-06-19 | 2015-08-03 | 2015-08-11 | 2015-08-14 | MBM CONSTRUCTION
NC 2015 | K10 (2015) | NIR | Siquijor | 190008 | Cantugbas PS | MARIA | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6219337.6381 |  |  | COMPLETED | 1 |  |  | 070415S00015 | 15HM-0071 | 2015-08-14 | 2015-08-21 | 2015-09-01 | 2015-11-06 | 2015-11-11 | BRB2 CONSTRUCTION & SUPPLY, CO.
NC 2015 | SHS (2015) | NIR | Siquijor | 303305 | Catulayan National High School | SAN JUAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00012 | 15HM-0056 | 2015-06-17 | 2015-06-19 | 2015-10-07 | 2015-10-14 | 2015-10-19 | NALE CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00010 | 15HM-0057 | 2015-06-17 | 2015-06-19 | 2015-09-29 | 2015-10-12 | 2015-10-15 | 8G CONSTRUCTION AND GENERAL SERVICES
NC 2015 | SHS (2015) | NIR | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00008 | 15HM-0058 | 2015-06-17 | 2015-06-19 | 2015-08-03 | 2015-08-10 | 2015-08-14 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303295 | Leon Parami High School | LAZI | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 070415S00009 | 15HM-0059 | 2015-06-17 | 2015-06-19 | 2015-09-29 | 2015-10-12 | 2015-10-15 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303298 | San Antonio National High School | SIQUIJOR (Capital) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 070415S00006 | 15HM-0052 | 2015-06-17 | 2015-06-19 | 2015-06-23 | 2015-07-08 | 2015-07-13 | VVER CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00007 | 15HM-0060 | 2015-06-17 | 2015-06-19 | 2015-07-09 | 2015-08-07 | 2015-08-14 | MBM CONSTRUCTION
NC 2015 | SHS (2015) | NIR | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 070415S00011 | 15HM-0061 | 2015-06-17 | 2015-06-19 | 2015-09-29 | 2015-10-12 | 2015-10-15 | NALE CONSTRUCTION
NC 2016 | SHS | NIR | Bacolod City | 302700 | Alangilan Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 67836000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302701 | Bacolod City Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302702 | Barangay Singcang-Airport Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33490440 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302703 | Bata National High School | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33575440 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47296129.59 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302705 | Domingo Lacson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302706 | Emiliano Lizares Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 117484 | Estefania Es | Bacolod City (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22253143.62 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 500190 | Fr. Gratian Murray, Afsc Is | Bacolod City (Capital) | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16942800 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302712 | Handumanan Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 3 CL | 66980000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302713 | Jovito H. Sayson Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2448130 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302709 | Luis Hervias Nhs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302711 | Luisa Medel Nhs | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 311201 | M. G. Medalla Integrated School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302710 | Mandalagan National High School | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34318179.297 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302714 | Mansilingan Agro-Ind. Hs | Bacolod City (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bacolod City | 302704 | Romanito Maravilla Nhs | Bacolod City (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16703510.712 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 40 | 4STY20CL | BATCH 9 CL | 66980000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bacolod City | 302716 | Sum-Ag National High School | Bacolod City (Capital) | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5379660 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bacolod City | 302718 | Teofilo M. Gensoli Sr. Nhs | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8471400 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 117524 | Mailum Es | Bago City | 4 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 117516 | R. M. Salas Es | Bago City | 4 | 1 | 4 | 1STY2CL | BATCH 5 CL | 3877212.08 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 15 | 3STY15CL | BATCH 3 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bago City | 302720 | Ramon Torres Dulao Nhs | Bago City | 4 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302724 | Ramon Torres Louisiana Nhs | Bago City | 4 | 1 | 30 | 3STY15CL | BATCH 1 CL | 43187226.9 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16429930.12 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302721 | Ramon Torres Maao Sugar Central Nhs | Bago City | 4 |  | 16 | 1STY4CL | BATCH 5 CL | 14671875.152 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302722 | Ramon Torres Malingin Nhs | Bago City | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 21754685.18 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302719 | Ramon Torres Nhs | Bago City | 4 | 1 | 40 | 4STY20CL | BATCH 1 CL | 63890580.54 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.06 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bago City | 302723 | Ramon Torres Sagasa Nhs | Bago City | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2417461.96 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bago City | 302725 | Ramon Torres Taloc Nhs | Bago City | 4 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 117571 | Cadiz Viejo Es | Cadiz City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 117573 | Caduha-An Es | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302728 | Caduha-An Nhs | Cadiz City | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302729 | Caduha-An Nhs - Andres Bonifacio Ext. Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6430000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 311401 | Caduha-An Nhs - Luna Ext. Hs | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814741 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 53085903.72 |  |  | Reverted | 0
NC 2016 | K10 | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs | Cadiz City | 2 |  | 15 | 3STY15CL | BATCH 9 CL |  |  |  | Reverted | 0
NC 2016 | K10 | NIR | Cadiz City | 311405 | Dr. Vicente F. Gustilo Memorial Nhs - Daga Ext. Hs To Banquerohan Nhs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6563273 |  |  | Reverted | 0
NC 2016 | SHS | NIR | Cadiz City | 302736 | Jerusalem National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 9834608.3325 |  |  | Completed | 1
NC 2016 | SHS | NIR | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11980076.8509 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Cadiz City | 302731 | Mabini National High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2427000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 311403 | Mabini Nhs - Alimatoc Ext. Hs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12100076.8509 |  |  | Completed | 1
NC 2016 | SHS | NIR | Cadiz City | 302727 | Sicaba National High School | Cadiz City | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Cadiz City | 302732 | Sped High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2505684.72 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302732 | Sped Hs | Cadiz City | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302733 | Tiglawigan Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Cadiz City | 302734 | Tiglawigan Nhs - Magsaysay Extension High School | Cadiz City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2552371.2576 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 117556 | Tres Andanas Es | Cadiz City | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1934741 |  |  | Completed | 1
NC 2016 | K10 | NIR | Cadiz City | 302735 | Villacin Nhs | Cadiz City | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | K10 | NIR | Escalante City | 325602 | Buenavista Nhs - Langub Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Escalante City | 302625 | Escalante Nhs | City Of Escalante | 1 | 1 | 16 | 2STY8CL | BATCH 13 CL | 24300153.698 |  |  | Completed | 1
NC 2016 | K10 | NIR | Escalante City | 325603 | Escalante Nhs - Pinapugasan Ext. | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2090000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Escalante City | 302660 | Mabini Nhs | City Of Escalante | 1 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12950000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Escalante City | 302626 | Old Poblacion Nhs | City Of Escalante | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117854 | Amian Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13398000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 |  | 12 | 2STY12CL | BATCH 3 CL | 15324000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302785 | Bantayan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2479549.27 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 38844537.58 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302786 | Binicuil National High School | City Of Kabankalan | 6 |  | 6 | 3STY6CL | BATCH 1 CL | 11017131.51 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11225000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302792 | Camansi Nhs | City Of Kabankalan | 6 |  | 6 | 2STY6CL | BATCH 5 CL | 8476000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117879 | Candiacap Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117836 | Carol-An Es | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 3056000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2617000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2153800 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302787 | Carol-An Nhs | City Of Kabankalan | 6 |  | 4 | 1STY4CL | BATCH 9 CL | 4075500 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1958000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117837 | Casipsipan Es | City Of Kabankalan | 6 |  | 3 | 1STY3CL | BATCH 5 CL | 2831000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117881 | Dacongcogon Elementary School | City Of Kabankalan | 6 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2931000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8416000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 18 | 3STY9CL | BATCH 5 CL | 30602000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302793 | Florentino Galang Sr. National High School | City Of Kabankalan | 6 |  | 12 | 3STY12CL | BATCH 5 CL | 18462000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 312103 | Hinapunan Integrated School | City Of Kabankalan | 6 | 1 | 5 | 1STY5CL | BATCH 5 CL | 4869000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302794 | Inapoy Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117844 | Mansumbil Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117846 | Noac Elementary School | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2108000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8396000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302798 | Pinaguinpinan Nhs | City Of Kabankalan | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4899098.54 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117850 | Pres. Osmena Es | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2158000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117891 | Sagumayon Ps | City Of Kabankalan | 6 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1210000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2689549.27 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302797 | Tabugon National High School | City Of Kabankalan | 6 | 1 | 24 | 3STY12CL | BATCH 1 CL | 39564537.58 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302799 | Tabugon Nhs - Tagoc Ext. | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302790 | Tagukon Nhs | City Of Kabankalan | 6 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2058000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782268.79 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302800 | Tampalon National High School | City Of Kabankalan | 6 |  | 4 | 2STY4CL | BATCH 1 CL | 6902000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 117853 | Tan-Awan Es | City Of Kabankalan | 6 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3855000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 10 | 2STY10CL | BATCH 1 CL | 14198000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 312101 | Tan-Awan National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 12 | 3STY12CL | BATCH 1 CL | 19782000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 |  | 8 | 2STY8CL | BATCH 1 CL | 12025000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Kabankalan City | 302801 | Tapi National High School | City Of Kabankalan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2559549.27 |  |  | Completed | 1
NC 2016 | K10 | NIR | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 | 1 | 32 | 2STY8CL | BATCH 9 CL | 45627903.56 |  |  | Completed | 1
NC 2016 | K10 | NIR | La Carlota City | 302751 | Dona H.S.Benedicto Nhs | La Carlota City | 4 |  | 12 | 2STY6CL | BATCH 9 CL | 16799979.18 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental |  | Shs In Calatrava, Negros Occidental | Calatrava | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental |  | Shs In Calatrava, Negros Occidental | Calatrava | 0 | 1 | 12 | 2STY12CL | BATCH 13 CL | 16022138.8978 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302684 | Andres Gumban Mnhs | Toboso | 1 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302597 | Bug-Ang National High School | Toboso | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 16690460.712 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302613 | Col. Griffin National High School | Calatrava | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6499337.64 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117406 | Hayangon Elementary School | Toboso | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2089214.1914 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302604 | Laga-An National High School | Calatrava | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23626314.795 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302604 | Laga-An National High School | Calatrava | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2425000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302683 | San Enrique Hs | San Enrique | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2564500 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302683 | San Enrique Hs | San Enrique | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8215000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. Nhs | Salvador Benedicto | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302693 | Toboso Nhs | Toboso | 1 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302693 | Toboso Nhs | Toboso | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302662 | Manapla Nhs | Manapla | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 23900153.7017 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117275 | Balasyang Elementary School To Alegria Es | Murcia | 3 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2997910.9364 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302609 | Cansilayan Nhs | Murcia | 3 | 1 | 12 | 2STY12CL | BATCH 9 CL | 16022138.8978 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302621 | Enrique B. Magalona Nhs | Enrique B. Magalona (Saravia) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 180526 | Hda. Puyas Elementary School | Murcia | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer Sof (Tasof) (Under The Reg'L Office) | City Of Talisay | 3 | 1 | 20 | 2STY10CL | BATCH 9 CL | 28066882.2047 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302659 | Lopez Jaena Nhs | Murcia | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6350000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302670 | Murcia National High School | Murcia | 3 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18042923.11 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302667 | Negros Occ National Science Hs | City Of Victorias | 3 | 1 | 24 | 3STY12CL | BATCH 9 CL | 40058991.338 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302667 | Negros Occ National Science Hs | City Of Victorias | 3 |  | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302678 | Rafael B. Lacson Nhs | City Of Talisay | 3 | 1 | 48 | 4STY24CL | BATCH 9 CL | 78281765.708 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302685 | San Isidro Nhs (Pontevedra) | Pontevedra | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 |  | 45 | 3STY15CL | BATCH 9 CL | 70518944.385 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 |  | 36 | 2STY12CL | BATCH 9 CL | 48066416.6933 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302695 | Victorias National High School | City Of Victorias | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7251000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302592 | Biao Nhs | Binalbagan | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2460000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302602 | Cabacungan Nhs | La Castellana | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117263 | Guinpana-An Es | Moises Padilla (Magallon) | 5 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117232 | Jose Soriano Es To Don Felix Robles Es | La Castellana | 5 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302654 | Libas Nhs | Isabela | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2520000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302590 | Andulauan Nhs - Ilog Poblacion Ext. | Ilog | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.06 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 116958 | Basak Es | Cauayan | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8376300 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302600 | Bilbao Uybico Nhs | Hinoba-An (Asia) | 6 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302600 | Bilbao Uybico Nhs | Hinoba-An (Asia) | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302593 | Bocana Nhs | Ilog | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302594 | Bocana Nhs - Galicia Ext. | Ilog | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302594 | Bocana Nhs - Galicia Ext. | Ilog | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | Hinoba-An (Asia) | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8264965.06 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117148 | Damutan Es | Hinoba-An (Asia) | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11198810 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302629 | Eva J. Montilla Nhs | Cauayan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117357 | Genaro P. Alvarez Elementary School | City Of Sipalay | 6 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Occidental | 117357 | Genaro P. Alvarez Elementary School | City Of Sipalay | 6 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302636 | Gil Montilla Nhs - Camindangan Ext. | City Of Sipalay | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8314965.06 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302636 | Gil Montilla Nhs - Camindangan Ext. | City Of Sipalay | 6 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4854000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302639 | Gil Montilla Nhs - Crossing Tanduay Ext. | City Of Sipalay | 6 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2046214.1914 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302639 | Gil Montilla Nhs - Crossing Tanduay Ext. | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302642 | Guiljungan Nhs - Abaca Ext. | Cauayan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302651 | Hinigaran Nhs | Hinigaran | 6 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62206000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302661 | Juan Gequillana Nhs (Manalad Nhs) | Ilog | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302664 | Nabulao Nhs | City Of Sipalay | 6 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302664 | Nabulao Nhs | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302666 | Nabulao Nhs - Maricalum Ext. | City Of Sipalay | 6 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302666 | Nabulao Nhs - Maricalum Ext. | City Of Sipalay | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Occidental | 302608 | Quirico G. Manzano Nhs | Candoni | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2470000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302633 | Sipalay City National High School | City Of Sipalay | 6 | 1 | 12 | 2STY12CL | BATCH 9 CL | 14579217.18 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Occidental | 302688 | Tabu Nhs | Ilog | 6 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 48970442.044 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302762 | Bato National High School | Sagay City | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8916630.47 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Sagay City | 302762 | Bato National High School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City | 117725 | Baviera Es | Sagay City | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302768 | Bulanon National High School | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 28292601 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City | 302763 | Campo Bago Nhs | Sagay City | 2 |  | 2 | 1STY2CL | BATCH 3 CL | 2088607 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20150000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Sagay City | 302764 | Colonia Divina Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2464550 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | Sagay City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429550 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302766 | Himogaan Baybay Integrated School | Sagay City | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 23477167 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302767 | Sagay Nhs | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 37473468 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City |  | Shs, Sagay City | Sagay City | 2 | 1 | 64 | 4STY32CL | BATCH 9 CL | 97940884.088 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Sagay City |  | Shs, Sagay City | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7288650 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City |  | Snhs-Lopez Jaena Ext. | Sagay City | 2 | 1 | 24 | 4STY24CL | BATCH 1 CL | 37473468 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City |  | Snhs-Rizal Ext. | Sagay City | 2 | 1 | 18 | 3STY9CL | BATCH 1 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | NIR | Sagay City | 117705 | Suyac Es | Sagay City | 2 | 1 | 2 | 2STY2CL | BATCH 9 CL | 4785541.84 |  |  | Completed | 1
NC 2016 | SHS | NIR | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 25032312 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Sagay City | 302771 | Vito Nhs | Sagay City | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7251000 |  |  | Completed | 1
NC 2016 | K10 | NIR | San Carlos City | 302774 | Don Carlos Ledesma Nhs | San Carlos City | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | San Carlos City | 302775 | Julio Ledesma Nhs | San Carlos City | 1 | 1 | 12 | 3STY6CL | BATCH 13 CL | 22100000 |  |  | Completed | 1
NC 2016 | SHS | NIR | San Carlos City | 302776 | Quezon Nhs | San Carlos City | 1 | 1 | 12 | 2STY12CL | BATCH 3 CL | 15006508.15 |  |  | Completed | 1
NC 2016 | SHS | NIR | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3850000 |  |  | Completed | 1
NC 2016 | SHS | NIR | San Carlos City | 302777 | Sipaway Nhs | San Carlos City | 1 |  | 5 | 1STY5CL | BATCH 3 CL | 4650000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 | 1 | 48 | 4STY24CL | BATCH 9 CL | 77100000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Silay City | 302780 | Doña Montserrat Lopez Memorial High School | Silay City | 3 |  | 48 | 4STY16CL | BATCH 9 CL | 80107408.26 |  |  | Completed | 1
NC 2016 | K10 | NIR | Silay City | 117826 | Sibato Integrated School | Silay City | 3 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1188254.6197 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bais City | 303212 | Bais City National High School | Bais City | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29605866.712 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22306281.62 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bais City | 303212 | Bais City National High School | Bais City | 2 |  | 16 | 4STY8CL | BATCH 11 CL | 29841708.82 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bais City | 303215 | Lonoy National High School | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bais City | 323007 | Mansangaban National Hs | Bais City | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2685555.5556 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bais City | 323012 | Mayor Praxedes P. Villanueva Ii Memorial High School | Bais City | 2 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1846080.17 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bais City | 120103 | Mayor Praxedes P. Villanueva Ii Memorial High School To Sab-Ahan Es | Bais City | 2 |  | 3 | 1STY3CL | BATCH 11 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321911 | Abundio Agarpao, Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2770365.4 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303218 | Actin National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10550902.144 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6640355.0552 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321908 | Antonio M. Lacson Sr. Memorial High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2471055.836 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 232001 | Baican Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2195835.6105 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bayawan City | 303219 | Bal-Os National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10794673.288 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321901 | Banaybanay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2834174.2 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303221 | Bayawan National High School | Bayawan City | 3 |  | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303238 | Bugay National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 120146 | Canabuan Elementary School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6710417.7692 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14492541.4582 |  |  | Reverted | 0 | [10 empty] | Reverted: The project is included in the CY 2018 BEFF
NC 2016 | TECHVOC | NIR | Bayawan City | 321912 | Cansumalig High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2616153.08 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 33888650.3943 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303227 | Dawis National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2914753.96 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 120153 | Hag-Um Primary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2147202.5861 |  |  | Reverted | 0 | [10 empty] | Reverted due to Failure of Bidding for the 5th Times
NC 2016 | K10 | NIR | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9031942.4637 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303239 | Kalamtukan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2627533.256 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303237 | Kalumboyan National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 120158 | Kangkawit Elementary School | Bayawan City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2160525.0915 |  |  | Completed | 1
NC 2016 | SHS | NIR | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11221272.79 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321905 | Lapay High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15236894.0284 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321909 | Malabugas High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2687150.44 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11322844.1 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303240 | Manduaw National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10672787.716 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321903 | Minaba National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2519421.584 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10957187.384 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303254 | Narra National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2599082.816 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303256 | Omod National High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2775682.8 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6621247.0422 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321910 | Pagatban High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2462520.704 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7156271.404 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321906 | San Jose High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10916558.86 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303241 | Tabuan Provincial Community High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2587702.64 |  |  | Completed | 1
NC 2016 | K10 | NIR | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23296465.4882 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 303242 | Tayawan National High School | Bayawan City | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5613284.576 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Bayawan City | 321904 | Villasol High School | Bayawan City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2892665.6 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | NIR | Dumaguete City | 303168 | Dumaguete City Hs | Dumaguete City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | K10 | NIR | Dumaguete City | 303169 | Rtpm - Dumaguete Science Hs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1
NC 2016 | K10 | NIR | Dumaguete City | 303171 | Taclobo Nhs | Dumaguete City (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15095721.2 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303271 | Ajong Nhs | Sibulan | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20057722.149 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 189530 | Alagasihan Primary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303207 | Amlan National High School | Amlan (Ayuquitan) | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12034916.2399 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303207 | Amlan National High School | Amlan (Ayuquitan) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312957 | Amlan Nhs - Jugno Campus | Amlan (Ayuquitan) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6529337.64 |  |  | Completed | 1 | [10 empty] | For punchlisting on November 25.
NC 2016 | TECHVOC | NIR | Negros Oriental | 312909 | Apo Island Hs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | REVERTED | 0
NC 2016 | TECHVOC | NIR | Negros Oriental | 303224 | Apolinar B. Macias Mhs (Casile Nhs) | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120169 | Atotes Es | Bindoy | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303206 | Avocado Chs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | REVERTED | 0
NC 2016 | SHS | NIR | Negros Oriental | 303210 | Ayungon Nhs | Ayungon | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 20926500 |  |  | Terminated | 0 | [10 empty] | TERMINATED
NC 2016 | K10 | NIR | Negros Oriental | 312962 | Ayungon Nhs-(Carol-An Ext.) | Ayungon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9236461.5561 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312962 | Ayungon Nhs-(Carol-An Ext.) | Ayungon | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312949 | Ayungon Sci-Hi | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 312949 | Ayungon Sci-Hi | Ayungon | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6460600 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312908 | Balugo Nhs | Valencia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120579 | Banga Es | Tayasan | 1 | 1 | 3 | 1STY3CL | BATCH 9 CL | 2954910.9364 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303245 | Barras Annex National High School | Mabinay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6509337.99 |  |  | COMPLETED | 1
NC 2016 | K10 | NIR | Negros Oriental | 303222 | Budlasan Hs | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8565000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312918 | Buntod Hs | Bacong | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120294 | Cabang Es | Jimalalud | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6470000 |  |  | REVERTED | 0
NC 2016 | SHS | NIR | Negros Oriental | 312917 | Cabcaban Chs | Bindoy | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 14072542.8037 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312917 | Cabcaban Chs | Bindoy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Terminated | 1 | [10 empty] | Requested for COA inventory dated October 8, 2019, June 8, 2020, December 1, 2020, January 26, 2021 and submitted required documents for inspection dated April 26, 2021
NC 2016 | SHS | NIR | Negros Oriental | 312927 | Cambaloctot Hs | San Jose | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6973023.7319 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312927 | Cambaloctot Hs | San Jose | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312924 | Campanun-An Provincial Community High School | Mabinay | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12150156.98 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120350 | Campo-Aling Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1824740.17 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312913 | Candugay Hs (Siaton Nhs Annex) | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312970 | Caticugan High School | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312929 | Cawitan Hs | Santa Catalina (North District) | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9021461.555 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312929 | Cawitan Hs | Santa Catalina (North District) | 3 |  | 6 | 3STY6CL | BATCH 13 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303246 | Dahile Pchs | Mabinay | 2 | 1 | 6 | 1STY6CL | BATCH 9 CL | 4787475.839 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120357 | Danawan Elementary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303225 | Dauin Nhs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303228 | Demetrio L. Alviola Nhs | Bindoy | 1 | 1 | 24 | 3STY12CL | BATCH 7 CL | 37824000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303228 | Demetrio L. Alviola Nhs | Bindoy | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303229 | Demetrio L. Alviola Nhs-(Nalundan Annex) | Bindoy | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5859821.8728 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303229 | Demetrio L. Alviola Nhs-(Nalundan Annex) | Bindoy | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312907 | Enrique Villanueva Hs | Sibulan | 2 | 1 | 8 | 2STY4CL | BATCH 9 CL | 13018676 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120459 | Felipe Tayko Mes | Siaton (East District) | 3 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312921 | Froilan A. Alanano Mhs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312941 | Giligaon Hs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8600000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 312904 | Guba Hs | Vallehermoso | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2904910.9364 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120360 | Himocdungon Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303234 | Inapoy High School | Mabinay | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9169325.9361 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303234 | Inapoy High School | Mabinay | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303208 | Jantianon National High School | Amlan (Ayuquitan) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6985386.5109 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303235 | Jimalalud Nhs | Jimalalud | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303235 | Jimalalud Nhs | Jimalalud | 1 |  | 4 | 2STY4CL | BATCH 13 CL | 7086271.404 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312922 | Jimalalud Nhs- (Tamao Ext.) | Jimalalud | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8500000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120032 | Jose B. Cardenas Mhs (Main) To Awa-An Es | Canlaon | 1 | 1 | 2 | 1STY2CL |  | 1996214.19 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120199 | Jose B. Cardenas Mhs (Main) To Binalbagan Es | Canlaon | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5909821.87 |  |  | Completed | 1 |  |  | 16GK0106 | 16GK0106 |  | 2016-08-25 | 2016-09-02 | 2016-09-15
NC 2016 | K10 | NIR | Negros Oriental | 120580 | Jose B. Cardenas Mhs (Main) To Cambaye Es | Canlaon | 1 | 1 | 9 | 1STY3CL |  | 8864732.82 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312965 | Jose B. Cardenas Mhs (Main) To Jbcmhs-Pula Ext. | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120389 | Jose B. Cardenas Mhs (Main) To Lamogong Es | Canlaon | 1 | 1 | 3 | 1STY3CL |  | 2954910.94 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120210 | Jose B. Cardenas Mhs (Main) To Manggapa Ps | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 312966 | Jose B. Cardenas Mhs (Main) To Manjuyod Nhs- Panciao Ext. | Canlaon | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120184 | Jose B. Cardenas Mhs (Main) To Manseje Es | Canlaon | 1 | 1 | 1 | 1STY2CL |  | 1996214.19 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120591 | Jose B. Cardenas Mhs (Main) To Matuog Es | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6350000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120303 | Jose B. Cardenas Mhs (Main) To Mongpong Es | Canlaon | 1 | 1 | 1 | 1STY2CL |  | 1990000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120052 | Jose B. Cardenas Mhs (Main) To Nabhang Es | Canlaon | 1 | 1 | 2 | 1STY2CL |  | 2096214.19 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120189 | Jose B. Cardenas Mhs (Main) To Pagsalayon Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2990000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120398 | Jose B. Cardenas Mhs (Main) To Sacsac Es | Canlaon | 1 | 1 | 4 | 2STY4CL |  | 6470000 |  |  | Terminated | 1 | [10 empty] | TERMINATED
NC 2016 | K10 | NIR | Negros Oriental | 120334 | Jose B. Cardenas Mhs (Main) To Solonggon Es | Canlaon | 1 | 1 | 4 | 1STY2CL |  | 3935000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120599 | Jose B. Cardenas Mhs (Main) To Suquib Es | Canlaon | 1 | 1 | 4 | 1STY2CL |  | 1990000 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120308 | Jose B. Cardenas Mhs (Main) To Tamao Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2995428.31 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120404 | Jose B. Cardenas Mhs (Main) To Tanglad Es | Canlaon | 1 | 1 | 1 | 1STY3CL |  | 2954910.94 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120059 | Jose B. Cardenas Mhs (Main) To Tiguib Es | Canlaon | 1 | 1 | 1 | 2STY10CL |  | 3935000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120218 | Jose B. Cardenas Mhs (Main) To Upper Lumapao Es | Canlaon | 1 | 1 | 6 | 2STY6CL |  | 8565000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312963 | Jose B. Cardenas Mhs-(Tabalogo Ext.) | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8600000 |  |  | REVERTED | 0 |  |  | 16GK0071 | 16GK0071 | 2391819 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580
NC 2016 | K10 | NIR | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 | 1 | 6 | 1STY3CL | BATCH 9 CL | 5909821.8728 |  |  | Completed | 1 |  |  | 16GK0073 | 16GK0073 | 2037829 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580
NC 2016 | K10 | NIR | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1 |  |  | 16GK0080 | 16GK0080 |  | 2016-07-08 | 2016-07-15 | 2016-07-29
NC 2016 | TECHVOC | NIR | Negros Oriental | 312916 | Jose B. Cardenas Mhs-(Uptown Annex) | Canlaon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1 |  |  | 16GK0074 | 16GK0074 | 2037830 | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580
NC 2016 | TECHVOC | NIR | Negros Oriental | 312933 | Kakha Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312903 | Kausawagan Hs | Manjuyod | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14300000 |  |  | Completed | 1 |  |  | 16GK0126 | 16GK0126 |  |  | 2016-10-20 | 2016-11-03
NC 2016 | K10 | NIR | Negros Oriental | 303243 | La Liberta Tech-Voc School | La Libertad | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26845224.6319 |  |  | Completed | 1 |  |  | 16GK0070 | 16GK0070 |  | 2016-06-06 |  |  | 2016-07-13 | 42580 | SOME PUNCHLISTED ITEMS NOT YET RECTIFIED; With letter to DPWH 1st for an updates/ follow-up
NC 2016 | K10 | NIR | Negros Oriental | 189523 | Lanot Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303277 | Mabato Pchs | Ayungon | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  | 16GK0107 | 16GK0107 |  | 2016-08-26 | 2016-09-07
NC 2016 | SHS | NIR | Negros Oriental | 303244 | Mabinay National High School | Mabinay | 2 | 1 | 24 | 4STY12CL | BATCH 1 CL | 45397981.68 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312951 | Mabinay Science High School | Mabinay | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6509338 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312954 | Malaiba Hs | Canlaon | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1 |  |  | 16GK0118 | 16GK0118 |  |  | 2016-10-06 | 2016-10-18
NC 2016 | TECHVOC | NIR | Negros Oriental | 303253 | Maloh Pchs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312919 | Malongcay Dacu Hs | Dauin | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120367 | Mampalasan Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1829740.17 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312901 | Maningcao Nhs | Sibulan | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9063478.3861 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303251 | Manjuyod Nhs | Manjuyod | 1 | 1 | 24 | 3STY12CL | BATCH 9 CL | 37737000 |  |  | Completed | 1 |  |  | 16GK0086 | 16GK0086 | 2391399 | 2016-07-14 | 2016-07-21 | 2016-08-04 | 2016-08-10 | 42608
NC 2016 | SHS | NIR | Negros Oriental | 303251 | Manjuyod Nhs | Manjuyod | 1 |  | 4 | 2STY4CL | BATCH 9 CL | 6350000 |  |  | Completed | 1 |  |  | 16GK0102 | 16GK0102 |  | 2016-08-18 | 2016-08-25 | 2016-09-08
NC 2016 | K10 | NIR | Negros Oriental | 120185 | Mantahaw Es | Bindoy | 1 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2096214.1914 |  |  | Terminated | 0 |  |  | 16GK0105 | 16GK0105 | [6 empty] | TERMINATED
NC 2016 | K10 | NIR | Negros Oriental | 120185 | Mantahaw Es | Bindoy | 1 |  | 1 | 1STY1CL | BATCH 9 CL | 1100000 |  |  | Terminated | 0 |  |  | 16GK0088 | 16GK0088 |  | 2016-08-02 |  |  |  |  | TERMINATED
NC 2016 | TECHVOC | NIR | Negros Oriental | 303252 | Maria Macahig Nhs | Siaton (West District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  |  | 16GK0117 |  | 2016-09-23 | 2016-10-07
NC 2016 | SHS | NIR | Negros Oriental | 312955 | Masulog Hs | Canlaon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8264965.051 |  |  | Completed | 1 |  |  | 16GK0099 | 16GK0099 |  | 2016-08-18 | 2016-08-25 | 2016-09-08
NC 2016 | K10 | NIR | Negros Oriental | 312959 | Mayaposi Community High School | Mabinay | 2 | 1 | 16 | 2STY8CL | BATCH 9 CL | 24190839.3617 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312959 | Mayaposi Community High School | Mabinay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312932 | Milagrosa Hs | Santa Catalina (South District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303255 | Negros Oriental Nhs | Dumaguete City | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28732387.793 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303255 | Negros Oriental Nhs | Dumaguete City | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303264 | Obat Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303257 | Owacan Pchs | Jimalalud | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 9171461.555 |  |  | Completed | 1 |  |  | 16GK0100 | 16GK0100 |  | 2016-08-18 | 2016-08-25 | 2016-09-08
NC 2016 | K10 | NIR | Negros Oriental | 120305 | Pacuan Es | Jimalalud | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | REVERTED | 0
NC 2016 | SHS | NIR | Negros Oriental | 303258 | Pacuan Nhs | La Libertad | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20279495.669 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 303247 | Paniabonan High School | Mabinay | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 5702403.8743 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303247 | Paniabonan High School | Mabinay | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 12150156.9809 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312912 | Pedro R. Abul Mhs | Santa Catalina (South District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | REVERTED | 0
NC 2016 | TECHVOC | NIR | Negros Oriental | 303261 | Pinalubngan Nhs | Tayasan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1 |  |  | 16GK0078 | 16GK0078 |  | 2016-06-06 | 2016-06-24 | 2016-07-07 | 2016-07-13 | 42580
NC 2016 | SHS | NIR | Negros Oriental | 303261 | Pinalubngan Nhs | Tayasan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6600000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312960 | Pinocauan Hs | Vallehermoso | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4560000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312960 | Pinocauan Hs | Vallehermoso | 1 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16900000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120596 | Pinocawan Es | Tayasan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Terminated | 0 | [10 empty] | TERMINATED
NC 2016 | K10 | NIR | Negros Oriental | 120375 | Samac Elementary School | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312902 | Sampiniton Pchs | Manjuyod | 1 |  | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312902 | Sampiniton Pchs | Manjuyod | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12900000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 303272 | San Antonio National High School | Sibulan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6536047.22 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120435 | San Jose Provincial High School To Alicia Calumpang (Naiba Es) | San Jose | 2 | 1 | 3 | 1STY3CL |  | 3946432.02 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120435 | San Jose Provincial High School To Alicia Calumpang (Naiba Es) | San Jose | 2 |  | 2 | 1STY2CL |  | 2758293.02 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120432 | San Jose Provincial High School To Cancawas Ps | San Jose | 2 | 1 | 3 | 1STY3CL |  | 3946432.02 |  |  | REVERTED | 0
NC 2016 | SHS | NIR | Negros Oriental | 189514 | San Jose Provincial High School To Guilongsoran Ps | San Jose | 2 | 1 | 3 | 1STY3CL | BATCH 9 CL | 3946432.02 |  |  | REVERTED | 0
NC 2016 | TECHVOC | NIR | Negros Oriental | 312934 | San Miguel Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303266 | San Miguel Nhs | Bacong | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312928 | Siapo Hs | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9063478.3861 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303268 | Siaton Nhs | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | SHS | NIR | Negros Oriental | 312945 | Sibulan Nhs - Balugo Ext. | Sibulan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6973023.7319 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312944 | Sibulan Science High School | Sibulan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2507271.0901 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312935 | Sta. Catalina Science Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312942 | Sumaliring Hs [Inalad Hs] | Siaton (East District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303275 | Tagbino Nhs | Vallehermoso | 1 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1 |  |  |  | 16GK0110 |  | 2016-09-23 | 2016-10-05
NC 2016 | SHS | NIR | Negros Oriental | 303276 | Tambo Nhs | Ayungon | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8500000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 312930 | Tamlang Hs | Santa Catalina (North District) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303278 | Tampi National High School | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 7408468.5459 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303278 | Tampi National High School | San Jose | 2 |  | 8 | 2STY8CL | BATCH 9 CL | 9804608.3325 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120438 | Tapon Norte Elementary School To Siapo Es | Mabinay | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120378 | Tara Elementary School | Mabinay | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2722110.255 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303248 | Tara Provincial Community High School | Mabinay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303290 | Tayasan Nhs- (Bago Campus) | Tayasan | 1 |  | 3 | 1STY3CL | BATCH 9 CL | 2640828.124 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303290 | Tayasan Nhs- (Bago Campus) | Tayasan | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8550000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 312950 | Tayasan Science Hs | Tayasan | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 14200000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 120485 | Tubigon High School To Calabnugan Es | Sibulan | 2 | 1 | 2 | 1STY2CL |  | 2704325.77 |  |  | REVERTED | 0
NC 2016 | K10 | NIR | Negros Oriental | 120490 | Tubigon High School To Looc Es | Sibulan | 2 | 1 | 6 | 1STY3CL | BATCH 7 CL | 7862805.74 |  |  | REVERTED | 0
NC 2016 | TECHVOC | NIR | Negros Oriental | 303291 | Valencia Nhs (Valencia Tech. Sch.) | Valencia | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | NIR | Negros Oriental | 303292 | Vallehermoso Pchs | Vallehermoso | 1 | 1 | 36 | 3STY12CL | BATCH 7 CL | 56392400 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Negros Oriental | 303292 | Vallehermoso Pchs | Vallehermoso | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 9120000 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2716157.6507 |  |  | Completed | 1
NC 2016 | K10 | NIR | Tanjay City | 322303 | Nagsala Hs | City Of Tanjay | 2 | 1 | 8 | 2STY8CL | BATCH 11 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303302 | Banban National High School | Siquijor (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | NIR | Siquijor | 120657 | Banban National High School To Cabulihan Is |  | 0 | 1 | 4 | 2STY4CL |  | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303305 | Banban National High School To Catulayan Nhs |  | 0 | 1 | 4 | 2STY4CL |  | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303299 | Banban National High School To Ponong Hs |  | 0 | 1 | 4 | 1STY4CL |  | 3484886.58 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303302 | Banban National High School | Siquijor (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2432393.98 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303303 | Basac National High School | Larena | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303303 | Basac National High School | Larena | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2419429.87 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303293 | Campalanas National High School | Lazi | 0 | 1 | 16 | 2STY4CL | BATCH 9 CL | 25277350.56 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303293 | Campalanas National High School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2432515.4 |  |  | Completed | 1
NC 2016 | K10 | NIR | Siquijor | 303304 | Candaping National High School | Maria | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303304 | Candaping National High School | Maria | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2419583.56 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303296 | Cang-Alwang National High School | Siquijor (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6321810.79 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303305 | Catulayan National High School | San Juan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432556.18 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303306 | Deped-Lazi National Agricultural School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432648.13 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303297 | Enrique Villanueva National High School | Enrique Villanueva | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303297 | Enrique Villanueva National High School | Enrique Villanueva | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4836556.18 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303295 | Leon Parami High School | Lazi | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303295 | Leon Parami High School | Lazi | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2432648.13 |  |  | Completed | 1
NC 2016 | K10 | NIR | Siquijor | 120665 | Roxas Elementary School | Enrique Villanueva | 0 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1014438.63 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303298 | San Antonio National High School | Siquijor (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2432684.35 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303301 | Siquijor Provincial Science High School | Siquijor (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1817323.74 |  |  | Completed | 1
NC 2016 | SHS | NIR | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | NIR | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4862851.85 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117463 | A. Mabini ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3070000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 4 | 3000000 |  |  | Completed | 1 | [10 empty] | WITH PUNCHLISTED DEFECTS - INCOMPLETE RECTIFICATION.
NC 2017 | K10 | NIR | Bacolod City | 117478 | DoÃ±a E.J. Garcia ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4036402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117475 | Don Crispino V. Ramos ES | BACOLOD CITY (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 4 | 4036402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117493 | A. M. Espinos ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117503 | B. Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2744779.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117505 | Dr. A. Sian ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2778267.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5125243.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117506 | Gen. Juan A. Araneta ES | BAGO CITY | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117498 | J.L. Araneta Elementary School | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117507 | Jalsis ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5122999.34 |  |  | REVERTED | 0 | [10 empty] | Unfunded
NC 2017 | K10 | NIR | Bago City | 117501 | T.M. Morada Sr. ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2728267.98 |  |  | Completed | 1
NC 2017 | SHS | NIR | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3944413.41 |  |  | Completed | 1
NC 2017 | SHS | NIR | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 |  | 3 | 1STY3CL | BATCH 4 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Escalante City | 117041 | Danao Port ES | CITY OF ESCALANTE | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4068435.02 |  |  | Completed | 1
NC 2017 | TVL | NIR | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2988254.77 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Escalante City | 117043 | Escalante CES | CITY OF ESCALANTE | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5188351.15 |  |  | Completed | 1
NC 2017 | K10 | NIR | Escalante City | 117046 | Jonobjonob ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Escalante City | 302660 | Mabini National High School | CITY OF ESCALANTE | 1 | 1 | 5 | WORKSHOP BLDG (7x18) | BATCH 4 | 17929528.62 |  |  | REVERTED | 0
NC 2017 | SHS | NIR | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 4 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Escalante City | 117050 | Tamlang ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Escalante City | 302627 | Tamlang NHS | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Escalante City | 117052 | Washington ES | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117856 | Camansi ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 3978202.4 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117887 | Magballo ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2781943.14 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117892 | Salong ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2768032.36 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117893 | San Jose ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2772133.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117869 | Tabugon ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2814243.51 |  |  | Completed | 1
NC 2017 | SHS | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2780463.27 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117870 | Tagoc ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2781943.14 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 302790 | TAGUKON NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2847936.07 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117895 | Tapi ES | CITY OF KABANKALAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4018606.34 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116945 | Candoni CES | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2972243.93 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2980294.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116946 | Galicano Temporosa I Memorial Elementary School | CANDONI | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4281119.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116949 | Gatuslao ES | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2986802.37 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116950 | Guinsiliban ES | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3049605.56 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116951 | Haba ES | CANDONI | 6 | 1 | 4 | 1STY4CL | BATCH 4 | 5635798.28 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116996 | Bulata ES | CAUAYAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4377987.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117000 | Camalanda-an ES | CAUAYAN | 6 | 1 | 4 | 1STY4CL | BATCH 4 | 5515399.7 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302605 | Camalanda-an NHS | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3078254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116963 | Cauayan CES | CAUAYAN | 6 | 1 | 5 | 1STY5CL | BATCH 4 | 6712854.49 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3018254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116974 | Mambugsay ES | CAUAYAN | 6 | 1 | 5 | 1STY5CL | BATCH 4 | 6752053.49 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117006 | Masaling Elementary School | CAUAYAN | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4174792.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117011 | Si-alay ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2986644.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116989 | Tuyom ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 2966644.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117367 | Binulig ES | CITY OF SIPALAY | 6 | 1 | 5 | 1STY5CL | BATCH 4 | 6936185.86 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117372 | Canturay ES | CITY OF SIPALAY | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4299475.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117357 | Genaro P. Alvarez Elementary School | CITY OF SIPALAY | 6 | 1 | 3 | 1STY3CL | BATCH 4 | 4298290.11 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117140 | Bacuyangan ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3066254.17 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302599 | Bulwangan NHS | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3144254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117163 | Canlamay ES | ILOG | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3045587.5 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117165 | Galicia ES | ILOG | 6 | 1 | 2 | 1STY2CL | BATCH 4 | 3029254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117300 | Canroma ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2794419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117300 | Canroma ES | PONTEVEDRA | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2735664.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117312 | Carmen ES | PONTEVEDRA | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3934738.2 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117313 | Casal-agan ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2843880.28 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302611 | Catalino Soliguen NHS | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2846578.48 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117315 | Pandan ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2843880.28 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117306 | San Isidro ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2788566.3 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117306 | San Isidro ES | PONTEVEDRA | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2788566.3 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117321 | Palaka ES | PULUPANDAN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2735664.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117322 | Patic ES | PULUPANDAN | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2735664.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117324 | Pulupandan ES | PULUPANDAN | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3950811.97 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117324 | Pulupandan ES | PULUPANDAN | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117340 | Don Esperidion Presbitero ES | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2669819.78 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117341 | Don Vicente Lopez ES | SAN ENRIQUE | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5189082.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117346 | San Enrique ES | SAN ENRIQUE | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2677697.78 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117426 | Ma. Palacios Presbitero ES | VALLADOLID | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2809419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117426 | Ma. Palacios Presbitero ES | VALLADOLID | 4 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3992934.93 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117427 | Pacol Elementary School | VALLADOLID | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2809419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117428 | Tabao ES | VALLADOLID | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3892934.93 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117428 | Tabao ES | VALLADOLID | 4 |  | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3892934.93 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117428 | Tabao ES | VALLADOLID | 4 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117429 | Valladolid ES | VALLADOLID | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3967934.93 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117513 | Atipuluan ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117515 | Caridad ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2728267.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117509 | Lag-asan ES | BAGO CITY | 4 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6270334.67 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117523 | Ma-ao ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2659107.95 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bago City | 117524 | Mailum ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2778267.98 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117831 | Ballo ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2666000.64 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Kabankalan City | 117832 | Basak ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2729854.38 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2705769.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2705769.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 312103 | Hinapunan Integrated School | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2661302.64 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2651389.86 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 7 | 2724815.36 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117630 | Ayungon ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2697850.06 |  |  | Completed | 1
NC 2017 | SHS | NIR | La Carlota City | 302751 | Dona H.S.Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5241842.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117648 | La Granja ES | LA CARLOTA CITY | 4 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4089045.87 |  |  | Completed | 1
NC 2017 | SHS | NIR | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2753738.35 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117643 | Salamanca ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2750003.1 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117395 | Domingo J. Rodriguez ES | CITY OF TALISAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3313745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302617 | Don Hilarion G. Gonzaga MHS | CITY OF TALISAY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3526504.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | 4 | 1STY4CL | BATCH 7 | 5870537.15 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117025 | E. B. Magalona ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 5 | 1STY5CL | BATCH 7 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117030 | Manta-angan ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117034 | Rita Lovino ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117037 | Tanza ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117250 | VICMICO ES II | MANAPLA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3013745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117280 | Don A.R. Montelibano ES | MURCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117422 | Alijis ES | VALLADOLID | 4 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 7 | 6395977.23 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117423 | Ayungon ES | VALLADOLID | 4 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5181842.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117425 | Emilio Infante ES | VALLADOLID | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2734419.38 |  |  | Completed | 1
NC 2017 | K10 | NIR | San Carlos City | 117785 | Andres Bonifacio ES | SAN CARLOS CITY | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5488351.15 |  |  | Reverted | 0
NC 2017 | SHS | NIR | San Carlos City | 302773 | Bagonbon NHS | SAN CARLOS CITY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | San Carlos City | 117794 | Lina dela Viña Valmayor ES | SAN CARLOS CITY | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 6872950.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | San Carlos City | 117765 | San Jose ES | SAN CARLOS CITY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Silay City | 117808 | La Purisima ES | SILAY CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 3263745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Silay City | 117817 | Mambag-id ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | K10 | NIR | Silay City | 312005 | Napilas Integrated School | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Silay City | 117809 | Napilas IS (Napilas ES) | SILAY CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Silay City | 117827 | Silay North ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | K10 | NIR | Silay City | 117828 | Sto. Rosario ES | SILAY CITY | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4734532.15 |  |  | Completed | 1
NC 2017 | TVL | NIR | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3872818.75 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Escalante City | 302615 | Dian-ay National High School | CITY OF ESCALANTE | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2988254.77 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Escalante City | 117044 | Escalante ES I | CITY OF ESCALANTE | 1 | 1 | 5 | 1STY5CL | BATCH 8 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Escalante City | 117044 | Escalante ES I | CITY OF ESCALANTE | 1 |  | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Escalante City | 302660 | Mabini National High School | CITY OF ESCALANTE | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3872818.75 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7745637.5 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Kabankalan City | 117830 | Balisong ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2648618.04 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2663657.04 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117874 | Bantayan ES | CITY OF KABANKALAN | 6 |  | 2 | 1STY2CL | BATCH 8 | 2663657.04 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117876 | Binicuil ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Kabankalan City | 302792 | Camansi NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2646145.6 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117884 | Jose G. Peralta MS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2646832.8 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117871 | Tampalon ES | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2653550.94 |  |  | Completed | 1
NC 2017 | SHS | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2653550.94 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302586 | Agpangi NHS | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302586 | Agpangi NHS | CALATRAVA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3038254.17 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302586 | Agpangi NHS | CALATRAVA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 5976509.44 |  |  | REVERTED | 0
NC 2017 | SHS | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | SHS | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116922 | Harbort Elementary School | CALATRAVA | 1 | 1 | 3 | 1STY3CL | BATCH 8 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116923 | Hinab-ongan ES | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 7645637.5 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5976509.44 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3038254.17 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302604 | Laga-an National High School | CALATRAVA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 3038254.17 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Occidental | 116925 | Lemery ES | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116911 | Menchaca ES | CALATRAVA | 1 | 1 | 3 | 1STY3CL | BATCH 8 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116914 | San Isidro ES | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 5976509.54 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Occidental | 116937 | Tigbao ES | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302691 | Tigbao NHS | CALATRAVA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3038254.17 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Occidental | 116916 | Tigbon ES | CALATRAVA | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116940 | Agboy ES | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2906108.02 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | 3 | 1STY3CL | BATCH 8 | 4344337.27 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5475171.84 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2854410.2 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2851088.62 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2838711.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2838711.95 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116948 | Cantomanyog ES | CANDONI | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2884790.14 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116997 | Calaogao ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2982135.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 3100525.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116981 | Talacdan ES | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2952135.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117350 | Barangay V ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2900926.86 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117368 | Bungabunga ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 3061172.48 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117375 | Genaro P. Alvarez ES II | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 3112128.6 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117358 | Gil Montilla ES | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2898188.6 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117362 | Nabulao Elementary School | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 3023334.18 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117142 | Bilbao-Watkins ES | HINOBA-AN (ASIA) | 6 | 1 | 5 | 1STY5CL | BATCH 8 | 7784650.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117144 | C.L. Hodges Elementary School | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117149 | Daug ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117151 | Don. M. Vasquez Estate ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117157 | Paz Vda. de Escamilla ES | HINOBA-AN (ASIA) | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2941745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117176 | Enclaro ES | ILOG | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2955745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117181 | Julian P. Gomilla ES (Manalad ES) | ILOG | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2955745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117182 | Perfecto P. Cuenca MS | ILOG | 6 | 1 | 2 | 1STY2CL | BATCH 8 | 2955745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3422818.46 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302659 | Lopez Jaena NHS | MURCIA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3422818.46 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 3422818.46 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2613745.92 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Occidental | 117312 | Carmen ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL | BATCH 8 | 2756089.66 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117318 | Zamora ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 8 | 3175129.71 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117326 | Bago ES | SALVADOR BENEDICTO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117333 | Kumaliskis ES | SALVADOR BENEDICTO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117331 | Mercedes S. Ayeng ES | SALVADOR BENEDICTO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117404 | Don Nicolas A. Lizares ES | TOBOSO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117416 | Tabun-ac ES | TOBOSO | 1 | 1 | 2 | 1STY2CL | BATCH 8 | 2813745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3693957.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 6 | WORKSHOP BLDG (7x18) | BATCH 10 | 17872071.3 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5957357.9 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5957357.9 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117640 | La Carlota North ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2697850.06 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2723948.4 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3101854.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6203710.7 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6203710.7 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302752 | La Granja NHS | LA CARLOTA CITY | 4 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 7142449.08 |  |  | Completed | 1
NC 2017 | K10 | NIR | La Carlota City | 117649 | San Miguel ES I | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2723948.4 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5755805.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5755805.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3872818.75 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 302762 | Bato National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Sagay City | 117695 | Buenaventura Rodriguez ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 302768 | Bulanon National High School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3872818.75 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500037 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Sagay City | 117714 | Fabrica ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4072818.75 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 3 | WORKSHOP BLDG (7x18) | BATCH 10 | 9564763.31 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 6376509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 500038 | Himogaan Baybay Integrated School | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Sagay City | 117718 | Himogaan Baybay IS | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Sagay City | 117722 | Ricardo Gamboa | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 14691275 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 343922 | Sagay City Senior High SChool | SAGAY CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 10 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 15293500 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 |  | 6 | WORKSHOP BLDG (7x18) | BATCH 10 | 17929528.62 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4068435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Sagay City | 117708 | Tu-ong ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Sagay City | 117735 | Valeriana G. Analucas ES | SAGAY CITY | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117461 | A. Lizares ES | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24655247.73 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117461 | A. Lizares ES | BACOLOD CITY (Capital) | 0 |  | 2 | 1STY2CL | BATCH 12 | 2645505.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24678047.73 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117468 | A.L. Jayme ES | BACOLOD CITY (Capital) | 0 |  | 9 | 3STY9CL | BATCH 12 | 24688047.73 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117456 | Bata ES II | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8980904.76 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117489 | Don R. A. Medel Sr. ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 12773014.84 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117489 | Don R. A. Medel Sr. ES | BACOLOD CITY (Capital) | 0 |  | 6 | 2STY6CL | BATCH 12 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117483 | EDUCATION & TRAINING CENTER SCHOOL III | BACOLOD CITY (Capital) | 0 | 1 | 12 | 3STY12CL | BATCH 12 | 29546467.25 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Bacolod City | 117483 | EDUCATION & TRAINING CENTER SCHOOL III | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6CL | BATCH 12 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117490 | F.R. Flores ES | BACOLOD CITY (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117471 | Handumanan ES-1 | BACOLOD CITY (Capital) | 0 | 1 | 9 | 3STY9CL | BATCH 12 | 24468047.73 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117485 | Mariano G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 12 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117467 | R. Alunan ES | BACOLOD CITY (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 12 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 117474 | Vista Alegre ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 12 | 9072261.76 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3570535.96 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3972818.46 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422818.46 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3822818.46 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3822818.46 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Kabankalan City | 117834 | Bula ES | CITY OF KABANKALAN | 6 | 1 | 5 | 1STY5CL | BATCH 12 | 6422650.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116884 | Cabiti ES | BINALBAGAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116868 | Canmoros ES | BINALBAGAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 116865 | Pedro Y. Ditching, Sr. - Bagroy ES | BINALBAGAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302598 | Bulata NHS | CAUAYAN | 6 | 1 | 2 | 1STY2CL | BATCH 12 | 2943745.92 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117089 | Aguisan ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117070 | Cantupa ES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117097 | Cunalum ES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117099 | Don Marcelo G. Vasquez MES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3086816.85 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117076 | Himamaylan CS | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4550000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117079 | Mahalang ES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3086816.85 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117085 | San Antonio ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4632250.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117105 | Saraet ES | CITY OF HIMAMAYLAN | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3075000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117107 | Talaban ES | CITY OF HIMAMAYLAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4600000 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302634 | Gil Montilla NHS - Binulig Ext. | CITY OF SIPALAY | 6 | 1 | 2 | 1STY2CL | BATCH 12 | 2695990.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302667 | Negros Occ National Science High School | CITY OF VICTORIAS | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302667 | Negros Occ National Science High School | CITY OF VICTORIAS | 3 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302621 | Enrique B. Magalona NHS | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5476509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302621 | Enrique B. Magalona NHS | ENRIQUE B. MAGALONA (SARAVIA) | 3 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5476509.54 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Negros Occidental | 117127 | Cambugsa ES | HINIGARAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4550000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117113 | Hinigaran ES-A | HINIGARAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117113 | Hinigaran ES-A | HINIGARAN | 5 |  | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117115 | Macario Natividad ES | HINIGARAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4500000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117135 | Quiwi ES | HINIGARAN | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4575000 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302614 | Culipapa National High School | HINOBA-AN (ASIA) | 6 | 1 | 3 | 1STY3CL | BATCH 12 | 4018435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117198 | Amin Moises ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117186 | Bungahin ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3020629.5 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117204 | Libas ES | ISABELA | 5 | 1 | 3 | 1STY3CL | BATCH 12 | 4557250.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117194 | Marikudo Settlement ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074574.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117208 | Riverside ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3207247.21 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117209 | San Agustin ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117211 | Sikatuna ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074575.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117212 | Tinongan ES | ISABELA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3086816.85 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117215 | Biaknabato ES | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074574.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117220 | La Castellana ES | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3036816.85 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117236 | Manghanoy Elementary School | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074574.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117225 | Pacita ES | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074574.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117239 | Policena ES | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3074574.82 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117228 | Soriano ES | LA CASTELLANA | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3020629.5 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117264 | Inolingan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 2 | 1STY2CL | BATCH 12 | 3036816.85 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302591 | ANTIPOLO NATIONAL HIGH SCHOOL | PONTEVEDRA | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3592312.05 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302591 | ANTIPOLO NATIONAL HIGH SCHOOL | PONTEVEDRA | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2907747.76 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302591 | ANTIPOLO NATIONAL HIGH SCHOOL | PONTEVEDRA | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2907747.76 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302611 | Catalino Soliguen NHS | PONTEVEDRA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3620982.24 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302611 | Catalino Soliguen NHS | PONTEVEDRA | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2898057.76 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302611 | Catalino Soliguen NHS | PONTEVEDRA | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5796116.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302611 | Catalino Soliguen NHS | PONTEVEDRA | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5796116.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5675041.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5675041.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302685 | San Isidro NHS | PONTEVEDRA | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2898057.76 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302624 | Enriqueta Montilla De Esteban MHS | PULUPANDAN | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2857478.16 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302624 | Enriqueta Montilla De Esteban MHS | PULUPANDAN | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302624 | Enriqueta Montilla De Esteban MHS | PULUPANDAN | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5714957.12 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS | SALVADOR BENEDICTO | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3521167.16 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3502127.65 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5591446.72 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2913745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302684 | Andres Gumban MNHS | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302597 | Bug-ang National High School | TOBOSO | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302597 | Bug-ang National High School | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117407 | Labilabi Elementary School | TOBOSO | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 9564763.31 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Completed | 1
NC 2017 | TVL | NIR | Sagay City | 302771 | Vito National High School | SAGAY CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3872818.75 |  |  | Completed | 1
NC 2017 | TVL | NIR | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422318.75 |  |  | Reverted | 0
NC 2017 | TVL | NIR | San Carlos City | 302775 | Julio Ledesma National High School | SAN CARLOS CITY | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5976509.54 |  |  | Reverted | 0
NC 2017 | TVL | NIR | San Carlos City | 302777 | Sipaway National High School | SAN CARLOS CITY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 3038254.17 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Silay City | 302780 | DoÃ±a Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3422818.75 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Bacolod City | 181005 | Handumanan ES II | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY6CL | BATCH 13 | 13935375.1 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bacolod City | 302669 | Felizardo C. Lipana NHS (Sta. Rita HS) | BACOLOD CITY (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 13 | 31824789.72 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 20 | 4STY20CL | BATCH 13 | 41513409.74 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 2 | 1STY2CL | BATCH 13 | 2789745.92 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 16 | 4STY16CL | BATCH 13 | 37120737.96 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302720 | Ramon Torres Dulao NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 13 | 8572434.48 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302724 | Ramon Torres Louisiana NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3570535.96 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 3 | WORKSHOP BLDG (7x18) | BATCH 13 | 8572434.48 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302721 | Ramon Torres Ma-ao Sugar Central NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976703.05 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302722 | Ramon Torres Malingin National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3647901.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5914533.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5914533.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302723 | Ramon Torres Sagasa National High School | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.55 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 13 | 2976702.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302685 | San Isidro NHS | PONTEVEDRA | 4 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5796116.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302685 | San Isidro NHS | PONTEVEDRA | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5796116.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5591446.72 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302686 | Tabao NHS | VALLADOLID | 4 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5641357.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302686 | Tabao NHS | VALLADOLID | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5642157.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 13 | 5714957.12 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117385 | Talisay Elementary School | CITY OF TALISAY | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 17900734.78 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117385 | Talisay Elementary School | CITY OF TALISAY | 3 |  | 6 | 2STY6CL | BATCH 14 | 17484252.03 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117389 | Talisay South ES | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9655846.28 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Negros Occidental | 117431 | Estado ES | CITY OF VICTORIAS | 3 | 1 | 6 | 2STY6CL | BATCH 14 | 21169692.83 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 117447 | Victorias North ES | CITY OF VICTORIAS | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 20674692.83 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 |  | 4 | 2STY4CL | BATCH 14 | 11670026.63 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9505846.28 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 | 1 | 2 | 1STY2CL | BATCH 14 | 3559375 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 3408375 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 14 | 3408375 |  |  | Completed | 1
NC 2017 | SHS | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 |  | 9 | 3STY9CL | BATCH 14 | 36702071.595 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 |  | 12 | 3STY12CL | BATCH 14 | 44038900.875 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Negros Occidental | 117164 | Filomena G. Gequillana Elementary School | ILOG | 6 | 1 | 12 | 2STY12CL | BATCH 14 | 25473952.16 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Occidental | 302589 | Andulauan NHS | ILOG | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9527002.9 |  |  | Completed | 1
NC 2017 | SHS | NIR | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9950846.28 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Silay City | 302779 | Don Felix T. Lacson Memorial National High School | SILAY CITY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 9050846.28 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Silay City | 302780 | Doña Montserrat Lopez MHS | SILAY CITY | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 20756429.32 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Silay City | 302780 | DoÃ±a Montserrat Lopez MHS | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9250846.28 |  |  | Reverted | 0
NC 2017 | SHS | NIR | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 17079734.78 |  |  | Completed | 1
NC 2017 | SHS | NIR | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9050846.28 |  |  | Completed | 1
NC 2017 | SHS | NIR | Silay City | 302781 | Brgy. E. Lopez National High School | SILAY CITY | 3 |  | 4 | 2STY4CL | BATCH 14 | 9050846.26 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Bayawan City | 120162 | Nangka Elem School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2770696.75 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bayawan City | 120166 | Telesforo Gargantiel MES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2762586.11 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120223 | Bulak Elementary School | DAUIN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 4096102.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120449 | Calañan Elementary School | SIATON | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 4299590.6 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120449 | Calañan Elementary School | SIATON | 3 |  | 3 | 1STY3CL | BATCH 2 | 4299590.6 |  |  | Completed | 1 | [10 empty] | site far flung
NC 2017 | K10 | NIR | Negros Oriental | 303262 | Pulangbato National High School | VALENCIA (LUZURRIAGA) | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2843654.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120654 | Zamboanguita CES | ZAMBOANGUITA | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2843654.17 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 323011 | Bais City Olympia National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2669464.8 |  |  | REVERTED | 0
NC 2017 | SHS | NIR | Bais City | 323001 | Cabugan National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2619376.53 |  |  | Completed | 1
NC 2017 | K10 | NIR | Bais City | 120086 | Calasga-an ES | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629830.38 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 303214 | Dodong EscaÃ±o Memorial High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2692074.95 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 303214 | Dodong EscaÃ±o Memorial High School | BAIS CITY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2692074.95 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629830.38 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2643704.83 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 323006 | Sto. Thomas National High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2632536.43 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2678328.94 |  |  | Completed | 1
NC 2017 | SHS | NIR | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2629854.46 |  |  | Completed | 1
NC 2017 | K10 | NIR | Guihulngan City | 120242 | Calamba CES | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3770000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Guihulngan City | 312910 | Guihulngan NHS, Hilaitan - Trinidad Annex | CITY OF GUIHULNGAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 3070000 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Guihulngan City |  | Lip-o (Sandayao) Ext. HS | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2948745.92 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Guihulngan City |  | Lip-o (Sandayao) Ext. HS | CITY OF GUIHULNGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2948745.92 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2875000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 |  | 2 | 1STY2CL | BATCH 4 | 2875000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Guihulngan City |  | Macalos Ext. HS (Bulado HS) | CITY OF GUIHULNGAN | 1 |  | 3 | 1STY3CL | BATCH 4 | 4058435.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Guihulngan City | 120632 | Macapso ES | VALLEHERMOSO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2725000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Guihulngan City | 120635 | Molobolo ES | VALLEHERMOSO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4030000 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120031 | Anibong Elementary School | AYUNGON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Oriental | 120031 | Anibong Elementary School | AYUNGON | 1 |  | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Negros Oriental | 120054 | South Poblacion Elementary School | AYUNGON | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120054 | South Poblacion Elementary School | AYUNGON | 1 |  | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120054 | South Poblacion Elementary School | AYUNGON | 1 |  | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120054 | South Poblacion Elementary School | AYUNGON | 1 |  | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120054 | South Poblacion Elementary School | AYUNGON | 1 |  | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120059 | Tiguib ES | AYUNGON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120059 | Tiguib ES | AYUNGON | 1 |  | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120060 | Tumampon Elementary School | AYUNGON | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120171 | Bindoy Central Elementary School | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120181 | Danawan Elementary School | BINDOY (PAYABON) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | REVERTED | 0
NC 2017 | SHS | NIR | Negros Oriental | 312965 | Jose B. Cardenas MHS - Pula Ext. | CANLAON CITY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120383 | Butong ES | MANJUYOD | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2730000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312903 | Kauswagan High School | MANJUYOD | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2667000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312966 | Panciao High School | MANJUYOD | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2667000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312966 | Panciao High School | MANJUYOD | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2667000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 303206 | Avocado Community High School | SANTA CATALINA | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2854845.84 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312933 | Kakha High School | SANTA CATALINA | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2899638.23 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School | SIATON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2774752.43 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312970 | Caticugan HS | SIATON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2783877 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental |  | Manjuyod Special Education Center |  | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | TVL | NIR | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2866054.11 |  |  | Completed | 1 | [9 empty] | ALOJA BUILDERS AND REALTY
NC 2017 | TVL | NIR | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2939036.73 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | K10 | NIR | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3940687.05 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2683720.56 |  |  | Completed | 1 | [10 empty] | Abandoned
NC 2017 | TVL | NIR | Tanjay City | 303287 | Lourdes L. del Prado MNHS (Pal-ew) | CITY OF TANJAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3138166.26 |  |  | Completed | 1
NC 2017 | TVL | NIR | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3149989.06 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 120556 | Luca ES | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2630063.54 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 234004 | Mandalamon Elementary School | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2683720.56 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 120559 | Novallas Elementary School | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2656445.45 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City |  | Pilipigan Indigenous People Integrated School (PIPIS) | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2690263.075 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Tanjay City |  | Pilipigan Indigenous People Integrated School (PIPIS) | CITY OF TANJAY | 2 |  | 2 | 1STY2CL | BATCH 4 | 2690263.075 |  |  | REVERTED | 0
NC 2017 | K10 | NIR | Tanjay City | 120564 | Sto. Nino ES | CITY OF TANJAY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2669619.24 |  |  | Completed | 1
NC 2017 | TVL | NIR | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3158811.34 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 120416 | Ilalan Elementary School | PAMPLONA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3928448.67 |  |  | Completed | 1
NC 2017 | TVL | NIR | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3084748.02 |  |  | Completed | 1
NC 2017 | TVL | NIR | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3084748.02 |  |  | Completed | 1
NC 2017 | K10 | NIR | Tanjay City | 234005 | Bulo Elementary School | Tanjay City North | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3822915.15 |  |  | COMPLETED | 1 | [10 empty] | Abandoned
NC 2017 | TVL | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3136017.37 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3234745.04 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bais City | 323007 | Mansangaban National High School | BAIS CITY | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3144165.4 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120351 | Canggohob Elementary School | MABINAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2717407.72 |  |  | Completed | 1
NC 2017 | K10 | NIR | Negros Oriental | 120354 | Capanun-an Elementary School | MABINAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2710776.95 |  |  | Completed | 1
NC 2017 | TVL | NIR | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | LARENA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3177110.87 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 |  | 3 | WORKSHOP BLDG (7x18) | BATCH 7 | 9109183.45 |  |  | completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 5875894.62 |  |  | completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303295 | Leon Parami High School | LAZI | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3128571.79 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3035909.16 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2907728.53 |  |  | completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833382.79 |  |  | Completed | 1 | [9 empty] | QUICKSILVER CONSTRUCTION SERVICES
NC 2017 | TVL | NIR | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2904693.95 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | TVL | NIR | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2886102.01 |  |  | Completed | 1 | [9 empty] | QUICKSILVER CONSTRUCTION SERVICES
NC 2017 | TVL | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2667000 |  |  | Completed | 1 | [10 empty] | abandoned by contractor
NC 2017 | TVL | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2617000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312916 | Jose B. Cardenas MHS - Uptown Annex | CANLAON CITY | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 8 | 7481000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312954 | Malaiba HS | CANLAON CITY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2567000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312954 | Malaiba HS | CANLAON CITY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2567000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312955 | Masulog HS | CANLAON CITY | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 8 | 7401000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 8 | 7661000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 |  | 6 | WORKSHOP BLDG (7x18) | BATCH 8 | 14562000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312922 | Jimalalud NHS - Tamao Ext. | JIMALALUD | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2617000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 303257 | Owacan Provincial Comm. HS | JIMALALUD | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2717000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303257 | Owacan Provincial Comm. HS | JIMALALUD | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2767000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2617000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5034000 |  |  | REVERTED | 0
NC 2017 | TVL | NIR | Negros Oriental | 303261 | Pinalubngan National High School | TAYASAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2717000 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303290 | Tayasan National High School - Bago Campus | TAYASAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 8 | 2617000 |  |  | Completed | 1 | [10 empty] | Abandoned; The contractor was advised to intensify work
NC 2017 | TVL | NIR | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 8 | 5084000 |  |  | Completed | 1 | [10 empty] | Abandoned; The contractor was advised to intensify work
NC 2017 | TVL | NIR | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3989801 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 303221 | Bayawan National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 303237 | Kalumboyan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3789801 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 303237 | Kalumboyan National High School | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3789801 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 321903 | Minaba National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3746058.84 |  |  | Completed | 1
NC 2017 | TVL | NIR | Bayawan City | 303242 | Tayawan National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3803801 |  |  | Completed | 1
NC 2017 | K10 | NIR | Dumaguete City | 119949 | South City ES | DUMAGUETE CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2729262.44 |  |  | Completed | 1
NC 2017 | TVL | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3530000 |  |  | Reverted | 0
NC 2017 | TVL | NIR | Guihulngan City | 312952 | Guihulngan National High School-Poblacion (Linantuyan Annex) | CITY OF GUIHULNGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3600000 |  |  | Reverted | 0
NC 2017 | K10 | NIR | Negros Oriental | 120020 | Amlan CES | AMLAN (AYUQUITAN) | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2627789.44 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312918 | Buntod High School | BACONG | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3694240 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3917437 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3698645 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 361077 | Pulangbato National Senior High School | VALENCIA (LUZURRIAGA) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | TVL | NIR | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3663818.32 |  |  | Completed | 1
NC 2017 | K10 | NIR | Siquijor | 120660 | Libo Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12307040.4 |  |  | completed | 1 | [9 empty] | MF CONSTRUCTION
NC 2017 | K10 | NIR | Siquijor | 120666 | Bogo Elementary School | MARIA | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9417542.22 |  |  | Completed | 1 | [9 empty] | TESAR BUILDERS | Note: Non-compliance to specifications on rebars
NC 2017 | K10 | NIR | Siquijor | 120677 | Lazi Central Elementary School | LAZI | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12334199.4 |  |  | Completed | 1 | [9 empty] | ALOJA BUILDERS AND REALTY
NC 2017 | K10 | NIR | Siquijor | 120678 | Lico-an Elementary School | MARIA | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 17463672.13 |  |  | Completed | 1 | [9 empty] | 8G CONSTRUCTION
NC 2017 | K10 | NIR | Siquijor | 120686 | Simacolong Elementary School | LAZI | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9503049.91 |  |  | completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | K10 | NIR | Siquijor | 120699 | Catulayan Elementary School | SAN JUAN | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12178977.31 |  |  | completed | 1 | [9 empty] | MF CONSTRUCTION | Note: Non-compliance to specifications on rebars
NC 2017 | K10 | NIR | Siquijor | 120701 | Luzong Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12138715.88 |  |  | Completed | 1 | [9 empty] | ROYAL STAR BUILDERS AND REALTY | Note: Non-compliance to specifications on rebars
NC 2017 | K10 | NIR | Siquijor | 120703 | Ponong Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9499017.19 |  |  | completed | 1 | [9 empty] | ALOJA BUILDERS AND REALTY
NC 2017 | K10 | NIR | Siquijor | 120704 | San Antonio Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9433993.11 |  |  | Completed | 1 | [9 empty] | ALOJA BUILDERS AND REALTY
NC 2017 | K10 | NIR | Siquijor | 120705 | San Juan Central Elementary School | SAN JUAN | 0 | 1 | 8 | 2STY8CL | BATCH 14 | 17608679.28 |  |  | completed | 1 | [9 empty] | 8G CONSTRUCTION | Note: Non-compliance to specifications on rebars
NC 2017 | K10 | NIR | Siquijor | 120706 | Siquijor Central Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 11963780.04 |  |  | Completed | 1 | [9 empty] | E.D. ANGAS CONSTRUCTION
NC 2017 | K10 | NIR | Siquijor | 313001 | Cabulihan Integrated School | LARENA | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9292138.2 |  |  | completed | 1 | [9 empty] | ALOJA BUILDERS AND REALTY
NC 2017 | K10 | NIR | Tanjay City | 234003 | Lugta Elementary School | Tanjay City West | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 181002 | Fr. Gratian Murray, AFCS IS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4506237.6667 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 8 | 4sty 8 regular workshop | BATCH 1 | 37852360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 |  | 3 | 3sty 3 regular workshop | BATCH 1 | 14305885 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302700 | Alangilan NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4sty- 8 regular workshop | BATCH 1 | 37712360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9540590 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | NIR | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 ICT lab | BATCH 1 | 9690590 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302702 | Barangay Singcang-Airport NHS | BACOLOD CITY (Capital) | 0 | 1 | 12 | 4STY 7 LAB (2 sci lab, 2 ICT, 3 regular workshop, 6 CL) | BATCH 1 | 48802065 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302703 | Bata NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37662360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4232865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302704 | Romanito Maravilla NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 20431180 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 42012360 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2STY regular workshop w/ 2CL | BATCH 1 | 15490590 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37562360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 4494571 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 37712360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302709 | Luis Hervias NHS | BACOLOD CITY (Capital) | 0 |  | 2 | 2sty- 2 regular workshop | BATCH 1 | 9575590 |  |  | COMPLETED | 1 | [10 empty] | ADDTINOAL FUND (BEFF 2021)
NC 2018 | TVL | NIR | Bacolod City | 302710 | Mandalagan NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | 4STY8 LAB (4 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 39212360 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4176198.5833 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 |  | 8 | 4STY4 LAB (2 sci lab, 2 ICT, w/ 4CL) | BATCH 1 | 19071180 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4267865.25 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Bacolod City | 302712 | Handumanan NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28531770 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | NIR | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4267865.25 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (ON GOING RECTIFICATION)
NC 2018 | TVL | NIR | Bacolod City | 302713 | Jovito H. Sayson NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 2STY6 LAB (2 regular workshop, 2 sci lab, 2 ICT lab) | BATCH 1 | 28546770 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4187865.25 |  |  | COMPLETED | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302714 | Mansilingan Agro-Ind. HS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28636770 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4382865.25 |  |  | Completed | 1 | [10 empty] | ADDTINOAL FUND (BEFF 2021)
NC 2018 | TVL | NIR | Bacolod City | 302715 | Paglaum Village NHS | BACOLOD CITY (Capital) | 0 |  | 6 | 3STY6 LAB (2 sci lab, 2 ICT, 2 regular workshop) | BATCH 1 | 28903770 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 | 1 | 6 | 3STY- 6 regular workshop | BATCH 1 | 28321770 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 302716 | Sum-ag NHS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 311201 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 4 | 4STY4 LAB (2 sci lab, 2 ICT lab) | BATCH 1 | 19141180 |  |  | Completed | 1 | [10 empty] | WITH DEFECTS (NOT YET RECTIFIED)
NC 2018 | TVL | NIR | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 1 | 4082865.25 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bacolod City | 311202 | Fr. Gratian Murray, AFSC IS | BACOLOD CITY (Capital) | 0 |  | 4 | 2STY WORKSHOP BLDG | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | SHS | NIR | Bacolod City | 343604 | ANDRES BONIFACIO SENIOR HIGH SCHOOL | BACOLOD CITY (Capital) | 0 | 1 | 4 | 2STY4 lab (2 science lab & 2 ICT lab) | BATCH 1 | 18931180 |  |  | Completed | 1
NC 2018 | SHS | NIR | Bacolod City | 343604 | ANDRES BONIFACIO SENIOR HIGH SCHOOL | BACOLOD CITY (Capital) | 0 |  | 4 | 2sty- 2 regular workshop | BATCH 1 | 13340590 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2769354.78 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bago City | 117510 | M.L. Araneta ES | BAGO CITY | 4 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2735664.46 |  |  | Completed | 1
NC 2018 | SHS | NIR | Bago City | 302719 | Ramon Torres NHS | BAGO CITY | 4 | 1 | 8 | 2STY8CL | Batch 3 | 22521688.93 |  |  | Completed | 1
NC 2018 | SHS | NIR | Bago City | 361021 | Bago City Senior High School | BAGO CITY | 4 | 1 | 8 | 2STY8CL | Batch 3 | 22521688.93 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bago City | 117523 | Ma-ao Elementary School | BAGO CITY | 4 | 1 | 6 | 2STY6CL | Batch 3 | 17661474.87 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302726 | Cadiz Viejo NHS | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 32894632.25 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302727 | Sicaba National High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 34489632.95 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302728 | Caduha-an NHS | Cadiz City | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 55544539.82 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302728 | Caduha-an NHS | CADIZ CITY | 2 |  | 16 | 4STY16CL | BATCH 1 | 49970613.06 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302729 | Caduha-an NHS - Andres Bonifacio Ext. HS | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 41850250.73 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 22742162.11 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302731 | Mabini National High School | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 49310613.07 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302732 | SPED High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 39958671.74 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302733 | Tiglawigan NHS | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 39499632.94 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10153930.91 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302734 | Tiglawigan NHS - Magsaysay Extension High School | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10142930.91 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302735 | Villacin National High School | CADIZ CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 38869671.74 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 302736 | Jerusalem National High School | CADIZ CITY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 50025613.07 |  |  | Completed | 1
NC 2018 | SHS | NIR | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 16020905.58 |  |  | completed | 1
NC 2018 | SHS | NIR | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10582930.91 |  |  | completed | 1
NC 2018 | SHS | NIR | Cadiz City | 311403 | Mabini NHS - Alimatoc Ext. HS | CADIZ CITY | 2 |  | 4 | 2STY4CL | BATCH 1 | 10582930.91 |  |  | completed | 1
NC 2018 | SHS | NIR | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 24167162.11 |  |  | completed | 1
NC 2018 | SHS | NIR | Cadiz City | 311405 | Banquerohan NHS (Dr. Vicente F Gustilo NHS-Banquerohan Ext) | CADIZ CITY | 2 |  | 8 | 2STY8CL | BATCH 1 | 24167162.11 |  |  | completed | 1
NC 2018 | TVL | NIR | Escalante City | 302595 | Buenavista NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | SHS | NIR | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12986784.82 |  |  | Completed | 1
NC 2018 | SHS | NIR | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 |  | 6 | 2STY6CL | BATCH 1 | 12986784.82 |  |  | Completed | 1
NC 2018 | TVL | NIR | Escalante City | 302615 | Dian-ay NHS | CITY OF ESCALANTE | 1 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | NIR | Escalante City | 302625 | Escalante NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | NIR | Escalante City | 302626 | Old Poblacion NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | NIR | Escalante City | 302627 | Tamlang NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | NIR | Escalante City | 302660 | Mabini NHS | CITY OF ESCALANTE | 1 | 1 | 4 | 2STY WORKSHOP BLDG (2STY4CL 2017 SCI LAB) | BATCH 1 | 9955930.91 |  |  | Completed | 1
NC 2018 | TVL | NIR | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3 sty regular workshop | BATCH 1 | 13954987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit-2 sty regular workshop | BATCH 1 | 9637002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9497002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302785 | Bantayan National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9497002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13644987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9327002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302786 | Binicuil NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2838745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9402002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302787 | CAROL-AN NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9602002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 | 1 | 2 | 2STY Regular Workshop | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9727002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9457002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302792 | Camansi National High School | CITY OF KABANKALAN | 6 |  | 2 | 2STY Regular Workshop | BATCH 1 | 9457002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13829987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9512002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9512002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9437002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302793 | Florentino Galang Sr. NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9437002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13674987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9357002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9757002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302796 | Salong NHS | CITY OF KABANKALAN | 6 |  | 4 | 1unit- 2sty ICT lab | BATCH 1 | 9757002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2758745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13689987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13689987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9472002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302797 | Tabugon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9472002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13684987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9467002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302800 | Tampalon NHS | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9467002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 | 1 | 3 | 1unit- 3sty Regular Workshop | BATCH 1 | 13684987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty Regular Workshop | BATCH 1 | 9367002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9467002.9 |  |  | Completed | 1
NC 2018 | TVL | NIR | Kabankalan City | 302801 | Tapi National High School | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9467002.9 |  |  | Completed | 1
NC 2018 | TVL | NIR | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2843745.92 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | NIR | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9557002.9 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | NIR | Kabankalan City | 312101 | TAN-AWAN NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9557002.9 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | K10 | NIR | La Carlota City | 117647 | La Carlota South ES II | LA CARLOTA CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 11386751.67 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | SHS | NIR | La Carlota City | 302754 | San Miguel NHS | LA CARLOTA CITY | 4 | 1 | 6 | 2STY6CL | Batch 3 | 17640895.68 |  |  | Completed | 1 | [10 empty] | under NEG OCC Division
NC 2018 | TVL | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4 | 1 | 2 | 2017 Unique TVL workshop | BATCH 1 | 7141071.92 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | 9 | 3STY9CL | BATCH 1 | 27925230.11 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 8 | 2STY8CL | BATCH 1 | 21484575.16 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 4 | 2STY4CL | BATCH 1 | 11377424.48 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 4 | 2STY4CL | BATCH 1 | 11377424.48 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 4 | 2STY4CL | BATCH 1 | 11377424.48 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 4 | 2STY4CL | BATCH 1 | 11377424.48 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 |  | 4 | 2STY4CL | BATCH 1 | 11377424.48 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302668 | Negros Occ. NAISHI | HINIGARAN | 5 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302671 | Binalbagan NHS (Paglaum NHS) | BINALBAGAN | 5 | 1 | 20 | 4STY20CL | BATCH 1 | 45336584.74 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302671 | Binalbagan NHS (Paglaum NHS) | BINALBAGAN | 5 |  | 6 | 2STY6CL | BATCH 1 | 15000704.16 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302675 | Payao National High School | BINALBAGAN | 5 | 1 | 10 | 2STY10CL | BATCH 1 | 24499268.55 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302675 | Payao National High School | BINALBAGAN | 5 |  | 8 | 2STY8CL | BATCH 1 | 21745451.51 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 | 1 | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9377002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9377002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 | 1 | 2 | 1unit- 2sty science lab | BATCH 1 | 9537002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9577002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 | 1 | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9377002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9377002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302598 | Bulata NHS | CAUAYAN | 6 | 1 | 2 | 1unit- 2sty science lab | BATCH 1 | 9473002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302598 | Bulata NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9473002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302599 | Bulwangan NHS | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9597002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302599 | Bulwangan NHS | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9597002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 | 4 | 2unit- Regular Workhop | BATCH 1 | 18954005.8 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9477002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9477002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 | 1 | 2 | 2STY WORKSHOP BLDG | BATCH 1 | 9477002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 |  | 2 | 2STY WORKSHOP BLDG | BATCH 1 | 9477002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302605 | Camalanda-an NHS | CAUAYAN | 6 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 1 | 2859745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302605 | Camalanda-an NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9587002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302605 | Camalanda-an NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9587002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9629587.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 |  | 1 | 1unit- 1sty science lab | BATCH 1 | 2737585.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 |  | 1 | 1unit- 1sty science lab | BATCH 1 | 2737585.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 | 1 | 1 | 1unit- 1sty Regular Workshop | BATCH 1 | 2851088.62 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 |  | 1 | 1unit- 1sty 1 science lab | BATCH 1 | 2838711.95 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302607 | Caningay NHS - Banga Ext. | CANDONI | 6 |  | 1 | 1unit- 1sty 1 ICT lab | BATCH 1 | 2838711.95 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2751929.59 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6 |  | 1 | 1unit- 1sty ICT lab | BATCH 1 | 2917239.66 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9432322.9 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6 | 1 | 6 | 2STY6CL | BATCH 1 | 12773014.84 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6 |  | 6 | 1unit- 3sty Regular Workshop | BATCH 1 | 14098987.47 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9601002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9491782.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302614 | Culipapa National High School | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9477002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302614 | Culipapa National High School | HINOBA-AN (ASIA) | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9477002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6 | 1 | 1 | 1unit- 1sty Regular Workshop | BATCH 1 | 2813745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9533002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302629 | Eva J. Montilla NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9673392.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302630 | Florentina F. CaÃ±a Recto NHS | CAUAYAN | 6 | 1 | 2 | 1unit- 2sty science lab | BATCH 1 | 9471197.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302630 | Florentina F. CaÃ±a Recto NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9277002.9 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | 12 | 3STY12CL | BATCH 1 | 31237024.22 |  |  | COMPLETED | 1 | [10 empty] | FOR PUNCHLISTING
NC 2018 | SHS | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 12 | 3STY12CL | BATCH 1 | 31237024.22 |  |  | COMPLETED | 1 | [10 empty] | FOR PUNCHLISTING
NC 2018 | SHS | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 4 | 2STY4CL | BATCH 1 | 9435670.42 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 8 | 8units- 1sty Regular Workshop | BATCH 1 | 22168794.08 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 1 | 1unit- Unique Workshop | BATCH 1 | 2968686.96 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9617002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2756604.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2756604.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9561770.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302633 | Sipalay City NHS | CITY OF SIPALAY | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9561770.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302634 | Gil Montilla NHS - Binulig Ext. | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2769159.66 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2740879.89 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9617002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9617002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2740879.89 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2740879.89 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302637 | Jacinto Montilla Memorial National High School | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2740879.89 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302639 | Gil Montilla NHS - Crossing Tanduay Ext. | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2768512.14 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302640 | Gil Montilla NHS - Manlucahoc Ext. | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2769102.61 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302640 | Gil Montilla NHS - Manlucahoc Ext. | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2769102.61 |  |  | COMPLETED | 1 | [10 empty] | FOR RECTIFICATION OF PUNCHLISTS
NC 2018 | TVL | NIR | Negros Occidental | 302641 | Guiljungan NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9327002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302641 | Guiljungan NHS | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9427002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302642 | Guiljungan NHS - Abaca Ext. | CAUAYAN | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 3059745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302642 | Guiljungan NHS - Abaca Ext. | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9751002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302642 | Guiljungan NHS - Abaca Ext. | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9751002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302644 | Guiljungan NHS - Talacdan Ext. | CAUAYAN | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2942745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302644 | Guiljungan NHS - Talacdan Ext. | CAUAYAN | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2942745.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302644 | Guiljungan NHS - Talacdan Ext. | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9556002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302644 | Guiljungan NHS - Talacdan Ext. | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9556002.9 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9357002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 |  | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9307002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302661 | Juan Gequillana NHS (Manalad NHS) | ILOG | 6 | 1 | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9347002.9 |  |  | Completed | 1 | [10 empty] | PHASE 1 - COMPLETED
NC 2018 | TVL | NIR | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Unique Workshop | BATCH 1 | 2759377.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2759377.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302664 | Nabulao NHS | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2759377.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302665 | Nabulao NHS - Cayhagan Extension | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2759899.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302666 | Nabulao NHS - Maricalum Ext. | CITY OF SIPALAY | 6 | 1 | 1 | 1unit- Regular Workshop | BATCH 1 | 2749899.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302666 | Nabulao NHS - Maricalum Ext. | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2749899.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302666 | Nabulao NHS - Maricalum Ext. | CITY OF SIPALAY | 6 |  | 1 | 1unit- Regular Workshop | BATCH 1 | 2784899.92 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302688 | Tabu NHS | ILOG | 6 | 1 | 2 | 1unit- 2sty ICT lab | BATCH 1 | 9527002.9 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Occidental | 302688 | Tabu NHS | ILOG | 6 |  | 2 | 1unit- 2sty science lab | BATCH 1 | 9527002.9 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302613 | Col. Griffin National High School | CALATRAVA | 1 | 1 | 12 | 2STY12CL | Batch 3 | 26492639.58 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | 12 | 3STY12CL | Batch 3 | 33657025.09 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 |  | 12 | 3STY12CL | Batch 3 | 33657025.09 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Negros Occidental | 302662 | Manapla National High School | MANAPLA | 2 | 1 | 4 | 2STY4CL (science lab) | Batch 3 | 11287377.2 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117385 | Talisay Elementary School | CITY OF TALISAY | 3 | 1 | 8 | 2STY8CL | Batch 3 | 17884790.26 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117385 | Talisay Elementary School | CITY OF TALISAY | 3 |  | 6 | 2STY6CL | Batch 3 | 14670210.02 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117389 | Talisay South ES | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11287377.2 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117431 | Estado ES | CITY OF VICTORIAS | 3 | 1 | 6 | 2STY6CL | Batch 3 | 15353018.43 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117435 | Victorias ES | CITY OF VICTORIAS | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11829672.28 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Negros Occidental | 117447 | Victorias North ES | CITY OF VICTORIAS | 3 | 1 | 8 | 2STY8CL | Batch 3 | 22467227.34 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12029672.28 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11237377.2 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302591 | ANTIPOLO NATIONAL HIGH SCHOOL | PONTEVEDRA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 11316669.65 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302685 | San Isidro NHS | PONTEVEDRA | 4 | 1 | 9 | 3STY9CL | Batch 3 | 25587489.23 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | 8 | 2STY8CL | Batch 3 | 22268159.01 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302686 | Tabao NHS | VALLADOLID | 4 | 1 | 6 | 2STY6CL | Batch 3 | 17549734.28 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302602 | Cabacungan NHS | LA CASTELLANA | 5 | 1 | 4 | 2STY4CL | Batch 3 | 9145902.09 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5 | 1 | 10 | 2STY10CL | Batch 3 | 24511728.72 |  |  | COMPLETED | 1 | [10 empty] | FOR RECTIFICATION OF PUNCHLISTS
NC 2018 | SHS | NIR | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | 20 | 4STY20CL | Batch 3 | 45267349.47 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | 16 | 3 units 4STY16CL | Batch 3 | 111652962.28 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 302692 | Tinongan NHS | ISABELA | 5 | 1 | 4 | 2STY4CL | Batch 3 | 11556329.29 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Negros Occidental | 311103 | Cabacungan NHS - Masulog Ext. | LA CASTELLANA | 5 |  | 4 | 2STY4CL | Batch 3 | 9145902.09 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 8 | 4STY WORKSHOP BLDG (4STY8CL Regular workshop) | BATCH 1 | 21792667.24 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | TVL | NIR | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL science lab) | BATCH 1 | 12337629.29 |  |  | COMPLETED | 1
NC 2018 | TVL | NIR | Sagay City | 302767 | Sagay NHS | SAGAY CITY | 2 |  | 4 | 2STY WORKSHOP BLDG (2STY4CL ICT lab) | BATCH 1 | 12447629.29 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Sagay City | 311802 | Sagay National High School - Rizal Extension | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 10245841.94 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 46289000.71 |  |  | COMPLETED | 1 | [10 empty] | COMPLETED AS PER DPWH POW BUT UNPAINTED
NC 2018 | SHS | NIR | Sagay City | 343922 | Sagay City SHS | SAGAY CITY | 2 |  | 6 | 2STY6CL | BATCH 1 | 13321184.82 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Sagay City | 117693 | Bulanon Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | K10 | NIR | Sagay City | 117695 | Buenaventura Rodriguez Elementary School | SAGAY CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23233053.68 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Sagay City | 117707 | Talusan Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Sagay City | 117709 | Vito Elementary School | SAGAY CITY | 2 | 1 | 6 | 2STY6CL | Batch 3 | 16341557.36 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Sagay City | 117716 | Gil Lopez Elementary School | SAGAY CITY | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23033053.68 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Sagay City | 117721 | Maria Lopez Elementary School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12027869.01 |  |  | COMPLETED | 1
NC 2018 | SHS | NIR | Sagay City | 302765 | Eusebio Lopez Memorial Integrated School | SAGAY CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12312331.69 |  |  | COMPLETED | 1 | [10 empty] | not yet submitted the Certificate of Occupancy and Completion
NC 2018 | K10 | NIR | San Carlos City | 117753 | Ramon Magsaysay ES | SAN CARLOS CITY | 1 | 1 | 8 | 2STY8CL | Batch 3 | 23133053.68 |  |  | Completed | 1
NC 2018 | K10 | NIR | San Carlos City | 117785 | Andres Bonifacio ES | SAN CARLOS CITY | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12277869.01 |  |  | Completed | 1
NC 2018 | K10 | NIR | Silay City | 117801 | Don Eustaquio Hofilena MS | SILAY CITY | 3 | 1 | 6 | 2STY6CL | Batch 3 | 14820210.02 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Silay City | 117807 | Gov. Emilio Gaston Memorial ES | SILAY CITY | 3 | 1 | 6 | 2STY6CL | Batch 3 | 14720210.02 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Silay City | 117807 | Gov. Emilio Gaston ES | SILAY CITY | 3 |  | 8 | 2STY8CL | Batch 3 | 22418487.82 |  |  | COMPLETED | 1
NC 2018 | K10 | NIR | Bais City | 120096 | Mangganay ES | BAIS CITY | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12549710.02 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19145815.06 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9363257.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303213 | Josefina T. Valencia National High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9838257.76 |  |  | Reverted | 0
NC 2018 | TVL | NIR | Bais City | 303214 | Dodong Escaño Memorial High School | BAIS CITY | 2 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | BATCH 1 | 10080911.97 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9714914.1 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303215 | Lonoy National High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 10189914.1 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 303216 | Bais City National Science High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19145815.06 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9228246.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 323003 | Governor Julian L. Teves Memorial HS | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9703246.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 323007 | Mansangaban National High School | BAIS CITY | 2 | 1 | 4 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 19689310.78 |  |  | completed | 1
NC 2018 | TVL | NIR | Bais City | 323009 | Tagpo National HS | BAIS CITY | 2 | 1 | 2 | 2sty- 1 ict lab & 1 science lab | BATCH 1 | 10018690.79 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 | 1 | 2 | 2sty- 2 science lab | BATCH 1 | 9243778.21 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2 |  | 2 | 2sty- 2 ict lab | BATCH 1 | 9718778.21 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bayawan City | 120107 | Basay Central School | BASAY | 3 |  | 4 | 2STY4CL | Batch 3 | 9182301.76 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bayawan City | 120132 | Lapay Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9835966.85 |  |  | Completed | 1
NC 2018 | K10 | NIR | Bayawan City | 120143 | Banga CES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL W/ TOILET | Batch 3 | 2343187.94 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 ICT) | Batch 3 | 17878600.37 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 SCI LAB) | Batch 3 | 18402430.06 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | 4 | 4STY4LAB (2 Reg. Workshop, 2 ICT) | Batch 3 | 18507787.49 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bayawan City | 303227 | Dawis National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 4STY4LAB (2 SCI LAB, 2 ICT) | Batch 3 | 18867432.03 |  |  | Completed | 1
NC 2018 | TVL | NIR | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | 4STY4LAB (2 SCI LAB, 2 ICT) | Batch 3 | 17309570.67 |  |  | Completed | 1
NC 2018 | SHS | NIR | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 9 | 3STY9CL | Batch 3 | 26953159.6 |  |  | Completed | 1
NC 2018 | K10 | NIR | Dumaguete City | 119939 | West City ES | DUMAGUETE CITY (Capital) | 2 | 1 | 9 | 3STY9CL | Batch 5 | 24659327.73 |  |  | completed | 1 | [10 empty] | with items for rectification; ongoing processing of occupancy permit
NC 2018 | K10 | NIR | Dumaguete City | 119939 | West City ES | DUMAGUETE CITY (Capital) | 2 |  | 9 | 3STY9CL | Batch 5 | 24659327.73 |  |  | completed | 1 | [10 empty] | with items for rectification; ongoing processing of building and occupancy permits
NC 2018 | TVL | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5318886.42 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15945215.59 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15945215.59 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303231 | Guihulngan NHS - Poblacion | CITY OF GUIHULNGAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 12663637.17 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303233 | Guihulngan NHS - Hilaitan | CITY OF GUIHULNGAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15588497.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 303275 | Tagbino National High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5561195.51 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 312904 | Guba High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5318886.42 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 312960 | Pinucauan High School | VALLEHERMOSO | 1 | 1 | 1 | unique workshop (7x22.5) | Batch 3 | 5561195.51 |  |  | Completed | 1
NC 2018 | TVL | NIR | Guihulngan City | 312960 | Pinucauan High School | VALLEHERMOSO | 1 |  | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 22078748.8 |  |  | Completed | 1
NC 2018 | K10 | NIR | Guihulngan City | 120236 | Bonbon ES | CITY OF GUIHULNGAN | 1 | 1 | 4 | 2UNITS 1STY2CL | Batch 5 | 9070339.31 |  |  | Reverted | 0 | [10 empty] | No bidders
NC 2018 | TVL | NIR | Negros Oriental | 303207 | Amlan National High School | AMLAN (AYUQUITAN) | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18089266.54 |  |  | Completed | 1 | [10 empty] | Under rectification of remaining punchlist. Included in the coordination meeting last November 17, 2022 to settle other concerns and to have target for completion.
NC 2018 | TVL | NIR | Negros Oriental | 312957 | Amlan NHS-Jugno Campus | AMLAN (AYUQUITAN) | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18117902.34 |  |  | Completed | 1 | [10 empty] | Under rectification of remaining punchlist. Included in the coordination meeting last November 17, 2022 to settle other concerns and to have target for completion.
NC 2018 | TVL | NIR | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17809570.67 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School | SIATON | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17655762.08 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12455115.89 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15442449.68 |  |  | Completed | 1
NC 2018 | SHS | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | 2 | 1STY2CL | Batch 5 | 4171998.88 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18511573.35 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18450442.14 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18349632.18 |  |  | Completed | 1 | [10 empty] | Under rectification of remaining punchlist. Included in the coordination meeting last November 17, 2022 to settle other concerns and to have target for completion.
NC 2018 | K10 | NIR | Negros Oriental | 120171 | Bindoy Central Elementary School | BINDOY (PAYABON) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11331674.33 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312918 | Buntod High School | BACONG | 3 | 1 | 4 | 4STY4 lab (4 reg workshop) | Batch 3 | 17409570.67 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental |  | Busilac Ext. HS | LA LIBERTAD | 1 | 1 | 4 | 2STY4CL | Batch 3 | 14980744.46 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312924 | Campanun-an Senior High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18651903.71 |  |  | Completed | 1 | [10 empty] | Under rectification of remaining punchlist. Included in the coordination meeting last November 17, 2022 to settle other concerns and to have target for completion.
NC 2018 | TVL | NIR | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 | 1 | 4 | 4STY4 lab (2 reg workshop, 2 ICT) | Batch 3 | 17517285.52 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312970 | Caticugan HS | SIATON | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17583666.38 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 | 1 | 4 | 4STY4 lab (2 reg workshop, 1 sci-lab, 1 ICT) | Batch 3 | 17479208.95 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | 4 | 2sty- 1 ict lab & 1 science lab | BATCH 1 | 9739263.29 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312956 | Gregorio Elmaga MHS | ZAMBOANGUITA | 3 | 1 | 4 | 4STY4 lab (2 reg workshop, 2 sci-lab) | Batch 3 | 17586523.8 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303234 | Inapoy High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18450442.14 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 11886703.52 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312922 | Jimalalud NHS - Tamao Ext. | JIMALALUD | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 14236750.48 |  |  | completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312916 | Jose B. Cardenas MHS - Uptown Annex | CANLAON CITY | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 14358457.22 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303243 | La Libertad Technical-Vocational School | LA LIBERTAD | 1 | 1 | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 21625373.28 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental | 120046 | Lamigan Elementary School | AYUNGON | 1 | 1 | 4 | 2UNITS 1STY2CL | Batch 3 | 8118638.1 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental | 120047 | Libtacon PS | AYUNGON | 1 | 1 | 3 | 1STY3CL | Batch 3 | 5111953.65 |  |  | completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303269 | Lorenza P. Palarpalar MHS (Bonbonon PCHS) | SIATON | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17690381.22 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15509824.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 15509825.76 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18349632.18 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312954 | Malaiba HS | CANLAON CITY | 1 | 1 | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 5 | 21751640.15 |  |  | Completed | 1 | [10 empty] | Under Canlaon City Division
NC 2018 | TVL | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | 4 | 4STY4 lab (2 reg workshop, 2 sci-lab) | Batch 3 | 17352844.6 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 |  | 4 | 4STY4 lab (2 reg workshop, 2 sci-lab) | Batch 3 | 17482666.38 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312955 | Masulog HS | CANLAON CITY | 1 | 1 | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 22078748.8 |  |  | Completed | 1 | [10 empty] | Under Canlaon City Division
NC 2018 | TVL | NIR | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18379009.35 |  |  | Completed | 1 | [10 empty] | UNDER RECTIFICATION OF PUNCHLISTED ITEMS; With coordination meeting with DPWH last October 25, 2022 to settle issues and concerns and set target completion of the project.
NC 2018 | TVL | NIR | Negros Oriental | 312931 | Nagbinlod High School | SANTA CATALINA | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17759619.51 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental |  | Nasunggan Ext. HS | LA LIBERTAD | 1 | 1 | 4 | 2STY4CL | Batch 3 | 15580512.86 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17684666.38 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303258 | Pacuan National High School | LA LIBERTAD | 1 | 1 | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 21751640.15 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18450442.14 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303261 | Pinalubngan National High School | TAYASAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 14279785.22 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303261 | Pinalubngan National High School | TAYASAN | 1 |  | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 14279786.22 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3 | 1 | 4 | 4STY4 lab (1 reg workshop, 1 sci-lab, 2 ICT) | Batch 3 | 17688123.8 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303209 | Silab Community High School Annex | AMLAN (AYUQUITAN) | 2 | 1 | 8 | 4sty- 2 ict lab & 2 science lab | BATCH 1 | 18158090.93 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303265 | Sta. Catalina National High School | SANTA CATALINA | 3 | 1 | 4 | 4STY4 lab (1 reg workshop, 1 sci-lab, 2 ICT) | Batch 3 | 17309570.67 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17459570.67 |  |  | Completed | 1
NC 2018 | K10 | NIR | Negros Oriental | 120193 | Tagaytay Elementary School | BINDOY (PAYABON) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11331674.33 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303289 | Tayasan National High School (Main) | TAYASAN | 1 | 1 | 4 | 4STY WORKSHOP BLDG. (7 X 18) | Batch 3 | 21582672.45 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1 | 1 | 2 | 2STY WORKSHOP BLDG. | Batch 3 | 11862362.17 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | 4 | 4STY4 lab (1 reg workshop, 1 sci-lab, 2 ICT) | Batch 3 | 17409570.67 |  |  | Completed | 1
NC 2018 | TVL | NIR | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 | 1 | 4 | 4STY4 lab (2 ICT, 2 sci-lab) | Batch 3 | 17309570.67 |  |  | Completed | 1
NC 2018 | K10 | NIR | Siquijor | 120689 | Banban Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 13108557.15 |  |  | Completed | 1
NC 2018 | K10 | NIR | Siquijor | 120694 | Cang-alwang Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 13350919.03 |  |  | Completed | 1
NC 2018 | K10 | NIR | Siquijor | 120695 | Cang-asa Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL | Batch 3 | 13181495.58 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 312926 | Apolinario Gerarda Arnaiz HS | PAMPLONA | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 9792614.55 |  |  | Completed | 1
NC 2018 | SHS | NIR | Tanjay City | 303281 | Azagra High School | Tanjay City North | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17024055.32 |  |  | Completed | 1
NC 2018 | K10 | NIR | Tanjay City | 120412 | Cantilo ES | Pamplona | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11847329.18 |  |  | Completed | 1
NC 2018 | SHS | NIR | Tanjay City | 322301 | Graciano Banogon HS | Tanjay City North | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12005853.06 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 9831976.52 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303274 | Isidoro Salma MSHS (Balayong ) | PAMPLONA | 2 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9331976.52 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303288 | Lourdes L. del Prado MNHS (Sto. Niño) | CITY OF TANJAY | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 10257801.44 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303284 | Lourdes Ledesma Del Prado MNHS | CITY OF TANJAY | 2 | 1 | 2 | 2sty-1 science lab & 1 ict lab | BATCH 1 | 9720152.75 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 322303 | Nagsala HS | CITY OF TANJAY | 2 | 1 | 4 | 2sty-2 science lab & 2 ict lab | BATCH 1 | 18153176.82 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303259 | Pamplona NHS | PAMPLONA | 2 | 1 | 8 | 4sty- 2 science lab, 2 ict lab & 4 regular workshop | BATCH 1 | 38517097.09 |  |  | Completed | 1
NC 2018 | K10 | NIR | Tanjay City | 120572 | Plaza CS | CITY OF TANJAY | 2 |  | 9 | 3STY9CL | BATCH 1 | 26036130.06 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 9792614.55 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303273 | Sta. Agueda National High School | PAMPLONA | 2 |  | 2 | 2sty- 2 science lab | BATCH 1 | 9292614.55 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 312905 | Sta. Agueda NHS - Calicanan HS Ext. | PAMPLONA | 2 | 1 | 2 | 2sty- 2 ict lab | BATCH 1 | 10093196.85 |  |  | Completed | 1
NC 2018 | TVL | NIR | Tanjay City | 303283 | Tanjay City Science HS | CITY OF TANJAY | 2 | 1 | 4 | 4sty- 2 science lab & 2 ict lab | BATCH 1 | 19089144.91 |  |  | Completed | 1
NC 2018 | K10 | NIR | Tanjay City | 120576 | Tanjay City South Central School | CITY OF TANJAY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9004050.12 |  |  | Completed | 1
NC 2019 | K10 | NIR | Bago City | 117511 | Alianza Elementary School | BAGO CITY | 4 | 1 | 2 | 1STY2CL |  | 4950531.9261 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | NIR | Escalante City | 311106 | Escalante NHS - Dr. Floro T. Bongco Mem. Ext. | CITY OF ESCALANTE | 1 | 1 | 8 | 2STY8CL |  | 21271534.0395 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 4975662.145 |  | completed | 1 |  |  |  | 19GN0097 | 7/31/2019 | 2019-08-07 | 2019-08-19 |  | 2019-09-12 |  |  | 0
NC 2019 | SHS | NIR | Negros Occidental | 302658 | Labilabi NHS | TOBOSO | 1 | 1 | 2 | 1STY2CL |  | 5058147.5443 |  | COMPLETED | 1 |  |  |  | 19GK0263 | [7 empty] | 0
NC 2019 | K10 | NIR | Negros Occidental | 117418 | Toboso CS | TOBOSO | 1 | 1 | 10 | 2STY10CL |  | 20085370.5058 |  | COMPLETED | 1 |  |  |  | 19GK0265 | [6 empty] | (PHASE 1 ONLY) | 0
NC 2019 | K10 | NIR | Negros Occidental | 117017 | Alacaygan ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 3344836.3377 | 3236724 | Completed | 1 |  |  |  | 19GK0261 | [7 empty] | 0
NC 2019 | SHS | NIR | Negros Occidental | 302588 | Barangay Alegria NHS | MURCIA | 3 | 1 | 6 | 2STY6CL with Water System |  | 14656760.5451 |  | COMPLETED | 1 |  |  |  | 19GK0271 | [7 empty] | 0
NC 2019 | K10 | NIR | Negros Occidental | 117025 | E. B. Magalona ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 10 | 2STY10CL |  | 20085370.3153 |  | COMPLETED | 1 |  |  |  | 19GK0298 | [7 empty] | 0
NC 2019 | K10 | NIR | Negros Occidental | 117028 | Jose M. Consing Memorial School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 4 | 2STY4CL with Water System |  | 15748290.9761 |  | completed | 1 |  |  |  | 19GK0272 | [7 empty] | 0
NC 2019 | K10 | NIR | Negros Occidental | 117031 | Nanca Elementary School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 10 | 2STY10CL |  | 20085370.5058 |  | COMPLETED | 1 |  |  |  | 19GK0264 | [6 empty] | (PHASE 1 ONLY) | 0
NC 2019 | K10 | NIR | Negros Occidental | 117299 | Cambarus ES | PONTEVEDRA | 4 | 1 | 2 | 1STY2CL W/ TOILET |  | 4958511.2247 |  | COMPLETED | 1 |  |  |  | 19GN0095 | [7 empty] | 0
NC 2019 | K10 | NIR | Negros Occidental | 117341 | Don Vicente Lopez ES | SAN ENRIQUE | 4 | 1 | 10 | 2STY10CL |  | 20085370.3153 |  | COMPLETED | 1 |  |  |  | 19GN0109 | [6 empty] | (PHASE 1 ONLY) | 0
NC 2019 | K10 | NIR | Negros Occidental | 117305 | Recreo ES | PONTEVEDRA | 4 | 1 | 10 | 2STY10CL |  | 20085370.5158 |  | COMPLETED | 1 |  |  |  | 19GN0110 | [6 empty] | (PHASE 1 ONLY) | 0
NC 2019 | K10 | NIR | Negros Occidental | 117232 | Don Felix Robles ES | LA CASTELLANA | 5 | 1 | 4 | 1STY4CL |  | 5571588.235 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Sagay City | 117717 | Hautea Elementary School | SAGAY CITY | 2 | 1 | 3 | 1STY3CL |  | 5223570.1395 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | 2 | 1STY2CL |  | 3244586.3377 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 2509551.1824 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Bayawan City | 303217 | Basay National High School | BASAY | 3 | 1 | 8 | 4STY8LAB (4 Reg. Workshop, 2 SCI LAB, 2 ICT) |  | 39416104.9561 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 6 | 2STY6CL |  | 15901486.5599 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Bayawan City | 120153 | Hag-um Primary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | 1STY2CL |  | 4362400.1032 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Guihulngan City |  | Binobohan HS | CITY OF GUIHULNGAN | 1 | 1 | 6 | 2STY6CL |  | 16295464.2279 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Guihulngan City | 120271 | Kapudlusan PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | 1STY3CL W/ TOILET |  | 5293200 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Guihulngan City | 189509 | Mandi-i ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL |  | 4411000 |  | COMPLETED | 1 | [10 empty] | Temporarily suspended | 0
NC 2019 | K10 | NIR | Negros Oriental | 120320 | La Libertad CES | LA LIBERTAD | 1 | 1 | 16 | 4STY16CL |  | 43641963.9779 |  | completed | 1 | [10 empty] | Lacking are Building permits including occupancy. On process | 0
NC 2019 | K10 | NIR | Negros Oriental | 120049 | Mabato ES | Ayungon | 1 | 1 | 3 | 1STY3CL W/ TOILET |  | 5293200 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120052 | Nabhang ES | AYUNGON | 1 | 1 | 2 | 1STY2CL W/ TOILET |  | 4451100 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120592 | Nabilog Elementary School | TAYASAN | 1 | 1 | 9 | 3UNITS 1STY3CL |  | 15047108.9224 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120341 | BANBAN ELEMENTARY SCHOOL | MABINAY | 2 | 1 | 2 | 1STY2CL |  | 3428791.6827 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120342 | Barang-barang Primary School | MABINAY | 2 | 1 | 3 | 1STY3CL |  | 5301439.4573 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Negros Oriental | 303224 | Apolinar B. Macias Memorial High School | DAUIN | 3 | 1 | 4 | 4STY4 lab (2 sci-lab, 2 ICT) |  | 17734607.173 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120507 | Cawitan Elementary School | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 3905461.305 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | 4 | 4STY4 lab (2 reg workshop, 1 sci-lab, 1 ICT) |  | 17630490.1095 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120459 | Felipe Tayko MCES | SIATON | 3 | 1 | 6 | 2STY6CL |  | 11785558.4401 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Negros Oriental | 120461 | Inalad Elementary School | SIATON | 3 | 1 | 6 | 2STY6CL |  | 14329571.9133 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | 4 | 4STY4 lab (4 reg workshop, 2 ICT) |  | 17603469.5967 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Negros Oriental | 361077 | Pulangbato National Senior High School | VALENCIA (LUZURRIAGA) | 3 | 1 | 10 | 4STY6 lab (2 reg workshop, 2 sci-lab, 2 ICT, 4CL) |  | 38548062.7924 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | NIR | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | LARENA | 0 | 1 | 2 | 1 unit, 2 Sty, Science Lab. Bldg |  | 14028697.4128 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | NIR | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 2 | 1STY2CL |  | 3090863.2083 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Siquijor | 120698 | Cantabon Elementary School | SIQUIJOR (Capital) | 0 | 1 | 6 | 2STY6CL |  | 14950657.5252 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | NIR | Siquijor | 120662 | New Corregidor Elementary School | LARENA | 0 | 1 | 2 | 1STY2CL |  | 3030349.5013 |  | COMPLETED | 1 | [11 empty] | 0
NC 2020 | K10 | NIR | Bacolod City | 181004 | Vista Alegre-Granada Relocation ES | Bacolod City (Capital) | 0 | 1 | 6 | 2STY6CL |  | 17687859.38 |  |  | completed | 1 | [10 empty] | completed
NC 2020 | SHS | NIR | Cadiz City | 302736 | Jerusalem National High School (yee-on Ext.) | Cadiz City | 2 | 1 | 4 | 1-unit 1-sty 4-cl with security grills, attached toilet |  | 10867540.7 |  |  | COMPLETED | 1
NC 2020 | SHS | NIR | Kabankalan City | 302794 | Inapoy NHS | Kabankalan City | 6 | 1 | 6 | 2STY6CL |  | 16190375 |  |  | COMPLETED | 1
NC 2020 | K10 | NIR | La Carlota City | 117631 | Balabag ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 5200849.65 |  |  | Completed | 1
NC 2020 | K10 | NIR | La Carlota City | 117632 | Batuan ES | LA CARLOTA CITY | 4 | 1 | 2 | 1STY2CL |  | 5350650.12 |  |  | Completed | 1
NC 2020 | SHS | NIR | Negros Occidental | 302658 | Labilabi NHS | TOBOSO | 1 | 1 | 2 | 1STY2CL W/ TOILET |  | 5058147.54 |  | 5045428.86 | COMPLETED | 1 | 2021-01-08 |  | P00470046VS-CW1 | 20GK0166 | 2020-01-16 | 2020-01-23 | 2020-02-06 | 2020-02-11 | 2020-08-11 | SBK Const.
NC 2020 | TVL | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS (Annex) | SALVADOR BENEDICTO | 1 | 1 | 2 | WORKSHOP BLDG. (7X18) |  | 5991450.81 |  | 5976486.72 | COMPLETED | 1 | 2020-11-14 |  | P00470047VS-CW1 | 20GK0235 | 2020-07-23 | 2020-07-31 | 2020-08-13 | 2020-08-18 | 2020-08-25 | Kenneth Const.
NC 2020 | SHS | NIR | Negros Occidental | 302663 | Manapla NHS - Purisima Extension | MANAPLA | 2 | 1 | 4 | 2UNITS 1STY2CL W/ TOILET |  | 10410325.71 |  | 9864711.83 | COMPLETED | 1 | 2021-02-24 |  | P00470048VS-CW1 | 20GK0154 |  | 2019-12-13 | 2019-12-26 | 2020-01-02 | 2020-08-17 | PVH CONSTRUCTION AND SUPLY
NC 2020 | K10 | NIR | Negros Occidental | 117028 | Jose M. Consing Memorial School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 6 | 2STY6CL |  | 18755790.98 |  | 18146863.26 | COMPLETED | 1 | 2021-01-13 |  | P00470049VS-CW1 | 20GK0234 |  | 2020-07-31 | 2020-08-13 | 2020-08-18 | 2020-08-25 | SILVERGRACES CONSTRUCTION
NC 2020 | K10 | NIR | Negros Occidental | 300683 | San Enrique NHS (Sibucao Ext.) | SAN ENRIQUE | 4 | 1 | 4 | 2STY4CL |  | 9266290.46 |  | 8965884.41 | Completed | 1 |  |  | P00470050VS-CW1 | 20GN0035 | [5 empty] | CGGFR CONSTRUCTION & CONSTRUCTION SUPPLY
NC 2020 | K10 | NIR | Negros Occidental | 117218 | Cabacungan ES | LA CASTELLANA | 5 | 1 | 4 | 2STY4CL |  | 13039516.17 |  |  | Completed | 1
NC 2020 | K10 | NIR | Negros Occidental | 117173 | Tabu ES | ILOG | 6 | 1 | 4 | 2STY4CL |  | 11390405 |  | 10792999.13 | completed | 1 |  |  | P00470052VS-CW1 | 20GM0081 | [5 empty] | SPOILED SPORTS CONSTRUCTION AND SUPPLY
NC 2020 | TVL | NIR | San Carlos City | 302775 | Julio Ledesma NHS | San Carlos City | 1 | 1 | 4 | 2stryICT Lab |  | 12030000 |  |  | COMPLETED | 1
NC 2020 | SHS | NIR | Silay City | 500198 | Silay SPED Center | SILAY CITY | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | COMPLETED | 1 | [9 empty] | Silvergraces Construction & Supply
NC 2020 | SHS | NIR | Bais City | 323004 | Cambagahan National HS | BAIS CITY | 2 | 1 | 4 | 2STY4CL |  | 10395925 |  |  | completed | 1
NC 2020 | K10 | NIR | Bayawan City | 120118 | Olandao Elementary School | BASAY | 3 | 1 | 8 | 2STY8CL |  | 23388679.27 |  |  | completed | 1 | [10 empty] | no manpower on site
NC 2020 | SHS | NIR | Dumaguete City | 303171 | Taclobo NHS | DUMAGUETE CITY | 2 | 1 | 4 | 2STY4CL |  | 9123973.58 |  |  | completed | 1
NC 2020 | K10 | NIR | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | 1STY2CL |  | 3920777.5 |  |  | COMPLETED | 1
NC 2020 | K10 | NIR | Guihulngan City | 120628 | Don Julian dela Vina Villegas Memorial ES | Vallehermoso | 1 | 1 | 2 | 1STY2CL |  | 3569902.5 |  |  | completed | 1
NC 2020 | K10 | NIR | Guihulngan City | 120634 | Malangsa ES | Vallehermoso | 1 | 1 | 3 | 1STY3CL |  | 5159867.5 |  |  | COMPLETED | 1
NC 2020 | K10 | NIR | Guihulngan City | 120249 | Laos ES | City of Guihulngan | 1 | 1 | 6 | 2 units 1Sty3CL W/ CR |  | 14496150 |  |  | COMPLETED | 1
NC 2020 | K10 | NIR | Negros Oriental | 120198 | Bayog Elementary School | CANLAON CITY | 1 | 1 | 6 | 2STY6CL |  | 17352272.5 |  |  | completed | 1 | [10 empty] | Under Canlaon City Division
NC 2020 | K10 | NIR | Negros Oriental | 120587 | Lutay ES | Tayasan | 1 | 1 | 8 | 2STY8CL |  | 24862000 |  |  | COMPLETED | 1 | [10 empty] | With remaining Puchlisted items to be rectified
NC 2020 | K10 | NIR | Negros Oriental |  | Carmen ES | CANLAON CITY | 1 | 1 | 2 | 1STY2CL W/ CR |  | 4466137.5 |  |  | completed | 1
NC 2020 | K10 | NIR | Negros Oriental |  | Pasto ES | CANLAON CITY | 1 | 1 | 2 | 1STY2CL W/ CR |  | 5037562.5 |  |  | completed | 1
NC 2020 | K10 | NIR | Negros Oriental | 120368 | Manlingay Elementary School | MABINAY | 2 | 1 | 6 | 2STY6CL |  | 16820547.35 |  |  | Completed | 1 | [10 empty] | Under rectification of Punchlisted Items; With coordination meeting with DPWH last October 25, 2022 to settle issues and concerns and set target completion of the project.
NC 2020 | K10 | NIR | Negros Oriental | 120488 | Escaguit Elementary School | SIBULAN | 2 | 1 | 4 | 2STY4CL |  | 10001854.28 |  |  | completed | 1
NC 2020 | K10 | NIR | Negros Oriental | 120062 | Buntod Elementary school | BACONG | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 3997994.28 |  |  | completed | 1
NC 2020 | K10 | NIR | Negros Oriental | 120226 | Maayongtubig ES | DAUIN | 3 | 1 | 4 | 2STY4CL |  | 12011846.68 |  |  | completed | 1
NC 2020 | K10 | NIR | Negros Oriental | 120507 | Cawitan Elementary School | SANTA CATALINA | 3 | 1 | 2 | 1STY2CL W/ TOILET |  | 3905461.31 |  |  | completed | 1
NC 2020 | SHS | NIR | Negros Oriental | 312968 | Palayuhan High School | SIATON | 3 | 1 | 4 | 2STY4CL |  | 12440190.55 |  |  | completed | 1
NC 2020 | K10 | NIR | Siquijor | 120659 | Larena Central Elementary School | LARENA | 0 | 1 | 4 | 2STY4CL |  | 11027500 |  |  | completed | 1
NC 2020 | K10 | NIR | Tanjay City | 120409 | Banawe Elementary School | Pamplona | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 4200475 |  |  | completed | 1
NC 2020 | K10 | NIR | Tanjay City | 120565 | Pilipigan Lnd. PIS | Tanjay | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 5002475 |  |  | REVERTED | 0 | [10 empty] | realigned
NC 2021 | TVL | NIR | Bacolod City | 302711 | Luisa Medel NHS | BACOLOD CITY (Capital) | 0 | 1 | 8 | Construction/Completion (4STY4 LAB (2 sci lab, 2 ICT, w/ 4CL)) |  | 12785885 | 12754000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Bacolod City | 311201 | M. G. Medalla Integrated School | BACOLOD CITY (Capital) | 0 | 1 | 4 | Construction/Completion (4STY4 LAB (2 sci lab, 2 ICT lab)) |  | 2265650 | 2260000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117418 | Toboso CS | TOBOSO | 1 | 1 | 10 | Construction/Completion (2STY10CL) |  | 5979912.5 | 5965000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117017 | Alacaygan ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET) |  | 554883.75 | 553500 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117025 | E. B. Magalona ES | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 10 | Construction/Completion (2STY10CL) |  | 1293285.15 | 1290060 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117031 | Nanca Elementary School | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 10 | Construction/Completion (2STY10CL) |  | 5863622.5 | 5849000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117447 | Victorias North ES | CITY OF VICTORIAS | 3 | 1 | 6 | Construction/Completion of School Buildings |  | 1157887.5 | 1155000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117305 | Recreo ES | PONTEVEDRA | 4 | 1 | 10 | Construction/Completion (2STY10CL) |  | 6369340.432 | 6353456.79 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Occidental | 117341 | Don Vicente Lopez ES | SAN ENRIQUE | 4 | 1 | 10 | Construction/Completion (2STY10CL) |  | 6282701.2241 | 6267033.64 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 | 1 | 2 | Construction/Completion (1unit- 2sty science lab) |  | 1768843.3607 | 1764432.28 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 716787.5 | 715000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302590 | Andulauan NHS - Ilog Poblacion Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty science lab) |  | 1303250 | 1300000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 | 1 | 2 | Construction/Completion (1unit- 2sty science lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty science lab) |  | 711775 | 710000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302593 | Bocana NHS | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 716787.5 | 715000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 | 1 | 2 | Construction/Completion (1unit- 2sty science lab) |  | 1768843.3607 | 1764432.28 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 716787.5 | 715000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302594 | Bocana NHS - Galicia Ext. | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty science lab) |  | 1303250 | 1300000 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 | 4 | Construction/Completion (2unit- Regular Workhop) |  | 1368412.5 | 1365000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 |  | 2 | Construction/Completion (1unit- 2sty science lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302600 | Bilbao Uybico NHS | HINOBA-AN (ASIA) | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 | 1 | 2 | Construction/Completion (2STY WORKSHOP BLDG) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 |  | 2 | Construction/Completion (2STY WORKSHOP BLDG) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 | 1 | 2 | Construction/Completion (2STY WORKSHOP BLDG) |  | 706762.5 | 705000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302601 | Bulwangan National High School - Talacagay Ext. | HINOBA-AN (ASIA) | 6 |  | 2 | Construction/Completion (2STY WORKSHOP BLDG) |  | 706762.5 | 705000 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 706762.5 | 705000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 1233075 | 1230000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 | 1 | 2 | Construction/Completion (1unit- 2sty science lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 812423.2532 | 810397.26 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 |  | 2 | Construction/Completion (1unit- 2sty science lab) |  | 711775 | 710000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302645 | Tuyom NHS (Guiljungan NHS - Tuyom Ext.) | CAUAYAN | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 716787.5 | 715000 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302661 | Juan Gequillana NHS (Manalad NHS) | ILOG | 6 | 1 | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 1768843.3607 | 1764432.28 |  | COMPLETED | 1
NC 2021 | TVL | NIR | Negros Occidental | 302661 | Juan Gequillana NHS (Manalad NHS) | ILOG | 6 |  | 2 | Construction/Completion (1unit- 2sty ICT lab) |  | 1233075 | 1230000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Sagay City | 117717 | Hautea Elementary School | SAGAY CITY | 2 | 1 | 3 | Construction/Completion (1STY3CL) |  | 773328.5 | 771400 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Silay City | 117801 | Don Eustaquio Hofilena Mem.Elem. School | SILAY CITY | 3 | 1 | 2 | Construction/Completion (1STY2CL) |  | 555685.75 | 554300 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 1182861.0682 | 1179911.29 |  | REVERTED | 0 | [10 empty] | Reverted
NC 2021 | K10 | NIR | Bayawan City | 120121 | Bahian E/S | CITY OF BAYAWAN (TULONG) | 3 |  | 1 | Construction/Completion (1STY2CL W/ TOILET ATTACHED) |  | 1182861.0682 | 1179911.29 | 1179717.93 | COMPLETED | 1 | 2022-03-13 |  | P00575132VS-CW1 | 21HL0148 |  |  |  |  | 2021-11-03 | HASA KONSTRUKT AND SUPPLY | Remaining work is energization from the Elec Coop
NC 2021 | K10 | NIR | Bayawan City | 120132 | Lapay Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1509144.242 | 1505380.79 | 1504692 | COMPLETED | 1 | 2022-02-07 |  | P00575134VS-CW1 | 21HL0146 |  |  |  |  | 2021-11-03 | MG CONSTRUCTION | Remaining work is energization from the Elec Coop
NC 2021 | K10 | NIR | Bayawan City | 120143 | Banga CES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 2 | Construction/Completion (1STY2CL W/ TOILET) |  | 1016440.4241 | 1013905.66 | 1013314.82 | COMPLETED | 1 | 2022-03-14 |  | P00575135VS-CW1 | 21HL0147 |  |  |  |  | 2021-11-03 | H.I.T. CONTRACTORS | Remaining work is energization from the Elec Coop
NC 2021 | TVL | NIR | Bayawan City | 303218 | Actin National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 ICT)) |  | 2602796.1234 | 2596305.36 | 2591636.75 | COMPLETED | 1 | 2022-02-07 |  | P00575136VS-CW1 | 21HL0149 |  |  |  |  | 2021-11-03 | SBK CONSTRUCTION INC. | Remaining work is energization from the Elec Coop
NC 2021 | TVL | NIR | Bayawan City | 303219 | Bal-os National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 SCI LAB)) |  | 1753681.9216 | 1749308.65 | 1744152 | COMPLETED | 1 | 2022-02-07 |  | P00575137VS-CW1 | 21HL0150 |  |  |  |  | 2021-11-03 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2021 | TVL | NIR | Bayawan City | 303220 | Maglinao National High School | BASAY | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 Reg. Workshop, 2 ICT)) |  | 2633074.1697 | 2626507.9 | 2611258 | COMPLETED | 1 | 2022-01-31 |  | P00575138VS-CW1 | 21HL0145 |  |  |  |  | 2021-10-25 | TRIBATA CONSTRUCTION AND DEVELOPMENT
NC 2021 | TVL | NIR | Bayawan City | 303227 | Dawis National High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 SCI LAB, 2 ICT)) |  | 1878599.3163 | 1873914.53 | 1865945.6 | COMPLETED | 1 | 2022-01-30 |  | P00575139VS-CW1 | 21HL0142 |  |  |  |  | 2021-10-26 | SBK CONSTRUCTION INC. | Remaining work is energization from the Elec Coop
NC 2021 | TVL | NIR | Bayawan City | 321902 | Bayawan City Science and Technology Education Center - High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 4 | Construction/Completion (4STY4LAB (2 SCI LAB, 2 ICT)) |  | 2770637.4002 | 2763728.08 | 2713684.8 | Completed | 1 | 2022-01-25 |  | P00575140VS-CW1 | 21HL0143 |  |  |  |  | 2021-10-25 | PHILSOUTH BUILDERS INC.
NC 2021 | SHS | NIR | Bayawan City | 321912 | Cansumalig High School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1917448.3968 | 1912666.73 | 1856039 | Completed | 1 | 2022-01-30 |  | P00575141VS-CW1 | 21HL0144 |  |  |  |  | 2021-10-26 | SBK CONSTRUCTION INC.
NC 2021 | K10 | NIR | Guihulngan City | 120625 | Don Vicente Lopez, Sr. MS (Bagawines ES) | VALLEHERMOSO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1674175 | 1670000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Guihulngan City | 120628 | Don Julian dela Vina Villegas Memorial ES | VALLEHERMOSO | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 3011510 | 3004000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Guihulngan City | 120638 | Tabon Elementary School | VALLEHERMOSO | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1674175 | 1670000 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Guihulngan City | 303230 | GUIHULNGAN NATIONAL AGRICULTURAL SCHOOL | CITY OF GUIHULNGAN | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 8461100 | 8440000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120052 | Nabhang ES | AYUNGON | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 18468055 | 18422000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 2054122.5 | 2049000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120206 | Linothangan ES | CANLAON CITY | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 2866147.5 | 2859000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120215 | Pula ES | CANLAON CITY | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1623047.5 | 1619000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120318 | Guihob ES | LA LIBERTAD | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1995977.5 | 1991000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120396 | Matambok ES | MANJUYOD | 1 | 1 | 14 | Construction/Completion (2STY8CL & 2STY6CL) |  | 39570680 | 39472000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120579 | Banga ES | TAYASAN | 1 | 1 | 1 | Construction/Completion (1STY1CL) |  | 1019542.5 | 1017000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120582 | Guincalaban Elementary School | TAYASAN | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6206477.5 | 6191000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 189503 | Agutayon Primary School | JIMALALUD | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 18468055 | 18422000 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120461 | Inalad Elementary School | SIATON | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1417801.0735 | 1414265.41 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120606 | Balabag Elementary School | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 15833321.9133 | 15793837.32 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120608 | Balugo Elementary School | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 15783196.9133 | 15743837.32 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Negros Oriental | 120608 | Balugo Elementary School | VALENCIA (LUZURRIAGA) | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 15783196.9133 | 15743837.32 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 ICT, 2 sci-lab)) |  | 1723485.6392 | 1719187.67 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 reg workshop, 2 sci-lab)) |  | 1690094.2389 | 1685879.54 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 reg workshop, 2 sci-lab)) |  | 1677544.0416 | 1673360.64 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 303269 | Lorenza P. Palarpalar MHS (Bonbonon PCHS) | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 ICT, 2 sci-lab)) |  | 1761402.3245 | 1757009.8 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 reg workshop, 2 ICT)) |  | 1693440.9648 | 1689217.92 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 ICT, 2 sci-lab)) |  | 1757955.3586 | 1753571.43 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | 4 | Construction/Completion (4STY4 lab (2 ICT, 2 sci-lab)) |  | 1720469.9889 | 1716179.54 |  | COMPLETED | 1
NC 2021 | SHS | NIR | Negros Oriental | 312918 | Buntod High School | BACONG | 3 | 1 | 4 | Construction/Completion (4STY4 lab (4 reg workshop)) |  | 1573110.6392 | 1569187.67 |  | COMPLETED | 1
NC 2021 | K10 | NIR | Siquijor | 120662 | New Corregidor Elementary School | LARENA | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 581450 | 580000 | 568295.24 | completed | 1 | 2021-12-27 |  |  | 21HM0064 | 2021-09-10 | 2021-10-07 | 2021-10-19 | 2021-10-22 | 2021-11-03 | Quicksilver Construction Services
NC 2021 | SHS | NIR | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 2 | Construction/Completion (1STY2CL) |  | 581450 | 580000 | 568295.24 | completed | 1 | 2021-12-27 |  |  | 21HM0065 | 2021-09-10 | 2021-10-07 | 2021-10-19 | 2021-10-22 | 2021-11-03 | Quicksilver Construction Services
NC 2021 | K10 | NIR | Tanjay City | 120423 | Pamplona CES | PAMPLONA | 2 | 1 | 18 | Construction/Completion (2UNITS 3STY9CL) |  | 54135000 | 54000000 |  | Completed | 1
NC 2022 | K10 | NIR | Bais City | 120077 | Olympia Elementary School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2 |  | 13127737.5 | 13095000 | Completed | 1 | 2023-06-20 | 2023-06-20 | P00675013VS-CW1 | 22HK0103 | 2022-06-07 | 2022-07-14 | 2022-07-26 | 2022-11-14 | 2022-11-24 | SILLIMAN AVENUE CONST & SUPPLY
NC 2022 | K10 | NIR | Guihulngan City | 120280 | Pitogo PS | CITY OF GUIHULNGAN | 1 | 1 | 5 | 1STY2CL WITH CR EACH CLASSROOM AND 1STY3CL WITH CR EACH CLASSROOM | 2 |  | 11401432.5 | 11373000 | Ongoing | 0.9 | 2023-11-05 |  | P00675028VS-CW1 | 22HJ0111 | 2022-06-24 | 2022-01-07 | 2022-07-15 | 2022-11-16 | 2022-11-28 | K.M. Golong Construction
NC 2022 | K10 | NIR | Negros Oriental | 120310 | Agbobolo ES (Aya ES) | LA LIBERTAD | 1 | 1 | 2 | 1STY2CL WITH CR EACH CLASSROOM | 2 |  | 4564382.5 | 4553000 | Ongoing | 0.95 | 2023-07-08 |  | P00675029VS-CW1 | 22HJ0110 | 2022-06-24 | 2022-01-07 | 2022-07-15 | 2022-11-16 | 2022-11-28 | Triple Jo Construction Services | Slow Pace; closely coordinated with DPWH; for punchlisting inspection on June 10, 2025
NC 2022 | K10 | NIR | Negros Oriental | 120435 | Alicia C. Calumpang Elementary School | SAN JOSE | 2 | 1 | 2 | 1STY2CL W/ TOILET | 2 |  | 5714250 | 5657641.92 | Completed | 1 | 2023-05-04 | 2023-05-04 | P00675030VS-CW1 | 22HK0101 | 2022-06-07 | 2022-07-14 | 2022-07-26 | 2022-11-14 | 2022-11-24 | TOP RAMP CONSTRUCTION CORPORATION
NC 2022 | K10 | NIR | Siquijor | 501430 | San Juan Integrated School | SAN JUAN | 0 | 1 | 6 | 2STY6CL | 2 |  | 21052500 | 20989828 | Ongoing | 0.96 | 2023-07-27 |  | P00675031VS-CW1 | 22HM0081 | 2022-11-16 | 2022-11-24 | 2022-06-12 | 2023-12-19 | 2023-03-01 | JCJD PREMIER BUILDERS CORPORATION | With approved 60 Calendar Days Time Extension due to RROW
NC 2022 | SHS | NIR | Negros Occidental | 302695 | Victorias NHS | CITY OF VICTORIAS | 3 | 1 | 6 | 2STY6CL | 1 |  | 17543750 |  | Completed | 1
NC 2022 | SHS | NIR | Negros Occidental | 302621 | Enrique B. Magalona NHS | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 6 | 2STY6CL | 1 |  | 17543750 |  | Completed | 1
NC 2022 | SHS | NIR | Bais City | 303216 | Bais City National Science High School | BAIS CITY | 2 | 1 | 4 | 2STY4CL | 2 |  | 13689137.5 | 12963482.6 | Completed | 1 | 2023-05-14 | 2023-05-14 | P00675012VS-CW1 | 22HK0102 | 2022-06-07 | 2022-07-14 | 2022-07-26 | 2022-11-14 | 2022-11-24 | DOUBLE J AND T CONSTRUCTION AND SUPPLY CORPORATION
NC 2023 | K10 | NIR | Bacolod City | 302699 | ABKASA NHS | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P00775013VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bacolod City | 117465 | Alberto D. Arceo Sr. ES | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P0077508VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | NIR | Bacolod City | 302701 | Bacolod City NHS | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-03 | P0077014VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bacolod City |  | Bacolod City NHS - Extension | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 |  | not yet started | 0 | [10 empty] | reverted due to allocated school site not yet established (no school id)
NC 2023 | K10 | NIR | Bacolod City | 117478 | Dona E.J. Garcia ES | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2402135 | Completed | 1 | 2024-01-03 | 2024-01-03 | P0077011VS-CW1 | [6 empty] | KJC CONSTRUCTION & SUPPLY | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | NIR | Bacolod City | 302706 | Emiliano Lizares NHS | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-01-29 | P00775016VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bacolod City | 117484 | Estefania ES | BACOLOD CITY (Capital) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5000000 | Completed | 1 | 2024-02-12 | 2024-02-12 | P00775012VS-CW1 | [6 empty] | SILVERRIA CONSTRUCTION AND CONSTRUCTION SUPPLY COMPANY | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bacolod City | 117472 | Jose Gonzaga ES | BACOLOD CITY (Capital) |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 | 30000000 | Completed | 1 | 2024-07-01 | 2024-07-31 | P00775009VS-CW1 | [6 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES INC. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | NIR | Bacolod City | 302704 | Romanito P. Maravilla, Sr. National High School | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-01-03 | 2024-02-29 | P00775015VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | SHS | NIR | Bacolod City | 302718 | Teofilo Gensoli,Sr. National High School | BACOLOD CITY (Capital) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 5000000 | Completed | 1 | 2024-02-12 | 2024-01-15 | P00775017VS-CW1 | [6 empty] | RVDP Construction | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bacolod City | 117474 | Vista Alegre ES | BACOLOD CITY (Capital) |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 | 2500000 | Completed | 1 | 2024-02-25 | 2024-02-25 | P00775010VS-CW1 | [6 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | Completed and turned-over to school. DPWH to provide complete Data
NC 2023 | K10 | NIR | Bago City | 117519 | Cristeta A. Dormido ES | BAGO CITY |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6534399.05 | Completed | 1 | 2024-01-06 | [8 empty] | Bachoco Construction and Supply | DPWH to provide complete Data
NC 2023 | K10 | NIR | Bago City | 117528 | Don Salvador Benedicto Memorial School | BAGO CITY |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6583541.79 | Completed | 1 | 2023-12-10 | [8 empty] | 911 Rovoca Development Co. | DPWH to provide complete Data
NC 2023 | K10 | NIR | Bago City | 117522 | Louisiana Elementary School | BAGO CITY |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10533450.47 | Completed | 1 | 2024-06-23 |  | P00775933LZ-CW1 | 23FK0107 |  | 2023-08-08 | 2023-08-22 | 2023-08-30 | 2023-09-07 | GKMM Construction and Supplies, Inc. | DPWH to provide complete Data
NC 2023 | K10 | NIR | Cadiz City | 117533 | Hiyang-Hiyang ES | CADIZ CITY |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 67650141.66 | ongoing | 0.6 | 2024-07-29 |  | P00775594-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV) | On-going
NC 2023 | K10 | NIR | Cadiz City | 117542 | Villacin ES | CADIZ CITY |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 21941660.47 | ongoing | 0.9 | 2024-07-29 |  | P00775944-CW1 | 23FL0069 | 2023-07-27 | 2023-08-03 | 2023-08-16 | 2023-08-30 | 2023-09-08 | Steven Const. and Supply / Kyla Const. Supply (JV) | On- going
NC 2023 | K10 | NIR | Kabankalan City | 117840 | Esteban R. Abada Memorial School - West SPED | CITY OF KABANKALAN |  | 1 | 1 |  | Batch 1 | 2521875 | 2500000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 116914 | San Isidro ES | CALATRAVA |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117327 | Bagong Silang ES | SALVADOR BENEDICTO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS | SALVADOR BENEDICTO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117024 | Don H. Maravilla MS | ENRIQUE B. MAGALONA (SARAVIA) |  | 1 | 4 |  | Batch 1 | 14122500 | 14000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117423 | Ayungon ES | VALLADOLID |  | 1 | 6 |  | Batch 1 | 6661039.51 | 6603260.98 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117119 | Tagda ES | HINIGARAN |  | 1 | 3 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117185 | Bulad ES | ISABELA |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117213 | Don Generoso M. Villanueva ES | LA CASTELLANA |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117222 | Mansalanao ES | LA CASTELLANA |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 117237 | Nato Soliguen ES | LA CASTELLANA |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 501793 | Baclao Integrated School | CAUAYAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Negros Occidental | 116985 | Tibak PS | CAUAYAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | NIR | Negros Occidental | 302688 | Tabu NHS | ILOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | SHS | NIR | Negros Occidental | 302689 | Tabu NHS - Canlamay Extension | ILOG |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | DPWH to provide complete Data
NC 2023 | K10 | NIR | Sagay City | 311801 | Old Sagay National High School | SAGAY CITY |  | 1 | 10 |  | Batch 1 | 10732989.77 | 10639890.72 | 10320198.76 | Completed | 1 | 2023-11-20 | 2023-11-20 | 23GK0206 | 23GK0206 | 2023-05-30 | 2023-06-07 | 2023-06-21 | 2023-07-10 | 2023-07-21 | GALFONS BUILDERS AND SUPPLY, INC.
NC 2023 | K10 | NIR | San Carlos City | 117776 | Iliranan IS | SAN CARLOS CITY |  | 1 | 5 |  | Batch 1 | 4788571.5 | 4747034.94 | 4718182.49 | Completed | 1 |  |  | 23GQ0065 |  | 2023-07-25 | 2023-08-01 | 2023-08-15 | 2023-09-08 |  | Kenneth Const. & Gen. Merchandise | DPWH to provide complete Data
NC 2023 | K10 | NIR | San Carlos City | 117794 | Lina dela Viña Valmayor ES | SAN CARLOS CITY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4710071.52 | Completed | 1 |  |  | 23GQ0066 |  | 2023-07-25 | 2024-08-01 | 2023-08-15 | 2023-09-08 |  | Kenneth Const. & Gen. Merchandise | DPWH to provide complete Data
NC 2023 | K10 | NIR | Sipalay City | 117365 | Barasbarasan Elementary School - Indangawan Annex | CITY OF SIPALAY |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4992477.72 | COMPLETED | 1 | 2023-12-06 | 2023-12-06 | P00775084VS-CW1 | 23GM0068 | 2023-06-15 | 2023-06-23 | 2023-07-05 | 2023-07-26 | 2023-08-17 | JVC TOUGH CORE CNST. AND BUILDERS CORP.
NC 2023 | K10 | NIR | Sipalay City | 117376 | Macarandan ES | CITY OF SIPALAY |  | 1 | 2 |  | Batch 1 | 2521875 | 2500000 | 2500000 | COMPLETED | 1 | 2023-12-07 | 2023-12-17 | P00775085VS-CW1 | 23GM0069 | 2023-07-14 | 2023-07-24 | 2023-08-07 | 2023-08-25 | 2023-09-19 | JVC TOUGH CORE CNST. AND BUILDERS CORP.
NC 2023 | K10 | NIR | Victorias City | 117431 | Estado ES | CITY OF VICTORIAS |  | 1 | 1 |  | Batch 1 | 16140000 | 16000000 | 15999999.62 | Completed | 1 | 2023-12-17 | 2024-01-19 | 23GK0208 | 23GK0208 | [5 empty] | KENBE CONSTRUCTION AND SUPPLY | Completed. DPWH to provide complete Data
NC 2023 | K10 | NIR | Canlaon City | 120215 | Pula ES | CANLAON CITY |  | 1 | 2 |  | Batch 1 | 5346375 | 5300000 | 5070392.13 | Completed | 1 | 2023-10-29 | 2023-10-29 |  | 23HJ0097 | [5 empty] | REKINA CONSTRUCTION SERVICES
NC 2023 | K10 | NIR | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN |  | 1 | 3 |  | Batch 1 | 6859500 | 6800000 | 6795000 | Completed | 1 | 2023-11-05 | 2023-11-06 | P00775141VS-CW1 | 23HJ0099 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | MAI Construction and Supply
NC 2023 | K10 | NIR | Guihulngan City | 305713 | Balogo National High School | CITY OF GUIHULNGAN |  | 1 | 2 |  | Batch 1 | 5144625 | 5100000 | 5144630 | Completed | 1 | 2023-12-29 | 2023-10-27 | P00775142VS-CW1 | 23HJ0096 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | MAI Construction and Supply
NC 2023 | K10 | NIR | Guihulngan City | 305915 | Calamba National High School | CITY OF GUIHULNGAN |  | 1 | 2 |  | Batch 1 | 4942875 | 4900000 | 4880060.96 | Completed | 1 | 2024-05-31 | 2024-05-31 | P00775143VS-CW1 | 23HJ0103 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2024-02-28 | 2024-03-01 | K.M. Golong Construction
NC 2023 | K10 | NIR | Guihulngan City | 136947 | Puti-an Elementary School | VALLEHERMOSO |  | 1 | 2 |  | Batch 1 | 4942875 | 4900000 | 4942880 | Completed | 1 | 2024-01-11 | 2024-01-11 | P00775144VS-CW1 | 23HJ0102 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2023-10-05 | 2023-10-16 | Rekina Construction Services
NC 2023 | K10 | NIR | Negros Oriental | 120031 | Anibong Elementary School | AYUNGON |  | 1 | 4 |  | Batch 1 | 10289250 | 10200000 | 10090000 | Completed | 1 | 2024-04-15 | 2024-01-29 | P00775148VS-CW1 | 23HJ0098 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | MAI Construction and Supply | Manual hauling; As per data given by DPWH FIRST DEO.
NC 2023 | K10 | NIR | Negros Oriental | 120327 | Martilo ES | LA LIBERTAD |  | 1 | 2 |  | Batch 1 | 4942875 | 4900000 | 4900000 | Completed | 1 | 2023-10-28 | 2023-10-28 | P00775149VS-CW1 | 23HJ0100 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | K.M. Golong Construction | as per data given by DPWH FIRST DEO.
NC 2023 | K10 | NIR | Negros Oriental | 120334 | Solonggon ES | LA LIBERTAD |  | 1 | 2 |  | Batch 1 | 4942875 | 4900000 | 4900000 | Completed | 1 | 2023-10-28 | 2023-10-28 | P00775150VS-CW1 | 23HJ0101 | 2023-06-15 | 2023-06-22 | 2023-07-04 | 2023-07-18 | 2023-07-31 | K.M. Golong Construction | as per data given by DPWH FIRST DEO.
NC 2023 | K10 | NIR | Negros Oriental | 305592 | Dr. Ernesto A. Uy Sr. National High School | MABINAY |  | 1 | 4 |  | Batch 1 | 17148750 | 17000000 | 16984305 | Completed | 1 | 2024-02-20 | 2024-02-20 | P00775151VS-CW1 | 23HK0159 | 2023-07-07 | 2023-07-15 | 2023-07-27 | 2023-08-22 | 2023-01-09 | R.R. Gadingan Construction | as per data given by DPWH 2nd DEO.
NC 2023 | K10 | NIR | Negros Oriental | 120430 | Basak Primary School | SAN JOSE |  | 1 | 2 |  | Batch 1 | 5835618.75 | 5785000 | 5779090 | Completed | 1 | 2024-02-26 | 2024-08-30 | P00775152VS-CW1 | 23HK0158 | 2023-07-07 | 2023-07-15 | 2023-07-27 | 2023-08-22 | 2023-04-09 | Ashleyka Const. & Supplies | as per data given by DPWH 2nd DEO.
NC 2023 | K10 | NIR | Negros Oriental | 120489 | Libertad Ong Calderon MES (Ajong Elementary S) | SIBULAN |  | 1 | 3 |  | Batch 1 | 12105000 | 12000000 | 11984960 | Completed | 1 | 2024-04-02 | 2024-04-15 | P00775153VS-CW1 | 23HK0160 | 2023-07-07 | 2023-07-15 | 2023-07-27 | 2023-08-22 | 2023-01-09 | Per Construction and Supply | as per data given by DPWH 2nd DEO.
NC 2023 | K10 | NIR | Negros Oriental | 120067 | San Miguel Elementary School | BACONG |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14848582.15 | Completed | 1 | 2024-02-11 | 2024-02-11 | P00775154VS-CW1 | 23HL0093 | 2023-06-29 | 2023-06-07 | 2023-07-18 | 2023-07-26 | 2023-08-14 | NRS BUILDERS AND SUPPLIES | as per data given by DPWH 3rd DEO
NC 2023 | K10 | NIR | Negros Oriental | 120610 | Bongbong ES | VALENCIA (LUZURRIAGA) |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14848913.96 | Completed | 1 | 2024-02-11 | 2024-02-11 | P00775155VS-CW1 | 23HL0094 | 2023-06-29 | 2023-06-07 | 2023-07-18 | 2023-07-26 | 2023-08-14 | NRS BUILDERS AND SUPPLIES | as per data given by DPWH 3rd DEO
NC 2023 | K10 | NIR | Siquijor | 120675 | Kimba Elementary School | LAZI |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 5996230.32 | Completed | 1 | 2023-11-10 | 2023-11-20 | P00775156VS-CW1 | 23HM0120 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | VNCO Construction | remove & replace reinforcing bars on footing & columns.
NC 2023 | K10 | NIR | Siquijor | 120676 | Kinamandagan Elementary School | LAZI |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 5989831.22 | Completed | 1 | 2023-11-10 | 2023-11-10 | P00775157VS-CW1 | 23HM0121 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | VNCO Construction | COA approval on the application for demolition was received last Oct. 16, 2023.
NC 2023 | K10 | NIR | Siquijor | 120680 | Logucan Elementary School | MARIA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4983826.36 | Completed | 1 | 2023-11-10 | 2023-11-10 | P00775158VS-CW1 | 23HM0122 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | TESAR BUILDERS | late mobilization of contractor
NC 2023 | K10 | NIR | Siquijor | 501429 | Maria Integrated School | MARIA |  | 1 | 4 |  | Batch 1 | 12105000 | 12000000 | 11981018.05 | Ongoing | 0.5 | 2023-12-15 |  | P00775160VS-CW1 | 23HM0124 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | TESAR BUILDERS
NC 2023 | K10 | NIR | Siquijor | 120683 | Pisong A Elementary School | MARIA |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 5939164.54 | Completed | 1 | 2023-11-10 | 2023-11-16 | P00775159VS-CW1 | 23HM0123 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | MUAÑA CONSTRUCTION AND DEVELOPMENT CORP. | waiting for COA approval on the application for demolition.
NC 2023 | K10 | NIR | Siquijor | 120708 | Tag-ibo Elementary School | SAN JUAN |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7424080.46 | Completed | 1 | 2023-11-20 | 2023-11-20 | P00775160VS-CW1 | 23HM0125 | 2023-06-30 | 2023-07-11 | 2023-07-25 | 2023-08-04 | 2023-08-15 | MUAÑA CONSTRUCTION AND DEVELOPMENT CORP.
NC 2024 |  | NIR | Bacolod City | 117452 | Banago Elementary School I | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925251.68 | Completed | 1 | 2024-10-28 | 2024-11-18 | 24GO0109 | 24GO0109 | [5 empty] | ROCK-WILLIAN CONSTRUCTION AND SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025). DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117455 | Bata Elementary School - I | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0105 | 24GO0105 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025)DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117475 | Don Crispino V. Ramos Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185853.7 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0108 | 24GO0108 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117484 | Estefania Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-11-25 | 24GO0105 | 24GO0105 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117490 | F.R. Flores Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4185926.78 | Completed | 1 | 2024-10-31 | 2024-04-11 | 24GO0106 | 24GO0106 | [5 empty] | SOLAPO CONSTRUCTION AND SUPPLY CO. | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117473 | Paglaum Village Elementary School | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-30 | 2024-11-30 | 24GO0102 | 24GO0102 | [5 empty] | KJC CONSTRUCTION & SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117473 | Paglaum Village Elementary School | BACOLOD CITY (Capital) |  |  | 16 | 4STY16CL | GAA 17B | 40000000 |  | 39800000 | Ongoing | 0.75 | 2025-04-30 |  | 24GO0103 | 24GO0103 | [5 empty] | GOLDSTAR MARKETING & CONSTRUCTION SERVICES, INC. / WILKINSON CONSTRUCTION | DPWH to provide complete Data
NC 2024 |  | NIR | Bacolod City | 117491 | Sum-ag ES | BACOLOD CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4741711.67 | Completed | 1 | 2024-11-11 | 2024-11-11 | 24GO0107 | 24GO0107 | [5 empty] | KENBE CONSTRUCTION & SUPPLY | COMPLETED AND JOINT INSPECTED (MAY 30, 2025) DPWH to provide complete Data
NC 2024 |  | NIR | Bago City | 117511 | Alianza Elementary School | BAGO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949269.88 | Completed | 1 | 2024-05-08 |  |  | 24GN0084 | [5 empty] | J. F. Uy Construction Services | DPWH to provide complete Data
NC 2024 |  | NIR | Bago City | 117505 | Dr. A. Sian ES | BAGO CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925053.59 | Completed | 1 | 2024-05-08 |  |  | 24GN0083 | [5 empty] | EMR Builders | DPWH to provide complete Data
NC 2024 |  | NIR | Cadiz City | 117547 | Cotcot ES | CADIZ CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  |  | Ongoing | 0.45 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | NIR | Cadiz City | 117532 | Dr. V.F.Gustilo ES | CADIZ CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  |  | Ongoing | 0.25 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | NIR | Escalante City | 117044 | Escalante Elementary School | CITY OF ESCALANTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944631.7 | Ongoing | 0.4 | 2025-01-29 |  | P00875370VS-CW1 | 24GQ0074 | 2024-07-24 | 2024-07-17 | 2024-08-14 | 2024-09-13 | 2024-09-24 | RJY Construction
NC 2024 |  | NIR | Escalante City | 325604 | Magsaysay National High School | CITY OF ESCALANTE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4945385.35 | Ongoing | 0.9 | 2025-01-29 |  | P00875371VS-CW1 | 24GQ0076 | 2024-07-24 | 2024-07-17 | 2024-08-15 | 2024-09-14 | 2024-09-25 | RJY Construction
NC 2024 |  | NIR | Escalante City | 302626 | Old Poblacion National High School | CITY OF ESCALANTE |  | 1 | 2 | Construction of School Building | BATCH 1 | 4652142 |  | 4599903.81 | Ongoing | 1 | 2025-01-29 | 2025-01-29 | P00875659VS-CW1 | 24GQ0081 | 2024-07-24 | 2024-07-17 | 2024-08-16 | 2024-09-15 | 2024-09-26 | RJY Construction
NC 2024 |  | NIR | Himamaylan City | 117072 | Cong. Eliseo P. Limsiaco Sr. MES | CITY OF HIMAMAYLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964992.49 | Completed | 1 |  | 2025-02-28 | 24GL0119 | 24GL0119 |  |  | 2024-04-29 |  | 2024-05-23 | NOVANNE VENTURES CONSTRUCTION CORPORATION | 2 MONTHS DELAYED AS PER CONTRACT. DPWH to provide complete Data
NC 2024 |  | NIR | Kabankalan City | 302789 | Kabankalan National High School | CITY OF KABANKALAN |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  |  | Not Yet Started | 0 | [10 empty] | WITH SUSPENSION ORDER. DPWH to provide complete Data
NC 2024 |  | NIR | La Carlota City | 117634 | Caiñaman ES | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-08-20 |  | 24GH0093 | 2024-03-19 |  | 2024-08-04 | 2024-04-18 | 2024-07-05 | LJJR FIRE PROTECTION SERVICES | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | La Carlota City | 117638 | Cubay ES | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-02-09 |  | 24GH0085 | 2024-03-14 |  | 2024-02-04 | 2024-04-19 | 2024-07-05 | SBK CONSTRUCTION AND SERVICES INC. | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | La Carlota City | 117650 | San Miguel ES II | LA CARLOTA CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1 |  | 2024-09-20 |  | 24GH0091 | 2024-03-19 |  | 2024-08-04 | 2024-04-19 | 2024-07-05 | EMR Builder | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302603 | Calatrava NHS | CALATRAVA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925121.4 | Ongoing | 0.99 | 2025-01-29 |  | P00875373VS-CW1 | 24GQ0073 | 2024-07-24 | 2024-07-31 | 2024-08-14 |  |  | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 116907 | Lalong ES | CALATRAVA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4921445.88 | Ongoing | 0.82 | 2025-01-29 |  | P00875374VS-CW1 | 24GQ0075 | 2024-07-24 | 2024-07-31 | 2024-08-14 |  |  | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 502112 | San Benito Integrated School | CALATRAVA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4924354.89 | Ongoing | 0.99 | 2025-01-29 |  | P00875375VS-CW1 | 24GQ0077 | 2024-07-24 | 2024-07-31 | 2024-08-14 |  |  | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS | SALVADOR BENEDICTO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4924386.05 | Ongoing | 0.96 | 2025-01-29 |  | P00875372VS-CW1 | 24GQ0078 | 2024-07-24 | 2024-07-31 | 2024-08-14 |  |  | KENNETH CONSTRUCTION AND GENERAL MERCHANDISE | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302620 | Dr. Antonio Lizares NHS - Ext. | CITY OF TALISAY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9650040.45 | Ongoing | 0.99 | 2024-10-31 |  | P00875379VS-CW1 | 24GK0215 |  |  |  | 2024-09-07 | 2024-07-18 | CANLAON BUILDERS AND DEVELOPMENT CORPORATION | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117018 | Alicante ES | ENRIQUE B. MAGALONA (SARAVIA) |  | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | GAA 17B | 7000000 |  | 6825694.92 | Completed | 1 | 2024-10-21 | [6 empty] | 2024-09-07 | 2024-07-18 | KENBE CONST. AND CONST SUPPLY | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117019 | Banilad ES | ENRIQUE B. MAGALONA (SARAVIA) |  | 1 | 3 | 1STY3CL WITH TOILET ATTACHED | GAA 17B | 7000000 |  | 6825689.92 | Ongoing | 1 | 2024-10-21 | [6 empty] | 2024-09-07 | 2024-07-18 | KENBE CONST. AND CONST SUPPLY | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117020 | Batea Elementary School | ENRIQUE B. MAGALONA (SARAVIA) |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  | 10615619.9 | Ongoing | 0.46 | 2025-04-17 |  |  | 24GK0227 |  |  |  |  | 2025-03-01 | SL 7 G CONSTRUCTION | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117311 | Camingawan ES | PONTEVEDRA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117314 | Mabini ES | PONTEVEDRA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 180504 | Pag-ayon ES | PULUPANDAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117340 | Don Esperidion Presbitero ES | SAN ENRIQUE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117428 | Tabao ES | VALLADOLID |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 116870 | Don A.Y. Locsin ES | BINALBAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 116885 | Doña Jesusa Arroyo ES | BINALBAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302676 | Payao NHS - Namulo Ext. | BINALBAGAN |  | 1 | 4 | 1STY4CL | BATCH 1 | 10110217.59 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 116865 | Pedro Y. Ditching, Sr. - Bagroy ES | BINALBAGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117188 | Cansalongon ES | ISABELA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302654 | Libas National High School | ISABELA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 311105 | Guinpana-an NHS - Poblacion Ext. | MOISES PADILLA (MAGALLON) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 117268 | Moises Padilla ES | MOISES PADILLA (MAGALLON) |  | 1 | 2 | 1STY2CL (SPED) | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 302612 | CAUAYAN NATIONAL HIGH SCHOOL | CAUAYAN |  | 1 | 12 | 3STY12CL | BATCH 1 | 40090000 |  |  | Ongoing | 0.8 | [10 empty] | DPWH to provide complete Data
NC 2024 |  | NIR | Negros Occidental | 116979 | Sibucao Elementary School | CAUAYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  |  | Completed | 1 | [10 empty] | Completed. DPWH to provide complete Data
NC 2024 |  | NIR | Sagay City | 117695 | Buenaventura Rodriguez Elementary School | SAGAY CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17680890 | Ongoing | 0.75 | 2024-05-12 |  | 24GK0216 | 24GK0216 | 2024-05-29 | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | KENBE CONSTRUCTION & SUPPLY | Ongoing
NC 2024 |  | NIR | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY |  | 1 | 12 | Construction of School Building | BATCH 1 | 30705000 |  | 30244039.3 | Ongoing | 0.15 | 2025-06-21 | [8 empty] | Kennith Construction | DPWH to provide complete Data
NC 2024 |  | NIR | San Carlos City | 117760 | Guadalupe ES | SAN CARLOS CITY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9800750 | Ongoing | 0.4 | 2025-04-15 |  |  |  |  | 2024-08-28 | 2024-11-09 |  |  | IDMU Construction | DPWH to provide complete Data
NC 2024 |  | NIR | Silay City | 185001 | Dominador 'Oking' Jison Memorial Elementary School | SILAY CITY |  | 1 | 8 | 4STY8CL | BATCH 1 | 36248000 |  | 35696291.09 | Ongoing | 0.3 |  |  | 24GK0210 |  |  | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | SILVERGRACES CONSTRUCTION & CONSTRUCTION SUPPLY | DPWH to provide complete Data
NC 2024 |  | NIR | Silay City | 500199 | Don Albino & Doña Dolores Jison Integrated School | SILAY CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875489.89 | Completed | 1 |  |  | 24GK0211 |  |  | 2024-04-06 | 2024-06-18 | 2024-12-07 | 2024-07-18 | KENBE CONSTRUCTION & SUPPLY | DPWH to provide complete Data
NC 2024 |  | NIR | Sipalay City | 302640 | Gil Montilla NHS - Manlucahoc Ext. | CITY OF SIPALAY |  | 1 | 4 | 2STY4CL | BATCH 1 | 14100000 |  | 14064750 | Completed | 1 | 2024-05-08 | 2024-11-25 | P00875400VS-CW1 | 24GM0065 | 2024-03-06 | 2024-11-06 | 2024-06-24 | 2024-07-16 | 2024-07-29 | GC ANDS CONSTRUCTION AND SUPPLY
NC 2024 |  | NIR | Sipalay City | 180522 | Omas ES | CITY OF SIPALAY |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 9975000 | Completed | 1 | 2024-04-02 | 2024-04-02 | P00875667VS-CW1 | 24GM0069 | 2024-10-07 | 2024-07-18 | 2024-07-30 | 2024-08-14 | 2024-08-29 | NOVANNE VENTURES CONST. CORP.
NC 2024 |  | NIR | Bayawan City | 501131 | Ali-is Integrated School | CITY OF BAYAWAN (TULONG) |  | 1 | 16 | 4STY16CL | BATCH 1 | 62946888.14 |  | 62578423.85 | Ongoing | 0.98 | 2025-07-06 |  | P00875668VS-CW1 | 24HL0062 | 2024-06-13 | 2024-06-20 | 2024-02-07 | 2024-09-07 | 2024-12-07 | LEBCURT CONSTRUCTION SERVICES/JANUARY BUILDERS (JV)
NC 2024 |  | NIR | Canlaon City | 136969 | Angas 1 Elementary School | CANLAON CITY |  | 1 | 2 | 1STY2CL with CR | GAA 17B | 5500000 |  | 5456718.16 | Completed | 1 | 2024-06-28 | 2024-06-28 | P00875480VS | 24HJ0107 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-26 | 2024-01-04 | REKINA CONSTRUCTION SERVICES | Completed
NC 2024 |  | NIR | Dumaguete City | 119935 | Camanjac Elementary School | DUMAGUETE CITY (Capital) |  | 1 | 12 | 3STY12CL | BATCH 1 | 30000000 |  | 29315691.03 | Ongoing | 0.45 | 2025-04-22 |  | P00875688VS-CW1 | 24HK0140 |  |  | 2024-07-08 | 2024-08-28 | 2024-06-09 | ISA CONSTRUCTION AND DEVELOPMENT CORPORATION | On-going
NC 2024 |  | NIR | Guihulngan City | 324801 | Magsaysay National High School | CITY OF GUIHULNGAN |  | 1 | 4 | 2STY Workshop Building | BATCH 1 | 15450746.27 |  | 15220135.55 | Ongoing | 0.97 | 2025-01-22 |  | P00875689VS | 24HJ0119 | 2024-04-23 | 2024-04-30 | 2024-05-14 | 2024-05-30 | 2024-03-06 | HIGEL CONSTRUCTION
NC 2024 |  | NIR | Guihulngan City | 324802 | P. Zamora National High School | CITY OF GUIHULNGAN |  | 1 | 4 | 2STY4CL | GAA 17B | 16000000 |  | 15829619.26 | Completed | 1 | 2024-10-21 | 2024-10-30 | P00875481VS | 24HJ0110 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-27 | 2024-01-04 | K.M. GOLONG CONSTRUCTION
NC 2024 |  | NIR | Guihulngan City | 120642 | Vallehermoso Central Elementary School | VALLEHERMOSO |  | 1 | 2 | 2STY2CL | GAA 17B | 7000000 |  | 6911026.67 | Completed | 1 | 2024-11-09 | 2025-02-20 | P00875483VS | 24HJ0111 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-27 | 2024-01-04 | REKINA CONSTRUCTION SERVICES
NC 2024 |  | NIR | Negros Oriental | 303235 | Jimalalud National Science High School | JIMALALUD |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5442513.86 | Ongoing | 0.99 | 2024-09-26 |  | P00875482V5 | 24HJ0108 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-26 | 2024-01-04 | KAWAII BUILDERS AND SUPPLIES | with suspension of work due to relocation and site settlement; Ongoing rectification of punchlisted items last June 3, 2024
NC 2024 |  | NIR | Negros Oriental | 303243 | La Libertad Technical-Vocational School Manluminsag Extension | LA LIBERTAD |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5960000 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875484V5 | 24HJ0109 | 2024-02-21 | 2024-02-28 | 2024-12-03 | 2024-03-27 | 2024-01-04 | MAI CONSTRUCTION AND SUPPLY
NC 2024 |  | NIR | Negros Oriental | 120366 | Mabinay Central School | MABINAY |  | 1 | 12 | 2STY6CL | GAA 17B | 40000000 |  | 39420107 | Ongoing | 0.85 | 2024-06-12 |  | P00875485VS-CW1 | 24HK0101 | 2024-02-27 | 2024-06-03 | 2024-03-18 | 2024-03-26 | 2024-04-16 | PER Construction and Supply/VVER Construction (Joint Venture) | Ongoing
NC 2024 |  | NIR | Siquijor | 501427 | Larena Integrated School | LARENA |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9899820.93 | Ongoing | 0.4 | 2024-09-02 |  | P00875486 VS-CW1 | 24HM0092 | 2024-04-17 | 2024-04-25 | 2024-04-25 | 2024-05-15 | 2024-05-27 | VNCO Construction
NC 2024 |  | NIR | Siquijor | 120668 | Campalanas Elementary School | LAZI |  | 1 | 12 | 2STY8CL & 2STY4CL | BATCH 1 | 46300000 |  | 46064864 | Ongoing | 0.2 | 2025-06-14 |  |  | 24HM0102 | 2024-08-09 | 2024-08-16 | 2024-08-28 | 2024-09-03 | 2024-09-13 | VNCO Construction
NC 2024 |  | NIR | Siquijor | 120708 | Tag-ibo Elementary School | SAN JUAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9907590.87 | Completed | 1 | 2024-07-29 | 2024-11-08 | P00875487 VS-CW1 | 24HM0090 | 2024-03-06 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-25 | VNCO Construction
NC 2024 |  | NIR | Siquijor | 120710 | Timbaon Elementary School | SAN JUAN |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9882656.64 | Ongoing | 0.62 | 2024-07-29 |  | P00875488 VS-CW1 | 24HM0091 | 2024-03-06 | 2024-03-14 | 2024-03-26 | 2024-04-15 | 2024-04-25 | Froy J Builders and Supplies/First Grandeur Builders Joint Ventures
NC 2024 |  | NIR | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9934995.14 | Completed | 1 | 2024-08-11 | 2024-11-08 | P00875489 VS-CW1 | 24HM0093 | 2024-03-22 | 2024-04-02 | 2024-04-16 | 2024-04-25 | 2024-05-03 | Froy J Builders and Supplies/First Grandeur Builders Joint Ventures

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.