## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 11, 2025
REPAIR 2020 | NIR | Bacolod City | 117480 | BACOLOD CITY SPED CENTER | BACOLOD CITY (Capital) | 0 | 1 | 10 | Repair of Classrooms | 3101751 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | NIR | Bacolod City | 117454 | Mandalagan ES | BACOLOD CITY (Capital) | 0 | 1 | 17 | Repair of Classrooms | 5231763 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | NIR | Bacolod City | 302718 | Teofilo M. Gensoli Sr. NHS | BACOLOD CITY (Capital) | 0 | 1 | 9 | Repair of Classrooms | 2161682 | 1 |  | COMPLETED | 1 | [10 empty] | RTA isuued, waiting for issuance of SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | Bago City | 117522 | Louisiana Elementary School | BAGO CITY | 4 | 1 | 6 | Repair of Classrooms | 2303740 | 1 | 1448262.47 | COMPLETED | 1 |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | Bago City | 117500 | Newton Jison ES | BAGO CITY | 4 | 1 | 9 | Repair of Classrooms | 3509767 | 1 | 2216066.59 | COMPLETED | 1 |  |  |  |  | 2020-02-10 | 2020-02-20 | 2020-03-04 | 2020-06-30 | 2020-11-06 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | Cadiz City | 302730 | Dr. Vicente F. Gustilo Memorial NHS | CADIZ CITY | 2 | 1 | 24 | Repair of Classrooms | 9493231 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 24 | 0 | 0
REPAIR 2020 | NIR | Cadiz City | 117564 | Luis Uy Chiat Elementary School | CADIZ CITY | 2 | 1 | 7 | Repair of Classrooms | 3333723 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Escalante City | 325605 | Escalante NHS - Libertad Ext. | CITY OF ESCALANTE | 1 | 1 | 5 | Repair of Classrooms | 1147308 | 1 | 1147307.33 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Escalante City | 117059 | Libertad Elementary School | CITY OF ESCALANTE | 1 | 1 | 12 | Repair of Classrooms | 2955791 | 1 | 2955791 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | NIR | Escalante City | 117060 | Mabini Central Elementary School | CITY OF ESCALANTE | 1 | 1 | 18 | Repair of Classrooms | 2527000 | 1 | 2526999.01 | COMPLETED | 1 |  |  |  |  | January 2, 2020 | January 13, 2020 | January 23, 2020 | February 3, 2020 |  | JPEG Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | NIR | Himamaylan City | 117071 | Catingib ES | CITY OF HIMAMAYLAN | 5 | 1 | 6 | Repair of Classrooms | 1291397 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | Himamaylan City | 117103 | Mambagaton ES | CITY OF HIMAMAYLAN | 5 | 1 | 13 | Repair of Classrooms | 4174262 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | NIR | Himamaylan City | 117108 | Manuel Yulo ES | CITY OF HIMAMAYLAN | 5 | 1 | 7 | Repair of Classrooms | 2452596 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 312102 | Bantayan NHS - Baras Diutay Ext. | CITY OF KABANKALAN | 6 | 1 | 5 | Repair of Classrooms | 2229775 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 302795 | Locotan NHS | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 4316400 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 117863 | Magtongtong ES | CITY OF KABANKALAN | 6 | 1 | 8 | Repair of Classrooms | 2943394 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 117844 | Mansumbil Elementary School | CITY OF KABANKALAN | 6 | 1 | 7 | Repair of Classrooms | 1382874 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 117865 | Pangyasan PS | CITY OF KABANKALAN | 6 | 1 | 2 | Repair of Classrooms | 592725 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | NIR | Kabankalan City | 117850 | Pres. Osmena ES | CITY OF KABANKALAN | 6 | 1 | 12 | Repair of Classrooms | 3207618 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | NIR | La Carlota City | 117631 | Balabag ES | LA CARLOTA CITY | 4 | 1 | 15 | Repair of Classrooms | 3606012 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | NIR | La Carlota City | 117635 | Ferlou ES | LA CARLOTA CITY | 4 | 1 | 16 | Repair of Classrooms | 3822948 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | NIR | La Carlota City | 500192 | La Carlota City SPED Integrated School | LA CARLOTA CITY | 4 | 1 | 12 | Repair of Classrooms | 2089503 | 1 |  | COMPLETED | 1 | [10 empty] | Already Submit the RTA/waiting for SARO | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116896 | Bagacay ES | CALATRAVA | 1 | 1 | 5 | Repair of Classrooms | 1570015 | 1 | 1570014.19 | COMPLETED | 1 | 2021-01-07 |  | 6777947 | 20-09-009 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116901 | Calatrava I Central School | CALATRAVA | 1 | 1 | 15 | Repair of Classrooms | 3604009 | 1 | 3604008.76 | COMPLETED | 1 | 2021-01-07 |  | 6777956 | 20-09-010 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116920 | Ecogan ES | CALATRAVA | 1 | 1 | 6 | Repair of Classrooms | 2042200 | 1 | 2042200 | COMPLETED | 1 | 2021-04-30 |  | 6778114 | 20-09-021 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-10-22 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116909 | R. Magsaysay MES | CALATRAVA | 1 | 1 | 13 | Repair of Classrooms | 3465960 | 1 | 3465959.26 | COMPLETED | 1 | 2021-01-07 |  | 6777970 | 20-09-011 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117394 | Concepcion ES | CITY OF TALISAY | 3 | 1 | 8 | Repair of Classrooms | 1851001 | 1 | 1851000.14 | COMPLETED | 1 | 2021-01-07 |  | 6777983 | 20-09-012 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 302623 | Enrique B. Magalona NHS - San Isidro Ext. | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 7 | Repair of Classrooms | 1477000 | 1 | 1477000 | COMPLETED | 1 | 2021-01-07 |  | 6777998 | 20-09-013 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117276 | B.R. Dela Rama ES | MURCIA | 3 | 1 | 22 | Repair of Classrooms | 5208404 | 1 | 5208403.98 | COMPLETED | 1 | 2021-01-07 |  | 6778008 | 20-09-014 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117293 | Lopez Jaena ES | MURCIA | 3 | 1 | 16 | Repair of Classrooms | 4399449 | 1 | 4399448.83 | COMPLETED | 1 | 2021-02-06 |  | 6778119 | 20-09-022 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-23 | 2020-09-29 | SUNSHINE SAPPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | 17 | Repair of Classrooms | 3462730 | 1 | 3462729.72 | COMPLETED | 1 | 2021-01-07 |  | 6778028 | 20-09-016 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117316 | Pontevedra North ES | PONTEVEDRA | 4 | 1 | 30 | Repair of Classrooms | 9087058 | 1 | 9087057.12 | COMPLETED | 1 | 2021-01-07 |  | 6778018 | 20-09-015 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116867 | Binalbagan South ES | BINALBAGAN | 5 | 1 | 1 | Repair of Classroom | 983374 | 1 | 983373.92 | COMPLETED | 1 | 2021-01-07 |  | 6778124 | 19-12-025 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 116869 | Doña Concepcion Y. Yusay Memorial School | BINALBAGAN | 5 | 1 | 10 | Repair of Classrooms | 2154887 | 1 | 2154886.46 | COMPLETED | 1 | 2021-01-07 |  | 6778075 | 20-04-017 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117011 | Si-alay ES | CAUAYAN | 6 | 1 | 10 | Repair of Classrooms | 2355031 | 1 | 2355030.15 | COMPLETED | 1 | 2021-01-07 |  | 6778091 | 20-04-018 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6 | 1 | 8 | Repair of Classrooms | 2405400 | 1 | 2405400 | COMPLETED | 1 | 2021-01-07 |  | 6778097 | 20-09-019 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-10-21 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Negros Occidental | 117162 | Bocana ES | ILOG | 6 | 1 | 17 | Repair of Classrooms | 3537884 | 1 | 3537883.01 | COMPLETED | 1 | 2021-01-07 |  | 6778106 | 20-09-020 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-18 | 2020-09-24 | FOUR SG ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | NIR | Sagay City | 117729 | Campo Santiago ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2352066 | 1 | 2352065.09 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Sagay City | 117717 | Hautea ES | Sagay City | 2 | 1 | 5 | Repair of Classrooms | 2225599 | 1 | 2225598.13 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Sagay City | 302770 | Sewahon National High School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 2972911 | 1 | 2972910.93 | COMPLETED | 1 |  |  |  |  | 2019-11-21 | 2019-11-29 | 2019-12-12 |  |  | ROMBER CONSTRUCTION & GENERAL MERCHANDISE |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | San Carlos City | 117796 | Malindog ES | SAN CARLOS CITY | 1 | 1 | 10 | Repair of Classrooms | 3494847 | 1 | 3491000 | COMPLETED | 1 | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | NIR | San Carlos City | 117764 | Punod ES | SAN CARLOS CITY | 1 | 1 | 9 | Repair of Classrooms | 3663014 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | San Carlos City | 117755 | Rizal ES | SAN CARLOS CITY | 1 | 1 | 2 | Repair of Classrooms | 716540 | 1 | 715000 | COMPLETED | 1 | 2021-05-15 | 2021-05-15 | 7142036-2020BEFF | 7142036-2020BEFF | 2020-07-07 | 2020-08-06 | 2020-08-19 | 2020-10-30 | 2020-12-21 | RISM Builders & Construction Services, Inc. | 100% completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | NIR | Silay City | 500199 | Don Albino & Doña Dolores Jison IS | SILAY CITY | 3 | 1 | 13 | Repair of Classrooms | 3869000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | NIR | Sipalay City | 117360 | Maricalum ES | CITY OF SIPALAY | 6 | 1 | 6 | Repair of Classrooms | 2144197 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | Bais City | 120094 | Lowason ES | BAIS CITY | 2 | 1 | 7 | Repair of Classrooms | 2503300 | 1 |  | COMPLETED | 1 | [9 empty] | PAR |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Bais City | 120100 | Palaypay ES | BAIS CITY | 2 | 1 | 12 | Repair of Classrooms | 3944563 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | NIR | Bayawan City | 120116 | Maglinao Elementary School | BASAY | 3 | 1 | 13 | Repair of Classrooms | 5188394 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | NIR | Bayawan City | 120156 | Kalumboyan ES | CITY OF BAYAWAN (TULONG) | 3 | 1 | 27 | Repair of Classrooms | 9371995 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0
REPAIR 2020 | NIR | Bayawan City | 120137 | San Jose Elementary School | CITY OF BAYAWAN (TULONG) | 3 | 1 | 8 | Repair of Classrooms | 1787212 | 1 |  | COMPLETED | 1 |  |  |  |  | 2019-12-03 | 2019-12-11 | 2019-12-23 | 2020-01-15 | 2020-09-10 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Dumaguete City | 119945 | Cantil-e ES | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1181000 | 1 | 2729546.51 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY | with variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Dumaguete City | 119940 | West City Exceptional Child Learning Center | DUMAGUETE CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 1405617 | 1 | 1181000 | COMPLETED | 1 | 2021-04-28 |  |  |  | 2020-01-22 | 2020-01-29 | 2020-02-10 | 2020-02-26 | 2020-12-22 | RISM Builders and Construction Services, Inc. | with variation order | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120260 | Agulang PS | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 691810 | 1 | 990614 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120241 | Calabaclabacan ES | CITY OF GUIHULNGAN | 1 | 1 | 8 | Repair of Classrooms | 2729547 | 1 | 1100736.86 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120250 | Lip-o ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1400423 | 1 | 1131560 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120252 | Magkanaway PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1131560 | 1 | 1922984 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120278 | Nagsaha ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 990614 | 1 | 1574195.47 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120281 | Plagatasanon ES | CITY OF GUIHULNGAN | 1 | 1 | 5 | Repair of Classrooms | 1574196 | 1 |  | COMPLETED | 1 |  |  |  |  | Nov. 25, 2019 | Dec. 03, 2019 | Dec. 16, 2019 | Jan. 13, 2020 |  | FROY J BUILDERS AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120286 | Tominhao PS | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1100737 | 1 | 1400423 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | PAR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Guihulngan City | 120641 | Ulay Elementary School | VALLEHERMOSO | 1 | 1 | 7 | Repair of Classrooms | 1922984 | 1 | 691810 | COMPLETED | 1 |  |  |  |  | 2019-11-29 | 2019-12-06 | 2019-12-19 | 2020-03-13 | 2020-09-28 | SUNSHINE SAPHIRE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120043 | Iniban Elementary School | AYUNGON | 1 | 1 | 9 | Repair of Classrooms | 1921000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120206 | Linothangan Elementary School | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3292082 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120208 | Malaiba Elementary School | CANLAON CITY | 1 | 1 | 3 | Repair of Classrooms | 843690 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120211 | Masulog ES | CANLAON CITY | 1 | 1 | 20 | Repair of Classrooms | 8310000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120213 | Panubigan Elementary School | CANLAON CITY | 1 | 1 | 16 | Repair of Classrooms | 6951280 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120216 | Tabalogo ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 3435981 | 1 |  | COMPLETED | 1 |  |  | 2019 - 48 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | ALOJA BUILDERS AND REALTY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120384 | Campuyo Elementary School | MANJUYOD | 1 | 1 | 9 | Repair of Classrooms | 4400000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 303207 | Amlan National High School | AMLAN (AYUQUITAN) | 2 | 1 | 17 | Repair of Classrooms | 6183000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120025 | Aurelio Ibero MES (Jugno ES) | AMLAN (AYUQUITAN) | 2 | 1 | 7 | Repair of Classroom | 1941000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120364 | Lumbangan Elementary School | MABINAY | 2 | 1 | 26 | Repair of Classrooms | 6532000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120488 | Escaguit Elementary School | SIBULAN | 2 | 1 | 4 | Repair of Classrooms | 1443000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120445 | Bantolinao Elementary School | SIATON | 3 | 1 | 6 | Repair of Classrooms | 1720574 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120462 | Lico-Lico Elementary School | SIATON | 3 | 1 | 9 | Repair of Classrooms | 2693714 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120474 | Palayuhan ES | SIATON | 3 | 1 | 8 | Repair of Classrooms | 1836000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Negros Oriental | 120647 | Kaladias ES | ZAMBOANGUITA | 3 | 1 | 14 | Repair of Classrooms | 3411000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | NIR | Siquijor | 120670 | Cangomantong Elementary School | LAZI | 0 | 1 | 8 | Repair of Classrooms | 2908041 | 1 |  | COMPLETED | 1 |  |  | 2019 - 49 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | NIR | Siquijor | 120682 | Minalulan Elementary School | MARIA | 0 | 1 | 10 | Repair of Classrooms | 2207997 | 1 |  | COMPLETED | 1 |  |  | 2019 - 50 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | VVER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | NIR | Siquijor | 120709 | Tambisan Elementary School | SAN JUAN | 0 | 1 | 7 | Repair of Classrooms | 2317963 | 1 |  | COMPLETED | 1 |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | NIR | Siquijor | 120696 | Cang-atuyom Elementary School | SIQUIJOR (Capital) | 0 | 1 | 4 | Repair of Classrooms | 645206 | 1 |  | COMPLETED | 1 |  |  | 2019 - 51 |  | Nov. 21 to Dec. 9, 2019 | Nov. 27, 2019 | Dec. 9, 2019 | Dec. 16, 2019 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | NIR | Siquijor | 120704 | San Antonio Elementary School | SIQUIJOR (Capital) | 0 | 1 | 5 | Repair of Classrooms | 1388364 | 1 | 5613375.27 | COMPLETED | 1 |  |  |  | 2020-001-Infra |  |  | December 18, 2019 | December 26, 2019 | September 28, 2020 | ESP Design, Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 120546 | Canghatap Elementary School | CITY OF TANJAY | 2 | 1 | 5 | Repair of Classrooms | 2178500 | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 120555 | Lamwas Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 120561 | Ponglo Elementary School | CITY OF TANJAY | 2 | 1 | 3 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 234002 | Rosario V. Moras Memorial School | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms |  | 1 |  | COMPLETED | 1 | [9 empty] | VVER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 120411 | Caningay Elementary School | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1968302 | 1 |  | COMPLETED | 1 | [9 empty] | VVER |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | NIR | Tanjay City | 120428 | Tigbao Elementary School | PAMPLONA | 2 | 1 | 5 | Repair of Classrooms |  | 1 | 3803586.63 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | NIR | Bacolod City | 302699 | ABKASA National High School | Bacolod City | 0 | 1 | 8 | Repair of Classrooms | 3844978.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Bago City | 117514 | Bagroy ES | BAGO CITY | 4 | 1 | 5 | Repair of Classrooms | 2681518.72 | 1 |  | COMPLETED | 1 | 2022-09-30 | [10 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | NIR | Cadiz City | 311405 | Banquerohan NHS | Cadiz City | 2 | 1 | 14 | Repair of Classrooms | 6452598.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | NIR | Cadiz City | 117538 | San Andres ES | Cadiz City | 2 | 1 | 3 | Repair of Classrooms | 1307681.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | NIR | Cadiz City | 117540 | SPED Training Center | Cadiz City | 2 | 1 | 18 | Repair of Classrooms | 6854463.18 | 1 |  | reverted | 0.85 | 2023-01-31 | [9 empty] | Under suspension due to issue on building permit | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2021 | NIR | Escalante City | 117042 | Don Esteban dela Rama Elementary School | CITY OF ESCALANTE | 1 | 1 | 11 | Repair of Classrooms | 4511858.06 | 1 |  | COMPLETED | 1 | 2022-09-30 | [9 empty] | Punclisted items are not yet addressed by the contractor | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | NIR | Himamaylan City | 117072 | Cong. Eliseo P. Limsiaco Sr. MES | CITY OF HIMAMAYLAN | 5 | 1 | 10 | Repair of Classrooms | 3443803.28 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | NIR | Kabankalan City | 117835 | Camingawan ES | CITY OF KABANKALAN | 6 | 1 | 15 | Repair of Classrooms | 5784190.44 | 1 | 5769246.44 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | NIR | Kabankalan City | 117880 | Daan Banua ES | CITY OF KABANKALAN | 6 | 1 | 22 | Repair of Classrooms | 4194461.43 | 1 | 4181072.72 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2021 | NIR | Kabankalan City | 117847 | Oringao ES | CITY OF KABANKALAN | 6 | 1 | 26 | Repair of Classrooms | 8719945.91 | 1 | 8705000 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 26 | 0 | 0
REPAIR 2021 | NIR | Kabankalan City | 117853 | Tan-awan ES | CITY OF KABANKALAN | 6 | 1 | 18 | Repair of Classrooms | 6184935.25 | 1 | 6171000 | COMPLETED | 1 | [9 empty] | Rism Builers and Construction services Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2021 | NIR | La Carlota City | 117638 | Cubay ES | LA CARLOTA CITY | 4 | 1 | 11 | Repair of Classrooms | 5314284.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 302669 | Negros Occidental High Schol | CITY OF BACOLOD | 0 | 1 | 8 | Repair of Classrooms | 3427235.39 | 1 | 1984312.59 | COMPLETED | 1 | 2021-12-10 |  |  | 21-07-004 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 116932 | Pesons ES | CALATRAVA | 1 | 1 | 2 | Repair of Classrooms | 981349.73 | 1 | 980319.48 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-006 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 302682 | Sofronio Carmona Mem. NHS - Bagong Silang Annex | SALVADOR BENEDICTO | 1 | 1 | 2 | Repair of Classrooms | 1428391.93 | 1 | 1363109.35 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-006 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117415 | Stop Aguinaldo ES | TOBOSO | 1 | 1 | 8 | Repair of Classrooms | 3107175.09 | 1 | 2941988.44 | COMPLETED | 1 | 2021-12-10 |  |  | 21-07-005 | [5 empty] | VALKYRIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 302663 | Manapla NHS - Purisima Extension | MANAPLA | 2 | 1 | 6 | Repair of Classrooms | 1523296.18 | 1 | 1439878.35 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-007 | [5 empty] | VALKYRIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117020 | Batea PS | ENRIQUE B. MAGALONA (SARAVIA) | 3 | 1 | 4 | Repair of Classrooms | 2005139.74 | 1 | 1981661.1 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-008 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117345 | Nayon ES | SAN ENRIQUE | 4 | 1 | 9 | Repair of Classrooms | 3169104.53 | 1 | 3132417.47 | COMPLETED | 1 | 2021-11-22 |  |  | 21-008-01 | [5 empty] | SUNSHINE SAPPHIRE CONST. AND SUPPLY INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117186 | Bungahin ES | ISABELA | 5 | 1 | 7 | Repair of Classrooms | 2887809.11 | 1 | 2820315.97 | COMPLETED | 1 | 2021-11-22 |  |  | 21-08-002 | [5 empty] | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117190 | Don Beneito Lpez ES | ISABELA | 5 | 1 | 4 | Repair of Classrooms | 1578283.16 | 1 | 1553000 | COMPLETED | 1 | 2021-11-11 |  |  | 21-07-009 | [5 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117205 | Limalima Es | ISABELA | 5 | 1 | 7 | Repair of Classrooms | 2556323.37 | 1 | 2533323 | COMPLETED | 1 | 2021-11-11 |  |  | 21-07-010 | [5 empty] | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117241 | Talaptap ES | LA CASTELLANA | 5 | 1 | 10 | Repair of Classrooms | 3772314.67 | 1 | 3731000 | COMPLETED | 1 | 2021-11-11 |  |  | 21-07-011 | [5 empty] | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117262 | E. Basa ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 3 | Repair of Classrooms | 1505897.25 | 1 | 1481100.38 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-012 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 116944 | Calamunding ES | CANDONI | 6 | 1 | 3 | Repair of Classrooms | 1721546.58 | 1 | 1691000 | COMPLETED | 1 | 2021-11-11 |  |  | 21-07-013 | [5 empty] | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 116947 | Cantacson ES | CANDONI | 6 | 1 | 4 | Repair of Classrooms | 1915351.62 | 1 | 1749022.05 | COMPLETED | 1 | 2021-11-13 |  |  | 21-07-014 | [5 empty] | GOLDEN PACE CONSTRUCTIONS CORPORATION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | NIR | Negros Occidental | 117184 | Vista Alegre ES | ILOG | 6 | 1 | 3 | Repair of Classrooms | 1680615.54 | 1 | 1654750.3 | COMPLETED | 1 | 2021-11-10 |  |  | 21-07-015 | [5 empty] | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | NIR | Sagay City | 117703 | Plaridel Elementary School | SAGAY CITY | 2 | 1 | 6 | Repair of Classrooms | 3004680.22 | 1 | 1832165.88 | COMPLETED | 1 | November 16, 2021 |  | 07-2021 | 07-2021 | June 7, 2021 | June 15, 2021 | June 30, 2021 | July 21, 2021 | August 16, 2021 | SANS CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | San Carlos City | 117742 | Ansulag ES | SAN CARLOS CITY | 1 | 1 | 6 | Repair of Classrooms | 2783150.74 | 1 | 2748000 | COMPLETED | 1 | 2021-06-25 | 2021-06-21 | 7773810-2021beff-ANSULAG ES | 7773810-2021beff-ANSULAG ES | 2021-06-17 | 2021-06-16 | 2021-07-07 | 2021-07-29 | 2021-08-20 | Rism Builders & Construction Services Inc. | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | Silay City | 302778 | Brgy. Guimbala-on NHS | SILAY CITY | 3 | 1 | 6 | Repair of Classrooms | 2442021.84 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | Sipalay City | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | 5 | Repair of Classrooms | 2673447.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | NIR | Bais City | 120088 | Cambagahan ES | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 550447.95 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | NIR | Bais City | 323005 | Manuel L. Teves Memorial HS | BAIS CITY | 2 | 1 | 1 | Repair of Classroom | 505199.54 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | NIR | Bais City | 120101 | Panalaan ES | BAIS CITY | 2 | 1 | 4 | Repair of Classrooms | 2031532.51 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | NIR | Bayawan City | 120114 | Don Pablo Carmen Blanco Utzurrum Memorial Elementary School | BASAY | 3 | 1 | 8 | Repair of Classrooms | 4820489.9 | 1 | 3424000 | COMPLETED | 1 |  |  |  | 2021-BEFF-001 | 6/18/2021 | 6/28/2021 | 2021-07-12 | 7/16/2021 | 6/27/2021 | RISM BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Dumaguete City | 303166 | Camanjac National High School | Dumaguete City | 2 | 1 | 13 | Repair of Classrooms | 2999999.73 | 1 | 2979000 | COMPLETED | 1 | 2022-01-02 | [5 empty] | 2021-06-15 |  | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2021 | NIR | Guihulngan City | 120264 | Banwague ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 756256.04 | 1 | 622167.9 | COMPLETED | 1 | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | NIR | Guihulngan City | 120251 | Maculos ES | CITY OF GUIHULNGAN | 1 | 1 | 3 | Repair of Classrooms | 1773747.19 | 1 | 1230581.49 | COMPLETED | 1 | 2021-12-29 |  |  | ITB 2021-06 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | NIR | Guihulngan City | 120283 | Taloto ES | CITY OF GUIHULNGAN | 1 | 1 | 2 | Repair of Classrooms | 1081239.33 | 1 | 775994.89 | COMPLETED | 1 | 2021-11-29 |  |  | ITB 2021-05 | 2021-08-04 | 2021-08-12 | 2021-08-24 | 2021-09-07 | 2021-09-21 | Triple Jo Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120053 | So-ok Elementary School | AYUNGON | 1 | 1 | 8 | Repair of Classrooms | 3721317.42 | 1 | 3003000 | COMPLETED | 1 | 2021-12-04 | 2021-12-03 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120199 | Binalbagan Elementary School | CANLAON CITY | 1 | 1 | 10 | Repair of Classrooms | 4706070.84 | 1 | 3522000 | COMPLETED | 1 | 2021-12-04 | 2022-07-11 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120217 | Tigbahi ES | CANLAON CITY | 1 | 1 | 6 | Repair of Classrooms | 4246688.66 | 1 | 3177000 | COMPLETED | 1 | 2021-12-04 | 2022-07-11 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120219 | Villa Iowa ES | CANLAON CITY | 1 | 1 | 8 | Repair of Classrooms | 5165453.02 | 1 | 3874000 | COMPLETED | 1 | 2021-12-02 | 2022-03-08 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120374 | Pedro Gobuyan, Sr. MES (Mayaposi ES) | MABINAY | 2 | 1 | 6 | Repair of Classrooms | 1965466.89 | 1 | 1475000 | COMPLETED | 1 | 2021-12-02 | 2021-11-19 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-27 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 120437 | San Roque Primary School | SAN JOSE | 2 | 1 | 4 | Repair of Classrooms | 1966423.02 | 1 | 1624000 | COMPLETED | 1 | 2021-12-04 | 2021-11-26 |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | NIR | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | 20 | Repair of Classrooms | 8901004.3 | 1 | 6664000 | COMPLETED | 1 | 2022-03-04 |  |  |  | 2021-06-09 | 2021-06-14 | 2021-06-28 | 2021-07-15 | 2021-11-28 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | processing of fire safety inspection certificate | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2021 | NIR | Siquijor | 120675 | Kimba Elementary School | Lazi | 1 | 1 | 5 | Repair of Classrooms | 2999578.32 | 1 | 2458560.33 | COMPLETED | 1 | 2021-11-15 |  |  |  | 2021-05-25 | 2021-06-02 | 2021-06-23 | 2021-06-30 | 2021-07-16 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | NIR | Tanjay City | 234006 | Canggabi Elementary School | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 484821.83 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | NIR | Tanjay City | 234001 | George Pilas MS (Aseotes PS) | CITY OF TANJAY | 2 | 1 | 1 | Repair of Classroom | 338983.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | NIR | Tanjay City | 120542 | Pelagio Jabel MS (Bahian ES) | CITY OF TANJAY | 2 | 1 | 2 | Repair of Classrooms | 1086834.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | NIR | Tanjay City | 120426 | Simborio ES | PAMPLONA | 2 | 1 | 3 | Repair of Classrooms | 1185395.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | NIR | Negros Oriental | 120311 | Aniniaw ES | LA LIBERTAD | 1 | 1 | 5 | Repair of Classrooms & Toilet | 2511000 | 2 | 2490201.33 | COMPLETED | 1 | 2023-04-10 | 2023-03-28 | ITB no. 2022-06-061 | BEFF 202209008 | 2022-07-04 | 2022-07-12 | 2022-07-25 | 2022-07-28 | 2022-09-20 | Tribata Construction and Development | with approved time extension. | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | NIR | Negros Oriental | 120433 | Janayjanay Elementary School | SAN JOSE | 2 | 1 | 5 | Repair of Classrooms | 2801981.26 | 1 | 2207000 | COMPLETED | 1 | 2022-10-14 | 2022-12-06 | ITB no. 2022-02-007 | ITB no. 2022-02-007 | 2022-02-14 | 2023-02-23 | 2022-03-07 | 2022-03-24 | 2022-06-03 | RISM Builders & Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | NIR | Siquijor | 120660 | Libo Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | 3 | Repair of Classrooms | 1766789.71 | 1 | 1429945.54 | COMPLETED | 1 | 2022-09-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | NIR | Siquijor | 500232 | Cabulihan Integrated School | LARENA | 0 | 1 | 1 | Repair of Classroom | 636955.25 | 1 | 535080.38 | COMPLETED | 1 | 2022-08-17 | 2022-09-26 |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | NIR | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 3 | Repair of Classrooms | 1614561.19 | 1 | 1307112.06 | COMPLETED | 1 | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | NIR | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | 4 | Repair of Classrooms | 3064866.16 | 1 | 2513189.24 | COMPLETED | 1 | 2022-10-17 |  |  |  | 2022-02-08 | 2022-02-16 | 2022-02-28 | 2022-03-22 |  | E.D. Angas Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | Bacolod City | 302705 | Domingo Lacson NHS | BACOLOD CITY (Capital) | Lone | 1 | 63 | Repair of Classrooms | 16000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 63 | 0 | 0
REPAIR 2023 | NIR | Bago City | 117494 | Abuanan ES | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 2988398.2 | DPWH (Batch 1) | 2840490.97 | COMPLETED | 1 |  |  |  | 23GN0088 | [5 empty] | 3rd Dragon Builders Innovation | for punchlisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Bago City | 117499 | Ma. Rosario Araneta ES | BAGO CITY | 4th | 1 | 2 | Repair of Classrooms | 967373.67 | DEPED (Batch 1) |  | Reverted | 0 | [10 empty] | Reverted; Revised Program of Works due to increased in the amount of allocation. New allocation amount is 933,515.59 as reflected in the Sub-ARO | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0
REPAIR 2023 | NIR | Bago City | 302725 | Ramon Torres Taloc NHS | BAGO CITY | 4th | 1 | 5 | Repair of Classrooms | 3685984.43 | DPWH (Batch 1) | 3556969.35 | COMPLETED | 1 |  |  |  | 23GN0089 | [5 empty] | SBK Construction Supplies &Services, Inc. | Punchlisted; For rectification works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Cadiz City | 117531 | Cadiz East Elem. School II | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4033015.36 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | NIR | Cadiz City | 117546 | Cadiz East I ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 2641333.48 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | NIR | Cadiz City | 117577 | M.V. Gamboa ES | CADIZ CITY | 2nd | 1 | 9 | Repair of Classrooms | 4138015.36 | DPWH (Batch 1) |  | Ongoing | 0.53 | [11 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0
REPAIR 2023 | NIR | Himamaylan City | 117076 | Himamaylan CS | CITY OF HIMAMAYLAN | 5th | 1 | 32 | Repair of Classrooms | 20710702.02 | DPWH (Batch 1) |  | COMPLETED | 1 | 2024-03-12 | [8 empty] | RISM |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 32 | 0 | 0
REPAIR 2023 | NIR | Himamaylan City | 302649 | Himamaylan NHS | CITY OF HIMAMAYLAN | 5th | 1 | 40 | Repair of Classrooms | 18127395.24 | DPWH (Batch 1) | 16617280.35 | COMPLETED | 1 | 2024-03-12 |  |  | 23GL0110 | [5 empty] | YRJ ENGINEERING SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 40 | 0 | 0
REPAIR 2023 | NIR | Kabankalan City | 117885 | Locotan ES | CITY OF KABANKALAN | 6th | 1 | 16 | Repair of Classrooms | 8750000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2023 | NIR | Kabankalan City | 302790 | TAGUKON NATIONAL HIGH SCHOOL | CITY OF KABANKALAN | 6th | 1 | 9 | Repair of Classrooms | 7400000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | NIR | La Carlota City | 117646 | Haguimit ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 2929318.76 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | La Carlota City | 117636 | La Carlota South ES I | LA CARLOTA CITY | 4th | 1 | 5 | Repair of Classrooms | 2147772.31 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | La Carlota City | 117645 | Miguel S. Mondia ES | LA CARLOTA CITY | 4th | 1 | 1 | Repair of Classrooms | 627522.77 | DEPED (Batch 1) | 575,831.40/29,723.19 | COMPLETED | 1 | 2024-04-30 | 2024-03-06 | PI2023-42 | 2024-01-004 | 2023-12-14 | 2024-01-06 | 2024-01-10 | 2024-01-19 | 2024-01-30 | Woodtrade Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | NIR | La Carlota City | 117642 | Nagasi ES | LA CARLOTA CITY | 4th | 1 | 4 | Repair of Classrooms | 2428520.48 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | La Carlota City | 117649 | San Miguel ES I | LA CARLOTA CITY | 4th | 1 | 2 | Repair of Classrooms | 1210779.49 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6th | 1 | 3 | Repair of Classrooms | 2245000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Occidental | 117144 | C.L. Hodges ES | HINOBA-AN (ASIA) | 6th | 1 | 3 | Repair of Classrooms | 2310000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6th | 1 | 4 | Repair of Classrooms | 2850000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | San Carlos City | 302774 | Don Carlos Ledesma NHS | SAN CARLOS CITY | 1st | 1 | 23 | Repair of Classrooms | 52600000 | DPWH (Batch 1) | 49509727.06 | Ongoing | 0.95 | 2024-10-01 |  | 23GQ0071 |  | 2023-09-05 | 2023-09-12 | SEPT. 28, 2023 | 2023-10-27 |  | Kenneth Construction & General Merchandise | On-going | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0
REPAIR 2023 | NIR | San Carlos City | 117749 | Marago-os ES | SAN CARLOS CITY | 1st | 1 | 3 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7250984.52 | COMPLETED | 1 | 2024-04-06 |  | 23GQ0072 |  | 2023-09-05 | 2023-09-12 | 2023-09-28 | 2023-10-27 |  | Kenneth Construction & General Merchandise | Finished | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Silay City | 185001 | Dominador 'Oking' Jison Memorial Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 3811382.65 | DPWH (Batch 2) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Silay City | 302779 | Don Felix T. Lacson Memorial National High School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 2073578.52 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Silay City | 117813 | Don Homero H. Tanpinco ES | SILAY CITY | 3rd | 1 | 8 | Repair of Classrooms | 3131408.66 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | NIR | Silay City | 500201 | Violeta Integrated School | SILAY CITY | 3rd | 1 | 4 | Repair of Classrooms | 1120212.37 | DPWH (Batch 1) |  | COMPLETED | 1 | [10 empty] | For punclisting | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | Bais City | 120071 | Amalao Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 4280000 | DPWH (Batch 1) | 4086043.23 | COMPLETED | 1 | 2023-12-21 | 2024-03-03 |  | 23HK0157 | 2023-07-06 | 2023-07-14 | 2023-07-26 | 2023-09-20 | 2023-10-04 | NALE Construction | to schedule punchlist | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Bais City | 120073 | Cambanjao ES | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 4110000 | DPWH (Batch 1) | 3960050 | COMPLETED | 1 | 2023-12-16 |  |  | 23HK0138 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Bais City | 120076 | Dansulan ES | BAIS CITY | 2nd | 1 | 5 | Repair of Classrooms | 3710000 | DPWH (Batch 1) | 3566960.5 | COMPLETED | 1 | 2023-12-11 |  |  | 23HK0137 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Dumduma Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Bais City | 120104 | San Vicente Elementary School | BAIS CITY | 2nd | 1 | 3 | Repair of Classrooms | 3340000 | DPWH (Batch 1) | - | COMPLETED | 1 |  | 2024-03-12 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Bayawan City | 120146 | Canabuan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 4 | Repair of Classrooms | 665000 | DEPED (Batch 1) | 641500 | COMPLETED | 1 | [6 empty] | 9/14/2023 | 2023-10-05 | 2023-10-06 | HIT Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | Bayawan City | 120128 | Dawis Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 2035000 | DPWH (Batch 1) | 1959000 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0107 | 23HL0107 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | Tribata Construction and Development |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Bayawan City | 120165 | Tayawan Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 3 | Repair of Classrooms | 1745000 | DPWH (Batch 1) | 1681912.41 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0108 | 23HL0108 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | RR Gadingan Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Bayawan City | 120141 | Villareal Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 5 | Repair of Classrooms | 3945000 | DPWH (Batch 1) | 3796987.33 | COMPLETED | 1 | 2023-12-31 | 2024-03-15 | 23HL0106 | 23HL0106 | 2023-08-24 | 2023-09-07 | 2023-09-19 | 2023-09-26 | 2023-12-10 | NRS Builders and Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120263 | BALOGO ELEMENTARY SCHOOL | CITY OF GUIHULNGAN | 1st | 1 | 1 | Repair of Classrooms | 2800000 | DPWH (Batch 1) | 2800000 | COMPLETED | 1 | 2023-12-29 | 2023-12-29 | P00775305NP | 23HJ0136 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120235 | Binobohan ES | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | Ongoing | 0.6 | 2024-01-06 |  | P00775303NP | 23HJ0117 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | KAWAII BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120244 | Don Pelagio Villegas Memorial E/S | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4600000 | COMPLETED | 1 | 2023-12-22 | 2023-12-22 | P00775304NP | 23HJ0107 | 2023-08-17 | 2023-08-24 | 2023-09-05 | 2023-09-13 | 2023-09-25 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120267 | Guihulngan South CS | CITY OF GUIHULNGAN | 1st | 1 | 3 | Repair of Classrooms | 4200000 | DPWH (Batch 1) | 4200000 | COMPLETED | 1 | 2024-01-06 | 2024-01-06 | P00775306NP | 23HJ0120 | 2023-08-22 | 2023-08-29 | 2023-09-11 | 2023-09-19 | 2023-09-28 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120272 | Linantuyan ES | CITY OF GUIHULNGAN | 1st | 1 | 2 | Repair of Classrooms | 3900000 | DPWH (Batch 1) | 3900000 | COMPLETED | 1 | 2023-12-29 | 2023-12-29 | P00775307NP | 23HJ0135 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | MAI CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 324802 | P. Zamora National High School | CITY OF GUIHULNGAN | 1st | 1 | 4 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5400000 | COMPLETED | 1 | 2024-01-18 | 2024-01-18 | P00775308NP | 23HJ0125 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | Guihulngan City | 120638 | Tabon Elementary School | VALLEHERMOSO | 1st | 1 | 3 | Repair of Classrooms | 4400000 | DPWH (Batch 1) | 4400000 | COMPLETED | 1 | 2024-04-15 | 2024-01-08 | P00775309NP | 23HJ0127 | 2023-08-24 | 2023-08-31 | 2023-09-13 | 2023-09-26 | 2023-10-02 | K.M. GOLONG CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120039 | Carol-an Elementary School | AYUNGON | 1st | 1 | 7 | Repair of Classrooms | 6900000 | DPWH (Batch 1) | 6608793.79 | COMPLETED | 1 | 02/20/2024 |  | P00775322NP | 23HJ0119 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120040 | Duli-Duli Elementary School | AYUNGON | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4385649.39 | COMPLETED | 1 | 12/22/23 |  | P00775323NP | 23HJ0108 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 6100000 | DPWH (Batch 1) | 5835766.89 | COMPLETED | 1 | 2024-10-02 |  | P00775326NP | 23HJ0122 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120057 | Tampocon I Elementary School | AYUNGON | 1st | 1 | 6 | Repair of Classrooms | 5200000 | DPWH (Batch 1) | 4968985.83 | COMPLETED | 1 | 2024-06-01 |  | P00775324NP | 23HJ0134 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120058 | Tibyawan Elementary School | AYUNGON | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5166301.97 | COMPLETED | 1 | 2024-08-01 |  | P00775325NP | 23HJ0129 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120170 | Batangan Elementary School | BINDOY (PAYABON) | 1st | 1 | 8 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7285000 | COMPLETED | 1 | 3/17/24 |  | P00775327NP | 23HJ0131 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1st | 1 | 12 | Repair of Classrooms | 8400000 | DPWH (Batch 1) | 8040003.5 | COMPLETED | 1 | 3/16/24 |  | P00775329NP | 23HJ0106 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/15/23 | 9/25/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 189519 | Naula-an Elementary School | BINDOY (PAYABON) | 1st | 1 | 2 | Repair of Classrooms | 5500000 | DPWH (Batch 1) | 5248804.6 | COMPLETED | 1 | 12/22/23 |  | P00775328NP | 23HJ0110 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120291 | Bangcal Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164904.61 | COMPLETED | 1 | 2024-06-01 |  | P00775330NP | 23HJ0115 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120293 | Buto Primary School | JIMALALUD | 1st | 1 | 2 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5191029.12 | COMPLETED | 1 | 2024-01-02 |  | P00775331NP | 23HJ0105 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120297 | Irene Elementary School | JIMALALUD | 1st | 1 | 1 | Repair of Classrooms | 2270000 | DPWH (Batch 1) | 2180230.39 | Ongoing | 0.99 | 2024-01-02 |  | P00775329NP | 23HJ0109 | 9/14/2023 | 9/21/23 | 2023-03-10 | 10/18/23 | 2023-03-11 | Kawaii Builders and Supplies |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120304 | Owacan ES | JIMALALUD | 1st | 1 | 6 | Repair of Classrooms | 4900000 | DPWH (Batch 1) | 4708620.97 | COMPLETED | 1 | 2024-10-02 |  | P00775333NP | 23HJ0124 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120308 | Tamao Elementary School | JIMALALUD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5205977.97 | COMPLETED | 1 | 2024-08-01 |  | P00775334NP | 23HJ0128 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Fakujo Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120314 | Biga-a ES | LA LIBERTAD | 1st | 1 | 3 | Repair of Classrooms | 2900000 | DPWH (Batch 1) | 2779994.93 | COMPLETED | 1 | 2024-06-01 |  | P00775335NP | 23HJ0116 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120315 | Busilac ES | LA LIBERTAD | 1st | 1 | 6 | Repair of Classrooms | 6500000 | DPWH (Batch 1) | 6202500 | COMPLETED | 1 | 3/17/24 |  | P00775336NP | 23HJ0118 | 9/14/23 | 9/21/23 | 2023-03-10 | 10/18/2023 | 2023-03-11 | H.I.T. Contractors |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120326 | Mapalasan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 3370000 | DPWH (Batch 1) | 3219891.04 | COMPLETED | 1 | 12/22/23 |  | P00775337NP | 23HJ0111 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120328 | Nasunggan ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 4600000 | DPWH (Batch 1) | 4399882.18 | Ongoing | 0.98 | 12/22/23 |  | P00775338NP | 23HJ0112 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/13/23 | 9/25/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120330 | Pangca ES | LA LIBERTAD | 1st | 1 | 2 | Repair of Classrooms | 7000000 | DPWH (Batch 1) | 6724010.14 | COMPLETED | 1 | 12/29/23 |  | P00775339NP | 23HJ0126 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | Higel Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120380 | Bagtic ES | MANJUYOD | 1st | 1 | 6 | Repair of Classrooms | 7600000 | DPWH (Batch 1) | 7305783.65 | COMPLETED | 1 | 2024-10-02 |  | P00775340NP | 23HJ0113 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120391 | LOCAY E/S | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 4700000 | DPWH (Batch 1) | 4510326.42 | COMPLETED | 1 | 2024-06-01 |  | P00775341NP | 23HJ0121 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Kouken Construction | on going rectification of punchlist items | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120397 | Palay ES | MANJUYOD | 1st | 1 | 2 | Repair of Classrooms | 5560000 | DPWH (Batch 1) | 5306555.02 | COMPLETED | 1 | 12/27/23 |  | P00775342NP | 23HJ0104 | 8/17/23 | 8/24/23 | 2023-05-09 | 9/19/23 | 9/28/23 | E.F.V. Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120399 | Sagrada ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5168401.97 | COMPLETED | 1 | 2024-08-01 |  | P00775343NP | 23HJ0132 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120402 | San Isidro ES | MANJUYOD | 1st | 1 | 5 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6416000 | COMPLETED | 1 | 2024-02-01 |  | P00775344NP | 23HJ0133 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | MAI Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120405 | Tubod ES | MANJUYOD | 1st | 1 | 3 | Repair of Classrooms | 5400000 | DPWH (Batch 1) | 5164201.97 | COMPLETED | 1 | 2024-08-01 |  | P00775345NP | 23HJ0130 | 8/24/23 | 8/31/23 | 09/13/2023 | 9/26/23 | 2023-02-10 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120579 | Banga Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 8000000 | DPWH (Batch 1) | 7670000 | COMPLETED | 1 | 02/20/2024 |  | P00775346NP | 23HJ0114 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | Gram Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120591 | Matuog Elementary School | TAYASAN | 1st | 1 | 7 | Repair of Classrooms | 6700000 | DPWH (Batch 1) | 6414976.03 | COMPLETED | 1 | 02/20/2024 |  | P00775347NP | 23HJ0123 | 8/22/23 | 8/29/23 | 2023-11-09 | 9/19/23 | 9/28/23 | EJJ Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120027 | Panusuan Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 2 | Repair of Classrooms | 2550000 | DPWH (Batch 2) | 0 | COMPLETED | 1 | 2024-05-10 |  |  |  | September 26, 2023 | October 04, 2023 | October 18, 2023 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 303209 | Silab Community High School Annex | AMLAN (AYUQUITAN) | 2nd | 1 | 8 | Repair of Classrooms | 3660000 | DPWH (Batch 1) | 3513835 | COMPLETED | 1 | 2023-12-10 |  |  | 23KH0133 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120029 | Tandayag Elementary School | AMLAN (AYUQUITAN) | 2nd | 1 | 7 | Repair of Classrooms | 8500000 | DPWH (Batch 2) | 0 | COMPLETED | 1 | 2024-06-08 |  |  |  | September 26, 2023 | October 04, 2023 | October 18, 2023 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 189530 | Alagasihan Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2140000 | DPWH (Batch 1) | 2059300 | COMPLETED | 1 | 2023-11-15 |  |  | 23KH0153 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120338 | Arebasore Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3360000 | DPWH (Batch 1) | 3236735.97 | COMPLETED | 1 | 2023-12-11 |  |  | 23KH0154 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 15, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120340 | Baliw Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3730000 | DPWH (Batch 1) | 3595000 | COMPLETED | 1 | 2023-12-14 |  |  | 23KH0144 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120344 | Basakan Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2320000 | DPWH (Batch 1) | 2216406.05 | Ongoing | 0.99 | 2023-11-17 |  |  | 23KH0149 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 312924 | Campanun-an Senior High School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2340000 | DPWH (Batch 1) | 2235488.03 | Ongoing | 0.98 | 2023-11-17 |  |  | 23KH0150 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120350 | Campo-aling Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2670000 | DPWH (Batch 1) | 2570218 | COMPLETED | 1 | 2023-12-03 |  |  | 23KH0151 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 05, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120352 | Cansal-ing Elementary School | MABINAY | 2nd | 1 | 2 | Repair of Classrooms | 2220000 | DPWH (Batch 1) | 2123745.83 | Ongoing | 0.99 | 2023-11-16 |  |  | 23KH0152 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120358 | Don Cristito C. Tirambulo MES | MABINAY | 2nd | 1 | 6 | Repair of Classrooms | 4830000 | DPWH (Batch 1) | 4650095 | COMPLETED | 1 | 2023-12-28 |  |  | 23KH0141 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120360 | Himocdungon Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 3940000 | DPWH (Batch 1) | 3793255 | Ongoing | 0.99 | 2023-12-17 |  |  | 23KH0156 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 189510 | Lower Capanun-an Elementary School | MABINAY | 2nd | 1 | 4 | Repair of Classrooms | 4530000 | DPWH (Batch 1) | 4361349 | COMPLETED | 1 | 2023-12-24 | 2025-02-10 |  | 23KH0143 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 19, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 2710000 | DPWH (Batch 1) | 2587158.27 | Ongoing | 0.99 | 2023-12-02 |  |  | 23KH0147 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120376 | Tadlong Elementary School | MABINAY | 2nd | 1 | 5 | Repair of Classrooms | 3050000 | DPWH (Batch 1) | 2928830 | COMPLETED | 1 | 2023-12-06 |  |  | 23KH0155 | July 06, 2023 | July 14, 2023 | July 26, 2023 | September 21, 2023 | October 04, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120378 | Tara Elementary School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3620000 | DPWH (Batch 1) | 3453184 | COMPLETED | 1 | 2023-12-13 | 2024-06-24 |  | 23KH0148 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 14, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2nd | 1 | 3 | Repair of Classrooms | 3410000 | DPWH (Batch 1) | 3285000 | COMPLETED | 1 | 2023-12-11 |  |  | 23KH0146 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120379 | Tingtingon ES | MABINAY | 2nd | 1 | 1 | Repair of Classrooms | 1830000 | DPWH (Batch 1) | 1747241.23 | Ongoing | 0.99 | 2023-11-11 |  |  | 23KH0142 | July 05, 2023 | July 13, 2023 | July 25, 2023 | September 20, 2023 | October 03, 2023 |  | ongoing rectification of punchlisted items | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120439 | Sra. Ascion Elementary School | SAN JOSE | 2nd | 1 | 9 | Repair of Classrooms | 8120000 | DPWH (Batch 1) | 7831080 | COMPLETED | 1 | 2024-02-21 |  |  | 23KH0132 | July 04, 2023 | July 12, 2023 | July 24, 2023 | September 19, 2023 | September 28, 2023 | Ashleyka Construction & Supplies |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120504 | Buenavista Elementary School | SANTA CATALINA | 3rd | 1 | 7 | Repair of Classrooms | 5920000 | DPWH (Batch 1) | 5706383.04 | COMPLETED | 1 | 2023-10-04 |  |  | 23HL0089 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120508 | Danao Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1550000 | DPWH (Batch 1) | 1493258.11 | COMPLETED | 1 | 2023-10-05 |  |  | 23HL0090 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120516 | Omol Elementary School | SANTA CATALINA | 3rd | 1 | 2 | Repair of Classrooms | 1780000 | DPWH (Batch 1) | 1715774.88 | COMPLETED | 1 | 2023-10-05 |  |  | 23HL0091 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120471 | Nawacat Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2310000 | DPWH (Batch 1) | 2223687.34 | COMPLETED | 1 | 2023-10-04 |  |  | 23HL0092 | June 23, 2023 | June 30, 2023 | August 30, 2023 | September 7, 2023 | September 22, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 189507 | Ulayan Elementary School | SIATON | 3rd | 1 | 3 | Repair of Classrooms | 2145000 | DPWH (Batch 1) | 2067761.72 | COMPLETED | 1 | 2023-10-15 |  |  | 23HL0103 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | NRS BUILDERS & SUPPLIES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Negros Oriental | 120612 | Dobdob ES | VALENCIA (LUZURRIAGA) | 3rd | 1 | 2 | Repair of Classrooms | 1480000 | DPWH (Batch 1) | 1425205.4 | COMPLETED | 1 | 2023-10-17 |  |  | 23HL0104 | August 29, 2023 | September 7, 2023 | September 19, 2023 | September 26, 2023 | Octoberber 12, 2023 | ALEXANDRIA CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Siquijor | 500232 | Cabulihan IS | LARENA | Lone | 1 | 6 | Repair of Classrooms | 3725844.65 | DPWH (Batch 1) | 3582195.42 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0126 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | VNCO Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | 6 | Repair of Classrooms | 3929375.04 | DPWH (Batch 1) | 3776406.34 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0128 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Tesar Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Siquijor | 120697 | Cansayang ES | SAN JUAN | Lone | 1 | 6 | Repair of Classrooms | 3877378.6 | DPWH (Batch 1) | 3726306.32 | COMPLETED | 1 | January 13, 2024 |  |  | 23HM0127 | September 4, 2023 | September 13, 2023 | September 26, 2023 | October 2, 2023 | October 11, 2023 | Quicksilver Construction Services |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Tanjay City | 120549 | Don Placido Mapa Memorial School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 3270000 | DPWH (Batch 1) | 3117045.62 | COMPLETED | 1 | 2023-12-08 |  | P00775389NP-CWS | 23HK0139 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | NIR | Tanjay City | 120553 | Fabiana G. Banogon MES (Camansi ES) | CITY OF TANJAY | 2nd | 1 | 5 | Repair of Classrooms | 3880000 | DPWH (Batch 1) | 3707378.74 | COMPLETED | 1 | 2023-12-15 |  | P00775390NP-CWS | 23HK0140 | 2023-07-01 | 2023-07-09 | 2023-07-21 | 2023-09-20 | 2023-10-03 | NALE Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | NIR | Tanjay City | 120408 | Balayong Elem School | PAMPLONA | 2nd | 1 | 6 | Repair of Classrooms | 6480000 | DPWH (Batch 1) | 6248144.77 | COMPLETED | 1 | 2024-01-25 | 2024-01-25 |  | 23HK0134 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | Ashleyka Const. and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | NIR | Tanjay City | 120425 | San Isidro Elementary School | PAMPLONA | 2nd | 1 | 2 | Repair of Classrooms | 3170000 | DPWH (Batch 1) | 3055741.71 | COMPLETED | 1 | 2023-12-08 | 2024-01-03 |  | 23HK0136 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-05 | Bigfoot Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | NIR | Tanjay City | 120427 | Sta. Agueda ES | PAMPLONA | 2nd | 1 | 9 | Repair of Classrooms | 8870000 | DPWH (Batch 1) | 8549504 | COMPLETED | 1 | 2024-03-03 | 2024-03-03 |  | 23HK0135 | 2023-06-30 | 2023-07-08 | 2023-07-20 | 2023-09-20 | 2023-10-02 | PER Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | NIR | Bacolod City | 117458 | Fernando F. Gonzaga Elementary School | BACOLOD CITY (Capital) | Lone | 1 | 6 | Repair of Classrooms | 3031152.68 | 1 | 2950000 | COMPLETED | 1 | 23/04/2025 |  | REPAIR 2024 -R06- BACOLOD CITY - 001 | R6BCD10112024-P159 | 2024-10-15 | 2024-10-22 | 2024-11-04 | 17/1/2025 | 17/1/2025 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | Ongoing implementation | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Cadiz City | 117538 | San Andres ES | CADIZ CITY | 2nd | 1 | 6 | Repair of Classrooms | 4292668.79 | 1 | 4149742.1 | COMPLETED | 1 |  |  |  |  | 2024-08-01 | 2024-08-12 | 2024-08-27 | 2024-08-28 |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Escalante City | 302625 | Escalante National High School | CITY OF ESCALANTE | 1st | 1 | 4 | Repair of Classrooms | 2873738.94 | 1 | 2100000 | COMPLETED | 1 | 2024-02-02 |  | Project 03-2024 | Project 03, 2024 | 2024-07-23 | Augusut 1, 2024 | 2024-08-13 | 2024-09-11 | 2024-10-02 | Valkyrie Construction | Completed with approved VO in the amount of Php 200,160.90 and revised project completion is March 21, 2025 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | NIR | Himamaylan City | 117092 | Cabanbanan ES | CITY OF HIMAMAYLAN | 5th | 1 | 5 | Repair of Classrooms | 4118434.58 | 1 | 2949000 | COMPLETED | 1 | 2025-03-09 | 2025-01-16 | IB-sdhc-062024-002 | IB-sdhc-062024-002 | 2024-06-26 | 2024-07-05 | 2024-07-17 | Sept. 3, 2024 | 2024-09-27 | RISM BUILDERS AND CONSTRUCTION SERVICES | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | NIR | Kabankalan City | 117829 | Badiangay Elementary School | CITY OF KABANKALAN | 6th | 1 | 6 | Repair of Classrooms | 4273340.4 | 1 | 4207191 | not yet started | 0 |  |  | 2024-SB-03-PB003 |  | 2024-09-20 | 2024-09-26 | 2024-10-09 | 2024-10-15 |  | RISM BUILDERS AND CONSTRUCTION SERVICES INC. | For contract perfection | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | NIR | La Carlota City | 117648 | La Granja ES | LA CARLOTA CITY | 4th | 1 | 6 | Repair of Classrooms | 4846699.89 | 1 | 3205383.35 | COMPLETED | 1 | 2025-12-30 | 2024-01-30 | 2024-15 |  | 2024-07-07 | 2024-07-14 | 2024-07-23 | 2024-08-16 | 2024-08-23 | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES | 100% Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Negros Occidental | 117283 | Murcia East ES | MURCIA | 3rd | 1 | 2 | Repair of Classrooms | 1406364.12 | 1 | 708927.75 | Not Yet Started | 0 |  |  | 09-42-24 |  | 2024-09-06 | 2024-09-16 | 2024-09-30 |  |  | KEANNE CONSTRUCTION SERVICES | For Award | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | NIR | Negros Occidental | 117429 | Valladolid ES | VALLADOLID | 4th | 1 | 6 | Repair of Classrooms | 3562789.12 | 1 |  | Not Yet Started | 0 | [6 empty] | 2024-12-02 |  |  |  | For Procurement | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | NIR | Sagay City | 500036 | Colonia Divina Integrated School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1968909.78 | 1 | 1580000 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | CPB-INFRA-01-2024 | CPB-INFRA-01-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | KEANNE CONSTRUCTION SERVICES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | NIR | Sagay City | 117733 | Lopez Jaena Elementary School | SAGAY CITY | 2nd | 1 | 3 | Repair of Classrooms | 1687636.95 | 1 | 1355000 | COMPLETED | 1 | 2025-01-31 | 2025-01-20 | CPB-INFRA-02-2024 | CPB-INFRA-02-2024 | 2024-06-29 | 2024-07-05 | 2024-07-22 | 2024-08-02 | 2024-09-26 | VALKYRIE CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | NIR | San Carlos City | 117745 | Don Juan Ledesma ES | SAN CARLOS CITY | 1st | 1 | 2 | Repair of Classrooms | 919209.43 | 1 | 912811.81 | COMPLETED | 1 | 2024-12-30 | 2024-10-24 |  | PR# 2024-06-0044 |  |  | 2024-06-28 |  | 2024-09-28 | TMTC Construction & Supply | for approval of resolution to award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | NIR | Silay City | 117812 | Camantero Elementary School | SILAY CITY | 3rd | 1 | 6 | Repair of Classrooms | 4245236.51 | 1 | 4196891.26 | Not Yet Started | 0 |  |  |  |  | 2024-06-29 | 2024-07-08 | 2024-07-22 | 2024-08-21 |  | PAR Builders Electrical and Construction Supply Corp. | Perfection of Contract | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | NIR | Sipalay City | 117372 | Canturay ES | CITY OF SIPALAY | 6th | 1 | 12 | Repair of Classrooms | 4380647.68 | 1 |  | Not Yet Started | 0 | [11 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0
REPAIR 2024 | NIR | Victorias City | 117444 | Salvacion ES | CITY OF VICTORIAS | 3rd | 1 | 5 | Repair of Classrooms | 4195227.21 | 1 | 2686903.84 | COMPLETED | 1 | 2025-03-15 |  | SDOVC-INFRA2024-002 | SDOVC-INFRA2024-002 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | NIR | Bais City | 303212 | Bais City National High School | BAIS CITY | 2nd | 1 | 6 | Repair of Classrooms | 1919274.94 | 1 | 1880000 | COMPLETED | 1 | 2025-02-15 | 2025-01-07 | BCD-2024-075 | [6 empty] | RISM | complete | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Bais City | 323013 | Tangculogan High School | BAIS CITY | 2nd | 1 | 2 | Repair of Classrooms | 1442191.82 | 1 | 1118578.74 | COMPLETED | 1 | 2025-02-15 | 2025-01-09 | BCD-2024-075 | BCD-2024-075 | [5 empty] | Triple Jo const. | complete | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | NIR | Bayawan City | 120138 | Senator Lorenzo G. Teves Memorial Elementary School | CITY OF BAYAWAN (TULONG) | 3rd | 1 | 8 | Repair of Classrooms | 4498259.02 | 1 | 4438000 | COMPLETED | 1 | 2025-01-05 |  | 2024-BEFF-002 | 2024-BEFF-002 | 2024-07-27 | 2024-07-03 | 2024-07-15 | 2024-07-30 | 2024-09-30 | RISM Buidlers and Construction Services inc. | On-going | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | NIR | Canlaon City | 120215 | Pula ES | CANLAON CITY | 1st | 1 | 5 | Repair of Classrooms | 4140248.27 | 1 | 4098845.79 | COMPLETED | 1 | 2025-02-15 |  | ITB2024-003 | 2024-003 | 2024-06-26 | 2024-07-03 | 2024-07-16 | 2024-07-25 | 2024-09-11 | R.R. Gadingan Construction | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2024 | NIR | Dumaguete City | 119932 | Amador Dagudag MES | DUMAGUETE CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 953206.76 | 1 | 676154.66 | COMPLETED | 1 | 2025-04-05 | 2025-03-31 | 2024-005 | 2024-005 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | Millenial Mammoth Development Corporation | COMPLETED | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | NIR | Dumaguete City | 119944 | Calindagan ES | DUMAGUETE CITY (Capital) | 2nd | 1 | 2 | Repair of Classrooms | 381282.71 | 1 | 273578.95 | COMPLETED | 1 | 2025-05-20 |  | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | NIR | Dumaguete City | 119946 | City Central Elementary School | DUMAGUETE CITY (Capital) | 2nd | 1 | 6 | Repair of Classrooms | 3240902.98 | 1 | 2325421.05 | COMPLETED | 1 | 2025-05-20 |  | 2024-004 | 2024-004 | 2024-11-21 | 2024-12-02 | 2024-12-18 | 2025-01-02 | 2025-02-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | ongoing | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Guihulngan City | 120248 | Lag-asan ES | CITY OF GUIHULNGAN | 1st | 1 | 6 | Repair of Classrooms | 5126087.05 | 1 | 4389914.25 | COMPLETED | 1 | 2025-04-21 |  | ITB 2024-013 | ITB 2024-013 | 2024-10-16 | 2024-10-24 | November 7, 22024 | 2024-11-25 | 2024-11-28 | G.PO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Negros Oriental | 120189 | Pagsalayon ES | BINDOY (PAYABON) | 1st | 1 | 6 | Repair of Classrooms | 6454488.69 | 1 | 6329000 | COMPLETED | 1 | 2025-04-04 | 2025-03-26 | ITB 2024-07-116 | BEFF202409031 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | NIR | Negros Oriental | 120432 | Cancawas Primary School | SAN JOSE | 2nd | 1 | 3 | Repair of Classrooms | 2304321.13 | 1 | 1932000 | COMPLETED | 1 | 2025-01-27 | 2025-01-16 | ITB 2024-07-117 | BEFF202409032 | 2024-07-09 | 2024-07-17 | 2024-07-30 | 2024-08-12 | 2024-10-07 | RISM Builders and Construction Services, Inc. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | NIR | Siquijor | 303305 | Catulayan National High School | SAN JUAN | Lone | 1 | 9 | Repair of Classrooms | 5830766.12 | 1 | 5756858.55 | COMPLETED | 1 | 2025-06-30 |  | 10889961 | 2024-032 | 2024-05-25 | 2024-05-30 | 2024-06-13 | 2024-06-19 | 2024-10-07 | Nale Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2024 | NIR | Tanjay City | 303285 | Bahi-an High School | CITY OF TANJAY | 2nd | 1 | 1 | Repair of Classrooms | 773357.01 | 1 | 3204000 | COMPLETED | 1 | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2024 | NIR | Tanjay City | 120558 | Mato-Bato Elementary School | CITY OF TANJAY | 2nd | 1 | 3 | Repair of Classrooms | 2468342.68 | 1 | 3204000 | COMPLETED | 1 | [5 empty] | 2024-09-06 | 2024-09-18 |  |  | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | SARO received | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%