## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | SHS (2014) | Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10977342.5917 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Alaminos City | 300157 | Alos National High School | CITY OF ALAMINOS | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14947518.84 |  |  | COMPLETED | 1 | 2016-04-29 |  | 010414S00207 | 15AG0112 | 2015-08-07 | 2015-08-10 | 2015-08-24 | 2015-08-27 | 2015-09-02 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Alaminos City | 300190 | Cayucay NHS | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00208 | A5AG0092(1) | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Alaminos City | 300240 | Polo NHS, Alaminos | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00209 | 15AG0091(1) | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Alaminos City | 300253 | San Vicente NHS | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00210 | 15AG0080 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-08-03 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Alaminos City | 300260 | Telbang NHS | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 010414S00211 | 15AG0076 | 2015-06-24 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | JONIK TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Batac City | 150010 | Baoa East ES | CITY OF BATAC | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3165174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Batac City | 300005 | Batac NHS | CITY OF BATAC | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8764965.051 |  |  | COMPLETED | 1 | 2016-03-03 |  | 010114S00033 | 15AB0081 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-29 |  | MSF CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Batac City | 320803 | Batac NHS (Payao Campus) | CITY OF BATAC | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6819337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00024 | 15AB0065 | 2015-08-13 | 2015-08-17 | 2015-08-28 | 2015-09-11 | 2015-10-02 | MSF CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Batac City | 300012 | Crispina Marcos Valdez NHS | CITY OF BATAC | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6694337.6381 |  |  | COMPLETED | 1 | 2016-01-28 |  | 010114S00064 | 15AB0067 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-01 | KRB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6339337.6381 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Candon City | 322601 | Candon City Information Technology NHS | CITY OF CANDON | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15122518.84 |  |  | Terminated | 0.1 | 2016-07-14 |  | 010214S00055 | 15AD0139 | 2015-09-09 | 2015-09-21 | 2015-09-25 | 2015-10-27 | 2015-11-19 | VIGAN FORTUNE CONSTRUCTION | The IO and the contractor entered into a mutual termination of contract.
NC 2014 | SHS (2014) | Region I | Candon City | 300044 | Candon National High School | CITY OF CANDON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8439965.051 |  |  | COMPLETED | 1 | 2016-03-24 |  | 010214S00050 | 15AD0116 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-11 | 2015-09-16 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8489965.051 |  |  | COMPLETED | 1 | 2016-03-23 |  | 010214S00051 | 15AD0118 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-11 | 2015-09-16 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Candon City | 300083 | Sto. Tomas National High School | CITY OF CANDON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 | 2016-03-24 |  | 010214S00052 | 15AD0121 | 2015-08-17 | 2015-08-19 | 2015-09-02 | 2015-09-14 | 2015-09-17 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-05-21 |  | 010414S00212 | 15AH0211 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-11-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Dagupan City | 300369 | Carael National HS | DAGUPAN CITY | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22182343.62 |  |  | COMPLETED | 1 | 2016-04-28 |  | 010414S00213 | 15AH0234 | 2015-08-23 | 2015-08-27 | 2015-09-08 | 2015-09-21 | 2015-10-02 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Dagupan City | 500053 | East Central IS | DAGUPAN CITY | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010414S00214 | 15AH0210 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-10-26 | BET CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 | 1 | 6 | 2STY4CL & 2STY2CL | 2014 K10 BATCH 3 | 10710564.375 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Dagupan City | 300371 | Judge Jose de Venecia, Sr. MNHS | DAGUPAN CITY | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | COMPLETED | 1 | 2016-04-28 |  | 010414S00216 | 15AH0196 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-24 | 2015-10-02 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Dagupan City | 500055 | Pugaro IS | DAGUPAN CITY | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6449337.6381 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 010414S00205 | 15AH0147 | 2015-07-06 | 2015-07-10 | 2015-07-21 | 2015-08-03 | 2015-08-11 | J.G. GARCIA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300001 | Adams NHS | ADAMS | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 010114S00070 | 15AA0099 | 2015-07-06 | 2015-07-19 | 2015-07-20 | 2015-07-27 | 2015-07-31 | ACCV BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100161 | Aggasi PS | PAGUDPUD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 1938606.04 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010114S00086 | 15AA0146 | 2015-09-25 | 2015-10-06 | 2015-10-12 |  |  | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8589965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-07-19 |  | 010114S00073 | 15AA0157 | 2015-10-28 | 2015-11-06 | 2015-11-26 |  |  | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-26 |  | 010114S00081 | 15AA0132 | 2015-09-03 | 2015-09-17 | 2015-09-29 | 2015-10-14 | 2015-10-29 | KATHA BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300007 | Cadaratan National High School | BACARRA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-26 |  | 010114S00083 | 15AA0133 | 2015-09-03 | 2015-09-16 | 2015-09-29 | 2015-10-14 | 2015-10-29 | ALTHEA CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100292 | Canaam Elementary School | VINTAR | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1212049.6543 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-12-13 | 010114S00018 | 15AA0121 | 2015-08-18 | 2015-08-30 | 2015-09-01 | 2015-09-09 | 2015-09-15 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-07 |  | 010114S00084 | 15AA0148 | 2015-09-30 | 2015-10-09 | 2015-10-13 | 2015-11-19 | 2015-12-10 | KATHA BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100166 | Caunayan Elementary School | PAGUDPUD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 1938606.04 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010114S00087 | 15AA0139 | 2015-09-16 | 2015-09-25 | 2015-09-29 |  |  | VIKING CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100167 | Dampig ES | PAGUDPUD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 1938606.04 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010114S00085 | 15AA0136 | 2015-09-16 | 2015-09-28 | 2015-09-29 | 2015-12-07 |  | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 010114S00079 | 15AA0092 | 2015-07-02 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-07-31 | BLUE MOUNTAIN BUILDERS & GENERAL MDSE.(FOR. BLUE M
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100296 | Esperanza Elementary School | VINTAR | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1934740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 010114S00015 | 15AA0117 | 2015-08-18 | 2015-08-30 | 2015-09-01 | 2015-09-14 | 2015-09-23 | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320827 | F. Camaquin Integrated School | VINTAR | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8589965.051 |  |  | COMPLETED | 1 | 2016-06-19 |  | 010114S00072 | 15AA0135 | 2015-08-27 | 2015-09-28 | 2015-09-29 |  |  | ALTHEA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1 | 2016-07-09 |  | 010114S00078 | 15AA0153 | 2015-10-26 | 2015-11-04 | 2015-11-26 | 2015-12-04 | 2015-12-28 | ASIAN PEARL CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100313 | Isic Isic ES | VINTAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1236329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320821 | Isic-Isic NHS | VINTAR | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-05-20 |  | 010114S00082 | 15AA0131 | 2015-09-03 | 2015-09-16 | 2015-09-29 |  |  | SOLSONA-GANAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100225 | Libnaoan ES | PIDDIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-21 | 2015-12-21 | 010114S00014 | 15AA0119 | 2015-08-18 | 2015-08-30 | 2015-09-01 | 2015-09-14 | 2015-09-23 | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300019 | Luzong NHS | PAGUDPUD | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8764965.051 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010114S00077 | 15AA0149 | 2015-09-30 | 2015-10-09 | 2015-10-13 | 2015-10-23 | 2015-11-25 | BUSILAC BUILDERS INC.
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100300 | Masadsaduel Elementary School | VINTAR | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1162049.6543 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 010114S00016 | 15AA0120 | 2015-08-18 | 2015-08-30 | 2015-09-01 | 2015-09-15 | 2015-09-23 | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300024 | Pagudpud NHS | PAGUDPUD | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8764965.051 |  |  | COMPLETED | 1 | 2016-04-28 |  | 010114S00076 | 15AA0147 | 2015-09-30 | 2015-10-10 | 2015-10-13 | 2015-11-03 | 2015-12-01 | VCD CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-25 |  | 010114S00075 | 15AA0134 | 2015-08-27 | 2015-09-28 | 2015-09-29 | 2015-10-13 | 2015-10-29 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320825 | Pandan IS | SARRAT | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-13 | 2015-12-13 | 010114S00074 | 15AA0118 | 2015-08-18 | 2015-08-31 | 2015-09-01 | 2015-09-09 | 2015-09-15 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100174 | Pasaleng ES | PAGUDPUD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 1938606.04 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010114S00088 | 15AA0145 | 2015-09-25 | 2015-10-06 | 2015-10-12 |  |  | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-06-17 |  | 010114S00080 | 15AA0160 | 2015-11-03 | 2015-11-11 | 2015-11-26 | 2015-12-07 | 2015-12-21 | REMAR CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15547518.84 |  |  | COMPLETED | 1 | 2016-07-19 |  | 010114S00066 | 15AA0159 | 2015-11-03 | 2015-11-15 | 2015-11-16
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100303 | Sagpat ES | VINTAR | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 010114S00017 | 15AA0115 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-20 | 2015-08-27 | ACCV BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 500344 | Salpad Integrated School | VINTAR | 1 | 1 | 2 | 1STY 2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 500344 | Salpad Integrated School | VINTAR | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | 12 | 3STY12CL | 2014 SHS BATCH 1 | 18597268.79 |  |  | COMPLETED | 1 | 2016-06-28 |  | 010114S00038 | 15AA0158 | 2015-10-28 | 2015-11-12 | 2015-11-26 | 2015-12-10 | 2015-12-22 | MEGAPOLITAN BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22527343.62 |  |  | COMPLETED | 1 | 2016-07-06 |  | 010114S00037 | 15AA0156 | 2015-10-28 | 2015-11-07 | 2015-11-26 | 2015-12-11 | 2015-12-21 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100213 | Surong PS | PASUQUIN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 010114S00013 | 15AA0116 | 2015-07-28 | 2015-08-09 | 2015-08-10 | 2015-08-20 | 2015-08-27 | ACCV BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-25 |  | 010114S00036 | 15AA0128 | 2015-09-03 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-29 | SOLSONA-GANAL CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon NHS | NUEVA ERA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-16 |  | 010114S00035 | 15AB0047 | 2015-07-06 | 2015-07-08 | 2015-08-18 | 2015-09-07 | 2015-09-18 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300004 | Banna National High School | BANNA (ESPIRITU) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010114S00034 | 15AB0076 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-29 |  | ZEDIK BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100140 | Barangobong ES | NUEVA ERA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1162049.6543 |  |  | COMPLETED | 1 | 2015-11-30 |  | 010114S00021 | 15AB0048 | 2015-07-06 | 2015-08-06 | 2015-08-18 | 2015-09-07 | 2015-09-18 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320826 | Caraitan Integrated School | BADOC | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-06 |  | 010114S00031 | 15AB0045 | 2015-07-06 | 2015-08-06 | 2015-08-18 | 2015-10-28 | 2015-11-16 | ASTRO BUILDERS AND CONSTRUCTION RESOURCES INC.
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300010 | Caribquib NHS | BANNA (ESPIRITU) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00055 | 15AB0063 | 2015-08-13 | 2015-08-17 | 2015-08-28 | 2015-09-11 | 2015-10-02 | ACCV BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300011 | Catagtaguen NHS | BANNA (ESPIRITU) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-13 |  | 010114S00039 | 15AB0079 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-29 | 2015-10-16
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300013 | Currimao NHS | CURRIMAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010114S00029 | 15AB0077 | 2015-09-02 | 2015-09-14 | 2015-09-16 | 2015-09-29 | 2015-10-16 | CURRIMAO CONSTRUCTION & DEVELOPMENT, INC.
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300015 | Dingras NHS/Lt. Edgar Foz Mem. NHS | DINGRAS | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11252342.5917 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010114S00028 | 15AB0083 | 2015-09-16 | 2015-09-18 | 2015-09-30 | 2015-10-15 | 2015-10-29 | AJ TAYLAN CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320806 | Dingras NHS/Lt. Edgar Foz Mem. NHS (Barong Campus) | DINGRAS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6894337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00027 | 15AB0071 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-01 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320808 | Dingras NHS/Lt. Edgar Foz Mem. NHS (San Marcos Campus) | DINGRAS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6694337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00026 | 15AB0070 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-01 | SOLSONA-GANAL CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320809 | Dingras NHS/Lt. Edgar Foz Mem. NHS (Sulquiano Campus) | DINGRAS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6694337.6381 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010114S00025 | 15AB0069 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-10-08 | 2015-10-23 | AJ TAYLAN CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100147 | Ferdinand ES | MARCOS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1136329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100031 | Lasien School | BADOC | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1 | 2015-11-20 |  | 010114S00019 | 15AB0049 | 2015-07-04 | 2015-08-06 | 2015-08-18 | 2015-09-07 | 2015-09-22 | BADOC BUILDERS AND SUPPLY (FORMERLY: BADOC BUILDER
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 150002 | Mabusag Sur ES | BADOC | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 7519337.6381 |  |  | COMPLETED | 1 |  |  | 010114S00020
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 500345 | Malaguip Integrated School | PAOAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010114S00047 | 15AB0073 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-02 | ACCV BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320811 | Marcos NHS (Agunit Campus) | MARCOS | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-26 |  | 010114S00049 | 15AB0044 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-12 | KRB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100183 | Monte PS | PAOAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-06 |  | 010114S00023 | 15AB0043 | 2015-07-04 | 2015-08-06 | 2015-08-18 | 2015-09-17 | 2015-09-22 | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 150003 | Nagbacalan West PS | PAOAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 3540828.124 |  |  | COMPLETED | 1 | 2016-03-04 | 2015-12-24 | 010114S00022 | 15AB0050 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-12 | TRI-LINE BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 300021 | Nagrebcan NHS | BADOC | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300021 | Nagrebcan NHS | BADOC | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300022 | Nueva Era NHS | NUEVA ERA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-12 |  | 010114S00054 | 15AB0075 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-28 | 2015-10-15 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300023 | Pagsanahan NHS | BADOC | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10792131.51 |  |  | COMPLETED | 1 | 2016-02-12 |  | 010114S00053 | 15AB0091 | 2015-10-21
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300025 | Paoay Lake NHS | PAOAY | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00052 | 15AB0072 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-02 | ASTRO BUILDERS AND CONSTRUCTION RESOURCES INC.
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300027 | Pinili NHS | PINILI | 2 | 1 | 12 | 3STY12CL | 2014 SHS BATCH 1 | 18222268.79 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010114S00051 | 15AB0084 | 2015-09-16
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320824 | Sacritan Integrated School | PINILI | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-18 | 2015-11-16 | 010114S00050 | 15AB0042 | 2015-07-06 | 2015-07-08 | 2015-07-21 | 2015-08-10 | 2015-08-21 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | K10 (2014) | Region I | Ilocos Norte | 100249 | Salanap ES | PINILI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3452592.44 |  |  | COMPLETED | 1 | 2016-01-29 |  | 010114S00089 | 15AB0062 | 2015-08-06 | 2015-08-10 | 2015-08-21 | 2015-09-10 | 2015-09-25 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320807 | San Marcelino National High School | DINGRAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8764965.051 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010114S00040 | 15AB0080 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-09-29 | 2015-10-16 | ZEDIK BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300028 | San Nicolas NHS | SAN NICOLAS | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 010114S00048
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320815 | San Nicolas NHS (Bingao Campus) | SAN NICOLAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 010114S00056 | 15AB0078 | 2015-09-02 | 2015-09-04 | 2015-09-16 | 2015-10-23 | 2015-11-09 | VCD CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 300030 | Solsona National High School, Maananteng Campus | SOLSONA | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1 |  |  | 010114S00046
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320817 | Solsona NHS (Bagbag Campus) | SOLSONA | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 010114S00045
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320818 | Solsona NHS (Talugtog Campus) | SOLSONA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6694337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010114S00044 | 15AB0068 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-02 | DJCM CONSTRUCTION CORPORATION (FORMERLY: DJCM CONSTRUCTION)
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320810 | SUYO NATIONAL HIGH SCHOOL | DINGRAS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6694337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010114S00043 | 15AB0066 | 2015-08-17 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-10-03 | MSF CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Norte | 320828 | Uguis Integrated School | NUEVA ERA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-16 |  | 010114S00042 | 15AB0046 | 2015-08-04 | 2015-08-06 | 2015-08-18 | 2015-09-07 | 2015-09-18 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300038 | Bantay NHS | BANTAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010214S00054 | 15AC0097 | 2015-08-18 | 2015-08-28 | 2015-09-01 | 2015-09-18 | 2015-09-24 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300040 | Belen NHS | SAN ILDEFONSO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-01 |  | 010214S00044 | 15AC0082 | 2015-08-14 | 2015-08-24 | 2015-08-26 | 2015-09-08 | 2015-09-14 | FIT CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 320906 | Binacud IS | SINAIT | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-11-11 | 010214S00056 | 15AC0087 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-04 | 2015-09-17 | BONICAB BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-08 |  | 010214S00057 | 15AC0098 | 2015-08-19 | 2015-08-28 | 2015-09-02 | 2015-09-16 | 2015-09-21 | 739 BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300045 | Caoayan NHS | CAOAYAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 010214S00038 | 15AC0090 | 2015-08-14 | 2015-08-24 | 2015-08-28 | 2015-09-11 | 2015-09-15 | FIT CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100645 | Dadalaquiten ES | SINAIT | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00082 | 15AC0104 | 2015-09-04 | 2015-09-14 | 2015-09-16 | 2015-09-22 | 2015-09-24 | N.A. IBARRA CONSTRUCTION(FOR. DIOCLETIANS CONST.)
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300055 | Lipit NHS | CABUGAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-08 |  | 010214S00058 | 15AC0085 | 2015-08-15 | 2015-08-24 | 2015-08-26 | 2015-09-08 | 2015-09-21 | BONICAB BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300056 | Lussoc NHS | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010214S00047 | 15AC0099 | 2015-08-19 | 2015-08-28 | 2015-09-02 | 2015-09-18 | 2015-09-22 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300057 | Magsingal NHS | MAGSINGAL | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-14 |  | 010214S00066 | 15AC0093 | 2015-08-18 | 2015-08-28 | 2015-09-29 | 2015-10-12 | 2015-10-23 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300058 | Manzante NHS | MAGSINGAL | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-11-17 | 010214S00069 | 15AC0086 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-04 | 2015-09-17 | 739 BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300060 | Naglaoa-an NHS | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010214S00068 | 15AC0094 | 2015-08-18 | 2015-08-28 | 2015-09-01 | 2015-09-15 | 2015-09-22 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300066 | Pantay Tamurong National High School | CAOAYAN | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-07 | 2015-10-23 | 010214S00067 | 15AC0089 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-03 | 2015-09-09 | FIT CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100460 | Puro ES | CAOAYAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3102592.44 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00083 | 15AC0106 | 2015-09-05 | 2015-09-14 | 2015-09-17 | 2015-09-22 | 2015-09-24 | FIT AND SONS INDUSTRIES, INC.
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300068 | Puro NHS, Caoayan | CAOAYAN | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-10-23 | 010214S00070 | 15AC0088 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-03 | 2015-09-10 | FIT CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300069 | Puro NHS, Magsingal | MAGSINGAL | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00065 | 15AC0091 | 2015-08-14 | 2015-08-24 | 2015-08-28 | 2015-09-11 | 2015-09-24 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300035 | SAN JUAN NHS | SAN JUAN (LAPOG) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-04 |  | 010214S00064 | 15AC0095 | 2015-08-18 | 2015-08-28 | 2015-09-29 | 2015-10-12 | 2015-10-23 | N.A. IBARRA CONSTRUCTION(FOR. DIOCLETIANS CONST.)
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 320909 | San Sebastian NHS | SAN VICENTE | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00063 | 15AC0092 | 2015-08-14 | 2015-08-24 | 2015-08-28 | 2015-09-11 | 2015-09-24 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 500348 | San Vicente IS | SAN VICENTE | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010214S00059 | 15AC0096 | 2015-08-18 | 2015-08-28 | 2015-09-01 | 2015-09-15 | 2015-09-24 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300080 | Sinait NHS | SINAIT | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 320908 | Sisim NHS | CABUGAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-28 |  | 010214S00071 | 15AC0084 | 2015-08-14 | 2015-08-24 | 2015-08-26 | 2015-09-08 | 2015-09-21 | BONICAB BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300081 | Solotsolot NHS | SAN JUAN (LAPOG) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010214S00061 | 15AC0083 | 2015-08-14 | 2015-08-24 | 2015-08-26 | 2015-09-08 | 2015-09-21 | MAGSAYSAY CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300033 | Alilem NHS (Alilem Daya HS) | ALILEM | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010214S00060 | 15AD0090 | 2015-07-27 | 2015-07-29 | 2015-08-10 | 2015-08-20 | 2015-09-04 | MAK-JAY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 500349 | Ambalayat IS | TAGUDIN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-23 |  | 010214S00049 | 15AD0117 | 2015-08-14 | 2015-08-17 | 2015-09-01 | 2015-09-11 | 2015-09-16 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300037 | Banayoyo NHS | BANAYOYO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010214S00039 | 15AD0091 | 2015-07-27 | 2015-07-29 | 2015-08-10 | 2015-08-20 | 2015-09-03 | MBB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100764 | Baracbac Comm. Sch. | TAGUDIN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00084 | 15AD0107 | 2015-08-03 | 2015-08-07 | 2015-08-20 | 2015-09-02 | 2015-09-04 | BATCH 81 ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100765 | Becques Community School | TAGUDIN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-13 |  | 010214S00078 | 15AD0125 | 2015-08-18 | 2015-08-19 | 2015-09-03 | 2015-09-11 | 2015-09-16 | MBB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100768 | Bitalag Elementary | TAGUDIN | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-26 |  | 010214S00077 | 15AD0140 | 2015-09-09 | 2015-09-22 | 2015-09-25 | 2015-10-28 | 2015-11-19 | MBB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 150520 | Bito PS | SUYO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3002592.44 |  |  | COMPLETED | 1 | 2016-03-23 |  | 010214S00079 | 15AD0127 | 2015-08-18 | 2015-08-19 | 2015-10-06 | 2015-10-19 | 2015-10-26 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100563 | Bulala-Leguey PS | SALCEDO (BAUGEN) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | COMPLETED | 1 | 2016-02-14 |  | 010214S00080 | 15AD0126 | 2015-08-18 | 2015-08-19 | 2015-09-03 | 2015-09-11 | 2015-09-28 | M.J. APIN BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300041 | Burgos NHS | BURGOS | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-20 |  | 010214S00085 | 15AD0131 | 2015-08-25 | 2015-09-08 | 2015-09-08 | 2015-09-17 | 2015-09-23 | MBB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300046 | Cervantes NHS | CERVANTES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 |  |  | 010214S00029 | 15AD0122 | 2015-10-13 | 2015-10-16 | 2015-12-22
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300049 | Dili NHS | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-23 |  | 010214S00020 | 15AD0105 | 2015-08-03 | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-09-16 | PRECIOUS CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300050 | Dinaratan NHS | SALCEDO (BAUGEN) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-31 |  | 010214S00018 | 15AD0084 | 2015-07-21 | 2015-07-23 | 2015-08-06 | 2015-08-17 | 2015-09-02 | TRIBU DESIGN & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300048 | G. DEL PILAR NHS | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-31 | 2015-12-08 | 010214S00021 | 15AD0086 | 2015-07-21 | 2015-07-23 | 2015-08-06 | 2015-08-18 | 2015-09-02 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300053 | Imelda NHS | NARVACAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-11-03 | 010214S00023 | 15AD0081 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-13 | 2015-09-01 | 739 BUILDERS
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 150521 | KINAYAD PS | SALCEDO (BAUGEN) | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | COMPLETED | 1 | 2016-02-14 |  | 010214S00072 | 15AD0128 | 2015-08-18 | 2015-08-19 | 2015-09-03 | 2015-09-11 | 2015-09-28 | M.J. APIN BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300054 | Lidlidda NHS | LIDLIDDA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-23 |  | 010214S00022 | 15AD0104 | 2015-08-03 | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-09-16 | M.V. CALDO ENGINEERING CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 500346 | Mabilbila IS | SANTA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-02 |  | 010214S00024 | 15AD0130 | 2015-08-25 | 2015-08-27 | 2015-10-06 | 2015-10-27 | 2015-11-05 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300063 | Narvacan Nat'l. Central HS | NARVACAN | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-19 |  | 010214S00025 | 15AD0134 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-09-23 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100526 | Orence ES | NARVACAN | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010214S00081 | 15AD0112 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-14 | MBB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100774 | Pacac ES | TAGUDIN | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010214S00076 | 15AD0108 | 2015-08-03 | 2015-08-07 | 2015-08-20 | 2015-09-02 | 2015-09-04 | 739 BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300064 | Pagangpang NHS | GALIMUYOD | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-23 |  | 010214S00026 | 15AD0103 | 2015-08-03 | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-09-16 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300065 | Palali NHS | SANTA LUCIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010214S00027 | 15AD0110 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-14 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100775 | Pallogan ES | TAGUDIN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00075 | 15AD0109 | 2015-08-03 | 2015-08-07 | 2015-08-20 | 2015-09-02 | 2015-09-04 | 739 BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 500347 | Pudoc West Integrated School | TAGUDIN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-11 |  | 010214S00028 | 15AD0102 | 2015-08-03 | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-09-04 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300070 | Quirino NHS | QUIRINO (ANGKAKI) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-05-27 |  | 010214S00019 | 14AD0089 | 2015-09-09 | 2015-09-21 | 2015-10-28 | 2015-11-17 | 2015-11-20 | MBB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300073 | Salcedo NHS | SALCEDO (BAUGEN) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-20 |  | 010214S00030 | 15AD0132 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-09-23 | M.J. APIN BUILDERS
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300074 | San Emilio NHS | SAN EMILIO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-18 | 2015-11-03 | 010214S00031 | 15AD0085 | 2015-07-21 | 2015-07-23 | 2015-08-06 | 2015-08-17 | 2015-08-20 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300075 | San Esteban NHS | SAN ESTEBAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010214S00032 | 15AD0111 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-14 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100778 | San Miguel ES | TAGUDIN | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 010214S00074 | 15AD0113 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-09-08 | 2015-09-14 | M.V. SABALBURO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300076 | San Pedro NHS | NARVACAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-11-03 | 010214S00033 | 15AD0082 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-13 | 2015-08-25 | M.A. TEJADA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300077 | Santa Maria NHS | SANTA MARIA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-20 |  | 010214S00043 | 15AD0129 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-09-23 | MBB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300078 | Santiago NHS | SANTIAGO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 010214S00035 | 15AD0089 | 2015-07-27 | 2015-07-29 | 2015-08-10 | 2015-08-20 | 2015-08-28 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300079 | Sigay NHS | SIGAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010214S00017 | 15AD0115 | 2015-08-14 | 2015-08-17 | 2015-09-28 | 2015-10-06 | 2015-10-13 | SUMAG BUILDERS CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300036 | Sugpon NHS | SUGPON | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 010214S00042 | AD150101 | 2015-08-03 | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-09-04 | MAK-JAY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 500001 | Sulvec IS | NARVACAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-11-03 | 010214S00041 | 15AD0083 | 2015-07-21 | 2015-07-23 | 2015-08-04 | 2015-08-13 | 2015-08-25 | M.A. TEJADA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300085 | Suyo NHS | SUYO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 010214S00040 | 15AD0088 | 2015-07-27 | 2015-07-29 | 2015-08-10 | 2015-08-20 | 2015-08-28 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 320904 | Suyo NHS Annex | SUYO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 320904 | Suyo NHS Annex | SUYO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300086 | Tagudin NHS | TAGUDIN | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-19 |  | 010214S00036 | 15AD0133 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-09-23 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Ilocos Sur | 100782 | Tampugo ES | TAGUDIN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-14 |  | 010214S00073 | 15AD0124 | 2015-08-19 | 2015-08-20 | 2015-09-03 | 2015-09-11 | 2015-09-16 | MBB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Ilocos Sur | 300072 | Teodoro Hernaez NHS | SANTA LUCIA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-25 | 2015-11-25 | 010214S00034 | 15AD0087 | 2015-07-21 | 2015-07-23 | 2015-08-06 | 2015-08-17 | 2015-09-02 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300095 | Bacnotan NHS | BACNOTAN | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22327343.62 |  |  | COMPLETED | 1 | 2016-06-11 |  | 010314S00061 | 15AE0125 | 2015-08-19 | 2015-08-31 | 2015-09-01 | 2015-09-11 | 2015-09-28 | MIG-WELLS CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | La Union | 300106 | Balaoan NHS-Castor Concepcion MNHS | BALAOAN | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22202343.62 |  |  | COMPLETED | 1 | 2016-06-13 |  | 010314S00062 | 15AE0124 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-08 | 2015-09-30 | AJ TAYLAN CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region I | La Union | 101076 | Banbanaba ES | SANTOL | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6369337.6381 |  |  | COMPLETED | 1 | 2016-03-27 |  | 010314S00090 | 15AE0146 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-10-05 | 2015-10-28 | JMBM CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 500351 | Bitalag Integrated School | BACNOTAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010314S00063 | 15AE0118 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-08-31 | 2015-09-16 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region I | La Union | 500354 | Bungro Sucoc Integrated School | LUNA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2019678.0092 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500354 | Bungro-Sucoc Integrated School | LUNA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300107 | Corrooy NHS | SANTOL | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-23 |  | 010314S00074 | 15AE0117 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-11 | 2015-09-30 | KRB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 101079 | Deccan PS | SANTOL | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6419337.6381 |  |  | COMPLETED | 1 | 2016-03-28 |  | 010314S00089 | 15AE0145 | 2015-09-08 | 2015-09-09 | 2015-09-22 | 2015-10-08 | 2015-10-28 | JMBM CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300114 | Dona F. Lacsamana Vda de Ortega MNHS | BANGAR | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22377343.62 |  |  | COMPLETED | 1 | 2016-06-13 |  | 010314S00065 | 15AE0115 | 2015-08-13 | 2015-08-14 | 2015-09-02 | 2015-09-18 | 2015-09-29 | MIG-WELLS CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | La Union | 300115 | Dona F. Lacsamana Vda de Ortega MNHS - Casa Cristo Annex | BANGAR | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15171327.92 |  |  | COMPLETED | 1 | 2016-06-05 |  | 010314S00058 | 15A0149 | 2015-09-17 | 2015-09-28 | 2015-09-30 | 2015-10-07 | 2015-11-06 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region I | La Union | 101107 | Duplas ES | SUDIPEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | COMPLETED | 1 | 2016-01-28 |  | 010314S00087 | 15AE0107 | 2015-08-10 | 2015-08-12 | 2015-08-24 | 2015-09-07 | 2015-09-30 | KRB CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 101080 | Liguay ES | SANTOL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1146945.576 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 321018 | LUNA NATIONAL VOCATIONAL HIGH SCHOOL | LUNA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 321018 | LUNA NATIONAL VOCATIONAL HIGH SCHOOL | LUNA | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2990828.124 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300120 | Luna NHS | LUNA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-05 |  | 010314S00067 | 15AE0129 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-11 | 2015-11-05 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 321003 | Luna NHS - Rimos Annex | LUNA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010314S00068 | 15AE0119 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-04 | 2015-10-06 | G.O. MARRON GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region I | La Union | 300124 | Oanari NHS | LUNA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14947518.84 |  |  | COMPLETED | 1 | 2016-07-07 |  | 010314S00069 | 15AE0147 | 2015-09-16 | 2015-09-25 | 2015-09-29 | 2015-10-06 | 2015-11-25 | J.D. MADRID CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300125 | Old Sudipen NHS | SUDIPEN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-04-10 |  | 010314S00070 | 15AE0128 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-14 | 2015-10-09 | AJ TAYLAN CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region I | La Union | 101082 | Paagan ES | SANTOL | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4773636.82 |  |  | COMPLETED | 1 | 2016-02-18 |  | 010314S00088 | 15AE0120 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-04 | 2015-09-24 | H.G. LOPEZ CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300111 | Paraoir NHS | BALAOAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-23 |  | 010314S00044 | 15AE0123 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-02 | 2015-09-30 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100902 | Pudoc ES | BANGAR | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3127592.44 |  |  | COMPLETED | 1 | 2016-01-13 | 2015-12-15 | 010314S00091 | 15AE0106 | 2015-08-11 | 2015-08-21 | 2015-08-24 | 2015-08-28 | 2015-09-14 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300132 | Regional Science HS, La Union | BANGAR | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-20 |  | 010314S00071 | 15AE0126 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-09 | 2015-10-06 | MIG-WELLS CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | La Union | 300135 | San Gabriel Vocational High School | SAN GABRIEL | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22452343.62 |  |  | COMPLETED | 1 | 2016-06-23 |  | 010314S00060 | 15AE0135 | 2015-08-31 | 2015-09-09 | 2015-09-14 | 2015-09-22 | 2015-10-07 | MIG-WELLS CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-04-25 |  | 010314S00086 | 15AE0133 | 2015-08-31 | 2015-09-08 | 2015-09-14 | 2015-09-23 | 2015-10-21 | MIG-WELLS CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | La Union | 300146 | Sto. Rosario NHS | SAN JUAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-04-05 |  | 010314S00085 | 15AE0127 | 2015-08-19 | 2015-08-20 | 2015-09-01 | 2015-09-09 | 2015-10-05 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300148 | Sudipen Voc'l Sch. | SUDIPEN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-23 |  | 010314S00084 | 15AE0116 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-03 | 2015-09-30 | KRB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300110 | Alipang NHS | ROSARIO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 010314S00083 | 0103-14-S-00083(CNTR) | 2015-08-18 | 2015-08-21 | 2015-08-24 | 2015-09-10 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 300091 | Amlang-Nagtagaan NHS | ROSARIO | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15047518.84 |  |  | COMPLETED | 1 |  |  | 010314S00082 | 0103-14-S-00082(CNTR) | 2015-09-07 | 2015-09-15 | 2015-09-17 | 2015-09-28 | 2015-10-08 | A.P.O. GENERAL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300094 | Baccuit NHS | BAUANG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00081 | 0103-14-S-00081(CNTR) | 2015-08-17 | 2015-08-20 | 2015-08-27 | 2015-09-16 | 2015-09-21 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region I | La Union | 300096 | Bail NHS | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6494337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00072 | 0103-14-S-00072(CNTR) | 2015-08-17 | 2015-08-21 | 2015-08-28 | 2015-09-09 | 2015-09-21 | J.A. CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100979 | Bimmotobot 2 Upper PS | NAGUILIAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1068049.6543 |  |  | COMPLETED | 1 | 2015-11-20 | 2015-11-20 | 010314S00026 | 0103-14-S-00026(CNTR) | 2015-08-17 | 2015-08-26 | 2015-09-07 | 2015-09-16 | 2015-09-21 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2014 | K10 (2014) | Region I | La Union | 100821 | Bitag ES | ARINGAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1234331.9056 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300102 | Burgos NHS | BURGOS | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15247518.84 |  |  | COMPLETED | 1 |  |  | 010314S00105 | 0103-14-S-00105(CNTR) | 2015-10-06 | 2015-10-19 | 2015-10-21 | 2015-11-06 | 2015-11-20 | ECDI ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 300104 | Caba NHS | CABA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1114175.7024 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300104 | Caba NHS | CABA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 500361 | Cabaruan Integrated School | SANTO TOMAS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500361 | Cabaruan Integrated School | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 500359 | CAPAS INTEGRATED SCHOOL | AGOO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2922477.9186 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500359 | CAPAS INTEGRATED SCHOOL | AGOO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 500358 | Casilagan Integrated School | BAUANG | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1146945.576 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500358 | CASILAGAN INTEGRATED SCHOOL | BAUANG | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 101119 | Daeng ES | TUBAO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | COMPLETED | 1 |  |  | 010314S00094 | 0103-14-S-00094(CNTR) | 2015-10-08 | 2015-10-16 | 2015-10-20 | 2015-11-04 | 2015-11-11 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 500352 | Dagup Integrated School | BAGULIN | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2893826.1743 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500352 | Dagup Integrated School | BAGULIN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300109 | Damortis NHS | SANTO TOMAS | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 010314S00075 | 0103-14-S-00075(CNTR) | 2015-08-17 | 2015-08-24 | 2015-08-24 | 2015-09-08 | 2015-09-21 | A.P.O. GENERAL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 500360 | Daramuangan Integrated School | NAGUILIAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500360 | Daramuangan Integrated School | NAGUILIAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300130 | Don Eufemio F. Eriguel MNHS | AGOO | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22602343.62 |  |  | COMPLETED | 1 |  |  | 010314S00043 | 0103-14-S-00043(CNTR) | 2015-09-25 | 2015-10-12 | 2015-10-13 | 2015-11-09 | 2015-11-20 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300112 | Don Eulogio De Guzman MNHS | BAUANG | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 |  |  | 010314S00038 | 0103-14-S-00038(CNTR) | 2015-08-31 | 2015-09-08 | 2015-09-18 | 2015-09-29 | 2015-10-08 | BONIMAR CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | La Union | 300090 | Eulogio Clarence De Guzman Junior Memorial National Vocational High School | BAUANG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00041 | 0103-14-S-00041(CNTR) | 2015-08-10 | 2015-08-24 | 2015-08-27 | 2015-09-15 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 151009 | EULOGIO CLARENCE M. DE GUZMAN Jr. ELEMENTARY SCHOOL | BAUANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1865740.174 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-20 | 010314S00028 | 0103-14-S-00028(CNTR) | 2015-08-24 | 2015-08-27 | 2015-09-07 | 2015-09-17 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300119 | Leones National High School | TUBAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 010314S00037 | 14AF0039 | 2015-08-14 | 2015-08-21 | 2015-08-31 | 2015-09-08 | 2015-09-21 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | La Union | 100864 | Libbo ES | BAGULIN | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2029530.0971 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 321025 | Libtong Integrated School | BURGOS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 321025 | Libtong Integrated School | BURGOS | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 500357 | Liquicia Integrated School | CABA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2951129.6629 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500357 | Liquicia Integrated School | CABA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300144 | Magungunay NHS - Southern Naguilian NHS | NAGUILIAN | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00036 | 0103-14-S-00036(CNTR) | 2015-08-24 | 2015-08-28 | 2015-08-31 | 2015-09-14 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 151007 | Maoasoas ES Annex | PUGO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300122 | Naguilian NHS | NAGUILIAN | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11077342.5917 |  |  | COMPLETED | 1 |  |  | 010314S00035 | 0103-14-S-00035(CNTR) | 2015-09-21 | 2015-10-07 | 2015-10-12 | 2015-10-16 | 2015-10-28 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100829 | New Bern (Alaska) ES | ARINGAY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00099 | 0103-14-S-00099(CNTR) | 2015-08-17 | 2015-08-21 | 2015-08-25 | 2015-09-15 | 2015-09-21 | J.A. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300127 | Parasapas NHS | ROSARIO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00034 | 0103-14-S-00034(CNTR) | 2015-08-14 | 2015-08-24 | 2015-09-01 | 2015-09-22 | 2015-10-07 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region I | La Union | 300128 | Paringao NHS | BAUANG | 2 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15271327.92 |  |  | COMPLETED | 1 |  |  | 010314S00033 | 0103-14-S-00033(CNTR) | 2015-08-31 | 2015-09-14 | 2015-09-23 | 2015-09-29 | 2015-10-08 | BONIMAR CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | La Union | 300129 | Pres. Elpidio. Quirino NHS | AGOO | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22602343.62 |  |  | COMPLETED | 1 |  |  | 010314S00032 | 0103-14-S-00032(CNTR) | 2015-09-21 | 2015-09-29 | 2015-10-13 | 2015-11-05 | 2015-11-20 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300131 | Pugo Central NHS | PUGO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15247518.84 |  |  | COMPLETED | 1 |  |  | 010314S00031 | 0103-14-S-00031(CNTR) | 2015-09-07 | 2015-09-14 | 2015-09-22 | 2015-10-06 | 2015-10-08 | A.P.O. GENERAL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 500002 | Rosario Integrated School | ROSARIO | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14165118.3984 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500002 | Rosario Integrated School | ROSARIO | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300136 | San Gregorio NHS | CABA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6544337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00029 | 0103-14-S-00029(CNTR) | 2015-08-24 | 2015-08-27 | 2015-09-07 | 2015-09-15 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300137 | San Jose NHS | CABA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15047518.84 |  |  | COMPLETED | 1 |  |  | 010314S00039 | 0103-14-S-00039(CNTR) | 2015-08-31 | 2015-09-09 | 2015-09-18 | 2015-09-28 | 2015-10-08 | BONIMAR CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | La Union | 300139 | San Manuel Norte NHS | AGOO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 010314S00050 | 0103-14-S-00050(CNTR2) | 2015-08-17 | 2015-08-24 | 2015-08-25 | 2015-09-09 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 500362 | Santiago Sur Integrated School | CABA | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1365411.4 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 500362 | Santiago Sur Integrated School | CABA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300142 | Saytan Integrated School | PUGO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00055 | 0103-14-S-00055(CNTR) | 2015-08-17 | 2015-08-24 | 2015-08-24 | 2015-09-10 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100867 | Sinabugan Elementary School | BAGULIN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1068049.6543 |  |  | COMPLETED | 1 |  |  | 010314S00027 | 0103-14-S-00027(CNTR) | 2015-08-24 | 2015-08-28 | 2015-09-07 | 2015-09-16 | 2015-09-21 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2014 | SHS (2014) | Region I | La Union | 321010 | Sto. Tomas NHS | SANTO TOMAS | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15047518.84 |  |  | COMPLETED | 1 |  |  | 010314S00054 | 0103-14-S-00054(CNTR) | 2015-09-11 | 2015-09-17 | 2015-09-18 | 2015-09-29 | 2015-10-08 | A.P.O. GENERAL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300149 | Suyo National High School | BAGULIN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 010314S00053 | 0103-14-S-00053(CNTR) | 2015-09-04 | 2015-09-10 | 2015-09-14 | 2015-09-29 | 2015-10-08 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100868 | Tagudtud ES | BAGULIN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3052592.44 |  |  | COMPLETED | 1 |  |  | 010314S00095 | 0103-14-S-00095(CNTR) | 2015-09-21 | 2015-09-28 | 2015-10-07 | 2015-10-19 | 2015-10-28 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300151 | Tanglag NHS | ROSARIO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00052 | 0103-14-S-00052(CNTR) | 2015-08-17 | 2015-08-20 | 2015-08-24 | 2015-09-11 | 2015-09-21 | E.E. MADAYAG CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 100869 | Tio-angan ES | BAGULIN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1146945.576 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 100869 | Tio-angan ES | BAGULIN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1079049.6543 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | La Union | 300152 | Tubao NHS | TUBAO | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22402343.62 |  |  | COMPLETED | 1 |  |  | 010314S00051 | 0103-14-S-00051(CNTR) | 2015-09-21 | 2015-09-24 | 2015-09-28 | 2015-10-16 | 2015-10-28 | R.C. TAGALA CONSTRUCTION
NC 2014 | K10 (2014) | Region I | La Union | 321011 | Tubao NHS Annex Halog West | TUBAO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1146945.576 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | La Union | 100995 | Tuddinggan ES | NAGUILIAN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6469337.6381 |  |  | COMPLETED | 1 |  |  | 010314S00093 | 0103-14-S-00093(CNTR) | 2015-08-17 | 2015-08-24 | 2015-08-28 | 2015-09-23 | 2015-09-29 | J.A. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | La Union | 300153 | Wenceslao National HS | CABA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | COMPLETED | 1 |  |  | 010314S00042 | 0103-14-S-00042(CNTR) | 2015-08-31 | 2015-09-07 | 2015-09-14 | 2015-09-25 | 2015-09-30 | BONIMAR CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | Laoag City | 500056 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1186329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-07-02 |  | 010114S00060 | 15AA0154 | 2015-10-26 | 2015-11-04 | 2015-11-26 | 2015-12-08 | 2015-12-21 | VIKING CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Laoag City | 300374 | Ilocos Norte NHS | LAOAG CITY (Capital) | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-07-02 |  | 010114S00061 | 15AA0155 | 2015-10-26 | 2015-11-04 | 2015-11-26 | 2015-12-07 | 2015-12-21 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2014 | SHS (2014) | Region I | Laoag City | 305601 | Ilocos Norte NHS - Caaoacan Annex | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-28 | 2015-09-28 | 010114S00065 | 15AA0098 | 2015-07-06 | 2015-07-19 | 2015-07-20 | 2015-07-27 | 2015-07-31 | ALTHEA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Laoag City | 300375 | Ilocos Norte Regional School of Fisheries | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6869337.6381 |  |  | COMPLETED | 1 | 2016-02-25 |  | 010114S00057 | 15AA0137 | 2015-09-16 | 2015-09-28 | 2015-09-29 | 2015-10-14 | 2015-10-29 | ACCV BUILDERS
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321123 | Abagatanen IS | AGNO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-13 | 2015-10-13 | 010414S00218 | 15AG0070 | 2015-06-24 | 2015-06-26 | 2015-07-08 | 2015-07-13 | 2015-07-16 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300154 | Agno NHS | AGNO | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22432343.62 |  |  | COMPLETED | 1 | 2016-02-28 |  | 010414S00219 | 15AG0118 | 2015-08-07 | 2015-08-10 | 2015-08-24 | 2015-08-27 | 2015-09-02 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300158 | Anda National High School | ANDA | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22202343.62 |  |  | COMPLETED | 1 | 2016-04-02 |  | 010414S00220 | 15AG0124 | 2015-08-18 | 2015-08-19 | 2015-09-23 | 2015-10-01 | 2015-10-06 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300159 | Arnedo NHS | BOLINAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2016-02-01 |  | 010414S00221 | 15AG0095(1) | 2015-07-14 | 2015-07-15 | 2015-07-29 | 2015-08-03 | 2015-08-06 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 010414S00222 | 15AG0078 | 2015-06-26 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300164 | Bangan-Oda NHS | AGNO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6539337.6381 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010414S00223 | 15AG099(1) | 2015-07-20 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300165 | Bani NHS | BANI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-04-04 |  | 010414S00224 | 15AG0090(1) | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 321126 | Barlo Integrated School | MABINI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300169 | Bayambang NHS (Infanta) | INFANTA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6469337.6381 |  |  | COMPLETED | 1 | 2016-02-29 |  | 010414S00229 | 151G0097 | 2015-08-13 | 2015-08-12 | 2015-08-25 | 2015-08-28 | 2015-09-03 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300172 | Binabalian NHS | BOLINAO | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1 | 2016-02-29 |  | 010414S00194 | 15AG0119 | 2015-08-13 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-01 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 500370 | Bolinao IS | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8398703.2031 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 500370 | Bolinao IS | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300175 | Bolinao SOF | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-16 |  | 010414S00215 | 15ag0079(1) | 2015-06-26 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00298 | 15AG0081 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-03 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan NHS | MABINI | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-13 | 2015-10-13 | 010414S00184 | 15AG0067 | 2015-06-24 | 2015-06-24 | 2015-07-08 | 2015-07-13 | 2015-07-16 | SAMANTHA ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300182 | Cabungan National High School | ANDA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-02-01 |  | 010414S00185 | 15AG0093(1) | 2015-07-15 | 2015-07-15 | 2015-07-29 | 2015-08-03 | 2015-08-06 | GED CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300187 | Carot NHS | ANDA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 010414S00186 | 15AG0088 | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321111 | Catubig Integrated School | BOLINAO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-10-12 | 010414S00187 | 15AG0066 | 2015-06-24 | 2015-06-24 | 2015-07-08 | 2015-07-13 | 2015-07-16 | A.A. BALAOING TRADING AND CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-10-12 | 010414S00188 | 15AG0068 | 2015-06-24 | 2015-06-24 | 2015-07-08 | 2015-07-13 | 2015-07-16 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300192 | Dacap Norte NHS | BANI | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-04 |  | 010414S00189 | 15AG0123(1) | 2015-08-18 | 2015-08-18 | 2015-08-28 | 2015-09-03 | 2015-09-08 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300194 | Dewey National High School | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 010414S00190 | 15AG0089 | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300201 | Eguia NHS | DASOL | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8339965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00191 | 15AG0085 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-08-03 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 321127 | Gayusan IS | AGNO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300207 | Ilog Malino NHS | BOLINAO | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2016-02-01 |  | 010414S00204 | 15AG0094(1) | 2015-07-15 | 2015-07-15 | 2015-07-29 | 2015-08-03 | 2015-08-06 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321120 | Infanta IS | INFANTA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8384965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 010414S00193 | 15AG0087 | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-02-28 |  | 010414S00297 | 15AG116 | 2015-08-13 | 2015-08-14 | 2015-08-24 | 2015-08-27 | 2015-09-02 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321109 | Liwa Liwa Integrated School | BOLINAO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-10-10 | 010414S00183 | A5AG0064 | 2015-06-24 | 2015-06-26 | 2015-07-08 | 2015-07-13 | 2015-07-16 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101355 | Lucero ES | BOLINAO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300215 | Luna National High School | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8309965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00195 | 15AG0082 | 2015-07-10 | 2015-07-13 | 2015-07-24 | 2015-07-29 | 2015-08-03 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300219 | Magalong NHS | MABINI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 010414S00159 | 15AG0075 | 2015-06-26 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300221 | Malimpin NHS | DASOL | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6494337.6381 |  |  | COMPLETED | 1 | 2016-02-17 |  | 010414S00196 | 15AG0098(1) | 2015-07-20 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | A.A. BALAOING TRADING AND CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321125 | Paitan IS | SUAL | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010414S00225 | 15AG0100(1) | 2015-07-20 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | M A M CONSTRUCTION & TRADING (FOR. MAM CONST.)
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 321104 | Pangascasan IS | SUAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300246 | Ranom Iloco NHS | BANI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 010414S00197 | 15AG0077 | 2015-06-24 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300249 | Sampaloc National High School | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00198 | 15AG0084 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-08-03 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300250 | San Jose NHS (Anda) | ANDA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 010414S00199 | 15AG0086 | 2015-07-13 | 2015-07-13 | 2015-07-27 | 2015-07-30 | 2015-08-04 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300252 | San Miguel NHS, Bani | BANI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 010414S00200 | 15AG0073 | 2015-06-26 | 2015-06-26 | 2015-07-10 | 2015-07-15 | 2015-07-20 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321119 | Sapa Grande IS | BURGOS | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-10-10 | 010414S00296 | 15AG0069 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-13 | 2015-07-16 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | SUAL | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-29 |  | 010414S00201 | 15AG110 | 2015-08-06 | 2015-08-07 | 2015-08-24 | 2015-08-27 | 2015-09-03 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300256 | Tagudin NHS | MABINI | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-02-28 |  | 010414S00202 | 15AG0117 | 2015-08-07 | 2015-08-10 | 2015-08-24 | 2015-08-27 | 2015-09-02 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101455 | Tambobong ES | DASOL | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 | 2016-05-02 |  | 010414S00285 | 15AG0131 | 2015-09-04 | 2015-09-04 | 2015-09-21 | 2015-10-01 | 2015-10-06 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300258 | Tambobong NHS | DASOL | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14957518.84 |  |  | COMPLETED | 1 | 2016-04-29 |  | 010414S00203 | 15AG0111 | 2015-08-07 | 2015-08-10 | 2015-08-24 | 2015-08-27 | 2015-09-03 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300264 | Tondol NHS | ANDA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010414S00192 | 15ag0096(10 | 2015-07-20 | 2015-07-20 | 2015-07-31 | 2015-08-07 | 2015-08-12 | CASIPIT TRADING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321108 | Tupa Integrated School | BOLINAO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-10-10 | 010414S00250 | 15AG0065 | 2015-06-26 | 2015-06-26 | 2015-07-08 | 2015-07-13 | 2015-07-16 | CASIPIT CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101368 | Tupa IS | BOLINAO | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101457 | Viga ES | DASOL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8309965.051 |  |  | COMPLETED | 1 | 2016-03-29 |  | 010414S00253 | 15AG0083 | 2015-07-10 | 2015-07-10 | 2015-07-24 | 2015-07-29 | 2015-08-03 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | AGUILAR | 2 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8448953.2031 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | AGUILAR | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8394965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300160 | Balangay NHS | URBIZTONDO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-22 |  | 010414S00255 | 15AH0200 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-24 | 2015-10-26 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300167 | Basista NHS | BASISTA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 010414S00256 | 15AH0151 | 2015-07-06 | 2015-07-10 | 2015-07-21 | 2015-08-03 | 2015-08-11 | CHRISTIAN IAN CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 500364 | Bayaoas IS | URBIZTONDO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 010414S00257 | 15AH0148 | 2015-07-06 | 2015-07-10 | 2015-07-21 | 2015-08-03 | 2015-08-11 | CDC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300173 | Bocboc East NHS | AGUILAR | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14987518.84 |  |  | COMPLETED | 1 | 2016-05-22 |  | 010414S00258 | 15AH0199 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-24 | 2015-10-26 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321107 | Bugallon IS | BUGALLON | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300181 | Cabayaoasan NHS | MANGATAREM | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1 | 2016-05-22 |  | 010414S00260 | 15AH0235 | 2015-08-23 | 2015-08-27 | 2015-09-08 | 2015-09-21 | 2015-10-26 | J.C. FERRER CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300185 | Camaley NHS | BINMALEY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 | 2016-01-16 |  | 010414S00262 | 15AH0157 | 2015-07-08 | 2015-07-10 | 2015-07-23 | 2015-08-04 | 2015-08-20 | BET CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321113 | Dalanguiring IS | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-11-25 | 2015-12-22 | 010414S00252 | 15AH0141 | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-15 | 2015-07-29 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 500367 | Domalandan Center IS | LINGAYEN (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8524965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00263 | 15AH0162 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300199 | Dulag NHS | BINMALEY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8544965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00264 | 15AH0160 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101474 | Dulig ES | LABRADOR | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 |  | 010414S00287 | 15AH0177 | 2015-07-16 | 2015-07-20 | 2015-07-31 | 2015-08-13 | 2015-08-27 | JF CRUZ TRADING & CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300203 | Estanza NHS | LINGAYEN (Capital) | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00265 | 15AH0163 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300204 | Galarin NHS | URBIZTONDO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8254965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00266 | 15AH0149 | 2015-07-06 | 2015-07-10 | 2015-07-21 | 2015-08-13 | 2015-08-24 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300211 | Lasip NHS | LINGAYEN (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15247518.84 |  |  | COMPLETED | 1 |  |  | 010414S00267 | 15AH0198 | 2015-07-26 | 2015-07-30 | 2015-08-11
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321118 | Malawa IS | LINGAYEN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-10-11 | 010414S00268 | 15AH0139 | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-15 | 2015-07-29 | CWME BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101606 | Muelang ES | MANGATAREM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 010414S00075 | 14AH007211 | 2014-12-09 |  | 2014-12-22 | 2014-12-29 | 2015-01-07 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 300227 | Naguilayan NHS | MANGATAREM | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300231 | Olo NHS | MANGATAREM | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010414S00269 | 15AH0212 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-10-26 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan SAT | LINGAYEN (Capital) | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22302343.62 |  |  | COMPLETED | 1 | 2016-04-28 |  | 010414S00270 | 15AH0236 | 2015-08-23 | 2015-08-20 | 2015-09-08 | 2015-09-21 | 2015-10-02 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300235 | Parayao NHS | BINMALEY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8494965.051 |  |  | COMPLETED | 1 | 2016-01-16 |  | 010414S00271 | 15AH0158 | 2015-07-08 | 2015-07-10 | 2015-07-23 | 2015-08-04 | 2015-08-20 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300241 | Polong NHS | BUGALLON | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-04-10 |  | 010414S00272 | 15AH0209 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-10-14 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300243 | Quetegan NHS | MANGATAREM | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6544337.6381 |  |  | COMPLETED | 1 | 2015-11-25 | 2015-11-25 | 010414S00273 | 15AH0142a | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-15 | 2015-07-29 | BRYLLE TRADING & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 500369 | Ramon Magsaysay IS | LABRADOR | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-11 | 2015-10-11 | 010414S00240 | 15AH0139 | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-15 | 2015-07-29 | CWME BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101397 | Salomague Sur ES | BUGALLON | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 |  | 010414S00284 | 15AH0175 | 2015-07-16 | 2015-07-20 | 2015-07-31 | 2015-08-13 | 2015-08-27 | CHESTINAN CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 500368 | Urbiztondo IS | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 321110 | A.P. Guevarra IS | BAYAMBANG | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101416 | Balani-Parongking ES | CALASIAO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101535 | Balite ES | MALASIQUI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 010414S00076 | 14AJ0043 | 2014-11-11 |  | 2014-11-25 | 2014-11-28 | 2014-12-03 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300162 | Baloling NHS | MAPANDAN | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-05-08 | 2015-11-30 | 010414S00238 | 15AJ0060 | 2015-06-29 | 2015-07-03 | 2015-07-14 | 2015-07-27 | 2015-08-03 | SHEN CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101418 | Banaoang ES | CALASIAO | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300163 | Banaoang NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15007518.84 |  |  | COMPLETED | 1 | 2016-04-11 |  | 010414S00261 | 15AJ0093 | 2015-08-11 | 2015-08-14 | 2015-08-25 | 2015-10-13 | 2015-10-15 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101536 | Barang ES | MALASIQUI | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-18 |  | 010414S00290 | 15AJ0084 | 2015-08-07 | 2015-08-07 | 2015-08-20 | 2015-09-02 | 2015-09-21 | LXS BUILDERS & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive NHS | CALASIAO | 3 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22552343.62 |  |  | COMPLETED | 1 | 2016-06-12 |  | 010414S00230 | 15AJ0118 | 2015-08-25 | 2015-08-28 | 2015-09-09 | 2015-11-11 | 2015-11-16 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300184 | Calbeg NHS | MALASIQUI | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00231 | 15AJ0077 | 2015-07-29 | 2015-07-31 | 2015-08-11 | 2015-08-18 | 2015-08-24 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 321121 | Catalino D. Cerezo NHS | MALASIQUI | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-05-08 | 2015-12-31 | 010414S00232 | 15AJ0060 | 2015-06-29 | 2015-07-03 | 2015-07-14 | 2015-07-27 | 2015-08-03 | SHEN CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba NHS | SANTA BARBARA | 3 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11177342.5917 |  |  | COMPLETED | 1 | 2016-02-17 |  | 010414S00233 | 15AJ0110 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-11 | 2015-09-21 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101430 | Dinalaoan ES | CALASIAO | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8314965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00289 | 15AJ0078 | 2015-07-29 | 2015-07-31 | 2015-08-11 | 2015-08-18 | 2015-08-24 | RPPARAYNO CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101618 | Golden ES | MAPANDAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4C | 4572048.49 |  |  | COMPLETED | 1 | 2016-02-04 |  | 010414S00286 | 15AJ0079 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-10-06 | 2015-10-08 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300206 | Hermosa NHS | BAYAMBANG | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-17 |  | 010414S00234 | 15AJ0117 | 2015-08-25 | 2015-08-28 | 2015-09-09 | 2015-09-14 | 2015-09-21 | MCB CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101564 | Iba ES | MALASIQUI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 010414S00078 | 14AJ0041 | 2014-11-11 |  | 2014-11-25 | 2014-11-28 | 2014-12-03 | BERSONs CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300210 | Lareglareg NHS | MALASIQUI | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-05-08 | 2015-12-31 | 010414S00235 | 15AJ0060 | 2015-06-29 | 2015-07-03 | 2015-07-14 | 2015-07-27 | 2015-08-03 | SHEN CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300212 | Lokeb Norte NHS | MALASIQUI | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 010414S00236 | 15AJ0071 | 2015-07-22 | 2015-07-24 | 2015-08-04 | 2015-08-12 | 2015-08-17 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101544 | Lokeb Sur ES | MALASIQUI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1 | 2015-01-31 | 2015-01-31 | 010414S00077 | 14AJ0042 | 2014-11-11 |  | 2014-11-25 | 2014-11-28 | 2014-12-03 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 300216 | Lunec NHS | MALASIQUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101547 | Mangan Dampay ES | MALASIQUI | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-24 |  | 010414S00291 | 15AJ0085 | 2015-08-07 | 2015-08-07 | 2015-08-20 | 2015-09-23 | 2015-09-28 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300225 | Matic-Matic NHS | SANTA BARBARA | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6619337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 010414S00251 | 15AJ0070 | 2015-07-22 | 2015-07-24 | 2015-08-04 | 2015-08-12 | 2015-08-17 | LXS BUILDERS & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan NHS | BAYAMBANG | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15197518.84 |  |  | COMPLETED | 1 | 2016-05-13 |  | 010414S00239 | 15AJ0106 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-11-11 | 2015-11-16 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 101278 | Nalsian ES | BAYAMBANG | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-21 |  | 010414S00275 | 15AJ0080 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-21 | 2015-08-25 | BERSONs CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300230 | Olea NHS | MALASIQUI | 3 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22352343.62 |  |  | COMPLETED | 1 | 2016-04-28 |  | 010414S00228 | 15AJ0116 | 2015-08-24 | 2015-08-28 | 2015-09-08 | 2015-09-30 | 2015-10-02 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300237 | Payas NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | COMPLETED | 1 | 2016-03-12 |  | 010414S00241 | 15AJ0092 | 2015-08-11 | 2015-08-14 | 2015-08-24 | 2015-09-08 | 2015-09-15 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 151519 | Potiocan PS | MALASIQUI | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300251 | San Julian NHS | MALASIQUI | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14997518.84 |  |  | COMPLETED | 1 | 2016-03-07 |  | 010414S00242 | 15AJ0091 | 2015-08-11 | 2015-08-14 | 2015-08-25 | 2015-09-03 | 2015-09-09 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300257 | Talospatang NHS | MALASIQUI | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-30 |  | 010414S00243 | 15AJ0102 | 2015-08-14 | 2015-08-17 | 2015-08-28 | 2015-11-27 | 2015-12-03 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan I, Lingayen | 300262 | Tobor NHS | MALASIQUI | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan I, Lingayen | 300266 | Tuliao NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 | 2016-03-21 |  | 010414S00244 | 15AJ0105 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-09 | 2015-09-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10817131.51 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010414S00245 | 15AH0216 | 2015-08-03 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-10-26 | BRYLLE TRADING & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300274 | Anonang NHS | SAN FABIAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10667131.51 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010414S00246 | 15AH0207 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-10-26 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101791 | Babasit ES | MANAOAG | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300280 | Baguinay NHS | MANAOAG | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 | 2015-12-17 |  | 010414S00247 | 15AH0154 | 2015-07-08 | 2015-07-10 | 2015-07-23 | 2015-08-06 | 2015-08-20 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10667131.51 |  |  | COMPLETED | 1 | 2016-04-30 |  | 010414S00248 | 15AH0208 | 2015-07-29 | 2015-07-31 | 2015-08-14 | 2015-08-28 | 2015-11-03 | BET CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500388 | Gueguesangen IS | MANGALDAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8544965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00249 | 15AH0161 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | J.G. GARCIA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300321 | Lobong NHS | SAN JACINTO | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22402343.62 |  |  | COMPLETED | 1 | 2016-07-11 |  | 010414S00217 | 15AH0242 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-01 | 2015-12-15 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101801 | Ma Tulong ES | MANAOAG | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300323 | Mabilao NHS | SAN FABIAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8484965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00160 | 15AH0164 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | J.G. GARCIA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300325 | Manaoag NHS | MANAOAG | 4 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11127342.5917 |  |  | COMPLETED | 1 | 2016-02-22 |  | 010414S00121 | 15AH0174 | 2015-07-16 | 2015-07-20 | 2015-07-31 | 2015-08-13 | 2015-08-27 | BET CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500383 | Mangaldan IS | MANGALDAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8464965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 010414S00122 | 15AH0159 | 2015-07-09 | 2015-07-13 | 2015-07-24 | 2015-08-10 | 2015-08-24 | BET CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500006 | San Fabian IS | SAN FABIAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10817131.51 |  |  | COMPLETED | 1 | 2016-04-30 |  | 010414S00123 | 15AH0217 | 2015-08-03 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-11-03 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300345 | San Fabian NHS | SAN FABIAN | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15117518.84 |  |  | COMPLETED | 1 | 2016-05-30 |  | 010414S00124 | 15AH0197 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-24 | 2015-11-03 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300348 | San Jacinto National High School | SAN JACINTO | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22402343.62 |  |  | COMPLETED | 1 | 2016-07-11 |  | 010414S00125 | 15AH0241 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-01 | 2015-12-15 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102014 | Agat ES | SISON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300271 | Amamperez Agro-Industrial HS | VILLASIS | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 010414S00126 | 15AI0107 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-15 | 2015-07-28 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1 | 2016-02-02 |  | 010414S00295 | 15AI0147 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-07 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300276 | Arboleda NHS | ALCALA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-29 | 010414S00128 | 15AI0139 | 2015-07-06 | 2015-07-07 | 2015-07-20 | 2015-07-23 | 2015-08-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102017 | Artacho ES | SISON | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4C | 4572048.49 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010414S00281 | 15AI0279 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | FRAMECON BUILDERS
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300282 | Baluyot NHS | BAUTISTA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-31 |  | 010414S00129 | 15AI0108 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | ALPHIN TRADING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500377 | Bantay Insik Integrated School | SISON | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-07 |  | 010414S00130 | 15AI0109 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-15 | 2015-07-28 | R.F. FLORES CONSTRUCTION (FORMERLY PATRIOT CONSTRU
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300284 | Barangobong NHS | VILLASIS | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 010414S00120 | 15AI0114 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-16 | 2015-07-29 | RPPARAYNO CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300288 | Bersamin Agro-Industrial HS | ALCALA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-31 |  | 010414S00132 | 15AI0106 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | ALPHIN TRADING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300292 | Bulaoen East NHS | SISON | 5 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00133 | 15AI0160 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101780 | Cabilaoan ES | LAOAC | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 500381 | Calmay IS | LAOAC | 5 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300298 | Capulaan NHS | VILLASIS | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 010414S00134 | 15AI0105 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-15 | 2015-07-28 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22227343.62 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300302 | Coloscaoayan NHS | BAUTISTA | 5 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15032518.84 |  |  | COMPLETED | 1 | 2016-04-10 |  | 010414S00136 | 15AI0274 | 2015-08-12 | 2015-08-13 | 2015-08-26 | 2015-09-01 | 2015-09-14 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500380 | Dilan Integrated School | POZZORUBIO | 5 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10552131.51 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00137 | 15AI0161 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300306 | Don Benito Agro-Industrial HS | POZZORUBIO | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 010414S00138 | 15AI0103 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-15 | 2015-07-28 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300308 | Don Ramon E. Costales MNHS | VILLASIS | 5 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10477131.51 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00139 | 15AI0162 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6379337.6381 |  |  | COMPLETED | 1 | 2016-02-10 | 2015-12-24 | 010414S00140 | 15AI0127 | 2015-06-29 | 2015-06-30 | 2015-07-15 | 2015-07-20 | 2015-07-31 | ALLEN CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500385 | Dungon IS | SISON | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 010414S00131 | 15AI0115 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | ALPHIN TRADING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500004 | Esperanza IS | SISON | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 010414S00115 | 15AI0146 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-07 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300311 | Eugenio P. Perez NHS | POZZORUBIO | 5 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-27 | 010414S00106 | 15AI0119 | 2015-06-28 | 2015-06-29 | 2015-07-13 | 2015-07-20 | 2015-07-31 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101854 | Haway ES | POZZORUBIO | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102032 | Inmalog ES | SISON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00104 | 15AI0140 | 2015-07-06 | 2015-07-07 | 2015-07-20 | 2015-07-23 | 2015-08-04 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300329 | Nama NHS | POZZORUBIO | 5 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10492131.51 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010414S00101 | 15AI0159 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 300337 | Pinmilapil NHS | SISON | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102125 | Puelay ES | VILLASIS | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101785 | Rufino Leal-Torralba Elementary School (CASCALINTA)(Inmanduyan ELementary School) | LAOAC | 5 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 | 2016-05-01 |  | 010414S00283 | 15AI0215 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-21 | 2015-09-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 321203 | San Antonio NHS | SANTO TOMAS | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-23 | 010414S00108 | 15AI0104 | 2015-06-24 | 2015-06-25 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300346 | San Felipe NHS | BINALONAN | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8376965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 010414S00105 | 15AI0149 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-07 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300355 | San Pedro Apartado NHS | ALCALA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 010414S00107 | 15AI0145 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-07 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500375 | Sison Central IS | SISON | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00103 | 15AI0143 | 2015-07-06 | 2015-07-07 | 2015-07-20 | 2015-07-23 | 2015-08-04 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300358 | Sta. Maria NHS, Binalonan | BINALONAN | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | 2016-01-03 |  | 010414S00109 | 15AI0148 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-07 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101789 | Turko ES | LAOAC | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 152004 | Yatyat Annex Elementary School | LAOAC | 5 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-02-04 |  | 010414S00282 | 15AI0263 | 2015-08-10 | 2015-08-11 | 2015-08-25 | 2015-08-28 | 2015-09-08 | 969 CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300273 | Angela Valdez Ramos NHS | ASINGAN | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00110 | 15AI0154 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102078 | Annam ES | UMINGAN | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-10-31 | 010414S00096 | 15AI0216 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-21 | 2015-09-04 | B.Q. CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300281 | Balungao NHS | BALUNGAO | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00111 | 15AI0131 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102079 | Barat ES | UMINGAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101722 | Bobonan Elementary School | ASINGAN | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010414S00280 | 15AI0205 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102080 | Cabalitian ES | UMINGAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300296 | Cacabugaoan NHS | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 010414S00294 | 15AI0112 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-16 | 2015-07-29 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102097 | Cadiz ES | UMINGAN | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 010414S00083 | 14AI0161 | 2014-11-16 | 2014-11-17 | 2014-12-01 | 2014-12-11 | 2014-12-23 | R.F. FLORES CONSTRUCTION (FORMERLY PATRIOT CONSTRU
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102081 | Calitlitan ES | UMINGAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101877 | Camangaan ES | ROSALES | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101893 | Casanicolasan ES | ROSALES | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102099 | Casilan ES | UMINGAN | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-10-31 | 010414S00097 | 15AI0217 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-21 | 2015-09-04 | JL MAXIBUILDERS CORP.
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102102 | Digap-Fulgosino Community School | UMINGAN | 6 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-02 | 2015-11-27 | 010414S00095 | 15AI0211 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-21 | 2015-09-04 | B.Q. CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00113 | 15AI0133 | 2015-07-02 | 2015-07-02 | 2015-07-16 | 2015-07-23 | 2015-08-04 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500005 | Flores Integrated School | SAN MANUEL | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00119 | 15AI0132 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300313 | Flores NHS | UMINGAN | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6409337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00114 | 15AI0151 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-08-03 | 2015-08-14 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300314 | Guiling-Coliling NHS | ROSALES | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00102 | 15AI0158 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | W.J.P. CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101988 | Kulangew ES | SAN NICOLAS | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1092049.6543 |  |  | COMPLETED | 1 | 2015-11-12 | 2015-11-12 | 010414S00094 | 15AI0296 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-01 | 2015-09-14 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300316 | La Paz NHS | UMINGAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00117 | 15AI0135 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 300318 | Lagasit NHS | SAN QUINTIN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102088 | Lubong Elementary School | UMINGAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 500386 | Lumayao Integrated School | SAN QUINTIN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101836 | Luna ES | NATIVIDAD | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102107 | Luna Este ES | UMINGAN | 6 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300324 | Malico NHS | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-26 | 2015-10-26 | 010414S00293 | 15AI0113 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-16 | 2015-07-29 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300327 | Maseil-seil Alo-o NHS | UMINGAN | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-11 | 2015-12-29 | 010414S00181 | 15AI0128 | 2015-06-29 | 2015-06-30 | 2015-07-15 | 2015-07-20 | 2015-07-31 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | SAN MANUEL | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010414S00163 | 15AI0157 | 2015-07-15 | 2015-07-17 | 2015-07-28 | 2015-08-03 | 2015-08-14 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010414S00164 | 15AI0152 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300333 | Panganiban NHS | TAYUG | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010414S00165 | 15AI0126 | 2015-06-29 | 2015-06-30 | 2015-07-15 | 2015-07-20 | 2015-07-31 | MKM MARKETING
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101881 | Pangaoan ES | ROSALES | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102113 | Prado Elementary School | UMINGAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300340 | Robert B. Estrella Memorial NHS | ROSALES | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-19 |  | 010414S00166 | 15AI0137 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300341 | Rosales NHS | ROSALES | 6 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11027342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101896 | Rosales North CS | ROSALES | 6 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8334965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010414S00278 | 15AI0201 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | W.J.P. CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101739 | San Aurelio ES | BALUNGAO | 6 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 3072592.44 |  |  | COMPLETED | 1 | 2016-01-05 |  | 010414S00279 | 15AI0264 | 2015-08-10 | 2015-08-11 | 2015-08-25 | 2015-08-28 | 2015-09-08 | W.J.P. CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300344 | San Aurelio NHS | BALUNGAO | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-09 |  | 010414S00168 | 15AI0153 | 2015-07-15 | 2015-07-16 | 2015-07-28 | 2015-08-03 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500379 | San Felipe IS | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-23 |  | 010414S00169 | 15AI0110 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-16 | 2015-07-29 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300347 | San Isidro NHS | SAN NICOLAS | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-02-16 |  | 010414S00170 | 15AI0129 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 300350 | San Leon NHS | BALUNGAO | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300351 | San Luis NHS | ROSALES | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00172 | 15AI0134 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | W.J.P. CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300353 | San Miguel NHS | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6399337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 010414S00162 | 15AI0150 | 2015-07-14 | 2015-07-15 | 2015-07-27 | 2015-08-03 | 2015-08-14 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300354 | San Nicolas NHS | SAN NICOLAS | 6 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-03-10 |  | 010414S00174 | 15AI0156 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102117 | San Pablo ES | UMINGAN | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-11-06 | 2015-10-31 | 010414S00098 | 15AI0251 | 2015-08-09 | 2015-08-10 | 2015-08-24 | 2015-08-28 | 2015-09-08 | JL MAXIBUILDERS CORP.
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101901 | San Pedro East ES | ROSALES | 6 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300356 | San Quintin NHS | SAN QUINTIN | 6 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22252343.62 |  |  | COMPLETED | 1 | 2016-05-10 |  | 010414S00150 | 15AI0293 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-09-01 | 2015-09-14 | VYRAGUS CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102052 | San Vicente ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-15 | 2015-05-15 | 010414S00082 | 14AI0202 | 2014-12-08 | 2014-12-09 | 2014-12-23 | 2015-01-06 | 2015-01-16 | R.G.TABIN CONST. AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 152009 | Sinabaan ES | UMINGAN | 6 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-15 |  | 010414S00100 | 15AI0210 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-24 | 2015-09-04 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 500384 | Sta. Cruz IS | SANTA MARIA | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 939848.6941 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 500384 | Sta. Cruz IS | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 102092 | Sta. Maria ES | UMINGAN | 6 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300359 | Sta. Maria NHS | SAN NICOLAS | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14937518.84 |  |  | COMPLETED | 1 | 2016-04-10 |  | 010414S00127 | 15AI0277 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 152008 | Sta. Rosa Elementary School | UMINGAN | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1 | 2015-11-06 | 2015-10-31 | 010414S00099 | 15AI0250 | 2015-08-09 | 2015-08-10 | 2015-08-24 | 2015-08-28 | 2015-09-08 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 321219 | Sta.Maria East IS | SANTA MARIA | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00176 | 15AI0136 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Pangasinan II, Binalonan | 101966 | Sto. Domingo ES | SAN MANUEL | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010414S00277 | 15AI0206 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | LEGACY CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11027342.5917 |  |  | COMPLETED | 1 | 2016-11-26 |  | 010414S00177 | 15AI0125 | 2015-06-29 | 2015-06-30 | 2015-07-15 | 2015-07-20 | 2015-07-31 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300364 | Toboy NHS | ASINGAN | 6 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00178 | 15AI0130 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central NHS | UMINGAN | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15077518.84 |  |  | COMPLETED | 1 | 2016-04-14 |  | 010414S00180 | 15AI0276 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | ALCEL CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Carlos City | 300376 | Abanon NHS | SAN CARLOS CITY | 3 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-17 |  | 010414S00152 | 15AJ0111 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-09 | 2015-09-21 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 500059 | Agdao Integrated School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102237 | Aponit Elementary School | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 300377 | Bacnar NHS | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300377 | Bacnar NHS | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102215 | Bolingit Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102255 | Bolosan Caingal Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102216 | Calomboyan Elementary School | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102242 | Candido Marcellano Elementary School | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300379 | Cobol NHS | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-22 |  | 010414S00143 | 15AJ0096 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-10-22 | 2015-10-26 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Carlos City | 300380 | Coliling National High School | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-13 |  | 010414S00144 | 15AJ0100 | 2015-08-14 | 2015-08-17 | 2015-08-28 | 2015-11-11 | 2015-11-16 | CHIARA CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Carlos City | 300381 | Doyong NHS | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-06 |  | 010414S00145 | 15AJ0095 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-11-05 | 2015-11-09 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Carlos City | 500058 | Guelew IS | SAN CARLOS CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 500058 | Guelew IS | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 102245 | Libas Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300382 | Libas NHS | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-14 |  | 010414S00147 | 15AJ0069 | 2015-07-22 | 2015-07-24 | 2015-08-04 | 2015-08-12 | 2015-08-17 | LXS BUILDERS & SUPPLIES
NC 2014 | SHS (2014) | Region I | San Carlos City | 300383 | Lilimasan NHS | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-29 | 2015-10-26 | 010414S00148 | 15AJ0061 | 2015-06-29 | 2015-07-03 | 2015-07-14 | 2015-07-27 | 2015-08-03 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | SHS (2014) | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-11 |  | 010414S00161 | 15AJ0068 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-11 | 2015-08-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Carlos City | 102232 | Malacañang Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300385 | Malacanang NHS | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-01 |  | 010414S00151 | 15AJ0097 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-10-01 | 2015-10-05 | ALCEL CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Carlos City | 102222 | Pangalangan Elementary School | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300389 | Tamayo NHS | SAN CARLOS CITY | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-21 |  | 010414S00153 | 15AJ0094 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-22 | 2015-09-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Carlos City | 300390 | Tandoc NHS | SAN CARLOS CITY | 3 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-20 |  | 010414S00154 | 15AJ0112 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-09-16 | 2015-09-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Carlos City | 102235 | Tarectec Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Fernando City | 300099 | Bangbangolan NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2016-02-08 |  | 010314S00047 | 15AE0122 | 2015-08-13 | 2015-08-14 | 2015-08-26 | 2015-09-03 | 2015-09-14 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-11 |  | 010314S00046 | 15AE0136 | 2015-08-31 | 2015-09-09 | 2015-09-14 | 2015-09-23 | 2015-10-09 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Fernando City | 321001 | La Union NHS - Sacyud Annex | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-28 |  | 010314S00045 | 14AE0003 | 2015-07-17 | 2015-07-28 | 2015-07-31 | 2015-08-12 | 2015-09-02 | E.E. MADAYAG CONSTRUCTION
NC 2014 | SHS (2014) | Region I | San Fernando City | 324102 | San Fernando City SPED High School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-11 |  | 010314S00057 | 15AE0092 | 2015-07-15 | 2015-07-24 | 2015-07-27 | 2015-07-30 | 2015-09-01 | FABRO CONSTRUCTION
NC 2014 | K10 (2014) | Region I | San Fernando City | 324101 | SAN FERNANDO SOUTH CENTRAL INTEGRATED SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | San Fernando City | 324101 | SAN FERNANDO SOUTH CENTRAL INTEGRATED SCHOOL | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102286 | Anonas East ES | CITY OF URDANETA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300392 | Anonas NHS | CITY OF URDANETA | 5 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-22 |  | 010414S00158 | 15AI0169 | 2015-07-27 | 2015-07-28 | 2015-08-10 | 2015-08-14 | 2015-08-26 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102269 | Badipa ES | CITY OF URDANETA | 5 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4A | 28774076.4844 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-08-15 | 010414S00080 | 14AI0203 | 2014-12-16 | 2014-12-17 | 2015-03-27 | 2015-04-22 | 2015-05-05 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2014 | K10 (2014) | Region I | Urdaneta City | 300394 | Badipa NHS | CITY OF URDANETA | 5 | 1 | 4 | 2 UNITS 2STY2CL | 2014 K10 BATCH 3 | 8583799.2188 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102270 | Bolaoen ES | CITY OF URDANETA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102271 | Cabaruan ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 010414S00157 | 15AI0144 | 2015-07-06 | 2015-07-07 | 2015-07-20 | 2015-07-23 | 2015-08-04 | RPPARAYNO CONSTRUCTION
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102288 | Calegu ES | CITY OF URDANETA | 5 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-01 |  | 010414S00276 | 15AI0214 | 2015-08-03 | 2015-08-18 | 2015-08-19 | 2015-08-24 | 2015-09-04 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300397 | Camabu NHS | CITY OF URDANETA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-10 |  | 010414S00156 | 15AI0116 | 2015-06-28 | 2015-06-29 | 2015-07-13 | 2015-07-20 | 2015-07-31 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300398 | Camantiles NHS | CITY OF URDANETA | 5 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-05-18 |  | 010414S00149 | 15AI0168 | 2015-08-20 | 2015-08-24 | 2015-09-07 | 2015-09-11 | 2015-09-22 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Urdaneta City | 500007 | Catablan IS | CITY OF URDANETA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-10 | 2015-12-29 | 010414S00179 | 15AI0118 | 2015-06-28 | 2015-06-29 | 2015-07-13 | 2015-07-20 | 2015-07-31 | 2-R CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102279 | Don Andres Maiquez Memorial School | CITY OF URDANETA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 300402 | Don Antonio Bongolan NHS (San Jose NHS) | CITY OF URDANETA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102281 | Don Clemente Blanco Memorial Elementary School | CITY OF URDANETA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 300403 | Don Mariano Q. Umipig NHS (Nancayasan NHS) | CITY OF URDANETA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300403 | Don Mariano Q. Umipig NHS (Nancayasan NHS) | CITY OF URDANETA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102300 | Lazaga ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region I | Urdaneta City | 102301 | Manan ES | CITY OF URDANETA | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-15 | 2015-03-16 | 010414S00081 | 14AI0201 | 2014-12-09 | 2014-12-10 | 2014-12-22 | 2015-01-06 | 2015-01-16 | RPPARAYNO CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300406 | Nancalobasaan NHS | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-10-25 | 010414S00112 | 15AI0138 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-23 | 2015-08-04 | JHI CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region I | Urdaneta City | 300409 | Pedro T. Orata NHS | CITY OF URDANETA | 5 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-27 | 2015-12-24 | 010414S00116 | 15AI0117 | 2015-06-28 | 2015-06-29 | 2015-07-13 | 2015-07-20 | 2015-07-31 | MKM MARKETING
NC 2014 | K10 (2014) | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5 | 1 | 19 | 3STY15CL & 2STY4CL | 2014 K10 BATCH 4A | 28774076.4844 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region I | Vigan City | 300052 | Ilocos Sur NHS | CITY OF VIGAN (Capital) | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-20 |  | 010214S00045 | 15AC0105 | 2015-09-04 | 2015-09-14 | 2015-09-16 | 2015-09-22 | 2015-09-24 | MBB CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Vigan City | 300088 | Vigan East NHS (Vigan NHS East) | CITY OF VIGAN (Capital) | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-03-21 |  | 010214S00048 | 15AC0103 | 2015-09-04 | 2015-09-14 | 2015-09-16 | 2015-09-22 | 2015-09-24 | VIGAN FORTUNE CONSTRUCTION
NC 2014 | SHS (2014) | Region I | Vigan City | 300089 | Vigan West NHS (Vigan NHS West) | CITY OF VIGAN (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 |  |  | 010214S00053 | 15AC0123 | 2015-11-19 | 2015-11-27 | 2015-12-01
NC 2015 | TECHVOC (2015) | Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2529549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Alaminos City | 101174 | Bolaney ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00098 | 15AG0132 | 2015-09-04 | 2015-09-04 | 2015-09-21 | 2015-10-01 | 2015-10-06 | JONIK TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00041 | 15AG0105 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-21 | MANIMELDS CONSTRUCTION & IRON WORKS
NC 2015 | K10 (2015) | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 010415S00097 | 15AG0130 | 2015-09-04 | 2015-09-05 | 2015-09-21 | 2015-10-01 | 2015-10-06 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2015 | K10 (2015) | Region I | Batac City | 100096 | Hilario Valdez Mem. Elem. School | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010115S00012 | 15AB0060 | 2015-08-06 | 2015-08-10 | 2015-08-21 | 2015-09-08 | 2015-09-18 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2015 | SHS (2015) | Region I | Batac City | 340748 | Proposed Stand-Alone SHS 2 - MMMES | CITY OF BATAC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Dagupan City | 300368 | Dagupan City NHS | Dagupan City | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26822469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Dagupan City | 300368 | Dagupan City NHS | Dagupan City | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26822469.42 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Dagupan City | 500054 | Federico N. Ceralde IS | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 14971327.92 |  |  | COMPLETED | 1 |  |  | 010415S00096 | 15AH0293 | 2015-11-29
NC 2015 | SHS (2015) | Region I | Dagupan City | 300370 | Salapingao NHS | Dagupan City | 4 | 1 |  | 3STY6CL | 2015 ADDITIONAL FUND BATCH 9 | 10267131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2804549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Ilocos Norte | 300014 | Davila NHS | PASUQUIN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 010115S00008 | 15AA0161 | 2015-11-03 | 2015-11-11 | 2015-11-26 | 2015-12-07 | 2015-12-22 | ACCV BUILDERS
NC 2015 | K10 (2015) | Region I | Ilocos Norte | 100235 | Barbar PS | PINILI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 010115S00013 | 15AB0061 | 2015-08-06 | 2015-08-10 | 2015-08-21 | 2015-09-10 | 2015-09-25 | JLP CONSTRUCTION & SUPPLY (FORMERLY: JLP CONSTRUCT
NC 2015 | SHS (2015) | Region I | Ilocos Norte | 320805 | Currimao NHS (Pias-Gaang Campus) | CURRIMAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010115S00009 | 15AB0064 | 2015-08-13 | 2015-08-17 | 2015-08-28 | 2015-09-11 | 2015-10-02 | CURRIMAO CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Ilocos Norte | 300020 | Marcos NHS | MARCOS | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18597268.79 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Ilocos Norte | 320814 | Paoay National High School | PAOAY | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 010115S00004 | 15AB0082 | 2015-09-16 | 2015-09-28 | 2015-09-29 |  |  | RCD GEN. CONTRACTOR & CONSTRUCTION SUPPLY
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100498 | Dacutan PS | MAGSINGAL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00055 | 15AC0107 | 2015-09-09 | 2015-09-17 | 2015-09-21 | 2015-10-02 | 2015-10-13 | 739 BUILDERS
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100648 | Marnay PS | SINAIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 010215S00054 | 15AC0108 | 2015-09-11 | 2015-09-21 | 2015-09-28 | 2015-10-12 | 2015-10-14 | BONICAB BUILDERS
NC 2015 | TECHVOC (2015) | Region I | Ilocos Sur | 300080 | Sinait NHS | SINAIT | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100700 | Ag-agrao ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 010215S00052 | 15AD0151 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-23 | 2015-10-30 | MBB CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100762 | AG-AGUMAN ELEM. SCHOOL | TAGUDIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00050 | 15AD0150 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-23 | 2015-10-30 | CLEOFEL CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Ilocos Sur | 300034 | Amarao NHS | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 010215S00044 | 15AD0154 | 2015-09-29 | 2015-10-13 | 2015-10-14 | 2015-10-27 | 2015-11-17 | PRECIOUS CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 500349 | Ambalayat IS | TAGUDIN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010215S00049 | 15AD0153 | 2015-09-21 | 2015-09-23 | 2015-09-30 | 2015-10-14 | 2015-10-21 | KIDFER CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100767 | Bio ES | TAGUDIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00045 | 15AD0145 | 2015-09-09 | 2015-09-21 | 2015-09-29 | 2015-10-19 | 2015-10-26 | M.A. TEJADA CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100769 | Cabugbugan Comm. Sch. | TAGUDIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00048 | 15AD0147 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-19 | 2015-10-26 | CLEOFEL CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100480 | Malaya ES | CERVANTES | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 010215S00053 | 15AD0143 | 2015-09-09 | 2015-09-21 | 2015-09-29 | 2015-10-12 | 2015-10-20 | MAK-JAY CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Ilocos Sur | 300059 | Nagbukel NHS | NAGBUKEL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 010215S00043 | 15AD0123 | 2015-08-17 | 2015-08-19 | 2015-09-02 | 2015-09-14 | 2015-09-17 | E.E. MADAYAG CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 500347 | Pudoc West Integrated School | TAGUDIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00056 | 15AD0146 | 2015-09-09 | 2015-09-21 | 2015-09-29 | 2015-10-19 | 2015-10-26 | M.A. TEJADA CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100583 | San Elias ES | SIGAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1988606.04 |  |  | COMPLETED | 1 |  |  | 010215S00057 | 15AD0144 | 2015-09-09 | 2015-09-21 | 2015-09-29 | 2015-10-12 | 2015-10-20 | CM-AL CONSTRUCTION AND AGGREGATES
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100779 | San Pedro Comm. Sch. | TAGUDIN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 010215S00047 | 15AD0152 | 2015-09-21 | 2015-10-03 | 2015-10-28 | 2015-11-17 | 2015-11-20 | 739 BUILDERS
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100713 | Silag-Pacang ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00051 | 15AD0149 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-19 | 2015-10-26 | MBB CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Ilocos Sur | 100781 | Tallaoen ES | TAGUDIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010215S00046 | 15AD0148 | 2015-09-16 | 2015-09-28 | 2015-09-30 | 2015-10-23 | 2015-10-30 | CLEOFEL CONSTRUCTION
NC 2015 | SHS (2015) | Region I | La Union | 300097 | Balbalayang NHS | SAN GABRIEL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6394337.6381 |  |  | COMPLETED | 1 |  |  | 010315S00005 | 15AE0144 | 2015-09-09 | 2015-09-10 | 2015-09-22 | 2015-10-02 | 2015-11-25 | J.D. MADRID CONSTRUCTION
NC 2015 | K10 (2015) | Region I | La Union | 100898 | Luzong Sur ES | BANGAR | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 010315S00020 | 15AE0157 | 2015-10-12 | 2015-10-14 | 2015-10-15 | 2015-11-06 | 2015-11-20 | E.E. MADAYAG CONSTRUCTION
NC 2015 | K10 (2015) | Region I | La Union | 101083 | Pisnadan PS | SANTOL | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010315S00021
NC 2015 | SHS (2015) | Region I | La Union | 340825 | Proposed Stand -Alone SHS 4 (San Gabriel CS) | SAN GABRIEL | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | La Union | 300134 | San Francisco NHS | SUDIPEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 010315S00010 | 15AE0006 | 2015-08-31 | 2015-09-02 | 2015-09-14 | 2015-09-22 | 2015-10-19 | E.E. MADAYAG CONSTRUCTION
NC 2015 | SHS (2015) | Region I | La Union | 300091 | Amlang-Nagtagaan NHS | ROSARIO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6469338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | La Union | 300092 | Anduyan NHS | TUBAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6439338 |  |  | COMPLETED | 1 |  |  | 010315S00012 | 0103-15-S-00012(CNTR) | 2015-08-13 | 2015-08-18 | 2015-08-24 | 2015-10-09 | 2015-10-19 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES
NC 2015 | SHS (2015) | Region I | La Union | 500350 | Baay Integrated School | BAGULIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1 |  |  | 010315S00009 | 0103-15-S-00009(CNTR) | 2015-09-24 | 2015-09-30 | 2015-10-05 | 2015-10-15 | 2015-10-28 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2015 | SHS (2015) | Region I | La Union | 300105 | Cambaly NHS | BAGULIN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | COMPLETED | 1 |  |  | 010315S00013 | 0103-15-S-00013(CNTR) | 2015-09-18 | 2015-09-28 | 2015-10-13 | 2015-10-19 | 2015-10-28 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2015 | SHS (2015) | Region I | La Union | 300113 | Don Rufino Olarte NHS | TUBAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010315S00014 | 0103-15-S-00014(CNTR) | 2015-08-14 | 2015-08-27 | 2015-08-28 | 2015-09-14 | 2015-10-19 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2015 | SHS (2015) | Region I | La Union | 300123 | Gusing NHS - Northern Naguilian NHS | NAGUILIAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 010315S00015 | 0103-15-S-00015(CNTR) | 2015-08-14 | 2015-08-24 | 2015-08-28 | 2015-09-09 | 2015-10-21 | E.E. MADAYAG CONSTRUCTION
NC 2015 | SHS (2015) | Region I | La Union | 300138 | San Luis NHS | PUGO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 010315S00019 | 0103-15-S-00019(CNTR) | 2015-10-09 | 2015-10-19 | 2015-10-20 | 2015-10-28 | 2015-11-11 | E.E. MADAYAG CONSTRUCTION
NC 2015 | SHS (2015) | Region I | La Union | 300145 | Sta. Teresa NHS | TUBAO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010315S00016 | 13-AF0046 | 2015-08-14 | 2015-08-26 | 2015-08-27 | 2015-09-18 | 2015-10-21 | MKM MARKETING
NC 2015 | K10 (2015) | Region I | La Union | 101102 | Tococ ES | SANTO TOMAS | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  | 010315S00023 | 0103-15-S-00023(CNTR) | 2015-10-09 | 2015-10-16 | 2015-10-19 | 2015-10-23 | 2015-11-02 | E.E. MADAYAG CONSTRUCTION
NC 2015 | SHS (2015) | Region I | La Union | 321009 | Upper Tumapoc National High School | BURGOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1988606 |  |  | COMPLETED | 1 |  |  | 010315S00017 | 0103-15-S-00017(CNTR) | 2015-09-21 | 2015-09-29 | 2015-10-13 | 2015-10-19 | 2015-10-28 | J.A. OLIVAR ENGINEERING DESIGN, CONSTRUCTION AND S
NC 2015 | SHS (2015) | Region I | Laoag City | 500056 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Laoag City | 300372 | Gabu NHS | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010115S00006 | 15AA0130 | 2015-08-28 | 2015-09-09 | 2015-09-29 | 2015-10-12 | 2015-11-25 | SOLSONA-GANAL CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 101513 | Bacnit IS | Bani | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6369337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00045 | 15AG0106 | 2015-08-05 | 2015-08-05 | 2015-08-19 | 2015-08-24 | 2015-08-27 | SAMANTHA ENTERPRISES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 321124 | Bani East IS | Bani | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6349337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00046 | 15AG107 | 2015-08-05 | 2015-08-05 | 2015-08-19 | 2015-08-24 | 2015-08-27 | JONIK TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300166 | Banog Sur NHS | BANI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010415S00070 | 15AG0120 | 2015-08-16 | 2015-08-17 | 2015-08-25 | 2015-10-06 | 2015-10-09 | SAMANTHA ENTERPRISES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 321126 | Barlo Integrated School | MABINI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101208 | Caniogan ES | ANDA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00095 | 15AG0128 | 2015-09-04 | 2015-09-04 | 2015-09-21 | 2015-10-01 | 2015-10-06 | A.A. BALAOING TRADING AND CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101350 | Gagaban ES | BOLINAO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00094 | 15AG129 | 2015-09-04 | 2015-09-04 | 2015-09-21 | 2015-10-01 | 2015-10-06
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300205 | Garrita NHS | Bani | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00048 | 15AG0108 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-24 | 2015-08-27 | JASA BUILDERS
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 321127 | Gayusan IS | Agno | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6579337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300214 | Luciente II NHS | BOLINAO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1 |  |  | 010415S00069 | 15AG0127 | 2015-08-24 | 2015-08-25 | 2015-09-07 | 2015-10-06 | 2015-10-09 | ROADTECH CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300217 | Macaleeng NHS | ANDA | 1 | 1 | 6 | 3sty6cl | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1 |  |  | 010415S00071 | 15AG0126 | 2015-08-24 | 2015-08-25 | 2015-09-07 | 2015-10-06 | 2015-10-09 | ROADTECH CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300238 | Pilar NHS | Bolinao | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8354965.051 |  |  | COMPLETED | 1 |  |  | 010415S00053 | 15AG0109 | 2015-08-05 | 2015-08-06 | 2015-08-19 | 2015-08-24 | 2015-08-27 | ALCEL CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300244 | Quinaoayanan NHS | Bani | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00057 | 15AG0114 | 2015-08-11 | 2015-08-12 | 2015-08-25 | 2015-08-28 | 2015-09-03 | JONIK TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300245 | Ranao NHS | Bani | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00056 | 15AG0104 | 2015-07-30 | 2015-08-12 | 2015-08-13 | 2015-08-18 | 2015-08-24 | SANRENZ CONSTRUCTION SERVICES AND SUPPLY
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300261 | Tiep NHS | BANI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010415S00074 | 15AG0121 | 2015-08-16 | 2015-08-17 | 2015-08-25 | 2015-10-06 | 2015-10-09 | JONIK TRADING & CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101373 | Asuncion ES | BUGALLON | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00092 | 15AH0282 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | ALPHIN TRADING & CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101673 | Balangay ES | URBIZTONDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00079 | 15AH0281 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | J.G. HIDALGO JR. CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300170 | Bayoyong NHS | BASISTA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1 |  |  | 010415S00059 | 15AH0286 | 2015-11-05 | 2015-11-12 | 2015-11-24 | 2015-12-07 | 2015-12-15 | ALCEL CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300232 | Binmaley SOF (Pangasinan COF) | BINMALEY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region I | Pangasinan I, Lingayen | 300232 | Binmaley SOF (Pangasinan COF) | BINMALEY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 300174 | Bogtong NHS | MANGATAREM | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 010415S00099 | 15AH0284 | 2015-11-05 | 2015-11-12 | 2015-11-24 | 2015-12-07 | 2015-12-15 | ZOTA TRADING & CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101375 | Bugallon IS | BUGALLON | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00091 | 15AH0273 | 2015-11-01 | 2015-11-05 | 2015-11-17 | 2015-11-24 | 2015-12-15 | CWME BUILDERS & SUPPLY
NC 2015 | TECHVOC (2015) | Region I | Pangasinan I, Lingayen | 321107 | Bugallon IS | BUGALLON | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101597 | Cabarabuan ES | MANGATAREM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00090 | 15AH0278 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | PRODEL CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101689 | Don Pio ES | URBIZTONDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00088 | 15AH0277 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | PRODEL CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101158 | Dona Catalina ES | AGUILAR | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00093 | 15AH0274 | 2015-11-01 | 2015-11-05 | 2015-11-17 | 2015-11-24 | 2015-12-15 | SARGASSO CONSTRUCTION & DEVELOPMENT CORP.
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300200 | Dumpay National High School | BASISTA | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22502344 |  |  | COMPLETED | 1 |  |  | 010415S00067 | 15AH0287 | 2015-11-05 | 2015-11-12 | 2015-11-24 | 2015-12-07 | 2015-12-15 | ALCEL CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region I | Pangasinan I, Lingayen | 300202 | Enrico T. Prado NHS | AGUILAR | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 010415S00106 | 15AH0251 | 2015-09-21 | 2015-09-24 | 2015-10-06 | 2015-10-14 | 2015-10-21 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | Bugallon | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 010415S00054 | 15AH0226 | 2015-08-11 | 2015-08-14 | 2015-08-25 | 2015-09-07 | 2015-09-14 | LEGACY CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300209 | Labrador NHS | Labrador | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 010415S00049 | 15AH0227 | 2015-08-11 | 2015-08-14 | 2015-08-25 | 2015-09-07 | 2015-12-15 | ALCEL CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300222 | Mangatarem NHS | MANGATAREM | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8434965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region I | Pangasinan I, Lingayen | 300222 | Mangatarem NHS | MANGATAREM | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300227 | Naguilayan NHS | MANGATAREM | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan NHS | Lingayen | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | COMPLETED | 1 |  |  | 010415S00058 | 15AH0240 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-01 | 2015-12-15 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101691 | Salavante ES | URBIZTONDO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00089 | 15AH0276 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | ALPHIN TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 500368 | URBIZTONDO INTEGRATED SCHOOL | Urbiztondo | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo NHS | Urbiztondo | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 010415S00050 | 15AH0223 | 2015-08-11 | 2015-08-14 | 2015-08-25 | 2015-09-07 | 2015-09-14 | T.J. VELASCO CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300156 | Aliaga NHS | MALASIQUI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010415S00065 | 15AJ0107 | 2015-08-19 | 2015-08-21 | 2015-09-02 | 2015-10-08 | 2015-10-12 | LXS BUILDERS & SUPPLIES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300168 | Bayambang NHS (Bayambang) | BAYAMBANG | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26842469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300168 | Bayambang NHS (Bayambang) | BAYAMBANG | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26842469.42 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 300178 | Buenlag NHS | CALASIAO | 3 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | COMPLETED | 1 |  |  | 010415S00100 | 15AJ0088 | 2015-08-10 | 2015-08-10 | 2015-08-24 | 2015-11-11 | 2015-11-16 | MKM MARKETING
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300186 | Canan NHS | MALASIQUI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6569338 |  |  | COMPLETED | 1 |  |  | 010415S00073 | 15AJ0089 | 2015-08-10 | 2015-08-10 | 2015-08-24 | 2015-09-18 | 2015-09-23 | JASA BUILDERS
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00024 | 15AJ0073 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-17 | 2015-08-20 | LXS BUILDERS & SUPPLIES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300213 | Lokeb Sur NHS | MALASIQUI | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00022 | 15AJ0074 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-17 | 2015-08-20 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui NHS | MALASIQUI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 010415S00025 | 15AJ0082 | 2015-07-30 | 2015-08-03 | 2015-08-14 | 2015-08-20 | 2015-08-25 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2015 | TECHVOC (2015) | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2729549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300226 | Minien NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 15047519 |  |  | COMPLETED | 1 |  |  | 010415S00061 | 15AJ0104 | 2015-08-17 | 2015-08-21 | 2015-09-01 | 2015-09-22 | 2015-09-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300229 | Nancapian NHS | MALASIQUI | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15371328 |  |  | COMPLETED | 1 |  |  | 010415S00064 | 15AJ0121 | 2015-08-26 | 2015-08-28 | 2015-09-10 | 2015-10-26 | 2015-10-28 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 321101 | Palapar NHS | MALASIQUI | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15271328 |  |  | COMPLETED | 1 |  |  | 010415S00063 | 15AJ0120 | 2015-08-26 | 2015-08-28 | 2015-09-10 | 2015-09-22 | 2015-09-24 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 300242 | Primicias NHS | MAPANDAN | 3 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | COMPLETED | 1 |  |  | 010415S00101 | 15AJ0087 | 2015-08-10 | 2015-08-10 | 2015-08-24 | 2015-11-05 | 2015-11-09 | MKM MARKETING
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300254 | Sanlibo NHS | BAYAMBANG | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1 |  |  | 010415S00066 | 15AJ0108 | 2015-08-19 | 2015-08-21 | 2015-09-02 | 2015-10-06 | 2015-10-08 | J.D. MADRID CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan I, Lingayen | 101439 | Songkoy ES | CALASIAO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00077 | 15AJ0130 | 2015-10-14 | 2015-10-16 | 2015-10-27 | 2015-11-23 | 2015-11-25 | JASA BUILDERS
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300259 | Tanolong NHS | BAYAMBANG | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 010415S00072 | 15AJ0090 | 2015-08-10 | 2015-08-10 | 2015-08-24 | 2015-10-06 | 2015-10-08 | JASA BUILDERS
NC 2015 | SHS (2015) | Region I | Pangasinan I, Lingayen | 300262 | Tobor NHS | MALASIQUI | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10567132 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 101907 | Gumot ES | SAN FABIAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010415S00086 | 15AH0280 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-29 | BET CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 101798 | Lelemaan ES | MANAOAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 010415S00087 | 15AH0279 | 2015-11-02 | 2015-11-05 | 2015-11-19 | 2015-12-02 | 2015-12-15 | BET CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300326 | Mangaldan NHS | MANGALDAN | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26752469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300326 | Mangaldan NHS | MANGALDAN | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26752469.42 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region I | Pangasinan II, Binalonan | 300326 | Mangaldan NHS | MANGALDAN | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 101930 | Palapad ES | SAN FABIAN | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 010415S00085 | 15AH0292 | 2015-11-29
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300279 | Alejandro F. Oligan HS (Asan Sur NHS) | SISON | 5 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 010415S00103 | 15AI0302 | 2015-08-20 | 2015-08-24 | 2015-09-07 | 2015-09-28 | 2015-10-09 | J.S. LIM CONSTRUCTION & TRADING (FORMERLY:J.S.LIM
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300278 | Artacho NHS | SISON | 5 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 010415S00104 | 15AI0303 | 2015-08-20 | 2015-08-24 | 2015-09-07 | 2015-09-28 | 2015-10-09 | J.S. LIM CONSTRUCTION & TRADING (FORMERLY:J.S.LIM
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300286 | Bautista NHS | BAUTISTA | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 010415S00028 | 15AI0208 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-24 | 2015-09-04 | A.M.P. CONSTRUCTION
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 010415S00029 | 15AI0209 | 2015-08-03 | 2015-08-04 | 2015-08-18 | 2015-08-24 | 2015-09-04 | FRAMECON BUILDERS
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300290 | Bobonan NHS | POZORRUBIO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00023 | 15AI0278 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | A.M.P. CONSTRUCTION
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 321218 | Castusu IS | LAOAC | 5 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 7 | 22162344 |  |  | COMPLETED | 1 |  |  | 010415S00102 | 15AI0292 | 2015-08-13 | 2015-08-14 | 2015-08-27 | 2015-10-12 | 2015-10-23 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION | No Remarks
NC 2015 | TECHVOC (2015) | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2504549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 500380 | Dilan Integrated School | POZZORUBIO | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1 |  |  | 010415S00084 | 15AI0280 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-09-01 | 2015-09-14 | R.F. FLORES CONSTRUCTION (FORMERLY PATRIOT CONSTRU
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 102057 | Doña Aurea ES | SANTO TOMAS | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1948606.04 |  |  | COMPLETED | 1 |  |  | 010415S00082 | 15AI0287 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | MKM MARKETING
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22402343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN | 5 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300332 | Palguyod NHS | POZORRUBIO | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00035 | 15AI0204 | 2015-08-02 | 2015-08-03 | 2015-08-17 | 2015-08-24 | 2015-09-04 | R.G.TABIN CONST. AND SUPPLY
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 102034 | Pilawan ES | SISON | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00083 | 15AI0281 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | R.F. FLORES CONSTRUCTION (FORMERLY PATRIOT CONSTRU
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300366 | Unzad NHS | VILLASIS | 5 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6399337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00031 | 15AI0283 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | 2-R CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 102124 | West Poblacion ES | VILLASIS | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00081 | 15AI0282 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | JHI CONSTRUCTION & SUPPLY
NC 2015 | TECHVOC (2015) | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2579549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 500386 | Lumayao Integrated School |  | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 102112 | Pemienta Elementary School | UMINGAN | 6 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00078 | 15AI0289 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | R.G.TABIN CONST. AND SUPPLY
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 102142 | Pugaro ES | BALUNGAO | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 010415S00076 | 15AI0286 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | MKM MARKETING
NC 2015 | TECHVOC (2015) | Region I | Pangasinan II, Binalonan | 300341 | Rosales NHS | ROSALES | 6 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2579549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | Pangasinan II, Binalonan | 101742 | San Leon ES | BALUNGAO | 6 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1 |  |  | 010415S00080 | 15AI0285 | 2015-08-12 | 2015-08-14 | 2015-08-26 | 2015-08-28 | 2015-09-14 | R.A. MATIAS CONSTRUCTION AND DEVELOPERS
NC 2015 | SHS (2015) | Region I | Pangasinan II, Binalonan | 300350 | San Leon NHS | BALUNGAO | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | San Carlos City | 300386 | Pangalangan NHS | SAN CARLOS CITY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | COMPLETED | 1 |  |  | 010415S00060 | 15AJ0122 | 2015-08-26 | 2015-08-28 | 2015-09-10 | 2015-10-12 | 2015-10-14 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;l. Agr'l. Sch. | SAN CARLOS CITY | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 010415S00038 | 15AJ0086 | 2015-08-07 | 2015-08-07 | 2015-08-20 | 2015-09-08 | 2015-09-10 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2015 | SHS (2015) | Region I | San Carlos City | 500057 | Tarece Integrated School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 010415S00034 | 15AJ0072 | 2015-07-23 | 2015-07-24 | 2015-08-06 | 2015-08-17 | 2015-08-20 | AQUINO-DELA CRUZ ENGINEERING & CONSTRUCTION
NC 2015 | SHS (2015) | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22227343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22227343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region I | San Fernando City | 101031 | Pao ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 010315S00022
NC 2015 | TECHVOC (2015) | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2016 | SHS | Region I | Alaminos City | 300155 | Alaminos City Nhs | City Of Alaminos | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62505780.54 |  |  | Completed | 1 | [7 empty] | 2016-06-17 |  | JANUARY 28, 2017
NC 2016 | SHS | Region I | Alaminos City | 300155 | Alaminos City Nhs | City Of Alaminos | 1 |  | 16 | 4STY8CL | BATCH 5 CL | 30295037.68 |  |  | Completed | 1 | [7 empty] | 2016-06-17 |  | DECEMBER 14, 2016
NC 2016 | SHS | Region I | Alaminos City | 300208 | Inerangan Nhs | City Of Alaminos | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 | [7 empty] | 2016-05-16 |  | JANUARY 17, 2017
NC 2016 | SHS | Region I | Alaminos City | 300253 | San Vicente Nhs | City Of Alaminos | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12771310.09 |  |  | Completed | 1 | [7 empty] | 2017-05-26 |  | JANUARY 20, 2017
NC 2016 | TECHVOC | Region I | Alaminos City | 300253 | San Vicente Nhs | City Of Alaminos | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2430000 |  |  | Completed | 1 | [7 empty] | 2016-06-22 |  | DECEMBER 19, 2016
NC 2016 | SHS | Region I | Alaminos City | 300260 | Telbang Nhs | City Of Alaminos | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15121327.92 |  |  | Completed | 1 | [7 empty] | 2016-06-22 |  | SEPTEMBER 19, 2016
NC 2016 | SHS | Region I | Batac City | 300005 | Batac National High School | City Of Batac | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22652343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Batac City | 300005 | Batac National High School | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Batac City | 320803 | Batac Nhs (Payao Campus) | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region I | Batac City | 320804 | Batac Nhs (Poblacion Campus) | City Of Batac | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region I | Batac City | 100092 | Bil-Loca Es | City Of Batac | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6936271.4019 |  |  | Completed | 1
NC 2016 | SHS | Region I | Batac City | 300012 | Crispina Marcos Valdez Nhs | City Of Batac | 2 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Batac City | 300012 | Crispina Marcos Valdez Nhs | City Of Batac | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Candon City | 300047 | Candon City High School | City Of Candon | 2 | 1 | 12 | 2STY12CL | BATCH 3 CL | 14724000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Candon City | 300044 | Candon National High School | Candon City | 2 | 1 | 40 | 4STY20CL | BATCH 1 CL | 62305780.54 |  |  | Completed | 1
NC 2016 | SHS | Region I | Candon City | 300044 | Candon National High School | Candon City | 2 |  | 4 | 2STY4CL | BATCH 1 CL | 6332000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | City Of Candon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2770000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Candon City | 300083 | Sto. Tomas National High School | City Of Candon | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15122000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Dagupan City | 305502 | Federico N. Ceralde Is | Dagupan City | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15171327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Dagupan City | 500055 | Pugaro Is | Dagupan City | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15221327.92 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100043 | Abaca Es | Bangui | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 300001 | Adams National High School | Adams | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469337.6381 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300002 | Bacarra Nchs | Bacarra | 1 | 1 | 32 | 4STY32CL | BATCH 1 CL | 44532220.04 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300002 | Bacarra Nchs | Bacarra | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2804549.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320801 | Banban Nhs | Bangui | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100047 | Bangui Ces | Bangui | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320802 | Bangui Nhs (Lanao Campus) | Bangui | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | Burgos | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25542620.18 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300007 | Cadaratan National High School | Bacarra | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300009 | Carasi Nhs | Carasi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2313627.8 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 300014 | Davila National High School | Pasuquin | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300017 | Dumalneg Nhs | Dumalneg | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300017 | Dumalneg Nhs | Dumalneg | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 320827 | Florentino Camaquin Integrated School | Vintar | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320827 | Florentino Camaquin Integrated School | Vintar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | Pasuquin | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | Pasuquin | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320821 | Isic-Isic Nhs | Vintar | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1914740.174 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300019 | Luzong Nhs | Pagudpud | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12821310.093 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300024 | Pagudpud Nhs | Pagudpud | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12821310.093 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300024 | Pagudpud Nhs | Pagudpud | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2288627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320819 | Pallas Integrated School | Vintar | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10952342.5917 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320825 | Pandan Is | Sarrat | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | Pasuquin | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300016 | Piddig National High School | Piddig | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.093 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300016 | Piddig National High School | Piddig | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100303 | Sagpat Es | Vintar | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320822 | Salpad Integrated School | Vintar | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 150009 | San Pedro Elementary School | Sarrat | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300029 | Sarrat National High School | Sarrat | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300029 | Sarrat National High School | Sarrat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320816 | Sta. Rosa National High School | Sarrat | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320816 | Sta. Rosa National High School | Sarrat | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300031 | Vintar Nhs | Vintar | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.6381 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300031 | Vintar Nhs | Vintar | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2313627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon Nhs | Nueva Era | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100025 | Badoc North Central School | Badoc | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300004 | Banna National High School | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 320815 | Bingao National High School | San Nicolas | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13217082.76 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320815 | Bingao National High School | San Nicolas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300008 | Caestebanan Nhs | Banna (Espiritu) | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15221327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300008 | Caestebanan Nhs | Banna (Espiritu) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2708700 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320826 | Caraitan Integrated School | Badoc | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8914965.05 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300010 | Caribquib Nhs | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300011 | Catagtaguen Nhs | Banna (Espiritu) | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300011 | Catagtaguen Nhs | Banna (Espiritu) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300013 | Currimao Nhs | Currimao | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320805 | Currimao Nhs (Pias-Gaang Campus) | Currimao | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 24002343.62 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100120 | Dingras Central Es | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300015 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs | Dingras | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 300015 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs | Dingras | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320806 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs (Barong Campus) | Dingras | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320808 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs (San Marcos Campus) | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 320809 | Dingras Nhs/Lt. Edgar Foz Mem. Nhs- (Sulquiano Campus) | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100147 | Ferdinand Es | Marcos | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100031 | Lasien School | Badoc | 2 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2790828.12 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320823 | Malaguip Integrated School | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300020 | Marcos Nhs | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320811 | Marcos Nhs (Agunit Campus) | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320812 | Marcos Nhs (Santiago Campus) | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320812 | Marcos Nhs (Santiago Campus) | Marcos | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 150003 | Nagbacalan West Elelementary School | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300021 | Nagrebcan Nhs | Badoc | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | Nueva Era | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938600 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 300022 | Nueva Era National High School | Nueva Era | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13217082.76 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300023 | Pagsanahan Nhs | Badoc | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300025 | Paoay Lake Nhs | Paoay | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320814 | Paoay National High School | Paoay | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300027 | Pinili Nhs | Pinili | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11402342.59 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320824 | Sacritan Integrated School | Pinili | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320807 | San Marcelino National High School | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300028 | San Nicolas Nhs | San Nicolas | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 300030 | Solsona National High School, Maananteng Campus | Solsona | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 24002343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320817 | Solsona Nhs (Bagbag Campus) | Solsona | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320818 | Solsona Nhs (Talugtog Campus) | Solsona | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320818 | Solsona Nhs (Talugtog Campus) | Solsona | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320810 | Suyo National High School | Dingras | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Norte | 320810 | Suyo National High School | Dingras | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2263627.8 |  |  | Completed | 1
NC 2016 | K10 | Region I | Ilocos Norte | 100041 | Turod Es | Badoc | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Norte | 320828 | Uguis Integrated School | Nueva Era | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6329337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300045 | Caoayan Nhs | Caoayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300057 | Magsingal Nhs | Magsingal | 1 | 1 | 8 | 2STY8CL | BATCH 13 CL | 11950076.849 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300058 | Manzante Nhs | Magsingal | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300035 | San Juan Nhs | San Juan (Lapog) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2497016.25 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 500349 | Ambalayat Is | Tagudin | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300041 | Burgos Nhs | Burgos | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300050 | Dinaratan National High School | Salcedo (Baugen) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2515000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300063 | Narvacan Nat'L. Central Hs | Narvacan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300063 | Narvacan Nat'L. Central Hs | Narvacan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300070 | Quirino Nhs | Quirino (Angkaki) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2530000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300077 | Santa Maria Nhs | Santa Maria | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300036 | Sugpon Nhs | Sugpon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2510000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300085 | Suyo Nhs | Suyo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Ilocos Sur | 300086 | Tagudin Nhs | Tagudin | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Ilocos Sur | 300086 | Tagudin Nhs | Tagudin | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 | [9 empty] | 739 Builders
NC 2016 | SHS | Region I | Ilocos Sur | 300072 | Teodoro Hernaez Nhs | Santa Lucia | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22302343.62 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 300114 | Doña Francisca Lacsamana De Ortega Memorial National High School | Bangar | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22850000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 321018 | Luna National Vocational High School | Luna | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300120 | Luna Nhs | Luna | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22850000 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 101109 | Old Sudipen Es | Sudipen | 1 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1814740.174 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 101071 | San Juan Ces | San Juan | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 101114 | Sudipen Central School | Sudipen | 1 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1814740.174 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300093 | Aringay Nhs | Aringay | 2 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15150000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300094 | Baccuit Nhs | Bauang | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300105 | Cambaly Nhs | Bagulin | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 7450000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 321020 | Casilagan Integrated School | Bauang | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300109 | Damortis Nhs | Santo Tomas | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15750000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 321022 | Daramuangan Integrated School | Naguilian | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300130 | Don Eufemio F. Eriguel Mnhs | Agoo | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300112 | Don Eulogio De Guzman Mnhs | Bauang | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 300122 | Naguilian National Hs | Naguilian | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22650000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300133 | Rosario Integrated School | Rosario | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300138 | San Luis Nhs | Pugo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6850000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union |  | Shs In Aringay, La Union | Aringay | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22317774.775 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union |  | Shs In Naguilian, La Union | Naguilian | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22650000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300150 | Tagudtud Nhs | Bagulin | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9500000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300151 | Tanglag Nhs | Rosario | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1
NC 2016 | K10 | Region I | La Union | 300152 | Tubao National High School | Tubao | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15650000 |  |  | Completed | 1
NC 2016 | SHS | Region I | La Union | 300153 | Wenceslao National Hs | Caba | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6800000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Laoag City | 305602 | Balatong Integrated School | Laoag City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 102189 | Darayday Es | Laoag City (Capital) | 1 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1012049.6543 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300372 | Gabu Nhs | Laoag City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300373 | Ilocos Norte College Of Arts & Trades | Laoag City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300373 | Ilocos Norte College Of Arts & Trades | Laoag City (Capital) | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 300374 | Ilocos Norte Nhs | Laoag City (Capital) | 1 |  | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region I | Laoag City | 305601 | Ilocos Norte Nhs - Caaoacan Annex | Laoag City (Capital) | 1 | 1 | 6 | 1STY6CL | BATCH 5 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | SHS | Region I | Laoag City | 300375 | Ilocos Norte Regional School Of Fisheries | Laoag City (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.051 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Laoag City | 300375 | Ilocos Norte Regional School Of Fisheries | Laoag City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2363000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 321131 | Anda Integrated School | Anda | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0050 | [5 empty] | 2016-05-13 | ALCEL CONSTRUCTION
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 321106 | Bacnit Integrated School | Mabini | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0049 | [5 empty] | 2016-05-13 | CASIPIT CONSTRUCTION & SUPPLY
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300161 | Balingasay Nhs | Bolinao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0087 | [5 empty] | 2015-08-09 | JONIK TRADING & CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321126 | Barlo Integrated School | Mabini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300169 | Bayambang Nhs (Infanta) | Infanta | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0051 | [5 empty] | 2016-05-13 | CASIPIT CONSTRUCTION & SUPPLY
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 321117 | Bolinao Integrated School | Bolinao | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0056 | [5 empty] | 2016-05-13 | ALCEL CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300179 | Burgos Nhs | Burgos | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0059 | [5 empty] | 2016-05-13 | ALCEL CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300180 | Cabanaetan Nhs | Mabini | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0057 | [5 empty] | 2016-05-13 | ALCEL CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300189 | Cato Nhs | Infanta | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321111 | Catubig Integrated School | Bolinao | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0086 | [5 empty] | 2016-08-09 | JONIK TRADING & CONSTRUCTION
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300201 | Eguia National High School | Dasol | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AG0053 | [5 empty] | 2016-05-13 | JONIK TRADING & CONSTRUCTION
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 321127 | Gayusan Integrated School | Agno | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0055 | [5 empty] | 2016-05-13 | BERSONs CONSTRUCTION & TRADING
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321109 | Liwa Liwa Integrated School | Bolinao | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0075 | [5 empty] | 2016-05-13 | ALCEL CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300215 | Luna National High School | Bolinao | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0085 | [5 empty] | 2016-08-09 | SAMANTHA ENTERPRISES
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300221 | Malimpin Nhs | Dasol | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | 16AG0054 | [5 empty] | 2016-05-13 | JASA BUILDERS
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321104 | Pangascasan Integrated School | Sual | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0052 | [5 empty] | 2016-05-13 | JONIK TRADING & CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300255 | Sual National High School | Sual | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AG0083 | [6 empty] | R.A.Matias
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321108 | Tupa Integrated School | Bolinao | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | 16AG0084 | [6 empty] | R.A.Matias
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | Aguilar | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 321128 | Aguilar Integrated School | Aguilar | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 500374 | Ambayat Is | Aguilar | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300167 | Basista Nhs | Basista | 2 | 1 | 32 | 4STY16CL | BATCH 3 CL | 53404938.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300232 | Binmaley Sof (Pangasinan Cof) | Binmaley | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321107 | Bugallon Is | Bugallon | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 321107 | Bugallon Is | Bugallon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321113 | Dalanguiring Is | Urbiztondo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 321114 | Domalandan Center Is | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300199 | Dulag National High School | Binmaley | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2460000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300202 | Enrico T. Prado Nhs | Aguilar | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300203 | Estanza Nhs | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300204 | Galarin National High School | Urbiztondo | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300209 | Labrador Nhs | Labrador | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300209 | Labrador Nhs | Labrador | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300218 | Macarang National High School | Mangatarem | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 101377 | Magsaysay Elementary School | Bugallon | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321118 | Malawa Is | Lingayen (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300222 | Mangatarem Nhs | Mangatarem | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300222 | Mangatarem Nhs | Mangatarem | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 321132 | Mapita Integrated School | Aguilar | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1864740.17 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan Sat | Lingayen (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300241 | Polong National High School | Bugallon | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300247 | Real National High School | Urbiztondo | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300248 | Salomague Nhs | Bugallon | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321115 | Urbiztondo Integrated School | Urbiztondo | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 321115 | Urbiztondo Integrated School | Urbiztondo | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300168 | Bayambang Nhs (Bayambang) | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300176 | Botao Nhs | Santa Barbara | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300177 | Bued National High School | Calasiao | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300177 | Bued National High School | Calasiao | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300183 | Calasiao Comprehensive Nhs | Calasiao | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28007601.243 |  |  | Completed | 1 |  |  | 16AJ0064 | [6 empty] | T.J VELASCO CONSTRUCTION & SUPPLY
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | 16AJ0065 | [6 empty] | CAD CONSTRUCTION
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 |  | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | 16AJ0066 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba Nhs | Santa Barbara | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300197 | Don Pedro National High School | Malasiqui | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300197 | Don Pedro National High School | Malasiqui | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300216 | Lunec Nhs | Malasiqui | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui Nhs | Malasiqui | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300220 | Malasiqui Nhs | Malasiqui | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | Mapandan | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300225 | Matic-Matic Nhs | Santa Barbara | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan Nhs | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | Bayambang | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | 16AJ0061 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES
NC 2016 | K10 | Region I | Pangasinan I, Lingayen | 300263 | Tococ National High School | Bayambang | 3 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | 16AJ0059 | [6 empty] | KENWOOD CONSTRUCTION ENTERPRISES
NC 2016 | SHS | Region I | Pangasinan I, Lingayen | 300265 | Torres Nhs | Mapandan | 3 | 1 | 6 | 3STY6CL | BATCH 11 CL | 10417131.51 |  |  | Completed | 1 |  |  | 16AJ0060 | [6 empty] | ORIENTAL SALES CENTER & CONTRACTOR
NC 2016 | TECHVOC | Region I | Pangasinan I, Lingayen | 300265 | Torres Nhs | Mapandan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300274 | Anonang Nhs | San Fabian | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300280 | Baguinay Nhs | Manaoag | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 152001 | Bisbisocol Es | San Fabian | 4 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1135000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321220 | Gueguesangen Is | Mangaldan | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300323 | Mabilao Nhs | San Fabian | 4 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300325 | Manaoag Nhs | Manaoag | 4 | 1 | 60 | 4STY20CL | BATCH 9 CL | 93308670.81 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300325 | Manaoag Nhs | Manaoag | 4 |  | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 500383 | Mangaldan Is | Mangaldan | 4 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300326 | Mangaldan Nhs | Mangaldan | 4 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300326 | Mangaldan Nhs | Mangaldan | 4 |  | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300315 | San Fabian Integrated School | San Fabian | 4 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300345 | San Fabian Nhs | San Fabian | 4 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300345 | San Fabian Nhs | San Fabian | 4 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300348 | San Jacinto National High School | San Jacinto | 4 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300271 | Amamperez Agro-Industrial Hs | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300275 | Antonio P. Villar National High School | Santo Tomas | 5 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300276 | Arboleda Nhs | Alcala | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321204 | Bantay Insik Integrated School | Sison | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan Ii, Binalonan | 321204 | Bantay Insik Integrated School | Sison | 5 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300284 | Barangobong Nhs | Villasis | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300286 | Bautista Nhs | Bautista | 5 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300286 | Bautista Nhs | Bautista | 5 |  | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300287 | Benigno V. Aldana Nhs | Pozzorubio | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300301 | Cipriano P. Primicias Nhs | Alcala | 5 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 |  | 16 | 4STY16CL | BATCH 9 CL | 24047222.478 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 |  | 8 | 4STY8CL | BATCH 9 CL | 13913507.9237 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300308 | Don Ramon E. Costales Mnhs | Villasis | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321205 | Don Valentin Torres Integrated School | Sison | 5 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300311 | Eugenio P. Perez Nhs | Pozzorubio | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300307 | Juan G. Macaraeg Nhs | Binalonan | 5 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300334 | Piaz National High School | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321203 | San Antonio Nhs | Santo Tomas | 5 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300346 | San Felipe National High School | Binalonan | 5 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 500375 | Sison Central Is | Sison | 5 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300362 | Sumabnit National High School | Binalonan | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300366 | Unzad Nhs | Villasis | 5 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101887 | Acop Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300273 | Angela Valdez Ramos Nhs | Asingan | 6 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan Ii, Binalonan | 300273 | Angela Valdez Ramos Nhs | Asingan | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101729 | Balungao Cs | Balungao | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300281 | Balungao Nhs | Balungao | 6 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102094 | Bantug Es | Umingan | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102095 | Baracbac Elementary School | Umingan | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300283 | Baracbac Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102002 | Cabalaoangan Es | San Quintin | 6 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12898000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101876 | Cabalaoangan Es | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101969 | Cabayawasan Es | San Nicolas | 6 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1221000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300296 | Cacabugaoan Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101710 | Calepaan Comm. Sch. | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101877 | Camangaan Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101891 | Capitan Tomas Pine Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101730 | Capulaan Es | Balungao | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101892 | Carmay Elementary School | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101878 | Carmen Elementary School | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102098 | Carosalesan Es | Umingan | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300303 | Dalumpinas Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 152007 | Decreto Community School | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101714 | Domanpot Es | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6473000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101714 | Domanpot Es | Asingan | 6 |  | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102004 | Don Luis Domingo Sr. Es | San Quintin | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102105 | Don Montano Elementary School | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101987 | East Central School | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300309 | Eastern Pangasinan Agricultural College | Santa Maria | 6 | 1 | 16 | 2STY8CL | BATCH 13 CL | 21970000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300309 | Eastern Pangasinan Agricultural College | Santa Maria | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102070 | Evangelista Es | Tayug | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 |  | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300312 | Flores Integrated School | San Manuel | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300313 | Flores Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102005 | Gonzalo Es | San Quintin | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300314 | Guiling-Coliling Nhs | Rosales | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101953 | Juan C. Laya Memorial School | San Manuel | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101733 | Kita-Kita Es | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101988 | Kulangew Elementary School | San Nicolas | 6 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1221000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101955 | Lapalo Es | San Manuel | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102064 | Legaspi Elementary School | Tayug | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101894 | Li Seng Giap Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300322 | Luciano Millan National Hs | Asingan | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300322 | Luciano Millan National Hs | Asingan | 6 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321214 | Lumayao Integrated School | San Quintin | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 300324 | Malico Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6432000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300327 | Maseil-Seil Alo-O Nhs | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 | 1 | 28 | 4STY28CL | BATCH 13 CL | 40067946.14 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 |  | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300328 | Mataas Na Paaralang Juan C. Laya | San Manuel | 6 |  | 1 | 1STY1CL | BATCH 13 CL | 1113254.6197 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101715 | Narciso R. Ramos Es Sped Center | Asingan | 6 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101837 | Natividad Cs | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6473000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101837 | Natividad Cs | Natividad | 6 |  | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300331 | Natividad Nhs | Natividad | 6 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102111 | Pangangaan Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300333 | Panganiban Nhs | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan Ii, Binalonan | 300333 | Panganiban Nhs | Tayug | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102090 | Papallasen Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102048 | Pugot Elementary School | Santa Maria | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101993 | Puyao Es | San Nicolas | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1873000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101882 | Rabago Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101895 | Rizal Es | Rosales | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1833000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300340 | Robert B. Estrella Memorial Nhs | Rosales | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300341 | Rosales Nhs | Rosales | 6 | 1 | 60 | 4STY20CL | BATCH 9 CL | 93308670.81 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101738 | San Aurelio 3Rd Es | Balungao | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300344 | San Aurelio Nhs | Balungao | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101960 | San Bonifacio Es | San Manuel | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 500379 | San Felipe Is | San Nicolas | 6 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300347 | San Isidro Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan Ii, Binalonan | 300347 | San Isidro Nhs | San Nicolas | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300350 | San Leon Nhs | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300351 | San Luis Nhs | Rosales | 6 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300352 | San Macario Nhs | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101743 | San Marcelino Es | Balungao | 6 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1958000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300353 | San Miguel Nhs | Natividad | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300354 | San Nicolas Nhs | San Nicolas | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102117 | San Pablo Es | Umingan | 6 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102051 | San Pablo Es | Santa Maria | 6 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3705000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300356 | San Quintin Nhs | San Quintin | 6 | 1 | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300356 | San Quintin Nhs | San Quintin | 6 |  | 18 | 3STY9CL | BATCH 13 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101977 | San Rafael Es | San Nicolas | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102012 | Sisenando V. Tecson Es | San Quintin | 6 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10985000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 101717 | Sobol Es | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 321212 | Sta. Cruz Is | Santa Maria | 6 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 321219 | Sta. Maria East Integrated School | Santa Maria | 6 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30242655.84 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102056 | Sta. Rosa Es | Santa Maria | 6 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | K10 | Region I | Pangasinan Ii, Binalonan | 102075 | Sto. Domingo Es | Tayug | 6 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1110000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300361 | Sto. Tomas Nhs | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region I | Pangasinan Ii, Binalonan | 300363 | Tayug Nhs | Tayug | 6 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300363 | Tayug Nhs | Tayug | 6 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62205780.54 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300364 | Toboy Nhs | Asingan | 6 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300364 | Toboy Nhs | Asingan | 6 |  | 2 | 1STY1CL | BATCH 13 CL | 2226509.2394 |  |  | Completed | 1
NC 2016 | SHS | Region I | Pangasinan Ii, Binalonan | 300365 | Umingan Central Nhs | Umingan | 6 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region I | San Carlos City | 300378 | Bolingit National High School | San Carlos City | 3 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 | [7 empty] | 2016-05-13 | 2016-05-20 | SARGASSO CONSTRUCTION & DEV'T CORP.
NC 2016 | SHS | Region I | San Carlos City | 300386 | Pangalangan Nhs | San Carlos City | 3 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22200000 |  |  | Completed | 1 | [7 empty] | 2016-05-13 | 2016-05-20 | SARGASSO CONSTRUCTION & DEV'T CORP.
NC 2016 | SHS | Region I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44400000 |  |  | Completed | 1 | [7 empty] | 2016-05-13 | 2016-05-20 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2016 | SHS | Region I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 |  | 15 | 3STY15CL | BATCH 5 CL | 21395200 |  |  | Completed | 1 | [7 empty] | 2016-05-13 | 2016-05-20 | MANIMELDS CONST'N & IRON WORKS/KENWOOD CONST'N ENTERPRISES
NC 2016 | TECHVOC | Region I | San Carlos City | 300388 | Speaker Eugenio Perez Nat;L. Agr'L. Sch. | San Carlos City | 3 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7800000 |  |  | Completed | 1 | [7 empty] | 2016-03-16 | 2016-03-23 | KENWOOD CONSTRUCTION ENTERPRISES
NC 2016 | SHS | Region I | San Carlos City | 300391 | Turac Nhs | San Carlos City | 3 | 1 | 2 | 1STY2CL | BATCH 13 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | K10 | Region I | San Fernando City | 300099 | Bangbangolan Nhs | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6385000 |  |  | Completed | 1 |  |  |  | - | [5 empty] | -
NC 2016 | K10 | Region I | San Fernando City | 101039 | Catbangen Es | City Of San Fernando (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22202343.62 |  |  | Completed | 1 |  |  |  | 16AE0085 | 2016-06-25 | 2016-07-06 | 2016-07-25 | 2016-07-28 | 2016-08-19 | ECDI ENGINEERING & CONSTRUCTION
NC 2016 | K10 | Region I | San Fernando City | 300116 | Dr. Quintin Balcita Sr. Nhs | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6335000 |  |  | Completed | 1 |  |  |  | 16AE0084 | 2016-06-25 | 2016-07-06 | 2016-07-18 | 2016-07-25 | 2016-08-05 | MY Builders & Construction
NC 2016 | SHS | Region I | San Fernando City | 300118 | La Union Nhs | City Of San Fernando (Capital) | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35600200 |  |  | Completed | 1 |  |  |  | - | [5 empty] | -
NC 2016 | K10 | Region I | San Fernando City | 321001 | La Union Nhs - Sacyud Annex | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  | 16AE0086 | 2016-07-06 | 2016-07-14 | 2016-07-27 | 2016-07-29 | 2016-08-19 | MY Builders & Construction
NC 2016 | TECHVOC | Region I | San Fernando City | 321001 | La Union Nhs - Sacyud Annex | City Of San Fernando (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2518000 |  |  | Completed | 1 |  |  |  | - | [5 empty] | -
NC 2016 | SHS | Region I | San Fernando City | 300126 | Pao National High School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6345000 |  |  | Completed | 1 |  |  |  | 16AE0087 | 2016-07-14 | 2016-07-25 | 2016-08-15 |  |  | -
NC 2016 | SHS | Region I | San Fernando City | 324102 | San Fernando City Sped High School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6355000 |  |  | Completed | 1 |  |  |  | 16AE0091 | 2016-07-26 | 2016-08-03 | 2016-08-15 |  |  | -
NC 2016 | SHS | Region I | San Fernando City | 324101 | San Fernando South Central Integrated School | City Of San Fernando (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6365000 |  |  | Completed | 1 |  |  |  | 16AE0090 | 2016-07-26 | 2016-08-03 | 2016-08-15 |  |  | -
NC 2016 | SHS | Region I | Urdaneta City | 300395 | Cabaruan National High School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10105 CY 2016 BEEF Batch 7 |  | 2016-03-10 | 2016-03-23 | 2016-05-16 | 2016-06-01 | Teachnowood Construction Enterprises
NC 2016 | K10 | Region I | Urdaneta City | 300397 | Camabu Nhs | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10106 CY 2016 BEEF Batch 7 |  | 2016-03-10 | 2016-03-23 | 2016-05-16 | 2016-06-01 | 2R Construction & Supply
NC 2016 | K10 | Region I | Urdaneta City | 300400 | Catablan Integrated School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10107 CY 2016 BEFF Batch 7 |  | 2016-03-10 | 2016-03-23 | 2016-05-16 | 2016-06-01 | T.J Velasco Construction & Supply
NC 2016 | K10 | Region I | Urdaneta City | 500061 | Don Alipio Fernandez ,Sr. Is | Urdaneta City | 5 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8314965.05 |  |  | Completed | 1 |  |  |  | 16A10108 CY 2016 BEFF Bacth 7 |  | 2016-03-10 | 2016-03-23 | 2016-05-13 | 2016-05-26 | Aquino-Dela Cruz Eng'g.& Construction
NC 2016 | SHS | Region I | Urdaneta City | 300406 | Nancalobasaan National High School | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  |  | 16A10109 CY 2016 BEFF Batch 7 |  | 2016-03-10 | 2016-03-23 | 2016-05-16 | 2016-06-01 | MKM Marketing
NC 2016 | K10 | Region I | Urdaneta City | 300409 | Pedro T. Orata Nhs | City Of Urdaneta | 5 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region I | Urdaneta City | 500060 | San Jose Leet Is | Urdaneta City | 5 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6390000 |  |  | Completed | 1 |  |  |  | 16A10054 CY 2016 BEFF |  | 2016-03-01 | 2016-03-15 | 2016-05-16 | 2016-06-01 | Teachnowood Construction Enterprises
NC 2016 | K10 | Region I | Urdaneta City | 300410 | Urdaneta City Nhs | City Of Urdaneta | 5 | 1 | 20 | 4STY20CL | BATCH 11 CL | 34198179.297 |  |  | Completed | 1 |  |  |  | 16A10055 CY 2016 BEFF |  | 2016-03-01 | 2016-03-15 | 2016-05-13 | 2016-05-26 | Teachnowood Construction Enterprises
NC 2016 | SHS | Region I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 | 1 | 24 | 4STY24CL | BATCH 1 CL | 35900000 |  |  | Completed | 1 | [9 empty] | NA Ibarra Construction
NC 2016 | TECHVOC | Region I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2800000 |  |  | Completed | 1 | [9 empty] | 739 builders
NC 2016 | SHS | Region I | Vigan City | 300052 | Ilocos Sur National High School | Vigan City | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 27450000 |  |  | Completed | 1 |  |  |  |  | 2016-09-01 | 2016-09-06 |  | 2016-09-22 | 2016-09-30
NC 2016 | K10 | Region I | Vigan City | 100800 | Vigan Central School | City Of Vigan (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958000 |  |  | Completed | 1 | [9 empty] | NA Ibarra Construction
NC 2016 | K10 | Region I | Alaminos City | 101168 | Amandiego Es | City Of Alaminos | 1 | 1 | 4 | 2STY4CL | BATCH 14 CL | 6379337.64 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2475115 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100002 | Bacarra CES | BACARRA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2401384.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100002 | Bacarra CES | BACARRA | 1 |  | 2 | 1STY2CL | BATCH 2 | 2401384.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3663151 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100206 | Nagsanga ES | PASUQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2407595 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100208 | Pasuquin Central Elementary School | PASUQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2520477 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100227 | Piddig Central ES | PIDDIG | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3363727 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100227 | Piddig Central ES | PIDDIG | 1 |  | 3 | 1STY3CL | BATCH 2 | 3363727 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100272 | Sarrat North CS | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2383087.11 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100315 | Lubnac ES | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2470029.78 |  |  | Completed | 1
NC 2017 | TVL | Region I | Alaminos City | 300155 | Alaminos City NHS | CITY OF ALAMINOS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2430000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Alaminos City | 300253 | San Vicente NHS | CITY OF ALAMINOS | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2530000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100403 | Cabugao South Central School | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100409 | Daclapan ES | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100506 | Namalpalan E/S | MAGSINGAL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100511 | Puro ES | MAGSINGAL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100522 | Lanipao ES | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4092595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100530 | St. Gregory E/S | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100530 | St. Gregory E/S | NARVACAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2733185.92 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Sur | 300035 | SAN JUAN NHS | SAN JUAN (LAPOG) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100650 | Sabangan ES | SINAIT | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100655 | Teppeng ES | SINAIT | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100745 | Baringcucurong ES | SUYO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101055 | Padang PS | SAN GABRIEL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2918084.25 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101080 | Liguay ES | SANTOL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2935119.95 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101084 | Ramot PS | SANTOL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2858084.25 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101086 | Sapdaan ES | SANTOL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3111268.11 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102207 | Vira ES | LAOAG CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3699871 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101146 | San Juan ES | AGNO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101154 | Bocboc West ES | AGUILAR | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101160 | Mapita ES | AGUILAR | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101242 | Quinaoayanan ES | BANI | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101256 | Dumpay ES | BASISTA | 2 | 1 | 5 | 1STY5CL | BATCH 4 | 6072550.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101272 | Buenlag ES | BAYAMBANG | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101288 | Carungay ES | BAYAMBANG | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101290 | Caturay Elementary School | BAYAMBANG | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101294 | Inirangan ES | BAYAMBANG | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101274 | Langiran ES | BAYAMBANG | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 151510 | Manambong Sur ES | BAYAMBANG | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101307 | WARDING ELEMENTARY SCHOOL | BAYAMBANG | 3 | 1 | 5 | 1STY5CL | BATCH 4 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101307 | WARDING ELEMENTARY SCHOOL | BAYAMBANG | 3 |  | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101331 | Linoc ES | BINMALEY | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101351 | Goyoden ES | BOLINAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101362 | Salud ES | BOLINAO | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5068351.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101364 | Sampaloc Elementary School | BOLINAO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2773745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101384 | Angarian ES | BUGALLON | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101389 | Dimantal E/S | BUGALLON | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101431 | Doyong Centro ES | CALASIAO | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101433 | Idoldol ES | CALASIAO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101426 | San Miguel ES | CALASIAO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101459 | Babuyan ES | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101480 | Uyong ES | LABRADOR | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101497 | Estanza ES | LINGAYEN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101571 | Bernabe Q. Jimenez E/S | MALASIQUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101563 | Goliman ES | MALASIQUI | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101572 | Olea ES | MALASIQUI | 3 | 1 | 5 | 1STY5CL | BATCH 4 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 151519 | Potiocan Primary School | MALASIQUI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101601 | Casilagan ES | MANGATAREM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101604 | Malabobo ES | MANGATAREM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101586 | Nancasalan ES | MANGATAREM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101640 | Banzal ES | SANTA BARBARA | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101674 | Batancaoa North ES | URBIZTONDO | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101686 | Malibong ES | URBIZTONDO | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 153507 | Jose Macam Paningbatan Sr. Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100076 | Colo-Mabaleng Elementary School | CITY OF BATAC | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5032000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100077 | Cumcumraas PS | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2543000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100077 | Cumcumraas PS | CITY OF BATAC | 2 |  | 3 | 1STY3CL | BATCH 7 | 3811000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100015 | Cabulalaan ES | BACARRA | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4928225.35 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100009 | Sabas-Sagisi Memorial Elem. School | BACARRA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2896572.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100024 | Ar-Arusip ES | BADOC | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5160000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300004 | Banna National High School | BANNA (ESPIRITU) | 2 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6330754 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300008 | Caestebanan NHS | BANNA (ESPIRITU) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3300717 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300011 | Catagtaguen National High School | BANNA (ESPIRITU) | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3300717 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300011 | Catagtaguen National High School | BANNA (ESPIRITU) | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6564129 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300011 | Catagtaguen National High School | BANNA (ESPIRITU) | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6564129 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300013 | Currimao NHS | CURRIMAO | 2 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6414000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2543000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300015 | Dingras NHS/Lt. Edgar Foz Mem. NHS | DINGRAS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3207000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100138 | Suyo ES | DINGRAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2475650 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320810 | SUYO NATIONAL HIGH SCHOOL | DINGRAS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3207000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100146 | F. Daquioag Mem. ES | MARCOS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2450650 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3207000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon NHS | NUEVA ERA | 2 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6330754 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320820 | Adriano P. Arzadon NHS | NUEVA ERA | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6330754 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100142 | Cabittauran ES | NUEVA ERA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3851000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100154 | Nueva Era Central Elementary School | NUEVA ERA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2543000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320828 | Uguis Integrated School | NUEVA ERA | 2 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6330754 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320828 | Uguis Integrated School | NUEVA ERA | 2 |  | 2 | Workshop Bldg. (7x18) | BATCH 7 | 6330754 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100257 | Filipinas East Elementary School | SAN NICOLAS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3821075 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100273 | Sta. Rosa ES | SARRAT | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4928225.35 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320818 | Talugtog Solsona National High School | SOLSONA | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3300717 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100326 | Alilem Central School | ALILEM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100347 | Banlo Elementary School | BANAYOYO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100349 | Bay-asan PS | BANAYOYO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100390 | Cabcaburao ES | BURGOS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4077595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100395 | Padayao ES | BURGOS | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4087595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100405 | Carusipan Elementary School | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100408 | Cuantacla -Sagsagat ES | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100416 | Pila ES | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100419 | Sabang ES | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100466 | Bissayot PS | CERVANTES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2853185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 150517 | Cabaroan ES | CERVANTES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2833185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100471 | Comillas South ES | CERVANTES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2853185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100488 | Quinayad ES | CERVANTES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2833185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100490 | San Juan ES | CERVANTES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2833185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100357 | Lidlidda South CS | LIDLIDDA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3992595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100367 | Tay-ac Elementary School | LIDLIDDA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100541 | Nagbukel CS | NAGBUKEL | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100541 | Nagbukel CS | NAGBUKEL | 2 |  | 3 | 1STY3CL | BATCH 7 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100513 | Ambulogan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100518 | Camarao ES | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100519 | Casilagan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4112595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100467 | Bucnit PS | QUIRINO (ANGKAKI) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2883185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100489 | Quirino CS | QUIRINO (ANGKAKI) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2883185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100584 | San Gaspar PS | SALCEDO (BAUGEN) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100613 | Bayubay ES | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100662 | Paratong ES | SANTA CATALINA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100691 | Don Pedro Festejo Mem. Sch. | SANTA LUCIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2693185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100703 | Bia-o ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2673185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100706 | Danuman ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3962595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100717 | Tangaoan ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3977595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100718 | Tinaan ES | SANTA MARIA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3967595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100636 | San Roque Elementary School | SANTIAGO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2733185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100642 | Cabarambanan ES | SINAIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100643 | Cadanglaan ES | SINAIT | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100643 | Cadanglaan ES | SINAIT | 1 |  | 3 | 1STY3CL | BATCH 7 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100766 | Bimmanga Community School | TAGUDIN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3947595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.59 |  |  | Completed | 1
NC 2017 | TVL | Region I | La Union |  | AGOO VNHS | AGOO | 2 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 7 | 5327491.84 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100803 | Bacsil ES | AGOO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.59 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 300139 | Dr. Manuel T. Cases Sr. National High School | AGOO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.59 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100816 | San Nicolas ES | AGOO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 321004 | Aringay National High School-Basca Annex | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.59 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100824 | Dulao ES | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 321007 | Manga National HS | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.59 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100829 | New Bern (Alaska) ES | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100830 | Pangao-aoan ES | ARINGAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 500470 | San Simon Integrated School | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100838 | Sta. Lucia ES | ARINGAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4195278.52 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100839 | Sta. Rita ES | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100840 | Sto. Rosario ES | ARINGAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100868 | Tagudtud ES | BAGULIN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100908 | Baccuit Elementary School | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100912 | Bawanta ES | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100922 | CASILAGAN INTEGRATED SCHOOL | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100914 | Paringao ES | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100927 | Payocpoc ES | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100930 | Santiago ES | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100930 | Santiago ES | BAUANG | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5427186.27 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100931 | Sta. Monica Elementary School | BAUANG | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100940 | Caba CES | CABA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2688745.92 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 300104 | Caba NHS | CABA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 300104 | Caba NHS | CABA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3025120.59 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100946 | San Gregorio ES | CABA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2875120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100948 | Santiago Sur Integrated School | CABA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 281525 | Baraoas Norte Elementary School | NAGUILIAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3818435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100980 | Cabaritan ES | NAGUILIAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100984 | Don Tomas R. Mendoza ES | NAGUILIAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100986 | Guesset ES | NAGUILIAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 100996 | Ambalite ES | PUGO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 300131 | Pugo Central NHS | PUGO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101003 | Saytan Integrated School | PUGO | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4195278.52 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 300142 | Saytan Integrated School | PUGO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101005 | Amlang ES | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2688746 |  |  | Completed | 1
NC 2017 | SHS | Region I | La Union | 300127 | Parasapas NHS | ROSARIO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101047 | Amontoc ES | SAN GABRIEL | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2956011.63 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101095 | Cupang ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101103 | Ubagan ES | SANTO TOMAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 101130 | Tubao CES | TUBAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2950120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | La Union | 321011 | Tubao NHS Annex-Halog West | TUBAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2925120.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102194 | Alipio N. Ignacio Mem. ES | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102188 | Cavit-Araniw ES | LAOAG CITY (Capital) | 1 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 4928225.35 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City |  | DON GALICANO ES | LAOAG CITY (Capital) | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3775727.43 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102201 | Pila ES | LAOAG CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 153001 | Sto. Nino Primary School | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2634373.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102192 | Tangid ES | LAOAG CITY (Capital) | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3775727.43 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101503 | Balococ ES | LINGAYEN (Capital) | 2 | 1 | 5 | 1STY5CL | BATCH 7 | 6072650.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101503 | Balococ ES | LINGAYEN (Capital) | 2 |  | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101484 | Magsaysay ES | LINGAYEN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101486 | Naguelguel Elementary School | LINGAYEN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan I, Lingayen | 101511 | Rosario ES | LINGAYEN (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101697 | Bersamin ES | ALCALA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2652932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101700 | Laoac ES | ALCALA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2667932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 300335 | Pindangan National High School -Alcala | ALCALA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101752 | Pogo ES | BAUTISTA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2652932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 300285 | Batasan NHS | BINALONAN | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2693683.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101763 | Calixto A. Bautista ES | BINALONAN | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2754632.48 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3313113.23 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan II, Binalonan | 300346 | San Felipe National HighSchool | BINALONAN | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3229859.75 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101766 | Sta. Catalina ES | BINALONAN | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3014750.62 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101788 | Don Maximo G. Gombio Panaga-Tabao Integrated School | LAOAC | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101784 | Don Rufino Tabayoyong CS | LAOAC | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2828432.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101787 | Nanbagatan ES | LAOAC | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2888693.18 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101792 | Baguinay ES | MANAOAG | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101793 | Baritao ES | MANAOAG | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101796 | Doña Consolacion Sta. Maria ES | MANAOAG | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101799 | Lipit Elementary School | MANAOAG | 4 | 1 | 3 | 1STY3CL | BATCH 7 | 3798435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101803 | Oraan ES | MANAOAG | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101822 | Maasin ES | MANGALDAN | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101824 | Malabago ES | MANGALDAN | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101852 | Dilan Integrated School | POZZORUBIO | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2667932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101868 | Don Benito ES | POZZORUBIO | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3844967.46 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101868 | Don Benito ES | POZZORUBIO | 5 |  | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3844967.46 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101870 | Inoman ES | POZZORUBIO | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3902454.56 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101922 | Binday ES | SAN FABIAN | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101931 | Awai ES | SAN JACINTO | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101939 | San Jose ES | SAN JACINTO | 4 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102059 | Salvacion ES | SANTO TOMAS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2667931.8 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102035 | Pinalpal Elementary School | SISON | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102134 | Capulaan ES | VILLASIS | 5 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 4971856.51 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102121 | Lipay ES | VILLASIS | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2652931.8 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300377 | Bacnar National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300377 | Bacnar National High School | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300380 | Coliling National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300380 | Coliling National High School | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300380 | Coliling National High School | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 153505 | Don Vicente G. Ferrer Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 102259 | Guelew Integrated School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 153506 | Julian Valerio Resuello Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300384 | Mabalbalino NHS | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 102261 | Mestizo Norte ES | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Carlos City | 102248 | Payar Elementary School | SAN CARLOS CITY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300387 | Salinap NHS | SAN CARLOS CITY | 3 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102285 | Anonas Elementary School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2798171.98 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102270 | Bolaoen ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | SHS | Region I | Urdaneta City | 300396 | Cabuloan NHS | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102272 | Camanang ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102289 | Camantiles ES | CITY OF URDANETA | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3961955.13 |  |  | Completed | 1
NC 2017 | SHS | Region I | Urdaneta City | 300399 | Casabula NHS | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2652932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102291 | Cayambanan ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2708683.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102275 | Florentino B. Goce Community School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | SHS | Region I | Urdaneta City | 300404 | Labit National High School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2693683.83 |  |  | Completed | 1
NC 2017 | SHS | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2768171.98 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102301 | Manan ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2768171.98 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102302 | Nanbacuran ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2678683.83 |  |  | Completed | 1
NC 2017 | SHS | Region I | Urdaneta City | 300407 | Palina East National High School | CITY OF URDANETA | 5 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3961955.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102305 | Pinmaludpod ES | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2768171.98 |  |  | Completed | 1
NC 2017 | TVL | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3445353.08 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102283 | Urdaneta I Central School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2678683.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102283 | Urdaneta I Central School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2678683.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Urdaneta City | 102284 | Vicente Taaca Memorial School | CITY OF URDANETA | 5 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2637932.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Vigan City | 100783 | Ayusan-Paoa Elementary School | CITY OF VIGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Vigan City | 100797 | Salindeg ES (Salindeg-Pong-ol, Barraca ES) | CITY OF VIGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2895907.5 |  |  | Completed | 1
NC 2017 | TVL | Region I | Batac City | 300005 | Batac National High School | CITY OF BATAC | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3489633 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100092 | Bil-loca ES | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2598824 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100075 | Catalino Acosta Mem. ES, Special Education Center | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2480000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Batac City | 320803 | City of Batac National high school Payao | CITY OF BATAC | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3306170 |  |  | Completed | 1
NC 2017 | TVL | Region I | Batac City | 300012 | Crispina Marcos Valdez NHS | CITY OF BATAC | 2 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 3230000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100080 | Maipalig-Quiom ES | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2696192 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100078 | Mariano Marcos Memorial Elementary School | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2593865 |  |  | Completed | 1
NC 2017 | K10 | Region I | Batac City | 100085 | Quiling ES | CITY OF BATAC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2573221 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100012 | Tambidao Elementary School | BACARRA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100012 | Tambidao Elementary School | BACARRA | 1 |  | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100025 | Badoc North Central School | BADOC | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2507928 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100043 | Abaca ES | BANGUI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2693968.54 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100055 | San Isidro Elementary School | BANGUI | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2694653.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100059 | Banna CES | BANNA (ESPIRITU) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5120812 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100065 | Catagtaguen ES | BANNA (ESPIRITU) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3828000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100069 | Macayepyep ES | BANNA (ESPIRITU) | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3851000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100102 | Bayog ES | BURGOS | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2664397.65 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100106 | Nagsurot ES | BURGOS | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3787697.91 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100112 | Dona Josefa Marcos ES | CURRIMAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2495674 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100123 | Medina Parado ES | DINGRAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2506450 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100050 | Dumalneg ES | DUMALNEG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2743638.96 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2506506 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 |  | 3 | 1STY3CL | BATCH 10 | 3852235 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100176 | Saud ES | PAGUDPUD | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2695337.71 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100177 | Subec ES | PAGUDPUD | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2695337.71 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100197 | Carusikis ES | PASUQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2650124.53 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100211 | Sta. Catalina ES | PASUQUIN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2650124.53 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100221 | Dupitac ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2650124.53 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100223 | Gayamat PS | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2803346.53 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100225 | Libnaoan ES | PIDDIG | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3994169.25 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100229 | San Antonio ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2637452.19 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100231 | Tangaoan ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2852332.34 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100231 | Tangaoan ES | PIDDIG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2852332.34 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100231 | Tangaoan ES | PIDDIG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2852332.34 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100231 | Tangaoan ES | PIDDIG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2852332.34 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100231 | Tangaoan ES | PIDDIG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2650124.53 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100232 | Tonoton ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2564058.88 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100232 | Tonoton ES | PIDDIG | 1 |  | 2 | 1STY2CL | BATCH 10 | 2564058.88 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100244 | Nagtrigoan ES | PINILI | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2478578 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100254 | Bugnay ES | SAN NICOLAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2418317 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100260 | San Nicolas ES | SAN NICOLAS | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5035243 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100261 | Binaratan ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100262 | Cabuloan ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100263 | Golgol ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100264 | Pandan IS | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2831258.9 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100265 | Parang ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100266 | Patad ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100267 | Ruiz ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100268 | Sagpatan ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100269 | San Antonio ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100270 | San Bernabe ES | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2636082.99 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 150009 | San Pedro Elementary School | SARRAT | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2637452.19 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100271 | Sarrat CS | SARRAT | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3816317.86 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100279 | Lipay ES | SOLSONA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2629087 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100288 | Alsem ES | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2711711.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100293 | Danao Elementary School | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2711711.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100311 | Dasar ES | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2711711.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 320819 | Pallas Integrated School | VINTAR | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3786609.7 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2642921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100306 | Visaya ES | VINTAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2642921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100368 | Balaleng ES | BANTAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100371 | Bantay West Central School | BANTAY | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100379 | Ora West ES | BANTAY | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100380 | Paing ES | BANTAY | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100382 | San Julian ES | BANTAY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100389 | Burgos Central School | BURGOS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4187595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100392 | Luna Community School | BURGOS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4127595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100393 | Macaoayan Comm. Sch. | BURGOS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4127595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100410 | Dardarat ES | CABUGAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100414 | Nagsincaoan ES | CABUGAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100424 | Turod ES | CABUGAO | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100459 | Pandan ES | CAOAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2481322 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100459 | Pandan ES | CAOAYAN | 1 |  | 2 | 1STY2CL | BATCH 10 | 2481322 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100567 | Concepcion ES | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2933185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100501 | Magsingal North Central School | MAGSINGAL | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100503 | Manzante ES | MAGSINGAL | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100505 | Miramar ES | MAGSINGAL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100547 | Rivadavia ES | NARVACAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2763185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100529 | Sarmingan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4187595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100531 | Sulvec IS | NARVACAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2783185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100532 | Turod ES | NARVACAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2793185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100483 | Namitpit ES | QUIRINO (ANGKAKI) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5387231.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100492 | Suagayan ES | QUIRINO (ANGKAKI) | 2 | 1 | 4 | 1STY4CL | BATCH 10 | 5217231.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100600 | Labnig ES | SAN JUAN (LAPOG) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100607 | San Juan North CS | SAN JUAN (LAPOG) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100615 | Pudoc Elementary School | SAN VICENTE | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100684 | Sta. Cruz CS | SANTA CRUZ | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4037595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100695 | Paoc ES | SANTA LUCIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2743185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100697 | Sabuanan Elementary School SPED Center | SANTA LUCIA | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3977595.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100700 | Ag-agrao ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2793185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100710 | Maynganay ES | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2793185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100710 | Maynganay ES | SANTA MARIA | 2 |  | 2 | 1STY2CL | BATCH 10 | 2793185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100715 | Sta. Maria West CS | SANTA MARIA | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2823185.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100727 | Lagatit ES | SANTO DOMINGO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100741 | Sto. Domingo South CS | SANTO DOMINGO | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 4962644 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100646 | Dean L. Yabes Mem. ES | SINAIT | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3907628 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Sur | 300085 | Suyo NHS | SUYO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2803745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Sur | 100765 | Becques Community School | TAGUDIN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2793185.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300376 | Abanon NHS | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300378 | Bolingit National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300379 | Cobol National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300381 | Doyong National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300382 | Libas NHS | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300383 | Lilimasan National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300385 | Malacañang National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300386 | Pangalangan NHS | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300389 | Tamayo National High School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 300390 | Tandoc NHS | SAN CARLOS CITY | 3 | 1 | 2 | Workshop Bldg. (7x18) | BATCH 10 | 5400000 |  |  | Completed | 1
NC 2017 | TVL | Region I | San Carlos City | 500057 | Tarece Integrated School | SAN CARLOS CITY | 3 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Vigan City | 100793 | Nagsangalan ES | CITY OF VIGAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2895907.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102155 | Caranglaan ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | BATCH 12 | 24498047.73 |  |  | Completed | 1
NC 2017 | SHS | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | 12 | 4STY12CL | BATCH 12 | 31889789.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102150 | Lucao ES | DAGUPAN CITY | 4 | 1 | 12 | 3STY12CL | BATCH 12 | 29439267.25 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102177 | Pantal ES | DAGUPAN CITY | 4 | 1 | 6 | 2STY6CL | BATCH 12 | 11696168.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102177 | Pantal ES | DAGUPAN CITY | 4 |  | 9 | 3STY9CL | BATCH 12 | 24528047.73 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102171 | Sabangan ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | BATCH 12 | 24538047.73 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102161 | Tambac ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | BATCH 12 | 24528047.73 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102153 | West CES II | DAGUPAN CITY | 4 | 1 | 12 | 3STY12CL | BATCH 12 | 29439267.25 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300286 | Bautista National High School | BAUTISTA | 5 | 1 | 20 | 4STY20CL | BATCH 12 | 45549250.71 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101987 | East Central School | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 11723060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101990 | Malilion ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 11385224.24 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300357 | San Rafael NHS | SAN NICOLAS | 6 | 1 | 6 | 3STY6CL | BATCH 12 | 15203466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300361 | Sto. Tomas NHS | SAN NICOLAS | 6 | 1 | 6 | 2STY6CL | BATCH 12 | 12821784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101998 | Talingkapor ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 11653060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101976 | West Central School | SAN NICOLAS | 6 | 1 | 6 | 2STY6CL | BATCH 12 | 12881784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102003 | Carayacan ES | SAN QUINTIN | 6 | 1 | 6 | 2STY6CL | BATCH 12 | 15636919.22 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102005 | Gonzalo ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 9915491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102007 | Lagasit ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 11683060.31 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300318 | Lagasit NHS | SAN QUINTIN | 6 | 1 | 8 | 2STY8CL | BATCH 12 | 18777269.29 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500386 | Lumayao Integrated School | SAN QUINTIN | 6 | 1 | 8 | 4STY8CL | BATCH 12 | 21988749.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102010 | San Pedro ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 9855491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102011 | San Quintin Central School | SAN QUINTIN | 6 | 1 | 8 | 2STY8CL | BATCH 12 | 22134937.29 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300356 | San Quintin NHS | SAN QUINTIN | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 40601811.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102012 | Sisenando V. Tecson ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 11933092.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102055 | West Central School | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 9840491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102063 | Carriedo ES | TAYUG | 6 | 1 | 4 | 2STY4CL | BATCH 12 | 9885491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6 | 1 | 16 | 4STY16CL | BATCH 12 | 40721811.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Fernando City | 101025 | Dalumpinas ES | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2793745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | San Fernando City | 101028 | Mameltac Elementary School | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY | 4 | 1 | 20 | 4STY20CL | BATCH 13 | 41648409.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102157 | East Central IS | DAGUPAN CITY | 4 | 1 | 15 | 3STY15CL | BATCH 13 | 33706939.69 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102168 | Gen. Gregorio del Pilar ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | BATCH 13 | 24498047.73 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102166 | Leon-Francisco Maramba ES | DAGUPAN CITY | 4 | 1 | 6 | 3STY6CL | BATCH 13 | 13799515.1 |  |  | Completed | 1
NC 2017 | K10 | Region I | Dagupan City | 102152 | West Central ES I | DAGUPAN CITY | 4 | 1 | 15 | 3STY15CL | BATCH 13 | 33706939.69 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101694 | Alcala CS | ALCALA | 5 | 1 | 6 | 2STY6CL | BATCH 13 | 14619376.64 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300276 | Arboleda NHS | ALCALA | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 22004394.03 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300276 | Arboleda NHS | ALCALA | 5 |  | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300288 | Bersamin Agro-Industrial HS | ALCALA | 5 | 1 | 16 | 4STY16CL | BATCH 13 | 38756274.86 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 | 1 | 20 | 4STY20CL | BATCH 13 | 52356518.28 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 |  | 6 | 3STY6CL | BATCH 13 | 15143466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300301 | Cipriano P. Primicias NHS | ALCALA | 5 |  | 4 | 2STY4CL | BATCH 13 | 9020901.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300355 | San Pedro Apartado NHS | ALCALA | 5 | 1 | 12 | 4STY12CL | BATCH 13 | 34814768.69 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300277 | Ariston-Bantog NHS | Asingan | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 16018675.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300299 | CAROSUCAN NORTE NATIONAL HIGH SCHOOL | ASINGAN | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 15274305.68 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 12234814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101727 | San Vicente West IS | ASINGAN | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 21381686.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101729 | Balungao CS | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101735 | Mauban ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300339 | Rajal Angayan NHS | BALUNGAO | 6 | 1 | 9 | 3STY9CL | BATCH 13 | 27019852.5 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300339 | Rajal-Angayan NHS | Balungao | 6 |  | 9 | 3STY9CL | BATCH 13 | 27019852.5 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101740 | San Joaquin ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9840491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300282 | Baluyot NHS | BAUTISTA | 5 | 1 | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300282 | Baluyot NHS | BAUTISTA | 5 |  | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300302 | Coloscaoayan NHS | BAUTISTA | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 17875953.5 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300302 | Coloscaoayan NHS | BAUTISTA | 5 |  | 8 | 4STY8CL | BATCH 13 | 18890527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300346 | San Felipe National HighSchool | BINALONAN | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18890527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300358 | Sta. Maria NHS, Binalonan | BINALONAN | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 22064394.03 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 |  | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 |  | 4 | 2STY4CL | BATCH 13 | 12026727.55 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101834 | Canarem ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11295224.24 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18890527.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101839 | SALUD ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11355224.24 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300343 | Salud-San Eugenio NHS | NATIVIDAD | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 15591919.22 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101840 | San Eugenio ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11295224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101845 | SAN MIGUEL ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11315224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101848 | Silag ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11593601.29 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZZORUBIO | 5 | 1 | 16 | 4STY16CL | BATCH 13 | 40601811.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZZORUBIO | 5 |  | 16 | 4STY16CL | BATCH 13 | 46339376.2 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300290 | Bobonan National High School | POZZORUBIO | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 22109394.03 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300311 | Eugenio P. Perez NHS | POZZORUBIO | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300329 | Nama NHS | POZZORUBIO | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18905527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300329 | Nama NHS | POZZORUBIO | 5 |  | 8 | 4STY8CL | BATCH 13 | 18905527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300332 | Palguyod NHS | POZZORUBIO | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18905527.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101860 | Pozorrubio CS | POZZORUBIO | 5 | 1 | 20 | 4STY20CL | BATCH 13 | 52416518.28 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101889 | Balincanaway ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101878 | Carmen Elementary School | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 10288328.01 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300314 | Guiling-Coliling NHS | ROSALES | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101894 | Li Seng Giap ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101880 | Palakipak ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9840491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101882 | Rabago ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11608601.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101896 | Rosales North CS | ROSALES | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 12881784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101885 | San Isidro Elementary School | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11933092.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101900 | San Luis ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11653060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101902 | San Pedro West ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9840491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 152002 | Sitio Baong ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11508601.49 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 321208 | Don Robert B. Estrella, Sr. NHS | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11653060.31 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300349 | San Juan NHS | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11993092.73 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300360 | Sto. Domingo National High School | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 10454451.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101984 | Cacabugaoan ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11295224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101985 | Calaocan ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9855491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500379 | San Felipe Integrated School | SAN NICOLAS | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18920527.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101975 | San Jose ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 10825082.12 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300354 | San Nicolas National High School | SAN NICOLAS | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40601811.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101978 | San Roque ANP Pilot School | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11723060.1 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300359 | Sta. Maria NHS | SAN NICOLAS | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18995527.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101980 | Sto. Tomas ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11355224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102041 | Bantog-Capandanan ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 46339376.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102046 | Pataquid ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102049 | Samon ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11723060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 321219 | Sta. Maria East Integrated School | SANTA MARIA | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40601811.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 | 1 | 6 | 3STY6CL | BATCH 13 | 18242332.91 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300275 | Antonio P. Villar National High School | SANTO TOMAS | 5 |  | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 321203 | San Antonio NHS | SANTO TOMAS | 5 | 1 | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300279 | Alejandro F. Oligan HS (Asan Sur NHS) | SISON | 5 | 1 | 12 | 4STY12CL | BATCH 13 | 33723777.1 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102017 | Artacho ES | SISON | 5 | 1 | 4 | 2STY4CL | BATCH 13 | 12006727.55 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300278 | Artacho NHS | SISON | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500377 | Bantay Insik Integrated School | SISON | 5 | 1 | 8 | 2STY8CL | BATCH 13 | 18672269.29 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 19218719.15 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500385 | Dungon IS | SISON | 5 | 1 | 12 | 4STY12CL | BATCH 13 | 35287768.69 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102030 | Esperanza Integrated School | SISON | 5 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.14 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500004 | Esperanza Integrated School | SISON | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18875526.91 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 300317 | Labayug National High School | SISON | 5 | 1 | 4 | 2STY4CL | BATCH 13 | 11916391.48 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102035 | Pinalpal Elementary School | SISON | 5 | 1 | 4 | 2STY4CL | BATCH 13 | 12006727.55 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102062 | Barangobong Elementary School | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11295224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102072 | Magallanes Elementary School | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11295224.24 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 22079394.03 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102094 | Bantug ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9855491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300283 | Baracbac NHS | UMINGAN | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 13608117.11 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300293 | Cabalitian NHS | UMINGAN | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 15274305.68 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102082 | Doña Nena Elementary School | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11723060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102084 | Evangelista ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11508601.49 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102085 | Flores ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102086 | La Paz ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 13 | 11653060.31 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300316 | La Paz NHS | UMINGAN | 6 | 1 | 16 | 4STY16CL | BATCH 13 | 40601811.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300327 | Maseil-seil Alo-o NHS | UMINGAN | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18935527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300338 | Prado NHS | UMINGAN | 6 | 1 | 6 | 2STY6CL | BATCH 13 | 15274305.68 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6 | 1 | 8 | 4STY8CL | BATCH 13 | 18935527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN | 6 |  | 16 | 4STY16CL | BATCH 13 | 46414376.2 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300284 | Barangobong NHS | VILLASIS | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18875527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300298 | Capulaan NHS | VILLASIS | 5 | 1 | 12 | 4STY12CL | BATCH 13 | 34814768.69 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102135 | Caramutan ES | VILLASIS | 5 | 1 | 4 | 2STY4CL | BATCH 13 | 13625377.88 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300308 | Don Ramon E. Costales MNHS | VILLASIS | 5 | 1 | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300308 | Don Ramon E. Costales MNHS | VILLASIS | 5 |  | 6 | 3STY6CL | BATCH 13 | 15113466.61 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300308 | Don Ramon E. Costales MNHS | VILLASIS | 5 |  | 6 | 3STY6CL | BATCH 13 | 18242332.9 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102123 | Piaz ES | VILLASIS | 5 | 1 | 10 | 2STY10CL | BATCH 13 | 26034465.11 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102123 | Piaz ES | VILLASIS | 5 |  | 10 | 2STY10CL | BATCH 13 | 26034465.11 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300334 | Piaz National High School | VILLASIS | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 22004394.03 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300366 | Unzad NHS | VILLASIS | 5 | 1 | 8 | 4STY8CL | BATCH 13 | 18890527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Batac City | 300012 | Crispina Marcos Valdez NHS | CITY OF BATAC | 2 | 1 | 3 | 1STY3CL | BATCH 14 | 3828000 |  |  | Completed | 1
NC 2017 | TVL | Region I | Batac City | 320804 | City of Batac NHS Poblacion | CITY OF BATAC | 2 | 1 | 1 | Regular Workshop | BATCH 14 | 3474127.32 |  |  | Completed | 1
NC 2017 | SHS | Region I | Candon City | 300047 | Candon City High School | CITY OF CANDON | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8995901.76 |  |  | Completed | 1 |  |  | P00183638LZ-CW1 | 17AD0197 | 2017-12-01 | 2017-12-08 | 2017-12-20 | 2017-12-27 | 2018-01-09 | FNDCC
NC 2017 | SHS | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9245901.76 |  |  | Completed | 1 |  |  | P00183639LZ-CW1 | 17AD0198 | 2017-12-01 | 2017-12-08 | 2017-12-20 | 2017-12-27 | 2018-01-09 | FNDCC
NC 2017 | K10 | Region I | Ilocos Norte | 100008 | Pulangi ES | BACARRA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100011 | Santo Cristo Elementary School | BACARRA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100045 | Bacsil PS | Bangui | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100047 | Bangui CES | BANGUI | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 11756168.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100104 | Bobon ES | BURGOS | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2761733.48 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100171 | Pagudpud Central Elementary School | PAGUDPUD | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100216 | AB-ABUT ES | PIDDIG | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100217 | ABUCAY ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100218 | BOYBOY ES | PIDDIG | 1 | 1 | 4 | 1STY4CL | BATCH 14 | 4903351.15 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100219 | CALAMBEG E/S | PIDDIG | 1 | 1 | 3 | 1STY3CL | BATCH 14 | 3788435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100221 | DUPITAC E/S | PIDDIG | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8158972.094 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100222 | ESTANCIA ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10944421.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100223 | Gayamat PS | PIDDIG | 1 |  | 4 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100224 | Lagandit ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10884421.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100225 | Libnaoan ES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10904421.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100227 | Piddig Central ES | PIDDIG | 1 | 1 | 10 | 2STY10CL | BATCH 14 | 18046128.7 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100228 | PIDDIG SOUTH CES | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100229 | San Antonio ES | PIDDIG | 1 | 1 | 5 | 1STY5CL | BATCH 14 | 6122650.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100230 | Sta. Maria ES | PIDDIG | 1 | 1 | 4 | 1STY2CL | BATCH 14 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100231 | TANGAOAN ES | PIDDIG | 1 |  | 6 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | ILOCOS NORTE | 100232 | TONOTON E/S | PIDDIG | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 10854421.2 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300001 | Adams National High School | ADAMS | 1 | 1 | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300001 | Adams National High School | ADAMS | 1 |  | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 | 1 | 6 | 6-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 33656939.69 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 |  | 3 | 3-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 24518874.73 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 |  | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9095901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 |  | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9095901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 |  | 1 | 1-UNIT UNIQUE WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA | 1 |  | 8 | 2STY8CL | BATCH 14 | 17174796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1 | 1 | 6 | 2-UNITS REGULAR WORKSHOP, 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (3STY) | BATCH 14 | 29659267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300003 | Bangui NHS | BANGUI | 1 |  | 1 | 1-UNIT UNIQUE WORKSHOP (1STY) | BATCH 14 | 2613745.13 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 | 1 | 6 | 6-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 29359267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300006 | Burgos Agro-Industrial School | BURGOS | 1 |  | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300007 | Cadaratan National High School | BACARRA | 1 | 1 | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9005901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300007 | Cadaratan National High School | BACARRA | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 | 1 | 1 | 1-UNIT UNIQUE WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300009 | Carasi NHS | CARASI | 1 |  | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1 | 1 | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300014 | Davila National High School | PASUQUIN | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 17559570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG | 1 |  | 3 | 3-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 14139515.16 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 | 1 | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300017 | Dumalneg NHS | DUMALNEG | 1 |  | 1 | 1-UNIT UNIQUE WORKSHOP (1STY) | BATCH 14 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 | 1 | 1 | 1-UNIT UNIQUE WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-UNIT SCI. LAB. (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-UNIT SCI. LAB. (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-UNIT ICT LAB. (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-UNIT ICT LAB. (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 | 1 | 4 | 4-UNITS REGULAR WORKSHOP (2STY) | BATCH 14 | 17474789.72 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 |  | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 17474789.72 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 17159570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 |  | 3 | 3-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 13739515.1 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1 | 1 | 1 | 1-UNIT REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300031 | VINTAR NHS | VINTAR | 1 |  | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320801 | BANBAN NHS | BANGUI | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 17309570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320802 | LANAO NATIONAL HIGH SCHOOL | BANGUI | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 17309570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 |  | 3 | 3-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 13739515.16 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1 | 1 | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320821 | ISIC-ISIC NATIONAL HIGH SCHOOL | VINTAR | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 9045901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320827 | FLORENTINO CAMAQUIN INTEGRATED SCHOOL | VINTAR | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320827 | FLORENTINO CAMAQUIN INTEGRATED SCHOOL | VINTAR | 1 |  | 3 | 3-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 13739515.16 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1 | 1 | 2 | 2-UNIT REGULAR WORKSHOP (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 500343 | Pallas Integrated School | VINTAR | 1 |  | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 500344 | Salpad Integrated School | VINTAR | 1 | 1 | 2 | 2-UNITS SCI. LAB. (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 500344 | Salpad Integrated School | VINTAR | 1 |  | 2 | 2-UNITS ICT LAB. (2STY) | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte |  | Special Education (SPED) Center | BACARRA | 1 | 1 | 2 | 2STY2CL | BATCH 14 | 5712645.05 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 | 1 | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 300018 | Ilocos Norte Agricultural College | PASUQUIN | 1 |  | 1 | 1-REGULAR WORKSHOP (1STY) | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100136 | Sagpatan ES | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100143 | Cacafean ES | Marcos | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2688745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100149 | Garnaden ES | Nueva Era | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2688745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100150 | Imelda ES | MARCOS | 2 | 1 | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100150 | Imelda ES | MARCOS | 2 |  | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100157 | Santo Nino ES | NUEVA ERA | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 3811000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100180 | Bacsil ES | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100184 | Mumulaan ES | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100192 | Sideg ES | Paoay | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100237 | Buanga PS | Pinili | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100238 | Bulbulala ES | Pinili | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 100246 | Puritac-Dalayap ES | Pinili | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 150004 | Upon PS | Pinili | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 150012 | Wilbur C. Go ES | Currimao | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 150018 | Barikir ES | Nueva Era | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2688745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Ilocos Norte | 150019 | Bugayong Elementary Sch. | NUEVA ERA | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2559020.4 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Norte | 320812 | Marcos NHS (Santiago Campus) | MARCOS | 2 | 1 | 3 | 1STY3CL | BATCH 14 | 3852235 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Sur | 300069 | Puro NHS, Magsingal | MAGSINGAL | 1 | 1 | 4 | 1STY4CL | BATCH 14 | 5213500 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Sur | 300069 | Puro NHS, Magsingal | MAGSINGAL | 1 |  | 4 | 1STY4CL | BATCH 14 | 5213500 |  |  | Completed | 1
NC 2017 | SHS | Region I | Ilocos Sur | 300069 | Puro NHS, Magsingal | MAGSINGAL | 1 |  | 4 | 1STY4CL | BATCH 14 | 5213500 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102184 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102185 | Buttong ES | LAOAG CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102186 | Cabeza ES | LAOAG CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 14 | 3925727.43 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102193 | A. P. Santos ES (SPED Center) | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2792921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102199 | E. F. Siazon Mem. ES | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2792921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102203 | Sta. Maria ES | LAOAG CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 14 | 13735515.16 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102204 | Suyo ES | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2792921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102206 | Barit ES | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL w/ TOILET | BATCH 14 | 8901172.2512 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102206 | Barit ES | LAOAG CITY (Capital) | 1 |  | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102208 | Faustino Reyes Mem. ES | LAOAG CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 14 | 2792921.01 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102209 | Gabaldon ES | LAOAG CITY (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 14 | 13735515.16 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 102214 | San Mateo ES | LAOAG CITY (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300372 | Gabu NHS | LAOAG CITY (Capital) | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 16974790.26 |  |  | Completed | 1
NC 2017 | SHS | Region I | Laoag City | 300372 | Gabu NHS | LAOAG CITY (Capital) | 1 |  | 2 | 1STY2CL | BATCH 14 | 2792921.01 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 17309570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 |  | 8 | 8-UNIT REGULAR WORKSHOP (4STY) | BATCH 14 | 29509267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 |  | 8 | 8-UNIT REGULAR WORKSHOP (4STY) | BATCH 14 | 29509267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 |  | 8 | 8-UNIT REGULAR WORKSHOP (4STY) | BATCH 14 | 29509267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 17309570.67 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) | 1 |  | 6 | 6-UNIT REGULAR WORKSHOP (3STY) | BATCH 14 | 33806939.69 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 300375 | Ilocos Norte Regional School of Fisheries | LAOAG CITY (Capital) | 1 | 1 | 6 | 2-UNIT REGUALR WORKSHOP, 2-UNIT SCI. LAB., 2-UNIT ICT LAB. (3STY) | BATCH 14 | 29359267.25 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 305601 | Caaoacan High School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 16974790.26 |  |  | Completed | 1
NC 2017 | TVL | Region I | Laoag City | 500056 | Balatong Integrated School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY) | BATCH 14 | 16974790.26 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City | 500742 | San Mateo IS | CITY OF LAOAG | 1 | 1 | 20 | 4STY20CL | BATCH 14 | 45000000 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City |  | Amarosa ES | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Laoag City |  | LAOAG CITY NAT. SCIENCE HS | LAOAG CITY (Capital) | 1 |  | 44 | 1 UNIT 4STY20CL, 2 UNITS 2STY8CL, 2 UNITS 2STY4CL | BATCH 14 | 102604410 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300170 | BAYOYONG NHS | BASISTA | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300173 | Bocboc East NHS | AGUILAR | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300181 | Cabayaoasan NHS | MANGATAREM | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300218 | Macarang National High School | MANGATAREM | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300234 | Pangasinan SAT | LINGAYEN (Capital) | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300241 | Polong NHS | BUGALLON | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region I | Pangasinan I, Lingayen | 300247 | Real NHS | URBIZTONDO | 2 | 1 | 1 | TVL | BATCH 14 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101924 | East Central Elementary School | San Fabian II | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 8975901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101924 | East Central Elementary School | SAN FABIAN | 4 |  | 4 | 2STY4CL | BATCH 14 | 9025901.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 9025901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 300289 | Binday NHS | SAN FABIAN | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 9075901.76 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101561 | San Juan ES | San Manuel | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 152003 | Silsilay ES | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101574 | San Isidro ES | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101710 | Calepaan Comm. Sch. | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9930491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101711 | Carosucan East ES | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101712 | Carosucan Norte ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12219814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101713 | Carosucan Sur ES | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 11593601.49 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101714 | Domanpot ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12234814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101715 | Narciso R. Ramos ES SPED Center | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12234814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101957 | Nagsaag ES | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9900491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101717 | Sobol ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101718 | Teofilo Gante ES | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101719 | Ariston Este ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101720 | Ariston-Bantug ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12249814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101721 | Asingan North CS | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9855491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101967 | Tacnien ES | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101723 | Don H. Velasco Comm. Sch. | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9840491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101724 | Don Teoderico Bauzon ES | Asingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101725 | Palaris ES | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 11295224.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101726 | San Vicente Este ES | Asingan | 6 | 1 | 6 | 3STY6CL | BATCH 14 | 16852737.06 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101950 | Cabacaraan ES | SAN MANUEL | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4079138.37 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101951 | Cabaritan ES | SAN MANUEL | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4079138.37 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101729 | Balungao CES | Balungao | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18747269.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101730 | Capulaan ES | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101979 | Sobol ES | SAN NICOLAS | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101731 | Esmeralda ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101732 | Irenio L. Guieb, Sr. ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101970 | Camindoroan ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101734 | Mabini ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102052 | San Vicente ES | SANTA MARIA | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101736 | Rajal-Angayan ES | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102106 | Gonzales ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101738 | San Aurelio ES | Balungao | 6 | 1 | 6 | 2STY6CL | BATCH 14 | 12881784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101846 | San Narciso Norte ES | NATIVIDAD | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102115 | Ricos ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4079138.37 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101981 | Villa Jose ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101741 | San Julian Elementary School | BALUNGAO | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101742 | San Leon ES | Balungao | 6 | 1 | 6 | 2STY6CL | BATCH 14 | 12926784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101744 | San Raymundo ES | Balungao | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101745 | Don Francisco Tuliao ES | BALUNGAO | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101831 | Barangobong ES | NATIVIDAD | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2883963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101833 | Calapugan ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12174814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101835 | Eulogio Arciaga ES | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.74 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101836 | Luna ES | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101837 | Natividad ES | Natividad | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18807269.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101841 | San Jose ES | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102096 | Cabangaran ES | UMINGAN | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101843 | San Macario Sur ES | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101843 | San Macario Sur ES | NATIVIDAD | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2883963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101847 | San Narciso Sur ES | Natividad | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101876 | Cabalaoangan ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101977 | San Rafael ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101879 | Guiling Coliling ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102000 | Baligayan ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101881 | Pangaoan ES | ROSALES | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 3958652.23 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101883 | Rosales South CES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101884 | San Bartolome ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102098 | Carosalesan ES | UMINGAN | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2883963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101886 | Tomana Elementary School SPED Center | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12174814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101887 | Acop ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102139 | Severo L. Castulo Elementary School | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101890 | Calanutan ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101891 | Capitan Tomas Pine ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101892 | Carmay ES | ROSALES | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9985491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101893 | Casanicolasan ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102081 | Calitlitan ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101897 | Salvacion ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102070 | Evangelista ES | TAYUG | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101899 | San Antonio ES | ROSALES | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101901 | San Pedro East ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101903 | San Vicente ES | Rosales | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102009 | Mantacdang ES | SAN QUINTIN | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101946 | An-Anonas ES | SAN MANUEL | 6 | 1 | 2 | 1STY2CL | BATCH 14 | 2803963.12 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101949 | Bomboaya ES | SAN MANUEL | 6 | 1 | 2 | 1STY2CL | BATCH 14 | 2803963.12 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101954 | Laclac Chayao School | SAN MANUEL | 6 | 1 | 2 | 1STY2CL | BATCH 14 | 2803963.12 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101959 | San Antonio ES | SAN MANUEL | 6 | 1 | 2 | 1STY2CL | BATCH 14 | 2803963.12 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101965 | Florencio P. Guzon E/S | SAN MANUEL | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101968 | Bulangit ES | SAN NICOLAS | 6 | 1 | 6 | 2STY4CL | BATCH 14 | 11723060.31 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101969 | Cabayawasan ES | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL | BATCH 14 | 2964463.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101973 | San Felipe Integrated School | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9985491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102067 | Tayug South CES | TAYUG | 6 | 1 | 10 | 2STY10CL | BATCH 14 | 21359808.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101983 | Cabitnongan ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101983 | Cabitnongan ES | SAN NICOLAS | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101986 | Dalumpinas ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101989 | Malico ES | San Nicolas | 6 | 1 | 6 | 2STY6CL | BATCH 14 | 12911784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102114 | Resurreccion ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101991 | Nining ES | SAN NICOLAS | 6 |  | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101992 | Pastoran ES | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101993 | Puyao ES | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101994 | San Antonio East ES | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101995 | San Antonio West ES | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102116 | San Juan ES | UMINGAN | 6 |  | 3 | 1STY3CL W/ TOILET | BATCH 14 | 4038652.23 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101997 | Sta. Maria ES | San Nicolas | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18792269.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101999 | Teofilo C. Quintin ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102001 | Bolintaguen ES | San Quintin | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102002 | Cabalaoangan ES | San Quintin | 6 | 1 | 12 | 2STY12CL | BATCH 14 | 24555652.16 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102008 | Lumayao IS | San Quintin | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12234814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102009 | Mantacdang ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9955491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102013 | Ungib ES | SAN QUINTIN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2883963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9840491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102045 | Namagbagan ES | Sta. Maria | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102050 | San Francisco ES | Sta. Maria | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102118 | San Vicente ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102054 | Sta. Maria East IS | Sta. Maria | 6 | 1 | 12 | 3STY12CL | BATCH 14 | 32295193.98 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102056 | Sta. Rosa ES | Sta. Maria | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102061 | Agno ES | TAYUG | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102064 | Legaspi ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102065 | Libertad ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102066 | Tayug Central Elementary School | TAYUG | 6 | 1 | 6 | 2STY6CL | BATCH 14 | 12921784.82 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102087 | Celestino L. Clariza Elementary School | UMINGAN | 6 |  | 4 | 2STY4CL | BATCH 14 | 12821784.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102067 | Tayug South CES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102068 | Tranchera ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102069 | C. Lichauco ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102071 | Lawak ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102073 | Panganiban ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102074 | Saleng ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102075 | Sto. Domingo ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102076 | Toketek ES | Tayug | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9870491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102091 | San Leon ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102081 | Calitlitan ES | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102083 | Esperanza ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 14 | 3958652.23 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102092 | Sta. Maria ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102089 | Mantacdang Elementary School | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102093 | Umingan CES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102093 | Umingan CES | Umingan | 6 |  | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102095 | Baracbac ES | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9900491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102097 | Cadiz ES | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9855491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102101 | Diaz Elementary School | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 10051615.22 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102104 | Don Alberto Vergara ES | UMINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102105 | Don Montano ES | Umingan | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18732269.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102107 | Luna Este ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 3065337.72 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102108 | Luna Weste ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 14 | 3958652.23 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102109 | Maseil-Seil Alo-O ES | Umingan | 6 | 1 | 6 | 2STY6CL | BATCH 14 | 12881784.83 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102110 | Nampalcan-Molina ES | Umingan | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 102047 | Pilar-Cauplasan ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101844 | San Maximo ES | NATIVIDAD | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9825491.94 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101964 | San Vicente West ES | SAN MANUEL | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2803963.13 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300273 | Angela Valdez Ramos NHS | ASINGAN | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 44096044.1 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300281 | Balungao NHS | BALUNGAO | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 40721811.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300296 | Cacabugaoan NHS | San Nicolas | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300299 | CAROSUCAN NORTE NATIONAL HIGH SCHOOL | ASINGAN | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12189814.42 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300318 | Lagasit NHS | SAN QUINTIN | 6 | 1 | 6 | 3STY6CL | BATCH 14 | 17707107.97 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300303 | Dalumpinas NHS | SAN NICOLAS | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 21902366.87 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18762269.29 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300313 | Flores NHS | UMINGAN | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 21332366.87 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG | 6 | 1 | 20 | 4STY20CL | BATCH 14 | 57379676.78 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 300324 | Malico NHS | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 9885491.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300338 | Prado NHS | UMINGAN | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 40601811.76 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300341 | Rosales NHS | ROSALES | 6 | 1 | 20 | 4STY20CL | BATCH 14 | 45549250.71 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300344 | San Aurelio NHS | BALUNGAO | 6 | 1 | 12 | 3STY12CL | BATCH 14 | 31708008.64 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300347 | San Isidro NHS | SAN NICOLAS | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 19132921.3 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300349 | San Juan NHS | San Manuel | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 18935527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300340 | Robert B. Estrella Memorial NHS | ROSALES | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 18890527.74 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300316 | La Paz NHS | UMINGAN | 6 | 1 | 12 | 3STY12CL | BATCH 14 | 32295193.98 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300352 | San Macario NHS | NATIVIDAD | 6 | 1 | 8 | 4STY8CL | BATCH 14 | 23093323.94 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300357 | San Rafael NHS | San Nicolas | 6 | 1 | 10 | 2STY10CL | BATCH 14 | 21284808.13 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300333 | Panganiban NHS | TAYUG | 6 | 1 | 6 | 3STY6CL | BATCH 14 | 14439095.7 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300300 | Carosucan Sur NHS | ASINGAN | 6 | 1 | 9 | 3STY9CL | BATCH 14 | 26425491.55 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 300364 | Toboy NHS | ASINGAN | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 39125382.24 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 321214 | Lumayao IS | San Quintin | 6 | 1 | 4 | 2STY4CL | BATCH 14 | 12234814.42 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan | 101720 | Ariston-Bantog ES | ASINGAN | 6 | 1 | 16 | 4STY16CL | BATCH 14 | 39863597 |  |  | Completed | 1
NC 2017 | SHS | Region I | Pangasinan II, Binalonan | 500384 | Sta. Cruz IS | SANTA MARIA | 6 | 1 | 8 | 2STY8CL | BATCH 14 | 18672269.29 |  |  | Completed | 1
NC 2017 | K10 | Region I | Pangasinan II, Binalonan |  | Bangar ES | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 14 | 2964463.13 |  |  | Completed | 1
NC 2017 | TVL | Region I | Ilocos Norte | 320816 | STA. ROSA NATIONAL HIGH SCHOOL | SARRAT | 1 | 1 | 4 | 2-UNITS SCI. LAB., 2-UNITS ICT LAB. (4STY) | BATCH 14 | 16974796.26 |  |  | Reverted | 0 | [10 empty] | Project is funded in CY2018 BEFF Funds
NC 2017 | K10 | Region I | Ilocos Norte | 100131 | Espiritu ES | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 14 | 2613745.92 |  |  | Reverted | 0
NC 2018 | K10 | Region I | Alaminos City | 101166 | Alaminos CS | Alaminos City | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11956168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101183 | Magsaysay ES | Alaminos City | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11836168.12 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101188 | Pangapisan IS | Alaminos City | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 24668047.73 |  |  | Completed | 1
NC 2018 | SHS | Region I | Alaminos City | 300157 | Alos NHS | CITY OF ALAMINOS | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 24838047.73 |  |  | Completed | 1
NC 2018 | SHS | Region I | Alaminos City | 300190 | Cayucay NHS | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12176168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101167 | Alos ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101168 | Amandiego ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101169 | Amangbangan ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101170 | Amangbangan ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101171 | Balayang ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101172 | Baleyadaan ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101173 | Bisocol ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101174 | Bolaney ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101175 | Bued ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101176 | Cabatuan ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101177 | Cayucay ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101178 | Dulacac ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101180 | Landoc ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9245901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101182 | Maawi ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9245901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101185 | Mona ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101186 | Palamis ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17534790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101187 | Pandan ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101189 | Pogo ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101190 | Polo ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101191 | Popantay ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101192 | Quibuar ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101193 | Sabangan ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101194 | San Jose ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101195 | San Roque ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101197 | Sta. Maria ES | CITY OF ALAMINOS | 1 | 1 | 8 | 2STY8CL | Batch 5 | 17434790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101198 | Tangcarang ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101199 | Tawintawin ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 101201 | Victoria ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City | 236001 | Linmansangan ES | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | SHS | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9395901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Alaminos City |  | LONGOS ELEMENTARY SCHOOL | CITY OF ALAMINOS | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9145901.76 |  |  | Completed | 1
NC 2018 | SHS | Region I | Batac City | 340747 | Gen. Artemio Ricarte SHS | CITY OF BATAC | 2 | 1 | 6 | 3STY6CL | Batch 3 | 12008512.5 |  |  | Completed | 1
NC 2018 | K10 | Region I | Candon City | 100436 | Candon South Central School | CITY OF CANDON | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 20058155.67 |  |  | Completed | 1 |  |  |  | 18AD0111 | 2018-06-28 | 2018-07-05 | 2018-07-17 | 2018-07-26 | 2018-08-02 | LINEAR CONSTRUCTION
NC 2018 | K10 | Region I | Candon City | 100445 | Patpata Elementary School | CITY OF CANDON | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8995901.76 |  |  | Completed | 1 |  |  |  | 18AD0114 | 2018-06-28 | 2018-07-05 | 2018-07-17 | 2018-07-26 | 2018-08-02 | FNDCC
NC 2018 | K10 | Region I | Dagupan City | 102159 | Mangin-Tebeng ES | Dagupan City | 4 | 1 | 6 | 2STY6CL | Batch 3 | 12502615.85 |  |  | Completed | 1 | [8 empty] | 2018-12-05 | ZOTA TRADING & CONST
NC 2018 | K10 | Region I | Dagupan City | 102163 | Bolosan ES | DAGUPAN CITY | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9493389.2 |  |  | Completed | 1 | [8 empty] | 2018-12-06 | KINGBHOI BUILDERS
NC 2018 | K10 | Region I | Dagupan City | 102170 | North Central Elementary School | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL | Batch 3 | 26234474.3 |  |  | Completed | 1 | [8 empty] | 2019-12-06 | BET CONST & SUPPLY
NC 2018 | K10 | Region I | Dagupan City | 102173 | T. Ayson Rosario ES | Dagupan City | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9689352.56 |  |  | Completed | 1 | [8 empty] | 2018-12-04 | KINGBHOI BUILDERS
NC 2018 | K10 | Region I | Dagupan City | 102180 | Suit ES | Dagupan City | 4 | 1 | 6 | 2STY6CL | Batch 3 | 12652615.85 |  |  | Completed | 1 | [8 empty] | 2018-12-05 | JG GARCIA CONST & SUPPLY
NC 2018 | SHS | Region I | Dagupan City | 300367 | Bonuan Buquig NHS | DAGUPAN CITY | 4 | 1 | 20 | 4STY20CL | Batch 3 | 49224271.75 |  |  | Completed | 1 | [8 empty] | 2018-12-05 | BET CONST & SUPPLY/ RA MATIAS CONST & DEVELOPERS (JV)
NC 2018 | TVL | Region I | Ilocos Norte | 300019 | Luzong NHS | Pagudpud | 1 | 1 | 6 | 2 UNITS 2 ICT, 2 UNITS SCI LAB, 2 UNITS REG WS | BATCH 1 | 32151222.49 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 300026 | Pasaleng NHS | Pagudpud | 1 | 1 | 2 | 2 storey (2 units Science Lab) | BATCH 1 | 9967011.96 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 320816 | Sta. Rosa NHS | Sarrat | 1 | 1 | 4 | 2 UNITS SCI LAB, 2 UNITS ICT LAB | BATCH 1 | 19733163.49 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Norte | 320807 | San Marcelino NHS | Dingras | 2 | 1 | 2 | 2STY4CL | BATCH 1 | 9784420 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Norte | 100131 | Espiritu ES | Dingras | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2705231.25 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Norte | 100145 | Escoda ES | Marcos | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9884420 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Norte | 100186 | Nalasin ES | Paoay | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9884420 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Norte | 100191 | Salbang ES | Paoay | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9884420 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 300015 | Dingras NHS | Dingras | 2 | 1 | 8 | 4STY8CL ( 2 SCI - 2 ICT) | BATCH 1 | 37513500 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 300020 | Marcos NHS | Marcos | 2 | 1 | 6 | 3STY6CL ( 2 REG- 2RWS) | BATCH 1 | 19544813.75 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 300022 | Nueva Era NHS | Nueva Era | 2 | 1 | 8 | 4STY8CL ( 2REG - 3RWS) | BATCH 1 | 37638500 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 300027 | Pinili NHS | Pinili | 2 | 1 | 4 | 4 STOREY (2units Regular Workshop, 1 unit Science Lab, 1 unit ICT) | BATCH 1 | 17209570.67 |  |  | Completed | 1 | [10 empty] | Completed as per POW and downloaded amount but not completed physically. Waiting for Buffer Funds
NC 2018 | TVL | Region I | Ilocos Norte | 300028 | San Nicolas NHS | San Nicolas | 2 | 1 | 8 | 4STY8CL ( 4 RWS) | BATCH 1 | 37638500 |  |  | Completed | 1
NC 2018 | TVL | Region I | Ilocos Norte | 320817 | Bagbag Solsona NHS | Solsona | 2 | 1 | 8 | 4STY8CL 2 REG - 3RWS) | BATCH 1 | 37563500 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | 20 | 4STY20CL | Batch 3 | 48150000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100453 | Anonang-Naguilian Comm. Sch. | CAOAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9350000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100456 | Caoayan CS | CAOAYAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12250000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100721 | Busiing ES | SAN ILDEFONSO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9200000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100771 | Garitan Community School | TAGUDIN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300038 | Bantay National High School | BANTAY | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 33741000 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300045 | Caoayan NHS | CAOAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9200000 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300055 | Lipit NHS | CABUGAO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9750000 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300058 | Manzante NHS | MAGSINGAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9300000 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300068 | Puro NHS, Caoayan | CAOAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9500000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 300087 | Tay-ac NHS | BANTAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9200000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100348 | Banucal ES | LIDLIDDA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100350 | Bequi-Walin ES | LIDLIDDA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11706168.02 |  |  | Completed | 1 | [9 empty] | VIPLEX Construction and Developer Corp.
NC 2018 | K10 | Region I | Ilocos Sur | 100356 | Lidlidda North CS | LIDLIDDA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100544 | Narvacan South CS (SPED Center) | NARVACAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11956168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100582 | Salcedo CS | SALCEDO (BAUGEN) | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17549790.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100711 | Nagsayaoan ES | SANTA MARIA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8965901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100712 | Nalvo ES | SANTA MARIA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11746168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100716 | Suso ES | SANTA MARIA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11731168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100775 | Pallogan ES | TAGUDIN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8983401.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100780 | Tagudin CS | TAGUDIN | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 20208155.67 |  |  | Completed | 1
NC 2018 | SHS | Region I | Ilocos Sur | 300086 | Tagudin NHS | TAGUDIN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9020901.76 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 320913 | KALUMSING INTEGRATED SCHOOL | SAN EMILIO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11706168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Ilocos Sur | 100663 | Sta. Catalina CS | SANTA CATALINA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 12250000 |  |  | Completed | 1
NC 2018 | SHS | Region I | La Union | 300095 | Bacnotan NHS | BACNOTAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 21335000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300114 | DOÑA FRANCISCA LACSAMANA DE ORTEGA MEMORIAL NATIONAL HIGH SCHOOL | BANGAR | 1 | 1 | 8 | 4STY REG WS | BATCH 1 | 28220000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300134 | San Francisco NHS | SUDIPEN | 1 | 1 | 8 | 4STY SCI/ ICT LAB | BATCH 1 | 29970000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1 | 1 | 8 | 4STY REG WS | BATCH 1 | 28000000 |  |  | Completed | 1
NC 2018 | SHS | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9265000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1 | 1 | 8 | 4STY REG WS | BATCH 1 | 28040000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 500471 | Bay-o Integrated School | SANTOL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9415000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 100929 | Pudoc ES | BAUANG | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 11680000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 101001 | Pugo Central School | PUGO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 16575000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 101091 | Balaoc ES | SANTO TOMAS | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 12000000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300093 | Aringay NHS | ARINGAY | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28120000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300104 | Caba NHS | CABA | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 27970000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300112 | Don Eulogio De Guzman MNHS | BAUANG | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28370000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300123 | Northern Naguilian National High School | NAGUILIAN | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28120000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300128 | Paringao National High School | BAUANG | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28120000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300129 | Pres. Elpidio. Quirino NHS | AGOO | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28120000 |  |  | Completed | 1
NC 2018 | SHS | Region I | La Union | 300130 | Don Eufemio F. Eriguel MNHS | AGOO | 2 | 1 | 12 | 4STY12CL | BATCH 1 | 36085000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 300131 | Pugo Central NHS | PUGO | 2 | 1 | 6 | 3STY6CL, TVL | BATCH 1 | 36195000 |  |  | Completed | 1
NC 2018 | TVL | Region I | La Union | 321007 | Manga National HS | ARINGAY | 2 | 1 | 4 | 4STY 4CL, TVL | BATCH 1 | 28620000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 321027 | AGOO NATIONAL VOCATIONAL HS | AGOO | 2 | 1 | 8 | 4STY4CL | BATCH 1 | 28120000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 500563 | SAN JULIAN IS | AGOO | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 21115000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 321027 | Agoo National Vocational High School | AGOO | 2 | 1 | 16 | 4STY16CL | Batch 3 | 48860000 |  |  | Completed | 1
NC 2018 | K10 | Region I | La Union | 321027 | Agoo National Vocational High School | AGOO | 2 |  | 9 | 3STY9TVL | Batch 3 | 54017000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Laoag City | 102187 | Calayab Elementary School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10298176.22 |  |  | Completed | 1
NC 2018 | K10 | Region I | Laoag City | 102200 | Navotas ES | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9095901.46 |  |  | Completed | 1
NC 2018 | K10 | Region I | Laoag City | 102205 | Bacsil Elementary School | LAOAG CITY (Capital) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10298176.22 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 300175 | Bolinao SOF | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 300215 | Luna National High School | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 300249 | Sampaloc National High School | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 321108 | Tupa Integrated School | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 321109 | Liwa Liwa Integrated School | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 500611 | Catubig Integrated School (High School) | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1 | 1 | 1 | TVL | BATCH 1 | 2730000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101422 | Calasiao Central School | CALASIAO | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12617261.26 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101427 | San Vicente ES | CALASIAO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9660481.08 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101538 | Bolaoit ES | MALASIQUI | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12432933.29 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300171 | Beleng NHS | BAYAMBANG | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 18348498.43 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300188 | Moises B. Rebamontan NHS | BAYAMBANG | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12617261.26 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300224 | Mapandan National High School | MAPANDAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9659936.93 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300259 | Tanolong National High School | BAYAMBANG | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18655134.92 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300154 | Agno NHS | AGNO | 1 | 1 | 12 | 4STY12CL | Batch 3 | 31869789.72 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 12 | 4STY12CL | Batch 3 | 31849789.72 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1 | 1 | 12 | 4STY12CL | Batch 3 | 31849789.72 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 500614 | Infanta Integrated School | INFANTA | 1 | 1 | 12 | 4STY12CL | Batch 3 | 31869789.72 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101164 | Sipitan ES | AGUILAR | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12174710.73 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101396 | Salomague Norte ES | BUGALLON | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12442615.85 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101398 | Tococ ES | BUGALLON | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9463389.2 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101482 | Libsong ES | LINGAYEN (Capital) | 2 | 1 | 15 | 3STY15CL | Batch 3 | 37216705.3 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101483 | Lingayen I CS | LINGAYEN (Capital) | 2 | 1 | 8 | 2STY8CL | Batch 3 | 18068893.88 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101488 | Quibaol ES | LINGAYEN (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101489 | Tonton Elementary School | LINGAYEN (Capital) | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12442614.85 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101490 | Tumbar ES | LINGAYEN (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9463387.2 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101491 | Baay ES | LINGAYEN (Capital) | 2 | 1 | 10 | 2STY10CL | Batch 3 | 21038840.46 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101512 | Wawa ES | LINGAYEN (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101587 | Olo ES | MANGATAREM | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101589 | Silag ES | MANGATAREM | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12440517.52 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101605 | Mangatarem II CS | MANGATAREM | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 101677 | Bayaoas IS | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101684 | Gueteb ES | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101693 | Urbiztondo I/S | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9463389.2 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan I, Lingayen | 300202 | Enrico T. Prado NHS | AGUILAR | 2 | 1 | 1 | TVL | Batch 3 | 4163527.73 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300203 | Estanza NHS | LINGAYEN (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9463389.2 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300209 | Labrador NHS | LABRADOR | 2 | 1 | 16 | 4STY16CL | Batch 3 | 38913402.54 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300236 | Urbiztondo National High School | URBIZTONDO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9413389.2 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300241 | Polong NHS | BUGALLON | 2 | 1 | 16 | 4STY16CL | Batch 3 | 38913402.54 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300243 | Quetegan NHS | MANGATAREM | 2 | 1 | 6 | 3STY6CL | Batch 3 | 14853269.48 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300267 | Irene Rayos Ombac NHS | BUGALLON | 2 | 1 | 8 | 4STY8CL | Batch 3 | 19304883.47 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 500366 | Tampac IS | AGUILAR | 2 | 1 | 8 | 4STY8CL | Batch 3 | 18265393.22 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101537 | Bogtong ES | MALASIQUI | 3 | 1 | 8 | 2STY8CL | Batch 3 | 18348498.43 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101543 | Lokeb Norte ES | MALASIQUI | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12628010.54 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300198 | Doyong-Malabago NHS | CALASIAO | 3 | 1 | 12 | 4STY12CL | Batch 3 | 34733050.93 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300225 | Maticmatic NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | Batch 3 | 19016834.34 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300228 | Nalsian-Tomling National High School | MALASIQUI | 3 | 1 | 12 | 4STY12CL | Batch 3 | 35249789.72 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300237 | Payas NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL | Batch 3 | 18659761.56 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300242 | Primicias NHS | MAPANDAN | 3 | 1 | 8 | 4STY8CL | Batch 3 | 18573802.38 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300159 | Arnedo NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300172 | Binabalian NHS | BOLINAO | 1 | 1 | 6 | 3STY6CL | Batch 5 | 14239515.1 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300175 | Bolinao SOF | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300194 | Dewey National High School | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300214 | Luciente II NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300215 | Luna National High School | BOLINAO | 1 | 1 | 6 | 3STY6CL | Batch 5 | 14239515.1 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300238 | Pilar NHS | BOLINAO | 1 | 1 | 6 | 3STY6CL | Batch 5 | 14239515.1 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101330 | Gayaman ES | BINMALEY | 2 | 1 | 4 | 2STY4CL | Batch 5 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101333 | Nagpalangan ES | BINMALEY | 2 | 1 | 4 | 2STY4CL | Batch 5 | 9669352.55 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101576 | Talospatang ES | MALASIQUI | 3 | 1 | 15 | 3STY15CL | Batch 5 | 37770113.22 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan I, Lingayen | 101648 | Maticmatic ES II | SANTA BARBARA | 3 | 1 | 9 | 3STY9CL | Batch 5 | 24468047.73 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102093 | Umingan Central ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4038652.23 |  |  | Completed | 1 |  |  |  | 18IA0236
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101737 | San Andres ES | BALUNGAO | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2964463.13 |  |  | Completed | 1 |  |  |  | 18IA0237
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101996 | Sapinit ES | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2964463.13 |  |  | Completed | 1 |  |  |  | 18IA0238
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101987 | East Central School | SAN NICOLAS | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4038652.23 |  |  | Completed | 1 |  |  |  | 18IA0239
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101972 | Salpad ES | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0240
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101971 | Cristobal Rodrigo ES | SAN NICOLAS | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0241
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102011 | San Quintin Central School | SAN QUINTIN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4038652.23 |  |  | Completed | 1 |  |  |  | 18IA0242
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102040 | Bal-loy Elementary School | SANTA MARIA | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0243
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102044 | Dalayap ES | SANTA MARIA | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0244
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101895 | Rizal ES | ROSALES | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0245
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101838 | Rizal ES | NATIVIDAD | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0246
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102048 | Pugot Elementary School | SANTA MARIA | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0247
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102050 | San Francisco ES | SANTA MARIA | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0248
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101738 | San Aurelio 3rd ES | BALUNGAO | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0249
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102078 | Annam ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0250
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102113 | Prado ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0251
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102077 | Zamora ES | TAYUG | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0252
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102086 | La Paz ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4038652.23 |  |  | Completed | 1 |  |  |  | 18IA0253
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102090 | Papallasen ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0254
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102112 | Pemienta ES | UMINGAN | 6 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 1 | 4038652.23 |  |  | Completed | 1 |  |  |  | 18IA0255
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102100 | Concepcion ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3065337.72 |  |  | Completed | 1 |  |  |  | 18IA0256
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102103 | Diket ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 3065337.72 |  |  | Completed | 1 |  |  |  | 18IA0257
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102106 | Gonzales ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0258
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102080 | Cabalitian ES | UMINGAN | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0259
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102042 | Caboluan ES | SANTA MARIA | 6 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 1 | 2803963.13 |  |  | Completed | 1 |  |  |  | 18IA0260
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101791 | Babasit ES | MANAOAG | 4 | 1 | 8 | 2STY8CL | Batch 3 | 18012895.44 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101795 | Cabanbanan ES | MANAOAG | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9677038.16 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101809 | Bari ES | MANGALDAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9677038.16 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101815 | Mangaldan Central School | MANGALDAN | 4 | 1 | 8 | 2STY8CL | Batch 3 | 17802641.68 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101819 | Embarcadero ES | MANGALDAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9657038.16 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101821 | Lanas ES | MANGALDAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9657038.16 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101828 | Salay ES | MANGALDAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9617038.16 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101911 | North Central ES | SAN FABIAN | 4 | 1 | 10 | 2STY10CL | Batch 3 | 22704033.38 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101922 | Binday ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL | Batch 3 | 18002845.19 |  |  | Completed | 1
NC 2018 | SHS | Region I | Pangasinan II, Binalonan | 300272 | Ambalangan Dalin NHS | SAN FABIAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9443389.2 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300274 | ANONANG NATIONAL HIGH SCHOOL | SAN FABIAN | 4 | 1 | 6 | 3STY 12 (2 Reg Workshop, 2 Sci Lab, 2 ICT) | Batch 3 | 29708097.07 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300280 | Baguinay NHS | MANAOAG | 4 | 1 | 6 | 2 UNITS 3STY 6 (1 Reg. Workshop, 2 ICT) | Batch 3 | 30245090.52 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300294 | Cabanbanan NHS | MANAOAG | 4 | 1 | 8 | 2 UNITS 4STY 8 (4 Sci Lab, 4 ICT) | Batch 3 | 37275644.69 |  |  | Completed | 1
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 500388 | Gueguesangen IS | MANGALDAN | 4 | 1 | 4 | 4STY8CL, ( 2 SCI LAB, 2 ICT) | Batch 3 | 18680997.87 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102014 | Agat ES | SISON | 5 | 1 | 4 | 2STY4CL | Batch 3 | 11345634.1 |  |  | Completed | 1 |  |  | 18IA0337
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102137 | Labit ES | VILLASIS | 5 | 1 | 6 | 2STY6CL | Batch 3 | 15776534.4 |  |  | Completed | 1 |  |  | 18IA0338
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 300337 | Pinmilapil NHS | SISON | 5 | 1 | 4 | 2STY4CL | Batch 3 | 11345634.1 |  |  | Completed | 1 |  |  | 18IA0339
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101716 | Sanchez-Cabalitian ES | ASINGAN | 6 | 1 | 4 | 2STY4CL | Batch 3 | 11345634.1 |  |  | Completed | 1 |  |  | 18IA0340
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101728 | Toboy ES | ASINGAN | 6 | 1 | 6 | 2STY6CL | Batch 3 | 18656534.4 |  |  | Completed | 1 |  |  | 18IA0341
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101877 | Camangaan ES | ROSALES | 6 | 1 | 4 | 2STY4CL | Batch 3 | 13505634.1 |  |  | Completed | 1 |  |  | 18IA0358
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102004 | Don Luis Domingo Sr. ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | Batch 3 | 13505634.1 |  |  | Completed | 1 |  |  | 18IA0342
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102013 | Ungib ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL | Batch 3 | 13505634.1 |  |  | Completed | 1 |  |  | 18IA0343
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102042 | Caboluan ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL | Batch 3 | 13505634.1 |  |  | Completed | 1 |  |  | 18IA0344
NC 2018 | SHS | Region I | Pangasinan II, Binalonan | 300277 | Ariston-Bantog NHS | ASINGAN | 6 | 1 | 16 | 4STY16CL | Batch 3 | 45082536.4 |  |  | Completed | 1 |  |  | 18IA0359
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | 2 | 2UW | Batch 3 | 10633754.3 |  |  | Completed | 1 |  |  | 18IA0345
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6 | 1 | 16 | 4STY16CL (2SCI, 2ICT, 4RW) | Batch 3 | 45082536.4 |  |  | Completed | 1 |  |  | 18IA0346
NC 2018 | TVL | Region I | Pangasinan II, Binalonan | 300322 | Luciano Millan National HS | ASINGAN | 6 |  | 8 | 4STY8CL (2SCI, 2ICT) | Batch 3 | 22641268.2 |  |  | Completed | 1 |  |  | 18IA0347
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101910 | Mabilao ES | SAN FABIAN | 4 | 1 | 4 | 2STY4CL | Batch 5 | 9853001.51 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101912 | Pangulong Marcos ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL | Batch 5 | 18002845.19 |  |  | Completed | 1
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101700 | Laoac ES | ALCALA | 5 | 1 | 6 | 3STY6CL | Batch 5 | 18393571.7 |  |  | Completed | 1 |  |  |  | 18IA0353
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101781 | Cabu-Cala ES | LAOAC | 5 | 1 | 6 | 2STY6CL | Batch 5 | 14914618.82 |  |  | Completed | 1 |  |  |  | 18IA0351
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101861 | Rosario ES | POZORRUBIO | 5 | 1 | 6 | 2STY6CL | Batch 5 | 14914618.82 |  |  | Completed | 1 |  |  |  | 18IA0349
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101869 | Imbalbalatong ES | POZORRUBIO | 5 | 1 | 10 | 2STY10CL | Batch 5 | 24750672.29 |  |  | Completed | 1 |  |  |  | 18IA0355
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 101874 | Sugcong ES | POZORRUBIO | 5 | 1 | 6 | 2STY6CL | Batch 5 | 14914618.82 |  |  | Completed | 1 |  |  |  | 18IA0350
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102125 | Puelay ES | VILLASIS | 5 | 1 | 8 | 2STY8CL | Batch 5 | 22551393.94 |  |  | Completed | 1 |  |  |  | 18IA0357
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102126 | Villasis I Central School SPED Center | VILLASIS | 5 | 1 | 4 | 2STY4CL | Batch 5 | 12243956.15 |  |  | Completed | 1 |  |  |  | 18IA0354
NC 2018 | K10 | Region I | Pangasinan II, Binalonan | 102145 | San Blas ES | VILLASIS | 5 | 1 | 6 | 2STY6CL | Batch 5 | 14914618.82 |  |  | Completed | 1 |  |  |  | 18IA0352
NC 2018 | K10 | Region I | San Carlos City | 102221 | Pagal Elementary School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9782430.15 |  |  | Completed | 1 | [9 empty] | Leza Construction and Supply
NC 2018 | K10 | Region I | San Carlos City | 102222 | Pangalangan Elementary School | SAN CARLOS CITY | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1
NC 2018 | K10 | Region I | San Carlos City | 102224 | Quintong Elementary School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9782430.15 |  |  | Completed | 1 | [9 empty] | MCB Construction and Supply
NC 2018 | K10 | Region I | San Carlos City | 102233 | Payapa Elementary School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9782430.15 |  |  | Completed | 1 | [9 empty] | Manimelds Construction & Iron Works
NC 2018 | SHS | Region I | San Carlos City | 102234 | Tarece Integrated School | SAN CARLOS CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9782430.15 |  |  | Completed | 1 | [9 empty] | JEUSMACK Builders & Construction Supply
NC 2018 | TVL | Region I | San Carlos City | 300391 | Turac NHS | SAN CARLOS CITY | 3 | 1 | 4 | 4STY 4 SCI LAB | BATCH 1 | 22346844.95 |  |  | Completed | 1
NC 2018 | K10 | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 36435000 |  |  | Completed | 1
NC 2018 | K10 | Region I | Urdaneta City | 102297 | Labit East ES | CITY OF URDANETA | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 9995583.9 |  |  | Completed | 1 |  |  | 18IA0261
NC 2018 | SHS | Region I | Urdaneta City | 300405 | Lananpin NHS | CITY OF URDANETA | 5 | 1 | 16 | 4STY16CL | BATCH 1 | 41816583.9 |  |  | Completed | 1 |  |  | 18IA0262
NC 2018 | TVL | Region I | Urdaneta City | 300410 | Urdaneta City NHS | CITY OF URDANETA | 5 | 1 | 8 | 4STY8CL (2 ICT 2 SCI) | BATCH 1 | 22805560.65 |  |  | Completed | 1 |  |  | 18IA0263
NC 2018 | SHS | Region I | Vigan City | 300052 | Ilocos Sur NHS | CITY OF VIGAN (Capital) | 1 | 1 | 8 | 4STY8CL | Batch 3 | 19320000 |  |  | Completed | 1
NC 2019 | K10 | Region I | Batac city | 100079 | Magnuang ES | Batac City | 2 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Candon City | 100433 | Calaoa-an Elementary School | Candon City | 2 | 1 | 4 | 2STY4CL |  | 11111557.9107 |  | completed | 1 |  |  |  | P00370048LZ-CW1 | 8/28/2019 | 2019-09-05 | 2019-09-18 | 2019-09-24 | 2019-10-03 |  |  | 0
NC 2019 | K10 | Region I | Candon City | 1004388 | Felomino G. Gagarin ES | CITY OF CANDON | 2 | 1 | 2 | 1STY2CL |  | 3755459.4455 |  | completed | 1 |  |  |  | P00370049LZ-CW1 | 8/23/2019 | 2019-08-30 | 2019-09-11 | 2019-09-24 | 2019-10-03 |  |  | 0
NC 2019 | K10 | Region I | Dagupan City | 102154 | Bacayao Sur ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL |  | 30578805.7434 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Dagupan City | 500053 | East Central IS | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL |  | 26610436.6411 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Dagupan City | 102149 | Juan L. Siapno ES | Dagupan City | 4 | 1 | 9 | 3STY9CL |  | 25472507.7231 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Dagupan City | 102181 | Juan P. Guadiz ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL |  | 26651925.5948 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Dagupan City | 102179 | Salapingao ES | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL |  | 26651925.5948 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Dagupan City | 102152 | West Central ES I | DAGUPAN CITY | 4 | 1 | 9 | 3STY9CL |  | 26651925.5948 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Norte | 100198 | Dadaeman Elementary School | Pasuquin | 1 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [10 empty] | completed as per POW and funds downloaded but not physically completed, waiting for release of buffer funds | 0
NC 2019 | K10 | Region I | Ilocos Norte | 100204 | Nagabungan ES | Pasuquin | 1 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [10 empty] | completed as per POW and funds downloaded but not physically completed, waiting for release of buffer funds | 0
NC 2019 | SHS | Region I | Ilocos Norte | 300029 | Sarrat National High School | SARRAT | 1 | 1 | 20 | 4STY20CL |  | 48270375 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Norte | 100214 | Tabungao PS | Pasuquin | 1 | 1 | 3 | 1STY3CL |  | 5695613.0538 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Norte | 100185 | Nagbacalan ES | PAOAY | 2 | 1 | 3 | 1STY3CL |  | 5858371.6957 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | 4 | 2STY4CL |  | 9589937.5763 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100513 | Ambulogan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100514 | Anteng PS | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100702 | Babal-lasioan ES | SANTA MARIA | 2 | 1 | 6 | 2STY6CL |  | 17866914.0053 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100516 | Banglayan Elementary School | NARVACAN | 2 | 1 | 4 | 2STY4CL |  | 10096781.8719 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100517 | Bulanos ES | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100536 | Cagayungan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100537 | Codoog ES | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100521 | Kakaldingan ES | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100393 | Macaoayan Comm. Sch. | BURGOS | 2 | 1 | 4 | 2STY4CL |  | 10096781.8719 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100395 | Padayao ES | BURGOS | 2 | 1 | 4 | 2STY4CL |  | 8995845.54 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Ilocos Sur | 100527 | Parparia Elementary School | NARVACAN | 2 | 1 | 3 | 1STY3CL |  | 5073993.8412 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | La Union | 101085 | Santol Central School | SANTOL | 1 | 1 | 4 | 2STY4CL |  | 9822142.12 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | La Union | 300141 | Santol Voc'l. HS - Liguay Annex | SANTOL | 1 | 1 | 2 | 1STY2CL |  | 4110250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | La Union | 100940 | Caba CES | CABA | 2 | 1 | 4 | 2STY4CL |  | 9822142.12 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | La Union | 101002 | San Luis ES | PUGO | 2 | 1 | 8 | 2STY8CL |  | 20116843.8429 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Laoag City | 102210 | Lagui-Sail Elementary School | Laoag City | 1 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101136 | Baruan ES | Agno | 1 | 1 | 4 | 2STY4CL |  | 11111557.9107 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101214 | Mal-ong ES | Anda | 1 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101391 | Laguit Centro ES | Bugallon I | 2 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101337 | Tombor ES | Binmaley | 2 | 1 | 6 | 3STY6CL |  | 15834261.5565 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101299 | Paragos ES | BAYAMBANG | 3 | 1 | 4 | 1STY4CL |  | 7811162.2676 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101557 | Biba ES | Malasiqui | 3 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101565 | J.C. Macaranas ES | Malasiqui | 3 | 1 | 5 | 1STY5CL |  | 9492688.4197 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101338 | Arnedo ES | BOLINAO | 1 | 1 | 6 | 2STY6CL |  | 13088808.4401 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300161 | Balingasay NHS | BOLINAO | 1 | 1 | 8 | 4STY8CL |  | 20916395.4873 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO | 1 | 1 | 8 | 4STY8CL |  | 20916395.4873 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101402 | Cabaruan ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101343 | Cabuyao Elementary School | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 9970766.5144 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101349 | Estanza ES | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 9970766.5144 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101370 | Yabyaban Elementary School | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 9970766.5144 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101408 | Ilio-Ilio ES | BURGOS | 1 | 1 | 3 | 1STY3CL |  | 5858371.6957 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101352 | Ilog-Malino ES | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 9970766.5144 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300207 | ILOG-MALINO NATIONAL HIGH SCHOOL | BOLINAO | 1 | 1 | 8 | 2STY8CL |  | 19082377.2357 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS (Pogoruac NHS) | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101353 | Lambes ES | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 9970766.5144 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101410 | Poguruac ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101411 | San Miguel ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101413 | Sapa Pequeña ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3905581.1338 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101414 | Tambacan ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101406 | Don Antonio Bonilla Mem. ES | BURGOS | 1 | 1 | 2 | 1STY2CL |  | 3196070.25 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101420 | Bued ES | CALASIAO | 3 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101416 | Balani-Parongking ES | CALASIAO | 3 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101629 | Balingueo Elementary School | SANTA BARBARA | 3 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101403 | Cabongaoan ES | BURGOS | 1 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300163 | Banaoang NHS | SANTA BARBARA | 3 | 1 | 8 | 4STY8CL |  | 18925955.3261 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101536 | Barang ES | MALASIQUI | 3 | 1 | 4 | 2STY4CL |  | 11373998.1852 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300178 | Buenlag NHS | CALASIAO | 3 | 1 | 8 | 4STY8CL |  | 18925955.3161 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101421 | Cabilocaan ES | CALASIAO | 3 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101630 | Dalongue ES | SANTA BARBARA | 3 | 1 | 4 | 2STY4CL |  | 10297281.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300193 | Daniel Maramba NHS | SANTA BARBARA | 3 | 1 | 9 | 3STY9CL |  | 23718244.5821 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101432 | Doyong Malabago ES | CALASIAO | 3 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101645 | Leet Elementary School | SANTA BARBARA | 3 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101434 | Longos Elementary School | CALASIAO | 3 | 1 | 6 | 2STY6CL |  | 16342899.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101437 | Mancup ES | CALASIAO | 3 | 1 | 4 | 2STY4CL |  | 10297281.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101634 | Maronong ES | SANTA BARBARA | 3 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 4 | 2STY4CL |  | 10096781.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 9 | 3STY9CL |  | 24529217.8493 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101438 | Nagsaing Elementary School | CALASIAO | 3 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101424 | Nalsian Bacayao ES | CALASIAO | 3 | 1 | 4 | 2STY4CL |  | 10297281.8671 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101651 | Payas ES | SANTA BARBARA | 3 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan I, Lingayen | 101440 | Talibaew ES | CALASIAO | 3 | 1 | 9 | 3STY9CL |  | 24018994.5821 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101904 | Bigbiga ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL |  | 18686460.442 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101925 | Jose N. Juguilon ES | SAN FABIAN | 4 | 1 | 4 | 2STY4CL |  | 10270104.5533 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101928 | Longos ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL |  | 18047852.303 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101929 | Longos Proper ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL |  | 18047852.303 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101913 | Rabon ES | SAN FABIAN | 4 | 1 | 4 | 2STY4CL |  | 10310723.4373 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101915 | Sanitas ES | SAN FABIAN | 4 | 1 | 8 | 2STY8CL |  | 18706769.8789 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan II, Binalonan | 300295 | Cabilaoan Agro-Industrial HS | LAOAC | 5 | 1 | 6 | 2STY6CL |  | 14562524.0714 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan II, Binalonan | 300319 | Laoac NHS | LAOAC | 5 | 1 | 6 | 2STY6CL |  | 14562524.0714 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101786 | Lebueg ES | LAOAC | 5 | 1 | 6 | 2STY6CL |  | 14562524.0714 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan II, Binalonan | 500376 | Macayo IS | ALCALA | 5 | 1 | 6 | 3STY6CL |  | 17506985.0969 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101873 | Palacpalac ES | POZORRUBIO | 5 | 1 | 4 | 2STY4CL |  | 11373998.1852 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 102037 | Pinmilapil ES | SISON | 5 | 1 | 4 | 2STY4CL |  | 11373998.1852 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 102125 | Puelay ES | VILLASIS | 5 | 1 | 6 | 2STY6CL |  | 23551696.2296 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan II, Binalonan | 321203 | San Antonio NHS | SANTO TOMAS | 5 | 1 | 6 | 3STY6CL |  | 17641149.7321 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 102060 | San Jose ES | SANTO TOMAS | 5 | 1 | 6 | 3STY6CL |  | 20584781.9809 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101706 | San Pedro Ili ES | ALCALA | 5 | 1 | 6 | 2STY6CL |  | 13514273.7508 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN | 5 | 1 | 12 | 4STY12CL |  | 39640816.8649 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101768 | Vacante ES | BINALONAN | 5 | 1 | 6 | 2STY6CL |  | 14562524.0714 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 152004 | Yatyat Annex Elementary School | LAOAC | 5 | 1 | 4 | 2STY4CL |  | 11373998.1852 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 102044 | Dalayap ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL |  | 11719416.1868 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101895 | Rizal Elementary School | ROSALES | 6 | 1 | 4 | 2STY4CL |  | 11719416.1868 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101972 | Salpad ES | SAN NICOLAS | 6 | 1 | 4 | 2STY4CL |  | 11848318.3786 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101842 | San Macario Norte Elementary School | NATIVIDAD | 6 | 1 | 4 | 2STY4CL |  | 11719416.1868 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 101999 | Teofilo C. Quintin ES | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL |  | 11719416.1868 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Pangasinan II, Binalonan | 102077 | Zamora ES | TAYUG | 6 | 1 | 4 | 2STY4CL |  | 11719416.1868 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | San Carlos City | 102250 | TALANG CENTRAL SCHOOL | San Carlos City | 3 | 1 | 4 | 2STY4CL |  | 10025000 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | San Fernando City | 500602 | South Central IS | San Fernando City | 1 | 1 | 6 | 2STY6CL |  | 21672302.0811 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region I | Urdaneta City | 102289 | Camantiles ES | Urdaneta City | 5 | 1 | 2 | 1STY2CL |  | 4711750 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region I | Vigan City | 300052 | Ilocos Sur NHS | Vigan City | 1 | 1 | 4 | 2STY4CL |  | 11111557.9107 |  | completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region I | Alaminos City | 101166 | Alaminos City Central School | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL |  | 17866914.01 |  |  | Completed | 1
NC 2020 | K10 | Region I | Alaminos City | 101183 | Magsaysay ES | CITY OF ALAMINOS | 1 | 1 | 6 | 2STY6CL |  | 17866914.01 |  |  | Completed | 1
NC 2020 | K10 | Region I | Alaminos City | 101196 | SAN VICENTE ES | ALAMINOS CITY | 1 | 1 | 4 | 2STY4CL |  | 12368194.24 |  |  | Completed | 1
NC 2020 | K10 | Region I | Batac City | 305491 | CITY OF BATAC NHS RAYURAY | Batac City | 2 | 1 | 4 | 2STY4CL |  | 10025000 |  |  | Completed | 1
NC 2020 | SHS | Region I | Candon City | 322601 | CANDON INFORMATION TECHNOLOGY NHS | Candon City | 2 | 1 | 8 | 4STY8CL |  | 20451000 |  |  | Completed | 1
NC 2020 | SHS | Region I | DAGUPAN CITY | 500054 | FEDERICO N. CERALDE IS | DAGUPAN CITY | 4 | 1 | 4 | 2STY4CL |  | 12267002.65 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100046 | Banban Elementary School | BANGUI | 1 | 1 | 3 | 1STY3CL |  | 6265625 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100054 | Paddagan ES | BANGUI | 1 | 1 | 4 | 2STY4CL |  | 18045000 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100100 | Ablan Community School | BURGOS | 1 | 1 | 3 | 1STY3CL |  | 6265625 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100037 | Paltit ES | BADOC | 2 | 1 | 6 | 2STY6CL |  | 16758483.7 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100120 | Dingras Central ES | DINGRAS | 2 | 1 | 6 | 2STY6CL |  | 16486288.84 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100158 | Tabucbuc Elementary School | MARCOS | 2 | 1 | 6 | 2STY6CL |  | 16636663.84 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100241 | Don Mariano Marcos Mem. Sch. | PINILI | 2 | 1 | 4 | 1STY4CL |  | 8935282.5 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Norte | 100252 | Barabar ES | SAN NICOLAS | 2 | 1 | 6 | 2STY6CL |  | 16242649.1 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Sur | 100402 | Cabugao North Central School | CABUGAO | 1 | 1 | 6 | 2STY6CL |  | 18045000 |  |  | Completed | 1
NC 2020 | SHS | Region I | Ilocos Sur | 300068 | Puro NHS, Caoayan | CAOAYAN | 1 | 1 | 4 | 2STY4CL |  | 12030000 |  |  | Completed | 1
NC 2020 | SHS | Region I | Ilocos Sur | 500348 | San Vicente IS | SAN VICENTE | 1 | 1 | 12 | 4STY12CL |  | 33731027.92 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Sur | 100624 | Nagpanaoan Community School | SANTA | 2 | 1 | 2 | 1STY2CL |  | 4611500 |  |  | Completed | 1
NC 2020 | K10 | Region I | Ilocos Sur | 100627 | Santa CS | SANTA | 2 | 1 | 8 | 2STY8CL |  | 20193567.12 |  |  | Completed | 1
NC 2020 | K10 | Region I | La Union | 101078 | Corrooy ES | SANTOL | 1 | 1 | 4 | 2STY4CL |  | 12010892.52 |  |  | Completed | 1
NC 2020 | SHS | Region I | La Union | 300103 | Butubut National High School | BALAOAN | 1 | 1 | 4 | 2STY4CL |  | 12512536.83 |  |  | Completed | 1
NC 2020 | SHS | Region I | La Union | 300117 | Duplas NHS | SUDIPEN | 1 | 1 | 6 | 2STY6CL |  | 18721130.07 |  |  | Completed | 1
NC 2020 | SHS | Region I | La Union | 500356 | Lipay Integrated School | SAN GABRIEL | 1 | 1 | 4 | 2STY4CL |  | 12350780.58 |  |  | Completed | 1
NC 2020 | SHS | Region I | La Union | 300112 | Don Eulogio De Guzman MNHS | BAUANG | 2 | 1 | 6 | 3STY6CL |  | 22556250 |  |  | Completed | 1
NC 2020 | K10 | Region I | Laoag City | 102209 | Gabaldon ES | LAOAG CITY | 1 | 1 | 3 | 1STY3CL |  | 6817000 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101144 | Patar ES | AGNO | 1 | 1 | 2 | 1STY2CL |  | 3938035.51 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101218 | San Jose ES | ANDA | 1 | 1 | 2 | 1STY2CL |  | 3938035.51 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101234 | Centro Toma ES | BANI | 1 | 1 | 4 | 2STY4CL |  | 11106460.06 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101359 | Patar ES | BOLINAO | 1 | 1 | 4 | 2STY4CL |  | 11027500 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101456 | Uli ES | DASOL | 1 | 1 | 2 | 1STY2CL |  | 3938035.51 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101457 | Viga ES | DASOL | 1 | 1 | 2 | 1STY2CL |  | 3938035.51 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101671 | Sual CS | SUAL | 1 | 1 | 4 | 2STY4CL |  | 11027500 |  |  | Completed | 1
NC 2020 | SHS | Region I | Pangasinan I, Lingayen | 500609 | Barlo Integrated School | MABINI | 1 | 1 | 6 | 2STY6CL |  | 17917039.01 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101325 | Basing Elementary School | BINMALEY | 2 | 1 | 4 | 2STY4CL |  | 12236411.62 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101336 | Sta. Rosa ES | BINMALEY | 2 | 1 | 6 | 3STY6CL |  | 19621932.5 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101485 | Matalava ES | LINGAYEN (Capital) | 2 | 1 | 4 | 2STY4CL |  | 10927250 |  |  | Completed | 1
NC 2020 | SHS | Region I | Pangasinan I, Lingayen | 300233 | Pangasinan National High School | LINGAYEN | 2 | 1 | 12 | 4STY12CL |  | 31600467.58 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan I, Lingayen | 101638 | Tuliao ES | SANTA BARBARA | 3 | 1 | 6 | 2STY6CL |  | 16283255.72 |  |  | Completed | 1
NC 2020 | SHS | Region I | Pangasinan I, Lingayen | 300176 | Botao NHS | STA. BARBARA | 3 | 1 | 8 | 4STY8CL |  | 19047500 |  |  | Completed | 1
NC 2020 | SHS | Region I | Pangasinan I, Lingayen | 300242 | Primicias NHS | MAPANDAN | 3 | 1 | 8 | 4STY8CL |  | 18973270.21 |  |  | Completed | 1
NC 2020 | SHS | Region I | Pangasinan I, Lingayen | 500365 | Mabulitec Integrated School | MALASIQUI | 3 | 1 | 8 | 4STY8CL |  | 19047500 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101799 | Lipit Elementary School | MANAOAG | 4 | 1 | 2 | 1STY2CL |  | 5012500 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101829 | Talogtog ES | MANGALDAN | 4 | 1 | 8 | 2STY8CL |  | 20341601.46 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101694 | Alcala CS | ALCALA | 5 | 1 | 6 | 2STY6CL |  | 16725475.44 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101703 | Pindangan West ES | ALCALA | 5 | 1 | 6 | 2STY6CL |  | 16725475.44 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzales ES | Sto Tomas | 5 | 1 | 8 | 2units 2STY4CL |  | 27630047.4 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 102122 | Maburac ES | VILLASIS | 5 | 1 | 4 | 2STY4CL |  | 12404150.27 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101756 | Biinalonan North CS SPED Center (Binalonan North Central Elementary School) | BINALONAN | 5 | 1 | 20 | 4STY20CL |  | 54633608.97 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 101961 | San Juan ES | SAN MANUEL | 6 | 1 | 6 | 2STY6CL |  | 14720475.44 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 102011 | San Quintin Central School | SAN QUINTIN | 6 | 1 | 4 | 2STY4CL |  | 13978424.37 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA | 6 | 1 | 4 | 2STY4CL |  | 11990091.19 |  |  | Completed | 1
NC 2020 | K10 | Region I | Pangasinan II, Binalonan | 102093 | Umingan Central School | UMINGAN | 6 | 1 | 12 | 4STY12CL |  | 34352548.24 |  |  | Completed | 1
NC 2020 | K10 | Region I | San Carlos City | 102254 | Balite Sur Elementary School | San Carlos City | 3 | 1 | 6 | 2STY6CL |  | 16283255.72 |  |  | Completed | 1
NC 2020 | TVL | Region I | San Fernando City | 321001 | La Union NHS - Sacyud Annex | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 4 | 2STY TECHVOC |  | 18560105.28 |  |  | Completed | 1
NC 2020 | K10 | Region I | San Fernando City | 500480 | Pagudpud IS | San Fernando City (Capital) | 1 | 1 | 4 | 2STY4CL |  | 10526250 |  |  | Completed | 1
NC 2020 | SHS | Region I | Urdaneta City | 300395 | Cabaruan NHS | CITY OF URDANETA | 5 | 1 | 4 | 4STY8CL (2SCI, 2ICT) |  | 23798301.34 |  |  | Completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101167 | Alos ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101168 | Amandiego ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101169 | Amangbangan ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101170 | Amangbangan ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101171 | Balayang ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101172 | Baleyadaan ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101173 | Bisocol ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101174 | Bolaney ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101175 | Bued ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101176 | Cabatuan ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101177 | Cayucay ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101178 | Dulacac ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101180 | Landoc ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101181 | Lucap ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101182 | Maawi ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101185 | Mona ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101186 | Palamis ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101187 | Pandan ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 646662.3343 | 645049.71 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101189 | Pogo ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101190 | Polo ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101191 | Popantay ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101192 | Quibuar ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101193 | Sabangan ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101194 | San Jose ES | CITY OF ALAMINOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101195 | San Roque ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101197 | Sta. Maria ES | CITY OF ALAMINOS | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 638198.8583 | 636607.34 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101198 | Tangcarang ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101199 | Tawintawin ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 101201 | Victoria ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | K10 | Region I | Alaminos City | 236001 | Linmansangan ES | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 589120.2177 | 587651.09 |  | completed | 1
NC 2021 | SHS | Region I | Alaminos City | 322701 | Ildefonso Quimson Community HS | CITY OF ALAMINOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 808817.1303 | 806800.13 |  | completed | 1
NC 2021 | SHS | Region I | Batac City | 340747 | Gen. Artemio Ricarte SHS | CITY OF BATAC | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 11328250 | 11300000 |  | completed | 1
NC 2021 | K10 | Region I | Dagupan City | 102161 | Tambac ES | DAGUPAN CITY | 4 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1203000 | 1200000 |  | completed | 1
NC 2021 | K10 | Region I | Dagupan City | 102166 | Leon-Francisco Maramba ES | DAGUPAN CITY | 4 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1203000 | 1200000 |  | completed | 1
NC 2021 | K10 | Region I | Dagupan City | 102168 | Gen. Gregorio del Pilar ES | DAGUPAN CITY | 4 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1203000 | 1200000 |  | completed | 1
NC 2021 | K10 | Region I | Dagupan City | 102171 | Sabangan ES | DAGUPAN CITY | 4 | 1 | 9 | Construction/Completion (3STY9CL) |  | 1203000 | 1200000 |  | completed | 1
NC 2021 | SHS | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 | 1 | 4 | Construction/Completion (4-UNITS REGULAR WORKSHOP (2STY)) |  | 1702974.5393 | 1698727.72 |  | completed | 1
NC 2021 | SHS | Region I | Ilocos Norte | 300024 | PAGUDPUD NHS | PAGUDPUD | 1 |  | 4 | Construction/Completion (2-UNITS SCI. LAB., 2-UNITS ICT LAB. (2STY)) |  | 1364123.6246 | 1360721.82 |  | completed | 1
NC 2021 | SHS | Region I | Ilocos Norte | 300027 | Pinili NHS | Pinili | 2 | 1 | 8 | 4STY8CL (4 UNITS REGULAR WORKSHOP BLDG) |  | 12380675.7631 | 12349801.26 |  | completed | 1
NC 2021 | SHS | Region I | Ilocos Sur | 300043 | Cabugao NHS | CABUGAO | 1 | 1 | 12 | Construction/Completion (3STY12CL) |  | 32083485.071 | 32003476.38 | 31345301.52 | COMPLETED | 1 | [6 empty] | 2021-09-27 |  |  |  | Suspended; Revise Expiry Date Feb 3, 2023; Reported DPWH Issued Calibrated action & Liquidated damages
NC 2021 | SHS | Region I | Ilocos Sur | 300057 | Magsingal NHS | MAGSINGAL | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 11347109.7318 | 11318812.7 | 11093368 | completed | 1 |  | 2022-07-18 |  |  |  |  | 2021-09-27
NC 2021 | K10 | Region I | La Union | 101076 | Deccan PS | SANTOL | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2855609.9919 | 2848488.77 |  | completed | 1
NC 2021 | K10 | Region I | La Union | 101079 | Banbanaba ES | SANTOL | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1074660.6919 | 1071980.74 |  | completed | 1
NC 2021 | K10 | Region I | La Union | 101083 | Pisnadan PS | SANTOL | 1 | 1 | 2 | Construction/Completion (1STY2CL (Toilet Attached)) |  | 1013865.7034 | 1011337.36 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300095 | Bacnotan NHS | BACNOTAN | 1 | 1 | 9 | Construction/Completion (3STY9CL) |  | 5865158.2999 | 5850531.97 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300097 | Balbalayang NHS | SAN GABRIEL | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1074660.6919 | 1071980.74 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300114 | DOÑA FRANCISCA LACSAMANA DE ORTEGA MEMORIAL NATIONAL HIGH SCHOOL | BANGAR | 1 | 1 | 8 | Construction/Completion (4STY REG WS) |  | 4717394.476 | 4705630.4 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300134 | San Francisco NHS | SUDIPEN | 1 | 1 | 8 | Construction/Completion (4STY SCI/ ICT LAB) |  | 1495747.0325 | 1492016.99 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300140 | Santol Voc'l. HS | SANTOL | 1 | 1 | 8 | Construction/Completion (4STY REG WS) |  | 3508129.663 | 3499381.21 |  | completed | 1
NC 2021 | SHS | Region I | La Union | 300146 | Sto. Rosario National High School | SAN JUAN | 1 | 1 | 8 | Construction/Completion (4STY REG WS) |  | 6557963.2731 | 6541609.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101445 | Don Juan Bernal Sr. ES | DASOL | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 5106585.5874 | 5093850.96 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300159 | Arnedo NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300172 | Binabalian NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 641262.9795 | 639663.82 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300175 | Bolinao SOF | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300194 | Dewey National High School | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300214 | Luciente II NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300215 | Luna National High School | BOLINAO | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 641262.9795 | 639663.82 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300238 | Pilar NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (3STY6CL) |  | 641262.9795 | 639663.82 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300268 | Zaragosa NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 321103 | Catuday NHS | BOLINAO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 606074.8486 | 604563.44 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101481 | Dulag ES | LINGAYEN (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 12887599.9031 | 12855461.25 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101376 | Gueset ES | BUGALLON | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 12887599.9031 | 12855461.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101486 | Naguelguel Elementary School | LINGAYEN (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 12887599.9031 | 12855461.25 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 500366 | Tampac IS | AGUILAR | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 4010000 | 4000000 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101416 | Balani-Parongking ES | CALASIAO | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 5969649.9075 | 5954763 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101420 | Bued ES | CALASIAO | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1215060.075 | 1212030 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101424 | Nalsian Bacayao ES | CALASIAO | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 5257338.57 | 5244228 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101434 | Longos Elementary School | CALASIAO | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 4919683.5375 | 4907415 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101438 | Nagsaing Elementary School | CALASIAO | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 7190050.6809 | 7172120.38 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101440 | Talibaew ES | CALASIAO | 3 | 1 | 4 | Construction/Completion (2STY6CL) |  | 332947.3326 | 332117.04 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101630 | Dalongue ES | SANTA BARBARA | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 516163.3604 | 514876.17 |  | COMPLETED | 1
NC 2021 | K10 | Region I | Pangasinan I, Lingayen | 101634 | Maronong ES | SANTA BARBARA | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6608412.8325 | 6591933 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan I, Lingayen | 300163 | Banaoang NHS | SANTA BARBARA | 3 | 1 | 4 | Construction/Completion (2STY6CL) |  | 592814.3099 | 591335.97 |  | COMPLETED | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 | 1 | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 2005000 | 2000000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300287 | Benigno V. Aldana NHS | POZORRUBIO | 5 |  | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 2005000 | 2000000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 | 1 | 8 | Construction/Completion (4STY8CL) |  | 515963.6624 | 514676.97 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 500378 | Don Valentin Torres Integrated School | SISON | 5 |  |  | Construction of Slope Protection |  | 2005000 | 2000000 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101714 | Domanpot ES | ASINGAN | 6 | 1 | 12 | Construction/Completion (2STY4CL and 2STY8CL) |  | 732854.0663 | 731026.5 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101717 | Sobol ES | ASINGAN | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1216937.3264 | 1213902.57 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101719 | Ariston Este ES | ASINGAN | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1309766.25 | 1306500 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101729 | Balungao CS | BALUNGAO | 6 | 1 | 8 | Construction/Completion (2STY8CL) |  | 1661213.3066 | 1657070.63 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101837 | Natividad CS | NATIVIDAD | 6 | 1 | 12 | Construction/Completion (2STY4CL) |  | 2506932.6524 | 2500680.95 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101842 | San Macario Norte Elementary School | NATIVIDAD | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 876599.2831 | 874413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101876 | Cabalaoangan ES | ROSALES | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 876599.2831 | 874413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101877 | Camangaan ES | ROSALES | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 941761.7831 | 939413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101892 | Carmay Elementary School | ROSALES | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 941761.7831 | 939413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101953 | Juan C. Laya Central School SPED Center | SAN MANUEL | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1661213.3066 | 1657070.63 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101977 | San Rafael ES | SAN NICOLAS | 6 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1216937.3264 | 1213902.57 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101987 | East Central School | SAN NICOLAS | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1539670.2767 | 1535830.7 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 101993 | Puyao ES | SAN NICOLAS | 6 | 1 | 2 | Construction/Completion (1STY2CL) |  | 2696136.7831 | 2689413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102002 | Cabalaoangan ES | SAN QUINTIN | 6 | 1 | 10 | Construction/Completion (2STY10CL) |  | 2333123.3928 | 2327305.13 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102012 | Sisenando V. Tecson ES | SAN QUINTIN | 6 | 1 | 8 | Construction/Completion (2STY8CL) |  | 876599.2831 | 874413.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102062 | Barangobong ES | TAYUG | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 449133.2831 | 448013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102065 | Libertad ES | TAYUG | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 449133.2831 | 448013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102068 | Trenchera ES | TAYUG | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 449133.2831 | 448013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102069 | C. Lichauco ES | TAYUG | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 544370.7831 | 543013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102071 | Lawak ES | TAYUG | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 383970.7831 | 383013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102081 | Calitlitan ES | UMINGAN | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 383970.7831 | 383013.25 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102093 | Umingan CES | UMINGAN | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 6586724.2964 | 6570298.55 |  | completed | 1
NC 2021 | K10 | Region I | Pangasinan II, Binalonan | 102105 | Don Montano Elementary School | UMINGAN | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1661213.3066 | 1657070.63 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300273 | Angela Valdez Ramos NHS | ASINGAN | 6 | 1 | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 1604000 | 1600000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300309 | Eastern Pangasinan Agricultural College | SANTA MARIA | 6 | 1 | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 1804500 | 1800000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300354 | San Nicolas National High School | SAN NICOLAS | 6 | 1 | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 1203000 | 1200000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 300363 | Tayug National High School | TAYUG | 6 | 1 | 44 | Construction/Completion (4STY16CL, 4STY8CL & 4STY20CL) |  | 4461464.0856 | 4450338.24 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 500623 | Sta. Maria East Integrated School | SANTA MARIA | 6 | 1 | 1 | Construction/Completion (Upgrading of Electrical Facilities) |  | 1804500 | 1800000 |  | completed | 1
NC 2021 | SHS | Region I | Pangasinan II, Binalonan | 501117 | Calepaan Integrated School | ASINGAN | 6 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2089997.2833 | 2084785.32 |  | completed | 1
NC 2021 | K10 | Region I | San Carlos City | 102250 | TALANG CENTRAL SCHOOL | San Carlos City | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2177234.5125 | 2171805 |  | COMPLETED | 1
NC 2021 | K10 | Region I | San Carlos City | 102254 | Balite Sur Elementary School | SAN CARLOS CITY | 3 | 1 | 6 | Construction/Completion (2STY 6CL) |  | 7089632.662 | 7071952.78 |  | COMPLETED | 1
NC 2021 | K10 | Region I | San Fernando City | 101030 | San Fernando North CS (North CES) | CITY OF SAN FERNANDO (Capital) | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 3681618.9145 | 3672437.82 |  | COMPLETED | 1 |  | 2021-11-20
NC 2022 | K10 | Region I | Ilocos Norte | 100160 | Adams CES | ADAMS | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 |  | 2023-04-18 | [7 empty] | JLP Construction and Supply
NC 2022 | K10 | Region I | Ilocos Norte | 100108 | Saoit ES | BURGOS | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 |  | 2023-04-18 | [7 empty] | JLP Construction and Supply | awaiting approved modification
NC 2022 | K10 | Region I | Ilocos Norte | 100220 | Carasi ES | CARASI | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 |  | 2023-03-24 | [7 empty] | JLP Construction and Supply
NC 2022 | K10 | Region I | Ilocos Norte | 100233 | Virbira-Angset Elementary School | CARASI | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [10 empty] | modified from Dumalneg ES
NC 2022 | K10 | Region I | Ilocos Sur | 100737 | SAGSAGAT ELEMENTARY SCHOOL | SAN ILDEFONSO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [8 empty] | 2023-02-06
NC 2022 | K10 | Region I | Ilocos Sur | 150522 | Mindoro Primary School | SAN VICENTE | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [8 empty] | 2023-02-06
NC 2022 | K10 | Region I | Ilocos Sur | 100660 | Calawaan Elementary School | SANTA CATALINA | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 | [8 empty] | 2023-02-06
NC 2022 | K10 | Region I | Ilocos Sur | 100564 | Bussot Priimary School | GREGORIO DEL PILAR (CONCEPCION) | 2 | 1 | 2 | 1STY2CL | 2 |  | 6584595.6079 |  | Completed | 1
NC 2022 | K10 | Region I | Ilocos Sur | 100552 | Tadao Elementary School | NAGBUKEL | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1
NC 2022 | K10 | Region I | Ilocos Sur | 100386 | Ansad ES | SAN ESTEBAN | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1 |  |  |  |  | 1900-01-17
NC 2022 | K10 | Region I | Ilocos Sur | 100587 | Sto. Rosario ES | SIGAY | 2 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1 |  |  |  |  | 1900-01-17 | [5 empty] | Work Suspended; non approval of community owners and staff despite approval during validation; for request of realignment
NC 2022 | K10 | Region I | Ilocos Sur | 100331 | Banga Elementary School | SUGPON | 2 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1
NC 2022 | K10 | Region I | La Union | 100861 | Cambaly Elementary School | BAGULIN | 2 | 1 | 6 | 2STY6CL | 2 |  | 12731750 |  | Completed | 1
NC 2022 | K10 | Region I | La Union | 100997 | Ambangonan ES | PUGO | 2 | 1 | 4 | 2STY4CL | 2 |  | 9724250 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan I, Lingayen | 101401 | Burgos Central School | BURGOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 15538750 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan I, Lingayen | 101404 | Concordia ES | BURGOS | 1 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan I, Lingayen | 101407 | Don Matias ES | BURGOS | 1 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan I, Lingayen | 101409 | Papallasen ES | BURGOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 15538750 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan II, Binalonan | 102058 | Ernesting Gonzalez CS | SANTO TOMAS | 5 | 1 | 4 | 2STY4CL | 2 |  | 15639000 |  | Completed | 1
NC 2022 | K10 | Region I | Pangasinan II, Binalonan | 501898 | San Vicente Integrated School | UMINGAN | 6 | 1 | 6 | 2STY6CL | 2 |  | 25062500 |  | Completed | 1
NC 2022 | SHS | Region I | Ilocos Sur | 300054 | Lidlidda National High School | LIDLIDDA | 2 | 1 | 4 | 2STY4CL | 2 |  | 12030000 |  | Completed | 1
NC 2022 | SHS | Region I | Pangasinan I, Lingayen | 300179 | Burgos NHS | BURGOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 15538750 |  | Completed | 1
NC 2022 | SHS | Region I | Pangasinan I, Lingayen | 300239 | Jose Rivera Bonsay NHS | BURGOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 15538750 |  | Completed | 1 | [10 empty] | suspended due to water tank obstruction
NC 2022 | SHS | Region I | Pangasinan I, Lingayen | 500620 | Sapa Grande Integrated School | BURGOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 15538750 |  | Completed | 1
NC 2023 | K10 | Region I | Alaminos City | 101170 | Balangobong ES | CITY OF ALAMINOS |  | 1 | 2 |  | Batch 1 | 5800312.5 | 5750000 | 5639500 | Completed | 1 | 2023-05-11 | 2024-03-01 | P00775113LZ-CW1 | 23AG0122 | 2023-06-20 | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-07-24 | SZCON BUILDERS INC.
NC 2023 | K10 | Region I | Batac City | 100079 | Magnuang ES | CITY OF BATAC |  | 1 | 4 |  | Batch 2 | 9942210 | 9606000 | 9604594.97 | Completed | 1 | 2024-08-28 | 2024-08-27 | 23AB0191 | 23AB0191 | 2023-09-27 | 2023-10-04 | 2023-10-17 | 2023-10-31 | 2023-11-16 | KRB Construction | COMPLETED
NC 2023 | K10 | Region I | Candon City | 100428 | Bagani Elementary School | CITY OF CANDON |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4849911.39 | Completed | 1 | 2023-11-03 | 2024-01-05 | P00775114LZ-CW1 | 23AD0100 |  | 2023-08-24 | 2023-08-24 | 2023-09-07 | 2024-09-14 | CANDON LUCKY FORTY SIX CONSTRUCTION AND DEV'T CORP. | COMPLETED
NC 2023 | K10 | Region I | Candon City | 100430 | Bagar Elementary School | CITY OF CANDON |  | 1 | 5 |  | Batch 1 | 10692750 | 10600000 | 10281975.05 | Completed | 1 | 2024-04-11 | 2024-11-29 | P00775115LZ-CW1 | 23AD0102 |  | 2023-08-24 | 2023-08-24 | 2023-09-07 | 2024-09-14 | 739 Builders | COMPLETED
NC 2023 | K10 | Region I | Candon City | 100437 | Caterman Elementary School | CITY OF CANDON |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4849911.37 | Completed | 1 | 2023-12-13 | 2024-04-19 | P00775116LZ-CW1 | 23AD0101 |  | 2023-08-24 | 2023-08-24 | 2023-09-07 | 2024-09-14 | CANDON LUCKY FORTY SIX CONSTRUCTION AND DEV'T CORP. | COMPLETED
NC 2023 | SHS | Region I | Dagupan City | 300368 | Dagupan City NHS | DAGUPAN CITY |  | 1 | 10 |  | Batch 1 | 30262500 | 30000000 | 27055090 | Completed | 1 | 2024-03-19 | 2024-03-19 | P00775117LZ-CW1 | 23AH0153 | 2023-05-18 | 2023-05-25 | 2023-06-13 | 2023-06-26 | 2023-06-29 | Mightyway Construction & Supply
NC 2023 | SHS | Region I | Dagupan City | 300370 | Salapingao National High School | DAGUPAN CITY |  | 1 | 6 |  | Batch 1 | 8687799.44 | 8612440.58 | 7768460 | Completed | 1 | 2024-04-18 | 2024-03-22 | P00775118LZ-CW1 | 23AH0154 | 2023-05-18 | 2023-05-25 | 2023-06-13 | 2023-06-26 | 2023-06-29 | JG Garcia Construction & Supply. | PHASE 1 ONLY (INCOMPLETE BLDG)
NC 2023 | K10 | Region I | Ilocos Norte | 100016 | Cadaratan ES | BACARRA |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 6000000 | Completed | 1 | 2023-12-30 | 2023-12-15 | P00775119LZ | 23AA0474 | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-07-25 | 2023-07-12 | BJMJB | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100199 | Davila ES | PASUQUIN |  | 1 | 8 |  | Batch 1 | 24210000 | 24000000 | 23999968.9 | Completed | 1 | 2024-04-23 | 2024-04-23 | P00775120LZ | 23AA0481 | 2023-07-05 | 2023-07-12 | 2023-07-24 | 2023-07-31 | 2023-08-10 | IGWT-JAV Const. & Dev't. Corp. | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100202 | Gabaldon ES | PASUQUIN |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 | 6000000 | Completed | 1 | 2023-12-30 | 2023-12-27 | P00775121LZ | 23AA0475 | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-07-25 | 2023-07-12 | BJMJB | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100305 | Vintar CES | VINTAR |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4999941.15 | Completed | 1 | 2023-12-15 | 2023-12-15 | P00775122LZ | 23AA0477 | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-07-25 | 2023-07-12 | AJ TAYLAN CONST CORP. | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 500000 | Caraitan Integrated School | BADOC |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4999998.42 | Completed | 1 | 2024-01-02 | [9 empty] | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100035 | Nagrebcan ES | BADOC |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4999998.42 | Completed | 1 | 2024-02-03 | [9 empty] | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100148 | Fortuna ES | MARCOS |  | 1 | 2 |  | Batch 1 | 11096250 | 11000000 | 10941662.05 | Completed | 1 | 2024-12-29 | [9 empty] | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 150004 | Upon ES | PINILI |  | 1 | 2 |  | Batch 1 | 5043748.99 | 4999999 | 4999369.76 | Completed | 1 | 2024-06-08 | [9 empty] | Completed
NC 2023 | K10 | Region I | Ilocos Norte | 100256 | Eladio V. Barangan Mem. ES | SAN NICOLAS |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4999998.42 | Completed | 1 | 2023-12-29 | [9 empty] | Completed
NC 2023 | SHS | Region I | Ilocos Sur | 300087 | Tay-ac National High School | BANTAY |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.93
NC 2023 | SHS | Region I | Ilocos Sur | 300035 | San Juan National High School | SAN JUAN (LAPOG) |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1
NC 2023 | K10 | Region I | Ilocos Sur | 502103 | Pangada-Cabaroan Integrated School | SANTA CATALINA |  | 1 | 4 |  | Batch 1 | 12299340.9 | 12192655.17 |  | Completed | 1
NC 2023 | K10 | Region I | Ilocos Sur | 501578 | Comillas North Integrated School | CERVANTES |  | 1 | 2 |  | Batch 1 | 4741125 | 4700000 |  | Completed | 1
NC 2023 | K10 | Region I | Ilocos Sur | 100579 | Pagangpang Elementary School | GALIMUYOD |  | 1 | 2 |  | Batch 1 | 4741125 | 4700000 |  | Completed | 1
NC 2023 | K10 | Region I | La Union | 500351 | Bitalag Integrated School | BACNOTAN |  | 1 | 4 |  | Batch 1 | 13478879.47 | 13361962.3 | 13001879.43 | Completed | 1 | 2024-04-17 | 2024-04-17 | P00775133LZ-CW1 | 23AE0089 | 2023-10-20 | 2023-10-17 | 2023-10-24 | 2023-12-13 | 2023-12-20 | JAJR CONSTRUCTION | COMPLETED - Re -align to BITALAG IS fROM QUIRINO IS, BACNOTAN, LA UNION
NC 2023 | K10 | Region I | La Union | 100857 | Zaragosa Elementary School | BACNOTAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9718037.17 | Completed | 1 | 2023-12-16 | 2023-12-16 | P00775134LZ-CW1 | 23AE0080 | 2023-06-10 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-21 | J.A. OLIVAR ENG'G DESIGN , CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2023 | SHS | Region I | La Union | 300124 | Oanari National High School | LUNA |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9719192.64 | Completed | 1 | 2024-01-15 | 2024-05-15 | P00775135LZ-CW1 | 23AE0081 | 2023-06-10 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-31 | D.C. GALVEZ CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region I | La Union | 101071 | San Juan CES | SAN JUAN |  | 1 | 4 |  | Batch 1 | 13682903.43 | 13564216.53 | 13184583.38 | Completed | 1 | 2024-01-15 | 2024-04-05 | P00775136LZ-CW1 | 23AE0082 | 2023-06-10 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-25 | J.A. OLIVAR ENG'G DESIGN , CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2023 | K10 | Region I | La Union | 300147 | San Juan National High School | SAN JUAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9706268.2 | Completed | 1 | 2024-01-12 | 2024-04-22 | P00775137LZ-CW1 | 23AE0083 | 2023-06-10 | 2023-06-20 | 2023-06-27 | 2023-07-13 | 2023-07-25 | J.A. OLIVAR ENG'G DESIGN , CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2023 | K10 | Region I | La Union | 500359 | Capas Integrated School | AGOO |  | 1 | 6 |  | Batch 1 | 12710250 | 12600000 | 12589979.21 | Completed | 1 | 2024-03-14 | 2024-03-10 | 23AF0162 | P00775140LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2023 | K10 | Region I | La Union | 100811 | San Manuel Sur ES | AGOO |  | 1 | 6 |  | Batch 1 | 12710250 | 12600000 | 12592509.96 | Completed | 1 | 2024-03-14 | 2024-03-02 | 23AF0159 | P00775138LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | KRYPTONITE 6S BUILDERS, INC. | COMPLETED
NC 2023 | SHS | Region I | La Union | 300149 | Suyo National High School | BAGULIN |  | 1 | 4 |  | Batch 1 | 10692245.63 | 10599500 | 10599500 | Completed | 1 | 2024-01-02 | 2024-01-08 | 23AF0160 | P00775140LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2023 | SHS | Region I | La Union | 300108 | Cuenca National High School | PUGO |  | 1 | 4 |  | Batch 1 | 10675601.25 | 10583000 | 10583000 | Completed | 1 | 2024-12-14 | 2024-12-20 | 23AF0161 | P00775140LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | RF FLORES CONSTRUCTION | COMPLETED
NC 2023 | SHS | Region I | La Union | 300119 | Leones National High School | TUBAO |  | 1 | 6 |  | Batch 1 | 15131250 | 15000000 | 14978289.89 | Completed | 1 | 2024-05-15 | 2024-05-20 | 23AF0164 | P00775142LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | BONIMAR CONSTRUCTION ENTERPRISES | COMPLETED
NC 2023 | SHS | Region I | La Union | 300152 | Tubao National High School | TUBAO |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29993639.44 | Completed | 1 | 2024-02-10 | 2024-02-02 | 23AF0165 | P00775142LZ-CW1 | 2023-05-29 | 2023-06-13 | 2023-06-20 | 2023-10-07 | 2023-07-18 | EE MADAYAG CONSTRUCTION | COMPLETED
NC 2023 | SHS | Region I | Laoag City | 305601 | Caaoacan High School | LAOAG CITY (Capital) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region I | Laoag City |  | MMSU Laboratory Elementary School | LAOAG CITY (Capital) |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 500606 | Anda Integrated School | ANDA |  | 1 | 2 |  | Batch 1 | 5295937.5 | 5250000 | 5134500 | Completed | 1 | 2023-11-05 | 2023-11-03 | P00775146LZ | 23AG0120 |  | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-07-24 | SZCON BUILDERS, INC.
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 101339 | Balingasay ES | BOLINAO |  | 1 | 3 |  | Batch 1 | 8070000 | 8000000 | 7838698.2 | Completed | 1 | 2023-11-20 | 2023-11-20 | P00775147LZ | 23AG0123 |  | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-07-24 | SZCON BUILDERS, INC.
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 101355 | Lucero Elementary School | BOLINAO |  | 1 | 2 |  | Batch 1 | 5800312.5 | 5750000 | 5640499.75 | Completed | 1 | 2023-11-05 | 2023-11-03 | P00775148LZ | 23AG0121 |  | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-07-24 | SZCON BUILDERS, INC.
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 500907 | Pita Integrated School | INFANTA |  | 1 | 2 |  | Batch 1 | 5295937.5 | 5250000 | 5143740.4 | Completed | 1 | 2024-01-04 | 2024-01-03 | P00775149LZ | 23AG0119 |  | 2023-06-29 | 2023-07-11 | 2023-07-17 | 2023-07-24 | SZCON BUILDERS, INC.
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 500605 | Aguilar Integrated School | AGUILAR |  | 1 | 6 |  | Batch 1 | 19166250 | 19000000 | 18904885.56 | Completed | 1 | 2025-01-09 | 2025-01-09 | P00775150LZ-CW1 | 23AH0157 | 2023-06-07 | 2023-06-13 | 2023-09-19 | 2023-09-25 | 2023-10-12 | AC Soliven Construction & Gen. Mdse.
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 151524 | Alejandro V. Frias Elementary School | BASISTA |  | 1 | 8 |  | Batch 2 | 29067937.33 | 28084963.6 | 27523315.63 | Completed | 1 | 2025-02-03 | 2025-02-03 | P00775949LZ -CW1 | 23AH0164 | 2023-09-13 | 2023-09-19 | 2023-11-17 | 2023-11-29 | 2023-12-14 | Shyka Construction & Trading | PHASE 1 ONLY
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 101475 | Kadampat ES | LABRADOR |  | 1 | 4 |  | Batch 1 | 11096250 | 11000000 | 10780062.25 | Completed | 1 | 2024-08-22 | 2024-08-22 | P00775151LZ-CW1 | 23AH0158 | 2023-09-27 | 2023-10-03 | 2023-11-09 | 2023-11-23 | 2023-12-07 | J-Three Bagwis Construction Company | PHASE 1 ONLY
NC 2023 | K10 | Region I | Pangasinan I, Lingayen | 101533 | Asin Este ES | MALASIQUI |  | 1 | 4 |  | Batch 1 | 12105000 | 12000000 | 11806370.98 | Completed | 1 | 2023-12-15 | 2024-01-22 | P00775152LZ-CW1 | 23AJ0136 | 2023-06-27 | 2023-07-04 | 2023-07-18 | 2023-08-07 | 2023-08-18 | Jeusmack Builders & Construction Supply
NC 2023 | K10 | Region I | Pangasinan II, Binalonan | 101935 | Labney ES | SAN JACINTO |  | 1 | 5 |  | Batch 1 | 10732989.77 | 10639890.72 | 10320504.34 | Completed | 1 | 2023-12-20 | 2023-11-28 | P00775153LZ-CW1 | 23AH0151 | 2023-05-16 | 2023-05-23 | 2023-06-26 | 2023-06-29 | 2023-07-14 | Mightyway Construction & Supply | Completed
NC 2023 | K10 | Region I | Pangasinan II, Binalonan | 101937 | Macayug ES | SAN JACINTO |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8353668.31 | Completed | 1 | 2024-03-31 | 2024-03-22 | P00775154LZ-CW1 | 23AH0152 | 2023-05-16 | 2023-05-23 | 2023-06-22 | 2023-06-29 | 2023-07-14 | ZOTA Trading & Construction | Completed
NC 2023 | K10 | Region I | Pangasinan II, Binalonan | 101771 | Binalonan South Central School | BINALONAN |  | 1 | 0 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1
NC 2023 | K10 | Region I | Pangasinan II, Binalonan | 102057 | Doña Aurea ES | SANTO TOMAS |  | 1 | 4 |  | Batch 1 | 15775841.25 | 15639000 |  | Completed | 1
NC 2023 | K10 | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1
NC 2023 | SHS | Region I | Pangasinan II, Binalonan | 300363 | Tayug NHS | TAYUG |  | 1 | 16 |  | Batch 1 | 50710637.91 | 50270768.68 |  | Completed | 1
NC 2023 | SHS | Region I | Pangasinan II, Binalonan | 300283 | Baracbac NHS | UMINGAN |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18073170.79 | Completed | 1 | 2024-03-05 | 2024-03-05 |  | 23AI0189 | 2023-06-23 | 2023-07-12 | 2023-07-20 |  | 2023-08-03 | Aquino - Dela Cruz Engineering & Construction
NC 2023 | K10 | Region I | San Carlos City | 102255 | Bolosan-Caingal Elementary School | SAN CARLOS CITY |  | 1 | 4 |  | Batch 1 | 12105000 | 12000000 | 11808979.18 | Completed | 1 | 2023-12-15 | 2024-02-13 | - | 23AJ0135 | 2023-06-21 |  | 2023-07-11 | 2023-08-16 | 2023-08-18 | Jeusmack Builders & Construction Supply | NO PROJECT ID AND DATE OF PRE-SUBMISSION CONFERENCE
NC 2023 | SHS | Region I | San Carlos City | 300391 | Turac National High School | SAN CARLOS CITY |  | 1 | 3 |  | Batch 1 | 6052500 | 6000000 | 5907355.19 | Completed | 1 | 2023-11-30 | 2023-01-15 | - | 23AJ0137 | 2023-06-27 |  | 2023-07-18 | 2023-08-16 | 2023-08-18 | Jeusmack Builders & Construction Supply | NO PROJECT ID AND DATE OF PRE-SUBMISSION CONFERENCE
NC 2023 | K10 | Region I | San Fernando City | 101039 | Catbangen ES | CITY OF SAN FERNANDO (Capital) |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14557381.36 | Completed | 1 | 2024-02-14 | 2024-03-21 | P00775162LZ-CW1 | 23AE0086 |  | 2023-06-14 | 2023-06-27 | 2023-07-13 | 2023-07-21 | AE SQUARE ENTERPRISED
NC 2023 | K10 | Region I | Urdaneta City | 102298 | Labit West Elementary School | CITY OF URDANETA |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14984220.01 | Completed | 1 | 2024-01-23 | 2024-01-23 |  | 23AI0190 | 2023-06-23 |  | 2023-07-12 | 2023-07-20 | 2023-08-03 | R.A. Matias Construction and Developers Inc.
NC 2024 |  | Region I | Alaminos City |  | Ildefonso Quimson Elementary School | CITY OF ALAMINOS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5865174.4 | Ongoing | 0.95 | 2024-09-08 |  | P00875125LZ | 24AG0171 |  |  | 2024-05-07 | 2024-05-20 | 2024-05-27 | JONIK TRADING & CONSTRUCTION | TRANSFERED TO ILDEFONSO QUIMSON COMM. HIGH SCHOOL
NC 2024 |  | Region I | Alaminos City | 101184 | Maliga ES | CITY OF ALAMINOS |  | 1 |  | Construction of School Building | GAA 17B | 5500000 |  | 5375811.42 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875097LZ | 24AG0169 |  |  | 2024-05-07 | 2024-05-20 | 2024-05-27 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Alaminos City | 500564 | Pangapisan Integrated School | CITY OF ALAMINOS |  |  |  | Construction of School Building | GAA 17B | 5500000 |  | 5374670.8 | Completed | 1 | 2024-10-05 | 2024-10-04 | P00875096LZ | 24AG0168 |  |  | 2024-05-07 | 2024-05-13 | 2024-05-20 | EJR BUILDERS AND CONSTRUCTION SUPPLY
NC 2024 |  | Region I | Alaminos City | 101196 | San Vicente ES | CITY OF ALAMINOS |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5863764.4 | Completed | 1 | 2024-09-21 | 2024-09-18 | P00875121LZ | 24AG0170 |  |  | 2024-05-07 | 2024-05-13 | 2024-05-20 | ST. ALMERS CONSTRUCTION AND ENTERPRISE
NC 2024 |  | Region I | Candon City | 100429 | Bagani-Tocgo Elementary School | CITY OF CANDON |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 4470668.71 | Ongoing | 0.45 | 2025-03-18 |  | P0087506LZ-CW1 | 24AD0116 | 2024-10-17 | 2024-11-07 | 2024-11-07 | 2024-12-03 | 2024-12-11 | Villar General Construction & Supplies | CHANGE OF SCOPE
NC 2024 |  | Region I | Candon City | 100430 | Bagar Elementary School | CITY OF CANDON |  | 1 | 4 | 2STY4CL | GAA 17B | 12500000 |  | 12135177.54 | Ongoing | 0.5 | 2025-04-24 |  | P00875062LZ-CW1 | 24AD0115 | 2024-10-14 | 2024-10-28 | 2024-10-28 | 2024-12-03 | 2024-12-11 | EJIEV CONSTRUCTION SERVICES | WITH APPROVED CHANGE OF SCHOOL( FROM BAGAR ES TO CANDON SOUTH CENTRAL SCHOOL)
NC 2024 |  | Region I | Candon City | 100432 | Bugnay Elementary School | CITY OF CANDON |  | 1 | 4 | 2STY4CL | GAA 17B | 12500000 |  | 12064430.61 | Ongoing | 0.75 | 2024-10-08 |  | P00875061LZ-CW1 | 24AD0101 | 2024-05-06 | 2024-05-20 | 2024-05-20 | 2024-06-04 | 2024-06-11 | FNDCC
NC 2024 |  | Region I | Candon City | 300051 | Dr. Ricardo Gacula Memorial National High School | CITY OF CANDON |  | 1 | 6 | 2STY6CL | GAA 17B | 17000000 |  | 16898058.84 | Ongoing | 0.75 | 2025-01-28 |  | P00875060LZ-CW1 | 24AD0102 | 2024-07-19 | 2024-08-13 | 2024-08-13 | 2024-09-02 | 2024-09-11 | ARTHIT
NC 2024 |  | Region I | Candon City | 100448 | Sto. Tomas Elementary School | CITY OF CANDON |  | 1 | 6 | 2STY6CL | GAA 17B | 17000000 |  | 16793475.96 | Ongoing | 0.8 | 2024-12-25 |  | P00875064LZ-CW1 | 24AD0104 | 2024-06-22 | 2024-07-15 | 2024-07-15 | 2024-07-30 | 2024-08-08 | VIGAN FORTUNE CONSTRUCTION | STO TOMAS ES TO STO TOMAS NATIONAL HIGH SCHOOL
NC 2024 |  | Region I | Dagupan City | 102175 | Carael ES | DAGUPAN CITY |  | 1 | 9 | 3STY9CL | GAA 17B | 20000000 |  | 19900000 | Completed | 1 | 2025-02-14 | 2025-02-14 |  |  | 2024-05-06 | 2024-06-13 | 2024-06-26 | 2024-06-28 | 2024-07-15 | MIGHTYWAY CONSTRUCTION AND SUPPLY | PHASE 1 ONLY (INCOMPLETE BLDG)
NC 2024 |  | Region I | Ilocos Norte | 300002 | Bacarra NCHS | BACARRA |  | 1 | 16 | 4STY16CL | GAA 17B | 48000000 |  | 47759906.38 | Ongoing | 0.95 | 2025-03-23 |  | P00875052LZ | 24AA0456 | 2024-03-27 | 2024-04-03 | 2024-05-03 | 2024-05-15 | 2024-05-22 | BJMJB Construction and Supply/Remar Construction(JV) | ongoing
NC 2024 |  | Region I | Ilocos Norte | 100056 | Suyo ES | BANGUI |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5969830.61 | Completed | 1 | 2024-07-11 | 2024-07-11 | P00875046LZ | 24AA0416 | 2024-02-28 | 2024-03-06 | 2024-03-18 | 2024-04-05 | 2024-04-12 | TMT Construction
NC 2024 |  | Region I | Ilocos Norte | 100233 | Virbira-Angset Elementary School | CARASI |  | 1 | 6 | 1STY6CL | GAA 17B | 6000000 |  | 5798982.21 | Not Yet Started | 0 | [10 empty] | waiting for approval of condemnation of PPP building from DepEd CO. With approved modification from 6CL to 2CL
NC 2024 |  | Region I | Ilocos Norte | 300019 | Luzong NHS | PAGUDPUD |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17909894.13 | Ongoing | 0.84 | 2025-01-01 |  | P00875051LZ | 24AA0455 | 2024-03-27 | 2024-04-03 | 2024-04-15 | 2024-04-26 | 2024-05-03 | RCD General Contractor & Construction Supply | ongoing
NC 2024 |  | Region I | Ilocos Norte | 300026 | Pasaleng National High School | PAGUDPUD |  | 1 | 4 | 2STY4CL | GAA 17B | 12000000 |  | 11939903.12 | Ongoing | 0.9 | 2024-09-23 |  | P00875048LZ | 24AA0418 | 2024-02-28 | 2024-03-06 | 2024-03-18 | 2024-04-05 | 2024-04-12 | PASCAL CONSTRUCTION | ongoing
NC 2024 |  | Region I | Ilocos Norte | 100194 | Binsang ES | PASUQUIN |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5969866.92 | Completed | 1 | 2024-09-24 | 2024-07-24 | P00875047LZ | 24AA0417 | 2024-02-28 | 2024-03-06 | 2024-03-18 | 2024-04-05 | 2024-04-12 | Zedik Builders
NC 2024 |  | Region I | Ilocos Norte | 300016 | Piddig National High School | PIDDIG |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  | 17476811.81 | Completed | 1 | 2024-12-31 | 2024-12-31 | P00875050LZ | 24AA0433 | 2024-03-08 | 2024-03-18 | 2024-03-27 | 2024-04-17 | 2024-04-25 | BJMJB Construction and Supply
NC 2024 |  | Region I | Ilocos Norte | 100230 | Sta.Maria ES | PIDDIG |  | 1 | 3 | 1STY3CL | GAA 17B | 9000000 |  | 8954731.75 | Completed | 1 | 2024-10-20 | 2024-10-20 | P00875044LZ | 24AA0414 | 2024-02-28 | 2024-03-06 | 2024-03-18 | 2024-04-05 | 2024-04-12 | North Tech Builders & Construction Supply
NC 2024 |  | Region I | Ilocos Norte | 150009 | San Pedro ES | SARRAT |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5969998.57 | Completed | 1 | 2024-11-21 | 2024-11-21 | P00875053LZ | 24AA0459 | 2024-04-04 | 2024-04-11 | 2024-04-23 | 2024-05-03 | 2024-05-10 | BJMJB Construction and Supply
NC 2024 |  | Region I | Ilocos Norte | 500344 | SALPAD INTEGRATED SCHOOL | VINTAR |  | 1 | 4 | 2STY4CL | GAA 17B | 12000000 |  | 11939911.72 | Completed | 1 | 2024-11-22 | 2024-11-22 | P00875049LZ | 24AA0421 | 2024-03-01 | 2024-03-08 | 2024-03-20 | 2024-04-05 | 2024-04-12 | BJMJB Construction and Supply
NC 2024 |  | Region I | Ilocos Norte | 300028 | San Nicolas NHS | SAN NICOLAS |  | 1 | 20 | 4STY20CL | GAA 17B | 40000000 |  | 39394161.38 | Ongoing | 0.27 |  |  | no data from DPWH | 24AB0101 | [5 empty] | SYNDTITE CONSTRUCTION CORPORATION | With approved modification from 20CL to 12CL
NC 2024 |  | Region I | Ilocos Norte | 100275 | Bagbago ES | SOLSONA |  | 1 | 4 | 2STY4CL | BATCH 1 | 13728000 |  | 11703856.65 | Ongoing | 0.55 | 2024-10-31 |  | no data from DPWH | 24AB0102 |  | 2024-05-16 | 2024-05-29 |  | 2024-07-04 | ACCELERATED METAL TECHNOLOGY AND CONSTRUCTION INC. | Suspended due to relocation of electric lines
NC 2024 |  | Region I | Ilocos Norte | 300030 | Solsona National High School | SOLSONA |  | 1 | 20 | 4STY12CL & 4STY8CL | BATCH 1 | 62240000 |  | 61111245.14 | Ongoing | 0.55 | 2025-03-12 |  | no data from DPWH | 24AB0103 |  | 2024-07-02 | 2024-07-16 | 2024-07-23 | 2024-07-31 | no data from DPWH | ongoing
NC 2024 |  | Region I | Ilocos Sur | 100458 | Pantay Tamurong Elementary School | CAOAYAN |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.59
NC 2024 |  | Region I | Ilocos Sur | 100461 | Villamar Elementary School | CAOAYAN |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.63
NC 2024 |  | Region I | Ilocos Sur | 500348 | San Vicente Integrated School | SAN VICENTE |  | 1 | 14 | 3STY14CL | GAA 17B | 40000000 |  |  | Ongoing | 0.37
NC 2024 |  | Region I | Ilocos Sur | 305821 | Santa National High School | SANTA |  | 1 | 6 | 2STY6CL | GAA 17B | 15000000 |  |  | Completed | 1
NC 2024 |  | Region I | La Union | 300132 | Regional Science HS, La Union | BANGAR |  | 1 | 4 | 2STY4CL | GAA 17B | 13000000 |  | 12933961.7 | Completed | 1 | 2024-11-24 | 2024-11-24 | 24AE0098 | 24AE0098 | 2024-03-02 | 2024-03-18 | 2024-03-25 | 2024-01-04 | 2024-04-23 | QUE CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101065 | Dasay ES | SAN JUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5967000 | Completed | 1 | 2024-11-23 | 2024-12-18 | 24AE0099 | 24AE0099 | 2024-03-02 | 2024-03-18 | 2024-03-25 | 2024-01-04 | 2024-04-23 | J.A. OLIVAR ENG'G. DESIGN, CONST. & SUPPLIES | COMPLETED
NC 2024 |  | Region I | La Union | 300147 | San Juan National High School | SAN JUAN |  | 1 | 4 | 2STY4CL | GAA 17B | 14000000 |  | 13574069.12 | Completed | 1 | 2025-04-06 | 2025-04-06 | 24AE0100 | 24AE0100 | 2024-03-09 | 2024-03-25 | 2024-04-01 | 2024-08-04 | 2024-09-06 | J.A. OLIVAR ENG'G. DESIGN, CONST. & SUPPLIES | COMPLETED
NC 2024 |  | Region I | La Union | 502074 | Cubal Integrated School | AGOO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4821386.22 | Completed | 1 | 2024-08-26 | 2024-05-09 | 24AF0129 | P00875087LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-29 | KRYPTONITE 6S BUILDERS, INC. | COMPLETED
NC 2024 |  | Region I | La Union | 500563 | San Julian Integrated School | AGOO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822173.21 | Completed | 1 | 2024-11-13 | 2024-10-11 | 24AF0153 | P00875082LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-07-17 | KRYPTONITE 6S BUILDERS, INC. | COMPLETED
NC 2024 |  | Region I | La Union |  | San Miguel Sur ES | AGOO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | N/A ( No San Miguel Sur ES in La Union Division | Completed | 1 | 2024-08-20 | 2024-05-09 | 24AF0132 | P00875086LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | KRYPTONITE 6S BUILDERS, INC. | N/A ( No San Miguel Sur ES in La Union Division
NC 2024 |  | Region I | La Union | 100825 | Gallano ES | ARINGAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822432.24 | Completed | 1 | 2024-10-16 | 2024-12-10 | 24AF0160 | P00875090LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-19 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 500350 | Baay Integrated School | BAGULIN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820644.35 | Completed | 1 | 2024-10-01 | 2024-12-12 | 24AF0148 | P00875078LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-04 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 100908 | Baccuit Elementary School | BAUANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820774.98 | Ongoing | 0.92 | 2024-08-20 |  | 24AF0131 | P00875076LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | SAPITOLA CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 100908 | Baccuit Elementary School | BAUANG |  | 1 |  | Construction of School Building | GAA 17B | 1700000 |  | 1637754.47 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0136 | P00875077LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 100909 | Ballay ES | BAUANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820320.55 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0137 | P00875088LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | VILLAR GEN. CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2024 |  | Region I | La Union | 100921 | Calumbaya ES | BAUANG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820774.98 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0133 | P00875085LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | KRYPTONITE 6S BUILDERS, INC. | COMPLETED
NC 2024 |  | Region I | La Union | 100935 | Delles ES | BURGOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4817587.51 | Completed | 1 | 2025-04-11 | 2024-10-04 | 24AF0182 | P00875085LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-12-13 | BONIMAR CONSTRUCTION ENTERPRISES | COMPLETED
NC 2024 |  | Region I | La Union |  | San Fermin Elementary School | CABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4823688.83 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0130 | P00875089LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 300136 | San Gregorio National High School | CABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4818617.05 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0134 | P00875075LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | BONIMAR CONSTRUCTION ENTERPRISES | COMPLETED
NC 2024 |  | Region I | La Union | 300137 | San Jose National High School | CABA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4819857.82 | Completed | 1 | 2024-10-21 | 2024-10-15 | 24AF0149 | P00875079LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-24 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 501362 | Cabaritan Sur Integrated School | NAGUILIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4819687.44 | Completed | 1 | 2024-10-01 | 2024-05-10 | 24AF0151 | P00875080LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-04 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 100988 | Lioac ES | NAGUILIAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820774.98 | Completed | 1 | 2024-10-01 | 2024-05-10 | 24AF0152 | P00875069LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-04 | J.B. BASALLO CONSTRUCTION & SUPPLIES | COMPLETED
NC 2024 |  | Region I | La Union | 151003 | Palina ES - Annex | PUGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822249.86 | Completed | 1 | 2024-08-26 | 2024-02-08 | 24AF0138 | P00875074LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-29 | R.F. FLORES CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101005 | Amlang ES | ROSARIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822474.17 | Completed | 1 | 2024-10-01 | 2024-05-10 | 24AF0150 | P00875074LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-04 | VILLAR GENERAL CONSTRUCTION AND SUPPLIES | COMPLETED
NC 2024 |  | Region I | La Union | 101011 | Don Jose B. Bernal Elementary School | ROSARIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820774.98 | Completed | 1 | 2024-08-26 | 2024-08-15 | 24AF0128 | P00875070LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-29 | R.F. FLORES CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101015 | Parasapas ES | ROSARIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4822092.14 | Completed | 1 | 2024-08-26 | 2024-08-15 | 24AF0127 | P00875083LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-29 | R.F. FLORES CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101018 | Tanglag ES | ROSARIO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4821700.72 | Completed | 1 | 2024-08-20 | 2024-08-15 | 24AF0135 | P00875081LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-04-23 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101093 | Casilagan ES | SANTO TOMAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4821121.48 | Completed | 1 | 2024-10-16 | 2024-10-10 | 24AF0159 | P00875092LZ-CW1 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-19 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | La Union | 101096 | Damortis ES | SANTO TOMAS |  | 1 |  | Construction of School Building | GAA 17B | 5300000 |  | 5110823.84 | Completed | 1 | 2024-10-16 | 2024-05-10 | 24AF0160 | P00875092LZ-CW2 | 2024-03-14 | 2024-03-27 | 2024-03-04 | 2024-10-04 | 2024-06-19 | E.E. MADAYAG CONSTRUCTION | COMPLETED
NC 2024 |  | Region I | Laoag City | 300374 | Ilocos Norte National High School | LAOAG CITY (Capital) |  | 1 | 12 | 3STY12CL | GAA 17B | 36000000 |  |  | Ongoing | 0.6
NC 2024 |  | Region I | Laoag City |  | Mariano Marcos Laboratory Elementary School | LAOAG CITY (Capital) |  | 1 | 12 | 4STY12CL | GAA 17B | 36000000 |  |  | Ongoing | 0.5
NC 2024 |  | Region I | Laoag City | 102211 | Plaridel Elementary School | LAOAG CITY (Capital) |  | 1 | 4 | 2STY4CL | GAA 17B | 12000000 |  |  | Completed | 1
NC 2024 |  | Region I | Laoag City | 102202 | Shamrock Elementary School | LAOAG CITY (Capital) |  | 1 | 8 | 4STY8CL | GAA 17B | 25000000 |  |  | Completed | 1
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500606 | Anda Integrated School | ANDA |  | 1 |  | Construction of School Building | GAA 17B | 7000000 |  | 6850879.87 | Completed | 1 | 2024-10-19 | 2024-10-18 | P00875094LZ | 24AG0172 |  | 2024-04-25 | 2024-05-07 | 2024-05-13 | 2024-05-20 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500370 | Bolinao Integrated School | BOLINAO |  | 1 |  | Construction of School Building | GAA 17B | 14000000 |  | 7820311.42 | Completed | 1 | 2024-10-10 | 2024-10-10 | P00875095LZ | 24AG0181 |  | 2024-04-30 | 2024-05-13 | 2024-05-22 | 2024-05-29 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101355 | Lucero Elementary School | BOLINAO |  | 1 |  | Construction of School Building | GAA 17B | 8000000 |  | 13683637.8 | Completed | 1 | 2025-02-03 | 2025-02-03 | P00875093LZ | 24AG0179 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | JONIK TRADING & CONSTRUCTION
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101442 | Bobonot ES | DASOL |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5853469.15 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875120LZ | 24AG0178 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101446 | Eguia ES | DASOL |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5369131.08 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875117LZ | 24AG0175 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 300189 | Cato NHS | INFANTA |  | 1 | 4 | 2STY4CL | GAA 17B | 14000000 |  | 5376464.65 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875115LZ | 24AG0173 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | ELMUEL JAY TRADING & CONSTRUCTION
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101466 | Maya Elementary School | INFANTA |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 13685546.38 | Completed | 1 | 2024-12-05 | 2024-12-05 | P00875124LZ | 24AG0180 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | ELMUEL JAY TRADING & CONSTRUCTION
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500607 | Bacnit Integrated School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5366438 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875118LZ | 24AG0176 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101521 | De Guzman Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5370310.16 | Completed | 1 | 2024-09-10 | 2024-09-10 | P00875119LZ | 24AG0177 |  | 2024-04-30 | 2024-05-13 | 2024-05-22 | 2024-05-29 | SZCON BUILDERS INC.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101668 | Seselangen ES | SUAL |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5863864.4 | Completed | 1 | 2024-09-08 | 2024-09-06 | P00875116LZ | 24AG0174 |  | 2024-04-30 | 2024-05-13 | 2024-05-20 | 2024-05-27 | JONIK TRADING & CONSTRUCTION
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500605 | Aguilar Integrated School | AGUILAR |  | 1 | 6 | 3STY6CL (PHASE 2) | GAA 17B | 8000000 |  | 7800065.26 | Ongoing | 0.22 | 2025-11-30 |  | P00875098LZ-CW1 | 24AH0164 | 2024-05-03 | 2024-05-09 | 2024-05-22 | 2024-05-31 | 2024-06-14 | J-THREE BAGWIS CONSTRUCTION COMPANY
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101152 | Bocacliw Elementary School | AGUILAR |  | 1 | 4 | 2STY4CL | GAA 17B | 9000000 |  | 8865033.77 | Ongoing | 0.2 | 2025-04-30 |  | P00875100LZ-CW1 | 24AH0176 | 2024-08-06 | 2024-08-13 | 2024-08-27 | 2024-09-16 | 2024-10-03 | Shyka Construction Trading | Suspended due to obstruction.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101475 | Kadampat ES | LABRADOR |  | 1 | 4 | 2STY4CL (PHASE 2) | GAA 17B | 5000000 |  | 4875638.41 | Completed | 1 | 2024-12-01 | 2024-11-11 | P00875099LZ-CW1 | 24AH0161 | 2024-03-26 | 2024-04-02 | 2024-04-16 | 2024-04-30 | 2024-05-17 | R.F. Flores Construction
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500369 | Ramon Magsaysay Integrated School | LABRADOR |  | 1 | 4 | 2STY4CL | GAA 17B | 9000000 |  | 8864636.93 | Ongoing | 0.84 | 2025-05-02 |  | P00875101LZ-CW1 | 24AH0178 | 2024-08-07 | 2024-08-15 | 2024-08-28 | 2024-09-17 | 2024-10-04 | Shyka Construction Trading | Suspended due to obstruction.
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101585 | Mangatarem I CS | MANGATAREM |  | 1 | 24 | 4STY24CL | BATCH 1 | 72000000 |  | 70923600 | Ongoing | 0.79 | 2025-08-25 |  | P00875802LZ-CW1 | 24AH0165 | 2024-05-16 | 2024-05-23 | 2024-08-27 | 2024-08-30 | 2024-09-16 | Berson's Trading & Construction
NC 2024 |  | Region I | Pangasinan I, Lingayen | 300231 | Olo NHS | MANGATAREM |  | 1 | 4 | 2STY4CL | GAA 17B | 9000000 |  | 8865538.28 | Completed | 1 | 2025-04-30 | 2025-04-30 | P00875102LZ-CW1 | 24AH0175 | 2024-08-06 | 2024-08-13 | 2024-08-27 | 2024-09-16 | 2024-10-03 | Shyka Construction Trading
NC 2024 |  | Region I | Pangasinan I, Lingayen | 500374 | Ambayat Integrated School | BAYAMBANG |  | 1 | 3 | 1STY3CL | GAA 17B | 6000000 |  | 5880374.33 | Completed | 1 | 2024-09-15 | 2024-09-15 | P00875109LZ-CW1 | 24AJ0105 | 2024-03-12 | 2024-03-19 | 2024-04-03 | 2024-05-23 | 2024-06-03 | Alphin Trading & Construction
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101302 | San Vicente ES | BAYAMBANG |  | 1 | 3 | 1STY3CL | GAA 17B | 6000000 |  | 5884876.93 | Completed | 1 | 2025-01-26 | 2025-01-26 | P00875108LZ-CW1 | 24AJ0104 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-11-20 | 2024-11-26 | RP Parayno Construction
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101561 | Don Pedro ES | MALASIQUI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 5889395.67 | Completed | 1 | 2025-01-26 | 2025-01-26 | P00875105LZ-CW1 | 24AJ0102 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-11-20 | 2024-11-26 | Jeusmack Builders & Construction Supply
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101546 | Malasiqui I CS | MALASIQUI |  | 1 | 3 | 1STY3CL | GAA 17B | 6000000 |  | 4903206.67 | Completed | 1 | 2024-08-08 | 2024-08-08 | P00875107LZ-CW1 | 24AJ0103 | 2024-03-12 | 2024-03-19 | 2024-04-03 | 2024-05-06 | 2024-05-16 | LXS Builders & Supplies
NC 2024 |  | Region I | Pangasinan I, Lingayen | 101575 | San Julian CS | MALASIQUI |  | 1 | 3 | 1STY3CL | GAA 17B | 6000000 |  | 5890608 | Completed | 1 | 2025-01-26 | 2025-02-04 | P00875106LZ-CW1 | 24AJ0099 | 2024-08-13 | 2024-08-20 | 2024-09-03 | 2024-12-06 | 2024-12-13 | Rockwell Construction & Supply
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300304 | David National High School | MANGALDAN |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19302732.31 | Completed | 1 | 2024-12-29 | 2024-12-03 | P00875111LZ-CW1 | 24AH0173 | 2024-06-06 | 2024-06-12 | 2024-06-25 | 2024-06-28 | 2024-07-03 | JG Garcia Construction & Supply
NC 2024 |  | Region I | Pangasinan II, Binalonan | 101703 | Pindangan West ES | Alcala |  | 1 | 8 | 2STY8CL | BATCH 1 | 31041591.08 |  |  | Ongoing | 0.95
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300307 | Juan G. Macaraeg NHS | BINALONAN |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39203048.1 | Ongoing | 0.7 | 2025-06-02 |  | 24AI0237 |  |  | 2024-04-26 | 2024-05-16 | 2024-06-03 | 2024-06-11
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300342 | Rosario NHS | POZORRUBIO |  | 1 | 12 | 4STY12CL (Phase I) | BATCH 1 | 20504392.13 |  |  | Completed | 1 | [5 empty] | 2024-04-26 | 2024-05-16 | 2024-06-03 | 2024-06-11 | JHI Construction and Supply
NC 2024 |  | Region I | Pangasinan II, Binalonan | 102128 | Bacag Central School | VILLASIS |  | 1 | 4 | 2STY4CL | GAA 17B | 14500000 |  | 14195588.87 | Completed | 1 | 2024-11-25 | 2025-01-10 | 24AI0216 |  |  | 2024-03-22 | 2024-04-15 | 2024-05-03 | 2024-05-07 | 88 North Construction and Trading Corporation
NC 2024 |  | Region I | Pangasinan II, Binalonan | 101731 | Esmeralda ES | BALUNGAO |  | 1 | 4 | 2STY4CL | GAA 17B | 12500000 |  | 12304392.24 | Completed | 1 | 2024-11-13 | 2025-05-12 | 24AI0217 |  |  | 2024-03-22 | 2024-04-15 | 2024-05-06 | 2024-05-14 | Rivbros Construction Factors & Development
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300339 | Rajal Angayan NHS | BALUNGAO |  | 1 | 9 | 3STY9CL | GAA 17B | 30000000 |  |  | Ongoing | 0.97
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300331 | Natividad NHS | NATIVIDAD |  | 1 | 8 | 4STY8CL | GAA 17B | 28000000 |  | 27480030.49 | Ongoing | 0.45 | 2025-06-13 |  | 24AI0218 |  |  | 2024-03-22 | 2024-04-16 | 2024-05-06 | 2024-05-14 | Rivbros Construction Factors & Development
NC 2024 |  | Region I | Pangasinan II, Binalonan | 101881 | Pangaoan E/S | ROSALES |  | 1 | 4 | 2STY4CL | GAA 17B | 12000000 |  | 11736764.95 | Ongoing | 0.98 |  |  | 24AI0217 |  |  | 2024-03-22 | 2024-04-16 | 2024-04-25 | 2024-05-02 | Rivbros Construction Factors & Development
NC 2024 |  | Region I | Pangasinan II, Binalonan | 101962 | San Roque ES | SAN MANUEL |  | 1 | 4 | 2STY4CL | GAA 17B | 12500000 |  |  | Completed | 1 | [5 empty] | 2024-05-01 | 2024-05-20 | 2024-06-03 | 2024-06-11
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300361 | Sto. Tomas NHS | SAN NICOLAS |  | 1 | 10 | Completion of 2STY4CL/2STY6CL | BATCH 1 | 4318356.16 |  |  | Completed | 1 | 2025-01-14 |  | 24AI0240 |  |  | 2024-05-01 | 2024-05-20 | 2024-06-03 | 2024-06-11 | DMGR Builders
NC 2024 |  | Region I | Pangasinan II, Binalonan | 102043 | Cal-litang ES | SANTA MARIA |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 229264.54 |  |  | Completed | 1
NC 2024 |  | Region I | Pangasinan II, Binalonan | 102072 | Magallanes ES | TAYUG |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 234000 |  |  | Completed | 1
NC 2024 |  | Region I | Pangasinan II, Binalonan | 102079 | Barat ES | UMINGAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  |  | Completed | 1 | 2025-01-14 |  | 24AI0239 |  |  | 2024-05-01 | 2024-05-20 | 2024-06-03 | 2024-06-11 | DMGR Builders
NC 2024 |  | Region I | Pangasinan II, Binalonan | 300365 | Umingan Central National High School | UMINGAN |  | 1 | 16 | 4STY16CL | BATCH 1 | 55766000 |  |  | Ongoing | 0.35
NC 2024 |  | Region I | San Carlos City | 102227 | Ano Elementary School | SAN CARLOS CITY |  | 1 | 3 | 1STY3CL | GAA 17B | 6000000 |  | 5896400 | Completed | 1 | 2024-08-28 | 2024-08-28 | - | 24AJ0101 | 2024-12-03 |  | 2024-03-04 | 2024-06-05 | 2024-05-16 | Mightyway Construction & Supply | NO PROJECT ID AND DATE OF PRE-SUBMISSION CONFERENCE
NC 2024 |  | Region I | San Carlos City | 102253 | Bacnar Elementary School | SAN CARLOS CITY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4921110 | Completed | 1 | 2024-08-08 | 2024-08-08 | - | 24AJ0100 | 2024-12-03 |  | 2024-03-04 | 2024-06-05 | 2024-05-16 | Rockwell Construction & Supply | NO PROJECT ID AND DATE OF PRE-SUBMISSION CONFERENCE
NC 2024 |  | Region I | San Carlos City | 500645 | Candido Marcellano Integrated School | SAN CARLOS CITY |  | 1 | 8 | 4STY8CL | BATCH 1 | 24886432.16 |  | 24422780 | Completed | 1 | 2025-01-20 | 2025-01-20 | - | 24AJ0114 | 2024-05-17 |  | 2024-06-06 | 2024-06-28 | 2024-10-07 | Mightyway Construction & Supply | NO PROJECT ID AND DATE OF PRE-SUBMISSION CONFERENCE. WAITING FOR THE ADDTIONAL FUND FOR THE COMPLETION OF THE BUILDING
NC 2024 |  | Region I | San Fernando City | 300118 | La Union NHS | CITY OF SAN FERNANDO (Capital) |  | 1 | 12 | 4STY12CL | BATCH 1 | 40830555.55 |  | 40624001.77 | Ongoing | 0.9 | 2025-03-13 |  |  | 24AE0101 |  |  | 2024-04-30 | 2024-05-13 | 2024-05-21 | ELITE GENERAL CONTRACTOR AND DEVELOPMENT CORP./A.C. NAVARRO CONSTRUCTION SERVICES AND SUPPLY
NC 2024 |  | Region I | Urdaneta City | 500442 | Calegu Integrated School | CITY OF URDANETA |  | 1 | 8 | 4STY8CL | BATCH 1 | 31137875.56 |  | 30514610.9 | Ongoing | 0.95 | 2025-02-18 |  | 24AI0248 | 6/11/2024 | 2024-05-13 | 2024-05-20 | 2024-06-03 | 2024-06-07 | 2024-06-14 | A.P. TAGARINO ENGINEERING & CONSTRUCTION SERVICES | Substantially completed/for punchlist
NC 2024 |  | Region I | Urdaneta City | 102273 | Casabula Elementary School | CITY OF URDANETA |  | 1 | 2 | 1STY2CL | GAA 17B | 5500000 |  | 5390654.31 | Completed | 1 | 2024-12-09 | 2025-01-15 | 24AI0221 | 5/24/2024 | 2024-05-04 |  | -612031 | 2024-05-20 | 2024-05-28 | BUILDERS EXPONENT EMPIRE CORPORATION
NC 2024 |  | Region I | Vigan City | 300052 | Ilocos Sur National High School | CITY OF VIGAN (Capital) |  | 1 | 16 | 4STY16CL | BATCH 1 | 48223484.12 |  |  | Ongoing | 0.5

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.