## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-23 | 030414S00010 | 14CI0010 | 2014-06-02 | 2014-06-06 | 2014-06-17 | 2014-06-30 | 2014-07-04 | RBDIWA BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region III | Angeles City | 107053 | CUAYAN ELEMENTARY SCHOOL | ANGELES CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-08-28 | 2014-08-28 | 030414S00011 | 14CI0011 | 2014-06-02 | 2014-06-06 | 2014-06-17 | 2014-06-30 | 2014-07-04 | MJBZ BUILDERS AND TRADING
NC 2014 | K10 (2014) | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4662528.49 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-15 | 030414S00025 | 15CI0056 | 2015-06-23 | 2015-06-26 | 2015-07-08 | 2015-07-16 | 2015-08-14 | GEOHEART CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Angeles City | 107032 | Pineda-Gutierrez ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7707 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-17 | 030414S00015 | 14CI0040 | 2014-11-20 | 2014-11-24 | 2014-12-05 | 2014-12-16 | 2014-12-19 | M.C.B. ZAMORA CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | Angeles City | 307201 | Rafael L. Lazatin Mem. HS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-05-26 |  | 030414S00045 | 15CI0079 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-12 | 2015-08-25 | AL-B DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region III | Angeles City | 107044 | Sapang Bato ES | ANGELES CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 030414S00012 | 14CI0012 | 2014-06-02 | 2014-06-06 | 2014-06-17 | 2014-07-23 | 2014-07-30 | GEOHEART CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Angeles City | 301043 | Sapangbato HS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 24152343.62 |  |  | COMPLETED | 1 | 2016-03-28 |  | 030414S00052 | 15CI0080 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-12 | 2015-09-01 | LUCKY STAR CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Angeles City | 107046 | Sitio Pader ES | ANGELES CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1 | 2015-12-02 | 2015-10-31 | 030414S00056 | 15CI0057 | 2015-06-23 | 2015-06-26 | 2015-07-07 | 2015-07-15 | 2015-07-29 | THREE KCS BUILDERS AND SUPPLY
NC 2014 | K10 (2014) | Region III | Aurora | 104409 | Baler CS | BALER (Capital) | 0 | 1 | 10 | 2sty10cl | 2014 K10 BATCH 4C | 12771310.093 |  |  | COMPLETED | 1 | 2016-05-18 |  | 030714S00012 | 15CN0124 | 2015-11-19 | 2015-11-20 | 2015-12-03 | 2015-12-10 | 2015-12-21
NC 2014 | K10 (2014) | Region III | Aurora | 104494 | Bernabe R. Dulay Memorial ES | MARIA AURORA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-26 |  | 030714S00017 | 15CN0067 | 2015-07-14 | 2015-07-16 | 2015-07-28 | 2015-08-10 | 2015-08-28 | VANMARVIL CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Aurora | 104422 | Calantas ES | CASIGURAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1760905.0717 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 030714S00003 | 14CN0079 | 2014-11-02 | 2014-11-05 | 2014-11-17 | 2014-11-25 | 2014-12-29 | RIJANNA ZOE CONSTRUCTION AND HARDWARE SUPPLY
NC 2014 | K10 (2014) | Region III | Aurora | 306510 | Carmen T. Valenzuela Integrated School | BALER (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1745830.0717 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 030714S00004 | 14CN0081 | 2014-11-02 | 2014-11-05 | 2014-11-17 | 2014-11-25 | 2014-12-29 | RADIANCE TRADERS & BUILDERS
NC 2014 | K10 (2014) | Region III | Aurora | 306513 | Dimanayat IS | SAN LUIS | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 |  |  | 030714S00015 |  | 2015-07-16 |  | 2015-09-28
NC 2014 | K10 (2014) | Region III | Aurora | 157501 | Esperanza ES | CASIGURAN | 0 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-27 |  | 030714S00016 | 15CN0126 | 2015-11-24 | 2015-11-26 | 2015-12-08 | 2015-12-17 | 2015-12-29
NC 2014 | K10 (2014) | Region III | Aurora | 104500 | Francisco Q. Dagyapen ES | MARIA AURORA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 974017.8499 |  |  | COMPLETED | 1 | 2015-04-19 | 2015-04-19 | 030714S00005 | 14VCN0088 | 2014-11-28 | 2014-12-08 | 2014-12-18 | 2014-12-29 | 2015-01-15 | RIJANNA ZOE CONSTRUCTION AND HARDWARE SUPPLY
NC 2014 | K10 (2014) | Region III | Aurora | 104522 | Kamalatan ES | SAN LUIS | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1765930.0717 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 030714S00002 | 14CN0080 | 2014-11-02 | 2014-11-05 | 2014-11-17 | 2014-11-25 | 2014-12-29 | JOHN DEE B. BUSTAMANTE CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Aurora | 104486 | Leon B. Hulipas ES | MARIA AURORA | 0 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3765805.49 |  |  | COMPLETED | 1 | 2015-02-27 | 2015-01-09 | 030714S00001 | 14CN0020 | 2014-06-16 | 2014-06-19 | 2014-07-31 | 2014-09-12 | 2014-09-19 | RADIANCE TRADERS & BUILDERS
NC 2014 | SHS (2014) | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | 0 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030714S00010 | 15CN0109 | 2015-10-11 | 2015-10-15 | 2015-10-26
NC 2014 | K10 (2014) | Region III | Aurora | 306514 | Tinib-Calangcuasan Integrated School | CASIGURAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1914740.174 |  |  | COMPLETED | 1 | 2015-11-29 | 2015-11-29 | 030714S00006 | 15CN0080 | 2015-07-16 | 2015-07-16 | 2015-07-30 | 2015-08-12 | 2015-09-01 | R.N.G.M. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 030114S00017 | 15CA0054 | 2015-09-18 | 2015-08-25 | 2015-10-08
NC 2014 | SHS (2014) | Region III | Bataan | 300705 | Hermosa NHS | HERMOSA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Bataan | 300704 | J. C. Payumo, Jr. Memo. HS | DINALUPIHAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8864965.051 |  |  | COMPLETED | 1 | 2016-01-14 |  | 030114S00022 | 15CA0038 | 2015-07-31 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-09 | E.R. VENZON CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bataan | 306614 | Kanawan Integrated School | MORONG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030114S00025 | 15CA0035 | 2015-07-31 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-09-03 | ORANI BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region III | Bataan | 300708 | Luakan National High School | DINALUPIHAN | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22552343.62 |  |  | COMPLETED | 1 |  |  | 030114S00021 | 15CA0055 | 2015-09-18 | 2015-09-25 | 2015-10-08
NC 2014 | K10 (2014) | Region III | Bataan | 104612 | Maite ES | HERMOSA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1132049.6543 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-11-01 | 030114S00006 | 15CA0034 | 2015-07-31 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-09-03 | RTDJR CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region III | Bataan | 300713 | Morong NHS | MORONG | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8389965.051 |  |  | COMPLETED | 1 | 2016-01-22 |  | 030114S00020 | 15CA0039 | 2015-07-31 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-09 | DE JESUS CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300715 | Orani NHS | ORANI | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22502343.62 |  |  | COMPLETED | 1 | 2016-05-02 |  | 030114S00019 | 15CA0051 | 2015-09-14 | 2015-09-21 | 2015-10-01 | 2015-10-09 | 2015-11-04 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region III | Bataan | 306608 | Orani NHS - Pagasa | ORANI | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1 | 2014-10-12 | 2014-09-15 | 030114S00001 | 14CA0012 | 2014-05-13 | 2014-05-15 | 2014-06-10 | 2014-06-25 | 2014-07-01 | E.R. VENZON CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8574965.051 |  |  | COMPLETED | 1 | 2016-01-14 |  | 030114S00024 | 15CA0040 | 2015-07-31 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-09 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region III | Bataan | 300718 | Pagalanggang NHS | DINALUPIHAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 030114S00005 | 15CA0036 | 2015-07-31 | 2015-08-06 | 2015-08-18 | 2015-08-28 | 2015-09-09 | RTDJR CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Bataan | 104618 | Pulo ES | HERMOSA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-09-12 | 2014-09-10 | 030114S00002 | 14CA0011 | 2014-05-13 | 2014-05-15 | 2014-06-10 | 2014-06-25 | 2014-07-01 | LTM BUILDERS
NC 2014 | SHS (2014) | Region III | Bataan | 300719 | Samal NHS | SAMAL | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15147518.84 |  |  | COMPLETED | 1 |  |  | 030114S00010 | 15CA0056 | 2015-09-18 | 2015-08-25 | 2015-10-08
NC 2014 | SHS (2014) | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 | 2016-04-07 |  | 030114S00011 | 15CB0048 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-06 | DE JESUS CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bataan | 500119 | Biaan Aeta Integrated School | MARIVELES | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1934740.174 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-12-04 | 030114S00004 | 15CB0031 | 2015-07-06 | 2015-07-14 | 2015-07-21 | 2015-07-29 | 2015-08-03 | DE JESUS CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bataan | 104543 | Binuangan ES | BAGAC | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1914740.174 |  |  | COMPLETED | 1 | 2015-11-15 | 2015-11-15 | 030114S00009 | 15CB0034 | 2015-07-13 | 2015-07-21 | 2015-07-28 | 2015-08-05 | 2015-08-12 | POLYMER-VIC CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300699 | E. C. Bernabe NHS | BAGAC | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8814965.051 |  |  | COMPLETED | 1 | 2016-04-07 |  | 030114S00012 | 15CB0049 | 2015-10-08 | 2015-10-15 | 2015-10-22 | 2015-10-29 | 2015-11-06 | DE JESUS CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 306601 | JUSTICE EMILIO ANGELES GANCAYCO MEMORIAL HIGH SCHOOL | ORION | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8389965.051 |  |  | COMPLETED | 1 | 2015-12-22 | 2015-12-22 | 030114S00013 | 15CB0035 | 2015-07-16 | 2015-07-24 | 2015-07-31 | 2015-08-10 | 2015-08-17 | VF CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300706 | Lamao NHS | LIMAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-20 | 2015-12-20 | 030114S00015 | 15CB0033 | 2015-07-13 | 2015-07-21 | 2015-07-28 | 2015-08-05 | 2015-08-12 | N.V. BALBUENA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300707 | Limay NHS | LIMAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Bataan | 306615 | Mariveles NHS Annex - Sisiman | MARIVELES | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-04 | 2015-12-30 | 030114S00027 | 15CB0042 | 2015-07-23 | 2015-07-31 | 2015-08-07 | 2015-08-19 | 2015-09-01 | ETM CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bataan | 306610 | Mariveles NHS, Cab.Annex (Batangas II) | MARIVELES | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6419337.6381 |  |  | COMPLETED | 1 | 2015-12-22 | 2015-12-22 | 030114S00008 | 15CB0036 | 2015-07-16 | 2015-07-24 | 2015-07-31 | 2015-08-10 | 2015-08-17 | DE JESUS CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bataan | 300710 | Mariveles NHS, Cabcaben | MARIVELES | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1 |  |  | 030114S00016 | 15CB0064 | 2015-12-01 | 2015-12-08 | 2015-12-15 | 2015-12-23
NC 2014 | SHS (2014) | Region III | Bataan | 300716 | P. Roman NHS | PILAR | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-09 |  | 030114S00014 | 15CB0057 | 2015-11-08 | 2015-11-17 | 2015-11-24 | 2015-12-02 | 2015-12-08 | ORANI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region III | Bataan | 104547 | Paysawan ES | BAGAC | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-11-04 | 2015-10-30 | 030114S00007 | 15CB0030 | 2015-07-06 | 2015-07-14 | 2015-07-21 | 2015-07-29 | 2015-08-03 | DE JESUS CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bataan | 104686 | Sta. Elena ES | Orion | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-04 | 2015-12-31 | 030114S00026 | 15CB0041 | 2015-07-23 | 2015-07-31 | 2015-08-07 | 2015-08-19 | 2015-09-01 | N.V. BALBUENA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bulacan | 105017 | Dulong Malabon ES | PULILAN | 1 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-01-06 | 2015-12-31 | 030214S00046 | 15CC0169 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-09-08 | ESN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 104805 | Frances Elementary School | CALUMPIT | 1 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2016-01-06 |  | 030214S00047 | 15CC0170 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-09-08 | M.G. FRANCISCO CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bulacan | 158533 | Nothville IX ES | CALUMPIT | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-04 | 2015-07-04 | 030214S00013 | 15CC0003 | 2015-01-13 | 2015-01-19 | 2015-02-04 | 2015-02-18 | 2015-03-06 | ESN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 105020 | Pulilan CS | PULILAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6595139.7656 |  |  | COMPLETED | 1 | 2015-07-03 | 2015-07-03 | 030214S00014 | 15CC0002 | 2015-01-13 | 2015-01-19 | 2015-02-04 | 2015-02-18 | 2015-03-05 | ESN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 105022 | S. ESguerra Sr. MS | PULILAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Bulacan | 105022 | S. ESguerra Sr. MS | PULILAN | 1 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Bulacan | 306729 | Batia High School | BOCAUE | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030214S00030 | 15CC0168 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-10-12 | JOSE RUBI CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bulacan | 104789 | Catacte ES | BUSTOS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-06 | 2015-12-31 | 030214S00038 | 15CC0173 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-09-08 | M.G. FRANCISCO CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bulacan | 300727 | Dr. Felipe de Jesus HS | PLARIDEL | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030214S00029 | 15CC0193 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-08-27
NC 2014 | K10 (2014) | Region III | Bulacan | 104824 | Dra. Ruperta G. Caluag ES (Ilang-Ilang PS) | GUIGUINTO | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-23 | 2015-07-23 | 030214S00012 | 15CC0004 | 2015-01-13 | 2015-01-19 | 2015-02-04 | 2015-02-18 | 2015-03-05 | LIBERTY RICH CONSTRUCTION & BUILDERS INC.
NC 2014 | K10 (2014) | Region III | Bulacan | 104825 | Malis ES | GUIGUINTO | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10667093.5547 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030214S00011 | 15CC0001 | 2015-01-13 | 2015-01-19 | 2015-02-04 | 2015-02-18 | 2015-04-15 | ST. BERNARDINE CONSTRUCTION & ENTERPRISES (FOR. ST
NC 2014 | K10 (2014) | Region III | Bulacan | 104827 | Pulonggubat ES | Guiguinto | 2 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-30 |  | 030214S00049 | 15CC0175 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-10-30 | ADIMRE CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Bulacan | 300730 | Calawitan NHS | SAN ILDEFONSO | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-30 |  | 030214S00036 | 15CD0117 a | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 300761 | North Hills Village High School | NORZAGARAY | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10679132.01 |  |  | COMPLETED | 1 | 2016-02-28 |  | 030214S00031 | 15CD0116 a | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS
NC 2014 | K10 (2014) | Region III | Bulacan | 105062 | Sapang Putik Elementary School | San Ildefonso South | 3 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-10-31 | 030214S00048 | 15CD0118 a | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 158534 | Sitio Biga PS | SAN ILDEFONSO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-02-28 |  | 030214S00024 | 15CD0116 b | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS
NC 2014 | K10 (2014) | Region III | Bulacan | 105089 | Sta. Lucia ES | San Miguel North | 3 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-10-31 | 030214S00043 | 15CD0118 b | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Bulacan | 105144 | C.M.De Jesus MS | SANTA MARIA | 4 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4B | 18222268.79 |  |  | COMPLETED | 1 | 2016-07-06 |  | 030214S00027 | 15CD0205 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-27 | 2015-12-08 | E.A. SANCHO CONST. INC. (FORM. E.A. SANCHO CONST.)
NC 2014 | K10 (2014) | Region III | Bulacan | 105145 | Camachile PS | SANTA MARIA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 030214S00006 | 14CD0067 | 2014-07-02 | 2014-07-03 | 2014-07-15 | 2014-07-24 | 2014-08-01 | MARGARITA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Bulacan | 104902 | FSS Patulo ES | MARILAO | 4 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10679132.01 |  |  | COMPLETED | 1 | 2016-02-28 |  | 030214S00028 | 15CD0112 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | AZUL BUILDERS
NC 2014 | K10 (2014) | Region III | Bulacan | 158514 | Heritage Homes ES | MARILAO | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-06-19 | 2015-06-18 | 030214S00009 | 14CD0254 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | AZUL BUILDERS
NC 2014 | K10 (2014) | Region III | Bulacan | 104907 | Loma de Gato Elementary School | MARILAO | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-19 | 030214S00010 | 14CD0253 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | LE REVE BUILDERS
NC 2014 | SHS (2014) | Region III | Bulacan | 300764 | Obando School of Fisheries | OBANDO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 | 2016-06-04 |  | 030214S00037
NC 2014 | SHS (2014) | Region III | Bulacan | 300766 | Prenza NHS | MARILAO | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-04-16 |  | 030214S00035 | 15CD0113 | 2015-07-01 | 2015-07-02 | 2015-08-25 | 2015-09-08 | 2015-09-17 | M.S. RAMOS CONSTRUCTION INC. (FORMERLY: M.S. RAMOS
NC 2014 | SHS (2014) | Region III | Bulacan | 300767 | Pulong Buhangin NHS | SANTA MARIA | 4 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-01 |  | 030214S00034 | 15CD0115 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | B. BERNARDO CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 107095 | Bakero Elementary School | CABANATUAN CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 030314S00022 | 15CF0105 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-09-09 | 2015-09-21 | R.G. DELA CRUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 107074 | Caalibangbangan ES | CABANATUAN CITY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1257329.12 |  |  | COMPLETED | 1 | 2014-09-24 | 2014-09-22 | 030314S00010 | 14CF0022 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-24 | 2014-08-05 | R.G. DELA CRUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 107109 | Cabanatuan North ES | CABANATUAN CITY | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 107109 | Cabanatuan North ES | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 107066 | Imelda ES | CABANATUAN CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1 | 2016-03-12 |  | 030314S00021 | 15CF0104 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-11-25 | 2015-12-07 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Cabanatuan City | 307305 | San Isidro Integrated School | CABANATUAN CITY | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-11-16 | 2015-11-16 | 030314S00130 | 15CF0057 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-13 | F.L. REGUYAL CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region III | Mabalacat City | 106075 | Dapdap ES | MABALACAT | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1 | 2015-05-15 | 2015-03-18 | 030414S00013 | 14CI0039 | 2014-11-20 | 2014-11-24 | 2014-12-05 | 2014-12-16 | 2014-12-19 | RBDIWA BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region III | Mabalacat City | 306909 | Mabalacat TVS | MABALACAT | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 030414S00044 | 15CI0060 | 2015-06-23 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 2015-07-27 | E.M.L. CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35596257.14 |  |  | COMPLETED | 1 | 2016-05-26 |  | 030414S00040 | 15CI0072 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-11 | 2015-08-25 | LUCKY STAR CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Mabalacat City | 306942 | Santos Ventura NHS | MABALACAT | 1 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35596257.14 |  |  | COMPLETED | 1 | 2016-05-26 |  | 030414S00043 | 15CI0073 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-08-11 | 2015-08-25 | R.M. VITUG CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Malolos City | 240006 | Calero Elementary School | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | REVERTED | 0 |  |  | 030214S00041 | 15CC0180 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25
NC 2014 | K10 (2014) | Region III | Malolos City | 104890 | Caniogan ES | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-06 |  | 030214S00042 | 15CC0176 | 2015-07-20 | 2015-07-22 | 2015-10-13 | 2015-11-02 | 2015-12-08 | FRAMECON BUILDERS
NC 2014 | K10 (2014) | Region III | Malolos City | 323607 | City of Malolos High School - Canalate | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6519892.1381 |  |  | COMPLETED | 1 | 2016-03-09 |  | 030214S00026 | 15CC0177 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-25 | 2015-11-10 | A.R.L. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Malolos City | 500404 | City of Malolos Integrated School - Atlag | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 | 2016-04-08 |  | 030214S00032 | 15CC0188 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-08-27 | 2015-11-10 | A.R.L. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Malolos City | 104875 | Mabolo ES | CITY OF MALOLOS (Capital) | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-21 | 030214S00007 | 14CC0034 | 2014-08-22 | 2014-08-22 | 2014-09-04 | 2014-09-15 | 2014-09-26 | ESN CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 |  | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Meycauayan City | 104915 | Bagbaguin ES | CITY OF MEYCAUAYAN | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-28 |  | 030214S00025 | 15CD0111 a | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | K10 (2014) | Region III | Meycauayan City | 104922 | Lawa ES | CITY OF MEYCAUAYAN | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-19 | 030214S00018 | 14CD0255 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | B. BERNARDO CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Meycauayan City | 104927 | Pantoc ES | CITY OF MEYCAUAYAN | 4 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | REVERTED | 0 |  |  | 030214S00039
NC 2014 | SHS (2014) | Region III | Meycauayan City | 306719 | Ubihan HS | CITY OF MEYCAUAYAN | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | REVERTED | 0 |  |  | 030214S00033
NC 2014 | K10 (2014) | Region III | Munoz Science City | 105555 | Pandalla PS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-10-10 | 030314S00023 | 15CE0094 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300783 | Aliaga National NHS | ALIAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-11 |  | 030314S00090 | 15CE0062 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105404 | Bacayao ES | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 030314S00008 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300786 | Baloy HS | CUYAPO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-23 | 030314S00089 | 15CE0050 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-07-22 | LISA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105375 | Bantug ES | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 030314S00009 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | MIVICO BUILDERS & DEVELOPERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | GUIMBA | 1 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10997342.5917 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00088 | 15CE0109 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 306829 | Bartolome R Sangalang NHS Annex-Macatcatuit | GUIMBA | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030314S00125 | 15CE0134 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-05 | 2015-08-19 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300788 | Batitang NHS | ZARAGOZA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-20 |  | 030314S00087 | 16CE0066 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105258 | Bibiclat ES | CUYAPO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 030314S00003 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-08-28 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300791 | Bulac NHS | TALAVERA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00086 | 15CE0112 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300796 | Carmen NHS | ZARAGOZA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-11 |  | 030314S00085 | 15CE0065 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105380 | Cavite ES | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 030314S00006 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105268 | Curva ES | CUYAPO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 030314S00004 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300801 | Cuyapo National NHS | CUYAPO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 030314S00073 | 15CE0081 | 2015-06-24 | 2015-07-02 | 2015-07-11 | 2015-07-23 | 2015-07-29 | LISA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105621 | Doña Lucia Elementary School | QUEZON | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-13 |  | 030314S00133 | 15CE0118 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-10-13 | R.G. DELA CRUZ CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030314S00083 | 15CE0080 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-08-28 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. HS | QUEZON | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300845 | Exequiel R. Lina National High School | LICAB | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-18 |  | 030314S00081 | 15CE0075 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300806 | Galvan HS | GUIMBA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 030314S00080 | 15CE0077 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306808 | Ganduz National High School | PANTABANGAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030314S00100 | 15CE0098 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | WIZARD TRADING AND CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105777 | Gen. Luna ES | SANTO DOMINGO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 030314S00011 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 159032 | Ilog Baliwag PS | SANTO DOMINGO | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-30 |  | 030314S00126 | 15CE0119 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00079 | 15CE0073 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105278 | Malineng ES | CUYAPO | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030314S00128 | 15CE0115 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105389 | Manacsac ES | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 030314S00005 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-09-04 | 2014-09-17 | FNR BUILDERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306815 | Manacsac HS (Former Nagpandayan HS Annex) | GUIMBA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-11 |  | 030314S00084 | 15CE0110 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | FNR CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105392 | Nagpandayan ES | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 030314S00007 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | 969 CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300825 | Nagpandayan NHS | GUIMBA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 030314S00078 | 15CE0111 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | FNR CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300838 | Nampicuan NHS | NAMPICUAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 030314S00077 | 15CE0079 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306810 | PACAC HIGH SCHOOL | GUIMBA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030314S00076 | 15CE0089 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | LISA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105283 | Paitan Norte ES | CUYAPO | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030314S00120 | 15CE0117 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300827 | Paitan Sur NHS | CUYAPO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-18 |  | 030314S00075 | 15CE0082 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | IRC CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105800 | Pantok Bulak PS | TALAVERA | 1 | 1 | 2 | 2sty2cl | 2014 K10 BATCH 4C | 4572048.49 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00127 | 15CE0140 | 2015-07-15 | 2015-07-23 | 2015-07-23 | 2015-08-26 | 2015-08-28 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 159006 | Pulong Buli ES | SANTO DOMINGO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 030314S00017 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-23 | 030314S00074 | 05CE0063 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-05 |  | 030314S00082 | 15CE0055 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-09-17 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300843 | San Andres HS | GUIMBA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-17 | 2015-12-28 | 030314S00102 | 15CE0076 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | SPECO BUILDERS INC. (FORMERLY:VRF CONSTRUCTION)
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00110 | 15CE0068 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300852 | Sibul NHS | TALAVERA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00114 | 15CE0069 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300855 | Sta. Maria NHS | LICAB | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-23 | 030314S00107 | 15CE0049 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-09-14 | R.G. DELA CRUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105189 | Sta. Monica ES | Aliaga | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030314S00129 | 15CE0115 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105430 | STA. VERONICA ELEMENTARY SCHOOL | GUIMBA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-07 | 030314S00014 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | SPECO BUILDERS INC. (FORMERLY:VRF CONSTRUCTION)
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300859 | Sto. Rosario NHS, Sto. Domingo | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-25 |  | 030314S00112 | 15CE0071 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-10-09 | MIVICO BUILDERS & DEVELOPERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300865 | Tabacao HS | TALAVERA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00111 | 15CE0070 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300864 | Talavera NHS | TALAVERA | 1 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35596257.14 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300869 | Triala NHS | GUIMBA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-19 |  | 030314S00108 | 15CE0078 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306811 | Umangan National High School | ALIAGA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-04 |  | 030314S00115 | 15CE0108 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-17 |  | 030314S00106 | 15CE0064 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | A.M.P. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105866 | Zaragoza CS | ZARAGOZA | 1 | 1 | 2 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-11 | 030314S00012 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-26 | 2014-09-10 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030314S00105 | 15CE0135 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-10 | 2015-08-19 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306826 | Zaragoza National High School-Annex | ZARAGOZA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 030314S00104 | 15CE0067 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-29 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300782 | Agbannawag National High School | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030314S00103 | 15CE0099 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | IRC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306806 | AGUPALO WESTE HIGH SCHOOL | LUPAO | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-22 | 030314S00095 | 15CE0056 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-07-22 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300784 | Andres Bonifacio NHS | LLANERA | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1 | 2015-11-26 | 2015-11-18 | 030314S00101 | 15CE0113 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | F.C. MARTINEZ CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300789 | Bicos NHS | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-04-15 |  | 030314S00116 | 15CE0100 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-28 | 2015-08-11 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105237 | Binbin ES | CARRANGLAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-21 | 2014-11-21 | 030314S00013 |  | 2014-07-03 | 2014-07-11 | 2014-07-24 | 2014-08-15 | 2014-08-28 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105491 | Bosque ES | LLANERA | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 030314S00124 | 15CE0120 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | SPECO BUILDERS INC. (FORMERLY:VRF CONSTRUCTION)
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 500121 | Bunga Integrated HS | CARRANGLAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-24 | 030314S00099 | 15CE0057 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-20 | 2015-07-22 | FNR CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300793 | Cabucbucan NHS | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030314S00098 | 15CE0101 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | IRC CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300795 | Canaan East NHS | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030314S00097 | 15CE0124 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-05 | 2015-08-19 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300798 | Capintalan HS | CARRANGLAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00096 | 15CE0131 | 2015-07-08 | 2015-07-15 | 2015-11-25 |  |  | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300797 | Carranglan NHS | CARRANGLAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030314S00093 | 15CE0093 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105520 | Cordero ES | LUPAO | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030314S00123 | 15CE0121 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-30 | 2015-08-10 | REBCOR CONSTRUCTION AND TRADING CORPORATION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105643 | Del Pilar ES | RIZAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300799 | Digdig HS | CARRANGLAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-03-10 |  | 030314S00068 | 15CE0132 | 2015-07-08 | 2015-07-28 | 2015-07-28 | 2015-08-05 | 2015-10-05 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300802 | Doña Juana Chioco NHS | LUPAO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030314S00041 | 15CE0092 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 500120 | Gen. Luna Integrated HS | CARRANGLAN | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-11-15 | 030314S00042 | 15CE0058 | 2015-06-19 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-07-22 | FNR CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300807 | General Luna NHS | LLANERA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030314S00046 | 15CE0090 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | IJK CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105500 | Inanama ES | LLANERA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-25 | 2015-10-14 | 030314S00024 | 15CE0095 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | ALLEN CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300870 | Llanera National HIgh School | LLANERA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 030314S00045 | 15ce0096 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | WIZARD TRADING AND CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300830 | Pantabangan NHS | PANTABANGAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 030314S00044 | 15ce097 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | F.L. REGUYAL CONSTRUCTION CORPORATION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300841 | Rizal NHS | RIZAL | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-10 |  | 030314S00043 | 15CE0097 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-05 | ALLEN CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306802 | San Felipe Integrated High School | LLANERA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-25 | 2015-09-25 | 030314S00036 | 15CE0059 | 2015-06-17 | 2015-06-24 | 2015-07-08 | 2015-07-16 | 2015-07-22 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300847 | San Isidro NHS | LUPAO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 030314S00039 | 15CE0114 | 2015-07-08 | 2015-07-21 | 2015-07-22 | 2015-07-30 | 2015-08-10 | ADROIT CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300866 | Talugtug NHS | TALUGTUG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-01-08 |  | 030314S00038 | 15CE0091 | 2015-06-24 | 2015-07-02 | 2015-07-14 | 2015-07-29 | 2015-08-06 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306828 | Talugtug NHS Annex-Saverona | TALUGTUG | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-24 | 2015-10-24 | 030314S00025 | 15CE0060 | 2015-06-17 | 2015-06-24 | 2015-07-07 | 2015-07-16 | 2015-07-22 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300787 | Barangay Militar NHS | PALAYAN CITY (Capital) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-18 |  | 030314S00037 | 15CF0090 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-09-09 | 2015-09-21 | A.M.P. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300790 | Bongabon NHS | BONGABON | 3 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10997342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 306287 | F. Buencamino Sr. Integrated School | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 030314S00020 | 15CF0059 | 2015-07-09 | 2015-07-10 | 2015-07-23 | 2015-08-03 | 2015-08-13 | D.G. SARMENTA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300805 | Gabaldon Voc'l. Agric. HS | GABALDON (BITULOK & SABANI) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-03-10 |  | 030314S00035 | 15CF0093 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-26 | 2015-09-07 | ALLEN CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300862 | Gen. Mamerto Natividad HS | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 | 2016-03-01 |  | 030314S00034 | 15CF0115 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-09-28 | D.G. SARMENTA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. HS | LAUR | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00033 | 15CF0094 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-26 | 2015-09-07 | MIVICO BUILDERS & DEVELOPERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300811 | Jorge M. Padilla NHS | LAUR | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00032 | 15CF0095 | 2015-07-27 | 2015-07-28 | 2015-08-13
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105206 | Labi ES | BONGABON | 3 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-30 |  | 030314S00122 | 15CF0086 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-09-16 | 2015-09-28 | L.A.V. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306814 | Ligaya National High School | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00031 | 15CF0087 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | L.A.V. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300816 | Macabaclay NHS | BONGABON | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-03-11 |  | 030314S00030 | 15CF0092 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-26 | 2015-09-07 | JERRY R. SANTIAGO CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300818 | Malacañang NHS | SANTA ROSA | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-02-01 |  | 030314S00029 | 15CF0091 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-09-18 | 2015-09-29 | ALLEN CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300819 | Maligaya NHS | PALAYAN CITY (Capital) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-03-16 |  | 030314S00028 | 15CF0097 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-10-01 | 2015-10-13 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300823 | Mataas Na Kahoy NHS | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-14 |  | 030314S00027 | 15CF0088 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | D.G. SARMENTA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300826 | Nueva Ecija NHS | CABANATUAN CITY | 3 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35716257.14 |  |  | COMPLETED | 1 |  |  | 030314S00026 | 15CF0181 | 2015-11-26 | 2015-11-27 | 2015-12-22
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300828 | Palayan City National High School | PALAYAN CITY (Capital) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00061 | 15CF0096 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-08-26 | 2015-09-07 | D.G. SARMENTA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306801 | Santa Rosa NHS | SANTA ROSA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00071 | 15CF0099 | 2015-07-27 | 2015-07-28 | 2015-08-13
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300858 | Sto. Rosario NHS , Sta. Rosa | SANTA ROSA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00070 | 15CF0100 | 2015-07-27 | 2015-07-28 | 2015-08-13
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300861 | Talabutab Norte National High School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2016-01-21 |  | 030314S00069 | 15CF0089 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | D.G. SARMENTA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300792 | Cabiao NHS | CABIAO | 4 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10997342.5917 |  |  | COMPLETED | 1 | 2016-02-24 |  | 030314S00059 | 15CF0114 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-09-28 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300794 | Calaba NHS | SAN ISIDRO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00067 | 15CF0066 | 2015-07-27 | 2015-07-28 | 2015-08-11
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306821 | Dr. Jose Lapuz Salonga HS (Former San Mariano NHS Annex) | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00066 | 15CF0067 | 2015-07-27 | 2015-07-28 | 2015-08-11
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 030314S00065 | 15CF0068 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 306816 | Jaen NHS (former Putlod-San Jose NHS-Annex) | JAEN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 306831 | Jaen NHS Annex-San Pablo | JAEN | 4 | 1 | 8 | 2sty8cl | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030314S00121 | 15CF0112 | 2015-08-18 | 2015-08-19 | 2015-09-01
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300836 | Lambakin National High School | JAEN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00064 | 15CF0070 | 2015-07-27 | 2015-07-28 | 2015-08-11
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300785 | Lino P. Bernardo NHS | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 030314S00063 | 15CF0071 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300817 | Magpapalayok NHS | SAN LEONARDO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00062 | 15CF0072 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | FRAMECON BUILDERS
NC 2014 | K10 (2014) | Region III | Nueva Ecija | 105683 | Malapit East ES | SAN ISIDRO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 030314S00015 | 14CF0027 | 2014-07-23 | 2014-07-24 | 2014-08-05 | 2014-08-13 | 2014-08-26 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300820 | Mallorca NHS | SAN LEONARDO | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10537131.51 |  |  | COMPLETED | 1 | 2016-02-24 |  | 030314S00048 | 15CF0111 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-09-28 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300821 | Mambangnan NHS | SAN LEONARDO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00060 | 15CF0073 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300832 | Penaranda National NHS | PEÑARANDA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00072 | 15CF0074 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300834 | Pulo NHS | SAN ISIDRO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00058 | 15CF0075 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300835 | Putlod-San Jose NHS | JAEN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00057 | 15CF0076 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | IJK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300840 | Rio-Chico National High School | GENERAL TINIO (PAPAYA) | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 030314S00056 | 15CF0077 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | LISA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300844 | San Anton NHS | SAN LEONARDO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00055 | 15CF0065 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | FRAMECON BUILDERS
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300846 | San Francisco NHS | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00054 | 15CF0078 | 2015-07-27 | 2015-07-28 | 2015-08-12
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300848 | San Mariano National High School | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 | 2016-02-09 |  | 030314S00053 | 15CF0079 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-08-26 | 2015-09-07 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300853 | STA. BARBARA NATIONAL HS | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00052 | 15CF0080 | 2015-07-27 | 2015-07-28 | 2015-08-12
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300856 | Sta. Rita NHS | CABIAO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00051 | 15CF0081 | 2015-07-27 | 2015-07-28 | 2015-08-12
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio NHS | SAN ISIDRO | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1 |  |  | 030314S00050 | 15CF0082 | 2015-07-27 | 2015-07-28 | 2015-08-12
NC 2014 | SHS (2014) | Region III | Nueva Ecija | 300854 | Zacarias C. Aquilizan HS (Sta. Barbara NHS Annex) | SAN ANTONIO | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 |  |  | 030314S00049 | 15CF0064 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-12-29
NC 2014 | K10 (2014) | Region III | Olongapo City | 107125 | Balic-Balic ES | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | REVERTED | 0 |  |  | 030614S00024
NC 2014 | K10 (2014) | Region III | Olongapo City | 107119 | Boton ES | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 030614S00028 | 15CM0021 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | AYSON P.D. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 107126 | Gordon Heights I ES | OLONGAPO CITY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 030614S00018 | 14CM0028 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-08-28 | 2014-09-10 | M.V.GUBALLA CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Olongapo City | 301053 | Gordon Heights NHS | OLONGAPO CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-05-25 |  | 030614S00033 | 15CM0068 | 2015-11-12 | 2015-11-12 | 2015-11-26 | 2015-12-08 | 2015-12-15 | REPOLMAN CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 107121 | Iram ES | OLONGAPO CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-14 | 2014-11-14 | 030614S00020 | 14CM0022 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-08-28 | 2014-09-14 | M.V.GUBALLA CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 500027 | James L. Gordon IS | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 030614S00029 | 15CM0020 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | AYSON P.D. CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Olongapo City | 301057 | New Cabalan NHS | OLONGAPO CITY | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2015-12-10 | 2015-12-10 | 030614S00039 | 15CM0014 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-06 | 2015-07-14 | CEDAR CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Olongapo City | 301058 | Regional Science High School | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-25 |  | 030614S00035 | 15CM0019 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-13 | AYSON P.D. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 500135 | Sergia Soriano Esteban IS II | OLONGAPO CITY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 030614S00021 | 14CM0024 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-08-28 | 2014-09-11 | REPOLMAN CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 500135 | Sergia Soriano Esteban IS of Kalaklan (Kalaklan ES) | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 030614S00030 | 15CM0022 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | AYSON P.D. CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Olongapo City | 301054 | Sta. Rita HS | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | REVERTED | 0 |  |  | 030614S00027
NC 2014 | SHS (2014) | Region III | Pampanga | 300875 | Balitucan National High School | MAGALANG | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-02-02 |  | 030414S00046 | 15CI0059 | 2015-06-23 | 2015-06-26 | 2015-07-07 | 2015-07-15 | 2015-07-31 | A.L. DARE CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Pampanga | 105979 | Basa Air Base CS | FLORIDABLANCA | 2 | 1 | 8 | 2sty8cl | 2014 K10 BATCH 4C | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030414S00062 | 15CH0067 | 2015-07-21 | 2015-07-09 | 2015-09-29 | 2015-10-15 | 2015-10-21 | A.L. DARE CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Pampanga | 300880 | Becuran NHS | SANTA RITA | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 030414S00051 | 15CH0122 | 2015-12-04 | 2015-12-22 | 2015-12-09
NC 2014 | SHS (2014) | Region III | Pampanga | 300882 | Betis NHS | GUAGUA | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22452343.62 |  |  | COMPLETED | 1 |  |  | 030414S00047 | 15CH0123 | 2015-12-04 | 2015-12-09 | 2015-12-22
NC 2014 | SHS (2014) | Region III | Pampanga | 300886 | Del Carmen NHS | LUBAO | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030414S00048 | 15CH0124 | 2015-12-04 | 2015-12-09 | 2015-12-22 |  | 2015-08-26
NC 2014 | K10 (2014) | Region III | Pampanga | 106289 | Diladila ES | SANTA RITA | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-09 | 2015-12-30 | 030414S00057 | 15CH0068 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-09-04 | OMICRON CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Pampanga | 300911 | Eastern Porac National High School | PORAC | 2 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 030414S00049 | 15CH0125 | 2015-12-04 | 2015-12-09 | 2015-12-22
NC 2014 | SHS (2014) | Region III | Pampanga | 300902 | Natividad NHS | GUAGUA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-12 |  | 030414S00050 | 15ch0066 | 2015-07-21 | 2015-07-09 | 2015-09-29 | 2015-10-19 | 2015-10-21 | ORANI BUILDERS & SUPPLY
NC 2014 | SHS (2014) | Region III | Pampanga | 300903 | Pulungmasle NHS (Natividad NHS - PulungMasle HS Annex) | GUAGUA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030414S00053 | 15CH0126 | 2015-12-04 | 2015-12-09 | 2015-12-22
NC 2014 | K10 (2014) | Region III | Pampanga | 306949 | San Jose Gumi IS | LUBAO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6619337.6381 |  |  | REVERTED | 0 |  |  | 030414S00024 | 15CH0070
NC 2014 | K10 (2014) | Region III | Pampanga | 306953 | San Roque Arbol High School | Apalit | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | REVERTED | 0 |  |  | 030414S00061
NC 2014 | K10 (2014) | Region III | Pampanga | 300884 | Camba NHS | ARAYAT | 3 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Pampanga | 306924 | Gerry Rodriguez HS | MEXICO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-28 |  | 030414S00054 | 15CG0126 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-25 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Pampanga | 300919 | San Isidro NHS (Sta. Ana) | Sta. Ana | 3 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 030414S00058 | 15CG0134 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | MARKNEST CONSTRUCTION AND TRADING (FORMERLY MARKNE
NC 2014 | SHS (2014) | Region III | Pampanga | 306901 | San Vicente Pilot School for Philippine Craftsmen | BACOLOR | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-24 |  | 030414S00041 | 15CG0183 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | FERDSTAR BUILDERS CONTRACTORS
NC 2014 | SHS (2014) | Region III | Pampanga | 306915 | Apalit HS | APALIT | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-05-07 |  | 030414S00037 | 15CG0199 | 2015-09-24 | 2015-09-25 | 2015-10-09 | 2015-10-26 | 2015-11-03 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 306934 | Emigdio Bondoc HS | SAN LUIS | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Pampanga | 306926 | Malauli High School | MASANTOL | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 030414S00036 | 15CG0150 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | PING-ANNs CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300899 | Mapaniqui NHS | CANDABA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 030414S00027 | 15CG0149 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | MARVERIC BUILDERS
NC 2014 | SHS (2014) | Region III | Pampanga | 300913 | Salapungan NHS | CANDABA | 4 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15397518.84 |  |  | COMPLETED | 1 | 2016-05-07 |  | 030414S00042 | 15CG0203 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-10-30 | 2015-11-03 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300918 | San Isidro NHS (San Luis) | SAN LUIS | 4 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11077342.5917 |  |  | COMPLETED | 1 | 2016-05-15 |  | 030414S00071 | 15CG0153 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300922 | San Juan-San Luis NHS | SAN LUIS | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-05-15 |  | 030414S00070 | 15CG0153 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Pampanga | 300923 | San Juan-San Luis NHS Annex (San Carlos) | SAN LUIS | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Pampanga | 306944 | San Luis NHS | SAN LUIS | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Pampanga | 306944 | San Luis NHS | SAN LUIS | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Pampanga | 306918 | San Simon High School | SAN SIMON | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-15 |  | 030414S00028 | 15CG0145 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | CHOLO CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300930 | San Vicente-San Francisco NHS | MACABEBE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 | 2016-04-15 |  | 030414S00029 | 15CG0152 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300935 | Sta. Maria NHS, Minalin | MINALIN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-14 |  | 030414S00030 | 15CG0146 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | CHOLO CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300936 | Sto. Rosario NHS | MINALIN | 4 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11197342.5917 |  |  | COMPLETED | 1 | 2016-04-14 |  | 030414S00031 | 15CG0151 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | CHOLO CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 306906 | Tarik Suliman High School | MASANTOL | 4 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 11377342.5917 |  |  | COMPLETED | 1 | 2016-04-15 |  | 030414S00032 | 15CG0152 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Pampanga | 300941 | Telacsan NHS | MACABEBE | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-04-15 |  | 030414S00039 | 15CG0152 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | San Fernando City | 307615 | Calulut Int. HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-09 |  | 030414S00033 | 15CG0169 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | NULAS BUILDERS
NC 2014 | K10 (2014) | Region III | San Fernando City | 307617 | Magliman Int. HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-31 | 2015-12-31 | 030414S00060 | 15CG0135 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | E.B. MATIAS CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | San Fernando City | 500145 | Maimpis Integrated High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-09 |  | 030414S00034 | 15CG0168 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | CHARIOTs CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | San Fernando City | 107192 | Malpitic ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 030414S00014 | 14CG0153 | 2014-11-18 | 2014-11-21 | 2014-12-05 | 2014-12-18 | 2014-12-23 | M.C.B. ZAMORA CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | San Fernando City | 307603 | Panipuan High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | San Fernando City | 301066 | Sindalan NHS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 12 | 3sty12cl | 2014 K10 BATCH 4C | 18222268.79 |  |  | COMPLETED | 1 | 2016-07-06 |  | 030414S00059 | 15CG0172 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | LUCKY STAR CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | San Fernando City | 307619 | Sta. Lucia Int. HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 | 2016-05-09 |  | 030414S00038 | 15CG0170 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | MARKNEST CONSTRUCTION AND TRADING (FORMERLY MARKNE
NC 2014 | K10 (2014) | Region III | San Jose City | 325802 | Tayabo High School - CPNHS Annex | San Jose City East | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-18 |  | 030414S00055 | 15CE0149 | 2015-08-04 | 2015-08-13 | 2015-08-25 | 2015-09-07 | 2015-09-16 | ADROIT CONSTRUCTION
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 107144 | Bagong Buhay E ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7707 |  |  | COMPLETED | 1 | 2015-06-19 | 2015-06-18 | 030214S00020 | 14CD0257 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 107159 | Benito Nieto ES (Muzon ES) | CITY OF SAN JOSE DEL MONTE | 0 |  |  | 4STY16CL | 2014 K10 BATCH 3 | 27389390.625 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 107154 | Francisco Homes ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4A | 8228453.2082 |  |  | COMPLETED | 1 | 2015-08-08 | 2015-08-07 | 030214S00021 | 14CD0260 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 162503 | Graceville ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7707 |  |  | COMPLETED | 1 | 2015-06-19 | 2015-06-18 | 030214S00019 | 14CD0258 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 307510 | Kaypian National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 18729509.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 162508 | Marangal Elementary School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 31900584.375 |  |  | COMPLETED | 1 | 2016-01-14 |  | 030214S00015 | 15CD0010 | 2015-02-12 | 2015-02-13 | 2015-04-21 | 2015-05-05 | 2015-05-15 | L.R. TIQUI BUILDERS, INC.
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 307511 | Marangal National High School | CITY OF SAN JOSE DEL MONTE | 0 |  |  | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 107162 | San Martin ES (BBC) | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4A | 8228453.2082 |  |  | COMPLETED | 1 | 2015-08-08 | 2015-08-07 | 030214S00023 | 14CD0259 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | K10 (2014) | Region III | San Jose del Monte City | 107151 | Sto. Cristo ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7707 |  |  | COMPLETED | 1 | 2015-06-19 | 2015-06-18 | 030214S00022 | 14CD0256 | 2014-12-04 | 2014-12-05 | 2014-12-17 | 2015-01-08 | 2015-01-19 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2014 | SHS (2014) | Region III | Tarlac | 300946 | Anao NHS | ANAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00046 | 15CJ0081 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Tarlac | 307004 | Balaoang HS Annex | PANIQUI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 955389.592 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 300948 | Balaoang NHS | PANIQUI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00047 | 15CJ0086 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 300950 | Bamban NHS | SAN CLEMENTE | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 030514S00048 | 15CJ0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300952 | Bilad HS | CAMILING | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-07 |  | 030514S00049 | 15CJ0097 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | ESER ENTERPRISES
NC 2014 | SHS (2014) | Region III | Tarlac | 300973 | Birbira High School | CAMILING | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00050 | 15CJ0082 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | NORTHERN BUILDERS
NC 2014 | SHS (2014) | Region III | Tarlac | 300953 | Buenavista High School | PURA | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 030514S00051 | 15CJ0096 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Tarlac | 300955 | Caanamongan High School | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 307010 | Calipayan NHS | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00052 | 15CJ0092 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region III | Tarlac | 106341 | Camiling East CES | CAMILING | 1 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-08 |  | 030514S00073 | 15CJ0101 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | SHS (2014) | Region III | Tarlac | 300958 | Camiling School of Home Industries | CAMILING | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00053 | 15CJ0083 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | NORTHERN BUILDERS
NC 2014 | K10 (2014) | Region III | Tarlac | 106549 | Capaoayan E/S | MONCADA | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1 | 2015-12-08 | 2015-12-08 | 030514S00015 | 15CJ0102 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | JAM-C BUILDERS
NC 2014 | SHS (2014) | Region III | Tarlac | 307008 | Carabaoan-Caocaoayan HS | MAYANTOC | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-02 |  | 030514S00054 | 15CJ0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300963 | Dueg High School | SAN CLEMENTE | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-02 |  | 030514S00068 | 15CJ0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | PANIQUI | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00056 | 15CJ0086 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Tarlac | 160014 | Enrado Bose Elementary School | SAN JOSE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-08 | 2015-11-08 | 030514S00014 | 15CJ0103 | 2015-07-15 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300964 | Estipona NHS | PURA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00044 | 15CJ0087 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-28 | NORTHERN BUILDERS
NC 2014 | K10 (2014) | Region III | Tarlac | 307003 | Estipona NHS - Annex | PURA | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 307003 | Estipona NHS - Annex | PURA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Tarlac | 307019 | Josephine M. Cojuangco NTVHS | MAYANTOC | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 13037519.5312 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region III | Tarlac | 307006 | Malacampa NHS | CAMILING | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00059 | 15CJ0083 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | NORTHERN BUILDERS
NC 2014 | SHS (2014) | Region III | Tarlac | 300972 | Marawi NHS | CAMILING | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-01 |  | 030514S00060 | 15CJ0082 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | NORTHERN BUILDERS
NC 2014 | SHS (2014) | Region III | Tarlac | 307011 | Moncada NHS | MONCADA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-03 |  | 030514S00061 | 15CJ0085 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP.
NC 2014 | SHS (2014) | Region III | Tarlac | 300975 | Nambalan NHS | SANTA IGNACIA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00038 | 15CJ0092 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00062 | 15CJ0091 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300980 | Pitombayog NHS | MAYANTOC | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-02 |  | 030514S00055 | 15CJ0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00063 | 15CJ0081 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 300983 | Sacata NHS | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00064 | 15CJ0091 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300984 | San Bartolome NHS | MAYANTOC | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-02 |  | 030514S00065 | 15CJ0084 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300985 | San Felipe NHS | SAN MANUEL | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-08 |  | 030514S00066 | 15CJ0098 | 2015-07-15 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP.
NC 2014 | K10 (2014) | Region III | Tarlac | 106678 | San Sotero ES | Sta. Ignacia | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2015-12-08 |  | 030514S00074 | 15CJ0101 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | SHS (2014) | Region III | Tarlac | 300991 | Sapang High School | MONCADA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00067 | 15CJ0085 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | ROYAL CROWN MONARCH CONSTRUCTION & SUPPLIES CORP.
NC 2014 | SHS (2014) | Region III | Tarlac | 300992 | Sta. Ines NHS | SANTA IGNACIA | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00057 | 15CJ0091 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300997 | Tarlac National HS - Annex | CITY OF TARLAC (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00036 | 15CJ0088 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-20 | 2015-08-28 | J.P. AQUINO CONSTRUCTION & ENTERPRISE (FORMERLY: J
NC 2014 | SHS (2014) | Region III | Tarlac | 300954 | Buenlag NHS | GERONA | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00029 | 15CJ0094 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300959 | Cardona NHS | GERONA | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00020 | 15CJ0094 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 307007 | Corazon C. Aquino HS | GERONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00026 | 15CJ0093 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | L.S.D. CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region III | Tarlac | 300965 | Gerona Western Public High School | GERONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00030 | 15CJ0094 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 301002 | Iba HS | SAN JOSE | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00025 | 15CJ0089 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300969 | Mababanaba NHS | SAN JOSE | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00024 | 15CJ0088 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-20 | 2015-08-28 | J.P. AQUINO CONSTRUCTION & ENTERPRISE (FORMERLY: J
NC 2014 | K10 (2014) | Region III | Tarlac | 106780 | Mangolago ES | VICTORIA | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-12-08 |  | 030514S00082 | 15CJ0100 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Tarlac | 106781 | Masalasa ES | VICTORIA | 2 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-12-08 |  | 030514S00077 | 15CJ0100 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 307001 | Moriones High School | SAN JOSE | 2 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00023 | 15CJ0089 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300986 | San Jose NHS | GERONA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-31 |  | 030514S00022 | 15CJ0088 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-08-20 | 2015-08-28 | J.P. AQUINO CONSTRUCTION & ENTERPRISE (FORMERLY: J
NC 2014 | K10 (2014) | Region III | Tarlac | 500125 | San Juan De Valdez IS | SAN JOSE | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4A | 955389.592 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 030514S00012 | 14CJ0076 | 2014-12-01 |  | 2014-12-15 | 2014-12-17 | 2014-12-19 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300995 | Tagumbao NHS | GERONA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00021 | 15CJ0093 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | L.S.D. CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region III | Tarlac | 106649 | Tangan-Tangan ES | San Jose | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Tarlac | 106649 | Tangan-Tangan ES | San Jose | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2014 K10 BATCH 4C | 2088606.04 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 301000 | Victoria NHS | VICTORIA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 301001 | Villa Aglipay NHS | SAN JOSE | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 030514S00031 | 15CJ0089 | 2015-07-02 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-29 | F.A. ASPRER CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300949 | Anastacio G. Yumul HS | CONCEPCION | 3 |  |  | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Tarlac | 500124 | Aranguren IS | CAPAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-10-15 | 030514S00002 | 14CK0051 | 2014-07-11 | 2014-07-11 | 2014-07-23 | 2014-08-06 | 2014-08-15 | BLACKRAM BUILDERS, INC.
NC 2014 | SHS (2014) | Region III | Tarlac | 300951 | Benigno S. ARuino NHS | CONCEPCION | 3 | 1 | 24 | 4STY24CL | 2014 SHS BATCH 1 | 35596257.14 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 300956 | Calangitan HS (Resettlement School) | CAPAS | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-08-29 | 2015-08-29 | 030514S00033 | 15CK0061 | 2015-05-23 | 2015-05-22 | 2015-06-04 | 2015-06-15 | 2015-06-24 | RJ NOVEDA BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region III | Tarlac | 300957 | Caluluan High School | CONCEPCION | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 030514S00045 | 15CK0068 | 2015-06-03 | 2015-06-02 | 2015-06-16 | 2015-06-24 | 2015-07-01 | R.G. DIAZ BUILDERS & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 307017 | Caluluan High School Annex | CONCEPCION | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-08-29 | 2015-08-29 | 030514S00034 | 15CK0063 | 2015-05-23 | 2015-05-22 | 2015-06-04 | 2015-06-15 | 2015-06-24 | B.G. GIRON CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region III | Tarlac | 300994 | Capas High School | CAPAS | 3 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-14 |  | 030514S00035 | 15CK0081 | 2015-07-11 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-12 | B.K. SY TU CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Tarlac | 300976 | Cristo Rey HS (ORES) | CAPAS | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 030514S00043 | 15CK0067 | 2015-06-03 | 2015-06-02 | 2015-06-16 | 2015-06-24 | 2015-07-01 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region III | Tarlac | 106391 | Cristo Rey West ES | CAPAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-11-19 | 030514S00006 | 14CK0052 | 2014-07-11 | 2014-07-11 | 2014-07-23 | 2014-08-06 | 2014-08-15 | J.P. AQUINO CONSTRUCTION & ENTERPRISE (FORMERLY: J
NC 2014 | SHS (2014) | Region III | Tarlac | 300962 | Dapdap HS | BAMBAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-11-04 | 2015-11-24 | 030514S00037 | 15CK0065 | 2015-06-03 | 2015-06-02 | 2015-06-16 | 2015-06-24 | 2015-07-01 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 300966 | Guevarra NHS | LA PAZ | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00028 | 15CK0077 | 2015-07-04 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-04 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 300967 | La Paz NHS | LA PAZ | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-11-04 | 2015-11-24 | 030514S00039 | 15CK0069 | 2015-06-03 | 2015-06-02 | 2015-06-16 | 2015-06-24 | 2015-07-01 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Tarlac | 106489 | La Purisima ES | LA PAZ | 3 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-15 |  | 030514S00079 | 15CK0080 | 2015-07-11 | 2015-07-10 | 2015-07-23 | 2015-07-31 | 2015-08-12 | ESER ENTERPRISES
NC 2014 | K10 (2014) | Region III | Tarlac | 106398 | Magao ES | CONCEPCION | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Tarlac | 106398 | Magao ES | CONCEPCION | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Tarlac | 300977 | O'Donnell HS | CAPAS | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-07 |  | 030514S00040 | 15CK0076 | 2015-07-04 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-08-04 | R.R. RICAFORT CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region III | Tarlac | 106407 | Pao Elementary School | CONCEPCION | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 030514S00005 | 14CK0043 | 2014-07-01 | 2014-06-30 | 2014-07-15 | 2014-07-30 | 2014-08-08 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region III | Tarlac | 106410 | San Agustin ES | CONCEPCION | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-11-30 | 030514S00004 | 14CK0054 | 2014-07-11 | 2014-07-11 | 2014-07-23 | 2014-08-06 | 2014-08-15 | A.C. SOLIVEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region III | Tarlac | 106438 | San Juan ES | CONCEPCION | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 030514S00003 | 14CK0042 | 2014-07-01 | 2014-06-30 | 2014-07-15 | 2014-07-30 | 2014-08-08 | STARDON CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region III | Tarlac | 106324 | San Pedro ES | BAMBAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-10-30 | 030514S00008 | 14CK0050 | 2014-07-11 | 2014-07-11 | 2014-07-23 | 2014-08-06 | 2014-08-15 | JAM-C BUILDERS
NC 2014 | SHS (2014) | Region III | Tarlac | 300990 | San Roque NHS | BAMBAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-11-24 | 2015-11-24 | 030514S00041 | 15CK0066 | 2015-06-03 | 2015-06-02 | 2015-06-16 | 2015-06-24 | 2015-07-01 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Tarlac | 307005 | Sta. Juliana HS (O'Donnell HS Annex) | CAPAS | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-19 |  | 030514S00042 | 15CK0074 | 2015-06-27 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-31 | J.P. AQUINO CONSTRUCTION & ENTERPRISE (FORMERLY: J
NC 2014 | K10 (2014) | Region III | Tarlac | 300993 | Sta. Lucia NHS | CAPAS | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-08-29 | 2015-08-29 | 030514S00016 | 14CK0081 | 2015-05-23 | 2015-05-22 | 2015-06-04 | 2015-06-15 | 2015-06-24 | B.G. GIRON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Tarlac | 106377 | Susuba ES | CAPAS | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-11-19 | 030514S00007 | 14CK0053 | 2014-07-11 | 2014-07-11 | 2014-07-23 | 2014-08-06 | 2014-08-15 | B.G. GIRON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Tarlac City | 106709 | Alvindia ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1 | 2015-06-22 | 2015-06-22 | 030514S00011 | 14CJ0108 | 2014-12-08 | 2014-12-09 | 2014-12-22 | 2015-03-16 | 2015-03-18 | F.A. ASPRER CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Tarlac City | 106751 | Apalang ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2sty4cl | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-22 |  | 030514S00080 | 15CJ0108 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | JAM-C BUILDERS
NC 2014 | K10 (2014) | Region III | Tarlac City | 106715 | Buhilit ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-08 | 2014-11-08 | 030514S00001 | 14CJ0017 | 2014-06-25 | 2014-06-26 | 2014-07-09 | 2014-08-22 | 2014-09-03 | F.A. ASPRER CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Tarlac City | 106759 | Pag-Asa ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-11-08 | 2015-11-08 | 030514S00019 | 15CJ0109 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | ARMD CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region III | Tarlac City | 106761 | Paradise ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | REVERTED | 0 |  |  | 030514S00081 | 15CJ0108 | 2015-07-07 | 2015-07-08 | 2015-07-21 |  |  | JAM-C BUILDERS
NC 2014 | K10 (2014) | Region III | Tarlac City | 106745 | San Francisco ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-11-08 | 2015-11-08 | 030514S00018 | 15CJ0109 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | ARMD CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region III | Zambales | 301013 | Agusuhin HS | SUBIC | 1 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 030614S00051 | 15CM0033 | 2015-07-22 | 2015-07-24 | 2015-08-07 | 2015-08-12 | 2015-08-18 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 106854 | Balaybay ES | CASTILLEJOS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 030614S00022 | 14CM0023 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-09-02 | 2014-09-11 | REPOLMAN CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Zambales | 107006 | Calapacuan ES | SUBIC | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-02-08 |  | 030614S00036 | 15CM0013 | 2015-06-17 | 2015-06-18 | 2015-06-30 | 2015-07-06 | 2015-07-14 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 307119 | Cawag Resettlement Annex III - Kinabuksan HS | SUBIC | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Zambales | 107009 | Cawag Resettlement ES | SUBIC | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Zambales | 307127 | Naugsol Integrated School | SUBIC | 1 | 1 | 4 | 1sty4cl (Toilet Attached) | 2014 K10 BATCH 4C | 3817968.78 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region III | Zambales | 107016 | Naugsol IS | SUBIC | 1 | 1 | 10 | 2sty10cl | 2014 K10 BATCH 4C | 12771310.093 |  |  | REVERTED | 0
NC 2014 | SHS (2014) | Region III | Zambales | 307124 | Subic NHS Annex IV - San Isidro HS | SUBIC | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 030614S00037 | 15CM0026 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 307126 | Subic NHS Annex VI-Aningway-Sacatihan HS | SUBIC | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 030614S00019 | 14CM0026 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-08-28 | 2014-09-11 | REPOLMAN CONSTRUCTION
NC 2014 | K10 (2014) | Region III | Zambales | 106991 | Bolitoc ES - Annex | SANTA CRUZ | 2 | 1 | 6 | 2sty6cl | 2014 K10 BATCH 4C | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-15 |  | 030614S00048 | 15CL0034 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Zambales | 160523 | Burgos ES | BOTOLAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 3240828.124 |  |  | COMPLETED | 1 | 2015-12-03 |  | 030614S00026 | 15CL0030 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | RBDIWA BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region III | Zambales | 301010 | Cabangan National High School | CABANGAN | 2 | 1 | 10 | 2STY10CL | 2014 SHS BATCH 1 | 12771310.093 |  |  | COMPLETED | 1 | 2016-01-03 |  | 030614S00045 | 15cl0021 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 106889 | Collat ES | MASINLOC | 2 | 1 | 12 | 3sty12cl | 2014 K10 BATCH 4C | 18222268.79 |  |  | COMPLETED | 1 | 2016-02-15 |  | 030614S00049 | 15CL0033 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Zambales | 307121 | Don Getulio F. Arendaeng HS | SAN FELIPE | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-30 | 2014-09-30 | 030614S00015 | 0306-S-13-00117 | 2014-06-01 | 2014-06-13 | 2014-06-16 | 2014-06-24 | 2014-07-11 | JECK CONSTRUCTION
NC 2014 | SHS (2014) | Region III | Zambales | 301021 | Gov Manuel Barretto National High School | SAN FELIPE | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00038 | 15cl0022 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Zambales | 301017 | La Paz NHS | SAN NARCISO | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00031 | 15CL0023 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 160510 | Nacolcol ES | BOTOLAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2014 K10 BATCH 4C | 2952592.44 |  |  | COMPLETED | 1 | 2016-01-15 |  | 030614S00046 | 15CL0035 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | H.E.M. CONSTRUCTION AND HARDWARE
NC 2014 | SHS (2014) | Region III | Zambales | 301026 | New Taugtog National High School | BOTOLAN | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00040 | 15CL0024 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 106967 | Paite-Balincaguing ES | SAN FELIPE | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 030614S00005 | 0306-14-S-00005 | 2014-06-01 | 2014-06-13 | 2014-06-16 | 2014-06-24 | 2014-07-11 | RBDIWA BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region III | Zambales | 500127 | Pamibian IS | CANDELARIA | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region III | Zambales | 500127 | Pamibian IS | CANDELARIA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region III | Zambales | 106832 | Reserva ES | CABANGAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 030614S00004 | 14CL0015 | 2014-08-04 | 2014-08-05 | 2014-08-15 | 2014-08-22 | 2014-08-26 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region III | Zambales | 307133 | San Agustin IS | Iba | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2014 K10 BATCH 4C | 4673636.82 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00047 | 15CL0036 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | MJBZ BUILDERS AND TRADING
NC 2014 | SHS (2014) | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00053 | 15CL0026 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Zambales | 307102 | Sta. Cruz NHS - Jesus F. Magsaysay HS Annex | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00043 | 15CL0027 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | STO. CRISTO CONSTRUCTION & TRADING
NC 2014 | SHS (2014) | Region III | Zambales | 301034 | Sta. Cruz NHS - Lipay HS | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 |  | 030614S00044 | 15CL0028 | 2015-07-02 | 2015-07-06 | 2015-07-13 | 2015-07-17 | 2015-07-23 | E.M.L. CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region III | Zambales | 307114 | Sta. Cruz South HS | SANTA CRUZ | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-24 | 030614S00009 | 0306-14-S-00009 | 2014-06-01 | 2014-06-13 | 2014-06-16 | 2014-06-24 | 2014-07-11 | RBDIWA BUILDERS AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region III | Zambales | 307116 | Sta. Cruz South HS | SANTA CRUZ | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Angeles City | 301038 | Angeles City Nat'l. Trade School | ANGELES CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Angeles City | 301038 | Angeles City Nat'l. Trade School | ANGELES CITY | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00054 | 15CI0083 | 2015-07-27 | 2015-07-31 | 2015-08-18 | 2015-09-22 | 2015-10-06 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Angeles City | 307202 | Angeles City Science HS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Angeles City | 301042 | Bonifacio V. Romero HS | ANGELES CITY | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00058 | 15CI0082 | 2015-07-27 | 2015-07-31 | 2015-08-18 | 2015-09-22 | 2015-10-06 | LUCKY STAR CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) | 0 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 030715S00008 | 15CN0093 | 2015-08-09 | 2015-08-12 | 2015-08-24 | 2015-09-09 | 2015-09-28 | VANMARVIL CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Aurora | 300673 | Aurora NHS | BALER (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030715S00020 | 15CN0106 | 2015-10-11 | 2015-10-15 | 2015-10-26 | 2015-11-10 | 2015-11-23 | R.N.G.M. CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Aurora | 300679 | Canili Area NHS | MARIA AURORA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300679 | Canili Area NHS | MARIA AURORA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 030715S00033 | 15CN0108 | 2015-10-11 | 2015-10-15 | 2015-10-26 | 2015-11-10 | 2015-11-23 | R.N.G.M. CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Aurora | 306504 | Diagyan High School | DILASAG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 306504 | Diagyan High School | DILASAG | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300681 | Dikapinisan NHS | SAN LUIS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300681 | Dikapinisan NHS | SAN LUIS | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 030715S00028 | 15CN0113 | 2015-11-03 | 2015-11-06 | 2015-11-18 | 2015-12-08 | 2015-12-17
NC 2015 | SHS (2015) | Region III | Aurora | 300684 | Dinadiawan NHS | DIPACULAO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030715S00029 | 15CN0107 | 2015-10-11 | 2015-10-15 | 2015-10-26 | 2015-11-10 | 2015-11-23 | R.N.G.M. CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030715S00030 | 15CN0125 | 2015-11-24 | 2015-11-26 | 2015-12-08 | 2015-12-17 | 2015-12-22
NC 2015 | SHS (2015) | Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1 |  |  | 030715S00031 | 15CN0112 | 2015-11-03 | 2015-11-06 | 2015-11-18 | 2015-12-08 | 2015-12-17
NC 2015 | SHS (2015) | Region III | Aurora | 300686 | Ditumabo NHS | SAN LUIS | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030715S00032 | 15CN0117 | 2015-11-19 | 2015-11-20 | 2015-12-03 | 2015-12-10 | 2015-12-21
NC 2015 | SHS (2015) | Region III | Aurora | 300687 | Eliceo C. Ronquillo Memorial NHS | MARIA AURORA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300687 | Eliceo C. Ronquillo Memorial NHS | MARIA AURORA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300688 | Ibona NHS | DINGALAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300688 | Ibona NHS | DINGALAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region III | Aurora | 104503 | Leon Diaz Sr. ES | MARIA AURORA | 0 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 030715S00034 |  | 2015-12-08 | 2015-12-10 | 2015-12-22
NC 2015 | SHS (2015) | Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 300691 | Maria Aurora NHS | MARIA AURORA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8394965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Aurora | 300691 | Maria Aurora NHS | MARIA AURORA | 0 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 030715S00009 | 15CN0114 | 2015-11-03 | 2015-11-06 | 2015-11-18 | 2015-12-08 | 2015-12-17
NC 2015 | SHS (2015) | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11177342.5917 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Balanga City | 322901 | City of Balanga High School | CITY OF BALANGA (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8464965.051 |  |  | COMPLETED | 1 |  |  | 030115S00010 | 15CB0037 | 2015-07-16 | 2015-07-24 | 2015-07-31 | 2015-08-10 | 2015-08-17 | DE JESUS CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region III | Bataan | 300705 | Hermosa NHS | HERMOSA | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Bataan | 300707 | Limay NHS | LIMAY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bataan | 300711 | Mariveles NHS,Poblacion | MARIVELES | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bataan | 300711 | Mariveles NHS,Poblacion | MARIVELES | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 306713 | Bajet-Castillo HS | PULILAN | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030215S00098 | [7 empty] | No Remarks
NC 2015 | SHS (2015) | Region III | Bulacan | 300735 | Dampol 2nd NHS | PULILAN | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | COMPLETED | 1 |  |  | 030215S00073
NC 2015 | SHS (2015) | Region III | Bulacan | 300738 | DoÑa Candeleria. Meneses Duque HS | BULACAN | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | COMPLETED | 1 |  |  | 030215S00094
NC 2015 | SHS (2015) | Region III | Bulacan | 300770 | Frances High School | CALUMPIT | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | COMPLETED | 1 |  |  | 030215S00068
NC 2015 | SHS (2015) | Region III | Bulacan | 300743 | Iba National High School | HAGONOY | 1 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 5 | 12771310 |  |  | COMPLETED | 1 |  |  | 030215S00069
NC 2015 | SHS (2015) | Region III | Bulacan | 300744 | Kapitangan National High School | PAOMBONG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00095
NC 2015 | SHS (2015) | Region III | Bulacan | 361078 | Proposed Stand Alone SHS 3 (Calumpit CES) | Calumpit | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region III | Bulacan | 361078 | Proposed Stand Alone SHS 3 (Calumpit CES) | Calumpit | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region III | Bulacan | 300754 | Ramona S. Trillana HS (Mayor Ramon Trillana Mem. HS (Iba NHS)) | HAGONOY | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 8 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030215S00097
NC 2015 | SHS (2015) | Region III | Bulacan | 306711 | San Francisco Xavier HS | BULACAN | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 030215S00067
NC 2015 | SHS (2015) | Region III | Bulacan | 306723 | San Miguel-Meysulao High School | CALUMPIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 030215S00086 | 15CC0261 | 2015-11-13 | 2015-11-13 | 2015-11-24 | 2015-12-09 | 2015-12-23 | ESN CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Bulacan | 300755 | San Pedro High School | HAGONOY | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15541327.92 |  |  | COMPLETED | 1 |  |  | 030215S00028
NC 2015 | SHS (2015) | Region III | Bulacan | 300745 | San Roque National HS | PAOMBONG | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15451327.92 |  |  | COMPLETED | 1 |  |  | 030215S00029 | 15CC0183 | 2015-07-22 | 2015-07-24 | 2015-08-06
NC 2015 | SHS (2015) | Region III | Bulacan | 300776 | Sta. Cruz NHS | PAOMBONG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00083
NC 2015 | SHS (2015) | Region III | Bulacan | 300736 | Sta. Lucia High School | CALUMPIT | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26952469.42 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | SHS (2015) | Region III | Bulacan | 300736 | Sta. Lucia High School | CALUMPIT | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15147518.84 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | SHS (2015) | Region III | Bulacan | 300756 | Sta. Monica National High School | HAGONOY | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10747131.51 |  |  | COMPLETED | 1 |  |  | 030215S00032 | 15CC0187 | 2015-07-22 | 2015-07-24 | 2015-08-06
NC 2015 | SHS (2015) | Region III | Bulacan | 300737 | Sta. Peregrina HS | PULILAN | 1 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 5 | 18222269 |  |  | COMPLETED | 1 |  |  | 030215S00074
NC 2015 | SHS (2015) | Region III | Bulacan | 300779 | Taliptip NHS | BULACAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8454965.051 |  |  | COMPLETED | 1 |  |  | 030215S00033 | 15CC0174 | 2015-07-20 | 2015-07-22 | 2015-08-03 | 2015-08-21
NC 2015 | SHS (2015) | Region III | Bulacan | 300720 | Alexis G. Santos National High School | BUSTOS | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00034 | 15CC0191 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-09-28 | 2015-10-12 | FRAMECON BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 300721 | Balagtas National Agricultural HS | BALAGTAS (BIGAA) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00035 | 15CC0192 | 2015-07-22 | 2015-07-24 | 2015-08-06
NC 2015 | SHS (2015) | Region III | Bulacan | 306730 | Banga HS | PLARIDEL | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030215S00036 | 15CC0185 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-10-16 | 2015-11-06 | L.R. TIQUI BUILDERS, INC.
NC 2015 | SHS (2015) | Region III | Bulacan | 300726 | Bintog HS (Jose J. Mariano MHS) | PLARIDEL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00037 | 15CC0194 | 2015-07-22 | 2015-07-24 | 2015-08-06
NC 2015 | SHS (2015) | Region III | Bulacan | 300728 | Bunsuran NHS | PANDI | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030215S00051 | 15CC0186 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-09-28 | 2015-10-12 | PRECIOUS CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Bulacan | 300733 | Cambaog NHS | BUSTOS | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 030215S00085
NC 2015 | SHS (2015) | Region III | Bulacan | 300734 | Dampol 1st NHS | PLARIDEL | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 030215S00064
NC 2015 | SHS (2015) | Region III | Bulacan | 300741 | Felizardo C. Lipana MHS (Sta. Rita HS) | GUIGUINTO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00103
NC 2015 | SHS (2015) | Region III | Bulacan | 300742 | Guiguinto Nat'l Voc'l. High School | GUIGUINTO | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | TECHVOC (2015) | Region III | Bulacan | 300742 | Guiguinto Nat'l Voc'l. High School | GUIGUINTO | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 306715 | Iluminada Mendoza-Roxas Memorial High School (Bambang NHS) | BOCAUE | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 030215S00096
NC 2015 | SHS (2015) | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300729 | Masagana HS | PANDI | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 030215S00101
NC 2015 | SHS (2015) | Region III | Bulacan | 345213 | Proposed Stand Alone SHS 1 (Birhen delos Flores ES) | Baliuag | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1 | [10 empty] | No Remarks
NC 2015 | SHS (2015) | Region III | Bulacan | 345213 | Proposed Stand Alone SHS 1 (Birhen delos Flores ES) | Baliuag | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 306712 | Sto. Nino HS | BALIUAG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8294965 |  |  | COMPLETED | 1 |  |  | 030215S00065 | 15CC0282 | 2015-12-09 | 2015-12-10 | 2015-12-22
NC 2015 | SHS (2015) | Region III | Bulacan | 300778 | Sulivan HS | BALIUAG | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00041 | 15CC0190 | 2015-07-22 | 2015-07-24 | 2015-08-06
NC 2015 | SHS (2015) | Region III | Bulacan | 300747 | Taal High School | BOCAUE | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 030215S00106
NC 2015 | SHS (2015) | Region III | Bulacan | 300780 | Tiaong NHS | GUIGUINTO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 030215S00077 | 15CC0283 | 2015-12-09 | 2015-12-10 | 2015-12-22
NC 2015 | SHS (2015) | Region III | Bulacan | 300781 | Tibagan National High School | BUSTOS | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00052 | 15CC0189 | 2015-07-22 | 2015-07-24 | 2015-08-06 | 2015-10-02 | 2015-10-29 | ADIMRE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Bulacan | 300731 | Akle HS | SAN ILDEFONSO | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 030215S00093 | 15CD0176 b | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Bulacan | 306702 | Angat HS (Binagbag NHS - Taboc NHS) | ANGAT | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00090 | 15CD0172 b | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | LE REVE BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 306707 | Binagbag HS - Angel M. del Rosario HS | ANGAT | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00089 | 15CD0172 a | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | LE REVE BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 300722 | Binagbag NHS | ANGAT | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00042 | 15CD0160 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | LE REVE BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030215S00099
NC 2015 | SHS (2015) | Region III | Bulacan | 300723 | Doña Remedios Trinidad High School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00043 | 15CD0161 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | C & F CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region III | Bulacan | 300774 | John J. Russel MHS (Sibul NHS) | SAN MIGUEL | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300774 | John J. Russel MHS (Sibul NHS) | SAN MIGUEL | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 306718 | Lydia D. Villangca Trade School | SAN RAFAEL | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 030215S00087 | 15CD0174 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | EIRISH BUILDERS & SUPPLY INC.
NC 2015 | SHS (2015) | Region III | Bulacan | 306708 | Maronquillo National High School | SAN RAFAEL | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00088 | 15CD0173 a | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | LE REVE BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 300758 | MINUYAN NATIONAL HIGH SCHOOL | NORZAGARAY | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030215S00044 | 15CD0162 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | ADIMRE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Bulacan | 300760 | Norzagaray National High School | NORZAGARAY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 030215S00112 | 15CD0192 | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-27 | 2015-12-08 | PERSAN CONSTRUCTION, INC. (FORMERLY: PERSAN CONST.
NC 2015 | SHS (2015) | Region III | Bulacan | 300772 | Partida HS (San Miguel NHS - Partida HS) | SAN MIGUEL | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1 |  |  | 030215S00081 | 15CD0178 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | EIRISH BUILDERS & SUPPLY INC.
NC 2015 | SHS (2015) | Region III | Bulacan | 306706 | Pres. Diosdado Macapagal MHS | ANGAT | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 030215S00078 | 15CD0171 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2015 | SHS (2015) | Region III | Bulacan | 300749 | Salapungan HS | SAN RAFAEL | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00091 | 15CD0173 b | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | LE REVE BUILDERS
NC 2015 | SHS (2015) | Region III | Bulacan | 300732 | San Ildefonso National High School | SAN ILDEFONSO | 3 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 5 | 12638675 |  |  | COMPLETED | 1 |  |  | 030215S00092 | 15CD0176 a | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Bulacan | 300771 | San Miguel NHS | SAN MIGUEL | 3 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 8 | 53404938.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Bulacan | 300771 | San Miguel NHS | SAN MIGUEL | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 030215S00082 | 15CD0175 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | ADIMRE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030215S00107
NC 2015 | SHS (2015) | Region III | Bulacan | 300740 | ASSEMBLYWOMAN FELICITA G. BERNARDINO MEMORIAL TRADE SCHOOL | MARILAO | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300740 | ASSEMBLYWOMAN FELICITA G. BERNARDINO MEMORIAL TRADE SCHOOL | MARILAO | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Bulacan | 300740 | ASSEMBLYWOMAN FELICITA G. BERNARDINO MEMORIAL TRADE SCHOOL | MARILAO | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 306714 | Catmon HS | SANTA MARIA | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15121328 |  |  | COMPLETED | 1 |  |  | 030215S00075 | 15CD0182 | 2015-12-03 | 2015-12-04 | 2015-12-17 | 2015-12-23 |  | C & F CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Bulacan | 300765 | Parada NHS | SANTA MARIA | 4 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 8 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 030215S00102 | 15CD0183 | 2015-10-07 | 2015-10-08 | 2015-10-20 | 2015-10-29 | 2015-11-06 | E.A. SANCHO CONST. INC. (FORM. E.A. SANCHO CONST.)
NC 2015 | SHS (2015) | Region III | Bulacan | 306726 | Sta. Cruz HS | SANTA MARIA | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030215S00066 | 15CD0167 a | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2015 | SHS (2015) | Region III | Bulacan | 300777 | Sta. Maria National. High School | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00105 | 15CD0167 b | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2015 | K10 (2015) | Region III | Cabanatuan City | 107062 | ACA ES | CABANATUAN CITY | 3 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 6 | 10727342.5917 |  |  | REVERTED | 0 |  |  | 030315S00037
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 301045 | Camp Tinio National High School | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8734965.051 |  |  | COMPLETED | 1 |  |  | 030315S00011 | 15CF0117 | 2015-08-18 | 2015-08-19 | 2015-09-01 | 2015-09-16 | 2015-09-28 | XP BUILDERS
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 307301 | Cesar E. Vergara MHS | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 030315S00012 | 15CF0101 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-10-08 | 2015-10-22 | XP BUILDERS
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 301049 | Eastern Cabu NHS | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 030315S00013 | 15CF0102 | 2015-07-27 | 2015-07-28 | 2015-08-13 | 2015-09-09 | 2015-09-21 | D.G. SARMENTA CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 301044 | Honorato C. Perez, Sr. Mem. Sci. HS | CABANATUAN CITY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10737131.51 |  |  | COMPLETED | 1 |  |  | 030315S00014 | 15CF0134 | 2015-10-12 | 2015-10-13 | 2015-10-27 | 2015-11-24
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 301047 | Marciano del Rosario NHS | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8734965.051 |  |  | COMPLETED | 1 |  |  | 030315S00016 | 15CF0116 | 2015-08-18 | 2015-08-19 | 2015-09-01
NC 2015 | SHS (2015) | Region III | Cabanatuan City | 301046 | Mayapyap NHS | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8534965.051 |  |  | COMPLETED | 1 |  |  | 030315S00026 | 15CF0103 | 2015-07-27 | 2015-07-28 | 2015-08-13
NC 2015 | SHS (2015) | Region III | Gapan City | 321301 | Herminio G. Nicolas High School | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00031 | 15CF0061 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | IJK CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 12 | 2STY12CL | 2015 SHS BATCH 2 | 14579217.1798 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 030415S00060 | 15CI0084 | 2015-07-27 | 2015-07-31 | 2015-08-11 | 2015-09-22 | 2015-10-06 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Mabalacat City | 345342 | Proposed Stand Alone SHS-1 (Sapang Biabas ES) | MABALACAT | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 030415S00083 | 15CI0095 | 2015-09-29 | 2015-10-02 | 2015-10-14 | 2015-10-22 | 2015-11-05 | R.D. SADSAD CONSTRUCTION & TRADING
NC 2015 | TECHVOC (2015) | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Malolos City | 300751 | MHPNHS | City of Malolos | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 030215S00084
NC 2015 | SHS (2015) | Region III | Malolos City | 300750 | MMFSL | City of Malolos | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8244965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Meycauayan City | 300757 | Meycauayan NHS | CITY OF MEYCAUAYAN | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Meycauayan City | 300757 | Meycauayan NHS | CITY OF MEYCAUAYAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 030315S00019 | 15CE0148 | 2015-08-04 | 2015-08-13 | 2015-08-25 | 2015-09-07 | 2015-09-16 | F.C. MARTINEZ CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Munoz Science City | 300824 | Munoz National HS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030315S00020 | 15CE0127 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-17 | 2015-08-19 | IJK CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Munoz Science City | 500398 | Palusapis IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8264965 |  |  | COMPLETED | 1 |  |  | 030315S00036 | 15ce0160 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-11-11 | F.C. MARTINEZ CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Munoz Science City | 322802 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Munoz Science City | 322802 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. HS | QUEZON | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2549549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00022 | 15CE0133 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-17 | 2015-08-19 | ADROIT CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Nueva Ecija | 300864 | TALAVERA NATIONAL HIGH SCHOOL | TALAVERA | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 306804 | BURGOS NATIONAL HIGH SCHOOL | CARRANGLAN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10767132 |  |  | COMPLETED | 1 |  |  | 030315S00034 | 15ce0161 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-11-11 | F.C. MARTINEZ CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 300790 | Bongabon NHS | BONGABON | 3 | 1 | 20 | ADDITONAL 4STY20CL | 2015 ADDITIONAL FUND BATCH 9 | 30952890.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Nueva Ecija | 300790 | Bongabon NHS | BONGABON | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5019098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 306813 | Bongabon NHS Annex (Vega HS) | BONGABON | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00023 | 15CF0085 | 2015-07-27 | 2015-07-28 | 2015-08-12
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 306803 | Buklod-Palad NHS (former Maligaya NHS Annex - Doña Josefa) | PALAYAN CITY (Capital) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00024 | 15CF0084 | 2015-07-27 | 2015-07-28 | 2015-08-12 | 2015-09-09 | 2015-09-21 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 300863 | Eduardo L. Joson Memorial HS | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 030315S00035 | 15CF0135 | 2015-10-12 | 2015-10-13 | 2015-10-27 | 2015-11-12 | 2015-11-23 | FRAMECON BUILDERS
NC 2015 | TECHVOC (2015) | Region III | Nueva Ecija | 300828 | Palayan City National High School | PALAYAN CITY (Capital) | 3 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 5019098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 306816 | Jaen NHS (former Putlod-San Jose NHS-Annex) | JAEN | 4 | 1 | 4 | ADDITONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Nueva Ecija | 306809 | LEONOR M. BAUTISTA HS (Pias Campus Annex) | GENERAL TINIO (PAPAYA) | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00025 | 15CF0063 | 2015-07-27 | 2015-07-28 | 2015-08-11 | 2015-08-26 | 2015-09-07 | LISA CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Olongapo City | 107132 | Baretto I ES | OLONGAPO CITY | 1 | 1 | 6 | 3STY6CL | 2015 ADDITIONAL FUND BATCH 9 | 2052166.459 |  |  | REVERTED | 0 |  |  | 030615S00049
NC 2015 | SHS (2015) | Region III | Olongapo City | 301056 | Kalalake NHS | OLONGAPO CITY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22332343.62 |  |  | COMPLETED | 1 |  |  | 030615S00044 | 15CM0034 | 2015-07-22 | 2015-07-24 | 2015-08-07 | 2015-09-25 | 2015-12-11 | REPOLMAN CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Olongapo City | 107128 | Mabayuan ES | OLONGAPO CITY | 1 | 1 | 6 | 2STY6CL and additional 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00050 | 15CM0067 | 2015-11-12 | 2015-11-12 | 2015-11-26 | 2015-12-08 | 2015-12-15 | M.V.GUBALLA CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region III | Pampanga | 306938 | AYALA | MAGALANG | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 306938 | AYALA NHS | MAGALANG | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 345531 | Proposed Stand Alone SHS 2 | Magalang | 1 | 1 | 24 | 2STY8CL | 2015 SHS BATCH 5 | 32782028 |  |  | COMPLETED | 1 |  |  | 030415S00078 | 15CI0091 | 2015-08-20 | 2015-08-21 | 2015-09-03 | 2015-10-29 | 2015-11-12 | LUCKY STAR CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300943 | Tinajero NHS - Sta. Lucia HS Annex | MAGALANG | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030415S00057 | 15CI0076 | 2015-07-16 | 2015-07-17 | 2015-07-30 | 2015-09-22 | 2015-10-06 | NORTHERN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 306911 | AMBROCIO S.SIMPAO EDUCATIONAL AND TRADET CENTER OF LEARNING | SANTA RITA | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3867968.78 |  |  | COMPLETED | 1 |  |  | 030415S00072 | 15CH0047 | 2015-07-21 | 2015-07-09 | 2015-07-21 | 2015-08-12 | 2015-08-26 | DAUNGAN CONSTRUCTION DEVT. & GEN. SUPPLIES INC.
NC 2015 | SHS (2015) | Region III | Pampanga | 300879 | Basa Air Base High School | FLORIDABLANCA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00059 | 15CH0057 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-09-04 | ORANI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region III | Pampanga | 300884 | Camba HS | Arayat | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 306913 | Camias HS | PORAC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 030415S00051 | 15CH0048 | 2015-07-21 | 2015-07-09 | 2015-07-21 | 2015-08-12 | 2015-08-26 | MDAN CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300890 | Floridablanca Nat'l. Agr'l. School | FLORIDABLANCA | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00061 | 15CH0113 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 300891 | Guillermo D. Mendoza NHS | GUAGUA | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18522268.79 |  |  | COMPLETED | 1 |  |  | 030415S00062
NC 2015 | SHS (2015) | Region III | Pampanga | 300892 | Gutad NHS | FLORIDABLANCA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00063 | 15CH0058 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-09-04 | A.L. DARE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 300893 | Gutad NHS - Floridablanca Integrated School | FLORIDABLANCA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | REVERTED | 0 |  |  | 030415S00065 |  | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24
NC 2015 | SHS (2015) | Region III | Pampanga | 300897 | Malusac NHS | SASMUAN (SEXMOAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 030415S00066 | 15CH0049 | 2015-07-21 | 2015-07-09 | 2015-07-21 | 2015-08-12 | 2015-08-26 | VERET CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 300904 | Pagyuruan NHS | FLORIDABLANCA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030415S00067 | 15CH0118 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 306933 | Planas High School | PORAC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00068 | 15CH0060 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-09-04 | PRIME PAVE CONSTRUCTION AND ASPHALT CORPORATION
NC 2015 | SHS (2015) | Region III | Pampanga | 300907 | Porac Model Comm. HS (Resettlement School) | PORAC | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00074 | 15CH0114 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 300910 | Pulung Santol High School-Annex | PORAC | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00085
NC 2015 | SHS (2015) | Region III | Pampanga | 300909 | Pulung Santol National High School | PORAC | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 030415S00073 | 15CH0115 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 300912 | Remedios NHS | LUBAO | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18422268.79 |  |  | COMPLETED | 1 |  |  | 030415S00071
NC 2015 | SHS (2015) | Region III | Pampanga | 300881 | San Basilio HS (Becuran NHS Annex) | SANTA RITA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00069 | 15CH0061 | 2015-07-15 | 2015-07-17 | 2015-11-20 | 2015-12-11
NC 2015 | SHS (2015) | Region III | Pampanga | 300920 | San Jose NHS | FLORIDABLANCA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00070 | 15CH0062 | 2015-07-30 | 2015-07-17 | 2015-07-30 | 2015-08-24 | 2015-09-04 | MIGGS CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region III | Pampanga | 300925 | San Pablo 2nd NHS | LUBAO | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00048 | 15CH0116 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 300928 | San Roque Dau NHS | LUBAO | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030415S00032 | 15CH0063 | 2015-09-29 | 2015-09-17 | 2015-09-29 | 2015-10-15 | 2015-10-21 | OMICRON CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 300929 | San Vicente NHS, Lubao | LUBAO | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 030415S00031 | 15CH0117 | 2015-11-26 | 2015-12-03 | 2015-12-16
NC 2015 | SHS (2015) | Region III | Pampanga | 306948 | Sebitanan NHS | SASMUAN (SEXMOAN) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 030415S00030 | 15CH0050 | 2015-07-21 | 2015-07-09 | 2015-07-21 | 2015-08-12 | 2015-08-26 | VERET CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 306912 | Sta. Cruz IS | LUBAO | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1 |  |  | 030415S00029
NC 2015 | SHS (2015) | Region III | Pampanga | 300937 | Sto. Tomas NHS, Sasmuan | SASMUAN (SEXMOAN) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6619337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00028 | 15CH0064 | 2015-07-30 | 2015-07-17 | 2015-12-09
NC 2015 | SHS (2015) | Region III | Pampanga | 300908 | Villa Maria Integrated School | PORAC | 2 | 1 | 2 | 2STY2CL | 2015 SHS BATCH 5 | 4772048 |  |  | COMPLETED | 1 |  |  | 030415S00075 | 15CH0098 | 2015-10-29 | 2015-10-30 | 2015-11-13
NC 2015 | K10 (2015) | Region III | Pampanga | 105898 | Arayat CS | ARAYAT | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030415S00080 | 15CG0187 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | N-22 CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 306935 | Bacolor HS | BACOLOR | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030415S00017 | 15CG0129 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | E.B. MATIAS CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 306908 | Diosdado Macapagal HS | MEXICO | 3 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21583013.45 |  |  | COMPLETED | 1 |  |  | 030415S00026 | 15CG0181 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | NULAS BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 306925 | Don Antonio Lee Chi Uan IS | BACOLOR | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00033 | 15CG0133 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | A.L. DARE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 300898 | Justino Sevilla High School | ARAYAT | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030415S00047 | 15CG0138 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300901 | Mexico NHS | MEXICO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 030415S00024 | 15CG0136 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | EL KAPITAN CONSTRUCTION SERVICES
NC 2015 | SHS (2015) | Region III | Pampanga | 300872 | Nicanor David Vergara HS (Anao NHS) | MEXICO | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 11027342.5917 |  |  | COMPLETED | 1 |  |  | 030415S00064 | 15CG0128 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-25 | CHARIOTs CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300905 | Pandacaque NHS (Resettlement School) DJ Gonzales | MEXICO | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Pampanga | 300905 | Pandacaque NHS (Resettlement School) DJ Gonzales | MEXICO | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 301065 | Potrero NHS | BACOLOR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00022 | 15CG0124 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-25 | E.B. MATIAS CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300917 | San Isidro NHS (Bacolor) | BACOLOR | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00021 | 15CG0125 | 2015-07-26 | 2015-07-30 | 2015-08-11 | 2015-08-20 | 2015-08-25 | MARKNEST CONSTRUCTION AND TRADING (FORMERLY MARKNE
NC 2015 | SHS (2015) | Region III | Pampanga | 300921 | San Juan NHS, Mexico | MEXICO | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030415S00020 | 15CG0127 | 2015-07-26 | 2015-07-31 | 2015-08-11 | 2015-08-20 | 2015-08-25 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300932 | Sta. Ana NHS | SANTA ANA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 030415S00019 | 15CG0137 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-24 | 2015-08-27 | E.B. MATIAS CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 306945 | Telesforo Natividad NHS | SANTA ANA | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 030415S00018 | 15CG0182 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | FERDSTAR BUILDERS CONTRACTORS
NC 2015 | SHS (2015) | Region III | Pampanga | 300874 | Bahay Pare NHS | CANDABA | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 030415S00025 | 15CG0204 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-10-30 | 2015-11-03 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300877 | Balucuc NHS | APALIT | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3767968.78 |  |  | COMPLETED | 1 |  |  | 030415S00043 | 15CG0175 | 2015-09-08 | 2015-09-10 | 2015-09-23 | 2015-10-02 | 2015-10-08 | N-22 CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300883 | Caduang Tete NHS | MACABEBE | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030415S00042 | 15CG0147 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | CHOLO CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300885 | Cansinala NHS | APALIT | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00041 | 15CG0143 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | MARVERIC BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300927 | CONCEPCION HS | SAN SIMON | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030415S00076 | 15CG0195 | 2015-09-24 | 2015-09-25 | 2015-10-09 | 2015-10-26 | 2015-11-03 | E.B. MATIAS CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 306937 | Dalayap HS | MACABEBE | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 030415S00036 | 15CG0164 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300887 | DELA PAZ LIBUTAD HS | SAN SIMON | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030415S00086 | 15CG0201 | 2015-09-24 | 2015-09-25 | 2015-10-20 | 2015-10-30 | 2015-11-03 | NULAS BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 306934 | Emigdio Bondoc HS | SAN LUIS | 4 | 1 | 4 | ADDITONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8348298.381 |  |  | COMPLETED | 1 |  |  | 030415S00049 | 15CG0148 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300906 | Pasig NHS | CANDABA | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1 |  |  | 030415S00027 | 15CG0205 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-10-30 | 2015-11-03 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 345530 | Proposed Stand Alone SHS 1 | APALIT | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22452344 |  |  | COMPLETED | 1 |  |  | 030415S00077 |  | 2015-11-30 | 2015-12-16 | 2015-12-16 | 2015-12-28 | 2015-12-29
NC 2015 | SHS (2015) | Region III | Pampanga | 300914 | Salapungan NHS - Annex Mandili | CANDABA | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6519337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00046 | 15CG0144 | 2015-08-09 | 2015-08-13 | 2015-08-25 | 2015-09-03 | 2015-09-11 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | K10 (2015) | Region III | Pampanga | 105961 | San Agustin ES | CANDABA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6669337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00079 | 15CG0196 | 2015-09-24 | 2015-09-25 | 2015-10-20 | 2015-10-30 | 2015-11-03 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300915 | San Esteban NHS | MACABEBE | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 4067968.78 |  |  | COMPLETED | 1 |  |  | 030415S00045 | 15CG0166 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | EL KAPITAN CONSTRUCTION SERVICES
NC 2015 | SHS (2015) | Region III | Pampanga | 300916 | San Esteban NHS - Consuelo | MACABEBE | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 030415S00044 | 15CG0166 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | EL KAPITAN CONSTRUCTION SERVICES
NC 2015 | SHS (2015) | Region III | Pampanga | 300923 | San Juan-San Luis NHS Annex (San Carlos) | SAN LUIS | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Pampanga | 300924 | San Matias NHS | SANTO TOMAS | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26802469.42 |  |  | COMPLETED | 1 |  |  | 030415S00034 | 15CG0219 | 2015-11-02 | 2015-11-05 | 2015-11-17 | 2015-11-27 | 2015-12-02 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300926 | San Pedro NHS | SAN SIMON | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030415S00050 | 15CG0197 | 2015-09-24 | 2015-09-25 | 2015-10-09 | 2015-10-26 | 2015-11-03 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 306923 | Sapang Kawayan HS | MASANTOL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 030415S00040 | 15CG0165 | 2015-09-02 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-06 | CHOLO CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300934 | Sta. Maria NHS, Macabebe | MACABEBE | 4 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18522268.79 |  |  | COMPLETED | 1 |  |  | 030415S00039 | 15CG0206 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-10-30 | 2015-11-03 | NES-SAN BUILDERS
NC 2015 | SHS (2015) | Region III | Pampanga | 300938 | Sto. Tomas NHS, Sto. Tomas | SANTO TOMAS | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030415S00038 | 15CG0207 | 2015-10-06 | 2015-10-08 | 2015-10-20 | 2015-10-30 | 2015-11-03 | A.L. DARE CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Pampanga | 306936 | Sucad HS | APALIT | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00037 | 15CG0177 | 2015-09-08 | 2015-09-10 | 2015-09-23 | 2015-10-02 | 2015-10-08 | N-22 CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Pampanga | 300939 | Tagulod NHS | CANDABA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2138606.04 |  |  | COMPLETED | 1 |  |  | 030415S00035 | 15CG0173 | 2015-09-08 | 2015-09-10 | 2015-09-23 | 2015-10-02 | 2015-10-08 | EDDMARI CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | San Fernando City | 301064 | Pampanga NHS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15721328 |  |  | COMPLETED | 1 |  |  | 030415S00094 | 15CG0171 | 2015-09-02 | 2015-09-15 | 2015-09-17 | 2015-11-13 | 2015-11-19 | TURQUOISE CONSTRUCTION & TRADING (FORMERLY: TURQUO
NC 2015 | TECHVOC (2015) | Region III | San Fernando City | 307603 | Panipuan High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Fernando City | 345268 | Proposed Stand Alone SHS 1 (Dolores ES) | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030415S00084 |  | 2015-11-30 | 2015-12-03 | 2015-12-16 | 2015-12-28 | 2015-12-29
NC 2015 | K10 (2015) | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00082 | 15CG0186 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | CHARIOTs CONSTRUCTION & TRADING
NC 2015 | K10 (2015) | Region III | San Fernando City | 107172 | St. Vincent of Quebiawan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 030415S00081 | 15CG0185 | 2015-09-13 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2015-10-21 | TONKA CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose City | 306817 | Caanawan High School | SAN JOSE CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030315S00030 | 15CE0125 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-05 | 2015-08-19 | ADROIT CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose City | 300800 | Constancio Padilla National High School | SAN JOSE CITY | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030315S00029 | 15CE0124 | 2015-07-06 | 2015-07-15 | 2015-07-28 | 2015-08-17 | 2015-08-19 | F.C. MARTINEZ CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose City | 300833 | Porais NHS | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030315S00028 | 15CE0128 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-17 | 2015-08-19 | IJK CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose City | 306805 | Sto. Nino 3rd National High School | SAN JOSE CITY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030315S00027 | 15ce0159 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-28 | 2015-11-11 | WIZARD TRADING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose City | 300868 | Tondod NHS | SAN JOSE CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030315S00032 | 15CE0130 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-17 | 2015-08-19 | WIZARD TRADING AND CONSTRUCTION
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307508 | Citrus National HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00056 | 15CD0157 a | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307506 | City of San Jose del Monte National Science High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00055 | 15CD0157 b | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307504 | Graceville NHS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030215S00100 | 15CD0168 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | TURQUOISE CONSTRUCTION & TRADING (FORMERLY: TURQUO
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307502 | Kakawate National HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00054 | 15CD0158 a | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | ORANI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307510 | Kaypian National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307511 | Marangal National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 24 | 4STY24CL | 2015 ADDITIONAL FUND BATCH 9 | 24168272.76 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307511 | Marangal National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307505 | Minuyan NHS (Golden Ville HS) | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00057 | 15CD0158 b | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | ORANI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307512 | Muzon Harmony Hills High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | REVERTED | 0 |  |  | 030215S00070 | 15CD0169 | 2015-09-24 | 2015-09-28 | 2015-10-13 |  |  | R.D. TALENS CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 301059 | Paradise Farms NHS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00058 | 15CD0159 a | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | JEMN BUILDERS
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307513 | San Jose del Monte Heights High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 24 | 4STY24CL | 2015 ADDITIONAL FUND BATCH 9 | 8056866.51 |  |  | COMPLETED | 1 |  |  | 030214S00008 | 15CD0191 b | 2015-11-05 | 2015-11-06 | 2015-11-19 | 2015-11-27 | 2015-12-08 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 301060 | San Jose del Monte HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030215S00060 | 15CD0156 | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 301061 | San Jose del Monte Nat'l. Trade School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 301061 | San Jose del Monte Nat'l. Trade School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307507 | San Martin National HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 030215S00038 | 15CD0159 b | 2015-09-10 | 2015-09-11 | 2015-09-24 | 2015-10-07 | 2015-10-15 | JEMN BUILDERS
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 301062 | Sapang Palay National NHS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12771310.093 |  |  | COMPLETED | 1 |  |  | 030215S00027 | 15CD0108 | 2015-07-01 | 2015-07-02 | 2015-07-14 | 2015-07-23 | 2015-07-31 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307509 | Sto. Cristo National HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | REVERTED | 0 |  |  | 030215S00071
NC 2015 | SHS (2015) | Region III | San Jose del Monte City | 307503 | Towerville HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 030215S00072 | 15CD0170 | 2015-09-24 | 2015-09-28 | 2015-10-13 | 2015-10-23 | 2015-10-30 | TRIPLE 8 CONSTRUCTION & SUPPLY, INC. (FORMERLY TRIPLE 8 CONST. & SUPPLY)
NC 2015 | SHS (2015) | Region III | Tarlac | 300947 | Aringin NHS | MONCADA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030515S00010 | 15CJ0106 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Tarlac | 307004 | Balaoang HS Annex | PANIQUI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Tarlac | 300955 | Caanamongan High School | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Tarlac | 300999 | Vargas High School | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030515S00013 | 15CJ0107 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | F.A. ASPRER CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 030515S00015 | 15CJ0114 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | ESER ENTERPRISES
NC 2015 | SHS (2015) | Region III | Tarlac | 300996 | Tarlac National HS | CITY OF TARLAC (Capital) | 2 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 2 | 35596257.14 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Tarlac | 300996 | Tarlac National HS | CITY OF TARLAC (Capital) | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Tarlac | 301000 | Victoria NHS | VICTORIA | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Tarlac | 300949 | Anastacio G. Yumul HS | CONCEPCION | 3 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2512377.5407 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Tarlac | 300951 | Benigno S. Aquino NHS | CONCEPCION | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Tarlac | 300961 | Comillas High School | LA PAZ | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 030515S00004 | 15CK0075 | 2015-06-27 | 2015-06-26 | 2015-07-09 | 2015-07-21 | 2015-07-31 | THREE KCS BUILDERS AND SUPPLY
NC 2015 | SHS (2015) | Region III | Tarlac City | 300944 | Alvindia-Aguso High School Main | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 030515S00005 | 15CJ0110 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | JAM-C BUILDERS
NC 2015 | SHS (2015) | Region III | Tarlac City | 321402 | Amucao HS (Annex) | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 030515S00016 | 15CJ0129 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-10-28 | 2015-10-30 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Tarlac City | 300945 | Amucao NHS | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 030515S00006 | 15CJ0111 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO
NC 2015 | SHS (2015) | Region III | Tarlac City | 500390 | Armenia IS | CITY OF TARLAC (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030515S00009 | 15CJ0110 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | JAM-C BUILDERS
NC 2015 | SHS (2015) | Region III | Tarlac City | 500389 | Balibago Primero IS | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 030515S00007 | 15CJ0112 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | L.S.D. CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region III | Tarlac City | 300960 | Central Azucarera de Tarlac NHS Main | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030515S00018 | 15CJ0131 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-10-28 | 2015-10-30 | JAM-C BUILDERS
NC 2015 | SHS (2015) | Region III | Tarlac City | 300971 | Maliwalo NHS (Annex) | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030515S00003 | 15CJ0112 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-07-30 | 2015-08-04 | L.S.D. CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region III | Tarlac City | 300970 | Maliwalo NHS (Main) | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 030515S00017 | 15CJ0166 | 2015-12-10 | 2015-12-11 | 2015-12-23 | 2015-12-28 |  | B.G. GIRON CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Tarlac City | 321401 | San Manuel HS (Annex) | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 SHS BATCH 2 | 5322651.88 |  |  | COMPLETED | 1 |  |  | 030515S00008 | 15CJ0111 | 2015-07-07 | 2015-07-08 | 2015-07-21 | 2015-08-26 | 2015-09-04 | FLORDES CONSTRUCTION & TRADING CORP. (FORMERLY FLO
NC 2015 | SHS (2015) | Region III | Tarlac City | 300988 | San Manuel HS (Main) | CITY OF TARLAC (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030515S00019 | 15CJ0130 | 2015-10-06 | 2015-10-07 | 2015-10-20 | 2015-10-28 | 2015-10-30 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 500126 | Batiawan-I Integrated School | SUBIC | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030615S00023 | 15CM0030 | 2015-07-22 | 2015-07-24 | 2015-08-07 | 2015-08-12 | 2015-08-18 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 301031 | Buhawen National High School | SAN MARCELINO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00021 | 15CM0023 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | REPOLMAN CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 301012 | Cawag HS (Resettlement School) | SUBIC | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030614S00016 | 14CM0025 | 2014-08-07 | 2014-08-08 | 2014-08-22 | 2014-08-28 | 2014-09-11 | REPOLMAN CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 307119 | Cawag Resettlement Annex III - Kinabuksan HS | SUBIC | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Zambales | 307106 | JESUS F. MAGSAYSAY TECHNICAL-VOCATIONAL HIGH SCHOOL | CASTILLEJOS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00041 | 15CM0027 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | M.V.GUBALLA CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 307112 | Nagyantok HS | SUBIC | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030615S00047 | 15CM0040 | 2015-08-19 | 2015-08-20 | 2015-09-03 | 2015-10-15 | 2015-10-23 | JOE ANAS BUILDERS
NC 2015 | SHS (2015) | Region III | Zambales | 301029 | San Guillermo NHS | SAN MARCELINO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00040 | 15CM0028 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 301030 | San Marcelino National HS | SAN MARCELINO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00039 | 15CM0024 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | AYSON P.D. CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 301035 | Sta. Fe NHS | SAN MARCELINO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00038 | 15CM0025 | 2015-07-09 | 2015-07-10 | 2015-07-22 | 2015-07-27 | 2015-08-03 | M.V.GUBALLA CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 030615S00046 | 15CM0039 | 2015-08-19 | 2015-08-20 | 2015-09-03 | 2015-10-15 | 2015-10-23 | JOE ANAS BUILDERS
NC 2015 | SHS (2015) | Region III | Zambales | 301037 | Zambales NHS | IBA (Capital) | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 8 | 35596257.14 |  |  | COMPLETED | 1 |  |  | 030615S00048
NC 2015 | SHS (2015) | Region III | Zambales | 301003 | Acoje NHS | SANTA CRUZ | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030615S00037 | 15CL0037 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | H.E.M. CONSTRUCTION AND HARDWARE
NC 2015 | SHS (2015) | Region III | Zambales | 301004 | Amungan NHS | IBA (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00036 | 15CL0046 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | KATHA BUILDERS
NC 2015 | SHS (2015) | Region III | Zambales | 301005 | Bani NHS | MASINLOC | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00032 | 15CL0050 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Zambales | 301006 | Bani NHS - Annex | MASINLOC | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00035 | 15CL0047 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Zambales | 301007 | BANI NHS - COTO ANNEX | MASINLOC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030615S00022 | 15CL0038 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Zambales | 301008 | Baquilan Resettlement High School | BOTOLAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region III | Zambales | 301008 | Baquilan Resettlement High School | BOTOLAN | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | 10 | 2STY10CL | 2015 SHS BATCH 2 | 12771310.093 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region III | Zambales | 301011 | Candelaria School of Fisheries | CANDELARIA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00024 | 15CL0048 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 301014 | Guisguis NHS | SANTA CRUZ | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030615S00031 | 15CL0043 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 SHS BATCH 2 | 4523636.82 |  |  | COMPLETED | 1 |  |  | 030615S00045 | 15CL0040 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | MDAN CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region III | Zambales | 301022 | Mena Mem. NHS (Bolitoc NHS) | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00030 | 15CL0051 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | JECK CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030615S00029 | 15CL0045 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | JECK CONSTRUCTION
NC 2015 | SHS (2015) | Region III | Zambales | 301032 | San Miguel NHS | SAN ANTONIO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 030615S00028 | 15CL0049 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | KATHA BUILDERS
NC 2015 | SHS (2015) | Region III | Zambales | 307104 | San Rafael Technical Vocational High School | SAN FELIPE | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 030615S00027 | 15CL0044 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Zambales | 307103 | San Salvador HS | MASINLOC | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 030615S00026 | 15CL0041 | 2015-07-24 | 2015-07-27 | 2015-08-03 | 2015-08-06 | 2015-08-19 | NEW MASINLOC HENRYs CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region III | Zambales | 301033 | Sta. Cruz NHS | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 030615S00025 | 15CL0052 | 2015-08-07 | 2015-07-10 | 2015-08-19 | 2015-08-24 | 2015-09-01 | JECK CONSTRUCTION
NC 2016 | K10 | Region III | Angeles City | 500131 | Amsic Is | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | J.S. LIM CONST. AND TRADING/511 BUILDERS (JV)
NC 2016 | K10 | Region III | Angeles City | 301038 | Angeles City Nat'L. Trade School | Angeles City | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | AL-B DEVELOPMENT CORPORATION
NC 2016 | K10 | Region III | Angeles City | 301038 | Angeles City Nat'L. Trade School | Angeles City | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | B-12 CONSTRUCTION AND TRADING CORP.
NC 2016 | SHS | Region III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 8 | 4STY8CL | BATCH 1 CL | 15634894.782 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | J.S. LIM CONST. AND TRADING/511 BUILDERS (JV)
NC 2016 | SHS | Region III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 23252460.801 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | A.D. GONZALES JR. CONST. AND TRADING CO. INC
NC 2016 | SHS | Region III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 23252460.801 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | MRRM TRADING AND CONST.
NC 2016 | SHS | Region III | Angeles City | 301039 | Angeles City Nhs | Angeles City | 1 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | MARKNEST CONST AND CONSTRUCTION
NC 2016 | SHS | Region III | Angeles City | 301042 | Bonifacio V. Romero Hs | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | BP CRUZ BUILDERS AND TRADING
NC 2016 | K10 | Region III | Angeles City | 107041 | Gueco Balibago Es | Angeles City | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | MCB ZAMORA CONSTRUCTION AND SUPPLY
NC 2016 | K10 | Region III | Angeles City | 107032 | Pineda-Gutierrez Es | Angeles City | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | RG DIAZ BUILDERS AND TRADING
NC 2016 | SHS | Region III | Angeles City |  | Shs In Brgy. Pandan, Angeles City | Angeles City | 1 | 1 | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | R.M. VITUG CONST.
NC 2016 | SHS | Region III | Angeles City |  | Shs In Brgy. Pandan, Angeles City | Angeles City | 1 |  | 12 | 4STY12CL | BATCH 1 CL | 22152343.62 |  |  | Completed | 1 | [8 empty] | 2016-06-02 | R.D. SADSAD CONST. & TRADING
NC 2016 | K10 | Region III | Angeles City | 107048 | Sta. Teresita Elementary School | Angeles City | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104452 | Abungan Es To Cabog Es | Dingalan | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1085000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300672 | Aurora National Science Hs | Baler (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8550000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300673 | Aurora Nhs | Baler (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11150000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 300677 | Baler Nhs | Baler (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8650000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 300674 | Bayanihan Nhs | Maria Aurora | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1895000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104452 | Cabog Is | Dingalan | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300679 | Canili Area Nhs | Maria Aurora | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3500000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300680 | Casiguran Nhs | Casiguran | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13256310.093 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300680 | Casiguran Nhs | Casiguran | 0 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5392400 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 306504 | Diagyan High School | Dilasag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2560000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 306504 | Diagyan High School | Dilasag | 0 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8709965.051 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 306507 | Diarabasin Nhs | Dipaculao | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2790000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104433 | Dicabasan Es | Dilasag | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300681 | Dikapinisan Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2540000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300682 | Dilasag Nhs | Dilasag | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13171310.093 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104469 | Dinadiawan Es | Dipaculao | 0 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104469 | Dinadiawan Es | Dipaculao | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 13063810.093 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300685 | Dingalan Nhs | Dingalan | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11177342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300685 | Dingalan Nhs | Dingalan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 306509 | Diniog Nhs | Dilasag | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2000000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300686 | Ditumabo Nhs | San Luis | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12771310.093 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300686 | Ditumabo Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 300687 | Eliseo C. Ronquillo Sr. Memorial Nhs | Maria Aurora | 0 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 157510 | Florida Es | Maria Aurora | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1895000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300688 | Ibona Nhs | Dingalan | 0 | 1 | 10 | 2STY10CL | BATCH 9 CL | 13191310.093 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300688 | Ibona Nhs | Dingalan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300689 | Juan C. Angara Memorial Nhs | Dinalungan | 0 | 1 | 16 | 2STY8CL | BATCH 7 CL | 23198734.83 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300689 | Juan C. Angara Memorial Nhs | Dinalungan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2540000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104515 | Kamalatan Es To Dibut Es | San Luis | 0 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4071272.138 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104475 | Lipit Es | Dipaculao | 0 | 1 | 1 | 1STY1CL | BATCH 13 CL | 1098449.69 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300690 | Lual Nhs | Casiguran | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2540000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300690 | Lual Nhs | Casiguran | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11382342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 300692 | Manggitahan Nhs | Dilasag | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 300691 | Maria Aurora Nhs | Maria Aurora | 0 | 1 | 12 | 2STY6CL | BATCH 9 CL | 16429930.102 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 306501 | Mariano D. Marquez High School | Dinalungan | 0 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10877342.59 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 306501 | Mariano D. Marquez Memorial National High School | Dinalungan | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2540000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 300694 | Mayor Cesario A. Pimentel Nhs | San Luis | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2700000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 157501 | Paraiso Es | Casiguran | 0 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2000000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. Nhs | San Luis | 0 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10917342.5917 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. Nhs | San Luis | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104527 | San Isidro Es | San Luis | 0 | 1 | 5 | 1STY5CL | BATCH 5 CL | 4300000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 306514 | Tinib-Calangcuasan Is | Casiguran | 0 | 1 | 4 | 1STY4CL | BATCH 13 CL | 3667968.78 |  |  | Completed | 1
NC 2016 | K10 | Region III | Aurora | 104442 | Ura Es | Dilasag | 0 | 1 | 3 | 1STY3CL | BATCH 13 CL | 3000000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Balanga City | 300702 | Bataan National High School | City Of Balanga (Capital) | 2 | 1 | 40 | 2STY10CL | BATCH 1 CL | 52685890.16 |  |  | Completed | 1 |  |  |  | 42536 | 2016-06-29 | 2016-07-12 | 2016-07-20 | 2016-07-26 |  | 42482
NC 2016 | K10 | Region III | Balanga City | 322901 | City Of Balanga National High School | City Of Balanga (Capital) | 2 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16279930.102 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 |  | 42701
NC 2016 | K10 | Region III | Balanga City | 322901 | City Of Balanga National High School | City Of Balanga (Capital) | 2 |  | 8 | 2STY8CL | BATCH 1 CL | 11327342.59 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 |  | 42669
NC 2016 | K10 | Region III | Bataan | 104658 | Alikabok Es | Orani | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072131LZ | 16CA0034 |  | 2016-02-24 | 2016-06-14 |  | 2016-07-12 | Pascal Construction
NC 2016 | K10 | Region III | Bataan | 300701 | Balsik Nhs | Hermosa | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6500000 |  |  | Completed | 1 |  |  | P00072128LZ | 16CA0031 |  | 2016-02-24 | 2016-06-14 |  | 2016-07-04 | Sto. Cristo Construction & Trading
NC 2016 | K10 | Region III | Bataan | 104607 | Bamban Es | Hermosa | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 2000000 |  |  | Completed | 1 |  |  | P00072129LZ | 16CA0019 |  | 2016-02-24 | 2016-03-23 |  | 2016-05-27 | Builders Exponent Enterprise
NC 2016 | SHS | Region III | Bataan | 300705 | Hermosa Nhs | Hermosa | 1 | 1 | 24 | 4STY12CL | BATCH 1 CL | 44154687.24 |  |  | Completed | 1 |  |  | P00070070LZ | 16CA0032 |  | 2016-06-19 | 2016-06-20 |  | 2016-08-05
NC 2016 | K10 | Region III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | Dinalupihan | 1 | 1 | 20 | 4STY20CL | BATCH 1 CL | 32602890.27 |  |  | Completed | 1 |  |  | P00070069LZ | 16CA0030 |  | 2016-02-24 | 2016-03-23 |  | 2016-05-27 | Orani Builders Supply
NC 2016 | TECHVOC | Region III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | Dinalupihan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2600000 |  |  | Completed | 1 |  |  | P00070198L2 | 16CA0044 |  | 2016-05-30 | 2016-06-27 |  | 2016-07-11 | De Jesus Construction
NC 2016 | K10 | Region III | Bataan | 104661 | Kaparangan Es | Orani | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8350000 |  |  | Completed | 1 |  |  | P00072132LZ | 16CA0035 |  | 2016-02-24 | 2016-08-02 |  | 2016-08-12 | LTM Construction
NC 2016 | K10 | Region III | Bataan | 300708 | Luakan Nhs | Dinalupihan | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14947518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bataan | 300709 | Mabatang Nhs | Abucay | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | P00072123LZ | 16CA0021 |  | 2016-02-24 | 2016-03-23 |  | 2016-05-27 | Builders Exponent Enterprise
NC 2016 | K10 | Region III | Bataan | 104652 | Mabayo Es | Morong | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072130LZ | 16CA0036 |  | 2016-02-24 | 2016-06-14 |  | 2016-07-04 | Pascal Construction
NC 2016 | SHS | Region III | Bataan | 300713 | Morong Nhs | Morong | 1 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27202469.42 |  |  | Completed | 1 |  |  | P00070071LZ | 16CA0037 |  | 2016-02-24 | 2016-06-14 |  | 2016-07-04 | DM House Const. Inc.
NC 2016 | SHS | Region III | Bataan | 300713 | Morong Nhs | Morong | 1 |  | 4 | 2STY4CL | BATCH 1 CL | 6169337.64 |  |  | Completed | 1 |  |  | P00070072LZ | 16CA0038 |  | 2016-02-24 | 2016-03-23 |  | 2016-05-27 | Pascal Construction
NC 2016 | TECHVOC | Region III | Bataan | 300713 | Morong Nhs | Morong | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 5100000 |  |  | Completed | 1 |  |  | P00070199L2 | 16CA0043 |  | 2016-05-30 | 2016-06-27 |  | 2016-07-11 | Builders Exponent Enterprise
NC 2016 | K10 | Region III | Bataan | 158001 | Naparing Es | Dinalupihan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | P00072124LZ | 16CA0023 |  | 2016-02-24 | 2016-05-23 |  | 2016-05-27 | Builders Exponent Enterprise
NC 2016 | SHS | Region III | Bataan | 300715 | Orani Nhs | Orani | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bataan | 104664 | Orani South Es | Orani | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | P00072133LZ | 16CA0033 |  | 2016-02-24 | 2016-05-14 |  | 2016-07-04 | Pascal Construction
NC 2016 | K10 | Region III | Bataan | 104585 | Pagalanggang Es | Dinalupihan | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6400000 |  |  | Completed | 1 |  |  | 16CA0029 | March 4-11, 2016 | 2016-02-24 | 2016-05-14 |  | 2016-07-04 |  | 42696
NC 2016 | K10 | Region III | Bataan | 104668 | Paraiso Es | Orani | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1900000 |  |  | Completed | 1 |  |  | 16CA0022 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 |  | 42626
NC 2016 | K10 | Region III | Bataan | 104589 | Pinulot Es | Dinalupihan | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 2000000 |  |  | Completed | 1 |  |  | 16CA0020 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 |  | 42626
NC 2016 | K10 | Region III | Bataan | 104589 | Pinulot Es | Dinalupihan | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1100000 |  |  | Completed | 1 |  |  | 16CA0024 | March 4-11, 2016 | 2016-02-24 | 2016-05-23 |  | 2016-05-27 |  | 42596
NC 2016 | SHS | Region III | Bataan | 300719 | Samal Nhs | Samal | 1 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bataan | 300719 | Samal Nhs | Samal | 1 |  | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bataan | 300719 | Samal Nhs | Samal | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5000000 |  |  | Completed | 1 |  |  | P00070764L2 | 16CA0025 |  | 2016-04-19 | 2016-05-17 |  | 2016-05-27 | Orani Builders & Supply
NC 2016 | SHS | Region III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18972268.79 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 |  | 42701
NC 2016 | SHS | Region III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 |  | 9 | 3STY9CL | BATCH 1 CL | 15471327.92 |  |  | Completed | 1 |  |  |  | 42419 | 2016-03-04 | 2016-03-16 | 2016-03-23 | 2016-05-26 |  | 42669
NC 2016 | TECHVOC | Region III | Bataan | 300703 | Bataan School Of Fisheries | Orion | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2750000 |  |  | Completed | 1 |  |  | P00070201L2 | 16CB0017 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 2016-05-31 | N. V. Balbuena Construction
NC 2016 | SHS | Region III | Bataan | 300699 | E. C. Bernabe Nhs | Bagac | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bataan | 306601 | Justice Emilio Angeles Gancayco Memorial High School | Orion | 2 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070078L2
NC 2016 | TECHVOC | Region III | Bataan | 306601 | Justice Emilio Angeles Gancayco Memorial High School | Orion | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2500000 |  |  | Completed | 1 |  |  | P00070202L2 | 16CB0018 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 2016-06-21 | Victoria Builders & Trading
NC 2016 | SHS | Region III | Bataan | 300706 | Lamao Nhs | Limay | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30242655.84 |  |  | Completed | 1 |  |  | P00070944L2
NC 2016 | TECHVOC | Region III | Bataan | 300706 | Lamao Nhs | Limay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2500000 |  |  | Completed | 1 |  |  | P00071563L2 | 16CB0021 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-17 | 2016-05-26 | N. V. Balbuena Construction
NC 2016 | SHS | Region III | Bataan | 300707 | Limay Nhs | Limay | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 | [10 empty] | With approved additional funds; reported completed based on DPWH Letter dated Oct 14, 2022 Subject: Joint Special Task Force
NC 2016 | TECHVOC | Region III | Bataan | 300707 | Limay Nhs | Limay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075067L2 | 16CB0057 | 2016-08-01 | 2016-08-09 | 2016-08-16 | 2016-08-24 | 2016-08-31 | De Jesus Construction
NC 2016 | SHS | Region III | Bataan | 300710 | Mariveles Nhs, Cabcaben | Mariveles | 2 | 1 | 16 | 2STY4CL | BATCH 1 CL | 26677350.56 |  |  | Completed | 1 |  |  | P00070073L2 | 16B0030 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-03-17 | 2016-03-26 | Orani Builders & Supply
NC 2016 | SHS | Region III | Bataan | 300710 | Mariveles Nhs, Cabcaben | Mariveles | 2 |  | 9 | 3STY9CL | BATCH 1 CL | 15721327.92 |  |  | Completed | 1 |  |  | P00070074L2 | 16B0060 | 2016-08-08 | 2016-08-16 | 2016-08-23 | 2016-09-06 | 2016-09-14
NC 2016 | SHS | Region III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2 | 1 | 40 | 4STY20CL | BATCH 1 CL | 64255780.54 |  |  | Completed | 1 |  |  | P00070075L2 | 16B0058 | 2016-08-01 | 2016-08-09 | 2016-08-16 | 2016-08-24 | 2016-08-31 | Orani Builders & Supply
NC 2016 | TECHVOC | Region III | Bataan | 300711 | Mariveles Nhs,Poblacion | Mariveles | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2550000 |  |  | Completed | 1 |  |  | P00070200L2 | 16CB0019 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-17 | 2016-05-26 | Poly-mervic Construction
NC 2016 | SHS | Region III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 | 1 | 30 | 2STY10CL | BATCH 1 CL | 38913930.27 |  |  | Completed | 1 |  |  | P00070079L2
NC 2016 | SHS | Region III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 |  | 12 | 2STY12CL | BATCH 1 CL | 14779217.18 |  |  | Completed | 1 |  |  | P00070080L2
NC 2016 | TECHVOC | Region III | Bataan | 300716 | P. Roman Nhs | Pilar | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2625000 |  |  | Completed | 1 |  |  | P00070203L2 | 16CB0020 | 2016-03-02 | 2016-03-09 | 2016-03-16 | 2016-05-23 | 2016-05-31 | N. V. Balbuena Construction
NC 2016 | K10 | Region III | Bulacan | 158522 | Bagumbayan Ps | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105023 | Balatong B Elementary School | Pulilan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105015 | Balatong Es | Pulilan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158506 | Basyo Es | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104945 | Cabayunan Elementary School | Doña Remedios Trinidad | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300770 | Frances National High School | Calumpit | 1 | 1 | 12 | 2STY12CL | BATCH 5 CL | 15085996.11 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105026 | Jose C. Castro Memorial Elementary School | Pulilan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158509 | Kambubuyugan Elementary School | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300744 | Kapitangan National High School | Paombong | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105019 | M. Del Rosario Ms | Pulilan | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104804 | Northville 9 Elementary School To F. Mendoza Memorial Es | Calumpit | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158510 | Pinag-Anakan Es | Doña Remedios Trinidad | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105020 | Pulilan Cs | Pulilan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300754 | Ramona S. Trillana Hs (Mayor Ramon Trillana Mem. Hs (Iba Nhs)) | Hagonoy | 1 | 1 | 24 | 2STY8CL | BATCH 3 CL | 33874191.09 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306724 | Romeo Acuña Santos Memorial High School | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306711 | San Francisco Xavier High School | Bulacan | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306723 | San Miguel-Meysulao High School | Calumpit | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13183972.54 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300755 | San Pedro National High School | Hagonoy | 1 | 1 | 24 | 4STY12CL | BATCH 3 CL | 44337636.41 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300745 | San Roque National Hs | Paombong | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300736 | Sta. Lucia High School | Calumpit | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300756 | Sta. Monica National High School | Hagonoy | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20167107.46 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300756 | Sta. Monica National High School | Hagonoy | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300737 | Sta. Peregrina Hs | Pulilan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 17127665.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105027 | Tabon Es | Pulilan | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104783 | Taliptip Es | Bulacan | 1 | 1 | 12 | 3STY12CL | BATCH 9 CL | 17127665.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300779 | Taliptip Nhs | Bulacan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 13183972.54 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300720 | Alexis G. Santos National High School | Bustos | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300721 | Balagtas National Agricultural Hs | Balagtas (Bigaa) | 2 | 1 | 48 | 4STY24CL | BATCH 7 CL | 71192514.28 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300721 | Balagtas National Agricultural Hs | Balagtas (Bigaa) | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 7290000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104761 | Bambang Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306730 | Banga High School | Plaridel | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104762 | Batia Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300726 | Bintog Hs (Jose J. Mariano Mhs) | Plaridel | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104764 | Bunducan Es | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104765 | Bunlo Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104972 | Bunsuran Es | Pandi | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300728 | Bunsuran Nhs | Pandi | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300728 | Bunsuran Nhs | Pandi | 2 |  | 12 | 4STY12CL | BATCH 5 CL | 22302344 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300734 | Dampol 1St National High School | Plaridel | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104767 | Duhat Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104741 | Engr. Vicente R. Cruz Memorial School | Baliuag | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6872696.155 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300741 | Felizardo C. Lipana Mhs (Sta. Rita Hs) | Guiguinto | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 28520975.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 | 1 | 72 | 4STY24CL | BATCH 5 CL | 106788771.42 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300742 | Guiguinto Nat'L Voc'L. High School | Guiguinto | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300746 | Lolomboy National Nhs | Bocaue | 2 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300729 | Masagana Hs | Pandi | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14750043.6516 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104975 | Matias B. Salvador Memorial Elementary School | Pandi | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158540 | Pandi Heights Elementary School | Pandi | 2 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30837850.48 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158539 | Pandi Residences Es | Pandi | 2 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104984 | Real De Cacarong Elementary Schol | Pandi | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104735 | Santol Elementary School | Balagtas (Bigaa) | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158542 | St. Martha Elementary School | Bocaue | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158542 | St. Martha Elementary School | Bocaue | 2 |  | 3 | 3STY3CL | BATCH 5 CL | 7118301.78 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104828 | Sta.Cruz Elementary | Guiguinto | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158515 | Sto. Nino Es | Pandi | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1847266.47 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306712 | Sto. Nino High School | Baliuag | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 306712 | Sto. Nino High School | Baliuag | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300778 | Sulivan National High School | Baliuag | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10316033.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300778 | Sulivan National High School | Baliuag | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4860000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104769 | Taal Elementary School | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300747 | Taal High School | Bocaue | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8128471.77 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 104769 | Taal High School To Taal Es | Bocaue | 2 |  | 15 | 3STY15CL | BATCH 7 CL | 21923487.88 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104770 | Tambubong Elementary School | Bocaue | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10316033.27 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300780 | Tiaong Nhs | Guiguinto | 2 | 1 | 10 | 2STY10CL | BATCH 5 CL | 13183972.54 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300780 | Tiaong Nhs | Guiguinto | 2 |  | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104760 | V Delas Flores Es | Baliuag | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 13422766.956 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300731 | Akle Hs | San Ildefonso | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11332636.597 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158541 | Alejandro E. Flores, Sr. Elementary School | Doña Remedios Trinidad | 3 | 1 | 4 | 1STY2CL | BATCH 5 CL | 3879259.63 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306702 | Angat Hs (Binagbag Nhs - Taboc Nhs) | Angat | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158505 | Bato Elementary School | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306707 | Binagbag Hs - Angel M. Del Rosario Hs | Angat | 3 | 1 | 12 | 2STY4CL | BATCH 5 CL | 19490250.79 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300748 | Carlos F. Gonzales Hs (Maguinao Cruz Na Daan Nhs) | San Rafael | 3 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104716 | Don Pablo Amisola Memorial School | Angat | 3 | 1 | 12 | 2STY6CL | BATCH 5 CL | 17115358.42 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158507 | Duplas Es | Doña Remedios Trinidad | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2954711.133 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158525 | Durumugan Es | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300774 | John J. Russel Mhs (Sibul Nhs) | San Miguel | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306703 | Julian B. Sumbillo High School | Norzagaray | 3 | 1 | 15 | 3STY15CL | BATCH 9 CL | 24100836.668 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 158526 | Karahumi Elementary School | Norzagaray | 3 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2031993.12 |  |  | Reverted | 0
NC 2016 | K10 | Region III | Bulacan | 158511 | Kawit Es | Doña Remedios Trinidad | 3 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1126464.405 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104960 | Luis Gravador Elementary School | Norzagaray | 3 | 1 | 16 | 4STY16CL | BATCH 3 CL | 27002469 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104960 | Luis Gravador Elementary School | Norzagaray | 3 |  | 12 | 4STY12CL | BATCH 3 CL | 22302344 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306718 | Lydia D. Villangca Trade School | San Rafael | 3 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20167107.46 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105054 | Maasim Elementary School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306708 | Maronquillo National High School | San Rafael | 3 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10315033.27 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300758 | Minuyan National High School | Norzagaray | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18825432.182 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 104952 | Norzagaray Es | Norzagaray | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300760 | Norzagaray National High School | Norzagaray | 3 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105058 | Palapala Elementary School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300772 | Partida Hs (San Miguel Nhs - Partida Hs) | San Miguel | 3 | 1 | 8 | 2STY8CL | BATCH 5 CL | 12415536.73 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300749 | Salapungan Hs | San Rafael | 3 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300732 | San Ildefonso National High School | San Ildefonso | 3 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300732 | San Ildefonso National High School | San Ildefonso | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 20167107.46 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 |  | 16 | 4STY8CL | BATCH 9 CL | 26845533.912 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300771 | San Miguel Nhs | San Miguel | 3 |  | 12 | 4STY12CL | BATCH 9 CL | 22168818.206 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300724 | Sapang Bulac High School | Doña Remedios Trinidad | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2031993.117 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306728 | Sta. Catalina Bata National High School | San Ildefonso | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300740 | Assemblywoman Felicita G. Bernardino Memorial Trade School | Marilao | 4 |  | 24 | 4STY12CL | BATCH 11 CL | 44604688 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300740 | Assemblywoman Felicita G. Bernardino Memorial Trade School | Marilao | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105141 | Balasing Elementary School | Santa Maria | 4 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21923487.88 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 306714 | Catmon Hs | Santa Maria | 4 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10316033.17 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105147 | Cay Pombo Es | Santa Maria | 4 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105149 | Caysio Elementary School | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105144 | Cornelia M. De Jesus Memorialcentral School | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15418925.24 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300739 | F. F. Halili Nat'L. Agr'L. School | Santa Maria | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Bulacan | 300739 | F. F. Halili Nat'L. Agr'L. School | Santa Maria | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105151 | Guyong Es | Santa Maria | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300765 | Parada Nhs | Santa Maria | 4 | 1 | 48 | 4STY24CL | BATCH 9 CL | 71192514.28 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan | 300767 | Pulong Buhangin Nhs | Santa Maria | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31358073.237 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105163 | San Vicente (Hulo) Es | Santa Maria | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15271328 |  |  | Completed | 1
NC 2016 | SHS | Region III | Bulacan |  | Shs In Obando, Bulacan | Obando | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22582794.06 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105166 | Sta. Clara Es | Santa Maria | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22302344 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 306726 | Sta. Cruz High School | Santa Maria | 4 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13183972.54 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105167 | Sta. Cruz Es | Santa Maria | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300777 | Sta. Maria National High School | Santa Maria | 4 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33936211.03 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 300777 | Sta. Maria National High School | Santa Maria | 4 |  | 6 | 3STY6CL | BATCH 3 CL | 10567132 |  |  | Completed | 1
NC 2016 | K10 | Region III | Bulacan | 105170 | Tumana Es | Santa Maria | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 107096 | Bakod Bayan Es | Cabanatuan City | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 107072 | Barlis Es | Cabanatuan City | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 107073 | Buliran Elementary School | Cabanatuan City | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 301045 | Camp Tinio Nhs | Cabanatuan City | 3 | 1 | 20 | 4STY20CL | BATCH 1 CL | 31738176.93 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 301045 | Camp Tinio Nhs | Cabanatuan City | 3 |  | 15 | 3STY15CL | BATCH 1 CL | 23610688 |  |  | Completed | 1
NC 2016 | SHS | Region III | Cabanatuan City | 307301 | Cesar E. Vergara Mhs | Cabanatuan City | 3 | 1 | 9 | 3STY9CL | BATCH 1 CL | 15311797.32 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 307303 | Daan Sarile Integrated School | Cabanatuan City | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Cabanatuan City | 301049 | Eastern Cabu Nhs | Cabanatuan City | 3 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18678518.39 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 301044 | Honorato C. Perez Sr. Mshs | Cabanatuan City | 3 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15932002.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 301047 | Marciano Del Rosario Mnhs | Cabanatuan City | 3 | 1 | 24 | 4STY12CL | BATCH 1 CL | 46435388.33 |  |  | Completed | 1
NC 2016 | SHS | Region III | Cabanatuan City | 301046 | Mayapyap Nhs | Cabanatuan City | 3 | 1 | 16 | 4STY16CL | BATCH 1 CL | 27024547.42 |  |  | Completed | 1
NC 2016 | SHS | Region III | Cabanatuan City | 301046 | Mayapyap Nhs | Cabanatuan City | 3 |  | 8 | 4STY8CL | BATCH 1 CL | 15289461.64 |  |  | Completed | 1
NC 2016 | SHS | Region III | Cabanatuan City | 301048 | San Josef National High School | Cabanatuan City | 3 | 1 | 24 | 4STY12CL | BATCH 11 CL | 46103799.53 |  |  | Completed | 1
NC 2016 | K10 | Region III | Cabanatuan City | 107091 | Talipapa Es | Cabanatuan City | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Gapan City | 300812 | Juan R. Liwag Mem. Nhs | City Of Gapan | 4 | 1 | 24 | 2STY8CL | BATCH 13 CL | 34236560.49 |  |  | Completed | 1
NC 2016 | K10 | Region III | Mabalacat City | 300931 | Camachiles National High School | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 2016-05-26 | B.P. Cruz Builders & Trading
NC 2016 | K10 | Region III | Mabalacat City | 106076 | Dau Elementary School | Mabalacat | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 23252460.801 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 2016-07-02 | Sto. Cristo Const'n & Trading
NC 2016 | K10 | Region III | Mabalacat City | 306927 | Dona Asuncion Lee Integrated School | Mabalacat | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Mabalacat City | 306916 | Mabalacat Comm. Hs | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 2016-07-02 | Al-B Development Corporation
NC 2016 | SHS | Region III | Mabalacat City | 300895 | Mabalacat Nhs | Mabalacat | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Mabalacat City | 306909 | Mabalacat Technical Vocational School | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 1 CL | 30530092.891 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 2016-05-26 | B.P. Cruz Builders & Trading
NC 2016 | K10 | Region III | Mabalacat City | 300900 | Mauaque Hs (Res) | Mabalacat | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 2016-05-26 | R.G. Diaz Builders & Trading
NC 2016 | K10 | Region III | Mabalacat City | 300900 | Mauaque Hs (Res) | Mabalacat | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 2016-05-26 | E.M. Danan Trading & Const'n
NC 2016 | SHS | Region III | Mabalacat City | 306942 | Santos Ventura Nhs | Mabalacat | 1 | 1 | 24 | 4STY24CL | BATCH 1 CL | 35596257.14 |  |  | Completed | 1 |  |  |  |  | 2016-02-26 | 2016-03-05 | 2016-03-17 | 2016-05-12 | 2016-05-26 | Sto. Cristo Const'n & Trading
NC 2016 | K10 | Region III | Mabalacat City | 106071 | Sapang Biabas Resettlement Es | Mabalacat | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 |  |  |  |  | 2016-05-11 | 2016-05-19 | 2016-05-31 | 2016-06-14 | 2016-07-02 | Al-B Development Corporation
NC 2016 | K10 | Region III | Malolos City | 240001 | Bangkal Es | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 13 CL | 10425630 |  |  | Completed | 1
NC 2016 | K10 | Region III | Malolos City | 104864 | Barihan Es | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11175630 |  |  | Reverted | 0 | [10 empty] | DPWH Report: Negotiation on project site produced negative result; funds reverted
NC 2016 | K10 | Region III | Malolos City | 104865 | Bulihan Elementary School | City Of Malolos (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10575630 |  |  | Completed | 1 |  |  | P00070992LZ | 16CC0173 | 2016-10-04 | 2016-10-13 | 2016-10-26
NC 2016 | SHS | Region III | Malolos City | 323601 | Bulihan Nhs | City Of Malolos (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2016 | K10 | Region III | Malolos City | 323607 | City Of Malolos High School - Canalate | City Of Malolos (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Reverted | 0 | [10 empty] | DPWH Report: Negotiation on project site produced negative result; funds reverted
NC 2016 | K10 | Region III | Malolos City | 323606 | City Of Malolos Integrated School - Sto. Rosario | City Of Malolos (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 7 CL | 42766026.9 |  |  | Completed | 1 |  |  | P00072136LZ | 16CC0187 | 2016-10-05 | 2016-10-14 | 2016-10-28
NC 2016 | K10 | Region III | Malolos City | 323606 | City Of Malolos Integrated School - Sto. Rosario | City Of Malolos (Capital) | 1 |  | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00072137LZ | 16CC0174 | 2016-10-04 | 2016-10-13 | 2016-10-26
NC 2016 | SHS | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | City Of Malolos (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 43446975.76 |  |  | Completed | 1 |  |  | P00070993LZ | 16CC0186 | 2016-10-05 | 2016-10-14 | 2016-10-28 |  |  |  | Reported by DPWH
NC 2016 | TECHVOC | Region III | Malolos City | 300751 | Marcelo H. Del Pilar National Hs | City Of Malolos (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  | P00075068LZ | 16CC0113 | 2016-08-03 | 2016-08-12 | 2016-08-25 | 2016-09-08 | 2016-10-25 | JMK BUILDERS CONSTRUCTION
NC 2016 | K10 | Region III | Meycauayan City | 104915 | Bagbaguin Es | City Of Meycauayan | 4 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1
NC 2016 | K10 | Region III | Meycauayan City | 104916 | Bahay Pare Elementary School | City Of Meycauayan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469338 |  |  | Completed | 1
NC 2016 | SHS | Region III | Meycauayan City | 300757 | Meycauayan Nhs | City Of Meycauayan | 4 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22302344 |  |  | Completed | 1
NC 2016 | K10 | Region III | Meycauayan City | 104935 | Meycauayan West Central School | City Of Meycauayan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 19952109.258 |  |  | Completed | 1
NC 2016 | K10 | Region III | Meycauayan City | 104926 | Pandayan Es | City Of Meycauayan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6469338 |  |  | Completed | 1
NC 2016 | K10 | Region III | Meycauayan City | 104928 | Perez Es | City Of Meycauayan | 4 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1
NC 2016 | SHS | Region III | Meycauayan City |  | Shs In Meycauayan City | City Of Meycauayan | 4 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region III | Munoz Science City | 300824 | Munoz National Hs | Science City Of Muñoz | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 63054977.86 |  |  | Completed | 1
NC 2016 | SHS | Region III | Munoz Science City | 322802 | San Antonio Integrated School | Science City Of Muñoz | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300783 | Aliaga National Nhs | Aliaga | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300786 | Baloy Hs | Cuyapo | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | Guimba | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | Guimba | 1 |  | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300788 | Batitang National High School | Zaragoza | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300796 | Carmen Nhs | Zaragoza | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26572907.4417 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300801 | Cuyapo National High School | Cuyapo | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47012629.59 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 105817 | Dimasalang Norte Es To Dimasalang Sur Es | Talavera | 1 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3811375.2325 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. Hs | Quezon | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300845 | Exequiel R. Lina National High School | Licab | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300806 | Galvan National High School | Guimba | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306808 | Ganduz National High School | Pantabangan | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz Nhs | Santo Domingo | 1 | 1 | 30 | 3STY15CL | BATCH 9 CL | 47012629.59 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306810 | Pacac High School | Guimba | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300827 | Paitan Sur Nhs | Cuyapo | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300842 | Salagusog National High School | Cuyapo | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300843 | San Andres Hs | Guimba | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300857 | Sto. Domingo Nts | Santo Domingo | 1 | 1 | 48 | 4STY24CL | BATCH 5 CL | 73886079.24 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300864 | Talavera National High School | Talavera | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 63054977.86 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300869 | Triala Nhs | Guimba | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306811 | Umangan National High School | Aliaga | 1 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300871 | Zaragoza National High School | Zaragoza | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300795 | Canaan East Nhs | Rizal | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300802 | Doña Juana Chioco National High School | Lupao | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300841 | Rizal Nhs | Rizal | 2 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31377488.93 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300841 | Rizal Nhs | Rizal | 2 |  | 16 | 4STY16CL | BATCH 5 CL | 26572907.4417 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306802 | San Felipe Integrated High School | Llanera | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6150000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Nueva Ecija | 306828 | Talugtug Nhs Annex-Saverona | Talugtug | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 105658 | Villa Labrador Es | Rizal | 2 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4700731.4693 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 159034 | Angel'S Ville Es | Santa Rosa | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 159012 | Atate Annex Primary School | Palayan City (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300790 | Bongabon Nhs | Bongabon | 3 | 1 | 60 | 4STY20CL | BATCH 3 CL | 94132466.79 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300790 | Bongabon Nhs | Bongabon | 3 |  | 10 | 2STY10CL | BATCH 3 CL | 13150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306813 | Bongabon Nhs Annex (Vega Hs) | Bongabon | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 159029 | Dupinga Elementary School | Gabaldon (Bitulok & Sabani) | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2650000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 306287 | F. Buencamino Sr. Integrated School | Gabaldon (Bitulok & Sabani) | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6672664.78 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300805 | Gabaldon Voc'L. Agric. Hs | Gabaldon (Bitulok & Sabani) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300805 | Gabaldon Voc'L. Agric. Hs | Gabaldon (Bitulok & Sabani) | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 159018 | Gawad Kalinga Es(Tagumpay Es Annex | Gabaldon (Bitulok & Sabani) | 3 | 1 | 4 | 1STY4CL | BATCH 13 CL | 3667968.78 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300862 | Gen. Mamerto Natividad National Hs | General Mamerto Natividad | 3 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26172907.4417 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. Hs | Laur | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. Hs | Laur | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 105578 | Langka Es | Palayan City (Capital) | 3 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1900000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 105354 | Mag-Asawang Sampaloc Es | General Mamerto Natividad | 3 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300819 | Maligaya Nhs | Palayan City (Capital) | 3 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300819 | Maligaya Nhs | Palayan City (Capital) | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300826 | Nueva Ecija Nhs | Cabanatuan City | 3 |  | 40 | 4STY20CL | BATCH 11 CL | 62754977.86 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300828 | Palayan City National High School | Palayan City (Capital) | 3 | 1 | 24 | 4STY24CL | BATCH 3 CL | 36793039.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300828 | Palayan City National High School | Palayan City (Capital) | 3 |  | 20 | 4STY20CL | BATCH 3 CL | 31377488.93 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 306801 | Santa Rosa National High School | Santa Rosa | 3 | 1 | 24 | 4STY24CL | BATCH 3 CL | 36793039.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300861 | Talabutab Norte National High School | General Mamerto Natividad | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300792 | Cabiao National High School | Cabiao | 4 | 1 | 60 | 4STY20CL | BATCH 11 CL | 93308670.81 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300794 | Calaba National High School | San Isidro | 4 | 1 | 20 | 2STY10CL | BATCH 3 CL | 26300000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306821 | Dr. Jose Lapuz Salonga Hs (Former San Mariano Nhs Annex) | San Antonio | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306821 | Dr. Jose Lapuz Salonga Hs (Former San Mariano Nhs Annex) | San Antonio | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300808 | General Tinio Nhs | General Tinio (Papaya) | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija |  | Gregorio Crespo Nhs | Entablado Cabiao | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306816 | Jaen Nhs (Former Putlod-San Jose Nhs-Annex) | Jaen | 4 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 306809 | Leonor M. Bautista Hs (Pias Campus Annex) | General Tinio (Papaya) | 4 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300817 | Magpapalayok Nhs | San Leonardo | 4 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22824373.66 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300817 | Magpapalayok Nhs | San Leonardo | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300820 | Mallorca National High School | San Leonardo | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 20300000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300820 | Mallorca National High School | San Leonardo | 4 |  | 6 | 3STY6CL |  | 10787131.51 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 105588 | Sabangan Es To Palale Es | General Tinio (Papaya) | 4 | 1 | 2 | 1STY2CL |  | 2138606 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija |  | Mambangnan Hs Annex | San Leonardo | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300821 | Mambangnan Nhs | San Leonardo | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22824373.66 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija |  | Mariano Llanera Nhs | San Vicente | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300832 | Penaranda National Nhs | Peñaranda | 4 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13150000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300834 | Pulo Nhs | San Isidro | 4 | 1 | 12 | 2STY6CL | BATCH 5 CL | 17330023.34 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300835 | Putlod-San Jose Nhs | Jaen | 4 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31377488.93 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija | 300840 | Rio Chico National High School | General Tinio (Papaya) | 4 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22824373.66 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300844 | San Anton Nhs | San Leonardo | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300844 | San Anton Nhs | San Leonardo | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 9021461.5561 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300846 | San Francisco Nhs | San Antonio | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300846 | San Francisco Nhs | San Antonio | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | K10 | Region III | Nueva Ecija |  | San Leonardo Nhs | San Leonardo | 4 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300856 | Sta. Rita Nhs | Cabiao | 4 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio Nhs | San Isidro | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11950076.8509 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300867 | Teodoro A. Dionisio Nhs | San Isidro | 4 |  | 6 | 2STY6CL | BATCH 9 CL | 8665011.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | Nueva Ecija | 300854 | Zacarias C. Aquilizan Hs (Sta. Barbara Nhs Annex) | San Antonio | 4 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6672664.78 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City |  | Barretto I Es | Olongapo City | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City |  | Barretto I Es | Olongapo City | 1 |  |  | Completion of 3STY6CL | BATCH 11 CL | 8214965.05 |  |  | Reverted | 0
NC 2016 | K10 | Region III | Olongapo City | 162003 | Iram Ii Es | Olongapo City | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1964740.17 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City | 500027 | James L. Gordon Is | Olongapo City | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region III | Olongapo City | 301056 | Kalalake Nhs | Olongapo City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18500000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 |  | 24 | 4STY24CL | BATCH 1 CL | 36150000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Olongapo City | 107122 | New Cabalan Es | Olongapo City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2550000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Olongapo City | 107123 | Old Cabalan Integrated School | Olongapo City | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region III | Olongapo City | 301058 | Regional Science High School | Olongapo City | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306938 | Ayala | Magalang | 1 | 1 | 16 | 2STY8CL | BATCH 1 CL | 22054685.18 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106128 | San Francisco Es | Magalang | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8364965.051 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga |  | Shs In Magalang, Pampanga | Magalang | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300943 | Tinajero Nhs - Sta. Lucia Hs Annex | Magalang | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306911 | Ambrocio S.Simpao Educational And Tradet Center Of Learning | Santa Rita | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11353662.8677 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300879 | Basa Air Base High School | Floridablanca | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300892 | Gutad Nhs | Floridablanca | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300894 | Lubao Nhs (Lubao Vocational School) | Lubao | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 24352577.982 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106222 | Manibaug Paralaya Es | Porac | 2 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6532000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300902 | Natividad Nhs | Guagua | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300904 | Pagyuruan Nhs | Floridablanca | 2 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16279930.102 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300909 | Pulung Santol National High School | Porac | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300912 | Remedios Nhs | Lubao | 2 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300881 | San Basilio Hs (Becuran Nhs Annex) | Santa Rita | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6658917.7692 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106016 | San Matias Es | Guagua | 2 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8446000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300929 | San Vicente Nhs, Lubao | Lubao | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 306935 | Bacolor Hs | Bacolor | 3 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306907 | Camba Nhs - Candating Hs | Arayat | 3 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15441327.92 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300901 | Mexico National High School | Mexico | 3 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16976379.0515 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300872 | Nicanor David Vergara Hs (Anao Nhs) | Mexico | 3 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 105923 | Potrero Es | Bacolor | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300921 | San Juan Nhs, Mexico | Mexico | 3 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106300 | San Matias Es | Santo Tomas | 4 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300874 | Bahay Pare Nhs | Candaba | 4 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15494444.4052 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300874 | Bahay Pare Nhs | Candaba | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15347518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300883 | Caduang Tete Hs | Macabebe | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300927 | Concepcion Is | San Simon | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8611414.0015 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306946 | Conrado P. Macapinlac , Sr. Nhs | Minalin | 4 | 1 | 12 | 2STY6CL | BATCH 1 CL | 16976379.0515 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106255 | Dela Paz Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306934 | Emigdio A. Bondoc High School | San Luis | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6658917.7692 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306952 | Lanang High School | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 105937 | Mandili I Es | Candaba | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106152 | Masantol Es | Masantol | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 16729930.1 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300933 | Masantol Hs (Sta. Lucia Nhs, Masantol) | Masantol | 4 | 1 | 12 | 2STY6CL | BATCH 13 CL | 17729930.1 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300906 | Pasig Nhs | Candaba | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300906 | Pasig Nhs | Candaba | 4 |  | 8 | 4STY8CL | BATCH 11 CL | 15347518.84 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306951 | Pulong Gubat Hs | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6936271.404 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300914 | Salapungan Nhs - Annex Mandili | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106256 | San Agustin Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106256 | San Agustin Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6882000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106240 | San Carlos Es | San Luis | 4 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 306944 | San Luis Nhs | San Luis | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8611414.0015 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300924 | San Matias Nhs | Santo Tomas | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15302343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106261 | San Pablo Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6882000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 105877 | San Vicente Es | Apalit | 4 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15721327.92 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga |  | Shs In Apalit, Pampanga | Apalit | 4 | 1 | 8 | 4STY8CL | BATCH 1 CL | 15419956.811 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106250 | Sta. Monica Es | San Luis | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6882000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306917 | Sta. Monica High School | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6882000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106266 | Sto. Nino Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 106266 | Sto. Nino Es | San Simon | 4 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6882000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Pampanga | 300936 | Sto. Rosario Nhs | Minalin | 4 | 1 | 6 | 2STY6CL | BATCH 1 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 300939 | Tagulod Nhs | Candaba | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6627321.081 |  |  | Completed | 1
NC 2016 | K10 | Region III | Pampanga | 306906 | Tarik Suliman High School | Masantol | 4 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6758917.7692 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Fernando City | 301064 | Pampanga Nhs | City Of San Fernando (Capital) | 3 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose City | 300800 | Constancio Padilla National High School | San Jose City | 2 | 1 | 24 | 4STY24CL | BATCH 11 CL | 36793039.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose City | 300800 | Constancio Padilla National High School | San Jose City | 2 |  | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose City | 325802 | Tayabo High School - Cpnhs Annex | San Jose City | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6150000 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107144 | Bagong Buhay E Es | City Of San Jose Del Monte | 0 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10567132 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107146 | Bagong Buhay G Es | City Of San Jose Del Monte | 0 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40067946.14 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107147 | Bagong Buhay I Es (Lawang Pari) | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 9 CL | 15677614.1562 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307508 | Citrus National Hs | City Of San Jose Del Monte | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22302344 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | San Jose Del Monte City | 307508 | Citrus National Hs | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307506 | City Of San Jose Del Monte National Science High School | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15047519 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107156 | Gumaok Es | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095038 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307510 | Kaypian National High School | City Of San Jose Del Monte | 0 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | San Jose Del Monte City | 307510 | Kaypian National High School | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307511 | Marangal National High School | City Of San Jose Del Monte | 0 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107158 | Muzon (Pabahay 2000) Es | City Of San Jose Del Monte | 0 |  | 16 | 4STY16CL | BATCH 9 CL | 26852469 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107158 | Muzon (Pabahay 2000) Es | City Of San Jose Del Monte | 0 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY16CL | BATCH 5 CL | 27002469 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 301059 | Paradise Farms Nhs | City Of San Jose Del Monte | 0 |  | 8 | 2STY8CL | BATCH 5 CL | 11291397.03 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107160 | S. Palay Proper Es | City Of San Jose Del Monte | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6469338 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107161 | San Jose Del Monte Central School | City Of San Jose Del Monte | 0 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22302344 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 301060 | San Jose Del Monte National Hs | City Of San Jose Del Monte | 0 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31020975.67 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 301061 | San Jose Del Monte Nat'L. Trade School | City Of San Jose Del Monte | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 44604688 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | San Jose Del Monte City | 301061 | San Jose Del Monte Nat'L. Trade School | City Of San Jose Del Monte | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107162 | San Martin Es (Bbc) | City Of San Jose Del Monte | 0 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 | 1 | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region III | San Jose Del Monte City | 307507 | San Martin National Hs | City Of San Jose Del Monte | 0 |  | 4 | 2STY4CL | BATCH 5 CL | 6252451.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 | 1 | 48 | 4STY24CL | BATCH 5 CL | 71492514.28 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 301062 | Sapang Palay National High School | City Of San Jose Del Monte | 0 |  | 6 | 3STY6CL | BATCH 5 CL | 10567132 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107164 | Sta. Cruz (Bbd) Elementary School | City Of San Jose Del Monte | 0 | 1 | 12 | 3STY12CL | BATCH 9 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region III | San Jose Del Monte City | 107151 | Sto. Cristo Es | City Of San Jose Del Monte | 0 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095038 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300946 | Anao Nhs | Anao | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300946 | Anao Nhs | Anao | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300948 | Balaoang Nhs | Paniqui | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300948 | Balaoang Nhs | Paniqui | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300950 | Bamban Nhs | San Clemente | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300950 | Bamban Nhs | San Clemente | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300952 | Bilad High School | Camiling | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12898000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300973 | Birbira High School | Camiling | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300973 | Birbira High School | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300953 | Buenavista High School | Pura | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300955 | Caanamongan High School | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300955 | Caanamongan High School | Santa Ignacia | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 307010 | Calipayan Nhs | Santa Ignacia | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300958 | Camiling School Of Home Industries | Camiling | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300958 | Camiling School Of Home Industries | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307008 | Carabaoan-Caocaoayan High School | Mayantoc | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307008 | Carabaoan-Caocaoayan High School | Mayantoc | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | Paniqui | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4860000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | Paniqui | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31413000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300964 | Estipona Nhs | Pura | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15272000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307019 | Josephine M. Cojuangco National Technicalvocationalhigh School | Mayantoc | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 307006 | Malacampa Nhs | Camiling | 1 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12764000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307006 | Malacampa Nhs | Camiling | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300972 | Marawi Nhs | Camiling | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15272000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307011 | Moncada National High School | Moncada | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307011 | Moncada National High School | Moncada | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300975 | Nambalan Nhs | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300978 | Padapada Nhs | Santa Ignacia | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26968000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300980 | Pitombayog Nhs | Mayantoc | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300980 | Pitombayog Nhs | Mayantoc | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300982 | Ramos National High School | Ramos | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21596000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300983 | Sacata Nhs | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300984 | San Bartolome Nhs | Mayantoc | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300985 | San Felipe Hs | San Manuel | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300985 | San Felipe Hs | San Manuel | 1 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15272000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300989 | San Pedro Nhs | Moncada | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22373000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300991 | Sapang High School | Moncada | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300992 | Sta. Ines Nhs | Santa Ignacia | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300992 | Sta. Ines Nhs | Santa Ignacia | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300999 | Vargas High School | Santa Ignacia | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307004 | Ventinilla Hs | Paniqui | 1 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10985000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300954 | Buenlag Nhs | Gerona | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300959 | Cardona Nhs | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307007 | Corazon C. Aquino High School | Gerona | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22372400 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307007 | Corazon C. Aquino High School | Gerona | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 106789 | Don Casimiro G. Tanedo Es | Victoria | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300965 | Gerona Western Public High School | Gerona | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 307001 | Moriones High School | San Jose | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307001 | Moriones High School | San Jose | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300981 | Quezon Nhs | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300986 | San Jose Nhs | Gerona | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 106456 | Sembrano Es | Gerona | 2 | 1 | 3 | 1STY3CL | BATCH 13 CL | 2802592.44 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300995 | Tagumbao Nhs | Gerona | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 301000 | Victoria Nhs | Victoria | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 301001 | Villa Aglipay Nhs | San Jose | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300949 | Anastacio G. Yumul High School | Concepcion | 3 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10985000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300949 | Anastacio G. Yumul High School | Concepcion | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | Concepcion | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 35950800 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | Concepcion | 3 |  | 12 | 4STY12CL | BATCH 13 CL | 22372400 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 160010 | Burog Elementary School | Bamban | 3 | 1 | 4 | 1STY4CL | BATCH 9 CL | 3500000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300956 | Calangitan Hs (Resettlement School) | Capas | 3 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8296000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300956 | Calangitan Hs (Resettlement School) | Capas | 3 |  | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300957 | Caluluan High School | Concepcion | 3 | 1 | 15 | 3STY15CL | BATCH 3 CL | 21596000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 307017 | Caluluan High School Annex | Concepcion | 3 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2668000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307017 | Caluluan High School Annex | Concepcion | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300994 | Capas High School | Capas | 3 | 1 | 24 | 4STY24CL | BATCH 13 CL | 35950800 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300961 | Comillas High School | La Paz | 3 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15271500 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300976 | Cristo Rey Hs (Ores) | Capas | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21595500 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300962 | Dapdap Hs | Bamban | 3 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300966 | Guevara Nhs | La Paz | 3 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18403000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300966 | Guevara Nhs | La Paz | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300967 | La Paz Nhs | La Paz | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31413000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300967 | La Paz Nhs | La Paz | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 106490 | Lara Ps | La Paz | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1958000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300977 | O'Donnell High School | Capas | 3 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22373000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300977 | O'Donnell High School | Capas | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300990 | San Roque Nhs | Bamban | 3 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26968000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 106389 | Sta. Juliana Es | Capas | 3 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2668000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell Hs Annex) | Capas | 3 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6382000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell Hs Annex) | Capas | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5000000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 106390 | Sta. Lucia Es | Capas | 3 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12898000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac | 300997 | Tarlac National Hs - Annex | City Of Tarlac (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Tarlac | 300997 | Tarlac National Hs - Annex | City Of Tarlac (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 321403 | Balibago Primero Integrated School | City Of Tarlac (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Tarlac City | 300960 | Central Azucarera De Tarlac Nhs Main | City Of Tarlac (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10878000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 300970 | Maliwalo Nhs | City Of Tarlac (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 300970 | Maliwalo Nhs | City Of Tarlac (Capital) | 2 |  | 4 | 2STY4CL | BATCH 9 CL | 6320000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 106759 | Pag-Asa Es | City Of Tarlac (Capital) | 2 | 1 | 1 | 1STY1CL | BATCH 5 CL | 1015000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 106759 | Pag-Asa Es | City Of Tarlac (Capital) | 2 |  | 2 | 1STY2CL | BATCH 5 CL | 1930000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac City | 321408 | Sto. Cristo Is | City Of Tarlac (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.5917 |  |  | Completed | 1
NC 2016 | K10 | Region III | Tarlac | 300996 | Tarlac National High School | City Of Tarlac (Capital) | 2 | 1 | 36 | 4STY12CL | BATCH 13 CL | 67117500 |  |  | Completed | 1 | [10 empty] | With approved additional funds
NC 2016 | K10 | Region III | Tarlac City | 106774 | Tibagan Es | City Of Tarlac (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6320000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Zambales | 301015 | Castillejos National High School | Castillejos | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14033441.1023 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 2016-08-04 | M.V. Guballa Const.
NC 2016 | SHS | Region III | Zambales | 301012 | Cawag Hs (Resettlement School) | Subic | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8564965.05 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 2016-08-04 | Sto. Cristo Const. & Trading
NC 2016 | K10 | Region III | Zambales | 160525 | Hanjin Integrated School | Castillejos | 1 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6469337.64 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 2016-08-04 | Repolman Const.
NC 2016 | K10 | Region III | Zambales | 107013 | Mapanao Es | Subic | 1 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8294965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 301029 | San Guillermo National High School | San Marcelino | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 11509179.0837 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 2016-08-04 | Repolman Const.
NC 2016 | K10 | Region III | Zambales | 301029 | San Guillermo National High School | San Marcelino | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8364965.05 |  |  | Completed | 1 |  |  |  |  | 2016-06-22 | 2016-06-30 | 2016-07-12 | 2016-07-21 | 2016-08-04 | MCB Zamora Const. & Supply
NC 2016 | SHS | Region III | Zambales | 301035 | Sta. Fe Nhs | San Marcelino | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 2016-08-04 | M.V. Guballa Const.
NC 2016 | SHS | Region III | Zambales | 301036 | Subic National High School | Subic | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 11509179.0837 |  |  | Completed | 1 |  |  |  |  | 2016-05-23 | 2016-06-02 | 2016-06-14 | 2016-07-21 | 2016-08-04 | MCB Zamora Const. & Supply
NC 2016 | K10 | Region III | Zambales | 106869 | Amungan Es | Iba (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1
NC 2016 | SHS | Region III | Zambales | 301004 | Amungan Nhs | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301004 | Amungan Nhs | Iba (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 2015-07-18 | E. R. DELACRUZ CONSTRUCTION
NC 2016 | K10 | Region III | Zambales | 106825 | Arew Es | Cabangan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 301007 | Bani National High School - Coto Annex | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6470000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | HIGH STRENGTH DEVELOPMENT CORPORATION
NC 2016 | K10 | Region III | Zambales | 106887 | Bani Relocation Es | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | STO CRISTO CONST. & TRADING
NC 2016 | K10 | Region III | Zambales | 106989 | Bayto Es (Biay Es) | Santa Cruz | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6350000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301025 | Botolan National High School | Botolan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301010 | Cabangan National High School | Cabangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301011 | Candelaria School Of Fisheries | Candelaria | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106829 | Casa-Tondo Es | Cabangan | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106906 | Cauyan Es | Palauig | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | FERMIDA CONST. SERVICES & SUPPLIES
NC 2016 | K10 | Region III | Zambales | 106907 | Dampay Es | Palauig | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | NEW MASINLOC HENRY'S CONST. & SUPPLY
NC 2016 | K10 | Region III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | San Felipe | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.5917 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | MCB ZAMORA CONST. & SUPPLY
NC 2016 | TECHVOC | Region III | Zambales | 301014 | Guisguis Nhs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106876 | Lipay-Dingin Es | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 2015-07-18 | E. R. DELACRUZ CONSTRUCTION
NC 2016 | TECHVOC | Region III | Zambales | 301028 | Locloc National High School | Palauig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106892 | Mandaloy Es | Masinloc | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | HIGH STRENGTH DEVELOPMENT CORPORATION
NC 2016 | K10 | Region III | Zambales | 307115 | Mena Mem. Nhs - San Fernando Hs | Santa Cruz | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 7408468.5459 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | STO. CRISTO CONST. & TRADING
NC 2016 | SHS | Region III | Zambales | 301022 | Mena Mem. Nhs (Bolitoc Nhs) | Santa Cruz | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8400000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 2015-07-18 | STO. CRISTO CONST. & TRADING
NC 2016 | TECHVOC | Region III | Zambales | 301022 | Mena Mem. Nhs (Bolitoc Nhs) | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 2015-07-18 | E. R. DELACRUZ CONSTRUCTION
NC 2016 | K10 | Region III | Zambales | 106965 | Namatacan Es | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | NEW MASINLOC HENRY'S CONST. & SUPPLY
NC 2016 | K10 | Region III | Zambales | 301018 | Paite-Balincaguing National High School | San Felipe | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6419337.6381 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | MICKAJETTE CONST. & TRADING
NC 2016 | K10 | Region III | Zambales | 106916 | Palauig Central School | Palauig | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | NEW MASINLOC HENRY'S CONST. & SUPPLY
NC 2016 | SHS | Region III | Zambales | 301027 | Rofulo M. Landa Hs (Salaza Nhs) | Palauig | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10950000 |  |  | Completed | 1 |  |  |  |  | 2016-03-03 | 2016-03-10 | 2016-03-22 | 2016-07-01 | 2015-07-12 | STO. CRISTO CONST. & TRADING
NC 2016 | K10 | Region III | Zambales | 106880 | San Agustin Integrated School | Iba (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8250000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | MCB ZAMORA CONST. & SUPPLY
NC 2016 | TECHVOC | Region III | Zambales | 307107 | San Antonio National High School | San Antonio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106968 | San Jose-Patrocinio Elementary | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | MICKAJETTE CONST. & TRADING
NC 2016 | TECHVOC | Region III | Zambales | 301032 | San Miguel National High School | San Antonio | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | NEW MASINLOC HENRY'S CONST. & SUPPLY
NC 2016 | K10 | Region III | Zambales | 106970 | San Narciso Elementary School | San Narciso | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | MICKAJETTE CONST. & TRADING
NC 2016 | TECHVOC | Region III | Zambales | 301033 | Sta. Cruz Nhs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301034 | Sta. Cruz Nhs - Lipay Hs | Santa Cruz | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 301006 | Taltal National High School | Masinloc | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12850000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region III | Zambales | 301006 | Taltal National High School | Masinloc | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106930 | West Dirita Es | San Antonio | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6350000 |  |  | Completed | 1 |  |  |  |  | 2016-05-24 | 2016-05-31 | 2016-06-24 | 2016-07-13 | 2016-08-09 | FERMIDA CONST. SERVICES & SUPPLIES
NC 2016 | TECHVOC | Region III | Zambales | 301037 | Zambales Nhs | Iba (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region III | Mabalacat City | 159545 | Sta. Maria Elementary School | Mabalacat | 1 | 1 | 2 | 1STY2CL w/ toilet attached | BATCH 14 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106862 | Pres. Ramon F. Magsaysay Es | Castillejos | 1 | 1 | 6 | 2STY6CL | BATCH 14 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region III | Zambales | 106863 | San Agustin Es | Castillejos | 1 | 1 | 6 | 2STY6CL | BATCH 14 CL | 8214965.05 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104543 | Binuangan ES | BAGAC | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2798745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104544 | Binukawan ES | BAGAC | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106943 | Baliwet ES | SAN MARCELINO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4030000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160506 | Aningway-Sacatihan Elementary school - Annex | SUBIC | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3930000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300673 | Aurora NHS | BALER (Capital) | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2689278.95 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300680 | Casiguran NHS | CASIGURAN | 0 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8568975.88 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300690 | Lual NHS | CASIGURAN | 0 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8598960.38 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 306504 | Diagyan NHS | DILASAG | 0 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8602149 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2689278.95 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300682 | Dilasag NHS | DILASAG | 0 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 6593763.24 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300692 | Manggitahan NHS | DILASAG | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2725300.99 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2715175.7 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300689 | Juan C. Angara Memorial NHS | DINALUNGAN | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3021334.47 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2714367.71 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 306501 | Mariano D. Marquez Memorial NHS | DINALUNGAN | 0 |  | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8547933.3 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300688 | Ibona NHS | DINGALAN | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2713559.71 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2689278.95 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300693 | Dipaculao NHS | DIPACULAO | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2995437.72 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300691 | Maria Aurora NHS | MARIA AURORA | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2737476.03 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300681 | Dikapinisan NHS | SAN LUIS | 0 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 8651011.68 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 300686 | Ditumabo NHS | SAN LUIS | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2689278.95 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2689278.95 |  |  | Completed | 1
NC 2017 | TVL | Region III | Aurora | 306508 | Rosauro R. Tangson, Sr. NHS | SAN LUIS | 0 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2995437.72 |  |  | Completed | 1
NC 2017 | K10 | Region III | Balanga City | 104555 | Cabog-Cabog Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2623745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Balanga City | 104566 | Tanato Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2798745.92 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bataan | 300709 | Mabatang NHS | ABUCAY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104572 | Colo ES | DINALUPIHAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bataan | 300704 | J. C. Payumo, Jr. Memo. HS | DINALUPIHAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2750000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104616 | Parapal ES | HERMOSA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 7500000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 307006 | Malacampa NHS | CAMILING | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2798530 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106335 | Surgui Elementary | CAMILING | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2758254.17 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106443 | Abagon ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2842837.33 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106462 | Amacalan ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2758254.17 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106463 | Ayson ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2923833.94 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106469 | Luna ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2760067.83 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106455 | Quezon ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2832585.83 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 307008 | Carabaoan-Caocaoayan High School | MAYANTOC | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2821410 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106560 | Balaoang ES | PANIQUI | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4279794.3 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106581 | Dapdap ES | PANIQUI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2910860.83 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | PANIQUI | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2798530 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5915000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106650 | Villa Aglipay ES | SAN JOSE | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2986206.83 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106677 | San Francisco ES | SANTA IGNACIA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2758254.17 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106682 | Sta. Ines CES | SANTA IGNACIA | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4298080.79 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106790 | Gabaldon ES | VICTORIA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2758254.17 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106781 | Masalasa ES | VICTORIA | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106783 | Victoria East CS | VICTORIA | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3931402.87 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac City | 106754 | Balanti ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2868630.51 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac City | 106708 | Villa Bacolor Elementary School | CITY OF TARLAC (Capital) | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4157258.19 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106815 | Beneg ES | BOTOLAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3894660.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160504 | Cabatuan ES | BOTOLAN | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5068846.15 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106805 | Loob-Bunga III Elementary School | BOTOLAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2633745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160510 | Nacolcol Elementary School | BOTOLAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2793575.37 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106810 | Paudpod ES | BOTOLAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3831547.52 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160526 | Poonbato Elementary School | BOTOLAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3993692.52 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160509 | San Juan ES Annex | CABANGAN | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5129883.65 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106878 | Lupang Pangako Resettlement School | IBA (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2753575.37 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106886 | Bani ES | MASINLOC | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3852585.02 |  |  | Completed | 1
NC 2017 | TVL | Region III | Zambales | 307103 | San Salvador High School | MASINLOC | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2992941.95 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106910 | Liozon ES | PALAUIG | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3894660.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106912 | Locloc ES | PALAUIG | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3894660.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106927 | San Miguel ES | SAN ANTONIO | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 4951463.65 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160520 | Banawen PS | SAN FELIPE | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2779003.42 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106963 | Doce-Martires ES | SAN NARCISO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2676858.42 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106972 | San Rafael-Natividad ES | SAN NARCISO | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3831547.52 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106973 | Simminublan ES | SAN NARCISO | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3873622.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bataan | 300704 | J. C. Payumo, Jr. Memo. HS | DINALUPIHAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 250000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 750000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104665 | Pag-Asa ES | Orani, Bataan | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4068435.02 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300721 | Balagtas National Agricultural HS | BALAGTAS (BIGAA) | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 7060000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104819 | Doña Damiana De Leon Macam Memorial E/S (San Miguel E/S) | CALUMPIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4068323.08 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300736 | Sta. Lucia High School | CALUMPIT | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2916585.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104837 | Hangga ES | HAGONOY | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4312148.74 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Bulacan | 104997 | Sto. Niño Elementary School | PAOMBONG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2979573.45 |  |  | Completed | 1
NC 2017 | TVL | Region III | Gapan City | 321301 | Herminio G. Nicolas High School | CITY OF GAPAN | 4 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 11039541.9 |  |  | Completed | 1 |  |  |  | 17CF0195 | 2017-09-20 | 2017-09-27 | 2017-10-10 |  | 2018-12-01 | R.A. PAHATI CONST. & SUPPLY, INC.
NC 2017 | TVL | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1 |  |  |  | 17CF0216 | 2017-11-15 | 2017-11-22 | 2017-04-12 |  | 2018-01-04 | A.M.P. CONSTRUCTION
NC 2017 | TVL | Region III | Gapan City | 300851 | San Roque NHS | CITY OF GAPAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1 |  |  |  | 17CF0217 | 2017-11-15 | 2017-11-22 | 2017-04-12 |  | 2018-01-04 | A.M.P. CONSTRUCTION
NC 2017 | TVL | Region III | Gapan City | 300813 | Sta. Cruz NHS | CITY OF GAPAN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1 |  |  |  | 17CF0218 | 2017-11-15 | 2017-11-22 | 2017-04-12 |  | 2018-01-04 | A.M.P. CONSTRUCTION
NC 2017 | TVL | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2822814.98 |  |  | Completed | 1 | [9 empty] | Ayana Construction & Trading
NC 2017 | TVL | Region III | Malolos City | 300751 | Marcelo H. del Pilar National HS | CITY OF MALOLOS (Capital) | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 8555881.44 |  |  | Completed | 1 | [9 empty] | F.R. Mapilisan Construction
NC 2017 | K10 | Region III | Munoz Science City | 105539 | Calabalabaan ES | Munoz | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105562 | Villa Cuizon ES | Munoz | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105543 | Franza ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105551 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 322805 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300790 | Bongabon NHS | BONGABON | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4270476.73 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300816 | Macabaclay National High School | BONGABON | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300826 | Nueva Ecija NHS | CABANATUAN CITY | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 11633775.5 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306814 | Ligaya National High School | GABALDON (BITULOK & SABANI) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4270476.73 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105313 | Tagumpay ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3193325.61 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300863 | Eduardo L. Joson Memorial HS | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300823 | Mataas Na Kahoy National High School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4131258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300861 | Talabutab Norte National High School | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4343713.14 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105389 | Manacsac ES | GUIMBA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300836 | Lambakin National High School | JAEN | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300810 | Hilario E. Hermosa Mem. HS | LAUR | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306812 | Ricardo Dizon Canlas Agr'l. HS (Former Jorge M. Padilla NHS Annex) | LAUR | 3 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 15445034.08 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 159022 | Don Dalmacio PS | LICAB | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105495 | Casile ES | LLANERA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105505 | Old Murcon PS | LLANERA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105515 | Alalay Grande ES | LUPAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105522 | Mapangpang ES | LUPAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105524 | Parista ES | LUPAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2703745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105528 | San Antonio Weste ES | LUPAO | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105573 | Recuerdo ES | NAMPICUAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306803 | Buklod-Palad NHS (former Maligaya NHS Annex - DoÃ±a Josefa) | PALAYAN CITY (Capital) | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300828 | Palayan City National High School | PALAYAN CITY (Capital) | 3 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105602 | Napon-Napon ES | PANTABANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300832 | Peñaranda National High School | PEÑARANDA | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300853 | STA. BARBARA NATIONAL HS | SAN ANTONIO | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300817 | Magpapalayok NHS | SAN LEONARDO | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4091258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300820 | MALLORCA NATIONAL HIGH SCHOOL | SAN LEONARDO | 4 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300818 | Malacañang NHS | SANTA ROSA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4011258.52 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 159032 | Ilog Baliwag PS | SANTO DOMINGO | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105803 | San Pascual ES | TALAVERA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105831 | Sibul ES | TALAVERA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2703745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105843 | Saverona ES | Talugtug | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105698 | Kaliwanagan ES | SAN JOSE CITY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2643745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 159025 | Habitat ES | San Jose City West | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106313 | Bamban Gabaldon ES | BAMBAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2692303.8 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106319 | Mainang Resett ES | BAMBAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106320 | Malasa ES | BAMBAN | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106368 | Benigno Aquino, Jr. ES (Calingcuan ES) | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666114.07 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106382 | Bueno Elementary School | CAPAS | 3 | 1 | 4 | 1STY4CL | BATCH 7 | 5043110.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 300994 | Capas High School | CAPAS | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3468286.84 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 160019 | Flora PS | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2798807.68 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 160018 | Manabayukan ES | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2789488.57 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106387 | Maruglo ES | CAPAS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2909492 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 160017 | San Agustin PS | CAPAS | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2847804.75 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell HS Annex) | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2827367.11 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106376 | Sta. Rita ES | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106378 | Talaga ES | CAPAS | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2666117.07 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106378 | Talaga ES | CAPAS | 3 |  | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | CONCEPCION | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3468286.84 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106393 | Cafe ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2847804.75 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106394 | Castillo ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106428 | Concepcion West Central ES | CONCEPCION | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106397 | Culatingan ES | CONCEPCION | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3846992.9 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106400 | Malupa ES | CONCEPCION | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4054862 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106408 | Parang ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2900172.9 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106409 | Pitabunan ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2639935.65 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106412 | San Miguel ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106416 | Talimundoc SM ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2900172.9 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106417 | Tinang ES | CONCEPCION | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3820803.17 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106495 | Balanoy ES | LA PAZ | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 4233323.8 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106486 | E.M. Castaneda CS | LA PAZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3277014.29 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106487 | Guevara Elementary School | LA PAZ | 3 | 1 | 3 | 1STY3CL | BATCH 7 | 3846992.9 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106489 | La Purisima ES | LA PAZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2900172.9 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106492 | Macalong ES | LA PAZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 3303204.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106504 | Rizal Multigrade | LA PAZ | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2900172.9 |  |  | Completed | 1
NC 2017 | SHS | Region III | Olongapo City | 345223 | SHS within Barretto 1 ES | OLONGAPO CITY | 1 | 1 | 8 | 4STY8CL | BATCH 8 | 17329570.67 |  |  | Completed | 1 |  |  |  | 17CM0086 | 2017-10-06 | 2017-10-13 | 2017-10-26 | 2017-11-13 | 2017-11-22 | R.J. IBARRA CONSTRUCTION
NC 2017 | TVL | Region III | Olongapo City | 345223 | SHS within Barretto 1 ES | OLONGAPO CITY | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 8 | 8945901.76 |  |  | Completed | 1 |  |  |  | 17CM0105 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | R.J. IBARRA CONSTRUCTION
NC 2017 | SHS | Region III | Olongapo City | 361079 | SHS within Tapinac ES | OLONGAPO CITY | 1 | 1 | 12 | 4STY12CL | BATCH 8 | 33319789.72 |  |  | Completed | 1 |  |  |  | 17CM0087 | 2017-10-06 | 2017-10-13 | 2017-10-26 | 2017-11-13 | 2017-11-22 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | TVL | Region III | Olongapo City | 361079 | SHS within Tapinac ES | OLONGAPO CITY | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 8 | 9995901.76 |  |  | Completed | 1 |  |  |  | 17CM0107 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | TVL | Region III | Angeles City | 301038 | Angeles City Nat'l. Trade School | ANGELES CITY | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 7590000 |  |  | Completed | 1 |  |  |  | 17CI0075 |  |  |  |  | 2018-01-10 | R.G. DIAZ BUILDERS & TRADING
NC 2017 | K10 | Region III | Bulacan | 104837 | Hangga ES | HAGONOY | 1 | 1 | 3 | 1STY3CL | BATCH 12 | 4312148.74 |  |  | Completed | 1
NC 2017 | TVL | Region III | Gapan City | 321301 | Herminio G. Nicolas High School | CITY OF GAPAN | 4 | 1 | 16 | WORKSHOP BLDG (7x18) | BATCH 12 | 74635388.42 |  |  | Completed | 1 |  |  |  | 17CF026 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | SQ. M. TRADING & CONSTRUCTION CORP.
NC 2017 | TVL | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 8 | WORKSHOP BLDG (7x18) | BATCH 12 | 43094289.61 |  |  | Completed | 1 |  |  |  | 17CF0229 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | JERRY R. SANTIAGO CONSTRUCTION
NC 2017 | TVL | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17788702.76 |  |  | Completed | 1 |  |  |  | 17CF0232 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2017 | TVL | Region III | Gapan City | 300822 | Maruhat NHS | CITY OF GAPAN | 4 | 1 | 12 | WORKSHOP BLDG (7x18) | BATCH 12 | 51898283.28 |  |  | Completed | 1 |  |  |  | 17CF0227 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | R.D. TALENS CONSTRUCTION AND TRADING
NC 2017 | TVL | Region III | Gapan City | 300851 | San Roque NHS | CITY OF GAPAN | 4 | 1 | 12 | WORKSHOP BLDG (7x18) | BATCH 12 | 51938283.28 |  |  | Completed | 1 |  |  |  | 17CF0228 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | R.A. PAHATI CONST. & SUPPLY, INC.
NC 2017 | TVL | Region III | Gapan City | 300813 | Sta. Cruz NHS | CITY OF GAPAN | 4 | 1 | 12 | WORKSHOP BLDG (7x18) | BATCH 12 | 17868702.76 |  |  | Completed | 1 |  |  |  | 17CF0231 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | R.A. PAHATI CONST. & SUPPLY, INC.
NC 2017 | TVL | Region III | Mabalacat City | 300895 | Mabalacat NHS | MABALACAT | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2530000 |  |  | Completed | 1 |  |  |  |  | 2018-01-10 |  |  |  | 2018-01-10 | 3-SIDES BUILDERS AND TRADING CORP.
NC 2017 | TVL | Region III | Mabalacat City | 306909 | Mabalacat Technical Vocational School | MABALACAT | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5060000 |  |  | Completed | 1 |  |  |  |  | 2018-01-10 |  |  |  | 2018-01-10 | AL-B DEVELOPMENT CORP.
NC 2017 | TVL | Region III | Mabalacat City | 306942 | Santos Ventura National High School | MABALACAT | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5060000 |  |  | Completed | 1 |  |  |  |  | 2018-01-10 |  |  |  | 2018-01-10 | E.L GOMEZ CONSTRUCTION
NC 2017 | TVL | Region III | Mabalacat City | 345342 | SHS within Sapang Biabas Resettlement ES | MABALACAT | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5060000 |  |  | Completed | 1 |  |  |  |  | 2018-01-10 |  |  |  | 2018-01-10 | AFRA CONSTRUCTION
NC 2017 | TVL | Region III | Mabalacat City | 300889 | Madapdap Resettlement HS | MAGALANG | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2530000 |  |  | Completed | 1 |  |  |  |  | 2018-01-10 |  |  |  | 2018-01-10 | ALBIT CONSTRUCTION
NC 2017 | TVL | Region III | Malolos City | 500404 | City of Malolos Integrated School - Atlag | CITY OF MALOLOS (Capital) | 1 | 1 | 2 | 2STY4CL (EQUIVALENT TO 2 LAB) | BATCH 12 | 18498000 |  |  | Completed | 1 | [9 empty] | Adimre Construction
NC 2017 | TVL | Region III | Malolos City | 300751 | Marcelo H. del Pilar National HS | CITY OF MALOLOS (Capital) | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 8555881.44 |  |  | Completed | 1
NC 2017 | TVL | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | SCIENCE CITY OF MUÑOZ | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9352220.58 |  |  | Completed | 1
NC 2017 | TVL | Region III | Munoz Science City | 300824 | Munoz National HS-Main | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Munoz Science City | 322802 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Munoz Science City | 322802 | SAN ANTONIO INTEGRATED SCHOOL | SCIENCE CITY OF MUÑOZ | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9352220.58 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 24423808.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 25183018.88 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 22673320.14 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300839 | Restituto B. Peria HS | ALIAGA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4 | 1 | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 17788702.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300801 | Cuyapo National High School | CUYAPO | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 29485001.73 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17124790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300827 | Paitan Sur NHS | CUYAPO | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 32622221.4 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9355901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9200727.42 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300842 | Salagusog National High School | CUYAPO | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9513045.63 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306809 | LEONOR M. BAUTISTA HS (Pias Campus Annex) | GENERAL TINIO (PAPAYA) | 4 | 1 | 8 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 35577405.52 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | GUIMBA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 12099429.89 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300809 | Bartolome R Sangalang National High School | GUIMBA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 12784074.97 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 31541738.12 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9999289.75 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300806 | Galvan National High School | GUIMBA | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 10436579.91 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306815 | Manacsac HS (Former Nagpandayan HS Annex) | GUIMBA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 20809543.53 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306815 | Manacsac HS (Former Nagpandayan HS Annex) | GUIMBA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 21398753.65 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300825 | Nagpandayan NHS | GUIMBA | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 29225001.73 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306810 | PACAC HIGH SCHOOL | GUIMBA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 20743834.78 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306810 | PACAC HIGH SCHOOL | GUIMBA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 20926129.29 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300843 | San Andres HS | GUIMBA | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 14812500.87 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300869 | Triala NHS | GUIMBA | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 17178641.01 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300845 | Exequiel R. Lina National High School | LICAB | 1 | 1 | 8 | WORKSHOP BLDG (7x18) | BATCH 12 | 48901444.61 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300855 | Sta. Maria NHS | LICAB | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 32522221.4 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300870 | Llanera National HIgh School | LLANERA | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 11228151.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300802 | Doña Juana Chioco National High School | LUPAO | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300847 | San Isidro NHS | LUPAO | 2 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 22673320.14 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300847 | San Isidro NHS | LUPAO | 2 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300838 | Nampicuan NHS | NAMPICUAN | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300838 | Nampicuan NHS | NAMPICUAN | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300837 | Recuerdo NHS | NAMPICUAN | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 32572221.4 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306808 | Ganduz National High School | PANTABANGAN | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 306808 | Ganduz National High School | PANTABANGAN | 1 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9352220.58 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300830 | Pantabangan NHS | PANTABANGAN | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300830 | Pantabangan NHS | PANTABANGAN | 2 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300789 | BICOS NATIONAL HIGH SCHOOL | RIZAL | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9442855.04 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300793 | Cabucbucan NHS | RIZAL | 2 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 22673320.14 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300793 | Cabucbucan NHS | RIZAL | 2 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300795 | Canaan East NHS | RIZAL | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9644264.98 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300841 | Rizal NHS | RIZAL | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9553630.45 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 | 1 | 6 | WORKSHOP BLDG (7x18) | BATCH 12 | 35356003.35 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300814 | Julia Ortiz Luiz NHS | SANTO DOMINGO | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 25183018.88 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300857 | Sto. Domingo NTS | SANTO DOMINGO | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300859 | Sto. Rosario NHS, Sto. Domingo | SANTO DOMINGO | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 14612500.87 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300791 | Bulac NHS | TALAVERA | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 29495001.73 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 17324790.26 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 20926129.29 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300852 | Sibul National High School | TALAVERA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 41219087.06 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300865 | Tabacao National High School | TALAVERA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300864 | TALAVERA NATIONAL HIGH SCHOOL | TALAVERA | 1 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300864 | TALAVERA NATIONAL HIGH SCHOOL | TALAVERA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 21568753.65 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300788 | Batitang National High School | ZARAGOZA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 12319429.89 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300788 | Batitang National High School | ZARAGOZA | 1 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 12 | 25393018.88 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300796 | Carmen NHS | ZARAGOZA | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 12644074.97 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1 | 1 | 3 | WORKSHOP BLDG (7x18) | BATCH 12 | 14266903.01 |  |  | Completed | 1
NC 2017 | TVL | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1 |  | 9 | WORKSHOP BLDG (7x18) | BATCH 12 | 46968587.49 |  |  | Completed | 1
NC 2017 | K10 | Region III | Olongapo City | 107121 | Iram ES | OLONGAPO CITY | 1 | 1 | 2 | 1STY2CL | BATCH 12 | 2963745.92 |  |  | Completed | 1 |  |  |  | 17CM0104 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Pampanga |  | Mangga High School | CANDABA | 4 | 1 | 3 | 1STY3CL | BATCH 12 | 3600000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga |  | Mangga High School | CANDABA | 4 |  | 3 | 1STY3CL | BATCH 12 | 3600000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 306951 | Pulong Gubat High School | CANDABA | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2400000 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300890 | Floridablanca Nat'l. Agr'l. School | FLORIDABLANCA | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 31850795.7 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300892 | Gutad NHS | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 9668781.86 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105975 | Sta. Monica ES | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 12 | 13098501.49 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300882 | Betis NHS | GUAGUA | 2 | 1 | 8 | 4STY8CL | BATCH 12 | 25573112.8 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106108 | San Esteban ES | MACABEBE | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | Pampanga | 306938 | AYALA HIGH SCHOOL | MAGALANG | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 12 | 2530000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Pampanga | 345531 | SHS in Magalang, Pampanga | Magalang | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5060000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Pampanga | 300943 | Tinajero NHS - Sta. Lucia HS Annex | MAGALANG | 1 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 5060000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106148 | Bulacus Elementary School | MASANTOL | 4 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1
NC 2017 | TVL | Region III | Pampanga | 306933 | Planas High School | PORAC | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 7310375.68 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300909 | Pulung Santol National High School | PORAC | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 31850795.7 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 306911 | AMBROCIO S.SIMPAO EDUCATIONAL AND TRADET CENTER OF LEARNING | SANTA RITA | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 12262930.63 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300880 | Becuran National High School | SANTA RITA | 2 | 1 | 12 | 4STY12CL | BATCH 12 | 42964647.25 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300881 | San Basilio HS (Becuran NHS Annex) | SANTA RITA | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 12412930.63 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Fernando City | 345268 | Dolores Stand Alone Senior High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 12 | 8445959.36 |  |  | Completed | 1 |  |  | P00181437LZ-CW1 | 17CG0347 |  |  |  |  | 2018-12-28 | ONE GIGATT CONSTRUCTION CORP.
NC 2017 | SHS | Region III | San Fernando City | 500145 | Maimpis Integrated High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 12 | 8445959.36 |  |  | Completed | 1 |  |  | P00181438LZ-CW1 | 17CG0346 |  |  |  |  | 2018-12-28 | AL DARE CONSTRUCTION
NC 2017 | SHS | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 12 | 8445959.36 |  |  | Completed | 1 |  |  | P00181439LZ-CW1 | 17CG0348 |  |  |  |  | 2018-12-28 | RTE CONSTRUCTION
NC 2017 | TVL | Region III | San Jose City | 306817 | Caanawan High School | SAN JOSE CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105698 | Kaliwanagan ES | SAN JOSE CITY | 2 | 1 | 2 | 1STY2CL | BATCH 12 | 2643745.92 |  |  | Completed | 1
NC 2017 | TVL | Region III | San Jose City | 300833 | Porais National High School | SAN JOSE CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9095901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | San Jose City | 300800 | San Jose City National High School (formerly Constancio Padilla National High School) | SAN JOSE CITY | 2 | 1 | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9295901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | San Jose City | 300800 | San Jose City National High School (formerly Constancio Padilla National High School) | SAN JOSE CITY | 2 |  | 2 | WORKSHOP BLDG (7x18) | BATCH 12 | 9352220.58 |  |  | Completed | 1
NC 2017 | TVL | Region III | San Jose del Monte City | 107157 | Kaypian ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 1 | TECH-VOC | BATCH 12 | 3689000 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300962 | Dapdap HS | BAMBAN | 3 | 1 | 12 | 3STY12CL | BATCH 12 | 29515590.08 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300962 | Dapdap HS | BAMBAN | 3 |  | 12 | 3STY12CL | BATCH 12 | 29359267.25 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300962 | Dapdap HS | BAMBAN | 3 |  | 8 | 2STY8CL | BATCH 12 | 16791466.71 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300990 | San Roque NHS | BAMBAN | 3 | 1 | 16 | 4STY16CL | BATCH 12 | 36910737.96 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106345 | Lasong ES | CAMILING | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300994 | Capas High School | CAPAS | 3 | 1 | 12 | 4STY12CL | BATCH 12 | 31727956.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300976 | Cristo Rey HS (ORES) | CAPAS | 3 | 1 | 16 | 4STY16CL | BATCH 12 | 38110737.96 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300977 | O'Donnell High School | CAPAS | 3 | 1 | 12 | 4STY12CL | BATCH 12 | 31727956.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 307005 | Sta. Juliana High School (O'Donnell HS Annex) | CAPAS | 3 | 1 | 8 | 2STY8CL | BATCH 12 | 17414168.56 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300949 | Anastacio G. Yumul High School | CONCEPCION | 3 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300949 | Anastacio G. Yumul High School | CONCEPCION | 3 |  | 8 | 2STY8CL | BATCH 12 | 16791466.71 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | CONCEPCION | 3 | 1 | 8 | 4STY8CL | BATCH 12 | 17211678.28 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | CONCEPCION | 3 |  | 16 | 4STY16CL | BATCH 12 | 36910737.96 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106482 | San Bartolome ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106566 | Manaois Elementary School | PANIQUI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106588 | Ramon U. Cojuangco ES (Samput ES) | PANIQUI | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106596 | Estipona ES | PURA | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106615 | Balloc ES | SAN CLEMENTE | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106643 | San Juan de Moriones ES | SAN JOSE | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac City | 106738 | Cutcut II ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | 1STY2CL W/TOILET | BATCH 12 | 2759000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106868 | Villaflor ES | CASTILLEJOS | 1 | 1 | 10 | 2STY10CL | BATCH 12 | 19998155.67 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301006 | Taltal National High School | MASINLOC | 2 | 1 | 9 | 3STY9CL | BATCH 12 | 24573235.23 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301006 | Taltal National High School | MASINLOC | 2 |  | 9 | 3STY9CL | BATCH 12 | 24573235.23 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301021 | Gov. Manuel D. Barretto National High School | SAN FELIPE | 2 | 1 | 12 | 3STY12CL | BATCH 12 | 29464454.75 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106989 | Bayto ES (Biay ES) | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 11782393.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106989 | Bayto ES (Biay ES) | SANTA CRUZ | 2 |  | 6 | 2STY6CL | BATCH 12 | 11782393.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301022 | Mena Mem. National High School (Bolitoc NHS) | SANTA CRUZ | 2 | 1 | 12 | 3STY12CL | BATCH 12 | 29359267.25 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 307115 | Mena Mem. NHS - San Fernando HS | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 11761355.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 107002 | Aningway-Sacatihan ES | SUBIC | 1 | 1 | 8 | 2STY8CL | BATCH 12 | 17164790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 107002 | Aningway-Sacatihan ES | SUBIC | 1 |  | 8 | 2STY8CL | BATCH 12 | 17164790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 107010 | Ilwas ES | SUBIC | 1 | 1 | 8 | 2STY8CL | BATCH 12 | 18554790.26 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Zambales | 107014 | Matain ES | SUBIC | 1 | 1 | 6 | 2STTY6CL | BATCH 12 | 11776168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 33359789.72 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Zambales | 307125 | Subic NHS Annex V-Ilwas HS | SUBIC | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 33419789.72 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | TVL | Region III | Gapan City | 321301 | Herminio G. Nicolas High School | CITY OF GAPAN | 4 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 13 | 17788702.76 |  |  | Completed | 1 |  |  |  | 17CF0230 | 2017-11-22 | 2017-11-29 | 2017-11-12 |  | 2018-01-09 | A.M.P. CONSTRUCTION
NC 2017 | TVL | Region III | San Jose City | 306817 | Caanawan High School | SAN JOSE CITY | 2 |  | 4 | WORKSHOP BLDG (7x18) | BATCH 13 | 17523087.2 |  |  | Completed | 1
NC 2017 | TVL | Region III | San Jose City | 300868 | Tondod NHS | SAN JOSE CITY | 2 | 1 | 4 | WORKSHOP BLDG (7x18) | BATCH 13 | 17815616.79 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 307017 | Caluluan High School Annex | CONCEPCION | 3 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300957 | Caluluan HS | CONCEPCION | 3 | 1 | 8 | 4STY8CL | BATCH 13 | 17289845.32 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300961 | Comillas High School | LA PAZ | 3 | 1 | 6 | 3STY6CL | BATCH 13 | 13765574.53 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300961 | Comillas High School | LA PAZ | 3 |  | 6 | 3STY6CL | BATCH 13 | 13739515.1 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300966 | Guevara NHS | LA PAZ | 3 | 1 | 8 | 4STY8CL | BATCH 13 | 17159570.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300967 | La Paz NHS | LA PAZ | 3 | 1 | 12 | 4STY12CL | BATCH 13 | 32249789.72 |  |  | Completed | 1
NC 2017 | SHS | Region III | Tarlac | 300967 | La Paz NHS | LA PAZ | 3 |  | 8 | 4STY8CL | BATCH 13 | 17559570.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 | 1 | 12 | 3STY12CL | BATCH 13 | 29509267.25 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301015 | Castillejos National High School | CASTILLEJOS | 1 |  | 1 | 4STY12CL | BATCH 13 | 41558409.74 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Zambales | 307118 | San Agustin HS | CASTILLEJOS | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 17429570.67 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Zambales | 106864 | San Isidro Elementary School | CASTILLEJOS | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9095901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301029 | San Guillermo National High School | SAN MARCELINO | 1 | 1 | 1 | 4STY21 | BATCH 13 | 33419789.72 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301029 | San Guillermo National High School | SAN MARCELINO | 1 |  | 1 | 4STY21 | BATCH 13 | 33419789.72 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301030 | San Marcelino National HS | SAN MARCELINO | 1 | 1 | 1 | 2STY8CL | BATCH 13 | 18714790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 107007 | Calapandayan ES | SUBIC | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 25968047.73 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Zambales | 107017 | Pamatawan IS | SUBIC | 1 | 1 | 12 | 4STY12CL | BATCH 13 | 31839789.72 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 | 1 | 1 | 4STY16C | BATCH 13 | 39100737.96 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301036 | Subic National High School | SUBIC | 1 |  | 1 | 4STY16C | BATCH 13 | 39100737.96 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | K10 | Region III | Angeles City | 107022 | Abelardo G. Tinio ES | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0099 |  |  |  |  | 2018-01-22 | PVB CONSTRUCTION AND TRADING/TURQUOISE CONSTRUCTION AND REALTY DEVELOPMENT
NC 2017 | K10 | Region III | Angeles City | 107023 | Angeles ES | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0096 |  |  |  |  | 2018-01-15 | B.P. CRUZ BUILDERS AND TRADING
NC 2017 | K10 | Region III | Angeles City | 107033 | Pulung Cacutud ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1 |  |  |  | 17CI0086 |  |  |  |  | 2018-01-15 | 3-SIDES BUILDERS & TRADING CORPORATION
NC 2017 | K10 | Region III | Angeles City | 107037 | Sapalibutad ES | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0090 |  |  |  |  | 2018-01-15 | STO. CRISTO CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Angeles City | 107042 | Malabanias IS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0097 |  |  |  |  | 2018-01-15 | J.SIMEON CONSTRUCTION
NC 2017 | K10 | Region III | Angeles City | 107044 | Sapang Bato ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1 |  |  |  | 17CI0084 |  |  |  |  | 2018-01-15 | GERCEL CONSTRUCTION & DEVELOPMENT GROUP, INC.
NC 2017 | K10 | Region III | Angeles City | 107048 | Sta. Teresita ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1 |  |  |  | 17CI0085 |  |  |  |  | 2018-01-15 | B-12 CONSTRUCTION & TRADING CORPORATION
NC 2017 | K10 | Region III | Angeles City | 107053 | Cuayan ES | ANGELES CITY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17309570.67 |  |  | Completed | 1 |  |  |  | 17CI0088 |  |  |  |  | 2018-01-15 | PING-ANN'S CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Angeles City | 107058 | M. Nepomuceno ES | ANGELES CITY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17309570.67 |  |  | Completed | 1 |  |  |  | 17CI0094 |  |  |  |  | 2018-01-15 | B-12 CONSTRUCTION & TRADING CORPORATION
NC 2017 | K10 | Region III | Angeles City | 107060 | Sto. Domingo IS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0093 |  |  |  |  | 2018-01-15 | B-12 CONSTRUCTION & TRADING CORPORATION
NC 2017 | K10 | Region III | Angeles City | 107060 | Sto. Domingo IS | ANGELES CITY | 1 |  | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0095 |  |  |  |  | 2018-01-15 | NORTHERN BUILDERS
NC 2017 | K10 | Region III | Angeles City | 301040 | Francisco G. Nepomuceno Mem. HS | ANGELES CITY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17309570.67 |  |  | Completed | 1 |  |  |  | 17CI0089 |  |  |  |  | 2018-01-15 | PING-ANN'S CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Angeles City | 307207 | Malabanias IS | ANGELES CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | Completed | 1 |  |  |  | 17CI0098 |  |  |  |  | 2018-01-22 | WILCU CONSTRUCTION
NC 2017 | K10 | Region III | Bataan | 104546 | Parang ES | BAGAC | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9445901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104550 | Saysain ES | BAGAC | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9445901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104631 | Lamao ES | LIMAY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 10745901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bataan | 104679 | Daan Pare ES | ORION | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9745901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104800 | Calumpang ES | CALUMPIT | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10074000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104801 | Calumpit Cs | CALUMPIT | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 17391000 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104811 | Longos ES | CALUMPIT | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 12415000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104818 | San Marcos ES | CALUMPIT | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 19317000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104836 | Hagonoy Cs | HAGONOY | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 12963000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104855 | San Pascual Elementary School | HAGONOY | 1 | 1 | 9 | 3STY9CL | BATCH 14 | 28476000 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2017 | K10 | Region III | Bulacan | 104859 | Tampok ES | HAGONOY | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 12882000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104994 | Pulo ES | PAOMBONG | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10366000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105026 | JOSE C. CASTRO MEMORIAL ELEMENTARY SCHOOL | PULILAN | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300737 | Sta. Peregrina HS | PULILAN | 1 | 1 | 6 | 3STY6LAB=3STY12CL SIZE | BATCH 14 | 24421000 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2017 | TVL | Region III | Bulacan | 300738 | Dona Candelaria Meneses Duque National High School | BULACAN | 1 | 1 | 4 | 4STY4LAB=4STY8CL SIZE | BATCH 14 | 17494000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300743 | Iba National High School | HAGONOY | 1 | 1 | 6 | 2STY12CL (EQUIVALENT TO 6LAB) | BATCH 14 | 20911000 |  |  | COMPLETED | 1
NC 2017 | TVL | Region III | Bulacan | 300744 | Kapitangan National High School | PAOMBONG | 1 | 1 | 4 | 2STY4CL (EQUIVALENT TO 2 LAB) | BATCH 14 | 8434000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300755 | San Pedro National High School | HAGONOY | 1 | 1 | 12 | 4STY12CL (EQUIVALENT TO 4LAB AND 4CL FOR K10) | BATCH 14 | 31927000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300756 | Sta. Monica National High School | HAGONOY | 1 | 1 | 8 | 4STY8CL (EQUIVALENT TO 4 LAB) | BATCH 14 | 22647000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300768 | Calumpit NHS (San Marcos NHS) | CALUMPIT | 1 | 1 | 8 | 4STY8LAB=4STY16CL SIZE | BATCH 14 | 35845000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300770 | Frances National High School | CALUMPIT | 1 | 1 | 8 | 4STY8LAB=4STY16CL SIZE | BATCH 14 | 41221000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 300779 | Taliptip National High Sschool | BULACAN | 1 | 1 | 6 | 2STY6LAB=3STY12CL SIZE | BATCH 14 | 25099000 |  |  | Completed | 1
NC 2017 | TVL | Region III | Bulacan | 306711 | San Francisco Xavier High School | BULACAN | 1 | 1 | 6 | 3STY6LAB=3STY12CL SIZE | BATCH 14 | 23464000 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104739 | Dr. G. Dela Merced | BALIUAG | 2 | 1 | 9 | 3STY9CL | BATCH 14 | 26768047.73 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2017 | K10 | Region III | Bulacan | 104743 | Jacinto Ponce Elementary School | BALIUAG | 2 | 1 | 12 | 3STY12CL | BATCH 14 | 31659267.25 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104751 | Calantipay Elementary School | BALIUAG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12956168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104762 | Batia ES | BOCAUE | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12156168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104763 | BIÑANG ES | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104764 | Bunducan ES | Bocaue | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104765 | Bunlo ES | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9645901.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104766 | Cong. E. R. Cruz Mem. School (Bocaue CS) | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 104771 | Turo Elementary School | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104789 | Catacte ES | BUSTOS | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 18274790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104975 | Matias B. Salvador Memorial Elementary School | PANDI | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 104983 | Pinagkuartelan ES | PANDI | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 19778790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 158538 | Bocaue Hills Elementary School | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300726 | Bintog HS (Jose J. Mariano MHS) | PLARIDEL | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 25029570.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300729 | Masagana HS | PANDI | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 19711910.56 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300733 | Cambaog NHS | BUSTOS | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 34949789.72 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Bulacan | 300734 | Dampol 1st National High School | PLARIDEL | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 30296570.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300741 | Felizardo C. Lipana NHS (Sta. Rita HS) | GUIGUINTO | 2 | 1 | 16 | 4STY16CL | BATCH 14 | 60828241.27 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9495901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300781 | Tibagan National High School | BUSTOS | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 20459570.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306712 | Sto. Nino High School | BALIUAG | 2 | 1 | 6 | 3STY6CL | BATCH 14 | 19965436.15 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 306730 | Banga High School | PLARIDEL | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 25029570.67 |  |  | Completed | 1 | [10 empty] | Request for completion cost P600k evaluated by Special Task Force with Memo dated Oct 6, 2022 DPWH Brice Hernandez Reported completed
NC 2017 | K10 | Region III | Bulacan | 104939 | Apugan ES | NORZAGARAY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 17344762 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105028 | Anyatam Elementary school | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10606358 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Bulacan | 105029 | Bubulong Malaki ES | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10606358 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105032 | Bulusukan Elementary School | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10606358 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105040 | Pulong Tamo Elementary School | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10486868 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105053 | Gabihan Elementary School | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10606358 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105077 | Kng. Kabayo ES | SAN MIGUEL | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10677077 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300722 | Binagbag NHS | ANGAT | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19630869 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300723 | Doña Remedios Trinidad High School | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19922771 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300730 | Calawitan NHS | SAN ILDEFONSO | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19618125 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Bulacan | 300731 | Akle HS | SAN ILDEFONSO | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19711299 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | 12 | 4STY12CL | BATCH 14 | 33873899 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300760 | Norzagaray National High School | NORZAGARAY | 3 | 1 | 16 | 4STY16CL | BATCH 14 | 36797426 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300771 | San Miguel NHS | SAN MIGUEL | 3 | 1 | 20 | 4STY20CL | BATCH 14 | 42776912 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Bulacan | 300772 | Partida HS (San Miguel NHS - Partida HS) | SAN MIGUEL | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19855578 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300774 | John J. Russell MHS (Sibul NHS) | SAN MIGUEL | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 16800352 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306702 | Angat HS (Binagbag NHS - Taboc NHS) | ANGAT | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 10675249 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306702 | Angat HS (Binagbag NHS - Taboc NHS) | ANGAT | 3 |  | 4 | 2STY4CL | BATCH 14 | 10675249 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19436457 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306706 | Pres. Diosdado Macapagal MHS | ANGAT | 3 | 1 | 12 | 4STY12CL | BATCH 14 | 30819357 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 306718 | Lydia D. Villangca Trade School | SAN RAFAEL | 3 | 1 | 8 | 4STY8CL | BATCH 14 | 19618125 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 105145 | Camatchile ES | SANTA MARIA | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | REVERTED | 0
NC 2017 | SHS | Region III | Bulacan | 300739 | F. F. Halili Nat'l. Agr'l. School | SANTA MARIA | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19688133 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300766 | Prenza NHS | MARILAO | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19664967 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300767 | Pulong Buhangin NHS | SANTA MARIA | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19613075 |  |  | Completed | 1
NC 2017 | SHS | Region III | Bulacan | 300777 | Sta. Maria National High School | SANTA MARIA | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19618125 |  |  | Completed | 1
NC 2017 | K10 | Region III | Bulacan | 306726 | Sta. Cruz High School | SANTA MARIA | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19618125 |  |  | Completed | 1
NC 2017 | K10 | Region III | Cabanatuan City | 107074 | Caalibangbangan ES | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | BATCH 14 | 12190833.8 |  |  | Completed | 1 |  |  | P00184052LZ-CW1 | 17CF0243 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | Far East Eagle Construction
NC 2017 | K10 | Region III | Cabanatuan City | 107094 | Bagong Sikat ES | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1 |  |  | P00184053LZ-CW1 | 17CF0244 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | A.M.P. Construction
NC 2017 | K10 | Region III | Cabanatuan City | 107113 | P.G. Crisostomo ES | CABANATUAN CITY | 3 | 1 | 8 | 2STY8CL | BATCH 14 | 17788702.76 |  |  | Completed | 1 |  |  | P00184054LZ-CW1 | 17CF0236 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | Jerry R. Santiago Construction
NC 2017 | TVL | Region III | Cabanatuan City | 301049 | Eastern Cabu NHS | CABANATUAN CITY | 3 | 1 | 6 | 3STY6WS | BATCH 14 | 33292155.14 |  |  | Completed | 1 |  |  | P00184055LZ-CW1 | 17CF0234 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | D.G. Sarmenta Construction
NC 2017 | TVL | Region III | Cabanatuan City | 301049 | Eastern Cabu NHS | CABANATUAN CITY | 3 |  | 4 | 2STY4WS | BATCH 14 | 17988702.76 |  |  | Completed | 1 |  |  | P00184056LZ-CW1 | 17CF0235 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | D.G. Sarmenta Construction
NC 2017 | TVL | Region III | Cabanatuan City | 307301 | Cesar E. Vergara Memorial High School | CABANATUAN CITY | 3 | 1 | 6 | 3STY6WS | BATCH 14 | 33292155.14 |  |  | COMPLETED | 1 |  |  | P00184057LZ-CW1 | 17CF0237 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-04 | D.G. Sarmenta Construction | DPWG Reported Completed
NC 2017 | K10 | Region III | Mabalacat City | 106072 | Sta. Ine ES | MABALACAT CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | COMPLETED | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | AL-B DEVELOPMENT CORP.
NC 2017 | K10 | Region III | Mabalacat City | 106076 | Dau ES | MABALACAT CITY | 1 | 1 | 16 | 4STY16CL | BATCH 14 | 37060737.96 |  |  | Completed | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | B.P CRUZ BUILDERS AND TRADING
NC 2017 | K10 | Region III | Mabalacat City | 106077 | Dau Homesite ES | MABALACAT CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | COMPLETED | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | B.P CRUZ BUILDERS AND TRADING
NC 2017 | K10 | Region III | Mabalacat City | 106077 | Dau Homesite ES | MABALACAT CITY | 1 |  | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | GJG CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Mabalacat City | 106082 | Mabiga ES | MABALACAT CITY | 1 | 1 | 12 | 4STY12CL | BATCH 14 | 31799789.72 |  |  | COMPLETED | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | AL-B DEVELOPMENT CORP.
NC 2017 | K10 | Region III | Mabalacat City | 106082 | Mabiga ES | MABALACAT CITY | 1 |  | 8 | 4STY8CL | BATCH 14 | 17309570.67 |  |  | Completed | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | R.G DIAZ BUILDERS AND TRADING
NC 2017 | K10 | Region III | Mabalacat City | 159529 | Monicayo ES | MABALACAT CITY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 17309570.67 |  |  | Completed | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | PING-ANNS CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Mabalacat City | 306922 | Duquit HS | MABALACAT CITY | 1 | 1 | 16 | 4STY16CL | BATCH 14 | 37060737.96 |  |  | COMPLETED | 1 |  |  |  |  | 2018-01-15 |  |  |  | 2018-01-15 | E.M.L CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | Malolos City | 104886 | Bagna ES | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 14 | 14157000 |  |  | Completed | 1 | [9 empty] | R.C. Pallarca Construction
NC 2017 | SHS | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 13049000 |  |  | Completed | 1 | [9 empty] | Alpha & Omega Gen. Contractor & Devt. Corp.
NC 2017 | TVL | Region III | Malolos City | 300750 | Malolos Marine Fishery School & Laboratory | CITY OF MALOLOS (Capital) | 1 |  | 8 | 4STY16CL (EQUIVALENT TO 8 LAB EACH) | BATCH 14 | 67352000 |  |  | Completed | 1 | [9 empty] | Framecon Builders.
NC 2017 | TVL | Region III | Malolos City | 300751 | Marcelo H. del Pilar National HS | CITY OF MALOLOS (Capital) | 1 |  | 4 | 4STY8CL (EQUIVALENT TO 4 LAB) | BATCH 14 | 16064000 |  |  | Completed | 1 | [9 empty] | EML Construction & Trading
NC 2017 | K10 | Region III | Malolos City | 323605 | Pres. Corazon Cojuangco Aquino Memorial National High School | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 14 | 27756000 |  |  | COMPLETED | 1 | [9 empty] | Jose Rubi Construction
NC 2017 | TVL | Region III | Malolos City | 345345 | SHS in Malolos City | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | 2STY8CL ( EQUIVALENT TO 4 LAB) | BATCH 14 | 14486000 |  |  | Completed | 1 | [9 empty] | Alpha & Omega Gen. Contractor & Devt. Corp.
NC 2017 | K10 | Region III | Meycauayan City | 104917 | Bancal ES | CITY OF MEYCAUAYAN | 4 | 1 | 8 | 2STY8CL | BATCH 14 | 17603483 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Meycauayan City | 104922 | Lawa ES | CITY OF MEYCAUAYAN | 4 | 1 | 6 | 3STY6CL | BATCH 14 | 14357558 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Meycauayan City | 300757 | Meycauayan NHS | CITY OF MEYCAUAYAN | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 19688133 |  |  | Completed | 1
NC 2017 | SHS | Region III | Meycauayan City | 345350 | Academic Senior High School of the City of Meycauayan | CITY OF MEYCAUAYAN | 4 | 1 | 12 | 4STY12CL | BATCH 14 | 37427933 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105542 | DepEd-CLSU ES (Lab.) | Munoz | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105545 | RICARDO VIOLA ADRIANO E/S | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105546 | Linglingay ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9385901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105547 | Magtanggol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9385901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105559 | San Antonio Integrated School | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11926168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Munoz Science City | 105565 | Villa Santos Elementary School | Munoz | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Munoz Science City | 300824 | Munoz National HS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12016168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105186 | San Pablo (B) ES | ALIAGA | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 20789645.45 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105796 | Calipahan ES | TALAVERA | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 17774790.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105796 | Calipahan ES | TALAVERA | 1 |  | 8 | 2STY8CL | BATCH 14 | 17124790.26 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300803 | Dr. Ramon de Santos NHS | CUYAPO | 1 | 1 | 10 | 2STY10CL | BATCH 14 | 19858155.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300838 | Nampicuan NHS | NAMPICUAN | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 17124790.26 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300850 | San Ricardo NHS | TALAVERA | 1 | 1 | 8 | 2STY6CL | BATCH 14 | 14284798.31 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105596 | Conversion ES | Pantabangan | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9215901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105605 | Pantabangan West CS | PANTABANGAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105608 | San Juan ES | PANTABANGAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9385901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105636 | Aglipay ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105639 | Cabucbucan ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105641 | Canaan West ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105644 | Don Lorenzo E. Aleta Elementary School | Rizal | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105645 | Estrella ES | Rizal | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105654 | Rizal West ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105655 | San Esteban ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105656 | San Gregorio ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105657 | Sta. Monica ES | RIZAL | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12006168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105658 | Villa Labrador ES | RIZAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105833 | Alula ES | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9335901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105839 | Mayamot I PS | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105844 | Sta. Catalina PS | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105845 | Sto. Domingo PS | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105847 | Talugtug West Central School | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9245901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105848 | Tandoc ES | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105851 | Villa Rosario PS | TALUGTUG | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300802 | Doña Juana Chioco National High School | LUPAO | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11806168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300866 | Talugtug NHS | TALUGTUG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11816168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105217 | Concepcion ES | CABIAO | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 9394687.19 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105664 | Lawang Kupang ES | SAN ANTONIO | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 9072180.68 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105675 | Sta. Barbara South ES | SAN ANTONIO | 4 | 1 | 8 | 2STY8CL | BATCH 14 | 17788702.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Nueva Ecija | 105675 | Sta. Barbara South ES | SAN ANTONIO | 4 |  | 10 | 2STY10CL | BATCH 14 | 21897204.42 |  |  | Completed | 1
NC 2017 | SHS | Region III | Nueva Ecija | 300856 | Sta. Rita NHS | Cabiao | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 9072180.68 |  |  | Completed | 1
NC 2017 | K10 | Region III | Olongapo City | 107122 | New Cabalan ES | OLONGAPO CITY | 1 | 1 | 9 | 3STY9CL | BATCH 14 | 26058047.73 |  |  | Completed | 1 |  |  |  | 17CM0098 | 2017-10-06 | 2017-10-13 | 2017-10-26 | 2017-11-13 | 2017-11-22 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Olongapo City | 107123 | Old Cabalan Integrated School | OLONGAPO CITY | 1 | 1 | 8 | 4STY8CL | BATCH 14 | 18309570.67 |  |  | Completed | 1 |  |  |  | 17CM0085 | 2017-10-06 | 2017-10-13 | 2017-10-26 | 2017-11-13 | 2017-11-22 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Olongapo City | 107124 | Olongapo City ES | OLONGAPO CITY | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 12826168.02 |  |  | Completed | 1 |  |  |  | 17CM0105 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | R.J. IBARRA CONSTRUCTION
NC 2017 | K10 | Region III | Olongapo City | 107126 | Gordon Heights I Elementary School | OLONGAPO CITY | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 12896168.02 |  |  | Completed | 1 |  |  |  | 17CM0104 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Olongapo City | 107127 | Gordon Heights II ES | OLONGAPO CITY | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 9985901.76 |  |  | COMPLETED | 1 |  |  |  | 17CM0104 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Olongapo City | 107141 | Tapinac ES | OLONGAPO CITY | 1 | 1 | 6 | 3STY6CL | BATCH 14 | 14829515.1 |  |  | Completed | 1 |  |  |  | 17CM0107 | 2017-11-06 | 2017-11-10 | 2017-11-24 | 2017-12-12 | 2017-12-20 | JAMJLE PROPERTIES AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region III | Pampanga | 105973 | San Pedro ES | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9602124.5 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105986 | Del Carmen ES | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 12465900.96 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 16683237.78 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106005 | Ascomo ES | GUAGUA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9602124.5 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106013 | San Antonio ES | GUAGUA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9602124.5 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106058 | Sta. Cruz CS | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9602124.5 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106295 | Sta. Rita CS | SANTA RITA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 10163317.7 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 300878 | Baruya NHS | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 16749890.6 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300879 | Basa Air Base High School | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300928 | San Roque Dau NHS | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 12189932.71 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300928 | San Roque Dau NHS | LUBAO | 2 |  | 4 | 2STY4CL | BATCH 14 | 12123275.36 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300929 | San Vicente NHS, Lubao | LUBAO | 2 | 1 | 8 | 4STY8CL | BATCH 14 | 27361335.63 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300937 | Sto. Tomas NHS, Sasmuan | SASMUAN (SEXMOAN) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 14816696.75 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300937 | Sto. Tomas NHS, Sasmuan | SASMUAN (SEXMOAN) | 2 |  | 4 | 2STY4CL | BATCH 14 | 14816696.75 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105882 | Camba ES | ARAYAT | 3 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105892 | San Mateo ES | ARAYAT | 3 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300898 | Justino Sevilla High School | ARAYAT | 3 | 1 | 10 | 2STY10CL | BATCH 14 | 19708155.67 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300898 | Justino Sevilla High School | ARAYAT | 3 |  | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300898 | Justino Sevilla High School | ARAYAT | 3 |  | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300905 | Don Jesus Gonzales High School | MEXICO | 3 | 1 | 12 | 4STY12CL | BATCH 14 | 33409789.72 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 300921 | San Juan NHS, Mexico | MEXICO | 3 | 1 | 12 | 4STY12CL | BATCH 14 | 33409789.72 |  |  | Completed | 1
NC 2017 | SHS | Region III | Pampanga | 306901 | San Vicente Pilot School for Philippine Craftsmen | BACOLOR | 3 | 1 | 12 | 4STY12CL | BATCH 14 | 33409789.72 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 105879 | Sucad ES | APALIT | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 8903710.97 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106240 | San Carlos ES | SAN LUIS | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 8706439.51 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106245 | San Luis CS | SAN LUIS | 4 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 106258 | San Jose ES | SAN SIMON | 4 | 1 | 4 | 2STY4CL | BATCH 14 | 8706439.51 |  |  | Completed | 1
NC 2017 | K10 | Region III | Pampanga | 306920 | Macabebe High School | MACABEBE | 4 | 1 | 6 | 2STY6CL | BATCH 14 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Fernando City | 107178 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184150LZ-CW1 | 17CG0361 |  |  |  |  | 2018-12-28 | CEDAR CONSTRUCTION
NC 2017 | K10 | Region III | San Fernando City | 107178 | Baliti IS | CITY OF SAN FERNANDO (Capital) | 3 |  | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184151LZ-CW1 | 17CG0362 |  |  |  |  | 2018-12-28 | CHIRSTIAN IAN CONSTRUCTION CORPORATION
NC 2017 | K10 | Region III | San Fernando City | 107179 | Calulut IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184152LZ-CW1 | 17CG0356 |  |  |  |  | 2018-12-28 | NT TULABUT CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region III | San Fernando City | 107180 | Del Rosario ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184153LZ-CW1 | 17CG0360 |  |  |  |  | 2018-12-28 | GEOHEART CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | San Fernando City | 107181 | Dela Paz Norte ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184154LZ-CW1 | 17CG0364 |  |  |  |  | 2018-12-28 | EL KAPITAN CONSTRUCTION SERVICES
NC 2017 | K10 | Region III | San Fernando City | 107182 | Dolores ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184155LZ-CW1 | 17CG0365 |  |  |  |  | 2018-12-28 | NULAS BUILDERS
NC 2017 | K10 | Region III | San Fernando City | 107184 | Maimpis IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184156LZ-CW1 | 17CG0359 |  |  |  |  | 2018-12-28 | NEW PROFILE CONSTRUCTION CO. INC.
NC 2017 | K10 | Region III | San Fernando City | 107186 | Panipuan ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184157LZ-CW1 | 17CG0363 |  |  |  |  | 2018-12-28 | STO CRISTO CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | San Fernando City | 107187 | Saguin IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184158LZ-CW1 | 17CG0358 |  |  |  |  | 2018-12-28 | STO CRISTO CONSTRUCTION AND TRADING
NC 2017 | K10 | Region III | San Fernando City | 107188 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | 2UNITS 2STY4CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184159Z-CW1 | 17CG0349 |  |  |  |  | 2018-12-28 | MARKNEST CONSTRUCTION AND TRADING | With Approved Buffer Funds 2018
NC 2017 | K10 | Region III | San Fernando City | 107193 | Magliman IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 14 | 14589515.1 |  |  | Completed | 1 |  |  | P00184160LZ-CW1 | 17CG0357 |  |  |  |  | 2018-12-28 | ONE GIGATT CONSTRUCTION CORP.
NC 2017 | SHS | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 20 | 4STY20CL | BATCH 14 | 43168409.74 |  |  | Completed | 1 |  |  | P00184161LZ-CW1 | 17CG0376
NC 2017 | K10 | Region III | San Jose City | 105698 | Kaliwanagan ES | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105700 | Malasin ES | San Jose City East | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105708 | San Agustin ES | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9295901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105712 | Tayabo ES | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9385901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105716 | Abar 1st Elementary School | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9095901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose City | 105730 | Sto. Nino 3rd ES | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9385901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 107160 | S. Palay Proper ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 3STY12CL | BATCH 14 | 31323800 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 107162 | San Martin ES (BBC) | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9856500 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 107164 | Sta. Cruz (BBD) Elementary School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 6 | 2STY6CL | BATCH 14 | 12198800 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 107165 | Tungkong Mangga ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 34190900 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 107165 | Tungkong Mangga ES | CITY OF SAN JOSE DEL MONTE | 0 |  | 12 | 4STY12CL | BATCH 14 | 34190900 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 162507 | Partida ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | 2STY4CL | BATCH 14 | 9825000 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City | 162507 | Partida ES | CITY OF SAN JOSE DEL MONTE | 0 |  | 9 | 3STY9CL | BATCH 14 | 24127000 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | San Jose del Monte City | 301061 | San Jose del Monte Nat'l. Trade School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 33160300 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Jose del Monte City | 301061 | San Jose del Monte Nat'l. Trade School | CITY OF SAN JOSE DEL MONTE | 0 |  | 8 | 4STY8CL | BATCH 14 | 19389300 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Jose del Monte City | 301062 | Sapang Palay National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 20 | 4STY20CL | BATCH 14 | 43422200 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Jose del Monte City | 301062 | Sapang Palay National High School | CITY OF SAN JOSE DEL MONTE | 0 |  | 4 | 2STY4CL | BATCH 14 | 9862850 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Jose del Monte City | 307504 | Graceville NHS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | 4STY8CL | BATCH 14 | 19195300 |  |  | Completed | 1
NC 2017 | SHS | Region III | San Jose del Monte City | 307509 | Sto. Cristo National HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | 4STY8CL | BATCH 14 | 19294200 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City |  | San Manuel HS | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 8 | 4STY8CL | BATCH 14 | 19080000 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City |  | BAGONG BUHAY ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL | BATCH 14 | 34091050 |  |  | Completed | 1
NC 2017 | K10 | Region III | San Jose del Monte City |  | BAGONG BUHAY ES | CITY OF SAN JOSE DEL MONTE | 0 |  | 12 | 4STY12CL | BATCH 14 | 34091050 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106354 | Telbang PS | CAMILING | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10564608.33 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106358 | Bobon 1st- Palimbo Proper ES | CAMILING | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 20046793.04 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106518 | Melecio Manganaan ES | MAYANTOC | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 20184696.83 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106524 | San Jose ES | MAYANTOC | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10256901.29 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106543 | Baquero Norte ES | MONCADA | 1 |  | 6 | 2STY6CL | BATCH 14 | 11656168.64 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106544 | Baquero Sur PS | MONCADA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10602720.3 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106546 | Calapan ES | MONCADA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10359470.3 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106583 | Nagmisaan ES | PANIQUI | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 13614970.33 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106597 | Linao ES | PURA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10481901.29 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106604 | Pura Community School | PURA | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 20046793.04 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac | 106667 | Caanamongan ES | SANTA IGNACIA | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10256901.29 |  |  | Completed | 1
NC 2017 | K10 | Region III | Tarlac |  | Ventinilla HS | PANIQUI | 1 | 1 | 4 | 2STY4CL | BATCH 14 | 10662470.3 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106947 | Laoag ES | SAN MARCELINO | 1 | 1 | 6 | 2STY6CL | BATCH 14 | 11776168.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301035 | Sta. Fe NHS | SAN MARCELINO | 1 | 1 | 8 | 2STY8CL | BATCH 14 | 18764790.26 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 307106 | Jesus F. Magsaysay Technical Vocational High School | CASTILLEJOS | 1 | 1 | 20 | 4STY20CL | BATCH 14 | 44058409.74 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 307119 | Kinabuksan Integrated School | SUBIC | 1 | 1 | 6 | 3STY6CL | BATCH 14 | 14899515.1 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106798 | Bancal ES | BOTOLAN | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106800 | Bihawo Elementary School | Botolan | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106806 | Mambog Elementary School | Botolan | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11782393.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106807 | New Taugtog I ES | BOTOLAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106807 | New Taugtog I ES | BOTOLAN | 2 |  | 4 | 2STY4CL | BATCH 14 | 8945901.76 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106811 | San Isidro ES | BOTOLAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9030051.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106817 | Botolan South Central Elementary School | BOTOLAN | 2 | 1 | 12 | 3STY12CL | BATCH 14 | 29443417.25 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106817 | Botolan South Central Elementary School | Botolan | 2 |  | 12 | 3STY12CL | BATCH 14 | 29443417.25 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106820 | Panan ES | BOTOLAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8966939.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106822 | San Juan Elementary School | BOTOLAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9072126.76 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106822 | San Juan Elementary School | BOTOLAN | 2 |  | 4 | 2STY4CL | BATCH 14 | 9072126.76 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106822 | San Juan Elementary School | BOTOLAN | 2 |  | 8 | 2STY8CL | BATCH 14 | 17101015.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106826 | Cabangan ES | CABANGAN | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11782393.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106828 | Camiing Elementary School | Cabangan | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106839 | Babancal Elementary School | Candelaria | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106840 | Binabalian ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106841 | Candelaria Central School | CANDELARIA | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 12058618.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106841 | Candelaria Central | CANDELARIA | 2 |  | 6 | 2STY6CL | BATCH 14 | 12058618.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106842 | Catol ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106843 | Dampay ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8987976.76 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106844 | Lauis ES | CANDELARIA | 2 | 1 | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106844 | Lauis ES | CANDELARIA | 2 |  | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106845 | Libertador ES | CANDELARIA | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106846 | Malimanga ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106851 | Taposo ES | CANDELARIA | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106873 | Iba Central ES | IBA (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106876 | Lipay-Dingin ES | IBA (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 14 | 13865740.1 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106877 | Little Baguio ES | IBA (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106880 | San Agustin Integrated School | IBA (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9072126.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106882 | Sto. Rosario ES | IBA (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106891 | Inhobol ES | MASINLOC | 2 | 1 | 12 | 3STY12CL | BATCH 14 | 29506529.75 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106897 | Sta. Rita ES | MASINLOC | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9030051.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106898 | Sto. Rosario ES | MASINLOC | 2 | 1 | 16 | 4STY16CL | BATCH 14 | 37015922.96 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106899 | Taltal ES | MASINLOC | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9030051.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106900 | Tapuac ES | MASINLOC | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106904 | Bato ES | PALAUIG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106909 | Emiliano M. Aragon Mem. ES | PALAUIG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11782393.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106918 | Zacarias L. Antiller ES | PALAUIG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11719280.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106919 | San Vicente ES | PALAUIG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11719280.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106921 | Dirita ES | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9030051.76 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106922 | Pundakit ES | SAN ANTONIO | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11865575.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106925 | San Gregorio ES | SAN ANTONIO | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106928 | San Nicolas ES | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9030051.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | ZAMBALES | 106930 | West Dirita Elementary School | San Antonio | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9009014.26 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106933 | Laoag Elementary School | San Felipe | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8985901.76 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 106959 | Alusiis ES | SAN NARCISO | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9088843.71 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106970 | San Narciso Elementary School | SAN NARCISO | 2 |  | 6 | 2STY4CL | BATCH 14 | 9114201.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106980 | Gama Elementary School | Sta. Cruz | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11740318.03 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106983 | Malabago ES | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11845505.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106985 | Pamonoran ES | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9005901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106989 | Bayto ES (Biay ES) | SANTA CRUZ | 2 |  | 6 | 2STY6CL | BATCH 14 | 11782393.02 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 106994 | Lupa ES | SANTA CRUZ | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9005901.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 106997 | Sabang Elementary School | Sta. Cruz | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8987976.76 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 160505 | Anthony Arana Guatlo ES | PALAUIG | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11781425.53 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 281505 | Moraza Elementary School | BOTOLAN | 2 | 1 | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 281505 | Moraza Elementary School | BOTOLAN | 2 |  | 3 | 1STY3CL | BATCH 14 | 3768435.02 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301003 | Acoje NHS | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | BATCH 14 | 11881425.53 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Zambales | 301005 | Bani National High School | MASINLOC | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 31859197.22 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Zambales | 301007 | Coto High School | MASINLOC | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 17284247.76 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301011 | Candelaria School of Fisheries | CANDELARIA | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 31754977.22 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301026 | New Taugtog High School | Botolan | 2 | 1 | 16 | 4STY16CL | BATCH 14 | 37070195.46 |  |  | COMPLETED | 1
NC 2017 | SHS | Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 37058000.46 |  |  | Reverted | 0
NC 2017 | SHS | Region III | Zambales | 301027 | Rofulo M. Landa HS (Salaza NHS) | PALAUIG | 2 |  | 16 | 4STY16CL | BATCH 14 | 37058000.46 |  |  | Completed | 1 | [10 empty] | DPWH reported completed
NC 2017 | SHS | Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 | 1 | 12 | 4STY12CL | BATCH 14 | 37108926.96 |  |  | Reverted | 0
NC 2017 | SHS | Region III | Zambales | 301028 | Locloc National High School | PALAUIG | 2 |  | 16 | 4STY16CL | BATCH 14 | 37108926.96 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301032 | San Miguel National High School | SAN ANTONIO | 2 | 1 | 20 | 4STY20CL | BATCH 14 | 41408409.74 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 301033 | Sta. Cruz National High School | SANTA CRUZ | 2 | 1 | 16 | 4STY16CL | BATCH 14 | 36952812.96 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 307101 | Zambales NHS - Jesus F. Magsaysay HS Annex | IBA (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 16974790.26 |  |  | Completed | 1
NC 2017 | SHS | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 | 1 | 20 | 4STY20CL | BATCH 14 | 41606598.74 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 307116 | Sta. Cruz NHS - Don Marcelo C. Marty HS | SANTA CRUZ | 2 | 1 | 10 | 2STY10CL | BATCH 14 | 19792305.67 |  |  | Completed | 1
NC 2017 | K10 | Region III | Zambales | 307116 | Sta. Cruz NHS - Don Marcelo C. Marty HS | SANTA CRUZ | 2 |  | 10 | 2STY10CL | BATCH 14 | 19560893.17 |  |  | Reverted | 0
NC 2017 | K10 | Region III | Zambales | 307120 | Pamibian IS | CANDELARIA | 2 | 1 | 16 | 4STY16CL | BATCH 14 | 37108926.96 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 307130 | Uacon IS | CANDELARIA | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 17101015.26 |  |  | COMPLETED | 1
NC 2017 | K10 | Region III | Zambales | 307134 | Dojoc Balite IS | BOTOLAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9025731.21 |  |  | Completed | 1
NC 2018 | K10 | Region III | Angeles City | 107059 | Pampang ES | ANGELES CITY | 0 | 1 | 12 | 4STY12CL | BATCH 1 | 31724789.72 |  |  | Completed | 1 |  |  |  | 18CI0099
NC 2018 | SHS | Region III | Angeles City | 500129 | Gov. Rafael L. Lazatin IS | ANGELES CITY | 0 | 1 | 20 | 4STY20CL | BATCH 1 | 41453409 |  |  | Completed | 1 |  |  |  | 18CI0091
NC 2018 | SHS | Region III | Angeles City | 500130 | Northville 15 Integrated school | ANGELES CITY | 0 | 1 | 20 | 4STY20CL | BATCH 1 | 41453409 |  |  | Completed | 1 |  |  |  | 18CI0093
NC 2018 | SHS | Region III | Angeles City | 301043 | Sapang Bato National High School | ANGELES CITY | 0 | 1 | 20 | 4STY20CL | BATCH 1 | 41453409 |  |  | Completed | 1 |  |  |  | 18CI0092
NC 2018 | K10 | Region III | Angeles City | 305554 | Dr. Clemente N. Dayrit St. MHS | Angeles City | 1 | 1 | 12 | 4STY12CL | Batch 3 | 37873000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 104524 | Nonong Sr. ES | SAN LUIS | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 11657000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 300677 | Baler NHS | BALER (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 9070000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 300695 | Umiray NHS | DINGALAN | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 12027000 |  |  | Completed | 1
NC 2018 | SHS | Region III | Aurora | 305191 | Baler Stand Alone | BALER (Capital) | 0 | 1 | 6 | 2STY6CL | BATCH 1 | 13316885 |  |  | Completed | 1
NC 2018 | SHS | Region III | Aurora | 305191 | Baler Stand Alone | BALER (Capital) | 0 |  | 6 | 2STY6CL | BATCH 1 | 13316885 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 104453 | Caragsacan ES | DINGALAN | 0 | 1 | 4 | 2STY4CL | Batch 3 | 9175000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 104455 | Dingalan CS | DINGALAN | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11925000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 104503 | Leon Diaz Sr. ES | MARIA AURORA | 0 | 1 | 6 | 2STY6CL | Batch 3 | 11624000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Aurora | 104419 | Agues ES | CASIGURAN | 0 | 1 | 3 | 1STY3CL | Batch 5 | 5843762.292 |  |  | Completed | 1
NC 2018 | K10 | Region III | Balanga City | 104553 | Bani Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9445901.76 |  |  | Completed | 1 |  |  | 18CB0104 | 18CB0104 | 2018-04-20 | 2018-06-13 | 2018-06-20 | 2018-07-05 | 2018-07-09 | Jepa Const. & Supplies
NC 2018 | SHS | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 30439267.25 |  |  | Completed | 1 |  |  | 18CB0105 | 18CB0105 | 2018-04-20 | 2018-06-13 | 2018-06-20 | 2018-07-05 | 2018-07-09 | RCS Construction
NC 2018 | SHS | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 13909515.1 |  |  | Completed | 1 |  |  | 18CB0106 | 18CB0106 | 2018-04-20 | 2018-06-13 | 2018-06-20 | 2018-07-05 | 2018-07-09 | BPQ Const. & Trading
NC 2018 | SHS | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2 |  | 6 | 3STY6CL | BATCH 1 | 13909515.1 |  |  | Completed | 1 |  |  | 18CB0107 | 18CB0107 | 2018-04-20 | 2018-06-13 | 2018-06-20 | 2018-07-05 | 2018-07-09 | RCS Construction
NC 2018 | SHS | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2 | 1 | 8 | 2STY8CL | Batch 5 | 21343205.73 |  |  | Completed | 1
NC 2018 | TVL | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1 | 1 | 16 | 4STY16CL (8 LAB WS) | BATCH 1 | 40600737.96 |  |  | Completed | 1 |  |  | P00270659LZ-CW1 | 18CA0081
NC 2018 | TVL | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1 |  | 8 | 4STY8CL (2 LAB WS 4CL) | BATCH 1 | 18874570.67 |  |  | Completed | 1 |  |  | P00270660LZ-CW1 | 18CA0082
NC 2018 | SHS | Region III | Bataan | 300704 | J. C. Payumo, Jr. Memo. HS | DINALUPIHAN | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 17959570.67 |  |  | Completed | 1 |  |  | P00270661LZ-CW1 | 18CA0084
NC 2018 | SHS | Region III | Bataan | 300704 | J. C. Payumo, Jr. Memo. HS | DINALUPIHAN | 1 |  | 4 | 2STY4CL | BATCH 1 | 9094101.65 |  |  | Completed | 1 |  |  | P00270662LZ-CW1 | 18CA0085
NC 2018 | SHS | Region III | Bataan | 300708 | Luakan National High School | DINALUPIHAN | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18859570.67 |  |  | Completed | 1 |  |  | P00270663LZ-CW1 | 18CA0083
NC 2018 | SHS | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 40600737.96 |  |  | Completed | 1 |  |  | P00270664LZ-CW1 | 18CA0079
NC 2018 | SHS | Region III | Bataan | 306606 | Orani NHS - Parang-Parang | ORANI | 1 |  | 16 | 4STY16CL | BATCH 1 | 40600737.96 |  |  | Completed | 1 |  |  | P00270665LZ-CW1 | 18CA0080
NC 2018 | K10 | Region III | Bataan | 104638 | Baseco ES | MARIVELES | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12116168.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 104678 | Capunitan ES | ORION | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9345901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 104682 | Orion ES | ORION | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12156168.02 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 300698 | Bagac NHS-Parang | BAGAC | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 18159570.67 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 39410737.96 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 300706 | Lamao NHS | LIMAY | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 19159570.67 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 300707 | Limay NHS | LIMAY | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 38910737.96 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 300716 | P. Roman NHS | PILAR | 2 | 1 | 16 | 2STY8CL | BATCH 1 | 18974790.26 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 306607 | Mariveles NHS Cab. Annex-New Alion | MARIVELES | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17474790.26 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 306610 | Mariveles NHS Cab .Annex-Batangas II | MARIVELES | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 19554790.26 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 306618 | MNHS- Camaya Campus | MARIVELES | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 41908409.74 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bataan | 361011 | Mariveles National Senior High School - Sitio Mabuhay | MARIVELES | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12356168.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 104655 | Nagbalayong ES | MORONG | 1 | 1 | 4 | 2STY4CL | Batch 3 | 13676774.01 |  |  | Completed | 1 |  |  | P00273763LZ-CW1
NC 2018 | K10 | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1 | 1 | 10 | 2STY10CL | Batch 9 Realignment | 27499999.8 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 300697 | B. Camacho NHS | ABUCAY | 1 |  | 12 | 2STY12CL | Batch 9 Realignment | 30990939.58 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 104534 | Kabukiran ES | ABUCAY | 1 | 1 | 8 | 2STY8CL | Batch 5 | 23999999.36 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bataan | 104537 | P. Rubiano ES | ABUCAY | 1 | 1 | 4 | 2STY4CL | Batch 5 | 9959999.41 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104772 | Bambang ES | Bulacan | 1 | 1 | 4 | 2S4CL | BATCH 1 | 12005370.93 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104776 | Marcelo H. Del Pilar Mem. School | Bulacan | 1 | 1 | 4 | 2S4CL | BATCH 1 | 13154784.91 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104789 | Sta. Ana ES | Bulacan | 1 | 1 | 4 | 2S4CL | BATCH 1 | 12577988.17 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104796 | Balite ES | Calumpit | 1 | 1 | 4 | 2S4CL | BATCH 1 | 10961272.05 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104816 | Pungo ES | Calumpit | 1 | 1 | 8 | 2S8CL | BATCH 1 | 20685963.53 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105017 | Dulong Malabon ES | Pulilan | 1 | 1 | 10 | 2S10CL | BATCH 1 | 27604881.07 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105020 | Pulilan CS | Pulilan | 1 | 1 | 8 | 2S8CL | BATCH 1 | 17067503.34 |  |  | Completed | 1
NC 2018 | TVL | Region III | Bulacan | 306713 | Bajet-Castillo HS | Pulilan | 1 | 1 | 16 | 4S16CL(EQUIV TO 4S8LAB) | BATCH 1 | 37533658.13 |  |  | Completed | 1
NC 2018 | TVL | Region III | Bulacan | 306723 | San Miguel-Meysulao HS | Calumpit | 1 | 1 | 16 | 4S16CL(EQUIV TO 4S8LAB) | BATCH 1 | 44319093.12 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104837 | Hangga ES | Hagonoy | 1 | 1 | 6 | 2S6CL | BATCH 1 | 15624514.57 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104848 | Don Miguel ES | Hagonoy | 1 | 1 | 4 | 2S4CL | BATCH 1 | 10423680.68 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104854 | San Nicolas ES | Hagonoy | 1 | 1 | 6 | 2S6CL | BATCH 1 | 15675961.82 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bulacan | 300743 | Iba NHS | Hagonoy | 1 | 1 | 6 | 2S6CL | BATCH 1 | 15696947.26 |  |  | completed | 1
NC 2018 | TVL | Region III | Bulacan | 300745 | San Roque NHS | Paombong | 1 | 1 | 8 | 2S8CL (EQUIV TO 2S4LAB) | BATCH 1 | 27221590.59 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104728 | Balagtas C/S | Balagtas | 2 | 1 | 6 | 2S6CL | BATCH 1 | 21488031.54 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104749 | Tilapayong ES | Baliuag North | 2 | 1 | 4 | 2S4CL | BATCH 1 | 13153781.61 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 104753 | Makinabang ES | Baliuag | 2 | 1 | 12 | 3S12CL | BATCH 1 | 40276267.25 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104756 | San Jose ES | Baliuag South | 2 | 1 | 8 | 2S8CL | BATCH 1 | 21185400 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104786 | Bustos CS | Bustos | 2 | 1 | 4 | 2S4CL | BATCH 1 | 9069120 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104788 | Cambaog ES | Bustos | 2 | 1 | 4 | 2S4CL | BATCH 1 | 11151381.27 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104791 | Liciada ES | Bustos | 2 | 1 | 4 | 2S4CL | BATCH 1 | 9121380 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104792 | Malamig ES | Bustos | 2 | 1 | 6 | 3S6CL | BATCH 1 | 16973962.68 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104823 | Guiguinto CS | Guiguinto | 2 | 1 | 4 | 2S4CL | BATCH 1 | 12071055 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104831 | Tabe ES | Guiguinto | 2 | 1 | 4 | 2S4CL | BATCH 1 | 14773994.4 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104833 | Tuktukan ES | Guiguinto | 2 | 1 | 6 | 2S6CL | BATCH 1 | 25201548.86 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104969 | Bagbaguin Es | Pandi | 2 | 1 | 4 | 2S4CL | BATCH 1 | 9954924.27 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104976 | Mamerto C. Bernardo Memorial Central School | Pandi | 2 | 1 | 8 | 2S8CL | BATCH 1 | 26309684.21 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2018 | K10 | Region III | Bulacan | 104982 | Masuso ES | Pandi | 2 | 1 | 4 | 2S4CL | BATCH 1 | 9954924.27 |  |  | Completed | 1 | [10 empty] | Reported by DPWH
NC 2018 | K10 | Region III | Bulacan | 104892 | Masuso ES | Pandi | 2 | 1 | 4 | 2S4CL | BATCH 1 | 9954924.27 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105009 | Plaridel CS | Plaridel | 2 | 1 | 4 | 2S4CL | BATCH 1 | 8389137 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bulacan | 300721 | Balagtas National Agricultural HS | Balagtas | 2 | 1 | 24 | 4S24CL | BATCH 1 | 62855715 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 300753 | Mariano Ponce NHS | Baliuag | 2 | 1 | 8 | 4S8CL | BATCH 1 | 21704985 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 306705 | Virgen Delas Flores HS | Baliuag | 2 | 1 | 12 | 4S12CL | BATCH 1 | 39898288.67 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104710 | Matias A. Fernando MES (Angat C/S) | Angat | 3 | 1 | 12 | 2units 2STY 6CL | BATCH 1 | 25487578 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104947 | F.V.R. Phase 3 Elementary School | Norzagaray | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 10685640 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104951 | NORTH HILLS VILLAGE ELEMENTARY SACHOOL | Norzagaray | 3 | 1 | 24 | 4STY 24CL | BATCH 1 | 50162201 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region III | Bulacan | 104960 | Luis Gravador Elementary School | Norzagaray | 3 | 1 | 8 | 2STY 8CL | BATCH 1 | 16860442 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 105038 | Mataas na Parang Elementary School | San Ildefonso North | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 10543694 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105075 | Kalayaan ES | Dona Remedios Trinidad | 3 | 1 | 2 | 1STY 2CL | BATCH 1 | 3675839 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105081 | Malinao PS | San Miguel North | 3 | 1 | 4 | 2STY 4CL | BATCH 1 | 10756358 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105095 | Batasan ES | San Miguel South | 3 | 1 | 4 | 2STY 4CL | BATCH 1 | 10827077 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105098 | Don Felix De Leon MS | San Miguel South | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 10969023 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105123 | Pantubig ES | San Rafael | 3 | 1 | 4 | 2STY 4CL | BATCH 1 | 10069490 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105128 | Pulo ES | San Rafael | 3 | 1 | 4 | 2STY 4CL | BATCH 1 | 10756358 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105138 | Tukod ES | San Rafael | 3 | 1 | 4 | 2STY 4CL | BATCH 1 | 10756358 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bulacan | 300730 | Calawitan NHS | San Ildefonso | 3 | 1 | 9 | 3STY 9CL | BATCH 1 | 22193021 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region III | Bulacan | 300762 | FVR National High School | Norzagaray | 3 | 1 | 8 | 4STY 8CL | BATCH 1 | 19036190 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104900 | Abangan Norte ES | Marilao | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10848900 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104907 | Loma de Gato Elementary School | Marilao | 4 | 1 | 16 | 4STY - 16CL | BATCH 1 | 36202814 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 104912 | Sta. Rosa I ES | Marilao | 4 | 1 | 16 | 4STY - 16CL | BATCH 1 | 36179647 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan |  | Patubig Elementary School | Marilao | 4 | 1 | 16 | 4STY - 16CL | BATCH 1 | 36373073.07 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 104965 | Paco ES | Obando | 4 | 1 | 8 | 2STY8CL | BATCH 1 | 22308245 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 105146 | Camangyanan ES | Sta. Maria | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 19303039 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105150 | Garden Village ES | Sta. Maria | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10685640 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bulacan | 300765 | Parada NHS | Sta. Maria | 4 | 1 | 12 | 3STY - 12CL | BATCH 1 | 26993039 |  |  | Completed | 1
NC 2018 | SHS | Region III | Bulacan | 300766 | Prenza NHS | Marilao | 4 | 1 | 12 | 4STY - 12CL | BATCH 1 | 30116193 |  |  | Completed | 1
NC 2018 | K10 | Region III | Bulacan | 105090 | Tartaro ES | SAN MIGUEL | 3 | 1 | 6 | 2STY6CL | Batch 3 | 18860150.88 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 105110 | San Juan ES | SAN MIGUEL | 3 | 1 | 8 | 4STY8CL | Batch 3 | 23447455.4 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 105143 | Buenavista Elementary School | SANTA MARIA | 4 | 1 | 8 | 4STY8CL | Batch 3 | 23125334.37 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 104774 | Gen. Gregorio H. del Pilar ES (for Gen. Gregorio H. Del Pilar HS) | BULACAN | 1 | 1 | 24 | 4STY24CL | Batch 5 | 60479008.26 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 104774 | Gen. Gregorio H. del Pilar ES (for Gen. Gregorio H. Del Pilar HS) | BULACAN | 1 |  | 24 | 4STY24CL | Batch 5 | 60639008.26 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 104774 | Gen. Gregorio H. del Pilar ES (for Gen. Gregorio H. Del Pilar HS) | BULACAN | 1 |  | 12 | 4STY12 | Batch 5 | 40320763.3 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 300775 | Virginia Ramirez-Cruz High School | PANDI | 2 | 1 | 20 | 4STY20CL | Batch 5 | 47985132.38 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 300775 | Virginia Ramirez-Cruz High School | PANDI | 2 |  | 20 | 4STY20CL | Batch 5 | 47985132.38 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 300775 | Virginia Ramirez-Cruz High School | PANDI | 2 |  | 20 | 4STY20CL | Batch 5 | 47985132.38 |  |  | completed | 1
NC 2018 | K10 | Region III | Bulacan | 300775 | Virginia Ramirez-Cruz High School | PANDI | 2 |  | 20 | 4STY20CL | Batch 5 | 47985132.38 |  |  | completed | 1
NC 2018 | K10 | Region III | Cabanatuan City | 107064 | Cabanatuan East CES | CABANATUAN CITY | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12018771.115 |  |  | Completed | 1 |  |  | P00270734LZ-CW1 | 18CF0187 | 2018-04-25 | 2018-05-02 | 2018-05-15 | 2018-05-29 | 2018-06-13 | D.G. SARMENTA CONSTRUCTION
NC 2018 | K10 | Region III | Cabanatuan City | 107064 | Cabanatuan East CES | CABANATUAN CITY | 3 |  | 6 | 2STY6CL | BATCH 1 | 12018771.115 |  |  | Completed | 1 |  |  | P00270735LZ-CW1 | 18CF0188 | 2018-04-25 | 2018-05-02 | 2018-05-15 | 2018-05-29 | 2018-06-13 | D.G. SARMENTA CONSTRUCTION
NC 2018 | K10 | Region III | Cabanatuan City | 107067 | J.P. Melencio Memorial Elementary School | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9025901.76 |  |  | Completed | 1 |  |  | P00270736LZ-CW1 | 18CF0198 | 2018-04-26 | 2018-05-03 | 2018-05-17 | 2018-05-29 | 2018-06-13 | IJK MAE CONSTRUCTION
NC 2018 | K10 | Region III | Cabanatuan City | 107069 | Mabini Homesite ES | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9025901.76 |  |  | Completed | 1 |  |  | P00270737LZ-CW1 | 18CF0199 | 2018-04-26 | 2018-05-03 | 2018-05-17 | 2018-05-29 | 2018-06-13 | FASTBUILT CONSTRUCTION INC.
NC 2018 | K10 | Region III | Cabanatuan City | 107099 | Calikid Norte ES | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270738LZ-CW1 | 18CF0197 | 2018-04-26 | 2018-05-03 | 2018-05-17 | 2018-05-29 | 2018-06-13 | FASTBUILT CONSTRUCTION INC.
NC 2018 | K10 | Region III | Cabanatuan City | 107112 | Lazaro Francisco Elementary School | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9272285.18 |  |  | Completed | 1 |  |  | P00270739LZ-CW1 | 18CF0203 | 2018-04-26 | 2018-05-03 | 2018-05-17 | 2018-05-29 | 2018-06-13 | IJK MAE CONSTRUCTION
NC 2018 | K10 | Region III | Cabanatuan City | 107103 | L.O. Francisco ES | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9272285.18 |  |  | Completed | 1 |  |  | P00270740LZ-CW1 | 18CF0204 | 2018-04-26 | 2018-05-03 | 2018-05-17 | 2018-05-29 | 2018-06-13 | CELCO C. FERRER CONSTRUCTION
NC 2018 | K10 | Region III | Gapan City | 105319 | Gapan North C/S | CITY OF GAPAN | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 19247363.47 |  |  | Completed | 1 |  |  | 900270741LZ | 18CF0180 | 2018-04-20 | 2018-04-27 | 2018-05-10 |  | 2018-06-19 | FORTHRIGHT CONSTRUCTION
NC 2018 | K10 | Region III | Gapan City | 105320 | Kapalangan ES | CITY OF GAPAN | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11816244.01 |  |  | Completed | 1 |  |  | P00270742LZ | 18CF0186 | 2018-04-25 | 2018-05-02 | 2018-05-15 |  | 2018-06-27 | FORTHRIGHT CONSTRUCTION
NC 2018 | K10 | Region III | Gapan City | 105335 | Malimba ES | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9101316.64 |  |  | Completed | 1 |  |  | P00270743LZ | 18CF0201 | 2018-04-26 | 2018-05-03 | 2018-05-17 |  | 2018-06-27 | FORTHRIGHT CONSTRUCTION
NC 2018 | K10 | Region III | Gapan City | 105341 | San Roque ES | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9190601.84 |  |  | Completed | 1 |  |  | P20070745LZ | 18CF0202 | 2018-04-26 | 2018-05-03 | 2018-05-17 |  | 2018-06-19
NC 2018 | K10 | Region III | Gapan City | 105344 | Sto. Cristo Sur ES | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9072180.68 |  |  | Completed | 1 |  |  | 18CF0200 | 18CF0200 | 2018-04-26 | 2018-05-03 | 2018-05-17 |  | 2018-06-19
NC 2018 | TVL | Region III | Gapan City | 300812 | Juan R. Liwag Mem. NHS | CITY OF GAPAN | 4 | 1 | 4 | 2STY4WS | BATCH 1 | 17788702.76 |  |  | Completed | 1 |  |  | P00270746LZ | 18CF0194 | 2018-04-25 | 2018-05-02 | 2018-05-15 |  | 2018-06-27 | FORTHRIGHT CONSTRUCTION
NC 2018 | TVL | Region III | Gapan City | 300813 | Sta. Cruz NHS | CITY OF GAPAN | 4 | 1 | 4 | 2STY4WS | BATCH 1 | 17868702.76 |  |  | Completed | 1 |  |  | P00270747LZ | 18CF0193 | 2018-04-25 | 2018-05-02 | 2018-05-15 |  | 2018-06-27 | FORTHRIGHT CONSTRUCTION
NC 2018 | TVL | Region III | Gapan City | 300829 | Pambuan HS | CITY OF GAPAN | 4 |  | 4 | 2STY4WS | BATCH 1 | 17868702.76 |  |  | Completed | 1 |  |  | 18CF0206 | 18CF0206 | 2018-05-29 | 2018-06-05 | 2018-06-19 |  |  | 816 ALLEN CONSTRUCTION
NC 2018 | SHS | Region III | Gapan City | 300829 | Pambuan HS | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | 18CF0194 | 18CF0194 | 2018-04-26 | 2018-05-03 | 2018-05-17 |  | 2018-06-27 | FORTHRIGHT CONSTRUCTION
NC 2018 | K10 | Region III | Gapan City | 500728 | Gapan East C/S | CITY OF GAPAN | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11897159.09 |  |  | Completed | 1 |  |  | P00270250LZ | 18CF0185 | 2018-04-25 | 2018-05-02 | 2018-05-15 |  | 2018-06-19 | R.A. PAHATI Construction and Supply
NC 2018 | K10 | Region III | Mabalacat City | 106065 | Haduan Negrito ES | MABALACAT CITY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 12674261.76 |  |  | Completed | 1 |  |  |  | 18CI0107 |  |  | 2018-07-25 | 2018-08-13 | 2018-09-03 | CDCC CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region III | Mabalacat City | 106088 | Talimundok ES | MABALACAT CITY | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 41408401 |  |  | Completed | 1 |  |  |  | 18CI0094 |  |  | 2018-05-24 | 2018-06-13 | 2018-06-25 | E.M.L. CONSTRUCTION AND TRADING
NC 2018 | K10 | Region III | Mabalacat City | 106089 | Villa Teodora ES | MABALACAT CITY | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 31799789.72 |  |  | Completed | 1 |  |  |  | 18CI0100 |  |  | 2018-06-06 | 2018-06-28 | 2018-07-10 | B.P. CRUZ BUILDERS AND TRADING
NC 2018 | K10 | Region III | Mabalacat City | 159505 | Marcos Village ES | MABALACAT CITY | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17119790.26 |  |  | completed | 1 |  |  |  | 18CI0102 |  |  | 2018-06-11 | 2018-06-11 | 2018-07-16 | AL-B DEVELOPMENT CORPORATION
NC 2018 | K10 | Region III | Mabalacat City | 106073 | Bical ES | MABALACAT CITY | 1 | 1 | 16 | 4STY16CL | Batch 3 | 38913402.54 |  |  | Completed | 1
NC 2018 | K10 | Region III | Mabalacat City | 106086 | San Francisco ES | MABALACAT CITY | 1 | 1 | 24 | 4STY24CL | Batch 5 | 48184340.48 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 240003 | Cofradia Elementary School | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 2STY4CL | BATCH 1 | 9509855.69 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 104863 | Barasoain Memo. ES | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 18932170.13 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 104870 | Ligas Elementary School | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26038602.99 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 104879 | Stma. Trinidad ES | CITY OF MALOLOS (Capital) | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 35971560.15 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 104871 | Longos ES | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL | Batch 3 | 29075958.73 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City | 240007 | Longos II Elementary School | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 21003906.84 |  |  | Completed | 1
NC 2018 | K10 | Region III | Malolos City |  | BARASOIN MEM ES- ANNEX | CITY OF MALOLOS (Capital) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 22754015.72 |  |  | Completed | 1
NC 2018 | K10 | Region III | Meycauayan City | 104938 | Zamora Elementary School | CITY OF MEYCAUAYAN | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 12579495 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region III | Munoz Science City | 105535 | Bantug ES | Munoz | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12554672.38 |  |  | Completed | 1
NC 2018 | K10 | Region III | Munoz Science City | 105552 | Munoz CS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12765621.91 |  |  | Completed | 1
NC 2018 | TVL | Region III | Munoz Science City | 300824 | Munoz National HS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 6 | 3STY6WS | Batch 3 | 31029459.54 |  |  | completed | 1
NC 2018 | TVL | Region III | Nueva Ecija | 300804 | Eduardo L. Joson Mem. HS | QUEZON | 1 | 1 | 8 | 4STY8WS | BATCH 1 | 42934289.61 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105304 | Camatchile ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105474 | San Juan ES | LAUR | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12437260.2 |  |  | Completed | 1 |  |  | P00270762LZ | 18CF0191 | [5 empty] | double Alpha Construction & Developent Corp.
NC 2018 | K10 | Region III | Nueva Ecija | 105589 | Palayan City CS | PALAYAN CITY (Capital) | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12270869.5 |  |  | Completed | 1 |  |  | P00270763LZ | 18CF0190 | [5 empty] | double Alpha Construction & Developent Corp.
NC 2018 | SHS | Region III | Nueva Ecija | 300826 | Nueva Ecija NHS | CABANATUAN CITY | 3 | 1 | 24 | 4STY24CL | BATCH 1 | 54571000 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105669 | Papaya ES | SAN ANTONIO | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 9394687.19 |  |  | Completed | 1 |  |  | P00270765LZ | 18CF0205
NC 2018 | K10 | Region III | Nueva Ecija | 105670 | San Antonio CS | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  | P00270765LZ | 18CF0181
NC 2018 | K10 | Region III | Nueva Ecija | 105676 | STO. CRISTO EAST ES | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11776226.16 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105677 | Sto. Cristo West ES | SAN ANTONIO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11776226.16 |  |  | Completed | 1 |  |  | P00270768 | 18CF0184 | [5 empty] | E.V. Inerior Construction
NC 2018 | K10 | Region III | Nueva Ecija | 105686 | Pulo Elementary School | SAN ISIDRO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  | P00270769LZ | 18CF0182
NC 2018 | TVL | Region III | Nueva Ecija | 300792 | Cabiao National High School | CABIAO | 4 | 1 | 8 | 4STY8WS | BATCH 1 | 42934289.61 |  |  | Completed | 1 |  |  | P00270770LZ | 18CF0180
NC 2018 | SHS | Region III | Nueva Ecija | 300856 | Sta. Rita NHS | CABIAO | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 12098094.03 |  |  | Completed | 1 |  |  | P00270771LZ | 18CF0189 | [5 empty] | Forthright Construction
NC 2018 | K10 | Region III | Nueva Ecija | 105173 | Bibiclat ES | ALIAGA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105183 | San Eustacio Elementary School | ALIAGA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12121891.31 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105191 | Sto. Tomas ES | ALIAGA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 14811647.85 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105256 | Bambanaba ES | CUYAPO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105259 | Bonifacio ES | CUYAPO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105260 | Bued PS | CUYAPO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105408 | Banitan ES | GUIMBA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11567595.69 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105487 | Tabing Ilog Elemetary School | LICAB | 1 | 1 | 4 | 2STY4CL | Batch 3 | 12347584.83 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105768 | Baloc ES | SANTO DOMINGO | 1 | 1 | 8 | 2STY8CL | Batch 3 | 18938821.56 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105771 | Cabugao ES | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL | Batch 3 | 13171471.39 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105799 | Matingkis ES | TALAVERA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105803 | San Pascual ES | TALAVERA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105810 | Bantug ES | TALAVERA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11506397.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105811 | Bantug Hacienda ES | TALAVERA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11506397.02 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105814 | Caputican ES | TALAVERA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 13190626.29 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105830 | San Ricardo ES | TALAVERA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105853 | Batitang ES | ZARAGOZA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 15488718.18 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105866 | Zaragoza CS | ZARAGOZA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11506397.02 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 159006 | Pulong Buli ES | SANTO DOMINGO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11667595.69 |  |  | completed | 1
NC 2018 | TVL | Region III | Nueva Ecija | 300783 | Aliaga National NHS | ALIAGA | 1 | 1 | 4 | 2STY4WS | Batch 3 | 22343774.94 |  |  | completed | 1
NC 2018 | SHS | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9762281.39 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija |  | Brgy. Tutuloy ES | CUYAPO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija |  | Cacapasan ES | CUYAPO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105237 | Binbin ES | CARRANGLAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 13190626.29 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105247 | Red Cross Village Elementary School | Carranglan | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9841216.91 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105251 | Puncan ES | CARRANGLAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10290650.57 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105497 | General Luna ES | LLANERA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105503 | Mabini ES | LLANERA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9762281.38 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105504 | Murcon ES | LLANERA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9762281.39 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105509 | San Vicente ES | LLANERA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9841216.91 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105510 | Sta. Barbara Integrated School(Elementary) | LLANERA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11667595.69 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105530 | San Pedro ES | Lupao | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105607 | Sampaloc ES | PANTABANGAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9792605.4 |  |  | Completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105650 | Paco Roman ES | RIZAL | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | SHS | Region III | Nueva Ecija | 306830 | Cambitala NHS | PANTABANGAN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 18514074.65 |  |  | completed | 1
NC 2018 | SHS | Region III | Nueva Ecija | 306832 | Conversion IS | PANTABANGAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 13111200 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9393076.36 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105359 | Apolinario Santiago ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | 3STY6CL | Batch 3 | 15593634.7 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105460 | Betania ES | LAUR | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9115620.4 |  |  | completed | 1
NC 2018 | K10 | Region III | Nueva Ecija | 105736 | C.I. Villaroman ES | SAN LEONARDO | 4 | 1 | 6 | 2STY6CL | Batch 3 | 12789002.71 |  |  | completed | 1
NC 2018 | SHS | Region III | Olongapo City | 301057 | New Cabalan NHS | OLONGAPO CITY | 1 | 1 | 8 | 2units 2STY4CL | BATCH 1 | 20131803.52 |  |  | Completed | 1 | [10 empty] | DPWH Reported Completed
NC 2018 | K10 | Region III | Olongapo City | 107139 | Kalalake ES | Olongapo City | 1 | 1 | 8 | 2STY8CL | Batch 3 | 22585654.3 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106128 | San Francisco ES | MAGALANG | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 300876 | Andres M. Luciano HS | MAGALANG | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105972 | San Nicolas ES | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-03 | 2018-08-16 | 2018-08-17
NC 2018 | K10 | Region III | Pampanga | 105974 | San Roque Elementary School | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-03 | 2018-08-16 | 2018-08-17
NC 2018 | K10 | Region III | Pampanga | 105977 | Valdez ES | FLORIDABLANCA | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-03 | 2018-08-02 | 2018-08-03
NC 2018 | K10 | Region III | Pampanga | 106233 | Sapang Uwak ES | PORAC | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2663745.92 |  |  | Completed | 1 |  |  |  |  | 2018-07-17 |  | 2018-08-08 | 2018-09-03 | 2018-09-05
NC 2018 | SHS | Region III | Pampanga | 300886 | Del Carmen National High School | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-08 | 2018-08-09 | 2018-08-10
NC 2018 | SHS | Region III | Pampanga | 300925 | San Pablo 2nd National High School | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-03 | 2018-08-09 | 2018-08-10
NC 2018 | K10 | Region III | Pampanga | 306904 | Wenceslao Village HS | Lubao | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-08-07 | 2018-09-03 | 2018-09-05
NC 2018 | SHS | Region III | Pampanga | 306912 | Sta. Cruz High Integrated School | LUBAO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  |  |  | 2018-06-07 |  | 2018-07-03 | 2018-08-16 | 2018-08-17
NC 2018 | K10 | Region III | Pampanga | 306953 | San Roque Arbol High School | LUBAO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  |  | 2018-07-17 |  | 2018-08-07 | 2018-09-03 | 2018-09-05
NC 2018 | K10 | Region III | Pampanga |  | Santiago HS | Lubao | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1 |  |  |  |  | 2018-07-17 |  | 2018-08-07 | 2018-09-03 | 2018-09-05
NC 2018 | K10 | Region III | Pampanga | 105891 | San Juan Bano ES | ARAYAT | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105897 | Anderson ES | ARAYAT | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105903 | Cacutud ES | ARAYAT | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105928 | Tinajero ES | BACOLOR | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106182 | Divisoria ES | MEXICO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106183 | Dolores ES (Piring ES) | MEXICO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106188 | Pandacaqaui ES | MEXICO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | SHS | Region III | Pampanga | 306908 | Diosdado Macapagal HS | MEXICO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 306921 | Gatiawin HS | ARAYAT | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga |  | Tinajero HS | BACOLOR | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105868 | Banag Elementary School | APALIT | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105869 | Cansinala ES | APALIT | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105876 | SAMPALOC ELEMENTARY SCHOOL | APALIT | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105942 | Pangclara ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105944 | Pulong Palazan ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105946 | Tagulod ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105947 | Talang ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105950 | Vizal San Pablo I ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105954 | Candaba ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105956 | Lanang ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105959 | Paralaya ES | CANDABA | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105962 | Sto. Rosario ES | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106238 | Don Emigdio Bondoc ES | SAN LUIS | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106243 | San Jose Proper ES | SAN LUIS | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106246 | San Nicolas ES | SAN LUIS | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106248 | Sta. Catalina ES | SAN LUIS | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106256 | San Agustin ES | SAN SIMON | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106266 | Sto. Nino ES | SAN SIMON | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 306951 | Pulong Gubat High School | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 306952 | Lanang High School | CANDABA | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga |  | Capalangan Elementary School | APALIT | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106139 | Sto. Nino ES | MAGALANG | 1 | 1 | 4 | 2STY4CL | Batch 3 | 8945901.76 |  |  | Completed | 1
NC 2018 | SHS | Region III | Pampanga | 300907 | Porac Model Community HS | Porac | 2 | 1 | 12 | 4STY12CL | Batch 3 | 34407194.27 |  |  | Completed | 1
NC 2018 | SHS | Region III | Pampanga | 306912 | Sta. Cruz HS | Lubao | 2 | 1 | 12 | 4STY12CL | Batch 3 | 34407194.27 |  |  | completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region III | Pampanga |  | Nabuklod HS | Floridablanca | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12475409.62 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 105900 | Baliti ES | ARAYAT | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12155860.18 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105902 | Buensuceso ES | ARAYAT | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12155860.18 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106162 | Acli ES | Mexico | 3 | 1 | 4 | 2STY4CL | Batch 3 | 9903915.17 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106179 | Sto. Rosario ES | MEXICO | 3 | 1 | 6 | 2STY6CL | Batch 3 | 12155860.18 |  |  | Completed | 1
NC 2018 | SHS | Region III | Pampanga | 300932 | Sta Ana HS | Sta Ana | 3 | 1 | 8 | 2STY8CL | Batch 3 | 18203689.73 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 105951 | Vizal Sto. Cristo ES | CANDABA | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11083848.29 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106090 | Batasan ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106091 | Caduang Tete ES | MACABEBE | 4 | 1 | 8 | 2STY8CL | Batch 5 | 19305688.78 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106092 | Candelaria ES | MACABEBE | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106093 | Macabebe Central ES | MACABEBE | 4 | 1 | 24 | 3UNITS 4STY8CL | Batch 5 | 61343571.84 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106094 | San Gabriel ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106096 | San Roque ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106097 | San Vicente Ferrer ES | MACABEBE | 4 | 1 | 6 | 3STY6CL | Batch 5 | 16199178.05 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106098 | San Vicente San Francisco ES | MACABEBE | 4 | 1 | 10 | 2STY10CL | Batch 5 | 23724534.05 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106099 | Saplad David ES | MACABEBE | 4 | 1 | 10 | 2STY10CL | Batch 5 | 23508295.99 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106100 | Sta. Rita ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106101 | Tacasan ES | MACABEBE | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14521174.84 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106102 | Telacsan Elementary | MACABEBE | 4 | 1 | 6 | 3STY6CL | Batch 5 | 15898007.21 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106103 | Castuli ES | MACABEBE | 4 | 1 | 4 | 2UNITS 1STY2CL | Batch 5 | 6288338.5 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106104 | Concuelo ES | MACABEBE | 4 | 1 | 2 | 1STY2CL | Batch 5 | 2989725.33 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106106 | Dalayap ES | MACABEBE | 4 | 1 | 6 | 3STY6CL | Batch 5 | 16298007.21 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106107 | Lolu ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11578329.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106109 | San Jose ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106110 | San Juan ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106111 | San Rafael ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11578329.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106112 | Sapang Malalam ES | MACABEBE | 4 | 1 | 4 | 1STY4CL | Batch 5 | 5755423.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106113 | Sta. Lutgarda ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11578329.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106114 | Sta. Maria CS | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106115 | Sto. Nino ES | MACABEBE | 4 | 1 | 2 | 1STY2CL | Batch 5 | 2927438.77 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106116 | Sto. Rosario Elementary School | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 159519 | Sitio Mindanao ES | MACABEBE | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300883 | Caduang Tete HS | Macabebe | 4 | 1 | 16 | 4STY16CL | Batch 5 | 35651601.43 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300915 | San Esteban HS | Macabebe | 4 | 1 | 2 | 1STY2CL | Batch 5 | 3144169.25 |  |  | Completed | 1
NC 2018 | SHS | Region III | Pampanga | 300930 | San Vicente-San Francisco NHS | MACABEBE | 4 | 1 | 10 | 2STY10CL | Batch 5 | 23724534.05 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300934 | Sta. Maria NHS, Macabebe | MACABEBE | 4 | 1 | 12 | 4STY12CL | Batch 5 | 34642740.3 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300941 | Telacsan NHS | MACABEBE | 4 | 1 | 8 | 4STY8CL | Batch 5 | 19968765.48 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 306920 | Macabebe HS | Macabebe | 4 | 1 | 27 | 3UNITS 3STY9CL | Batch 5 | 86500061.34 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 306937 | Dalayap HS | Macabebe | 4 | 1 | 2 | 1STY2CL | Batch 5 | 3144169.25 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga |  | Consuelo HS | MACABEBE | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14521174.84 |  |  | Completed | 1
NC 2018 | K10 | Region III | Pampanga | 106143 | Alauli ES | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106144 | Bagang ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11578329.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106145 | Balibago ES | MASANTOL | 4 | 1 | 12 | 2STY12CL | Batch 5 | 28210100 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106146 | Bebe Anac ES | MASANTOL | 4 | 1 | 15 | 3STY15CL | Batch 5 | 36157430.43 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106147 | Bebe Matua ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106148 | Bulacus ES | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14236331.18 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106149 | Caingin ES | MASANTOL | 4 | 1 | 12 | 2UNITS 2STY 6CL | Batch 5 | 27929731.36 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106151 | Malauli ES | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14249709.33 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106152 | Masantol Central ES | MASANTOL | 4 | 1 | 12 | 2UNITS 2STY 6CL | Batch 5 | 27929731.36 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106153 | Nigui ES | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106154 | Palimpe ES | MASANTOL | 4 | 1 | 10 | 2STY6CL & 2STY4CL | Batch 5 | 25814660.22 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106155 | Puti ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11394779.63 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106156 | San Isidro Matua ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106158 | Sapang Kawayan ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106160 | Sta. Lucia Matua ES | MASANTOL | 4 | 1 | 20 | 2UNITS 2STY 6CL & 2UNITS 2STY 4CL | Batch 5 | 51721449 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106161 | Sua ES | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 159530 | Sta. Cruz E/S (Annex) | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 159531 | Sagrada Familia ES | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 159541 | San Pedro PS | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14249709.33 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 306906 | Sagrada HS (Tarik Suliman HS) | Masantol | 4 | 1 | 12 | 3STY12CL | Batch 5 | 31864168.77 |  |  | Reverted | 0 | [10 empty] | soil boring test failed
NC 2018 | SHS | Region III | Pampanga | 306923 | Sapang Kawayan High School | MASANTOL | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11794564.59 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 306926 | Malauli HS | Masantol | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106202 | Lourdes ES | MINALIN | 4 | 1 | 12 | 2STY12CL | Batch 5 | 27113900 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106204 | Sto. Rosario ES (MINALIN ES) | MINALIN | 4 | 1 | 6 | 2STY6CL | Batch 5 | 14249709.33 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106205 | San Francisco ES | MINALIN | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11394779.63 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106206 | San Isidro ES | MINALIN | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106207 | San Pedro ES | MINALIN | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106209 | Sta. Maria ES | MINALIN | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11611015.17 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4 | 1 | 8 | 2STY8CL | Batch 5 | 19305688.78 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106211 | Sto. Domingo ES | MINALIN | 4 | 1 | 10 | 2STY10CL | Batch 5 | 23724534.05 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300935 | Sta. Maria HS | Minalin | 4 | 1 | 20 | 4STY20CL | Batch 5 | 45093902.59 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300936 | Sto. Rosarion HS | Minalin | 4 | 1 | 6 | 2STY6CL | Batch 5 | 13964865.68 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 306939 | Bulac HS | Minalin | 4 | 1 | 4 | 2STY4CL | Batch 5 | 11578329.04 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 306946 | Conrado P. Mapinlac Sr. HS | Minalin | 4 | 1 | 9 | 3STY9CL | Batch 5 | 28535690.49 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106299 | San Bartolome ES | SANTO TOMAS | 4 | 1 | 12 | 3STY12CL | Batch 5 | 33790101.94 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106300 | San Matias ES | SANTO TOMAS | 4 | 1 | 12 | 3STY12CL | Batch 5 | 33790101.94 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106301 | San Vicente ES | SANTO TOMAS | 4 | 1 | 9 | 3STY9CL | Batch 5 | 28535690.49 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106302 | Sapa ES | SANTO TOMAS | 4 | 1 | 9 | 3STY9CL | Batch 5 | 28535690.49 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga | 106303 | Sto. Rosarion Pau ES | SANTO TOMAS | 4 | 1 | 9 | 3STY9CL | Batch 5 | 28322498.19 |  |  | completed | 1
NC 2018 | SHS | Region III | Pampanga | 300924 | San Matias NHS | SANTO TOMAS | 4 | 1 | 30 | 3UNITS 4STY8CL & 2STY6CL | Batch 5 | 73871162.12 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga |  | Poblacion ES | SANTO TOMAS | 4 | 1 | 8 | 2STY8CL | Batch 5 | 18264796.15 |  |  | completed | 1
NC 2018 | K10 | Region III | Pampanga |  | Poblacion HS | SANTO TOMAS | 4 | 1 | 12 | 3STY12CL | Batch 5 | 33790101.94 |  |  | completed | 1
NC 2018 | K10 | Region III | San Fernando City | 107169 | Del Carmen IS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270816LZ | 18CG0158 |  |  |  |  | 2018-06-19 | St. Loiue Prime Bldrs. & Devt. Corp.
NC 2018 | K10 | Region III | San Fernando City | 107175 | San Jose-Juliana ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270817LZ | 18CG0174 |  |  |  |  | 2018-06-19 | R.G. Diaz Builders & Trading
NC 2018 | K10 | Region III | San Fernando City | 107177 | Alasas ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270818LZ | 18CG0175 |  |  |  |  | 2018-06-19 | R.G. Diaz Builders & Trading
NC 2018 | K10 | Region III | San Fernando City | 107192 | Malpitic ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270819LZ | 18CG0159 |  |  |  |  | 2018-06-19 | Geoheart Const. & Trdg.
NC 2018 | SHS | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 15 | 3STY15CL | BATCH 1 | 33656939.69 |  |  | Completed | 1 |  |  | P00270820LZ | 18CG0179 |  |  |  |  | 2018-06-19 | Sto Cristo Const. & Trdg
NC 2018 | SHS | Region III | San Fernando City | 307601 | Information and Communication Technology High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18919570.67 |  |  | completed | 1 |  |  | P00270821LZ | 18CG0178 |  |  |  |  | 2018-06-19 | Nes-san Builders
NC 2018 | K10 | Region III | San Fernando City | 307613 | Telabastagan Integrated HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00270822LZ | 18CG0160 |  |  |  |  | 2018-06-19 | Carl Josh Builders
NC 2018 | K10 | Region III | San Fernando City | 307615 | Calulut Int. HS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 18919570.67 |  |  | Completed | 1 |  |  | P00270823LZ | 18CG0177 |  |  |  |  | 2018-06-19 | B-12 Const. & Trdg. Corp
NC 2018 | K10 | Region III | San Fernando City |  | San Fernando ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13739515.1 |  |  | Completed | 1 |  |  | P00270824LZ | 18CG0246 |  |  |  |  | 2018-07-02 | R.G. Diaz Builders & Trading
NC 2018 | SHS | Region III | San Fernando City |  | City of San Fernando Tech Voc SHS | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | Completed | 1 |  |  | P00270825LZ | 18CG0261 |  |  |  |  | 2018-07-02 | N.T. Tulabut Const. & Supply
NC 2018 | K10 | Region III | San Jose City | 105707 | Porais ES | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9671309.43 |  |  | Completed | 1
NC 2018 | K10 | Region III | San Jose City | 105709 | San Jose East CS | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 9762281.39 |  |  | Completed | 1
NC 2018 | K10 | Region III | San Jose City | 105716 | Abar 1st ES | San Jose City | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12554672.38 |  |  | Completed | 1
NC 2018 | K10 | Region III | San Jose City | 105725 | San Jose West Central School | San Jose City | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12554672.38 |  |  | Completed | 1
NC 2018 | K10 | Region III | San Jose del Monte City | 107143 | Bagong Buhay B ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 20 | 4STY20CL | Batch 3 | 44456228.64 |  |  | completed | 1
NC 2018 | K10 | Region III | San Jose del Monte City | 107144 | Bagong Buhay E ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45855018.79 |  |  | completed | 1
NC 2018 | K10 | Region III | San Jose del Monte City | 107146 | Bagong Buhay G ES | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 20 | 4STY20CL | Batch 3 | 45855018.79 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106333 | Pindangan First ES | CAMILING | 1 | 1 | 3 | 1STY3CL | BATCH 1 | 3993435.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106351 | Sinilian II ES | CAMILING | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9865460.2 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106521 | Pitombayog ES | MAYANTOC | 1 | 1 | 3 | 1STY3CL W/ CR | BATCH 1 | 3993435.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106528 | Calamay ES | MONCADA | 1 | 1 | 4 | 1STY4CL | BATCH 1 | 5113351.15 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106536 | San Roque PS | MONCADA | 1 | 1 | 3 | 1STY 3CL W/ CR | BATCH 1 | 4069909.82 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106548 | Camposanto ES | MONCADA | 1 | 1 | 4 | 2STY4CL | BATCH 6 Realignment | 11627027.6 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106586 | Patalan ES | PANIQUI | 1 | 1 | 3 | 1STY3CL W/ CR | BATCH 1 | 4009435.02 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106598 | Maasin Elementary School | PURA | 1 | 1 | 2 | 1STY2CL W/ CR | BATCH 1 | 2744433.22 |  |  | Completed | 1
NC 2018 | SHS | Region III | Tarlac | 300958 | Camiling School of Home Industries | CAMILING | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9865460.2 |  |  | Completed | 1
NC 2018 | TVL | Region III | Tarlac | 300997 | Tarlac National High School - Annex | CITY OF TARLAC (Capital) | 1 | 1 | 1 | 1 UNIQUE WORKSHOP | BATCH 1 | 2798530 |  |  | Completed | 1
NC 2018 | TVL | Region III | Tarlac | 300998 | Eduardo Cojuangco National Vocational High School | PANIQUI | 1 | 1 | 1 | 1STY UWS | BATCH 1 | 2798530 |  |  | Completed | 1
NC 2018 | TVL | Region III | Tarlac | 307011 | Moncada National High School | MONCADA | 1 | 1 | 1 | 1 UW | BATCH 1 | 2798530 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106323 | San Nicolas ES | BAMBAN | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9545901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106370 | Capas East Central | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12064922.99 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106371 | Capas Gabaldon ES | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11694403.94 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106373 | Dolores ES | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11759736.24 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106383 | Capas West Central | CAPAS | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16988600.65 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106384 | Lawy ES | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11759736.24 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106390 | Sta. Lucia ES | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12064922.99 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106392 | Cristo Rey East ES | CAPAS | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11791425.87 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106392 | Cristo Rey East ES | CAPAS | 3 |  | 6 | 2STY6CL | BATCH 1 | 11597382.27 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106404 | Concepcion North CS | CONCEPCION | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106414 | Sta. Rosa IS | CONCEPCION | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8998009.37 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106436 | San Antonio ES | CONCEPCION | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 11898034.04 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106500 | Dumarais ES | LA PAZ | 3 | 1 | 8 | 2STY8CL | BATCH 1 | 16988600.65 |  |  | Completed | 1
NC 2018 | SHS | Region III | Tarlac | 300976 | Cristo Rey HS (ORES) | CAPAS | 3 | 1 | 9 | 3STY9CL | BATCH 1 | 24774381.81 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300993 | Sta. Lucia NHS | CAPAS | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9050128.23 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106526 | Aringin Elemenary School | MONCADA | 1 | 1 | 8 | 2STY8CL | Batch 3 | 19577691.38 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106550 | Moncada South CS | MONCADA | 1 | 1 | 6 | 2STY6CL | Batch 3 | 15298659.18 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300946 | Anao NHS | ANAO | 1 | 1 | 16 | 4STY16CL | Batch 3 | 42018504.82 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300948 | Balaoang NHS | PANIQUI | 1 | 1 | 12 | 3STY12CL | Batch 3 | 33346000 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106459 | Sulipa ES | GERONA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 14361126.91 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106465 | Bularit ES | GERONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12553505.43 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106470 | Mabini ES | GERONA | 2 | 1 | 8 | 2STY8CL | Batch 3 | 21737175.84 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106484 | Santiago ES | GERONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11918610.85 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106628 | Catigaacan ES | SAN JOSE | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11230207.78 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106784 | Balayang Elementary School | VICTORIA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12847486.72 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106791 | Lalapac ES | VICTORIA | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12627048.27 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300954 | Buenlag NHS | GERONA | 2 | 1 | 6 | 3STY6CL | Batch 3 | 15773169.1 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300959 | Cardona NHS | GERONA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 36817861.74 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300965 | Gerona Western Public High School | GERONA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20846909.66 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300981 | Quezon NHS | GERONA | 2 | 1 | 8 | 2STY8CL | Batch 3 | 23362100.04 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300986 | San Jose NHS | GERONA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20929015.63 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 300995 | Tagumbao NHS | GERONA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21059270.05 |  |  | completed | 1
NC 2018 | TVL | Region III | Tarlac | 300996 | Tarlac National HS | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 4STY8CL (4WS) | Batch 3 | 18452560.48 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac | 106310 | Anupul ES | BAMBAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10756021.92 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106315 | Dapdap Resettlement ES | Bamban | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13650484.41 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 229503 | Concepcion Special Education Center | CONCEPCION | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13145937.87 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac | 106443 | Abagon ES | GERONA | 2 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED | Batch 5 | 4106421.04 |  |  | Completed | 1
NC 2018 | SHS | Region III | Tarlac | 307007 | Corazon C. Aquino High School | GERONA | 2 | 1 | 16 | 4STY16CL | Batch 5 | 54908638.91 |  |  | completed | 1
NC 2018 | SHS | Region III | Tarlac | 307007 | Corazon C. Aquino High School | GERONA | 2 |  | 20 | 4STY20CL | Batch 5 | 60483534.42 |  |  | completed | 1
NC 2018 | K10 | Region III | Tarlac City | 106736 | Camp Aquino ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12245753.92 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac City | 106764 | San Jose de Urquico ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10884093.17 |  |  | Completed | 1
NC 2018 | SHS | Region III | Tarlac City | 300970 | Maliwalo NHS | CITY OF TARLAC (Capital) | 2 | 1 | 36 | 4STY36CL | Batch 3 | 111125729.64 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac City | 500556 | BUROT INTEGRATED SCHOOL | CITY OF TARLAC (Capital) | 2 | 1 | 12 | 4STY12CL | Batch 3 | 35751889.73 |  |  | Completed | 1
NC 2018 | K10 | Region III | Tarlac City | 106746 | San Miguel CS | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 5 | 21059270.05 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106934 | Maloma Community ES | SAN FELIPE | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9055682.26 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106975 | Babuyan ES | SANTA CRUZ | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.03 |  |  | Completed | 1
NC 2018 | SHS | Region III | Zambales | 307131 | Lakas High School | BOTOLAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11802708.03 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 307122 | San Rafael High School | SAN MARCELINO | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 10045901.76 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106859 | Looc Elementary School | CASTILLEJOS | 1 | 1 | 6 | 2STY6CL | Batch 3 | 16722690.48 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106955 | San Marcelino Elementary School | SAN MARCELINO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 15435747.55 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 107018 | San Isidro Elementary School | SUBIC | 1 | 1 | 10 | 2STY10CL | Batch 3 | 26598115.14 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 107020 | Subic Central School | SUBIC | 1 | 1 | 10 | 2STY10CL | Batch 3 | 26348439.92 |  |  | Completed | 1 | [10 empty] | DPWH Reported Completed
NC 2018 | K10 | Region III | Zambales | 500128 | Hanjin Integrated School | CASTILLEJOS | 1 | 1 | 8 | 4STY8CL | Batch 3 | 20362772.13 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 500510 | Naugsol Integrated School | SUBIC | 1 | 1 | 8 | 4STY8CL | Batch 3 | 20636474.99 |  |  | Completed | 1 | [10 empty] | DPWH Reported Completed
NC 2018 | K10 | Region III | Zambales | 106893 | Masinloc Central Elementary School | MASINLOC | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17034790.26 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106964 | La Paz Elementary School | SAN NARCISO | 2 | 1 | 6 | 2STY6CL | Batch 3 | 11859343.03 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106979 | Don Marcelo C. Marty Elementary School | SANTA CRUZ | 2 | 1 | 10 | 2STY10CL | Batch 3 | 19942965.67 |  |  | Completed | 1
NC 2018 | SHS | Region III | Zambales | 301010 | Cabangan National High School | CABANGAN | 2 | 1 | 20 | 4STY20CL | Batch 3 | 41618219.74 |  |  | Completed | 1
NC 2018 | SHS | Region III | Zambales | 301025 | Botolan National High School | BOTOLAN | 2 | 1 | 20 | 4STY20CL | Batch 3 | 42189284.74 |  |  | Completed | 1
NC 2018 | SHS | Region III | Zambales | 301037 | Zambales National High School | IBA (Capital) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20362772.13 |  |  | Completed | 1
NC 2018 | K10 | Region III | Zambales | 106856 | Castillejos Elementary School | CASTILLEJOS | 1 | 1 | 10 | 2STY10CL | Batch 5 | 20035282.31 |  |  | Completed | 1 | [10 empty] | DPWH Reported Completed
NC 2018 | K10 | Region III | Zambales | 106857 | Del Pilar Elementary School | CASTILLEJOS | 1 | 1 | 6 | 2STY6CL | Batch 5 | 11930580 |  |  | Completed | 1
NC 2019 | K10 | Region III | Angeles City | 107035 | Salapungan ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL |  | 11408450 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Angeles City | 107056 | Leoncia Village ES | ANGELES CITY | 1 | 1 | 4 | 2STY4CL |  | 11278125 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Angeles City | 107052 | Apung Guidang Nepomuceno Elementary School | ANGELES CITY | 1 | 1 | 4 | 2STY4CL |  | 11408450 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY | 1 | 1 | 16 | 4STY16CL |  | 37243614.8049 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Angeles City | 107031 | Jose P. Dizon ES | Angeles City | 1 | 1 | 16 | 4STY16CL |  | 41966940.1711 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 104415 | Reserva ES | BALER (Capital) | 0 | 1 | 16 | 2UNITS 2STY8CL |  | 39380767.8737 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 104479 | Puangi ES | DIPACULAO | 0 | 1 | 3 | 1STY3CL |  | 5276161.2293 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 305397 | Mijares National High School | DIPACULAO | 0 | 1 | 6 | 2STY6CL |  | 20683422.828 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 104412 | Diego T. Ortiz ES | Baler | 0 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 157516 | Diamanen PS | Dipaculao | 0 | 1 | 2 | 1STY2CL |  | 4895701.3716 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Aurora | 104463 | Bayabas ES | DIPACULAO | 0 | 1 | 3 | 1STY3CL |  | 5276161.2293 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | BALANGA CITY | 104552 | Balanga Elementary School | Balanga City | 2 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | compLeted | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104603 | Tucop ES | DINALUPIHAN | 1 | 1 | 6 | 2STY6CL |  | 16560095.396 |  | compLeted | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104539 | T. Pinpin MES | ABUCAY | 1 | 1 | 10 | 2STY10CL |  | 27568749.1779 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104600 | Sta. Isabel ES | DINALUPIHAN | 1 | 1 | 4 | 2STY4CL |  | 16103622.5999 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104538 | Salian ES | ABUCAY | 1 | 1 | 10 | 2STY10CL |  | 27568749.1779 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104610 | Hermosa ES | HERMOSA | 1 | 1 | 6 | 2STY6CL |  | 19492200.0677 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104576 | Happy Valley ES | DINALUPIHAN | 1 | 1 | 4 | 2STY4CL |  | 15642467.7778 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104702 | F.C. Del Rosario ES | SAMAL | 1 | 1 | 4 | 2STY4CL |  | 15423968.6823 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104575 | Dinalupihan ES | DINALUPIHAN | 1 | 1 | 8 | 2UNITS 2STY4CL |  | 27752809.5514 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104573 | Daang Bago ES | DINALUPIHAN | 1 | 1 | 4 | 2STY4CL |  | 16054978.7635 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104531 | Bangkal ES | ABUCAY | 1 | 1 | 4 | 2STY4CL |  | 15423968.6823 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104531 | Bangkal ES | ABUCAY | 1 |  | 4 | 2STY4CL |  | 15642467.7778 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Bataan | 300701 | Balsik NHS | HERMOSA | 1 | 1 | 6 | 2STY6CL |  | 19492200.0677 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104687 | Sto. Domingo ES | ORION | 2 | 1 | 8 | 2STY8CL |  | 20852000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 300700 | Saysain NHS | BAGAC | 2 | 1 | 6 | 2STY6CL |  | 17875114.9064 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Bataan | 306618 | Mariveles NHS - Camaya Campus | MARIVELES | 2 | 1 | 20 | 4STY20CL |  | 47217750 |  | completed | 1 | [10 empty] | With approved additional funds; reported completed based on DPWH Letter dated Oct 14, 2022 Subject: Joint Special Task Force | 0
NC 2019 | K10 | Region III | Bataan | 104631 | Lamao ES | LIMAY | 2 | 1 | 4 | 2STY4CL |  | 10726750 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bataan | 104643 | Ipag ES | MARIVELES | 2 | 1 | 8 | 2STY8CL |  | 20852000 |  | completed | 1 | [10 empty] | With approved additional funds; reported completed based on DPWH Letter dated Oct 14, 2022 Subject: Joint Special Task Force | 0
NC 2019 | K10 | Region III | Bataan | 104636 | Alasasin ES | MARIVELES | 2 | 1 | 6 | 2STY6CL |  | 15238000 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Bulacan | 300776 | Sta. Cruz NHS | PAOMBONG | 1 | 1 | 4 | 1STY4CL |  | 7077921.6775 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Bulacan | 300754 | Ramona S. Trillana HS (Mayor Ramon Trillana Mem. HS (Iba NHS)) | HAGONOY | 1 | 1 | 12 | 4STY12CL |  | 41966940.1711 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104825 | Malis ES | GUIGUINTO | 2 | 1 | 20 | 4STY20CL |  | 55217179.6022 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104959 | T.P. Policarpio ES (Minuyan ES) | NORZAGARAY | 3 | 1 | 10 | 2STY10CL |  | 27748075.9569 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3 | 1 | 8 | 2STY8CL |  | 21968818.8043 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104726 | Sulucan ES | ANGAT | 3 |  | 6 | 2STY6CL |  | 16974423.8741 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105087 | Sibul Elementary School | SAN MIGUEL | 3 | 1 | 6 | 2STY6CL |  | 18949613.6243 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105099 | Dr. Juan F. Pascual MS (formerly Silangan ES) | SAN MIGUEL | 3 | 1 | 8 | 2STY8CL |  | 24551364.3976 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 158502 | San Vicente ES | SAN MIGUEL | 3 | 1 | 9 | 3STY9CL |  | 30349438.9063 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL | 3 | 1 | 20 | 4STY20CL |  | 63323606.8917 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104957 | San Mateo Elementary School | NORZAGARAY | 3 | 1 | 8 | 2STY8CL |  | 20315938.1274 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 3 | 1 | 10 | 2STY10CL |  | 27088174.5775 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104950 | Matictic Elementary School | NORZAGARAY | 3 | 1 | 4 | 2STY4CL |  | 10416182.5877 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105055 | Malipampang ES | SAN ILDEFONSO | 3 | 1 | 9 | 3STY9CL |  | 26024144.5962 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105120 | Maguinao Elementary School | SAN RAFAEL | 3 | 1 | 12 | 4STY12CL |  | 33955115.4584 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105036 | Lapnit Elementary School | SAN ILDEFONSO | 3 | 1 | 4 | 2STY4CL |  | 11553268.6939 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105115 | Caingin ES | SAN RAFAEL | 3 | 1 | 10 | 2STY10CL |  | 27229215.4605 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 104966 | Panghulo Elementary School | OBANDO | 4 | 1 | 6 | 3STY6CL |  | 23523321.5798 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105153 | Kaylawig ES | SANTA MARIA | 4 | 1 | 8 | 4STY8CL |  | 23131517.7528 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Bulacan | 105147 | Cay Pombo ES | SANTA MARIA | 4 | 1 | 15 | 3STY15CL |  | 37857022.5601 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Cabanatuan City | 107115 | San Josef ES | Cabanatuan City | 3 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4 | 1 | 4 | 2STY4CL |  | 8968266.5144 |  | Completed | 1 | [11 empty] | 0
NC 2019 | TVL | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4 |  | 4 | 4STY8WS |  | 39937576.1029 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Gapan City | 105339 | San Nicolas Central School | CITY OF GAPAN | 4 | 1 | 8 | 2STY8CL |  | 21654000 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Gapan City | 105325 | Mahipon ES | Gapan City | 4 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Gapan City | 105334 | Gapan South CS | CITY OF GAPAN | 4 | 1 | 12 | 3STY12CL |  | 28571250 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Mabalacat City | 300900 | Mauaque HS (Res) | MABALACAT CITY | 1 | 1 | 16 | 4STY16CL |  | 37003014.8049 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Mabalacat City | 106079 | Gasdam ES | MABALACAT CITY | 1 | 1 | 8 | 4STY8CL |  | 20462528.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Mabalacat City | 106063 | Calapi Negrito ES | MABALACAT CITY | 1 | 1 | 4 | 2STY4CL |  | 12472607.5795 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Malolos City | 104877 | Santor ES | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | 2STY4CL |  | 12472607.5795 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Meycauayan City | 265001 | Caingin Bayanihan ES | CITY OF MEYCAUAYAN | 4 | 1 | 8 | 4STY8CL |  | 20298212.6843 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Munoz Science City | 105561 | Sapang Cawayan ES | SCIENCE CITY OF MUÑOZ | 2 | 1 | 3 | 1STY3CL |  | 5695613.0538 |  | COmpleted | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Munoz Science City | 500395 | Gabaldon IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 3 | 1STY3CL |  | 5695613.0538 |  | COmpleted | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Nueva Ecija | 300860 | Vicente R. Bumanlag, Sr. National HS | ALIAGA | 1 | 1 | 15 | 3STY15CL |  | 41015159.2928 |  | COmpleted | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105807 | Talavera North Elementary School | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Nueva Ecija | 300864 | TALAVERA NATIONAL HIGH SCHOOL | TALAVERA | 1 | 1 | 20 | 4STY20CL |  | 44303156.9782 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105806 | Talavera CS | TALAVERA | 1 | 1 | 20 | 4STY20CL |  | 47655164.2386 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105829 | San Miguel Na Munti ES | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Nueva Ecija | 306807 | San Carlos High School | ALIAGA | 1 | 1 | 12 | 4STY12CL |  | 36017544.4027 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105181 | San Carlos ES | ALIAGA | 1 | 1 | 12 | 3STY12CL |  | 33508110.2923 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105828 | PULA ES | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105827 | Paludpod ES | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105823 | LA TORRE ES | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105813 | CABUBULAUNAN ELEMENTARY SCHOOL | TALAVERA | 1 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105792 | Bakal III ES | TALAVERA | 1 | 1 | 15 | 3STY15CL |  | 38782535.0613 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105523 | NAMULANDAYAN ES | LUPAO | 2 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105502 | LLANERA CS | LLANERA | 2 | 1 | 6 | 2STY6CL |  | 17905789.7924 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105519 | BURGOS ES | LUPAO | 2 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105765 | SANTA ROSA CENTRAL SCHOOL | STA. ROSA | 3 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105687 | SAN ISIDRO CS | SAN ISIDRO | 4 | 1 | 4 | 2STY4CL |  | 14502998.6189 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Nueva Ecija | 105588 | PALALE ES | GEN. TINIO | 4 | 1 | 6 | 2STY6CL |  | 17905789.7924 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Olongapo City | 107118 | BANGAL ES | Olongapo City | 1 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 106123 | Magalang CS | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 106117 | Ayala ES | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 11278125 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 106122 | Escaler ES | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 11408450 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 106135 | San Vicente ES | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 11278125 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 106050 | Remedios Elementary School | LUBAO | 2 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga | 102292 | Francisco Henson Elementary School | PORAC | 2 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Pampanga |  | San Juan Bano HS | ARAYAT | 3 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Pampanga | 300896 | Malino NHS | MEXICO | 3 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | San Fernando City | 107198 | San Pedro ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL |  | 8968266.5144 |  | Completed | 1 | [10 empty] | compleed as per contract | 0
NC 2019 | K10 | Region III | San Fernando City | 500978 | Pulung Bulu ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL |  | 8968266.5144 |  | Completed | 1 | [10 empty] | compleed as per contract | 0
NC 2019 | K10 | Region III | San Fernando City | 107167 | Bulaon ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | San Jose City | 105725 | San Jose West Central School | SAN JOSE CITY | 2 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | San Jose del Monte City | 301062 | SAPANG PALAY NHS | San Jose del Monte City | 0 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | San Jose del Monte City | 107145 | BAGONG BUHAY F ES | San Jose del Monte City | 0 | 1 | 12 | 4STY12CL |  | 32653646.4899 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 305562 | San Manuel National High School | SAN MANUEL | 1 | 1 | 16 | 4STY16CL |  | 50514232.4746 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106611 | SAN JUAN ES | RAMOS | 1 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106548 | CAMPOSANTO ES | MONCADA | 1 | 1 | 6 | 2STY6CL |  | 17875114.9064 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106575 | BRILLANTE ES | PANIQUI | 1 | 1 | 4 | 2STY4CL |  | 12222713.7028 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Tarlac | 301000 | Victoria National High School | VICTORIA | 2 | 1 | 32 | 2UNITS 4STY16CL |  | 105486115.2641 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106647 | Sula ES | SAN JOSE | 2 | 1 | 4 | 2STY4CL |  | 13186902.634 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 4882388.1917 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106642 | Pisapungan ES | SAN JOSE | 2 |  | 6 | 2STY6CL |  | 18604294.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106793 | Palacpalac ES | VICTORIA | 2 | 1 | 2 | 1STY2CL W/TOILET |  | 4381118.8133 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | Region III | Tarlac | 106640 | Moriones ES | SAN JOSE | 2 | 1 | 1 | 1 UNIQUE WORKSHOP |  | 3054354.3538 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106633 | Labney ES | SAN JOSE | 2 | 1 | 6 | 2STY6CL |  | 16931222.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106451 | Gerona North CES | GERONA | 2 | 1 | 18 | 2STY18CL L-TYPE SCHOOL BLDG. |  | 56282867.3276 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106631 | E.V.A. Abelling PS | SAN JOSE | 2 | 1 | 6 | 2STY6CL |  | 17875114.9064 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106775 | Bangar Elementary | VICTORIA | 2 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106324 | San Pedro ES | BAMBAN | 3 | 1 | 4 | 2STY4CL |  | 10808983.6815 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106411 | SAN JOSE ES | CONCEPCION | 3 | 1 | 10 | 2STY10CL |  | 26571116.7465 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106432 | Ligaya ES | CONCEPCION | 3 | 1 | 2 | 1STY2CL W/ TOILET ATTACHED |  | 4999651.9199 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106315 | Dapdap Resettlement ES | BAMBAN | 3 | 1 | 8 | 2STY8CL |  | 21382823.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 | 1 | 4 | 2STY4CL |  | 10840341.9718 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 |  | 6 | 2STY6CL |  | 13842988.2577 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106388 | Cristo Rey Central E/S | CAPAS | 3 |  | 8 | 2STY8CL |  | 20162722.0925 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106421 | Concepcion South ES | CONCEPCION | 3 | 1 | 6 | 2STY6CL |  | 14155226.1659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac | 106419 | Balutu ES | CONCEPCION | 3 | 1 | 4 | 2STY4CL |  | 11172148.6799 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region III | Tarlac | 500124 | Aranguren Integrated School | CAPAS | 3 | 1 | 12 | 4STY12CL |  | 41072853.8595 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106722 | Sinait ES | Tarlac City | 2 | 1 | 6 | 2STY6CL |  | 14951254.7045 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106695 | San Sebastian ES | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 2STY8CL |  | 19055159.491 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106706 | San Pascual ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2STY4CL |  | 11213725.1619 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106694 | San Nicolas ES | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 4STY8CL |  | 18611233.7743 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106702 | Maliwalo Central ES | CITY OF TARLAC (Capital) | 2 | 1 | 20 | 4STY20CL |  | 51654096.7388 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Tarlac City | 106698 | Balingcanaway Centro ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2STY4CL |  | 11988052.2722 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Zambales | 106858 | KANAYNAYAN COMMUNITY SCHOOL | CASTILLEJOS | 1 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Zambales | 160512 | Mapalad Elementary School | STA CRUZ | 2 | 1 | 2 | 1STY2CL |  | 3797075.3659 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Zambales | 106934 | Maloma Community Elementary School | SAN FELIPE | 2 | 1 | 6 | 2STY6CL |  | 17875114.9064 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region III | Zambales | 101782 | Alao Elementary School | BOTOLAN | 2 | 1 | 3 | 1STY3CL |  | 5695613.0538 |  | completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region III | Angeles City | 107041 | Gueco Balibago ES | Angeles City | 1 | 1 | 12 | 4STY12CL |  | 36793823.84 |  |  | completed | 1
NC 2020 | K10 | Region III | Angeles City | 107057 | Lourdes Northwest ES | ANGELES CITY | 1 | 1 | 24 | 4STY24CL |  | 60250250 |  |  | completed | 1
NC 2020 | K10 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY | 1 | 1 | 20 | 4STY20CL |  | 48621250 |  |  | completed | 1
NC 2020 | K10 | Region III | Aurora | 104511 | Villa Aurora ES | Maria Aurora | 0 | 1 | 4 | 2UNITS 1STY2CL |  | 7619000 |  |  | completed | 1
NC 2020 | SHS | Region III | Balanga City | 300702 | Bataan National High School | CITY OF BALANGA (Capital) | 2 | 1 | 20 | 4STY20CL |  | 61734052.95 |  |  | completed | 1
NC 2020 | SHS | Region III | Balanga City | 322901 | City of Balanga National High School | CITY OF BALANGA (Capital) | 2 | 1 | 6 | 3STY6CL |  | 19769670.03 |  |  | completed | 1
NC 2020 | K10 | Region III | Balanga City | 305619 | Balanga City National Science High School | CITY OF BALANGA (Capital) | 2 | 1 | 8 | 2STY8CL |  | 22524990.05 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104571 | Bayan-Bayanan ES | DINALUPIHAN | 1 | 1 | 4 | 2STY4CL |  | 15599810.63 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104579 | Layac ES | DINALUPIHAN | 1 | 1 | 8 | 2STY8CL |  | 28050088.59 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104668 | Paraiso ES | ORANI | 1 | 1 | 6 | 2STY6CL |  | 22556248.31 |  |  | Completed | 1
NC 2020 | SHS | Region III | Bataan | 300714 | Nagbalayong NHS | MORONG | 1 | 1 | 16 | 4STY16CL |  | 56841750 |  |  | Completed | 1
NC 2020 | K10 | Region III | Bataan | 104674 | Bantan ES | ORION | 2 | 1 | 4 | 2STY4CL |  | 14522677.81 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104675 | Bilolo ES | ORION | 2 | 1 | 10 | 2STY10CL |  | 32611509.11 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104678 | Capunitan ES | ORION | 2 | 1 | 4 | 2STY4CL |  | 14773292.79 |  |  | completed | 1
NC 2020 | K10 | Region III | Bataan | 104685 | Sabatan ES | ORION | 2 | 1 | 4 | 2STY4CL |  | 14121677.81 |  |  | completed | 1
NC 2020 | SHS | Region III | Bataan | 300712 | Mariveles NHS Malaya | MARIVELES | 2 | 1 | 4 | 2STY4CL |  | 15153959.1 |  |  | completed | 1
NC 2020 | SHS | Region III | Bataan | 361011 | Mariveles SHS - Sitio Mabuhay | MARIVELES | 2 | 1 | 4 | 2STY4CL |  | 14602517.09 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104813 | Meyto Elementary School | CALUMPIT | 1 | 1 | 4 | 2STY4CL |  | 17978742.05 |  |  | Completed | 1
NC 2020 | K10 | Region III | Bulacan | 104945 | Cabayunan Elementary School | DOÑA REMEDIOS TRINIDAD | 1 | 1 | 4 | 1STY4CL |  | 8789662.34 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104730 | Borol 2nd Elementary School | BALAGTAS (BIGAA) | 2 | 1 | 4 | 2STY4CL |  | 17099890.68 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104762 | Batia ES | BOCAUE | 2 | 1 | 6 | 3STY6CL |  | 24166957.52 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104768 | Lolomboy ES | BOCAUE | 2 | 1 | 6 | 2STY6CL |  | 22556250 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104823 | Guiguinto Central School | GUIGUINTO | 2 | 1 | 6 | 2STY6CL |  | 23587038.7 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104980 | Mapulang lupa ES | PANDI | 2 | 1 | 12 | 4STY12CL |  | 52744745.97 |  |  | completed | 1
NC 2020 | SHS | Region III | Bulacan | 300746 | Lolomboy National NHS | BOCAUE | 2 | 1 | 8 | 4STY8CL |  | 34343384.86 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 3 | 1 | 10 | 2STY10CL |  | 30050602.34 |  |  | Completed | 1
NC 2020 | K10 | Region III | Bulacan | 104727 | A. S. De Guzman ES (Taboc ES) | ANGAT | 3 | 1 | 8 | 2STY8CL |  | 22616140.73 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104939 | Apugan ES | NORZAGARAY | 3 | 1 | 8 | 2STY8CL |  | 24551379.7 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104947 | FVR Phase 3 Elementary School | NORZAGARAY | 3 | 1 | 8 | 4STY8CL |  | 30050602.34 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY | 3 | 1 | 10 | 2STY10CL |  | 30050602.34 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 105072 | Camachin ES | DOÑA REMEDIOS TRINIDAD | 3 | 1 | 6 | 2STY6CL |  | 21795596.58 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 105080 | Maligaya ES | SAN MIGUEL | 3 | 1 | 4 | 2STY4CL |  | 12064074.6 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 105122 | Paco Elementary School | SAN RAFAEL | 3 | 1 | 6 | 2STY6CL |  | 24880514.21 |  |  | completed | 1
NC 2020 | SHS | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | 8 | 4STY8CL |  | 22556250 |  |  | completed | 1
NC 2020 | K10 | Region III | Bulacan | 104914 | Tabing Ilog ES | MARILAO | 4 | 1 | 8 | 4STY8CL |  | 25141315.4 |  |  | completed | 1
NC 2020 | K10 | Region III | CABANATUAN CITY | 500561 | Daan Sarile Integrated School | CABANATUAN CITY | 3 | 1 | 4 | 2STY4CL |  | 12283407.4 |  |  | completed | 1
NC 2020 | K10 | Region III | City of San Fernando | 501141 | Malino Integrated School | City of San Fernando | 3 | 1 | 6 | 3STY6CL |  | 16840002.23 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Gapan City | 105330 | Sta. Cruz ES | Gapan City | 4 | 1 | 4 | 2STY4CL |  | 8822000 |  |  | Completed | 1
NC 2020 | K10 | Region III | Malolos City | 104866 | Bungahan Elementary School | CITY OF MALOLOS (Capital) | 1 | 1 | 12 | 3STY12CL |  | 37437759.42 |  |  | Completed | 1
NC 2020 | K10 | Region III | Malolos City | 104871 | Longos ES | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL |  | 29845684.21 |  |  | Completed | 1
NC 2020 | K10 | Region III | Malolos City | 104882 | Tikay ES | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL |  | 30015663.49 |  |  | Completed | 1
NC 2020 | SHS | Region III | Malolos City | 323601 | Bulihan NHS | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL |  | 33089763.02 |  |  | Completed | 1
NC 2020 | SHS | Region III | Malolos City | 323605 | Pres. Corazon Cojuangco-Aquino MNHS | CITY OF MALOLOS (Capital) | 1 | 1 | 9 | 3STY9CL |  | 29740746.24 |  |  | Completed | 1
NC 2020 | K10 | Region III | Munoz Science City | 500397 | Maragol IS | SCIENCE CITY OF MUÑOZ | 2 | 1 | 2 | 1STY2CL |  | 3709250 |  |  | completed | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105175 | Don Emiliano Soriano ES | ALIAGA | 1 | 1 | 6 | 2STY6CL |  | 19047500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105269 | Cuyapo CS | CUYAPO | 1 | 1 | 15 | 3STY15CL |  | 41102500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105272 | Doroteo R. Jose Elementary School | CUYAPO | 1 | 1 | 6 | 2STY6CL |  | 19047500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105378 | Cabaruan ES | GUIMBA | 1 | 1 | 4 | 2STY4CL |  | 14536250 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105415 | Guimba West CS | GUIMBA | 1 | 1 | 8 | 2STY8CL |  | 23057500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105774 | Concepcion ES | SANTO DOMINGO | 1 | 1 | 6 | 2STY6CL |  | 19047500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105815 | Collado ES | TALAVERA | 1 | 1 | 6 | 2STY6CL |  | 19047500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105820 | Homestead I ES | TALAVERA | 1 | 1 | 6 | 2STY6CL |  | 21052500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105825 | Mamandil PS | TALAVERA | 1 | 1 | 6 | 2STY6CL |  | 19047500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105826 | Minabuyok ES | TALAVERA | 1 | 1 | 8 | 2STY8CL |  | 23057500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105240 | Camanggahan ES | CARRANGLAN | 2 | 1 | 2 | 1STY2CL |  | 3709250 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105513 | Agupalo Weste ES | LUPAO | 2 | 1 | 4 | 2STY4CL |  | 14247630.99 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105526 | Salvacion 2nd ES | LUPAO | 2 | 1 | 2 | 1STY2CL |  | 3709250 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105302 | Bugnan ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 4 | 2STY4CL |  | 12283407.4 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 501168 | Virginia D. Dulay Integrated School | GEN. MAMERTO NATIVIDAD | 3 | 1 | 4 | 2STY4CL |  | 12283407.4 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4 | 1 | 4 | 2STY4CL |  | 8822000 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105438 | Jaen West Elementary School | JAEN | 4 | 1 | 8 | 2STY8CL |  | 23057500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105457 | Sto. Tomas North ES | JAEN | 4 | 1 | 8 | 2STY8CL |  | 23057500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105689 | Sto. Cristo ES | SAN ISIDRO | 4 | 1 | 4 | 2STY4CL |  | 8822000 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105740 | San Anton ES | SAN LEONARDO | 4 | 1 | 8 | 2STY8CL |  | 23057500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Nueva Ecija | 105744 | Tambo North E/S | SAN LEONARDO | 4 | 1 | 4 | 2STY4CL |  | 8822000 |  |  | COMPLETED | 1
NC 2020 | K10 | Region III | Pampanga | 106123 | Magalang CS | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 12932250 |  |  | completed | 1
NC 2020 | SHS | Region III | Pampanga | 300875 | Balitucan National High School | MAGALANG | 1 | 1 | 4 | 2STY4CL |  | 12932250 |  |  | completed | 1
NC 2020 | SHS | Region III | Pampanga | 300920 | San Jose High School | FLORIDABLANCA | 2 | 1 | 12 | 4STY12CL |  | 38095000 |  |  | completed | 1
NC 2020 | K10 | Region III | Pampanga | 106198 | Sta. Maria ES | MEXICO | 3 | 1 | 6 | 2STY6CL |  | 14536250 |  |  | Completed | 1
NC 2020 | SHS | Region III | Pampanga | 301065 | Potrero NHS | BACOLOR | 3 | 1 | 4 | 2STY4CL |  | 13478597.53 |  |  | completed | 1
NC 2020 | K10 | Region III | Pampanga | 305740 | San Juan Bano High School | ARAYAT | 3 | 1 | 4 | 2STY4CL |  | 12932250 |  |  | Completed | 1
NC 2020 | K10 | Region III | Pampanga | 105878 | Sto. Rosario ES | APALIT | 4 | 1 | 3 | 1STY3CL |  | 5814500 |  |  | completed | 1
NC 2020 | K10 | Region III | Pampanga | 105940 | MAPANIQUI ELEMENTARY | CANDABA | 4 | 1 | 8 | 2STY8CL |  | 25554389.84 |  |  | completed | 1
NC 2020 | K10 | Region III | Pampanga | 106263 | San Simon Elementary School | SAN SIMON | 4 | 1 | 8 | 2STY8CL |  | 22761710.88 |  |  | completed | 1
NC 2020 | K10 | Region III | San Jose del Monte City | 107150 | Paradise Farms Community School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 12 | 4STY12CL |  | 40098984.38 |  |  | Completed | 1
NC 2020 | SHS | Region III | Munoz Science City | 322801 | Munoz National High School (Annex) | Science City of Munoz | 2 | 1 | 4 | 2STY4CL |  | 12431502.6 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106347 | Marawi ES | Camiling | 1 | 1 | 8 | 2STY8CL |  | 25441577.73 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106548 | Camposanto ES | MONCADA | 1 | 1 | 4 | 1STY4CL |  | 9717124.49 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106576 | Burgos ES | PANIQUI | 1 | 1 | 3 | 1STY3CL |  | 5850827.01 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106617 | Cat-Nag ES | SAN CLEMENTE | 1 | 1 | 4 | 1STY4CL WITH CR |  | 4858561.99 |  |  | completed | 1
NC 2020 | SHS | Region III | Tarlac | 300952 | Bilad High School | CAMILING | 1 | 1 | 8 | 2STY8CL |  | 24449405.99 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106452 | Magaspac ES | Gerona | 2 | 1 | 9 | 3STY9CL |  | 28322604.74 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106730 | Sulipa ES | Gerona | 2 | 1 | 4 | 2STY4CL |  | 13915922.07 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106404 | Concepcion North CES | Concepcion | 3 | 1 | 10 | 2STY10CL |  | 23636118.77 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac | 106498 | Caut ES | LA PAZ | 3 | 1 | 6 | 2STY6CL |  | 14727508.31 |  |  | completed | 1
NC 2020 | SHS | Region III | Tarlac | 500124 | Aranguren Integrated School | CAPAS | 3 | 1 | 10 | 2STY10CL |  | 24089406.06 |  |  | completed | 1
NC 2020 | K10 | Region III | Tarlac City | 106767 | San Vicente ES Main | CITY OF TARLAC (Capital) | 2 | 1 | 4 | 2STY4CL |  | 12719758.5 |  |  | Completed | 1
NC 2020 | SHS | Region III | Tarlac City | 321402 | Baras Baras HS | CITY OF TARLAC (Capital) | 2 | 1 | 8 | 4STY8CL |  | 26373770 |  |  | Completed | 1
NC 2020 | K10 | Region III | Zambales | 160513 | Josephine F. Khonghun Special Education Center | SUBIC | 1 | 1 | 6 | 2STY6CL |  | 23057500 |  |  | Completed | 1
NC 2020 | K10 | Region III | Zambales | 106813 | Bangan -Capayawan Elementary School | BOTOLAN | 2 | 1 | 8 | 2STY8CL |  | 25062500 |  |  | Completed | 1
NC 2021 | K10 | Region III | Aurora | 104455 | Dingalan CS | DINGALAN | 0 | 1 | 6 | Construction/Completion (2STY6CL) |  | 15986114.6225 | 15946249 |  | Completed | 1
NC 2021 | K10 | Region III | Aurora | 104462 | Umiray ES | DINGALAN | 0 | 1 | 6 | Construction/Completion (2STY6CL) |  | 15986114.6225 | 15946249 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | DINALUPIHAN | 1 | 1 | 20 | Construction/Completion (4STY20CL) |  | 7107615.126 | 7089890.4 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300704 | Jose C. Payumo Jr. Memorial High School | DINALUPIHAN | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 5493535.2492 | 5479835.66 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300708 | Luakan NHS | DINALUPIHAN | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 6255534.226 | 6239934.39 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300708 | Luakan NHS | DINALUPIHAN | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 5834325.7407 | 5819776.3 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300708 | Luakan NHS | DINALUPIHAN | 1 |  | 8 | Construction/Completion (4STY8CL) |  | 5493535.2492 | 5479835.66 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 | 1 | 12 | Construction/Completion (3STY12CL) |  | 6009894.5281 | 5994907.26 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300703 | Bataan School of Fisheries | ORION | 2 |  | 9 | Construction/Completion (3STY9CL) |  | 5275807.0962 | 5262650.47 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300706 | Lamao NHS | LIMAY | 2 | 1 | 18 | Construction/Completion (2UNITS 3STY9CL) |  | 10551614.1924 | 10525300.94 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300707 | Limay NHS | LIMAY | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 6255534.226 | 6239934.39 |  | Completed | 1
NC 2021 | SHS | Region III | Bataan | 300710 | Mariveles NHS Cabcaben | MARIVELES | 2 | 1 | 9 | Construction/Completion (3STY9CL) |  | 5275807.0962 | 5262650.47 |  | Completed | 1
NC 2021 | SHS | Region III | Bulacan | 501633 | Gen. Gregorio H. del Pilar Integrated School | BULACAN | 1 | 1 | 60 | Construction/Completion (2 units of 4STY24CL & 1 unit of 4STY12CL) |  | 3007500 | 3000000 |  | Completed | 1
NC 2021 | SHS | Region III | Bulacan | 300721 | Balagtas National Agricultural HS | BALAGTAS (BIGAA) | 2 | 1 | 48 | Construction/Completion (2UNITS 4STY24CL) |  | 3508750 | 3500000 |  | Completed | 1
NC 2021 | SHS | Region III | Bulacan | 300775 | Virginia Ramirez-Cruz High School | PANDI | 2 | 1 | 80 | Construction/Completion (4 units of 4STY20CL) |  | 4511250 | 4500000 |  | Completed | 1
NC 2021 | SHS | Region III | Bulacan | 300778 | Sulivan National High School | BALIUAG | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 5012500 | 5000000 |  | Completed | 1
NC 2021 | K10 | Region III | Bulacan | 104951 | NORTH HILLS VILLAGE ELEMENTARY SCHOOL | Norzagaray | 3 | 1 | 24 | Construction/Completion (4STY 24CL) |  | 2950623.0522 | 2943264.89 |  | Completed | 1
NC 2021 | K10 | Region III | Bulacan | 105034 | Calawitan Elementary School | SAN ILDEFONSO | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 13784375 | 13750000 |  | COMPLETED | 1
NC 2021 | K10 | Region III | Bulacan | 105043 | Sta. Catalina Bata Elementary School | SAN ILDEFONSO | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 20010922.7505 | 19961020.2 |  | COMPLETED | 1
NC 2021 | K10 | Region III | Bulacan | 105132 | San Agustin ES | SAN RAFAEL | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 20010922.7505 | 19961020.2 |  | COMPLETED | 1
NC 2021 | SHS | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL | 3 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2647918.6885 | 2641315.4 |  | Completed | 1
NC 2021 | K10 | Region III | Gapan City | 105330 | Sta. Cruz ES | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3409215.4843 | 3400713.7 |  | Completed | 1
NC 2021 | K10 | Region III | Gapan City | 105335 | Malimba ES | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 503275.9623 | 502020.91 |  | Completed | 1
NC 2021 | K10 | Region III | Gapan City | 105341 | San Roque ES | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 887161.4126 | 884949.04 |  | Completed | 1
NC 2021 | K10 | Region III | Gapan City | 105344 | Sto. Cristo Sur ES | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 557674.69 | 556283.98 |  | Completed | 1
NC 2021 | SHS | Region III | Gapan City | 300829 | Pambuan National High School | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 496163.706 | 494926.39 |  | Completed | 1
NC 2021 | SHS | Region III | Gapan City | 300829 | Pambuan National High School | CITY OF GAPAN | 4 |  | 8 | Construction/Completion (2STY4WS) |  | 1551964.6661 | 1548094.43 |  | Completed | 1
NC 2021 | SHS | Region III | Gapan City | 300849 | San Nicolas NHS | CITY OF GAPAN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3307536.7513 | 3299288.53 |  | Completed | 1
NC 2021 | K10 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 23230619.7902 | 23172688.07 |  | Completed | 1
NC 2021 | K10 | Region III | Munoz Science City | 105535 | Bantug ES | Munoz | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 4511250 | 4500000 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105183 | San Eustacio Elementary School | ALIAGA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2423681.9747 | 2417637.88 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105260 | Bued ES | CUYAPO | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3508750 | 3500000 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105284 | Paitan Sur ES | CUYAPO | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 25062500 | 25000000 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105408 | Banitan ES | GUIMBA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2739754.7962 | 2732922.49 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105422 | Narvacan I ES | GUIMBA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 20050000 | 20000000 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105487 | Tabing Ilog Elemetary School | LICAB | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2277397.295 | 2271718 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105799 | Matingkis ES | TALAVERA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2654464.5524 | 2647844.94 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105866 | Zaragoza CS | ZARAGOZA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 4097594.3297 | 4087375.89 |  | Completed | 1
NC 2021 | SHS | Region III | Nueva Ecija | 300871 | ZARAGOZA NATIONAL HIGH SCHOOL | ZARAGOZA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2476234.3079 | 2470059.16 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105650 | Paco Roman ES | RIZAL | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3508750 | 3500000 |  | Completed | 1
NC 2021 | SHS | Region III | Nueva Ecija | 306830 | Cambitala NHS | PANTABANGAN | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 6015000 | 6000000 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2882597.5827 | 2875409.06 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105359 | Apolinario Santiago ES | GENERAL MAMERTO NATIVIDAD | 3 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1488305.4148 | 1484593.93 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105460 | Betania ES | LAUR | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3160747.1725 | 3152865.01 |  | Completed | 1
NC 2021 | K10 | Region III | Nueva Ecija | 105736 | C.I. Villaroman ES | SAN LEONARDO | 4 | 1 | 6 | Construction/Completion (2STY6CL) |  | 4337307.9593 | 4326491.73 |  | Completed | 1
NC 2021 | K10 | Region III | Olongapo City | 107118 | BANGAL ES | Olongapo City | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2531810.532 | 2525496.79 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106118 | Balitucan ES | MAGALANG | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 15304856.1636 | 15266689.44 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 105973 | San Pedro ES | FLORIDABLANCA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3628302.2352 | 3619254.1 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3835145.4337 | 3825581.48 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106010 | Natividad ES | GUAGUA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 728449.0512 | 726632.47 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106013 | San Antonio ES | GUAGUA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 5149478.2316 | 5136636.64 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106050 | Remedios Elementary School | LUBAO | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3835145.4337 | 3825581.48 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106058 | Sta. Cruz CS | LUBAO | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 4451833.1283 | 4440731.3 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 300879 | Basa Air Base High School | FLORIDABLANCA | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 728449.0512 | 726632.47 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 306912 | Sta. Cruz HS | LUBAO | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 9939221.8795 | 9914435.79 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 300896 | Malino NHS | MEXICO | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1414814.5158 | 1411286.3 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga |  | San Juan Bano HS | ARAYAT | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1414814.5158 | 1411286.3 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106093 | Macabebe Elementary School | MACABEBE | 4 | 1 | 24 | Construction/Completion (3UNITS 4STY8CL) |  | 6115250 | 6100000 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106101 | Tacasan ES | MACABEBE | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 135129.9524 | 134792.97 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106106 | Dalayap ES | MACABEBE | 4 | 1 | 6 | Construction/Completion (3STY6CL) |  | 3007500 | 3000000 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106110 | San Juan ES | MACABEBE | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 155689.2024 | 155300.95 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106143 | Alauli ES | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 22086.1477 | 22031.07 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106144 | Bagang ES | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 77585.9812 | 77392.5 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106146 | Bebe Anac ES | MASANTOL | 4 | 1 | 15 | Construction/Completion (3STY15CL) |  | 902250 | 900000 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106148 | Bulacus Elementary School | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 430602.201 | 429528.38 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106154 | Palimpe ES | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 526550.1927 | 525237.1 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106155 | Puti ES | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 113275.5326 | 112993.05 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 16551.676 | 16510.4 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 106245 | San Luis CS | SAN LUIS | 4 | 1 | 8 | Construction/Completion (2STY8CL) |  | 22761710.8813 | 22704948.51 |  | Completed | 1
NC 2021 | K10 | Region III | Pampanga | 159530 | Sta. Cruz E/S (Annex) | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 15641.3358 | 15602.33 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 300924 | San Matias NHS | SANTO TOMAS | 4 | 1 | 30 | Construction/Completion (3UNITS 4STY8CL AND 2STY6CL) |  | 4360875 | 4350000 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 27279.228 | 27211.2 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 306920 | Macabebe High School | MACABEBE | 4 | 1 | 27 | Construction/Completion (3UNITS 3STY9CL) |  | 4360875 | 4350000 |  | Completed | 1
NC 2021 | SHS | Region III | Pampanga | 306926 | Malauli High School | MASANTOL | 4 | 1 | 4 | Construction/Completion (2STY4CL) |  | 41379.19 | 41276 |  | Completed | 1
NC 2021 | K10 | Region III | San Fernando City | 107167 | Bulaon ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1414814.5158 | 1411286.3 |  | Completed | 1
NC 2021 | K10 | Region III | San Fernando City | 107195 | San Fernando ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | Construction/Completion (3STY6CL) |  | 2103067.0262 | 2097822.47 |  | Completed | 1
NC 2021 | K10 | Region III | San Fernando City | 107198 | San Pedro ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 4677397.8237 | 4665733.49 |  | Completed | 1
NC 2021 | SHS | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1167357.2152 | 1164446.1 |  | Completed | 1
NC 2021 | SHS | Region III | San Fernando City | 500141 | San Isidro Integrated School | CITY OF SAN FERNANDO (Capital) | 3 |  | 4 | Construction/Completion (2STY4CL) |  | 833177.2287 | 831099.48 |  | Completed | 1
NC 2021 | SHS | Region III | San Fernando City | 500978 | Pulung Bulu ES | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 4 | Construction/Completion (2STY4CL) |  | 4677397.8237 | 4665733.49 |  | Completed | 1
NC 2021 | K10 | Region III | San Jose City | 105707 | Porais ES | SAN JOSE CITY | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3508750 | 3500000 |  | Completed | 1
NC 2021 | K10 | Region III | San Jose City | 105709 | San Jose East CS | SAN JOSE CITY | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 3508750 | 3500000 |  | Completed | 1
NC 2021 | K10 | Region III | San Jose del Monte City | 107164 | Sta. Cruz (BBD) Elementary School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | Construction/Completion (2STY4CL) |  | 14235500 | 14200000 |  | Completed | 1
NC 2021 | SHS | Region III | San Jose del Monte City | 301062 | Sapang Palay National High School | CITY OF SAN JOSE DEL MONTE | 0 | 1 | 4 | Construction/Completion (2STY4CL) |  | 14235500 | 14200000 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac | 106526 | Aringin Elemenary School | MONCADA | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 3493384.7226 | 3484673.04 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106550 | Moncada South CS | MONCADA | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 802451.7265 | 800450.6 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106575 | BRILLANTE ES | PANIQUI | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 215892.6256 | 215354.24 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106611 | SAN JUAN ES | RAMOS | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 172872.0022 | 172440.9 |  | completed | 1
NC 2021 | SHS | Region III | Tarlac | 300946 | Anao NHS | ANAO | 1 | 1 | 16 | Construction/Completion (4STY16CL) |  | 10514887.7853 | 10488666.12 |  | completed | 1
NC 2021 | SHS | Region III | Tarlac | 300948 | Balaoang NHS | PANIQUI | 1 | 1 | 12 | Construction/Completion (3STY12CL) |  | 1549532.0096 | 1545667.84 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106459 | Sulipa ES | GERONA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 2029943.0822 | 2024880.88 |  | completed | 1
NC 2021 | TVL | Region III | Tarlac | 106640 | Moriones ES | SAN JOSE | 2 | 1 | 1 | Construction/Completion (1 UNIQUE WORKSHOP) |  | 2082455.947 | 2077262.79 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106775 | Bangar Elementary | VICTORIA | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 314611.4272 | 313826.86 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106784 | Balayang Elementary School | VICTORIA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 4034406.4139 | 4024345.55 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106791 | Lalapac ES | VICTORIA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 3963854.3536 | 3953969.43 |  | completed | 1
NC 2021 | SHS | Region III | Tarlac | 300954 | Buenlag NHS | GERONA | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 2391159.8321 | 2385196.84 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac | 300959 | Cardona NHS | GERONA | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 2872224.3041 | 2865061.65 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac | 300965 | Gerona Western Public High School | GERONA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2056907.9563 | 2051778.51 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac | 300986 | San Jose NHS | GERONA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2061177.3231 | 2056037.23 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac | 300995 | Tagumbao NHS | GERONA | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 2056907.9563 | 2051778.51 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac | 300996 | Tarlac National HS | CITY OF TARLAC (Capital) | 2 | 1 | 8 | Construction/Completion (4STY8CL (4WS)) |  | 4849498.7832 | 4837405.27 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac | 106411 | SAN JOSE ES | CONCEPCION | 3 | 1 | 10 | Construction/Completion (2STY10CL) |  | 3526067.9168 | 3517274.73 |  | completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106694 | San Nicolas ES | CITY OF TARLAC (Capital) | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 3088562.972 | 3080860.82 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106695 | San Sebastian ES | CITY OF TARLAC (Capital) | 2 | 1 | 8 | Construction/Completion (2STY8CL) |  | 2022187.4715 | 2017144.61 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106698 | Balingcanaway Centro ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 192527.1576 | 192047.04 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106702 | Maliwalo Central ES | CITY OF TARLAC (Capital) | 2 | 1 | 20 | Construction/Completion (4STY20CL) |  | 4899752.043 | 4887533.21 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106706 | San Pascual ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1107651.9644 | 1104889.74 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106746 | San Miguel CS | CITY OF TARLAC (Capital) | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 3493093.8472 | 3484382.89 |  | Completed | 1
NC 2021 | K10 | Region III | Tarlac City | 106764 | San Jose de Urquico ES | CITY OF TARLAC (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2275599.211 | 2269924.4 |  | Completed | 1
NC 2021 | SHS | Region III | Tarlac City | 500556 | BUROT INTEGRATED SCHOOL | CITY OF TARLAC (Capital) | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 2865441.2688 | 2858295.53 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106855 | Balaybay Resettlement Elementary School | CASTILLEJOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 31077279.9913 | 30999780.54 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106855 | Balaybay Resettlement Elementary School | CASTILLEJOS | 1 |  | 8 | Construction/Completion (2STY8CL) |  | 35087044.9151 | 34999546.05 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106856 | Castillejos Elementary School | CASTILLEJOS | 1 | 1 | 10 | Construction/Completion (2STY10CL) |  | 4076435.5748 | 4066269.9 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106857 | Del Pilar Elementary School | CASTILLEJOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 5657774.1926 | 5643665.03 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106858 | KANAYNAYAN COMMUNITY SCHOOL | CASTILLEJOS | 1 | 1 | 2 | Construction/Completion (1STY2CL) |  | 1161339.6087 | 1158443.5 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106865 | San Nicolas Primary School | CASTILLEJOS | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 30074814.4172 | 29999814.88 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106891 | Inhobol ES | MASINLOC | 2 | 1 | 12 | Construction/Completion (3STY12CL) |  | 2506250 | 2500000 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106934 | Maloma Community ES | SAN FELIPE | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1051430.02 | 1048808 |  | Completed | 1
NC 2021 | K10 | Region III | Zambales | 106975 | Babuyan ES | SANTA CRUZ | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 975000.2922 | 972568.87 |  | Completed | 1
NC 2021 | SHS | Region III | Zambales | 301011 | Candelaria School of Fisheries | CANDELARIA | 2 | 1 | 12 | Construction/Completion (4STY12CL) |  | 3007500 | 3000000 |  | Completed | 1
NC 2021 | SHS | Region III | Zambales | 301032 | San Miguel National High School | SAN ANTONIO | 2 | 1 | 20 | Construction/Completion (4STY20CL) |  | 2005000 | 2000000 |  | Completed | 1
NC 2021 | SHS | Region III | Zambales | 301033 | Sta. Cruz National High School | SANTA CRUZ | 2 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2506250 | 2500000 |  | Completed | 1
NC 2021 | SHS | Region III | Zambales | 307107 | San Antonio National High School | SAN ANTONIO | 2 | 1 | 20 | Construction of Slope Protection |  | 3257383.3405 | 3249260.19 |  | Completed | 1
NC 2021 | SHS | Region III | Zambales | 307131 | Lakas High School | BOTOLAN | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1370267.125 | 1366850 |  | Completed | 1
NC 2022 | K10 | Region III | Bataan | 305899 | Bataan HS for the Arts | BAGAC | 2 | 1 | 20 | Construction of School Building | 1 |  | 50125000 |  | ongoing | 0.5
NC 2022 | K10 | Region III | Bulacan | 105068 | Buliran ES | SAN MIGUEL | 3 | 1 | 6 | 2STY6CL | 2 |  | 18045000 | 18000000 | Completed | 1 | 2023-08-27 | 2023-08-27 | P00675099LZ | 22CD0224 | 2022-07-07 | 2022-07-14 | 2022-07-28 | 2022-11-21 | 2022-11-25 | GMO CONSTRUCTION
NC 2022 | K10 | Region III | Bulacan | 105133 | San Rafael Cs | SAN RAFAEL | 3 | 1 | 6 | 2STY6CL | 2 |  | 18045000 | 17694430.76 | Completed | 1 | 2023-08-27 | 2023-08-27 | P00675101LZ | 22CD0226 | 2022-07-07 | 2022-07-14 | 2022-07-28 | 2022-11-21 | 2022-11-25 | EIRISH BUILDERS & SUPPLY, INC.
NC 2022 | K10 | Region III | Nueva Ecija | 105256 | Bambanaba ES | CUYAPO | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 128367 | Cacapasan Elementary School | CUYAPO | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 105566 | Alzate Village ES | NAMPICUAN | 1 | 1 | 2 | 1STY2CL | 2 |  | 5052047.0411 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 105568 | Maeling Elementary School | NAMPICUAN | 1 | 1 | 4 | 2STY4CL | 2 |  | 15338250 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 105768 | Baloc ES | SANTO DOMINGO | 1 | 1 | 8 | COMPLETION OF 2STY8CL | 2 |  | 8020000 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 105810 | Bantug ES | TALAVERA | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 105814 | Caputican ES | TALAVERA | 1 | 1 | 6 | COMPLETION OF 2STY6CL | 2 |  | 6015000 |  | Completed | 1
NC 2022 | K10 | Region III | Nueva Ecija | 501822 | San Pascual Integrated School | TALAVERA | 1 | 1 | 4 | COMPLETION OF 2STY4CL | 2 |  | 4010000 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106306 | Bantog ES | ANAO | 1 | 1 | 4 | 2STY4CL | 2 |  | 13553800 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106309 | San Jose ES | ANAO | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106610 | Ramos CS | RAMOS | 1 | 1 | 4 | 2STY4CL | 2 |  | 13559815 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106614 | Toledo ES | RAMOS | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 160006 | Don Cesar Abad Gualberto MGS | SAN CLEMENTE | 1 | 1 | 2 | 1STY2CL | 2 |  | 5012500 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE | 1 | 1 | 4 | 2STY4CL | 2 |  | 13551795 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106665 | Sta. Maria ES | SAN MANUEL | 1 | 1 | 4 | PROPOSED CONSTRUCTION OF ONE (1) STOREY - FOUR (4) CLASSROOMS SCHOOL BUILDING (WITHOUT TOILET) WITH PROVISION OF RAINWATER COLLECTOR, WATER AND SANITATION FACILITIES (4 - SEATER), SCHOOL FURNITURE, AND WATER SYSTEM | 2 |  | 11446070.9278 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 502183 | Amacalan Integrated School | GERONA | 2 | 1 | 4 | 2STY4CL | 2 |  | 15458550 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106445 | Buenlag ES | GERONA | 2 | 1 | 4 | 2STY4CL | 2 |  | 15458550 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 501833 | Calayaan Integrated School | GERONA | 2 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106475 | Padapada PS | GERONA | 2 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106455 | Quezon ES | GERONA | 2 | 1 | 2 | 1STY2CL | 2 |  | 6516250 |  | Completed | 1
NC 2022 | K10 | Region III | Tarlac | 106485 | Villa Paz ES | GERONA | 2 | 1 | 4 | 1STY4CL | 2 |  | 12030000 |  | Completed | 1
NC 2022 | SHS | Region III | Aurora | 300695 | Umiray NHS | DINGALAN | 0 | 1 | 4 | 2STY4CL | 2 |  | 15799400 |  | Completed | 1
NC 2022 | SHS | Region III | Bulacan | 306716 | Upig High School | SAN ILDEFONSO | 3 | 1 | 10 | 2STY10CL | 2 |  | 33299410.925 | 33215486.62 | Completed | 1 | 2023-09-26 | 2023-09-26 | P00675098LZ | 22CD0227 | 2022-07-12 | 2022-07-19 | 2022-08-09 | 2022-11-21 | 2022-11-25 | OLYMPUS MINING AND BUILDERS GROUP PHILS. CORP. / LE BRON CONSTRUCTION (JV)
NC 2022 | SHS | Region III | Bulacan | 306704 | Vedasto R. Santiago HS | SAN MIGUEL | 3 | 1 | 6 | 3STY6CL | 2 |  | 20887812.3075 | 20835723 | Completed | 1 | 2023-07-28 | 2023-07-28 | P00675100LZ | 22CD0225 | 2022-07-07 | 2022-07-14 | 2022-07-28 | 2022-11-21 | 2022-11-25 | OLYMPUS MINING AND BUILDERS GROUP PHILS. CORP. / LE BRON CONSTRUCTION (JV)
NC 2022 | SHS | Region III | Pampanga | 300876 | Andres M. Luciano HS | MAGALANG | 1 | 1 | 8 | 2STY8CL | 2 |  | 25664000 |  | COMPLETED | 1
NC 2022 | SHS | Region III | San Fernando City | 301064 | Pampanga High School | CITY OF SAN FERNANDO (Capital) | 3 | 1 | 6 | 3STY6CL | 2 |  | 22055000 |  | Completed | 1 | [10 empty] | Project was suspended from January 23,2023-March 16, 2023
NC 2022 | SHS | Region III | Tarlac | 300956 | Calangitan HS (Resettlement School) | CAPAS | 3 | 1 | 6 | 2STY6CL | 2 |  | 16280951.2459 |  | Ongoing | 0.9
NC 2022 | SHS | Region III | Tarlac | 300951 | Benigno S. Aquino National High School | CONCEPCION | 3 | 1 | 20 | 4STY20CL | 2 |  | 48611005.2721 |  | Completed | 1
NC 2023 | SHS | Region III | Angeles City | 301039 | Angeles City NHS | ANGELES CITY |  | 1 | 16 |  | Batch 1 | 51446250 | 51000000 | 50998611.44 | Not Yet Started | 1 | 2024-04-26 | 2024-04-26 | P00775217LZ | 45097 | 2023-06-30 | 2023-07-11 | 2023-07-17 | 2023-07-27 |  | B12 Construction and Development Corporation
NC 2023 | K10 | Region III | Angeles City | 107029 | EPZA Resettlement ES | ANGELES CITY |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14696936.8 | Completed | 1 | 2024-03-22 | 2024-03-22 | P00775215LZ | 45091 | 2023-06-23 | 2023-07-11 | 2023-07-17 | 2023-07-27 |  | GMO Construction
NC 2023 | K10 | Region III | Angeles City | 107030 | Mining Elementary School | ANGELES CITY |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14869431.15 | Completed | 1 | 2024-03-22 | 2024-04-21 | P00775216LZ | 45091 | 2023-06-23 | 2023-07-11 | 2023-07-17 | 2023-07-27 |  | GMO Construction
NC 2023 | SHS | Region III | Aurora | 300672 | Aurora National Science HS | BALER (Capital) |  | 1 | 8 |  | Batch 1 | 20175000 | 20000000 |  | Ongoing | 0.1
NC 2023 | K10 | Region III | Aurora | 300677 | Baler NHS | BALER (Capital) |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.1
NC 2023 | K10 | Region III | Aurora | 104431 | Camilo Osias ES | DILASAG |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 |  | Completed | 1
NC 2023 | K10 | Region III | Aurora | 104464 | Borlongan ES | DIPACULAO |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 |  | Completed | 1
NC 2023 | SHS | Region III | Aurora | 300691 | Maria Aurora NHS | MARIA AURORA |  | 1 | 12 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.1
NC 2023 | K10 | Region III | Aurora | 300694 | Mayor Cesario A. Pimentel NHS | SAN LUIS |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.3
NC 2023 | SHS | Region III | Balanga City | 305944 | Bataan National High School - Senior High School | CITY OF BALANGA (Capital) |  | 1 | 6 |  | Batch 1 | 20175000 | 20000000 |  | Completed | 1
NC 2023 | K10 | Region III | Balanga City | 502032 | Tuyo Integrated School | CITY OF BALANGA (Capital) |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 |  | Completed | 1
NC 2023 | SHS | Region III | Bataan | 306608 | Orani NHS - Pagasa | ORANI |  | 1 | 6 |  | Batch 1 | 27366544.66 | 27129164.47 | 27061341.38 | Completed | 1
NC 2023 | SHS | Region III | Bataan | 300698 | Bagac NHS-Parang | BAGAC |  | 1 | 4 |  | Batch 1 | 13920750 | 13800000 |  | Completed | 1
NC 2023 | SHS | Region III | Bataan | 306612 | Roosevelt National High School | DINALUPIHAN |  | 1 | 2 |  | Batch 1 | 5447250 | 5400000 |  | Completed | 1
NC 2023 | K10 | Region III | Bataan | 306615 | Mariveles NHS Pob. Annex-Sisiman | MARIVELES |  | 1 | 2 |  | Batch 1 | 5447250 | 5400000 |  | Completed | 1
NC 2023 | K10 | Region III | Bataan | 501331 | Sampaloc Integrated School | MORONG |  | 1 | 2 |  | Batch 1 | 5447250 | 5400000 |  | Completed | 1
NC 2023 | K10 | Region III | Bulacan | 104757 | Sta. Barbara ES | BALIUAG |  | 1 | 9 |  | Batch 1 | 33288750 | 33000000 |  | Completed | 1 | 2024-07-26 | 2024-09-24 | P00775231LZ | 23CC0458 | 2023-08-13 | 2023-08-21 | 2023-10-03 | 2023-10-13 |  | INDUSTRIAL CONTROLS CORPORATION | Phase 1 only. Incomplete building. Waiting for additional funds
NC 2023 | K10 | Region III | Bulacan | 158525 | Durumugan ES | DOÑA REMEDIOS TRINIDAD |  | 1 | 4 |  | Batch 2 | 17595000 | 17000000 |  | Completed | 1 | 2024-06-30 | 2024-06-30 |  | 23C00345 |  |  |  |  | 2024-01-03 | RVR3 Construction Supply and Services
NC 2023 | K10 | Region III | Bulacan | 105111 | San Miguel Elementary | SAN MIGUEL |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | 2024-05-29 | 2024-05-29 |  | 23C00333 |  |  |  |  | 2023-12-13 | RVR3 Construction Supply and Services
NC 2023 | SHS | Region III | Bulacan | 300748 | Carlos F. Gonzales HS (Maguinao Cruz na Daan NHS) | SAN RAFAEL |  | 1 | 20 |  | Batch 1 | 72630000 | 72000000 |  | Ongoing | 0.5 | 2024-07-30 |  |  | 23C00335 |  |  |  |  | 2023-12-13 | Eirish Builders & Supply Inc.
NC 2023 | SHS | Region III | Bulacan | 300773 | San Rafael Nat'l Trade School | SAN RAFAEL |  | 1 | 20 |  | Batch 1 | 72630000 | 72000000 |  | Completed | 1 | 2024-10-28 | 2025-02-28 |  | 23C00336 |  |  |  |  | 2023-12-13 | Exelcius Engineering Services
NC 2023 | K10 | Region III | Bulacan | 105137 | Tambubong ES | SAN RAFAEL |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14099260.93 | Completed | 1 | 2024-06-15 | 2024-06-15 |  | 23C00334 |  |  |  |  | 2023-12-13 | Plerm Construction and Development Corporation
NC 2023 | K10 | Region III | Bulacan | 104764 | Bunducan ES | BOCAUE |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14097399.22 | Ongoing | 1 | 2024-05-20 | 2024-09-22 | P00775236LZ | 23CC0456 | 2023-08-13 | 2023-08-21 | 2023-10-03 | 2023-10-13 |  | 121 CONSTRUCTION CORPORATION
NC 2023 | K10 | Region III | Bulacan | 104765 | Bunlo Elementary School | BOCAUE |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 29099277.9 | Ongoing | 1 | 2024-05-20 | 2024-09-27 | P00775237LZ | 23CC0457 | 2023-08-13 | 2023-08-21 | 2023-10-03 | 2023-10-13 |  | R. ROSE CONSTRUCTION SERVICES
NC 2023 | K10 | Region III | Bulacan | 104978 | Malibong Matanda ES | PANDI |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 9911725.3 | Completed | 1 | 2024-05-07 | 2024-07-06 | P00775238LZ | 23CC0452 | 2023-07-28 | 2024-08-04 | 2023-08-17 | 2023-08-24 |  | A.C. VALDERAMA CONSTRUCTION AND DEVELOPMENT CORP
NC 2023 | K10 | Region III | Bulacan | 104952 | Norzagaray ES | NORZAGARAY |  | 1 | 2 |  | Batch 1 | 10087500 | 10000000 | 14818154.17 | Completed | 1 | 2023-12-28 | 2023-12-28 | P00775239LZ | 23CD0158 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-18 | 2023-07-26 | EMICA BUILDERS AND SUPPLY
NC 2023 | K10 | Region III | Bulacan | 105152 | Jose Juan Serapio ES (Catmon ES) | SANTA MARIA |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 14818154.17 | Completed | 1 | 2024-01-27 | 2024-01-27 | P00775240LZ | 23CD0159 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-18 | 2023-07-26 | 1199S CONSTRUCTION
NC 2023 | SHS | Region III | Bulacan | 305573 | San Gabriel national High School | SANTA MARIA |  | 1 | 8 |  | Batch 3 | 42148773 | 40673565.94 |  | Completed | 1 | 2025-05-26 | 2025-01-03 |  | 23CD0218 | 2024-08-07 | 2024-08-15 | 2024-08-28 | 2024-09-06 | 2024-12-27 | YPR Gen. Contractor and Construction Supply Inc.
NC 2023 | K10 | Region III | Bulacan | 105164 | San Vicente Elementary School | SANTA MARIA |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 | 29999998.03 | Completed | 1 | 2024-01-27 | 2024-01-27 | P00775241LZ | 23CD0160 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-18 | 2023-07-26 | SAMJS CONSTRUCTION SERVICES
NC 2023 | K10 | Region III | Cabanatuan City | 107084 | Obrero ES | CABANATUAN CITY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1 | 2023-02-25 | 2023-02-25 | P00775253LZ | 23CD0162 | 2023-06-15 | 2023-06-22 | 2023-07-06 | 2023-07-18 | 2023-07-26 | TRIPLE 8 CONSTRUCTION
NC 2023 | K10 | Region III | Cabanatuan City | 107114 | Pagas Elementary School | CABANATUAN CITY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1
NC 2023 | K10 | Region III | Cabanatuan City | 107088 | Samon ES | CABANATUAN CITY |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1
NC 2023 | K10 | Region III | Cabanatuan City | 107089 | Sapang ES | CABANATUAN CITY |  | 1 | 6 |  | Batch 1 | 16346916.47 | 16205121.65 | 32075518 | Completed | 1
NC 2023 | K10 | Region III | City of San Jose Del Monte | 307514 | San Manuel National High School | CITY OF SAN JOSE DEL MONTE |  | 1 | 12 |  | Batch 1 | 42959122.17 | 42586490.38 |  | Completed | 1 | 2024-11-19 | 2024-11-19
NC 2023 | K10 | Region III | City of San Jose Del Monte | 107163 | San Rafael (BBH) Elementary School | CITY OF SAN JOSE DEL MONTE |  | 1 | 9 |  | Batch 1 | 29982569.88 | 29722498.02 |  | Completed | 1 | 2024-11-19 | 2024-11-19
NC 2023 | K10 | Region III | Gapan City | 105315 | Balante ES | CITY OF GAPAN |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11182182.94 | Completed | 1 | 2024-10-04 | 2025-02-01 | 23CF0127 | 23CF0127 | 2023-08-25 | 2023-09-05 | 2023-09-19 | 2023-12-18 | 2023-12-19 | R Mallanes Construction
NC 2023 | K10 | Region III | Gapan City | 501200 | Marelo Integrated School | CITY OF GAPAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9844551.01 | Completed | 1 | 2024-06-16 | 2024-06-11 | 23CF0128 | 23CF0128 | 2023-08-25 | 2023-09-05 | 2023-09-19 | 2023-12-18 | 2023-12-19 | R Mallanes Construction
NC 2023 | K10 | Region III | Malolos City | 104873 | Look 1st ES | CITY OF MALOLOS (Capital) |  | 1 | 8 |  | Batch 1 | 30262500 | 30000000 | 29099789.16 | Completed | 1 |  | 2024-12-01 | P00775250LZ | 23CC0450 | 2023-07-28 | 2023-08-04 | 2023-08-17 | 2023-08-17 |  | RHR Construction
NC 2023 | K10 | Region III | Malolos City | 104897 | Panasahan ES | CITY OF MALOLOS (Capital) |  | 1 | 12 |  | Batch 1 | 50437140.23 | 49999643.35 | 48014471.6 | Completed | 1 |  | 2024-12-01 | P00775252LZ | 23CC0449 | 2023-07-28 | 2023-08-04 | 2023-08-17 | 2023-08-17 |  | Excelsius Engineering Services
NC 2023 | K10 | Region III | Malolos City | 104878 | Sta. Isabel ES | CITY OF MALOLOS (Capital) |  | 1 | 20 |  | Batch 1 | 80223770.76 | 79527901.62 | 77142224 | Completed | 1 |  | 2024-12-01 | P00775251LZ | 23CC0451 | 2023-07-28 | 2023-08-04 | 2023-08-17 | 2023-08-17 |  | Excelsius Engineering Services/SYMS Construction Trading (JV)
NC 2023 | K10 | Region III | Meycauayan City | 500965 | Saluysoy Integrated School | CITY OF MEYCAUAYAN |  | 1 | 9 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.4
NC 2023 | K10 | Region III | Munoz Science City | 105555 | Pandalla ES | SCIENCE CITY OF MUÑOZ |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4949999.27 | Completed | 1 | 2024-11-11 | 2024-11-15 | P00775254LZ | 23CE0207 | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-08-02 | 2023-08-11 | Ninas Construction & Supplies | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | Munoz Science City | 105558 | San Andres ES | SCIENCE CITY OF MUÑOZ |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4949997.18 | Completed | 1 | 2024-11-11 | 2024-11-08 | P00775255LZ | 23CE0208 | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-08-02 | 2023-08-11 | Ninas Construction & Supplies | COMPLETED AS PER CONTRACT
NC 2023 | SHS | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA |  | 1 | 3 |  | Batch 1 | 10087500 | 10000000 | 11352474.25 | Completed | 1 | 2024-01-29 | 2024-02-28 | P00775278LZ | 23CG0295 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-25 | 2023-09-28 | P.C. Panopio Construction and Trading | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | Nueva Ecija | 105193 | Umangan ES | ALIAGA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 18262675.97 | Completed | 1 | 2024-02-28 | 2024-08-11 | P00775279LZ | 23CG0288 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-25 | 2023-09-28 | Three in One Const. & Trading | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | Nueva Ecija | 105273 | Dr. A. Ongsiako Sr. ES | CUYAPO |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 9899920.8 | Completed | 1 | 2023-12-23 | 2024-03-25 | 23CE0206 | P00775280LZ | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-08-02 | 2023-08-11 | Ninas Construction Services | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | Nueva Ecija | 105410 | Calem Elementary | GUIMBA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 501658 | Maybubon Integrated School | GUIMBA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105829 | San Miguel Na Munti ES | TALAVERA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105804 | Sicsican Matanda ES | TALAVERA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105502 | Llanera CS | LLANERA |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 500122 | Sta. Barbara Integrated School(Elementary) | LLANERA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105519 | Burgos ES | LUPAO |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 502146 | Fronda Integrated School | TALUGTUG |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105218 | Entablado ES | CABIAO |  | 1 | 10 |  | Batch 2 | 28192908.04 | 27239524.68 |  | Ongoing | 0.8
NC 2023 | SHS | Region III | Nueva Ecija | 300808 | General Tinio NHS | GENERAL TINIO (PAPAYA) |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 |  | Completed | 1
NC 2023 | K10 | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 |  | Completed | 1
NC 2023 | K10 | Region III | Olongapo City | 107139 | Kalalake ES | OLONGAPO CITY |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.9
NC 2023 | K10 | Region III | Pampanga | 159520 | Balik Barangay (Manibaug Pasig) ES | PORAC |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | 2024-02-17 | 2024-07-31 | P00775271LZ | 23CH0106 | 2023-07-25 | 2023-08-01 | 2023-08-15 | 2023-09-04 | 2023-09-15 | V. TRILLANA BUILDERS & TRADING
NC 2023 | K10 | Region III | Pampanga | 159537 | Diaz ES | PORAC |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1 | 2024-02-17 | 2024-07-31 | P00775272LZ | 23CH0107 | 2023-07-25 | 2023-08-01 | 2023-08-15 | 2023-09-04 | 2023-09-15 | TRI-TON ENGINEERING SERVICES
NC 2023 | SHS | Region III | Pampanga | 300906 | Pasig NHS | CANDABA |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | 2023-12-30 | 2023-12-30 | P00775273LZ | 23CG0286 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-22 | 2023-09-28 | Eddmari Construction and Trading
NC 2023 | SHS | Region III | Pampanga | 300933 | Masantol HS (Sta. Lucia NHS, Masantol) | MASANTOL |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | 2024-02-23 | 2024-02-23 | P00775274LZ | 23CG0284 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-22 | 2023-09-28 | Eddmari Construction and Trading
NC 2023 | K10 | Region III | Pampanga | 106210 | Sta. Rita ES | MINALIN |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | 2023-12-30 | 2023-12-30 | P00775275LZ | 23CG0283 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-22 | 2023-09-28 | Eddmari Construction and Trading
NC 2023 | K10 | Region III | Pampanga | 106252 | Sto. Nino ES | SAN LUIS |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | 2023-12-30 | 2023-12-30 | P00775276LZ | 23CG0287 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-22 | 2023-09-28 | JK Viray Construction Services
NC 2023 | K10 | Region III | Pampanga | 106259 | San Miguel ES | SAN SIMON |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1 | 2024-02-28 | 2024-02-28 | P00775277LZ | 23CG0285 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-22 | 2023-09-28 | Cholo Construction and Trading
NC 2023 | K10 | Region III | San Fernando City | 500145 | Maimpis IS | CITY OF SAN FERNANDO (Capital) |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 | 11352474.25 | Completed | 1 | 2024-01-29 | 2024-02-28 | P00775278LZ | 23CG0295 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-25 | 2023-09-28 | P.C. Panopio Construction and Trading | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | San Fernando City | 500149 | San Agustin IS | CITY OF SAN FERNANDO (Capital) |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 | 18262675.97 | Completed | 1 | 2024-02-28 | 2024-08-11 | P00775279LZ | 23CG0288 | 2023-08-24 | 2023-09-01 | 2023-09-14 | 2023-09-25 | 2023-09-28 | Three in One Const. & Trading | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | San Jose City | 105731 | Sto. Tomas Elementary School | SAN JOSE CITY |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9899920.8 | Completed | 1 | 2023-12-23 | 2024-03-25 | 23CE0206 | P00775280LZ | 2023-06-23 | 2023-06-30 | 2023-07-12 | 2023-08-02 | 2023-08-11 | Ninas Construction Services | COMPLETED AS PER CONTRACT
NC 2023 | K10 | Region III | Tarlac | 306089 | Camiling Science High School | CAMILING |  | 1 | 3 |  | Batch 1 | 9078750 | 9000000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106559 | Apulid ES | PANIQUI |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106568 | Paniqui North CS | PANIQUI |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Not Yet Started | 0 | [10 empty] | Realigned to Sta. Ignacia NHS
NC 2023 | SHS | Region III | Tarlac | 300982 | Ramos National High School | RAMOS |  | 1 | 12 |  | Batch 1 | 45635850 | 45240000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106614 | Toledo ES | RAMOS |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106618 | Daldalayap ES | SAN CLEMENTE |  | 1 | 6 |  | Batch 1 | 22696875 | 22500000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106619 | Doclong 1st ES | SAN CLEMENTE |  | 1 | 4 |  | Batch 1 | 16170262.5 | 16030000 | 15864891 | Completed | 1 | [9 empty] | GMO Construction
NC 2023 | K10 | Region III | Tarlac | 106620 | Doclong 2nd Elementary School | SAN CLEMENTE |  | 1 | 4 |  | Batch 1 | 16442625 | 16300000 | 16132110 | Completed | 1 | [9 empty] | GMO Construction
NC 2023 | K10 | Region III | Tarlac | 501609 | San Clemente Integrated School | SAN CLEMENTE |  | 1 | 4 |  | Batch 1 | 15131250 | 15000000 |  | Completed | 1
NC 2023 | SHS | Region III | Tarlac | 300978 | Padapada NHS | SANTA IGNACIA |  | 1 | 2 |  | Batch 1 | 6052500 | 6000000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 502180 | Maamot Integrated School | SAN JOSE |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 |  | Completed | 1
NC 2023 | SHS | Region III | Tarlac | 307021 | Balayang HS | VICTORIA |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 |  | Completed | 1
NC 2023 | SHS | Region III | Tarlac | 307014 | Calibungan HS | VICTORIA |  | 1 | 3 |  | Batch 1 | 10591875 | 10500000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac | 106408 | Parang ES | CONCEPCION |  | 1 | 6 |  | Batch 1 | 17148750 | 17000000 |  | Ongoing | 0.85
NC 2023 | K10 | Region III | Tarlac | 106442 | Sto. Nino ES | CONCEPCION |  | 1 | 4 |  | Batch 1 | 13113750 | 13000000 |  | Completed | 1
NC 2023 | K10 | Region III | Tarlac City | 500390 | Armenia Integrated School | CITY OF TARLAC (Capital) |  | 1 | 2 |  | Batch 1 | 6556875 | 6500000 |  | Completed | 1
NC 2023 | K10 | Region III | Zambales | 501225 | Looc Integrated School | CASTILLEJOS |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 1 |  | 2024-12-24
NC 2023 | K10 | Region III | Zambales | 107019 | Sto. Tomas Elementary School | SUBIC |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.95
NC 2023 | K10 | Region III | Zambales | 501169 | Porac Integrated School | BOTOLAN |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 |  | Completed | 1 | [8 empty] | 2023-10-06
NC 2023 | K10 | Region III | Zambales | 160502 | ADBSA Aeta School (Jesmag Iba) | IBA (Capital) |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 |  | Completed | 1 | [8 empty] | 2023-10-06
NC 2023 | SHS | Region III | Zambales | 301037 | Zambales National High School | IBA (Capital) |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 |  | Completed | 1 | [8 empty] | 2023-10-06
NC 2023 | SHS | Region III | Zambales | 307123 | Angel C. Manglicmot High School | SAN ANTONIO |  | 1 | 6 |  | Batch 1 | 20175000 | 20000000 |  | Ongoing | 0.85 | [8 empty] | 2023-10-06
NC 2023 | K10 | Region III | Zambales | 106928 | San Nicolas Elementary School | SAN ANTONIO |  | 1 | 4 |  | Batch 1 | 11451808.4 | 11352474.25 |  | Completed | 1 | [8 empty] | 2023-10-06
NC 2023 | SHS | Region III | Zambales | 301034 | Lipay High School | SANTA CRUZ |  | 1 | 6 |  | Batch 1 | 18422474.39 | 18262675.97 |  | Completed | 1 | [8 empty] | 2023-10-06
NC 2024 |  | Region III | Angeles City | 500131 | Amsic IS | ANGELES CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 43000000 |  | 40799043.59 | Ongoing | 0.9 | 2025-03-04 |  | 24CI0098 | 41678201.810000002 | 2024-04-15 | 2024-04-26 | 2024-05-09 | 2024-05-22 | 2024-06-03 | GMO Construction
NC 2024 |  | Region III | Angeles City | 501022 | Don Ambrocio Mendiola Integrated School | ANGELES CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 25000000 |  | 24874241.95 | Completed | 1 | 2024-10-22 | 2024-10-22 | 24CI0095 | 24297942.59 | 2024-03-07 | 2024-03-15 | 2024-03-27 | 2024-04-16 | 2024-04-26 | B12 CONSTRUCTION TRADING INC.
NC 2024 |  | Region III | Angeles City | 107056 | Leoncia Village ES | ANGELES CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  | 14924852.28 | Completed | 1 | 2024-10-22 | 2024-10-22 | 24CI0096 | 14566427.4 | 2024-03-07 | 2024-03-15 | 2024-03-27 | 2024-04-16 | 2024-04-26 | B12 CONSTRUCTION TRADING INC.
NC 2024 |  | Region III | Angeles City | 107058 | M.Nepomuceno ES | ANGELES CITY |  | 1 | 12 | 4STY12CL | BATCH 1 | 42000000 |  | 41678201.81 | Ongoing | 0.9 | 2025-02-25 |  | 24CI0003 | 40799043.590000004 | 2023-10-25 | 2023-11-03 | 2024-04-25 | 2024-05-14 | 2024-05-27 | GMO Construction
NC 2024 |  | Region III | Aurora | 104423 | Casiguran CS | CASIGURAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Aurora | 104439 | Lawang ES | DILASAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Aurora | 104447 | Mapalad ES | DINALUNGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Aurora | 500751 | Cabog IS | DINGALAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Aurora | 104465 | Calaocan ES | DIPACULAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Aurora | 104510 | Suguit ES | MARIA AURORA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Aurora | 302766 | Suguit NHS | MARIA AURORA |  | 1 | 8 | 2STY8CL | BATCH 1 | 24000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Aurora | 104516 | Dikapinisan ES | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Aurora | 104528 | San Luis CS | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Balanga City | 305944 | Bataan National High School - Senior High School | CITY OF BALANGA (Capital) |  | 1 | 20 | 4STY20CL | BATCH 1 | 73432000 |  | 71511467.67 | Ongoing | 0.7 | 2025-03-15
NC 2024 |  | Region III | Balanga City | 502029 | Cabog-Cabog Integrated School | CITY OF BALANGA (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 1 | [10 empty] | Waiting for turnover
NC 2024 |  | Region III | Balanga City | 502343 | Tanato Integrated School | CITY OF BALANGA (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4865236.25 | Completed | 1 | 2024-08-11
NC 2024 |  | Region III | Baliwag | 104737 | Baliuag North C/S | BALIUAG |  | 1 | 9 | 3STY9CL | BATCH 1 | 43240000 |  |  | Ongoing | 0.4 |  |  | P00875828LZ | 24cc0567 | 2024-10-01 | 2024-10-09 | 2024-10-22
NC 2024 |  | Region III | Bataan | 104615 | Pandatung ES | HERMOSA |  | 1 | 4 | 2STY4CL | GAA 17B | 16200000 |  |  | Ongoing | 0.55
NC 2024 |  | Region III | Bataan | 300715 | Orani NHS | ORANI |  | 1 | 8 | 4STY8CL | BATCH 1 | 31224007.655 |  |  | Ongoing | 0.08
NC 2024 |  | Region III | Bataan | 104707 | Samal North ES | SAMAL |  | 1 | 6 | 2STY6CL | GAA 17B | 23800000 |  |  | Ongoing | 0.4
NC 2024 |  | Region III | Bataan | 104687 | Sto. Domingo ES | ORION |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  |  | Not Yet Started | 0 | [10 empty] | r Modification from 2storey/4classroom to 1storey/3classroom due to insufficient fund
NC 2024 |  | Region III | Bataan | 104688 | Alauli ES | PILAR |  | 1 | 4 | 2STY4CL | BATCH 2 | 20169448.07 |  |  | Ongoing | 0
NC 2024 |  | Region III | Bataan | 300717 | Dr. Victoria B. Roman MHS | PILAR |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  |  | Ongoing | 0.08
NC 2024 |  | Region III | Bataan | 104545 | Overland ES | BAGAC |  | 1 | 4 | 2STY4CL | GAA 17B | 13334000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Bataan | 104600 | Sta. Isabel ES | DINALUPIHAN |  | 1 | 4 | 2STY4CL | GAA 17B | 13333000 |  |  | Ongoing | 0.2
NC 2024 |  | Region III | Bataan | 104637 | Balon ES | MARIVELES |  | 1 | 4 | 2STY4CL | GAA 17B | 13333000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Bulacan | 300745 | San Roque National HS | PAOMBONG |  | 1 | 8 | 4STY8CL | BATCH 2 | 42000000 |  |  | Ongoing | 0.15 | 2025-07-30 |  |  | 24CC0568 | 2024-11-19 | 2024-11-27 | 2024-12-10 | 2024-12-13 | 2024-12-17 | C.T. Leoncio Construction and Trading
NC 2024 |  | Region III | Bulacan | 104794 | San Pedro ES | BUSTOS |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38408138.53 | Completed | 1 | 2025-03-07 | 2025-03-07 | P00875280LZ | 24CC0493 | 2024-04-22 | 2024-04-30 | 2024-05-14 | 2024-06-03 | 2024-06-11 | C.T. Leoncio Construction and Trading
NC 2024 |  | Region III | Bulacan | 104714 | Camachile Elementary School | DOÑA REMEDIOS TRINIDAD |  | 1 | 9 | 3STY9CL | BATCH 1 | 48000000 |  |  | Ongoing | 0.38 | 2025-06-20 |  |  | 24C00646 |  |  |  |  | 2024-12-23 | ADSL Construction & Trading
NC 2024 |  | Region III | Bulacan | 104722 | Pulong Sampaloc ES | DOÑA REMEDIOS TRINIDAD |  | 1 | 6 | 2STY6CL | BATCH 1 | 31398912.71 |  |  | Completed | 1 | 2024-12-29 | 2024-12-29 |  | 24C00586 |  |  |  |  | 2024-08-06 | ADSL Construction & Trading
NC 2024 |  | Region III | Bulacan | 104722 | Pulong Sampaloc ES | DOÑA REMEDIOS TRINIDAD |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.92 | 2025-04-06 |  |  | 24C00645 |  |  |  |  | 2024-11-12 | ADSL Construction & Trading
NC 2024 |  | Region III | Bulacan | 105108 | Salacot ES | SAN MIGUEL |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.95 | 2024-12-29 |  |  | 24C00587 |  |  |  |  | 2024-08-06 | SYMS Construction Trading
NC 2024 |  | Region III | Bulacan | 105110 | San Juan ES | SAN MIGUEL |  | 1 | 8 | 4STY8CL | BATCH 2 | 40000000 |  |  | Under Procurement | 0
NC 2024 |  | Region III | Bulacan | 105087 | Sibul Elementary School | SAN MIGUEL |  | 1 | 8 | 2STY8CL | BATCH 1 | 38603892.56 |  |  | Ongoing | 0.8 | 2025-04-23 |  |  | 24C00647 |  |  |  |  | 2024-11-25 | A.C. Soliven Construction and General Merchandise
NC 2024 |  | Region III | Bulacan | 105120 | Maguinao Elementary School | SAN RAFAEL |  | 1 | 4 | 2STY4CL | BATCH 2 | 20000000 |  |  | Under Procurement | 0
NC 2024 |  | Region III | Bulacan | 158543 | Balagtas Heights Elementary School | BALAGTAS (BIGAA) |  | 1 | 8 | 4STY8CL | BATCH 1 | 36000000 |  |  | Ongoing | 0.2 | 2025-07-30 |  | P00875832LZ | 24cc0566 | 2024-09-24 | 2024-10-02 | 2024-11-08 | 2024-11-18 | 2024-11-25 | GMO Construction
NC 2024 |  | Region III | Bulacan | 104761 | Bambang ES | BOCAUE |  | 1 | 8 | 2STY8CL | BATCH 1 | 35000000 |  |  | Ongoing | 0.58 | 2025-07-30 |  |  | 24cc0510 | 2024-09-24 | 2024-10-02 | 2024-11-08 | 2024-11-18 | 2024-11-25 | C.T. Leoncio Construction & Trading
NC 2024 |  | Region III | Bulacan | 104762 | Batia ES | BOCAUE |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19451375.75 | Completed | 1 | 2025-01-19 | 2025-01-19 | P00875277LZ | 24cc0532 | 2024-06-06 | 2024-06-13 | 2024-06-27 | 2024-07-16 | 2024-07-24 | SAMJS Construction Services
NC 2024 |  | Region III | Bulacan | 104766 | Cong. E. R. Cruz Mem. School (Bocaue CS) | BOCAUE |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19402609.04 | Completed | 1 | 2025-01-19 | 2025-01-19 | P00875276LZ | 24cc0531 | 2024-06-06 | 2024-06-13 | 2024-06-27 | 2024-07-16 | 2024-07-24 | AESIC Construction
NC 2024 |  | Region III | Bulacan | 104822 | DOÑA ESCOLASTICA ALDABA PUNONGBAYAN ES | GUIGUINTO |  | 1 | 4 | 2STY4CL | GAA 17B | 40000000 |  |  | Ongoing | 0.05 | 2025-06-30 |  | P00875282LZ | 24CC0612 | 2024-11-26 | 2024-12-04 | 2024-12-17 | 2025-02-13 | 2025-02-21 | Orani Construction and Supply Corporation
NC 2024 |  | Region III | Bulacan | 104975 | Matias B. Salvador Memorial Elementary School | PANDI |  | 1 | 8 | 4STY8CL | BATCH 1 | 42560000 |  | 41288520 | Ongoing | 0.57 | 2025-03-10 |  | P00875834LZ | 24CC0544 | 2024-07-03 | 2024-07-10 | 2024-07-23 | 2024-08-05 | 2024-08-13 | C.T. Leoncio Construction & Trading
NC 2024 |  | Region III | Bulacan | 300722 | Binagbag NHS | ANGAT |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  | 14925000 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875275LZ | 24CD0181 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | SAMJS CONSTRUCTION SERVICES
NC 2024 |  | Region III | Bulacan | 105141 | Balasing Elementary School | SANTA MARIA |  | 1 | 4 | 2STY4CL | GAA 17B | 16000000 |  | 15919752.83 | Completed | 1 | 2024-11-25 | 2024-09-12 | P00875283LZ | 24CD0180 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | 1199S CONSTRUCTION
NC 2024 |  | Region III | Bulacan | 105147 | Cay Pombo ES | SANTA MARIA |  | 1 | 2 | 2STY2CL | GAA 17B | 10000000 |  | 9845122.86 | Completed | 1 | 2024-11-27 |  | P00875288LZ | 24CD0255 | 2024-06-14 | 2024-06-21 | 2024-07-04 | 2024-07-22 | 2024-07-25 | 1199S CONSTRUCTION
NC 2024 |  | Region III | Bulacan | 105150 | Garden Village ES | SANTA MARIA |  | 1 | 6 | 2STY6CL | GAA 17B | 24000000 |  | 23879897.11 | Completed | 1 | 2024-11-25 | 2024-09-12 | P00875284LZ | 24CD0184 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | FORTUNE RDC ENTERPRISES
NC 2024 |  | Region III | Bulacan | 105152 | Jose Juan Serapio ES (Catmon ES) | SANTA MARIA |  | 1 | 2 | 2STY2CL | GAA 17B | 9000000 |  | 8860076.8 | Completed | 1 | 2024-08-27 | 2024-05-30 | P00875287LZ | 24CD0179 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | FORTUNE RDC ENTERPRISES
NC 2024 |  | Region III | Bulacan | 105154 | Lalakhan ES | SANTA MARIA |  | 1 | 4 | 2STY4CL | GAA 17B | 16000000 |  | 15919946.75 | Completed | 1 | 2024-11-25 | 2024-09-12 | P00875285LZ | 24CD0182 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | SAMJS CONSTRUCTION SERVICES
NC 2024 |  | Region III | Bulacan | 105167 | Sta. Cruz ES | SANTA MARIA |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  | 14924887.76 | Completed | 1 | 2024-09-26 | 2024-09-12 | P00875286LZ | 24CD0183 | 2024-03-14 | 2024-03-21 | 2024-04-03 | 2024-04-19 | 2024-04-24 | CAF BUILDERS
NC 2024 |  | Region III | Cabanatuan City | 107110 | Calagundian Elementary School | CABANATUAN CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  | 14761144.65 | Completed | 1 | 2024-11-04 | 2024-04-24 |  | 24CF0098 | 2024-03-26 | 2024-03-27 | 2024-04-11 | 2024-04-29 | 2024-05-10 | CELSO C. FERRER CONSTRUCTION CORPORATION
NC 2024 |  | Region III | City of San Jose Del Monte | 162506 | Goldenville Elementary School | CITY OF SAN JOSE DEL MONTE |  | 1 | 6 | 3STY6CL | GAA 17B | 18000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | City of San Jose Del Monte |  | Mulawin ES | CITY OF SAN JOSE DEL MONTE |  | 1 | 8 | 4STY 8CL | BATCH 1 | 27139277.58 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | City of San Jose Del Monte | 107158 | Muzon (Pabahay 2000) Elementary School | CITY OF SAN JOSE DEL MONTE |  | 1 | 8 | 4STY8CL | GAA 17B | 22000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Gapan City | 300851 | San Roque NHS | CITY OF GAPAN |  | 1 | 8 | 4STY8CL | BATCH 1 | 26957606.83 |  | 26550027.16 | Ongoing | 0.85 | 2025-04-23 |  | 24CF0117 | 24CF0117 | 2024-04-19 | 2024-04-26 | 2024-05-08 | 2024-06-21 | 2024-07-02 | Grundstein Construction and Development Corporation
NC 2024 |  | Region III | Malolos City | 501231 | Barasoain Memorial Integrated School | CITY OF MALOLOS (Capital) |  | 1 | 15 | 3STY15CL | BATCH 1 | 45000000 |  |  | Not Yet Started | 0 | [10 empty] | Waiting for the approval, clarifications from DPWH central office-the approved amount is for 3 sty. 15cl but as per DPWH, the given amount is not sufficient- so itwas change to 3 sty. 9cl.
NC 2024 |  | Region III | Malolos City | 500404 | CITY OF MALOLOS INTEGRATED SCHOOL - ATLAG | CITY OF MALOLOS (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 30000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Malolos City | 104873 | Look 1st ES | CITY OF MALOLOS (Capital) |  | 1 | 2 | 2STY2CL | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | Waiting for the demolition of 2cl
NC 2024 |  | Region III | Meycauayan City | 104915 | Bagbaguin ES | CITY OF MEYCAUAYAN |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Nueva Ecija | 300783 | Aliaga National High School | ALIAGA |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 4435728.01 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105174 | Bucot ES | ALIAGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105268 | Curva ES | CUYAPO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105416 | Lamorito ES | GUIMBA |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 13932941.88 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105480 | Licab CS | LICAB |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105572 | Nampicuan Central School | NAMPICUAN |  | 1 | 6 | Completion of 2STY6CL | BATCH 1 | 17578197.94 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105572 | Nampicuan Central School | NAMPICUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 501820 | San Alejandro Integrated School | QUEZON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105786 | Sto. Domingo CS | SANTO DOMINGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 501821 | Bakal II Integrated School | TALAVERA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105857 | Don Cirilo B. Acosta ES | ZARAGOZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105861 | San Isidro Elementary School | ZARAGOZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105864 | Sta. Lucia (Y) ES | ZARAGOZA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105240 | Camanggahan ES | CARRANGLAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | to Gen. Luna ES, Llanera
NC 2024 |  | Region III | Nueva Ecija | 105489 | A. Bonifacio Norte ES | LLANERA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105501 | Ligaya ES | LLANERA |  | 1 | 3 | Completion of 1STY3CL | BATCH 1 | 8562691.92 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105515 | Alalay Grande ES | LUPAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105529 | San Isidro ES | LUPAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 306832 | Conversion IS | PANTABANGAN |  | 1 | 4 | Completion of 2STY4CL | BATCH 1 | 3143638.19 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 300830 | Pantabangan NHS | PANTABANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 502259 | Pantabangan West Integrated School | PANTABANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105636 | Aglipay Elementary School | RIZAL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105637 | Ballesteros ES | RIZAL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 300789 | Bicos National High School | RIZAL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 137034 | Sampaloc Elementary School | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105845 | Sto. Domingo Elementary School | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105846 | Talugtug East CS | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105850 | Villa Boado ES | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105851 | Villa Rosario ES | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | to Buted ES, Talugtug
NC 2024 |  | Region III | Nueva Ecija | 105852 | Villa Rosenda Elementary School | TALUGTUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 105205 | J. Tomacruz ES | BONGABON |  | 1 | 4 | 2STY4CL | GAA 17B | 15000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija |  | SAN ISIDRO NHS-JMPNHS ANNEX | LAUR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 300828 | Palayan City National High School | PALAYAN CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Nueva Ecija | 105614 | Peñaranda CS | PEÑARANDA |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Completed | 1
NC 2024 |  | Region III | Nueva Ecija | 502149 | Sto. Cristo Integrated School | SAN ISIDRO |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.5315
NC 2024 |  | Region III | Olongapo City | 107124 | Olongapo City ES | OLONGAPO CITY |  | 1 | 12 | 4STY12CL | GAA 17B | 20000000 |  |  | Ongoing | 0 | [10 empty] | issue with allocation, per DPWH it will be divided into phases
NC 2024 |  | Region III | Pampanga | 106124 | Mapina Elementary School | MAGALANG |  | 1 | 4 | 2STY4CL | BATCH 1 | 15000000 |  | 14920736.36 | Completed | 1 | 2024-12-16 | 2024-12-16 | P00875843LZ | 24CI0099 | 2024-08-05 | 2024-05-17 | 2024-05-29 | 2024-09-06 | 2024-06-20 | GMO CONSTRUCTION
NC 2024 |  | Region III | Pampanga | 105966 | FLORIDABLANCA ELEMENTARY SCHOOL | FLORIDABLANCA |  | 1 | 4 | 2STY4CL | BATCH 2 | 15131250 |  | 14723770.97 | Ongoing | 0.35 | 2025-05-31 |  | P00876031LZ | 24CH0151 | 2024-12-11 | 2024-11-19 | 2024-03-12 | 2024-12-13 | 2024-12-27 | D MASTERS V2 BUILDERS OPC
NC 2024 |  | Region III | Pampanga | 106049 | Prado Siongco ES | LUBAO |  | 1 | 4 | 1STY4CL | BATCH 1 | 10000000 |  | 9750995.12 | Completed | 1 | 2024-02-12 | 2024-02-12 | P00875844LZ | 24CH0141 | 2024-11-06 | 2024-06-18 | 2024-02-07 | 2024-07-16 | 2024-07-30 | V. TRILLANA BUILDERS & TRADING
NC 2024 |  | Region III | Pampanga | 106222 | Manibaug Paralaya ES | PORAC |  | 1 | 16 | 4STY16CL | BATCH 1 | 40000000 |  | 38964266.8 | Ongoing | 0.25 | 2025-09-10 |  | P00875845LZ | 24CH0150 | 2024-12-11 | 2024-11-19 | 2024-12-17 | 2024-12-23 | 2025-06-01 | V. TRILLANA BUILDERS & TRADING | MODIFIED TO 3STY12CL
NC 2024 |  | Region III | Pampanga | 300884 | Camba NHS | ARAYAT |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9464332.92 | Completed | 1 | 2024-10-19 | 2024-10-19 | P00875327LZ | 24CG0191 | 2024-09-05 | 2024-05-17 | 2024-05-30 | 2024-10-06 | 2024-06-14 | N.T. TULABUT CONSTRUCTION & SUPPLY
NC 2024 |  | Region III | Pampanga |  | BACOLOR CENTRAL INTEGRATED SCHOOL | BACOLOR |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 18933553.02 | Completed | 1 | 2024-12-23 | 2024-12-23 | P00875330LZ | 24CG0219 | 2024-11-06 | 2024-06-19 | 2024-02-07 | 2024-11-07 | 2024-07-17 | EL KAPITAN COSTRUCTION SERVICES
NC 2024 |  | Region III | Pampanga | 306901 | San Vicente Pilot School for Philippine Craftsmen | BACOLOR |  | 1 | 20 | 4STY20CL | GAA 17B | 50000000 |  | 47195668.94 | Ongoing | 0.75 | 2025-08-02 |  | P00875325LZ | 24CG0200 | 2024-09-05 | 2024-05-17 | 2024-05-30 | 2024-10-06 | 2024-06-14 | N.T. TULABUT CONSTRUCTION & SUPPLY | Suspended
NC 2024 |  | Region III | Pampanga | 300896 | Malino NHS | MEXICO |  | 1 | 12 | 4STY12CL | GAA 17B | 32000000 |  | 31840000 | Completed | 1 | 2025-07-01 | 2025-07-01 | P00875328LZ | 24CG0199 | 2024-09-05 | 2024-05-17 | 2024-05-30 | 2024-10-06 | 2024-06-14 | CHARIOT'S CONSTRUCTION AND TRADING
NC 2024 |  | Region III | Pampanga | 106276 | San Agustin ES | SANTA ANA |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  | 10413571.42 | Completed | 1 | 2024-10-19 | 2024-10-19 | P00875326LZ | 24CG0193 | 2024-09-05 | 2024-05-17 | 2024-05-30 | 2024-10-06 | 2024-06-14 | N.T. TULABUT CONSTRUCTION & SUPPLY
NC 2024 |  | Region III | Pampanga | 300906 | Pasig NHS | CANDABA |  | 1 | 6 | 2STY6CL | BATCH 1 | 15000000 |  | 14172112.29 | Completed | 1 | 2024-12-12 | 2025-12-03 | P00875846LZ | 24CG0218 | 2024-11-06 | 2024-06-19 | 2024-02-07 | 2024-11-07 | 2024-07-17 | ST. LOUISE PRIME BUILDERS & DEVELOPMENT CORP.
NC 2024 |  | Region III | Pampanga | 106113 | Sta. Lutgarda ES | MACABEBE |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7547791.5 | Completed | 1 | 2024-09-28 | 2025-01-21 | P00875333LZ | 24CG0178 | 2024-04-24 | 2024-02-05 | 2024-05-14 | 2024-05-23 | 2024-05-29 | ECA CAYANAN'S CONSTRUCTION
NC 2024 |  | Region III | Pampanga | 106157 | San Nicolas Elementary School | MASANTOL |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7556874.39 | Ongoing | 0.9 | 2025-01-12 |  | P00875332LZ | 24CG0153 | 2024-03-26 | 2024-03-04 | 2024-04-16 | 2024-04-26 | 2024-03-05 | CHOLO CONSTRUCTION & TRADING
NC 2024 |  | Region III | Pampanga |  | PEDRITA NHS | MINALIN |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7960000 | Ongoing | 0.5 | 2025-06-25 |  | P00875335LZ | 24CG0264 | 2024-07-29 | 2024-06-08 | 2024-08-20 | 2025-06-01 | 2025-01-16 | ST. LOUISE PRIME BUILDERS & DEVELOPMENT CORP.
NC 2024 |  | Region III | Pampanga | 306944 | San Luis NHS | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7960000 | Completed | 1 | 2024-09-15 | 2024-09-15 | P00875336LZ | 24CG0163 | 2024-04-04 | 2024-12-04 | 2024-04-25 | 2024-06-05 | 2024-05-17 | SMARTBUILD CONSTRUCTION AND TRADING
NC 2024 |  | Region III | Pampanga |  | STA. LUCIA ES | SAN LUIS |  | 1 | 2 | 1STY2CL | GAA 17B | 8000000 |  | 7960000 | Completed | 1 | 2024-09-15 | 2024-09-15 | P00875334LZ | 24CG0162 | 2024-04-04 | 2024-12-04 | 2024-04-25 | 2024-06-05 | 2024-05-17 | ST. LOUISE PRIME BUILDERS & DEVELOPMENT CORP.
NC 2024 |  | Region III | San Fernando City | 307603 | Panipuan High School | CITY OF SAN FERNANDO (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 17000000 |  | 16213026.23 | Ongoing | 0.9 | 2024-11-20 | [8 empty] | Geoheart Construction and Trading
NC 2024 |  | Region III | San Fernando City | 107195 | San Fernando Elementary School | CITY OF SAN FERNANDO (Capital) |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 16662637.43 | Completed | 1 | 2024-11-04 | 2025-03-14 | [7 empty] | Three in One Construction and Trading
NC 2024 |  | Region III | Science City of Muñoz | 300824 | Munoz National HS-Main | SCIENCE CITY OF MUÑOZ |  | 1 | 20 | 4STY20CL | BATCH 1 | 55000000 |  | 54451667.13 | Ongoing | 0.2 | 2025-05-27 |  | 24CE0316 | 24CE0316 | 2024-04-04 | 2024-11-04 | 2024-04-23 |  |  | WIZARD CONCRETE SOLUTIONS AND CONSTRUCTION CORP. | on going construction
NC 2024 |  | Region III | Science City of Muñoz | 105557 | Rizal ES | SCIENCE CITY OF MUÑOZ |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4950189.55 | Ongoing | 0.98 | 2024-08-13 |  | 24CE0273 | 24CE0273 | 2023-03-13 |  | 2024-02-04 |  |  | NINA`S CONSTRUCTION AND SUPPLIES | on going construction
NC 2024 |  | Region III | Tarlac | 106590 | San Juan De Milla Elementary School | PANIQUI |  | 1 | 6 | 2STY6CL | BATCH 1 | 22399936 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 106606 | Singat PS | PURA |  | 1 | 3 | 1STY3CL | GAA 17B | 12000000 |  |  | Completed | 1 |  |  |  | 24CE0316
NC 2024 |  | Region III | Tarlac | 305973 | Santa Ignacia National High School | SANTA IGNACIA |  | 1 | 5 | 1STY5CL | GAA 17B | 28000000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 501833 | Calayaan Integrated School | GERONA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 106467 | Cardona ES | GERONA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 502198 | Burgos Integrated School | SAN JOSE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 300969 | Mababanaba High School | SAN JOSE |  | 1 | 12 | 3STY12CL | BATCH 1 | 45202254 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 501213 | Don Casimiro G. Tanedo Integrated School | VICTORIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 106310 | Anupul ES | BAMBAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5450000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 106367 | Angelina Dizon Jimenez ES (Sto. Domingo ES) | CAPAS |  | 1 | 4 | 2STY4CL | GAA 17B | 12740000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Tarlac | 106400 | Malupa ES | CONCEPCION |  | 1 | 6 | 2STY6CL | GAA 17B | 16360000 |  |  | Completed | 1
NC 2024 |  | Region III | Tarlac | 106504 | Rizal Multigrade | LA PAZ |  | 1 | 2 | 1STY2CL | GAA 17B | 5450000 |  |  | Not Yet Started | 0
NC 2024 |  | Region III | Tarlac City | 500390 | Armenia Integrated School | CITY OF TARLAC (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925420.4 | Completed | 1 | 2024-06-21
NC 2024 |  | Region III | Tarlac City | 106739 | Don Pepe Cojuangco Homes ES | CITY OF TARLAC (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Not Yet Started | 0 | [10 empty] | SITE OWNERSHIP ISSUE
NC 2024 |  | Region III | Tarlac City | 106720 | San Juan De Mata ES | CITY OF TARLAC (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4987500 | Completed | 1
NC 2024 |  | Region III | Tarlac City | 501518 | Sapang Maragul Integrated School | CITY OF TARLAC (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4923795.19 | Completed | 1 | 2024-07-12
NC 2024 |  | Region III | Tarlac City | 500557 | Sto. Cristo IS | CITY OF TARLAC (Capital) |  | 1 | 12 | 4STY12CL | BATCH 1 | 51600000 |  |  | Completed | 1
NC 2024 |  | Region III | Zambales | 106854 | Balaybay Elementary School | CASTILLEJOS |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.85
NC 2024 |  | Region III | Zambales | 160513 | Josephine F. Khonghun Special Education Center | SUBIC |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  |  | Ongoing | 0.8
NC 2024 |  | Region III | Zambales | 106848 | Pinagrealan Elementary School | CANDELARIA |  | 1 | 4 | 1STY4CL | GAA 17B | 12000000 |  |  | Ongoing | 0.9
NC 2024 |  | Region III | Zambales | 106849 | San Roque Elementary School | CANDELARIA |  | 1 | 6 | 2STY6CL | BATCH 1 | 15600000 |  |  | Ongoing | 0.9
NC 2024 |  | Region III | Zambales | 301017 | La Paz National High School | SAN NARCISO |  | 1 | 6 | 2STY6CL | GAA 17B | 18000000 |  |  | Ongoing | 0.8
NC 2024 |  | Region III | Zambales | 106988 | Acoje Elementary School | SANTA CRUZ |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  |  | Ongoing | 0.9

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.