## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | No. of Sites Reverted | No. of Sites Not yet started | No. of Sites Under Procurement | No. of Sites On Going | No. of Sites Completed | No. of CL Reverted | No. of CL Not yet started | No. of CL Under Procurement | No. of CL On Going | No. of CL Completed | No. of Sites Terminated | No. of CL Terminated | Status as of July 11, 2025
REPAIR 2020 | Region IV-A | Antipolo City | 109339 | San Isidro ES |  | 1 | 1 | 17 | Repair of Classrooms | 3736502 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region IV-A | Antipolo City | 109347 | Binayoyo ES | CITY OF ANTIPOLO | 2 | 1 | 12 | Repair of Classrooms | 2281358 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2 | 1 | 33 | Repair of Classrooms | 7994549.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 33 | 0 | 0
REPAIR 2020 | Region IV-A | Antipolo City | 109338 | Peñafrancia ES Annex | CITY OF ANTIPOLO | 2 | 1 | 6 | Repair of Classrooms | 1859001 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Antipolo City | 109357 | Rizza ES | CITY OF ANTIPOLO | 2 | 1 | 8 | Repair of Classrooms | 1205668 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107403 | Dayapan ES | LEMERY | 1 | 1 | 4 | Repair of Classrooms | 813141 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107392 | Talaga Elementary School | LEMERY | 1 | 1 | 15 | Repair of Classrooms | 6362453 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107825 | Gregorio Agoncillo Elementary School | TUY | 1 | 1 | 13 | Repair of Classrooms | 5441535 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107202 | Agoncillo Central School | AGONCILLO | 3 | 1 | 3 | Repair of Classrooms | 882972 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 307705 | Agoncillo National High School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1549056 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107205 | Banyaga Elementary School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1206729 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 301076 | Banyaga National High School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 1226698 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107207 | Bilibinwang Elementary School | AGONCILLO | 3 | 1 | 2 | Repair of Classrooms | 616467 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107212 | Pook Elementary School | AGONCILLO | 3 | 1 | 9 | Repair of Classrooms | 616467 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107213 | Subic Elementary School | AGONCILLO | 3 | 1 | 4 | Repair of Classrooms | 959460 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107338 | Col. Pedro Pasia Memorial School | CUENCA | 3 | 1 | 19 | Repair of Classrooms | 5539065 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 301100 | Fermin La Rosa National High School | CUENCA | 3 | 1 | 12 | Repair of Classrooms | 2074812 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107367 | As-Is Elementary School | LAUREL | 3 | 1 | 4 | Repair of Classrooms | 1557093 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107370 | Bignay Primary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 603365 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107371 | Bugaan Integrated School | LAUREL | 3 | 1 | 7 | Repair of Classrooms | 2089701 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107372 | Buso-Buso Elementary School | LAUREL | 3 | 1 | 9 | Repair of Classrooms | 2648916 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107374 | Laurel Central School | LAUREL | 3 | 1 | 11 | Repair of Classrooms | 5112153 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 163517 | Martin Esperanza Elementary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 591592 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107377 | Niyugan Elementary School | LAUREL | 3 | 1 | 5 | Repair of Classrooms | 2432662 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107378 | Paliparan Elementary School | LAUREL | 3 | 1 | 3 | Repair of Classrooms | 1204785 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107380 | San Gabriel Elementary School | LAUREL | 3 | 1 | 5 | Repair of Classrooms | 2360701 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107383 | Sta. Maria Elementary School | LAUREL | 3 | 1 | 2 | Repair of Classrooms | 1234099 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas | 107572 | Rosario West Central School | ROSARIO | 4 | 1 | 13 | Repair of Classrooms | 6376574 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109587 | Banaba South ES | BATANGAS CITY (Capital) | 5 | 1 | 8 | Repair of Classrooms | 2560001 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109546 | Bilogo ES | BATANGAS CITY (Capital) | 5 | 1 | 5 | Repair of Classrooms | 1600000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109564 | Dela Paz Itaas ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1000335 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109603 | Dumuclay ES | BATANGAS CITY (Capital) | 5 | 1 | 7 | Repair of Classrooms | 2147232 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109617 | Lilinggiwan ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | Repair of Classrooms | 652643 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109579 | Talahib Payapa ES | BATANGAS CITY (Capital) | 5 | 1 | 4 | Repair of Classrooms | 1342702 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109557 | Talumpok Proper ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 998072 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Batangas City | 109580 | Tibig ES | BATANGAS CITY (Capital) | 5 | 1 | 6 | Repair of Classrooms | 1972311 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Binan City | 164511 | Dr. Jose Tamayo MES | CITY OF BIÑAN | 5 | 1 | 8 | Repair of Classrooms | 507252 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Binan City | 108227 | Platero ES | CITY OF BIÑAN | 5 | 1 | 22 | Repair of Classrooms | 3106003 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2020 | Region IV-A | Binan City | 108229 | San Vicente ES | CITY OF BIÑAN | 5 | 1 | 27 | Repair of Classrooms | 3583812 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 27 | 0 | 0
REPAIR 2020 | Region IV-A | Binan City | 108215 | Tomas A. Turalba Memorial Elementary | CITY OF BIÑAN | 5 | 1 | 8 | Repair of Classrooms | 1006701 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Binan City | 164512 | Zapote ES | CITY OF BIÑAN | 5 | 1 | 10 | Repair of Classrooms | 1443118 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Cabuyao City | 108234 | Baclaran Elementary School | CABUYAO | 2 | 1 | 8 | Repair of Classrooms | 3796819 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Cabuyao City | 108238 | Butong Elementary School | CABUYAO | 2 | 1 | 4 | Repair of Classrooms | 1936897 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Cabuyao City | 108243 | Gulod Elementary School | CABUYAO | 2 | 1 | 4 | Repair of classrooms/toilets | 1714134 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Calamba City | 109816 | Jose Platon MS | CITY OF CALAMBA | 2 | 1 | 15 | Repair of Classrooms | 3025658 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region IV-A | Calamba City | 109833 | Looc ES | CITY OF CALAMBA | 2 | 1 | 21 | Repair of Classrooms | 2606952 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0
REPAIR 2020 | Region IV-A | Calamba City | 109858 | Punta Elementary School | CITY OF CALAMBA | 2 | 1 | 12 | Repair of Classrooms | 2340802 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Calamba City | 109838 | San Juan Elementary School | CITY OF CALAMBA | 2 | 1 | 7 | Repair of Classrooms | 1114794 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Calamba City | 109863 | Ulango Elementary School | CITY OF CALAMBA | 2 | 1 | 4 | Repair of Classrooms | 1329429 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107937 | Bulihan ES | GMA | 5 | 1 | 8 | Repair of Classrooms | 3518909 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107939 | Family Village Resources ES | GMA | 5 | 1 | 4 | Repair of Classrooms | 2080029 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301202 | Lumil NHS | Silang | 5 | 1 | 8 | Repair of Classrooms | 4328589 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108116 | Mataas na Burol ES | Silang | 5 | 1 | 2 | Repair of Classrooms | 1065511 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301199 | Lucsuhin NHS | Alfonso | 7 | 1 | 4 | Repair of Classrooms | 1762538 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107860 | Loma ES | Amadeo | 7 | 1 | 6 | Repair of Classrooms | 3244084 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301217 | Talon National High School | Amadeo | 7 | 1 | 12 | Repair of Classrooms | 5659631 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108003 | Agus-Os ES | Indang | 7 | 1 | 6 | Repair of Classrooms | 2730777 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301167 | Amaya Sch. of Home Industries | Tanza | 7 | 1 | 16 | Repair of Classrooms | 6753518 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301219 | Tanza National Trade School | Tanza | 7 | 1 | 12 | Repair of Classrooms | 6782126 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108179 | Bagong Pook ES | Trece Martires City | 7 | 1 | 8 | Repair of Classrooms | 3528386 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108180 | Conchu ES | Trece Martires City | 7 | 1 | 10 | Repair of Classrooms | 4943386 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108184 | Lapidario ES | Trece Martires City | 7 | 1 | 13 | Repair of Classrooms | 5864012 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108185 | Osorio ES | Trece Martires City | 7 | 1 | 18 | Repair of Classrooms | 8564806 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 164014 | Southville ES | Trece Martires City | 7 | 1 | 10 | Repair of Classrooms | 4355169 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301165 | Alfonso National High School | Alfonso | 8 | 1 | 8 | Repair of Classrooms | 5018720 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107841 | Bilog ES | Alfonso | 8 | 1 | 6 | Repair of Classrooms | 3261082 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107843 | Esperanza ES | Alfonso | 8 | 1 | 6 | Repair of Classrooms | 3360912 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107934 | Narvaez ES | GEA | 8 | 1 | 2 | Repair of Classrooms | 1181930 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 107935 | Tabora ES | GEA | 8 | 1 | 2 | Repair of Classrooms | 1178657 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108041 | Layong Mabilog ES | Maragondon | 8 | 1 | 2 | Repair of Classrooms | 1106870 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108043 | Maragondon ES | Maragondon | 8 | 1 | 12 | Repair of Classrooms | 5957416 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301204 | Maragondon NHS | Maragondon | 8 | 1 | 15 | Repair of Classrooms | 7685021 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 108040 | Marcelo D. Samaniego ES (former Bucal IV ES) | Maragondon | 8 | 1 | 3 | Repair of Classrooms | 1674148 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite | 301169 | Constancio E. Aure Sr. NHS (Asis NHS) | Mendez | 8 | 1 | 12 | Repair of Classrooms | 6098488 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite City | 109635 | Dalahican Elem. School | CAVITE CITY | 1 | 1 | 4 | Repair of Classrooms | 2150367 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Cavite City | 109633 | Ovidio S. Dela Rosa ES | CAVITE CITY | 1 | 1 | 4 | Repair of Classrooms | 1039842 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Dasmarinas City | 301187 | Pag-asa NHS (Dasmarinas NHS - Pag-asa Annex) | CITY OF DASMARIÑAS | 4 | 1 | 6 | Repair of Classrooms | 1815112 | 1 | 1815111.48 | COMPLETED | 1 | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Dasmarinas City | 107912 | Salawag ES | CITY OF DASMARIÑAS | 4 | 1 | 14 | Repair of Classrooms | 4599517 | 1 | 4599516.34 | COMPLETED | 1 | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IV-A | Dasmarinas City | 107914 | Z. H. Gana Mem. Sch. (San Jose) | CITY OF DASMARIÑAS | 4 | 1 | 4 | Repair of Classrooms | 1278118 | 1 | 1278117.33 | COMPLETED | 1 | 2021-01-10 | 2020-12-09 | CY2020 BEFF RRC C1 |  | 2019-11-26 | 2019-12-04 | 2019-12-16 | 2020-01-13 |  | R. A. DEL ROSARIO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Gen. Trias City | 107944 | Angel L. Bawalan ES (Alingaro ES) | CITY OF GENERAL TRIAS | 6 | 1 | 5 | Repair of Classrooms | 2718895 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Gen. Trias City | 107959 | Diego Mojica MS | CITY OF GENERAL TRIAS | 6 | 1 | 15 | Repair of Classrooms | 7358248 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2020 | Region IV-A | Gen. Trias City | 107947 | Gen. Trias MES | CITY OF GENERAL TRIAS | 6 | 1 | 11 | Repair of Classrooms | 4946085 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region IV-A | Gen. Trias City | 107950 | Luis Ferrer III MES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 2522689 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Gen. Trias City | 107951 | Manggahan ES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 3400058 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Imus City | 107969 | Anabu II Elementary School | IMUS | 3 | 1 | 14 | Repair of Classrooms | 4926134 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IV-A | Imus City | 107974 | Imus Pilot Elementary School | IMUS | 3 | 1 | 4 | Repair of Classrooms | 1748352 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108429 | Sampaguita Village ES | SAN PEDRO | 1 | 1 | 8 | Repair of Classrooms | 3458474 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 307907 | San Pedro Relocation Center NHS, Main (Langgam) Campus | SAN PEDRO | 1 | 1 | 21 | Repair of Classrooms | 8878108 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 21 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108201 | Bitin ES | BAY | 2 | 1 | 7 | Repair of Classrooms | 2852805 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108203 | Maitim ES | BAY | 2 | 1 | 3 | Repair of Classrooms | 1296378 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108210 | Sto. Domingo ES | BAY | 2 | 1 | 10 | Repair of Classrooms | 3948040 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3 | 1 | 10 | Repair of Classrooms | 3861753 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108253 | Balayhangin ES | CALAUAN | 3 | 1 | 8 | Repair of Classrooms | 3024363 | 1 |  | COMPLETED | 1 |  |  |  |  | 2018-11-23 | 2018-12-14 | 2019-12-27 | 2019-08-02 | 2019-08-09 | MICLOVER GEN. CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108351 | Abo- Bukal ES | NAGCARLAN | 3 | 1 | 10 | Repair of Classrooms | 3780806 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108359 | Labangan ES | NAGCARLAN | 3 | 1 | 4 | Repair of Classrooms | 1457353 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108373 | Yukos ES Annex | NAGCARLAN | 3 | 1 | 6 | Repair of Classrooms | 2707348 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 301248 | Lumot NHS | CAVINTI | 4 | 1 | 13 | Repair of Classrooms | 5333167 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108282 | Talaongan West ES | CAVINTI | 4 | 1 | 2 | Repair of Classrooms | 792989 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108296 | F.S. Brosas MES | LILIW | 4 | 1 | 5 | Repair of Classrooms | 1832132 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108323 | Balubad ES | LUMBAN | 4 | 1 | 2 | Repair of Classrooms | 822837 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108324 | Caliraya ES | LUMBAN | 4 | 1 | 3 | Repair of Classrooms | 1076827 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108293 | E.G. Olarte ES | MABITAC | 4 | 1 | 3 | Repair of Classrooms | 1222658 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 164504 | San Miguel ES | MABITAC | 4 | 1 | 4 | Repair of Classrooms | 730364 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 164531 | Munting Kawayan ES | MAJAYJAY | 4 | 1 | 1 | Repair of Classroom | 376471 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 301268 | Sta. Catalina NHS | MAJAYJAY | 4 | 1 | 5 | Repair of Classrooms | 2654182 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108350 | Suba ES | MAJAYJAY | 4 | 1 | 3 | Repair of Classrooms | 1194039 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108375 | Paete CES | PAETE | 4 | 1 | 16 | Repair of Classrooms | 5833108 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108382 | M. Z. Lanuza ES | PAGSANJAN | 4 | 1 | 2 | Repair of Classrooms | 841515 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108387 | San Isidro ES | PAGSANJAN | 4 | 1 | 6 | Repair of Classrooms | 2376771 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108388 | Unson ES | PAGSANJAN | 4 | 1 | 4 | Repair of Classrooms | 1444867 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108397 | J.Z. Fernandez MES | PAKIL | 4 | 1 | 3 | Repair of Classrooms | 1179649 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108406 | Concepcion-Mojon E/S | PILA | 4 | 1 | 7 | Repair of Classrooms | 2475101 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108420 | Cuyab ES | SAN PEDRO | 4 | 1 | 7 | Repair of Classrooms | 2872892 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 342346 | Laguna SHS | SANTA CRUZ | 4 | 1 | 1 | Repair of Classroom | 612269 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108443 | Palasan ES | SANTA CRUZ | 4 | 1 | 8 | Repair of Classrooms | 3395768 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 164507 | New Little Baguio ES | SANTA MARIA | 4 | 1 | 2 | Repair of Classrooms | 761982 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108464 | PARANG NG BUHO ELEM. SCHOOL | SANTA MARIA | 4 | 1 | 4 | Repair of Classrooms | 1521878 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Laguna | 108493 | Palanas ES | SINILOAN | 4 | 1 | 4 | Repair of Classrooms | 1540458 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109658 | Abundio Torre Memorial Elementary School | LIPA CITY | 4 | 1 | 8 | Repair of Classrooms | 1397581 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 4 | 1 | 6 | Repair of Classrooms | 3643773 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109660 | Bulacnin ES | Lipa City | 4 | 1 | 5 | Repair of Classrooms | 1273544 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 301489 | Bulacnin NHS | Lipa City | 4 | 1 | 23 | Repair of Classrooms | 4986899 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 23 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 4 | 1 | 17 | Repair of Classrooms | 4955247 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 4 | 1 | 2 | Repair of Classrooms | 936336 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109695 | Paninsingin ES | LIPA CITY | 4 | 1 | 7 | Repair of Classrooms | 2933558 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109687 | San Sebastian ES | LIPA CITY | 4 | 1 | 3 | Repair of Classrooms | 1703412 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109705 | Tangway Loob ES | LIPA CITY | 4 | 1 | 8 | Repair of Classrooms | 3772262 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 301488 | Bugtongnapulo NHS | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6101653 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109674 | Cumba-Quezon ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2420000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109681 | Malagonlong ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1024241 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109654 | Sto. Niño ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 1498468 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109655 | Sto. Toribio ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2574861 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Lipa City | 109704 | Tangway ES | LIPA CITY | 6 | 1 | 17 | Repair of Classrooms | 2010303 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 17 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 109730 | Dalahican Elementary School | LUCENA CITY (Capital) | 2 | 1 | 10 | Repair of Classrooms | 4097038 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 167503 | Dalahican ES Annex | LUCENA CITY (Capital) | 2 | 1 | 4 | Repair of Classrooms | 1319563 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 109741 | Domoit Elementary School | LUCENA CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 2457753 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 308503 | Gulang-Gulang NHS | LUCENA CITY (Capital) | 2 | 1 | 22 | Repair of Classrooms | 8145631 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 22 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 109737 | Ibabang Iyam ES | LUCENA CITY (Capital) | 2 | 1 | 11 | Repair of Classrooms | 3858173 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 | 1 | 16 | Repair of Classrooms | 5279994 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 109714 | Lucena East VII Elementary School | LUCENA CITY (Capital) | 2 | 1 | 6 | Repair of Classrooms | 2319110 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Lucena City | 109732 | Lucena South II Elementary School | LUCENA CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 4647094 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108562 | Cabugao ES | BURDEOS | 1 | 1 | 5 | Repair of Classrooms | 3416495 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108786 | Gumian ES | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 894813 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108789 | Libjo Elementary School | INFANTA | 1 | 1 | 4 | Repair of Classrooms | 1164616 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108983 | Gango ES | JOMALIG | 1 | 1 | 4 | Repair of Classrooms | 2797662 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108891 | Concepcion ES | MAUBAN | 1 | 1 | 5 | Repair of Classrooms | 1376750 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108636 | Candelaria Elementary School 1 & 2 | CANDELARIA | 2 | 1 | 12 | Repair of Classrooms | 3539600 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108618 | KINATIHAN II ES | CANDELARIA | 2 | 1 | 7 | Repair of Classrooms | 2592006 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108678 | Don Eulogio Capino ES | DOLORES | 2 | 1 | 6 | Repair of Classrooms | 2216058 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108679 | Don Eulogio Capino ES Annex (Putol) | DOLORES | 2 | 1 | 5 | Repair of Clas+R357+N355 | 2026980 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108682 | Pedro Bombane ES | DOLORES | 2 | 1 | 3 | Repair of classrooms/toilets | 926963 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 109112 | San Antonio CS | SAN ANTONIO | 2 | 1 | 7 | Repair of Classrooms | 2929484 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 165001 | Bagong Silang ES | BUENAVISTA | 3 | 1 | 6 | Repair of Classrooms | 3214035 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108536 | Batabat ES | BUENAVISTA | 3 | 1 | 4 | Repair of classrooms/toilets | 1883276 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108555 | Villa Veronica ES | BUENAVISTA | 3 | 1 | 1 | Repair of Classroom | 564648 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS - Tagabas Ibaba Ext) | CATANAUAN | 3 | 1 | 3 | Repair of Classrooms | 1225610 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 301282 | Ajos National High School | MULANAY | 3 | 1 | 8 | Repair of Classrooms | 3681693 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108924 | Burgos ES | MULANAY | 3 | 1 | 7 | Repair of Classrooms | 2904311 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 301394 | San Isidro NHS, Padre Burgos | PADRE BURGOS | 3 | 1 | 8 | Repair of Classrooms | 3419402 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 109125 | Look Awasan ES | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | Repair of Classrooms | 3443009 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 109141 | Busokbusokan Elementary School | SAN NARCISO | 3 | 1 | 1 | Repair of Classroom | 605617 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 8 | Repair of Classrooms | 2516266 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108521 | Malusak ES | ATIMONAN | 4 | 1 | 10 | Repair of Classrooms | 5296233 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108597 | Cunalum ES | CALAUAG | 4 | 1 | 2 | Repair of Classrooms | 1334835 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108606 | Pinagkamaligan ES | CALAUAG | 4 | 1 | 3 | Repair of Classrooms | 1402288 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108752 | Bamban ES | GUMACA | 4 | 1 | 3 | Repair of Classrooms | 1759020 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Quezon | 108815 | Rosario ES | LOPEZ | 4 | 1 | 1 | Repair of Classroom | 459795 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109311 | Dona Nieves Songco MES | Angono | 1 | 1 | 4 | Repair of Classrooms | 1158203 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109374 | Bangad ES | Binangonan | 1 | 1 | 9 | Repair of Classrooms | 3293120 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 301445 | Janosa NHS | Binangonan | 1 | 1 | 6 | Repair of Classrooms | 2689105 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109369 | Macamot ES | BINANGONAN | 1 | 1 | 6 | Repair of Classrooms | 1997198 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109371 | Pilapila ES | Binangonan | 1 | 1 | 8 | Repair of Classrooms | 3000675 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109399 | Francisco P. Felix ES Unit 1 | CAINTA | 1 | 1 | 12 | Repair of classrooms | 3456558 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109406 | Saint Anthony ES | CAINTA | 1 | 1 | 19 | Repair of classrooms | 5015368 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109409 | San Juan Elementary School | CAINTA | 1 | 1 | 6 | Repair of classrooms | 902993 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109411 | St. Joseph ES | CAINTA | 1 | 1 | 6 | Repair of classrooms | 772619 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109542 | San Francisco ES | Taytay | 1 | 1 | 4 | Repair of Classrooms | 989591 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109533 | Sta. Ana ES | Taytay | 1 | 1 | 8 | Repair of Classrooms | 2147633 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109427 | Malalim ES | Baras | 2 | 1 | 9 | Repair of Classrooms | 1938313 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109421 | Subay ES | Cardona | 2 | 1 | 5 | Repair of Classrooms | 2157759 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 308120 | Jalajala NHS | Jalajala | 2 | 1 | 8 | Repair of Classrooms | 2197501 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 165503 | Hulo ES | Pililla | 2 | 1 | 8 | Repair of Classrooms | 2549915 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109452 | Matagbak ES | Pililla | 2 | 1 | 2 | Repair of Classrooms | 777922 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109470 | Macabud ES | Rodriguez | 2 | 1 | 8 | Repair of Classrooms | 1485871 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 301449 | Mascap NHS | Rodriguez | 2 | 1 | 4 | Repair of Classrooms | 1786744 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 301451 | Montalban Heights NHS | Rodriguez | 2 | 1 | 14 | Repair of Classrooms | 4147244 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 301460 | Jose F. Diaz MNHS | San Mateo | 2 | 1 | 3 | Repair of Classrooms | 1154908 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 109502 | Cayabu ES | Tanay | 2 | 1 | 1 | Repair of Classroom | 348116 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 308138 | Tanay West NHS | TANAY | 2 | 1 | 12 | Repair of Classrooms | 2565674 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2020 | Region IV-A | Rizal | 308123 | Pantay NHS | Teresa | 2 | 1 | 10 | Repair of Classrooms | 2403242 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109788 | C.M. Azcarate Elementary School | SAN PABLO CITY | 3 | 1 | 10 | Repair of Classrooms | 4280501 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109781 | Fule Almeda Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms & Covered Pathway | 2407838 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109782 | Major Juan Eseo Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms | 3961119 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | SAN PABLO CITY | 3 | 1 | 3 | Repair of Classrooms & Covered Pathway | 3046850 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109769 | San Crispin Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms | 3489626 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 301503 | San Cristobal National High School | SAN PABLO CITY | 3 | 1 | 6 | Repair of Classrooms & Covered Pathway | 3487254 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109808 | San Diego Elementary School | SAN PABLO CITY | 3 | 1 | 1 | Repair of Classrooms & Covered Pathway | 1579633 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | San Pablo City | 109754 | San Gabriel Elementary School | SAN PABLO CITY | 3 | 1 | 7 | Repair of Classrooms & Covered Pathway | 4071014 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 6 | Repair of Classrooms | 2836803 | 1 | 628546.8 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-002 | R4A-STA.ROSA-2019-01 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108484 | Sinalhan Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 584002 | 1 | 555634.92 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Sta. Rosa City | 251501 | Southville 4 Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 770721 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Sta. Rosa City | 108485 | Tagapo Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | Repair of Classrooms | 830666 | 1 | 555634.92 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 321602 | BALELE HIS | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 2702927 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107769 | NATATAS ES | CITY OF TANAUAN | 3 | 1 | 5 | Repair of Classrooms | 1838936 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107746 | Ambulong ES | CITY OF TANAUAN | 3 | 1 | 13 | Repair of Classrooms | 6592443 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 13 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107750 | Banadero ES | CITY OF TANAUAN | 3 | 1 | 7 | Repair of Classrooms | 4180287 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107755 | BOOT ES | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 3547896 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107758 | GONZALES ES | CITY OF TANAUAN | 3 | 1 | 8 | Repair of Classrooms | 4727664 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107759 | Hidalgo Elementary School | CITY OF TANAUAN | 3 | 1 | 6 | Repair of Classrooms | 1015976 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107761 | JANOPOL ORIENTAL ES | CITY OF TANAUAN | 3 | 1 | 10 | Repair of Classrooms | 4731762 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107766 | MARIA PAZ ES | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 5934108 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107767 | MAUGAT ELEMENTARY SCHOOL | CITY OF TANAUAN | 3 | 1 | 1 | Repair of Classroom | 669396 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 301128 | NATATAS NATIONAL HIGH SCHOOL | CITY OF TANAUAN | 3 | 1 | 6 | Repair of Classrooms | 2345842 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107780 | Paaralang Sentral ng Talaga | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 3195329 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107780 | Paaralang Sentral ng Talaga | CITY OF TANAUAN | 3 |  | 6 | Repair of Classrooms | 394703 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107773 | Sala ES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 2817668 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 301154 | TANAUAN SCHOOL OF FISHERIES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 4411730 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 107787 | WAWA ES | CITY OF TANAUAN | 3 | 1 | 3 | Repair of Classrooms | 1763211 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2020 | Region IV-A | Tanauan City | 301163 | Wawa NHS | CITY OF TANAUAN | 3 | 1 | 4 | Repair of Classrooms | 1922021 | 1 |  | COMPLETED | 1 | [10 empty] | For Award | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS | 1 | 1 | 4 | Repair of Classrooms | 1571379 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Tayabas City | 109235 | Katigan-Alupay ES | CITY OF TAYABAS | 1 | 1 | 4 | Repair of Classrooms | 1760000 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2020 | Region IV-A | Tayabas City | 301381 | Rosario Quesada Mem. NHS | CITY OF TAYABAS | 1 | 1 | 8 | Repair of Classrooms | 2931720 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Antipolo City | 342175 | Antipolo City SHS | CITY OF ANTIPOLO | 1 | 1 | 20 | Repair of Classrooms | 2060510.67 | 1 |  | COMPLETED | 1 |  | 2021-12-23 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2021 | Region IV-A | Antipolo City | 109330 | Mambugan I ES | CITY OF ANTIPOLO | 1 | 1 | 9 | Repair of Classrooms | 2330000 | 1 |  | COMPLETED | 1 |  |  |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | N.Q. Villapando Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region IV-A | Antipolo City | 109331 | Mayamot ES | CITY OF ANTIPOLO | 1 | 1 | 12 | Repair of Classrooms | 3485696.99 | 1 | 4923244.483 | COMPLETED | 1 |  |  |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | N.Q. Villapando Const. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Antipolo City | 109350 | Isaias S. Tapales ES | CITY OF ANTIPOLO | 2 | 1 | 7 | Repair of Classrooms | 1660265.55 | 1 |  | COMPLETED | 1 |  | 2021-12-29 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Antipolo City | 109336 | Peace Village ES | CITY OF ANTIPOLO | 2 | 1 | 10 | Repair of Classrooms | 2278722.59 | 1 |  | COMPLETED | 1 |  | 2021-12-23 |  |  | 2021-04-08 | 2021-11-08 | 8-24-21 |  |  | Hawkstw Const & Devt. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 107878 | Bayanan ES | BACOOR | 2 | 1 | 4 | Repair of Classrooms | 205499.66 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 305685 | City of Bacoor National High School - Georgetown | BACOOR | 2 | 1 | 2 | Repair of Classrooms | 814525.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 301188 | Eastern Bacoor NHS | BACOOR | 2 | 1 | 10 | Repair of Classrooms | 1169325.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 107870 | Habay ES | BACOOR | 2 | 1 | 1 | Repair of Classroom | 272944.35 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 164009 | Poblacion ES (Bacoor ES (Annex)) | BACOOR | 2 | 1 | 4 | Repair of Classrooms | 107278.62 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Bacoor City | 305689 | Responsible Village Leaders Learning Academy (REVILLA) High School | BACOOR | 2 | 1 | 6 | Repair of Classrooms | 191032.44 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas | 107670 | Bayanan Elementary School | SAN PASCUAL | 2 | 1 | 5 | Repair of Classrooms | 2823484.28 | 1 | 2798484 | COMPLETED | 1 | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 004 | REPAIR 2021 - R IV-A - Batangas Province - 004 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | Supplicon Builders |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas | 107675 | Malakimpook Elementary School | SAN PASCUAL | 2 | 1 | 6 | Repair of Classrooms | 2404006.82 | 1 | 2394766.84 | COMPLETED | 1 | 2021-11-24 | 2021-11-24 | REPAIR 2021 - R IV-A - Batangas Province - 003 | REPAIR 2021 - R IV-A - Batangas Province - 003 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | RRE Erectors Construction and Trading Specialist |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas | 107548 | Calantas Elementary School | ROSARIO | 4 | 1 | 5 | Repair of Classrooms | 3065032.18 | 1 | 3046773.49 | COMPLETED | 1 | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 001 | REPAIR 2021 - R IV-A - Batangas Province - 001 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | VRV Cosntruction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas | 301161 | Tulos National High School | ROSARIO | 4 | 1 | 7 | Repair of Classrooms | 4431241.78 | 1 | 4420000 | COMPLETED | 1 | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 002 | REPAIR 2021 - R IV-A - Batangas Province - 002 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas | 107620 | Paaralang Elementarya ng Muzon | SAN JUAN | 4 | 1 | 5 | Repair of Classrooms | 1526816.02 | 1 | 1507138.14 | COMPLETED | 1 | 2021-11-24 | 2021-11-12 | REPAIR 2021 - R IV-A - Batangas Province - 005 | REPAIR 2021 - R IV-A - Batangas Province - 005 | 2021-06-17 | 2021-06-24 | 2021-07-07 | 2021-07-21 | 2021-07-27 | GS Motar Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 109544 | Bagong Silang ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | Repair of Classrooms | 820765.96 | 1 | 640187.3 | COMPLETED | 1 | 10/29/2021 | 11/19/2021 | R4A-DI-BEFF- 2021-06-01 | INFRA- 2021-001 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 109607 | Eulalia Talban Ebora MES (Malalim ES) | BATANGAS CITY (Capital) | 5 | 1 | 1 | Repair of Classroom | 569506.79 | 1 | 562449.74 | COMPLETED | 1 | 10/15/2021 | 10/15/2021 | R4A-DI-BEFF- 2021-06-05 | INFRA- 2021-005 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | VRV Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 109615 | Jose C. Pastor ES (Pallocan ES) | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1247915.18 | 1 | 1120000 | COMPLETED | 1 | 10/29/2021 | 2021-08-10 | R4A-DI-BEFF- 2021-06-02 | INFRA- 2021-002 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Botey Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 301483 | Talumpok NHS | BATANGAS CITY (Capital) | 5 | 1 | 6 | Repair of Classrooms | 2467827.74 | 1 | 2337742.39 | COMPLETED | 1 | 11/29/2021 | 11/29/2021 | R4A-DI-BEFF- 2021-06-06 | INFRA- 2021-006 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | VRV Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 109562 | Tulo 1 ES | BATANGAS CITY (Capital) | 5 | 1 | 3 | Repair of Classrooms | 1255251.59 | 1 | 978989.46 | COMPLETED | 1 | 10/29/2021 | 11/19/2021 | R4A-DI-BEFF- 2021-06-03 | INFRA- 2021-003 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | Marakesh Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Batangas City | 109559 | Tulo II ES | BATANGAS CITY (Capital) | 5 | 1 | 4 | Repair of Classrooms | 1663537.15 | 1 | 1445893.05 | COMPLETED | 1 | 11/13/2021 | 10/20/2021 | R4A-DI-BEFF- 2021-06-04 | INFRA- 2021-004 | 07/15/2021 | 07/26/2021 | 2021-09-08 | 2021-12-08 | 08/25/2021 | EUGE Construction and Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Binan City | 108225 | Pagkakaisa ES | CITY OF BIÑAN | 0 | 1 | 8 | Repair of Classrooms | 3010686.91 | 1 | 2220628.1 | COMPLETED | 1 | 12/25/2021 |  | R4A-BNN-2021-01 |  | 2021-07-19 | 2021-07-29 | 2021-08-10 | 2021-08-24 | 2021-09-16 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Cabuyao City | 108251 | San Isidro ES | CABUYAO | 2 | 1 | 8 | Repair of Classrooms | 3799177.85 | 1 | 3143580.78 | COMPLETED | 1 | 2022-02-01 | [8 empty] | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Calamba City | 301517 | Canlubang Integrated School | CITY OF CALAMBA | 0 | 1 | 10 | Repair of Classrooms | 1936281.06 | 1 | 1388822.15 | COMPLETED | 1 | 01/27/2022 |  | 7736402 | Contract no. 4 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-08-17 | JB Alarcon Enterprises |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Calamba City | 109846 | Laguerta ES | CITY OF CALAMBA | 0 | 1 | 4 | Repair of Classrooms | 833288.86 | 1 | 666050.88 | COMPLETED | 1 | 01/27/2022 |  | 7736417 | Contract no. 2 s. 2021 | 2021-06-01 | 2021-06-09 | 2021-06-21 | 2021-08-05 | 2021-08-17 | Aaron Construction & Supply |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108018 | Binakayan Elementary School | KAWIT | 1 | 1 | 15 | Repair of classrooms | 10177851.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 301174 | Binakayan National High School | KAWIT | 1 | 1 | 14 | Repair of classrooms | 7648351.74 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108102 | Bulihan Sites & Services Project Elementary School | SILANG | 5 | 1 | 12 | Repair of classrooms | 8157208.21 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108123 | Kaong Elementary School | SILANG | 5 | 1 | 4 | Repair of classrooms | 2631294.41 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108110 | Silang Central School | SILANG | 5 | 1 | 4 | Repair of classrooms | 2628381.64 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108162 | Halayhay Elementary School | TANZA | 7 | 1 | 6 | Repair of classrooms | 4022060.16 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108164 | Julugan Elementary School | TANZA | 7 | 1 | 4 | Repair of classrooms | 2629178.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108077 | Petronilo L. Torres Memorial Elementary School | NAIC | 8 | 1 | 8 | Repair of classrooms | 5611258.26 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite | 108154 | Tagaytay City Central School | TAGAYTAY CITY | 8 | 1 | 9 | Repair of classrooms | 5607232.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 | 1 | 7 | Repair of classrooms | 3000000 | 1 | 2103930.08 | COMPLETED | 1 | 2022-01-16 |  |  |  | 2021-07-06 | 2021-07-13 | 2021-07-25 | 2021-08-06 | 2021-08-19 | RA del Rosario |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Dasmarinas City | 107924 | Salitran Elementary | CITY OF DASMARIÑAS | 4 | 1 | 8 | Repair of Classrooms | 2842498.24 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | General Trias City | 107961 | Mary Cris ES | CITY OF GENERAL TRIAS | 6 | 1 | 8 | Repair of Classrooms | 3643612.19 | 1 |  | COMPLETED | 1 | [7 empty] | 2021-07-15 | 2021-10-15 | R.A. Yolangco Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | General Trias City | 107963 | Parklane ES | CITY OF GENERAL TRIAS | 6 | 1 | 6 | Repair of Classrooms | 2595334.03 | 1 |  | COMPLETED | 1 | [7 empty] | 2021-07-15 | 2021-10-15 | R.A. Yolangco Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Imus City | 107972 | Buhay na Tubig ES | IMUS | 3 | 1 | 12 | Repair of Classrooms | 1696167.25 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Imus City | 164002 | Palico Elementary School | IMUS | 3 | 1 | 8 | Repair of Classrooms | 1302935.53 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Laguna | 108272 | Burol Elementary School | CAVINTI | 4 | 1 | 8 | Repair of Classrooms | 3694494.47 | 1 |  | COMPLETED | 1 |  |  |  |  | 2018-11-23 | 2018-12-14 | 2001-06-21 | 2019-08-02 | 2019-08-09 | N.T. Sotelo Construction & Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Laguna | 164517 | Layasin Elementary School | CAVINTI | 4 | 1 | 3 | Repair of Classrooms | 1301264.28 | 1 |  | COMPLETED | 1 | [6 empty] | 2001-06-21 |  |  | N.T. Sotelo Construction & Supply Corp. |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109640 | Anangi ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1106822.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109671 | Anilao ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 1642536.71 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 301486 | Anilao National High School | LIPA CITY | 6 | 1 | 10 | Repair of Classrooms | 5706481.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109688 | Bagongpook ES | LIPA CITY | 6 | 1 | 11 | Repair of Classrooms | 6185163.7 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109642 | Brion- Silva ES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2284424.96 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109692 | Cipriano Andal MES (Halang ES) | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 1324432.81 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 501184 | Cumba-Quezon Integrated School | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1186688.79 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109661 | Dagatan ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109690 | Duhatan ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2064541.58 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109645 | Edilberto L. Mendoza MES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2089854.51 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 | 4606330.1 | COMPLETED | 1 |  |  |  | R4A-LC-2019-11 | JULY 15-22, 2019 | 2019-07-24 | 2019-08-05 | 2019-08-27 | 2019-10-18 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109662 | Inosloban-Marawoy ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy Integrated National High School | LIPA CITY | 6 | 1 | 18 | Repair of Classrooms | 9484206.54 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109676 | Labac Elementary School | LIPA CITY | 6 | 1 | 11 | Repair of Classrooms | 6236230.8 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 303491 | Lipa City Senior High School | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2284424.96 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109682 | Pagolingin Bata ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 2428660.78 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 500888 | Pangao Integrated School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 301497 | Pinagtongulan Integrated National High School | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 1921678.28 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109664 | Plaridel ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109684 | Rizal Elementary School | LIPA CITY | 6 | 1 | 14 | Repair of Classrooms | 3366304.02 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109685 | Sampaguita ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2642639.01 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109652 | San Isidro ES | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6761943.11 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 301500 | San Isidro Integrated National High School | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 | 2098281.46 | COMPLETED | 1 | [9 empty] | EUGE CONSTRUCTION & SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109666 | Santo Toribio ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School ( | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 6490636.92 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3396854.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109655 | Sto. Toribio ES | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1130408.2 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109702 | Tagbakin Elementary School | LIPA CITY | 6 | 1 | 2 | Repair of Classrooms | 1120702.21 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109703 | Tambo ES | LIPA CITY | 6 | 1 | 6 | Repair of Classrooms | 3424350.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 2867464.75 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Lucena City | 109729 | BLISS Elementary School | LUCENA CITY (Capital) | 2 | 1 | 14 | Repair of Classrooms | 9138166.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2021 | Region IV-A | Lucena City | 109724 | Reymar Compound Elementary School | LUCENA CITY (Capital) | 2 | 1 | 8 | Repair of Classrooms | 5313624.1 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108790 | Lual Elementary School | INFANTA | 1 | 1 | 8 | Repair of Classrooms | 2200040.47 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108791 | Magsaysay ES | INFANTA | 1 | 1 | 6 | Repair of Classrooms | 2050705.26 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108890 | Balaybalay ES | MAUBAN | 1 | 1 | 2 | Repair of Classrooms | 1116692.17 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 301301 | Cagbalete Island National High School | MAUBAN | 1 | 1 | 7 | Repair of Classrooms | 4598852.81 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 | 1 | 2 | Repair of Classrooms | 1627177.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108970 | Pagbilao CES (Pagbilao CES & Pabilao East CES) | PAGBILAO | 1 | 1 | 10 | Repair of Classrooms | 3451870.14 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109085 | Sampaloc Elementary School (Main) | SAMPALOC | 1 | 1 | 19 | Repair of Classrooms | 7673789.08 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 19 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108681 | Kinabuhayan ES | DOLORES | 2 | 1 | 2 | Repair of Classrooms | 973956.31 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108673 | Rosendo Algenio ES | DOLORES | 2 | 1 | 4 | Repair of Classrooms | 1860393.3 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109159 | Balubal ES | SARIAYA | 2 | 1 | 2 | Repair of Classrooms | 850184.87 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109174 | BIGNAY II ES | SARIAYA | 2 | 1 | 2 | Repair of Classrooms | 1417683.51 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109183 | Janagdong II ES | SARIAYA | 2 | 1 | 1 | Repair of Classroom | 659568.15 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109167 | Pantoc Elementary School | SARIAYA | 2 | 1 | 3 | Repair of Classrooms | 1496369.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109172 | Tumbaga II ES | SARIAYA | 2 | 1 | 3 | Repair of Classrooms | 1470422.11 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 109266 | BEHIA ES | TIAONG | 2 | 1 | 3 | Repair of Classrooms | 1925971.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108543 | Hagonghong ES | BUENAVISTA | 3 | 1 | 7 | Repair of Classrooms | 3780814.07 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 7 | Repair of Classrooms | 1229887.31 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108548 | San Isidro Ibaba ES | BUENAVISTA | 3 | 1 | 2 | Repair of Classrooms | 1324966.8 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108549 | San Isidro Ilaya ES | BUENAVISTA | 3 | 1 | 2 | Repair of Classrooms | 1233004.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108645 | Bolo Elementary School | CATANAUAN | 3 | 1 | 3 | Repair of Classrooms | 2134049.76 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108888 | Tubigan ES | MACALELON | 3 | 1 | 3 | Repair of Classrooms | 1182153.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108942 | Santa Rosa ES | MULANAY | 3 | 1 | 3 | Repair of Classrooms | 1255904.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108607 | Sabang ES | CALAUAG | 4 | 1 | 8 | Repair of Classrooms | 3914874.7 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108586 | Tabansak ES | CALAUAG | 4 | 1 | 5 | Repair of Classrooms | 3328109.68 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108736 | GAPAS ES | GUINYANGAN | 4 | 1 | 3 | Repair of Classrooms | 2134776.73 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108762 | Panikihan Elementary school | GUMACA | 4 | 1 | 5 | Repair of Classrooms | 3609988.12 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108812 | Magallanes Elementary School | LOPEZ | 4 | 1 | 2 | Repair of Classrooms | 493289.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Quezon | 108813 | Pamampangin ES | LOPEZ | 4 | 1 | 2 | Repair of Classrooms | 1119102.28 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 109372 | Tatala ES | BINANGONAN | 1 | 1 | 2 | Repair of Classrooms | 994592.59 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 109318 | Tayuman ES | BINANGONAN | 1 | 1 | 5 | Repair of Classrooms | 1663582.73 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 165506 | Cresdaville Elementary School | TAYTAY | 1 | 1 | 2 | Repair of Classrooms | 495604.18 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 301429 | Baras NHS | BARAS | 2 | 1 | 18 | Repair of Classrooms | 9359836.78 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 18 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 109461 | Amityville ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | Repair of Classrooms | 466449.45 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 109499 | Balimbing ES | TANAY | 2 | 1 | 4 | Repair of Classrooms | 1360728.49 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Rizal | 109524 | Tablon ES | TANAY | 2 | 1 | 3 | Repair of Classrooms | 1081677.35 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | San Pablo City | 109782 | Major Juan Eseo Elementary School to Fernando A. Quisumbing ES | SAN PABLO CITY | 3 | 1 | 8 | Repair of Classrooms Covered Court & Pathways | 5025125.63 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2021 | Region IV-A | San Pablo City | 109800 | San Joaquin Elementary School | SAN PABLO CITY | 3 | 1 | 5 | Repair of Classrooms Covered Court & Pathways | 3015075.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | SAN PABLO CITY | 3 | 1 | 11 | Repair of Classrooms | 4495601.76 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 | 1 | 3 | Repair of Classrooms | 1067606.2 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 |  | 6 | Repair of Classrooms | 2135212.19 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4255980.96 | 1 | 628546.8 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-002 | R4A-STA.ROSA-2019-01 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301239 | Don Jose National High School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4185000.94 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108478 | Malitlit Elementary School | CITY OF SANTA ROSA | 1 | 1 | 4 | Repair of Classrooms | 1702001.76 | 1 | 1156018.52 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-004 | R4A-STA.ROSA-2019-04 | 11/27/2018 | 2018-03-12 | 12/14/2018 | 2018-12-19 | 2019-08-30 | GS MOTAR BUILDERS CONSTRUCTION & TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301260 | Pulong Sta. Cruz NHS | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4072781.23 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 108481 | Santa Rosa Elementary School Central II | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 4342980.16 | 1 | 628546.8 | COMPLETED | 1 | 2019-11-30 |  | REPAIR 2019- RIV-4A -STA. ROSA CITY-003 | R4A-STA.ROSA-2019-03 | 2018-08-11 | 11/15/2018 | 11/29/2018 | 2019-02-28 | 2019-08-30 | N.Q. Villapando Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Sta. Rosa City | 301272 | Sto. Domingo National High School | CITY OF SANTA ROSA | 1 | 1 | 10 | Repair of Classrooms | 2999999.56 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2021 | Region IV-A | Tanauan City | 107747 | Bagbag ES | CITY OF TANAUAN | 3 | 1 | 12 | Repair of Classrooms | 5283395.07 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2021 | Region IV-A | Tanauan City | 107752 | Banjo Laurel ES | CITY OF TANAUAN | 3 | 1 | 5 | Repair of Classrooms | 2822777.45 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2021 | Region IV-A | Tanauan City | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 11 | Repair of Classrooms | 5546991.93 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 11 | 0 | 0
REPAIR 2021 | Region IV-A | Tanauan City | 107770 | Pagaspas ES | CITY OF TANAUAN | 3 | 1 | 9 | Repair of Classrooms | 5979808.48 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2021 | Region IV-A | Tanauan City | 107782 | Tanauan South Central School | CITY OF TANAUAN | 3 | 1 | 1 | Repair of Classroom | 1811750.89 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2021 | Region IV-A | Tayabas City | 109252 | Gibanga ES | CITY OF TAYABAS | 1 | 1 | 3 | Repair of Classrooms | 502214.46 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2021 | Region IV-A | Tayabas City | 109233 | EAST PALALE ES | TAYABAS | 1 | 1 | 7 | Repair of Classrooms | 2997134.61 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2022 | Region IV-A | Batangas | 107807 | Banalo Elementary School | TINGLOY | 2 | 1 | 2 | Repair of Classrooms | 2831199.38 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region IV-A | Batangas | 107811 | Marikaban Elementary School | TINGLOY | 2 | 1 | 5 | Repair of Classrooms | 724950.42 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Batangas | 301073 | Balete National High School | BALETE | 3 | 1 | 5 | Repair of Classrooms | 2705209.33 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Batangas | 107658 | Abelo Elementary School | SAN NICOLAS | 3 | 1 | 3 | Repair of Classrooms | 844486.32 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region IV-A | Batangas | 301149 | Sta. Teresita National High School | SANTA TERESITA | 3 | 1 | 4 | Repair of Classrooms | 1456771.03 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IV-A | Cavite | 107926 | Bailen Elementary School | GENERAL EMILIO AGUINALDO | 8 | 1 | 4 | Repair of Classrooms | 2548374.42 | 1 | 628586.93 | COMPLETED | 1 | 2022-10-27 | 2022-10-27 | REPAIR 2022-IVA-BATANGAS-03 | REPAIR 2022-IVA-BATANGAS-03 | 2022-06-14 | 2022-06-21 | 2022-07-04 | 2022-07-12 | 2022-07-29 | Rogelio F. Cruz Construction |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Memorial National High School | RIZAL | 3 | 1 | 5 | Repair of Classrooms | 3232835.39 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Laguna | 108293 | Eugenia Games Olarte Reyes Elem. Sch. | MABITAC | 4 | 1 | 5 | Repair of Classrooms | 1272055.97 | 1 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Laguna | 108393 | Casinsin ES | PAKIL | 4 | 1 | 5 | Repair of Classrooms | 1664779.55 | 1 |  | COMPLETED | 1 |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 301487 | BOLBOK INTEGRATED NATIONAL HIGH SCHOOL | LIPA CITY | 6 | 1 | 16 | Repair of Classrooms | 8948954.48 | 2 | 2700000 | COMPLETED | 1 |  |  |  | R4A-LC-2019-7 | JULY 15-22, 2019 | 2019-07-24 | 2019-08-05 | 2019-08-27 | 2019-10-15 | BOTEY CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109690 | Duhatan ES | LIPA CITY | 6 | 1 | 3 | Repair of Classrooms | 2037231.5 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy Integrated National High School | LIPA CITY | 6 | 1 | 8 | Repair of Classrooms | 4504429.69 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 301494 | Lodlod Integrated National High School | LIPA CITY | 6 | 1 | 8 | Repair of Classrooms | 5358892.3 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 301495 | Lumbang Integrated NHS | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2719356.92 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109683 | Pagolingin ES | LIPA CITY | 6 | 1 | 4 | Repair of Classrooms | 2730004.58 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 6 | 1 | 10 | Repair of Classrooms | 6581221.69 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109697 | Rafael M. Lojo MS | LIPA CITY | 6 | 1 | 12 | Repair of Classrooms | 7445722.2 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109666 | Santo Toribio ES | LIPA CITY | 6 | 1 | 5 | Repair of Classrooms | 3292261.64 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2022 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 6 | 1 | 9 | Repair of Classrooms | 7442046.68 | 2 |  | COMPLETED | 1 | [10 empty] | BID OUT, FOR POST QUALIFICATION | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN | 1 | 1 | 2 | Repair of Classrooms | 1407120.6 | 1 |  | COMPLETED | 1 |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 109084 | Caldong Resettlement ES | SAMPALOC | 1 | 1 | 1 | Repair of Classroom | 1760999.14 | 1 |  | COMPLETED | 1 |  |  |  |  | February 28, 2022 | March 7, 2022 | March 21, 2022 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 108948 | Dayap ES | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 527643.68 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 301321 | Elias A. Salvador NHS | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 2203957.52 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 1 | Repair of Classroom | 534417.42 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | CATANAUAN | 3 | 1 | 12 | Repair of Classrooms | 8377828.7 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 301354 | Malaya NHS | GENERAL LUNA | 3 | 1 | 6 | Repair of Classrooms | 4393375.16 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 301360 | Olongtao National High School | MACALELON | 3 | 1 | 16 | Repair of Classrooms | 15546791.97 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 301376 | Pitogo Community High School | PITOGO | 3 | 1 | 16 | Repair of Classrooms | 11159543.31 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 301414 | Unisan Integrated High School (Formerly Unisan NHS) | UNISAN | 3 | 1 | 6 | Repair of Classrooms | 2969709.9 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 109052 | Del Pilar Elementary School | QUEZON | 4 | 1 | 1 | Repair of Classroom | 1689722.45 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 109054 | Gumubat ES | QUEZON | 4 | 1 | 1 | Repair of Classroom | 1182116.92 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 109057 | Quezon ES | QUEZON | 4 | 1 | 1 | Repair of Classroom | 2219256.16 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2022 | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3rd | 1 | 14 | Repair of Classrooms | 13925839.47 | 2 |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0
REPAIR 2022 | Region IV-A | Tayabas City | 109251 | Domoit ES | CITY OF TAYABAS | 1 | 1 | 2 | Repair of Classrooms | 962073.64 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region IV-A | Tayabas City | 109253 | Ipilan-Alitao ES | CITY OF TAYABAS | 1 | 1 | 2 | Repair of Classrooms | 993543.89 | 1 |  | COMPLETED | 1 | [10 empty] | For release of NTP | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2022 | Region IV-A | Tayabas City | 109247 | Wakas ES | CITY OF TAYABAS | 1 | 1 | 5 | Repair of Classrooms | 2050225.03 | 1 |  | COMPLETED | 1 |  |  |  |  | 2022-02-08 | 2022-02-15 | 2022-02-28 | 2022-03-09 |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | Antipolo City | 301421 | Kaysakat NHS | CITY OF ANTIPOLO | 2nd | 1 | 8 | Repair of Classrooms | 3806072.156 | DPWH (Batch 2) | 3561987.53 | COMPLETED | 1 | 2024-03-26 | 2024-03-26 | P00775739NP | 23DN0147 | 2023-10-06 | 2023-10-13 | 2023-10-26 | 2023-11-07 | 2023-11-21 | BELVIAN BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2023 | Region IV-A | Batangas | 301134 | Papaya National High School | TINGLOY | 2nd | 1 | 6 | Repair of Classrooms | 4591234.1 | DPWH (Batch 1) | 4430540.91 | Ongoing | 0.95 | 2024-02-22 |  | P00775119NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region IV-A | Batangas | 107813 | Pisa Elementary School | TINGLOY | 2nd | 1 | 8 | Repair of Classrooms | 3711204 | DPWH (Batch 1) | 3581311.86 | Ongoing | 0.95 | 2024-02-22 |  | P00775120NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0
REPAIR 2023 | Region IV-A | Batangas | 107814 | San Jose Elementary School | TINGLOY | 2nd | 1 | 6 | Repair of Classrooms | 1649424 | DPWH (Batch 1) | 1591694.16 | Ongoing | 0.75 | 2024-02-22 |  | P00775121NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2023 | Region IV-A | Batangas | 107818 | Talahib Elementary School | TINGLOY | 2nd | 1 | 4 | Repair of Classrooms | 1649424 | DPWH (Batch 1) | 1591694.16 | Ongoing | 0.95 | 2024-02-22 |  | P00775122NP | 23DE0168 | 24/08/2023 | 2023-01-09 | 14/09/2023 | 21/09/2023 | 26/09/2023 | LLEB CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2023 | Region IV-A | Batangas | 301114 | Maabud National High School | SAN NICOLAS | 3rd | 1 | 6 | Repair of Classrooms | 7000000 | DPWH (Batch 2) |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IV-A | Binan City | 108221 | Langkiwa ES | CITY OF BIÑAN | 1st | 1 | 4 | Repair of Classrooms | 911599.61 | DEPED (Batch 2) | 873239.8 | COMPLETED | 1 | 2024-06-09 | 2024-06-11 | 10553108 | 10553108 |  |  |  | 2024-02-19 | 2024-02-21 | GS Motar Builders Construction & Trading | With time extension | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IV-A | Binan City | 307932 | Mamplasan NHS (Jacobo Annex) | CITY OF BIÑAN | 1st | 1 | 6 | Repair of Classrooms | 999163.1 | DEPED (Batch 2) | 958837.78 | COMPLETED | 1 | 2024-04-22 | 2024-04-23 | 10556258 | 10556258 |  |  |  | 2024-02-19 | 2024-02-21 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IV-A | Cavite | 107926 | Bailen Elementary School | GENERAL EMILIO AGUINALDO | 8th | 1 | 3 | Repair of Classrooms | 2600000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Laguna | 108286 | Matalatala ES | MABITAC | 4th | 1 | 9 | Repair of Classrooms | 6099507 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0
REPAIR 2023 | Region IV-A | Laguna | 301243 | Kabulusan Integrated National High School | PAKIL | 4th | 1 | 5 | Repair of Classrooms | 3388617 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | Laguna | 108400 | Maulawin ES | PAKIL | 4th | 1 | 2 | Repair of Classrooms | 1355447 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109728 | Barra Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 950950.44 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109739 | Ilayang Talim Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 935780.08 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109740 | Isabang Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 956890.8 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 167502 | Isabang Elementary School - Bocohan Annex | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 950890.78 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109731 | Lucena South I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 975860.86 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109742 | Lucena West I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 933457.9 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109744 | Lucena West III Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 925795.78 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109745 | Lucena West IV Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 940980.36 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109735 | Mayao Parada Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 966367.8 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Lucena City | 109736 | Talao-Talao Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 1 | Repair of Classroom | 945890.9 | DEPED (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 1st | 1 | 12 | Repair of Classrooms | 9655035 | DPWH (Batch 1) | 9654451 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 108985 | Jomalig CES | JOMALIG | 1st | 1 | 12 | Repair of Classrooms | 9655035 | DPWH (Batch 2) | 9653886.66 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 108991 | Sinintan ES | PATNANUNGAN | 1st | 1 | 2 | Repair of Classrooms | 1655668.9 | DPWH (Batch 2) | 1636376.22 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 108518 | Maligaya ES | ATIMONAN | 4th | 1 | 3 | Repair of Classrooms | 3900000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 108520 | Malinao Ilaya ES | ATIMONAN | 4th | 1 | 10 | Repair of Classrooms | 3640000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301400 | San Rafael NHS | ATIMONAN | 4th | 1 | 2 | Repair of Classrooms | 1950000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th | 1 | 5 | Repair of Classrooms | 6435000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 6 | Repair of Classrooms | 5395000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 12 | Repair of Classrooms | 7150000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 5 | Repair of Classrooms | 7865000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4th |  | 3 | Repair of Classrooms | 6890000 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 109056 | Pedro Cabangon ES | QUEZON | 4th | 1 | 1 | Repair of Classroom | 808244.65 | DEPED (Batch 1) | 778000 | COMPLETED | 1 |  | 2023-09-27 | [8 empty] | Sub-ARO amount is 779,956.09 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 109056 | Pedro Cabangon ES | QUEZON | 4th | 1 | 1 | Repair of Classroom | 808244.65 | DEPED (Batch 2) | 778000 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4th | 1 | 5 | Repair of Classrooms | 4100365.65 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | Quezon | 109059 | Sabang ES | QUEZON | 4th | 1 | 5 | Repair of Classrooms | 4100365.65 | DPWH (Batch 2) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 5 | 0 | 0
REPAIR 2023 | Region IV-A | San Pedro City | 301261 | Sampaguita Vill. NHS | SAN PEDRO | 1st | 1 | 10 | Repair of Classrooms | 4043773.47 | DPWH (Batch 2) |  | COMPLETED | 1 | 2024-08-31 | 2024-08-16 | 23DI0197 | 23DI0197 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2023 | Region IV-A | San Pedro City | 307939 | Southville 3A (Sampaguita Ext.) | SAN PEDRO | 1st | 1 | 20 | Repair of Classrooms | 3965689.88 | DPWH (Batch 2) |  | Completed | 1 | [10 empty] | with NOA, Suspended due to structural concern | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2023 | Region IV-A | San Pedro City | 164528 | Southville 3A ES | SAN PEDRO | 1st | 1 | 30 | Repair of Classrooms | 5754265.09 | DPWH (Batch 2) | 5406845 | COMPLETED | 1 | 2024-08-31 | 2024-08-08 | 23DI0198 | 23DI0198 | 2024-03-15 | 2024-03-22 | 2024-04-04 | 2024-04-25 | 2024-05-03 | GMO CONSTRUCTION |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 30 | 0 | 0
REPAIR 2023 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | CITY OF TANAUAN | 3rd | 1 | 6 | Repair of Classrooms | 8500000 | DPWH (Batch 2) |  | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109236 | LAKAWAN ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109237 | LAWIGUE ES | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 2400000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109257 | Malao-A / Calantas ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109238 | Masin Elementary School | CITY OF TAYABAS | 1st | 1 | 1 | Repair of Classroom | 600000 | DEPED (Batch 2) | 577854.4 | COMPLETED | 1 | 2024-06-20 | 2024-07-02 | ITB-INFRA-2024-003 | ITB-INFRA-2024-003 | 2024-03-06 | 2024-03-14 | 2024-03-26 | 2024-05-03 | 2024-05-14 | LA PROFUGO CONSTRUCTION AND SUPPLY |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109258 | POTOL ES | CITY OF TAYABAS | 1st | 1 | 3 | Repair of Classrooms | 1500000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 109260 | Tayabas West CS II | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 2000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2023 | Region IV-A | Tayabas City | 301416 | West Palale National High School | CITY OF TAYABAS | 1st | 1 | 6 | Repair of Classrooms | 3000000 | DPWH (Batch 1) |  | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0
REPAIR 2024 | Region IV-A | Antipolo City | 500391 | Apia IS | CITY OF ANTIPOLO | 2nd | 1 | 10 | Repair of Classrooms | 5930924.83 | 1 | 5860000 | COMPLETED | 1 | 2025-01-14 | 2025-01-07 |  | BEFF-ANT-2024-04 | 2024-07-10 | 2024-07-18 | 2024-07-30 | 2024-09-23 | 2024-10-15 | HAWKSTOW CONST AND DEVELOPMENT |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region IV-A | Bacoor City | 107889 | San Nicolas Elementary School | BACOOR | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
REPAIR 2024 | Region IV-A | Batangas | 307706 | Lian National High School | LIAN | 1st | 1 | 4 | Repair of Classrooms | 3469896.97 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0
REPAIR 2024 | Region IV-A | Batangas | 107607 | Calabasahan Elementary School | SAN JUAN | 4th | 1 | 6 | Repair of Classrooms | 3939393.94 | 1 |  | under procurement | 0 | [11 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0
REPAIR 2024 | Region IV-A | Batangas City | 109572 | Parang Cueva ES | BATANGAS CITY (Capital) | 5th | 1 | 4 | Repair of Classrooms | 3282828.28 | 1 | 3150000 | Completed | 1 | 2025-05-24 |  | 001-01-2025 | 001-01-2025 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-20 | 2025-01-24 | Botey Construction | For Installation of Roofings | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | Batangas City | 109621 | Pinamukan ES | BATANGAS CITY (Capital) | 5th | 1 | 1 | Repair of Classrooms | 384808.08 | 1 | 350000 | COMPLETED | 1 | 2025-05-24 | 2025-02-17 | 001-01-2025 | 001-01-2025 | 2024-11-19 | 2024-11-27 | 2024-12-09 | 2024-12-20 | 2025-01-24 | Botey Constructioin | Completed | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2024 | Region IV-A | Cabuyao City | 108236 | Banlic Elementary School | CABUYAO | 2nd | 1 | 4 | Repair of Classrooms | 2626262.63 | 1 | 2284632.74 | Completed | 1 | 2025-05-04 |  | 2024-07-0051 | 2024-07-0051 | 2024-09-30 | 2024-10-02 | 2024-10-14 | 2024-10-26 | 2024-12-09 | GS Motar Builders Construction & Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | Cavite | 108083 | San Antonio Elementary School | NOVELETA | 1st | 1 | 2 | Repair of Classrooms | 2234126.31 | 1 | 2193417.05 | COMPLETED | 1 |  |  |  | RIVACaviteBACInfra 003-2024 |  | 2024-08-08 | 2024-08-27 | Nov. 25, 2024 | 2025-12-18 | Langit Construction | Slow Pace of Work | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region IV-A | Cavite | 301193 | Gen. Vito Belarmino Integrated National High School | SILANG | 5th | 1 | 4 | Repair of Classrooms | 3709069.7 | 1 | 3650284.6 | Ongoing | 0.4 |  |  |  | RIVACaviteBACInfra 003-2024 |  | 2024-08-08 | 2024-08-27 | Nov. 25, 2024 | 2025-12-18 | Langit Construction | Slow Pace of Work | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0
REPAIR 2024 | Region IV-A | Cavite City | 109632 | Ladislao Diwa ES | CAVITE CITY | 1st | 1 | 4 | Repair of Classrooms | 2534098.23 | 1 | 1881331.85 | COMPLETED | 1 | 2025-01-24 | 2024-12-13 | 2024-07-00007 | 2024-07-00007 | 2024-06-28 | 2024-07-09 | July 22, 2024 - July 29, 2024 (actual) | 2024-08-02 | 2024-09-26 | L2A Builders and Trading | * | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | City of Biñan | 108214 | Our Lady of Lourdes ES (Brgy. Malamig PS) | CITY OF BIÑAN | Lone | 1 | 8 | Repair of Classrooms | 4340603.52 | 1 | 3695579.1 | COMPLETED | 1 | 2025-02-07 | 2025-01-07 | R4A-BNN-2024-06 | R4A-BNN-2024-06 | July 24 - August 13, 2024 | 2024-08-01 | 2024-08-13 | 2024-08-27 | 2024-10-10 | GS Motar Builders Construction & Trading | Awaiting SARO Release | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region IV-A | Dasmarinas City | 107915 | Bautista Elementary School | CITY OF DASMARIÑAS | 4th | 1 | 8 | Repair of Classrooms | 4042483.14 | 1 | 3933887.8 | COMPLETED | 1 | 2025-04-12 | 2025-03-19 | CY2024 BEFF Batch 1 RRC | CY2024 BEFF Batch 1 RRC | August 26-September 13, 2024 | 2024-09-13 | 2024-09-25 | 2024-10-11 | 2024-11-13 | Open Builders Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3rd | 1 | 8 | Repair of Classrooms | 4083303.35 | 1 | 4011225.37 | Completed | 1 | May 8, 2025 |  | 2024-10-003 | 2024-10-003 | Nov. 12, 2024 | Nov. 19, 2024 | Dec. 2, 2024 | Dec. 20, 2024 | Dec 27, 2024 | JKK Construction Services | ongoing installation of electrical wirings, fixtures, and painting works | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region IV-A | Laguna | 108500 | San Francisco ES | VICTORIA | 3rd | 1 | 6 | Repair of Classrooms | 3477422.29 | 1 | 2841560.04 | Ongoing | 0.75 | 2025-09-11 |  | R4A-2024-17 | R4A-2024-17 | 27/09/2024 | 10/7/2024 (Pre-Bid Conference) | Oct. 21, 2024 | 2025-07-02 | 2025-04-03 | Open Builders Incorporated |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0
REPAIR 2024 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6th | 1 | 4 | Repair of Classrooms | 2185807.35 | 1 | 2153928.39 | COMPLETED | 1 | 2025-02-21 |  | REPAIR 2024-RIV A-LIPA CITY 001 | REPAIR 2024-RIV A-LIPA CITY 001 | 2024-07-05 | 2024-07-16 | July 29,2024 | 2024-08-08 | 2024-10-17 | TRACCOR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | Lipa City | 301499 | San Celestino Integrated National High School | LIPA CITY | 6th | 1 | 2 | Repair of Classrooms | 1728183.83 | 1 | 1700800.48 | COMPLETED | 1 | 2025-01-22 | 2024-12-05 | REPAIR 2024-RIV A-LIPA CITY 002 | REPAIR 2024-RIV A-LIPA CITY 002 | 2024-07-05 | 2024-07-16 | July 29,2024 | 2024-08-08 | 2024-10-17 | TRACCOR BUILDERS |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 0
REPAIR 2024 | Region IV-A | Lucena City | 167501 | Hermana Fausta Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 4 | Repair of Classrooms | 3362920.1 | 1 | 3327225.43 | Completed | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | Quezon | 109001 | Cabulihan ES | PITOGO | 3rd | 1 | 1 | Repair of Classrooms | 1352208.72 | 1 | 1330000 | COMPLETED | 1 |  | 2024-11-15 | [9 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
REPAIR 2024 | Region IV-A | Quezon | 108845 | Ilayang Ilog B ES | LOPEZ | 4TH | 1 | 3 | Repair of Classrooms | 3824717.87 | 1 | 3778556.12 | COMPLETED | 1 | [11 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0
REPAIR 2024 | Region IV-A | Rizal | 301452 | Morong National High School | MORONG | 2nd | 1 | 8 | Repair of Classrooms | 4504148.49 | 1 | 3735628.16 | COMPLETED | 1 | 2025-04-26 |  | INFRA-2024-002 | INFRA-2024-002 | 2024-09-24 | 2024-10-01 | 2024-10-15 | 2024-10-22 | 2024-11-28 | J.G. Gutierrez Construction and Trading |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0
REPAIR 2024 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3rd | 1 | 7 | Repair of Classrooms | 3181818.18 | 1 | 3109999.88 | COMPLETED | 1 | 2025-04-19 | 2025-04-05 | BEFF-RC-001-2024 | BEFF-RC-001-2024 | 2024-10-22 | 2024-11-06 | 2024-11-19 | 2024-11-22 | 2024-12-20 | N.T. Sotelo Construction and Supply Corporation |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 7 | 0 | 0
REPAIR 2024 | Region IV-A | San Pedro City | 108434 | San Vicente Elementary School | SAN PEDRO | 1st | 1 | 20 | Repair of Classrooms | 3037968.19 | 1 | 2139121.38 | COMPLETED | 1 | 2025-03-20 | 2025-02-01 | 2024-PB-024 | 2024-PB-024 | 2024-06-25 | 2024-07-03 | 2024-07-15 | 2024-10-07 | 2024-10-21 | Open Builders Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 20 | 0 | 0
REPAIR 2024 | Region IV-A | Sto. Tomas City | 107697 | San Antonio Elementary School | SANTO TOMAS | 3rd | 1 | 10 | Repair of Classrooms | 5777777.78 | 1 | 5238161.19 | COMPLETED | 1 | 2025-04-07 | 2025-04-07 | CW-2024-11-0001 | CW-2024-11-0001 | 2024-11-25 | 2024-12-05 | 2024-12-17 | 2024-12-20 | 2024-12-23 | Open Builders Incorporated |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0
REPAIR 2024 | Region IV-A | Tanauan City | 107763 | Luyos ES | CITY OF TANAUAN | 3rd | 1 | 4 | Repair of Classrooms | 4067564.39 | 1 | 3987906.55 | COMPLETED | 1 | 2024-12-21 | 2024-12-21 | BEFF 2024- IV A TANAUAN-001 | BEFF 2024- IV A TANAUAN-001 | 8/16/204 | 2024-08-27 | 2024-09-09 | 2024-10-02 | 2024-10-21 | MARAKESH ENTERPRISES |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0
REPAIR 2024 | Region IV-A | Tayabas City | 109249 | Eugenio Francia Elementary School | CITY OF TAYABAS | 1st | 1 | 4 | Repair of Classrooms | 3122920.91 | 1 | 2935000 | COMPLETED | 1 | 2025-04-09 | 2025-04-03 | ITB-INFRA-2024-007 | ITB-INFRA-2024-007 | 2024-11-08 | 2024-11-18 | 2024-12-02 | 2024-12-20 | 2024-12-27 | LLEB CONSTRUCTION AND TRADING |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 0 | 0

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%