## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
SCHOOL HEALTH FACILITIES 2024 | Region IX | Dapitan City | 500675 | Kauswagan Integrated School | DAPITAN CITY | 1st | 1 |  | Construction of School Clinic | 3656520.52 |  | 3601234.72 | Completed | 1 | July 17, 2024 | - | SDODAP-INFRA-2023-005 | SDODAP-INFRA-2023-005 | November 14, 2023 | November 21, 2023 | December 07, 2023 | May 06, 2024 | May 17, 2024 | MORTE CONSTRUCTION | -
SCHOOL HEALTH FACILITIES 2024 | Region IX | Isabela City | 126028 | Cabunbata Elementary School | CITY OF ISABELA (Capital) | Lone | 1 |  | Construction of School Clinic | 3196585.16 |  | 3001865.23 | ongoing | 0.99 | November 20, 2024 | - | INFRAEPA2024-03 | INFRAEPA2024-03 | - | November 15, 2023 | December 4, 2023 | May 16, 2024 | August 20, 2024 | AL-QATANI ENTERPRISES | none
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303715 | Piñan National High School | PIÑAN (NEW PIÑAN) | 1st | 1 |  | Construction of School Clinic | 4139595.02 |  | 4113576.02 | Completed | 1 | August 15, 2024 | September 27, 0204 | 2024-03-CBZN | CB-2024-015 | December 12, 2023 | December 11, 2023 | December 27, 2023 | January 05, 2024 | May 15, 2024 | YSL Builder | none
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | Sindangan | 2nd | 1 |  | Construction of School Clinic | 4139595.02 |  | 4113576.02 | Completed | 1 | August 15, 2024 | July 18, 2024 | 2024-10-CBZN | CB-2024-016 | November 21, 2023 | November 24, 2023 | December 07, 2024 | December 22, 2023 | May 15, 2024 | YSL Builder | none
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3rd | 1 |  | Construction of School Clinic | 4139595.02 |  | 4077553.98 | Completed | 1 | August 13, 2024 | August 30, 2024 | 2024-11-CBZN | CB-2024-017 | November 21, 2023 | November 24, 2023 | December 07, 2024 | December 27, 2023 | May 15, 2024 | CPAN Engineering & Enterprises | none
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1st | 1 |  | Proposed Construction Of One (1) Storey - Health Facilities | 2812007.03 |  | 2806210.33 | Completed | 1 | August 13, 2024 | August 13, 2024 | ZDS-24-HF-01 | ZDS-24-HF-01 | November 13, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2024 | May 15, 2024 | CPIN BUILDERS
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga del Sur | 303768 | Tabina National High School | TABINA | 2nd | 1 |  | Proposed Construction Of One (1) Storey - Health Facilities | 2859772.23 |  | 2854537.14 | Completed | 1 | August 13, 2024 | August 13, 2024 | ZDS-24-HF-02 | ZDS-24-HF-02 | November 13, 2023 | November 21, 2023 | December 4, 2023 | December 29, 2024 | May 15, 2024 | AYUS BUILDERS AND ENTERPRISES
SCHOOL HEALTH FACILITIES 2024 | Region IX | Zamboanga Sibugay | 125628 | Pangi Elementary School | Ipil | 2nd | 1 |  | Construction of Group Handwashing Facility - For Elementary (Option 1A - with Roofing, with Counter, with Tile Finish) | 282032.21 |  | 250149.56 | Completed | 1 | August 23, 2024 | November 22, 2024 | ZSY-2024HEALTH-01 | ZSY-2024HEALTH-01 | November 22, 2023 | November 29, 2023 | December 15, 2023 | February 28, 2024 | June 25, 2024 | AAFIAH CONSTRUCTION | Rectification of Punchlisted Items
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124533 | Alvenda ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124534 | Buena Suerte ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124535 | Delampinas ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124539 | Juan C. Dumaog Sr. ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124544 | Tinglan ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124545 | Totongon ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124546 | Tubak ES | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 314119 | Mutia NHS Extension - Alvenda | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303714 | Mutia NHS Annex - Tubak | MUTIA | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108064.83 | BATCH 1 | 108064.83 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124738 | Bagacay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124741 | Calube ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124743 | Kanim ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124744 | Libay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124745 | Magsaysay ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124746 | Marapong ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124750 | Sawang ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124751 | Sibutad CS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 108568.12 | BATCH 1 | 108568.12 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 124753 | Sipaloc ES | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 155060.65 | BATCH 1 | 155060.65 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303694 | Kanim NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303695 | Sawang NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Norte | 303737 | Sibutad NHS | SIBUTAD | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF TEN (10) - FAUCET HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH TILE FINISH) | 156747.73 | BATCH 1 | 156747.73 | Completed | 1 | 31/10/2022 | 31/10/2022 | WINS 2022 - RIX - ZAMBOANGA DEL NORTE | WINS 2022 - BEFF - RIX - ZDN | 44655 | 13/04/2022 | 26/04/2022 | 44656 | 30/06/2022 | YSL Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 501159 | Bogo Calabat IS | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259557.41 | BATCH 1 | 259557.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-01 | ZDS-22-HWF-01 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Chioco Builders and Supplies
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125078 | Dawa ES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259399.91 | BATCH 1 | 259399.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-02 | ZDS-22-HWF-02 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Chioco Builders and Supplies
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125080 | Josefina CES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 257509.91 | BATCH 1 | 257509.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-02 | ZDS-22-HWF-02 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Chioco Builders and Supplies
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125090 | Upper Bag-ong Tudela ES | Josefina | 1 | 1 | 1 | Construction Of Handwashing Facilities | 259452.41 | BATCH 1 | 259452.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-01 | ZDS-22-HWF-01 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Chioco Builders and Supplies
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125385 | Lumangoy ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 258874.91 | BATCH 1 | 258874.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-05 | ZDS-22-HWF-05 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Ayus Builders and Ent.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125386 | New Carmen ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 258822.41 | BATCH 1 | 258822.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Long Island Builders & Const.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 196032 | Sominot CES-SPED | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256774.91 | BATCH 1 | 256774.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-03 | ZDS-22-HWF-03 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125395 | Tungawan ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256722.41 | BATCH 1 | 256722.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Long Island Builders & Const.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125396 | Upper Sicpao ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256732.91 | BATCH 1 | 256732.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-04 | ZDS-22-HWF-04 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Long Island Builders & Const.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125394 | Eastern Sominot ES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256738.16 | BATCH 1 | 256738.16 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-05 | ZDS-22-HWF-05 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Ayus Builders and Ent.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125393 | Sominot CES | Sominot | 1 | 1 | 1 | Construction Of Handwashing Facilities | 256774.91 | BATCH 1 | 256774.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-03 | ZDS-22-HWF-03 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125457 | Limas ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258454.91 | BATCH 1 | 258454.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-09 | ZDS-22-HWF-09 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125459 | Maragang ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256144.91 | BATCH 1 | 256144.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-07 | ZDS-22-HWF-07 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125463 | Nilo ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256165.91 | BATCH 1 | 256165.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-07 | ZDS-22-HWF-07 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125464 | Tigbao CES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256176.41 | BATCH 1 | 256176.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-06 | ZDS-22-HWF-06 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125465 | Timolan ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258664.91 | BATCH 1 | 258664.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-09 | ZDS-22-HWF-09 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125467 | Woodland ES | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 258507.41 | BATCH 1 | 258507.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-08 | ZDS-22-HWF-08 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256186.91 | BATCH 1 | 256186.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-08 | ZDS-22-HWF-08 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | Tigbao | 2 | 1 | 1 | Construction Of Handwashing Facilities | 256197.41 | BATCH 1 | 256197.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-06 | ZDS-22-HWF-06 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | JZ Mago Construction & Enterprises
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125498 | Kapatagan ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259504.91 | BATCH 1 | 259504.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-10 | ZDS-22-HWF-10 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125499 | Limason ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259410.41 | BATCH 1 | 259410.41 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-11 | ZDS-22-HWF-11 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125500 | Linoguayan ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259399.91 | BATCH 1 | 259399.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-12 | ZDS-22-HWF-12 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | AJT Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125502 | Lunib ES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 259378.91 | BATCH 1 | 259378.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-12 | ZDS-22-HWF-12 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | AJT Construction
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 125507 | Vincenzo Sagun CES | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 257509.91 | BATCH 1 | 257509.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-11 | ZDS-22-HWF-11 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga del Sur | 303765 | Cogon NHS | Vincenzo A. Sagun | 2 | 1 | 1 | Construction Of Handwashing Facilities | 257404.91 | BATCH 1 | 257404.91 | Completed | 1 | 44601 | 44812 | ZDS-22-HWF-10 | ZDS-22-HWF-10 | 25/03/2022 | 44565 | 22/04/2022 | 16/06/2022 | 44658 | Cpin Builders
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 235553.07 | BATCH 1 | 235553.07 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125843 | Baganipay ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 238178.33 | BATCH 1 | 238178.33 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125853 | Samonte ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 242903.07 | BATCH 1 | 242903.07 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125848 | Kawilan ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 245570.59 | BATCH 1 | 245570.59 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125852 | Sagay ES | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 249780.83 | BATCH 1 | 249780.83 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.
SCHOOL HEALTH FACILITIES 2022 | Region IX | Zamboanga Sibugay | 125842 | Aurora PS | Talusan | 1 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 251849.59 | BATCH 1 | 251849.59 | Completed | 1 | 28/08/2022 | 45138 | ZSY-2022H-01 | ZSY-2022H-01 | 19/03/2022 | 28/03/2022 | 44869 | 29/04/2022 | 22/06/2022 | Sibugay RGT Construction Inc.

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%