## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2019 | Region VI | Aklan | 500171 | Lezo IS | LEZO | 0 | 1 | 5 | 1STY5CL W/ TOILET | 8794811.81 | 1 |  | Completed | 1 | 2020-05-01 |  | DEPED-REGIONVI-D1-2019QRFBATCH1-035-2019 | DEPED-REGIONVI-D1-2019QRFBATCH1-035-2019 | 2019-05-10 | 2019-05-17 | 2019-05-29 | 2019-06-14 | 2019-06-25 | First Makeen Construction | suspended Waiting for Building Permit
QRF 2019 | Region VI | Guimaras | 302430 | East Valencia National High School | BUENAVISTA | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 1818952.12 | 1 | 1500393.978 | Completed | 1 | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC.
QRF 2019 | Region VI | Guimaras | 115845 | Tinadtaran Elementary School | BUENAVISTA | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 2017883.65 | 1 | 1426275.672 | Completed | 1 | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC.
QRF 2019 | Region VI | Guimaras | 115862 | Don Pedro Vasquez Memorial School | JORDAN (Capital) | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1337767.73 | 1 | 1037532.27 | Completed | 1 | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC.
QRF 2019 | Region VI | Guimaras | 115870 | Espinosa Elementary School | JORDAN (Capital) | 0 | 1 | 8 | 1STY2CL W/ TOILET | 5602739.08 | 1 | 4382589.37 | Completed | 1 | 2019-12-26 |  | 01-2019 |  | 2019-05-11 | 2019-05-20 | 2019-07-03 | 2019-07-10 | 2019-07-24 | ARRIANNE MERCHANDSING AND CONSTRUCTION SERVICES, INC.
QRF 2020 | Region VI | Aklan | 302286 | Altavas National School | ALTAVAS | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 595334.53 | 1 | 489315.07 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114630 | DINA-UT ELEMENTARY SCHOOL | ALTAVAS | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 941250.66 | 1 | 931622.6 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 302309 | JOSE FELICIANO MEÑEZ MEMORIAL NATIONAL HIGH SCHOOL | BALETE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1390694.68 | 1 | 1142832.61 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114654 | Guanko Elementary School | BALETE | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 415787.69 | 1 | 341491.72 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 310602 | Mangan National High School | BANGA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 543063.6 | 1 | 539823.02 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHSNDISING
QRF 2020 | Region VI | Aklan | 114671 | Muguing ES | BANGA | 1 | 1 | 1 | REPAIR OF CLASSROOM | 1985700.94 | 1 | 1632641.53 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114681 | Batan Elementary School | BATAN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 2790841.14 | 1 | 2758634.82 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS
QRF 2020 | Region VI | Aklan | 302294 | Bay-ang-Magpag-ong NHS | BATAN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 818121.39 | 1 | 672695.06 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 302300 | Camaligan National High School | Batan | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 307071.25 | 1 | 252024.01 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 302301 | Camanci National High School | BATAN | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1121205.42 | 1 | 1112092.14 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 500640 | Ipil Integrated School | Batan | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 459203.67 | 1 | 455093.99 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114684 | CABUGAO ELEMENTARY SCHOOL | BATAN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1998105.89 | 1 | 1578488.91 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114752 | NEW BUSWANG ELEMENTARY SCHOOL | KALIBO | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1223802.91 | 1 | 966761.49 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 500545 | BAKHAW NORTE INTEGRATED SCHOOL | KALIBO (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3881635.52 | 1 | 3872738.39 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 302323 | Gaudencio L. Vega NHS (Nalook NHS) | KALIBO (Capital) | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 1064473.92 | 1 | 881275.6 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 500179 | Kalibo Integrated Special Education Center | KALIBO (Capital) | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 749837.63 | 1 | 747259.43 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 302313 | Linabuan NHS | KALIBO (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 275571.25 | 1 | 273750 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114759 | MOBO ELEMENTARY SCHOOL | KALIBO (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2059387.57 | 1 | 1611679.28 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114798 | ROSAL ELEMENTARY SCHOOL | LIBACAO | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 1056440.03 | 1 | 873660.85 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114804 | BACYANG PS | MADALAG | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 843785.93 | 1 | 623594.43 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114808 | Catabana PS | MADALAG | 1 | 1 | 1 | REPAIR OF CLASSROOM | 597861.39 | 1 | 439879.86 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114816 | MADALAG ELEMENTARY SCHOOL | MADALAG | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1777256.95 | 1 | 1485251.61 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 302302 | CANDELARIA NATIONAL HIGH SCHOOL | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 201102.87 | 1 | 200000 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114902 | Guinbaliwan ES | NEW WASHINGTON | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2151618.59 | 1 | 1690143.32 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114907 | New Washington ES | NEW WASHINGTON | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 3151041.45 | 1 | 3121202.54 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 302328 | Ochando National High School | NEW WASHINGTON | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 377604.5 | 1 | 373791.79 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 500186 | Pinamuk-an Integrated School | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 867507.12 | 1 | 862750 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114912 | Tambak ES | NEW WASHINGTON | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 430472.51 | 1 | 416890.59 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS
QRF 2020 | Region VI | Aklan | 114703 | BURUANGA ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 3987376.05 | 1 | 3980222.31 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 114704 | CABUGAO PRIMARY SCHOOL | BURUANGA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1678662.91 | 1 | 1398716.73 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 500182 | HABANA INTEGRATED SCHOOL | BURUANGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1304729.83 | 1 | 1291911.68 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114706 | KATIPUNAN ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 579650.18 | 1 | 482957.23 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114708 | PEPE ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2771247.16 | 1 | 2181493.99 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114709 | SANTANDER ELEMENTARY SCHOOL | BURUANGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 878754.75 | 1 | 723074.43 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114714 | AGUTAY ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1413248.63 | 1 | 1044403.63 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114716 | AQUINO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1561562.59 | 1 | 1154056.13 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114734 | Cabugao PS | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 2123435.38 | 1 | 1669611.98 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114721 | Mabusao ES | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 2659490.62 | 1 | 2639788.53 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 114723 | MALOCO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2879905.95 | 1 | 2871841.25 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 302321 | NAILE NATIONAL HIGH SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1335635.25 | 1 | 1039649.38 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114724 | ONDOY ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 832619.75 | 1 |  | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 114713 | AGBAGO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 1055552.18 | 1 | 780085.49 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114719 | IBAJAY CENTRAL SCHOOL | IBAJAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 2768795.78 | 1 | 2744654.09 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 114735 | MINA-A ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1579132.27 | 1 | 1538358.4 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS
QRF 2020 | Region VI | Aklan | 114737 | NAILE ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1095503.55 | 1 | 1080493.81 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | HF ENTERPRISES
QRF 2020 | Region VI | Aklan | 114738 | NAISUD CENTRAL SCHOOL | IBAJAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1384182.93 | 1 | 1175337.5 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114742 | RIZAL ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3664360.37 | 1 | 2885839.73 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114743 | SAN ISIDRO ELEMENTARY SCHOOL | IBAJAY | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1235624.75 | 1 | 975978.43 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114763 | AGCAWILAN SILAKAT NONOK ELEMENTARY SCHOOL | LEZO | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1124439.2 | 1 | 888059.84 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114768 | TAYHAWAN ELEMENTARY SCHOOL | LEZO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 470288.37 | 1 | 463525.22 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 114832 | CABATANGA ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2278330.32 | 1 | 1887044.25 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114836 | Castillo ES | MAKATO | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2364341.96 | 1 | 1958360.36 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114837 | CAYANGWAN ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3975645.21 | 1 | 3294339.15 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114842 | MANTIGUIB ELEMENTARY SCHOOL | MAKATO | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 866461.62 | 1 | 682877.77 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114845 | ARGAO ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2437500.16 | 1 | 1925461.92 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114847 | CATICLAN ELEMENTARY SCHOOL | MALAY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1933938.78 | 1 | 1601796.32 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114850 | MALAY ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2179109.43 | 1 | 1804928.08 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114851 | MANOC MANOC ELEMENTARY SCHOOL | MALAY | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1004012.2 | 1 | 831595.39 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114857 | BANAY BANAY ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 2262269.17 | 1 | 1786373.21 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114864 | LILO-AN ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 820342.19 | 1 | 647054.13 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 302312 | LILO-AN NATIONAL HIGH SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 488089.1 | 1 | 385349.33 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 302319 | MALINAO SCHOOL FOR PHILIPPINE CRAFTSMEN | MALINAO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2505469.69 | 1 | 1979260.19 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114871 | SAN DIMAS ELEMENTARY SCHOOL | MALINAO | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1845590.17 | 1 | 1456761.06 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 500643 | SAN ROQUE INTEGRATED SCHOOL | MALINAO | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3007858.2 | 1 | 2930000 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114881 | GIBON ELEMENTARY SCHOOL | NABAS | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 3575685.96 | 1 | 2809380.39 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114895 | Unidos Elementary School | NABAS | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 5243622.52 | 1 | 4114844.56 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | NAGAMOS BUILDERS
QRF 2020 | Region VI | Aklan | 302340 | Union National High School | NABAS | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 3979019.97 | 1 | 3969473.61 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | ANJUSH BUILDERS
QRF 2020 | Region VI | Aklan | 114884 | LIBERTAD ELEMENTARY SCHOOL | NABAS | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1338285.52 | 1 | 1330500 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114888 | NAGUSTAN ELEMENTARY SCHOOL | NABAS | 2 | 1 | 7 | REPAIR OF CLASSROOMS | 2426859.98 | 1 | 2412000 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | RISM BUILDERS AND CONSTRUCITON SERVICES, INC.
QRF 2020 | Region VI | Aklan | 114891 | RIZAL ELEMENTARY SCHOOL | NABAS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 2278337.19 | 1 | 2269712.29 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EARLY RISER CONSTRUCTION
QRF 2020 | Region VI | Aklan | 114892 | SOLIDO ELEMENTARY SCHOOL | NABAS | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 3147061.55 | 1 | 3109689.56 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 302337 | TOLEDO NATIONAL HIGH SCHOOL | NABAS | 2 | 1 | 10 | REPAIR OF CLASSROOMS | 802530.39 | 1 | 633756.4 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114896 | UNION ELEMENTARY SCHOOL | NABAS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 613868.81 | 1 | 594893.21 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | SOLID MERCHANDISING
QRF 2020 | Region VI | Aklan | 114915 | BADIO ELEMENTARY SCHOOL | NUMANCIA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1677639.66 | 1 | 1670421.19 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EARLY RISER CONSTRUCTION
QRF 2020 | Region VI | Aklan | 500639 | BAYBAY ALIBAGON INTEGRATED SCHOOL | NUMANCIA | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1693989.76 | 1 | 1338879.56 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 500035 | NUMANCIA INTEGRATED SCHOOL | NUMANCIA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 907335.74 | 1 | 897505.98 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | EARLY RISER CONSTRUCTION
QRF 2020 | Region VI | Aklan | 302327 | NUMANCIA NATIONAL SCHOOL OF FISHERIES | NUMANCIA | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 619521.73 | 1 | 489318.45 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | EDISON C. BUILDERS & CONSTRUCTION SUPPLY
QRF 2020 | Region VI | Aklan | 114933 | Sergio L. Taligatos ES | TANGALAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1826628 | 1 | 1527563.59 | Completed | 1 | 2020-12-29 | 2021-03-19 |  |  | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-10-22 | 2020-11-12 | MBM CONSTRUCTION
QRF 2020 | Region VI | Aklan | 500173 | TAMALAGON INTEGRATED SCHOOL | TANGALAN | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 808936.62 | 1 | 768000 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Aklan | 302336 | TANGALAN NATIONAL HIGH SCHOOL | TANGALAN | 2 | 1 | 11 | REPAIR OF CLASSROOMS | 5052738.08 | 1 | 4977000 | Completed | 1 | 2020-12-29 |  |  |  | 2020-06-15 | 2020-06-22 | 2020-07-06 | 2020-08-14 | 2020-08-24 | FIRST MAKEEN CONSTRUCTION
QRF 2020 | Region VI | Antique | 115003 | Alegria ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1169609.29 | 1 |  | Completed | 1 | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 115004 | Bacong ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2244175.24 | 1 |  | Completed | 1 | 2022-09-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 115005 | Banago ES | Caluya | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 4702937.78 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01D-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 115006 | Bonbon ES | Caluya | 0 | 1 | 9 | REPAIR OF CLASSROOMS | 3945027 | 1 |  | Completed | 1 | January 16, 2021 | March 12, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS
QRF 2020 | Region VI | Antique | 115007 | Caluya CS | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 6760487.52 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION
QRF 2020 | Region VI | Antique | 302350 | Caluya NHS | Caluya | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2145761.69 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION
QRF 2020 | Region VI | Antique | 115009 | Dionela PS | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2682474.88 | 1 |  | Completed | 1 | 2022-10-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 115010 | Harigue ES | Caluya | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 4089461.89 | 1 |  | Completed | 1 | 2022-09-30 |  |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 115011 | Hininga-an ES | Caluya | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1792265.18 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115014 | Lim ES | Caluya | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 1314074.66 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 115015 | Masanag ES | Caluya | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 7057906.86 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115016 | Sabang I ES | Caluya | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 726124.73 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01F-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | BENZEN CONSTRUCTION
QRF 2020 | Region VI | Antique | 115018 | Salamento ES | Caluya | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 624416.96 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01G-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115019 | Semirara ES | Caluya | 0 | 1 | 27 | REPAIR OF CLASSROOMS | 4395797.15 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 310705 | Semirara NHS | Caluya | 0 | 1 | 30 | REPAIR OF CLASSROOMS | 2396467.2 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 115021 | Sibato ES | Caluya | 0 | 1 | 13 | REPAIR OF CLASSROOMS | 7148019.21 | 1 |  | Completed | 1 | December 27, 2020 |  |  | R6-D2-2020QRF-01D-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 115022 | Sibay ES | Caluya | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 3095973.97 | 1 |  | Completed | 1 | January 16, 2021 | March 12, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS
QRF 2020 | Region VI | Antique | 310706 | Sibay NHS | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4977373.62 | 1 |  | Completed | 1 | January 16, 2021 | March 16, 2021 |  | R6-D2-2020QRF-01C-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | NAGAMOS BUILDERS
QRF 2020 | Region VI | Antique | 115023 | Sibolo ES | Caluya | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 4728747.3 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01B-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | ANJUSH BUILDERS
QRF 2020 | Region VI | Antique | 115025 | Tinogboc ES | Caluya | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2997956.14 | 1 |  | Completed | 1 | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 302382 | Tinogboc NHS | Caluya | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1670487.61 | 1 |  | Completed | 1 | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 115026 | Villarises ES | Caluya | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 2605244.65 | 1 |  | Completed | 1 | 2022-10-30 |  |  | R6-D2-2020QRF-01A-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | HADDEN CONSTRUCTION & SUPPLY | Repair still on-going. Very slow pacing due to lack of materials delivered in the island. All buildings were replaced roofing and trusses. Ceiling were installed. Remaining works includes windows, completion painting works, installation electrical fixtures,
QRF 2020 | Region VI | Antique | 302363 | Libertad NVS | LIBERTAD | 0 | 1 | 21 | REPAIR OF CLASSROOMS | 9725143.32 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115133 | Paz ES | LIBERTAD | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1478555.46 | 1 |  | Completed | 1 | January 16, 2021 | March 15, 2021 |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115137 | Taboc ES | LIBERTAD | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 755799.61 | 1 |  | Completed | 1 | January 16, 2021 | March 16, 2021 |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 302383 | Union NHS | LIBERTAD | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 420473.56 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01H-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115141 | Agripino Tambagahan MS | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 243256.8 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115146 | Buang ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 2152026.97 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115147 | Cabugao ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 301687.19 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115149 | Circiaco M. Tayco MS | Pandan | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1951904.87 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115152 | Guia ES | Pandan | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 2289937.5 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 302365 | Mag-aba NHS | Pandan | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 67617.78 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115161 | Pandan CS | Pandan | 0 | 1 | 11 | REPAIR OF CLASSROOMS | 72002.46 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115169 | Tabay ES | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 902382.95 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115170 | Talisay ES | Pandan | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 302048.99 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115172 | Vidal Gelito ES | Pandan | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 351019.46 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Antique | 115173 | Zaldivar ES | Pandan | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 363055.76 | 1 |  | Completed | 1 | January 16, 2021 |  |  | R6-D2-2020QRF-01 I-SR | June 18, 2020 | June 26, 2020 | July 8, 2020 | July 29, 2020 | September 18, 2020 | MJSB CONSTRUCTION & SUPPLY
QRF 2020 | Region VI | Capiz | 501089 | Bago Chiquito Integrated School | PANAY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1179035.37 | 1 | 953272.0764 | Completed | 1
QRF 2020 | Region VI | Capiz | 115635 | Navitas ES | PANAY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 348429.7 | 1 | 281711.9063 | Completed | 1
QRF 2020 | Region VI | Capiz | 500429 | AGLALANA INTEGRATED SCHOOL | Pilar | 1 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2340265.98 | 1 | 1899238.0662 | Completed | 1
QRF 2020 | Region VI | Capiz | 115692 | CABUGAO PRIMARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1332449.09 | 1 | 1009892.2482 | Completed | 1
QRF 2020 | Region VI | Capiz | 115670 | CARLOS V. LOPEZ ELEMENTARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1284078.81 | 1 | 1038201.6573 | Completed | 1
QRF 2020 | Region VI | Capiz | 302400 | Dulangan NHS | Pilar | 1 | 1 |  | REPLACEMENT OF FENCE | 1227585.69 | 1 | 930413.987 | Completed | 1
QRF 2020 | Region VI | Capiz | 115675 | Pilar Elementary School | PILAR | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 4704973.69 | 1 | 3550572.91 | Completed | 1
QRF 2020 | Region VI | Capiz | 115678 | San Esteban ES | PILAR | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1136198.18 | 1 | 829362.5097 | Completed | 1
QRF 2020 | Region VI | Capiz | 115681 | SAN RAMON ELEMENTARY SCHOOL | Pilar | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1058455.29 | 1 | 772614.4503 | Completed | 1
QRF 2020 | Region VI | Capiz | 115684 | STA. FE ELEMENTARY SCHOOL | Pilar | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 4288748.44 | 1 | 2895129.98 | Completed | 1
QRF 2020 | Region VI | Capiz | 310811 | Yating National high School | Pilar | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 710522.61 | 1 | 538520.5947 | Completed | 1
QRF 2020 | Region VI | Capiz | 115688 | Agbanog ES | Pontevedra | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 802415.74 | 1 | 604471.0526 | Completed | 1
QRF 2020 | Region VI | Capiz | 115698 | Hipona ES | PONTEVEDRA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 489070.33 | 1 | 368423.5574 | Completed | 1
QRF 2020 | Region VI | Capiz | 115704 | Rizal ES | PONTEVEDRA | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3412083.95 | 1 | 2487450.02 | Completed | 1
QRF 2020 | Region VI | Capiz | 310804 | Maindang National High School | CUARTERO | 2 | 1 |  | CONSTRUCTION OF RETAINING WALL | 9596206.74 | 1 | 5940052.74 | Completed | 1
QRF 2020 | Region VI | Capiz | 115464 | Sta. Rita ES | DUMALAG | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 102008.98 | 1 | 82785.176 | Completed | 1
QRF 2020 | Region VI | Capiz | 302406 | Ivisan NHS | IVISAN | 2 | 1 | 4 | REPAIR OF CLASSROOMS | 1178987.33 | 1 | 853021.9568 | Completed | 1
QRF 2020 | Region VI | Capiz | 115579 | Atiplo Elementary School | Mambusao | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 735104.19 | 1 | 531863.2332 | Completed | 1
QRF 2020 | Region VI | Capiz | 501095 | Calixto Loyola Sr. Integrated School | SIGMA | 2 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 532436.58 | 1 | 432097.8178 | Completed | 1
QRF 2020 | Region VI | Iloilo | 116118 | Abong ES | Carles | 3 | 1 | 2 | REPAIR OF CLASSROOMS | 913825.86 | 1 | 892785.23 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116010 | Bacolod PS | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 957041.07 | 1 | 813307.761 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116012 | Balasan CES | Balasan | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 1585598.25 | 1 | 1347497.97 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 302454 | Balasan NHS | Balasan | 5 | 1 | 42 | REPAIR OF CLASSROOMS | 2841359.36 | 1 | 2045727.76 | Completed | 1 | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders
QRF 2020 | Region VI | Iloilo | 116013 | Batuan ES | Balasan | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 686237.07 | 1 | 582880.42 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116015 | Gimamanay ES | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 769455.5 | 1 | 653804.98 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116016 | Kinalkalan ES | Balasan | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2264359.01 | 1 | 1639543.32 | Completed | 1 | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L2 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 116018 | Mamhut ES | Balasan | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2898061.78 | 1 | 2097510.66 | Completed | 1 | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L2 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 180030 | Mamhut PS | Balasan | 5 | 1 | 1 | REPAIR OF CLASSROOM | 321035.62 | 1 | 272527.2 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116020 | Pedro Bedez ES | Balasan | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1973278.4 | 1 | 1996126.5 | Completed | 1 | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L3 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 116021 | Quisan ES | Balasan | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 769455.5 | 1 | 653394.43 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L1 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116025 | Zaragosa ES | Balasan | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 2759380.9 | 1 | 1439412.98 | Completed | 1 | 2021-01-26 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L3 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 116093 | Binon-an ES | Batad | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 937111.78 | 1 | 702530.625 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116095 | Jose P. Gonzaludo ES | Batad | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 380482.45 | 1 | 285081.6975 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116099 | Malico ES | Batad | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1974140.79 | 1 | 1480217.7975 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116100 | Pasayan PS | Batad | 5 | 1 | 1 | REPAIR OF CLASSROOM | 399175.07 | 1 | 298937.76 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L4 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 180021 | Sta. Ana ES | Batad | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 835117.01 | 1 | 830383.64 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 311001 | Valerio Palmares NHS | Batad | 5 | 1 | 12 | REPAIR OF CLASSROOMS | 725529.38 | 1 | 720235.49 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 116199 | Alipata ES | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1427101.42 | 1 | 1394341.17 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116200 | Asluman ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1806457.34 | 1 | 1800266.79 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 116236 | Bagotao | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1048842.02 | 1 | 1017173.44 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 501492 | Barangcalan IS | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 492461.58 | 1 | 476727.2 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 180045 | Batuan IS | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 1102610.65 | 1 | 1094247 | Completed | 1 | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 501493 | Binuluangan IS | Carles | 5 | 1 | 15 | REPAIR OF CLASSROOMS | 3240027.28 | 1 | 3233722.48 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 116206 | Bito-on ES | Carles | 5 | 1 | 11 | REPAIR OF CLASSROOMS | 1435144.38 | 1 | 1402165.76 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116207 | Bolo ES | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 3275062.51 | 1 | 3270118.63 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L8 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 501486 | Buenavista IS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2053364.11 | 1 | 2003815.47 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L13 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116211 | Cana PS | Carles | 5 | 1 | 1 | REPAIR OF CLASSROOM | 561671.58 | 1 | 548307.84 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L5 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116213 | Cawayan ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2354426.17 | 1 | 1695466.3 | Completed | 1 | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders
QRF 2020 | Region VI | Iloilo | 302482 | Cawayan NHS | Carles | 5 | 1 | 13 | REPAIR OF CLASSROOMS | 1394637.96 | 1 | 1004170.48 | Completed | 1 | 2021-01-26 | 2021-12-20 | QRF2020-RVI-ILOILO-B1-L7 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | Sky Builders
QRF 2020 | Region VI | Iloilo | 302494 | Don Casimero Andrada NHS | Carles | 5 | 1 | 3 | REPAIR OF CLASSROOMS | 380482.45 | 1 | 2554599.41 | Completed | 1 | 2021-01-14 | 2021-11-12 | QRF2020-RVI-ILOILO-B1-L22 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | MBM Construction
QRF 2020 | Region VI | Iloilo | 116217 | Granada ES | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 930705.26 | 1 | 919886.46 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 302505 | Granada NHS | Carles | 5 | 1 | 5 | REPAIR OF CLASSROOMS | 1023901.19 | 1 | 1015313.69 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 311009 | Granada NHS - Ballesteros Campus | Carles | 5 | 1 | 20 | REPAIR OF CLASSROOMS | 3096850.34 | 1 | 2996800 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L20 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116219 | Lantangan ES | Carles | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 6256169.73 | 1 | 6213161.89 | Completed | 1 | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L15 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 501489 | Manlot IS | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1777067.09 | 1 | 1724299.36 | Completed | 1 | 2021-01-26 | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L12 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116255 | Martin Azuelo MS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 3526759.03 | 1 | 2965893.11 | Completed | 1 | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L14 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 116221 | Naborot ES | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2410394.5 | 1 | 2397198.59 | Completed | 1 | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L9 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders
QRF 2020 | Region VI | Iloilo | 116222 | Pantalan IS | Carles | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2721365.52 | 1 | 2695355.31 | Completed | 1 | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L9 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders
QRF 2020 | Region VI | Iloilo | 116223 | Piagao PS | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 482775.42 | 1 | 476106.93 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L6 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 116225 | San Fernando ES | Carles | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 1751891.33 | 1 | 1740873.46 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L10 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 501487 | Tabugon IS | Carles | 5 | 1 | 8 | REPAIR OF CLASSROOMS | 2098301.4 | 1 | 2047784.52 | Completed | 1 |  | 2021-06-16 | QRF2020-RVI-ILOILO-B1-L13 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 |  | RISM Builders and Services, Inc.
QRF 2020 | Region VI | Iloilo | 116227 | Talinting ES | Carles | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 4413345.79 | 1 | 4364729.89 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L10 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 302577 | Talinting NHS | Carles | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 5020686.68 | 1 | 4994871.08 | Completed | 1 | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L11 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 116228 | Tarong ES | Carles | 5 | 1 | 9 | REPAIR OF CLASSROOMS | 2733580.58 | 1 | 2312185.38 | Completed | 1 | 2021-01-14 | 2021-01-08 | QRF2020-RVI-ILOILO-B1-L14 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 116229 | Tinigban IS | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 727158.47 | 1 | 722474.15 | Completed | 1 | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 116230 | Toong ES | Carles | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 1665686.79 | 1 | 1658730.72 | Completed | 1 | 2021-01-14 | 2021-01-06 | QRF2020-RVI-ILOILO-B1-L23 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-09 | Micro Asia Builders Corp
QRF 2020 | Region VI | Iloilo | 116233 | Tupaz ES | Carles | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 2683766.38 | 1 | 2626964.41 | Completed | 1 | 2021-01-27 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L8 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | Early Riser Construction
QRF 2020 | Region VI | Iloilo | 116263 | Taloto-an ES | Concepcion | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 2385019.62 | 1 | 2380331.98 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 116346 | Bayas ES | Estancia | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 4769183.85 | 1 | 4752274.32 | Completed | 1 | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders
QRF 2020 | Region VI | Iloilo | 302462 | Bayas NHS | Estancia | 5 | 1 | 6 | REPAIR OF CLASSROOMS | 338763.96 | 1 | 329090.38 | Completed | 1 | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders
QRF 2020 | Region VI | Iloilo | 116347 | Botongon ES | Estancia | 5 | 1 | 7 | REPAIR OF CLASSROOMS | 1995704.07 | 1 | 1410628.26 | Completed | 1 | 2021-01-26 | 2021-12-13 | QRF2020-RVI-ILOILO-B1-L18 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 116349 | Estancia CES | Estancia | 5 | 1 | 10 | REPAIR OF CLASSROOMS | 3132916.19 | 1 | 2175718.12 | Completed | 1 | 2021-01-26 | 2021-12-13 | QRF2020-RVI-ILOILO-B1-L18 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-21 | MJBL Construction
QRF 2020 | Region VI | Iloilo | 302500 | Estancia NHS | Estancia | 5 | 1 | 18 | REPAIR OF CLASSROOMS | 3500000 | 1 | 227810.58 | Completed | 1 | 2021-01-15 | 2021-11-12 | QRF2020-RVI-ILOILO-B1-L22 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | MBM Construction
QRF 2020 | Region VI | Iloilo | 116351 | Loguingot ES | Estancia | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 838104.79 | 1 | 832213.44 | Completed | 1 | 2021-01-15 | 2021-01-20 | QRF2020-RVI-ILOILO-B1-L16 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | Anjush Builders
QRF 2020 | Region VI | Iloilo | 116355 | San Roques ES | Estancia | 5 | 1 | 4 | REPAIR OF CLASSROOMS | 2217169.99 | 1 | 1706805.64 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L19 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116356 | Tanza ES | Estancia | 5 | 1 | 14 | REPAIR OF CLASSROOMS | 2789328.5 | 1 | 2146498.74 | Completed | 1 | 2021-01-27 | 2021-11-05 | QRF2020-RVI-ILOILO-B1-L19 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-22 | SLW8 Builders
QRF 2020 | Region VI | Iloilo | 116675 | Amayong PS | SAN DIONISIO | 5 | 1 | 1 | REPAIR OF CLASSROOM | 434642.77 | 1 | 431061.92 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 116684 | Madanlog Elementary School | SAN DIONISIO | 5 | 1 | 2 | REPAIR OF CLASSROOMS | 697640.13 | 1 | 692861.87 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Iloilo | 116685 | Malunoy ES | San Dionisio | 5 | 1 | 1 | REPAIR OF CLASSROOM | 508286.01 | 1 | 504739.84 | Completed | 1 | 2021-01-15 | 2020-12-21 | QRF2020-RVI-ILOILO-B1-L17 |  | June 10, 2020 | June 18, 2020 | July 1, 2020 | 2020-09-03 | 2020-09-10 | HF Enterprises
QRF 2020 | Region VI | Roxas City | 302756 | Balijuagan NHS | Roxas City | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 249849.27 | 1 | 230989.57 | Completed | 1 | 2021-02-13 | 2020-11-10 |  | CON-2020-016/1 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY
QRF 2020 | Region VI | Roxas City | 117681 | Don Jose Acevedo ES | Roxas City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 267455.2 | 1 | 234618.83 | Completed | 1 | 2021-02-13 | 2020-11-17 |  | CON-2020-016/3 |  |  |  | 2020-09-13 | 2020-10-05 | NANA BUILDERS
QRF 2020 | Region VI | Roxas City | 117657 | Dumolog ES | Roxas City | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 649479.2 | 1 | 590706.37 | Completed | 1 | 2021-02-13 | 2020-11-23 |  | CON-2020-016/4 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY
QRF 2020 | Region VI | Roxas City | 302760 | Milibili NHS | Roxas City | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 227053.34 | 1 | 204225.29 | Completed | 1 | 2021-02-13 | 2020-11-10 |  | CON-2020-016/2 |  |  |  | 2020-09-13 | 2020-10-05 | GGMU CONST &SUPPLY
QRF 2022 | Region VI | Guimaras | 115844 | Supang Central School | BUENAVISTA | 0 | 1 | 4 | REPAIR/ REHABILITATION | 2926129.7794 | 1 | 2433541.73 | completed | 1 | 2022-12-29 | 2022-12-26 | 05-2022-lot 1 | 05-2022-lot 1 | No. 05-A-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | ALJ Construction and Supply
QRF 2022 | Region VI | Guimaras | 115897 | Nueva Valencia Central School | NUEVA VALENCIA | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2464442.2247 | 1 | 3155555.55 | completed | 1 | 2022-12-29 | 2023-12-29 | 05-2022-lot2 | 05-2022-lot2 | No. 05-B-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | Early Riser Construction
QRF 2022 | Region VI | Guimaras | 115877 | Ayangan Elementary School | SIBUNAG | 0 | 1 | 6 | REPAIR/ REHABILITATION | 3191080.3436 | 1 | 2900000 | completed | 1 | 2022-12-29 | 2022-12-28 | 05-2022-lot3 | 05-2022-lot3 | No. 05-C-2022 | 2022-05-23 | 2022-06-09 | 2022-06-23 | 2022-07-01 | IJOJPA Construction
QRF 2022 | Region VI | Iloilo | 116570 | Miagao Central Elementary School | MIAGAO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 2089631.17 | 1 |  | completed | 1 |  | 2022-11-17 | QRF2022-RVI-022-ILOILO-L1 |  | 2022-06-03 |  | 2022-06-27 | 2022-08-08 | 2022-10-14 | ANJUSH BUILDERS
QRF 2022 | Region VI | Iloilo | 116740 | San Joaquin Central Elementary School | SAN JOAQUIN | 1 | 1 | 2 | REPAIR/ REHABILITATION | 842235.89 | 1 |  | completed | 1 |  | 2022-11-17 | QRF2022-RVI-022-ILOILO-L1 |  | 2022-06-03 |  | 2022-06-27 | 2022-08-08 | 2022-10-14 | ANJUSH BUILDERS
QRF 2022 REPLENISHMENT | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1358264.3352 | 1 | 1078677.99 | Completed | 1 | 2023-06-02 | 2023-06-02 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | 2023-02-06 | 2023-02-13 | 2023-02-27 | 2023-03-08 | 2023-03-27 | AGM SILVER CONSTRUCTION
QRF 2022 REPLENISHMENT | Region VI | Aklan | 114786 | Libacao Central ES | LIBACAO | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1505376.28 | 1 | 1248136.99 | COMPLETED | 1 | 2023-06-02 | 2023-06-02 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | DepED-RO6-D1-2022QRF(REPAIR)-007-2023 | 2023-02-06 | 2023-02-13 | 2023-02-27 | 2023-03-08 | 2023-03-27 | AGM SILVER CONSTRUCTION | completed
QRF 2022 REPLENISHMENT | Region VI | Guimaras | 115858 | Suclaran Central School | SAN LORENZO | Lone | 1 | 14 | REPAIR OF CLASSROOMS | 6521637.2579 | 1 | 6471000 | COMPLETED | 1 | 2023-09-05 | 2023-09-01 | 01-2023 | 01-2023 | 2023-02-02 | 2023-02-27 | 2023-03-02 | 2023-03-15 | 2023-03-27 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | substancially completed; conducted final inspection
QRF 2024 | Region VI | Iloilo | 116055 | Salihid ES | BAROTAC NUEVO | 4th | 1 | 2 | 1STY2CL | 9475815.29 | 1- NC | 6702484.43 | Ongoing | 0.87 | 2025-08-06 |  | QRF2024-RVI-022-ILOILO-L1 | QRF2024-RVI-022-ILOILO-L1 | 2024-08-08 | 2024-08-14 | 2024-08-30 | 2024-09-11 | 2024-12-06 | EARLY RISER CONSTRUCTION | For Contract

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%