## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 11, 2025
ELECTRIFICATION 2017 | Region VII | Bohol | 118491 | Badbad ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 347696.8 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 186504 | Cabacungan ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 291626.73 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118474 | Cabilao ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1082997.16 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118476 | Cambaquiz ES | LOON | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 392980.38 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118542 | Lagtangon ES | MARIBOJOC | 1 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 154103.28 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118059 | Anonang PS | BUENAVISTA | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 122092.55 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118330 | Corte-Baud ES | JETAFE | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 281657 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | Region VII | Bohol | 118814 | Cuya Elem School | UBAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 83692.63 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2018 | Region VII | Bogo City | 500407 | City of Bogo Science and Arts Academy | CITY OF BOGO | 4 | 1 | UPGRADING | 2 | 2041601.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302850 | Fatima NHS | CORTES | 1 | 1 | UPGRADING | 1 | 934429.73 | 928930.49 | COMPLETED | 1 |  |  |  | 2018-INFRA-034 | 2018-07-30 | 2018-08-07 | 2018-08-20 | 2018-10-25 | Sept. 5, 2018 | MEGABLUE KONTRAK CORP. |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302817 | Biking Tech-Voc HS | DAUIS | 1 | 1 | UPGRADING | 1 | 2927879.56 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302908 | Tabalong NHS | DAUIS | 1 | 1 | UPGRADING | 1 | 1170845.23 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302881 | Pagnito-an NHS | MARIBOJOC | 1 | 1 | UPGRADING | 1 | 1272128.36 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302906 | Sikatuna NHS | SIKATUNA | 1 | 1 | UPGRADING | 1 | 2100247.26 | 2085170.52 | COMPLETED | 1 |  |  |  | 2018-INFRA-034 | 2018-07-30 | 2018-08-07 | 2018-08-20 | 2018-10-25 | 2018-09-05 | MEGABLUE KONTRAK CORP. |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 312333 | Tubigon West Central HS | TUBIGON | 1 | 1 | UPGRADING | 1 | 1841339.03 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302822 | Tubigon West NHS | TUBIGON | 1 | 1 | UPGRADING | 1 | 1831127.71 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302886 | Pres. Carlos P. Garcia Technical Vocational School of Fisheries and Arts | BIEN UNIDO | 2 | 1 | UPGRADING | 1 | 2244438.83 |  | COMPLETED | 1 | [9 empty] | WIL TAN CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302830 | Cangawa NHS | BUENAVISTA | 2 | 1 | UPGRADING | 1 | 2190473.84 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302842 | Cantubod NHS | DANAO | 2 | 1 | UPGRADING | 1 | 1473448.07 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302841 | Danao NHS | DANAO | 2 | 1 | UPGRADING | 1 | 1480446.26 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302891 | San Jose NHS | INABANGA | 2 | 1 | UPGRADING | 1 | 1598514.16 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302913 | Tulang NHS | JETAFE | 2 | 1 | UPGRADING | 1 | 1705970.03 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302888 | Eugenio V. Amores MHS | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 1174611.91 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 312309 | JAPER Memorial High Shoool | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 1478617.91 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302887 | San Agustin NHS | SAGBAYAN (BORJA) | 2 | 1 | UPGRADING | 1 | 2050773.44 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302873 | Mahayag National High School | SAN MIGUEL | 2 | 1 | UPGRADING | 2 | 1740854.71 | 1455092.1 | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302893 | San Jose NHS | TALIBON | 2 | 1 | UPGRADING | 1 | 1998749.2 |  | COMPLETED | 1 | [9 empty] | MAQUESERG CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302816 | Biabas Trade High School | UBAY | 2 | 1 | UPGRADING | 1 | 1390322.41 |  | COMPLETED | 1 | [9 empty] | MABB CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302825 | Camambugan NHS | UBAY | 2 | 1 | UPGRADING | 1 | 1568580.44 |  | COMPLETED | 1 | [9 empty] | MABB CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302899 | San Pascual National Agr'l HS | UBAY | 2 | 1 | UPGRADING | 1 | 2030908.29 |  | COMPLETED | 1 | [9 empty] | MABB CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302914 | Union NHS | UBAY | 2 | 1 | UPGRADING | 1 | 1471889.96 |  | COMPLETED | 1 | [9 empty] | MABB CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302809 | Alicia Technical-Voc'l HS | ALICIA | 3 | 1 | UPGRADING | 1 | 2241906.13 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302810 | Ambassador Pablo R. Suarez, Jr. NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 1064141.97 |  | COMPLETED | 1 | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302860 | Katipunan NHS | CARMEN | 3 | 1 | UPGRADING | 1 | 2806151.62 |  | COMPLETED | 1 | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302885 | Policronio S. Dano, Sr. HS | CARMEN | 3 | 1 | UPGRADING | 1 | 1112355.22 |  | COMPLETED | 1 | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 312339 | Ponciano F. Ramasola Sr. High School | CARMEN | 3 | 1 | UPGRADING | 1 | 1294081.44 |  | COMPLETED | 1 | [9 empty] | HME CLAVITE CONSTRUCTION AND SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302855 | Guinsularan High School | DUERO | 3 | 1 | UPGRADING | 2 | 995481.66 | 855231.3 | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302849 | Faraon NHS | JAGNA | 3 | 1 | UPGRADING | 2 | 1023687.84 | 834545.25 | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302884 | Pilar Technical-Vocational HS | PILAR | 3 | 1 | UPGRADING | 1 | 2898887.62 |  | COMPLETED | 1 | [9 empty] | WIL TAN CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302848 | Dusita High School | SIERRA BULLONES | 3 | 1 | UPGRADING | 1 | 1031990.82 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302905 | Sierra Bullones Technical Vocational High School | SIERRA BULLONES | 3 | 1 | UPGRADING | 1 | 2750227.21 |  | COMPLETED | 1 | [9 empty] | RONNYL CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Bohol | 302916 | Valencia Tech-Voc HS | VALENCIA | 3 | 1 | UPGRADING | 1 | 2980751.81 |  | COMPLETED | 1 | [9 empty] | LTS BUILDERS & CONSTRUCTION SUPPLY |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 302970 | Can-asujan NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2347731.87 | 2217698.26 | COMPLETED | 1 | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CAN-ASUJAN NATIONAL HIGH SCHOOL (Lot 1) | 2018-eloectrification-carcar-lot1 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 302972 | Carcar Central National High School (Pob. Night) | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2031404 | 1873580.29 | COMPLETED | 1 | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ CARCAR CENTRAL NATIONAL HIGH SCHOOL (Lot 2) | 2018-eloectrification-carcar-lot2 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 303016 | Maximino Noel Memorial National High School | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2770566.64 | 2327102.41 | COMPLETED | 1 | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ MAXIMINO NOEL MEMORIAL NATIONAL HIGH SCHOOL (Lot 3) | 2018-eloectrification-carcar-lot3 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 303066 | OCAÑA NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 1975444.19 | 1660698.44 | COMPLETED | 1 | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ OCAÑA NATIONAL HIGH SCHOOL (Lot 4) | 2018-eloectrification-carcar-lot4 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 303082 | ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2010499.34 | 1896106.26 | COMPLETED | 1 | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ ROBERTO E. SATO MEMORIAL NATIONAL HIGH SCHOOL (Lot 5) | 2018-eloectrification-carcar-lot5 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 324904 | Tuyom National High School | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2089088.32 | 1743738.88 | COMPLETED | 1 | 2018-11-08 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ TUYOM NATIONAL HIGH SCHOOL (Lot 6) | 2018-eloectrification-carcar-lot7 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-03 | 2018-08-03 | PJA CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Carcar City | 303126 | Valencia VOCATIONAL NHS | CITY OF CARCAR | 1 | 1 | UPGRADING | 1 | 2344712.74 | 2215627.09 | COMPLETED | 1 | 2018-11-25 |  | CY 2018 BEFF ELECTRIFICATION PROGRAM @ VALENCIA VOCATIONAL NATIONAL HIGH SCHOOL (Lot 7) | 2018-eloectrification-carcar-lot6 | 2018-05-30 | 2018-06-05 | 2018-06-19 | 2018-08-10 | 2018-08-20 | SUKI TRADING CORPORATION |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303049 | Magsico NHS | SAN FERNANDO | 1 | 1 | UPGRADING | 2 | 1133120.63 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303022 | Julian Enad MNHS | SIBONGA | 1 | 1 | UPGRADING | 2 | 955332.52 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303018 | Guiwanon NHS | GINATILAN | 2 | 1 | UPGRADING | 2 | 1374105.86 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302928 | Balao NHS | BARILI | 3 | 1 | UPGRADING | 1 | 1282976.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303069 | Bartolome & Manuela Pañares MNHS | BARILI | 3 | 1 | UPGRADING | 1 | 2547911.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302939 | Bateria NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 2 | 2647612.01 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302962 | Malingin NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 1 | 1250231.37 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302963 | Paypay NHS | DAANBANTAYAN | 4 | 1 | UPGRADING | 2 | 1337053.81 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302964 | Tapilon National High School | DAANBANTAYAN | 4 | 1 | UPGRADING | 1 | 1244277.65 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303048 | San Agustin NHS | MADRIDEJOS | 4 | 1 | UPGRADING | 2 | 1413045.85 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303054 | Medellin National High School | MEDELLIN | 4 | 1 | UPGRADING | 2 | 1600155.61 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303027 | Medellin National Science and Technology School | MEDELLIN | 4 | 1 | UPGRADING | 2 | 841720.41 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 500220 | Anapog IS | San Remegio | 4 | 1 | UPGRADING | 1 | 1347045.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 500221 | Busogon IS | San Remegio | 4 | 1 | UPGRADING | 1 | 1067155.76 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303030 | Lambusan NHS | SAN REMIGIO | 4 | 1 | UPGRADING | 1 | 1518405.3 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303041 | Libaong National High School | SAN REMIGIO | 4 | 1 | UPGRADING | 2 | 828800.91 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303046 | Luyang NHS | SAN REMIGIO | 4 | 1 | UPGRADING | 2 | 1237904.04 |  | COMPLETED | 1 | [9 empty] | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303106 | Borbon NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1792226.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303107 | Campusong NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1730711.16 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303104 | Tabunan NHS | BORBON | 5 | 1 | UPGRADING | 1 | 1751641.51 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302975 | Cantumog NHS | CARMEN | 5 | 1 | UPGRADING | 1 | 2388626.23 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 312447 | Catmon Integrated School | CATMON | 5 | 1 | UPGRADING | 1 | 2468951.37 | 2448368.96 | COMPLETED | 1 |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-04 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-04 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302979 | Ceferino Sususco MNHS | CATMON | 5 | 1 | UPGRADING | 1 | 2525970.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302980 | Tinabyonan NHS | CATMON | 5 | 1 | UPGRADING | 1 | 1541167.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 312448 | Bagalnga Integrated School | COMPOSTELA | 5 | 1 | UPGRADING | 1 | 2018447.79 | 1995402.85 | COMPLETED | 1 |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303062 | Mulao NHS | COMPOSTELA | 5 | 1 | UPGRADING | 1 | 1428334.68 | 1413806.38 | COMPLETED | 1 |  |  | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018 BEFFF ELECTRIFICATION BATCH 1-DEPED-R7-CEBU-05 | 2018-03-01 | 2018-03-08 | 2018-03-20 | 2018-03-27 | 2018-05-09 | Rovilla Construction |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 312407 | Arcelo Memorial National Night High School | LILOAN | 5 | 1 | UPGRADING | 2 | 456948.79 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302954 | Cabangahan NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1381008.6 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302988 | Consolacion NHS - Day Class | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1740293.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302989 | Consolacion NHS - Evening Class | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1593451.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 303010 | Garing NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 2014254.07 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302992 | Tolotolo NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 622369.41 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302993 | Tugbongan NHS | CONSOLACION | 6 | 1 | UPGRADING | 1 | 1130749.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu | 302955 | Cordova NHS | CORDOBA | 6 | 1 | UPGRADING | 1 | 1284016.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303152 | Barrio Luz NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1358540.5692 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303136 | Busay National High School | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 492928.39 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303157 | Guba NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 510261.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303139 | Lahug NHS (Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 1386454.8506 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303132 | Lusaran NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 390803.7096 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303151 | MABOLO NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 995711.3531 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303137 | Paril NHS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 383685.6969 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303156 | Zapatera NHS (Day & Night) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | 2 | 2120006.304 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303134 | Bonbon NHS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 324999.5883 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303143 | Bulacao Community HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 465552.23 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303141 | Cebu City National Science HS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1057985.3984 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303133 | Don Vicente Rama Mem. NHS (Basak NHS) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1980550.9437 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303145 | Inayawan National High School | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 1079973.4794 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303159 | Pardo NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 864341.69 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Cebu City | 303147 | Pasil NHS (Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING | 2 | 858364.18 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | City of Naga, Cebu | 303120 | Tuyan National High School | CITY OF NAGA | 0 | 1 | UPGRADING | 2 | 1130846.69 |  | COMPLETED | 1 | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | City of Naga, Cebu | 303121 | Uling National High School | CITY OF NAGA | 0 | 1 | UPGRADING | 2 | 1361639.32 |  | COMPLETED | 1 | 2018-09-09 | 2018-09-24 | cityofnaga 2018-003 |  | April 13-20, 2018 | 2018-04-13 | 2018-04-26 | 2018-05-14 | 2018-06-04 | QCC CONSTRUCTION AND SUPPLY |  | Y | UPGRADING
ELECTRIFICATION 2018 | Region VII | Danao City | 303037 | Maslog National High School | DANAO CITY | 5 | 1 | UPGRADING | 2 | 1877921.65 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303174 | Bankal NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 1934925.66 | 1913070.65 | COMPLETED | 1 | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303177 | Lo-ok National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 1823236.74 | 2237468.87 | COMPLETED | 1 | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Lapu-Lapu City | 303184 | Pajo NHS | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | 1 | 2250748.96 | 1813193.79 | COMPLETED | 1 | September 27, 2018 | [6 empty] | April 23, 2018 | June 27, 2018 | Golden Hammer Const. & Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303195 | Canduman NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 1191779.37 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303198 | Jagobiao NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 923407.94 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Mandaue City | 303199 | Mandaue City Comprehensive NHS | MANDAUE CITY | 6 | 1 | UPGRADING | 1 | 1196363.52 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | Region VII | Tagbilaran City | 302876 | Tagbilaran City Science High School | TAGBILARAN CITY (Capital) | 1 | 1 | UPGRADING | 1 | 1682365.93 |  | COMPLETED | 1 | December 31, 2018 | [8 empty] | DOLCI Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 322204 | Bulacao NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 435845.86 | 432795.6713 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 119799 | Jaclupan ES | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 478753.59 | 475256.61 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 322206 | Lagtang Night HS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 431634.01 | 428633.8283 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303040 | Lawaan NHS, Talisay | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 509937.6 | 505787.3821 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 322201 | Maghaway NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 552344.64 | 547585.844 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303056 | Mohon NHS (Mohon Divino Amore NHS) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 415655.55 | 412816.1243 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303020 | Pooc NHS (Jaclupan NHS - Pooc Ext.) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 460428.75 | 456866.8163 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303088 | San Roque NHS ( Laray NHS - Jaclupan NHS Ext.) | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 415293.38 | 412850.5643 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303111 | Tabunok Night HS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 475590.16 | 471024.6803 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 303113 | Talisay City National High School | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 570530.15 | 566019.5863 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Talisay City | 322208 | Tapul NHS | CITY OF TALISAY | 1 | 1 | UPGRADING | 1 | 483053.92 | 479566.3253 | COMPLETED | 1 |  |  |  |  | 5/59/2018 | 2018-06-04 | 2018-06-19 | 2018-06-27 | 2018-07-30 | QCC Construction |  |  | UPGRADING
ELECTRIFICATION 2018 | Region VII | Toledo City | 303308 | Bato NHS | TOLEDO CITY | 3 | 1 | UPGRADING | 2 | 858349.32 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 312431 | Anonang Sur Tabaco Frasco National High School | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 764782.24 | 756394.8 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 312405 | Bartolome C.Pianar MNHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 694909.17 | 687119.16 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302931 | Binabag NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 1219758.42 | 1201604.17 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302932 | Cayang NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 990347.65 | 976920.87 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 500408 | Don Celestino Martinez Sr. Taytayan IS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1205778.44 | 1187851.32 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302933 | Don Potenciano Catarata MNHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 1181894.88 | 1150857.5 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302930 | Eduardo T. Oporto Memorial National High School | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1163306.89 | 1153023.49 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | May 10, 2019 | May 20, 2019 | June 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302934 | Jovencio N. Masong NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 2124036.52 | 2029454.29 | COMPLETED | 1 | Nov. 27, 2019 | Mar. 12, 2020 | [5 empty] | Jan. 11, 2019 | August 29,2019 | FE AND A |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302935 | La Paz NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 1260924.03 | 1247945.84 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302936 | Libertad NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 1 | 2380700.33 | 2359221.93 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | May 10, 2019 | June 20, 2019 | August 4, 2019 | june 13, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bogo City | 302937 | Odlot NHS | CITY OF BOGO | 4 | 1 | UPGRADING | Batch 3 | 885454.79 | 875318.51 | COMPLETED | 1 | Nov. 27, 2019 |  |  |  | July 9, 2019 | July 19, 2019 | August 1, 2019 | August 5, 2019 | August 29,2019 | NGP CONSTRUCTION |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302907 | Bantolinao National High School | ANTEQUERA | 1 | 1 | UPGRADING |  | 1500130.47 | 1342928.34 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | ROMERO CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302824 | Mayor A. R. Tuazon Nat'l Sch. of Fisheries | CALAPE | 1 | 1 | UPGRADING | Batch 3 | 1441092.24 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302833 | Catigbian NHS | CATIGBIAN | 1 | 1 | UPGRADING |  | 1306035.61 | 1298492.96 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 312320 | Haguilanan High School | CATIGBIAN | 1 | 1 | UPGRADING | Batch 3 | 934808.92 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302877 | Mantacida National High School | CATIGBIAN | 1 | 1 | UPGRADING | Batch 3 | 1037282.51 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302839 | Corella National High School | CORELLA | 1 | 1 | UPGRADING |  | 1121295.01 | 1059900.95 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | WIL TAN CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302853 | Gov. Jacinto Borja National High School | LOON | 1 | 1 | UPGRADING |  | 1279258.03 | 1122580.33 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | ROMERO CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302819 | Busao National High School | MARIBOJOC | 1 | 1 | UPGRADING |  | 1439183.94 | 1360376.14 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | WIL TAN CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302835 | Cawayanan NHS | TUBIGON | 1 | 1 | UPGRADING |  | 1121295.01 | 1114621.36 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302879 | Nahawan NHS | CLARIN | 2 | 1 | UPGRADING |  | 1622744.38 | 1453167.3 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | QUICKSILVER CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302840 | Dagohoy NHS / Integrated SHS | DAGOHOY | 2 | 1 | UPGRADING | Batch 3 | 2044307.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302827 | Campao Oriental High School | GETAFE | 2 | 1 | UPGRADING |  | 1296500.39 | 1161015.54 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | QUICKSILVER CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302808 | Aguining National High School | PRES. CARLOS P. GARCIA (PITOGO) | 2 | 1 | UPGRADING |  | 1118740.94 | 1111579.64 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | MABB CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 500213 | Cabanugan IS | SAN ISIDRO | 2 | 1 | UPGRADING | Batch 3 | 1254384.31 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302897 | San Miguel Technical Vocational School | SAN MIGUEL | 2 | 1 | UPGRADING |  | 1657336.99 | 1647049.98 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | YS CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302895 | President Carlos P. Garcia Memorial High School | TALIBON | 2 | 1 | UPGRADING |  | 1223518.06 | 1081533.6 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | HUSAIN CONSTRUCTION AND SUPPLY CO. |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302910 | Tagum Sur NHS | TRINIDAD | 2 | 1 | UPGRADING |  | 1514170.88 | 1333198.44 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | HUSAIN CONSTRUCTION AND SUPPLY CO. |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 312351 | Cagting High School | UBAY | 2 | 1 | UPGRADING | Batch 3 | 772287.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 500215 | Tubog IS | UBAY | 2 | 1 | UPGRADING | Batch 3 | 1395894.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Bohol | 302852 | Garcia-Hernandez HS | GARCIA HERNANDEZ | 3 | 1 | UPGRADING |  | 1679323.91 | 1668875.84 | COMPLETED | 1 |  |  |  |  | 2018-10-31 | 2018-11-07 | 2018-11-20 | 2018-12-19 |  | MABB CONSTRUCTION |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Carcar City | 303127 | Gelacio C. Babao, Sr. MNHS | CITY OF CARCAR | 1 | 1 | UPGRADING |  | 1864201.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Carcar City | 303072 | Perrelos NHS | CITY OF CARCAR | 1 | 1 | UPGRADING |  | 1998094.9 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303042 | Lipata NHS | MINGLANILLA | 1 | 1 | UPGRADING | Batch 3 | 1538720.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 312457 | Manatad National High School | SIBONGA | 1 | 1 | UPGRADING | Batch 3 | 893827.04 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303067 | Teodoro dela Vega Memorial National High School | SIBONGA | 1 | 1 | UPGRADING | Batch 3 | 741211.29 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302951 | Bulak NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 1334760.2 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302941 | Dumanjug NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 1804027.61 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302952 | Tubod Dugoan NHS | DUMANJUG | 2 | 1 | UPGRADING |  | 985206.8 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302924 | Bakhawan National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 1772322.18 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302995 | Daanbantayan National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 2050960.55 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303053 | Maya National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 665408.64 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302996 | Sir Knight Luis P. Cañete Sr. NHS | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 1109878.51 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302965 | Tominjao National High School | DAANBANTAYAN | 4 | 1 | UPGRADING |  | 3003822.81 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303026 | Curva National High School | MEDELLIN | 4 | 1 | UPGRADING |  | 1076389.77 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303024 | Kawit NHS | MEDELLIN | 4 | 1 | UPGRADING |  | 941659.28 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303001 | Dapdap NHS, San Remigio | SAN REMIGIO | 4 | 1 | UPGRADING |  | 684764.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303021 | Jose R. Martinez Memorial National High School | SAN REMIGIO | 4 | 1 | UPGRADING |  | 725929.14 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 500920 | Kinawahan Integrated School | SAN REMIGIO | 4 | 1 | UPGRADING |  | 710628.06 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119669 | San Remigio Central ES | SAN REMIGIO | 4 | 1 | UPGRADING |  | 1561178.06 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 500665 | Tambongon IS | SAN REMIGIO | 4 | 1 | UPGRADING |  | 1073551.43 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119141 | Borbon Central ES | BORBON | 5 | 1 | UPGRADING | Batch 3 | 1520194.22 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303108 | Doña Milagros MNHS | BORBON | 5 | 1 | UPGRADING |  | 1060183.8 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119187 | Carmen Central ES | CARMEN | 5 | 1 | UPGRADING | Batch 3 | 1871896.59 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302978 | Catmon NHS | CATMON | 5 | 1 | UPGRADING |  | 1394827.68 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119226 | Compostela Central ES | COMPOSTELA | 5 | 1 | UPGRADING | Batch 3 | 1855667.47 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303063 | Compostela National High School(Day Class) | COMPOSTELA | 5 | 1 | UPGRADING |  | 2750363.05 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 312406 | Compostela Science & Technology High School | COMPOSTELA | 5 | 1 | UPGRADING |  | 830428.32 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303092 | Liloan NHS | LILOAN | 5 | 1 | UPGRADING |  | 1973022.81 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303109 | Liki NHS | SOGOD | 5 | 1 | UPGRADING | Batch 3 | 1298572.1 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303110 | Mohon NHS | SOGOD | 5 | 1 | UPGRADING | Batch 3 | 1271670.56 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119240 | Garing ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1040435.13 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119241 | Jugan ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 2156222.53 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302990 | Jugan NHS | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1004489.83 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 119244 | Nangka ES | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 842559.08 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 302991 | Pulpogan NHS | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1351102.74 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu | 303114 | Tayud National High School | CONSOLACION | 6 | 1 | UPGRADING | Batch 3 | 1336948.75 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500669 | Adlaon IS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 704596.94 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500043 | Agsungot IS | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 761992.88 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 312503 | Banilad Night HS | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1081846.59 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303131 | BINALIW NATIONAL HIGH SCHOOL | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 436612.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500044 | Mabini Integrated School | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 1362393.54 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303160 | Pit-os National High School | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1676992.77 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303165 | Vicente Cosido NHS (Cambinocot NHS) | CEBU CITY (Capital) | 1 | 1 | UPGRADING | Batch 3 | 540255.69 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303150 | Don Sergio Osmeña, Sr. Memorial HS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1486432.37 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500224 | Dr. Emilio Osmeña IS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 602168.23 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303146 | Mambaling NHS (Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1031692.14 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303162 | OPRRA NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1631492.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500226 | Pamutan Integrated School | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 599065.32 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303161 | Ramon Duterte Memorial NHS (Day & Night) | CEBU CITY (Capital) | 2 | 1 | UPGRADING |  | 1301297.22 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 303163 | Sinsin NHS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 519287.03 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Cebu City | 500670 | Toong IS | CEBU CITY (Capital) | 2 | 1 | UPGRADING | Batch 3 | 479897.4 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 325301 | Alpaco National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 976338.5 | 971405.34 | COMPLETED | 1 | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 303002 | Don Emilio Canonigo Memorial National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 900921.84 | 896366.92 | COMPLETED | 1 | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 303065 | Naga National High School | CITY OF NAGA | 1 | 1 | UPGRADING |  | 4383858.3 | 3808193.58 | COMPLETED | 1 | 2019-10-31 | 2019-10-31 | cityofnaga 2018-0002 | - | 2018-11-07 | 2018-11-13 | 2018-11-26 | 2018-12-19 | 2019-07-31 | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 500218 | Naga Special Education Center Elementary | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 516631.46 | 513977.39 | COMPLETED | 1 | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | City of Naga, Cebu | 325303 | Tinaan National High School | CITY OF NAGA | 1 | 1 | UPGRADING | Batch 3 | 506001.94 | 503421.45 | COMPLETED | 1 | 2019-12-31 | 2019-12-31 | cityofnaga 2019-0005 | - | 2019-08-07 | 2019-08-15 | 2019-08-28 | 2019-09-02 | 2019-10-22 | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Danao City | 302959 | Elpidio H. Perez Memorial Technical-Vocational High School | DANAO CITY | 5 | 1 | UPGRADING | Batch 3 | 2208910.57 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Danao City | 302956 | Estefa O. Monte Memo. National High School | DANAO CITY | 5 | 1 | UPGRADING |  | 2143925.8 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Danao City | 322003 | Ramon M. Durano Sr. Foundation - Science and Technology Education Center | DANAO CITY | 5 | 1 | UPGRADING |  | 2126360.55 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Danao City | 303039 | Ramon M. Durano Sr. MNHS | DANAO CITY | 5 | 1 | UPGRADING | Batch 3 | 2213442.72 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 303172 | Babag National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING |  | 3693802.81 | 3391690.156 | COMPLETED | 1 |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 303178 | Mactan National High School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING |  | 3560873.36 | 3256413.0028 | COMPLETED | 1 |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | DBB INDUSTRIAL SERVICES |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Lapu-Lapu City | 119979 | Marigondon Elementary School | LAPU-LAPU CITY (OPON) | 6 | 1 | UPGRADING | Batch 3 | 3178120.9 |  | COMPLETED | 1 |  |  |  |  | 2018-11-01 | 2018-11-14 | 2018-11-26 | 2018-12-06 |  | GOLDEN HAMMER CONST. AND SUPPLY |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Mandaue City | 119994 | Cesar M. Cabahug ES (Looc) | MANDAUE CITY | 6 | 1 | UPGRADING | Batch 3 | 1454413.14 | 1660967.69 | COMPLETED | 1 |  |  | 19-005 | 2019-005 | 2018-10-30 | 2018-11-09 | 2018-11-22 | 2018-12-03 |  | DBB Industrial Service |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303203 | Paknaan NHS | MANDAUE CITY | 6 | 1 | UPGRADING |  | 1703057.37 |  | COMPLETED | 1 |  |  | 19-009 |  | 2019-07-11 | 2019-07-18 | 2019-08-07 | 2019-08-09 |  | DBB Industrial Service |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303202 | Subangdaku Tech-Voc HS (Mandaue City CNHS - Subangdaku NHS Ext.) | MANDAUE CITY | 6 | 1 | UPGRADING | Batch 3 | 822903.96 | 1093151.38 | COMPLETED | 1 |  |  | 19-005 | 2019-005 | 2018-10-30 | 2018-11-09 | 2018-11-22 | 2018-12-03 |  | DBB Industrial Service |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Mandaue City | 303204 | Tipolo NHS | MANDAUE CITY | 6 | 1 | UPGRADING |  | 1098728.74 |  | COMPLETED | 1 |  |  | 19-008 |  | 2019-07-11 | 2019-07-18 | 2019-08-07 | 2019-08-09 |  | DBB Industrial Service |  |  | UPGRADING
ELECTRIFICATION 2019 | Region VII | Tagbilaran City | 118708 | Dao Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | UPGRADING | Batch 2 | 1913651.14 | 1652962.32 | COMPLETED | 1 | January 27, 2020 | January 9, 2020 |  |  |  |  | September 1, 2019 |  |  | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Talisay City | 119785 | Borromeo Brothers Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 574834.53 | 723962.8553 | COMPLETED | 1 |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | Region VII | Talisay City | 119788 | Maghaway Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 574200.11 | 570699.0793 | COMPLETED | 1 |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Talisay City | 119790 | San Roque Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 3 | 574200.11 | 569431.98 | COMPLETED | 1 |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Talisay City | 119791 | Talisay City Central Elementary School | CITY OF TALISAY | 1 | 1 | UPGRADING | Batch 1 | 729760.29 | 569592.2953 | COMPLETED | 1 |  |  |  |  | 2019-03-05 | 2019-03-12 | 2019-03-25 | 2019-04-15 | 2019-08-23 | QCC Construction and Supply |  | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303307 | AWIHAO NATIONAL HIGH SCHOOL | TOLEDO CITY | 3 | 1 | UPGRADING |  | 1442889.59 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303310 | Don Andres Soriano NHS | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 798288.1 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303311 | General Climaco NHS | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 1601790.21 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303318 | LURAY II NATIONAL HIGH SCHOOL (DAY & NIGHT)) | TOLEDO CITY | 3 | 1 | UPGRADING |  | 910940.96 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303312 | Magdugo National High School | TOLEDO CITY | 3 | 1 | UPGRADING | Batch 3 | 1068777.06 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303313 | Matab-ang NHS | TOLEDO CITY | 3 | 1 | UPGRADING |  | 1578804.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | Region VII | Toledo City | 303316 | Toledo National Vocational School | TOLEDO CITY | 3 | 1 | UPGRADING |  | 854559.93 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302900 | San Roque National High School | ALBURQUERQUE | 1 | 1 |  |  | 3167392.32 | 2491290.6 | TERMINATED | 0.25 |  |  | ELEC2020-RVII-BOHOL-005 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | TERMINATED |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302811 | Baclayon National High School | BACLAYON | 1 | 1 |  |  | 2466194.59 | 1964481.18 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-001 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302838 | Cong. Pablo Malasarte NHS | BALILIHAN | 1 | 1 |  |  | 2843579.25 | 2266156.83 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-003 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302856 | Hanopol NHS | BALILIHAN | 1 | 1 |  |  | 2843093.18 | 2257691.98 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-004 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302883 | Calape National High School | CALAPE | 1 | 1 |  |  | 2835435.15 | 2257691.98 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-002 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | Scheduled for tapping main line |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 312304 | Dauis National High School | DAUIS | 1 | 1 |  |  | 2500340.23 |  | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-006 | [7 empty] | ONGOING NEGOTIATION WITH THE SERVICE PROVIDER |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302896 | SIKATUNA NATIONAL AGRICULTURAL HIGH SCHOOL | TALIBON | 2 | 1 |  |  | 2941545.98 | 2342694.72 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-010 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302892 | Inabanga HS- Nabuad | INABANGA | 2 | 1 |  |  | 3275154.24 | 2591610.27 | TERMINATED | 0.25 |  |  | ELEC2020-RVII-BOHOL-009 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | TERMINATED on july 12, 2022 |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302829 | Candabong National High School | ANDA | 3 | 1 |  |  | 2423626.17 | 1848253.65 | TERMINATED | 0.9 |  |  | ELEC2020-RVII-BOHOL-019 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | MABB | Recommended for termination |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 302864 | La Union NHS | CANDIJAY | 3 | 1 |  |  | 2871885.8 | 2288311.28 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-023 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Bohol | 312311 | Mayor Pablo O. Lim MHS | VALENCIA | 3 | 1 |  |  | 2863499.44 | 2282871.03 | COMPLETED | 1 |  |  | ELEC2020-RVII-BOHOL-025 |  | 2019-12-03 | 2019-12-09 | 2019-12-23 | 2020-03-02 |  | GOLDENTECH | transformers on calibration with the service provider and for tapping |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 302917 | Alcoy National High School | ALCOY | 2 | 1 | UPGRADING |  | 1589621.19 | 1426884.26 | COMPLETED | 1 | 2021-02-25 | 2020-12-10 | Elec2020-RVII-CEBU-008 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-04 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services | ONGOING NEGOTIATION WITH THE SERVICE PROVIDER | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 302921 | Badian NHS | BADIAN | 2 | 1 | UPGRADING |  | 2927126.25 | 2471043.22 | COMPLETED | 1 |  |  | Elec2020-RVII-CEBU-016 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-05 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | JY BONTILAO |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 302997 | Dalaguete National High School | DALAGUETE | 2 | 1 | UPGRADING |  | 2174862.7 | 1638877.59 | COMPLETED | 1 | 2021-02-25 | 2020-12-10 | Elec2020-RVII-CEBU-006 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-04 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 303098 | Argao National High School | Santander | 2 | 1 | UPGRADING |  | 1389209.52 |  | COMPLETED | 1 |  |  | Elec2020-RVII-CEBU-020 | [8 empty] | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 312409 | Patao NHS | Bantayan | 4 | 1 | UPGRADING |  | 1617091.23 | 1305979.12 | COMPLETED | 1 | 2021-03-07 | 2020-12-16 | Elec2020-RVII-CEBU-022 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-03 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 303094 | Santa Fe NHS | Santa Fe | 4 | 1 | UPGRADING |  | 1260998.3 | 1021501.56 | COMPLETED | 1 | 2021-03-07 | 2020-12-16 | Elec2020-RVII-CEBU-023 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-03 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 303091 | Arcelo MNHS | LILOAN | 5 | 1 | UPGRADING |  | 1037093.99 | 899518.34 | COMPLETED | 1 | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-018 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 500423 | Calero IS | LILOAN | 5 | 1 | UPGRADING |  | 1198633.89 | 1196633 | COMPLETED | 1 | 2021-02-28 |  | Elec2020-RVII-CEBU-003 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU | 2020-11-29 | 2020-11-26 | 2020-12-09 | 2020-12-14 | 2020-12-22 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 119414 | Liloan CS | LILOAN | 5 | 1 | UPGRADING |  | 1076432.22 | 902702.9 | COMPLETED | 1 | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-002 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 119423 | Yati ES | LILOAN | 5 | 1 | UPGRADING |  | 967688.14 | 732367.05 | COMPLETED | 1 | 2021-01-06 | 2020-12-11 | Elec2020-RVII-CEBU-001 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-02 | 2020-01-29 | 2020-02-05 | 2020-02-18 | 2020-05-04 | 2020-09-30 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu | 302955 | Cordova NHS | CORDOVA | 6 | 1 | UPGRADING |  | 970303.71 | 965750 | COMPLETED | 1 | 2021-04-12 |  | Elec2020-RVII-CEBU-017 | CY 2020 BEFF ELECTRIFICATION-R7-CEBU-RFQ | - | - | - | - | 2021-01-04 | DBB Industrial Services |  | Y | UPGRADING
ELECTRIFICATION 2020 | Region VII | Cebu City | 119930 | Regino Mercado ES | CEBU CITY (Capital) | 1 | 1 | UPGRADING |  | 1558067.85 |  | COMPLETED | 1 |  |  | Elec-2020-RVII-CEBUCITY-004 | [8 empty] | N | UPGRADING
ELECTRIFICATION 2020 | Region VII | Lapu-Lapu City | 303180 | Marigondon National High School | LAPU-LAPU CITY (OPON) | 6 | 1 |  |  | 5969870.35 |  | COMPLETED | 1 |  |  | Elec2020-RVII-LAPULAPU-003 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Mandaue City | 120004 | Banilad ES | MANDAUE CITY | 6 | 1 |  |  | 1697087.76 |  | COMPLETED | 1 |  |  | ELEC2020-RVII-MANDAUE-001 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Mandaue City | 312810 | Tingub High School | MANDAUE CITY | 6 | 1 |  |  | 2447039.44 | 2046593.18 | COMPLETED | 1 | 2021-10-16 |  | ELEC2020-RVII-MANDAUE-002 | 2021-06-043 | 21-Apr-21 | 28-Apr-21 | 10-May-21 | 03-Jun-21 | 2021-06-18 | CCO Eng'g. Const. & Supply |  |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 119797 | Candulawan ES | Talisay City | 1 | 1 |  |  | 551154.79 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 130922 | Dumlog ES | Talisay City | 1 | 1 |  |  | 513643.43 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 119798 | Iba ES | Talisay City | 1 | 1 |  |  | 487735.26 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 119800 | Lagtang ES | Talisay City | 1 | 1 |  |  | 549981.44 | 548254.3433 | COMPLETED | 1 | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 233501 | Linao ES | Talisay City | 1 | 1 |  |  | 536318.54 | 534342.6226 | COMPLETED | 1 | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 119802 | San Isidro ES | Talisay City | 1 | 1 |  |  | 534308.78 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 322205 | Talisay City Science HS | Talisay City | 1 | 1 |  |  | 504372.41 | 502338.883 | COMPLETED | 1 | 2020-12-26 |  |  |  | 2020-03-04 |  |  | 2020-03-10 | 2020-09-28 | Quirante Construdtion |  |  | UPGRADING
ELECTRIFICATION 2020 | Region VII | Talisay City | 312402 | Tangke NHS | Talisay City | 1 | 1 |  |  | 496419.6 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Toledo City | 303310 | DAS NHS | Toledo | 3 | 1 |  |  | 1499034.41 |  | COMPLETED | 1 |  |  | Elec2020RVII-Toledo City | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Toledo City | 303311 | Gen. Climaco NHS | Toledo | 3 | 1 |  |  | 3128056.8 |  | COMPLETED | 1 |  |  | Elec2020 RVII-Toledo City | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | Region VII | Toledo City | 303312 | Magdugo NHS | Toledo | 3 | 1 |  |  | 1697679.38 |  | COMPLETED | 1 |  |  | Elec2020-Toledo City | [9 empty] | UPGRADING
ELECTRIFICATION 2023 | Region VII | Bohol | 302903 | Sevilla National High School | SEVILLA | 3rd | 1 | Upgrading of Electrical System | 1 | 4000000 | 3400799.37 | COMPLETED | 1 | 2024-04-14 | 2024-03-22 | [8 empty] | Has just inspected on Nov 22, 2023 |  | UPGRADING
ELECTRIFICATION 2023 | Region VII | Cebu | 500650 | Pasol-Pugalo IS | ALCOY | 2nd | 1 | Modernization of Electrical System On-grid Schools | 1 | 1353368.18 | 1348287.91 | COMPLETED | 1 | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-01 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS |  | UPGRADING
ELECTRIFICATION 2023 | Region VII | Cebu | 303090 | Samboan National High School | SAMBOAN | 2nd | 1 | Modernization of Electrical System On-grid Schools | 1 | 1480733.8 | 1476640.36 | COMPLETED | 1 | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-02 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS |  | UPGRADING
ELECTRIFICATION 2023 | Region VII | Cebu | 302922 | Alcantara NHS | ALCANTARA | 7th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1619602.19 | 1617873.04 | COMPLETED | 1 | 2023-11-01 |  | CY 2023 electrification-deped-r7-cebu | CY 2023 electrification-deped-r7-cebu-03 | JUNE 13, 2023 | JUNE 20,2023 | JULY 3, 2023 | JULY 10, 2023 | 2023-07-27 | DBB INDUSTRIAL SERVICES | PERMITS ON-PROCESS |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Bogo City | 119118 | Bogo II Central ES | CITY OF BOGO | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2403087.48 | 2393306.37 | COMPLETED | 1 | 2024-10-14 |  | ITB202310-03 | ITB202310-03 | 2023-10-27 | 2023-11-06 | 2023-11-20 | 2023-11-23 | 2024-07-09 | CCO Engineering Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Bohol | 312321 | San Miguel-Puertos HS | DAGOHOY | 2nd | 1 | Upgrading of Electrical System | 1 | 3005471.66 | 2000000 | not yet started | 0 | [5 empty] | 2024-06-06 | 2024-06-19 |  |  |  | received saro September 19, 2024. For preparation of contract. |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Bohol | 302865 | Candijay National High School | CANDIJAY | 3rd | 1 | Upgrading of Electrical System | 1 | 5841150.25 | 4000000 | not yet started | 0 | [5 empty] | 2024-06-06 | 2024-06-19 |  |  |  | received saro September 19, 2024. For preparation of contract. |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Carcar City | 119158 | CARCAR CENTRAL ELEMENTARY SCHOOL | Carcar City | 2nd | 1 | Upgrading of Electrical System | 1 | 3018081.07 | 2594330.24 | COMPLETED | 1 | 2024-09-26 |  | Electrification24-01Carcar | BEFF 2024-Electrification Program-Upgrading of Electrical System (Overhead System) at Carcar Central Elementary School | 2024-03-13 | 2024-03-19 | 2024-04-03 | 2024-04-17 | 2024-06-21 | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu | 312401 | BALUD NATIONAL HIGH SCHOOL | SAN FERNANDO | 1st | 1 | Modernization of Electrical System On-grid Schools | 1 | 1588869.78 | 1578017.31 | COMPLETED | 1 |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-01 | CY 2024 BEFF Electrification-DepED-R7-Cebu-01 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2nd | 1 | Upgrading Electrical System On Grid Schools | 1 | 1405321.08 | 1401580.92 | COMPLETED | 1 |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-02 | CY 2024 BEFF Electrification-DepED-R7-Cebu-02 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu | 119048 | Bantayan Central ES | BANTAYAN | 4th | 1 | Upgrading Electrical System On Grid Schools | 1 | 2297427.36 | 2272717.96 | COMPLETED | 1 |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-03 | CY 2024 BEFF Electrification-DepED-R7-Cebu-03 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu | 119421 | Tayud Elementary School | LILOAN | 5th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1066650.16 | 916643.04 | COMPLETED | 1 |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-04 | CY 2024 BEFF Electrification-DepED-R7-Cebu-04 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu | 118866 | Alcantara Central ES | ALCANTARA | 7th | 1 | Modernization of Electrical System On-grid Schools | 1 | 1313160.75 | 1307416.92 | COMPLETED | 1 |  |  | CY 2024 BEFF Electrification-DepED-R7-Cebu-05 | CY 2024 BEFF Electrification-DepED-R7-Cebu-05 | 2024-06-11 | 2024-06-18 | 2024-07-02 | 2024-07-11 |  | DBB INDUSTRIAL SERVICES |  |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu City | 119923 | Paril ES | CEBU CITY (Capital) | 1st | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2250000 | 1949622.05 | COMPLETED | 1 | Nov. 11, 2024 |  | ELECT 2024 - REGION VII - CEBU CITY - 001 | DEPED CCD 2024 - 02 | Nov. 24, 2023 | Dec. 4, 2023 | Dec. 15, 2023 | Dec. 29, 2023 | August 7, 2024 | CCO ENGINEERING CONSTRUCTION AND SUPPLY | On-Going |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Cebu City | 119908 | Mangabon ES | CEBU CITY (Capital) | 2nd | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2100000 | 1800639.08 | COMPLETED | 1 | Nov. 11, 2024 |  | ELECT 2024 - REGION VII - CEBU CITY - 003 | DEPED CCD 2024 - 03 | Nov. 24, 2023 | Dec. 4, 2023 | Dec. 15, 2023 | Dec. 29, 2023 | August 7, 2024 | CCO ENGINEERING CONSTRUCTION AND SUPPLY | On-Going |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | City of Naga, Cebu | 303035 | Placido L. Senor National High School | CITY OF NAGA | 1st | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 1690172.56 | 1689762.64 | ONGOING | 0.4 | 2024-09-28 |  | cityofnaga 2023-003 | 45463 | 2023-11-21 | 2023-11-28 | 2023-12-11 | 2023-12-19 | 2024-06-24 | DBB INDUSTRIAL SERVICES |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region VII | Lapu-Lapu City | 119953 | Cawhagan Elementary School | LAPU-LAPU CITY (OPON) | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 966934.52 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2024 | Region VII | Mandaue City | 303194 | Cabancalan NHS | MANDAUE CITY | 6th | 1 | Electrification of Un-Energized Schools and Modernization of Electrical Systems of On-Grid Schools | 1 | 2142278.63 | 1757499.69 | COMPLETED | 1 | 2024-08-03 | 2024-08-09 | 2023ELEC01 | 2024-01 | 2023-12-11 | 2023-12-18 | 2024-01-02 | 2024-01-10 | 2024-05-20 | DBB Industrial Services |  |  | ENERGIZATION
ELECTRIFICATION 2024 | Region VII | Tagbilaran City | 118711 | Mansasa Elementary School | TAGBILARAN CITY (Capital) | 1st | 1 | Upgrading/ Modernization of Electrical System | 1 | 5946563.06 | 4346783.45 | COMPLETED | 1 | 2024-10-02 | 2024-10-16 | 2023-001-Services | 2023-001-Services | 2023-11-08 | 2023-11-17 | 2023-11-29 | 2023-12-04 | 2024-05-28 | CCO Engineering Construction and Supply | With VO No. 1 |  | UPGRADING
ELECTRIFICATION 2024 | Region VII | Talisay City | 233502 | Lawaan III Elementary School | CITY OF TALISAY | 1st | 1 | Upgrading of Electrical System | 1 | 1915741.65 | 1909888 | COMPLETED | 1 | 2024-09-25 | 2024-09-25 | 2024-002 | 45469 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-06-27 | Quirante Construction Corporation | On going |  | UPGRADING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%