## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2019 | Region VIII | Ormoc City | 124203 | Cogon Central School | ORMOC CITY | 4 | 1 | 4 | 1STY4CL | 6844288.3 | 1 | 5607979.9956 | Completed | 1 | January 18, 2020 | January 18, 2020 | QRF-2019-RP-B0 | QRF-2019-RP-B1 | May 15, 2019 | May 23, 2019 | June 10, 2019 | August 9, 2019 | August 14, 2019 | J. Custorio Construction
QRF 2020 | Region VIII | Biliran | 120777 | CANILLA ES | BILIRAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1323658.4 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Biliran | 120814 | USON ES | CAIBIRAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1798169.42 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Biliran | 120815 | Acaban Elementary School | CULABA | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1057517.75 | 1 |  | Completed | 1 | [10 empty] | re-aligned to calumpang cs, naval biliran 100% completed (repair of 1 unit 1STY 2CL and 1 unit 1STY 1CL) from acaban es slope protection
QRF 2020 | Region VIII | Biliran | 303326 | KAWAYAN NHS | KAWAYAN | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 5657769.82 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Biliran | 120843 | UNGALE I ES | KAWAYAN | 0 | 1 | 12 | REPAIR OF CLASSROOMS | 4066702.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Biliran | 120868 | CALUMPANGES | NAVAL | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1154531.45 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Biliran | 120859 | LARRAZABAL ES | NAVAL | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2301989.2 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Borongan City | 122393 | Banuyo ES | BORONGAN CITY(Capital) | 0 | 1 | 8 | REPAIR OF CLASSROOMS | 2698984.53 | 1 | 2697984.88 | Completed | 1
QRF 2020 | Region VIII | Borongan City | 122356 | Bato ES | BORONGAN CITY(Capital) | 0 | 1 | 15 | REPAIR OF CLASSROOMS | 4641631.5 | 1 | 4630626.7 | Completed | 1
QRF 2020 | Region VIII | Borongan City | 303500 | ESNCHS | BORONGAN CITY(Capital) | 0 | 1 | 20 | REPAIR OF CLASSROOMS | 7012642.3 | 1 | 7007776.7 | Completed | 1
QRF 2020 | Region VIII | Borongan City | 122403 | Lalawigan CES | BORONGAN CITY(Capital) | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2107991.37 | 1 | 2095000 | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124118 | Baay Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1436793.56 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124120 | Bantian Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 721753.77 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124081 | Cabicahan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 705939.96 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124131 | Cagmanipis Norte Elementary School | CALBAYOG CITY | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 3184345.08 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124130 | Cagmanipis Sur Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 682674.94 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 123989 | Calbayog Pilot Central School | CALBAYOG CITY | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3359829.67 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124008 | Carmen Elementary School | CALBAYOG CITY | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2110000.16 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124090 | Dinabongan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 721349.96 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124061 | Dinagan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 351051.41 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 500237 | Gadgaran Integrated School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 251034.03 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124012 | Giragaan Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 730038.53 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124016 | Himalandrog Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 330524.63 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124099 | Mag ubay Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1039080.53 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124137 | Malaga Central Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 704331.65 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 313811 | Malaga NHS-Peña Annex | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 687096.34 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 500748 | Malajog Integrated School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 323404.16 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124138 | Malayog Elementary School | CALBAYOG CITY | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1866042.41 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124125 | Malopalo Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 991009.88 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124126 | Manguinoo Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 720607.02 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124019 | Matobato Elementary School | CALBAYOG CITY | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 596122.63 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 123996 | Naga Elemenetary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1424000.85 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124041 | Navarro Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 381033.45 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 123998 | Obrero Elementary School | CALBAYOG CITY | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1695088.2 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 303646 | Oquendo National High School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 340001.91 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124106 | Panoypoy Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 321659.55 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124139 | Peña I Central Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1396476.91 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124072 | Pilar Elementary School | CALBAYOG CITY | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 3779115.22 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124001 | Rawis Elementary School | CALBAYOG CITY | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 1872283.94 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124074 | Roxas II Elementary School | CALBAYOG CITY | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1833623.2 | 1 |  | Completed | 1 | [10 empty] | 45% Accomplishment (affected by Covid-19 Pandemic) resume work
QRF 2020 | Region VIII | Calbayog City | 303650 | San Joaquin National HIgh School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 324464.24 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124048 | San Policarpo Central Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 974798.24 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124049 | Saputan Elementary School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1051815.33 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124075 | Sigo Elementary School | CALBAYOG CITY | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1871467.51 | 1 |  | Completed | 1 | [10 empty] | 45% Accomplishment (affected by Covid-19 Pandemic) resume work
QRF 2020 | Region VIII | Calbayog City | 500238 | Tabawan Integrated School | CALBAYOG CITY | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1074941.53 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124003 | Tapae Elementary School | CALBAYOG CITY | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 697589.97 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124115 | Tarabucan Elementary School | CALBAYOG CITY | 1 | 1 | 1 | REPAIR OF CLASSROOM | 380079.6 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124142 | Tinaplacan Elementary School | CALBAYOG CITY | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1406301.77 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Calbayog City | 124051 | Trinidad Central Elementary School | CALBAYOG CITY | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 3695919.22 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122325 | Arteche Central Elementary School | ARTECHE | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 6465046.61 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303495 | Balangkayan National High School | BALANGKAYAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 1390426.81 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122614 | Cantubi Elementary School | BALANGKAYAN | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1188892.32 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122618 | Guinpoliran Elementary School | BALANGKAYAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 821101.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122623 | Maramag Elementary School | BALANGKAYAN | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1501905.97 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122631 | Talisay Elementary School | BALANGKAYAN | 0 | 1 | 6 | REPAIR OF CLASSROOMS | 2614013.02 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303501 | Gen. MacArthur National Agricultural School | GENERAL MACARTHUR | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1183642.32 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122501 | Sta. Cruz Elementary School | GENERAL MACARTHUR | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 821101.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122505 | Vigan Elementary School | GENERAL MACARTHUR | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1165930.75 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122515 | President Roxas Elementary School | GIPORLOS | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1171201.46 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122555 | Baras Elementary School | GUIUAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 826351.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122524 | Guiuan East Central School | GUIUAN | 0 | 1 | 17 | REPAIR OF CLASSROOMS | 5191517.3 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303504 | Taytay Integrated School | GUIUAN | 0 | 1 | 10 | REPAIR OF CLASSROOMS | 2003527.78 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122480 | Canciledes Elementary School | HERNANI | 0 | 1 | 5 | REPAIR OF CLASSROOMS | 1537532.03 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122575 | Jipapad Central School | JIPAPAD | 0 | 1 | 14 | REPAIR OF CLASSROOMS | 6398216.2 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303510 | Jipapad National High School | JIPAPAD | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3292064.76 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122355 | TAGUITE ES | LAWAAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 815851.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122587 | Barobo Elementary School | LLORENTE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 808109.64 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122594 | Llorente Central Elementary School | LLORENTE | 0 | 1 | 18 | REPAIR OF CLASSROOMS | 5526925.69 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303513 | Llorente National High School | LLORENTE | 0 | 1 | 15 | REPAIR OF CLASSROOMS | 3976649.83 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122598 | Naubay Elementary School | LLORENTE | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1212843.94 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122604 | Tabok Elementary School | LLORENTE | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 803410.97 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 313514 | Maydolong National High School | MAYDOLONG | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 2463918.37 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122532 | Anuron Elementary School | MERCEDES | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1202953.7 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122544 | Mercedes Central School | MERCEDES | 0 | 1 | 7 | REPAIR OF CLASSROOMS | 3000004.73 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122550 | San Roque Primary School | MERCEDES | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1217992.29 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122678 | Cantinio Primary School | QUINAPONDAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 849378.95 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303521 | Quinapondan National High School | QUINAPONDAN | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 818609.64 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122718 | Matarinao Elementary School | SALCEDO | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1222290.14 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 313509 | Salcedo Vocational High School | SALCEDO | 0 | 1 | 34 | REPAIR OF CLASSROOMS | 2499885.58 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122719 | Sta. Cruz Primary School | SALCEDO | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1188892.32 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 313503 | Tagbacan National High School | SALCEDO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 864999.65 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 313507 | Nena National High School (Nena School of Arts and Trades) | SAN JULIAN | 0 | 1 | 16 | REPAIR OF CLASSROOMS | 6167023.6 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 303523 | Samar National Pilot Opportunity School Of Agriculture | SAN POLICARPO | 0 | 1 | 4 | REPAIR OF CLASSROOMS | 1737539.87 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122744 | Tabo Elementary School | SAN POLICARPO | 0 | 1 | 2 | REPAIR OF CLASSROOMS | 869878.32 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Eastern Samar | 122752 | San Isidro Elementary School | SULAT | 0 | 1 | 3 | REPAIR OF CLASSROOMS | 1212843.94 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 120963 | Binongtoan Central School | ALANGALANG | 1 | 1 | 2 | REPAIR OF CLASSROOMS | 525011.03 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 120969 | Hubang Elementary School | ALANGALANG | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1728546.61 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313341 | Mariano Salazar National High School | ALANGALANG | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 899987.18 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 120951 | Mariquita Cinco Memorial Elementary School | ALANGALANG | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1178550.18 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313335 | Palo National High School-Pawing Annex | PALO | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 1388194.73 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121762 | San Fernando Elementary School | PALO | 1 | 1 | 9 | REPAIR OF CLASSROOMS | 2744087.36 | 1 |  | COMPLETED | 1
QRF 2020 | Region VIII | Leyte | 303424 | San Joaquin National High School | PALO | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 604571.6 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 305523 | Sta. Fe Stand Alone Senior High School | SANTA FE | 1 | 1 | 20 | REPAIR OF CLASSROOMS | 1869087.94 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121954 | San Roque ES | TOLOSA | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 2322519.85 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121957 | Telegrafo Elementary School | TOLOSA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 667493.32 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte |  | Telegrafo Elementary School Annex | TOLOSA | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1963099.05 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121293 | Dagami North Central School | DAGAMI | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 700000 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 303432 | Sta. Mesa National High School | DAGAMI | 2 | 1 | 26 | REPAIR OF CLASSROOMS | 1832713.1 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 303369 | Dulag National High School | DULAG | 2 | 1 | 1 | REPAIR OF CLASSROOM | 493523.44 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313336 | Bienvenido Guillera Celebre National High School | JARO | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 804428.74 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 303371 | Granja-Kalinawan National High School | JARO | 2 | 1 | 28 | REPAIR OF CLASSROOMS | 1249347.5 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121620 | Liwayway Elementary School | MACARTHUR | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 948410.35 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121816 | Halaba Primary School | PASTRANA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 458685.15 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121820 | Lourdes Primary School | PASTRANA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 378464.8 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121821 | Macalpiay Elementary School | PASTRANA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 717883.04 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313330 | Manaybanay National High School | PASTRANA | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 735947.97 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121956 | Tanghas Elementary School | TOLOSA | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 811316.2 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121212 | Casiongan Elementary School | CALUBIAN | 3 | 1 | 5 | REPAIR OF CLASSROOMS | 1005286.5 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313317 | Felix Caneja Lafuente National High School | CALUBIAN | 3 | 1 | 13 | REPAIR OF CLASSROOMS | 1667039.85 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 313340 | Rafaelito Cabanas Martinez National High School | CALUBIAN | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 897969.14 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 303390 | Leyte National High School | LEYTE | 3 | 1 | 12 | REPAIR OF CLASSROOMS | 802071.72 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121885 | Don Bernardo Elementary School | TABANGO | 3 | 1 | 7 | REPAIR OF CLASSROOMS | 2415570.71 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 303416 | Pastor Salazar National High School | TABANGO | 3 | 1 | 8 | REPAIR OF CLASSROOMS | 1084464.66 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121555 | Tongonan Elementary School | KANANGA | 4 | 1 | 4 | REPAIR OF CLASSROOMS | 1195699.85 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 305522 | Matag-ob Stand Alone Senior High School | MATAG-OB | 4 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 2900000 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Leyte | 121808 | Tabunok Elementary School | PALOMPON | 4 | 1 | 2 | REPAIR OF CLASSROOMS | 941473.26 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122777 | Allen Central Elementary School | ALLEN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2219107.39 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122778 | Cabacungan ES | ALLEN | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 1688376.1 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122779 | Calarayan ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 421741.27 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122782 | Guin-Arawayan ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 296314.5 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122783 | Jubasan ES | ALLEN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1533908.06 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122784 | Kinaguitman ES | ALLEN | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 1873480.86 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122785 | Lagundi ES | ALLEN | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1679784.01 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122786 | Lipata ES | ALLEN | 1 | 1 | 1 | REPAIR OF CLASSROOM | 297649.59 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122788 | Pili ES | ALLEN | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1248177.71 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122844 | Baybay ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1754819.92 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122854 | Bocsol Es | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1238329.73 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122835 | Daganas ES | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1264299.48 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122839 | Guba Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 773392.82 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122869 | Hinatad ES | CATARMAN (Capital) | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1523186.96 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122871 | McKinley ES | CATARMAN (Capital) | 1 | 1 | 8 | REPAIR OF CLASSROOMS | 3354089.74 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122841 | New Rizal ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1994115.19 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122842 | Old Rizal ES | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 2093096.36 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122859 | Paticua Elementary School | CATARMAN (Capital) | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1828854.23 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122860 | Salvacion Elementary School | CATARMAN (Capital) | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 1259293.75 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122850 | Somoge ES | CATARMAN (Capital) | 1 | 1 | 6 | REPAIR OF CLASSROOMS | 2335859.79 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123058 | Barobaybay ES | LAVEZARES | 1 | 1 | 5 | REPAIR OF CLASSROOMS | 1405261.15 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123080 | Bayho ES | LOPE DE VEGA | 1 | 1 | 4 | REPAIR OF CLASSROOMS | 1269833.14 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123089 | Henaronagan ES | LOPE DE VEGA | 1 | 1 | 1 | REPAIR OF CLASSROOMS | 414137.13 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123096 | Osme¤a ES | LOPE DE VEGA | 1 | 1 | 3 | REPAIR OF CLASSROOMS | 209969.63 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122882 | Guibuangan ES | CATUBIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1020773.28 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122916 | Bangon Elementary school | GAMAY | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1840650.82 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122948 | Talisay Elementary School | LAOANG | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 1744732.01 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122997 | Lo-ok ES | LAPINIG | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 665260.39 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 122999 | May-igot ES | LAPINIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1212193.13 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123000 | Palanas elementary school | LAPINIG | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1202836.1 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Northern Samar | 123006 | Bulao ES | LAS NAVAS | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1729965.63 | 1 |  | Completed | 1
QRF 2020 | Region VIII | Ormoc City | 124214 | Liloan CS | Ormoc City | 4 | 1 | 3 | REPAIR OF CLASSROOMS | 1132238.19 | 1 | 1105733 | Completed | 1
QRF 2020 | Region VIII | Samar (Western Samar) | 123750 | Inaraguiao ES | STA. MARGARITA | 1 | 1 | 10 | REPAIR OF CLASSROOMS | 4310353.12 | 1 | 4256944.87 | Completed | 1 | [9 empty] | VHITS | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 303628 | Simeon Ocdol NHS | BASEY | 2 | 1 | 6 | REPAIR OF CLASSROOMS | 630232.36 | 1 | 624852.88 | Completed | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 303637 | Valerino C. Yancha MAS | Basey | 2 | 1 | 3 | REPAIR OF CLASSROOMS | 1073110.41 | 1 | 1055584.99 | Completed | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123363 | BULUAN ES | CALBIGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 911764.14 | 1 | 909613.27 | Completed | 1 | [9 empty] | GG | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123679 | PELAON ES | CALBIGA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 692955.19 | 1 | 690930.18 | Completed | 1 | [9 empty] | GG | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 313719 | Bagacay NHS | DARAM | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 2826478.62 | 1 | 2810915.74 | Completed | 1 | [9 empty] | MORI | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123470 | BAKHAW ES | DARAM | 2 | 1 | 1 | REPAIR OF CLASSROOM | 300756.93 | 1 | 295957.19 | Completed | 1 | [9 empty] | MORI | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 313709 | BAKHAW NHS | DARAM | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 952365.62 | 1 | 947336.71 | Completed | 1 | [9 empty] | GPUY | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 303601 | DARAM NHS | DARAM | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 918756.27 | 1 | 913734.37 | Completed | 1 | [9 empty] | GPUY | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123919 | LOKILOKON ES | PARANAS | 2 | 1 | 13 | REPAIR OF CLASSROOMS | 4873038.89 | 1 | 4870535.54 | Completed | 1 | [9 empty] | G BUILDERS | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123931 | TULA ES | PARANAS | 2 | 1 | 1 | REPAIR OF CLASSROOM | 442423 | 1 | 439914.46 | Completed | 1 | [9 empty] | G BUILDERS | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123668 | LAYGAYON ES | PINABACDAO | 2 | 1 | 1 | REPAIR OF CLASSROOM | 268194.84 | 1 | 264681.12 | Completed | 1 | [9 empty] | REVCON | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 313723 | Parasanon NHS | PINABACDAO | 2 | 1 | 9 | REPAIR OF CLASSROOMS | 2992512.26 | 1 | 2988110.24 | COMPLETED | 1 | [9 empty] | REVCON | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123715 | CANMAHAGAY ES | SAN SEBASTIAN | 2 | 1 | 5 | REPAIR OF CLASSROOMS | 1852565.73 | 1 | 1829569.07 | Completed | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 313716 | Anibongon IS | SANTA RITA | 2 | 1 | 1 | REPAIR OF CLASSROOM | 400384.67 | 1 | 398187.45 | Completed | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123777 | Bugho ES | SANTA RITA | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 604135.15 | 1 | 600970.01 | COMPLETED | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 303636 | TOMINAMOS IS | STA. RITA | 2 | 1 | 8 | REPAIR OF CLASSROOMS | 806808.3 | 1 | 802189.44 | Completed | 1 | [9 empty] | JFR | for award
QRF 2020 | Region VIII | Samar (Western Samar) | 123892 | Ulayan ES | VILLAREAL | 2 | 1 | 2 | REPAIR OF CLASSROOMS | 730541.72 | 1 | 727268.02 | Completed | 1 | [9 empty] | REVCON | for award
QRF 2020 | Region VIII | Southern Leyte | 192024 | Tuba-on Elementary School | SILAGO | 0 | 1 |  | CONSTRUCTION OF SLOPE PROTECTION | 1727522.54 | 1 | 1705367.27 | Completed | 1 |  |  | QRF-CY2020- Slope Protection | QRF-CY2020- Slope Protection | 2020-06-03 | 2020-06-15 | 2020-06-29 | 2020-07-27 | 2020-08-11 | VHITS D.G. BUILDERS & ENTERPRISES
QRF 2020 | Region VIII | Tacloban City | 124255 | Cabalawan ES | TACLOBAN CITY (Capital) | 1 | 1 | 11 | REPAIR OF CLASSROOMS | 1310206.11 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | JFR CONSTRUCTION
QRF 2020 | Region VIII | Tacloban City | 124235 | Lucio Vivero ES | TACLOBAN CITY (Capital) | 1 | 1 | 14 | REPAIR OF CLASSROOMS | 1532003.85 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | GPUY CONSTRUCTION AND SUPPLY
QRF 2020 | Region VIII | Tacloban City | 314004 | Northern Tacloban City National High School | TACLOBAN CITY (Capital) | 1 | 1 | 63 | REPAIR OF CLASSROOMS | 5302173.26 | 1 |  | Completed | 1 | 2020-10-31 | 2020-10-31 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | RD COBACHA CONSTRUCTION
QRF 2020 | Region VIII | Tacloban City | 303666 | Sagkahan National High School | TACLOBAN CITY (Capital) | 1 | 1 | 40 | REPAIR OF CLASSROOMS | 1853041.92 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | LRD CONSTRUCTION AND SUPPLY
QRF 2020 | Region VIII | Tacloban City | 124248 | Salvacion Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 7 | REPAIR OF CLASSROOMS | 655281.39 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | VHITS D.G. BUILDERS & ENTERPRISES
QRF 2020 | Region VIII | Tacloban City | 124259 | Sta. Elena ES | TACLOBAN CITY (Capital) | 1 | 1 | 12 | REPAIR OF CLASSROOMS | 1762162.47 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | GPUY CONSTRUCTION AND SUPPLY
QRF 2020 | Region VIII | Tacloban City | 303669 | Tacloban National Agricultural School | TACLOBAN CITY (Capital) | 1 | 1 | 30 | REPAIR OF CLASSROOMS | 991335.76 | 1 |  | Completed | 1 | 2020-09-16 | 2020-09-16 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | VHITS D.G. BUILDERS & ENTERPRISES
QRF 2020 | Region VIII | Tacloban City | 124242 | Tagpuro Elementary School | TACLOBAN CITY (Capital) | 1 | 1 | 15 | REPAIR OF CLASSROOMS | 2097695.31 | 1 |  | Completed | 1 | 2020-10-01 | 2020-10-01 |  |  | 2020-06-03 | 2020-06-10 | 2020-06-22 | 2020-06-26 | 2020-07-03 | 4 ANGLE CONSTRUCTION
QRF 2022 | Region VIII | Eastern Samar | 122606 | Balangkayan Central Elementary School | BALANGKAYAN | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2595388.38 | 1 |  | Completed | 1 | 2023-10-05
QRF 2022 | Region VIII | Eastern Samar | 303502 | Giporlos National Trade School | GIPORLOS | 0 | 1 | 24 | REPAIR/ REHABILITATION | 7737161.07 | 1 |  | completed | 1 | 2023-08-06
QRF 2022 | Region VIII | Eastern Samar | 122485 | Hernani Central Elementary School | HERNANI | 0 | 1 | 6 | REPAIR/ REHABILITATION | 2592763.38 | 1 |  | Completed | 1 | 2023-09-29
QRF 2022 | Region VIII | Eastern Samar | 303512 | Lawaan National School of Craftsmanship and Home Industries | LAWAAN | 0 | 1 | 32 | REPAIR/ REHABILITATION | 6867954.14 | 1 |  | completed | 1 | 2023-11-28
QRF 2022 | Region VIII | Leyte | 303350 | Bontoc Senior High School | HINDANG | 5 | 1 | 6 | REPAIR/ REHABILITATION | 779227.1 | 1 | 768434.28 | Completed | 1 | 2023-10-29 |  |  |  | 2022-09-12
QRF 2022 | Region VIII | Maasin City | 122153 | BOGO MULTIGRADE SCHOOL | CITY OF MAASIN (Capital) | 1 | 1 | 2 | REPAIR/ REHABILITATION | 1404999.36 | 1 | 1382613.1 | COMPLETED | 1 | 2023-11-10 | 2022-09-26 | QRF-22-05-Lot 4 | QRF-22-05-Lot 4 | 2022-05-05
QRF 2022 | Region VIII | Maasin City | 122125 | Cambooc MGS | CITY OF MAASIN (Capital) | 1 | 1 | 5 | REPAIR/ REHABILITATION | 3253353.731 | 1 | 3089138.14 | COMPLETED | 1 | 2023-11-10 | 2023-01-26 | QRF-22-05-Lot 3 | QRF-22-05-Lot 3 | 2022-05-05
QRF 2022 | Region VIII | Maasin City | 122135 | Maasin Central School | CITY OF MAASIN (Capital) | 1 | 1 | 28 | REPAIR/ REHABILITATION | 14596082.8742 | 1 | 14455745.63 | completed | 1 | 2023-10-05 | 2023-07-12 | QRF-22-08-Lot 1 | QRF-22-08-Lot 1 | 2022-08-12
QRF 2022 | Region VIII | Maasin City | 122174 | San Rafael ES | CITY OF MAASIN (Capital) | 1 | 1 | 9 | REPAIR/ REHABILITATION | 3767359.1745 | 1 | 2899480.95 | COMPLETED | 1 | 2023-08-16 | 2023-01-03 | QRF-22-05-Lot 2 | QRF-22-05-Lot 2 | 2022-05-05
QRF 2022 | Region VIII | Ormoc City | 124194 | Alegria Batuan ES | ORMOC CITY | 4 | 1 | 3 | REPAIR/ REHABILITATION | 2184122.06 | 1 | 2130557.53 | completed | 1 | 2023-09-30 | 2023-04-03 | QRF-2021-RVIII-Ormoc | QRF-CY2022-REPAIR | 2022-08-03
QRF 2022 | Region VIII | Southern Leyte | 121996 | Bontoc Central School | BONTOC | 1 |  | 4 | REPAIR/ REHABILITATION | 7631879.2227 | 1 | 7555561.07 | COMPLETED | 1 | 2023-10-30 |  | CY2022-QRF-Gabaldon-L16 | CY2022-QRF-Gabaldon-L16 | 2022-04-27
QRF 2022 | Region VIII | Southern Leyte | 121996 | Bontoc Central School | BONTOC | 1 | 1 | 34 | REPAIR/ REHABILITATION | 12766248.59 | 1 | 7555561.07 | COMPLETED | 1 | 2023-10-30 |  | CY2022-QRF-Gabaldon-L16 | CY2022-QRF-Gabaldon-L16 | 2022-04-27
QRF 2022 | Region VIII | Southern Leyte | 122006 | Himakilo Primary School | BONTOC | 1 | 1 | 1 | REPAIR/ REHABILITATION | 570045.72 | 1 | 564999.05 | COMPLETED | 1 | 2023-10-29 |  | CY2022-QRF-Repair-L9 | CY2022-QRF-Repair-L9 | 2022-04-27
QRF 2022 | Region VIII | Southern Leyte | 303465 | LIMASAWA NATIONAL HIGH SCHOOL | LIMASAWA | 1 | 1 | 36 | REPAIR/ REHABILITATION | 12804218.42 | 1 | 12703879.05 | Completed | 1 |  |  | CY2022-QRF-Repair-L1 | CY2022-QRF-Repair-L1 | 2022-04-27 | [5 empty] | for procurement;revised pow
QRF 2022 | Region VIII | Southern Leyte | 122221 | Lugsongan Elementary School | LIMASAWA | 1 | 1 | 9 | REPAIR/ REHABILITATION | 5112651.73 | 1 | 2073549.03 | Completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 | 1 | 9 | REPAIR/ REHABILITATION | 5283041.75 | 1 | 12305913.39 | COMPLETED | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-02 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | ANIELTHON CONSTRUCTION AND SUPPLY
QRF 2022 | Region VIII | Southern Leyte | 122223 | Magallanes Elementary School | LIMASAWA | 1 |  | 2 | NEW CONSTRUCTION | 5702801.39 | 1 | 693338 | COMPLETED | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-01 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 | Region VIII | Southern Leyte | 122225 | San Agustin Elementary School | LIMASAWA | 1 | 1 | 7 | REPAIR/ REHABILITATION | 3026805.88 | 1 | 5707088.03 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-03 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | GELA CONSTRUCTION
QRF 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 | 1 | 6 | REPAIR/ REHABILITATION | 3261340.07 | 1 | 3560851.53 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-04 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | SB & T CONSTRUCTION
QRF 2022 | Region VIII | Southern Leyte | 122226 | San Bernardo Elementary School | LIMASAWA | 1 |  | 2 | NEW CONSTRUCTION | 6575848.24 | 1 | 2491050.24 | completed | 1 | 2023-09-06 |  | CY 2022 QRF BATCH 2 | CY 2022 QRF BATCH 2-DEPED-R7-CEBU-05 | 2023-02-22 | 2023-03-01 | 2023-03-13 |  | 2023-06-01 | HERO CONTRUCTION AND DEVELOPMENT CORP.
QRF 2022 | Region VIII | Southern Leyte | 122189 | Macrohon Central School | MACROHON | 1 | 1 | 12 | REPAIR/ REHABILITATION | 5504070.6474 | 1 | PHP 1,472,159.77 | Completed | 1 | 2023-08-22 |  | CY 2022 QRF BATCH 2 | ITB 2023-002 | 2023-03-03 | 2023-03-10 | 2023-03-22 | 2023-04-14 | 2023-04-19 | TRIPLE JO CONSTRUCTION SERVICES
QRF 2022 | Region VIII | Southern Leyte | 122189 | Macrohon Central School | MACROHON | 1 |  | 6 | REPAIR/ REHABILITATION | 9943819.5515 | 1 | 6, 210,000.00 | Completed | 1 | 2023-12-01 |  | ITB-2023-02-018 | QRF202304018 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRIBATA Construction | With time extension.
QRF 2022 | Region VIII | Southern Leyte | 305533 | Malitbog National High School | MALITBOG | 1 | 1 | 8 | REPAIR/ REHABILITATION | 4430312.8767 | 1 | 6741884.8 | Completed | 1 | 2023-12-01 |  | ITB-2023-02-025 | QRF202304021 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp. | For Post Qualification of Winning Bidders
QRF 2022 | Region VIII | Southern Leyte | 122030 | Hinunangan East Central School | HINUNANGAN | 2 | 1 | 1 | REPAIR/ REHABILITATION | 588537.43 | 1 | 14860634.65 | completed | 1 | 2023-11-01 |  | ITB-2023-02-019 | QRF202304019 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | Micro Asia Builders Corporation | For Post Qualification of Winning Bidders
QRF 2022 | Region VIII | Southern Leyte | 122031 | Hinunangan West Central School | HINUNANGAN | 2 | 1 | 1 | REPAIR/ REHABILITATION | 628174.33 | 1 | 10996219.44 | Completed | 1 | 2023-12-31 | December 18, 2023 | ITB-2023-02-026 | QRF202304022 | February 23, 2023 | March 3, 2023 | March 15, 2023 | April 5, 2023 | April 20, 2023 | PAR Builders, Elecrical and Construction Supply Corp. | With time extension.
QRF 2022 | Region VIII | Southern Leyte | 122031 | Hinunangan West Central School | HINUNANGAN | 2 |  | 4 | NEW CONSTRUCTION | 9930079.05 | 1 | 37483431.65 | Completed | 1 | 2024-01-10 |  | ITB-2023-02-020 | QRF202304020 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRINITYCAD Corporation
QRF 2022 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2 | 1 | 12 | REPAIR/ REHABILITATION | 2527676.6584 | 1 | 16952019.97 | Completed | 1 | December 4, 2023 |  | 2023-003-Infra | CY2022-QRF-Repair-L13 | 2023-03-10 |  | 2023-03-31 | 2023-04-05 | 2023-04-20
QRF 2022 | Region VIII | Southern Leyte | 122101 | Liloan Central School | LILOAN | 2 |  | 4 | NEW CONSTRUCTION | 9877536.42 | 1 | 2493388.2 | Completed | 1 | 2023-07-04 | 2023-05-25 | 2023-001-Infra | CY2022-QRF-Repair-L13 | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise
QRF 2022 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | PINTUYAN | 2 | 1 | 16 | REPAIR/ REHABILITATION | 6740151.561 | 1 | 6664922.47 | Completed | 1 | 2023-07-04 | 2023-05-25 | 2023-002-Infra | CY2022-QRF-Repair-L15 | 2023-02-24 |  | 2023-03-17 | 2023-03-21 | 2023-04-03 | C.Jansen Construction and General Merchandise
QRF 2022 | Region VIII | Southern Leyte | 122302 | Saint Bernard Central School | SAINT BERNARD | 2 | 1 | 35 | REPAIR/ REHABILITATION | 17360731.01 | 1 | 17187696.03 | Completed | 1 |  |  | CY2022-QRF-Repair-L8 | CY2022-QRF-Repair-L8 | 2022-04-27
QRF 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1115785.6755 | 1 | 1099486.78 | Completed | 1 |  |  | CY2022-QRF-Repair-L13 | CY2022-QRF-Repair-L13 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | VHITS D.G. BUILDERS AND ENTERPRISES | Awarded / Perfection of Contract
QRF 2022 | Region VIII | Southern Leyte | 122114 | Sta. Paz Elementary School | SAN FRANCISCO | 2 |  | 4 | NEW CONSTRUCTION | 9979524.06 | 1 | 9071932.33 | Completed | 1 |  |  | CY2022-QRF-NewCon-L21 | CY2022-QRF-NewCon-L21 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | BLACK NAZARENE BUILDERS AND ENTERPRISES | Awarded / Perfection of Contract
QRF 2022 | Region VIII | Southern Leyte | 122243 | San Ricardo Central School | SAN RICARDO | 2 | 1 | 22 | REPAIR/ REHABILITATION | 11898857.161 | 1 | 11817766.38 | Completed | 1 |  |  | CY2022-QRF-Repair-L14 | CY2022-QRF-Repair-L14 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | MIGHTY A's CONSTRUCTION AND HARDWARE SUPPLY | Awarded / Perfection of Contract
QRF 2022 | Region VIII | Southern Leyte | 122059 | Silago Central School | SILAGO | 2 | 1 | 4 | REPAIR/ REHABILITATION | 1633987.3352 | 1 | 1630175.36 | Completed | 1 |  |  | CY2022-QRF-Repair-L7 | CY2022-QRF-Repair-L7 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | JUNCYNTH CONSTRUCTION & GENERAL SERVICES | Awarded / Perfection of Contract
QRF 2022 | Region VIII | Southern Leyte | 122263 | Hindangan PS | SOGOD | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1327870.84 | 1 | 1312776.25 | Completed | 1 |  |  | CY2022-QRF-Repair-L9 | CY2022-QRF-Repair-L9 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Awarded / Perfection of Contract
QRF 2022 | Region VIII | Southern Leyte | 122280 | Sogod Central School | SOGOD | 2 | 1 | 35 | REPAIR/ REHABILITATION | 18323076.66 | 1 | 12448789.14 | Completed | 1 |  |  | CY2022-QRF-Repair-L11 | CY2022-QRF-Repair-L11 | 2022-04-27 | 2022-05-05 | 2022-05-18 | 2022-07-12 |  | 3MC KING CIVIL ENGINEERING CONSTRUCTION | Awarded / Perfection of Contract
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122544 | Mercedes Central School | MERCEDES | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2600638.38 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122685 | Quinapondan Central Elementary School | QUINAPONDAN | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2158793.15 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region VIII | Eastern Samar | 122700 | Salcedo Central Elementary School | SALCEDO | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2604913.04 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121408 | Hindang Central School | HINDANG | 5th | 1 | 5 | REPAIR OF CLASSROOMS | 1610308.64 | 1 | 1574959.81 | Completed | 1 | 2023-06-17 |  |  |  | 2023-01-17 | [5 empty] | awarded
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121688 | Cahagnaan Central School | MATALOM | 5th | 1 | 4 | Replacement | 11429257.0851 | 1 | 8518483.48 | Completed | 1 | 2023-09-27 | 2023-12-15 |  |  | 2023-01-17 | [5 empty] | awarded
QRF 2022 REPLENISHMENT | Region VIII | Leyte | 121679 | Matalom North Central School | MATALOM | 5th | 1 | 6 | REPAIR OF CLASSROOMS | 1620963.13 | 1 | 1600533.44 | Completed | 1 | 2023-06-29 |  |  |  | 2023-01-17 | [5 empty] | awarded
QRF 2022 REPLENISHMENT | Region VIII | Ormoc City | 124214 | Liloan Central School | ORMOC CITY | 4th | 1 | 4 | REPAIR OF CLASSROOMS | 2048640.94 | 1 | 1105733 | Completed | 1
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122210 | Malitbog Central School | MALITBOG | 1st | 1 | 11 | REHABILITATION OF GABALDON BUILDINGS | 11495051.46 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122210 | Malitbog Central School | MALITBOG | 1st |  | 36 | REPAIR OF CLASSROOMS | 18891179.44 | 1 |  | COMPLETED | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122224 | Padre Burgos Central School | PADRE BURGOS | 1st | 1 | 24 | REPAIR OF CLASSROOMS | 13508714.81 | 1 |  | COMPLETED | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122323 | Tomas Oppus Central School | TOMAS OPPUS | 1st | 1 | 23 | REPAIR OF CLASSROOMS | 11267143.87 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122065 | Anahawan Central School | ANAHAWAN | 2nd | 1 | 18 | REPAIR OF CLASSROOMS | 7337793.07 | 1 |  | COMPLETED | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 4 | Replacement | 9905392.58 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122071 | Hinundayan Central School | HINUNDAYAN | 2nd | 1 | 22 | REPAIR OF CLASSROOMS | 8732039.79 | 1 |  | COMPLETED | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122080 | Libagon Central School | LIBAGON | 2nd | 1 | 25 | REPAIR OF CLASSROOMS | 11525925.34 | 1 |  | COMPLETED | 1
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2nd | 1 | 4 | Replacement | 9936994.3 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122111 | San Francisco Central School | SAN FRANCISCO | 2nd | 1 | 13 | REPAIR OF CLASSROOMS | 6948729.04 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd | 1 | 6 | REHABILITATION OF GABALDON BUILDINGS | 8894453.9649 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2022 REPLENISHMENT | Region VIII | Southern Leyte | 122252 | San Juan Central Elementary School with SPED CENTER | SAN JUAN (CABALIAN) | 2nd |  | 34 | REPAIR OF CLASSROOMS | 14172687.09 | 1 |  | Completed | 1 | [10 empty] | FOR AWARD
QRF 2023 | Region VIII | Biliran | 313203 | ICT High School of Eastern Biliran | CAIBIRAN | Lone | 1 | 10 | REPAIR OF CLASSROOMS | 1655029.6 | 2-R |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122369 | Ando Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1614713.4117 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122357 | Calico-an Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2140685.7011 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122398 | Camada Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2409150.2189 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122361 | Eugenio S. Daza Pilot Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 6 | REPAIR OF CLASSROOMS | 2522036.6047 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122403 | Lalawigan Central Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 5721759.0761 | 1 | 2095000 | Completed | 1
QRF 2023 | Region VIII | Borongan City | 502290 | Sabang Integrated School | CITY OF BORONGAN (Capital) | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2404559.8182 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122362 | San Gabriel Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 4841848.0755 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122363 | San Jose Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 3138856.835 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122387 | San Saturnino Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1598425.2174 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122364 | Siha Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 2 | 1STY2CL | 6828901.78 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122388 | Sta. Fe Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1601069.0943 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 303525 | Sta. Fe National High School | CITY OF BORONGAN (Capital) | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 4990026.13 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122389 | Surok Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 3149287.661 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Borongan City | 122390 | Tabunan Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 3536422.7091 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122347 | Guinmaayohan Elementary School | BALANGIGA | Lone | 1 | 9 | REPAIR OF CLASSROOMS | 4658658.32 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 192519 | San Juan Elementary School | GUIUAN | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 4049092.3203 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122554 | Tubabao Elementary School | GUIUAN | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1972578.1556 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 501932 | Cagpile Integrated School | ORAS | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 2606947.213 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122664 | Gamot Primary School | ORAS | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1429380.0865 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122668 | Oras West Central Elementary School | ORAS | Lone | 1 | 15 | REPAIR OF CLASSROOMS | 7768905.12 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122674 | Buenavista Elementary School | QUINAPONDAN | Lone | 1 | 8 | REPAIR OF CLASSROOMS | 4229092.3203 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122681 | Naga Elementary School | QUINAPONDAN | Lone | 1 | 7 | REPAIR OF CLASSROOMS | 4221755.4143 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122686 | San Pedro Elementary School | QUINAPONDAN | Lone | 1 | 3 | REPAIR OF CLASSROOMS | 1792578.1556 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122690 | Abejao Elementary School | SALCEDO | Lone | 1 | 2 | REPAIR OF CLASSROOMS | 1404404.1132 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 122739 | Japunan Elementary School | SAN POLICARPO | Lone | 1 | 5 | REPAIR OF CLASSROOMS | 3106437.0164 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Eastern Samar | 303529 | Taft National High School | TAFT | Lone | 1 | 11 | REPAIR OF CLASSROOMS | 5890643.09 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Leyte | 121301 | Patoc Elementary School | DAGAMI | 2 | 1 | 3 | 1STY3CL | 8343500.28 | 1 | 8320904.13 | Completed | 1 | 2024-01-11 |  |  |  | 2023-07-17
QRF 2023 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1st | 1 | 11 | REPAIR OF CLASSROOMS | 6650571.4861 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122081 | Magkasag Elementary School | LIBAGON | 2nd | 1 | 4 | REPAIR OF CLASSROOMS | 2599910.7911 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122082 | Mayuga Elementary School | LIBAGON | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 4997420.14 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122237 | Manglit Elementary School | PINTUYAN | 2nd | 1 | 12 | REPAIR OF CLASSROOMS | 7224374.6487 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122238 | Nueva Estrella Elementary School | PINTUYAN | 2nd | 1 | 10 | REPAIR OF CLASSROOMS | 6130124.6202 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122245 | Son-Ok Elementary School | PINTUYAN | 2nd | 1 | 14 | REPAIR OF CLASSROOMS | 8314713.815 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 122104 | Marayag Elementary School | SAN FRANCISCO | 2nd | 1 | 9 | REPAIR OF CLASSROOMS | 5713718.537 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 303489 | Sta. Paz National High School | SAN FRANCISCO | 2nd | 1 | 34 | REPAIR OF CLASSROOMS | 11438604.33 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 303483 | San Ricardo National High School | SAN RICARDO | 2nd | 1 | 25 | REPAIR OF CLASSROOMS | 7915072.1224 | 1 |  | Completed | 1
QRF 2023 | Region VIII | Southern Leyte | 501048 | Saub Integrated School | SAN RICARDO | 2nd | 1 | 8 | REPAIR OF CLASSROOMS | 4988712.6263 | 1 |  | Completed | 1 |  | 00:00:00
QRF 2024 | Region VIII | Calbayog City | 502375 | Himalandrog Seven-Hills Integrated School | CALBAYOG CITY | 1st | 1 | 8 | 2-UNITS 1STY4CL WITH COMMON TOILET, PROVISION OF RAINWATER COLLECTOR, SCHOOL FURNITURE, SOLAR PV ENERGY SYSTEM, WATER SYSTEM & SITE DEVELOPMENT | 43063753.9 | 1- NC | 43050034.22 | Ongoing | 0.3 | 2025-12-06 |  | 2024-RVIII(calbayog)-QRF2024 | 2024-024 | 2024-08-07 | 2025-08-15 | 2024-08-27 | 2024-09-16 | 2024-11-15 | JFR Construction, Inc. | Ongoing
QRF 2024 | Region VIII | Southern Leyte | 122194 | San Joaquin Elementary School | MACROHON | 1st | 1 | 9 | Repair of Classrooms | 5624065.38 | 1- R | 4442556.41 | Completed | 1 | 2025-04-26 |  | CY2024-QRF-Repair -B1-L1 | CY2024-QRF-Repair -B1-L1 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed
QRF 2024 | Region VIII | Southern Leyte | 122198 | Villa Jacinta Elementary School | MACROHON | 1st | 1 | 12 | Repair of Classrooms | 7349218.58 | 1- R | 6088992.84 | Completed | 1 | 2025-05-11 |  | CY2024-QRF-Repair -B1-L2 | CY2024-QRF-Repair -B1-L2 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 122216 | Tigbawan Elementary School | MALITBOG | 1st | 1 | 5 | Repair of Classrooms | 3118839.65 | 1- R | 2463791.18 | Completed | 1 | 2025-03-12 |  | CY2024-QRF-Repair -B1-L3 | CY2024-QRF-Repair -B1-L3 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Completed
QRF 2024 | Region VIII | Southern Leyte | 122236 | Kinachawa Elementary School | SAN RICARDO | 2nd | 1 | 8 | Repair of Classrooms | 5001198.13 | 1- R | 3946273.17 | completed | 1 | 2025-04-26 |  | CY2024-QRF-Repair -B1-L4 | CY2024-QRF-Repair -B1-L4 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 122240 | Pinut-an Elementary School | SAN RICARDO | 2nd | 1 | 15 | Repair of Classrooms | 9003187.23 | 1- R | 5697169.02 | Completed | 1 | 2025-05-26 |  | CY2024-QRF-Repair -B1-L5 | CY2024-QRF-Repair -B1-L5 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 122270 | Mac Elementary School | SOGOD | 2nd | 1 | 13 | Repair of Classrooms | 7761485.49 | 1- R | 6438909.96 | completed | 1 | 2025-05-11 |  | CY2024-QRF-Repair -B1-L6 | CY2024-QRF-Repair -B1-L6 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | 3MC King Civil Engineering Construction | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 122271 | Magatas Elementary School | SOGOD | 2nd | 1 | 7 | Repair of Classrooms | 4199183.59 | 1- R | 3490366.11 | completed | 1 | 2025-03-27 |  | CY2024-QRF-Repair -B1-L7 | CY2024-QRF-Repair -B1-L7 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Bench Construction | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 303455 | Esperanza National High School | SAN RICARDO | 2nd | 1 | 9 | Repair of Classrooms | 5721707.02 | 1- R | 5700717.97 | Completed | 1 | 2025-04-26 |  | CY2024-QRF-Repair -B1-L8 | CY2024-QRF-Repair -B1-L8 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Bench Construction | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 303478 | Pinut-an National High School | SAN RICARDO | 2nd | 1 | 16 | Repair of Classrooms | 9707352.08 | 1- R | 6111355.94 | Completed | 1 | 2025-05-26 |  | CY2024-QRF-Repair -B1-L9 | CY2024-QRF-Repair -B1-L9 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 303470 | Marayag National High School | SAN FRANCISCO | 2nd | 1 | 14 | Repair of Classrooms | 8399226.38 | 1- R | 5625583.19 | completed | 1 | 2025-05-21 |  | CY2024-QRF-Repair -B1-L10 | CY2024-QRF-Repair -B1-L10 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Ongoing Repairs
QRF 2024 | Region VIII | Southern Leyte | 303449 | Consolacion National High School | SOGOD | 2nd | 1 | 8 | Repair of Classrooms | 4879554.1 | 1- R | 3442383.46 | completed | 1 | 2025-03-27 |  | CY2024-QRF-Repair -B1-L11 | CY2024-QRF-Repair -B1-L11 | 2024-08-19 | 2024-08-27 | 2024-09-09 | 2024-11-14 | 2024-11-27 | Vhits D.G. Builders & Enterprises | Ongoing Repairs

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%