## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region XII | General Santos City | 131292 | Aspang Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-04-30 | 120614S00046 | 14MB0047 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-10-10 | 2014-11-07 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 317003 | Baluan NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | [9 empty] | FUENTABUILT CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region XII | General Santos City | 131275 | Balunto ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-04-15 | 120614S00037 | 14MB0037 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-03 | 2014-10-21 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131294 | Bawing Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4375314.6094 |  |  | COMPLETED | 1 | 2015-07-23 | 2015-07-23 | 120614S00111 | 14MB0121 | 2015-01-27 | 2015-01-15 | 2015-01-27 | 2015-03-06 | 2015-03-20 | A.L. ACHARON CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | General Santos City | 304644 | Bawing NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | [9 empty] | MGBJ Rising Const. & Land Dev't
NC 2014 | K10 (2014) | Region XII | General Santos City | 210008 | Bia-o Primary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1930402.75 |  |  | COMPLETED | 1 | 2015-04-20 | 2015-04-20 | 120614S00122 | 14MB0103 | 2014-12-10 | 2014-11-26 | 2014-12-10 | 2014-12-29 | 2015-01-30 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | General Santos City | 131295 | Blagan Elementary School(Gawan PS) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3047674.43 |  |  | COMPLETED | 1 | 2015-05-05 | 2015-04-30 | 120614S00124 | 14MB0101 | 2014-12-10 | 2014-11-26 | 2014-12-10 | 2014-12-29 | 2015-01-30 | FREDEN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131301 | Daanbanwang ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00044 | 14MB0055 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-09 | 2014-10-03 | FREDEN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131276 | Dadiangas West CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11318184.375 |  |  | COMPLETED | 1 | 2015-07-11 | 2015-07-11 | 120614S00114 | 14MB0113 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-23 | 2015-02-06 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 304646 | Gen. Santos City HS - Lanton HS Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2923174.43 |  |  | COMPLETED | 1 | [8 empty] | 2015-03-11 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | General Santos City | 131310 | GSC Elem. Sch. for the Arts | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-15 | 120614S00110 | 14MB0117 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-23 | 2015-02-11 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 304655 | GSC Nat'l. Sec. Sch. Of Arts & Trades | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | [9 empty] | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | General Santos City | 131303 | H. Bayan Sr. Central Elem. School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY1CL | 2014 K10 BATCH 1 | 2175530.49 |  |  | COMPLETED | 1 | 2014-11-29 | 2015-01-31 | 120614S00043 | 14MB0056 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-27 | 2014-09-25 | LAWRENCE ERIC
NC 2014 | K10 (2014) | Region XII | General Santos City | 131296 | H. N. Cahilsot ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1930402.75 |  |  | COMPLETED | 1 | [9 empty] | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | General Santos City | 304645 | Johnny Ang NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | [9 empty] | FREDEN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131272 | Jose Catolico Sr. ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-08-25 | 120614S00115 | 14MB0114 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-23 | 2015-01-28 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 131311 | Jose P. Laurel Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-02-15 | 120614S00042 | 14MB0040 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-03 | 2014-09-30 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | General Santos City | 210012 | Jose R. Lansang PS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-08 | 2014-12-31 | 120614S00021 | 14MB0045 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-01 | 2014-10-20 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | General Santos City | 131285 | Lagao 2nd Bo. ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2015-02-13 | 120614S00048 | 14MB0054 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-10-21 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 304653 | Lagao NHS (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4A | 8228453.2031 |  |  | COMPLETED | 1 | [9 empty] | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 131279 | Lanton ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14141118.3984 |  |  | COMPLETED | 1 | 2015-09-23 | 2015-09-23 | 120614S00116 | 14MB0111 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-23 | 2015-02-06 | DELLOSA DESIGN-BUILD SERVICES
NC 2014 | K10 (2014) | Region XII | General Santos City | 131286 | Mabuhay ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 120614S00047 | 14MB0043 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-09-25 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 210009 | Maligaya Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-03-05 | 120614S00049 | 14MB0071 | 2014-08-12 | 2014-07-31 | 2014-08-12 | 2014-09-19 | 2014-10-27 | T-SQUARE CONSTRUCTION CORPORATION (FORMERLY:T-SQUARE BUILDERS)
NC 2014 | K10 (2014) | Region XII | General Santos City | 131321 | NASA ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 2972731.86 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-29 | 120614S00039 | 14MB0057 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-09-25 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131313 | New Society Central ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27389390.625 |  |  | COMPLETED | 1 | 2015-10-05 | 2015-12-18 | 120614S00113 | 14MB0107 | 2014-12-16 | 2014-12-16 | 2014-12-16 | 2014-12-29 | 2015-02-17 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | General Santos City | 131315 | P. Kindat ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 120614S00041 | 14MB0038 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-03 | 2014-10-21 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131280 | Saavedra Saway CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6094 |  |  | COMPLETED | 1 | 2015-06-27 | 2015-07-31 | 120614S00117 | 14MB0122 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-23 | 2015-02-13 | FUENTABUILT CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region XII | General Santos City | 304637 | Tinagacan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | General Santos City | 131308 | Upper Labay ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 940201.37 |  |  | COMPLETED | 1 | [9 empty] | FUENTABUILT CONSTTRUCTION CORP.
NC 2014 | K10 (2014) | Region XII | General Santos City | 304652 | Upper Labay HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | [9 empty] | FUENTABUILT CONSTRUCTION CORP.
NC 2014 | K10 (2014) | Region XII | General Santos City | 131324 | Upper Tambler ES II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-07 | 2015-03-22 | 120614S00023 | 14MB0044 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-10-24 | 2014-11-21 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | General Santos City | 131323 | Upper Tambler I Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2983674.43 |  |  | COMPLETED | 1 | 2015-01-06 | 2015-01-31 | 120614S00038 | 14MB0041 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-06 | 2014-10-03 | FREDEN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 131329 | Balabag ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2015-02-25 | 120414S00115 | 14MC0058-1 | 2014-06-19 | 2014-06-27 | 2014-07-10 | 2014-07-20 | 2014-08-29 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 210505 | Bangsa Moro ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 317110 | Binoligan Integrated School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3785805.49 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-31 | 120414S00122 | 14MC0039-5 | 2014-07-30 | 2014-08-08 | 2014-08-20 | 2014-09-02 | 2014-09-24 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 210501 | Datu Pananggom E. Andagkit MES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-01-17 | 2014-12-31 | 120414S00147 | 14MC0058-5 | 2014-06-19 | 2014-06-27 | 2014-07-10 | 2014-07-20 | 2014-08-29 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 210504 | Habitat Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-01-17 | 2014-12-31 | 120414S00121 | 14MC0058-4 | 2014-06-19 | 2014-06-27 | 2014-07-10 | 2014-07-23 | 2014-08-29 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 500303 | Lake Agco IS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 131345 | Luvimin ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2014-12-31 | 120414S00116 | 14MC0058-2 | 2014-06-19 | 2014-06-27 | 2014-07-10 | 2014-07-18 | 2014-08-29 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 500304 | Macebolig IS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-31 | 120414S00129 | 14MC0039-1 | 2014-07-30 | 2014-08-08 | 2014-08-20 | 2014-09-02 | 2014-09-24 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 500305 | Marciano Mancera IS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 500306 | Mua-an IS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 317109 | Nuangan Integrated School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2060417.57 |  |  | COMPLETED | 1 | 2015-01-17 | 2014-12-31 | 120414S00112 | 14MC0058-3 | 2014-06-19 | 2014-06-27 | 2014-07-10 | 2014-07-22 | 2014-08-29 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 131369 | Patadon ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 317204 | Puasinda Integrated School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 131372 | San Roque ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-02-26 | 120414S00117 | 14MC0039-3 | 2014-07-30 | 2014-08-08 | 2014-08-20 | 2014-09-02 | 2014-09-24 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 500307 | Singao IS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-31 | 120414S00120 | 14MC0039-2 | 2014-07-30 | 2014-08-08 | 2014-08-20 | 2014-09-02 | 2014-09-24 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XII | Kidapawan City | 210503 | St. Gregory Public ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2014-12-31 | 120414S00118 | 14MC0039-4 | 2014-07-30 | 2014-08-08 | 2014-08-20 | 2014-09-02 | 2014-09-24 | LLM CONCRETE PRODUCTS
NC 2014 | K10 (2014) | Region XII | Koronadal City | 304672 | Marbel 7 National High School | CITY OF KORONADAL (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 |  | 2015-02-28
NC 2014 | K10 (2014) | Region XII | Koronadal City | 131409 | Matulas ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2016-06-10 | 2016-07-31 | 1206-14-S-00136 | 15MG0033 | 2015-11-21 | 2015-11-27 | 2015-12-09 | 2015-12-23 | 2016-01-06 | Reydan Builders
NC 2014 | K10 (2014) | Region XII | Koronadal City | 317202 | Saravia NHS (Koronadal NCHS - Annex, Saravia Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Koronadal City | 131400 | Sto. Nino ES | CITY OF KORONADAL (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-06 | 2015-02-28 | 14MG0030-001 |  | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-08 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130036 | B. Bernardez ES | LIBUNGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00104 | 14-MD-0047 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207533 | Bacolod Annex PS | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 120414S00143 | 14-MD-0112 | 2014-07-24 | 2014-09-26 | 2014-09-30 | 2014-10-03 | 2014-10-14 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129858 | Balisawan ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00096 | 14-MD-0049 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130334 | Balong ES | PIKIT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00156 | 14-MD-0071 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130305 | Balongis ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00155 | 14-MD-0069 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130284 | Banucagon ES | PIGKAWAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00150 | 14-MD-0077 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130335 | Binandal PS | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-04-02 | 2015-04-20 | 120414S00138 | 14MD0095 | 2014-07-17 | 2014-11-12 | 2014-12-22 | 2014-12-23 | 2015-01-06 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130320 | Bulol ES | PIKIT | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4090835.14 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00163 | 14-MD-0059 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130040 | Cabpangi ES | LIBUNGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00106 | 14-MD-0062 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207507 | Central Katingawan ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00148 | 14-MD-0057 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130038 | Cornelio V. Cocal ES Annex | LIBUNGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00105 | 14-MD-0038 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207525 | Dabpil Sampulna ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-12-21 |  |  | 15-MD-0106 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2016-08-25 | 2015-09-15 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207574 | Dagadas ES | PIKIT | 1 | 1 | 7 | 2UNITS 1STY 2CL & 1UNIT 1STY 3CL | 2014 K10 BATCH 1 | 6976009.57 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-11-18 | 120414S00142 | 14-MD-0048 | 2014-06-16 | 2014-06-27 | 2014-07-18 | 2014-07-22 | 2014-07-24 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130307 | Dalingaoen ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00165 | 14-MD-0067 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130288 | Datu Binasing ES | PIGKAWAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00151 | 14-MD-0078 | 2014-07-18 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316550 | Datu Bitol Mangansakan Memorial High School | PIKIT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 120414S00048 | 14MD0096 | 2014-07-17 | 2014-07-29 | 2014-10-28 | 2014-11-11 | 2014-11-14 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130223 | Datu Guilem Piang ES (Upper Olandang ES) | MIDSAYAP | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00160 | 14-MD-0093 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129837 | Del Pilar ES | ALAMADA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00125 | 14-MD-0082 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130209 | Don Miguel Latada ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00110 | 14-MD-0092 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129838 | Dulao ES | ALAMADA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1217329.12 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 120414S00126 | 14MD0109 | 2014-07-24 | 2014-10-24 | 2014-10-28 | 2014-11-11 | 2014-11-14 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130308 | Ganasi ES | PIKIT | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00157 | 14-MD-0052 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130324 | Gligli ES | PIKIT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2670828.124 |  |  | COMPLETED | 1 | 2016-01-20 |  |  | 15-MD-0104 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2016-09-15 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130309 | Gokotan ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00149 | 14MD0070 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207519 | Guntong ES | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1237329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 120414S00130 | 14MD0116 | 2014-07-28 | 2014-10-24 | 2014-10-28 | 2014-11-11 | 2014-11-13 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130215 | Hadji Ungkakay ES (Lower Olandang ES) | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-12-21 |  |  | 15-MD-0107 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316548 | Juan Dillo Memorial High School | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00034 | 14-MD-0042 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130310 | Kalakacan ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130027 | Kapayawi ES | LIBUNGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00102 | 14MD0094 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130185 | KIMAGANGO ANNEX ELEMENTARY SCHOOL | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00109 | 14MD0085 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129825 | Kisulao ES | ALAMADA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00123 | 14-MD-0087 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316552 | Kitubod HS | LIBUNGAN | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4130835.14 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 120414S00037 | 14MD0072 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207531 | Kolambog ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 120414S00141 | 14MD0112(By Admin) | 2014-11-27 | 2014-12-09 | 2014-12-10 | 2014-12-17 | 2014-12-23 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130340 | Lagunde ES | PIKIT | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 120414S00131 | 14MD0113(BY Admin) | 2014-11-27 | 2014-12-09 | 2014-12-10 | 2014-12-17 | 2014-12-23 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207532 | Lamuak ES | PIKIT | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00140 | 14-MD-0054 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129839 | Lamuyon ES | ALAMADA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2015-03-09 | 2015-03-09 | 120414S00127 | 14MD0081 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130341 | Langayen ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1187329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00132 | 14-MD-0100 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129863 | Lawili ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00097 | 14-MD-0051 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130290 | Libungan Torreta ES | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00152 | 14-MD-0079 | 2014-07-18 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129864 | Lower Mingading ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 120414S00098 | 14-MD-0050 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130172 | Lt. Jesus Yermo ES (Bagumba ES) | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1187329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00108 | 14-MD-0039 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129841 | Macabasa ES | ALAMADA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 120414S00128 | 14MD0089 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-28 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129866 | Malapang ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00099 | 14-MD-0111 | 2014-07-24 | 2014-08-05 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130344 | Manaulanan ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00133 | 14-MD-0097 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316543 | Manglicmot HS | ALAMADA | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4130835.14 |  |  | COMPLETED | 1 | 2014-11-27 |  |  | 14MD0090 | 2014-07-26 | 2014-08-01 | 2014-08-14 | 2014-08-22 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130345 | Mapagkaya PS | PIKIT | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4130835.14 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 120414S00134 | 14-MD-0113 | 2014-07-24 | 2014-09-26 | 2014-09-30 | 2014-10-03 | 2014-10-14 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129828 | Marabuhay ES | ALAMADA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2985174.43 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00124 | 14-MD-0083 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207565 | Mimbalawag PS | ALAMADA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2995174.43 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-11 | 120414S00145 | 14-MD-0084 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130219 | Nabalawag ES | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00095 | 14-MD-0041 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130311 | Nabundas ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00161 | 14-MD-0102 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130272 | Nagret ES (New Igbaras) | PIGKAWAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00153 | 14-MD-0075 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129844 | New Leon ES | ALAMADA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00103 | 14-MD-0088 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316546 | Padura-Espabo High School | LIBUNGAN | 1 | 1 | 6 | 1STY2CL | 2014 K10 BATCH 1 | 6076252.71 |  |  | COMPLETED | 1 | 2015-03-07 | 2015-02-25 | 120414S00033 | 14MD0074 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304414 | Pagangan HS | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1134329.12 |  |  | COMPLETED | 1 | 2015-03-06 | 2015-03-06 | 120414S00137 | 14MD0086 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129869 | Palacat ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 120414S00100 | 14MD0098 | 2014-07-17 | 2014-07-29 | 2014-10-28 | 2014-11-03 | 2014-11-14 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130032 | Palao ES | LIBUNGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00094 | 14MD0099 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304492 | Pigcawaran NHS | ALAMADA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1187329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00113 | 14-MD-0115 | 2014-07-24 | 2014-08-05 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130297 | Pigcawayan CES | PIGKAWAYAN | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4000835.14 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00158 | 14-MD-0061 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129848 | Quintas ES | ALAMADA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2115417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00101 | 14-MD-0108 | 2014-07-24 | 2014-08-05 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304495 | Rajah Muda High School | PIKIT | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00073 | 14-MD-0065 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316544 | Rangayen HS | ALAMADA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2960174.43 |  |  | COMPLETED | 1 | 2014-11-27 |  |  | 14MD0080 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | PHILTIL CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304501 | Salunayan HS | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-18 |  |  | 14MD0043 | 2014-06-18 | 2014-06-25 | 2014-07-08 | 2014-07-14 | 2016-07-24 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304502 | Salunayan HS - Kapinpilan Annex | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00028 | 14-MD-0045 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316526 | Salunayan HS - Nabalawag HS Annex | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 120414S00029 | 14-MD-0046 | 2014-06-13 | 2014-06-25 | 2014-07-18 | 2014-07-22 | 2014-07-24 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130222 | Sambulawan ES | MIDSAYAP | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00146 | 14-MD-0055 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207508 | San Pedro ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00139 | 14-MD-0056 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207543 | Senior Malao ES | PIKIT | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 120414S00144 | 14MD0101 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-28 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130348 | Silik CES | PIKIT | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2055417.57 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00135 | 14MD0066 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129871 | Sta. Cruz ES | ALEOSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00111 | 14-MD-0040 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129872 | Sulok PS | ALEOSAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2670828.124 |  |  | COMPLETED | 1 | 2016-01-20 |  |  | 15MD0105 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | LLABAN CONST
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130314 | Sultan Mem. ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00162 | 14-MD-0068 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130332 | Talitay ES | PIKIT | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00164 | 14-MD-0058 | 2014-06-16 | 2014-06-27 | 2014-06-30 | 2014-07-08 | 2014-07-23 | MUST ENTERPRISES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129853 | Teren-teren PS | ALAMADA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-03-10 | 120414S00119 | 14MD0110 | 2014-07-24 | 2014-10-24 | 2014-10-28 | 2014-11-11 | 2014-11-14 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130300 | Tubon ES | PIGKAWAYAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-03-04 | 2015-03-04 | 120414S00154 | 14MD0076 | 2014-07-18 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-28 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316549 | Tukuran T. Kendenga High School | MIDSAYAP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 120414S00035 | 14MD0114 | 2014-07-24 | 2014-10-27 | 2014-10-28 | 2014-10-31 | 2014-11-14 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207506 | Vicente Rapacon Memorial ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-11-16 | 120414S00136 | 14-MD-0044 | 2014-06-13 | 2014-06-25 | 2014-06-26 | 2014-07-02 | 2014-07-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130042 | Wendelin Eduarte ES (Gumaga ES) | LIBUNGAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-19 | 2015-02-19 | 120414S00107 | 14MD0073 | 2014-07-17 | 2014-07-29 | 2014-11-12 | 2014-11-20 | 2014-11-25 | RDEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316545 | Yanson High School | ALAMADA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2095417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120414S00032 | 14-MD-0091 | 2014-07-17 | 2014-07-29 | 2014-08-14 | 2014-08-20 | 2014-09-02 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130047 | AMABIL ELEMENTARY SCHOOL | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129893 | Anapolon ES | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-07-31 | 120414S00039 | 14MC0072-3 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129894 | Anuling PS | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129896 | Arakan ES (Badiangon) | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130070 | Bagumbayan ES | MAGPET | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-04-29 | 120414S00013 | 14MC0044-1 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-12 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316538 | Bagumbayan HS | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-17 | 120414S00076 | 14MC0044-6 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130071 | Basak ES | MAGPET | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-04-30 | 120414S00004 | 14MC0044-2 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-08 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130108 | Bato ES | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-02 | 2015-02-15 | 120414S00005 | 14MC0046-2 | 2014-06-28 | 2014-07-04 | 2014-07-17 | 2014-07-25 | 2014-08-29 | KRBS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316528 | Bienvenido Orteza NHS | MAKILALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2014-11-15 | 120414S00075 | 14MC0068-1 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130097 | Bulatukan ES | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130369 | Cabangbangan ES | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-25 | 120414S00019 | 14MC0066-2 | 2014-08-28 | 2014-09-05 | 2014-09-17 | 2014-10-05 | 2014-10-30 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130074 | Cebomailo ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-04-30 | 120414S00011 | 14MC0044-4 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-15 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316553 | Datu Ladayon HS | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1844740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130051 | Datu Mantawil ES | MAGPET | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-17 | 120414S00045 | 14MC0052-1 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-06 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130352 | Datu Sundungan ES | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-25 | 120414S00025 | 14MC0066-3 | 2014-08-28 | 2014-09-05 | 2014-09-17 | 2014-09-30 | 2014-10-30 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130076 | Del Pilar ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130053 | Don Panaca ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-04-28 | 120414S00018 | 14MC0044-3 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-15 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129902 | Doroluman CES | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-26 | 120414S00040 | 14MC0071-2 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130371 | Egmedio Fernando ES (Jose Tuburan Sr.) | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130372 | F. Cajelo ES | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-25 | 120414S00020 | 14MC0066-1 | 2014-08-28 | 2014-09-05 | 2014-09-17 | 2014-10-05 | 2014-10-30 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130098 | Garsika ES | MAKILALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-31 | 120414S00008 | 14MC0045-3 | 2014-06-09 | 2014-06-19 | 2014-07-10 | 2014-07-25 | 2014-08-29 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130374 | Greenhills ES | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130112 | Guangan ES | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130354 | Hope PS | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304441 | Katipunan HS | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130115 | Kawayanon PS | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129910 | Kiatao PS | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-08-15 | 120414S00041 | 14MC0072-1 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130058 | Kisandal ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2014-12-31 | 120414S00047 | 14MC0052-3 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304456 | Kisante NHS | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316519 | Kisante NHS - Batasan HS Annex | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130357 | Kisupaan ES | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-05-31 | 120414S00017 | 14MC0065-1 | 2014-11-11 | 2014-11-17 | 2014-11-19 | 2014-11-25 | 2015-01-05 | By Administration
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130358 | Lamalama ES | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130360 | Lebpas ES | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-08-15 | 120414S00012 | 14MC0065-2 | 2014-11-11 | 2014-11-18 | 2014-11-19 | 2014-11-28 | 2015-01-05 | By Administration
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130379 | Lomonay ES | PRESIDENT ROXAS | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4000835.14 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00021 | 14MC0043-3 | 2014-06-11 | 2014-06-20 | 2014-07-24 | 2014-07-28 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130059 | Lubas PS | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130118 | Luna Norte ES | MAKILALA | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3980835.14 |  |  | COMPLETED | 1 | 2015-01-02 | 2015-02-15 | 120414S00010 | 14MC0046-1 | 2014-06-28 | 2014-07-04 | 2014-07-17 | 2014-07-25 | 2014-08-29 | KRBS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130381 | Mahayag ES | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00022 | 14MC0043-1 | 2014-06-11 | 2014-06-20 | 2014-07-24 | 2014-07-29 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129918 | Makalangot ES | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-06-12 | 120414S00042 | 14MC0072-2 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304424 | Malabuan HS | MAKILALA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-26 | 120414S00038 | 14MC0067-1 | 2014-08-28 | 2014-09-05 | 2014-09-17 | 2014-09-29 | 2014-10-30 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129890 | Malire ES | ANTIPAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2100417.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-02-25 | 120414S00026 | 14MC0056-3 | 2014-06-16 | 2014-06-26 | 2014-10-03 | 2014-10-22 | 2014-10-30 | JOHN RAY DEVELOPER AND SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130121 | Malungon ES | MAKILALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2015-02-15 | 120414S00015 | 14MC0046-3 | 2014-06-28 | 2014-07-04 | 2014-07-17 | 2014-07-25 | 2014-08-29 | KRBS CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130062 | Manobo ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-17 | 120414S00036 | 14MC0052-4 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316501 | Manumba National HS | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-17 | 120414S00074 | 14MC0052-6 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129921 | Naje ES | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-25 | 120414S00043 | 14MC0071-1 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129922 | Napalico ES | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-31 | 120414S00044 | 14MC0047-4 | 2014-07-14 | 2014-07-24 | 2014-08-04 | 2014-08-20 | 2014-08-29 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130090 | New Cebu ES | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-02-15 | 120414S00009 | 14MC0045-1 | 2014-06-09 | 2014-06-19 | 2014-07-10 | 2014-07-23 | 2014-08-29 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304484 | New Israel HS | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207518 | Noa PS Annex | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130063 | Owas ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207502 | Paco-Paco ES | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-31 | 120414S00024 | 14MC0047-1 | 2014-07-14 | 2014-07-24 | 2014-08-04 | 2014-08-20 | 2014-08-29 | R.N.H. BENTULAN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130104 | Rodero ES | MAKILALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-10 | 120414S00007 | 14MC0045-4 | 2014-06-09 | 2014-06-19 | 2014-07-10 | 2014-07-22 | 2014-08-29 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129923 | Saje ES | ARAKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1032049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130105 | San Isidro PS | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130081 | Sibug ES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-04-29 | 120414S00014 | 14MC0044-5 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-06 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207544 | Sinayawan ES | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1894740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130107 | Sto. Nino ES | MAKILALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-31 | 120414S00006 | 14MC0045-2 | 2014-06-09 | 2014-06-19 | 2014-07-10 | 2014-07-23 | 2014-08-29 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130386 | Sumakwelan PS | PRESIDENT ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1042049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130066 | Tagbac CES | MAGPET | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-17 | 120414S00016 | 14MC0052-5 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-15 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130388 | Upper Ipuan ES | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00023 | 14MC0043-2 | 2014-06-11 | 2014-06-20 | 2014-07-24 | 2014-07-29 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1187329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130144 | Arakan PS | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-05-31 | 120414S00087 | 14MC0057-4 | 2014-06-16 | 2014-06-26 | 2014-07-08 | 2014-07-26 | 2014-08-29 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130400 | Bacong ES | TULUNAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2990174.43 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00056 | 14MC0041-2 | 2014-06-09 | 2014-06-19 | 2014-06-30 | 2014-07-15 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130127 | Bato ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2015-02-27 | 120414S00082 | 14MC0056-4 | 2014-06-16 | 2014-06-26 | 2014-10-03 | 2014-10-22 | 2014-10-30 | JOHN RAY DEVELOPER AND SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316556 | Bentangan HS | CARMEN | 3 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4348392.2448 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130391 | Bituan ES | TULUNAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00055 | 14MC0041-1 | 2014-06-09 | 2014-06-19 | 2014-06-30 | 2014-07-15 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207516 | Buay-Buay PS | BANISILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1207329.12 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 120414S00049 | 14MD0097(BY Admin) | 2014-07-24 | 2014-11-14 | 2014-11-27 | 2014-12-13 | 2014-12-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316516 | Carmen NHS - Liliongan Annex | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00171 | 14-MD-0106 | 2014-07-24 | 2014-08-05 | 2014-08-14 | 2014-08-20 | 2014-09-02 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130145 | Central Malamote ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-04-02 | 120414S00088 | 14MC0070-1 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | ALZEN ENGINEERING & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130161 | Condrado B. Biscarra PS | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-25 | 120414S00090 | 14MC0069-1 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | ALZEN ENGINEERING & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130007 | Cuyapon ES | KABACAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 120414S00079 | 14MD0119 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207572 | Diosdado Almarines ES | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2055417.57 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-02-26 | 120414S00063 | 14MC0057-1 | 2014-06-16 | 2014-06-26 | 2014-07-08 | 2014-07-25 | 2014-08-29 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207552 | Eden Elementary School-Maligaya Primary School Annex | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1187329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-09-15 | 120414S00062 | 14MC0042-1 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-07 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130257 | Gaunan ES | M'LANG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00053 | 14MC0053-6 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-05 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129959 | Gawasan ES | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1237329.12 |  |  | COMPLETED | 1 | 2015-03-18 | 2015-03-18 | 120414S00167 | 14MD0122 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130149 | Ilian ES | MATALAM | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2960174.43 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-09-15 | 120414S00089 | 14MC0042-4 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304449 | Kabulacan HS | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-04-02 | 120414S00064 | 14MC0069-3 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | ALZEN ENGINEERING & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207540 | Kalalagan PS | BANISILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1222329.12 |  |  | COMPLETED | 1 | 2015-01-08 | 2015-01-08 | 120414S00061 | 14-MD-0104 | 2014-07-24 | 2014-09-26 | 2014-09-30 | 2014-10-03 | 2014-10-14 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130407 | Kanibong ES | TULUNAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2014-12-31 | 120414S00057 | 14MC0041-3 | 2014-06-09 | 2014-06-19 | 2014-06-30 | 2014-07-15 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129983 | Kibenes ES | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 120414S00180 | 14MD0123 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-14 | 2014-10-17 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130163 | Kilada ES (Matalam Central Annex ES) | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-04-02 | 120414S00091 | 14MC0069-2 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | ALZEN ENGINEERING & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207503 | Kilala ES | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2014-11-27 | 2014-11-27 | 120414S00170 | 14-MD-0107 | 2014-07-24 | 2014-08-05 | 2014-08-14 | 2014-08-20 | 2014-09-02 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 207501 | Kulawan ES | BANISILAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2135417.57 |  |  | COMPLETED | 1 | 2015-05-10 | 2015-05-10 | 120414S00059 | 14MD0096(BY Admin) | 2015-01-14 | 2015-01-26 | 2015-01-28 | 2015-02-04 | 2015-02-13 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129985 | Langogan Elementary School | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00173 | 14MD0126 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129962 | Lanoon ES | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00168 | 14MD0125 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-20 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130131 | Latagan ES | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2065417.57 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-08-15 | 120414S00071 | 14MC0042-5 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-09 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129967 | Malapag ES | CARMEN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1834740.174 |  |  | COMPLETED | 1 | 2015-12-21 |  |  | 15MD0108 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129986 | Manarapan ES | CARMEN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00172 | 14MD0127 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130165 | New Abra ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-09-15 | 120414S00060 | 14MC0042-3 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-10 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304477 | New Alimodian HS | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-05-31 | 120414S00065 | 14MC0057-5 | 2014-06-16 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-29 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130166 | New Bugasong ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-02-26 | 120414S00083 | 14MC0070-2 | 2014-08-29 | 2014-09-05 | 2014-09-19 | 2014-09-30 | 2014-10-30 | ALZEN ENGINEERING & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130252 | New Lawaan ES | M'LANG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00052 | 14MC0053-5 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-05 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130228 | New Rizal ES | M'LANG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00081 | 14MC0053-2 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-02 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129971 | Old Bentangan ES | CARMEN | 3 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4348392.2448 |  |  | COMPLETED | 1 | 2016-01-20 |  |  | 15MD0103 | 2016-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130230 | Pag-asa (Inside) ES | M'LANG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1177329.12 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00050 | 14MC0053-4 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-05 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130262 | Pangcog ES | M'LANG | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00054 | 14MC0053-1 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-08 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129944 | Pantar ES | BANISILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1202329.12 |  |  | COMPLETED | 1 | 2015-01-18 | 2015-01-18 | 120414S00077 | 14MD0128 | 2014-09-17 | 2014-09-29 | 2014-09-30 | 2014-10-03 | 2014-10-14 | K.A. BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130232 | Perez ES | M'LANG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2055417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-06-10 | 120414S00051 | 14MC0053-3 | 2014-07-22 | 2014-07-25 | 2014-08-18 | 2014-09-12 | 2014-09-24 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130139 | Pinamaton ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-05-30 | 120414S00084 | 14MC0057-2 | 2014-06-16 | 2014-06-26 | 2014-07-08 | 2014-07-22 | 2014-08-29 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130416 | Popoyon ES | TULUNAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2014-12-31 | 120414S00070 | 14MC0041-4 | 2014-06-09 | 2014-06-19 | 2014-06-30 | 2014-07-15 | 2014-08-29 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130141 | Sarayan ES | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2016-02-19 | 2015-02-25 | 120414S00085 | 14MC0056-2 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 304503 | Sarayan HS | MATALAM | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2055417.57 |  |  | COMPLETED | 1 | 2016-02-19 | 2015-02-26 | 120414S00066 | 14MC0056-1 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130022 | Simone ES | KABACAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00080 | 14MD0120 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 316540 | Sta. Maria High School | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-08-15 | 120414S00068 | 14MC0042-2 | 2014-08-06 | 2014-08-14 | 2014-08-26 | 2014-09-08 | 2014-09-24 | M.S. CONSTRUCTION AND MARKETING
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130143 | Taguranao ES | MATALAM | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-02-25 | 120414S00086 | 14MC0057-3 | 2014-06-16 | 2014-06-26 | 2014-07-08 | 2014-07-25 | 2014-08-29 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | North Cotabato | 130023 | Tamped ES | KABACAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00093 | 14MD0121 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129952 | Thailand ES | BANISILAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1207329.12 |  |  | COMPLETED | 1 | 2015-03-19 | 2015-03-19 | 120414S00078 | 14MD0111(by Admin) | 2014-11-27 | 2014-12-09 | 2014-12-10 | 2014-12-17 | 2014-12-23 | J-ONE BUILDERS
NC 2014 | K10 (2014) | Region XII | North Cotabato | 129992 | Tonganon ES | CARMEN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 120414S00166 | 14MD0124 | 2014-09-24 | 2014-10-06 | 2014-10-07 | 2014-10-10 | 2014-10-21 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130497 | A. F. dela Cruz (Katubao) ES | KIAMBA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120714S00034 | 14ME0074-2 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-12-23 | 2014-12-29 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sarangani | 316634 | Alabel Central Integrated SPED Center | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 304518 | Alabel NHS (Alabel BHS) | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130419 | Alegria Central Elementary School | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1007197.9953 |  |  | COMPLETED | 1 | 2015-05-02 | 2015-06-15 | 120714S00098 | 14ME0172 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | SHEPPERD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 304519 | Alegria NHS | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208003 | Anecito Bartulaba ES | GLAN | 0 | 1 | 4 | 1STY3CL and 1STY1CL | 2014 K10 BATCH 3 | 3890813.0589 |  |  | COMPLETED | 1 | 2015-07-30 |  | 120714S00113 | 15ME0032 | 2015-02-03 | 2015-03-16 | 2015-03-16 | 2015-03-23 | 2015-03-27 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130587 | Balitangan PS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-01-06 | 2015-02-20 | 120714S00039 | 14ME0103 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-23 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130443 | Baliton ES | GLAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1 | 2015-08-01 |  | 120714S00096 | 15ME0024 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-19 | JOMAREL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 304521 | Baliton NHS | GLAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6374039.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130588 | Banahaw ES | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 120714S00017 | 14ME0057 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-02 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130589 | Bangkal ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-02-13 | 2015-02-13 | 120714S00018 | 14ME0093 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-13 | 2014-10-31 | PALMARES GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region XII | Sarangani | 500289 | Banlibato IS | ALABEL (Capital) | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 500259 | Batulaki IS | GLAN | 0 | 1 | 7 | 1STY4CL & 1STY3CL | 2014 K10 BATCH 1 | 6825979.92 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-12-31 | 120714S00028 | 14ME0098 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-10 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130487 | Bocay- Il ES | KIAMBA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1167329.12 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-16 | 120714S00043 | 14ME0083 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-25 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 208012 | Bongo ES | MAASIM | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2220417.57 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 120714S00069 | 14ME0085 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-12 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 500262 | Cabales Enarbia Sr. IS | KIAMBA | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6399164.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 500262 | Cabales-Enarbia CIS (Lomuyon ES) | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 120714S00003 | 14ME0072 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 500280 | Cablalan IS | GLAN | 0 | 1 | 5 | 1STY5CL | 2014 K10 BATCH 4B | 4273392.2448 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130452 | Calpidong ES | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1107697.9953 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-05-22 | 120714S00095 | 14ME0178 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | CS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 304523 | Colon NHS | MAASIM | 0 | 1 | 12 | 2STY6CL | 2014 K10 BATCH 3 | 16456906.4062 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130453 | Congan ES | GLAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-02-28 | 120714S00030 | 14ME0099 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 500275 | Consolacion IS | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1027297.9953 |  |  | COMPLETED | 1 | 2015-01-06 | 2015-01-06 | 120714S00063 | 14ME0062 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-27 | 2014-10-03 | N. CONGSON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 500275 | Consolacion IS | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208037 | D. Masalon Y. Recto PS | GLAN | 0 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 3066571.7358 |  |  | COMPLETED | 1 | 2015-06-01 |  | 120714S00110 | 14ME0180 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130549 | Daan Suyan Integrated School | MALAPATAN | 0 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 3 | 3840563.0589 |  |  | COMPLETED | 1 | 2015-07-22 | 2015-08-05 | 120714S00109 | 15ME0033 | 2015-02-03 | 2015-02-16 | 2015-02-16 | 2015-02-27 | 2015-03-19 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 500272 | Daan Suyan IS | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130593 | Dalamuan ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 2009123.7405 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-10-16 | 120714S00099 | 14ME0176 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | GRECO CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 208010 | Danao ES | MALUNGON | 0 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 5085592 |  |  | COMPLETED | 1 | 2015-03-10 |  | 120714S00067 | 14ME0063 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-14 | 2014-10-31 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | Sarangani | 500256 | Datal Anggas IS | ALABEL (Capital) | 0 | 1 | 7 | 2STY4CL & 1STY3CL | 2014 K10 BATCH 3 | 9333029.8292 |  |  | COMPLETED | 1 | 2015-08-08 | 2015-12-01 | 120714S00100 | 15ME0017 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-06 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 500256 | Datal Anggas IS | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130595 | Datal Baca ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 120714S00019 | 14ME0119 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 500273 | Datal Bila IS | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1292329.12 |  |  | COMPLETED | 1 | 2015-02-18 | 2015-02-18 | 120714S00062 | 14ME0120 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130598 | Datal Tampal ES | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-15 | 120714S00020 | 14ME0094 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-11-20 | SHEPPERD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130510 | Datu Abdulbali (Tinoto) ES | MAASIM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1007197.9953 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-22 | 120714S00089 | 14ME0175 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | SHEPPERD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130490 | Datu Dani ES | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120714S00042 | 14ME0074-1 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-12-23 | 2014-12-29 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130550 | Datu Pangolima Integrated School | MALAPATAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2015-01-26 | 120714S00012 | 14ME0061 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | Sarangani | 130551 | Del Hilado ES | MALAPATAN | 0 | 1 | 4 | 1STY1CL & 1STY3CL | 2014 K10 BATCH 3 | 3890813.0589 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region XII | Sarangani | 130448 | Domingo R. Cania Mem. ES (Calabalol ES) | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-03 | 120714S00029 | 14ME0123 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-20 | SHEPPERD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130457 | E. Alegado Integrated School | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1342329.12 |  |  | COMPLETED | 1 | 2015-03-15 |  | 120714S00031 | 14ME0122 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-20 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 500258 | E. Alegado IS | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208021 | Enrique D. Yap, Sr. ES (Lovesville ES) | GLAN | 0 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 3 | 2890696.7358 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-06-01 | 120714S00112 | 14ME0181 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130500 | Fermin Fuster (Kitagas ES) | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 120714S00032 | 14ME0072 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130459 | Glan CES | GLAN | 0 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1 | 2015-08-07 | 2015-10-31 | 120714S00094 | 15ME0018 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-05 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 304524 | Glan School of Arts and Trade | GLAN | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 304525 | Glan-Padidu NHS | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208038 | Green Valley PS | KIAMBA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-03-05 |  | 120714S00084 | 14ME0112 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130461 | Gulo ES | GLAN | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 4010805.49 |  |  | COMPLETED | 1 | 2015-04-04 |  | 120714S00044 | 14ME0097 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130552 | H. Diamalod Ebrahin ES | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-12-27 | 2015-01-08 | 120714S00002 | 14ME0061 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | Sarangani | 316635 | Hadji Musa Integrated School | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 500283 | Hadji Musa IS | GLAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-22 | 2015-06-22 | 120714S00093 | 15ME0026 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-09 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130515 | Hilltop ES | MAASIM | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-03-16 | 120714S00007 | 14ME0084 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130516 | Ireneo C. Lopez (Lumasal) ES | MAASIM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-03-16 | 120714S00008 | 14ME0084 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 500263 | JBT Caing Sr. IS | KIAMBA | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130484 | Jose Ah Young (Tango) ES | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 120714S00061 | 14ME0080 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-10 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130517 | Kablacan ES | MAASIM | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-03-16 | 120714S00009 | 14ME0084 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 208041 | Kalbangan | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 120714S00083 | 14ME0117 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-21 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130599 | Kalon Barak ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-11-30 | 120714S00021 | 14ME0066 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130463 | Kaltuad ES | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-05-31 | 120714S00033 | 14ME0124 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-21 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 208044 | Kanyugan PS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3115174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-05-14 | 120714S00081 | 14ME0067 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-21 | GRECO CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130495 | Kapanal ES | KIAMBA | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4040835.14 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120714S00013 | 14ME0075 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-12 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130426 | Kawas CES | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 304526 | Kawas NHS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130553 | Kiahe Elementary School | MALAPATAN | 0 | 1 | 6 | 1STY 3CL | 2014 K10 BATCH 1 | 5980348.86 |  |  | COMPLETED | 1 | 2015-03-10 | 2015-05-09 | 120714S00014 | 14ME0101 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 304527 | Kiamba NHS | KIAMBA | 0 | 1 | 7 | 2STY6CL & 1STY1CL | 2014 K10 BATCH 3 | 9235651.1984 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208015 | KibaK PS | ALABEL (Capital) | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4140835.14 |  |  | COMPLETED | 1 | 2015-03-05 |  | 120714S00075 | 14ME0069 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130601 | Kiblat ES | MALUNGON | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-01-28 | 2015-03-04 | 120714S00011 | 14ME0102 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-25 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130531 | Kipalkuda ES | MAITUM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-04 | 120714S00010 | 14ME0059 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130602 | Kisablay ES | MALUNGON | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 120714S00060 | 14ME0116 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130603 | Kityan ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-11-30 | 120714S00078 | 14ME0066 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 208043 | Laginan PS | MALUNGON | 0 | 1 | 6 | 1STY 3CL | 2014 K10 BATCH 3 | 5515980.1272 |  |  | COMPLETED | 1 | 2015-09-29 | 2015-10-14 | 120714S00101 | 15ME0028 | 2015-01-27 | 2015-05-05 | 2015-05-05 | 2015-05-14 | 2015-05-27 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 208014 | Lanao Kapanglao PS | GLAN | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4240835.14 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region XII | Sarangani | 208030 | Langaran PS | MAASIM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-03-03 | 120714S00082 | 14ME0077 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-25 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130556 | Lasang ES | MALAPATAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-11-29 | 120714S00015 | 14ME0106 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-26 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130429 | Latian ES | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1107697.9953 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-06-05 | 120714S00097 | 14ME0173 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 208031 | Lebe PS | MAASIM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1 | 2015-01-13 | 2015-02-18 | 120714S00087 | 14ME0060 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-25 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 500286 | Leopoldo D. Dacera Sr. IS | ALABEL (Capital) | 0 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4985592 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 120714S00080 | 14ME0088 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-12 | CURVE-LINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 500286 | Leopoldo P. Dacera IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 316612 | Lumigo IS | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1342329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130560 | Lun Padidu Central Elementary School | MALAPATAN | 0 | 1 | 5 | 1STY1CL & 2STY4CL | 2014 K10 BATCH 3 | 7305862.7609 |  |  | COMPLETED | 1 | 2015-07-18 | 2015-11-10 | 120714S00118 | 15ME0031 | 2015-02-03 | 2015-02-16 | 2015-02-16 | 2015-02-27 | 2015-03-05 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 304531 | Lun Padidu NHS | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130609 | Lutay ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2015-01-30 | 2015-01-30 | 120714S00076 | 14ME0057 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-02 | RITZTOK CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130505 | M. Quinto (Suli-Blucon) ES | KIAMBA | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-29 | 120714S00004 | 14ME0082 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130467 | Macatimbol ES | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2014-12-24 | 120714S00023 | 14ME0090 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-10 | LEGACY CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 316631 | Malabod IS | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 304533 | Malalag Cogon NHS | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 316639 | Malalag NHS - Upo Annex | MAITUM | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130611 | Malandag CES | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-08-03 | 2015-08-05 | 120714S00115 | 15ME0027 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-09 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | Sarangani | 130561 | Malapatan CES | MALAPATAN | 0 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-09-25 | 120714S00117 | 15ME0029 | 2015-01-27 | 2015-02-09 | 2015-02-09 | 2015-02-23 | 2015-03-17 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | 0 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11277984.375 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130612 | Malinis ES | MALUNGON | 0 | 1 | 4 | 1STY3CL and 1STY1CL | 2014 K10 BATCH 3 | 3790313.0589 |  |  | COMPLETED | 1 | 2015-07-08 | 2015-10-17 | 120714S00114 | 15ME0035 | 2015-02-03 | 2015-02-16 | 2015-02-16 | 2015-02-27 | 2015-03-05 | GRECO CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130563 | Mama Nawa Elementary School | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-11-29 | 120714S00001 | 14ME0106 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-26 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130564 | Millona Upper Suyan ES | MALAPATAN | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4190835.14 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-24 | 120714S00016 | 14ME0087 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-26 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 316609 | New Canaan IS | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1292329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208047 | Nian Integrated School | MALUNGON | 0 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 4B | 10877342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130524 | Nomoh IS | MAASIM | 0 | 1 | 2 | 1STY1CL | 2014 K10 BATCH 3 | 2054595.9906 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-22 | 120714S00088 | 14ME0185 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 316618 | Nomoh IS | MAASIM | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208017 | Nop PS | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-01-20 |  | 120714S00066 | 14ME0064 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-27 | 2014-10-07 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130473 | Panambalan ES | GLAN | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3464886.575 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130474 | Pangyan ES | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-03-05 | 120714S00035 | 14ME0104 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130434 | Paraiso ES | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-19 | 120714S00024 | 14ME0065 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-25 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130435 | Pongoleel ES | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-17 | 120714S00025 | 14ME0078 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | LAWRENCE ERIC CONSTRUCTION & ENGINEERING SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 208018 | Saliluk L. Macantal Elementary School | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2965174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-17 | 120714S00077 | 14ME0078 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | LAWRENCE ERIC CONSTRUCTION & ENGINEERING SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 130477 | San Jose ES | GLAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-04-30 | 120714S00036 | 14ME0091 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-03 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130620 | San Juan ES | MALUNGON | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4090835.14 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 120714S00072 | 14ME0070 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-02 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 208040 | Segafu Esgapo PS | GLAN | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 4B | 3629480.3479 |  |  | Reverted | 0
NC 2014 | K10 (2014) | Region XII | Sarangani | 208028 | Severino Ibon, Sr. PS | GLAN | 0 | 1 | 2 | 1STY1CL | 2014 K10 BATCH 3 | 2114895.9906 |  |  | COMPLETED | 1 | 2015-04-22 | 2015-04-22 | 120714S00111 | 14ME0184 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130496 | Severo Inong (Kapate) ES | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1883498.7405 |  |  | COMPLETED | 1 | 2015-05-02 | 2015-05-02 | 120714S00090 | 14ME0182 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130479 | Small Margus ES | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1908623.7405 |  |  | COMPLETED | 1 | 2015-05-02 | 2015-09-02 | 120714S00092 | 14ME0179 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | CS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130437 | Sofan ES | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1 | 2014-12-11 | 2014-12-11 | 120714S00026 | 14ME0107 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-12 | N. CONGSON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130508 | Tablao ES | KIAMBA | 0 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3990835.14 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-29 | 120714S00005 | 14ME0082 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 208024 | Tabotong PS | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-28 |  | 120714S00079 | 14ME0113 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130622 | Taclobo ES | MALUNGON | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-01-20 | 2015-05-12 | 120714S00070 | 14ME0058 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-12 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 316637 | Tagaytay Integrated School | ALABEL (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1242329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 130509 | Tamadang ES | KIAMBA | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-29 | 120714S00006 | 14ME0082 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130481 | Tamala ES | GLAN | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3115174.43 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-03-23 | 120714S00037 | 14ME0091 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-10-03 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130482 | Tampus IS | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 208036 | Tandawanan ES | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-04-15 | 120714S00085 | 14ME0071 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-21 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 316630 | Tangali IS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2120417.57 |  |  | COMPLETED | 1 | 2015-03-21 | 2015-03-21 | 120714S00064 | 14ME0118 | 2014-07-20 | 2014-07-21 | 2014-10-28 | 2014-11-07 | 2014-11-20 | VERTICAL BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130483 | Tangan Integrated School | GLAN | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1107697.9953 |  |  | COMPLETED | 1 | 2015-05-22 | 2015-11-03 | 120714S00091 | 14ME0177 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | VERGUZ CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sarangani | 130544 | Ticulab ES | MAITUM | 0 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-04 | 120714S00022 | 14ME0059 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130568 | Tuyan ES | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1808123.7405 |  |  | COMPLETED | 1 | 2015-05-02 | 2015-05-02 | 120714S00107 | 14ME0183 | 2014-11-30 | 2014-12-16 | 2014-12-16 | 2014-12-23 | 2015-02-16 | SHEPPERD CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sarangani | 130440 | Upper Alabel ES | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-17 | 120714S00027 | 14ME0078 | 2014-07-20 | 2014-07-21 | 2014-09-30 | 2014-10-14 | 2014-10-31 | LAWRENCE ERIC CONSTRUCTION & ENGINEERING SERVICES
NC 2014 | K10 (2014) | Region XII | Sarangani | 316621 | Upper Lumabat IS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region XII | Sarangani | 316633 | Wali IS | MAITUM | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-05-04 | 120714S00048 | 14ME0059 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-14 | 2014-10-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sarangani | 130485 | Young ES | GLAN | 0 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2015-03-05 | 120714S00040 | 14ME0104 | 2014-07-20 | 2014-07-21 | 2014-08-04 | 2014-08-18 | 2014-09-16 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130851 | Albagan ES | TAMPAKAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-03-10 | 120614S00072 | 14MB0060 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-30 | 2014-10-21 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130899 | Benigno S. Aquino ES | TUPI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1252329.12 |  |  | COMPLETED | 1 | 2015-01-23 | 2015-01-05 | 120614S00069 | 14MB0064 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-01 | 2014-10-20 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130721 | Dole Cannery CES | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-24 | 2015-02-24 | 120614S00078 | 14MB0075 | 2014-08-12 | 2014-07-31 | 2014-08-12 | 2014-09-19 | 2014-11-06 | TRIPLE Z MERCHANDISING AND ELECTRICAL SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130856 | Escobillo ES | TAMPAKAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-03 | 2015-02-23 | 120614S00071 | 14MB0061 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-02 | 2014-09-29 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208500 | Glandang PS | TUPI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-03-31 | 120614S00050 | 14MB0068 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-01 | 2014-10-20 | MFN BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130739 | Jose Natividad Jr. ES | POLOMOLOK | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2015-02-18 | 120614S00077 | 14MB0058 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-03 | 2014-10-09 | FREDEN CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130740 | Juan Bayan ES | POLOMOLOK | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2015-03-03 | 120614S00076 | 14MB0059 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-18 | 2014-10-10 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304564 | Kablon NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | [5 empty] | 2014-07-30 |  | 2014-09-25 | KEVIN YOSHI BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130903 | Kalkam ES | TUPI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-11 | 2015-01-31 | 120614S00068 | 14MB0065 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-10-07 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130859 | Lambayong ES | TAMPAKAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-29 | 2015-02-06 | 120614S00070 | 14MB0062 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-27 | 2014-09-25 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130742 | LR Morandante ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-03-16 | 120614S00075 | 14MB0048 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-03 | 2014-11-05 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130905 | Lunen ES | TUPI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2015-03-09 | 120614S00067 | 14MB0066 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-10-10 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304556 | Maltana NHS | TAMPAKAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | [5 empty] | 2014-07-30 |  | 2014-10-30 | FUENTABUILT CONST. CORP.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130906 | Miasong ES | TUPI | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2015-04-30 | 120614S00066 | 14MB0067 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-08-29 | 2014-10-21 | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304559 | Poblacion Polomolok NHS | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-24 | [5 empty] | 2014-08-12 |  | 2014-10-21 | REYDAN BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130745 | Polomolok CES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2015-02-15 | 120614S00074 | 14MB0051 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-02 | 2014-09-25 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-31 | [5 empty] | 2014-08-12 |  | 2014-11-12 | ROCKSTONE CONST SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304567 | Silway 8 NHS | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-26 | [5 empty] | 2014-08-12 |  | 2014-11-20 | MFN BULDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130750 | Viray-Lising ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-02-15 | 120614S00073 | 14MB0049 | 2014-07-29 | 2014-07-17 | 2014-07-30 | 2014-09-01 | 2014-10-21 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130639 | Aida B. Gonzales ES (Libas ES) | BANGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-15 | 120614S00056 | 14MG0034-005 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-09-03 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130764 | B. Magan ES | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 120614S00103 | 14MG0037-002 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-08-20 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208501 | Balnabo PS | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-03-02 | 120614S00082 | 14MG0044-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-11-17 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130799 | Basag PS | T'BOLI | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 4B | 4755568.2979 |  |  | COMPLETED | 1 | 2016-06-10 | [5 empty] | 2015-12-07 |  | 2016-01-06 | REYDAN BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130801 | Bianan ES | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00106 | 14MG0043-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-23 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316713 | Colongulo NHS - Libertad NHS Annex | SURALLAH | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-24 | [5 empty] | 2014-07-21 |  | 2014-08-20 | Cofejok Const. & Supply Corp.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208503 | Coong ES | T'BOLI | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3222746.69 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-05-27 | 120614S00081 | 14MG0044-003 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-11-27 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130806 | Datal Bob ES | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00107 | 14MG0043-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-23 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130808 | Datal Nabong PS | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-11-01 | 2015-04-15 | 120614S00034 | 14MG0039-004 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-27 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130663 | Denlag ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-26 | 2015-04-15 | 120614S00052 | 14MG0039-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-27 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130811 | Desawo ES | T'BOLI | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4040835.14 |  |  | COMPLETED | 1 | 2015-05-06 | 2015-05-06 | 120614S00108 | 14MG0040-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130664 | Diente ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 120614S00093 | 14MG0046-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130870 | Dumadalig ES | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-12-28 | 120614S00086 | 14MG0031-001 | 2014-06-25 | 2014-07-18 | 2014-07-27 | 2014-08-20 | 2014-09-10 | PALMARES GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316909 | Faviola Villa-Gasis NHS - San Miguel NHS Annex | NORALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00011 | 14MG0035-003 | 2014-06-25 | 2014-07-10 | 2014-07-19 | 2014-08-17 | 2014-09-29 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130666 | Haliland ES | LAKE SEBU | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2015-04-27 | 120614S00063 | 14MG0041-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | AGUERO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130754 | J. Blanco ES | SANTO NIÑO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00095 | 14MG0035-005 | 2014-06-25 | 2014-07-08 | 2014-07-15 | 2014-08-22 | 2014-09-29 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208528 | Jose P. Lim PS | TANTANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-23 | 2015-03-23 | 120614S00018 | 14MG0032-003 | 2014-06-25 | 2014-08-05 | 2014-10-14 | 2014-11-05 | 2014-11-27 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130629 | Kataan ES | BANGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 120614S00059 | 14MG0033-001 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-03 | 2014-09-09 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130816 | Kebuling PS | T'BOLI | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4080835.14 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-05-26 | 120614S00051 | 14MG0054 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208519 | Kiantay ES | SURALLAH | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2014-12-24 | 2015-02-20 | 120614S00020 | 14MG0036-003 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130770 | L. T. Morales ES | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 120614S00104 | 14MG0037-003 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-08-20 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130817 | Lacag ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-10-21 | 120614S00080 | 14MG0040-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | [5 empty] | 2014-07-21 |  | 2014-07-21 | ILBI CONST. SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316919 | Lake Soluton Integrated HS | LAKE SEBU | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-14 | [5 empty] | 2014-07-21 |  | 2014-08-20 | ILBI CONST. SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130819 | Lambangan ES | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2015-01-15 | 120614S00094 | 14MG0042-003 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130820 | Lambuling ES | T'BOLI | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3132746.69 |  |  | COMPLETED | 1 | 2015-03-27 | 2015-03-27 | 120614S00100 | 14MG0042-004 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130673 | Lamcade ES | LAKE SEBU | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3900805.49 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-05-27 | 120614S00065 | 14MG0046-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130821 | Lamhako ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-16 | 2015-01-16 | 120614S00092 | 14MG0042-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130633 | Lampari ES | BANGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-01-31 | 120614S00058 | 14MG0033-002 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-04 | 2014-09-09 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130824 | Lamsalome ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-02-15 | 120614S00091 | 14MG0042-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-22 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130634 | Lamtabong ES | BANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-12-15 | 120614S00057 | 14MG0033-003 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-09-09 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208529 | Lembotu PS | LAKE SEBU | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4100835.14 |  |  | COMPLETED | 1 | 2015-04-03 | 2015-04-03 | 120614S00017 | 14MG0052 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130676 | Lemlunay ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-19 | 120614S00096 | 14MG0045-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-12-01 | MARBEL DYNAMIC BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6439064.7656 |  |  | COMPLETED | 1 | [6 empty] | 2015-03-05 |  | 2015-04-17 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130652 | Little Baguio ES | BANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-12-28 | 120614S00055 | 14MG0034-004 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-09-03 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208515 | Lower Tinago ES | NORALA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-16 | 2015-01-16 | 120614S00036 | 14MG0035-002 | 2014-06-25 | 2014-07-08 | 2014-07-18 | 2014-08-17 | 2014-09-29 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130873 | Luayan ES | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-12-28 | 120614S00085 | 14MG0031-002 | 2014-06-25 | 2014-07-08 | 2014-07-16 | 2014-08-16 | 2014-09-10 | PALMARES GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208508 | Lubol ES | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-04 | 2015-01-15 | 120614S00102 | 14MG0036-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316917 | Lubol Integrated HS | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-04 | [5 empty] | 2014-07-21 |  | 2014-08-20 | Cofejok Const. & Supply Corp.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130829 | Lugan CES | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-28 | 120614S00090 | 14MG0039-003 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-27 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316921 | Lusok Integrated HS | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-07 | [5 empty] | 2014-07-21 |  | 2014-09-23 | LTB BUILDERS & CONST
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130831 | Maan ES | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-03-02 | 120614S00089 | 14MG0044-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-11-27 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130779 | Mabini ES | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 120614S00105 | 14MG0037-001 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-06 | 2014-08-20 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130653 | Malaya ES | BANGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-29 | 2015-01-15 | 120614S00054 | 14MG0034-001 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-04 | 2014-09-03 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130654 | Malaya-A ES | BANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-18 | 2014-12-15 | 120614S00053 | 14MG0034-002 | 2014-06-10 | 2014-06-21 | 2014-07-23 | 2014-08-04 | 2014-09-03 | MIGO CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316912 | Mangilala Integrated HS | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 120614S00009 | 14MG0032-004 | 2014-06-25 | 2014-10-24 | 2014-10-24 | 2014-11-05 | 2014-11-27 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316916 | Naci Integrated HS | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 120614S00006 | 14MG0037-005 | 2014-06-10 | 2014-06-23 | 2014-07-23 | 2014-08-06 | 2014-08-20 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130681 | Odos Angkoy ES | LAKE SEBU | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 1 | 3800805.49 |  |  | COMPLETED | 1 | 2015-06-25 | 2015-06-29 | 120614S00097 | 14MG0045-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-12-01 | MARBEL DYNAMIC BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208523 | Paglaum ES | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2015-01-31 | 120614S00019 | 14MG0031-004 | 2014-06-25 | 2014-07-05 | 2014-07-14 | 2014-08-15 | 2014-09-10 | PALMARES GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130837 | Pandian ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-01-22 | 2015-01-22 | 120614S00088 | 14MG0043-004 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-09-23 | LTB BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130682 | Proper Ned ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2110417.57 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-05-31 | 120614S00098 | 14MG0047-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2015-01-14 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316920 | Pulo Subong Integrated HS | LAKE SEBU | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-04-17 | [5 empty] | 2014-12-17 |  | 2015-01-14 | ILBI CONST. SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316915 | Rang-ay Integrated HS | BANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-18 | [5 empty] | 2014-07-23 |  | 2014-09-10 | MIGO CONST.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208530 | Salabanog ES | T'BOLI | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 3015174.43 |  |  | COMPLETED | 1 | 2015-03-24 | 2015-07-15 | 120614S00016 | 14MG0051 | 2014-06-25 | 2014-07-15 | 2014-07-26 | 2014-08-25 | 2014-09-29 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130840 | Salacafe ES | T'BOLI | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2015-04-15 | 120614S00087 | 14MG0039-001 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-27 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316703 | San Jose NHS | BANGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-17 | [5 empty] | 2014-07-23 |  | 2014-09-09 | ROCKSTONE CONST SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 304568 | Sto. Niño NHS | SANTO NIÑO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-15 | [5 empty] | 2014-07-31 |  | 2014-09-29 | ILBI CONST. SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130684 | Sungan CES | LAKE SEBU | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2015-04-17 | 2015-05-04 | 120614S00099 | 14MG0047-002 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2015-01-14 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316701 | Surallah NHS | SURALLAH | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-04 | [5 empty] | 2014-07-21 |  | 2014-08-20 | YAP MABUHAY ENT.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130883 | Tacub ES | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 120614S00084 | 14MG0032-001 | 2014-06-25 | 2014-08-05 | 2014-10-14 | 2014-11-05 | 2014-11-27 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316910 | Tacub Integrated HS | TANTANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 120614S00010 | 14MG0032-002 | 2014-06-25 | 2014-08-05 | 2014-10-14 | 2014-10-25 | 2014-11-27 | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316918 | Talisay Integrated HS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-14 | [5 empty] | 2014-07-21 |  | 2014-08-20 | ILBI CONST. SUPPLY
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130690 | T'boyung ES | LAKE SEBU | 2 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3282746.69 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-05-25 | 120614S00109 | 14MG0053 | 2014-06-25 | 2014-07-04 | 2014-07-21 | 2014-07-25 | 2014-08-20 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 208531 | Tuburan ES | LAKE SEBU | 2 | 1 | 6 | 1STY 3CL | 2014 K10 BATCH 4B | 5481656.248 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-07 |  | 2016-01-06 | REYDAN BUILDERS
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130717 | Upper Lamungkot ES | NORALA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-07 | 2014-12-07 | 120614S00101 | 14MG0035-001 | 2014-06-25 | 2014-07-16 | 2014-07-24 | 2014-08-11 | 2014-09-29 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region XII | South Cotabato | 316725 | Upper Maculan NHS - Lake Sebu NHS Annex | LAKE SEBU | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4835592 |  |  | COMPLETED | 1 | 2015-05-29 | [5 empty] | 2014-07-21 |  | 2014-09-22 | AGEURO CONST.
NC 2014 | K10 (2014) | Region XII | South Cotabato | 130886 | Upper Tantangan ES | TANTANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 120614S00083 | 14MG0031-003 | 2014-06-25 | 2014-07-07 | 2014-07-18 | 2014-08-19 | 2014-09-10 | PALMARES GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130956 | Balisan PS | COLUMBIO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2044417.57 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 120514S00023 | 14MF0017 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209029 | Baumol ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3504886.575 |  |  | COMPLETED | 1 | 2015-12-27 | 2016-03-22 |  |  | 2015-07-06 | 2015-07-17 | 2015-07-20 | 2015-08-14 | 2015-08-19 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131145 | Bayasong ES | LUTAYAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2887174.43 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00069 | 14MF0015 | 2014-06-25 | 2014-07-30 | 2014-08-11 | 2014-08-25 | 2014-09-12 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131207 | Bayawa ES | PRESIDENT QUIRINO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-01-03 | 120514S00039 | 14MF0011 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130969 | Datablao ES | COLUMBIO | 1 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4913592 |  |  | COMPLETED | 1 | 2015-01-03 | 2014-12-31 | 120514S00056 | 14MF0017 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131172 | Isuko Elementary | PALIMBANG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2083417.57 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-05-31 | 120514S00036 | 14MH0105 | 2014-07-22 | 2014-07-31 | 2014-09-30 | 2014-10-04 | 2014-10-20 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131173 | Kalibuhan ES | PALIMBANG | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4100835.14 |  |  | COMPLETED | 1 | 2014-12-13 | 2015-07-31 | 120514S00037 | 14MH0104 | 2014-07-22 | 2014-07-31 | 2014-08-12 | 2014-08-16 | 2014-09-09 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131091 | Katitisan ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1982417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00064 | 14MF0012 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-24 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131023 | Lagandang ES | ISULAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1114329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-10-22 | 120514S00062 | 14MF0014 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130970 | Lam-alis ES | COLUMBIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1130329.12 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120514S00057 | 14MF0018 | 2014-06-25 | 2014-09-03 | 2014-09-15 | 2014-10-08 | 2014-10-24 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131197 | Lamasan Elementary school | PRESIDENT QUIRINO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1106329.12 |  |  | COMPLETED | 1 | 2015-01-03 | 2014-12-19 | 120514S00038 | 14MF0011 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131093 | Lilit ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00065 | 14MF0012 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304607 | Madanding NHS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 |  |  | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | Cofejok Const. & Supply Corp.
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130959 | Makat ES | COLUMBIO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120514S00070 | 14MF0018 | 2014-06-25 | 2014-09-03 | 2014-09-15 | 2014-10-08 | 2014-10-24 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304608 | Maligaya NHS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1838740.174 |  |  | COMPLETED | 1 | 2015-11-23 | 2015-11-23 |  |  | 2015-07-06 | 1900-01-01 | 2015-07-20 | 2015-08-14 | 2015-08-19 | DELLOSA DESIGN-BUILD SERVICES
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131151 | Mamali Elementary Scholl | LUTAYAN | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3972835.14 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00022 | 14MF0015 | 2014-06-25 | 2014-07-30 | 2014-08-11 | 2014-08-27 | 2014-09-12 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131100 | Mamali ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00066 | 14MF0012 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131026 | Mapantig ES | ISULAN (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-22 | 2014-10-22 | 120514S00053 | 14MF0014 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131101 | Midtapok ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00067 | 14MF0013 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130976 | New Bantangan ES | COLUMBIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1111329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 120514S00058 | 14MF0019 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130977 | Old Bantangan ES | COLUMBIO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2016417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 120514S00059 | 14MF0019 | 2014-06-25 | 2014-09-03 | 2014-09-15 | 2014-10-08 | 2014-10-24 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131104 | Pimbalayan ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1988417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00068 | 14MF0013 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130963 | Polomolok ES | COLUMBIO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2959174.43 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120514S00054 | 14MF0018 | 2014-06-25 | 2014-09-03 | 2014-09-15 | 2014-10-08 | 2014-10-24 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304618 | Pres. Quirino NHS - C. Mangilala HS | PRESIDENT QUIRINO | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2883174.43 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00041 | 14MF0011 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131158 | R. Lacamento PS | LUTAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1982417.57 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00044 | 14MF0016 | 2014-06-25 | 2014-07-30 | 2014-08-11 | 2014-09-08 | 2014-09-19 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131159 | Sampao ES | LUTAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1844740.174 |  |  | COMPLETED | 1 | 2015-12-07 | 2016-07-31 |  |  | 2015-07-06 | 2015-07-17 | 2015-07-20 | 2015-08-14 | 2015-08-19 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130979 | Sinapulan PS | COLUMBIO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1996417.57 |  |  | COMPLETED | 1 | 2015-03-14 | 2015-03-14 | 120514S00060 | 14MF0018 | 2014-06-25 | 2014-09-03 | 2014-09-15 | 2014-10-08 | 2014-10-24 | BETTER WORK CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131160 | Sisiman ES | LUTAYAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2891174.43 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00063 | 14MF0016 | 2014-06-25 | 2014-07-30 | 2014-08-11 | 2014-09-08 | 2014-09-19 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131163 | Tananzang ES | LUTAYAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1984417.57 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 120514S00061 | 14MF0016 | 2014-06-25 | 2014-07-30 | 2014-08-11 | 2014-09-08 | 2014-09-19 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130980 | Telafas ES | COLUMBIO | 1 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3940835.14 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 120514S00071 | 14MF0019 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 316806 | Telafas NHS - Datalblao NHS Annex | COLUMBIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1128329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 120514S00052 | 14MF0019 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130968 | Upper Lomoyon ES | COLUMBIO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-01-03 | 2014-12-31 | 120514S00055 | 14MF0017 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131107 | Zeneben ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1982417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-04 | 120514S00042 | 14MF0013 | 2014-06-25 | 2014-07-03 | 2014-07-15 | 2014-07-26 | 2014-07-31 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209037 | Abang PS | ESPERANZA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2066417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2016-07-01 | 120514S00082 | 14MH0110 | 2014-07-22 | 2014-07-31 | 2014-08-12 | 2014-08-16 | 2014-09-09 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131119 | Adalla PS | LEBAK | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2931174.43 |  |  | COMPLETED | 1 | 2015-01-24 |  | 120514S00045 | 14MH0053 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131030 | Artemio L. Martin ES (Obial ES) | KALAMANSIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1 | 2015-01-03 | 2015-07-15 | 120514S00007 | 14MH0063 | 2014-06-17 | 2014-06-19 | 2014-09-09 | 2014-09-12 | 2014-09-29 | BRE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130931 | Bacalto PS | BAGUMBAYAN | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4128835.14 |  |  | COMPLETED | 1 | 2014-12-27 | 2015-01-31 | 120514S00047 | 14MH0075 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | CURVE-LINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131049 | Balite ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2986174.43 |  |  | COMPLETED | 1 | 2015-01-03 | 2014-12-31 | 120514S00032 | 14MH0068 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131068 | Banali ES | SEN. NINOY AQUINO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1121329.12 |  |  | COMPLETED | 1 | 2014-11-11 | 2014-12-15 | 120514S00011 | 14MH0067 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131166 | Baranayan PS | PALIMBANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 120514S00100 | 14MH0099 | 2014-06-17 | 2014-06-26 | 2014-09-30 | 2014-10-04 | 2014-10-20 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131069 | Basag Elementary School | SEN. NINOY AQUINO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1133329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2015-01-15 | 120514S00017 | 14MH0066 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 316803 | Biwang HS (Bagumbayan NHS ( Biwang Annex)) | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1982417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-31 |  |  | 2014-06-11 | 2014-07-26 | 2014-07-10 | 2014-07-17 | 2014-08-08 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209034 | Bongo-Bongo PS | ESPERANZA | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4112835.14 |  |  | COMPLETED | 1 | 2015-02-11 |  | 120514S00107 | 14MH0109 | 2014-07-22 | 2014-07-31 | 2014-08-12 | 2014-08-16 | 2014-09-09 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131051 | Bugso ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-12-06 | 2015-01-15 | 120514S00031 | 14MH0071 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | ROBETH GEN. MDSE. CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131120 | Bululawan ES | LEBAK | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2017417.57 |  |  | COMPLETED | 1 | 2014-12-10 |  | 120514S00085 | 14MH0040 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130932 | Campo 3 ES | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2975174.43 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-02-25 | 120514S00048 | 14MH0082 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131110 | Christianuevo ES | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1104329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-12-03 | 120514S00028 | 14MH0048 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130936 | Dante ES | BAGUMBAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1124329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2015-05-26 | 120514S00049 | 14MH0077 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | CURVE-LINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130981 | Dapulan ES | ESPERANZA | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3604886.575 |  |  | COMPLETED | 1 | 2016-03-26 |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209038 | Datu Etang Primary School | KALAMANSIG | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4996592 |  |  | COMPLETED | 1 | 2015-01-06 | 2015-04-25 | 120514S00073 | 14MH0055 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130924 | Dawing ES | BAGUMBAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2015-01-15 | 120514S00043 | 14MH0079 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131122 | Dimapitan ES | LEBAK | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2024417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2015-06-30 | 120514S00117 | 14MH0043 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131112 | Don M. Concha MES (Taguisa ES) | LEBAK | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-23 | 120514S00046 | 14MH0051 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131034 | DON MODESTO BUENAFLOR SR. ELEMENTARY SCHOOL | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 120514S00006 | 14MH0059 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131170 | Dumolol E/S | PALIMBANG | 2 | 1 | 7 | 1STY3CL & 2 units 1STY2CL | 2014 K10 BATCH 1 | 6926009.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-15 | 120514S00099 | 14MH0101 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | SOPHIA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304586 | E. Arcano Mem. NHS (Basak NHS) | LEBAK | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2887174.43 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-22 |  |  | 2016-06-11 | 2014-07-19 | 2014-07-08 | 2014-07-16 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130983 | Esperanza CS | ESPERANZA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2879174.43 |  |  | COMPLETED | 1 | 2014-12-12 | 2016-03-04 | 120514S00013 | 14MH0091 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | B.C. CUERPO CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304589 | Esperanza NHS | ESPERANZA | 2 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 3 | 15277538.9062 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-10-01 |  |  | 2014-11-26 | 2014-12-04 | 2014-12-16 | 2014-12-18 | 2015-01-12 | SOPHIA CONST. SUPPLY/THREE BUILDERS, INC.
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131135 | Gestosani Mem. ES | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1110329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2015-05-31 | 120514S00109 | 14MH0046 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131136 | Guintales PS | LEBAK | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-25 | 120514S00101 | 14MH0039 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131041 | Hinalaan ES | KALAMANSIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-01-15 | 120514S00002 | 14MH0056 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209033 | Kabanalian PS | ESPERANZA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2013417.57 |  |  | COMPLETED | 1 | 2014-11-12 | 2015-01-15 | 120514S00108 | 14MH0088 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209035 | Kanalan PS | ESPERANZA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2073417.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-06-30 | 120514S00098 | 14MH0089 | 2014-06-17 | 2014-06-26 | 2014-08-26 | 2014-08-30 | 2014-09-15 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131174 | Kanipaan ES | PALIMBANG | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4933592 |  |  | COMPLETED | 1 | 2015-01-11 | 2016-07-01 | 120514S00102 | 14MH0093 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | MINROCK MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131175 | Kilbog ES | PALIMBANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1135329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-07-31 | 120514S00096 | 14MH0112 | 2014-07-22 | 2014-07-31 | 2014-09-30 | 2014-10-04 | 2014-10-20 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130940 | Kipuso PS | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2048417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-01-23 | 120514S00050 | 14MH0081 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131055 | Kuden ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2973174.43 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-31 | 120514S00030 | 14MH0069 | 2014-06-17 | 2014-06-19 | 2014-10-07 | 2014-10-11 | 2014-10-30 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131178 | Langali PS | PALIMBANG | 2 | 1 | 6 | 1STY 3CL | 2014 K10 BATCH 1 | 5874348.86 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-03-31 | 120514S00105 | 14MH0096 | 2014-06-17 | 2014-06-26 | 2014-09-09 | 2014-09-13 | 2014-09-23 | CS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304604 | Lebak NHS - Annex Keytodac HS | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1129329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2016-06-30 |  |  | 2016-06-11 | 2014-07-19 | 2014-07-08 | 2014-07-16 | 2014-08-06 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130984 | Legodon ES | ESPERANZA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2967174.43 |  |  | COMPLETED | 1 | 2014-12-27 | 2015-05-03 | 120514S00012 | 14MH0087 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131042 | Limulan ES | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-03 | 2014-12-31 | 120514S00005 | 14MH0057 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131184 | Lupoken ES (Wal PS) | PALIMBANG | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4912592 |  |  | COMPLETED | 1 | 2015-01-11 | 2015-05-31 | 120514S00115 | 14MH0097 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209039 | Maat PS | KALAMANSIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2942174.43 |  |  | COMPLETED | 1 | 2015-05-19 | 2015-05-15 | 120514S00074 | 14MH0113 | 2014-07-22 | 2014-07-31 | 2014-09-30 | 2014-10-04 | 2014-10-30 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131179 | Maganao PS | PALIMBANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2026417.57 |  |  | COMPLETED | 1 | 2014-12-22 | 2015-05-15 | 120514S00111 | 14MH0102 | 2014-06-17 | 2014-06-26 | 2014-09-09 | 2014-09-13 | 2014-09-23 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131189 | Malisbong ES | PALIMBANG | 2 | 1 | 6 | 1STY 3CL | 2014 K10 BATCH 1 | 5816348.86 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-01-31 | 120514S00114 | 14MH0098 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130985 | Manirub CS | ESPERANZA | 2 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4871592 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-05-28 | 120514S00010 | 14MH0092 | 2014-06-17 | 2014-06-26 | 2014-09-09 | 2014-09-13 | 2014-09-29 | BRE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130943 | Masiag ES | BAGUMBAYAN | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4060835.14 |  |  | COMPLETED | 1 | 2014-12-03 | 2014-12-31 | 120514S00051 | 14MH0080 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131077 | Matanao ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2972174.43 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-06-15 | 120514S00025 | 14MH0107 | 2014-07-22 | 2014-07-31 | 2014-09-30 | 2014-10-04 | 2014-10-20 | FPJ CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131035 | Minorok ES | KALAMANSIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2921174.43 |  |  | COMPLETED | 1 | 2015-04-16 | 2015-05-15 | 120514S00004 | 14MH0062 | 2014-06-17 | 2014-06-19 | 2014-10-07 | 2014-10-11 | 2014-10-27 | C.A. BETALAC CONSTRUCTION & GEN. MDSE.
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131043 | Nalilidan PS | KALAMANSIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-11-30 | 120514S00026 | 14MH0064 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131113 | Nuling ES | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-12-05 | 120514S00021 | 14MH0050 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131044 | Pag-asa ES | KALAMANSIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-11-19 | 2014-12-15 | 120514S00033 | 14MH0060 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131134 | Pakil MES (Barurao ES) | LEBAK | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1986417.57 |  |  | COMPLETED | 1 | 2014-12-25 | 2014-12-22 | 120514S00103 | 14MH0052 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131182 | Palimbang CS | PALIMBANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1113329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2015-01-15 | 120514S00116 | 14MH0103 | 2014-06-17 | 2014-06-26 | 2014-09-30 | 2014-10-04 | 2014-10-20 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130989 | Pamantingan ES | ESPERANZA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2913174.43 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-31 | 120514S00016 | 14MH0086 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131079 | Pinandian ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2977174.43 |  |  | COMPLETED | 1 | 2015-03-25 | 2015-05-31 | 120514S00034 | 14MH0108 | 2014-07-22 | 2014-07-31 | 2014-09-30 | 2014-10-04 | 2014-10-20 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209004 | Plamango ES (transfer from Kalamansig II, St. Andrew B) | ESPERANZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1144329.12 |  |  | COMPLETED | 1 | 2014-12-13 | 2015-06-30 | 120514S00112 | 14MH0111 | 2014-07-22 | 2014-07-31 | 2014-08-12 | 2014-08-16 | 2014-09-09 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131060 | Rajah Muda ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2022417.57 |  |  | COMPLETED | 1 | 2015-01-12 | 2015-01-15 | 120514S00029 | 14MH0106 | 2014-07-22 | 2014-07-31 | 2014-08-12 | 2014-08-16 | 2014-09-09 | CS CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131128 | S.A. Balabagan ES | LEBAK | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2017417.57 |  |  | COMPLETED | 1 | 2014-12-04 | 2014-12-31 | 120514S00104 | 14MH0042 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 304621 | Salabaca NHS | ESPERANZA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-12-31 | 120514S00077 | 14MH0090 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | JARGON CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130992 | Salumping ES | ESPERANZA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2957174.43 |  |  | COMPLETED | 1 | 2015-02-18 | 2015-11-15 | 120514S00009 | 14MH0084 | 2014-06-17 | 2014-06-26 | 2014-08-19 | 2014-08-23 | 2014-09-15 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131192 | San Roque ES | PALIMBANG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2903174.43 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-15 | 120514S00113 | 14MH0095 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | SOPHIA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130948 | Santo Nino ES | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-05-31 | 120514S00097 | 14MH0074 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | CURVE-LINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131064 | Sewod ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2037417.57 |  |  | COMPLETED | 1 | 2014-12-05 | 2015-01-31 | 120514S00024 | 14MH0072 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130927 | South Sepaka ES | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-02-05 | 120514S00035 | 14MH0083 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131037 | Sta. Maria ES | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-19 | 2014-12-31 | 120514S00003 | 14MH0058 | 2014-06-17 | 2014-06-19 | 2014-07-17 | 2014-07-21 | 2014-08-15 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130993 | Sultan Sinanggayan ES | ESPERANZA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2003417.57 |  |  | COMPLETED | 1 | 2014-11-12 | 2014-12-31 | 120514S00008 | 14MH0085 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130953 | Sumilil ES | BAGUMBAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1134329.12 |  |  | COMPLETED | 1 | 2014-11-11 | 2015-01-15 | 120514S00015 | 14MH0078 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131038 | T Patalinghug (Cadiz ES) | KALAMANSIG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2893174.43 |  |  | COMPLETED | 1 | 2015-01-24 | 2014-12-31 | 120514S00001 | 14MH0061 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131080 | Tacupis ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2977174.43 |  |  | COMPLETED | 1 | 2015-01-09 | 2015-02-28 | 120514S00072 | 14MH0065 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131116 | Tapudi ES | LEBAK | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4054835.14 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-25 | 120514S00020 | 14MH0041 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131130 | Tibong-tibong PS | LEBAK | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2029417.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-07-31 | 120514S00095 | 14MH0054 | 2014-06-17 | 2014-06-19 | 2014-08-19 | 2014-08-23 | 2014-09-15 | STONELINE CONSTRUCTION
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131065 | Tinalon ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2986174.43 |  |  | COMPLETED | 1 | 2014-12-10 | 2015-01-15 | 120514S00027 | 14MH0070 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131117 | Tinonggos ES | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1130329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-30 | 120514S00018 | 14MH0045 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 131118 | Tran ES | LEBAK | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1098329.12 |  |  | COMPLETED | 1 | 2014-11-10 | 2014-11-30 | 120514S00019 | 14MH0047 | 2014-06-17 | 2014-06-19 | 2014-07-08 | 2014-07-12 | 2014-08-06 | JV CONSTECH
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 130955 | Tulale ES | BAGUMBAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1129329.12 |  |  | COMPLETED | 1 | 2014-12-25 | 2015-07-15 | 120514S00014 | 14MH0076 | 2014-06-17 | 2014-06-26 | 2014-09-30 | 2014-10-04 | 2014-10-20 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209013 | Wal PS | PALIMBANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2013417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-06-30 | 120514S00110 | 14MH0094 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Sultan Kudarat | 209011 | Wasag PS | PALIMBANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2014-11-12 | 2015-05-15 | 120514S00106 | 14MH0100 | 2014-06-17 | 2014-06-26 | 2014-07-10 | 2014-07-14 | 2014-08-08 | M.K. GUIAMANO MULTI-BUILDERS
NC 2014 | K10 (2014) | Region XII | Tacurong City | 326102 | San Emmanuel National High School-Annex | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 120514S00079 | 14MF0010 | 2014-07-01 | 2014-07-14 | 2014-07-15 | 2014-07-28 | 2014-07-31 | COFEJOK CONSTRUCTION AND SUPPLY CORPORATION (FORME
NC 2014 | K10 (2014) | Region XII | Tacurong City | 326101 | Upper Katungal National High School-TNHS Annex | CITY OF TACURONG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | General Santos City | 304636 | A.G. Busano, Sr. HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131282 | Arizala ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1 | [7 empty] | 2015-11-17 | 2015-12-10 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | K10 (2015) | Region XII | General Santos City | 131299 | Baluan ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1 | [9 empty] | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | General Santos City | 317003 | Baluan NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [8 empty] | 2015-12-10 | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131293 | Banisil Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 15121327.92 |  |  | COMPLETED | 1 | [7 empty] | 2015-12-23 | 2015-01-19 | F.H. GOPITEO CONST. AND SUPPLY
NC 2015 | SHS (2015) | Region XII | General Santos City | 304643 | Banisil National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | FREDEN CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | General Santos City | 304644 | Bawing NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  |  | VERTICAL BUILDERS
NC 2015 | SHS (2015) | Region XII | General Santos City | 304638 | Buayan NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | J.G. ORANZA CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304639 | Bula National School of Fisheries | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-s-00090 |  |  |  | 2015-11-12 |  |  | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | TECHVOC (2015) | Region XII | General Santos City | 304639 | Bula National School of Fisheries | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 | [8 empty] | 2015-12-15 | VERGUZ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | General Santos City | 317005 | Dadiangas North High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 120614S00126 | 14MB0123 | 2014-12-16 | 2014-12-04 | 2014-12-16 | 2014-12-29 | 2015-02-17 | C E K CONSTRUCTION AND WATER SUPPLY
NC 2015 | SHS (2015) | Region XII | General Santos City | 304649 | Datu B. Balunto NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | General Santos City | 317004 | Elias Buscano Sr. HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [9 empty] | KEVIN YOSHI BUILDERS(FORMERLY:CON BUILDERS)
NC 2015 | SHS (2015) | Region XII | General Santos City | 304640 | Engracia L. Valdomar NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131319 | Fatima CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | COMPLETED | 1 | [7 empty] | 2015-12-29 | 2016-02-15 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | General Santos City | 304641 | Fatima NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | FUENTABUILT CONSTRUCTION CORP.
NC 2015 | TECHVOC (2015) | Region XII | General Santos City | 304641 | Fatima NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 | [9 empty] | HANNA BIA DESIGN AND CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304646 | Gen. Santos City HS - Lanton HS Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  |  | VERTICAL BUILDERS
NC 2015 | SHS (2015) | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 | [8 empty] | 2016-03-29 | F.H. GOPITEO CONST. AND SUPPLY
NC 2015 | SHS (2015) | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-29 |  | 2016-03-10 | VERTICAL BUILDERS
NC 2015 | TECHVOC (2015) | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-17 |  | 2016-03-10 | LAWRENCE ERIC
NC 2015 | SHS (2015) | Region XII | General Santos City | 304655 | GSC Nat'l. Sec. Sch. Of Arts & Trades | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 8 | 15646327.92 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-12 | 2015-12-10 |  | J.G. ORANZA CONST.
NC 2015 | TECHVOC (2015) | Region XII | General Santos City | 304655 | GSC Nat'l. Sec. Sch. Of Arts & Trades | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 210001 | GSC SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 24 | 2STY12CL | 2015 K10 BATCH 6 | 29158434.3596 |  |  | COMPLETED | 1 | [7 empty] | 2015-12-29 | 2016-03-09 | F.H. GOPITEO CONST. AND SUPPLY
NC 2015 | K10 (2015) | Region XII | General Santos City | 210001 | GSC SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | SARANGANI ROCKMIXER
NC 2015 | SHS (2015) | Region XII | General Santos City | 317001 | GSC SPED Integrated School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131296 | H.N. Cahilsot CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | COMPLETED | 1 | [8 empty] | 2015-12-10 | J.G. ORANZA CONST.
NC 2015 | K10 (2015) | Region XII | General Santos City | 210011 | H.N. Cahilsot CES II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6319337.6381 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 210004 | Habitat Community ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1 | [8 empty] | 2015-12-16 | FORTSTONE CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304648 | Irineo Santiago NHS of Metro Dadiangas (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-10 |  | 2016-05-23 | J.G. ORANZA CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304645 | Johnny Ang NHS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | J.G. ORANZA CONST.
NC 2015 | K10 (2015) | Region XII | General Santos City | 131304 | Katangawan Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12771310.093 |  |  | COMPLETED | 1 | [9 empty] | MFN BUILDERS
NC 2015 | SHS (2015) | Region XII | General Santos City | 304650 | Labangal NHS (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | [9 empty] | J.G. ORANZA CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304653 | Lagao NHS (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | [9 empty] | MFN BUILDERS
NC 2015 | SHS (2015) | Region XII | General Santos City | 304654 | Lagao NHS Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6569337.6381 |  |  | COMPLETED | 1 | [9 empty] | SARANGANI ROCKMIXER
NC 2015 | SHS (2015) | Region XII | General Santos City | 304651 | Ligaya HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131287 | New Mabuhay Eementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 | [9 empty] | LAWRENCE ERIC
NC 2015 | K10 (2015) | Region XII | General Santos City | 131287 | New Mabuhay Eementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | FFJJ CONST.
NC 2015 | TECHVOC (2015) | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | General Santos City | 317002 | Pao-Pao HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [9 empty] | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | K10 (2015) | Region XII | General Santos City | 131297 | Romana C. Acharon Central ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 24 | 2STY12CL | 2015 K10 BATCH 6 | 29158434.3596 |  |  | COMPLETED | 1 | [7 empty] | 2015-12-08 | 2015-12-29 | J.G. ORANZA CONST.
NC 2015 | K10 (2015) | Region XII | General Santos City | 131281 | Saludin Anas ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 | [9 empty] | YAP MABUHAY ENTERPRISES INCORPORATED
NC 2015 | SHS (2015) | Region XII | General Santos City | 317006 | SAMBOANG - NGILAY HIGH SCHOOL | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 2 | 3667968.78 |  |  | COMPLETED | 1 | [9 empty] | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131307 | Tinagacan ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 | [9 empty] | FUENTABUILT CONST.
NC 2015 | SHS (2015) | Region XII | General Santos City | 304637 | Tinagacan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 | [9 empty] | DELLOSA DESIGN-BUILD SERVICES
NC 2015 | K10 (2015) | Region XII | General Santos City | 131308 | Upper Labay ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | VERGUZ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | General Santos City | 131308 | Upper Labay ES | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [9 empty] | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | General Santos City | 304652 | Upper Labay HS | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 | [9 empty] | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | Kidapawan City | 304658 | Ginatilan NHS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 24 | 4STY24CL | 2015 K10 BATCH 7 | 35596257 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Kidapawan City | 304659 | Manongol NHS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Kidapawan City | 304659 | Manongol NHS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2512377.5407 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Kidapawan City | 304664 | Mt. Apo High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Kidapawan City | 131361 | Sumbac ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Koronadal City | 317201 | Bacongco NHS (Koronadal NCHS - Annex, Bacongco Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-S00070 | 15MG0049 |  | 2015-09-16 | 2015-09-29 | 2015-10-14 | 2015-10-30 | Marbel Dynamic Builders
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-S-00066 | 15MG0048 | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-15 | 2015-11-05 | Migo Const.
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304670 | Esperanza NHS | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-S00069 | 15MG0047 | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-15 | 2015-11-02 | Aguero Const.
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00068 | 15MG0073 | 2015-10-12 | 2015-10-21 | 2015-11-03 | 2015-10-12 | 2015-11-27 | Reydan Builders
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00028 | 15MG0074 | 2015-10-12 | 2015-10-21 | 2015-11-03 | 2015-10-12 | 2015-11-27 | Reydan Builders
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00007 | 15MG0044 | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-09 | 2015-10-27 | LTB Builders and Const.
NC 2015 | TECHVOC (2015) | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00181 |  |  |  | 2015-11-03 |  | 2015-11-27 | Nirvana Construction and Supplies
NC 2015 | K10 (2015) | Region XII | Koronadal City | 131394 | Marbel 1 CES | CITY OF KORONADAL (Capital) | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00120 | 15MG0075 | 2015-11-04 | 2015-11-13 | 2015-11-26 | 2015-12-11 | 2016-03-08 | AJYSC Marketing
NC 2015 | SHS (2015) | Region XII | Koronadal City | 304672 | Marbel 7 National High School | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00103 | 15MG0050 | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-09 | 2015-11-02 | AJYSC Marketing
NC 2015 | SHS (2015) | Region XII | Koronadal City | 317203 | Rotonda National High School | CITY OF KORONADAL (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00039 |  | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-16 | 2015-11-04 | Palmares Gereal Mechandise
NC 2015 | SHS (2015) | Region XII | Koronadal City | 317202 | Saravia NHS (Koronadal NCHS - Annex, Saravia Campus) | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 1206-15-S-00078 |  | 2015-09-07 | 2015-09-16 | 2015-09-29 | 2015-10-09 | 2015-10-30 | Reydan Builders
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304410 | Agriculture High School | MIDSAYAP | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0234 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304410 | Agriculture High School | MIDSAYAP | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0234 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | K.A. BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304412 | Alamada NHS | ALAMADA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8609694.261 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0118 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304413 | Aleosan NHS | ALEOSAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0134 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130181 | Arizona ES | MIDSAYAP | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0183 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129956 | Aroman ES | CARMEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0126 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-04 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129956 | Aroman ES | CARMEN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0126 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-04 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129930 | Badtucon ES | BANISILAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0201 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130316 | Bagoinged ES | PIKIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0213 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129976 | Bai Matabay Plang MPS | CARMEN | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0124 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130303 | Balabak ES | PIKIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0211 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130303 | Balabak ES | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129931 | Balindong PS | BANISILAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0202 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304421 | Bannawag HS | KABACAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0236 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | MARCUS CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316551 | Barongis HS | LIBUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0238 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130306 | Batulawan Central ES | PIKIT | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0212 | 2015-11-18 | 2015-11-25 | 2015-12-08 | 2015-12-11 | 2015-12-29 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130286 | Cabpangi ES | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0209 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130321 | Calawag ES | PIKIT | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0214 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129935 | Carugmanan ES | BANISILAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0145 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | PADER CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304430 | Dado High School | ALAMADA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0119 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130210 | Damatulan ES | MIDSAYAP | 1 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 5605184.88 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0233 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316541 | Datu Embak Mangasing Mem. HS | PIKIT | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6339337.6381 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0140 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-04 | 2015-09-15 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129999 | Datu Mantawil ES | KABACAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0184 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207542 | Datu Mantil PS | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0182 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207575 | Datu Tumindeg Sultan MES | PIKIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0169 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | K.A. BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0141 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | TECHVOC (2015) | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 | 1 | 3 | Construction of Standard Technical and Vocational Building | 2015 TVL | 7176187.99 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0222 | 2015-10-14 | 2015-10-21 | 2015-11-03 | 2015-11-06 | 2015-11-19 | BANDAR KUTAWATO CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207568 | Dimanalao ES | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0220 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | K.A. BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304435 | Dualing NHS | ALEOSAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 5-MD-0134 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316502 | Dualing NHS - Katalicanan HS Annex | ALEOSAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0237 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207522 | F. Cabrillos, Sr. PS | CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0185 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130322 | Fort Pikit ES | PIKIT | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0215 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129824 | Guiling ES | ALAMADA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0226 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130325 | Inug-ug ES | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0216 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130211 | Kadigasan ES | MIDSAYAP | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0208 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130289 | KADINGILAN ELEMENTARY SCHOOL | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15-MD-0210 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316555 | Kiaring HS | BANISILAN | 1 | 1 | 6 | 1STY6CL (Toilet Attached) | 2015 K10 BATCH 3 | 5472651.88 |  |  | COMPLETED | 1 |  |  |  | 15MD0147 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129982 | Kibayao ES | CARMEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0181 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130006 | Kilagasan ES | KABACAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0127 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130006 | Kilagasan ES | KABACAN | 1 |  | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0127 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304454 | Kimagango NHS | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0167 | 2015-08-28 | 2015-09-14 | 2015-09-17 | 2015-09-22 | 2015-10-05 | J-ONE BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304458 | Kitub-Bao NHS | ALAMADA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0132 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129939 | Kudon Elementary School | BANISILAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0203 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0102 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130214 | Lomopog ES | MIDSAYAP | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  |  | 15MD0276 | 2015-11-17 | 2015-12-04 | 2016-06-29 | 2016-08-05 | 2016-08-19 | SHERATANNOR CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130214 | Lomopog ES | MIDSAYAP | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0276 | 2015-11-17 | 2015-12-04 | 2016-06-29 | 2016-08-05 | 2016-08-19 | SHERATANNOR CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130201 | Lower Kiwanan Elementary School | MIDSAYAP | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0123 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130186 | LT. ANDRES CALUNGSUD ES | MIDSAYAP | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0120 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207539 | Lt. Tito S. Orejudos ES | ALAMADA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0198 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2005-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129964 | Macabenban ES | CARMEN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0241 | 2015-11-17 | 2015-11-24 | 2015-12-07 | 2015-12-10 | 2015-12-29 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129965 | Mainline ES | CARMEN | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  |  | 15MD0192 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129966 | Makatactac ES | CARMEN | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1 |  |  |  | 15MD0206 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130030 | Malengen ES | LIBUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0196 | 2015-10-02 | 2015-10-09 | 2015-10-22 | 2015-10-26 | 2015-11-10 | MUST ENTERPRISES
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129968 | Manili ES | CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0191 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304474 | Manuangan HS | PIGKAWAYAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  | 15MD0115 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304474 | Manuangan HS | PIGKAWAYAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  | 15MD0115 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129842 | Mapurok ES | ALAMADA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0228 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129829 | Maracabac ES | ALAMADA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0227 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129969 | Mesopa PS | CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0190 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304487 | Nicaan HS | LIBUNGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0121 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207571 | Nueva Fuerza Elementary | LIBUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0207 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | LLABAN CONST
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207520 | Nunguan ES | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0219 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-01-12 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207528 | Pagangan Annex PS | ALEOSAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0196 | 2015-10-02 | 2015-10-09 | 2015-10-22 | 2015-10-26 | 2015-11-10 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129988 | Palanggalan ES | CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0240 | 2015-11-17 | 2015-11-24 | 2015-12-07 | 2015-12-10 | 2015-12-29 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130346 | Pamalian ES | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0218 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304491 | Patindeguen HS | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1 |  |  |  | 15MD0230 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130275 | Patot ES | PIGKAWAYAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0170 | 2015-08-28 | 2015-09-04 | 2015-10-20 | 2015-10-23 | 2015-11-09 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207548 | Pidatan ES | ALAMADA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0243 | 2015-11-17 | 2015-11-24 | 2015-12-07 | 2015-12-10 | 2016-06-03 | LLABAN CONST
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0101 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | FORSTONE CONST.
NC 2015 | TECHVOC (2015) | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2469549.27 |  |  | COMPLETED | 1 |  |  |  | 15MD0221 | 2015-10-14 | 2015-10-21 | 2015-11-03 | 2015-11-06 | 2015-11-19 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316520 | Pigcawayan NHS - Libungan Torreta Annex | PIGKAWAYAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  |  | 15MD0142 | 2015-09-04 | 2015-09-11 | 2015-09-24 | 2015-09-30 | 2015-10-16 | SHERATANNOR CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130330 | Pikit CES | PIKIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0217 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304494 | Pikit NHS | PIKIT | 1 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  | 15MD0131 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316512 | Pikit NHS - Gokotan Annex | PIKIT | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  | 15MD0225 | 2015-10-14 | 2015-10-21 | 2015-11-03 | 2015-11-06 | 2015-11-19 | K.A. BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304499 | Presbitero HS | PIGKAWAYAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0135 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MUST ENTERPRISES
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129851 | Rebi ES | ALAMADA | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3912212.08 |  |  | COMPLETED | 1 |  |  |  | 15MD0229 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304501 | Salunayan HS | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0110 | 2015-07-30 | 2015-08-06 | 2015-08-19 | 2015-08-25 | 2015-09-15 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316532 | Salunayan NHS-Dabpil Sampulna Olandang HS Annex | MIDSAYAP | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 7 | 3667969 |  |  | COMPLETED | 1 |  |  |  | 15MD0225 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130003 | Sanggadong ES | KABACAN | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0186 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | MARCUS CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207570 | Satinitigan ES | PRESIDENT ROXAS | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304505 | Silik High School | PIKIT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0174 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316557 | Simone HS | KABACAN | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 3 | 4673636.82 |  |  | COMPLETED | 1 |  |  |  | 15MD0147 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | SAREX BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304506 | Simsiman HS | PIGKAWAYAN | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3484886.575 |  |  | COMPLETED | 1 |  |  |  | 15MD0116 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | SHARIFF CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304506 | Simsiman HS | PIGKAWAYAN | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  |  | 15MD0116 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | SHARIFF CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304507 | Sinawingan HS | LIBUNGAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0117 | 2015-08-06 | 2015-08-13 | 2015-08-26 | 2015-09-02 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129832 | Siya-Siya ES | ALAMADA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0171 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207527 | Tabunan ES | ALAMADA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0231 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316547 | Taguranao HS | MATALAM | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 3877212 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304508 | Takepan HS | PIKIT | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0143 | 2015-08-07 | 2015-08-14 | 2015-09-24 | 2015-09-30 | 2015-10-16 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316525 | Takepan NHS- Bulol NHS Annex | PIKIT | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1 |  |  |  | 15MD0242 | 2015-11-17 | 2015-11-24 | 2015-12-07 | 2015-12-10 | 2015-12-29 | K.A. BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207549 | Talha ES | ALAMADA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0199 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2016-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129974 | Tawagon PS | CARMEN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0188 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129852 | Tawas-Abaga Elementary School | ALAMADA | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0230 | 2015-10-23 | 2016-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129953 | Tinimbakan ES | BANISILAN | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  |  | 15MD0204 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304512 | Tubak NHS | ALEOSAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0128 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | RDEN CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207550 | Tubak Primary School Annex | ALEOSAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0200 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | J-ONE BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207569 | Tulunan ES | KABACAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0194 | 2015-10-02 | 2015-10-09 | 2015-10-22 | 2015-10-26 | 2015-11-10 | MARCUS CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207569 | Tulunan ES | KABACAN | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129954 | Tumbao ES | BANISILAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0205 | 2015-10-08 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-12 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304516 | Villarica High School | MIDSAYAP | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129955 | Wadya ES | BANISILAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0144 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | PADER CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130068 | Alibayon ES | MAGPET | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304415 | Antipas NHS | ANTIPAS | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10917342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316529 | Banayal HS -Bacong HS Annex | TULUNAN | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 7 | 3667969 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304422 | Basak NHS | MAGPET | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130349 | Batobato ES | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316554 | Binoongan HS | ARAKAN | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304423 | Bulakanon HS | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304438 | Dallag HS | ARAKAN | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6369337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130075 | Datu Celo ES | MAGPET | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129900 | Datu Ladayon ES | ARAKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2847592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8224965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304442 | F. A. Andolana Mem. NHS | ARAKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1978606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304442 | F. A. Andolana Mem. NHS | ARAKAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130148 | F. Valdevieso ES | MATALAM | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129904 | Ganatan ES | ARAKAN | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129905 | Guitawan ES | ARAKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130077 | Inac ES | MAGPET | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130240 | Inas ES | M'LANG | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130099 | Kabilaw ES | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1973606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129907 | Kapayahan PS | ARAKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130087 | Katipunan ES | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304441 | Katipunan HS | ARAKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130152 | Kibudoc ES | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129911 | Kinawayan ES | ARAKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129911 | Kinawayan ES | ARAKAN | 2 |  | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130130 | Kinilid ES | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304456 | Kisante NHS | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316519 | Kisante NHS - Batasan HS Annex | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129913 | Kulaman ES | ARAKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207529 | Kulog ES | MATALAM | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207529 | Kulog ES | MATALAM | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207573 | Langka ES | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130132 | Layangan ES | MATALAM | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207566 | Lower Saguing ES | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304486 | Luayon NHS | MAKILALA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130380 | Mabuhay ES | PRESIDENT ROXAS | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4572048.49 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130410 | Magbok ES | TULUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304463 | Magpet NHS | MAGPET | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130079 | Mahongkog ES | MAGPET | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3877212.08 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304464 | Mahongkog High School | MAGPET | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304466 | Makilala NHS | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 129888 | Malangag ES | ANTIPAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304470 | Malatab HS | ANTIPAS | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6359337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304471 | Malibatuan HS | ARAKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207562 | Migcuan ElementarySchool | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130394 | Nabundasan ES | TULUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130164 | Natutungan ES | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130102 | New Bulatukan ES | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304484 | New Israel HS | MAKILALA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6354337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130397 | New Panay (Dimakanit) ES | TULUNAN | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304490 | Pangao-an HS | MAGPET | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130415 | Paraiso ES | TULUNAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130383 | Pres. Roxas CES | PRESIDENT ROXAS | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 3 | 12771310.093 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316513 | Pres. Roxas NHS - Idaoman Annex | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304457 | Ricardo L. Ipong Mem. NHS | MAKILALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 304504 | Sibsib High School | TULUNAN | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130142 | Sta. Maria ES | MATALAM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 316530 | Sto. Niño High School | MAKILALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130067 | Timodos PS | MAGPET | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2847592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130067 | Timodos PS | MAGPET | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1983606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | MATALAM | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316521 | Aringay National High School | KABACAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304419 | Banayal HS | TULUNAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316556 | Bentangan HS | CARMEN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130012 | Buluan ES | KABACAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0187 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | SAREX BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  | 15MD0125 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  | 15MD0148 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304427 | Carmen NHS | CARMEN | 3 |  | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  | 15MD0149 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304431 | Dalapitan HS | MATALAM | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8224965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207551 | Dangleg Elementary School | KABACAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0172 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207551 | Dangleg Elementary School | KABACAN | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0172 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207546 | DILUTAN ELEMENTARY SCHOOL | KABACAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0175 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207546 | DILUTAN ELEMENTARY SCHOOL | KABACAN | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0175 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304444 | Kabacan NHS | KABACAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0130 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304462 | Lika HS | M'LANG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11077342.5917 |  |  | COMPLETED | 1 |  |  |  | 15MD0136 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | MARCUS CONST.
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304472 | Malinao HS | BANISILAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0166 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304418 | Mariano Untal HS | M'LANG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304476 | Matalam NHS, Brgy Linao | MATALAM | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304478 | Matalam NHS, Brgy Poblacion | MATALAM | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 316514 | Minapan High School | TULUNAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207547 | Mulita Elementary School | KABACAN | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  | 15MD0232 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | SHERATANNOR CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 207547 | Mulita Elementary School | KABACAN | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0232 | 2015-10-23 | 2015-10-30 | 2015-11-12 | 2015-11-17 | 2015-11-27 | SHERATANNOR CONST.
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130019 | Nangaan ES | KABACAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0189 | 2015-09-29 | 2015-10-08 | 2015-10-20 | 2015-10-23 | 2015-11-09 | SAREX BUILDERS
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130395 | New Alimodian ES | TULUNAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304488 | Nueva Vida National High School | M'LANG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  |  | 15MD0137 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304500 | Salama NHS | BANISILAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15MD0138 | 2015-08-07 | 2015-08-14 | 2015-08-27 | 2015-09-03 | 2015-09-15 | BORDERLINE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | North Cotabato | 130020 | Siento Trenta ES | KABACAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15MD0173 | 2015-08-28 | 2015-09-04 | 2015-09-17 | 2015-09-22 | 2015-10-05 | SAREX BUILDERS
NC 2015 | SHS (2015) | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8244965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208027 | Adelina Tuardon Recto PS | GLAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316634 | Alabel Central Integrated SPED Center | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304517 | Alabel Nat'l Science HS | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304518 | Alabel NHS | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304518 | Alabel NHS | ALABEL (Capital) | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304519 | Alegria NHS | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316604 | Amado M. Quirit Sr., Annex LPNHS | MALAPATAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316654 | Anecito Bartulaba Integrated School | GLAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208004 | Arcal ES | MAASIM | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130486 | Badtasan ES | KIAMBA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304521 | Baliton NHS | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500289 | Banlibato IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500259 | Batulaki IS | GLAN | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316644 | B'laan Integrated School | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316644 | B'laan Integrated School | MALUNGON | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208001 | Blat ES | MAASIM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208001 | Blat ES | MAASIM | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316645 | Bongo Integrated School | MAASIM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316645 | Bongo Integrated School | MAASIM | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500262 | Cabales Enarbia Sr. IS | KIAMBA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500280 | Cablalan IS | GLAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304523 | Colon NHS | MAASIM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316606 | Colon NHS - Aniceto Lopez NHS Annex | MAASIM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500275 | Consolacion IS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500272 | Daan Suyan IS | MALAPATAN | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500299 | Danao IS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500256 | Datal Anggas IS | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500270 | Datal Batong IS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500265 | Datu Molod IS | MAASIM | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316623 | Datu Pangolima Integrated School | MALAPATAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130456 | Dlama PS | GLAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500258 | E. Alegado IS | GLAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208016 | Edro Malayo ES | KIAMBA | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304524 | Glan School of Arts and Trades | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304524 | Glan School of Arts and Trades | GLAN | 0 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304525 | Glan-Padidu NHS | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304525 | Glan-Padidu NHS | GLAN | 0 | 1 | 3 | Construction of Standard Technical and Vocational Building | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316635 | Hadji Musa Integrated School | GLAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208025 | James Alfred Strong ES | MAITUM | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304529 | JAMES L. CHIONGBIAN NATIONAL TRADE SCHOOL | KIAMBA | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500263 | JBT Caing Sr. IS | KIAMBA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304526 | Kawas NHS | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500301 | Kiahe IS | MALAPATAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304527 | Kiamba NHS | KIAMBA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130427 | Kiangkos Elementary School | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130427 | Kiangkos Elementary School | ALABEL (Capital) | 0 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130600 | Kibala ES | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130600 | Kibala ES | MALUNGON | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316602 | Kiblat NHS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500288 | Kinabalan IS | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500288 | Kinabalan IS | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500288 | Kinabalan IS | MALUNGON | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130555 | Kinam Elementary School | MALAPATAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304529 | Kling National High School | KIAMBA | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316626 | Kyumad Integrated School | MAASIM | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500292 | Lamlabong IS | MAASIM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500292 | Lamlabong IS | MAASIM | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208042 | Langkuas ES | MALUNGON | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208042 | Langkuas ES | MALUNGON | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 500286 | Leopoldo P. Dacera Sr. IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130557 | Libi Integrated School | MALAPATAN | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 500293 | Libi IS | MALAPATAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316648 | Luis Casiple Sr. IS | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316648 | Luis Casiple Sr. IS | MALUNGON | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316612 | Lumigo IS | GLAN | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304531 | Lun Padidu NHS | MALAPATAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304531 | Lun Padidu NHS | MALAPATAN | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316620 | Lutay IS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304532 | Maguling NHS | MAITUM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316631 | Malabod IS | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304533 | Malalag Cogon NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304534 | Malalag NHS | MAITUM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316639 | Malalag NHS - Upo Annex | MAITUM | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304535 | Malandag National High School | MALUNGON | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304535 | Malandag NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316605 | Malapatan NHS - Kinam Annex | MALAPATAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130522 | Malbang ES | MAASIM | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130613 | Malungon CES SPED Center | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316603 | Malungon Gamay NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304538 | Malungon NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130614 | Manabawon Elementary Scholl | MALUNGON | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316619 | Mangelen IS | MAASIM | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208029 | Matingao PS | KIAMBA | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130431 | New Canaan Integrated School | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130431 | New Canaan Integrated School | ALABEL (Capital) | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316609 | New Canaan IS | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316640 | Nian Integrated School | MALUNGON | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 208019 | Nicomedes I. Sunio ES | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316618 | Nomoh IS | MAASIM | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130617 | Oliverio ES | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130617 | Oliverio ES | MALUNGON | 0 |  | 1 | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316607 | Pag-asa IS | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130433 | Pait IS | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316649 | Pait IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316649 | Pait IS | ALABEL (Capital) | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304541 | Pangyan NHS | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Sarangani | 304541 | Pangyan NHS | GLAN | 0 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316636 | PH Millona Integrated School | MALAPATAN | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130566 | Policarpo H. Millona Central Integrated School | MALAPATAN | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130526 | Rogaya Bajunaid IS | MAASIM | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316616 | Rogaya Bajunaid IS | MAASIM | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316613 | Roque Adarna IS | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304528 | Salakit National High School | KIAMBA | 0 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304539 | San Roque NHS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316601 | San Vicente NHS | GLAN | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130438 | Spring IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 316651 | Spring IS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130581 | Tagaytay ES | MALUNGON | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316637 | Tagaytay Integrated School | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304542 | Talus NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304536 | Tamban NHS | MALUNGON | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316629 | Tampus IS | GLAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 |  |  | 120714S00038 | 14ME0114 | 2014-07-20 | 2014-07-21 | 2014-09-29 | 2014-10-13 | 2014-10-31 | NIRVANA CONSTRUCTION & SUPPLIES
NC 2015 | K10 (2015) | Region XII | Sarangani | 130583 | Tangali IS | MALUNGON | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316628 | Tangan Integrated School | GLAN | 0 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304520 | Tokawal NHS | ALABEL (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130545 | Tuanadatu ES | MAITUM | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130441 | Upper Domolok ES | ALABEL (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 316621 | Upper Lumabat IS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Sarangani | 304540 | Upper Mainit NHS | MALUNGON | 0 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130528 | Virginia Tanedo Garcia (Balunok) ES | MAITUM | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region XII | Sarangani | 130528 | Virginia Tanedo Garcia (Balunok) ES | MAITUM | 0 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-11 |  | 2015-09-13 | FREDEN CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-11 |  | 2015-09-13 | FREDEN CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304576 | Cebuano NHS | TUPI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-07 |  | 2015-09-28 | ROCKSTONE CONST. SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316707 | Danlag NHS | TAMPAKAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2008606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-18 |  | 2016-03-09 | FORTSTONE CONST. ENTERPRISES
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130855 | Datal Biao ES | TAMPAKAN | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | FFJJ CONST
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316717 | Emiliano P. Baquial NHS - Tupi NHS Annex | TUPI | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2016-01-14 |  | 2016-01-08 | ROCKSTONE CONST. SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304562 | Jose D. Escobillo NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3664886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-15 |  | 2015-09-15 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304564 | Kablon NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-11 |  | 2015-09-13 | CEK CONSTRUCTION & WATER SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316711 | Lampitak NHS - Tampakan NHS Annex | TAMPAKAN | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2014-11-05 | VERGUZ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316712 | Landan NHS | POLOMOLOK | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2014-11-05 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304571 | Liberty NHS | TAMPAKAN | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-12 |  | 2015-12-16 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304556 | Maltana NHS | TAMPAKAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-12-29 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304545 | Nicolas B. Barreras NHS - Bentung Sulit NHS Annex | POLOMOLOK | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-12 |  | 2015-12-16 | C.A.V. BUILDERS & SUPPLY CORP.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316702 | Pablo Valencia NHS - Pob. Polomolok NHS Annex | POLOMOLOK | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-12 |  | 2015-12-16 | SOPHIA CONST. & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304559 | Poblacion Polomolok NHS | POLOMOLOK | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8239965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-27 |  | 2015-12-12 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8249965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-11-05 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130747 | Silway 8 ES | POLOMOLOK | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-12-16 | KEVIN YOSHI BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304567 | Silway 8 NHS | POLOMOLOK | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-27 |  | 2014-11-20 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316716 | Tablu NS - Tampakan NHS Annex | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-11-05 | FREDEN CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304570 | Tampakan NHS | TAMPAKAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-27 |  | 2015-10-08 | LAWRENCE ERIC CONSTRUCTION & ENG'G SERVICES
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208527 | Tampakan SPED Center | TAMPAKAN | 1 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | CEK CONSTRUCTION & WATER SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304563 | Teodoro P. Prudente NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6329337.6381 |  |  | COMPLETED | 1 | [6 empty] | 2016-02-04 |  | 2015-11-20 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130867 | Tokay Mal ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-08 |  | 2015-12-29 | FFJJ CONST
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 |  | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 | 10 | 2STY10CL | 2015 ADDITIONAL FUND BATCH 9 | 4406345.042 |  |  | COMPLETED | 1 | [6 empty] | 2016-02-04 |  | 2016-04-25 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | TECHVOC (2015) | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-12 |  |  | VERGUZ CONST
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304577 | Upper Klinan NHS | POLOMOLOK | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5106910.09 |  |  | COMPLETED | 1 | [6 empty] | 2016-11-12 |  | 2015-12-16 | ROCKSTONE CONST SERVICES & SUPPLY
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208516 | A. G. Monsale ES | SURALLAH | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316727 | Aflek NHS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1963606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304543 | Banga NHS | BANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-11-05 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316720 | Basag NHS - Tboli Annex | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1844740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316720 | Basag NHS - Tboli Annex | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208520 | Bengue ES | T'BOLI | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304565 | Bukay Pait NHS | TANTANGAN | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208512 | Bulol Lahak ES | LAKE SEBU | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304546 | Centrala NHS | SURALLAH | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304546 | Centrala NHS | SURALLAH | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316713 | Colongulo NHS - Libertad NHS Annex | SURALLAH | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130803 | Dangcong Elementary School | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130805 | Datal Bila ES | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-26 |  | 2016-02-24 | BETTER WORKS CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208521 | Datal Calon ES | T'BOLI | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130648 | Ebenezer ES | BANGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | LTB BUILDERS & CONST
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304547 | Edwards NHS | T'BOLI | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-11-02 | C.A. BETALAC CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304547 | Edwards NHS | T'BOLI | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-11-04 | C.A. BETALAC CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304548 | Guinsang-an NHS | SANTO NIÑO | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304549 | Katipunan NHS | SANTO NIÑO | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316708 | Kibang NHS - Lake Sebu NHS Annex | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2016-01-27 |  | 2016-02-24 | BETTER WORK CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130669 | Klubi ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | LTB BUILDERS & CONST
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316922 | L. Escovidal IS | SURALLAH | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-03 | ROCKSTONE CONST
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316922 | L. Escovidal IS | SURALLAH | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-03 | ROCKSTONE CONST
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130818 | Laconon IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316926 | Laconon IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | LTB BUILDERS
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130670 | Lake Lahit ES | LAKE SEBU | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-24 | COFEJOK CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-02 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316919 | Lake Soluton IS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1958606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | LTB BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316704 | Lamba NHS - Banga NHS Annex | BANGA | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304553 | Lambontong NHS | SURALLAH | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130674 | Lamfugon ES | LAKE SEBU | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | HVC SAGITTARIUS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316923 | Lamhako IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1968606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316923 | Lamhako IS | T'BOLI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304552 | Lamian NHS | SURALLAH | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-10-30 | COFEJOK
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316924 | Lamsalome IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-24 | HVC SAGITTARIUS
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130825 | Lamsine ES | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | COFEJOK CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130825 | Lamsine ES | T'BOLI | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | COFEJOK CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316710 | Lamsugod National High School | SURALLAH | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-10-30 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304554 | Lapuz NHS | NORALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | PALMARES GEN. MDSE.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8294965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-11-02 | AGUERO CONST.
NC 2015 | TECHVOC (2015) | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4859098.54 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-02 | YAP MABUHAY ENTERPRISES
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130772 | Little Baguio ES | SURALLAH | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2016-01-15 | NIRVANA CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130828 | Lubiya ES | T'BOLI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316917 | Lubol IS | SURALLAH | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2018606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130830 | Lusok Integrated School | T'BOLI | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316921 | Lusok IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316719 | Maan NHS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1998606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316714 | Malaya NHS - Banga NHS Annex | BANGA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304551 | Ned NHS | LAKE SEBU | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3604886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316706 | New Dumangas NHS | SURALLAH | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-17 |  | 2015-12-02 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316706 | New Dumangas NHS | SURALLAH | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-17 |  | 2015-12-02 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316911 | New Lambunao Integrated HS | TANTANGAN | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304557 | Norala NHS | NORALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-10-30 | COFEJOK CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304578 | Palkan National High School - Upper Klinan Annex | POLOMOLOK | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3484886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-12-29 |  | 2016-03-06 | SOPHIA CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304558 | Panay NHS | SANTO NIÑO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-04 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304561 | Polonuling NHS | TUPI | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-08-27 |  | 2015-09-08 | COFEJOK CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316709 | Proper Ned NHS - Lake Sebu NHS Annex | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2078606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316920 | Pulo Subong IS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2058606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316705 | Punong Grande NHS - Banga NHS Annex | BANGA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2700828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316915 | Rang-ay Integrated HS | BANGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-02 | FFJJ CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316723 | Rizal (Bo. 3) NHS - Banga NHS Annex | BANGA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316703 | San Jose NHS | BANGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316715 | San Jose NHS - Lapuz NHS Annex | NORALA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6379337.6381 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-10-27 | PASE CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304566 | San Miguel NHS | NORALA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-04 | ROCKSTONE CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316718 | San Vicente NHS - Banga NHS Annex | BANGA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1894740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316718 | San Vicente NHS - Banga NHS Annex | BANGA | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316724 | Sergio L. Legayada NHS - Norala NHS Annex | NORALA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | MIGO CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208507 | Seven Lakes ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304568 | Sto. Niño NHS | SANTO NIÑO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-02 | AGUERO CONST.
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304569 | Sto. Niño NSAT | SANTO NIÑO | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | MIGO CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316701 | Surallah NHS | SURALLAH | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-02 | AGUERO CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130844 | Talambong ES | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208524 | Talambongan ES | TANTANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | LTB BUILDERS & CONST
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316918 | Talisay Integrated HS | LAKE SEBU | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-10-30 | LTB BUILDERS & CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130846 | Talufo IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316925 | Talufo IS | T'BOLI | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | HVC SAGITTARIUS
NC 2015 | K10 (2015) | Region XII | South Cotabato | 316925 | Talufo IS | T'BOLI | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | HVC SAGITTARIUS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304572 | Tantangan NHS | TANTANGAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-29 |  | 2015-10-30 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304573 | Tantangan NTHS | TANTANGAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8229965.051 |  |  | COMPLETED | 1 | [6 empty] | 2015-09-30 |  | 2015-11-02 | REYDAN BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 |  | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | [6 empty] | 2016-02-22 |  | 2016-03-30 | VERTICAL BUILDERS
NC 2015 | SHS (2015) | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 | 12 | 3STY12CL | 2015 ADDITIONAL FUND BATCH 9 | 9857303.739 |  |  | COMPLETED | 1 | [6 empty] | 2016-02-22
NC 2015 | TECHVOC (2015) | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2549549.27 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | NIRVANA CONST. & SUPPLIES
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130776 | Tubi-allah ES | SURALLAH | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | HVC SAGITTARIUS
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208532 | Tuburan ES | NORALA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2248606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | COFEJOK CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 208532 | Tuburan ES | NORALA | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-11-27 | COFEJOK CONST.
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130693 | Ubo ES | LAKE SEBU | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | FFJJ CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | South Cotabato | 130694 | Upper Maculan ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 | [6 empty] | 2015-11-03 |  | 2015-12-01 | FFJJ CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | South Cotabato | 316725 | Upper Maculan NHS - Lake Sebu NHS Annex | LAKE SEBU | 2 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | [6 empty] | 2015-10-14 |  | 2015-11-04 | C.A. BETALAC CONST.
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304585 | Bambad NHS | ISULAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Robeth Gen. Msde. Const. & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304588 | Columbio NHS | COLUMBIO | 1 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5086910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-09-30 | 2015-10-14 | 2015-10-21 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209022 | DATU TALIPASAN IMPAO ES | ISULAN (Capital) | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10417131.51 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-10-15 | 2015-10-15 | 2015-10-31 | 2015-11-16 | C.A. BETALAC CONSTRUCTION & GEN. MDSE.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131007 | DON JUAN P. GARCIA Sr. MES | ISULAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | Robeth Gen. Msde. Const. & Supply
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131007 | DON JUAN P. GARCIA Sr. MES | ISULAN (Capital) | 1 | 1 | 1 | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | Robeth Gen. Msde. Const. & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304590 | Isulan NHS | ISULAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Cofejok Const. & Supply Corp.
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304594 | Kalanawe II NHS | PRESIDENT QUIRINO | 1 | 1 | 4 | 1STY4CL | 2015 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | FPJ Construction & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304595 | Kapingkong NHS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Robeth Gen. Msde. Const. & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304596 | Laguilayan NHS | ISULAN (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Robeth Gen. Msde. Const. & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304597 | Lambayong NHS (Mariano Marcos NHS) | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Minrock Multi-Builders
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304598 | Lambayong NHS (Mariano Marcos NHS) - Pimbalayan HS Annex | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-08 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Minrock Multi-Builders
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304606 | Lutayan NHS | LUTAYAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Minrock Multi-Builders
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304607 | Madanding NHS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | Robeth Gen. Msde. Const. & Supply
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131150 | MAINDANG ES | LUTAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-11-12 | 2015-11-26 | 2016-01-12 | 2016-01-29 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304609 | Mamali NHS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | Minrock Multi-Builders
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209030 | MANGANDOG ES | LUTAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-09-22 | 2015-11-26 | 2016-01-14 | 2016-01-29 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131025 | MANTISAO ES | ISULAN (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2016-01-02 | 2016-01-12 | 2016-01-30 | 2016-02-11 | AGUERO CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209019 | MAUNO PS | COLUMBIO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-10-15 | 2015-10-15 | 2015-10-31 | 2015-11-16 | Robeth Gen. Msde. Const. & Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304614 | New Pangasinan NHS | ISULAN (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | CEK Construction and Water Supply
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304617 | Pres. Quirino NHS | PRESIDENT QUIRINO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-02 | 2015-06-10 | 2015-07-31 | 2015-08-16 | 2015-08-27 | AGUERO CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region XII | Sultan Kudarat | 304617 | PRES. QUIRINO NHS | PRESIDENT QUIRINO | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-10-03 | 2015-10-15 | 2015-10-31 | 2015-11-26 | FORTSTONE CONSTRUCTION ENTERPRISES
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131200 | PUROK 4 ES | PRESIDENT QUIRINO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 130978 | SALNAONG PS | COLUMBIO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2016-01-02 | 2016-01-12 | 2016-01-30 | 2016-02-11 | AGUERO CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131086 | SIGAYAN ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304625 | Telafas NHS | COLUMBIO | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-04 | 2015-08-08 | 2015-08-20 | 2015-09-01 | 2015-09-17 | ROBETH GENERAL MERCHANDISE CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131105 | TINUMIGUES ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-10-15 | 2015-10-15 | 2015-10-31 | 2015-11-16 | Robeth Gen. Msde. Const. & Supply
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131164 | BADIANGON ES | PALIMBANG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | FORTSTONE CONST. ENTERPRISES
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5206910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | ROBETH GEN. MDSE. CONST. & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304582 | Bagumbayan NHS - Masiag HS | BAGUMBAYAN | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5356910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | ROBETH GEN. MDSE. CONST. & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304584 | Bai Saripinang NHS | BAGUMBAYAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | ROBETH GEN. MDSE. CONST. & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131185 | BALIANGO ES | PALIMBANG | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | MK GUIAMANO MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131167 | BARONGIS ES | PALIMBANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | CURVE-LINE CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131167 | BARONGIS ES | PALIMBANG | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | A.M AYUNAN CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209017 | BASAG ES - TINALON ANNEX | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-10 | 2015-09-17 | 2015-11-19 | 2015-11-20 | 2015-12-11 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 316803 | Biwang HS (Bagumbayan NHS ( Biwang Annex)) | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | JARGON CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131109 | BOLEBAK ES | LEBAK | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-07 | 2015-09-24 | WHITE YOUNG CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131050 | BUENAFLORES ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-10 | 2015-09-17 | 2015-09-03 | 2015-09-04 | 2015-10-01 | ROBETH GEN. MDSE. CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304587 | Busok NHS | BAGUMBAYAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | COFEJOK CONSTRUCTION & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 316810 | DANTE IS | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-24 | CURVE-LINE CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131033 | DATU MALAYAT ES | KALAMANSIG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-31 | 2015-07-07 | 2015-08-20 | 2015-09-01 | 2015-09-18 | PALMARES GENERAL MERCHANDISE
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131169 | DIONESIO CAGADOC SR. ES | PALIMBANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | FORTSTONE CONST. ENTERPRISES
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304586 | E. Arcano Mem. NHS (Basak NHS) | LEBAK | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8429965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | BRE CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304589 | Esperanza NHS | ESPERANZA | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | THREE W BUILDERS, INC. /SOPHIA CONSTRUCTION & SUPPLY (Joint Venture)
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 316805 | Esperanza NHS - Salumping NHS Annex | ESPERANZA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 316805 | Esperanza NHS - Salumping NHS Annex | ESPERANZA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 316805 | Esperanza NHS - Salumping NHS Annex | ESPERANZA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | CURVE-LINE CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131048 | FB CONCHA MEMORIAL PS | KALAMANSIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-10 | 2015-09-17 | 2015-10-01 | 2015-10-12 | 2015-10-26 | JV CONSTECH
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304601 | Gapok HS (Langgal NHS - Gapok HS) | SEN. NINOY AQUINO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | ROBETH GEN. MDSE. CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | COFEJOK CONSTRUCTION & SUPPLY CORP.
NC 2015 | TECHVOC (2015) | Region XII | Sultan Kudarat | 304591 | KALAMANSIG NHS | KALAMANSIG | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-12 | 2015-08-20 | 2015-09-03 | 2015-09-14 | 2015-10-01 | BRE CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304593 | Kalamansig NHS - Annex B | KALAMANSIG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | MK GUIAMANO MULTI-BUILDERS | Noo Remarks
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 130939 | KANULAY ES | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-01 | 2015-09-24 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 304581 | KAPAYA NHS | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  |  |  | 2016-10-14 | 2015-10-22 | 2015-11-12 | 2015-11-20 | 2015-12-07 | Pearl Construction and Supply
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131054 | KIADSAM ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-16 | 2015-10-01 | COMPACT CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131137 | KINUDALAN ES | LEBAK | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | WHITE YOUNG CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131137 | KINUDALAN ES | LEBAK | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | CEK CONSTRUCTION & WATER SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209012 | KISADAY ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-02 | 2015-10-26 | SHERATANNOR ENG’G. CONST. & SUPPLY, CO.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131187 | KRAAN ES | PALIMBANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131187 | KRAAN ES | PALIMBANG | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304599 | Langgal NHS | SEN. NINOY AQUINO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | DELPAR CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 316802 | Langgal NHS - Sewod NHS Annex | SEN. NINOY AQUINO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | ROBETH GEN. MDSE. CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304605 | Lebak Legislated HS | LEBAK | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | ROBETH GEN. MDSE. CONST. & SUPPLY
NC 2015 | TECHVOC (2015) | Region XII | Sultan Kudarat | 304605 | LEBAK LEGISLATED NHS | LEBAK | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-12 | 2015-08-20 | 2015-09-03 | 2015-09-14 | 2015-10-01 | ROBETH GEN. MDSE. CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304604 | Lebak NHS - Annex Keytodac HS | LEBAK | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-20 | 2015-09-03 | 2015-09-17 | 2015-10-01 | MINROCK MULTI-BUILDERS | Noo Remarks
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131188 | MAGUID PS | PALIMBANG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-01 | 2015-09-11 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131057 | MALEGDEG ES | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-16 | 2015-10-01 | COMPACT CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131180 | MANDOD ES | PALIMBANG | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | A.M. AYUNAN CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131180 | MANDOD ES | PALIMBANG | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | A.M. AYUNAN CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131058 | MIDTUNGOK ES | SEN. NINOY AQUINO | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-16 | 2015-10-01 | COMPACT CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304610 | Milbuk NHS | PALIMBANG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2760828.124 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | CEK CONSTRUCTION & WATER SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304610 | Milbuk NHS | PALIMBANG | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | CEK CONSTRUCTION & WATER SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304611 | Milbuk NHS - Baluan NHS Annex | PALIMBANG | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5396910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131059 | NATI ES | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-16 | 2015-10-01 | COMPACT CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131126 | NEW CALINOG ES | LEBAK | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304613 | New Panay NHS | ESPERANZA | 2 | 1 | 3 | 1STY3CL | 2015 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-24 | 2015-07-07 | 2015-07-14 | 2015-07-23 | 2015-08-10 | SOPHIA CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304615 | Palimbang NHS | PALIMBANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8434965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-13 | 2015-08-27 | 2015-09-16 | 2015-09-24 | A.M. AYUNAN CONSTRUCTION
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209018 | PIGEL ES | LEBAK | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-24 | 2015-09-03 | 2015-09-08 | 2015-10-01 | SHERATANNOR ENGINEERING CONST. & SUPPLY CO.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 316809 | PLAMANGO IS | ESPERANZA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-31 | 2015-08-07 | 2015-08-20 | 2015-09-01 | 2015-09-16 | ILBI CONSTRUCTION SUPPLY & SERVICES
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131142 | POSADAS ES | LEBAK | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-31 | 2015-08-07 | 2015-08-20 | 2015-09-01 | 2015-09-18 | PALMARES GENERAL MERCHANDISE
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304619 | Purikay NHS | LEBAK | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | JARGON CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131143 | SALAMAN CES | LEBAK | 2 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | COFEJOK CONSTRUCTION & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131143 | SALAMAN CES | LEBAK | 2 |  | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | COFEJOK CONSTRUCTION & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131143 | SALAMAN CES | LEBAK | 2 |  | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-21 | 2015-07-29 | 2015-08-17 | JARGON CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304592 | SANGAY NATIONAL HIGH SCHOOL | KALAMANSIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | MK GUIAMANO MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304623 | Santa Clara NHS | KALAMANSIG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | BRE CONSTRUCTION
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304602 | Sen. Ninoy Aquino NHS | SEN. NINOY AQUINO | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5486910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-03 | 2015-07-16 | 2015-07-30 | 2015-08-10 | 2015-08-24 | FPJ CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 130951 | SENAGANDAL ES | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-04 | 2015-09-24 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 316811 | TAPUDI IS | LEBAK | 2 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1 |  |  |  |  | 2015-06-25 | 2015-07-07 | 2015-07-28 | 2015-08-05 | 2015-08-18 | COFEJOK CONSTRUCTION & SUPPLY CORP.
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209005 | TIBUHOL ES | PALIMBANG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-08-06 | 2015-08-19 | 2015-08-27 | 2015-09-01 | 2015-09-24 | MINROCK MULTI-BUILDERS
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 131105 | TINUMIGUES ES | LAMBAYONG (MARIANO MARCOS) | 2 |  | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-22 | 2015-10-15 | 2015-10-15 | 2015-10-31 | 2015-11-16 | Robeth General Merchandise Construction & Supply
NC 2015 | K10 (2015) | Region XII | Sultan Kudarat | 209024 | TUDOG PS | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  |  | 2015-09-10 | 2015-09-17 | 2015-10-01 | 2015-10-12 | 2015-10-26 | COMPACT CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region XII | Sultan Kudarat | 304603 | Villamonte NHS ( Lebak NHS Main) | LEBAK | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5356910.09 |  |  | COMPLETED | 1 |  |  |  |  | 2015-07-22 | 2015-07-30 | 2015-08-13 | 2015-08-20 | 2015-09-07 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region XII | Tacurong City | 304579 | A.S. Bernardo Mem. NHS | CITY OF TACURONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Tacurong City | 304620 | Rajah Muda HS | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Tacurong City | 304622 | San Emmanuel NHS | CITY OF TACURONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region XII | Tacurong City | 304627 | V.F. Grino Mem. NHS | CITY OF TACURONG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2016 | SHS | Region XII | General Santos City | 304636 | A.G. Busano, Sr. Hs | General Santos City (Dadiangas) | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12931310.09 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 317003 | Baluan Nhs | General Santos City (Dadiangas) | 1 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15271327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 317003 | Baluan Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 304643 | Banisil Nhs | General Santos City (Dadiangas) | 1 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26852890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304643 | Banisil Nhs | General Santos City (Dadiangas) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4859098.54 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131294 | Bawing Es | General Santos City (Dadiangas) | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15271327.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304644 | Bawing Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304639 | Bula National School Of Fisheries | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131269 | Conel Ces | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 317005 | Dadiangas North Hs | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304649 | Datu B. Balunto Nhs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304649 | Datu B. Balunto Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 317004 | E.J. Buscano Sr, Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 317004 | E.J. Buscano Sr, Hs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 304640 | Engracia I. Valdomar Nhs | General Santos City (Dadiangas) | 1 | 1 | 18 | 3STY9CL | BATCH 5 CL | 30542655.84 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304641 | Fatima Nhs | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65222918.24 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304641 | Fatima Nhs | General Santos City (Dadiangas) | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 27820322.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 |  | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 |  | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304646 | Gsc Hs - Lanton Hs Annex | General Santos City (Dadiangas) | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7318647.81 |  |  | Completed | 1 | [9 empty] | C.A.V. Builders and Supply Corp.
NC 2016 | SHS | Region XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 66129161.84 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 |  | 8 | 2STY8CL | BATCH 1 CL | 11227925.59 |  |  | Completed | 1 | [9 empty] | Vertical Builders
NC 2016 | TECHVOC | Region XII | General Santos City | 304655 | Gsc Nat'L. Sec. Sch. Of Arts & Trades | General Santos City (Dadiangas) | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 4887746.99 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 317001 | Gsc Sped Integrated School | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 317001 | Gsc Sped Integrated School | General Santos City (Dadiangas) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8464965.05 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304648 | Irineo Santiago Nhs Of Metro Dadiangas (Main) | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 3 CL | 62505780.54 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304648 | Irineo Santiago Nhs Of Metro Dadiangas (Main) | General Santos City (Dadiangas) | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304645 | Johnny Ang Nhs | General Santos City (Dadiangas) | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12921310.09 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304645 | Johnny Ang Nhs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131272 | Jose Catolico Sr. Es | General Santos City (Dadiangas) | 1 | 1 | 12 | 3STY12CL | BATCH 13 CL | 20029495.669 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304650 | Labangal Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31252890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304650 | Labangal Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131285 | Lagao 2Nd Bo. Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304653 | Lagao Nhs (Main) | General Santos City (Dadiangas) | 1 |  | 16 | 4STY16CL | BATCH 1 CL | 28244890.27 |  |  | Completed | 1 | [9 empty] | AB Vision Engineering
NC 2016 | SHS | Region XII | General Santos City | 304653 | Lagao Nhs (Main) | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65989780.54 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304654 | Lagao Nhs Annex | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 304654 | Lagao Nhs Annex | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131279 | Lanton Es | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304651 | Ligaya Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131286 | Mabuhay Es | General Santos City (Dadiangas) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8374465.05 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 210009 | Maligaya Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1829740.17 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131321 | Nasa Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304647 | New Society National High School | General Santos City (Dadiangas) | 1 | 1 | 40 | 4STY20CL | BATCH 1 CL | 65690501.84 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304647 | New Society National High School | General Santos City (Dadiangas) | 1 |  | 8 | 2STY8CL | BATCH 1 CL | 11236925.59 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 317002 | Pao - Pao Hs | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | General Santos City | 317002 | Pao - Pao Hs | General Santos City (Dadiangas) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2449549.27 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131316 | Pao-Pao Es | General Santos City (Dadiangas) | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1834740.17 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131280 | Saavedra Saway Ces | General Santos City (Dadiangas) | 1 | 1 | 6 | 3STY6CL | BATCH 3 CL | 10567131.51 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 317006 | Samboang-Ngilay Hs | General Santos City (Dadiangas) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11037342.59 |  |  | Completed | 1
NC 2016 | SHS | Region XII | General Santos City | 304652 | Upper Labay Hs | General Santos City (Dadiangas) | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8504965.05 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131324 | Upper Tambler Es I | General Santos City (Dadiangas) | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11027342.59 |  |  | Completed | 1
NC 2016 | K10 | Region XII | General Santos City | 131323 | Upper Tambler Es I Ces | General Santos City (Dadiangas) | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11055006.99 |  |  | Completed | 1 | [9 empty] | GP & H Const.
NC 2016 | SHS | Region XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8387706.21 |  |  | Completed | 1 | [9 empty] | LTB Builders
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304656 | Amas Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2507239.6 |  |  | Completed | 1 | [9 empty] | Llaban Const.
NC 2016 | SHS | Region XII | Kidapawan City | 304658 | Ginatilan Nhs | City Of Kidapawan (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 3 CL | 18224268.79 |  |  | Completed | 1 | [9 empty] | Aguero Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304658 | Ginatilan Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const.
NC 2016 | K10 | Region XII | Kidapawan City | 210504 | Habitat Elementary School | City Of Kidapawan (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [9 empty] | Isulan ECT Const.
NC 2016 | SHS | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11196007.09 |  |  | Completed | 1 | [9 empty] | Verguz Const.
NC 2016 | SHS | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8498904.05 |  |  | Completed | 1 | [9 empty] | Verguz Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School Of Arts And Trades | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2546473.75 |  |  | Completed | 1 | [9 empty] | Verguz Const.
NC 2016 | K10 | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Mem. Nhs | City Of Kidapawan (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [9 empty] | Isulan ECT Const.
NC 2016 | K10 | Region XII | Kidapawan City | 304663 | Kalaisan National High School | City Of Kidapawan (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 1 CL | 11178693.34 |  |  | Completed | 1 | [9 empty] | GP & H Const.
NC 2016 | K10 | Region XII | Kidapawan City | 304663 | Kalaisan National High School | City Of Kidapawan (Capital) | 2 |  | 6 | 2STY6CL | BATCH 1 CL | 8487053.05 |  |  | Completed | 1 | [9 empty] | Aguero Const.
NC 2016 | SHS | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | City Of Kidapawan (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 | [9 empty] | Jargon Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | Jargon Const.
NC 2016 | K10 | Region XII | Kidapawan City | 317101 | Linangkob National High School | City Of Kidapawan (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6469337.64 |  |  | Completed | 1 | [9 empty] | Llaban Const.
NC 2016 | SHS | Region XII | Kidapawan City | 304659 | Manongol Nhs | City Of Kidapawan (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8364965.05 |  |  | Completed | 1 | [9 empty] | Cofejok Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304659 | Manongol Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const.
NC 2016 | SHS | Region XII | Kidapawan City | 304668 | Paco Nhs | City Of Kidapawan (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15121327.92 |  |  | Completed | 1 | [9 empty] | AYU Eng'g & Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304668 | Paco Nhs | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | RNH Bentulan Const.
NC 2016 | K10 | Region XII | Kidapawan City | 131369 | Patadon Es | City Of Kidapawan (Capital) | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2640828.12 |  |  | Completed | 1 | [9 empty] | John Rey Devt & Supply
NC 2016 | K10 | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18395418.84 |  |  | Completed | 1 | [9 empty] | Jargon Const.
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2554041.64 |  |  | Completed | 1 | [9 empty] | LTB Builders
NC 2016 | TECHVOC | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | City Of Kidapawan (Capital) | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2500000 |  |  | Completed | 1 | [9 empty] | LTB Builders
NC 2016 | TECHVOC | Region XII | Koronadal City | 317201 | Bacongco National High School | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00071694MN | 16MG0044 | 2016-06-22 | 2016-07-04 | 2016-07-18 | 2016-08-10 | 2016-08-24 | Cofejok Construction and Supply
NC 2016 | SHS | Region XII | Koronadal City | 304671 | Koronadal Nchs | City Of Koronadal (Capital) | 2 | 1 | 24 | 4STY12CL | BATCH 13 CL | 48705155.964 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | Koronadal City | 304671 | Koronadal Nchs | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Koronadal City | 304672 | Marbel 7 National High School | City Of Koronadal (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00072497MN | 16MG0102 | 2016-06-16 | 2016-06-28 | 2016-07-11 | 2016-07-25 | 2016-08-09 | FH Gopiteo Construction and Supply
NC 2016 | TECHVOC | Region XII | Koronadal City | 304672 | Marbel 7 National High School | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00072652MN | 16MG0083 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-06-10 | 2016-06-24 | Rockstone Construction Services and Supply
NC 2016 | SHS | Region XII | Koronadal City | 317205 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) (Realigned To Esperanza Nhs Annex- San Jose Campus) | City Of Koronadal (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Koronadal City | 317202 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) | City Of Koronadal (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072499MN | 16MG0046 | 2016-02-29 | 2016-03-09 | 2016-03-21 | 2016-06-10 | 2016-06-24 | Reydan Builders
NC 2016 | TECHVOC | Region XII | Koronadal City | 317202 | Saravia Nhs (Koronadal Nchs - Annex, Saravia Campus) | City Of Koronadal (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 |  |  | P00072653MN | 16MG0084 | 2016-06-20 | 2016-06-30 | 2016-07-12 | 2016-07-25 | 2016-08-09 | Reydan Builders
NC 2016 | K10 | Region XII | Koronadal City | 131400 | Sto. Nino Es | City Of Koronadal (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 |  |  | P00070639MN | 16MG0121 | 2016-06-20 | 2016-06-30 | 2016-07-12 | 2016-07-25 | 2016-08-09 | FH Gopiteo Construction and Supply
NC 2016 | SHS | Region XII | North Cotabato | 304412 | Alamada Nhs | Alamada | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26712469.42 |  |  | Completed | 1 |  |  | P00070640MN | 16MD0063 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 2016-08-11 | ACJ Construction
NC 2016 | SHS | Region XII | North Cotabato | 304413 | Aleosan Nhs | Aleosan | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35606257.14 |  |  | Completed | 1 |  |  | P00071231MN | 16MD0083 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-13 | 2016-09-26 | FFJJ Const.
NC 2016 | SHS | Region XII | North Cotabato | 316521 | Aringay National High School | Kabacan | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 10887342.59 |  |  | Completed | 1 |  |  | P00070641MN | 16MD0051 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-22 | MARCUS Const.
NC 2016 | SHS | Region XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8314965.051 |  |  | Completed | 1 |  |  | P00072508MN | 16MD0067 | 2016-06-24 | 2016-07-01 | 2016-07-15 | 2016-07-29 | 2016-08-11 | PADER Const
NC 2016 | SHS | Region XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 |  | 1 | 1STY1CL | BATCH 7 CL | 1112049.6543 |  |  | Completed | 1 |  |  | P00072509MN | 16MD0055 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 2016-06-14 | BORDERLINE Const.
NC 2016 | TECHVOC | Region XII | North Cotabato | 316556 | Bentangan Hs | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2563728.13 |  |  | Completed | 1 |  |  | P00072657MN | 16MD0059 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 2016-06-23 | BORDERLINE Const.
NC 2016 | K10 | Region XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21408013.45 |  |  | Completed | 1 |  |  | P00072510MN | 16MD0073 | 2016-07-11 | 2016-07-18 | 2016-08-02 | 2016-10-06 | 2016-10-17 | MARCUS Const.
NC 2016 | K10 | Region XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6344337.6381 |  |  | Completed | 1 |  |  | P00072511MN | 16MD0054 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-22 | MARCUS Const.
NC 2016 | TECHVOC | Region XII | North Cotabato | 304427 | Carmen National High School | Carmen | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5102456.26 |  |  | Completed | 1 |  |  | P00072658MN | 16MD0061 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 2016-06-23 | BORDERLINE Const.
NC 2016 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00070172MN | 16MD0046 | 2016-02-13 | 2016-02-22 | 2016-03-08 | 2016-03-11 | 2016-06-03 | BANDAR KUTAWATO
NC 2016 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 |  | 20 | 4STY20CL | BATCH 1 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00070173MN | 16MD0070 | 2016-07-05 | 2016-07-13 | 2016-07-26 | 2016-07-29 | 2016-08-11 | ACJ/RDEN Const. (Joint Venture)
NC 2016 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | Midsayap | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26712469.42 |  |  | Completed | 1 |  |  | P00074327MN | 16MD0064 | 2016-06-24 | 2016-07-01 | 2016-08-02 | 2016-08-09 | 2016-08-22 | ACJ/RDEN Const. (Joint Venture)
NC 2016 | K10 | Region XII | North Cotabato | 304444 | Kabacan National Hs | Kabacan | 1 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44572220.04 |  |  | Completed | 1 |  |  | P00071232MN | 16MD0081 |  | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-30 | 42660
NC 2016 | K10 | Region XII | North Cotabato | 304444 | Kabacan National Hs | Kabacan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14937518.84 |  |  | Completed | 1 |  |  | P00071233MN | 16MD0066 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 2016-08-11 | MARCUS Const.
NC 2016 | SHS | Region XII | North Cotabato | 304458 | Kitub-Bao Nhs | Alamada | 1 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21453013.45 |  |  | Completed | 1 |  |  | P00071234MN | 16MD0071 | 2016-08-11 | 2016-08-18 | 2016-08-31 | 2016-12-13 | 2016-12-23 | ACJ/RDEN Const. (Joint Venture)
NC 2016 | SHS | Region XII | North Cotabato | 304468 | Malapag Nhs | Carmen | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26802469.42 |  |  | Completed | 1 |  |  | P00072512MN | 16MD0065 | 2016-06-24 | 2016-07-01 | 2016-07-14 | 2016-07-29 | 2016-08-11 | MARCUS Const.
NC 2016 | TECHVOC | Region XII | North Cotabato | 304468 | Malapag Nhs | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2563728.13 |  |  | Completed | 1 |  |  | P00072659MN | 16MD0060 | 2016-05-17 | 2016-05-24 | 2016-06-06 | 2016-06-09 | 2016-06-23 | BORDERLINE Const.
NC 2016 | K10 | Region XII | North Cotabato | 304472 | Malinao High School | Banisilan | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 21513013.45 |  |  | Completed | 1
NC 2016 | SHS | Region XII | North Cotabato | 304474 | Manuangan Hs | Pigkawayan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6329337.64 |  |  | Completed | 1 |  |  | P00070643MN | 16MD0049 | 2016-02-25 | 2016-03-04 | 2016-03-22 | 2016-03-29 | 2016-06-03 | LLABAN CONST.
NC 2016 | SHS | Region XII | North Cotabato | 304493 | Pigcawayan National High School | Pigkawayan | 1 | 1 | 28 | 4STY28CL | BATCH 9 CL | 40107946.14 |  |  | Completed | 1 |  |  | P00074328MN | 16MD0080
NC 2016 | TECHVOC | Region XII | North Cotabato | 304493 | Pigcawayan National High School | Pigkawayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2500000 |  |  | Completed | 1 |  |  | P00074619MN | 16MD0057 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 2016-06-14 | SHERATANNOR CONST.
NC 2016 | SHS | Region XII | North Cotabato | 316520 | Pigcawayan Nhs - Libungan Torreta Annex | Pigkawayan | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15191327.92 |  |  | Completed | 1 |  |  | P00070644MN | 16MD0072 | 2016-07-05 | 2016-07-13 | 2016-07-27 |  |  | STONELINE/CURVELINE (Joint Venture)
NC 2016 | SHS | Region XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 | 1 | 32 | 4STY32CL | BATCH 9 CL | 44572220.84 |  |  | Completed | 1 |  |  | P00074330MN | 16MD0079 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 2016-10-21 | HEXAMINDZ
NC 2016 | SHS | Region XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 |  | 24 | 4STY24CL | BATCH 9 CL | 35636257.14 |  |  | Completed | 1 |  |  | P00074331MN | 16MD0084 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 2016-10-21 | HEXAMINDZ
NC 2016 | TECHVOC | Region XII | North Cotabato | 304494 | Pikit Nhs | Pikit | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5000000 |  |  | Completed | 1 |  |  | P00074620MN | 16MD0056 | 2016-04-28 | 2016-05-06 | 2016-05-24 | 2016-05-27 | 2016-06-14 | J-ONE BUILDERS
NC 2016 | SHS | Region XII | North Cotabato | 304499 | Presbitero Hs | Pigkawayan | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12781310.09 |  |  | Completed | 1 |  |  | P00070645MN | 16MD0052 | 2016-08-11 | 2016-08-18 | 2016-08-31 | 2016-09-05 | 2016-09-20 | STONELINE CONST.
NC 2016 | TECHVOC | Region XII | North Cotabato | 304429 | Ranzo National High School | Carmen | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2551228.13 |  |  | Completed | 1 |  |  | P00075351MN | 16MD0085 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-13 | 2016-10-04 | HAQ CONSTRUCTION
NC 2016 | SHS | Region XII | North Cotabato | 304500 | Salama Nhs | Banisilan | 1 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10977342.59 |  |  | Completed | 1 |  |  | P00071235MN | 16MD0048 | 2016-07-11 | 2016-07-19 | 2016-08-09 | 2016-08-12 | 2016-08-26 | K.A.BUILDERS/CAMIA Const. (Joint Vwnture)
NC 2016 | SHS | Region XII | North Cotabato | 304501 | Salunayan Hs | Midsayap | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31112890.27 |  |  | Completed | 1 |  |  | P00072500MN | 16MD0069 | 2016-07-05 | 2016-07-13 | 2016-08-31 | 2016-09-05 | 2016-09-20 | K.A.BUILDERS/CAMIA Const. (Joint Vwnture)
NC 2016 | SHS | Region XII | North Cotabato | 304501 | Salunayan Hs | Midsayap | 1 |  | 4 | 2STY4CL | BATCH 7 CL | 6329337.64 |  |  | Completed | 1 |  |  | P00072501MN | 16MD0053 | 2016-03-17 | 2016-03-28 | 2016-04-11 | 2016-04-14 | 2016-06-30 | DINGO BUILDERS & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304505 | Silik High School | Pikit | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31177890.27 |  |  | Terminated | 1 |  |  | P00070646MN | 16MD0078 | 2016-08-18 | 2016-08-25 | 2016-09-07 | 2016-09-30 | 2016-10-21 | HEXAMINDZ | Terminated due to contractor's fault: Hexamindz Corporation; added demolition of structure which was the incomplete structure been abandoned by the said contractor;PROCESS OF BLACKLISTING THE CONTRACTOR!
NC 2016 | SHS | Region XII | North Cotabato | 304505 | Silik High School | Pikit | 1 |  | 16 | 4STY16CL | BATCH 3 CL | 26777469.42 |  |  | Terminated | 1 |  |  | P00070647MN | 16MD0082 | 2016-08-18 | 2016-08-25 | 2016-09-01 | 2016-09-30 | 2016-10-21 | HEXAMINDZ | Terminated due to contractor's fault: Hexamindz Corporation; added demolition of structure which was the incomplete structure been abandoned by the said contractor;PROCESS OF BLACKLISTING THE CONTRACTOR!
NC 2016 | SHS | Region XII | North Cotabato | 304507 | Sinawingan Hs | Libungan | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8224965.05 |  |  | Completed | 1 |  |  | P00070642MN | 16MD0050 | 2016-07-11 | 2016-07-19 | 2016-08-02 | 2016-08-09 | 2016-08-22 | RDEN CONST.
NC 2016 | SHS | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | Matalam | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072517MN | 16MC0150 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 2016-08-12 | BORDERLINE CONST & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304415 | Antipas Nhs | Antipas | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22229351.8227 |  |  | Completed | 1 |  |  | P00072502MN | 16MC158 | 2016-06-07 | 2016-06-16 | 2016-06-27 | 2016-07-15 | 2016-08-12 | BRE CONSTRUCTION
NC 2016 | TECHVOC | Region XII | North Cotabato | 304415 | Antipas Nhs | Antipas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2517500 |  |  | Completed | 1 |  |  | P00072654MN | 16MC0138 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-07-04 | 2016-07-22 | SHEPPERD CONST. & SUPPLY
NC 2016 | K10 | Region XII | North Cotabato | 130400 | Bacong Es | Tulunan | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8327874.5607 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | North Cotabato | 304419 | Banayal Hs | Tulunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075353MN | 16MC0208 | 2016-08-10 | 2016-08-18 | 2016-08-30 | 2016-09-06 | 2016-09-19 | MEGALINE BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | North Cotabato | 304423 | Bulakanon High School | Makilala | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00072515MN | 16MC0145 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 2016-06-21 | THREE W BUILDERS, INC
NC 2016 | SHS | Region XII | North Cotabato | 304431 | Dalapitan Hs | Matalam | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072518MN | 16MC0152 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-15 | 2016-06-21 | BORDERLINE CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304438 | Dallag Hs | Arakan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6364337.64 |  |  | Completed | 1 |  |  | P00072504MN | 16MC0154 | 2016-03-28 | 2016-04-06 | 2016-04-18 | 2016-06-03 | 2016-06-28 | JARGON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. Hs | President Roxas | 2 | 1 | 10 | 2STY10CL | BATCH 13 CL | 12771310.09 |  |  | Completed | 1
NC 2016 | SHS | Region XII | North Cotabato | 304436 | Greenfield Nhs | Arakan | 2 | 1 | 8 | 2STY8CL | BATCH 13 CL | 10977342.59 |  |  | Completed | 1
NC 2016 | SHS | Region XII | North Cotabato | 304440 | Kabalantian Hs | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8259965.05 |  |  | Completed | 1 |  |  | P00072505MN | 16MC0161 | 2016-03-28 | 2016-04-06 | 2016-04-18 | 2016-05-06 | 2016-06-28 | JARGON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304441 | Katipunan Hs | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072506MN | 16MC0151 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-10 | 2016-06-27 | CHJ CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | North Cotabato | 304441 | Katipunan Hs | Arakan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072656MN | 16MC0140 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 2016-07-11 | CHJ CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304452 | Kibia Hs | Matalam | 2 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00072519MN | 16MC0147 | 2016-03-12 | 2016-03-10 | 2016-03-21 | 2016-05-06 | 2016-07-04 | JARGON CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | North Cotabato | 316519 | Kisante Nhs - Batasan Hs Annex | Makilala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2500000 |  |  | Completed | 1 |  |  | P00075352MN | 16MC0207 | 2015-08-10 | 2016-08-18 | 2016-08-30 | 2016-09-06 | 2016-09-25 | CARLSON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304463 | Magpet Nhs | Magpet | 2 | 1 | 15 | 3STY15CL | BATCH 7 CL | 21383013.45 |  |  | Completed | 1 |  |  | P00072513MN | 16MC0144 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-06 | 2016-06-27 | BRE CONSTRUCTION
NC 2016 | TECHVOC | Region XII | North Cotabato | 304463 | Magpet Nhs | Magpet | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072660MN | 16MC0139 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 2016-06-27 | MEGALINE BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | North Cotabato | 304466 | Makilala National High School | Makilala | 2 | 1 | 12 | 3STY12CL | BATCH 1 CL | 18282268.79 |  |  | Completed | 1 |  |  | P00070174MN | 16MC0116 | 2016-02-10 | 2016-02-16 | 2016-02-29 | 2016-05-10 | 2016-06-20 | GP & H Const. & Supply
NC 2016 | SHS | Region XII | North Cotabato | 304470 | Malatab Hs | Antipas | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10914888.2891 |  |  | Completed | 1 |  |  | P00072503MN | 16MC0160 | 2016-03-02 | 2016-03-10 | 2016-03-22 | 2016-05-06 | 2016-06-27 | ACJ CONST. RESOURSES
NC 2016 | TECHVOC | Region XII | North Cotabato | 304470 | Malatab Hs | Antipas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2517500 |  |  | Completed | 1 |  |  | P00072655MN | 16MC0137 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-06 | 2016-06-27 | Y.R. BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | North Cotabato | 304471 | Malibatuan High School | Arakan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00072507MN | 16MC0153 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 2016-08-12 | JARGON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304473 | Manobo Nhs | Magpet | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  | P00072514MN | 16MC0159 | 2016-06-07 | 2016-06-16 | 2016-06-27 | 2016-07-15 | 2016-08-12 | AGUERO CONSTRUCTION
NC 2016 | TECHVOC | Region XII | North Cotabato | 304473 | Manobo Nhs | Magpet | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072661MN | 16MC0143 | 2016-06-09 | 2016-06-17 | 2016-06-29 | 2016-07-15 | 2016-08-12 | BRE CONSTRUCTION
NC 2016 | SHS | Region XII | North Cotabato | 304418 | Mariano Untal Hs | M'Lang | 2 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8244965.05 |  |  | Completed | 1 |  |  | P00074328MN | 16MC0171 | 2016-04-15 | 2016-04-22 | 2016-03-29 | 2016-05-18 | 2016-06-21 | J & S ESCUADRA CONST.
NC 2016 | TECHVOC | Region XII | North Cotabato | 304418 | Mariano Untal Hs | M'Lang | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 7500000 |  |  | Completed | 1 |  |  | P00074618MN | 16MC0170 | 2016-04-15 | 2016-04-22 | 2016-05-05 | 2016-06-02 | 2016-06-21 | WHITE YOUNG CONST.
NC 2016 | SHS | Region XII | North Cotabato | 304476 | Matalam Nhs, Brgy Linao | Matalam | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26757469.42 |  |  | Completed | 1 |  |  | P00072520MN | 16MC0187 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-08-26 | 2016-09-22 | JARGON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 304478 | Matalam Nhs, Brgy Poblacion | Matalam | 2 | 1 | 24 | 4STY24CL | BATCH 13 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | K10 | Region XII | North Cotabato | 316534 | Meocan High School | Arakan | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22460376.4307 |  |  | Completed | 1 |  |  | P00074939MN | 16MC0216 | 2016-09-06 | 2016-09-15 | 2016-09-27 | 2015-10-07 | 2016-11-16 | JARGON CONST. & SUPPLY
NC 2016 | SHS | Region XII | North Cotabato | 316514 | Minapan High School | Tulunan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00072521MN | 16MC0184 | 2016-06-28 | 2016-07-06 | 2016-07-18 | 2016-08-05 | 2016-09-05 | ISULAN ECT CONST.
NC 2016 | TECHVOC | Region XII | North Cotabato | 316514 | Minapan High School | Tulunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2500000 |  |  | Completed | 1 |  |  | P00072662MN | 16MC0141 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-10 | 2016-06-21 | ISULAN ECT CONST.
NC 2016 | SHS | Region XII | North Cotabato | 304480 | M'Lang Nhs | M'Lang | 2 | 1 | 32 | 4STY32CL | BATCH 5 CL | 44582220.04 |  |  | Completed | 1 |  |  | P00071236MN | 16MC0186 | 2016-06-30 | 2016-07-08 | 2016-07-20 | 2016-08-08 | 2016-11-14 | LEGACY CONSTRUCTION
NC 2016 | SHS | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | President Roxas | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region XII | North Cotabato | 304457 | Ricardo L. Ipong Nhs | Makilala | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00072516MN | 16MC0155 | 2016-03-01 | 2016-03-09 | 2016-03-21 | 2016-05-18 | 2016-06-21 | ISULAN ECT CONST,.
NC 2016 | K10 | Region XII | North Cotabato | 130123 | San Vicente Elementary School | Makilala | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8327874.5607 |  |  | Completed | 1
NC 2016 | SHS | Region XII | North Cotabato | 304515 | Tulunan Nhs | Tulunan | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64269040.35 |  |  | Completed | 1 |  |  | P00074332MN | 16MC0185 | 2016-07-29 | 2016-08-05 | 2016-08-18 | 2016-08-26 | 2016-11-16 | JARGON CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | North Cotabato | 304515 | Tulunan Nhs | Tulunan | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5000000 |  |  | Completed | 1 |  |  | P00074621MN | 16MC0172 | 2016-04-15 | 2016-04-22 | 2016-05-05 | 2016-05-31 | 2016-06-21 | WHITE YOUNG CONST.
NC 2016 | SHS | Region XII | Sarangani | 316634 | Alabel Central Integrated Sped Center | Alabel (Capital) | 0 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24715057.382 |  |  | Completed | 1 |  |  | P00074333MN-CW1 | 16ME0135 |  |  | 2016-07-08 |  | 2016-08-02 | R.R. Seismundo Construction & Supply
NC 2016 | SHS | Region XII | Sarangani | 304517 | Alabel Nat'L Science Hs | Alabel (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6440885.48 |  |  | Completed | 1 |  |  | P00070648MN-CW1 | 16ME0114 |  |  | 2016-06-27 |  | 2016-07-21 | MIGO Construction
NC 2016 | SHS | Region XII | Sarangani | 304518 | Alabel Nhs | Alabel (Capital) | 0 | 1 | 24 | 4STY12CL | BATCH 13 CL | 49067635.3627 |  |  | Completed | 1 |  |  | P00076040MN-CW1 | 16ME0173 |  |  | 2016-12-05 |  | 2016-12-23 | LHE Construction & Industrial Services
NC 2016 | SHS | Region XII | Sarangani | 304519 | Alegria Nhs | Alabel (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6450485.7993 |  |  | Completed | 1 |  |  | P00072522MN-CW1 | 16ME0117 |  |  | 2016-06-27 |  | 2016-07-21 | Shepperd Construction & Supply
NC 2016 | SHS | Region XII | Sarangani | 500262 | Cabales Enarbia Sr. Is | Kiamba | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8608332.7 |  |  | Completed | 1 |  |  | P00070652MN-CW1 | 16ME0115 |  |  | 2016-08-10 |  | 2016-08-30 | Verguz Construction
NC 2016 | SHS | Region XII | Sarangani | 500280 | Cablalan Is | Glan | 0 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8577020.39 |  |  | Completed | 1 |  |  | P00070649MN-CW1 | 16ME0116 |  |  | 2016-06-27 |  | 2016-07-21 | LTB Builders & Construction
NC 2016 | SHS | Region XII | Sarangani | 304523 | Colon Nhs | Maasim | 0 | 1 | 24 | 4STY12CL | BATCH 9 CL | 50215800.7102 |  |  | Completed | 1 |  |  | P00074340MN-CW1 | 16ME0124 |  |  | 2016-07-08 |  | 2016-08-01 | Three W Builders/Sophia Construction
NC 2016 | SHS | Region XII | Sarangani | 304523 | Colon Nhs | Maasim | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17229338.8409 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 316623 | Datu Pangolima Integrated School | Malapatan | 0 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6486813.8622 |  |  | Completed | 1 |  |  | P00072523MN-CW1 | 16ME0121 |  |  | 2016-06-27 |  | 2016-07-21 | Lawrence Eric Construction & Eng'g Services
NC 2016 | K10 | Region XII | Sarangani | 130457 | E. Alegado Integrated School | Glan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8696912.556 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 304524 | Glan School Of Arts And Trades | Glan | 0 | 1 | 32 | 4STY16CL | BATCH 9 CL | 60941225.2172 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 304524 | Glan School Of Arts And Trades | Glan | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 2077794.145 |  |  | Completed | 1 |  |  | P00074335MN-CW1 | 16ME0128 |  |  | 2106-06-29 |  | 2016-07-28 | LTB Builders & Construction
NC 2016 | SHS | Region XII | Sarangani | 304525 | Glan-Padidu Nhs | Glan | 0 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17631965.0809 |  |  | Completed | 1 | [6 empty] | 2016-12-27 |  | 2017-02-13 | LTB Builders & Construction
NC 2016 | K10 | Region XII | Sarangani | 130516 | Ireneo E. Lopez (Lumasal) Es | Maasim | 0 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8577204.6765 |  |  | Completed | 1 |  |  | P0006053MN-CW1 | 16ME0178 |  |  | 2016-12-05 |  | 2016-12-29 | Legacy Construction
NC 2016 | K10 | Region XII | Sarangani | 130516 | Ireneo E. Lopez (Lumasal) Es | Maasim | 0 |  | 3 | 1STY3CL | BATCH 13 CL | 3218505.9715 |  |  | Completed | 1 |  |  |  | 16ME0179 |  |  | 2016-12-29 |  | 2017-02-13 | LTB Builders & Construction
NC 2016 | K10 | Region XII | Sarangani | 304529 | James L. Chiongbian National Trade School | Kiamba | 0 | 1 | 30 | 3STY15CL | BATCH 9 CL | 50625885.0217 |  |  | Completed | 1 |  |  | P00074336MN-CW1 | 16ME0137 |  |  | 2016-07-08 |  | 2016-08-10 | Sarangani Rockmixer
NC 2016 | K10 | Region XII | Sarangani | 304529 | James L. Chiongbian National Trade School | Kiamba | 0 |  | 2 | 1STY2CL | BATCH 9 CL | 2129946.3493 |  |  | Completed | 1 |  |  | P00074337MN-CW1 | 16ME0129 |  |  | 2016-08-02 |  | 2016-08-22 | LTB Builders & Construction
NC 2016 | K10 | Region XII | Sarangani | 130463 | Kaltuad Es | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6520116.768 |  |  | Completed | 1 |  |  | P00076045MN-CW1 | 16ME0174 |  |  | 2016-12-05 |  | 2016-12-23 | Legacy Construction
NC 2016 | K10 | Region XII | Sarangani | 304527 | Kiamba National High School | Kiamba | 0 | 1 | 16 | 4STY16CL | BATCH 9 CL | 31143449.222 |  |  | Completed | 1 |  |  | P000743398MN-CW1 | 16ME0122 |  |  | 2016-08-09 |  | 2016-09-13 | R.Semilla Construction & Marketing
NC 2016 | K10 | Region XII | Sarangani | 304527 | Kiamba National High School | Kiamba | 0 |  | 1 | 1STY1CL | BATCH 9 CL | 1183053.5453 |  |  | Completed | 1 |  |  | P00074339MN-CW1 | 16ME0127
NC 2016 | K10 | Region XII | Sarangani | 130428 | Ladol Elementary School | Alabel (Capital) | 0 | 1 | 8 | 2STY4CL | BATCH 7 CL | 12820255.1921 |  |  | Completed | 1
NC 2016 | K10 | Region XII | Sarangani | 208014 | Lanao Kapanglao Es | Glan | 0 | 1 | 9 | 1STY3CL | BATCH 13 CL | 10173410.5572 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 | 1 | 32 | 4STY16CL | BATCH 13 CL | 62288952.7915 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 |  | 12 | 4STY12CL | BATCH 13 CL | 25696006.5788 |  |  | Completed | 1 |  |  | P00076042MN-CW1 | 16ME0172 |  |  | 2016-12-05 |  | 2016-12-29 | Jargon Construction & Supply
NC 2016 | SHS | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | Glan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2264970.5238 |  |  | Completed | 1 |  |  | P00076043MN-CW1 | 16ME0180 |  |  | 2016-12-05 |  | 2016-12-22 | DJE Design Builders
NC 2016 | SHS | Region XII | Sarangani | 130466 | Lumigo Is | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6659035.9093 |  |  | Completed | 1
NC 2016 | SHS | Region XII | Sarangani | 130466 | Lumigo Is | Glan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2307549.6433 |  |  | Completed | 1
NC 2016 | K10 | Region XII | Sarangani | 304531 | Lun Padidu National High School | Malapatan | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 35028414.292 |  |  | Completed | 1 |  |  | P00074344MN-CW1 | 16ME0138 |  |  | 2016-06-29 |  | 2016-08-01 | Curveline Construction
NC 2016 | K10 | Region XII | Sarangani | 304531 | Lun Padidu National High School | Malapatan | 0 |  | 4 | 2STY4CL | BATCH 9 CL | 6414681.6735 |  |  | Completed | 1 |  |  | P00074345MN-CW1 | 16ME0130 |  |  | 2016-06-29 |  | 2016-08-01 | Curveline Construction
NC 2016 | K10 | Region XII | Sarangani | 304534 | Malalag National High School | Maitum | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 36822205.5095 |  |  | Completed | 1 |  |  | P00074342MN-CW1 | 16ME0136 |  |  | 2016-07-08 |  | 2016-08-01 | AB Vision Eng'g & Construction
NC 2016 | K10 | Region XII | Sarangani | 304534 | Malalag National High School | Maitum | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17898232.0111 |  |  | Completed | 1 |  |  | P00074343MN-CW1 | 16ME0132 |  |  | 2016-08-09 |  | 2016-08-31 | R. Semilla Construction & Marketing
NC 2016 | K10 | Region XII | Sarangani | 304535 | Malandag National High School | Malungon | 0 | 1 | 20 | 4STY20CL | BATCH 9 CL | 35087749.8435 |  |  | Completed | 1 |  |  | P00074348MN-CW1 | 16ME0137 |  |  | 2016-07-08 |  | 2016-08-11 | J.G. Oranza Construction
NC 2016 | K10 | Region XII | Sarangani | 304535 | Malandag National High School | Malungon | 0 |  | 9 | 3STY9CL | BATCH 9 CL | 17051169.4911 |  |  | Completed | 1 |  |  | P00074349MN-CW1 | 16ME0133 |  |  | 2016-07-08 |  | 2016-08-10 | J.G. Oranza Construction
NC 2016 | SHS | Region XII | Sarangani | 304537 | Malapatan Nhs | Malapatan | 0 | 1 | 36 | 4STY12CL | BATCH 9 CL | 74555902.3581 |  |  | Completed | 1 |  |  | P00074346MN-CW1 | 16ME0126 |  |  |  |  | 2016-09-26 | LHE Construction & Industrial Services
NC 2016 | SHS | Region XII | Sarangani | 304537 | Malapatan Nhs | Malapatan | 0 |  | 6 | 2STY6CL | BATCH 9 CL | 8431606.7031 |  |  | Completed | 1 |  |  | P00074347MN-CW1 | 16ME0131 |  |  | 2016-08-10 |  | 2016-08-30 | Palmares General Merchandise
NC 2016 | SHS | Region XII | Sarangani | 304538 | Malungon Nhs | Malungon | 0 | 1 | 10 | 2STY10CL | BATCH 3 CL | 13722509.59 |  |  | Completed | 1 |  |  | P00070653MN-CW1 | 16ME0113 |  |  | 2016-08-10 |  | 2016-08-30 | Freden Construction
NC 2016 | K10 | Region XII | Sarangani | 130564 | Millona Upper Suyan Es | Malapatan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8311652.1846 |  |  | Completed | 1 |  |  |  | 16ME0176 |  |  | 2016-12-27 |  | 2017-02-13 | Curveline Construction
NC 2016 | K10 | Region XII | Sarangani | 130564 | Millona Upper Suyan Es | Malapatan | 0 |  | 2 | 1STY2CL | BATCH 13 CL | 2195933.542 |  |  | Completed | 1 |  |  |  | 16ME0181 |  |  | 2016-12-27 |  | 2017-02-13 | Curveline Construction
NC 2016 | SHS | Region XII | Sarangani | 500261 | Roque Adarna Is | Glan | 0 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13109259.47 |  |  | Completed | 1 |  |  | P00070650MN-CW1 | 16ME0119 |  |  | 2016-06-27 |  | 2016-08-03 | Freden Construction
NC 2016 | K10 | Region XII | Sarangani | 130477 | San Jose Es | Glan | 0 | 1 | 8 | 1STY4CL | BATCH 13 CL | 8876484.4476 |  |  | Completed | 1 |  |  |  | 16ME0175 |  |  | 2016-12-29 |  | 2017-02-13 | Yap Mabuhay Enterprises, Inc.
NC 2016 | SHS | Region XII | Sarangani | 316601 | San Vicente Nhs | Glan | 0 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13099717.72 |  |  | Completed | 1 |  |  | P00070651MN-CW1 | 16ME0118 |  |  | 2016-06-27 |  | 2016-07-25 | FFJJ Construction
NC 2016 | K10 | Region XII | Sarangani | 208040 | Segafu Esgapo Ps | Glan | 0 | 1 | 6 | 1STY3CL | BATCH 13 CL | 6782273.7048 |  |  | Completed | 1
NC 2016 | K10 | Region XII | Sarangani | 130485 | Young Es | Glan | 0 | 1 | 9 | 1STY3CL | BATCH 13 CL | 9823766.482 |  |  | Completed | 1 |  |  |  | 16ME0177 |  |  | 2017-12-29 |  | 2017-02-13 | LTB Builders & Construction
NC 2016 | K10 | Region XII | South Cotabato | 304544 | Bentung Sulit National High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.25 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-09-23 | FH GOPITEO CONSTRUCTION & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130852 | Bukang Liwayway Es | Tampakan | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-09-30 | NIRVANA CONST. & SUPPLIES
NC 2016 | K10 | Region XII | South Cotabato | 130718 | Bukay-Eel Elementary School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1988000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-09-23 | FFJJ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 304576 | Cebuano National High School | Tupi | 1 |  | 4 | 2STY4CL | BATCH 3 CL | 6489337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-09-23 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304576 | Cebuano National High School | Tupi | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 2016-09-30 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316707 | Danlag High School | Tampakan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6549337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-10-26 | MARCUS CONST. & SUPPLIES
NC 2016 | K10 | Region XII | South Cotabato | 316717 | Emiliano P. Baquial National High School | Tupi | 1 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15281327.92 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-09-23 | FFJJ CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 304545 | Glamang High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-09-23 | CAV BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304545 | Glamang High School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1963000 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-26 | CAV BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130723 | Guaza Elementary School | Polomolok | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1130000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-10-26 | FFJJ CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 304562 | Jose D. Escabilio National High School | Tupi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2479549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-26 | FFJJ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 304562 | Jose D. Escabilio National High School | Tupi | 1 | 1 | 2 | 1STY2CL | BATCH 3 CL | 2008000 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-09-23 | FFJJ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 130739 | Jose Natividad Elementary School | Polomolok | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2841000 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-10-26 | NIRVANA CONST. & SUPPLIES
NC 2016 | K10 | Region XII | South Cotabato | 130740 | Juan Bayan Elementary School | Polomolok | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2841000 |  |  | Completed | 1 | [6 empty] | 2016-09-13 |  |  | TRIPLE Z MERCHANDISING & ELEC. SERVICES
NC 2016 | TECHVOC | Region XII | South Cotabato | 304564 | Kablon National High School | Tupi | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2449549.27 |  |  | Completed | 1 | [6 empty] | 2016-06-30 |  | 2016-09-02 | VERGUZ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 316711 | Lampitak High School | Tampakan | 1 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2846000 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-09-30 | NIRVANA CONST. & SUPPLIES
NC 2016 | K10 | Region XII | South Cotabato | 316712 | Landan National High School | Polomolok | 1 | 1 | 10 | 2STY10CL | BATCH 3 CL | 12971310.09 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 2016-10-26 | R.R. SEISMUNDO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 208526 | Ludovico I. Senador Es | Tupi | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-26 | JARGON CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 304556 | Maltana Nhs | Tampakan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-24 | MARBEL DYNAMIC BUILDERS
NC 2016 | SHS | Region XII | South Cotabato | 304556 | Maltana Nhs | Tampakan | 1 | 1 | 8 | 2STY8CL | BATCH 5 CL | 11037342.59 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-09-23 | MARBEL DYNAMIC BUILDERS
NC 2016 | TECHVOC | Region XII | South Cotabato | 316702 | Pablo Valencia High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2439549.27 |  |  | Completed | 1 | [6 empty] | 2016-06-30 |  | 2016-08-26 | VERGUZ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 316702 | Pablo Valencia High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-09-23 | SOPHIA CONSTRUCTION & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 304578 | Palkan High School | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2439549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-26 | SOPHIA CONSTRUCTION & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304578 | Palkan High School | Polomolok | 1 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8404965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-09-08 | SOPHIA CONSTRUCTION & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 304559 | Poblacion Polomolok Nhs | Polomolok | 1 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 7288647.81 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-09-02 | LEIGHCHEEN CONSTRUCTION CORPORATION
NC 2016 | SHS | Region XII | South Cotabato | 304559 | Poblacion Polomolok Nhs | Polomolok | 1 | 1 | 40 | 4STY20CL | BATCH 3 CL | 62505780.54 |  |  | Completed | 1 | [6 empty] | 2016-07-27 |  | 2016-10-21 | LEGACY CONST. (JOINT VENTURE) & VERGUZ CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130745 | Polomolok Central Elementary School | Polomolok | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11027342.59 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-20 | AB VISION CONST.
NC 2016 | TECHVOC | Region XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-21 | VERGUZ CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 15271327.92 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-24 | R. SEMILLA CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304560 | Polomolok Nhs | Polomolok | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31252890.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-09-23 | LEGACY CONST. (JOINT VENTURE) & VERGUZ CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130907 | Polonuling Central Elementary School | Tupi | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-12-06 |  | 2017-01-27 | LLM Concrete Products
NC 2016 | TECHVOC | Region XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 4859098.54 |  |  | Completed | 1 | [6 empty] | 2016-06-30 | 2016-07-26 | 2016-08-26 | SHEPPERD CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 |  | 9 | 3STY9CL | BATCH 5 CL | 15271327.92 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-10-26 | R.R SEISMUNDO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304567 | Silway-8 National High School | Polomolok | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31252890.27 |  |  | Completed | 1 | [6 empty] | 2016-10-24 |  | 2016-11-29 | VERTICAL BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 316716 | Tablu High School | Tampakan | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6509337.64 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-24 | MARCUS CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 304570 | Tampakan National High School | Tampakan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2434549.27 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-24 | MARBEL DYNAMIC BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 304570 | Tampakan National High School | Tampakan | 1 | 1 | 20 | 4STY20CL | BATCH 5 CL | 31272890.27 |  |  | Completed | 1 | [6 empty] | 2016-08-02 |  | 2016-09-30 | F.H. GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304563 | Teodoro P. Prudente National High School | Tupi | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6509337.64 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-10-26 | CEK CONST. & WATER SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 304575 | Tupi Nhs | Tupi | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26852890.27 |  |  | Completed | 1 | [6 empty] | 2016-07-28 |  | 2016-10-24 | R. SEMILLA CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304575 | Tupi Nhs | Tupi | 1 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62505780.54 |  |  | Completed | 1 | [6 empty] | 2016-08-03 |  | 2016-10-24 | FFJJ CONST.
NC 2016 | K10 | Region XII | South Cotabato | 304577 | Upper Klinan High School | Polomolok | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1968000 |  |  | Completed | 1 | [6 empty] | 2016-09-08 |  | 2016-09-29 | VERGUZ CONST.
NC 2016 | K10 | Region XII | South Cotabato | 208505 | Abboy Es | Lake Sebu | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 3002592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-28 | DALANON CONST., REF. SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316727 | Aflek Nhs - Edwards Nhs Annex | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8264965.05 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 2017-01-30 | MFN BUILDERS
NC 2016 | SHS | Region XII | South Cotabato | 304543 | Banga Nhs | Banga | 2 | 1 | 18 | 3STY9CL | BATCH 13 CL | 33236921.424 |  |  | Completed | 1 | [6 empty] | 2017-05-08 |  | 2017-06-14 | REYDAN BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130799 | Basag Elementary School | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3687968.78 |  |  | Completed | 1 | [6 empty] | 2016-08-12 |  | 2016-11-07 | HAQ CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 316720 | Basag Nhs - Tboli Annex | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 2016-08-25 | MIGO CONST.
NC 2016 | SHS | Region XII | South Cotabato | 316720 | Basag Nhs - Tboli Annex | T'Boli | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6469337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-25 | MIGO CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130801 | Bianan Es | T'Boli | 2 |  | 1 | 1STY1CL | BATCH 3 CL | 1109434.19 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-24 | COFEJOK CONST. & SUPPLY CORP.
NC 2016 | K10 | Region XII | South Cotabato | 130801 | Bianan Es | T'Boli | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-08-24 |  | 2016-11-04 | HVC SAGITTARIUS COMMERCIAL & COMMERCIAL
NC 2016 | K10 | Region XII | South Cotabato | 130660 | Blit Es | Lake Sebu | 2 | 1 | 6 | 1STY3CL | BATCH 3 CL | 6145184.88 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-28 | DALANON CONST., REF. SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 304565 | Bukay Pait Nhs | Tantangan | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.59 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-23 | REYDAN BUILDERS
NC 2016 | SHS | Region XII | South Cotabato | 304546 | Centrala Nhs | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-08 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 316713 | Colongulo Nhs - Libertad Nhs Annex | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-10-03 |  | 2016-11-07 | MIGO CONST.
NC 2016 | K10 | Region XII | South Cotabato | 208503 | Coong Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-27 | STONELINE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130807 | Datal Dlanag Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-08-31 | CEK CONST. & WATER SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130809 | Datal Tablo Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1973606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-08-31 | CEK CONST. & WATER SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130768 | Defensor Es | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1864740.17 |  |  | Completed | 1 | [6 empty] | 2016-08-23 |  | 2016-09-27 | MRS BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130810 | Demamis Es | T'Boli | 2 |  | 2 | 1STY2CL | BATCH 3 CL | 1988606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-27 | STONELINE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130810 | Demamis Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2882592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 | 2016-12-27 | 2016-12-27 | STONELINE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130811 | Desawo Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-08-23 | 2016-09-27 | 2016-09-27 | NASCON BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130664 | Diente Es | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1968606 |  |  | Completed | 1 | [6 empty] | 2016-08-12 |  | 2016-11-07 | HAQ CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 304547 | Edwards Nhs | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 2016-09-27 | MRS BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316914 | El Nonok Integrated School | Banga | 2 | 1 | 12 | 2STY6CL | BATCH 3 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 304548 | Guinsang-An Nhs | Santo Niño | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-24 | ISULAN ECT CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304548 | Guinsang-An Nhs | Santo Niño | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130666 | Haliland Es | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1968606 |  |  | Completed | 1 | [6 empty] | 2016-08-11 |  | 2016-11-07 | HAQ CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 130702 | Julio Zuyco Memorial Es | Norala | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1814740.17 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-10 | LEIGHCHEEN CONST. CORP.
NC 2016 | K10 | Region XII | South Cotabato | 130629 | Kataan Es | Banga | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-24 | COFEJOK CONST. & SUPPLY CORP.
NC 2016 | SHS | Region XII | South Cotabato | 304549 | Katipunan Nhs | Santo Niño | 2 | 1 | 8 | 2STY4CL | BATCH 7 CL | 12638675.28 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-24 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130816 | Kebuling Es | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3717968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-26 |  | 2016-08-31 | SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 208519 | Kiantay Es | Surallah | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2852592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-28 | DALANON CONS., REF.
NC 2016 | SHS | Region XII | South Cotabato | 316708 | Kibang Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11057342.59 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 2017-01-20 | AGUERO CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 316926 | Laconon Integrated Hs | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3667968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 2016-08-30 | COFEJOK CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316919 | Lake Soluton Integrated School | Lake Sebu | 2 | 1 | 12 | 2STY6CL | BATCH 7 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 316704 | Lamba Nhs - Banga Nhs Annex | Banga | 2 | 1 | 8 | 2STY8CL | BATCH 5 CL | 10877342.59 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-23 | REYDAN BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130819 | Lambangan Es | T'Boli | 2 | 1 | 8 | 2STY4CL | BATCH 13 CL | 12678675.28 |  |  | Completed | 1 | [6 empty] | 2017-04-03 |  | 2017-05-06 | NASCON BUILDERS
NC 2016 | TECHVOC | Region XII | South Cotabato | 304553 | Lambontong Nhs | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.42 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-23 | HVC SAGITTARIUS
NC 2016 | SHS | Region XII | South Cotabato | 304553 | Lambontong Nhs | Surallah | 2 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-23 | HVC SAGITTARIUS
NC 2016 | K10 | Region XII | South Cotabato | 130820 | Lambuling Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1958606.04 |  |  | Completed | 1 | [6 empty] | 2016-12-01 | 2016-12-28 | 2016-12-27 | KGD BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130673 | Lamcade Es | Lake Sebu | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8294695.05 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-30 | BETTER WORKS CONST.
NC 2016 | TECHVOC | Region XII | South Cotabato | 304552 | Lamian Nhs | Surallah | 2 | 1 | 3 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 7288647.81 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | MIGO CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304552 | Lamian Nhs | Surallah | 2 | 1 | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1 | [6 empty] | 2016-03-22 |  | 2016-06-27 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130823 | Lamla Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [8 empty] | 2016-11-04 | MRS BUILDERS & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 316710 | Lamsugod National High School | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | REYDAN BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 316710 | Lamsugod National High School | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 5 CL | 1814740.17 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-24 | MIGO CONST.
NC 2016 | TECHVOC | Region XII | South Cotabato | 304554 | Lapuz Nhs | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | FH GOPITEO
NC 2016 | SHS | Region XII | South Cotabato | 304554 | Lapuz Nhs | Norala | 2 | 1 | 6 | 1STY6CL | BATCH 5 CL | 5373000 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | FH GOPITEO
NC 2016 | SHS | Region XII | South Cotabato | 304555 | Libertad Nhs | Surallah | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1 | [6 empty] | 2017-05-08 |  | 2017-06-14 | FH GOPITEO
NC 2016 | SHS | Region XII | South Cotabato | 304555 | Libertad Nhs | Surallah | 2 |  | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region XII | South Cotabato | 316917 | Lubol Is | Surallah | 2 | 1 | 8 | 2STY4CL | BATCH 3 CL | 12838675.28 |  |  | Completed | 1 | [8 empty] | 2017-02-20 | REYDAN BUILDERS
NC 2016 | SHS | Region XII | South Cotabato | 316921 | Lusok Is | T'Boli | 2 | 1 | 8 | 2STY4CL | BATCH 5 CL | 12788675.28 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-09 | FH GOPITEO
NC 2016 | TECHVOC | Region XII | South Cotabato | 316719 | Maan Nhs - Tboli Annex | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2459549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-23 |  | 2016-06-24 | ROCKSTONE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 316719 | Maan Nhs - Tboli Annex | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8269965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-23 | REYDAN BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130875 | Maibo Es | Tantangan | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 2016-08-10 | PALMARES GEN. MDSE.
NC 2016 | SHS | Region XII | South Cotabato | 316714 | Malaya Nhs - Banga Nhs Annex | Banga | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | YAP MABUHAY
NC 2016 | SHS | Region XII | South Cotabato | 316714 | Malaya Nhs - Banga Nhs Annex | Banga | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-24 | YAP MABUHAY
NC 2016 | K10 | Region XII | South Cotabato | 316912 | Mangilala Integrated School | Tantangan | 2 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-24 | MIGO CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 304551 | Ned National High School | Lake Sebu | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2579549.27 |  |  | Completed | 1 | [6 empty] | 2016-10-12 |  | 2016-11-09 | DALANON CONST. REF SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 304551 | Ned National High School | Lake Sebu | 2 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13038675.28 |  |  | Completed | 1 | [6 empty] | 2016-08-11 |  | 2016-11-07 | FH GOPITEO CONST. & SUPPLY
NC 2016 | TECHVOC | Region XII | South Cotabato | 316706 | New Dumangas Nhs | T'Boli | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 2016-11-04 | HVC SAGITTARIUS
NC 2016 | SHS | Region XII | South Cotabato | 316706 | New Dumangas Nhs | T'Boli | 2 | 1 | 6 | 2STY6CL | BATCH 5 CL | 8214965.05 |  |  | Completed | 1 | [8 empty] | 2016-11-04 | HVC SAGITTARIUS
NC 2016 | K10 | Region XII | South Cotabato | 316911 | New Lambunao Integrated Hs | Tantangan | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-09 | ISULAN ECT CONST. & GEN. MDSE.
NC 2016 | TECHVOC | Region XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [8 empty] | 2016-06-24 | FH GOPITEO CONST. & SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 |  | 12 | 3STY12CL | BATCH 5 CL | 18222268.79 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-24 | FH GOPITEO CONST. & SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 304557 | Norala Nhs | Norala | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-07-13 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130681 | Odos Angkoy Es | Lake Sebu | 2 |  | 4 | 2STY4CL | BATCH 3 CL | 6359337.64 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 2016-11-09 | EC SOLICON BUILDERS & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130681 | Odos Angkoy Es | Lake Sebu | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8274695.05 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-27 | AGUERO CONST.
NC 2016 | SHS | Region XII | South Cotabato | 304558 | Panay Nhs | Santo Niño | 2 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130682 | Proper Ned Es | Lake Sebu | 2 | 1 | 6 | 1STY3CL | BATCH 3 CL | 5905184.88 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 2016-11-09 | CEK CONST. & WATER SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 316709 | Proper Ned Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6519337.64 |  |  | Completed | 1 | [6 empty] | 2016-10-11 |  | 2016-11-09 | CEK CONST. & WATER SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316920 | Pulo Subong Integrated Hs | Lake Sebu | 2 | 1 | 4 | 1STY2CL | BATCH 3 CL | 4177212 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-28 | DALANON CONST. REF. SUPPLY
NC 2016 | SHS | Region XII | South Cotabato | 316705 | Punong Grande Nhs - Banga Nhs Annex | Banga | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-07-25 | MIGO CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 316723 | Rizal 3 National High School- Banga Nhs Annex | Banga | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2802592.44 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-09 | FH GOPITEO CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 208530 | Salabanog Es | T'Boli | 2 | 1 | 9 | 1STY3CL | BATCH 3 CL | 8647777.32 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-27 | STONELINE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130840 | Salacafe Es | T'Boli | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3687968.78 |  |  | Completed | 1 | [6 empty] | 2016-10-12 |  | 2016-11-09 | HAQ CONSTRUCTION
NC 2016 | TECHVOC | Region XII | South Cotabato | 316703 | San Jose Nhs | Banga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 2016-08-25 | MIGO CONSTRUCTION
NC 2016 | SHS | Region XII | South Cotabato | 316703 | San Jose Nhs | Banga | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3667968.78 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-09 | FH GOPITEO CONST.
NC 2016 | SHS | Region XII | South Cotabato | 316715 | San Jose Nhs - Lapuz Nhs Annex | Norala | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-23 | C.A. BETALAC CONST.
NC 2016 | TECHVOC | Region XII | South Cotabato | 304566 | San Miguel National High School | Norala | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-23 | ROCKSTONE CONSTRUCTION
NC 2016 | SHS | Region XII | South Cotabato | 304566 | San Miguel National High School | Norala | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-24 | MIGO CONSTRUCTION
NC 2016 | SHS | Region XII | South Cotabato | 316718 | San Vicente Nhs - Banga Nhs Annex | Banga | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-09 | SOPHIA CONST. & SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 316724 | Sergio L. Legayada Nhs - Norala Nhs Annex | Norala | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 8214965.05 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-24 | MIGO CONSTRUCTION
NC 2016 | K10 | Region XII | South Cotabato | 130713 | Simsiman Es | Norala | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1012049.65 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-10 | LEIGHCHEEN CONST. CORP.
NC 2016 | SHS | Region XII | South Cotabato | 304568 | Sto. Niño Nhs | Santo Niño | 2 | 1 | 24 | 3STY12CL | BATCH 1 CL | 36486537.58 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-27 | BETTERWORK CONST
NC 2016 | TECHVOC | Region XII | South Cotabato | 304569 | Sto. Niño Nsat | Santo Niño | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | MIGO CONSTRUCTION
NC 2016 | SHS | Region XII | South Cotabato | 304569 | Sto. Niño Nsat | Santo Niño | 2 | 1 | 12 | 2STY6CL | BATCH 5 CL | 16429930.1 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-23 | REYDAN BUILDERS
NC 2016 | TECHVOC | Region XII | South Cotabato | 316701 | Surallah Nhs | Surallah | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | MIGO CONSTRUCTION
NC 2016 | SHS | Region XII | South Cotabato | 316701 | Surallah Nhs | Surallah | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-03-22 |  | 2016-06-23 | KGD BUILDERS
NC 2016 | K10 | Region XII | South Cotabato | 130785 | Talahik Es | Surallah | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-07-12 |  | 2016-08-10 | LEIGHCHEEN CONST. CORP.
NC 2016 | K10 | Region XII | South Cotabato | 130845 | Talcon Es | T'Boli | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606.04 |  |  | Completed | 1 | [6 empty] | 2016-08-23 |  | 2016-09-27 | NASCON BUILDERS
NC 2016 | TECHVOC | Region XII | South Cotabato | 316918 | Talisay Integrated Hs | Lake Sebu | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4859098.54 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 2016-08-24 | COFEJOK CONST. & SUPPLY CORP.
NC 2016 | K10 | Region XII | South Cotabato | 316918 | Talisay Integrated Hs | Lake Sebu | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1 | [6 empty] | 2016-03-21 |  | 2016-06-24 | KGD BUILDERS
NC 2016 | TECHVOC | Region XII | South Cotabato | 304572 | Tantangan Nhs | Tantangan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2429549.27 |  |  | Completed | 1 | [6 empty] | 2016-03-08 |  | 2016-06-24 | REYDAN BUILDERS
NC 2016 | SHS | Region XII | South Cotabato | 304572 | Tantangan Nhs | Tantangan | 2 | 1 | 15 | 3STY15CL | BATCH 5 CL | 21383013.45 |  |  | Completed | 1 | [6 empty] | 2016-03-14 |  | 2016-06-24 | FH GOPITEO
NC 2016 | SHS | Region XII | South Cotabato | 304573 | Tantangan Nths | Tantangan | 2 | 1 | 16 | 2STY8CL | BATCH 3 CL | 21754685.18 |  |  | Completed | 1 | [6 empty] | 2016-07-11 |  | 2016-08-09 | FH GOPITEO
NC 2016 | SHS | Region XII | South Cotabato | 304574 | Tboli Nhs | T'Boli | 2 | 1 | 36 | 4STY12CL | BATCH 1 CL | 66517030.86 |  |  | Completed | 1 | [6 empty] | 2016-02-22 |  | 2016-08-30 | FFJJ CONST. (JV) & BETTER WORKS CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130690 | T'Boyung Es | Lake Sebu | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-28 | DALANON CONST., REF. SUPPLY
NC 2016 | K10 | Region XII | South Cotabato | 130848 | Tuburan Es Realigned To T'Bolok Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-10-27 |  | 2016-11-28 | COFEJOK CONST. & SUPPLY CORP.
NC 2016 | K10 | Region XII | South Cotabato | 130658 | Tuburan Es Realigned To Bakdulong Es | Lake Sebu | 2 | 1 | 4 | 1STY4CL | BATCH 3 CL | 3867968.78 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-02 | STONELINE CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130850 | Tudok Es | T'Boli | 2 | 1 | 3 | 1STY3CL | BATCH 3 CL | 2952592.44 |  |  | Completed | 1 | [6 empty] | 2016-12-01 |  | 2016-12-27 | STONELINE CONST.
NC 2016 | SHS | Region XII | South Cotabato | 316725 | Upper Maculan Nhs - Lake Sebu Nhs Annex | Lake Sebu | 2 | 1 | 2 | 1STY2CL | BATCH 3 CL | 1938606 |  |  | Completed | 1 | [6 empty] | 2016-07-18 |  | 2016-08-25 | C.A BETALAC CONST.
NC 2016 | K10 | Region XII | South Cotabato | 130793 | V. L. Barber Es | Surallah | 2 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1109434.19 |  |  | Completed | 1 | [8 empty] | 2016-11-04 | HVC SAGITTARIUS
NC 2016 | K10 | Region XII | Sultan Kudarat | 130956 | Balisan Ps | Columbio | 1 | 1 | 1 | 1STY1CL | BATCH 7 CL | 1059556.05 |  |  | Completed | 1 |  |  | P00072543MN_CW1 | 16MF0059 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | SHS | Region XII | Sultan Kudarat | 304585 | Bambad Nhs | Isulan | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 32317976 |  |  | Completed | 1 |  |  | P00072536MN_CW1 | 16MF0076 | 2016-06-23 | 2016-07-01 | 2016-07-15 | 2016-08-15
NC 2016 | K10 | Region XII | Sultan Kudarat | 131207 | Bayawa Es | President Quirino | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2737525.25 |  |  | Completed | 1 |  |  | P00072548MN_CW1 | 16MF0058 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | K10 | Region XII | Sultan Kudarat | 304588 | Columbio National High School | Columbio | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30866854.06 |  |  | Completed | 1 |  |  | P00072537MN_CW1 | 16MF0071 | 2016-06-23 | 2016-07-01 | 2016-07-15 | 2016-08-15
NC 2016 | K10 | Region XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 | 1 | 30 | 3STY15CL | BATCH 13 CL | 47012629.59 |  |  | Completed | 1
NC 2016 | K10 | Region XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 |  | 12 | 3STY12CL | BATCH 13 CL | 20000467.74 |  |  | Completed | 1
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304590 | Isulan National High School | Isulan (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1 |  |  |  | 16MF0030 | 2016-02-22 | 2016-03-02 | 2016-03-10
NC 2016 | SHS | Region XII | Sultan Kudarat | 304594 | Kalanawe Ii Nhs | President Quirino | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 9002105.5 |  |  | Completed | 1 |  |  | P00072542MN_CW1 | 16MF0067 | 2016-05-18 | 2016-06-01 | 2016-06-13 | 2016-07-18 | 2016-08-03 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304594 | Kalanawe Ii Nhs | President Quirino | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072670MN_CW1 | 16MF0056 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | FPJ Const. & Supply
NC 2016 | SHS | Region XII | Sultan Kudarat | 304595 | Kapingkong Nhs | Lambayong | 1 | 1 | 18 | 3STY9CL | BATCH 7 CL | 30866850.06 |  |  | Completed | 1 |  |  | P00072539MN_CW1 | 16MF0070 | 2016-05-18 | 2016-06-01 | 2016-06-13 | 2016-07-18 | 2016-08-03 | Blimex Construction & Supply
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304595 | Kapingkong Nhs | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072667MN_CW1 | 16MF0053 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | K10 | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 32577116 |  |  | Completed | 1 |  |  | P00072534MN_CW1 | 16MF0074 | 2016-06-09 | 2016-06-17 | 2016-06-30 | 2016-07-26
NC 2016 | K10 | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26044086 |  |  | Completed | 1 |  |  | P00072535MN_CW1 | 16MF0072 | 2016-06-23 | 2016-07-01 | 2016-07-15 | 2016-08-15
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | Lambayong (Mariano Marcos) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00072665MN_CW1 | 16MF0051 | 2016-07-28 | 2016-08-05 | 2016-08-18
NC 2016 | K10 | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 | 1 | 12 | 3STY12CL | BATCH 1 CL | 20522649.79 |  |  | Completed | 1 |  |  | P00070177MN_CW1 | 16MF0064 | 2016-05-18 | 2016-06-01 | 2016-06-13
NC 2016 | K10 | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 |  | 10 | 2STY10CL | BATCH 1 CL | 14684021.713 |  |  | Completed | 1 |  |  | P00070178MN_CW1 | 16MF0038 | 2016-02-22 | 2016-03-02 | 2016-03-14 | 2016-05-11 | 2016-05-26 | Gemma Const. Supply Inc.
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | Lutayan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 2 TVL | 2831034.44 |  |  | Completed | 1 |  |  | P00070223MN_CW1 | 16MF0029 | 2016-02-22 | 2016-03-02 | 2016-03-10 | 2016-05-11 | 2016-05-26 | Gemma Const Supply Inc.
NC 2016 | SHS | Region XII | Sultan Kudarat | 304607 | Madanding Nhs | Lambayong | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15433427 |  |  | Completed | 1 |  |  | P00072540MN_CW1 | 16MF0069 | 2016-05-18 | 2016-06-01 | 2016-06-13 | 2016-07-18 | 2016-08-03 | Stoneline Construction
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304607 | Madanding Nhs | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072668MN_CW1 | 16MF0054 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | CEK Const. & Supply
NC 2016 | SHS | Region XII | Sultan Kudarat | 304608 | Maligaya Nhs | Lambayong | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6812821 |  |  | Completed | 1 |  |  | P00072544MN_CW1 | 16MF0048 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Cofejok Const. & Supply Corp.
NC 2016 | K10 | Region XII | Sultan Kudarat | 131152 | Mangudadatu Es | Lutayan | 1 | 1 | 4 | 1STY4CL | BATCH 7 CL | 3764244 |  |  | Completed | 1 |  |  | P00072546MN_CW1 | 16MF0060 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-11 | Minrock Multi-Builders
NC 2016 | SHS | Region XII | Sultan Kudarat | 304614 | New Pangasinan Nhs | Isulan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11418798 |  |  | Completed | 1 |  |  | P00072538MN_CW1 | 16MF0066 | 2016-05-18 | 2016-06-01 | 2016-06-13 | 2016-07-18 | 2016-08-03 | C.S. Construction & Supply
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304614 | New Pangasinan Nhs | Isulan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072668MN_CW1 | 16MF0054 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | CEK Const. & Supply
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304598 | Pimbalayan Nhs - Lambayong Annex | Lambayong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2770298.44 |  |  | Completed | 1 |  |  | P00072669MN_CW1 | 16MF0055 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Minrock Multi-Builders
NC 2016 | SHS | Region XII | Sultan Kudarat | 304598 | Pimbalayan Nhs - Lambayong Annex | Lambayong | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4425866.5 |  |  | Completed | 1 |  |  | P00072541MN_CW1 | 16MF0049 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | K10 | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | President Quirino | 1 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26149190 |  |  | Completed | 1 |  |  | P00070726MN_CW1 | 16MF0062 | 2016-06-23 | 2016-07-01 | 2016-07-15 | 2016-08-15
NC 2016 | K10 | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | President Quirino | 1 |  | 6 | 2STY6CL | BATCH 3 CL | 8601369.5 |  |  | Completed | 1 |  |  | P00070727MN_CW1 | 16MF0037 | 2016-02-22 | 2016-03-02 | 2016-03-10 | 2016-05-11 | 2016-05-26 | Robeth Gen. Mdse. Const. & Supply
NC 2016 | K10 | Region XII | Sultan Kudarat | 131160 | Sisiman Es | Lutayan | 1 | 1 | 5 | 1STY5CL | BATCH 7 CL | 4425866.5 |  |  | Completed | 1 |  |  | P00072547MN_CW1 | 16MF0050 | 2016-05-05 | 2016-05-13 | 2016-05-26 | 2016-06-21 | 2016-07-08 | Minrock Multi-Builders
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304625 | Telafas National High School | Columbio | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2692979.7865 |  |  | Completed | 1 |  |  |  | 16MF0079 | 2016-07-28 | 2016-08-05 | 2016-08-18
NC 2016 | K10 | Region XII | Sultan Kudarat | 131107 | Zeneben Es | Lambayong | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1978047.5 |  |  | Completed | 1 |  |  | P00072545MN_CW1 | 16MF0057 | 2016-07-28 | 2016-08-05 | 2016-08-18
NC 2016 | K10 | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 16740000 |  |  | Completed | 1 |  |  | P00074353MN | 16MH0027 | 2016-05-27 | 2016-07-07 | 2016-07-19 | 2016-07-29 |  | FFJJ Construction
NC 2016 | K10 | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 |  | 6 | 3STY6CL | BATCH 9 CL | 10537131.51 |  |  | Completed | 1 |  |  | P00074354MN | 16MH0030 | 2016-05-27 | 2016-07-07 | 2016-07-19 | 2016-07-29 |  | JV Constech
NC 2016 | K10 | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 |  | 10 | 2STY10CL | BATCH 9 CL | 13975000 |  |  | Completed | 1 |  |  | P00074355MN | 16MH0028 | 2016-05-27 | 2016-07-07
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | Kalamansig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2688700 |  |  | Completed | 1 |  |  | P00074623MN | 16MH0029 | 2016-05-27 | 2016-06-06 | 2016-06-21 | 2016-07-04 | 2016-07-17 | Jargon Const. & Supply
NC 2016 | K10 | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | Lebak | 2 | 1 | 24 | 3STY12CL | BATCH 9 CL | 33480000 |  |  | Completed | 1 |  |  | P00074356MN | 16MH0026 | 2016-05-27 | 2016-07-07 | 2016-07-19 | 2016-07-29 |  | FFJJ Construction
NC 2016 | K10 | Region XII | Sultan Kudarat | 304613 | New Panay National High School | Esperanza | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 20887500 |  |  | Completed | 1 |  |  | P00074352MN | 16MH0031 | 2016-05-27 | 2016-07-07 | 2016-07-19 | 2016-07-29 |  | FFJJ Construction
NC 2016 | TECHVOC | Region XII | Sultan Kudarat | 304613 | New Panay National High School | Esperanza | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2688700 |  |  | Completed | 1 |  |  | P00074624MN | 16MH0032 | 2016-05-27 | 2016-06-06 | 2016-06-21 | 2016-07-04 | 2016-07-17 | CEK Const. & Supply
NC 2016 | SHS | Region XII | Tacurong City | 304579 | A.S. Bernardo Mem. Nhs | City Of Tacurong | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6812821 |  |  | Completed | 1 |  |  | P00070728MNCWI | 16MF0033 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | K.A. Builders And Supply
NC 2016 | TECHVOC | Region XII | Tacurong City | 304579 | A.S. Bernardo Mem. Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00070805MNCWI | 16MF0027 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | Bandar Kutawato Const. & Supply
NC 2016 | K10 | Region XII | Tacurong City | 304620 | Rajah Muda Nhs | City Of Tacurong | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11418798 |  |  | Completed | 1 |  |  | P00070729MNCWI | 16MF0035 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | Palmares Gen. MDSE
NC 2016 | K10 | Region XII | Tacurong City | 326102 | San Emmanuel National High School-Annex | City Of Tacurong | 1 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6765435 |  |  | Completed | 1 |  |  | P00070731MNCWI | 16MF0034 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | Robeth Gen Mdse.Const & Supply
NC 2016 | SHS | Region XII | Tacurong City | 304622 | San Emmanuel Nhs | City Of Tacurong | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11418798 |  |  | Completed | 1 |  |  | P00070730MNCWI | 16MF0034 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | Palmares Gen. MDSE
NC 2016 | TECHVOC | Region XII | Tacurong City | 304622 | San Emmanuel Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2735034.44 |  |  | Completed | 1 |  |  | P00070806MNCWI | 16MF0026 | 2016-02-19 | 2016-02-26 | 2016-03-10 | 2016-05-22 | 2016-05-26 | Robeth Gen Mdse.Const & Supply
NC 2016 | TECHVOC | Region XII | Tacurong City | 304627 | V.F. Grino Mem. Nhs | City Of Tacurong | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2692979.7865 |  |  | Completed | 1 |  |  | P00075358MNCW1 | 16-MF-0078 |  |  | 2016-08-05 |  | 2016-10-07 | Robeth Gen Mdse.Const & Supply
NC 2017 | K10 | Region XII | North Cotabato | 129933 | Busaon ES | BANISILAN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2731635.73 |  |  | Completed | 1 |  |  | P00170894 | 17MD0101 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | J-ONE BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 129933 | Busaon ES | BANISILAN | 3 |  | 4 | 1STY4CL | BATCH 2 | 4762967.56 |  |  | Completed | 1 |  |  | P00170895 | 17MD0109 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | J-ONE BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 207540 | Kalalagan Elementary School | BANISILAN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 3892944.64 |  |  | Completed | 1 |  |  | P00170896 | 17MD0151 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129977 | C. Northwest ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2533232.2 |  |  | Completed | 1 |  |  | P00170897 | 17MD0102 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | NCCS
NC 2017 | SHS | Region XII | North Cotabato | 304427 | Carmen National High School | CARMEN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 3554034.32 |  |  | Completed | 1 |  |  | P00170898 | 17MD0147 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 129982 | Kibayao ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2556113.97 |  |  | Completed | 1 |  |  | P00170899 | 17MD0104 | 2017-10-20 | 2017-10-27 | 2017-11-08 |  | 2017-12-04 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 207535 | Kilabao ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2617496.91 |  |  | Completed | 1 |  |  | P00170900 | 17MD0106 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | NCCS
NC 2017 | K10 | Region XII | North Cotabato | 129962 | Lanoon ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2533232.2 |  |  | Completed | 1 |  |  | P00170901 | 17MD0105 | 2017-10-20 | 2017-10-27 | 2017-11-08 |  | 2017-12-05 | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 129967 | Malapag ES | CARMEN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 3662742.97 |  |  | Completed | 1 |  |  | P00170902 | 17MD0148 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 207521 | Malugasa ES | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2622749.31 |  |  | Completed | 1 |  |  | P00170903 | 17MD0103 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | NCCS
NC 2017 | K10 | Region XII | North Cotabato | 129973 | Tambad Elementary School | CARMEN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2647641.05 |  |  | Completed | 1 |  |  | P00170904 | 17MD0107 | 2017-10-30 | 2017-11-06 | 2017-11-18 |  | 2017-12-05 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 207545 | Dilanggalen ES | KABACAN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2602810.2 |  |  | Completed | 1 |  |  | P00170905 | 17MD0112 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | HAQ CONST.
NC 2017 | K10 | Region XII | North Cotabato | 130008 | Lower Paatan ES | KABACAN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2544546.9 |  |  | Completed | 1 |  |  | P00170906 | 17MD0111 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | MINROCK MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 316509 | Osias High School | KABACAN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2603360.82 |  |  | Completed | 1 |  |  | P00170907 | 17MD0108 | 2017-07-14 | 2017-07-21 | 2017-08-02 |  | 2017-09-04 | HAQ CONST.
NC 2017 | K10 | Region XII | North Cotabato | 130021 | Simbuhay ES | KABACAN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 3789125.23 |  |  | Completed | 1 |  |  | P00170908 | 17MD0150 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130021 | Simbuhay ES | KABACAN | 3 |  | 3 | 1STY3CL | BATCH 2 | 3789125.23 |  |  | Completed | 1 |  |  | P00170909 | 17MD0150 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130021 | Simbuhay ES | KABACAN | 3 |  | 3 | 1STY3CL | BATCH 2 | 3789125.23 |  |  | Completed | 1 |  |  | P00170909 | 17MD0150 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130022 | Simone ES | KABACAN | 3 | 1 | 3 | 1STY3CL | BATCH 2 | 3789125.23 |  |  | Completed | 1 |  |  | P00170911 | 17MD0149 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130022 | Simone ES | KABACAN | 3 |  | 3 | 1STY3CL | BATCH 2 | 3789125.23 |  |  | Completed | 1 |  |  | P00170912 | 17MD0149 | 2017-09-01 | 2017-09-08 | 2017-09-20 |  | 2017-10-13 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130023 | Tamped ES | KABACAN | 3 | 1 | 2 | 1STY2CL | BATCH 2 | 2746706.49 |  |  | Completed | 1 |  |  | P00170913 | 17MD0110 | 2017-10-20 | 2017-10-27 | 2017-11-08 |  | 2017-12-05 | ILON MULTIBUILDERS
NC 2017 | SHS | Region XII | Sarangani | 304518 | Alabel NHS | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2560000 |  |  | Completed | 1 |  |  | P00170914MN-CW1 | 17ME0086 |  |  | 2017-08-29 |  | 2017-09-22 | MARDI INFRA Builders
NC 2017 | K10 | Region XII | Sarangani | 130421 | Datu Abdullah Tondog ES | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2530000 |  |  | Completed | 1 |  |  | P00170915MN-CW1 | 17ME0085 |  |  | 2017-07-26 |  | 2017-09-05 | RNS Cons. Engineering
NC 2017 | K10 | Region XII | Sarangani | 130425 | Famorcan ES | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170916MN-CW1 | 17ME0086 |  |  | 2017-08-29 |  | 2017-09-22 | MARDI INFRA Builders
NC 2017 | K10 | Region XII | Sarangani | 208017 | Nop Elementary School | ALABEL (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2530000 |  |  | Completed | 1 |  |  | P00170917MN-CW1 | 17ME0085 |  |  | 2017-07-26 |  | 2017-09-05 | RNS Cons. Engineering
NC 2017 | K10 | Region XII | Sarangani | 130449 | Calabanit ES | GLAN | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170918MN-CW1 | 17ME0102 |  |  | 2017-07-26 |  | 2017-09-05 | Cofejok Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 208037 | D. Masalon Y. Recto ES | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170919MN-CW1 | 17ME0090 |  |  | 2017-07-26 |  | 2017-09-05 | BR, Gultiano Const.
NC 2017 | K10 | Region XII | Sarangani | 130456 | Dlama Elementary School | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170920MN-CW1 | 17ME0116 |  |  | 2017-08-14 |  | 2017-09-07 | CS Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 130448 | Domingo R. Cania Mem. ES | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3883366.49 |  |  | Completed | 1 |  |  | P00170921MN-CW1 | 17ME0117 |  |  | 2017-08-14 |  | 2017-09-07 | Kevin Yoshi Builders
NC 2017 | K10 | Region XII | Sarangani | 208021 | Enrique D. Yap, Sr. ES | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170922MN-CW1 | 17ME0103 |  |  | 2017-07-26 |  | 2017-09-05 | Verguz Construction
NC 2017 | SHS | Region XII | Sarangani | 500260 | Lumigo Integrated School | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3820000 |  |  | Completed | 1 |  |  | P00170923MN-CW1 | 17ME0114 |  |  | 2017-08-14 |  | 2017-09-07 | LTB Builders & Construction
NC 2017 | K10 | Region XII | Sarangani | 130470 | Miasong Integrated School | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3790000 |  |  | Completed | 1 |  |  | P00170924MN-CW1 | 17ME0089 |  |  | 2017-07-26 |  | 2017-09-06 | Shepperd Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 316656 | Miasong Integrated School | GLAN | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2550000 |  |  | Completed | 1 |  |  | P00170925MN-CW1 | 17ME0089 |  |  | 2017-07-26 |  | 2017-09-06 | Shepperd Const. & Supply
NC 2017 | SHS | Region XII | Sarangani | 304541 | Pangyan National High School | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170926MN-CW1 | 17ME0115 |  |  | 2017-08-14 |  | 2017-09-07 | LTB Builders & Construction
NC 2017 | K10 | Region XII | Sarangani | 208049 | Pio L. Siao PS | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170927MN-CW1 | 17ME0090 |  |  | 2017-07-26 |  | 2017-09-05 | BR Gultiano Const.
NC 2017 | K10 | Region XII | Sarangani | 130475 | Tonga Lim Siao Sr. Integrated School | GLAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3820000 |  |  | Completed | 1 |  |  | P00170928MN-CW1 | 17ME0123 |  |  | 2017-08-14 |  | 2017-09-07 | LTB Builders & Construction
NC 2017 | K10 | Region XII | Sarangani | 316661 | Tonga Lim Siao Sr. Integrated School | GLAN | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 4780000 |  |  | Completed | 1 |  |  | P00170929MN-CW1 | 17ME0131 |  |  | 2017-08-29 |  | 2017-09-22 | JICLAM Builders & Enterprises
NC 2017 | K10 | Region XII | Sarangani | 130497 | A. F. dela Cruz (Katubao) ES | KIAMBA | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170930MN-CW1 | 17ME0101 |  |  | 2017-07-26 |  | 2017-09-05 | Nirvana Const. & Supply
NC 2017 | SHS | Region XII | Sarangani | 316606 | Aniceto C. Lopez Sr. NHS | MAASIM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2530000 |  |  | Completed | 1 |  |  | P00170931MN-CW1 | 17ME0100 |  |  | 2017-07-26 |  | 2017-09-05 | CS Construction & Supply
NC 2017 | K10 | Region XII | Sarangani | 316657 | Blat Integrated School | MAASIM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3770000 |  |  | Completed | 1 |  |  | P00170932MN-CW1 | 17ME0091 |  |  | 2017-07-26 |  | 2017-09-05 | RNS Construction Engineering
NC 2017 | K10 | Region XII | Sarangani | 130511 | Bo. Site Elementary School | MAASIM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3710000 |  |  | Completed | 1 |  |  | P00170933MN-CW1 | 17ME0092 |  |  | 2017-07-26 |  | 2017-09-05 | Triple Z Merch. & Elec. Services
NC 2017 | K10 | Region XII | Sarangani | 281512 | Claudio L. Lim IP School | MAASIM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3790000 |  |  | Completed | 1 |  |  | P00170934MN-CW1 | 17ME0092 |  |  | 2017-07-26 |  | 2017-09-05 | Triple Z Merch. & Elec. Services
NC 2017 | K10 | Region XII | Sarangani | 208030 | Langaran Elementary School | MAASIM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 4080000 |  |  | Completed | 1 |  |  | P00170935MN-CW1 | 17ME0125 |  |  | 2017-08-14 |  | 2017-09-07 | Fuentabuilt Construction Corp.
NC 2017 | K10 | Region XII | Sarangani | 130521 | Maasim CES | MAASIM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170936MN-CW1 | 17ME0119 |  |  | 2017-08-14 |  | 2017-09-07 | RDF Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 130527 | San Felipe Central Elementary School | MAASIM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170937MN-CW1 | 17ME0118 |  |  | 2017-08-14 |  | 2017-09-07 | Sophia Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 281522 | Tambuan Dani IP School | MAASIM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 5340000 |  |  | Completed | 1 |  |  | P00170938MN-CW1 | 17ME0124 |  |  | 2017-08-14 |  | 2017-09-07 | Fuentabelt Construction Corp.
NC 2017 | K10 | Region XII | Sarangani | 130529 | Batian ES | MAITUM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3790000 |  |  | Completed | 1 |  |  | P00170939MN-CW1 | 17ME0122 |  |  | 2017-09-29 |  | 2017-10-18 | Nirvana Const. & Supplies
NC 2017 | K10 | Region XII | Sarangani | 130530 | Kiayap ES | MAITUM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3770000 |  |  | Completed | 1 |  |  | P00170940MN-CW1 | 17ME0121 |  |  | 2017-08-14 |  | 2017-09-07 | SAREX Builders & Supply
NC 2017 | K10 | Region XII | Sarangani | 130536 | Mindupok ES | MAITUM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2590000 |  |  | Completed | 1 |  |  | P00170941MN-CW1 | 17ME0096 |  |  | 2017-07-26 |  | 2017-09-05 | CEK Const. & Water Supply
NC 2017 | K10 | Region XII | Sarangani | 130537 | Pangi ES | MAITUM | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2590000 |  |  | Completed | 1 |  |  | P00170942MN-CW1 | 17ME0098 |  |  | 2017-07-26 |  | 2017-09-05 | LTB Builders & Construction
NC 2017 | K10 | Region XII | Sarangani | 130538 | Perrett CES | MAITUM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3820000 |  |  | Completed | 1 |  |  | P00170943MN-CW1 | 17ME0099 |  |  | 2017-07-26 |  | 2017-09-05 | LTB Builders & Construction
NC 2017 | K10 | Region XII | Sarangani | 130540 | Reganit (Maguling) ES | MAITUM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3805000 |  |  | Completed | 1 |  |  | P00170944MN-CW1 | 17ME0097 |  |  | 2017-07-26 |  | 2017-09-06 | BR Gultiano Construction
NC 2017 | K10 | Region XII | Sarangani | 130541 | Rudes ES | MAITUM | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170945MN-CW1 | 17ME0120 |  |  | 2017-08-14 |  | 2017-09-07 | RDF Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 130556 | Lasang ES | MALAPATAN | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2530000 |  |  | Completed | 1 |  |  | P00170946MN-CW1 | 17ME0087 |  |  | 2017-07-26 |  | 2017-09-05 | Curve-line Construction
NC 2017 | SHS | Region XII | Sarangani | 130557 | Libi Integrated School | MALAPATAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3720000 |  |  | Completed | 1 |  |  | P00170948MN-CW1 | 17ME0088 |  |  | 2017-07-26 |  | 2017-09-05 | Freden Construction
NC 2017 | K10 | Region XII | Sarangani | 316647 | Libi IS | MALAPATAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3720000 |  |  | Completed | 1 |  |  | P00170947MN-CW1 | 17ME0088 |  |  | 2017-07-26 |  | 2017-09-05 | Freden Construction
NC 2017 | K10 | Region XII | Sarangani | 130560 | Lun Padidu Central Elementary School | MALAPATAN | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 4700000 |  |  | Completed | 1 |  |  | P00170949MN-CW1 | 17ME0133 |  |  | 2017-08-29 |  | 2017-09-22 | HVC Sagittarius Comm. & Const.
NC 2017 | SHS | Region XII | Sarangani | 316605 | Malapatan NHS - Kinam Annex | MALAPATAN | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3790000 |  |  | Completed | 1 |  |  | P00170950MN-CW1 | 17ME0087 |  |  | 2017-07-26 |  | 2017-09-05 | Curve-line Construction
NC 2017 | SHS | Region XII | Sarangani | 316660 | Millona Upper Suyan Integrated School | MALAPATAN | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 6200000 |  |  | Completed | 1 |  |  | P00170951MN-CW | 17ME0130 |  |  | 2017-08-29 |  | 2017-09-22 | Curve-line Construction
NC 2017 | K10 | Region XII | Sarangani | 130587 | Balitangan ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2580000 |  |  | Completed | 1 |  |  | P00170952MN-CW1 | 17ME0113 |  |  | 2017-10-13 |  | 2017-11-02 | Nirvana Const. & Supplies
NC 2017 | K10 | Region XII | Sarangani | 130572 | Biangan ES | MALUNGON | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170953MN-CW1 | 17ME0093 |  |  | 2017-07-26 |  | 2017-09-05 | CS Construction
NC 2017 | K10 | Region XII | Sarangani | 130591 | Columbio Elementary School | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2580000 |  |  | Completed | 1 |  |  | P00170954MN-CW1 | 17ME0106 |  |  | 2017-10-13 |  | 2017-11-02 | Vertical Builders
NC 2017 | K10 | Region XII | Sarangani | 281519 | Fye Falel IP School | MALUNGON | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170955MN-CW1 | 17ME0107 |  |  | 2017-09-26 |  | 2017-10-18 | Nirvana Const. & Supplies
NC 2017 | K10 | Region XII | Sarangani | 130573 | J.P. Laurel ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2590000 |  |  | Completed | 1 |  |  | P00170956MN-CW1 | 17ME0105 |  |  | 2017-08-14 |  | 2017-09-06 | A.L. Acharon Const. & Supply
NC 2017 | K10 | Region XII | Sarangani | 208034 | JWB Adoracion ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 4020000 |  |  | Completed | 1 |  |  | P00170957MN-CW1 | 17ME0126 |  |  | 2017-08-14 |  | 2017-09-07 | BR Gultiano Construction
NC 2017 | K10 | Region XII | Sarangani | 208041 | Kalbangan ES | MALUNGON | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3765000 |  |  | Completed | 1 |  |  | P00170958MN-CW1 | 17ME0108 |  |  | 2017-10-13 |  | 2017-11-02 | Vertical Builders
NC 2017 | K10 | Region XII | Sarangani | 316658 | Laginan Integrated School | MALUNGON | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3833000 |  |  | Completed | 1 |  |  | P00170959MN-CW1 | 17ME0109 |  |  | 2017-09-29 |  | 2017-10-18 | Nirvana Const. & Supplies
NC 2017 | K10 | Region XII | Sarangani | 208046 | Lamlangil ES | MALUNGON | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 4750000 |  |  | Completed | 1 |  |  | P00170960MN-CW1 | 17ME0132 |  |  | 2017-08-29 |  | 2017-09-22 | JICLAM Builders & Enterprises
NC 2017 | K10 | Region XII | Sarangani | 130577 | Malalag Cogon ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2550000 |  |  | Completed | 1 |  |  | P00170961MN-CW1 | 17ME0112 |  |  | 2017-10-13 |  | 2017-11-02 | Kevin Yoshi Builders
NC 2017 | K10 | Region XII | Sarangani | 130615 | Mateo ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2550000 |  |  | Completed | 1 |  |  | P00170962MN-CW1 | 17ME0111 |  |  | 2017-08-14 |  | 2017-09-07 | Freden Construction
NC 2017 | K10 | Region XII | Sarangani | 130618 | Panamin ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2550000 |  |  | Completed | 1 |  |  | P00170963MN-CW1 | 17ME0094 |  |  | 2017-07-26 |  | 2017-09-05 | Verguz Construction
NC 2017 | K10 | Region XII | Sarangani | 316662 | San Juan Integrated School | MALUNGON | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3790000 |  |  | Completed | 1 |  |  | P00170964MN-CW1 | 17ME0095 |  |  | 2017-07-26 |  | 2017-09-05 | JICLAM Builders & Enterprises
NC 2017 | K10 | Region XII | Sarangani | 130621 | San Roque ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2550000 |  |  | Completed | 1 |  |  | P00170965MN-CW1 | 17ME0095 |  |  | 2017-07-26 |  | 2017-09-05 | JICLAM Builders & Enterprises
NC 2017 | K10 | Region XII | Sarangani | 208036 | Tandawanan ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2680000 |  |  | Completed | 1 |  |  | P00170966MN-CW1 | 17ME0110 |  |  | 2017-10-13 |  | 2017-11-02 | Vertical Builders
NC 2017 | K10 | Region XII | Sarangani | 130626 | Upper Mainit ES | MALUNGON | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2570000 |  |  | Completed | 1 |  |  | P00170967MN-CW1 | 17ME0094 |  |  | 2017-07-26 |  | 2017-09-05 | Verguz Construction
NC 2017 | K10 | Region XII | Sultan Kudarat | 209032 | Balnate Elementary School | COLUMBIO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130960 | MAYO ES | COLUMBIO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131020 | D. LOTILLA ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131026 | MAPANTIG ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131010 | P.C. BAYANIHAN ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131097 | BILUMIN ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 3195000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131095 | PALUMBE ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2240000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209014 | Sumilalao Elementary School | PRESIDENT QUIRINO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2240000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | General Santos City | 131294 | Bawing Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2653745.92 |  |  | Completed | 1 |  |  | P0017417MN-CW1 17MBO117 | [5 empty] | 2017-11-16 | LTB Builders & Construction
NC 2017 | TVL | Region XII | General Santos City | 304644 | Bawing National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984549.27 |  |  | Completed | 1 |  |  | P00174176MN CW1 17MBO132 | 17MB0132 |  |  |  |  | 2017-11-16 | CJEP BUILDERS & ENG'G SERVICES
NC 2017 | TVL | Region XII | General Santos City | 304642 | Calumpang High School, General Santos City National High School (Annex) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984549.27 |  |  | Completed | 1 |  |  | P00174175MN-CW1 17MB0131 | 17MB0131 |  |  |  |  | 2017-11-16 | A.L. ACHARON CONSTRUCTION
NC 2017 | TVL | Region XII | General Santos City | 304646 | Gen. Santos City High School - Lanton High School Annex | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2994549.27 |  |  | Completed | 1 |  |  | P00174177MN-CW1 | 17MB0133 |  |  |  |  | 2018-01-09 | TRIPLE Z MERCHANDIZING
NC 2017 | TVL | Region XII | General Santos City | 304655 | GSC National Secondary School of Arts & Trades | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984549.27 |  |  | Completed | 1 |  |  | P00174179MN-CW1 | 17MB0135 |  |  |  |  | 2017-11-17 | RG BATIANCILA CONSTRUCTION
NC 2017 | TVL | Region XII | General Santos City | 304655 | GSC National Secondary School of Arts & Trades | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984549.27 |  |  | Completed | 1 |  |  | P00174180MN-CW1 | 17MB0136 |  |  |  |  | 2017-12-07 | KEVIN YOSHI BUILDERS
NC 2017 | K10 | Region XII | General Santos City | 131303 | H. Bayan Sr. Central Elem. School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2648745.92 |  |  | Completed | 1 |  |  | P00174173MN-CW1 17MB0118 | [5 empty] | 2017-11-24 | LTB BUILDERS
NC 2017 | K10 | Region XII | General Santos City | 131272 | Jose Catolico Sr. ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P0017417OMN-CW1 17MB0115 | [5 empty] | 2017-11-16 | LLM UNIFIED BUILDERS 7 TRADING CORP.
NC 2017 | K10 | Region XII | General Santos City | 131286 | Mabuhay ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1 |  |  | P00174171MN-CW1 17MB0116 | [5 empty] | 2017-12-07 | SAREX BUILDERS AND SUPPLY
NC 2017 | TVL | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2984549.27 |  |  | Completed | 1 | [9 empty] | H.P. Gopeteo Construction
NC 2017 | K10 | Region XII | General Santos City | 131322 | San Jose ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745.92 |  |  | Completed | 1 |  |  | P00174174MN-CW1 17MBO119 | 17MB0119 |  |  |  |  | 2017-11-16 | KEVIN YOSHI BUILDERS
NC 2017 | K10 | Region XII | Kidapawan City | 131325 | Datu Saliman ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2826246.44 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Memorial National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3068890.63 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Kidapawan City | 304668 | Paco National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3015232.74 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Kidapawan City | 304668 | Paco National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Kidapawan City | 131361 | Sumbac ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5017681.76 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Koronadal City | 131401 | Bacongco (San Isidro) ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1 |  |  | P00174191MN | 17MGO138 |  |  | 2017-08-09 |  | 2017-10-27 | Aguero Construction
NC 2017 | K10 | Region XII | Koronadal City | 131375 | Kakub ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2658745.92 |  |  | Completed | 1 |  |  | P00174186MN | 17MGO140 |  |  | 2017-08-09 |  | 2017-10-27 | HVC Sagitarius Commercial & Construction
NC 2017 | TVL | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3211721.55 |  |  | Completed | 1 |  |  | P00174193MN | 17MGO140 |  |  | 2017-08-17 |  | 2017-10-27 | HVC Sagitarius Commercial & Construction
NC 2017 | K10 | Region XII | Koronadal City | 131391 | Magsaysay ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2688745.92 |  |  | Completed | 1 |  |  | P00174188MN | 17MGO142 |  |  | 2017-08-09 |  | 2017-10-27 | Vergusz Construction
NC 2017 | K10 | Region XII | Koronadal City | 131393 | Mangga ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2725745.92 |  |  | Completed | 1 |  |  | P00174189MN | 17MGO137 |  |  | 2017-08-09 |  | 2017-10-27 | Yap Mabuhay Enterprises
NC 2017 | K10 | Region XII | Koronadal City | 131393 | Mangga ES | CITY OF KORONADAL (Capital) | 2 |  | 3 | 1STY3CL | BATCH 4 | 3885435.02 |  |  | Completed | 1 |  |  | P00174190MN | 17MGO143 |  |  | 2017-08-09 |  | 2017-10-27 | Yap Mabuhay Enterprises
NC 2017 | K10 | Region XII | Koronadal City | 131380 | Marbel 5 CES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2683745.92 |  |  | Completed | 1 |  |  | P00174187MN | 17MGO141 |  |  | 2017-08-09 |  | 2017-10-27 | HVC Sagitarius Commercial & Construction
NC 2017 | K10 | Region XII | Koronadal City | 131414 | Sta. Cruz ES | CITY OF KORONADAL (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2703745.92 |  |  | Completed | 1 |  |  | P00174192MN | 17MGO139 |  |  | 2017-08-09 |  | 2017-11-06 | Migo Construction
NC 2017 | K10 | Region XII | North Cotabato | 129844 | New Leon ES | ALAMADA | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2677649.11 |  |  | Completed | 1 |  |  | P00174194 | 17MD0159 | 2017-09-09 | 2017-09-16 | 2017-09-28 |  | 2017-10-30 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129844 | New Leon ES | ALAMADA | 1 |  | 2 | 1STY2CL | BATCH 4 | 2677649.11 |  |  | Completed | 1 |  |  | P00174195 | 17MD0156 | 2017-09-09 | 2017-09-16 | 2017-09-28 |  | 2017-10-30 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129851 | Rebi Elementary School | Alamada | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2645508.01 |  |  | Completed | 1 |  |  | P00174196 | 17MD0156 | 2017-09-09 | 2017-09-16 | 2017-09-28 |  | 2017-10-30 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129861 | Katalicanan ES | ALEOSAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3617322.19 |  |  | Completed | 1 |  |  | P00174197 | 17MD0156 | 2017-09-22 | 2017-09-29 | 2017-10-11 |  | 2017-11-21 | BARRIST CONST.
NC 2017 | TVL | Region XII | North Cotabato | 304415 | ANTIPAS NHS | ANTIPAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3081193.22 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129883 | Dolores Elementary School | ANTIPAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2826468.78 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129889 | Malatab ES | ANTIPAS | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5287326.44 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 304437 | Badiangon HS | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2826468.78 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129904 | Ganatan ES | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2875249.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3158274.77 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129910 | Kiatao Elementary School | ARAKAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4046194.64 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304460 | Lanao Kuran NVTHS | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2883804.85 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304439 | Marciano Dahan HS | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2987047.15 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304439 | Marciano Dahan HS | ARAKAN | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2910951.01 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207502 | Paco-Paco ES | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2948713.3 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129925 | San Miguel ES | ARAKAN | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4051793.72 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207544 | Sinayawan ES | ARAKAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2942049.27 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 316552 | Kitubod HS | LIBUNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673086.58 |  |  | Completed | 1 |  |  | P00174198 | 17MD0186 | 2017-09-30 | 2017-10-07 | 2017-10-19 |  | 2017-11-21 | ILON MULTIBUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130069 | Apostol MES | MAGPET | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3887933.99 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 500461 | Manobisa High School | MAGPET | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 500460 | Sallab High School | MAGPET | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3844787.63 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304456 | Kisante National High School | MAKILALA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3131701.135 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304456 | Kisante National High School | MAKILALA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3131701.135 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304456 | Kisante National High School | MAKILALA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3152072.63 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | MAKILALA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3015232.74 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130090 | New Cebu ES | MAKILALA | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 4967152.58 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130103 | New Israel ES | MAKILALA | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5287326.45 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130223 | Datu Guilem Piang Elementary School | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2733626.84 |  |  | Completed | 1 |  |  | P00174202 | 17MD0193 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-11-25 | J-ONE BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130217 | Malingao Elementary School | MIDSAYAP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2617242.06 |  |  | Completed | 1 |  |  | P00174201 | 17MD0198 | 2017-09-30 | 2017-10-07 | 2017-10-19 |  | 2017-11-21 | J-ONE BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130175 | Miguel Intes (Katingawan) ES | MIDSAYAP | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3640842.99 |  |  | Completed | 1 |  |  | P00174199 | 17MD0199 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-11-21 | RDEN CONST.
NC 2017 | K10 | Region XII | North Cotabato | 130175 | Miguel Intes (Katingawan) ES | MIDSAYAP | 1 |  | 2 | 1STY2CL | BATCH 4 | 2612203.78 |  |  | Completed | 1 |  |  | P00174199 | 17MD0199 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-11-21 | RDEN CONST.
NC 2017 | SHS | Region XII | North Cotabato | 304489 | Olandang NHS | MIDSAYAP | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3898659 |  |  | Completed | 1 | [9 empty] | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 207524 | Lower Baguer Elementry School | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2688339.86 |  |  | Completed | 1 | [9 empty] | ARS CONST. & SUPPLY
NC 2017 | K10 | Region XII | North Cotabato | 130291 | Lower Pangangcalan Primary School | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2815090.73 |  |  | Completed | 1 | [9 empty] | ARS CONST. & SUPPLY
NC 2017 | SHS | Region XII | North Cotabato | 316510 | Pigcawayan NHS - Patot Annex | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2674033.99 |  |  | Completed | 1 | [9 empty] | HAQ CONST
NC 2017 | K10 | Region XII | North Cotabato | 207538 | Balibet ES | PIKIT | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2690216.13 |  |  | Completed | 1 |  |  | P00174208 | 17MD0196 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-11-02 | MINROCK MULTIBUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 316541 | Datu Embak Mangansing Memorial High School | PIKIT | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3248448.95 |  |  | Completed | 1 |  |  | P00174212 | 17MD0201 | 2017-10-19 | 2017-10-26 | 2017-11-07 |  | 2017-12-04 | K.A. BUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 316541 | Datu Embak Mangansing Memorial High School | PIKIT | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3248448.95 |  |  | Completed | 1 |  |  | P00174213 | 17MD0201 | 2017-10-19 | 2017-10-26 | 2017-11-07 |  | 2017-12-04 | K.A. BUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 316541 | Datu Embak Mangansing Memorial High School | PIKIT | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3296627.25 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130331 | Rajah Muda ES | PIKIT | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2729469.25 |  |  | Completed | 1 | [9 empty] | ANGKAT CONST
NC 2017 | TVL | Region XII | North Cotabato | 304505 | Silik High School | PIKIT | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3172275.8 |  |  | Completed | 1 |  |  | P00174210 | 17MD0201 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-12-18 | K.A. BUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 304505 | Silik High School | PIKIT | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3172275.8 |  |  | Completed | 1 |  |  | P00174211 | 17MD0201 | 2017-10-19 | 2017-10-26 | 2017-11-07 |  | 2017-12-18 | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130332 | Talitay ES | PIKIT | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5002492.24 |  |  | Completed | 1 |  |  | P00174208 | 17MD0196 | 2017-10-06 | 2017-10-13 | 2017-10-25 |  | 2017-11-02 | K.A. BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130352 | Datu Sundungan ES | PRESIDENT ROXAS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 4047364.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130356 | Kimahuring ES | PRESIDENT ROXAS | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 4977936.01 |  |  | Completed | 1
NC 2017 | TVL | Region XII | South Cotabato | 304543 | Banga NHS | BANGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3193721.55 |  |  | Completed | 1 |  |  | P00174266MN | 17MG0145 |  |  | 2017-08-17 |  | 2017-11-06 | Triple Z Merchandising & Electrical Supplies
NC 2017 | K10 | Region XII | South Cotabato | 130632 | Lambukay ES | BANGA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2643745.92 |  |  | Completed | 1 |  |  | P00174264MN | 17MG0117 |  |  | 2017-08-09 |  | 2017-10-27 | Sophia Const. & Supply
NC 2017 | TVL | Region XII | South Cotabato | 316714 | Malaya NHS - Banga NHS Annex | BANGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3221721.55 |  |  | Completed | 1 |  |  | P00174268MN | 17MG0146 |  |  | 2017-08-17 |  | 2017-11-06 | Migo Construction
NC 2017 | TVL | Region XII | South Cotabato | 316703 | San Jose NHS | BANGA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3221721.55 |  |  | Completed | 1 |  |  | P00174267MN | 17MG0147 |  |  | 2017-08-17 |  | 2017-11-09 | Virguz Construction
NC 2017 | K10 | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2708745.92 |  |  | Completed | 1 |  |  | P00174265MN | 17MG0116 |  |  | 2017-08-09 |  | 2017-11-03 | South Ironrock Corporation
NC 2017 | K10 | Region XII | South Cotabato | 130660 | Blit ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3073745.92 |  |  | REVERTED | 0
NC 2017 | K10 | Region XII | South Cotabato | 130664 | Diente ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745.92 |  |  | Completed | 1 |  |  | P00174270MN | 17MG0119 |  |  | 2017-09-11 |  | 2017-10-27 | KGD Builders
NC 2017 | SHS | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2688745.92 |  |  | Completed | 1 |  |  | P00174276MN | 17MG0136 |  |  | 2017-08-09 |  | 2017-11-09 | Migo Const.
NC 2017 | SHS | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2 |  | 2 | 1STY2CL | BATCH 4 | 2688745.92 |  |  | Completed | 1 |  |  | P00174277MN | 17MG0136 |  |  | 2017-08-09 |  | 2017-11-09 | Migo Const.
NC 2017 | K10 | Region XII | South Cotabato | 130678 | Maculan ES | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00174271MN | 17MG0120 |  |  | 2017-08-09 |  | 2017-10-27 | HVC Sagittarius
NC 2017 | TVL | Region XII | South Cotabato | 304551 | Ned NHS | LAKE SEBU | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3491721.55 |  |  | Completed | 1 |  |  | P00174278MN | 17MG0148 |  |  | 2017-08-17 |  | 2017-11-09 | Goyo Const. & Supply
NC 2017 | TVL | Region XII | South Cotabato | 304551 | Ned NHS | LAKE SEBU | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3491721.55 |  |  | Completed | 1 |  |  | P00174279MN | 17MG0148 |  |  | 2017-08-17 |  | 2017-11-09 | Goyo Const. & Supply
NC 2017 | K10 | Region XII | South Cotabato | 130683 | Pulo Subong IS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3008745.92 |  |  | Completed | 1 |  |  | P00174272MN | 17MG0121 |  |  |  |  | 2018-01-17 | ILBI Const. Supply
NC 2017 | K10 | Region XII | South Cotabato | 208507 | Seven Lakes ES | LAKE SEBU | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4318435.02 |  |  | Completed | 1 |  |  | P00174275MN | 17MG0122 |  |  |  |  | 2018-01-17 | ILBI Const. Supply
NC 2017 | K10 | Region XII | South Cotabato | 130688 | Talisay Integrated School | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1 |  |  | P00174273MN | 17MG0133 |  |  | 2017-08-09 |  | 2017-10-27 | Migo Const.
NC 2017 | K10 | Region XII | South Cotabato | 130688 | Talisay Integrated School | LAKE SEBU | 2 |  | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1 |  |  | P00174274MN | 17MG0134 |  |  | 2017-08-09 |  | 2017-11-06 | Migo Const.
NC 2017 | TVL | Region XII | South Cotabato | 316918 | Talisay IS | LAKE SEBU | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3261721.55 |  |  | Completed | 1 |  |  | P00174280MN | 17MG0149 |  |  | 2017-08-17 |  | 2017-10-27 | Migo Const.
NC 2017 | SHS | Region XII | South Cotabato | 360849 | Tboli Sbu SHS | LAKE SEBU | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2723745.92 |  |  | Completed | 1 |  |  | P00174300MN | 17MG0135 |  |  | 2017-08-09 |  | 2017-10-27 | Palmares Gen. Mdse.
NC 2017 | TVL | Region XII | South Cotabato | 360849 | Tboli Sbu SHS | LAKE SEBU | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3241721.55 |  |  | Completed | 1 |  |  | P00174280MN | 17MG0150 |  |  | 2017-08-17 |  | 2017-10-27 | HVC Sagittarius
NC 2017 | K10 | Region XII | South Cotabato | 208510 | Bato PS | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1 |  |  | P00174252MN-CW1 | 17MB0110 |  |  | 2017-11-23 |  | 2018-02-07 | RG Bitiancila Const.
NC 2017 | K10 | Region XII | South Cotabato | 130718 | Bukay-eel ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2733745.92 |  |  | Completed | 1 |  |  | P00174239MN-CW1 | 17MB0101 |  |  | 2017-11-23 |  | 2018-02-07 | RG Bitiancila Const.
NC 2017 | K10 | Region XII | South Cotabato | 130720 | Crossing Palkan ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2683745.92 |  |  | Completed | 1 |  |  | P00174240MN-CW1 | 17MB0102 |  |  | 2017-09-26 |  | 2017-11-16 | CEK Const.
NC 2017 | K10 | Region XII | South Cotabato | 130721 | Dole Cannery Central Elementary School | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2703745.92 |  |  | Completed | 1 |  |  | P00174241MN-CW1 | 17MB0103 |  |  | 2017-09-26 |  | 2017-11-24 | LEIGHCHEEN Const.
NC 2017 | K10 | Region XII | South Cotabato | 130737 | Eugenio L. Lido Ranada ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2638745.92 |  |  | Completed | 1 |  |  | P00174245MN-CW1 | 17MB0107 |  |  | 2017-09-26 |  | 2017-12-29 | GRECO Const.
NC 2017 | K10 | Region XII | South Cotabato | 130738 | Glamang ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2643745.92 |  |  | Completed | 1 |  |  | P00174246MN-CW1 | 17MB0108 |  |  | 2017-09-26 |  | 2017-11-16 | FUENTABUILT Const.
NC 2017 | K10 | Region XII | South Cotabato | 130727 | Klinan -6 ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2623745.92 |  |  | Completed | 1 |  |  | P00174243MN-CW1 | 17MB0105 |  |  | 2017-09-26 |  | 2017-11-16 | BR GULTIANO Const.
NC 2017 | K10 | Region XII | South Cotabato | 130741 | Koronadal Proper ES | POLOMOLOK | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 4888351.15 |  |  | Completed | 1 |  |  | P00174247MN-CW1 | 17MB0124 |  |  | 2017-09-27 |  | 2017-11-16 | MARDI INFRA Builders
NC 2017 | K10 | Region XII | South Cotabato | 130731 | Palakasam Elementary School | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2703745.92 |  |  | Completed | 1 |  |  | P00174244MN-CW1 | 17MB0106 |  |  | 2017-09-26 |  | 2017-11-24 | MARDI INFRA Builders
NC 2017 | K10 | Region XII | South Cotabato | 130722 | Perfecto B. Salada ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2638745.92 |  |  | Completed | 1 |  |  | P00174242MN-CW1 | 17MB0104 |  |  | 2017-09-26 |  | 2017-11-16 | KEVIN YOSJI Builders
NC 2017 | K10 | Region XII | South Cotabato | 130745 | Polomolok CES | POLOMOLOK | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3778435.02 |  |  | Completed | 1 |  |  | P00174248MN-CW1 | 17MB0120 |  |  | 2017-09-27 |  | 2017-11-24 | EYMAN Realty and Const.
NC 2017 | K10 | Region XII | South Cotabato | 130745 | Polomolok CES | POLOMOLOK | 1 |  | 3 | 1STY3CL | BATCH 4 | 3778435.02 |  |  | Completed | 1 |  |  | P00174249MN-CW1 | 17MB0121 |  |  | 2017-09-27 |  | 2017-12-18 | VIRGUZ Const.
NC 2017 | K10 | Region XII | South Cotabato | 130745 | Polomolok CES | POLOMOLOK | 1 |  | 3 | 1STY3CL | BATCH 4 | 3778435.02 |  |  | Completed | 1 |  |  | P00174250MN-CW1 | 17MB0122 |  |  | 2017-09-27 |  | 2017-12-18 | EYMAN Realty and Const.
NC 2017 | TVL | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3139549.27 |  |  | Completed | 1 |  |  | P00174253MN-CW1 | 17MB0125 |  |  | 2017-09-27 |  | 2017-11-16 | NIRVANA Const.
NC 2017 | TVL | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3139549.27 |  |  | Completed | 1 |  |  | P00174254MN-CW1 | 17MB0126 |  |  | 2017-09-27 |  | 2017-11-07 | CAV Builders
NC 2017 | TVL | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3139549.27 |  |  | Completed | 1 |  |  | P00174255MN-CW1 | 17MB0127 |  |  | 2017-09-27 |  | 2017-11-22 | COFEJOK Const.
NC 2017 | TVL | Region XII | South Cotabato | 304560 | Polomolok NHS | POLOMOLOK | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3139549.27 |  |  | Completed | 1 |  |  | P00174256MN-CW1 | 17MB0128 |  |  | 2017-09-27 |  | 2017-11-24 | MARK ANTHONY Const.
NC 2017 | K10 | Region XII | South Cotabato | 130747 | Silway 8 ES | POLOMOLOK | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2618745.92 |  |  | Completed | 1 |  |  | P00174251MN-CW1 | 17MB0109 |  |  | 2017-09-26 |  | 2017-11-24 | YAP MABUHAY ENT.
NC 2017 | TVL | Region XII | South Cotabato | 304577 | Upper Klinan NHS | POLOMOLOK | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3154549.27 |  |  | Completed | 1 |  |  | P00174257MN-CW1 | 17MB0129 |  |  | 2017-09-27 |  | 2017-11-16 | VERGUZ Const.
NC 2017 | K10 | Region XII | South Cotabato | 130759 | Panay ES | SANTO NIÑO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2638745.92 |  |  | Completed | 1 |  |  | P00174281MN | 17MG0132 |  |  | 2017-08-09 |  | 2017-11-03 | Reydan Builders
NC 2017 | TVL | Region XII | South Cotabato | 304552 | Lamian NHS | SURALLAH | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3226721.55 |  |  | Completed | 1 |  |  | P00174284MN | 17MG0151 |  |  | 2017-08-17 |  | 2017-10-27 | Megaline Builders
NC 2017 | K10 | Region XII | South Cotabato | 130790 | Lamsogod ES | SURALLAH | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2623745.92 |  |  | Completed | 1 |  |  | P00174283MN | 17MG0123 |  |  | 2017-08-09 |  | 2017-10-27 | South Ironrock Corporation
NC 2017 | TVL | Region XII | South Cotabato | 304555 | Libertad NHS | SURALLAH | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3261721.55 |  |  | Completed | 1 |  |  | P00174285MN | 17MG0152 |  |  | 2017-08-17 |  | 2017-10-27 | South Ironrock Corporation
NC 2017 | TVL | Region XII | South Cotabato | 316917 | Lubol IS | SURALLAH | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3631721.55 |  |  | Completed | 1 |  |  | P00174286MN | 17MG0153 |  |  | 2017-08-17 |  | 2017-10-27 | Reydan Builders
NC 2017 | K10 | Region XII | South Cotabato | 130783 | Surallah CES | SURALLAH | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2633745.92 |  |  | Completed | 1 |  |  | P00174282MN | 17MG0124 |  |  | 2017-08-09 |  | 2017-10-27 | Migo Const.
NC 2017 | K10 | Region XII | South Cotabato | 130854 | Danlag ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2638745.92 |  |  | Completed | 1 |  |  | P00174258MN-CW1 | 17MB0111 |  |  | 2017-09-26 |  | 2017-11-24 | MARCUS Const.
NC 2017 | K10 | Region XII | South Cotabato | 130859 | Lambayong ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1 |  |  | P00174259MN-CW1 | 17MB0112 |  |  | 2017-09-26 |  | 2017-11-16 | FH GOPITEO Const.
NC 2017 | K10 | Region XII | South Cotabato | 130860 | Lampitak ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2693745.92 |  |  | Completed | 1 |  |  | P00174260MN-CW1 | 17MB0113 |  |  | 2017-09-26 |  | 2017-11-22 | NIRVANA Const.
NC 2017 | K10 | Region XII | South Cotabato | 130863 | San Isidro ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2678745.92 |  |  | Completed | 1 |  |  | P00174261MN-CW1 | 17MB0114 |  |  | 2017-09-26 |  | 2017-11-16 | FH GOPITEO Const.
NC 2017 | TVL | Region XII | South Cotabato | 304565 | Bukay Pait NHS | TANTANGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3261721.55 |  |  | Completed | 1 |  |  | P00174287MN | 17MG0154 |  |  | 2017-08-17 |  | 2017-10-27 | Reydan Builders
NC 2017 | K10 | Region XII | South Cotabato | 130796 | Aflek ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2643745.92 |  |  | Completed | 1 |  |  | P00174288MN | 17MG0125 |  |  | 2017-08-09 |  | 2017-10-27 | LTB Builders & Const.
NC 2017 | K10 | Region XII | South Cotabato | 130797 | Afus ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2933745.92 |  |  | Completed | 1 |  |  | P00174289MN | 17MG0126 |  |  | 2017-08-09 |  | 2017-10-27 | Megaline Builbers & Supply
NC 2017 | K10 | Region XII | South Cotabato | 130806 | Datal Bob ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2753745.92 |  |  | Completed | 1 |  |  | P00174290MN | 17MG0127 |  |  | 2017-09-11 |  | 2017-10-27 | KGD Builders
NC 2017 | K10 | Region XII | South Cotabato | 130807 | Datal Dlanag ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2693745.92 |  |  | Completed | 1 |  |  | P00174291MN | 17MG0128 |  |  | 2017-08-09 |  | 2017-10-27 | Aguero Construction
NC 2017 | K10 | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4513435.02 |  |  | REVERTED | 0
NC 2017 | K10 | Region XII | South Cotabato | 130827 | Lemsnolon ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2648745.92 |  |  | Completed | 1 |  |  | P00174293MN | 17MG0130 |  |  | 2017-08-09 |  | 2017-11-09 | Migo Construction
NC 2017 | K10 | Region XII | South Cotabato | 130827 | Lemsnolon ES | T'BOLI | 2 |  | 2 | 1STY2CL | BATCH 4 | 2648745.92 |  |  | Completed | 1 |  |  | P00174294MN | 17MG0130 |  |  | 2017-08-09 |  | 2017-11-09 | Migo Construction
NC 2017 | TVL | Region XII | South Cotabato | 316921 | Lusok IS | T'BOLI | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3216721.55 |  |  | Completed | 1 |  |  | P00174298MN | 17MG0155 |  |  | 2017-08-17 |  | 2017-11-09 | Nascon Builders
NC 2017 | TVL | Region XII | South Cotabato | 316921 | Lusok IS | T'BOLI | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3216721.55 |  |  | Completed | 1 |  |  | P00174299MN | 17MG0155 |  |  | 2017-08-17 |  | 2017-11-09 | Nascon Builders
NC 2017 | TVL | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3201721.55 |  |  | Completed | 1 |  |  | P00174296MN | 17MG0156 |  |  | 2017-08-17 |  | 2017-11-09 | Migo Construction
NC 2017 | TVL | Region XII | South Cotabato | 304574 | Tboli NHS | T'BOLI | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3201721.55 |  |  | Completed | 1 |  |  | P00174297MN | 17MG0156 |  |  | 2017-08-17 |  | 2017-11-09 | Migo Construction
NC 2017 | K10 | Region XII | South Cotabato | 130848 | T'bolok ES | T'BOLI | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 4168435.02 |  |  | Completed | 1 |  |  | P00174295MN | 17MG0132 |  |  | 2017-08-09 |  | 2017-10-27 | Angkat Const. & Supplies
NC 2017 | TVL | Region XII | South Cotabato | 304561 | Polonuling NHS | TUPI | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3084549.27 |  |  | Completed | 1 |  |  | P00174263MN-CW1 | 17MB0130 |  |  | 2017-09-27 |  | 2017-11-16 | RG BATIANCILA Const.
NC 2017 | K10 | Region XII | South Cotabato | 130896 | Tupi CES | TUPI | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1 |  |  | P00174262MN-CW1 | 17MB0123 |  |  | 2017-09-27 |  | 2017-11-16 | GOYO Const.
NC 2017 | K10 | Region XII | Sultan Kudarat | 209041 | Laquicon ES | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209041 | Laquicon ES | BAGUMBAYAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130957 | COLUMBIO CES | COLUMBIO | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209037 | Abang Elementary School | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130996 | DALADAP ES | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 281529 | Datu Gambangan Saliling Primary School | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209035 | Kanalan Elementary School | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131002 | NEW PANAY ES | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130992 | Salumping Elementary School | ESPERANZA | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5112814.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 316815 | Sultan Sinanggayan Integrated School | ESPERANZA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209036 | Tiger Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209020 | Ugis Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3200000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131040 | Datu Wasay Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131048 | Francisco Baluyot Concha Memorial Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131043 | Nalilidan Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3200000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131083 | LAMBAYONG CS | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131102 | New Cebu Elementary School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131132 | Ampad-Guiabar Memorial Elementary School | LEBAK | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131133 | B. DIFUNTORUM SR. MES | LEBAK | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 5112815.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 281527 | Bitogen Primary School | LEBAK | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 281530 | Datu Manggong Primary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131134 | Pakil Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209018 | Pigel Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209018 | Pigel Elementary School | LEBAK | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131128 | S.A. Balabagan Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131129 | Salangsang Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131116 | Tapudi Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131131 | Villamonte Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131150 | Maindang Elementary School | LUTAYAN | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131168 | Datu Sipot Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131176 | Kiponget Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131054 | Kiadsam Elementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131077 | Matanao Elementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131058 | Midtungok Elementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2738254.17 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209025 | Tamangan Elementary School | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Tacurong City | 131219 | Amado Fernandez Sr. CES | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00174341MN-CW1 | 17MF0072 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Palmares Gen. Mdse.
NC 2017 | TVL | Region XII | Tacurong City | 304579 | Apolinario S. Bernardo National High School | CITY OF TACURONG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3226000 |  |  | Completed | 1 |  |  | P00174344MN-CW1 | 17MF0068 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Cofejok Construction and Suplly Corp.
NC 2017 | K10 | Region XII | Tacurong City | 131222 | New Lagao ES | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00174343MN-CW1 | 17MF0073 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Sophia Cons. & Supply
NC 2017 | TVL | Region XII | Tacurong City | 304620 | Rajah Muda NHS | CITY OF TACURONG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3200000 |  |  | Completed | 1 |  |  | P00174345MN-CW1 | 17MF0067 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Pearl Construction
NC 2017 | TVL | Region XII | Tacurong City | 304622 | San Emmanuel NHS | CITY OF TACURONG | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3200000 |  |  | Completed | 1 |  |  | P00174346MN-CW1 | 17MF0064 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | FPJ Const. & Supply
NC 2017 | SHS | Region XII | Tacurong City | 304622 | San Emmanuel NHS | CITY OF TACURONG | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00174347MN-CW1 | 17MF0074 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | C.S. Construction Const. & Supply
NC 2017 | K10 | Region XII | Tacurong City | 131220 | Tacurong Pilot ES | CITY OF TACURONG | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 3834565.34 |  |  | Completed | 1 |  |  | P00174342MN-CW1 | 17MF0077 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | ECT
NC 2017 | SHS | Region XII | Tacurong City | 304627 | Virginia F. Griño National High School | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00174348MN-CW1 | 17MF0075 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Robeth Gen. Mdse. Const. & Supply
NC 2017 | SHS | Region XII | Tacurong City | 304627 | Virginia F. Griño National High School | CITY OF TACURONG | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 2738254.17 |  |  | Completed | 1 |  |  | P00174349MN-CW1 | 17MF0076 |  | 2017-11-10 | 2017-11-24 | 2017-12-08 | 2017-12-18 | Blimex Construction
NC 2017 | K10 | Region XII | Kidapawan City | 131341 | Lapan ES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 2844731.72 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130057 | Kinarum ES | MAGPET | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 5 | 4075503.62 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130059 | Lubas ES | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 2767041.84 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130062 | Manobo ES | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 2855648.94 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130062 | Manobo ES | MAGPET | 2 |  | 4 | 1STY4CL W/ TOILET | BATCH 5 | 5069062.54 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130080 | Noa ES | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 2824412.69 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207541 | Temporan Elementary School-Annex | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 5 | 2828539.19 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 5 | 3052833.665 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 5 | 3052833.665 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 5 | 3240000 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131031 | Kubo Banday Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 5 | 2738254.14 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131031 | Kubo Banday Elementary School | KALAMANSIG | 2 |  | 2 | 1STY2CL | BATCH 5 | 2738254.14 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209002 | Saint Andrews Mission School - Main | KALAMANSIG | 2 |  | 2 | 1STY2CL | BATCH 5 | 2738254.17 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 24 | 4STY24CL | BATCH 7 | 64693596.8 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 12 | 3STY12CL | BATCH 7 | 35228874.79 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129834 | Alamada CES | ALAMADA | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4601280.22 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129825 | Kisulao ES | ALAMADA | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3674323.48 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129833 | Upper Bao ES | ALAMADA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2569701.46 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207533 | Bacolod Annex PS | ALEOSAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3646611.39 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129857 | Bagolibas Elementary | ALEOSAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3588033 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129858 | Balisawan Elementary School | ALEOSAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2512948.92 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129859 | Dualing Elementary School | Aleosan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2533232.2 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304414 | Dunguan-Matanog NHS-Pagangan HS Ext. | ALEOSAN | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4632985.67 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304414 | Dunguan-Matanog NHS-Pagangan HS Ext. | ALEOSAN | 1 |  | 3 | 1STY3CL | BATCH 7 | 3645957.12 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129867 | New Leon ES | ALEOSAN | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3617322.19 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 129897 | Binaton Elementary School | ARAKAN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3117780.18 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207571 | Nueva Fuerza ES | LIBUNGAN | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4601280.22 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 316546 | Padura-Espabo High School | LIBUNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2585569.7 |  |  | Completed | 1 |  |  | P00174210 | 17MD0201 | 2017-10-19 | 2017-10-26 | 2017-11-07 |  | 2017-12-04 | BARRIST BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 130068 | Alibayon ES | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2799595.26 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130075 | Datu Celo ES | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2889856.61 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130054 | ILIAN ELEMENTARY SCHOOL | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2775597.51 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 316501 | Manumba National HS | MAGPET | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2860275.4 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304423 | Bulakanon High School | MAKILALA | 2 | 1 | 4 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 23084148.2 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304467 | Jose Rizal NHS | MAKILALA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304467 | Jose Rizal NHS | MAKILALA | 2 | 1 | 4 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 22976648.2 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 316519 | Kisante NHS - Batasan HS Annex | MAKILALA | 2 | 1 | 2 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 10891394.94 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 316519 | Kisante NHS - Batasan HS Annex | MAKILALA | 2 |  | 2 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 10891394.94 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 316519 | Kisante NHS - Batasan HS Annex | MAKILALA | 2 |  | 2 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 10891394.94 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207504 | Luis Socias MES | MAKILALA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2874239.73 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304424 | Malabuan HS | MAKILALA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2786581.99 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304424 | Malabuan HS | MAKILALA | 2 | 1 | 4 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 23221648.2 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304484 | NEW ISRAEL HIGH SCHOOL | MAKILALA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10841394.94 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304484 | NEW ISRAEL HIGH SCHOOL | MAKILALA | 2 | 1 | 4 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 23221648.2 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130123 | San Vicente Elementary School | MAKILALA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2844731.72 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207560 | Sitio Mainit ES | MAKILALA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2874115.84 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130180 | Anonang ES | MIDSAYAP | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4765187.63 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130181 | Arizona Elementary School | Midsayap | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2544546.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130186 | Lt. Andres Calungsod Elementary School | Midsayap | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2584832.53 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130190 | Upper Bulanan ES | MIDSAYAP | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4724849.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130190 | Upper Bulanan ES | MIDSAYAP | 1 |  | 2 | 1STY2CL | BATCH 7 | 2544585.53 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130192 | Villarica ES | MIDSAYAP | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3581489.33 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130192 | Villarica ES | MIDSAYAP | 1 |  | 3 | 1STY3CL | BATCH 7 | 3581489.33 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130292 | Malagakit Elementary School | Pigcawayan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2551537.62 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207523 | Central Panatan PS | PIGKAWAYAN | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 5809674.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207542 | Datu Mantil PS | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2556996.29 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130280 | Tabarangao PS | PIGKAWAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2512948.89 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130316 | Bagoinged ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3694483.46 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130305 | Balongis ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3640393.07 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130305 | Balongis ES | PIKIT | 1 |  | 2 | 1STY2CL | BATCH 7 | 2556113.97 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130317 | Barungis ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3697619.65 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130320 | Bulol Elementary School | PIKIT | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4820355.91 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130321 | Calawag ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3554034.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207568 | Dimanalao ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3646611.39 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130322 | Fort Pikit ES | PIKIT | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2544546.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130308 | Ganasi ES | PIKIT | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 5557472.35 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207531 | Kolambog ES | PIKIT | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3617322.19 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207532 | Lamuak ES | PIKIT | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4790345.25 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207520 | Nunguan ES | PIKIT | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 4589368.25 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130330 | Pikit CES | PIKIT | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2534234.71 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 316525 | Takepan NHS- Bulol NHS Annex | PIKIT | 1 | 1 | 5 | 1STY5CL | BATCH 7 | 5555203.09 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130374 | Greenhills Elementary School | PRESIDENT ROXAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 7 | 2746837.03 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130376 | Kamarahan ES | PRESIDENT ROXAS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 3989981.75 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304483 | New Cebu HS | PRESIDENT ROXAS | 2 | 1 | 2 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 10886394.94 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304483 | New Cebu HS | PRESIDENT ROXAS | 2 |  | 2 | 2 STOREY WORKSHOP BLDG (7x18) | BATCH 7 | 10886394.94 |  |  | Completed | 1
NC 2017 | TVL | Region XII | South Cotabato | 360849 | Tboli Sbu SHS | LAKE SEBU | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3241721.55 |  |  | Completed | 1 |  |  | P00177367MN | 17MG0171 |  |  | 2017-12-18 |  | 2018-01-17 | JTA Builders
NC 2017 | K10 | Region XII | South Cotabato | 130713 | Simsiman ES | NORALA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 8188972.94 |  |  | Completed | 1 |  |  | P00177365MN | 17MG0169 |  |  | 2017-12-18 |  | 2018-01-17 | South Ironrock Corp.
NC 2017 | SHS | Region XII | South Cotabato | 316916 | Naci Integrated HS | SURALLAH | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 8138972.94 |  |  | Completed | 1 |  |  | P00177366MN | 17MG0170 |  |  | 2017-12-18 |  | 2018-01-17 | LHE Const.
NC 2017 | K10 | Region XII | South Cotabato | 130864 | Tablu ES | TAMPAKAN | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2693745.92 |  |  | Completed | 1 |  |  | P00177352MN-CW1 | 17MB0140 |  |  | 2017-10-30 |  | 2018-01-04 | SAREX Builders & Supply
NC 2017 | K10 | Region XII | South Cotabato | 130897 | Acfaon ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1 |  |  | P00177353MN-CW1 | 17MB0141 |  |  | 2017-10-30 |  | 2018-01-04 | CEK Const.
NC 2017 | K10 | Region XII | South Cotabato | 130897 | Acfaon ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2633745.92 |  |  | Completed | 1 |  |  | P00177361MN-CW1 | 17MB0142 |  |  | 2017-10-30 |  | 2018-01-04 | CEK Const.
NC 2017 | K10 | Region XII | South Cotabato | 130898 | Acmonan ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2653745.92 |  |  | Completed | 1 |  |  | P00177354MN-CW1 | 17MB0143 |  |  | 2017-10-30 |  | 2018-01-29 | VERGUZ Const.
NC 2017 | K10 | Region XII | South Cotabato | 130888 | Bololmala ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1 |  |  | P00177355MN-CW1 | 17MB0144 |  |  | 2017-10-30 |  | 2017-12-21 | CAV Builders
NC 2017 | K10 | Region XII | South Cotabato | 130889 | Cebuano ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2623745.92 |  |  | Completed | 1 |  |  | P00177356MN-CW1 | 17MB0145 |  |  | 2017-10-30 |  | 2018-01-04 | ROCKSTONE Const.
NC 2017 | K10 | Region XII | South Cotabato | 130889 | Cebuano ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2623745.92 |  |  | Completed | 1 |  |  | P00177362MN-CW1 | 17MB0146 |  |  | 2017-10-30 |  | 2018-01-04 | ROCKSTONE Const.
NC 2017 | SHS | Region XII | South Cotabato | 304564 | Kablon NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2623745.92 |  |  | Completed | 1 |  |  | P00177357MN-CW1 | 17MB0147 |  |  | 2017-10-30 |  | 2018-01-09 | DJE Design Builders
NC 2017 | K10 | Region XII | South Cotabato | 130903 | Kalkam ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2648745.92 |  |  | Completed | 1 |  |  | P00177358MN-CW1 | 17MB0148 |  |  | 2017-10-30 |  | 2017-12-29 | COFEJOK Const.
NC 2017 | K10 | Region XII | South Cotabato | 130903 | Kalkam ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2648745.92 |  |  | Completed | 1 |  |  | P00177363MN-CW1 | 17MB0149 |  |  | 2017-10-30 |  | 2018-01-04 | COFEJOK Const.
NC 2017 | K10 | Region XII | South Cotabato | 130905 | Lunen ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1 |  |  | P00177359MN-CW1 | 17MB0150 |  |  | 2017-10-30 |  | 2017-12-29 | ROCKSTONE Const.
NC 2017 | SHS | Region XII | South Cotabato | 304561 | Polonuling NHS | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1 |  |  | P00177361MN-CW1 | 17MB0152 |  |  | 2017-10-30 |  | 2018-01-04 | LLM Unified Builders
NC 2017 | K10 | Region XII | South Cotabato | 130909 | Upper Tupi ES | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2613745.92 |  |  | Completed | 1 |  |  | P00177360MN-CW1 | 17MB0151 |  |  | 2017-10-30 |  | 2017-12-20 | DJE Design Builders
NC 2017 | TVL | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3345939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3345939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272070.32 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304587 | Busok National High School | BAGUMBAYAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3292070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209006 | Spur 2 Elementary School | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209006 | Spur 2 Elementary School | BAGUMBAYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209034 | Bongo-Bongo Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2933815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209034 | Bongo-Bongo Elementary School | ESPERANZA | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2933815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272154.09 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272154.09 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272154.09 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272154.09 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304621 | Salabaca National High School | ESPERANZA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304621 | Salabaca National High School | ESPERANZA | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131012 | Bambad ES | ISULAN (Capital) | 1 | 1 | 8 | 2STY8CL | BATCH 7 | 22946648.2 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131006 | Dansuli ES | ISULAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131021 | Impao ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131008 | ISULAN CENTRAL SCHOOL SPED CENTER | ISULAN (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5112814.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131016 | Kudanding ES | ISULAN (Capital) | 1 | 1 | 6 | 2STY6CL | BATCH 7 | 14775277.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131023 | Lagandang ES | ISULAN (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131024 | Laguilayan CES | ISULAN (Capital) | 1 | 1 | 4 | 1STY4CL | BATCH 7 | 5112814.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131017 | Maremco ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131029 | Tayugo ES | ISULAN (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 3834565.34 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304593 | Datu Wasay National High School | KALAMANSIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3405939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131044 | Pag-asa Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131044 | Pag-asa Elementary School | KALAMANSIG | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304592 | Sangay National High School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2933815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304592 | Sangay National High School | KALAMANSIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3323728.61 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304623 | Sta. Clara National High School | KALAMANSIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131100 | MAMALI ES | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131121 | Capilan Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131121 | Capilan Elementary School | LEBAK | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2903815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304586 | E. Arcaño Memorial National High School | LEBAK | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3277346.7 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304604 | Keytodac National High School | LEBAK | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3375939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304604 | Keytodac National High School | LEBAK | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3375939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304603 | Lebak National High School | LEBAK | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3272154.09 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3365939.67 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304626 | Tran National High School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131153 | MANILI ES | LUTAYAN | 1 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2738254.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3397681.73 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3397681.73 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131172 | Isuko Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2882311.12 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131187 | Kraan ES | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2892311.12 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131187 | Kraan ES | PALIMBANG | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2892311.12 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3366023.44 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3366023.44 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3391299.82 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3351299.82 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3351299.82 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304601 | Gapok National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3325922.93 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304599 | Langgal National High School | SEN. NINOY AQUINO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3857681.73 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3365939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3365939.67 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316802 | Sewod National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3325922.93 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Tacurong City | 131231 | J. Hector Lacson ES | CITY OF TACURONG | 1 | 1 | 8 | 2STY8CL | BATCH 7 | 22946648.2 |  |  | Completed | 1 |  |  | P00177423MN-CW1 | 17MF0098 |  | 2017-12-07 | 2017-12-20 | 2017-12-27 | 2018-01-08 | Legacy
NC 2017 | K10 | Region XII | Tacurong City | 131237 | New Isabela Central Elementary School | CITY OF TACURONG | 1 | 1 | 12 | 2STY12CL | BATCH 7 | 29278377.06 |  |  | Completed | 1 |  |  | P00177424MN-CW1 | 17MF0099 |  | 2017-12-07 | 2017-12-20 | 2017-12-27 | 2018-01-08 | Cofejok Construction and Suplly Corp.
NC 2017 | SHS | Region XII | North Cotabato | 304430 | Dado High School | ALAMADA | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 4668698.81 |  |  | Completed | 1 |  |  | P00180971MN | 17MD0141
NC 2017 | K10 | Region XII | North Cotabato | 129840 | LOWER DADO ELEMENTARY SCHOOL | ALAMADA | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3726908.84 |  |  | Completed | 1 |  |  | P00180966MN | 17MD0166 | 2017-09-17 | 2017-09-24 | 2017-10-06 |  | 2017-12-22 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129840 | LOWER DADO ELEMENTARY SCHOOL | ALAMADA | 1 |  | 3 | 1STY3CL | BATCH 10 | 3726908.84 |  |  | Completed | 1 |  |  | P00180967MN | 17MD0166 | 2017-09-17 | 2017-09-24 | 2017-10-06 |  | 2017-12-22 | PHILTIL CONST.
NC 2017 | K10 | Region XII | North Cotabato | 129850 | Raradangan ES | ALAMADA | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3695411.7 |  |  | Completed | 1 |  |  | P00180967MN | 17MD0061 | 2017-09-09 | 2017-09-16 | 2017-09-28 |  | 2017-12-22 | J-ONE BUILDERS
NC 2017 | K10 | Region XII | North Cotabato | 129856 | Bacolod ES | ALEOSAN | 1 | 1 | 4 | 1STY4CL | BATCH 10 | 4563763 |  |  | Completed | 1 |  |  | P00180968MN | 17MD0143
NC 2017 | TVL | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3371078.39 |  |  | Completed | 1 |  |  | P00181006MN | 17MD0245
NC 2017 | TVL | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3371078.39 |  |  | Completed | 1 |  |  | P00181007MN | 17MD0245
NC 2017 | K10 | Region XII | North Cotabato | 129946 | Pinamulaan ES | BANISILAN | 3 | 1 | 3 | 1STY3CL | BATCH 10 | 3718734.9 |  |  | Completed | 1 |  |  | P00180972MN | 17MD0174
NC 2017 | TVL | Region XII | North Cotabato | 316556 | Bentangan HS | CARMEN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3314554.9 |  |  | Completed | 1 |  |  | P00181014MN | 17MD0241
NC 2017 | K10 | Region XII | North Cotabato | 129978 | Carmen Central ES | CARMEN | 3 | 1 | 3 | 1STY3CL | BATCH 10 | 3588032.99 |  |  | Completed | 1 |  |  | P0018073MN | 17MD0162
NC 2017 | K10 | Region XII | North Cotabato | 129978 | Carmen Central ES | CARMEN | 3 |  | 2 | 1STY2CL | BATCH 10 | 2512948.89 |  |  | Completed | 1 |  |  | P0018074MN | 17MD0126
NC 2017 | TVL | Region XII | North Cotabato | 304427 | Carmen National High School | CARMEN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3223899.73 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00181001MN | 17MD0242 | [5 empty] | BATUA ENG'G. SERVICES
NC 2017 | TVL | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00181002MN | 17MD0242 | [5 empty] | BATUA ENG'G. SERVICES
NC 2017 | TVL | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00181003MN | 17MD0243 | [5 empty] | KING BUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00181004MN | 17MD0243 | [5 empty] | KING BUILDERS
NC 2017 | TVL | Region XII | North Cotabato | 304468 | Malapag NHS | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3291898.71 |  |  | Completed | 1 |  |  | P00181005MN | 17MD0239 | [5 empty] | BATUA ENG'G. SERVICES
NC 2017 | TVL | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3291898.71 |  |  | Completed | 1 |  |  | P00180989MN | 17MD0235
NC 2017 | TVL | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00180990MN | 17MD0237
NC 2017 | TVL | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00180991MN | 17MD0237
NC 2017 | TVL | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00180992MN | 17MD0238
NC 2017 | TVL | Region XII | North Cotabato | 304429 | Ranzo National High School | CARMEN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3241192.66 |  |  | Completed | 1 |  |  | P00180993MN | 17MD0238
NC 2017 | K10 | Region XII | North Cotabato | 130007 | Cuyapon ES | KABACAN | 3 | 1 | 5 | 1STY5CL | BATCH 10 | 5617126.7 |  |  | Completed | 1 |  |  | P00180975MN | 17MD0229
NC 2017 | TVL | Region XII | North Cotabato | 304444 | Kabacan Senior High School | KABACAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3283185.02 |  |  | Completed | 1 |  |  | P00180994MN | 17MD0240
NC 2017 | TVL | Region XII | North Cotabato | 304444 | Kabacan Senior High School | KABACAN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3224460.785 |  |  | Completed | 1 |  |  | P00180995MN | 17MD0246
NC 2017 | TVL | Region XII | North Cotabato | 304444 | Kabacan Senior High School | KABACAN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3224460.785 |  |  | Completed | 1 |  |  | P00180996MN | 17MD0246
NC 2017 | TVL | Region XII | North Cotabato | 304444 | Kabacan Senior High School | KABACAN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3224460.785 |  |  | Completed | 1 |  |  | P00180997MN | 17MD0247
NC 2017 | TVL | Region XII | North Cotabato | 304444 | Kabacan Senior High School | KABACAN | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3224460.785 |  |  | Completed | 1 |  |  | P00180998MN | 17MD0247
NC 2017 | K10 | Region XII | North Cotabato | 130025 | Barongis ES | LIBUNGAN | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3588032.99 |  |  | Completed | 1 |  |  | P00180969MN | 17MD0164
NC 2017 | K10 | Region XII | North Cotabato | 130153 | Kidama ES | MATALAM | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2738254.17 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304478 | Matalam High School (Poblacion) | MATALAM | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3052833.665 |  |  | Completed | 1 |  |  | P00181008MN | 17MC0138
NC 2017 | TVL | Region XII | North Cotabato | 304478 | Matalam High School (Poblacion) | MATALAM | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3052833.665 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304478 | Matalam High School (Poblacion) | MATALAM | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2799157.88 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 207562 | Migcuan ElementarySchool | MATALAM | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2770905.08 |  |  | Completed | 1 |  |  | P00180986MN | 17MC0206
NC 2017 | SHS | Region XII | North Cotabato | 304503 | Sarayan HS | MATALAM | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2796635.68 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130255 | Bagontapay CES | M'LANG | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2885741.8 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130247 | Lika CES | M'LANG | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3909682.22 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304462 | Lika NHS | M'LANG | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3207079.735 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304462 | Lika NHS | M'LANG | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3207079.735 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3838373.74 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130348 | Silik CES | PIKIT | 1 | 1 | 5 | 1STY5CL | BATCH 10 | 5568904.79 |  |  | Completed | 1 |  |  | P00180970MN | 17MD0232
NC 2017 | K10 | Region XII | North Cotabato | 130400 | Bacong ES | TULUNAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2976849.71 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130390 | Banayal ES | TULUNAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3926658.3 |  |  | Completed | 1
NC 2017 | SHS | Region XII | North Cotabato | 304419 | Banayal HS | TULUNAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4001215.46 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130401 | Batang ES | TULUNAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4025065.96 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130391 | Bituan ES | TULUNAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2822716 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130398 | Tuburan ES | TULUNAN | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3960862.24 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130399 | Tulunan CES | TULUNAN | 3 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4031155.54 |  |  | Completed | 1
NC 2017 | K10 | Region XII | North Cotabato | 130399 | Tulunan CES | TULUNAN | 3 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2868670.38 |  |  | Completed | 1
NC 2017 | TVL | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3015232.74 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130954 | S'Daf Panamin Primary School | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209033 | Kabanalian Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130984 | Legodon Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209015 | LIfi-Lifian Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131030 | Artemio L. Martin Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131039 | Datu Ito Andong Memorial Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2993815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131033 | Datu Malayat Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131034 | Don Modesto Buenaflor Sr. Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209039 | Maat Primary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209003 | St. Andrew's Mission ES - Annex | KALAMANSIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131123 | Elem Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2993815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304619 | Purikay National High School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 316811 | Tapudi Integrated School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2923815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131130 | Tibong-Tibong Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2973815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131181 | Dona Catalina Memorial Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2953815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131172 | Isuko Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2882311.12 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131188 | Maguid Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131189 | Malisbong Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304612 | Mamansual Adbul National High School - Palimbang Annex | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209005 | Tibuhol Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2923815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209017 | Basag Elementary School - Tinalon Annex | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2933815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209012 | Kisaday Elementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2933815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 281538 | Lageten Primary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131074 | Lagubang Elemenary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2903815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 209023 | Manobo Village ELementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131063 | Sewal Elementary School | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL w/ TOILET | BATCH 10 | 4288749.44 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Tacurong City | 304622 | San Emmanuel NHS | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL WITH ATTACHED TOILET, GRILLE WINDOW AND PLYWOOD PARTIRION | BATCH 10 | 2738254.17 |  |  | Completed | 1 |  |  | P00181041MN-CW1 | 17MF0087 |  | 2017-11-23 | 2017-12-12 | 2017-12-20 | 2018-01-03 | Betalac
NC 2017 | SHS | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | 2 | 1STY2CL WITH ATTACHED TOILET, GRILLE WINDOW AND PLYWOOD PARTIRION | BATCH 10 | 2328000 |  |  | Completed | 1 |  |  | P00181042MN-CW1 | 17MF0088 |  | 2017-11-23 | 2017-12-12 | 2017-12-20 | 2018-01-03 | FPJ Const. & Supply
NC 2017 | SHS | Region XII | General Santos City | 304638 | Buayan National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 29496171.25 |  |  | Completed | 1 |  |  | P00182282MN=CW1 | 17MB0159 |  |  | 2017-12-06 |  | 2018-01-06 | MFN BUILDERS
NC 2017 | SHS | Region XII | General Santos City | 304637 | Datu Andiam Manza NHS (Formerly Tinagacan National High School) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | BATCH 12 | 37068641.96 |  |  | Completed | 1 |  |  | P00182281MN-CW1 | 17MB0158 |  |  | 2017-12-06 |  | 2018-02-06 | LHE Construction
NC 2017 | K10 | Region XII | General Santos City | 131307 | Datu Dumagkal Danial ES - Formerly Tinagacan ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 29488171.25 |  |  | Completed | 1 |  |  | P00182280MN-CW1 | 17MB0157 |  |  | 2017-12-06 |  | 2018-02-12 | BRE CONSTRUCTION
NC 2017 | K10 | Region XII | General Santos City | 131296 | H.N. Cahilsot CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 29567171.25 |  |  | Completed | 1 |  |  | P00182278MN-CW1 | 17MB0155 |  |  | 2017-12-06 |  | 2018-02-13 | MR VARGAS CONST. / FUENTABUILT CONST. JV
NC 2017 | K10 | Region XII | General Santos City | 131304 | Katangawan Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 29425267.25 |  |  | Completed | 1 |  |  | P00182279MN-CW1 | 17MB0156 |  |  | 2017-12-06 |  | 2018-01-29 | FH GOPITEO CONST.
NC 2017 | TVL | Region XII | South Cotabato | 360849 | Tboli Sbu SHS | LAKE SEBU | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 12 | 3241721.55 |  |  | Completed | 1 |  |  | P00182284MN | 17MG0172 |  |  | 2017-12-18 |  | 2018-01-17 | Palmares Gen. Merchandise
NC 2017 | SHS | Region XII | South Cotabato | 304576 | Cebuano NHS | TUPI | 1 | 1 | 12 | 3STY12CL | BATCH 12 | 31029267.25 |  |  | Completed | 1 |  |  | P00182283MN-CW1 | 17MB0160 |  |  | 2017-12-06 |  | 2018-02-05 | FH Gopiteo Const.
NC 2017 | SHS | Region XII | General Santos City | 304636 | A.G. Busano, Sr. High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 37093641.96 |  |  | Completed | 1 |  |  | P00183519MN-CW1 | 17MB0165 |  |  | 2017-12-06 |  | 2018-01-10 | AB VISION ENG'G CONSTRUCTION
NC 2017 | SHS | Region XII | General Santos City | 304643 | Banisil National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 37105641.96 |  |  | Completed | 1 |  |  | P00183522MN-CW1 | 17MB0168 |  |  | 2017-12-07 |  | 2018-05-08 | LHE CONSTRUCTION
NC 2017 | SHS | Region XII | General Santos City | 304639 | Bula National School of Fisheries | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 37145641.96 |  |  | Completed | 1 |  |  | P00183520MN-CW1 | 17MBO166 |  |  | 2017-12-07 |  | 2018-02-28 | PUREGOLD CONST. DEVT. CORP. / ORIENTECH CONST. JV.
NC 2017 | SHS | Region XII | General Santos City | 304639 | Bula National School of Fisheries | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 8 | 2STY8CL | BATCH 13 | 17044790.26 |  |  | Completed | 1 |  |  | p0018352mn-cw1 | 17MB0167 |  |  | 2017-12-07 |  | 2018-02-12 | BRE CONSTRUCTION
NC 2017 | K10 | Region XII | General Santos City | 210011 | H.N. Cahilsot CES II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9007901.76 |  |  | Completed | 1 |  |  | P00183519MN-CW1 | 17MB0165 |  |  | 2017-12-06 |  | 2018-03-21 | Nirvana Construction
NC 2017 | SHS | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 37069641.96 |  |  | Completed | 1 |  |  | P00183523MN-CW1 | 17MB0169 |  |  | 2017-12-07 |  | 2018-01-29 | ST. GERRALD CONST. AND DEV'T CORP.
NC 2017 | SHS | Region XII | General Santos City | 304647 | New Society National High School | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 13 | 13775515.1 |  |  | Completed | 1 |  |  | P00183524MN-CW1 | 17MB0170 |  |  | 2017-12-07 |  | 2018-01-29 | Oranza Construction
NC 2017 | SHS | Region XII | General Santos City | 317002 | Pao-Pao High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9083722.4 |  |  | Completed | 1 |  |  | P00183525MN-CW1 | 17MB0171 |  |  | 2017-12-07 |  | 2018-01-24 | KEVIN YOSHI BUILDERS
NC 2017 | K10 | Region XII | General Santos City | 131297 | Romana C. Acharon Central ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | BATCH 13 | 24544047.73 |  |  | Completed | 1 |  |  | P00183516MN-CW1 | 17MB0162 |  |  | 2018-12-06 |  | 2018-02-15 | VERTICAL BUILDERS
NC 2017 | K10 | Region XII | General Santos City | 131281 | Saludin Anas ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9005722.4 |  |  | Completed | 1 |  |  | P00183515MN-CW1 | 17MB0161 |  |  | 2017-12-06 |  | 2018-01-29 | LEIGHCHEEN CONSTRUCTION CORP.
NC 2017 | K10 | Region XII | General Santos City | 131317 | Sinawal ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 8975901.76 |  |  | Completed | 1 |  |  | P00183517MN-CW1 | 17MB0163 |  |  | 2017-12-06 |  | 2018-01-10 | KEILANA RESOURCES AND DEV'T CORP.
NC 2017 | K10 | Region XII | North Cotabato |  | Matalam NHS Annex, Brgy. Estado | MATALAM | 3 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2752244.91 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sarangani | 281507 | Akbual IP School | MALAPATAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2738254.17 |  |  | Completed | 1 |  |  | P00183530MN-CW1 | 17ME0158 |  |  | 2018-12-27 |  | 2018-01-09 | Curve-line Const.
NC 2017 | K10 | Region XII | Sarangani | 281508 | Alna IP School | MALAPATAN | 0 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 13 | 5112814.7 |  |  | Completed | 1 |  |  | P00183531MN-CW1 | 17ME0159 |  |  | 2018-12-27 |  | 2018-01-09 | Dumalag Surveying & Eng'g Services
NC 2017 | K10 | Region XII | Sarangani | 281509 | Alyeng IP School | MALAPATAN | 0 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 13 | 5112814.7 |  |  | Completed | 1 |  |  | P00183532MN-CW1 | 17ME0154 |  |  | 2018-12-27 |  | 2018-01-09 | Curve-line Const.
NC 2017 | K10 | Region XII | Sarangani | 208008 | Aspang Elementary School | MALAPATAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2738254.17 |  |  | Completed | 1 |  |  | P00183529MN-CW1 | 17ME0149 |  |  | 2017-12-04 |  | 2017-12-28 | Curve-line Const.
NC 2017 | K10 | Region XII | Sarangani | 281511 | Calay IP School | MALAPATAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2738254.17 |  |  | Completed | 1 |  |  | P00183533MN-CW1 | 17ME0151 |  |  | 2017-12-04 |  | 2017-12-28 | Curve-line Const.
NC 2017 | K10 | Region XII | Sarangani | 130562 | Malkahi Elementary School | MALAPATAN | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3834565.34 |  |  | Completed | 1 |  |  | P00183527MN-CW1 | 17ME0148 |  |  | 2017-12-04 |  | 2017-12-28 | Dumalag Surveying & Eng'g Services
NC 2017 | K10 | Region XII | Sarangani | 281521 | Niyas M. Mental IP Primary School | MALAPATAN | 0 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2738254.17 |  |  | Completed | 1 |  |  | P00183534MN-CW1 | 17ME0152 |  |  | 2018-12-27 |  | 2018-01-09 | Yanchi Enterprise
NC 2017 | K10 | Region XII | Sarangani | 208006 | Pitak Elementary School | MALAPATAN | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3834565.34 |  |  | Completed | 1 |  |  | P00183528MN-CW1 | 17ME0150 |  |  | 2017-12-04 |  | 2017-12-28 | Dumalag Surveying & Eng'g Services
NC 2017 | K10 | Region XII | Sarangani | 281523 | Tusan IP School | MALAPATAN | 0 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 13 | 3834565.34 |  |  | Completed | 1 |  |  | P00183535MN-CW1 | 17ME0153 |  |  | 2018-12-27 |  | 2018-01-09 | Curve-line Const.
NC 2017 | K10 | Region XII | Sarangani | 281523 | Tusan IP School | MALAPATAN | 0 |  | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2738254.17 |  |  | Completed | 1 |  |  | P00183536MN-CW1 | 17ME0153 |  |  | 2018-12-27 |  | 2018-01-09 | Curve-line Const.
NC 2017 | SHS | Region XII | South Cotabato | 316712 | Landan NHS | POLOMOLOK | 1 | 1 | 6 | 3STY6CL | BATCH 13 | 13949515.1 |  |  | Completed | 1 |  |  | P00183541MN-CW1 | 17MB0176 |  |  | 2017-12-07 |  |  | RR Seismundo Const.
NC 2017 | SHS | Region XII | South Cotabato | 316702 | Pablo Valencia NHS - Pob. Polomolok NHS Annex | POLOMOLOK | 1 | 1 | 16 | 4STY16CL | BATCH 13 | 38630737.96 |  |  | Completed | 1 |  |  | P00183540MN-CW1 | 17MB0175 |  |  | 2017-12-07 |  | 2018-01-29 | FH Gopiteo Const.
NC 2017 | SHS | Region XII | South Cotabato | 316716 | Tablu NS - Tampakan NHS Annex | TAMPAKAN | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 17414790.26 |  |  | Completed | 1 |  |  | P00183542MN-CW1 | 17MB0177 |  |  | 2017-12-07 |  | 2018-01-18 | MARCUS Const.
NC 2017 | SHS | Region XII | South Cotabato | 304562 | Jose D. Escobillo NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9165901.76 |  |  | Completed | 1 |  |  | P00183538MN-CW1 | 17MB0173 |  |  | 2017-12-07 |  | 2018-01-29 | LTB Builders
NC 2017 | SHS | Region XII | South Cotabato | 304562 | Jose D. Escobillo NHS - Polonuling NHS Annex | TUPI | 1 |  | 4 | 2STY4CL | BATCH 13 | 9165901.76 |  |  | Completed | 1 |  |  | P00183539MN-CW1 | 17MB0174 |  |  | 2017-12-07 |  | 2018-12-18 | NIRVANA Const.
NC 2017 | SHS | Region XII | South Cotabato | 304561 | Polonuling NHS | TUPI | 1 | 1 | 2 | 1STY2CL | BATCH 13 | 2638745.92 |  |  | Completed | 1 |  |  | P00183537MN-CW1 | 17MB0172 |  |  | 2017-12-16 |  | 2018-01-29 | LTB Builders
NC 2017 | SHS | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 5 | 1STY5CL | BATCH 13 | 6691879.34 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 |  | 2 | 2 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6691879.34 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304580 | BAGUMBAYAN NHS | BAGUMBAYAN | 2 |  | 4 | 1STY4CL w/ TOILET | BATCH 13 | 5292459.8 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304584 | Bai Saripinang National High School | BAGUMBAYAN | 2 | 1 | 4 | 1STY4CL | BATCH 13 | 5272459.8 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304584 | BAI SARIPINANG NHS | BAGUMBAYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 13 | 2893815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 | 1 | 4 | 2 UNITS 1STY2CL w/ TOILET | BATCH 13 | 5747631.8 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 |  | 3 | 1STY3CL w/ TOILET | BATCH 13 | 4228749.44 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 |  | 5 | 1STY5CL | BATCH 13 | 6691879.34 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3272070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130921 | BUSOK ES | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL w/ TOILET | BATCH 13 | 4140397.76 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304587 | Busok National High School | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2893815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304587 | Busok National High School | BAGUMBAYAN | 2 |  | 5 | 1STY5CL | BATCH 13 | 6711879.34 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304587 | Busok National High School | BAGUMBAYAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3292070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130934 | Chua Elementary School | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2893815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130914 | Kapaya Elementary School | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304581 | Kapaya National High School | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 4120397.76 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304582 | Masiag National High School - Bagumbayan Annex | BAGUMBAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130928 | TUKA ES | BAGUMBAYAN | 2 | 1 | 3 | 1STY3CL w/ TOILET | BATCH 13 | 4140397.76 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 | 1 | 4 | 4 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 13088616.36 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304613 | New Panay National High School | ESPERANZA | 2 | 1 | 4 | 1STY4CL | BATCH 13 | 5272459.8 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130987 | Numo Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 130990 | Sagasa Elementary School | ESPERANZA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304621 | Salabaca National High School | ESPERANZA | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304593 | Datu Wasay National High School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2933815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304593 | Datu Wasay National High School | KALAMANSIG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3405939.67 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131041 | Hinalaan Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3272070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131045 | Roquildo D. Talapian Sr. Memorial Elementary School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304592 | Sangay National High School | KALAMANSIG | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 4140397.76 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304592 | Sangay National High School | KALAMANSIG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3323728.61 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304623 | Sta. Clara National High School | KALAMANSIG | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304623 | Sta. Clara National High School | KALAMANSIG | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3272070.32 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131108 | Babato Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2908815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131109 | Bolebak Integrated School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2903815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304586 | E. Arcaño Memorial National High School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304586 | E. Arcaño Memorial National High School | LEBAK | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3277346.7 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131135 | Gestosani Memorial Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131136 | Guintales Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304604 | Keytodac National High School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2933815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304604 | Keytodac National High School | LEBAK | 2 |  | 2 | 2 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6751879.34 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304603 | Lebak National High School | LEBAK | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304603 | Lebak National High School | LEBAK | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3272154.09 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 13 | 2913815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 |  | 2 | 1STY2CL | BATCH 13 | 2893815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3365939.67 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131134 | Pakil Elementary School | LEBAK | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6013254.5 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131141 | Pasandalan Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131143 | Salaman Central Elementary School | LEBAK | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131165 | Baluan Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2973815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 | 1 | 4 | 1STY4CL | BATCH 13 | 5312459.8 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 |  | 2 | 2 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6795363.46 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131169 | Dionisio Cagadoc Sr. Memorial Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2943815.9 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131171 | Imam Adil Memorial Elem School | PALIMBANG | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6073254.5 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131175 | Kilbog Elementary School | PALIMBANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 3023815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2 | 1 | 4 | 1STY4CL | BATCH 13 | 5312459.8 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2 |  | 2 | 2 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6732046.88 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 | 1 | 5 | 1STY5CL W/ TOILET | BATCH 13 | 6213254.5 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 13 | 2913815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 |  | 4 | 1STY4CL | BATCH 13 | 5312459.8 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 |  | 3 | 3 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 10093899.46 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304601 | Gapok National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 5 | 1STY5CL | BATCH 13 | 6711879.34 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304601 | Gapok National High School - Langgal Annex | SEN. NINOY AQUINO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3325922.93 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304599 | Langgal National High School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2953815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304599 | Langgal National High School | SEN. NINOY AQUINO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3857681.73 |  |  | Completed | 1
NC 2017 | K10 | Region XII | Sultan Kudarat | 131057 | Malegdeg Elementary School | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 13 | 2873815.9 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 4160397.76 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 |  | 2 | 2 UNITS UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 6731879.34 |  |  | Completed | 1
NC 2017 | SHS | Region XII | Sultan Kudarat | 316802 | Sewod National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2893815.9 |  |  | Completed | 1
NC 2017 | TVL | Region XII | Sultan Kudarat | 316802 | Sewod National High School - Langgal Annex | SEN. NINOY AQUINO | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3325922.93 |  |  | Completed | 1
NC 2017 | K10 | Region XII | South Cotabato | 130714 | Sotelo ES | NORALA | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 8965901.76 |  |  | Completed | 1 |  |  | P00184616MN | 17MG0173 |  |  | 2017-12-18 |  | 2018-01-17 | Nascon Builders
NC 2018 | K10 | Region XII | General Santos City | 131270 | Dadiangas Heights ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8815901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131271 | Francisco Oringo Sr. Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8847901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131273 | Lagao CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 16926790.26 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131275 | Balunto Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 29373171.25 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131276 | Dadiangas West CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 24375868.37 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131280 | Saavedra Saway CES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8858901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131285 | Lagao 2nd Bo. ELEMENTARY SCHOOL | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8815901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131293 | Banisil Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 12 | 3STY12CL | BATCH 1 | 29504171.25 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131295 | Blagan/Ondok Gawan Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8841901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131295 | Blagan/Ondok Gawan Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 4 | 2STY4CL | BATCH 1 | 8841901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131310 | GSC Elementary School for the Arts | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 13669515.1 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131310 | GSC Elementary School for the Arts | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 1 | 13669515.1 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131311 | Jose P. Laurel Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11578168.02 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131313 | New Society Central ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 16940790.26 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131323 | Upper Tambler I Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8915901.76 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 210004 | Habitat Community ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8893722.4 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14089618.3 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 1 | 14089618.3 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 1 | 14089618.3 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 1 | 14089618.3 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 6 | 3STY6CL | BATCH 1 | 14089618.3 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 20 | 4STY20CL | BATCH 1 | 41629217.74 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 |  | 16 | 4STY16CL | BATCH 1 | 36889641.96 |  |  | Completed | 1
NC 2018 | K10 | Region XII | General Santos City | 131299 | Baluan Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL | Batch 3 | 11042959.1 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 304642 | General Santos City National High School (Main) | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 20 | 4STY20CL | Batch 3 | 43928152.62 |  |  | Completed | 1
NC 2018 | SHS | Region XII | General Santos City | 317005 | Dadiangas North High School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 6 | 3STY6CL | Batch 3 | 15830367.2 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304656 | Amas National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17499485.63 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304656 | Amas National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17818684.8 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304658 | Ginatilan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 16 | 4STY16CL WORKSHOP BLDG (7x18) | BATCH 1 | 38263887.53 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304659 | Manongol National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) | BATCH 1 | 29840229.89 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304661 | Kidapawan City National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 24 | 4STY24CL WORKSHOP BLDG (7x18) | BATCH 1 | 51233743.44 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Memorial National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17939465.92 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304662 | Juan P. Jalipa Memorial National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17587998.16 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304663 | Kalaisan National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17944205.83 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304663 | Kalaisan National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9228816.19 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304663 | Kalaisan National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9524340.67 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region XII | Kidapawan City | 304664 | Mt. Apo National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9299992.08 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9120994.77 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 304665 | Saniel Cruz National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 12 | 3STY12CL WORKSHOP BLDG (7x18) | BATCH 1 | 29989190.14 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304666 | Spottswood NHS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9120992.83 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 304668 | Paco NHS | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) | BATCH 1 | 17752195.01 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9561897.03 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 317101 | Linangkob National High School | CITY OF KIDAPAWAN (Capital) | 2 |  | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9197005.91 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) | BATCH 1 | 30112383.33 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | Kidapawan City | 317102 | Juan L. Gantuangco School of Arts and Trades | CITY OF KIDAPAWAN (Capital) | 2 |  | 4 | 2STY4CL WORKSHOP BLDG (7x18) | BATCH 1 | 9343231.67 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Koronadal City | 131374 | Esperanza ES | CITY OF KORONADAL (Capital) | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 19908155.67 |  |  | Completed | 1 |  |  | P00272623MN | I8MGO187 |  |  | 2018-05-11 |  | 2018-06-08 | Verguz Construction
NC 2018 | K10 | Region XII | Koronadal City | 131388 | Chua ES | CITY OF KORONADAL (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9113401.76 |  |  | Completed | 1 |  |  | P00272624MN | I8MGO203 |  |  | 2018-05-11 |  | 2018-06-08 | Migo Construction
NC 2018 | K10 | Region XII | Koronadal City | 131399 | Siodina ES | CITY OF KORONADAL (Capital) | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11796168.02 |  |  | Completed | 1 |  |  | P00272625MN | I8MGO204 |  |  | 2018-05-11 |  | 2018-06-08 | Three G Builders
NC 2018 | K10 | Region XII | Koronadal City | 131400 | Sto. Nino ES | CITY OF KORONADAL (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9140901.76 |  |  | Completed | 1 |  |  | P00272626MN | I8MGO205 |  |  | 2018-05-11 |  | 2018-06-25 | FH Gopiteo Const. & Supply
NC 2018 | K10 | Region XII | Koronadal City | 131394 | Marbel 1 CES | CITY OF KORONADAL (Capital) | 2 | 1 | 8 | 2STY8CL | Batch 3 | 21805173.57 |  |  | Completed | 1 |  |  | P00272625MN | I8MGO204 | [5 empty] | Palmares Gen. Merchandise
NC 2018 | SHS | Region XII | North Cotabato | 304413 | Aleosan NHS | ALEOSAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26853320.78 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304430 | Dado High School | ALAMADA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12225371.49 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304430 | Dado High School | ALAMADA | 1 |  | 6 | 2STY6CL | BATCH 1 | 12225371.49 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11556168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 |  | 9 | 3STY9CL | BATCH 1 | 26703320.78 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304432 | Dilangalen National High School | MIDSAYAP | 1 |  | 9 | 3STY9CL | BATCH 1 | 26703320.78 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304435 | Dualing High School | ALEOSAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304435 | Dualing High School | ALEOSAN | 1 |  | 6 | 2STY6CL | BATCH 1 | 11656168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304454 | Kimagango NHS | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11641168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304458 | Kitub-Bao NHS | ALAMADA | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 27521518.97 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26703320.78 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304461 | Libungan NHS | LIBUNGAN | 1 |  | 6 | 2STY6CL | BATCH 1 | 11992348.2 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 27840907.91 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304472 | Malinao High School | BANISILAN | 1 |  | 9 | 3STY9CL | BATCH 1 | 27840907.91 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304487 | Nicaan High School | LIBUNGAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11621166.05 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304487 | Nicaan High School | LIBUNGAN | 1 |  | 6 | 2STY6CL | BATCH 1 | 11621166.05 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11571168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304493 | Pigcawayan National High School | PIGKAWAYAN | 1 |  | 9 | 3STY9CL | BATCH 1 | 26833320.78 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304494 | Pikit NHS | PIKIT | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 26703320.78 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304501 | Salunayan HS | MIDSAYAP | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11506168.02 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304505 | Silik High School | PIKIT | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11685698.38 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304505 | Silik High School | PIKIT | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11505698.38 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region XII | North Cotabato | 304508 | Takepan HS | PIKIT | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11570698.38 |  |  | Completed | 1
NC 2018 | K10 | Region XII | North Cotabato | 130123 | San Vicente Elementary School | MAKILALA | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12079592.21 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304415 | ANTIPAS NHS | ANTIPAS | 2 | 1 | 16 | 4STY16CL WORKSHOP BLDG (7x18) 4REG,2SCI,2ICT | BATCH 1 | 38114494.96 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304416 | Antipas NHS - Malire Annex | ANTIPAS | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17711998.89 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304422 | Basak NHS | MAGPET | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 30303588.61 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304423 | Bulakanon High School | MAKILALA | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17486619.98 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304434 | Don Antonio Jayme Mem. HS | PRESIDENT ROXAS | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29797008.95 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304436 | Greenfield NHS | ARAKAN | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 30426923.03 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304439 | Marciano Dahan HS | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17997617.61 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304440 | Kabalantian HS | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18286969.06 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304442 | F. A. Andolana Mem. NHS | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17568950.12 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304456 | Kisante National High School | MAKILALA | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17602195.01 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304456 | Kisante National High School | MAKILALA | 2 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17250727.25 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304457 | Ricardo L. Ipong NHS | MAKILALA | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17981136.51 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304460 | Lanao Kuran NVTHS | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18322163.39 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304463 | Magpet National High School | MAGPET | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29706426.87 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304464 | Mahongkog High School | MAGPET | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17799639.51 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304465 | Temporan National High School | MAGPET | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18064364.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304466 | Makilala National High School | MAKILALA | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17596654.19 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | MAKILALA | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 6REG | BATCH 1 | 29433283.54 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304469 | Malasila National Vocational and Technological High School | MAKILALA | 2 |  | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29814892.34 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304470 | Malatab HS | ANTIPAS | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 30369165.55 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304471 | MALIBATUAN HIGH SCHOOL | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18363831.97 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304473 | Manobo NHS | MAGPET | 2 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 30530625.45 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304490 | Pangao-an NHS | MAGPET | 2 | 1 | 16 | 4STY16CL WORKSHOP BLDG (7x18) 4REG,2SCI,2ICT | BATCH 1 | 38462260.19 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304496 | Pres. Roxas National High School | PRESIDENT ROXAS | 2 | 1 | 16 | 4STY16CL WORKSHOP BLDG (7x18) 4REG,2SCI,2ICT | BATCH 1 | 37969272.55 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304498 | Ilustre HS | PRESIDENT ROXAS | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18068777.13 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 316501 | Manumba National HS | MAGPET | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18046119.51 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 316534 | Meocan High School | ARAKAN | 2 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18689685.78 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304418 | Mariano Untal HS | M'LANG | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17988473.54 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304418 | Mariano Untal HS | M'LANG | 3 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17636515.53 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304419 | Banayal HS | TULUNAN | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17684294.81 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304419 | Banayal HS | TULUNAN | 3 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17332827.05 |  |  | Completed | 1
NC 2018 | SHS | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12140371.49 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304431 | Dalapitan HS | MATALAM | 3 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29710235.3 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17759005.59 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304452 | Kibia HS | MATALAM | 3 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17747787.03 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304462 | Lika NHS | M'LANG | 3 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 30129592.04 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304476 | Matalam National High School, Brgy Linao | MATALAM | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18049337.99 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304476 | Matalam National High School, Brgy Linao | MATALAM | 3 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17697870.23 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304477 | New Alimodian HS | MATALAM | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18049337.99 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304478 | Matalam High School (Poblacion) | MATALAM | 3 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 6REG | BATCH 1 | 29277913.6 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304478 | Matalam High School (Poblacion) | MATALAM | 3 |  | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29659522.4 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17602195.01 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304480 | M'lang NHS | M'LANG | 3 |  | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17250727.25 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304488 | Nueva Vida National High School | M'LANG | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18626026.67 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304503 | Sarayan HS | MATALAM | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17921236.15 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | TVL | Region XII | North Cotabato | 304504 | Sibsib High School | TULUNAN | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 17822140.25 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18096481.21 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 304515 | Tulunan NHS | TULUNAN | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 4REG | BATCH 1 | 17745013.45 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 316507 | Agustin M. Valdevieso, Sr. High School | MATALAM | 3 | 1 | 8 | 2STY8CL WORKSHOP BLDG (7x18) 2SCI,2ICT | BATCH 1 | 18247868.04 |  |  | Completed | 1
NC 2018 | TVL | Region XII | North Cotabato | 316514 | Minapan High School | TULUNAN | 3 | 1 | 12 | 3STY12CL WORKSHOP BLDG (7x18) 2SCI,2ICT,2REG | BATCH 1 | 29954189.84 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sarangani | 304518 | Alabel National High School | ALABEL (Capital) | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 35023105.95 |  |  | Completed | 1 |  |  | P00272701MN-CW1 | 18ME0111 |  |  | 2018-05-17 |  | 2018-07-03 | R. Semilla Const.
NC 2018 | SHS | Region XII | Sarangani | 304524 | Glan School of Arts and Trades | GLAN | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 35314998.63 |  |  | Completed | 1 |  |  | P00272702MN-CW1 | 18ME0112 |  |  | 2018-05-17 |  | 2018-07-03 | FH Gopiteo Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 304529 | James L. Chiongbian National Trade School | KIAMBA | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 35636891.28 |  |  | Completed | 1 |  |  | P00272703MN-CW1 | 18ME0113 |  |  | 2018-05-17 |  | 2018-07-03 | BRE Const./Amplex Const. & Supplies (JV)
NC 2018 | SHS | Region XII | Sarangani | 304531 | Lun Padidu National High School | MALAPATAN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00272704MN-CW1 | 18ME0116 |  |  | 2018-05-17 |  | 2018-07-03 | The Trendsetter Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 304532 | Maguling NHS | MAITUM | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16974000 |  |  | Completed | 1 |  |  | P00272705MN-CW1 | 18ME0104 |  |  | 2018-06-19 |  | 2018-07-18 | Marcus Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 304533 | Malalag Cogon NHS | MALUNGON | 0 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1 |  |  | P00272706MN-CW1 | 18ME0091 |  |  | 2018-05-17 |  | 2018-07-03 | BRE Const.
NC 2018 | SHS | Region XII | Sarangani | 304534 | Malalag National High School | MAITUM | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16630000 |  |  | Completed | 1 |  |  | P00272707MN-CW1 | 18ME0105 |  |  | 2018-05-17 |  | 2018-07-03 | FH Gopiteo Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 304535 | Malandag National High School | MALUNGON | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16165000 |  |  | Completed | 1 |  |  | P00272708MN-CW1 | 18ME0103 |  |  | 2018-05-17 |  | 2018-07-03 | Verguz Const.
NC 2018 | SHS | Region XII | Sarangani | 304537 | Malapatan NHS | MALAPATAN | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 35050790.2 |  |  | Completed | 1 |  |  | P00272709MN-CW1 | 18ME0114 |  |  | 2018-05-17 |  | 2018-07-03 | FH Gopiteo Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 304541 | Pangyan National High School | GLAN | 0 | 1 | 16 | 4STY16CL | BATCH 1 | 35640555.45 |  |  | Completed | 1 |  |  | P00272710MN-CW1 | 18ME0115 |  |  | 2018-05-17 |  | 2018-07-03 | FH Gopiteo Const. & Supply
NC 2018 | SHS | Region XII | Sarangani | 316603 | Malungon Gamay National High School | MALUNGON | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1 |  |  | P00272711MN-CW1 | 18ME0102 |  |  | 2018-05-17 |  | 2018-07-03 | AB Vision Eng'g & Const.
NC 2018 | SHS | Region XII | Sarangani | 316604 | Amado M. Quirit Sr National High School | MALAPATAN | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16325000 |  |  | Completed | 1 |  |  | P00272712MN-CW1 | 18ME0097 |  |  | 2018-05-17 |  | 2018-07-03 | Verguz Const.
NC 2018 | SHS | Region XII | Sarangani | 316605 | Malapatan NHS - Kinam Annex | MALAPATAN | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16490000 |  |  | Completed | 1 |  |  | P00272713MN-CW1 | 18ME0096 |  |  | 2018-05-17 |  | 2018-07-03 | Legacy Const. & Corp.
NC 2018 | SHS | Region XII | Sarangani | 316634 | Alabel Central Integrated SPED Center | ALABEL (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16600000 |  |  | Completed | 1 |  |  | P00272714MN-CW1 | 18ME0093 |  |  | 2018-05-17 |  | 2018-07-03 | Verguz Const.
NC 2018 | SHS | Region XII | Sarangani | 500256 | Datal Anggas Integrated School | ALABEL (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16974790.26 |  |  | Completed | 1 |  |  | P00272715MN-CW1 | 18ME0095 |  |  | 2018-06-19 |  | 2018-07-18 | Legacy Const. & Corp.
NC 2018 | SHS | Region XII | Sarangani | 500257 | New Canaan Integrated School | ALABEL (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16775000 |  |  | Completed | 1 |  |  | P00272716MN-CW1 | 18ME0094 |  |  | 2018-06-19 |  | 2018-07-17 | Legacy Const. & Corp.
NC 2018 | SHS | Region XII | Sarangani | 500258 | E. Alegado Integrated School | GLAN | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16720000 |  |  | Completed | 1 |  |  | P00272718MN-CW1 | 18ME0101 |  |  | 2018-05-17 |  | 2018-07-03 | LTB Builders
NC 2018 | SHS | Region XII | Sarangani | 500260 | Lumigo Integrated School | GLAN | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16770000 |  |  | Completed | 1 |  |  | P00272718MN-CW1 | 18ME0101 |  |  | 2018-05-17 |  | 2018-07-03 | LTB Builders
NC 2018 | SHS | Region XII | Sarangani | 500261 | Roque Adarna Integrated School | GLAN | 0 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00272719MN-CW1 | 18ME0117 |  |  | 2018-05-17 |  | 2018-07-03 | LTB Builders
NC 2018 | SHS | Region XII | Sarangani | 500264 | Rogaya Bajunaid IS | MAASIM | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16218000 |  |  | Completed | 1 |  |  | P00272720MN-CW1 | 18ME0098 |  |  | 2018-05-17 |  | 2018-07-03 | Cofejok Const. & Supply Corp.
NC 2018 | TVL | Region XII | Sarangani | 500268 | Lutay Integrated School | MALUNGON | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 2890000 |  |  | Completed | 1 |  |  | P00272721MN-CW1 | 18ME0142 |  |  | 2018-10-16 |  | 2018-11-21 | Verguz Const.
NC 2018 | TVL | Region XII | Sarangani | 500268 | Lutay Integrated School | MALUNGON | 0 |  | 1 | REGULAR WORKSHOP | BATCH 1 | 2890000 |  |  | Completed | 1 |  |  | P00272722MN-CW1 | 18ME0143 |  |  | 2018-10-16 |  | 2018-11-21 | Verguz Const.
NC 2018 | SHS | Region XII | Sarangani | 500274 | Kyumad Integrated School | MAASIM | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16540000 |  |  | Completed | 1 |  |  | P00272723MN-CW1 | 18ME0099 |  |  | 2018-05-17 |  | 2018-07-03 | Aguero Const./M.S. Lagman Tractors & Const. Inc. (JV)
NC 2018 | TVL | Region XII | Sarangani | 500275 | Consolacion IS | MALUNGON | 0 | 1 | 1 | UNIQUE WORKSHOP | BATCH 1 | 2490000 |  |  | Completed | 1 |  |  | P00272724MN-CW1 | 18ME0140 |  |  | 2018-10-16 |  | 2018-11-21 | FH Gopiteo Const. & Supply
NC 2018 | TVL | Region XII | Sarangani | 500275 | Consolacion IS | MALUNGON | 0 |  | 1 | REGULAR WORKSHOP | BATCH 1 | 2490000 |  |  | Completed | 1 |  |  | P00272725MN-CW1 | 18ME0141 |  |  | 2018-10-16 |  | 2018-11-21 | Leigcheen Const. Corp.
NC 2018 | SHS | Region XII | Sarangani | 500286 | Leopoldo D. Dacera Sr. IS | ALABEL (Capital) | 0 | 1 | 8 | 2STY8CL | BATCH 1 | 16635000 |  |  | Completed | 1 |  |  | P00272726MN-CW1 | 18ME0092 |  |  | 2018-05-17 |  | 2018-07-03 | Aguero Const.
NC 2018 | SHS | Region XII | Sarangani | 304530 | Leonard Young Sr. National High School | GLAN | 0 | 1 | 16 | 4STY16CL | Batch 3 | 35676814.5 |  |  | Completed | 1 |  |  |  | 18ME0152 |  |  | 2018-12-04 |  | 2018-12-20 | MFN Builders
NC 2018 | SHS | Region XII | Sarangani | 316602 | Kiblat NHS | MALUNGON | 0 | 1 | 16 | 4STY16CL | Batch 3 | 35202586.1 |  |  | Completed | 1 |  |  |  | 18ME0149 |  |  | 2018-12-04 |  | 2018-12-20 | Vertical Builders
NC 2018 | SHS | Region XII | Sarangani | 316602 | Kiblat NHS | MALUNGON | 0 |  | 16 | 4STY16CL | Batch 3 | 35202586.1 |  |  | Completed | 1 |  |  |  | 18ME0150 |  |  | 2018-12-04 |  | 2018-12-20 | L.H.E. Const. & Industial Services
NC 2018 | SHS | Region XII | Sarangani | 500265 | Datu Molod IS | MAASIM | 0 | 1 | 12 | 3STY12CL | Batch 3 | 29359267.25 |  |  | Completed | 1 |  |  |  | 18ME0151 |  |  | 2018-12-04 |  | 2018-12-20 | Verguz Const.
NC 2018 | K10 | Region XII | South Cotabato | 130737 | Eugenio L. Lido Ranada ES | POLOMOLOK | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 13839515.1 |  |  | Completed | 1 |  |  | P00272727MN-CW1 | 18MB0147
NC 2018 | K10 | Region XII | South Cotabato | 130906 | Miasong ES | TUPI | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11876168.02 |  |  | Completed | 1 |  |  | P00272728MN-CW1 | 18MB0137
NC 2018 | SHS | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17584790.26 |  |  | Completed | 1 |  |  | P00272729MN-CW1 | 18MB0155
NC 2018 | SHS | Region XII | South Cotabato | 304545 | Nicolas B. Barreras NHS - Bentung Sulit NHS Annex | POLOMOLOK | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17234790.26 |  |  | Completed | 1 |  |  | P00272730MN-CW1 | 18MB0152
NC 2018 | SHS | Region XII | South Cotabato | 304563 | Teodoro P. Prudente NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 6 | 3STY6CL | BATCH 1 | 14649515.1 |  |  | Completed | 1 |  |  | P00272731MN-CW1 | 18MB0148
NC 2018 | SHS | Region XII | South Cotabato | 304564 | Kablon NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17144790.26 |  |  | Completed | 1 |  |  | P00272732MN-CW1 | 18MB0151
NC 2018 | SHS | Region XII | South Cotabato | 304575 | Tupi NHS | TUPI | 1 | 1 | 12 | 2 UNITS 3STY6CL | BATCH 1 | 29159030.2 |  |  | Completed | 1 |  |  | P00272733MN-CW1 | 18MB0149
NC 2018 | SHS | Region XII | South Cotabato | 304577 | Upper Klinan NHS | POLOMOLOK | 1 | 1 | 8 | 2STY8CL | BATCH 1 | 17184790.26 |  |  | Completed | 1 |  |  | P00272734MN-CW1 | 18MB0156
NC 2018 | K10 | Region XII | South Cotabato | 130640 | Liwanay ES | BANGA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17249790.26 |  |  | Completed | 1 |  |  | P00272735MN | 18MG0179
NC 2018 | K10 | Region XII | South Cotabato | 130644 | Sancho ES | BANGA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2703745.92 |  |  | Completed | 1 |  |  | P00272736MN | 18MG088
NC 2018 | K10 | Region XII | South Cotabato | 130650 | Lam-asam ES | BANGA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2723745.92 |  |  | Completed | 1 |  |  | P00272737MN | 18MG0189
NC 2018 | K10 | Region XII | South Cotabato | 130671 | Lake Sebu CES | LAKE SEBU | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11776168.02 |  |  | Completed | 1 |  |  | P00272738MN | 18MG0190
NC 2018 | K10 | Region XII | South Cotabato | 130699 | El Kuda ES | NORALA | 2 | 1 | 4 | 2 UNITS 1STY2CL | BATCH 1 | 5457491.84 |  |  | Completed | 1 |  |  | P00272739MN | 18MG0191
NC 2018 | K10 | Region XII | South Cotabato | 130771 | Lambusong ES | SURALLAH | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00272740MN | 18MG0192
NC 2018 | K10 | Region XII | South Cotabato | 130783 | Surallah CES | SURALLAH | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11906168.02 |  |  | Completed | 1 |  |  | P00272741MN | 18MG0193
NC 2018 | K10 | Region XII | South Cotabato | 130808 | Datal Nabong ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2813745.92 |  |  | Completed | 1 |  |  | P00272742MN | 18MG0194
NC 2018 | K10 | Region XII | South Cotabato | 130813 | Edwards ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2638745.92 |  |  | Completed | 1 |  |  | P00272743MN | 18MG0195
NC 2018 | K10 | Region XII | South Cotabato | 130818 | Laconon IS | T'BOLI | 2 | 1 | 8 | 2 UNITS 2STY4CL | BATCH 1 | 17991803.52 |  |  | Completed | 1 |  |  | P00272744MN | 18MG0180
NC 2018 | K10 | Region XII | South Cotabato | 130825 | Lamsine ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2663745.92 |  |  | Completed | 1 |  |  | P00272745MN | 18MG0196
NC 2018 | K10 | Region XII | South Cotabato | 130829 | Lugan CES | T'BOLI | 2 | 1 | 12 | 2 UNITS 2STY6CL | BATCH 1 | 23637336.04 |  |  | Completed | 1 |  |  | P00272746MN | 18MG0181
NC 2018 | K10 | Region XII | South Cotabato | 130844 | Talambong ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 3363745.92 |  |  | Completed | 1 |  |  | P00272747MN | 18MG0197
NC 2018 | K10 | Region XII | South Cotabato | 130846 | Talufo IS | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2688745.92 |  |  | Completed | 1 |  |  | P00272748MN | 18MG0198
NC 2018 | K10 | Region XII | South Cotabato | 130847 | Tboli ES | T'BOLI | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1 |  |  | P00272749MN | 18MG0199
NC 2018 | K10 | Region XII | South Cotabato | 130870 | Dumadalig Integrated School | TANTANGAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11936168.02 |  |  | Completed | 1 |  |  | P00272750MN | 18MG0200
NC 2018 | K10 | Region XII | South Cotabato | 130879 | New Iloilo ES | TANTANGAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17249790.26 |  |  | Completed | 1 |  |  | P00272751MN | 18MG0182
NC 2018 | K10 | Region XII | South Cotabato | 208501 | Balnabo ES | T'BOLI | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2823745.92 |  |  | Completed | 1 |  |  | P00272752MN | 18MG0201
NC 2018 | SHS | Region XII | South Cotabato | 304550 | Lake Sebu NHS | LAKE SEBU | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 24668047.73 |  |  | Completed | 1 |  |  | P00272745MN | 18MG0196
NC 2018 | K10 | Region XII | South Cotabato | 316909 | Fabiola Villa-Gasis NHS - San Miguel NHS Annex | NORALA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2663745.92 |  |  | Completed | 1 |  |  | P00272746MN | 18MG0181
NC 2018 | SHS | Region XII | South Cotabato | 316911 | New Lambunao IS | TANTANGAN | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17074790.26 |  |  | Completed | 1 |  |  | P00272747MN | 18MG0197
NC 2018 | SHS | Region XII | South Cotabato | 316915 | Rang-ay IS | BANGA | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17074790.26 |  |  | Completed | 1 |  |  | P00272748MN | 18MG0198
NC 2018 | SHS | Region XII | South Cotabato | 316915 | Rang-ay IS | BANGA | 2 |  | 8 | 2STY8CL | BATCH 1 | 17094790.26 |  |  | Completed | 1 |  |  | P00272749MN | 18MG0199
NC 2018 | SHS | Region XII | South Cotabato | 304570 | Tampakan NHS | TAMPAKAN | 1 | 1 | 8 | 2STY8CL | Batch 3 | 19129195.24 |  |  | Completed | 1
NC 2018 | SHS | Region XII | South Cotabato | 316711 | Lampitak NHS - Tampakan NHS Annex | TAMPAKAN | 1 | 1 | 8 | 2STY8CL | Batch 3 | 19169195.24 |  |  | Completed | 1
NC 2018 | K10 | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2 | 1 | 3 | 1STY3CL | Batch 3 | 5657588.75 |  |  | Completed | 1 |  |  | P00275296MN | 18MG0250
NC 2018 | TVL | Region XII | South Cotabato | 304543 | Banga NHS | BANGA | 2 | 1 | 12 | 2STY12CL (6RW LAB) | Batch 3 | 30270193.49 |  |  | Completed | 1 |  |  | P00275297MN | 18MG0258
NC 2018 | TVL | Region XII | South Cotabato | 304543 | Banga NHS | BANGA | 2 |  | 4 | 2STY4CL (2SL LAB) | Batch 3 | 12013481.81 |  |  | Completed | 1 |  |  | P00275298MN | 18MG0261
NC 2018 | TVL | Region XII | South Cotabato | 304543 | Banga NHS | BANGA | 2 |  | 4 | 2STY4CL (2ICT LAB) | Batch 3 | 11805981.81 |  |  | Completed | 1 |  |  | P00275299MN | 18MG0262
NC 2018 | TVL | Region XII | South Cotabato | 316704 | Lamba NHS - Banga NHS Annex | BANGA | 2 | 1 | 4 | 2STY4CL (2SL LAB) | Batch 3 | 11955981.81 |  |  | Completed | 1 |  |  | P00275300MN | 18MG0263
NC 2018 | TVL | Region XII | South Cotabato | 316714 | Malaya NHS - Banga NHS Annex | BANGA | 2 | 1 | 6 | 2STY6CL (3RW LAB) | Batch 3 | 15361459.76 |  |  | Completed | 1 |  |  | P00275301MN | 18MG0259
NC 2018 | TVL | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2 | 1 | 4 | 2STY4CL (2SL LAB) | Batch 3 | 11884481.81 |  |  | Completed | 1 |  |  | P00275302MN | 18MG0264
NC 2018 | TVL | Region XII | South Cotabato | 316914 | El Nonok IS | BANGA | 2 | 1 | 4 | 2STY4CL (2ICT LAB) | Batch 3 | 11965981.81 |  |  | Completed | 1 |  |  | P00275303MN | 18MG0265
NC 2018 | K10 | Region XII | Sultan Kudarat | 130968 | Aguil Elementary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2772000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 130970 | Lam-alis Elementary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2780000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 130971 | Lasak Elementary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2780000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 130977 | Old Bantangan Elementary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2780000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 131104 | Pimbalayan Elementary School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2755000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 131161 | Sumapal Elementary School | LUTAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2772000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 209019 | Mauno Primary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2820000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 209032 | Balnate Elementary School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2780000 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304585 | Bambad National High School | ISULAN (Capital) | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36603000 |  |  | Completed | 1 |  |  | 18MF0088 | P00272766MN-CW1 | [5 empty] | LHE & Robeth (Joint Venture)
NC 2018 | TVL | Region XII | Sultan Kudarat | 304585 | Bambad National High School | ISULAN (Capital) | 1 |  | 4 | 2STY4CL LAB | BATCH 1 | 21810000 |  |  | Completed | 1 |  |  | 18MF0083 | P00272767MN-CW1 | [5 empty] | C.S. Construction
NC 2018 | TVL | Region XII | Sultan Kudarat | 304588 | Columbio National High School | COLUMBIO | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36669000 |  |  | Completed | 1 |  |  | 18MF0089 | P00272768MN-CW1 | [5 empty] | Legacy
NC 2018 | TVL | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36585000 |  |  | Completed | 1 |  |  | 18MF0086 | P00272769MN-CW1 | [5 empty] | JTA & Dalanon (Joint Venture)
NC 2018 | TVL | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) | 1 |  | 8 | 4STY8CL LAB | BATCH 1 | 46675000 |  |  | Completed | 1 |  |  | 18MF0100 | P00272770MN-CW1 | [5 empty] | JTA & Dalanon (Joint Venture)
NC 2018 | TVL | Region XII | Sultan Kudarat | 304594 | Kalanawe II National High School | PRESIDENT QUIRINO | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18362000 |  |  | Completed | 1 |  |  | 18MF0106 | P00272771MN-CW1 | [5 empty] | Pearl Construction
NC 2018 | TVL | Region XII | Sultan Kudarat | 304595 | Kapingkong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18380000 |  |  | Completed | 1 |  |  | 18MF0107 | P00272772MN-CW1 | [5 empty] | Cofejok Construction & Supply Corporation
NC 2018 | TVL | Region XII | Sultan Kudarat | 304596 | Laguilayan National High School | ISULAN (Capital) | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36595000 |  |  | Completed | 1 |  |  | 18MF0090 | P00272773MN-CW1 | [5 empty] | JTA & Dalanon (Joint Venture)
NC 2018 | TVL | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36590000 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304597 | Lambayong National High School | LAMBAYONG (MARIANO MARCOS) | 1 |  | 4 | 2STY4CL LAB | BATCH 1 | 21920000 |  |  | Completed | 1 |  |  | 18MF0083 | P00272775MN-CW1 | [5 empty] | Blimex Construction
NC 2018 | TVL | Region XII | Sultan Kudarat | 304598 | Pimbalayan National High School - Lambayong Annex | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18362000 |  |  | Completed | 1 |  |  | 18MF0105 | P00272776MN-CW1 | [5 empty] | Blimex Construction
NC 2018 | TVL | Region XII | Sultan Kudarat | 304606 | Lutayan National High Schoool | LUTAYAN | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36580000 |  |  | Completed | 1 |  |  | 18MF0087 | P00272777MN-CW1 | [5 empty] | Legacy
NC 2018 | TVL | Region XII | Sultan Kudarat | 304607 | Madanding National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18328000 |  |  | Completed | 1 |  |  | 18MF0104 | P00272778MN-CW1 | [5 empty] | Palmares Gen. Mdse.
NC 2018 | TVL | Region XII | Sultan Kudarat | 304608 | Maligaya National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36605000 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304609 | Mamali National High School | LAMBAYONG (MARIANO MARCOS) | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18328000 |  |  | Completed | 1 |  |  | 18MF0103 | P00272780MN-CW1 | [5 empty] | Blimex Construction
NC 2018 | TVL | Region XII | Sultan Kudarat | 304614 | New Pangasinan National High School | ISULAN (Capital) | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18345000 |  |  | Completed | 1 |  |  | 18MF0099 | P00272781MN-CW1 | [5 empty] | Palmares Gen. Mdse.
NC 2018 | TVL | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36580000 |  |  | Completed | 1 |  |  | 18MF0092 | P00272782MN-CW1 | [5 empty] | Stoneline
NC 2018 | TVL | Region XII | Sultan Kudarat | 304618 | Central Mangilala High School - President Quirino Annex | PRESIDENT QUIRINO | 1 | 1 | 3 | 3STY3CL LAB | BATCH 1 | 18389000 |  |  | Completed | 1 |  |  | 18MF0101 | P00272783MN-CW1 | [5 empty] | C.A. Betalac
NC 2018 | TVL | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36688000 |  |  | Completed | 1 |  |  | 18MF0085 | P00272784MN-CW1 | [5 empty] | BRE Construction
NC 2018 | SHS | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1 |  | 6 | 2STY6CL | BATCH 1 | 14880000 |  |  | Completed | 1 |  |  | 18MF0084 | P00272785MN-CW1 | [5 empty] | Robeth Construction & Gen. Mdse.
NC 2018 | SHS | Region XII | Sultan Kudarat | 304625 | Telafas National High School | COLUMBIO | 1 |  | 2 | 1STY2CL | BATCH 1 | 2772000 |  |  | Completed | 1 |  |  | 18MF0076 | P00272786MN-CW1 | [5 empty] | Nirvana
NC 2018 | K10 | Region XII | Sultan Kudarat | 316806 | Datalblao National High School | COLUMBIO | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2780000 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 131032 | DATU GUIABAR PILOT SCHOOL | KALAMANSIG | 2 | 1 | 15 | 3STY15CL w/ TOILET | BATCH 1 | 34137450.12 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Sultan Kudarat | 131129 | Salangsang Elementary School | LEBAK | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 22607261 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10287002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304581 | Kapaya National High School | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304582 | Masiag National High School - Bagumbayan Annex | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10307002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304584 | Bai Saripinang National High School | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10327002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304586 | E. Arcaño Memorial National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304587 | Busok National High School | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10267002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 |  | 12 | 2 UNITS 2STY6CL | BATCH 1 | 25246029.62 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 |  | 12 | 4STY12CL | BATCH 1 | 36304788.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sultan Kudarat | 304591 | Kalamansig National High School | KALAMANSIG | 2 |  | 9 | 3STY9CL | BATCH 1 | 25563708.4 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304592 | Sangay National High School | KALAMANSIG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10307002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304593 | Datu Wasay National High School | KALAMANSIG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10287002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304599 | Langgal National High School | SEN. NINOY AQUINO | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10387002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304601 | Gapok National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10267002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10267002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304603 | Lebak National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10267002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304604 | Keytodac National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10347002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10267002.9 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sultan Kudarat | 304605 | Lebak Legislated National High School | LEBAK | 2 |  | 6 | 2STY6CL | BATCH 1 | 12623014.81 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304610 | Milbuk National High School | PALIMBANG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10347002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10347002.9 |  |  | Completed | 1
NC 2018 | SHS | Region XII | Sultan Kudarat | 304611 | Baluan Senior High School | PALIMBANG | 2 |  | 6 | 2STY6CL | BATCH 1 | 12923014.81 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304613 | New Panay National High School | ESPERANZA | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304615 | Palimbang National High School | PALIMBANG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10347002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304619 | Purikay National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304621 | Salabaca National High School | ESPERANZA | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304623 | Sta. Clara National High School | KALAMANSIG | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 304626 | Tran National High School | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 316802 | Sewod National High School - Langgal Annex | SEN. NINOY AQUINO | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10307002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 316803 | Biwang NHS - Bagumbayan Annex | BAGUMBAYAN | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10227002.9 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK | 2 | 1 | 4 | 2STOREY2LAB | BATCH 1 | 10287002.9 |  |  | Completed | 1
NC 2018 | K10 | Region XII | Tacurong City | 131232 | Josue Alcasid CS | CITY OF TACURONG | 1 | 1 | 8 | 2 UNITS 2STY4CL | BATCH 1 | 21850000 |  |  | Completed | 1
NC 2018 | TVL | Region XII | Tacurong City | 304579 | Apolinario S. Bernardo National High School | CITY OF TACURONG | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36760000 |  |  | Completed | 1 |  |  | P00272823MN-CW1 | 18MF0098 |  | 2018-06-21 | 2018-07-03 | 2018-07-13 | 2018-07-24 | Bre Construction
NC 2018 | TVL | Region XII | Tacurong City | 304620 | Rajah Muda NHS | CITY OF TACURONG | 1 | 1 | 4 | 2STY4CL LAB | BATCH 1 | 21815000 |  |  | Completed | 1 |  |  | P00272824MN-CW1 | 18MF0082 |  | 2018-06-21 | 2018-07-03 | 2018-07-13 | 2018-07-24 | Cofejok Construction & Supply
NC 2018 | TVL | Region XII | Tacurong City | 304622 | San Emmanuel NHS | CITY OF TACURONG | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36680000 |  |  | Completed | 1 |  |  | P00272825MN-CW1 | 18MF0095 |  | 2018-06-21 | 2018-07-03 | 2018-07-06 | 2018-07-17 | Arcinue Commercial Corp.
NC 2018 | TVL | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36635000 |  |  | Completed | 1 |  |  | P00272826MN-CW1 | 18MF0093 |  | 2018-06-21 | 2018-07-03 | 2018-07-06 | 2018-07-17 | R. Semilla Const. & Marketing
NC 2018 | TVL | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 |  | 2 | 2STY2CL LAB | BATCH 1 | 11297000 |  |  | Completed | 1 |  |  | P00272827MN-CW1 | 18MF0079 |  | 2018-06-21 | 2018-07-03 | 2018-07-06 | 2018-07-17 | C.A. Betalac Const. & Gen. Mdse.
NC 2018 | SHS | Region XII | Tacurong City | 304624 | Tacurong NHS | CITY OF TACURONG | 1 |  | 16 | 4STY16CL | BATCH 1 | 38765000 |  |  | Completed | 1 |  |  | P00272828MN-CW1 | 18MF0102 |  | 2018-07-13 | 2018-07-26 | 2018-07-31 |  | Stoneline Construction
NC 2018 | TVL | Region XII | Tacurong City | 304627 | Virginia F. Griño National High School | CITY OF TACURONG | 1 | 1 | 6 | 3STY6CL LAB | BATCH 1 | 36635000 |  |  | Completed | 1 |  |  | P00272829MN-CW1 | 18MF0094 |  | 2018-06-21 | 2018-07-03 | 2018-07-06 | 2018-07-17 | LHE Const. & Industrial Sevice Inc. / Robeth Gen. Mdse. Const. & Supply (JV)
NC 2019 | K10 | Region XII | General Santos City | 131284 | Irineo Santiago ES | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 4 | 2STY4CL |  | 10143273.8472 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | Koronadal City | 131388 | Chua Elementary School | CITY OF KORONADAL (Capital) | 2 | 1 | 4 | 2STY4CL |  | 10848034.2645 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 8 | 2STY8CL |  | 22466024.4687 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | North Cotabato | 316545 | Yanson High School | ALAMADA | 1 | 1 | 4 | 1STY4CL |  | 9763900.9502 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | North Cotabato | 304697 | Bongolanon High School | MAGPET | 2 | 1 | 8 | 2STY8CL |  | 22372395.3997 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XII | North Cotabato | 304420 | Banisilan NHS | BANISILAN | 3 | 1 | 15 | 3STY15CL |  | 52124547.1519 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | Sarangani | 500710 | James Alfred Strong Integrated School | MAITUM | 0 | 1 | 4 | 2STY4CL |  | 9327655.6466 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XII | Sarangani | 304525 | Glan-Padidu NHS | GLAN | 0 | 1 | 16 | 4STY16CL |  | 35354981.5363 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | Sarangani | 500835 | Dakok Tamulon Integrated School | MALUNGON | 0 | 1 | 4 | 2STY4CL |  | 9357498.2671 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region XII | Sarangani | 304521 | Baliton NHS | GLAN | 0 | 1 | 12 | 3STY12CL |  | 29432665.4181 |  | completed | 1 | [11 empty] | 0
NC 2019 | TVL | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 2 | 2STY4CL (2REG WS) |  | 10239355.8833 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region XII | South Cotabato | 130660 | Blit ES | LAKE SEBU | 2 | 1 | 4 | 2UNITS 1STY2CL |  | 7442573.634 |  | Completed | 1 |  |  |  | 19MG0166 |  |  |  |  | 2019-10-21 |  |  | 0
NC 2019 | K10 | Region XII | South Cotabato | 130810 | Demamis ES | T'BOLI | 2 | 1 | 3 | 1STY3CL |  | 5671732.7219 |  | completed | 1 |  |  |  | 19MG0167 |  |  |  |  | 2019-10-21 |  |  | 0
NC 2019 | SHS | Region XII | South Cotabato | 304547 | Edwards NHS | T'BOLI | 2 | 1 | 6 | 2STY6CL |  | 15389838.4094 |  | completed | 1 |  |  |  | 19MG0168 |  |  |  |  | 2019-10-21 |  |  | 0
NC 2020 | K10 | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 15 | 3STY15CL |  | 39789598.43 |  |  | Completed | 1
NC 2020 | K10 | Region XII | Kidapawan City | 131357 | New Bohol Elementary School | Kidapawan City | 2 | 1 | 6 | 2STY6CL |  | 16999783.75 |  |  | Completed | 1
NC 2020 | K10 | Region XII | Koronadal City | 131378 | Marbel 3 ES | Koronadal City | 2 | 1 | 6 | 2STY6CL |  | 16665796.82 |  |  | Completed | 1 | [8 empty] | 2020-08-10 | Alexander Construction
NC 2020 | TVL | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 16 | 4STY16CL (2SL, 2ICT, & 4RW) LAB WORKSHOP |  | 43147006.54 |  |  | Completed | 1 | [8 empty] | 2020-08-10 | FH Gopiteo Construction and Supply
NC 2020 | K10 | Region XII | North Cotabato | 130174 | Midsayap Pilot ES | Midsayap | 1 | 1 | 10 | 2STY10CL |  | 29290446.76 |  |  | Completed | 1
NC 2020 | K10 | Region XII | North Cotabato | 303624 | Cesar C. Cabaya Sr. HS | Libungan | 1 | 1 | 4 | 1STY4CL |  | 10780502.7 |  |  | Completed | 1
NC 2020 | K10 | Region XII | North Cotabato | 130082 | Temporan ES | MAGPET | 2 | 1 | 3 | 1STY3CL |  | 7639050 |  |  | Completed | 1
NC 2020 | K10 | Region XII | North Cotabato | 500460 | Sallab High School | MAGPET | 2 | 1 | 2 | 1STY2CL |  | 4779562.95 |  |  | Completed | 1
NC 2020 | K10 | Region XII | North Cotabato | 129948 | Rancho ES | Banisilan | 3 | 1 | 4 | 1STY4CL |  | 9563400.95 |  |  | Completed | 1
NC 2020 | SHS | Region XII | North Cotabato | 304510 | New Rizal HS | M'LANG | 3 | 1 | 8 | 2STY8CL |  | 19452510 |  |  | Completed | 1
NC 2020 | SHS | Region XII | Sarangani | 500263 | JBT Caing Sr. Memorial Integrated School | KIAMBA | 0 | 1 | 8 | 2STY8CL |  | 18538693.47 |  |  | Completed | 1
NC 2020 | K10 | Region XII | Sarangani | 500711 | Francisco A. Cagang Sr. Integrated School | MALAPATAN | 0 | 1 | 8 | 2STY8CL |  | 18538693.47 |  |  | Completed | 1
NC 2020 | K10 | Region XII | Sarangani | 130452 | Calpidong ES | GLAN | 0 | 1 | 2 | 1STY2CL |  | 4836180.9 |  |  | Completed | 1
NC 2020 | K10 | Region XII | South Cotabato | 130721 | Dole Cannery CES | POLOMOLOK | 1 | 1 | 4 | 2STY4CL |  | 13342901.57 |  |  | Completed | 1
NC 2020 | K10 | Region XII | South Cotabato | 100617 | El Nino ES | LAKE SEBU | 2 | 1 | 4 | 2UNITS-1STY2CL |  | 10189984.57 |  |  | Completed | 1
NC 2020 | K10 | Region XII | South Cotabato | 100777 | Datal Ligaw Elementary School | LAKE SEBU | 2 | 1 | 6 | 2UNITS-1STY3CL |  | 14501765.4 |  |  | Completed | 1
NC 2020 | K10 | Region XII | South Cotabato | 281569 | Datu Kahar Macasayon ES | LAKE SEBU | 2 | 1 | 6 | 2STY6CL |  | 16705896.82 |  |  | Completed | 1
NC 2020 | K10 | Region XII | Sultan Kudarat | 131085 | Pinguiaman Elementary School | Lambayong | 1 | 1 | 3 | 1STY 3CL w/ Toilet @ Each Classroom |  | 6215500 |  |  | Completed | 1 | 2020-11-27 | 2021-06-14 |  | 20MF0061 | [5 empty] | ALPXR Constrcution & Builders Corp.
NC 2020 | K10 | Region XII | Sultan Kudarat | 131209 | Malingon Elementary School | Pres. Quirino | 1 | 1 | 3 | 1STY 3CL w/ Toilet @ Each Classroom |  | 6115250 |  |  | COMPLETED | 1 | 2020-11-27 | 2021-02-19 |  | 20MF0062 | [5 empty] | ALPXR Constrcution & Builders Corp.
NC 2020 | K10 | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | Lutayan | 1 | 1 | 5 | 1STY 5CL w/ Toilet @ Each Classroom |  | 10225500 |  |  | Completed | 1 | 2021-01-16 |  |  | 20MF0060 | [5 empty] | Dalanon Construction
NC 2020 | K10 | Region XII | Sultan Kudarat | 130910 | Bagumbayan Central Elementary School | BAGUMBAYAN | 2 | 1 | 6 | 2STY6CL |  | 15037500 |  |  | COMPLETED | 1 | 2021-04-12 |  |  | 20MH0104 | [5 empty] | Dalanon Construction
NC 2020 | K10 | Region XII | Sultan Kudarat | 131124 | Keytodac Central School | LEBAK | 2 | 1 | 6 | 2STY6CL |  | 15087625 |  |  | COMPLETED | 1 | 2021-03-24 |  |  | 20MH0071 | [5 empty] | Albanor Construction
NC 2020 | K10 | Region XII | Sultan Kudarat | 131132 | Ampad-Guiabar Memorial Elementary School | LEBAK | 2 | 1 | 6 | 2STY6CL |  | 14937250 |  |  | COMPLETED | 1 | 2021-03-24 | 2021-10-25 |  | 20MH0072 | [5 empty] | Robeth Gen. Merchandise
NC 2020 | SHS | Region XII | Sultan Kudarat | 304580 | Bagumbayan National High School | BAGUMBAYAN | 2 | 1 | 6 | 2STY6CL |  | 15037500 |  |  | COMPLETED | 1 | 2021-04-12 | 2022-03-18 |  | 20MH0105 | [5 empty] | FPJ Construction & Supply
NC 2020 | SHS | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA | 2 | 1 | 6 | 2STY6CL |  | 15037500 |  |  | COMPLETED | 1 | 2021-03-28 |  |  | 20MH0106 | [5 empty] | Dalanon Construction
NC 2020 | SHS | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO | 2 | 1 | 6 | 2STY6CL |  | 15037500 |  |  | COMPLETED | 1 | 2021-04-12 | 2021-07-16 |  | 20MH0107 | [5 empty] | FPJ Construction & Supply
NC 2021 | K10 | Region XII | General Santos City | 131273 | Lagao Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 101682.5525 | 101428.98 |  | COMPLETED | 1
NC 2021 | K10 | Region XII | General Santos City | 131313 | New Society Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 127773.2866 | 127454.65 |  | COMPLETED | 1
NC 2021 | SHS | Region XII | South Cotabato | 304544 | Bentung Sulit NHS | POLOMOLOK | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 848028.6146 | 845913.83 |  | COMPLETED | 1
NC 2021 | SHS | Region XII | South Cotabato | 304545 | Nicolas B. Barreras NHS - Bentung Sulit NHS Annex | POLOMOLOK | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 105524.6938 | 105261.54 |  | COMPLETED | 1
NC 2021 | SHS | Region XII | South Cotabato | 304564 | Kablon NHS - Polonuling NHS Annex | TUPI | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 3516853.1574 | 3508082.95 |  | COMPLETED | 1
NC 2021 | SHS | Region XII | South Cotabato | 304577 | Upper Klinan NHS | POLOMOLOK | 1 | 1 | 8 | Construction/Completion (2STY8CL) |  | 1843039.0874 | 1838442.98 |  | COMPLETED | 1
NC 2023 | K10 | Region XII | General Santos City | 131267 | A. Biscayda Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 4 |  | Batch 1 | 15338241.37 | 15205195.9 | 14962758.61 | completed | 1 | 2024-04-21 | 2024-08-11 | P00775555MB-CW1 | 23MB0164 | 2023-09-06 | 2023-06-16 | 2023-12-12 | 2023-12-22 | 2023-12-29 | JCML BUILDERS INC | Completed
NC 2023 | K10 | Region XII | General Santos City | 131282 | Arizala Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 4 |  | Batch 1 | 15325086.91 | 15192155.55 | 15101699.71 | completed | 1 | 2024-04-21 | 2024-08-01 | P00775557MB-CW1 | 23MB0166 | 2023-09-06 | 2023-06-16 | 2023-12-12 | 2023-12-22 | 2023-12-29 | EJC BUILDERS & MERCHANDISE | Completed
NC 2023 | K10 | Region XII | General Santos City | 210011 | H.N. Cahilsot Central Elementary School II | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 4 |  | Batch 1 | 8894561.03 | 8817408.7 | 8717357.46 | completed | 1 | 2024-06-03 | 2024-05-01 | P0077558MN-CW1 | 23MB0167 | 2023-07-08 | 2023-08-14 | 2023-08-29 | 2023-09-10 | 2023-10-28 | TAJ BUILDER AND SUPPLY (45862) | Completed
NC 2023 | K10 | Region XII | General Santos City | 131279 | Lanton Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 |  | Batch 1 | 4573525.66 | 4533854.43 | 4518787.27 | completed | 1 | 2024-04-21 | 2024-05-21 | P00775556MN-CW1 | 23MB0165 | 2023-09-06 | 2023-06-16 | 2023-12-12 | 2023-12-22 | 2023-12-29 | COFEJOK CONST. & SUPPLY CORP. | Completed
NC 2023 | K10 | Region XII | Kidapawan City | 131341 | Lapan Elementary School | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 4 |  | Batch 1 | 10302591.52 | 10213225.79 | 9887912.33 | ongoing | 1 | 2024-02-24 | 2024-03-24 | 23MC0086 |  |  | 2023-08-25 | 2023-09-06 | 2023-09-25 | 2023-10-11 | REEM CONSTRUCTION AND SUPPLY | Completed
NC 2023 | K10 | Region XII | Kidapawan City | 131334 | Manongol CES | CITY OF KIDAPAWAN (Capital) | 2 | 1 | 8 |  | Batch 1 | 26573342.74 | 26342842.86 | 23852056.13 | completed | 1 | 2024-03-15 | 2024-05-23 | 23MC0079 |  |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-12-10 | EQUICON ENGINEERING SERVICES | Completed
NC 2023 | SHS | Region XII | Koronadal City | 304669 | Concepcion NHS | CITY OF KORONADAL (Capital) |  | 1 | 6 |  | Batch 1 | 13618125 | 13500000 | 13489856.98 | completed | 1 | 2024-07-30 | 2024-12-05 | 23MG0067 |  | 2023-10-21 | 2023-10-31 | 2023-11-13 | 2023-12-21 | 2024-01-02 | Gemma Construction Supply, Inc. | Completed
NC 2023 | K10 | Region XII | Koronadal City | 131407 | Koronadal Central II ES | CITY OF KORONADAL (Capital) |  | 1 | 6 |  | Batch 1 | 30262500 | 30000000 | 29989984.68 | completed | 1 | 2024-07-30 | 2024-12-05 | 23MG0067 |  | 2023-10-21 | 2023-10-31 | 2023-11-13 | 2023-12-21 | 2024-01-02 | Gemma Construction Supply, Inc. | Completed
NC 2023 | SHS | Region XII | Koronadal City | 304672 | Marbel 7 National High School | CITY OF KORONADAL (Capital) |  | 1 | 8 |  | Batch 1 | 26675637.19 | 26444250 | 26390903.46 | completed | 1 | 2024-05-06 | 2024-12-05 | 23MG0063 |  | 2023-09-20 | 2023-09-28 | 2023-10-10 | 2023-10-17 | 2023-10-25 | Dedase Construction Services | Completed
NC 2023 | K10 | Region XII | North Cotabato | 130058 | Kisandal ES | MAGPET | 2 | 1 | 2 |  | Batch 1 | 6117516.88 | 6064452.92 | 6061154.1 | completed | 1 | 2024-09-01 |  | P00775564MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-11 | PSN Construction & Supply | Completed
NC 2023 | K10 | Region XII | North Cotabato | 130094 | Biangan Elementary School | MAKILALA | 2 | 1 | 3 |  | Batch 1 | 8733555.17 | 8657799.42 | 8571220.83 | completed | 1 | 2024-01-19 |  | P00775567MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-11 | REEM Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 130085 | Indangan ES | MAKILALA | 2 | 1 | 2 |  | Batch 1 | 6329230.77 | 6274330.38 | 6211587.06 | completed | 1 | 2024-10-01 |  | P00775565MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-11 | REEM Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 130116 | Leboce ES | MAKILALA | 2 | 1 | 3 |  | Batch 1 | 8306991.98 | 8234936.29 | 8148923.81 | completed | 1 | 2024-01-19 |  | P00775568MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-11 | REEM Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 207566 | Lower Saguing ES | MAKILALA | 2 | 1 | 4 |  | Batch 1 | 10607423.9 | 10515414.03 | 10510390.5 | completed | 1 | 2024-02-26 |  | P00775570MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-10-26 | 2023-10-10 | PSN Construction & Supply
NC 2023 | K10 | Region XII | North Cotabato | 130088 | Makilala Central Elementary School | MAKILALA | 2 | 1 | 3 |  | Batch 1 | 8880155.21 | 8803127.84 | 8796029.6 | completed | 1 | 2024-01-20 |  | P00775566MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-11 | PSN Construction & Supply
NC 2023 | K10 | Region XII | North Cotabato | 130125 | Villaflores ES | MAKILALA | 2 | 1 | 3 |  | Batch 1 | 8739381.86 | 8663575.57 | 8652453.09 | completed | 1 | 2024-01-20 |  | P00775569MN-CW1 | 8/7/2023 to 9/6/2023 |  | 2023-08-25 | 2023-09-06 | 2023-09-26 | 2023-10-12 | 3M1 Construction
NC 2023 | K10 | Region XII | North Cotabato | 130257 | Gaunan ES | Mlang | 3 | 1 | 2 |  | Batch 1 | 6034144.68 | 5981803.89 | 5971393.33 | completed | 1 | 2024-10-01 |  | P00775571MN | 9/1/2023 | 2023-09-01 | 2023-09-08 | 2023-09-21 | 2023-09-28 | 2023-10-12 | ARBY'S Builders and Construction Supply Corp.
NC 2023 | K10 | Region XII | North Cotabato | 130391 | Bituan ES | Tulunan | 3 | 1 | 2 |  | Batch 1 | 6025065.78 | 5972803.75 | 5962707.09 | completed | 1 | 2024-10-01 |  | P00775572MN | 9/1/2023 | 2023-09-01 | 2023-09-08 | 2023-09-21 | 2023-09-28 | 2023-10-12 | ARBY'S Builders and Construction Supply Corp.
NC 2023 | K10 | Region XII | North Cotabato | 130394 | Nabundasan ES | TULUNAN | 3 | 1 | 6 |  | Batch 1 | 16744583.56 | 16599339.34 | 16589219.61 | completed | 1 | 2024-03-30 |  | P00775573PM | 8/15/2023 | 2023-08-15 | 2023-08-22 | 2023-09-04 | 2023-09-18 | 2023-09-25 | John Ray Developer and Supplies
NC 2023 | K10 | Region XII | North Cotabato | 129843 | Mirasol ES | ALAMADA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4999000 | completed | 1 | 2023-12-20 |  | P00775574MN (23MD0091) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-18 | 2023-08-31 | LLABAN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 129849 | Rangayen ES | ALAMADA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4949951.46 | completed | 1 | 2023-12-20 |  | P00775575MN (23MD0094) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-18 | 2023-08-31 | RDEN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 130031 | Nicaan Central Elementary School | LIBUNGAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948686.16 | completed | 1 | 2023-12-28 |  | P00775576MN (23MD0089) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-31 | 2023-09-12 | RDEN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 130175 | Miguel Intes (Katingawan) ES | MIDSAYAP |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4996939.16 | completed | 1 | 2023-12-28 |  | P00775577MN (23MD0092) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-31 | 2023-09-12 | RDEN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 130178 | Salunayan ES | MIDSAYAP |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948686.16 | completed | 1 | 2023-12-28 |  | P00775578MN (23MD0090) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-31 | 2023-09-12 | RDEN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 130204 | Sta. Cruz ES | MIDSAYAP |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4948977.86 | completed | 1 | 2023-12-20 |  | P00775579MN (23MD0093) |  | 2023-07-20 | 2023-07-27 | 2023-08-10 | 2023-08-18 | 2023-08-31 | RDEN CONST. & SUPPLY
NC 2023 | K10 | Region XII | North Cotabato | 304706 | Inac High School | MAGPET |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4996304.37 | completed | 1 | 2024-10-01 |  | P00775580MN-CW1 |  |  | 2023-07-21 | 2023-08-02 | 2023-09-25 | 2023-10-12 | PSN Construction & Supply
NC 2023 | K10 | Region XII | North Cotabato | 100922 | Braulio G. Dano Elementary School | MAKILALA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4997000.01 | completed | 1 | 2023-06-12 |  | P00775581MN-CW1 |  |  | 2023-07-21 | 2023-08-02 | 2023-08-24 | 2023-09-07 | PSN Construction & Supply
NC 2023 | K10 | Region XII | North Cotabato | 130095 | Buena Vida ES | MAKILALA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4996500 | completed | 1 | 2023-12-12 |  | P00775582MN-CW1 |  |  | 2023-07-21 | 2023-08-02 | 2023-08-25 | 2023-09-13 | PSN Construction & Supply
NC 2023 | K10 | Region XII | North Cotabato | 130096 | Buhay ES | MAKILALA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4950000 | completed | 1 | 2024-10-01 |  | P00775583MN-CW1 |  |  | 2023-07-21 | 2023-08-02 | 2023-09-25 | 2023-10-12 | REEM Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 316539 | Malungon High School | MAKILALA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 |  | Not Yet Started | 0 | [10 empty] | Fund Riverted
NC 2023 | K10 | Region XII | North Cotabato | 130105 | San Isidro ES | MAKILALA |  | 1 | 1 |  | Batch 1 | 2824500 | 2800000 | 2379450.02 | COMPLETED | 1 | 2023-11-17 |  | P00775584MN-CW1 |  |  | 2023-07-21 | 2023-08-02 | 2023-08-25 | 2023-09-13 | M3-FR Developer and Construction Corp
NC 2023 | SHS | Region XII | North Cotabato | 304453 | Kibudtungan NHS | CARMEN |  | 1 | 6 |  | Batch 1 | 16539013.56 | 16395552.47 | 16370268.21 | COMPLETED | 1 | 2024-04-19 |  | P00775588MN |  | 2023-09-22 | 2023-09-29 | 2023-12-10 | 2023-09-28 | 2023-10-12 | PSN Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 129970 | New Bentangan PS | CARMEN |  | 1 | 2 |  | Batch 1 | 6000686.52 | 5948635.95 | 5933455.36 | COMPLETED | 1 | 2024-10-01 |  | P00775586MN |  | 2023-01-09 | 2023-08-09 | 2023-09-21 | 2023-09-28 | 2023-12-10 | PSN Construction and Supply
NC 2023 | K10 | Region XII | North Cotabato | 129992 | Tonganon ES | CARMEN |  | 1 | 4 |  | Batch 1 | 10852663.91 | 10758526.8 | 10733478.55 | COMPLETED | 1 | 2024-01-30 |  | P00775587MN |  | 2023-01-09 | 2023-08-09 | 2023-09-21 | 2023-09-28 | 2023-12-10 | PSN Construction and Supply
NC 2023 | K10 | Region XII | Sarangani | 130469 | Margus Elementary School | GLAN |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 6794163.71 | COMPLETED | 1 | 2024-03-21 | 2024-04-28 | P00775589MN-CW1 | 23ME0084 |  | 2023-08-16 | 2023-09-06 | 2023-09-19 | 2023-09-26 | THREE MB BUILDERS
NC 2023 | K10 | Region XII | Sarangani | 130507 | Salakit Elementary School | KIAMBA |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7390000 | COMPLETED | 1 | 2024-03-13 | 2024-03-01 | P00775590MN-CW1 | 23ME0081 |  | 2023-08-16 | 2023-09-06 | 2023-09-26 | 2023-10-02 | VERGUZ CONSTRUCTION
NC 2023 | K10 | Region XII | Sarangani | 130521 | Maasim CES | MAASIM |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7449877.98 | COMPLETED | 1 | 2024-04-02 | 2024-04-02 | P00775591MN-CW1 | 23ME0083 |  | 2023-08-16 | 2023-09-06 | 2023-09-13 | 2023-09-19 | SHEPPERD CONSTRUCTION & SUPPLY
NC 2023 | SHS | Region XII | Sarangani | 304522 | Banate National High School | MALUNGON |  | 1 | 3 |  | Batch 1 | 7565625 | 7500000 | 7400000 | COMPLETED | 1 | 2024-03-30 | 2024-03-27 | P00775592MN-CW1 | 23ME0082 |  | 2023-08-16 | 2023-09-06 | 2023-09-13 | 2023-09-19 | THE TRENDSETTER CONSTRUCTION AND SUPPLY CORP.
NC 2023 | K10 | Region XII | South Cotabato | 501847 | LR Morandante Integrated School | POLOMOLOK |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4734037.81 | Completed | 1 | 2024-07-01 | 2024-07-01 | P00775595MN-CW1 | 23MB0170 | 2023-07-13 | 2023-01-08 | 2023-08-14 | 2023-08-25 | 2023-11-09 | ED SIXTY FOUR ENTERPRISES | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 501198 | Polomolok Creek Integrated School | POLOMOLOK |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4730344.96 | Completed | 1 | 2024-07-01 | 2024-07-01 | P00775594MN-CW1 | 23MB0169 | 2023-07-13 | 2023-01-08 | 2023-08-14 | 2023-08-25 | 2023-11-09 | JAMI CONSTRUCTION AND SUPPLY | COMPLETED
NC 2023 | SHS | Region XII | South Cotabato | 304560 | Polomolok National High School | POLOMOLOK |  | 1 | 3 |  | Batch 1 | 6661042.54 | 6603263.98 | 6568015.41 | Completed | 1 | 2024-03-31 | 2024-03-31 | P00775593MN-CW1 | 23MB0168 | 2023-07-08 | 2023-08-14 | 2023-08-29 | 2023-06-11 | 2023-11-22 | FREDEN CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 502160 | Silway 7 Integrated School | POLOMOLOK |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4716378.89 | Completed | 1 | 2024-07-01 | 2024-07-01 | P00775596MN-CW1 | 23MB0171 | 2023-07-23 | 2023-01-08 | 2023-08-14 | 2023-08-25 | 2023-11-09 | VERGUZ CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 208527 | Tampakan SPED Center | TAMPAKAN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4726773.59 | Completed | 1 | 2024-07-01 | 2024-07-01 | P00775597MN-CW1 | 23MB0172 | 2023-07-23 | 2023-01-08 | 2023-08-14 | 2023-08-25 | 2023-11-09 | MCHAI CONSTRUCTION & HARDWARE SUPPLY | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 502385 | Juan-Loreto Tamayo Integrated School | TUPI |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 9949439.16 | Completed | 1 | 2024-02-23 | 2024-02-23 | P00775598MN-CW1 | 23MB0176 | 2023-07-08 | 2023-08-14 | 2023-08-29 | 2023-09-22 | 2023-09-10 | AMPLEX CONSTRUCTION & SUPPLIES | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 130891 | Lote Elementary School | TUPI |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4949497.44 | Completed | 1 | 2024-03-02 | 2024-03-02 | P00775599MN-CW1 | 23MB0173 | 2023-07-08 | 2023-08-14 | 2023-08-29 | 2023-09-22 | 2023-09-10 | AMPLEX CONSTRUCTION & SUPPLIES | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 501664 | Lunen Integrated School | TUPI |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4972579.37 | Completed | 1 | 2024-03-02 | 2024-03-02 | P00775592MN-CW1 | 23MB0175 | 2023-07-08 | 2023-08-14 | 2023-08-29 | 2023-09-22 | 2023-09-10 | RED BRICKS CONSTRUCTION SERVICE & SUPPLY | COMPLETED
NC 2023 | SHS | Region XII | South Cotabato | 304575 | Tupi National High School | TUPI |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4728070.48 | Completed | 1 | 2024-07-01 | 2024-07-01 | P00775591MN-CW1 | 23MB0174 | 2023-07-23 | 2023-01-08 | 2023-08-14 | 2023-08-25 | 2023-11-09 | VPMS OPC | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 130646 | Banga Central Elementary School | BANGA |  | 1 | 2 |  | Batch 2 | 7245000 | 7000000 | 6989913.33 | Completed | 1 | 2024-07-30 | 2024-11-28 | P00775529MN-CW1 | 23MG0067 | 2023-10-21 | 2023-10-31 | 2023-11-13 | 2023-12-20 | 2024-02-01 | Gemma Construction Supply, Inc. | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 501270 | Lambukay Integrated School | BANGA |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4954048.43 | Completed | 1 | 2024-04-02 | 2024-04-02 | P00775530MN-CW1 | 23MG0064 | 2023-08-08 | 2023-08-15 | 2023-08-29 | 2023-12-09 | 2023-09-25 | JMND Const. & Supply | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 130651 | Lamkot ES | Banga |  | 1 | 3 |  | Batch 2 | 7864226.3 | 7598286.28 | 7588243.83 | Completed | 1 | 2024-07-30 | 2024-11-28 | P00775531MN-CW1 | 23MG0067 | 2023-10-21 | 2023-10-31 | 2023-11-13 | 2023-12-20 | 2024-02-01 | Gemma Construction Supply, Inc. | COMPLETED
NC 2023 | K10 | Region XII | South Cotabato | 130884 | Tantangan Central Elementary School | TANTANGAN |  | 1 | 2 |  | Batch 1 | 5043750 | 5000000 | 4269991.28 | Completed | 1 | 2023-12-31 | 2023-12-31 | P00775532MN-CW1 | 23MG0065 | 2023-08-08 | 2023-08-15 | 2023-08-29 | 2023-11-09 | 2023-09-25 | VYS Construction | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 209032 | Balnate Elementary School | COLUMBIO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4736668.57 | Completed | 1 | 2023-12-02 |  | P00775604MN-CW1 | 23MF0065 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | FPJ Constructon and Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 500761 | Upper Bunawan Integrated School | COLUMBIO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4736668.57 | Completed | 1 | 2023-12-02 | 2024-03-01 | P00775605MN-CW1 | 23MF0066 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | FPJ Constructon and Supply | COMPLETED
NC 2023 | SHS | Region XII | Sultan Kudarat | 304590 | Isulan National High School | ISULAN (Capital) |  | 1 | 4 |  | Batch 1 | 8687799.44 | 8612440.58 | 8559182.53 | Completed | 1 | 2023-12-27 | 2024-03-01 | P00775606MN-CW1 | 23MF0067 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | Blimex Construction and Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 500762 | Palumbe Integrated School | LAMBAYONG (MARIANO MARCOS) |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735772.98 | Completed | 1 | 2023-12-07 | 2024-05-01 | P00775608MN-CW1 | 23MF0069 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | CEK Construction and Water Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 131085 | Pinguiaman Elementary School | LAMBAYONG (MARIANO MARCOS) |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735772.98 | Completed | 1 | 2023-12-07 | 2024-08-01 | P00775607MN-CW1 | 23MF0068 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | CEK Construction and Water Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 500716 | Antong Integrated School | LUTAYAN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735772 | Completed | 1 | 2023-12-07 | 2024-07-01 | P00775610MN-CW1 | 23MF0071 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | FPJ Constructon and Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 500434 | Palavilla Integrated School | LUTAYAN |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735772.98 | Completed | 1 | 2023-12-07 | 2024-07-01 | P00775609MN-CW1 | 23MF0070 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | FPJ Constructon and Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 131206 | Bannawag Elementary School | PRESIDENT QUIRINO |  | 1 | 2 |  | Batch 1 | 4788571.5 | 4747034.94 | 4735772 | Completed | 1 | 2023-12-07 | 2024-03-01 | P00775611MN-CW1 | 23MF0072 | 2023-07-27 | 2023-07-27 | 2023-08-08 | 2023-08-23 | 2023-08-29 | FPJ Constructon and Supply | COMPLETED
NC 2023 | SHS | Region XII | Sultan Kudarat | 304589 | Esperanza National High School | ESPERANZA |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 7263316.25 | Completed | 1 | 2024-02-25 | 2024-11-01 | P00775612MN | 23MH0103 |  | 2023-07-13 | 2023-07-23 | 2023-08-23 | 2023-08-29 | Barrist Builders & Construction Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 131044 | Pag-asa Elementary School | KALAMANSIG |  | 1 | 4 |  | Batch 1 | 10087500 | 10000000 | 7362813.73 | Completed | 1 | 2024-02-25 | 2024-11-01 | P00775613MN | 23MH0104 |  | 2023-07-13 | 2023-07-23 | 2023-08-23 | 2023-08-29 | Barrist Builders & Construction Supply | COMPLETED
NC 2023 | K10 | Region XII | Sultan Kudarat | 131046 | Ricardo Cabaluna Memorial Elementary School | KALAMANSIG |  | 1 | 4 |  | Batch 1 | 8070000 | 8000000 | 5884430.59 | Completed | 1 | 2024-01-11 | 2024-11-01 | P00775614MN | 23MH0105 |  | 2023-07-13 | 2023-07-23 | 2023-08-23 | 2023-08-29 | Barrist Builders & Construction Supply | COMPLETED
NC 2023 | SHS | Region XII | Sultan Kudarat | 316804 | Mangudadatu National High School - Villamonte Annex | LEBAK |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 5841596.6 | Completed | 1 | 2023-12-27 |  | P00775615MN | 23MH0106 |  | 2023-07-13 | 2023-07-23 | 2023-08-23 | 2023-08-29 | Barrist Builders & Construction Supply | COMPLETED
NC 2023 | SHS | Region XII | Sultan Kudarat | 304602 | Senator Ninoy Aquino National High School | SEN. NINOY AQUINO |  | 1 | 3 |  | Batch 1 | 6661039.51 | 6603260.98 | 6552560.62 | Completed | 1 | 2023-12-27 | 2024-11-01 | P00775616MN | 23MH0107 |  | 2023-07-13 | 2023-07-23 | 2023-08-23 | 2023-08-29 | Barrist Builders & Construction Supply | COMPLETED
NC 2024 |  | Region XII | General Santos City | 281533 | Balnabo Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970078.76 | Completed | 1 | 2024-11-08 | 2024-12-09 | P00875240MN-CW1 | P00875240MN-CW1 | 2022-11-24 | 2022-11-25 | 2024-06-05 | 2024-07-05 | 2024-07-11 | DYZ CONSTRUCTION SERVICES | COMPLETED
NC 2024 |  | Region XII | General Santos City | 281534 | Banwalan Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944999.92 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875238MN-CW1 | P00875238MN-CW1 | 2022-11-07 | 2022-11-17 | 2024-06-05 | 2024-07-05 | 2024-07-11 | FZI CONSTRUCTION, PARTS AND SUPPLY | COMPLETED
NC 2024 |  | Region XII | General Santos City | 131300 | Batomelong Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4958049.78 | Completed | 1 | 2024-11-08 | 2024-11-24 | P00875225MN-W1 | P00875225MN-W1 | 2022-11-07 | 2022-11-13 | 2024-06-05 | 2024-07-05 | 2024-07-11 | JP BEATHRIZ CONSTRUCTION AND SUPPLY | COMPLETED
NC 2024 |  | Region XII | General Santos City | 131295 | Blagan Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4958049.78 | Completed | 1 | 2024-11-08 | 2024-12-22 | P00875237MN-CW1 | P00875237MN-CW1 | 2022-11-09 | 2022-11-18 | 2024-06-05 | 2024-07-05 | 2024-07-11 | GRECO CONSTRUCTION SUPPLY | COMPLETED
NC 2024 |  | Region XII | General Santos City | 131276 | Dadiangas West Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 |  | 2-Storey School Building | GAA 17B | 10000000 |  |  | Not Yet Started | 0 | [10 empty] | hold in abeyance request for additional budget
NC 2024 |  | Region XII | General Santos City |  | Datal Salvan High School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4966118.26 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875241MN-CW1 | P00875241MN-CW1 | 2022-11-18 | 2022-11-25 | 2024-06-05 | 2024-07-05 | 2024-07-11 | THE TRENDSETTER CONSTRUCTION AND SUPPLY CORP. | COMPLETED
NC 2024 |  | Region XII | General Santos City |  | Florence Santos High School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4963608.21 | Completed | 1 | 2024-11-08 | 2024-11-25 | P00875236MN-CW1 | P00875236MN-CW1 | 2022-11-07 | 2022-11-17 | 2024-06-05 | 2024-07-05 | 2024-07-11 | KEVIN YOSHI BUILDERS | COMPLETED
NC 2024 |  | Region XII | General Santos City |  | Lozano High School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4929000 | Completed | 1 | 2024-11-08 | 2024-12-11 | P00875242MN-CW1 | P00875242MN-CW1 | 2023-05-03 | 2023-05-10 | 2024-06-05 | 2024-07-05 | 2024-07-11 | FUENTABUILT CONSTRUCTION CORP. | COMPLETED
NC 2024 |  | Region XII | General Santos City |  | Maligaya High School | GENERAL SANTOS CITY (DADIANGAS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969242.69 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875239MN-CW1 | P00875239MN-CW1 | 2022-11-24 | 2022-11-25 | 2024-06-05 | 2024-07-05 | 2024-07-11 | WICH MECHANICAL INNOVATIONS & GENERAL CONSTRUCTION INC | COMPLETED
NC 2024 |  | Region XII | Kidapawan City | 131325 | Datu Saliman Elementary School | CITY OF KIDAPAWAN (Capital) |  | 1 | 8 | 2STY8CL | BATCH 1 | 26586096.76 |  | 26352849.27 | Completed | 1 | 2025-02-03 | 2025-05-09 | 23MC0086 | 24MC0103 |  | 2024-05-22 | 2024-06-06 | 2024-06-25 | 2024-08-02 | Equicon Engineering Services | For Turnover
NC 2024 |  | Region XII | Koronadal City | 317205 | Esperanza National High School – Annex, San Jose Campus | CITY OF KORONADAL (Capital) |  | 1 | 12 | 4STY12CL | BATCH 1 | 42300000 |  | 42021634.18 | Ongoing | 0.9798 | 2024-12-16 |  | 24MG0109 | 24MG0109 | 2024-06-21 | 2024-06-28 | 2024-07-11 | 2024-07-25 | 2024-07-29 | Dedase Construction Services
NC 2024 |  | Region XII | Koronadal City | 131407 | Koronadal Central II ES | CITY OF KORONADAL (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969820.85 | Completed | 1 | 2024-12-20 | 2025-02-01 | 24MG0138 | 24MG0138 | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | Megaline Construction | for final inspection
NC 2024 |  | Region XII | North Cotabato | 304412 | Alamada High School | ALAMADA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4973002.38 | Completed | 1 | 2024-08-27 | 2024-08-27 | P00875197MN | 24MD0067 |  | 2024-11-04 | 2024-04-25 | 2024-04-30 | 2024-10-05 | RDEN Construction | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 129824 | Guiling ES | ALAMADA |  | 1 | 6 | 2UNITS 1STY3CL | BATCH 1 | 16039980.36 |  | 15927702.87 | Completed | 1 | 2024-12-22 | 2025-03-03 | P00875433MN | 24MD0079 |  | 2024-03-19 | 2024-04-07 | 2024-07-15 | 2024-07-26 | LIMSA Const. & Supply | for final inspection
NC 2024 |  | Region XII | North Cotabato | 129852 | Tawas-Abaga Elementary School | ALAMADA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972558.35 | Completed | 1 | 2024-08-27 | 2024-02-09 | P00875196MN | 24MD0070 |  | 2024-11-04 | 2024-04-25 | 2024-04-30 | 2024-10-05 | RDEN Construction | for final inspection
NC 2024 |  | Region XII | North Cotabato | 129854 | Upper Dado Central Elementary School | ALAMADA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972853.29 | Completed | 1 | 2024-08-27 | 2024-08-27 | P00875195MN | 24MD0071 |  | 2024-11-04 | 2024-04-25 | 2024-04-30 | 2024-10-05 | RDEN Construction | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130037 | Cornelio V. Cocal Elementary School | LIBUNGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925249.99 | Completed | 1 | 2024-08-08 | 2024-11-04 | P00875198MN | 24MD0061 |  | 2024-03-19 | 2024-02-04 | 2024-04-15 | 2024-04-19 | J-1 Builders | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130043 | Lope T. Quial Sr. CES (Libungan CES) | LIBUNGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4925249.99 | Completed | 1 | 2024-08-27 | 2024-10-01 | P00875199MN | 24MD0069 |  | 2024-11-04 | 2024-04-25 | 2024-04-30 | 2024-10-05 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130207 | Elpidio Singco Elementary School | MIDSAYAP |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969898.5 | Completed | 1 | 2024-08-08 | 2024-08-08 | P00875202MN | 24MD0060 |  | 2024-03-19 | 2024-02-04 | 2024-04-15 | 2024-04-19 | RDEN Construction | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130183 | Ilbocean Elementary School | MIDSAYAP |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4971998.73 | Completed | 1 | 2024-08-27 | 2024-11-18 | P00875200MN | 24MD0068 |  | 2024-11-04 | 2024-04-25 | 2024-04-30 | 2024-10-05 | RDEN Construction | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130184 | Kimagango Central Elementary School | MIDSAYAP |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969996.67 | Completed | 1 | 2024-08-08 | 2024-10-01 | P00875201MN | 24MD0062 |  | 2024-03-19 | 2024-02-04 | 2024-04-15 | 2024-04-19 | RDEN Construction | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 129877 | Antipas CES | ANTIPAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-09-26 | 2024-09-26 | P00875204MN-CW1 | 24MC0089 |  | 2024-04-17 | 2024-04-29 | 2024-05-21 | 2024-05-29 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 137110 | Inamong Elementary School | ARAKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-04-06 | 2024-09-19 | P00875203MN-CW1 | 24MC0093 |  | 2024-04-17 | 2024-04-29 | 2024-05-21 | 2024-05-29 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130069 | Apostol Memorial Central Elementary School | MAGPET |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968004.75 | Completed | 1 | 2024-05-06 | 2024-09-26 | P00875205MN-CW1 | 24MC0090 |  | 2024-04-17 | 2024-04-29 | 2024-05-23 | 2024-05-30 | PSN Construction and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130093 | Batasan ES | MAKILALA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970001 | Completed | 1 | 2024-06-20 | 2024-12-26 | P00875208MN-CW1 | 24MC0091 |  | 2024-04-17 | 2024-04-29 | 2024-05-30 | 2024-06-14 | Nascon Builders | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 103590 | Don Mariano C. Pamintuan Elementary School | MAKILALA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-04-06 | 2024-12-26 | P00875206MN-CW1 | 24MC0092 |  | 2024-04-17 | 2024-04-29 | 2024-05-21 | 2024-05-29 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130113 | Jose Rizal Elementary School | MAKILALA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-05-06 | 2024-11-28 | P00875209MN-CW1 | 24MC0094 |  | 2024-04-17 | 2024-04-29 | 2024-05-23 | 2024-05-30 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130088 | Makilala Central Elementary School | MAKILALA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965000 | Completed | 1 | 2024-05-06 | 2024-09-25 | P00875207MN-CW1 | 24MC0096 |  | 2024-04-17 | 2024-04-29 | 2024-05-23 | 2024-05-30 | Llaban Const. and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 130357 | Kisupaan Elementary School | PRESIDENT ROXAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4972398.75 | Completed | 1 | 2024-05-06 | 2024-11-23 | P008752010MN-CW1 | 24MC0095 |  | 2024-04-17 | 2024-04-29 | 2024-05-23 | 2024-05-30 | Jjal Construction and Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 102383 | Bai Sibayan Elementary School | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964516.97 | Completed | 1 | 2025-12-03 | 2024-12-03 | P00875214MN-CW1 | 24MI0095 |  | 2024-07-31 | 2024-08-12 | 2024-09-03 | 2024-09-09 | Pader Construction | for final inspection
NC 2024 |  | Region XII | North Cotabato | 304453 | Kibudtungan National High School | CARMEN |  | 1 | 8 | 2STY8CL | GAA 17B | 20000000 |  | 19879803.14 | Ongoing | 0.705 | 2025-11-07 |  | P00875211MN-CW1 | 24MI0102 | 2024-06-12 | 2024-11-12 | 2024-12-23 | 2024-12-27 | 2025-07-01 | Jargon Construction and Supply
NC 2024 |  | Region XII | North Cotabato | 129968 | Manili ES | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4963323.35 | Completed | 1 | 2024-09-27 | 2024-11-23 | P00875213MN-CW1 | 24MI0084 |  | 2024-05-24 | 2024-05-06 | 2024-10-06 | 2024-02-07 | Pader Construction & Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 305984 | Manili High School | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965660.57 | Completed | 1 | 2024-09-27 | 2024-11-23 | P00875212MN-CW1 | 24MI0083 |  | 2024-05-24 | 2024-05-06 | 2024-10-06 | 2024-02-07 | Pader Construction & Supply | COMPLETED
NC 2024 |  | Region XII | North Cotabato | 136920 | Mansamad Saliling Elementary School | CARMEN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962014.34 | Completed | 1 | 2024-09-27 | 2024-10-26 | P00875215MN-CW1 | 24MI0085 |  | 2024-05-24 | 2024-05-06 | 2024-10-06 | 2024-02-07 | Pader Construction & Supply | COMPLETED
NC 2024 |  | Region XII | Sarangani | 304519 | Alegria NHS | ALABEL (Capital) |  | 1 | 10 | 2STY10CL | GAA 17B | 29000000 |  | 28841245.73 | Ongoing | 0.8944 | 2025-06-24 |  | P00875216MN-CW1 | 24ME0117 |  | 2024-07-25 | 2024-08-06 | 2024-08-13 | 2024-08-29 | COFEJOK CONSTRUCTION & SUPPLY CORPORATION
NC 2024 |  | Region XII | Sarangani | 500828 | Batutuling Integrated School | Glan |  | 1 | 2 | 1STY2CL | BATCH 1 | 9975600 |  | 8042073.05 | Completed | 1 | 2024-12-26 | 2025-04-21 | P00875434MN-CW1 | 24ME0115 |  | 2024-07-25 | 2024-08-06 | 2024-08-13 | 2024-08-29 | MANUELA CONSTRUCTION SERVICES | Granted 88 Days Time Extension
NC 2024 |  | Region XII | Sarangani | 304533 | Malalag Cogon NHS | MALUNGON |  | 1 | 4 | 2STY4CL | GAA 17B | 11000000 |  | 10935064.65 | Ongoing | 0.6858 | 2025-01-25 |  | P00875217MN-CW1 | 24ME0116 |  | 2024-07-25 | 2024-08-06 | 2024-08-13 | 2024-08-29 | REYDAN BUILDERS | Granted 72 Days Time Extension
NC 2024 |  | Region XII | South Cotabato | 130720 | Crossing Palkan Elementary School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4961627.4 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875221MN-CW1 | 24MB0107 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-26 | 2024-07-11 | MCHAI CONSTRUCTION AND HARDWARE SUPPLY | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 501145 | Kalyong Integrated School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962813.12 | Completed | 1 | 2025-07-01 | 2025-07-01 | P00875223MN-CW1 | 24MB0109 |  |  | 2024-06-13 | 2024-06-20 | 2024-02-07 | 7/23/2024 | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 501233 | Klinan Integrated School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4931000 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875220MN-CW1 | 24MB0106 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-27 | 2024-07-11 | BAYTORR CONSTRUCTION AND DEVELOPMENT CORPORATION | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 501199 | Lumakil Integrated School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964538.5 | Ongoing | 0.65 | 2024-11-21 |  | P00875222MN-CW1 | 24MB0108 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-07-08 | 2024-07-24 | SOKABE CONSTRUCTION | SLOW PERFORMANCE, NOTIFY DPWH TO FAST TRACK CONTRACTOR
NC 2024 |  | Region XII | South Cotabato | 501260 | Polo Integrated School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4950000 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875218MN-CW1 | 24MB0104 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-26 | 2024-07-11 | BAYTORR CONSTRUCTION AND DEVELOPMENT CORPORATION | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 130745 | Polomolok Central Elementary School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4944941.98 | Completed | 1 | 2024-11-08 | 2024-11-24 | P00875219MN-CW1 | 24MB0105 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-25 | 2024-07-11 | ED SIXTY FOUR ENTERPRISES | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 112750 | Sulit Elementary School | POLOMOLOK |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4955226.21 | Completed | 1 | 2024-11-08 | 2024-11-24 | P00875250MN-CW1 | 24MB0102 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-25 | 2024-07-11 | J.G. ORANZA CONSTRUCTION | COMPLETED
NC 2024 |  | Region XII | South Cotabato |  | Lambayong Integrated School | TAMPAKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4962451.17 | Completed | 1 | 2024-11-21 | 2024-12-07 | P00875225MN-CW1 | 24MB0092 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-07-09 | 2024-07-24 | ROCKSTONE CONSTRUCTION SERVICES & SUPPLY | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 208527 | Tampakan SPED Center | TAMPAKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970005.24 | Completed | 1 | 2024-11-08 | 2024-11-24 | P00875249MN-CW1 | 24MB0101 | 2024-05-17 | 2024-05-24 | 2024-06-05 | 2024-06-25 | 2024-07-11 | JJTE CONSTRUCTION CORPORATION | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 130889 | Cebuano Elementary School - Mambusong Extension | TUPI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4954290.09 | Completed | 1 | 2024-12-06 | 2024-12-06 | P00875243MN-CW1 | 24MB0103 | 2024-06-13 | 2024-06-20 | 2024-07-02 | 2024-07-23 | 2024-08-08 | FIVE CONSTRUCTION SERVICES | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 501664 | Lunen Integrated School | TUPI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4937737.63 | Ongoing | 1 | 2025-02-26 |  | P00875224MN-CW1 | 24MB0110 | 2024-08-13 | 2024-08-23 | 2024-03-09 | 2024-09-18 | 2024-03-10 | RED BRICKS CONSTRUCTION SERVICE AND SUPPLY | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 501848 | Denlag Integrated School | LAKE SEBU |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969941.41 | Ongoing | 1 | 2025-07-03 | 2025-07-03 | P00875246MN | 24MB0139-CLUSTER XIII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-29 | 2024-09-09 | MEGALINE BUILDERS AND SUPPLY | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 130710 | Puti Elementary School | NORALA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969874.27 | Completed | 1 | 2025-07-03 | 2025-07-03 | P00875248MN | 24MB0139-CLUSTER XIII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-29 | 2024-09-09 | MEGALINE BUILDERS AND SUPPLY | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 501631 | Talahik Integrated School | SURALLAH |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4965874.31 | Ongoing | 1 | 2025-07-03 |  | P00875247MN | 24MB0139-CLUSTER XIII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-29 | 2024-09-09 | MEGALINE BUILDERS AND SUPPLY | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 130868 | Bukay Pait Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970011.79 | Ongoing | 1 | 2025-07-03 |  | P00875227MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 130869 | Eleonor D. Belotindos Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969753.86 | Ongoing | 1 | 2025-07-03 |  | P00875233MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 208528 | Jose P. Lim, Jr. Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970000 | Ongoing | 1 | 2025-03-13 | 2025-03-13 | P00875232MN-CW1 | 24MG0141 | 2024-05-09 | 2024-12-09 | 2024-09-25 | 2024-09-30 | 2024-10-10 | GOLDEN A NINE CONSTRUCTION | COMPLETED
NC 2024 |  | Region XII | South Cotabato | 130872 | Libas Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969650.61 | Ongoing | 1 | 2025-07-03 |  | P00875228MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 501992 | Mangilala Integrated School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969690.93 | Ongoing | 1 | 2025-07-03 |  | P00875231MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 130879 | New Iloilo Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969520.13 | Ongoing | 1 | 2025-07-03 |  | P00875226MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 130881 | San Felipe Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4960549.85 | Ongoing | 1 | 2025-07-03 |  | P00875230MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 130885 | Tinongcop Elementary School | TANTANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969644.45 | Ongoing | 1 | 2025-07-03 |  | P00875229MN | 24MB0133-CLUSTER XII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-28 | 2024-09-09 | BETTER WORK CONSTRUCTION/MEGALINE BUILDERS AND SUPPLY (JV) | FOR RECTIFICATION OF PUNCHLSTED ITEM/ FOR ISSUANCE OF COC
NC 2024 |  | Region XII | South Cotabato | 502201 | Datal Bila Integrated School | T'BOLI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4949925.65 | Ongoing | 0.9 | 2025-07-03 |  | P00875245MN | 24MB0139-CLUSTER XIII | 2024-07-19 | 2024-07-26 | 2024-08-08 | 2024-08-29 | 2024-09-09 | MEGALINE BUILDERS AND SUPPLY | FOR FINAL INSPECTION
NC 2024 |  | Region XII | Sultan Kudarat | 131020 | D. Lotilla Elementary School | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967196.89 | Completed | 1 | 2024-11-06 | 2024-11-01 | P00875256MN-CW1 | 24MF0050 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | CEK Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 131006 | Dansuli Elementary School | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967694.36 | Completed | 1 | 2024-11-22 | 2024-12-01 | P00875251MN-CW1 | 24MF0049 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | CEK Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 131008 | Isulan Central School SPED Center | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 6047351.98 | Completed | 1 | 2025-02-03 | 2025-04-01 | P00875252MN-CW1 | 24MF0055 | 2024-06-20 | 2024-06-28 | 2024-07-10 | 2024-07-24 | 2024-08-09 | Blimex Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 131014 | Kalawag Central School | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967196.89 | Completed | 1 |  |  | P00875261MN-CW1 | 24MF0053 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | Woodridge Builders Construction & Supplies, Inc. | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 209001 | Kalawag III Elementary School | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4966888.88 | Completed | 1 | 2024-11-23 | 2024-12-01 | P00875255MN-CW1 | 24MF0054 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | Blimex Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 131023 | Lagandang Elementary School | ISULAN (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4966201.96 | Completed | 1 | 2024-12-03 | 2024-12-01 | P00875262MN-CW1 | 24MF0051 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | FPJ Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 304617 | President Quirino National High School | PRESIDENT QUIRINO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4966670.56 | Completed | 1 | 2024-11-05 | 2024-11-01 | P00875254MN-CW1 | 24MF0052 | 2024-04-03 | 2024-04-11 | 2024-04-23 | 2024-04-29 | 2024-05-13 | FPJ Construction & Supply | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 500717 | Dante Integrated School | BAGUMBAYAN |  | 1 | 4 | 1STY4CL | GAA 17B | 12394000 |  | 12204602.76 | Ongoing | 0.24 | 2025-09-28 |  | P00875257MN_CW1 | 24MH0108 | 2024-12-21 | 2025-01-06 | 2025-01-21 | 2025-03-01 | 2025-03-14 | Bulldog Engineering | Delayed implementation due to project modification
NC 2024 |  | Region XII | Sultan Kudarat | 131119 | Adalla Elementary School | LEBAK |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 8327976.02 | Ongoing | 0.79 | 2024-11-04 |  | P000875260MN_CW1 | 24MH0107 | 2024-04-12 | 2024-04-19 | 2024-05-02 | 2024-05-08 | 2024-05-22 | Albanor Construction | Ongoing, delayed project
NC 2024 |  | Region XII | Sultan Kudarat | 131133 | Bonifacio M. Difuntorum Sr. Elementary School | LEBAK |  | 1 | 3 | 1STY3CL | GAA 17B | 10000000 |  | 9626055.2 | Completed | 1 | 2024-11-04 | 2025-02-01 | P000875258MN_CW1 | 24MH0105 | 2024-04-12 | 2024-04-19 | 2024-05-02 | 2024-05-08 | 2024-05-22 | JV Constech | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 131138 | Lagandang Elementary School | LEBAK |  | 1 | 2 | 1STY2CL | GAA 17B | 7606000 |  | 7338029.88 | Completed | 1 | 2024-11-01 | 2025-02-01 | P000875259MN_CW1 | 24MH0106 | 2024-04-12 | 2024-04-19 | 2024-05-02 | 2024-05-28 | 2024-06-03 | Bulldog Engineering | Completed
NC 2024 |  | Region XII | Sultan Kudarat | 127198 | Datu Gas Tubo Elementary School | SEN. NINOY AQUINO |  | 1 | 4 | 1STY4CL | BATCH 1 | 9657229 |  | 9512853.2 | Ongoing | 0.92 | 2025-01-16 |  | P000875435MN_CW1 | 24MH0109 | 2024-06-12 | 2024-06-19 | 2024-07-02 | 2024-07-17 | 2024-08-01 | PSN Construction & Supply | Partially Completed, for Final Inspection
NC 2024 |  | Region XII | Tacurong City | 131216 | Casilda P. Venus ES | CITY OF TACURONG |  | 1 | 3 | 1STY3CL | BATCH 1 | 7925000 |  | 7873524.37 | Completed | 1 | 2024-12-21 | 2025-07-02 | Construction of 1STY3CL, Casilda P. Venus ES, City of Tacurong, Sultan Kudarat | 24MF0065 | 2024-06-21 | 2024-06-28 | 2024-07-10 | 2024-07-24 | 2024-12-08 | CEK Construction & Water Supply | Completed
NC 2024 |  | Region XII | Tacurong City | 326102 | San Pablo National High School | CITY OF TACURONG |  | 1 | 2 | 1STY2CL | GAA 17B | 10000000 |  | 6041649.34 | Completed | 1 | 2024-08-12 | 2025-02-19 | Construction of 1STY2CL, San Pablo NHS, City of Tacurong, Sultan Kudarat | 24MF0056 | 2024-06-21 | 2024-06-28 | 2024-07-10 | 2024-07-24 | 2024-12-08 | CEK Construction & Water Supply | Completed

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.