## Sheet1
CATEGORY | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks
SCHOOL HEALTH FACILITIES 2024 | Region VI | Negros Occidental | 311104 | Efegenio Lizares National High School | CITY OF TALISAY | 3rd | 1 |  | Construction/Repair of Health Facilities | 3308711.07 |  | 2534432.95 | Completed | 1 | December 13, 2024 | December 19, 2024 | 24-09-001 | 12016 | November 11, 2023 | November 27, 2023 | December 11, 2023 | July 25, 2024 | August 30, 2024 | Sunshine Sapphire Construction And Supply Inc | Completed
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone | 1 |  | Construction of Hanwashing Facilities | 200898.19 |  | 188138.49 | completed | 1 | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction
SCHOOL HEALTH FACILITIES 2024 | Region VII | Siquijor | 190004 | Cangmunag Elementary School | SAN JUAN | Lone |  |  | Construction of School Clinic | 3010654.85 |  | 2153178.16 | completed | 1 | August 21, 2024 | January 6, 2025 | 10336657 | 2023-88 | November 20, 2023 | November 28, 2023 | December 11, 2023 | December 12, 2023 | May 21, 2024 | Quicksilver Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120431 | Jose R. Remollo ES (Cambaloctot ES) | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY (OPTION 1A - WITH ROOFING, WITH COUNTER WITH TILE FINISH) | 193423.04 | BATCH 1 | 192459.09 | Completed | 1 | 2022-11-30 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 120438 | Siapo Elementary School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 79744.75 | BATCH 1 | 78628.58 | Completed | 1 | 2022-11-30 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Negros Oriental | 303278 | Crisostomo O. Retes National High School | San Jose | 2 | 1 | 1 | PROPOSED CONSTRUCTION OF THREE (3) UNITS GROUP HANDWASHING FACILITY - FOR SECONDARY - (OPTION 2B - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 218188.87 | BATCH 1 | 217530.71 | Completed | 1 | 2022-12-15 |  |  |  | 03/28/22; 07/04/22 | 04/6/22; 07/12/22 | 4/18/22; 07/25/22 | 2022-08-09 | 2022-10-21 | Sagittarius Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120658 | Enrique Villanueva Central Elementary School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303303 | BASAC NATIONAL HIGH SCHOOL | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501427 | Larena Integrated School | Larena | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120669 | Candaping Elementary School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501429 | Maria Integrated School | Maria | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 120699 | Catulayan Elementary School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303300 | Tambisan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 303305 | Catulayan National High School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF ONE (1) UNIT GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 94981.36 | BATCH 1 | 94714.17 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction
SCHOOL HEALTH FACILITIES 2022 | Region VII | Siquijor | 501430 | San Juan Integrated School | San Juan | 0 | 1 | 1 | PROPOSED CONSTRUCTION OF TWO (2) UNITS GROUP HANDWASHING FACILITY - FOR ELEMENTARY - (OPTION 2A - WITHOUT ROOFING, WITH COUNTER WITH PAINTED CEMENT FINISH) | 184826.54 | BATCH 1 | 176198.13 | Completed | 1 | 2022-10-31 |  |  |  | 2022-03-29 | 2022-04-05 | 2022-04-18 | 2022-04-21 | 2022-06-28 | E.D. Angas Construction