## GABALDON 2020- 2024
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks
GABALDON 2020 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3477721.44 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Benguet | 135397 | Topdac ES | ATOK | 0 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 12177572.29 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Benguet | 135737 | Tublay Central Elementary School | TUBLAY | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 13636660.38 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Mt. Province | 136248 | Tambuan Elementary School | BESAO | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12055183.04 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Mt. Province | 136356 | Balaoa Elementary School | TADIAN | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4108545.8707 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Mt. Province | 136358 | Bantey Elementary School | TADIAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12490756.76 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Mt. Province | 136363 | Dacudac Elementary School | TADIAN | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6837175.68 | 1 |  | Completed | 100%
GABALDON 2020 | CAR | Mt. Province | 136367 | Kayan Elementary School | TADIAN | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 17916759.49 | 1 |  | Completed | 100%
GABALDON 2020 | CARAGA | Surigao del Sur | 132786 | Barcelona Central Elementary School | Lingig | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3791557.1457 | 1 | 2850645.4 | Completed | 100% | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2020 | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4262264.1005 | 1 | 3203616.66 | Completed | 100% | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2020 | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2 |  | 1 | 1 | Rehabilitation of Gabaldon Building | 3727184.6834 | 1 | 2802461.99 | Completed | 100% | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2020 | NCR | Manila | 136438 | Magat Salamat Elementary School | TONDO | 1 | 1 | 30 | 1 | Rehabilitation of Gabaldon Building | 22518985.22 | 1 | 22438862.19 | Completed | 100% | March 20, 2021 | 2021-07-02 | [6 empty] | June 3, 2020 | Sherf Builders Corporation
GABALDON 2020 | Region I | Candon City | 100427 | Ayudante Elementary School | CITY OF CANDON | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1990377.99 | 1 |  | Completed | 100% | [10 empty] | DEFFERED PROCUREMENT
GABALDON 2020 | Region I | Ilocos Norte | 100202 | Gabaldon ES | PASUQUIN | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10410704.18 | 1 | 10251139.45 | Completed | 100% | 2022-02-23 | 2021-12-09 | 2021-05-08 | 2021-06-21 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-30 | Elocin Construction | COMPLETED
GABALDON 2020 | Region I | Ilocos Sur | 100459 | Pandan ES | CAOAYAN | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 13610112.44 | 1 | 13563377.97 | Completed | 100% | 2021-04-15 | [7 empty] | 2020-09-17 | MA TEJADA CONSTRUCTION
GABALDON 2020 | Region I | Ilocos Sur | 100638 | Santiago South Central School | SANTIAGO | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3537854.71 | 1 | 3514079.29 | Completed | 100% | 2021-01-15 | [7 empty] | 2020-09-17 | MA TEJADA CONSTRUCTION
GABALDON 2020 | Region I | La Union | 100846 | Bacnotan Central School | BACNOTAN | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 17585093.32 | 1 | 17559001.02 | Completed | 100% | 2022-01-03 | 2021-12-20 | 2023-07-006-PB-Works | 2021-06-16 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2020 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 8439581.13 | 1 | 8416617.77 | Completed | 100% | 2022-01-03 | 2021-12-10 | 2023-07-005-PB-Works | 2021-06-17 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2020 | Region I | Pangasinan II, Binalonan | 101703 | Pindangan West ES | ALCALA | 5 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8491938.58 | 1 | 8475978.91 | Completed | 100% | 2022-02-12 | 2021-12-14 | 2021-05-08 | 2021-06-18 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2020 | Region I | Pangasinan II, Binalonan | 101784 | Don Rufino Tabayoyong CS | LAOAC | 5 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 5038139.51 | 1 | 5011673.02 | Completed | 100% | 2022-01-05 | 2021-12-06 | 2021-05-08 | 2021-06-19 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2020 | Region II | Batanes | 500062 | Itbud Integrated School | UYUGAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 8995156.39 | 1 | 8526166.78 | Completed | 100% | October 27, 2021 | April 2024 |  | 2021-06-016 | April 8,2021 | April 15, 2021 | April 27,2021 | June 23,2021 | June 28,2021 | KNB Construction
GABALDON 2020 | Region II | Cagayan | 102442 | Aparri East CS | APARRI | 1 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 8951555.83 | 1 |  | Reverted | 0%
GABALDON 2020 | Region II | Cagayan | 102403 | Amulung East CS | AMULUNG | 3 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 8667454.4523 | 1 | 5526283.97 | Completed | 100% | October 27, 2021 | April 2024 |  | 2021-06-017 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 23,2021 | June 28,2021 | KNB Construction
GABALDON 2020 | Region II | Nueva Vizcaya | 104202 | Imugan ES | Santa Fe | 0 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 7013953.09 | 1 | 7915455.79 | Completed | 100% | August 29, 2021 | November 5, 2021 |  | 2021-02-004 |  |  | December 17, 2020 | February 23,2021 | March 1, 2021 | Pecdasen Builders
GABALDON 2020 | Region III | Bataan | 104539 | T. Pinpin MES | ABUCAY | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 12124803.73 | 1 |  | Completed | 100% | [10 empty] | Issued Suspension of Procurement
GABALDON 2020 | Region III | Bulacan | 104801 | Calumpit CS | Calumpit | 1 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 14289812.4 | 1 |  | Completed | 100% | [10 empty] | CO ISSUED SUSPENSION OF PROCUREMENT
GABALDON 2020 | Region III | Nueva Ecija | 105765 | Santa Rosa Central School | SANTA ROSA | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 5621063.31 | 1 |  | Completed | 100% | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE
GABALDON 2020 | Region III | Nueva Ecija | 105437 | Jaen Central School | JAEN | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 8791110.01 | 1 |  | Completed | 100% | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE
GABALDON 2020 | Region III | Nueva Ecija | 105670 | San Antonio Central School | SAN ANTONIO | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 10441684.8 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6751373.93 | 1 |  | Completed | 100% | [10 empty] | FOR IMPLEMENTATION OF REGIONAL OFFICE
GABALDON 2020 | Region III | Pampanga | 105997 | Guagua ES | GUAGUA | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 15369088.53 | 1 |  | Completed | 100% | 2024-02-10 |  | R3INFRA-ITB2023-004 |  | 2023-09-12 | 2023-09-19 | 2023-10-03 | N/A | N/A | N/A | Under Procurement for Take over contract; Re-posted for the partial completion of 7 CL. FFE elevated up to 0.9m due to school prone to flooding
GABALDON 2020 | Region III | Pampanga | 106295 | Sta. Rita CS | STA. RITA | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 13155093.73 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Pampanga | 106284 | Sta. Ana Elementary | SANTA ANA | 3 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7694696.87 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Pampanga | 106152 | Masantol ES | MASANTOL | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5630830.42 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | San Fernando City | 107195 | San Fernando Elementary School | San Fernando City | 3 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 5708292.54 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6223490.48 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Tarlac | 106370 | Capas East Central Elementary School | Capas | 3 | 1 | 10 | 1 | Rehabilitation of Gabaldon Building | 15029045.63 | 1 |  | Completed | 100%
GABALDON 2020 | Region III | Zambales | 106932 | Bobulon Elementary School | SAN FELIPE | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4389934.38 | 1 |  | Completed | 100%
GABALDON 2020 | Region IV-A | Laguna | 108446 | Santa Cruz CES | SANTA CRUZ (Capital) | 4 | 1 | 14 | 1 | Rehabilitation of Gabaldon Building | 18433661.59 | 1 | 18351437.96 | Completed | 100% |  | 2021-12-13 | Gabaldon 2020 - R IVA - Laguna - 001 |  | 2020-08-21 |  | 2020-09-14 | 2020-09-17 | 2020-11-25 | VRV Construction and Trading
GABALDON 2020 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 25231446.67 | 1 |  | Completed | 100% | 2022-09-30
GABALDON 2020 | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | San Pablo City | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2233477.93 | 1 | 1981761.12 | Completed | 100% |  | 2021-02-12 | GAB 2020 - RIV-A - San Pablo - 003 |  | 2019-11-18 |  | 2019-12-10 | 2020-09-02 | 2020-09-14 | M2 Builders Corporation
GABALDON 2020 | Region IV-A | San Pablo City | 109758 | Stmo. Rosario Elementary School | San Pablo City | 3 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2086153.2721 | 1 | 2035730.39 | Completed | 100% |  | 2021-02-12 | GAB 2020 - RIV-A - San Pablo - 002 |  | 2019-11-18 |  | 2019-12-10 | 2020-09-02 | 2020-09-14 | M2 Builders Corporation
GABALDON 2020 | Region IV-B | Marinduque | 109870 | Don Luis Hidalgo MS | BOAC (Capital) | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 14026827.51 | 1 | 14026827.51 | Completed | 100% |  |  | N/A | N/A | 2020-01-14 | 2020-01-21 | 2020-04-02 | 2020-01-10 | 2020-10-29 | GS Mortar Builders Construction and Trading
GABALDON 2020 | Region IV-B | Marinduque | 109957 | Sayao ES | MOGPOG | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 17278471.82 | 1 | 9955505.71 | Completed | 100% | 2022-03-30 | 2022-05-15 | N/A | N/A | 2021-05-27 | 2020-01-14 | 2020-04-02 | 2020-01-10 | 2020-10-29 | CMSEL Construction & Developer
GABALDON 2020 | Region IV-B | Oriental Mindoro | 110490 | Jose L. Basa Memorial School | NAUJAN | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 9955505.71 | 1 | 16923951.09 | Completed | 100% | 2022-03-30 |  | N/A | N/A | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-07-23 | 2021-02-08 | GS Mortar Builders Construction and Trading
GABALDON 2020 | Region IV-B | Oriental Mindoro | 110662 | San Teodoro CS | SAN TEODORO | 1 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 9411119.41 | 1 | 8046318.19 | Completed | 100% | 2022-09-30 |  | N/A | N/A | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | NMDC Construction Corp.
GABALDON 2020 | Region IV-B | Romblon | 111329 | Looc CES | LOOC | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 11297198.88 | 1 | 9032617.13 | Completed | 100% | 2022-01-30 |  | N/A | N/A | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development
GABALDON 2020 | Region IV-B | Romblon | 111356 | Odiongan South CES | ODIONGAN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6016250.46 | 1 | 5032593.98 | Completed | 100% | 2021-12-30 | 2021-12-29 | N/A | N/A | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-07-23 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development
GABALDON 2020 | Region IV-B | Romblon | 111411 | San Agustin CES | SAN AGUSTIN | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6037432.64 | 1 | 5049882.03 | Completed | 100% | 2021-12-30 | 2021-12-29 | N/A | N/A | 2021-05-27 | 2021-04-06 | 2021-06-16 | 2021-09-07 | 2021-02-08 | RMR Construction & Trading Hawkstow Construction & Development
GABALDON 2020 | Region IX | Zamboanga City | 126121 | Curuan CS | Zamboanga City | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 5000000 | 1 | 4750000 | Completed | 100% | January 31,2022 | February 8,2022 | ZC-GAB-2020-B | ZC-GAB-2020-B | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. | None
GABALDON 2020 | Region IX | Zamboanga City | 126189 | Mercedes CS | Zamboanga City | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8000000 | 1 | 7600000 | Completed | 100% | January 31,2022 | February 5,2022 | ZC-GAB-2020-A | ZC-GAB-2020-A | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. | None
GABALDON 2020 | Region V | Albay | 111630 | Camalig North CS | Camalig | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 12541895.31 | 1 |  | Completed | 100% | [9 empty] | JagVail Construction and Supply
GABALDON 2020 | Region V | Albay | 111727 | Guinobatan West CS | Guinobatan | 3 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 11628072.02 | 1 | 7885654.93 | Completed | 100% | 2022-02-18 |  | Infra 2021-02 | 2021-09-222 | [5 empty] | Law-an Builders & Supply
GABALDON 2020 | Region V | Camarines Sur | 112745 | Lupi CS | LUPI | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 9529471.9 | 1 | 7647166.69 | Completed | 100% | 2022-03-24 |  | Infra 2021-02 | 2021-10-260 | [5 empty] | Riders Corners Const & Gen. Merch.
GABALDON 2020 | Region V | Camarines Sur | 113067 | Sipocot North Central School | Sipocot | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7773645.3689 | 1 |  | Completed | 100% | [9 empty] | Jurassic Const. & Supplies
GABALDON 2020 | Region V | Camarines Sur | 112506 | Canaman Central School | Canaman | 3 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4064090.3945 | 1 |  | Completed | 100% | [9 empty] | Jurassic Const. & Supplies
GABALDON 2020 | Region V | Camarines Sur | 112427 | Bula Central School | BULA | 5 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3275410.57 | 1 |  | Completed | 100% | [9 empty] | Jurassic Const. & Supplies
GABALDON 2020 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3365279.79 | 1 |  | Completed | 100% | [8 empty] | 2020-12-16 | Cam. Sur Bicol Trading, Inc.
GABALDON 2020 | Region V | Sorsogon City | 114534 | Bacon West Central School | Bacon West | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4467718.18 | 1 | 3089669.02 | Completed | 100% | 2022-02-18 |  | Infra 2021-02 | 2021-09-219 |  |  |  |  | 2021-10-21 | Law-an Builders & Supply
GABALDON 2020 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 9438616.92 | 1 |  | Completed | 100% | [8 empty] | 2020-12-16 | Cam. Sur Bicol Trading, Inc.
GABALDON 2020 | Region VI | Aklan | 114719 | Ibajay Central School | IBAJAY | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 6238558.58 | 1 | 6218000 | Completed | 100% | 2021-06-02 | 2021-05-13 | CY 2020 GABALDON - 001 | CY 2020 GABALDON - 001 | 2020-08-25 | 2020-09-01 | 2020-09-14 | 2020-09-25 | 2020-11-27 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
GABALDON 2020 | Region VI | Bacolod City | 117449 | Andres Bonifacio I ES | BACOLOD CITY (Capital) | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6638076.54 | 1 | 4653000 | Completed | 100% | 2021-12-27 | 2021-12-27 | r6bcd04142021-P25 | r6bcd04142021-P25 | 2021-04-16 | 2021-04-26 | 2021-05-10 | 2021-05-21 | 2021-07-30 | RISM BUILDERS & CONST. SERVICES INC.
GABALDON 2020 | Region VI | Iloilo | 116375 | Igbaras CES | IGBARAS | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 7538808.48 | 1 | 5490282.08 | Completed | 100% | 2022-09-30 | 2022-10-06 | Gab2020-RVI-022-ILOILO-B1-L1 | Gab2020-RVI-022-ILOILO-B1-L1 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises | On-going Rectification of Punchlisted Items
GABALDON 2020 | Region VI | Iloilo | 116616 | New Lucena CES | NEW LUCENA | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5645882.9412 | 1 | 3604983.51 | Completed | 100% | 2021-05-13 | 2021-12-20 | Gab2020-RVI-022-ILOILO-B1-L2 | Gab2020-RVI-022-ILOILO-B1-L2 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises
GABALDON 2020 | Region VI | Iloilo | 116119 | Cabatuan CES | CABATUAN | 3 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 6311025.38 | 1 | 4526000 | Completed | 100% | 2021-05-15 | 2021-09-20 | Gab2020-RVI-022-ILOILO-B1-L3 | Gab2020-RVI-022-ILOILO-B1-L | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-09 | RISM BUILDERS & CONST. SERVICES INC.
GABALDON 2020 | Region VI | Iloilo | 116043 | Barotac Nuevo CES | BAROTAC NUEVO | 4 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 19897556.7664 | 1 | 12905885.78 | Completed | 100% | Ocober 30, 2022 | 2022-09-27 | Gab2020-RVI-022-ILOILO-B1-L4 | Gab2020-RVI-022-ILOILO-B1-L4 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-11-17 | 2020-12-07 | Four SG Enterprises | On-going but with slow workmanship
GABALDON 2020 | Region VI | Iloilo | 116349 | Estancia Central Elementary School | ESTANCIA | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 5863706.88 | 1 | 4204000 | Completed | 100% | 2021-11-22 | 2021-10-12 | Gab2020-RVI-022-ILOILO-B1-L4 | Gab2020-RVI-022-ILOILO-B1-L4 | 2020-02-21 | 2020-02-27 | 2020-03-10 | 2020-10-01 | 2021-06-22 | RISM Builders and Merchandising
GABALDON 2020 | Region VI | Iloilo City | 117626 | A. Montes ES I | ILOILO CITY (Capital) | 0 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 16198458.88 | 1 |  | Completed | 100% | [10 empty] | REQUEST FOR REALIGNMENT (Realignment of A. MONTES ES1 TO AREVALO ES 100%, RIZAL ES 100%, and ESTEBAN JUNTADOR SR. MEMORIAL ES 100%)
GABALDON 2020 | Region VI | Iloilo City | 117629 | Jalandoni MS | ILOILO CITY (Capital) | 0 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 18915275.98 | 1 | 13229998.95 | Completed | 100% | 2021-07-19 | 0.28 | 20-12-006 | 20-12-006 | 2020-11-06 | 2020-11-13 | 2020-11-27 | 2020-12-04 | 2021-01-13 | 4SG Enterprises | COMPLETED
GABALDON 2020 | Region VI | Kabankalan City | 117858 | Esteban R. Abada Memorial School(East) | Kabankalan City | 6 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 12934200.86 | 1 |  | Completed | 100%
GABALDON 2020 | Region VI | La Carlota City | 302751 | Doña Hortencia Salas Benedicto NHS | LA CARLOTA CITY | 4 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6732754.41 | 1 | 3835451.66 | Completed | 100% | October 18, 2021 | [8 empty] | FOUR SG ENTERPRISES | Bidding Cancelled due to ECQ
GABALDON 2020 | Region VI | Negros Occidental | 117385 | Talisay ES | CITY OF TALISAY | 3 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3492344.95 | 1 | 3477970.42 | Completed | 100% | 2021-11-02 | Nov. 22, 2021 |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26D S.2020 |  | FOUR SG ENTERPRISES
GABALDON 2020 | Region VI | Negros Occidental | 117385 | Talisay ES | CITY OF TALISAY | 3 |  | 2 | 1 | Rehabilitation of Gabaldon Building | 2816674.04 | 1 | 2789325.92 | Completed | 100% | 2021-11-02 | Nov. 22, 2021 |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26C S.2020 |  | FOUR SG ENTERPRISES
GABALDON 2020 | Region VI | Negros Occidental | 117268 | Moises Padilla ES | MOISES PADILLA (MAGALLON) | 5 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 14261569.8 | 1 | 14241535.89 | Completed | 100% | 2021-04-05 | 2021-03-30 | 6974325 | 20-11-002 | 2020-04-24 | 2020-05-04 | 2020-05-18 | 2020-11-18 | 2020-11-23 | FOUR SG ENTERPRISES
GABALDON 2020 | Region VI | Negros Occidental | 116963 | Cauayan CES | CAUAYAN | 6 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5284051.93 | 1 | 5262334.53 | Completed | 100% | 2021-04-05 | 2021-02-28 | 6974361 | 20-11-001 | 2020-04-24 | 2020-05-04 | 2020-05-18 | 2020-11-18 | 2020-11-23 | FOUR SG ENTERPRISES
GABALDON 2020 | Region VI | Negros Occidental | 117162 | Bocana ES | ILOG | 6 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1915596.29 | 1 | 1898971.66 | Completed | 100% | 2021-11-02 |  |  |  | 2020-04-21 | 2020-05-04 | 2020-05-18 | 26A S.2020 |  | FOUR SG ENTERPRISES
GABALDON 2020 | Region VI | Sagay City | 117692 | Elia T. Canoy Esperancilla Elementary School | SAGAY CITY | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2418204.21 | 1 | 1810000 | Completed | 100% | December 16, 2021 | August 21, 2021 | 02-2020 | 02-2020 | 2020-02-25 | 2020-03-03 | 2020-03-16 |  | June 21, 2021 | RISM BUILDERS & CONSTRUCTION SERVICES, INC.
GABALDON 2020 | Region VI | Silay City | 117804 | Silay South Elementary School | SAGAY CITY | 3 | 1 | 29 | 1 | Rehabilitation of Gabaldon Building | 24820703.04 | 1 | 20338749.46 | Completed | 100% | 2022-09-30 |  |  | R6-D18-GAB-B2-2020 | March 27, 2020 | May 7, 2020 | May 19, 2020 | June 18, 2021 | July 27, 2021 | FOUR SG ENTERPRISES | On-going Rectification of Punchlisted Items
GABALDON 2020 | Region VII | Bohol | 118106 | Tultugan ES | CALAPE | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6655556.76 | 1 |  | COMPLETED | 100% | [6 empty] | January 20, 2021
GABALDON 2020 | Region VII | Bohol | 118504 | Sto. Niño Dela Paz ES | LOON | 1 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5424493.98 | 1 | 5404011.5 | Completed | 100% | 2021-12-15 |  | 6944754-Lot 1 | 44320 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 19, 2021 | ELEEO CONSTRUCTION AND SUPPLY
GABALDON 2020 | Region VII | Bohol | 118065 | Dagohoy Central Elementary | BUENAVISTA | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 4447691.3 | 1 | 4401399.38 | COMPLETED | 100% | 2021-12-08 |  |  | 44321 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-04 | C. JANSEN CONSTRUCTION AND GENERAL MERCHANDISE
GABALDON 2020 | Region VII | Bohol | 118358 | Guindulman Central ES | GUINDULMAN | 3 | 1 | 17 | 1 | Rehabilitation of Gabaldon Building | 17354037.14 | 1 | 13669174.29 | COMPLETED | 100% | 2022-09-30 |  | 6944754-Lot 3 | 44324 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 30, 2021 | JY BONTILAO CONSTRUCTION AND ENTERPRISE
GABALDON 2020 | Region VII | Carcar City | 119170 | Valladolid Elementary School | CITY OF CARCAR | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 7095987.75 | 1 |  | COMPLETED | 100% | [6 empty] | January 20, 2021
GABALDON 2020 | Region VII | Cebu | 118872 | Alcoy Central ES | ALCOY | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 9684010.33 | 1 | 6905228.73 | Completed | 100% | 2022-10-30 |  | 6944754-Lot 4 | 44325 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-25 | JY BONTILAO CONSTRUCTION AND ENTERPRISE
GABALDON 2020 | Region VII | Cebu | 119377 | DUMANJUG CENTRAL SCHOOL | DUMANJUG | 2 | 1 | 17 | 1 | Rehabilitation of Gabaldon Building | 14736225.74 | 1 | 10885703.67 | COMPLETED | 100% | 2021-12-28 |  | 6944754-Lot 5 | 44326 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION
GABALDON 2020 | Region VII | Cebu | 119566 | Pinamungajan Central School | PINAMUNGAHAN | 3 | 1 | 14 | 1 | Rehabilitation of Gabaldon Building | 16571044.5 | 1 | 12738307.98 | Completed | 100% | 2022-09-30 |  | 6944754-Lot 6 | 44322 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 10, 2021 | MP SORELA CONSTRUCTION AND SUPPLY AND MARINE SERVICES
GABALDON 2020 | Region VII | Cebu City | 119910 | Pardo Ext. Elementary School | CEBU CITY | 2 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 3257286.22 | 1 | 2896989.43 | COMPLETED | 100% | 2021-11-20 |  | 6944754-Lot 7 | 44327 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-16 | GELA CONSTRUCTION
GABALDON 2020 | Region VII | Danao City | 119357 | Severo Duterte MES | DANAO CITY | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 5532839.71 | 1 | 4514013.67 | COMPLETED | 100% | 2021-11-18 |  | 6944754-Lot 8 | 44331 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 14, 2021 | PB OBIAL CONSTRUCTION
GABALDON 2020 | Region VII | Mandaue City | 120010 | Canduman Elementary School | MANDAUE CITY | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3305576.84 | 1 | 2412962.02 | COMPLETED | 100% | 2021-10-29 | August 25, 2021 | 6944754-Lot 9 | 44328 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION | None
GABALDON 2020 | Region VII | Negros Oriental | 120587 | Lutay ES | TAYASAN | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4097116.4 | 1 | 4077000 | COMPLETED | 100% | 2021-12-14 |  | 6944754-Lot 10 | 44323 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 10, 2021 | RISM BUILDERS AND CONSTRUCTION
GABALDON 2020 | Region VII | Tagbilaran City | 118713 | Tagbilaran City Central Elementary School | TAGBILARAN CITY (Capital) | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 1857042.7 | 1 | 1836406.24 | COMPLETED | 100% | 2021-10-29 |  | 6944754-Lot 11 | 44329 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION
GABALDON 2020 | Region VII | Talisay City | 119787 | Lawaan Elementary School | CITY OF TALISAY | 1 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1851252.72 | 1 | 1348308.86 | COMPLETED | 100% | 2021-10-29 | August 25, 2021 | 6944754-Lot 12 | 44330 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | 2021-06-23 | TRI BAIRN CONSTRUCTION
GABALDON 2020 | Region VIII | Baybay City | 121102 | Baybay II Central School | CITY OF BAYBAY | 5 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 8001304.06 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Baybay City | 121125 | Plaridel Central School | CITY OF BAYBAY | 5 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4824381.51 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Biliran | 120758 | Almeria CS | ALMERIA | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4140117.82 | 1 | 4108000 | Completed | 100% | [9 empty] | J. Custorio Construction
GABALDON 2020 | Region VIII | Biliran | 120758 | Almeria CS (Balwarte Camp) | ALMERIA | 0 |  | 2 | 1 | Rehabilitation of Gabaldon Building | 4128547.93 | 1 | 4108000 | Completed | 100% | [9 empty] | J. Custorio Construction
GABALDON 2020 | Region VIII | Catbalogan City | 123416 | Catbalogan V CES (Mercedes ES) | CITY OF CATBALOGAN (Capital) | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1205717.66 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Leyte | 121154 | Burauen North Central School | BARAUEN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 8204817.56 | 1 | 8154000 | Completed | 100% | [9 empty] | J. Custorio Construction
GABALDON 2020 | Region VIII | Leyte | 121685 | Waterloo Elementary School | MATALOM | 5 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3610927.59 | 1 |  | Completed | 100% | [10 empty] | SUSPENDED
GABALDON 2020 | Region VIII | Maasin | 122174 | San Rafael Elementary School | CITY OF MAASIN (Capital) | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2101688.56 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Samar (Western Samar) | 123374 | Literon Elementary School | CALBIGA | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1037799.8 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD
GABALDON 2020 | Region VIII | Samar (Western Samar) | 303643 | Zumarraga NHS | ZUMARRAGA | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2751335.62 | 1 |  | Completed | 100% | [10 empty] | FOR AWARD
GABALDON 2020 | Region VIII | Southern Leyte | 122074 | Mahalo Elementary School | Anahawan | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2714955.1855 | 1 | 2900170.11 | Completed | 100% | [9 empty] | AAVB Construction and Supply
GABALDON 2020 | Region VIII | Southern Leyte | 122020 | Sta. Cruz Elementary School | Bontoc | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2750323.3 | 1 |  | Completed | 100% | [10 empty] | SUSPENDED
GABALDON 2020 | Region VIII | Southern Leyte | 122080 | Libagon Central School | Libagon | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2314497.8116 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Southern Leyte | 122185 | Ichon Elementary School | Macrohon | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2055875.565 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Southern Leyte | 122213 | San Vicente Elementary School | Malitbog | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 6301644.6507 | 1 |  | Completed | 100%
GABALDON 2020 | Region VIII | Southern Leyte | 122239 | Pintuyan Central School | Pintuyan | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 2459716.8771 | 1 | 2492209.98 | Completed | 100% | [9 empty] | AAVB Construction and Supply
GABALDON 2020 | Region VIII | Southern Leyte | 122252 | San Juan Central ElementarySchool | San Juan (Cabalian) | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3133535.5186 | 1 | 2900170.11 | Completed | 100% | [9 empty] | AAVB Construction and Supply
GABALDON 2020 | Region X | Cagayan de Oro City | 127962 | Consolacion Elementary School | CAGAYAN DE ORO CITY (Capital) | 2 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 2602587.62 | 1 | 2320989.95 | COMPLETED | 100% | 2021-08-02 | 2021-08-01 | 44044 | 20-12-BAC07 | September 21-25, 2020 | Canvass | 2020-09-28 | 2020-10-07 | 2020-12-11 | JARM Construction Services and Supply | Project completed
GABALDON 2020 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 9860389.51 | 1 | 8424360.07 | COMPLETED | 100% | 2021-09-25 | 2021-09-25 | 43831 | 20-03-BAC01 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-16 | JDE Construction | Project completed
GABALDON 2020 | Region X | Camiguin | 126914 | Mambajao CS | MAMBAJAO (Capital) | 0 |  | 1 | 1 | Rehabilitation of Gabaldon Building (Home Economics) | 2518346.23 | 1 | 2262723.44 | COMPLETED | 100% | 2021-07-27 | 2021-07-27 | 43831 | 20-03-BAC01 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-16 | JDE Construction | Project completed
GABALDON 2020 | Region X | Lanao del Norte | 127095 | Linamon Central School | LINAMON | 1 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 3350950.38 | 1 | 2842031.84 | COMPLETED | 100% | 2021-03-18 | 2021-07-30 | 43831 | 20-03-BAC02 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-18 | AbrahamBM Construction | Project completed
GABALDON 2020 | Region X | Lanao del Norte | 127099 | Samburon Elementary School | LINAMON | 1 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 7722092.81 | 1 | 6787587.22 | COMPLETED | 100% | 2021-07-30 | 2021-07-30 | 43831 | 20-03-BAC02 | 2020-01-10 | 2020-01-17 | 2020-02-06 | 2020-02-26 | 2020-11-18 | AbrahamBM Construction | Project completed
GABALDON 2020 | Region X | Misamis Occidental | 127244 | Aloran Central School | ALORAN | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 7057211.69 | 1 | 5596707.61 | COMPLETED | 100% | 2022-09-30 | 2024-07-31 | 44228 | 21-08-BAC05 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 13, 2021 | JARM Construction Services and Supply | Project completed
GABALDON 2020 | Region X | Misamis Occidental | 127273 | Baliangao CS | BALIANGAO | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 9373297.57 | 1 | 7662360.48 | COMPLETED | 100% | 2022-02-05 | 2022-02-05 | 44228 | 21-09-BAC09 | 2021-07-29 | 2021-08-05 | 2021-08-17 | 2021-08-31 | Sept. 20, 2021 | AFS construction | Project completed
GABALDON 2020 | Region X | Misamis Occidental | 127426 | Mansabay Alto ES | LOPEZ JAENA | 1 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 5847866.3 | 1 | 4903966.68 | Completed | 100% | 2022-09-30 | 2022-11-30 | 44228 | 21-08-BAC04 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 7, 2021 | Parbros Construction Services and Supply | Project completed
GABALDON 2020 | Region XI | Compostela Valley | 128552 | Napnapan ES | PANTUKAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3272205.59 | 1 |  | Completed | 100% | [10 empty] | For Mobilization
GABALDON 2020 | Region XI | Compostela Valley | 304208 | Pantukan NHS | PANTUKAN | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 1740426.25 | 1 |  | Completed | 100% | [10 empty] | For Mobilization
GABALDON 2020 | Region XI | Davao City | 129712 | BAGO ELEMENTARY SCHOOL | DAVAO CITY | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 6026983.08 | 1 |  | Completed | 100% | [10 empty] | FOR ISSUANCE OF RTA
GABALDON 2020 | Region XI | Davao City | 129557 | Kapt. T. Monteverde Sr. CES | DAVAO CITY | 1 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 8390772.6 | 1 |  | Completed | 100%
GABALDON 2020 | Region XI | Davao City | 129513 | Teofilo Fernandez ES | DAVAO CITY | 2 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 6250198.88 | 1 |  | Completed | 100% | [10 empty] | FOR ISSUANCE OF RTA
GABALDON 2020 | Region XI | Davao del Sur | 129049 | Padada CES | PADADA | 0 | 1 | 10 | 1 | Rehabilitation of Gabaldon Building | 9240000 | 1 |  | Completed | 100%
GABALDON 2020 | Region XI | Davao Oriental | 129211 | Caraga Central ES | Caraga | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 6519391.44 | 1 |  | Completed | 100%
GABALDON 2020 | Region XI | Davao Oriental | 129356 | Gregorio Moralizon ES | Manay | 1 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 3709572.11 | 1 |  | Completed | 100%
GABALDON 2020 | Region XII | General Santos City | 131273 | Lagao Central Elementary School | GENERAL SANTOS CITY (DADIANGAS) | 1 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10140232.79 | 1 |  | Completed | 100%
GABALDON 2020 | Region XII | North Cotabato | 129994 | Ugalingan ES | Carmen | 3 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 6000000 | 1 |  | Completed | 100%
GABALDON 2020 | Region XII | Sarangani | 500795 | Glan Central Integrated SPED Center | Glan | 0 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 6801120.53 | 1 |  | Completed | 100%
GABALDON 2021 | CAR | Abra | 134989 | Bucay CS | BUCAY | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5216538 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CAR | Abra | 135017 | Dolores CS | DOLORES | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4582774 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CAR | Abra | 135103 | Luba CS | LUBA | 0 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 5026084 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CAR | Benguet | 135435 | Bokod CS | BOKOD | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 16817332 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CAR | Mt. Province | 136202 | Bauko Central School | BAUKO | 0 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 38640021 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CARAGA | Cabadbaran City | 131574 | Calamba ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2840561 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1878693 | 1 |  | COMPLETED | 100%
GABALDON 2021 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 9363712 | 1 |  | COMPLETED | 100%
GABALDON 2021 | Region I | Laoag City | 300373 | Ilocos Norte College of Arts & Trades | LAOAG CITY (Capital) | 1 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 3071403 | 1 | 2911465.28 | COMPLETED | 100% | 2021-10-30 | 2021-10-30 | 2021-05-09 | 2021-06-22 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-30 | Elocin Construction | COMPLETED
GABALDON 2021 | Region I | Pangasinan II, Binalonan | 102126 | Villasis I Central School SPED Center | VILLASIS | 5 | 1 | 8 | 1 | Rehabilitation of Gabaldon Building | 10107429 | 1 | 10095606.34 | COMPLETED | 100% | 2022-01-06 | 2021-12-06 | 2021-05-09 | 2021-06-20 | 2021-05-19 | 2021-05-27 | 2021-06-08 | 2021-06-18 | 2021-07-07 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2021 | Region II | Batanes | 102316 | Itbayat Central School | ITBAYAT | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 23912552 | 1 | 23896225.01 | Completed | 100% | December 27, 2021 | April 28, 2023 |  | 2021-06-015 | April 6, 2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 29, 2021 | Pecdasen Builders | Total CA due to variation: 24,376,207.54
GABALDON 2021 | Region II | Nueva Vizcaya | 104089 | Kongkong Elementary School | KASIBU | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 6795389 | 1 | 4371705.54 | COMPLETED | 100% | October 28, 2021 | January 10,2022 |  | 2021-06-013 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 29, 2021 | Zyrrone Construction | Total CA due to variation: 4,798,651.92
GABALDON 2021 | Region II | Tuguegarao City | 104406 | Tuguegarao West CS | TUGUEGARAO CITY(Capital) | 3 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 9764168 | 1 | 6878702.89 | COMPLETED | 100% | October 28, 2021 | September 2023 |  | 2021-06-014 | April 8,2021 | April 15, 2021 | April 27, 2021 | June 21, 2021 | June 28, 2021 | Lucky Gems Construction
GABALDON 2021 | Region III | Balanga City | 104552 | Balanga Elementary School | CITY OF BALANGA (Capital) | 2 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 7397597 | 1 | 5100000 | COMPLETED | 100% | 2022-03-30 |  |  | ITB2021-10-020 |  |  |  |  | 2021-10-13 | V. TRILLANA BUILDERS AND TRADING
GABALDON 2021 | Region III | Tarlac City | 106691 | Matatalaib Bato ES | CITY OF TARLAC (Capital) | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4496502 | 1 | 3390249.63 | COMPLETED | 100% |  |  |  | ITB2021-10-021 |  |  |  |  | 2021-10-14 | DMGR BUILDERS
GABALDON 2021 | Region III | Zambales | 501224 | Botolan North Integrated School | BOTOLAN | 2 | 1 | 12 | 1 | Rehabilitation of Gabaldon Building | 8711059 | 1 | 8668888.88 | Completed | 100% | 2024-02-10 |  | R3INFRA-ITB2023-004 |  | 2023-09-12 | 2023-09-19 | 2023-10-03 | N/A | N/A | N/A | Under Procurement for Take over contract; Re-posted for the partial completion of 7 CL. FFE elevated up to 0.9m due to school prone to flooding
GABALDON 2021 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 13 | 1 | Rehabilitation of Gabaldon Building | 16342158.44 | 1 |  | Completed | 100% |  | 2021-11-11 | Gabaldon 2021 - R IVA - Laguna - 001 |  | 2021-03-10 |  | 2021-04-05 | 2021-04-07 | 2021-07-14 | Hackstow Construction and Development
GABALDON 2021 | Region IV-B | Oriental Mindoro | 110558 | Juan Morente Sr. Mem. Pilot Sch. | PINAMALAYAN | 2 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 3145338 | 1 | 3145338 | COMPLETED | 100% |  |  | N/A | N/A | 2021-04-07 | 2021-04-07 | 2021-04-26 | 2021-05-07 | 2021-05-11 | CMSEL Construction & Developer
GABALDON 2021 | Region IX | Zamboanga City | 126226 | Mampang Elementary School | ZAMBOANGA CITY | 2 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5000000 | 1 | 4995000 | Completed | 100% | January 31,2022 | November 30,2021 | ZC-GAB-2021 | ZC-GAB-2021 | May 3, 2021 | May 17, 2021 | May 31,2021 | July 8, 2021 | July 30,2021 | Zamboanga 3VC Constrution,INC. | None
GABALDON 2021 | Region V | Catanduanes | 113182 | Bato Central Elementary School | BATO | 0 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 1421396 | 1 | 1390915.91 | COMPLETED | 100% | 2022-02-18 | 2022-02-18 | Infra 2021-02 | 2021-09-220 |  |  |  |  | 2021-09-29 | Duamon Const. & Supply
GABALDON 2021 | Region V | Catanduanes | 113352 | Virac Pilot Elementary School | VIRAC | 0 | 1 | 38 | 1 | Rehabilitation of Gabaldon Building | 19675334 | 1 | 15284032.31 | COMPLETED | 100% | 2022-04-17 | 2022-04-17 | Infra 2021-02 | 2021-09-221 |  |  |  |  | 2021-11-03 | LDN Builders & Const. Supply
GABALDON 2021 | Region V | Sorsogon | 114263 | Jose Alindogan CS | JUBAN | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 18047175 | 1 | 17697175 | COMPLETED | 100% | 2022-05-08 | 2022-09-30 | Infra 2021-02 | 2021-09-218 |  |  |  |  | 2021-11-09 | Alhadrax Const. & Supply
GABALDON 2021 | Region V | Tabaco City | 302285 | Tabaco National High School | CITY OF TABACO | 1 | 1 | 28 | 1 | Rehabilitation of Gabaldon Building | 47362452 | 1 | 39888038.97 | COMPLETED | 100% | 2023-01-29 |  | Infra 2021-04 | 2021-12-482 | 2021-07-02 |  | 2021-07-27 |  |  | ZKR Construction & Supply
GABALDON 2021 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 16213839 | 1 | 8643152.52 | Reverted | 46% | 2022-12-22 |  | Infra 2021-04 | 2021-12-405 | 2021-07-02 |  | 2021-07-27 | 2021-12-02 |  | Gemwealth Const. & Trading | Terminated on Sep. 12, 2023, for reprogramming
GABALDON 2021 | Region VI | Aklan | 114738 | Naisud CS | IBAJAY | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 6399403 | 1 | 6335000 | COMPLETED | 100% | 2022-03-17 | 2022-03-04 | CY 2021 GABALDON - 001 | CY 2021 GABALDON - 001 | 2021-05-31 | 2021-06-07 | 2021-06-21 | 2021-07-12 | 2021-08-12 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
GABALDON 2021 | Region VI | Iloilo | 116012 | Balasan CES | BALASAN | 5 | 1 | 11 | 1 | Rehabilitation of Gabaldon Building | 9800503 | 1 | 6455847.57 | COMPLETED | 100% | 2021-11-22 | 2021-11-08 | R-06-BEFF Gabaldon-2020-B2-L1 | R-06-BEFF Gabaldon-2020-B2-L1 | 2020-02-21 |  | 2020-03-10 | 2020-10-01 | 2021-06-25 | Early Riser Construction
GABALDON 2021 | Region VI | Negros Occidental | 117212 | Tinongan ES | ISABELA | 5 | 1 | 4 | 1 | Rehabilitation of Gabaldon Building | 5776301 | 1 | 3692000 | completed | 100% | 2021-12-15 |  |  |  | 2021-06-08 | 2021-06-15 | 2021-06-28 | 2021-07-002 | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
GABALDON 2021 | Region VI | Negros Occidental | 117116 | Bulata ES | CAUAYAN | 6 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 4331131 | 1 | 2752000 | completed | 100% | 2021-12-15 |  |  |  | 2021-06-08 | 2021-06-15 | 2021-06-28 | 2021-07-003 | 2021-07-29 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC.
GABALDON 2021 | Region VI | San Carlos City | 117772 | Codcod ES | San Carlos City | 1 | 1 | 1 | 1 | Completion of Abandoned Gabaldon | 396661 | 1 | 393994.87 | completed | 100% | 2021-12-26 | 2021-10-18 | 7774758-2021-GABALDON | 7774758-2021-GABALDON | 2021-06-17 | 2021-06-25 | 2021-07-07 | 2021-07-29 | 2021-08-06 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 100% Completed
GABALDON 2021 | Region VI | San Carlos City | 117788 | Katingal-an ES | San Carlos City | 1 | 1 | 5 | 1 | Completion of Abandoned Gabaldon | 1511665 | 1 | 1501505.13 | completed | 100% | 2021-12-26 | 2021-12-20 | 7774758-2021-GABALDON | 7774758-2021-GABALDON | 2021-06-17 | 2021-06-25 | 2021-07-07 | 2021-07-29 | 2021-08-06 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | 100% Completed
GABALDON 2021 | Region VII | Bohol | 118331 | Getafe Central ES | GETAFE | 2 | 1 | 3 | 1 | Rehabilitation of Gabaldon Building | 3538205 | 1 | 3502098.85 | COMPLETED | 100% | 2021-12-08 |  | 7595364-Lot 2 | 44318 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 4, 2021 | C. JANSEN CONSTRUCTION AND GENERAL MERCHANDISE
GABALDON 2021 | Region VII | Cebu | 119864 | VILLAHERMOSA ES | TUDELA | 5 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2804104 | 1 | 2779358.3 | COMPLETED | 100% | 2021-10-16 |  | 7595364-Lot 3 | 44319 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 11, 2021 | BARR STEEL CONSTRUCTION
GABALDON 2021 | Region VII | Dumaguete City | 119935 | Camanjac Elementary School | DUMAGUETE CITY (Capital) | 2 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 4102769 | 1 | 4061000 | COMPLETED | 100% | 2021-12-14 | c/o Maam Daday Guillen/Region-Implemented | 7595364-Lot 1 | 44317 | April 29, 2021 | April 15, 2021 | May 7, 2021 | May 27, 2021 | June 10, 2021 | RISM BUILDERS AND CONSTRUCTION
GABALDON 2021 | Region VIII | Baybay City | 121082 | Gaas Elementary School | CITY OF BAYBAY | 5 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3661725 | 1 | 3585000 | COMPLETED | 100%
GABALDON 2021 | Region VIII | Eastern Samar | 122484 | Gen. MacArthur Central Elementary School | GENERAL MACARTHUR | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 4910770 | 1 |  | COMPLETED | 100% | 2022-01-15 | 2022-01-15 | 21-04-262 | 012-2021 | 2021-05-15 | 2021-04-21 | 2021-06-23 | 2021-09-09 | 2021-09-17 | QCC Construction and Supply
GABALDON 2021 | Region VIII | Eastern Samar | 122758 | Sulat Central Elementary School | SULAT | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 5510971 | 1 |  | COMPLETED | 100% | 2022-01-15 | 2022-01-15 | 21-04-263 | 012-2022 | 2021-05-15 | 2021-04-21 | 2021-06-23 | 2021-09-09 | 2021-09-18 | QCC Construction and Supply
GABALDON 2021 | Region X | Bukidnon | 126508 | Lantapan CES | ANTAPAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2354739 | 1 | 1999294.989 | Completed | 100% | September 30, 2022 | 2023-04-18 | 44228 | 21-08-BAC08 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 24, 2021 | Tri-FB Construction | Project completed
GABALDON 2021 | Region X | Cagayan de Oro City | 127979 | Mambuaya Elementary School | CAGAYAN DE ORO CITY (Capital) | 1 | 1 | 3 | 1 | Reconstruction of Type 4 - Rectangular Type Gabaldon Building | 7606016 | 1 | 6056773.59 | COMPLETED | 100% | September 30, 2022 | 2022-12-06 | 44228 | 21-08-BAC06 | 2021-03-11 | 2021-03-18 | 2021-06-21 | 2021-07-21 | Sept. 9. 2021 | Nonabon Enterprises | Project completed
GABALDON 2021 | Region XI | Davao City | 129492 | Binugao CES | DAVAO CITY | 3 | 1 | 16 | 1 | Rehabilitation of Gabaldon Building | 2944439 | 1 |  | COMPLETED | 100% | [6 empty] | June 30, 2021 |  | Sept. 27, 2021 | J&S Escuadra Construction and Supply
GABALDON 2021 | Region XI | Mati City | 129380 | Rabat-Rocamora Mati CES I | CITY OF MATI (Capital) | 2 | 1 | 20 | 1 | Rehabilitation of Gabaldon Building | 23181008 | 1 |  | COMPLETED | 100% | 2022-09-30 |  |  |  | 2021-05-13 |  | 2021-06-02 | 2021-06-14 | 2021-06-21 | MATT GLASS
GABALDON 2021 | Region XII | General Santos city | 131290 | Jose Divinagracia ES | General Santos city | 1 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 9254653 | 1 |  | COMPLETED | 100%
GABALDON 2022 | CAR | Mt. Province | 136239 | Dandanac Elementary School | BESAO | 0 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 14828997.48 | 1 | 147777975.49 | Completed | 100% | 5/31/2023 | August 10, 2023 | INF2022GAB001 | INF2022GAB001 | 7/30/2022 | 2022-02-08 | 8/15/2022 | Sept 19, 2022 | 11/25/2022 | JM-MAS Construction & Gen. MDSE.
GABALDON 2022 | CAR | Mt. Province | 136342 | Ambasing Elementary School | SAGADA | 0 | 1 | 6 | 1 | Rehabilitation of Gabaldon Building | 37800000 | 1 | 37720000 | Completed | 100% | 7/30/2023 | July 12, 2024 | INF2022GAB002 | INF2022GAB002 | 7/30/2023 | 2022-02-08 | 8/15/2022 | Sept 19, 2022 | 11/25/2022 | BAJE CONSTRUCTIOIN
GABALDON 2022 | Region II | Batanes | 102322 | Ivana Elementary School | IVANA | 0 | 1 | 7 | 1 | Rehabilitation of Gabaldon Building | 17516777.66 | 1 | 12530440.87 | Completed | 100% | February 07, 2024 | March 27, 2025 | 2022-07-0112 | 2022-07-0112 | July 12, 2022 | July 12, 2022 | August 02, 2022 | October 17, 2022 | October 20, 2022 | Wakaii Construction | Completed
GABALDON 2022 | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3 | 1 | 1 | 1 | Restoration of Gabaldon-Home Economics Building | 4782422.34 | 1 | 4221580.35 | Completed | 100% | 4/25/2023 | 4/25/2023 | R4A-2022-025 | R4A-2022-025 | 2022-09-09 | 9/15/2022 | 9/27/2022 | 11/21/2022 | 11/24/2022 | Open Builders Incorporated | Completed
GABALDON 2022 | Region IV-B | Marinduque | 109952 | Mogpog Central School | MOGPOG | 0 | 1 | 15 | 1 | Rehabilitation of Gabaldon Building | 5234939.52 | 1 | 5182728.28 | COMPLETED | 100% | 2023-02-08 | 7/28/2023 | 2022-10-BEFF-04 | 2022-11-020 | 2022-10-10 | 10/21/2022 | 2022-03-11 | 11/23/2022 | 2022-05-12 | GS Motar Builders Construction and Trading
GABALDON 2022 | Region VII | Bohol | 118223 | Dagohoy Central Elementary | DAGOHOY | 2 | 1 | 5 | 1 | Rehabilitation of Gabaldon Building | 952221.1 | 1 |  | Reverted | 0% |  |  | 6944754-Lot 2 | 44321 | [6 empty] | REVERTED SINCE FUNDED IN THE QRF BATCH 2
GABALDON 2022 | Region X | El Salvador | 127672 | Himaya ES | CITY OF EL SALVADOR | 2 | 1 | 3 | 1 | Restoration of Gabaldon Building | 8936669.89 | 1 | 6629086.32 | COMPLETED | 100% | 2023-01-04 | 2/29/2024 | 2022-10-0229 | 2022-12-0328 | 10/25/2022 | 2022-03-11 | 11/15/2022 | 11/28/2022 | 12/15/2022 | Hid Construction | Project completed
GABALDON 2022 | Region X | Misamis Oriental | 127714 | ALICOMOHAN CS | SUGBONGCOGON | 2 | 1 | 4 | 1 | Repair & Rehabilitation of 4-Rectangular Type Gabaldon Building | 7905972.01 | 1 | 7770174.85 | Completed | 100% | 3/20/2023 | 8/20/2023 | PB - Repair 2022-02 | 3916422 | 9/16/2022 | 2022-03-10 | 10/17/2022 | 2022-04-11 | 11/13/2022 | Meter King Inc. | Project completed
GABALDON 2023 | CAR | Baguio City | 136382 | Baguio Central School | BAGUIO CITY | 0 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 41223103.23 | 1 | 40014561 | Ongoing | 40% | November 5,2025 | NA | No.027,s.2023 | No.027,s.2023 | December 9, 2023 | December 15, 2023 | December 29, 2023 | January 18, 2024 | February 20, 2024 | EZRAH Construction Services/HGW=3 Engineering and Construction | Project suspended as to LGU's order while the submission and approval of Conservation Management Plan and Building Permit
GABALDON 2023 | CAR | Benguet | 135402 | Bagu ES | BAKUN | 0 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 10000000 | 1 | 10000000 | COMPLETED | 100% | 9/17/2024 | 12/13/2024 | GAB-2023-01 | GAB-2023-02 | 2023-05-05 | 2023-12-05 | 5/25/2023 | 7/28/2023 | 9/18/2023 | SCA JR BUILDERS
GABALDON 2023 | CARAGA | Agusan del Norte | 131468 | Las Nieves CES | LAS NIEVES | 1 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 2307345.08 | 1 | 2292004.81 | Completed | 100% | 2023-11-13 | 2023-11-20 | GAB-2023-CARAGA-AGUSAN DEL ORTE-003 | GAB-2023-CARAGA-AGUSAN DEL ORTE-003 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | J-R3 Const. & Supply | with time extension
GABALDON 2023 | CARAGA | Agusan del Norte | 131421 | Gosoon ES | CARMEN | 2 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 3608213.56 | 1 | 2865569.03 | COMPLETED | 100% | 2023-12-04 |  | GAB-2023-CARAGA-AGUSAN DEL ORTE-002 | GAB-2023-CARAGA-AGUSAN DEL ORTE-002 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | ILMAR CONST | with time extension due to weather condition and proposed V.O
GABALDON 2023 | CARAGA | Agusan del Norte | 131491 | Amontay ES | NASIPIT | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 4368940.25 | 1 | 3308793.92 | COMPLETED | 100% | 2023-12-04 |  | GAB-2023-CARAGA-AGUSAN DEL ORTE-001 | GAB-2023-CARAGA-AGUSAN DEL ORTE-001 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | BN BUILDERS | with time extension due to weather condition and proposed V.O
GABALDON 2023 | CARAGA | Surigao del Sur | 132930 | Anahao Bag-o Elementary School | TAGO | 1 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 4078781.46 | 1 |  | Completed | 100% | 2024-06-26 | 2024-06-24 | GAB 2023 - R XIII - SURIGAO DEL SUR - 001 | 2023-012 |  |  |  |  | 2023-12-29 | CYL CONSTRUCTION & SUPPLY | with Time Extension due to Extra Work Order
GABALDON 2023 | CARAGA | Surigao del Sur | 132933 | Badong Elementary School | TAGO | 1 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 4670841.77 | 1 |  | Completed | 100% | 2024-06-26 | 2024-06-24 | GAB 2023 - R XIII - SURIGAO DEL SUR - 002 | 2023-009 |  |  |  |  | 2023-12-29 | CYL CONSTRUCTION & SUPPLY | with Time Extension due to Extra Work Order
GABALDON 2023 | Region I | Ilocos Sur | 100525 | Narvacan North Central School | NARVACAN | 2 | 1 | 20 | 1 | Restoration & Conservation of Gabaldon Building | 10727623.23 | 1 | 8759254.25 | Completed | 100% | 1/31/2024 | 2024-10-04 | 2023-07-006-PB-Works | n/a | 7/25/2023 | 2023-01-08 | 8/14/2023 | 8/25/2023 | 2023-04-09 | MA Tejada Construction
GABALDON 2023 | Region I | La Union | 100801 | Agoo East CES | AGOO | 2 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 2300000 | 1 | 2282755.65 | COMPLETED | 100% | 9/27/2023 | 9/22/2023 | 2023 GAB-RO1-01 |  | 5/27/2023 | 2023-05-06 | 6/19/2023 | 6/26/2023 | 6/29/2023 | MANIMELDS IRON WORKS AND CONSTRUCTION | COMPLETED
GABALDON 2023 | Region II | Nueva Vizcaya | 104173 | Solano East CS | SOLANO | 0 | 1 | 9 | 1 | Restoration & Conservation of Gabaldon Building | 12975814.87 | 1 | 8950988.1 | COMPLETED | 100% | April 7, 2024 | September 15, 2024 | PB5-001-SDONV-GABALDON-SECS-INFRA | PB5-001-SDONV-GABALDON-SECS-INFRA | May 19, 2023 | May 25, 2023 | June 6, 2023 | July 10, 2023 | August 4, 2023 | Pecdasen Builders | with time extension and additional works Savings Contract: 4,024,727.00 CD: 90 CD
GABALDON 2023 | Region III | Mabalacat City | 106066 | Mabalacat ES | MABALACAT CITY | 1 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 4883900 | x | 4873237.23 | COMPLETED | 100% | 11/27/2023 | 11/24/2023 | PB-2023-07-004 | SBR-2023-08-004 | 2023-05-07 | 2023-12-07 | 7/24/2023 | 8/22/2023 | 8/29/2023 | S.M. SEVERINO CONSTRUCTION AND TRADING
GABALDON 2023 | Region IV-A | Cavite | 108068 | Naic Elementary School | NAIC | 8 | 1 | 40 | 1 | Restoration & Conservation of Gabaldon Building | 73500276.2 | 1 | 170000000 | Ongoing | 70% | 2025-11-09 | N/A - ONGOING | N/A | RIVACaviteBAC-Infra 001-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC | Waiting for the delivery of wood and already finishing the removal of plastering on the adobe walls
GABALDON 2023 | Region IV-A | Laguna | 108194 | San Benito ES | ALAMINOS | 3 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 9433708.8 | 1 | 7063460.67 | Completed | 100% | 2/29/2024 | 2024-09-02 | 9822217 | R4A-2023-002 | 6/5-14/2023 | 6/13/2023 | 6/26/2023 | 6/29/2023 | 2023-05-07 | J.B. Alarcon Enterprises | Completed
GABALDON 2023 | Region IV-A | Quezon | 108847 | Lopez West Elementary School Bldg. I | LOPEZ | 4 | 1 | 22 | 1 | Restoration & Conservation of Gabaldon Building | 28732371.6 | 1 | 28714340 | Completed | 100% | 5/21/2024 | 2024-06-05 | 2023-02A-INFRA | 2023-02A-INFRA | 5/26/2023 | 2023-02-06 | 6/14/2023 | 8/16/2023 | 8/23/2023 | Hawkstow Construction and Development | Completed
GABALDON 2023 | Region IV-A | Quezon | 108996 | Perez CS | PEREZ | 4 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 2913266.4 | 1 | 2903257.83 | Completed | 100% | 12/22/2023 | 2023-01-12 | 2023-03R-INFRA | 2023-03R-INFRA | 2023-08-08 | 8/16/2023 | 8/29/2023 | 2023-06-09 | 9/13/2023 | M.G Villamin Construction | The school name is incorrect, it should be Perez West ES
GABALDON 2023 | Region IV-B | Marinduque | 109924 | Bangbang ES | GASAN | 0 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 10616143.68 | 1 | 10616143.68 | COMPLETED | 100% | 4/28/2024 | 2024-10-06 | 2023-OSEC-4B-23-1799-002 | 2023-08-006 | 6/16/2023 | 6/27/2023 | 2023-11-07 | 7/18/2023 | 8/25/2023 | GS Motar Builders Construction and Trading
GABALDON 2023 | Region IX | Zamboanga del Norte | 124369 | Katipunan Central School | KATIPUNAN | 2 | 1 | 16 | 1 | Restoration & Conservation of Gabaldon Building | 17112890.01 | 1 | 17093932.97 | Completed | 100% | 2023-07-11 | - | 2023-7-CBZN | CB-2023-007 | 2023-05-04 | 4/14/2023 | 4/27/2023 | 5/30/2023 | 2023-07-06 | YSL BUILDERS | None
GABALDON 2023 | Region IX | Zamboanga del Sur | 125371 | San Pablo CES | SAN PABLO | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 4907365.3 | 1 | 4877195.13 | Completed | 100% | 2023-04-11 | November 4, 2023 | ZDS-23-RG-01 | ZDS-23-RG-01 | 4/13/2023 | 4/26/2023 | 2023-08-05 | 5/22/2023 | 5/31/2023 | ASCS CONSTRUCTION | None
GABALDON 2023 | Region V | Sorsogon | 114235 | Irosin Central School | IROSIN | 2 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 18897276.98 | 1 | 15966021.18 | COMPLETED | 100% | 4/25/2024 | 9/26/2024 | 2023-09-001 | 23-09-001 | 2023-05-09 | 9/13/2023 | 9/25/2023 | 11/24/2023 | 12/28/2023 | Duamon Construction and Supply | NTP conforme December 28, 2023
GABALDON 2023 | Region VI | Negros Occidental | 117113 | Hinigaran ES-A | HINIGARAN | 5 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 11443993.61 | 1 | 9126569.32 | completed | 100% | 7/24/2024 | 7/23/2024 | 38952 | JO# 25-11-002 | 8/25/2023 | 2023-01-09 | 9/14/2023 | No. 040 s. 2023 | 12/27/2023 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY
GABALDON 2023 | Region VII | Bohol | 118672 | SEVILLA CENTRAL ELEMENTARY SCHOOL | SEVILLA | 3 | 1 | 6 | 1 | Restoration & Conservation of Gabaldon Building | 7036885.43 | 1 |  | COMPLETED | 100%
GABALDON 2023 | Region VII | Cebu | 119613 | Samboan Central ES | SAMBOAN | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 15492410.45 | 1 | 15431357.88 | COMPLETED | 100% | 2024-10-02 | 2024-03-08 | cy 2023 gabaldon-deped-region 7-cebu | cy 2023 gabaldon-deped-region 7-cebu-02 | 11/29/2023 | 2023-06-12 | 12/18/2023 | 2024-01-05 | 2024-01-26 | Anielthon construction and supply
GABALDON 2023 | Region VII | Cebu | 119549 | Pilar Central School | PILAR | 5 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 9189509.48 | 1 | 9133229.31 | COMPLETED | 100% | 2024-08-03 | 2024-08-03 | cy 2023 gabaldon-deped-region 7-cebu | cy 2023 gabaldon-deped-region 7-cebu-01 | 11/29/2023 | 2023-06-12 | 12/18/2023 | 2024-01-05 | 2024-01-26 | Barr steel construction
GABALDON 2023 | Region VIII | Biliran | 120770 | TABUNAN ES | ALMERIA | 0 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 2809414.04 | 1 | 659450.8 | Completed | 100% | 12/13/2023 | 12/13/2023 | 2024INFRA-Repair-008 | CY 2023 REPAIR/REHAB OF GABALDON BLDG-01 | 2023-02-06 | 6/26/2023 | 6/26/2023 | 7/20/2023 | 2023-09-08 | MB ANG CONSTRUCTION AND SUPPLY | COMPLETED
GABALDON 2023 | Region VIII | Eastern Samar | 122775 | Taft Central Elementary School | TAFT | 0 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 6520393.33 | 1 |  | completed | 100% | ################ | 9/30/2023 | CY2023-GAB-B1-LOT1 | CY2023-GAB-B1-LOT1 | 3/29/2023 | 2023-03-05 | 2023-03-05 | ########### | 5/26/2023 | Vhits D.G Builders & Enterprises
GABALDON 2023 | Region VIII | Samar (Western Samar) | 123655 | Pagsanghan Central Elementary School | PAGSANGHAN | 1 | 1 | 7 | 1 | Restoration & Conservation of Gabaldon Building | 14000000 | 1 | 13951642.86 | completed | 100% | 1/15/2024 | 2/25/2024 | CY2023GABLOT1 | 2023-018 | 2023-06-04 | 4/28/2023 | 4/28/2023 | ########### | 6/23/2023 | MJM BUILDERS | WITH TIME EXTENSIONS AND WITH LIQUIDATED DAMAGES
GABALDON 2023 | Region VIII | Southern Leyte | 122230 | Triana Elementary School | LIMASAWA | 1 | 1 | 5 | 1 | Restoration & Conservation of Gabaldon Building | 6428742.23 | 1 | 6302256.68 | Completed | 100% | 1/25/2024 | 2024-12-01 | CY2023-Gabaldon-L1 | CY2023-Gabaldon-L1 | 4/17/2023 | 2023-09-05 | 2023-09-05 | 7/17/2023 | 2023-03-08 | QCC Construction and Supply | Completed
GABALDON 2023 | Region X | Lanao del Norte | 500689 | Lala Proper IS | LALA | 2 | 1 | 10 | 1 | Restoration & Conservation of Gabaldon Building | 18049936.9 | 1 | 13418727.45 | Completed | 100% | 4/30/2024 | 10/16/2024 | 2023-04(Infra)-Rebid | 45047 | 7/26/2023 | 2023-02-08 | 8/14/2023 | 8/28/2023 | 9/25/2023 | Millineum Builders and Construction | Project completed
GABALDON 2023 | Region XII | Koronadal City | 304671 | Koronadal NCHS | CITY OF KORONADAL (Capital) | 2 | 1 | 13 | 1 | Restoration & Conservation of Gabaldon Building | 25735852.11 | 1 | 21312201.38 | Ongoing | 98.5% | 2024-12-09 | ongoing | 2023-09-001 | 2023-12-006 | 2023-09-26 | 2023-10-04 | 2023-10-16 | 2023-11-05 | 2023-12-14 | JANMARIE CONSTRUCTION SERVICE AND SUPPLY | No Submission for March update
GABALDON 2024 | CAR | Abra | 134979 | Bangued West CS | BANGUED (Capital) | Lone | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 12905610 | 1 | 12887697.3 | Completed | 100% | November 5, 2024 | November 5, 2024 | CAR-ABRA-2024-04-006 | 2024-07-007 | April 17, 2024 | April 24, 2024 | May 7, 2024 | May 16, 2024 | July 8, 2024 | BAJE CONSTRUCTIOIN
GABALDON 2024 | CAR | Abra | 135223 | San Juan CS | SAN JUAN | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 25000000 | 1 | 24988913.87 | Ongoing | 90% | February 3, 2025 |  | CAR-ABRA-2024-04-006 | 2024-07-007 | April 17, 2024 | April 24, 2024 | May 7, 2024 | May 16, 2024 | July 8, 2024 | BAJE CONSTRUCTIOIN
GABALDON 2024 | CAR | Benguet | 135438 | Daklan ES | BOKOD | Lone | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 19094390 | 1 | 18378750 | Ongoing | 45% | August 5,2025 |  | GAB-2024-02 | GAB-2024-02 | MAY 29. 2024 | 2024-10-06 | 6/24/2024 | September 26, 2024 | October 31, 2024 | MHIGS CONSTRUCTION
GABALDON 2024 | CAR | Benguet | 135619 | Bekkel ES | LA TRINIDAD (Capital) | Lone | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 23919100 | 1 | 22932793.89 | Ongoing | 70% | August 5,2025 |  | GAB-2024-01 | GAB-2024-01 | MAY 29. 2024 | 2024-10-06 | 6/24/2024 | September 26, 2024 | October 31, 2024 | JRF ANGOYNA GENERAL CONSTRUCTION/REKO KONSTRUCT-JV
GABALDON 2024 | CAR | Ifugao | 220020 | Ifugao SPED Center | LAGAWE (Capital) | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 34222823.15 | 1 |  | Not Yet Started | 0% | [10 empty] | Ongoing Preparation of Plans, POW and CMP
GABALDON 2024 | CARAGA | Agusan del Norte | 131532 | LUIS B. AZURA SR. MEMORIAL ES | RTR | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 4162296.96 | 1 | 4154361.34 | Ongoing | 48% | June 8, 2025 | - | GABALDON 2023 - AGUSAN DEL NORTE - 001 | GABALDON 2023 - AGUSAN DEL NORTE - 001 |  |  | September 6, 2024 | December 20, 2024 | December 23, 2024 | BN BUILDERS & CONST. SUPPLIES INC.
GABALDON 2024 | CARAGA | Butuan City | 132040 | Taligaman ES | BUTUAN CITY (Capital) | 1st | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 24000000 | 1 | 23984589.1 | ongoing | 95% | June 30, 2025 | - | GABALDON 2024 - CARAGA - BUTUAN CITY - 001 | GABALDON 2024 - CARAGA - BUTUAN CITY - 001 | April 30, 2024 | May 8, 2024 | May 20, 2024 | May 28, 2024 | September 18, 2024 | RELY CONSTRUCTION & SUPPLY INC. | Delayed due to the delayed delivery of wood materials from far flung source of the materials
GABALDON 2024 | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 4415934.04 | 1 | 4400505.74 | Ongoing | 70% |  | - | GABALDON 2024 - CARAGA |  |  |  |  | 12/20/2024 | 2024-12-12 | J-R3 CONSTRUCTION & SUPPLY | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | CARAGA | Surigao City | 132272 | Surigao City Pilot Sch. | SURIGAO CITY (Capital) | 2nd | 1 | 14 | 1 | Conservation and Restoration of Gabaldon School Building | 5419736.68 | 1 | 3404082.78 | Ongoing | 75% | July 13, 2025 | - | GABALDON 2024 - CARAGA - SURIGAO CITY - 001 | FY-2024-INF-026 | October 24, 2024 | October 21, 2024 | November 13, 2024 | November 13, 2024 | March 10, 2025 | WINDFALL CONSTRUCTION
GABALDON 2024 | CARAGA | Surigao del Sur | 132768 | Anibongan Elementary School | LIANGA | 1st | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3767382.84 | 1 | 2536593.52 | Completed | 100% | June 01, 2025 | May 06, 2025 | GAB 2024 - R XIII - SURIGAO DEL SUR - 001 | 005 - 2024 | August 30, 2024 | September 05, 2024 | September 17, 2024 | October 14, 2024 | January 03, 2025 | CYL CONSTRUCTION & SUPPLY | COMPLETED
GABALDON 2024 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 3907026.54 | 1 | 2466129.4 | Not Yet Started | 0% |  |  | EPA-2024-07-159 | EPA-2024-07-159 | July 24, 2024 | August 1, 2024 | August 13, 2024 |  |  | cYL CONSTRUCTION & SUPPLY | CONDUCTED EPA AND WAITING FOR THE SUBARO
GABALDON 2024 | NCR | Manila | 136433 | Emilio Jacinto Elementary School | TONDO | 1st | 1 | 46 | 1 | Conservation and Restoration of Gabaldon School Building | 70290443 | 1 | 64926690.13 | Ongoing | 45% | 9/24/2025 |  | N/A | N/A | 9/17/2024 | 9/25/2024 | 2024-07-10 | 10/29/2024 | 2025-03-01 | Flordes Construction and Trading | Currently on-going
GABALDON 2024 | NCR | Quezon City | 136524 | Placido del Mundo ES | QUEZON CITY | 6th | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 12449405.63 | 1 | 11900000 | Not Yet Started | 0% |  |  | SDOQC-2024-INFRA-002 |  | 11/19/2024 | 11/27/2024 | 2024-09-12 | 12/16/2024 |  | Aylan Construction and Trading | To request CO for Architectural Plan, Drafting CMP & awaiting for Sub ARO
GABALDON 2024 | NCR | Taguig City and Pateros | 136896 | Pateros Elementary School | PATEROS | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 13343097.49 | 1 | 13243142.21 | Not Yet Started | 0% |  |  |  |  | 2/26/2025 | 2025-04-03 | 3/17/2025 | 3/24/2025 |  |  | For issuance of NOA, Contract and NTP. Awaiting for the lift of election ban
GABALDON 2024 | Region I | Pangasinan I, Lingayen | 101420 | Bued ES | CALASIAO | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 10000000 | 1 |  | Under Procurement | 0% | [10 empty] | waiting for the approved plans for the restoration
GABALDON 2024 | Region I | San Carlos City | 300388 | Speaker Eugenio Perez National Agricultural School | SAN CARLOS CITY | 3rd | 1 | 17 | 1 | Conservation and Restoration of Gabaldon School Building | 19117181.04 | 1 |  | Under Procurement | 0% | [10 empty] | STIIL COMPLYING THE DOCUMENTS NEEDED BY NCCA.
GABALDON 2024 | Region II | Nueva Vizcaya | 104182 | Solano North ES | SOLANO | Lone | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 18633863.75 | 1 | 11953716.99 | Ongoing | 39% | May 26, 2025 | - | PB 10-001 S.2024 | PB 10-001 S.2024 | August 6, 2024 | August 12, 2024 | August 27, 2024 | October 3, 2024 | December 27, 2024 | KNB CONSTRUCTION | On Going Construction with Variation Order
GABALDON 2024 | Region III | Bulacan | 104710 | Matias A. Fernando MS (Angat C/S) | ANGAT | 6th | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 10662171.54 | 1 | 6695000 | Completed | 100% | 4/19/2025 | 4/18/2025 | PB-24-011 | PB-24-011 | 6/28/2024 | 2024-08-07 | 7/22/2024 | 2024-06-08 | 10/14/2024 | V. Trillana Builders and Trading
GABALDON 2024 | Region III | Pampanga | 105897 | Anderson ES | ARAYAT | 3rd | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 12033643.5 | 1 | 11983176.6 | Completed | 100% | 12/30/2024 | 2024-09-12 | g-2024-013 | g-2024-013 | 4/25/2024 | 2024-06-05 | 5/20/2024 | 7/29/2024 | 2024-02-08 | S.M. SEVERINO CONSTRUCTION AND TRADING
GABALDON 2024 | Region III | Tarlac | 501609 | San Clemente Central Integrated School | SAN CLEMENTE | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 6039174.81 | 1 | 3994303.57 | completed | 100% | 3/23/2025 | 1/13/2025 |  |  | 5/24/2024 | 2024-03-06 | 6/17/2024 | 6/28/2024 | 9/24/2024 | T. DEL ROSARIO CONSTRUCTION
GABALDON 2024 | Region III | Tarlac City | 106698 | Balingcanaway Centro ES | CITY OF TARLAC (Capital) | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 3765154.63 | 1 | 3759728.61 | COMPLETED | 100% | 9/23/2024 | 9/23/2024 | TCSD-IP-03-2024 | TCSD-IP-03-2024 | 2024-05-03 | 3/13/2024 | 3/25/2024 | 2024-01-04 | 6/24/2024 | JFM ALTITUDE CONSTRUCTION CORPORATION | NONE
GABALDON 2024 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2nd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 7211999.95 | 1 | N/A | Not Yet Started | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Awaiting approval of submitted CMP
GABALDON 2024 | Region IV-A | Batangas | 107263 | Bauan East Central School | BAUAN | 2nd | 1 | 18 | 1 | Conservation and Restoration of Gabaldon School Building | 20221416 | 1 | N/A | Not Yet Started | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Waiting approval of NHCP
GABALDON 2024 | Region IV-A | Batangas | 107736 | Venancio Trinidad Sr. Memorial School | TALISAY | 3rd | 1 | 1 | 1 | Conservation and Restoration of Gabaldon School Building | 4322959.77 | 1 | N/A | Not Yet Started | 0% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Waiting approval of NHCP
GABALDON 2024 | Region IV-A | Cavite | 107994 | Indang Central Elementary School | Indang | 7th | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 25823069.04 | 1 | 17000000 | Ongoing | 70% | 5/14/2025 | N/A - ONGOING | N/A | RIVACaviteBAC-Infra 002-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC | With Approved Extension due to scarcity of wood
GABALDON 2024 | Region IV-A | Cavite | 108068 | Naic Elementary School | NAIC | 8th | 1 | 40 | 1 | Conservation and Restoration of Gabaldon School Building | 99704396.58 | 1 | Combined with Phase 1 | Ongoing | 70% | 2025-11-09 | N/A - ONGOING | N/A | RIVACaviteBAC-Infra 001-2024 | 5/14/2024 | 5/21/2024 | 2024-07-06 | 8/29/2024 | 9/16/2024 | JS LIM CONSTRUCTION AND TRADING, OPC | None
GABALDON 2024 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 11565863.92 | 1 | 7798828.33 | Completed | 100% | 4/22/2025 | 2025-03-06 | 2024-06-0006 | 2024-06-0006 | 2024-04-06 | 6/13/2024 | 6/26/2024 | 2024-04-07 | 9/24/2024 | ASS Construction | None
GABALDON 2024 | Region IV-A | Dasmarinas City | 107911 | Sabang Elementary School | CITY OF DASMARIÑAS | 4th | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 21481580.08 | 1 | 15021854.56 | Not Yet Started | 0% | N/A | N/A | CY2024 BEFF - | CY2024 BEFF - | March 13, 2024- | 3/21/2024 | 2024-03-04 | 2024-03-05 | N/A | GS Motar Builders | Waiting for Approval of CMP from NCCA (CMP IS ALREADY APPROVED BY NHCP)
GABALDON 2024 | Region IV-A | Gen. Trias City | 107957 | Bacao Elementary School | CITY OF GENERAL TRIAS | 6th | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 4888490 | 1 | N/A | Not Yet Started | 0% | N/A | N/A | Conservation and Restoration | Gabaldon | March 20, 2024 |  |  |  |  | Construction and Trading | Waiting for Approval of CMP from NCCA and NHCP
GABALDON 2024 | Region IV-A | Laguna | 301278 | Upland INHS | NAGCARLAN | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 5800201.57 | 1 | 4325917.97 | Ongoing | 70% | 2025-11-09 | - | of Gabaldon Building | [6 empty] | N/A | Ongoing
GABALDON 2024 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 31535799.71 | 1 | 31485799.71 | Completed | 100% | 3/30/2025 | 4/26/2025 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Open Builders Incorporated
GABALDON 2024 | Region IV-A | Lipa City | 109703 | Tambo ES | LIPA CITY | 6th | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 18284448.8 | 1 | 18234448.8 | Completed | 100% | 3/30/2025 | 2024-05-12 | R4A-2024-008 | R4A-2024-008 | 2024-02-05 | May 9, 2025 | May 23,2024 | 2024-07-08 | 2025-03-04 | gs motar builders/ marakesh enterprises jv
GABALDON 2024 | Region IV-A | Lipa City | 109669 | Teodoro M. Kalaw MS | LIPA CITY | 6th | 1 | 5 | 1 | Conservation and Restoration of Gabaldon School Building | 13347715.85 | 1 | 13297705.45 | Completed | 100% | 1/29/2025 | 11/13/2024 |  |  |  | (Pre-Bid Conference) |  |  |  | gs motar builders/ tpmcs corp jv
GABALDON 2024 | Region IV-A | Lucena City | 109742 | Lucena West I Elementary School | LUCENA CITY (Capital) | 2nd | 1 | 18 | 1 | Conservation and Restoration of Gabaldon School Building | 16591885.38 | 1 | 16540591.57 | Completed | 100% | 5/31/2025 | 1/25/2025 | GAB 2024-RIVA-LIPA CITY-002 | GAB 2024-RIVA-LIPA CITY-002 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | marakesh enterprises | Completed
GABALDON 2024 | Region IV-A | Quezon | 109272 | Claro M. Recto Memorial CS | TIAONG | 2nd | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building -13CL (39.00m x 35.00m) | 16923003.49 | 1 | 16870000 | Completed | 100% | 2/18/2025 | 11/15/2024 | GAB 2024-RIVA-LIPA CITY-003 | GAB 2024-RIVA-LIPA CITY-003 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | GS MOTAR BUILDERS CONSTRUCTION AND TRADING | N/A
GABALDON 2024 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3rd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 9477101.16 | 1 | 9450000 | Completed | 100% | 1/19/2025 | 2025-07-01 | GAB 2024-RIVA-LIPA CITY-001 | GAB 2024-RIVA-LIPA CITY-001 | 2024-06-05 | 5/14/2024 | 5/27/2024 | 2024-10-06 | 2024-02-08 | Botey Construction | N/A
GABALDON 2024 | Region IV-A | San Pablo City | 109763 | San Cristobal Elementary School | SAN PABLO CITY | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6400000 | 1 | N/A | Under Procurement | 0% | N/A | N/A | 2023-LUCENA CITY-005 | 2023-LUCENA CITY-005 | 6/27/2024 | 2024-05-07 | 7/17/2024 | 9/27/2024 | 2024-04-10 | Botey Construction | for approval of CMP
GABALDON 2024 | Region IV-A | Tanauan City | 107782 | Tanauan South Central School | CITY OF TANAUAN | 3rd | 1 | 10 | 1 | Conservation and Restoration of Gabaldon School Building | 17478526.17 | 1 | 17421569.07 | Completed | 100% |  | 2/28/2025 | 2024-01-INFRAEPA | 2024-01-INFRAEPA | 3/27/2024 | 2024-03-04 | 4/15/2024 | 2024-12-07 | 7/24/2024 | N/A | NONE
GABALDON 2024 | Region IV-B | Marinduque | 109952 | Mogpog CS | GASAN | Lone | 1 | 16 | 1 | Conservation and Restoration of Gabaldon School Building (2 bldgs) | 14164230.3 | 1 |  | Under Procurement | 0%
GABALDON 2024 | Region IX | Dapitan City | 125916 | Ilaya Elementary School | DAPITAN CITY | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 5000000 | 1 | 4956744.84 | Ongoing | 80% | 2025-02-06 | - | CY2024-10-12 | CY2024-10-12 | 8/22/2024 | 2024-09-11 | 9/25/2024 | 10/16/2024 | 2025-03-01 | Stars and Stripes Construction | ON-GOING
GABALDON 2024 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | Lone | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 18000000 | 1 | - | Not Yet Started | 0% | - | - | - | - | - | - | - | - | - | - | With RTA waiting for SARO
GABALDON 2024 | Region IX | Zamboanga del Norte | 124588 | Lapayanbaja ES | POLANCO | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building with 16KW Solar PV | 23015000 | 1 | 22999627.62 | Ongoing | 85% | February 09, 2025 | - | 2024-026-CBZN | CB-2024-037 | April 23, 2024 | May 02,2024 | May 15, 2024 | June 25, 2024 | July 07, 2024 | YSL BUILDERS | -
GABALDON 2024 | Region IX | Zamboanga del Norte | 124596 | Sianib ES | POLANCO | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 24015000 | 1 | 23995323.36 | Ongoing | 90% | February 09, 2025 | - | 2024-025-CBZN | CB-2024-036 | April 23, 2024 | May 02,2024 | May 15, 2024 | June 25, 2024 | July 07, 2024 | YSL BUILDERS | -
GABALDON 2024 | Region V | Sorsogon | 114034 | Bulan South CS | BULAN | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 2717489.2 | 1 | 2714939.05 | Ongoing | 85% | 2025-09-09 |  | 24-09-001 | 24-09-001 | 2024-03-09 | 2024-11-09 | 9/23/2024 | 11/13/2024 | 3/14/2025 | 144 CUBITS BUILDERS & SUPPLY
GABALDON 2024 | Region V | Sorsogon | 114263 | Jose G. Alindogan ES | JUBAN | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 17571213.3 | 1 | 17563523.95 | Ongoing | 40% | 2025-09-09 |  | 24-09-001 | 24-09-001 | 2024-03-09 | 2024-11-09 | 9/23/2024 | 11/13/2024 | 3/14/2025 | 144 CUBITS BUILDERS & SUPPLY
GABALDON 2024 | Region V | Tabaco City | 114624 | Tabaco South CES | CITY OF TABACO | 1st | 1 | 20 | 1 | Conservation and Restoration of Gabaldon School Building | 10693357.76 | 1 |  | Under Procurement | 0% |  |  | 2024-10-172 |  | 10/29/2024 | 2024-06-11 | 2024-03-12 | 2024-10-12 |  |  | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | Region VI | Aklan | 114850 | Malay Elementary School | MALAY | 2nd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 8597231.29 | 1 | 8562000 | completed | 100% | 1/20/2025 | 1/20/2025 | DepEd-RO6-D1-2024GABALDON-012-2024 | DepEd-RO6-D1-2024GABALDON-012-2024 | 2024-08-05 | 5/15/2024 | 5/27/2024 | 6/19/2024 | 7/17/2024 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | COMPLETED
GABALDON 2024 | Region VI | Guimaras | 115895 | Igang Elementary School | NUEVA VALENCIA | Lone | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 7762335.08 | 1 | 7707000 | COMPLETED | 100% | 2024-03-12 | 2024-10-10 | Project 04-2024 | Project 04-2024 | 2024-01-03 | 2024-12-03 | 3/26/2024 | 6/25/2024 | 2024-01-07 | RISM BUILDERS AND CONSTRUCTION SERVICES, INC. | completed and turn-over
GABALDON 2024 | Region VI | Himamaylan City | 117076 | Himamaylan Central School | CITY OF HIMAMAYLAN | 5th | 1 | 9 | 1 | Conservation and Restoration of Gabaldon School Building | 13950000 | 1 | 13850000 | Ongoing | 95% | 2025-01-06 |  | IB-sdhc-082024-007 | IB-sdhc-082024-007 | 8/14/2024 | 8/22/2024 | 2024-03-09 | 9/13/2024 | 2025-10-01 | RISM BUILDERS AND CONSTRUCTION SERVICES | for final inspection and punchlisting on June 7, 2025
GABALDON 2024 | Region VI | Iloilo | 116839 | Tigbauan CES | TIGBAUAN | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 13363220.1 | 1 | 13324432.63 | COMPLETED | 100% | 3/13/2025 | 2024-12-12 | BEFF2024-RVI-ILOILO-022-GAB-L1 | BEFF2024-RVI-ILOILO-022-GAB-L1 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 7/15/2024 | EARLY RISER CONSTRUCTION
GABALDON 2024 | Region VI | Iloilo | 116394 | Janiuay Pilot ES | JANIUAY | 3rd | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 8456526.87 | 1 | 8446849.01 | COMPLETED | 100% | 2025-12-01 | 2025-08-04 | BEFF2024-RVI-ILOILO-022-GAB-L2 | BEFF2024-RVI-ILOILO-022-GAB-L2 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 7/15/2024 | EARLY RISER CONSTRUCTION
GABALDON 2024 | Region VI | Iloilo | 116777 | Hugo T. Apelo MES | SARA | 5th | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 3758099.02 | 1 | 3750285.99 | COMPLETED | 100% | 2024-09-12 | 10/29/2024 | BEFF2024-RVI-ILOILO-022-GAB-L3 | BEFF2024-RVI-ILOILO-022-GAB-L3 | 2024-06-03 | 3/21/2024 | 2024-02-04 | 5/17/2024 | 2024-11-07 | ANJUSH BUILDERS
GABALDON 2024 | Region VI | Negros Occidental | 117429 | Valladolid ES | VALLADOLID | 4th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 13287607.81 | 1 | 8258170.51 | Under Procurement | 0% |  |  | 45717 |  | 12/27/2024 | 2025-06-01 | 1/20/2025 | 3/19/2025 |  | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY | Request for the release of Sub-ARO with RTAs was alredy submitted -still waiting from CO to provide us Sub-ARO.
GABALDON 2024 | Region VI | Negros Occidental | 117154 | Luis C. Tembrevilla ES | HINOBA-AN (ASIA) | 6th | 1 | 11 | 1 | Conservation and Restoration of Gabaldon School Building | 16334630.93 | 1 | 10000000 | Under Procurement | 0% |  |  | 45689 |  | 12/27/2024 | 2025-07-01 | 1/20/2025 | 3/19/2025 |  | KEANNE CONSTRUCTION SERVICES | Request for the release of Sub-ARO with RTAs was alredy submitted -still waiting from CO to provide us Sub-ARO.
GABALDON 2024 | Region VII | Cebu | 119566 | Pinamungajan Central School | PINAMUNGAHAN | 3rd | 1 |  | 1 | Conservation and Restoration of Gabaldon School Building | 485257.42 | 1 |  | Not Yet Started | 0% | [9 empty] | MP Sorela Construction | RO is waiting for the release of SARO as payment of the V.O. to MP Sorela Construction declined by DO. Variation order implemented by RO. Several Letters sent by RO to CO requesting for the release of the fund. The project was already 100% completed.
GABALDON 2024 | Region VII | Cebu | 119248 | Tayud ES | CONSOLACION | 6th | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3731085.93 | 1 | 3710147.91 | completed | 100% | 2025-02-13 | 2025-02-12 | CY 2024 BEFF Gabaldon-DepED-R7-Cebu | CY 2024 BEFF Gabaldon-DepED-R7-Cebu | 2024-06-11 | 2024-06-18 | 2024-07-01 | 2024-07-22 | 2024-09-13 | JAJ&L CONSTRUCTION AND ENGINEERING SERVICES
GABALDON 2024 | Region VII | Cebu City | 119874 | City Central ES | CEBU CITY (Capital) | 1st | 1 | 20 | 1 | Conservation and Restoration of Gabaldon School Building | 8310520 | 1 | 6093285.05 | Completed | 100% | 1/27/2025 | 3/13/2025 | Gabaldon 2024 - R VII - Cebu City - 002 | DepED CCD - Contract # 2024 - 11 | 2024-06-06 | 6/14/2024 | 6/26/2024 | 7/24/2024 | 9/23/2024 | JAJ & L CONSTRUCTION AND ENGINEERING SERVICES | Completed with (45 days extension)
GABALDON 2024 | Region VII | Danao City | 119357 | Severo Duterte Memo. ES | DANAO CITY | 5th | 1 |  | 1 | Conservation and Restoration of Gabaldon School Building | 424730.16 | 1 |  | Not Yet Started | 0% | 11/18/2021 |  | 6944754-Lot 8 | 44331 | April 29, 2021 | April 15, 2021 | May 11, 2021 | May 27, 2021 | June 14, 2021 | PB OBIAL CONSTRUCTION | Declined to Procure (with letter submitted thru Regional Director, dated May 31, 2024). RO is also waiting for a response from CO on the downloading of funds for V.O. The project was satisfactorily done by the Contractor. Follow-up letter sent to Usec. Cabral dated Dec. 8, 2024
GABALDON 2024 | Region VII | Dumaguete City | 119938 | North City ES | DUMAGUETE CITY (Capital) | 2nd | 1 | 16 | 1 | Conservation and Restoration of Gabaldon School Building | 10057346.25 | 1 | 6973017 | Ongoing | 93% | 2025-02-03 | N/A | 2024-003 | 2024-003 | 6/20/2024 | 2024-01-07 | 7/16/2024 | 2024-02-08 | 9/27/2024 | Four SG Enterprises | On - Going
GABALDON 2024 | Region VII | Mandaue City | 119998 | Basak ES | MANDAUE CITY | 6th | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6033004.04 | 1 | 5993579.01 | Completed | 100% | 9/20/2024 | 9/20/2024 | 2024GAB01 | 45323 | 2024-12-04 | 4/20/2024 | 2024-02-05 | 2024-07-05 | 6/24/2024 | Golden Hammer Construction and Supply | None
GABALDON 2024 | Region VII | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building (10 Classrooms + 2 Offices) | 36145286.53 | 1 | 35761963.38 | Ongoing | 65% | 12/26/2025 |  | ITB 2024-03-038 | GAB202406026 | 3/27/2024 | 2024-04-04 | 4/16/2024 | 5/15/2024 | 6/24/2024 | TrinityCAD Corporation | with time extension due to erratic weather conditions, processing of cutting permit, and scarcity of wood supply
GABALDON 2024 | Region VII | Siquijor | 501429 | Maria Integrated School | MARIA | Lone | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 5057563.48 | 1 | 4996657.17 | Ongoing | 70% | Jan. 26, 2025 |  | 10743443 | 2024-025 | 2024-11-04 | 4/18/2024 | 4/30/2024 | 2024-05-05 | 2024-01-07 | Nale Construction | with Time Extention. Revised Target Completion March 17, 2025
GABALDON 2024 | Region VII | Tagbilaran City | 302846 | Dr. Cecilio Putong NHS (Bohol NHS) | TAGBILARAN CITY (Capital) | 1st | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building | 24222461.26 | 1 | 24202271.24 | Completed | 100% | 3/25/2025 | 1/30/2025 | 2024-001-Infra | 2024-001-Infra | 2024-11-03 | 3/21/2024 | 2024-05-04 | 2024-10-04 | 6/21/2024 | CJANSEN CONSTRUCTION AND GENERAL MERCHANDISE
GABALDON 2024 | Region VII | Toledo City | 120757 | South City Central School | TOLEDO CITY | 3rd | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 8822869.51 | 1 | 7032361.23 | Completed | 100% | 11/18/2024 | 10/31/2024 | GAB 2022-R VII-TOLEDO-001 | 2024-001 | 2024-05-03 | 3/14/2024 | 3/26/2024 | 2024-03-04 | 2024-08-06 | Anielthone Construction & Supply
GABALDON 2024 | Region VIII | Borongan City | 122387 | San Saturnino Elementary School | CITY OF BORONGAN (Capital) | Lone | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 6331343.3 | 1 | 6326335.72 | COMPLETED | 100% | 11/18/2024 | 11/15/2024 | CY 2024 GABALDON | CY 2024 GABALDON | 2024-11-03 | 3/20/2024 | 2024-02-04 | 2024-08-04 | 7/17/2024 | LEXBUILD CONSTRUCTION | COMPLETED
GABALDON 2024 | Region VIII | Eastern Samar | 122524 | Guiuan East Central School | GUIUAN | Lone | 1 | 5 | 1 | Conservation and Restoration of Gabaldon School Building | 5974124.58 | 1 | 5946102.72 | Ongoing | 70% | 2024-01-11 |  | CY2024-GABALDON-L1 | CY2024-GABALDON-L1 | 2024-03-03 | 2024-11-03 | 3/25/2024 | 2024-10-07 | 7/27/2024 | TUBIGAN BUILDERS
GABALDON 2024 | Region VIII | Leyte | 121004 | Tinag-an Elementary School | ALBUERA | 4th | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 5036203.53 | 1 | 3878143.65 | Ongoing | 75% | 2025-04-02 |  | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-1 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-1 | 2024-03-04 | 4/15/2024 | 4/29/2024 | 6/21/2024 | 2024-01-08 | SAINT JOSPEH CONSTRUCTION | with time extension
GABALDON 2024 | Region VIII | Leyte | 121446 | Matlang Elementary School | ISABEL | 4th | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 4010447.89 | 1 | 3958128.42 | COMPLETED | 100% | 12/30/2024 | 12/30/2024 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-2 | CY 2024 BEFF_Conservation and Restoration of Gabaldon School Building Program-(RVIII)-LEYTE-Lot-2 | 2024-03-04 | 4/15/2024 | 4/29/2024 | 6/21/2024 | 7/26/2024 | FOUR K BUILDERS & CONST. SUPPLIES
GABALDON 2024 | Region VIII | Maasin City | 122177 | Tomas Oppus Pilot School (TOPS) | CITY OF MAASIN (Capital) | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 8601473.61 | 1 | 5962743.44 | Ongoing | 35% | 7/21/2025 | N/A | INFRA-2024-04 | INFRA-2024-04 | 2024-11-07 | 7/19/2024 | 7/31/2024 | 9/25/2024 | 2025-08-01 | VHITS D.G. BUILDERS & ENTERPRISES | Ongoing
GABALDON 2024 | Region X | Cagayan de Oro City | 127963 | Kauswagan Central School | CAGAYAN DE ORO CITY (Capital) | 1st | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 12113951.57 | 1 | 9585902.87 | Completed | 100% | 12/31/2024 | 3/15/2025 | GABALDON 2024- RX - CAGAYAN DE ORO CITY - 001 | 2024-012 | 3/20/2024 | 2024-01-04 | 4/17/2024 | 2024-07-05 | 2024-04-07 | JDE Construction | Subject for Punchlist
GABALDON 2024 | Region X | Camiguin | 126908 | Baylao Elementary School | MAMBAJAO (Capital) | Lone | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3000000 | 1 |  | Ongoing | 50% |  |  | Infra-01-04-2024 |  | 9/23/2024 | 2024-01-10 | 10/14/2024 |  |  | Vinlabz Construction | Ongoing installation of Wall Studs
GABALDON 2024 | Region X | Gingoog City | 128055 | Manuel Lugod Central School | GINGOOG CITY | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 14000000 | 1 | 13900000 | Ongoing | 60% | 3/13/2025 |  | GABALDON 2024- RX - GINGOOG CITY - 001 | GAAAO-2024-MLCS | 6/17/2024 | 6/24/2024 | 2024-03-07 | 7/26/2024 | 2024-04-10 | L & L Construction | Time extension for approval.
GABALDON 2024 | Region X | Misamis Oriental | 127747 | Lagonglong CS | LAGONGLONG | 1st | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 16768109.2 | 1 | 14067930.31 | Ongoing | 30% | 7/17/2025 |  | PB 2024 009-027 | N/A | 7/29/2024 | 2024-07-08 | 8/20/2024 | 2024-10-09 | 2025-08-01 | Minkonstrak Engineering and General Services | Ongoing
GABALDON 2024 | Region XI | Davao City | 129680 | Alambre ES | DAVAO CITY | 3rd | 1 | 4 | 1 | Conservation and Restoration of Gabaldon School Building | 7827466.16 | 1 |  | Ongoing | 85% | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | Region XI | Davao City | 129490 | Baracatan ES | DAVAO CITY | 3rd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 6530565.38 | 1 |  | Ongoing | 85% | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | Region XI | Davao City | 129494 | Catigan ES | DAVAO CITY | 3rd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 6824294.85 | 1 |  | Ongoing | 85% | May 11, 2025 |  | BEFF-004-2024 | Contract #2 s.2025 INF DL-XI | June 28, 2024-July 18,2024 | July 5, 2024 | July 18, 2024 | Sept. 30, 2024 | Jan.10, 2025 | R. FABALE CONST. CORP. | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | Region XI | Davao de Oro | 128263 | Compostela Central Elementary School SPED Center | COMPOSTELA | 1st | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 5250000 | 1 | 4987335.03 | Ongoing | 85% | 4/24/2024 |  | SDD0-013-2024 | SDD0-013-2024 | August 08, 2024 | August 16, 2024 | August 29,2024 | September 30,2024 | December 23,2024 | DQMB CONST. & SUPPLY CORP. | ON GOING WORKS OF PUNCHLIST
GABALDON 2024 | Region XI | Davao de Oro | 128335 | Mabini CES | MABINI (DOÑA ALICIA) | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 6550000 | 1 | 6222512.37 | Ongoing | 85% | 5/24/2024 |  | SDD0-014-2024 | SDD0-014-2024 | August 08, 2024 | August 16, 2024 | August 29,2024 | September 30,2024 | December 23,2024 | DQMB CONST. & SUPPLY CORP. | ON GOING PAINTING WORKS
GABALDON 2024 | Region XI | Davao del Sur | 128954 | Malalag CES | Malalag | 1st | 1 | 12 | 1 | Conservation and Restoration of Gabaldon School Building | 17321825.17 | 1 |  | Not Yet Started | 0% | October 22, 2025 |  | DS-GABALDON-2024-F |  |  | June 26, 2024 | July 08, 2024 | August 09, 2024 |  | DIGOS CONSTRAK CORPORATION (DCC) | The Contractor refused to accept the contract due to Non-Issuance of Tax Clearance from the BIR. Re-Bid
GABALDON 2024 | Region XI | Davao Occidental | 128881 | Jose Abad Santos Central Elementary School | JOSE ABAD SANTOS (TRINIDAD) | Lone | 1 | 13 | 1 | Conservation and Restoration of Gabaldon School Building | 13970092.52 | 1 | 13960510.52 | Completed | 100% | January 13, 2025 | December 19, 2024 | ITB W-01-2024 | contract no. 2024-006 | April 15, 2024- April 29, 2024 | April 23, 2024 | April 29, 2024 | May 27, 2024 | July 17, 2024 | DIGOS CONSTRAK CORPORATION (DCC) | completed ahead of time
GABALDON 2024 | Region XI | Davao Oriental | 129177 | BanayBanay CES | Banaybanay | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 2224912.53 | 1 | 1656888.85 | Completed | 100% | 12/27/2024 | February 24, 2025 | GS-2024-078. | 2024-.24 | 2024-06-06 | 6/13/2024 | 6/25/2024 | 2024-07-09 | 8/29/2024 | MANIMBO CONST.
GABALDON 2024 | Region XI | Davao Oriental | 129329 | Comara T. Manuel Central Elementary School SPED Center | LUPON | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 2109850.67 | 1 | 1710636.55 | Completed | 100% | 12/27/2024 | February 24, 2025 | GS-2024-077 | 2024-025 | 2024-06-06 | 6/13/2024 | 6/25/2024 | 2024-07-09 | 8/29/2024 | MANIMBO CONST.
GABALDON 2024 | Region XII | South Cotabato | 130708 | Norala Central Elementary School | NORALA | 2nd | 1 | 7 | 1 | Conservation and Restoration of Gabaldon School Building | 17337379.73 | 1 |  | Ongoing | 4.33%