## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF BUILDINGS | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
GABALDON 2020 | CARAGA | Surigao del Sur | 132786 | Barcelona Central Elementary School | Lingig | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 3791557.1457 | 1 | 2850645.4 | Completed | 1 | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2020 | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2 | 1 | 1 | 1 | Rehabilitation of Gabaldon Building | 4262264.1005 | 1 | 3203616.66 | Completed | 1 | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2020 | CARAGA | Surigao del Sur | 132796 | Lingig Central Elementary School | Lingig | 2 |  | 1 | 1 | Rehabilitation of Gabaldon Building | 3727184.6834 | 1 | 2802461.99 | Completed | 1 | [9 empty] | BN BUILDERS | Notice of Award
GABALDON 2021 | CARAGA | Cabadbaran City | 131574 | Calamba ES | CITY OF CABADBARAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 2840561 | 1 |  | COMPLETED | 1
GABALDON 2021 | CARAGA | Cabadbaran City | 500312 | North Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 2 | 1 | Rehabilitation of Gabaldon Building | 1878693 | 1 |  | COMPLETED | 1
GABALDON 2021 | CARAGA | Cabadbaran City | 131580 | South Cabadbaran CES | CITY OF CABADBARAN | 2 | 1 | 9 | 1 | Rehabilitation of Gabaldon Building | 9363712 | 1 |  | COMPLETED | 1
GABALDON 2023 | CARAGA | Agusan del Norte | 131468 | Las Nieves CES | LAS NIEVES | 1 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 2307345.08 | 1 | 2292004.81 | Completed | 1 | 2023-11-13 | 2023-11-20 | GAB-2023-CARAGA-AGUSAN DEL ORTE-003 | GAB-2023-CARAGA-AGUSAN DEL ORTE-003 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | J-R3 Const. & Supply | with time extension
GABALDON 2023 | CARAGA | Agusan del Norte | 131421 | Gosoon ES | CARMEN | 2 | 1 | 1 | 1 | Restoration & Conservation of Gabaldon Building | 3608213.56 | 1 | 2865569.03 | COMPLETED | 1 | 2023-12-04 |  | GAB-2023-CARAGA-AGUSAN DEL ORTE-002 | GAB-2023-CARAGA-AGUSAN DEL ORTE-002 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | ILMAR CONST | with time extension due to weather condition and proposed V.O
GABALDON 2023 | CARAGA | Agusan del Norte | 131491 | Amontay ES | NASIPIT | 2 | 1 | 2 | 1 | Restoration & Conservation of Gabaldon Building | 4368940.25 | 1 | 3308793.92 | COMPLETED | 1 | 2023-12-04 |  | GAB-2023-CARAGA-AGUSAN DEL ORTE-001 | GAB-2023-CARAGA-AGUSAN DEL ORTE-001 | 2023-05-11 | 2023-05-18 | ######### | ######### | ######### | BN BUILDERS | with time extension due to weather condition and proposed V.O
GABALDON 2023 | CARAGA | Surigao del Sur | 132930 | Anahao Bag-o Elementary School | TAGO | 1 | 1 | 3 | 1 | Restoration & Conservation of Gabaldon Building | 4078781.46 | 1 |  | Completed | 1 | 2024-06-26 | 2024-06-24 | GAB 2023 - R XIII - SURIGAO DEL SUR - 001 | 2023-012 |  |  |  |  | 2023-12-29 | CYL CONSTRUCTION & SUPPLY | with Time Extension due to Extra Work Order
GABALDON 2023 | CARAGA | Surigao del Sur | 132933 | Badong Elementary School | TAGO | 1 | 1 | 4 | 1 | Restoration & Conservation of Gabaldon Building | 4670841.77 | 1 |  | Completed | 1 | 2024-06-26 | 2024-06-24 | GAB 2023 - R XIII - SURIGAO DEL SUR - 002 | 2023-009 |  |  |  |  | 2023-12-29 | CYL CONSTRUCTION & SUPPLY | with Time Extension due to Extra Work Order
GABALDON 2024 | CARAGA | Agusan del Norte | 131532 | LUIS B. AZURA SR. MEMORIAL ES | RTR | 2nd | 1 | 2 | 1 | Conservation and Restoration of Gabaldon School Building | 4162296.96 | 1 | 4154361.34 | Ongoing | 0.48 | June 8, 2025 | - | GABALDON 2023 - AGUSAN DEL NORTE - 001 | GABALDON 2023 - AGUSAN DEL NORTE - 001 |  |  | September 6, 2024 | December 20, 2024 | December 23, 2024 | BN BUILDERS & CONST. SUPPLIES INC.
GABALDON 2024 | CARAGA | Butuan City | 132040 | Taligaman ES | BUTUAN CITY (Capital) | 1st | 1 | 8 | 1 | Conservation and Restoration of Gabaldon School Building | 24000000 | 1 | 23984589.1 | ongoing | 0.95 | June 30, 2025 | - | GABALDON 2024 - CARAGA - BUTUAN CITY - 001 | GABALDON 2024 - CARAGA - BUTUAN CITY - 001 | April 30, 2024 | May 8, 2024 | May 20, 2024 | May 28, 2024 | September 18, 2024 | RELY CONSTRUCTION & SUPPLY INC. | Delayed due to the delayed delivery of wood materials from far flung source of the materials
GABALDON 2024 | CARAGA | Cabadbaran City | 131520 | Del Pilar CES | CITY OF CABADBARAN | 2nd | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 4415934.04 | 1 | 4400505.74 | Ongoing | 0.7 |  | - | GABALDON 2024 - CARAGA |  |  |  |  | 12/20/2024 | 2024-12-12 | J-R3 CONSTRUCTION & SUPPLY | Submitted RTA to Central Office; awaiting subaro release
GABALDON 2024 | CARAGA | Surigao City | 132272 | Surigao City Pilot Sch. | SURIGAO CITY (Capital) | 2nd | 1 | 14 | 1 | Conservation and Restoration of Gabaldon School Building | 5419736.68 | 1 | 3404082.78 | Ongoing | 0.75 | July 13, 2025 | - | GABALDON 2024 - CARAGA - SURIGAO CITY - 001 | FY-2024-INF-026 | October 24, 2024 | October 21, 2024 | November 13, 2024 | November 13, 2024 | March 10, 2025 | WINDFALL CONSTRUCTION
GABALDON 2024 | CARAGA | Surigao del Sur | 132768 | Anibongan Elementary School | LIANGA | 1st | 1 | 3 | 1 | Conservation and Restoration of Gabaldon School Building | 3767382.84 | 1 | 2536593.52 | Completed | 1 | June 01, 2025 | May 06, 2025 | GAB 2024 - R XIII - SURIGAO DEL SUR - 001 | 005 - 2024 | August 30, 2024 | September 05, 2024 | September 17, 2024 | October 14, 2024 | January 03, 2025 | CYL CONSTRUCTION & SUPPLY | COMPLETED
GABALDON 2024 | CARAGA | Tandag City | 132979 | Tandag Pilot Elementary School | CITY OF TANDAG (Capital) | 1st | 1 | 6 | 1 | Conservation and Restoration of Gabaldon School Building | 3907026.54 | 1 | 2466129.4 | Not Yet Started | 0 |  |  | EPA-2024-07-159 | EPA-2024-07-159 | July 24, 2024 | August 1, 2024 | August 13, 2024 |  |  | cYL CONSTRUCTION & SUPPLY | CONDUCTED EPA AND WAITING FOR THE SUBARO

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%