## Sheet1
Category | Region | Division | School ID | School Name | Municipality | LD | No of Sites | SCOPE OF WORK | Batch | Project Allocation | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | WITH TRANSFOPMER (Y/N) | CATEGORY 2 | Status as of July 11, 2025
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180505 | Tugas ES | CITY OF HIMAMAYLAN | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 1116889.07 |  | COMPLETED | 1 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117202 | Canlupa PS | ISABELA | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 263400 | 265174.3 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117258 | Binata-an ES | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 536631.35 | 698921.58 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117262 | E. Basa PS | MOISES PADILLA (MAGALLON) | 5 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 699806.92 | 535718.22 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C3 | 17-12-111 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116971 | Macapula ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 629037.28 | 628377.12 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116973 | Maloy-a Elementary School | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 669838 | 667903.43 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116977 | Payong PS | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 758672.56 | 757285.55 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116979 | Sibucao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 896856.69 | 896003.99 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 116983 | Talimagao ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 349163.74 | 348928.02 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C2 | 17-12-110 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117014 | Taya-o ES | CAUAYAN | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 549601.5 | 548807.25 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C1 | 17-12-109 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180518 | Aguinaldo Primary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 723035.78 | 922663.56 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117143 | Bonifacio ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 923210.17 | 722527.62 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C7 | 17-12-117 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117145 | Cabanbanan PS | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 835486.41 | 834624.64 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117146 | Cemeco ES | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 970538.94 | 969541.76 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 180508 | MAATOP ELEMENTARY SCHOOL | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 958158.87 | 956847.73 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C6 | 17-12-114 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Occidental | 117155 | Manlawa-an Elementary School | HINOBA-AN (ASIA) | 6 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 786342.28 | 784935.17 | COMPLETED | 1 |  |  | R6-D13-2017BEFF-E-C5 | 17-12-113 |  |  | 2017-12-23 | 2017-12-29 | 2018-02-22 | PAR Builders, Electrical and Construction Supply Corp. |  |  | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 189530 | Alagasihan PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 39782.2 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120342 | Barang-barang PS | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 41069.35 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120350 | Campo-aling ES | MABINAY | 2 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 184157.53 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 120523 | Sto. Tomas ES | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 71674.73 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Negros Oriental | 189521 | Tubod PS | SANTA CATALINA | 3 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 52592.75 |  | REVERTED | 0 | [12 empty] | ENERGIZATION
ELECTRIFICATION 2017 | NIR | Siquijor | 190008 | Cantugbas PS | MARIA | 0 | 1 | Electrification of Un-Energized Schools On-Grid | Batch 1 | 75845.97 | 75742.97 | COMPLETED | 1 | Dec. 30, 2017 |  |  |  | Oct. 31, 2017 |  | Nov. 6, 2017 | Nov. 9, 2017 | Dec. 15, 2017 | Vanzdarryl Construction Design & Consultancy |  |  | ENERGIZATION
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302669 | Negros Occidental HS | BACOLOD CITY (Capital) | 0 | 1 | UPGRADING | 1 | 5285721.3 | 4974653.02 | COMPLETED | 1 |  |  | 5460136 | 18-09-013 | July 3, 2018 | July 11, 2018 | August 20, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302652 | Inocencio V. Ferrer SOF (TASOF) (under the Reg'l Office) | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3764775.05 | 3721032.46 | COMPLETED | 1 |  |  | 5460154 | 18-09-014 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302678 | Rafael B. Lacson NHS | CITY OF TALISAY | 3 | 1 | UPGRADING | 1 | 3817604.51 | 3788330.6 | COMPLETED | 1 |  |  | 5605695 | 18-10-015 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302695 | Victorias National High School | CITY OF VICTORIAS | 3 | 1 | UPGRADING | 1 | 5241938.17 | 5205258.47 | COMPLETED | 1 |  |  | 5605347 | 18-10-014 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302609 | Cansilayan NHS | MURCIA | 3 | 1 | UPGRADING | 1 | 1274910.45 | 1249959.61 | COMPLETED | 1 |  |  | 5463534 | 18-09-017 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302670 | Murcia National High School | MURCIA | 3 | 1 | UPGRADING | 1 | 3382586.69 | 3346741.14 | COMPLETED | 1 |  |  | 5460097 | 18-09-012 | July 3, 2018 | July 11, 2018 | July 23, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302677 | Pontevedra NHS | PONTEVEDRA | 4 | 1 | UPGRADING | 1 | 3817604.51 | 3780045.51 | COMPLETED | 1 |  |  | 5463520 | 18-09-016 | July 4, 2018 | July 12, 2018 | July 24, 2018 | September 10, 2018 | September 21, 2018 | Romber Construction and General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116882 | Binadlan ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116875 | Nabu-ac ES | BINALBAGAN | 5 | 1 | SOLAR PANEL | 1 | 473564.08 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117087 | Tiqui ES | CITY OF HIMAMAYLAN | 5 | 1 | SOLAR PANEL | 1 | 614377.15 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302651 | Hinigaran NHS | HINIGARAN | 5 | 1 | UPGRADING | 1 | 5608104.57 | 5180471.84 | COMPLETED | 1 |  |  | 5460162 | 18-09-015 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302668 | Negros Occ. NAISHI ( under the Reg'l Office) | HINIGARAN | 5 | 1 | UPGRADING | 1 | 3745342.73 | 3461829.73 | COMPLETED | 1 |  |  | 5460063 | 18-09-011 | July 3, 2018 | July 11, 2018 | August 2, 2018 | September 10, 2018 | September 21, 2018 | TMTC Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302653 | Isabela National High School | ISABELA | 5 | 1 | UPGRADING | 1 | 2814054.98 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117256 | Agogolo ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117259 | Cuyaoyao ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 881548.26 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117270 | Nacurohan ES | MOISES PADILLA (MAGALLON) | 5 | 1 | SOLAR PANEL | 1 | 1287247.06 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 116967 | Jerusalem ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 612976.08 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117009 | Pinamay-an ES | CAUAYAN | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 180521 | Dung-I ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1079342.74 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 302632 | GIL MONTILLA NATIONAL HIGH SCHOOL | CITY OF SIPALAY | 6 | 1 | UPGRADING | 1 | 4406315.1 | 4372766.4 | COMPLETED | 1 |  |  | 5605736 | 18-10-016 | September 4, 2018 | September 12, 2018 | September 24, 2018 | October 15, 2018 | November 27, 2018 | LJPM Builders and Construction Supply |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117359 | Hda. Maricalum ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 875895.2 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Occidental | 117378 | Patag Magbanua ES | CITY OF SIPALAY | 6 | 1 | SOLAR PANEL | 1 | 1491653.57 |  | COMPLETED | 1 | [11 empty] | N | SOLAR
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312962 | Ayungon NHS - Carol-an Extension | AYUNGON | 1 | 1 | UPGRADING | 1 | 586439.48 | 580894.29 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312949 | Ayungon Science High School | AYUNGON | 1 | 1 | UPGRADING | 1 | 484435.16 | 479852.65 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303277 | Mabato Provincial Community HS | AYUNGON | 1 | 1 | UPGRADING | 1 | 627304.52 | 621371.36 | terminated | 0.5 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303276 | Tambo National High School | AYUNGON | 1 | 1 | UPGRADING | 2 | 590808.68 | 587371.98 | terminated | 0.32 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312917 | Cabcaban CHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 616259.07 | 610118.41 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303229 | Demetrio Alviola NHS - Nalundan Annex | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 1 | 457294.38 | 452742 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303228 | Demetrio L. Alviola NHS | BINDOY (PAYABON) | 1 | 1 | UPGRADING | 2 | 1125370.28 | 1119476.6 | terminated | 0.34 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303251 | Manjuyod National High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 1027398.05 | 1009106.87 | COMPLETED | 1 | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312961 | Manjuyod Science High School | MANJUYOD | 1 | 1 | UPGRADING | 1 | 466436.24 | 461791.5 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312902 | Sampiniton Provincial Community HS | MANJUYOD | 1 | 1 | UPGRADING | 1 | 596480.44 | 588081.49 | COMPLETED | 1 | 2018-09-29 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-13 | MAQUESERG Contruction & Gen. Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303255 | Negros Oriental High School | DUMAGUETE CITY (Capital) | 2 | 1 | UPGRADING | 2 | 643928.75 | 634357.53 | terminated | 0.45 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303211 | Bagtic National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659054.43 | 652943.57 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303245 | Barras Annex National High School | MABINAY | 2 | 1 | UPGRADING | 1 | 577903.93 | 571012.457 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303247 | Benedicto P. Tirambulo Mem. National High School | MABINAY | 2 | 1 | UPGRADING | 2 | 637792.52 | 640485.86 | terminated | 0.47 | 2018-09-26 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-18 | SM & MST CONSTRUCTION | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312924 | Campanun-an Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 576820.9 | 570934.14 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312923 | Canggohob HS | MABINAY | 2 | 1 | UPGRADING | 1 | 479603.42 | 475162.71 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303246 | Dahile PCHS | MABINAY | 2 | 1 | UPGRADING | 1 | 605633.91 | 599603.8 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312951 | Mabinay Science High School | MABINAY | 2 | 1 | UPGRADING | 1 | 623832.57 | 616712.597 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312967 | Manlingay High School | MABINAY | 2 | 1 | UPGRADING | 1 | 471654.73 | 466289.46 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312959 | Mayaposi Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 631634.17 | 624474.947 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303260 | Pantao NHS | MABINAY | 2 | 1 | UPGRADING | 1 | 663993.05 | 657672.6 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303248 | Tara Provincial Community High School | MABINAY | 2 | 1 | UPGRADING | 1 | 659889.99 | 653772.57 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303278 | Crisostomo O. Retes NHS (Tampi NHS) | SAN JOSE | 2 | 1 | UPGRADING | 1 | 769006.9 | 759164.24 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303267 | Ong Che Tee - Bacong HS | BACONG | 3 | 1 | UPGRADING | 1 | 566903.28 | 560064.537 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303266 | San Miguel NHS | BACONG | 3 | 1 | UPGRADING | 1 | 778525.78 | 768635.76 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental |  | Antonio B. Alejado MHS (Campus II) | DAUIN | 3 | 1 | UPGRADING | 2 | 516957.6 | 514088.84 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303226 | Antonio B. Alejado MHS (Mag-aso HS) | DAUIN | 3 | 1 | UPGRADING | 2 | 502304.6 | 499512.55 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303224 | Apolinar B. Macias MHS (Casile NHS) | DAUIN | 3 | 1 | UPGRADING | 1 | 674191.81 | 666821.297 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303225 | Dauin NHS | DAUIN | 3 | 1 | UPGRADING | 1 | 694285.21 | 686814.167 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312921 | Froilan A. Alanano MHS | DAUIN | 3 | 1 | UPGRADING | 1 | 541118.53 | 534418.067 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312919 | Malongcay Dacu HS | DAUIN | 3 | 1 | UPGRADING | 1 | 618741.84 | 611657.187 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303206 | Avocado Community High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 549572.35 | 544576 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303250 | Casiano Z. Napigkit NHS (Manalongon NHS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 755011.31 | 745225.04 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312929 | Cawitan High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 633408.36 | 599043.49 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312932 | Eligio T. Monte De Ramos HS (Milagrosa HS) | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 642188.83 | 638347.21 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312933 | Kakha High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 569707.8 | 566218.9 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312936 | Nagbalaye HS | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 661279.82 | 655171.5 | terminated | 0.27 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312934 | San Miguel High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 685131.65 | 675674.96 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312935 | Sta. Catalina Science High School | SANTA CATALINA | 3 | 1 | UPGRADING | 1 | 682615.65 | 678509.1 | terminated | 0.35 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312937 | Aurelia G. Merecido Memorial High School (Cabangahan HS) | SIATON | 3 | 1 | UPGRADING | 2 | 563035.84 | 559881.45 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303253 | Maloh PCHS | SIATON | 3 | 1 | UPGRADING | 2 | 698194.63 | 693171.23 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303252 | Maria Macahig National High School | SIATON | 3 | 1 | UPGRADING | 1 | 748699.97 | 740620.75 | terminated | 0.16 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312942 | Sumaliring HS [Inalad HS] | SIATON | 3 | 1 | UPGRADING | 1 | 664886.16 | 657899.52 | terminated | 0.92 | 2018-09-22 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-05 | SM & MST Construction | Terminated |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312908 | Balugo National High School | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 773368.09 | 763493.11 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303291 | Valencia National High School (Valencia Tech. Sch.) | VALENCIA (LUZURRIAGA) | 3 | 1 | UPGRADING | 1 | 891964.53 | 881506.89 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 303249 | Santiago Delmo MHS (Maluay HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | 2 | 855825.17 | 850910.43 | COMPLETED | 1 | 2018-09-19 |  |  |  | 2018-04-21 | 2018-04-27 | 2018-05-15 | 2018-05-18 | 2018-06-08 | TRINITY CONSTRUCTION AND DEVELOPMENT |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Negros Oriental | 312947 | Zamboanguita Science HS | ZAMBOANGUITA | 3 | 1 | UPGRADING | 1 | 651972.91 | 644724.747 | COMPLETED | 1 | 2018-09-18 |  |  |  | 2018-03-07 | 2018-03-15 | 2018-03-27 | 2018-04-23 | 2018-06-04 | RISM Builders and Construction Services, Inc. |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303297 | Enrique Villanueva National High School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | 1 | 2787612.5 | 2338366.12 | terminated | 0.55 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303303 | Basac National High School | LARENA | 0 | 1 | UPGRADING | 1 | 5937774.35 | 5314986.57 | terminated | 0.45 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303293 | Campalanas National High School | LAZI | 0 | 1 | UPGRADING | 1 | 2636170.21 | 2467591.87 | terminated | 0.75 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303306 | DepED-Lazi National Agricultural School | LAZI | 0 | 1 | UPGRADING | 1 | 3700754.43 | 3399753.16 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303295 | Leon Parami High School | LAZI | 0 | 1 | UPGRADING | 1 | 5722840.8 | 5216947.16 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 120669 | Candaping Elementary School | MARIA | 0 | 1 | UPGRADING | 1 | 2800298.26 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303305 | Catulayan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 2955591.79 | 2788223.92 | terminated | 0.65 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303300 | Tambisan National High School | SAN JUAN | 0 | 1 | UPGRADING | 1 | 3067762.82 | 2795296.97 | terminated | 0.8 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303302 | Banban National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 2657032.83 | 2608113.44 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 120694 | Cang-alwang Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 |  | REVERTED | 0 | [12 empty] | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303296 | Cang-alwang National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1677180.96 | 1352254.37 | REVERTED | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise |  |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303298 | San Antonio National High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 8550699.35 | 8162560.7 | terminated | 0.8 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2018 | NIR | Siquijor | 303301 | Siquijor Provincial Science High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | 1 | 1606427.72 | 1353112.32 | terminated | 0.9 | 2018-08-22 |  |  |  | Feb. 27 - Mar. 19, 2018 | 2018-03-06 | 2018-03-20 | 2018-03-23 | 2018-05-17 | Maqueserg Construction & General Merchandise | TERMINATED |  | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 343897 | SHS in Calatrava | CALATRAVA | 1 | 1 | UPGRADING | Batch 1 | 2150211.82 | 1731414 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302693 | Toboso NHS | TOBOSO | 2 | 1 | UPGRADING | Batch 1 | 1780753.92 | 2370390.96 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302656 | La Castellana NHS | LA CASTELLANA | 5 | 1 | UPGRADING | Batch 1 | 1708168.21 | 1697812.15 | COMPLETED | 1 | 2019-12-27 | [6 empty] | 2019-08-19 | 2019-08-19 | TMTC Construction and Supply |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Occidental | 302606 | Caningay NHS | CANDONI | 6 | 1 | UPGRADING | Batch 1 | 2535306.24 | 1432540 | COMPLETED | 1 | 2020-01-31 | [6 empty] | 2019-08-02 | 2019-09-23 | Romber Construction and General Merchandise |  | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 |  | UPGRADING | Batch 3 | 922397.2 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303235 | Jimalalud National High School | JIMALALUD | 1 | 1 | UPGRADING |  | 3988592.91 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303243 | La Libertad Technical-Vocational School | LA LIBERTAD | 1 | 1 | UPGRADING |  | 1863791.25 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303289 | Tayasan National High School (Main) | TAYASAN | 1 | 1 | UPGRADING | Batch 3 | 694554.96 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312950 | Tayasan National Science High School | TAYASAN | 1 |  | UPGRADING | Batch 3 | 604060.01 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303208 | Jantianon National High School | AMLAN (AYUQUITAN) | 2 |  | UPGRADING | Batch 3 | 627950.94 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303234 | Inapoy High School | MABINAY | 2 |  | UPGRADING | Batch 3 | 675652.01 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303244 | Mabinay National High School | MABINAY | 2 | 1 | UPGRADING | Batch 3 | 910437.58 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 |  | UPGRADING | Batch 3 | 577473.63 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312901 | Maningcao National High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 551832.88 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312944 | Sibulan Science High School | SIBULAN | 2 |  | UPGRADING | Batch 3 | 406268.6 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312918 | Buntod High School | BACONG | 3 |  | UPGRADING | Batch 3 | 639294.81 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312920 | Dauin Science High School | DAUIN | 3 |  | UPGRADING | Batch 3 | 628569.22 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303263 | Don Emilio Macias MNHS (San Francisco NHS) | SANTA CATALINA | 3 | 1 | UPGRADING |  | 1728758.38 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303264 | Obat High School | SANTA CATALINA | 3 |  | UPGRADING | Batch 3 | 606756.89 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303265 | Sta. Catalina National High School | SANTA CATALINA | 3 | 1 | UPGRADING | Batch 3 | 900675.34 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312913 | Candugay HS (Siaton NHS Annex) | SIATON | 3 |  | UPGRADING | Batch 3 | 693170.34 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312970 | Caticugan HS | SIATON | 3 |  | UPGRADING | Batch 3 | 597167.29 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312941 | Giligaon High School | SIATON | 3 |  | UPGRADING | Batch 3 | 622658.35 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 |  | UPGRADING | Batch 3 | 608533.6 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312938 | Paciente Cesar G. Cabrera HS (Napacao HS) | SIATON | 3 | 1 | UPGRADING | Batch 3 | 712287.99 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303268 | Siaton NHS | SIATON | 3 | 1 | UPGRADING |  | 1923841.45 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 312914 | Siaton Science HS | SIATON | 3 |  | UPGRADING | Batch 3 | 558999.52 |  | COMPLETED | 1 | [11 empty] | N | UPGRADING
ELECTRIFICATION 2019 | NIR | Negros Oriental | 303236 | Jose Marie Locsin MHS (Mayabon HS) | ZAMBOANGUITA | 3 | 1 | UPGRADING | Batch 3 | 666385.77 |  | COMPLETED | 1 | [11 empty] | Y | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120658 | Enrique Villanueva Central Elementary School | ENRIQUE VILLANUEVA | 0 | 1 | UPGRADING | Batch 3 | 291882.27 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 500232 | Cabulihan Integrated School ( Junior & Senior HS) | LARENA | 0 | 1 | UPGRADING |  | 142341.17 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120659 | Larena Central Elementary School | LARENA | 0 | 1 | UPGRADING |  | 422610.72 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120675 | Kimba Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 228294.34 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120676 | Kinamandagan Elementary School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 286904.23 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303294 | Kinamandagan High School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 250257.68 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120677 | Lazi Central School | LAZI | 0 | 1 | UPGRADING | Batch 3 | 372866.19 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303304 | Candaping National High School | MARIA | 0 | 1 | UPGRADING |  | 2389150.46 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120705 | San Juan Central School | SAN JUAN | 0 | 1 | UPGRADING |  | 532602.64 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120703 | Ponong Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 224400.12 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 303299 | Ponong High School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING | Batch 3 | 234567.49 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2019 | NIR | Siquijor | 120706 | Siquijor Central Elementary School | SIQUIJOR (Capital) | 0 | 1 | UPGRADING |  | 268142.84 |  | COMPLETED | 1 | [12 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302603 | Calatrava NHS | CALATRAVA | 1 | 1 |  |  | 5349237.01 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-005 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302624 | ENRIQUETA MONTILLA DE ESTEBAN MEMORIAL HIGH SCHOOL | PULUPANDAN | 4 | 1 |  |  | 6176278.18 | 6140194.07 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-006 | 20-09-007 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply |  |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302683 | San Enrique NHS | SAN ENRIQUE | 4 | 1 |  |  | 4601842.13 |  | COMPLETED | 1 |  |  | Elec2020-R6-Negros Occidental-007 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Occidental | 302600 | Bilbao-Uybico NHS | HINOBA-AN (ASIA) | 6 | 1 |  |  | 8670357.39 | 3296807.84 | COMPLETED | 1 | 2020-12-30 |  | Elec2020-R6-Negros Occidental-004 | 20-09-006 | 2019-12-27 | 2020-01-03 | 2020-01-15 | 2020-09-17 | 2020-09-21 | JPEG Construction and Supply | Energized already on OCT |  | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 303210 | Ayungon NHS | AYUNGON | 1 | 1 |  |  | 3171684.86 |  | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-024 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 312906 | San Jose Provincial High School | SAN JOSE | 2 | 1 |  |  | 721415.76 |  | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-017 | [9 empty] | UPGRADING
ELECTRIFICATION 2020 | NIR | Negros Oriental | 312939 | Mantiquil Masaligan High School | SIATON | 3 | 1 |  |  | 850816.56 | 764758.06 | COMPLETED | 1 |  |  | Elec2020-RVII-NEGROSORIENTAL-013 | [5 empty] | 2021-09-02 | Tribata Construction and Development |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Negros Occidental | 302694 | Valladolid NHS | VALLADOLID | 4th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3233807.07 | 3223059.63 | COMPLETED | 1 | 2025-02-02 | 2025-04-17 | 23-11-33 | 24-09-002 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Negros Occidental | 302608 | Quirico G. Manzano NHS | CANDONI | 6th | 1 | Upgrading of Electrical System (Overhead System) | 1 | 3416277.7 | 3394508.88 | COMPLETED | 1 | 2025-02-02 | 2025-04-02 | 23-11-30 | 24-08-001 | 2023-11-20 | 2023-11-27 | 2023-12-12 | 2024-08-29 | 2024-09-20 | PAR BUILDERS, ELECTRICAL AND CONSTRUCTION SUPPLY CORP. |  |  | UPGRADING
ELECTRIFICATION 2024 | NIR | Siquijor | 120655 | Basac ES | Larena | Lone | 1 | Upgrading of Electrical System (Overhead System) | 1 | 2497039.92 | 2068253.96 | COMPLETED | 1 | 2024-08-21 |  | 10336674 | 2023-90 | 2023-11-20 | 2023-11-28 | 2023-12-11 | 2023-12-12 | 2024-05-21 | Global Power Equipment Marketing Corporation | for approval from local cooperative |  | UPGRADING

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%