## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2022 | NIR | Negros Occidental | 116901 | Calatrava I Central School | CALATRAVA | 1 | 1 | 1 | REPAIR/ REHABILITATION | 518534.72 | 1 | 514321.31 | Completed | 1 | 2023-03-15 | 2023-01-23 | 22-06-57 | 22-12-002 | 2022-07-09 |  | 2022-06-15 | Sept. 8, 2022 | Dec.5, 2022 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY
QRF 2022 | NIR | Negros Occidental | 117418 | Toboso CS | TOBOSO | 1 | 1 | 5 | REPAIR/ REHABILITATION | 8089258.7 | 1 | 5297304.81 | Completed | 1 | 2023-04-09 |  | 22-05-20 | 22-10-003 | 2022-05-25 | 2022-06-02 | 2022-06-14 | 2022-08-09 | 2022-11-10 | TACOLOD ENTERPRISES INC. | subject for final inspection
QRF 2022 | NIR | Negros Occidental | 116945 | Candoni CES | CANDONI | 6 | 1 | 10 | REPAIR/ REHABILITATION | 5967014.47 | 1 | 3500000 | completed | 1 | 2023-05-08 |  | 22-07-24 | 22-10-004 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 18, 2022 | ############# | TACOLOD ENTERPRISES INC. | resumed
QRF 2022 | NIR | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6 |  | 2 | NEW CONSTRUCTION | 7130281.67 | 1 | 5399595.7 | Completed | 1 | 2023-04-22 | 2023-06-14 | 22-07-05 | 22-10-005 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 15, 2022 | ############# | EVERACTIVE CONSTRUCTION AND ENGINEERING SERVICES
QRF 2022 | NIR | Negros Occidental | 117003 | Inayauan CES | CAUAYAN | 6 | 1 | 10 | REPAIR/ REHABILITATION | 4031169.304 | 1 | 2768808.34 | Completed | 1 | 2023-02-22 | 2023-02-08 | 22-07-23 | 22-10-006 | 2022-07-04 | 2022-07-12 | 2022-07-25 | Sept. 13, 2022 | 2022-11-11 | CGGFR CONSTRUCTION AND CONSTRUCTION SUPPLY
QRF 2022 | NIR | Negros Oriental | 120171 | Bindoy Central Elementary School | BINDOY (PAYABON) | 1 | 1 | 2 | REPAIR/ REHABILITATION | 6064404.0823 | 1 | 4807442.21 | completed | 1 | 2023-02-04 |  | ITB 2022-04-023 | QRF202209011 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-26 | TRIBATA CONSTRUCTION AND DEVELOPMENT
QRF 2022 | NIR | Negros Oriental | 120320 | La Libertad CES | LA LIBERTAD | 1 | 1 | 11 | REPAIR/ REHABILITATION | 11136631.2814 | 1 | 11129033.97 | completed | 1 | 2023-03-06 |  | ITB 2022-04-024 | QRF202209012 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP.
QRF 2022 | NIR | Negros Oriental | 120604 | Tayasan CES | TAYASAN | 1 | 1 | 24 | REPAIR/ REHABILITATION | 9524722.2311 | 1 | 9519067.28 | completed | 1 | 2023-03-06 |  | ITB 2022-04-026 | QRF202209014 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP.
QRF 2022 | NIR | Negros Oriental | 120366 | Mabinay Central School | MABINAY | 2 | 1 | 8 | REPAIR/ REHABILITATION | 4478136.1502 | 1 | 3627000 | completed | 1 | 2023-02-04 |  | ITB 2022-04-025 | QRF202209013 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-17 | 2022-09-26 | PAR BUILDERS ELECTRICAL & CONSTRUCTION SUPPLY CORP.
QRF 2022 | NIR | Negros Oriental | 189514 | Guilongsoran Primary School | SAN JOSE | 2 | 1 | 2 | REPAIR/ REHABILITATION | 1318876.303 | 1 | 1000473.71 | completed | 1 | 2022-11-29 |  | ITB 2022-04-021 | QRF202209009 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-29 | MDBD CONSTRUCTION
QRF 2022 | NIR | Negros Oriental | 120438 | Siapo Elementary School | SAN JOSE | 2 | 1 | 5 | REPAIR/ REHABILITATION | 2429147.1364 | 1 | 1850263.91 | completed | 1 | 2023-02-07 |  | ITB 2022-04-022 | QRF202209010 | 2022-04-26 | 2022-05-04 | 2022-05-16 | 2022-06-14 | 2022-09-29 | MDBD CONSTRUCTION
QRF 2022 REPLENISHMENT | NIR | Negros Oriental | 120033 | Ayungon CES | AYUNGON | 1st | 1 | 13 | REPAIR OF CLASSROOMS | 7088958.8048 | 1 | 6, 210,000.00 | completed | 1 | 2023-10-02 |  | ITB-2023-02-018 | QRF202304018 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRIBATA Construction
QRF 2022 REPLENISHMENT | NIR | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 3 | Replacement | 6803850.4069 | 1 | 6741884.8 | completed | 1 | 2023-12-01 |  | ITB-2023-02-025 | QRF202304021 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp.
QRF 2022 REPLENISHMENT | NIR | Negros Oriental | 120298 | Jimalalud Central School | JIMALALUD | 1st | 1 | 8 | REPAIR OF CLASSROOMS | 14977836.0543 | 1 | 14860634.65 | completed | 1 | 2023-11-01 |  | ITB-2023-02-019 | QRF202304019 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | Micro Asia Builders Corporation
QRF 2022 REPLENISHMENT | NIR | Negros Oriental | 120395 | Manjuyod CES | MANJUYOD | 1st | 1 | 5 | Replacement | 11766399.6233 | 1 | 10996219.44 | completed | 1 | 2023-12-01 | December 18, 2023 | ITB-2023-02-026 | QRF202304022 | 2023-02-23 | 2023-03-03 | 2023-03-15 | 2023-04-05 | 2023-04-20 | PAR Builders, Elecrical and Construction Supply Corp.
QRF 2022 REPLENISHMENT | NIR | Negros Oriental | 120395 | Manjuyod CES | MANJUYOD | 1st | 1 | 40 | REPAIR OF CLASSROOMS | 40783735.5341 | 1 | 37483431.65 | completed | 1 | 2024-01-10 | December 18, 2023 | ITB-2023-02-020 | QRF202304020 | 2023-02-17 | 2023-02-27 | 2023-03-13 | 2023-04-05 | 2023-04-24 | TRINITYCAD Corporation
QRF 2024 | NIR | Negros Oriental | 120356 | Dahile ES | MABINAY | 2nd | 1 | 8 | 2-UNITS 1STY4CL with Common Toilet | 26312604.57 | 1- NC | 24508091.67 | Ongoing | 0.45 | February 15,2026 |  | ITB2024-07-143 | QRF202409029 | August 8, 2024 | August 16, 2024 | August 28, 2024 | September 19, 2024 | October 11,2024 | TrinityCAD Corporation
QRF 2024 | NIR | Negros Oriental | 120474 | Palayuhan ES | SIATON | 3rd | 1 | 7 | Repair of Classrooms | 1801517.91 | 1- R | 1329769.5 | Completed | 1 | December 21, 2024 |  | ITB2024-07-144 | QRF202409030 | August 8, 2024 | August 16, 2024 | August 28, 2024 | September 19, 2024 | October 11,2024 | MCS-9 Construction

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%