## Sheet1
CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | SCOPE OF WORK | PROJECT ALLOCATION | BATCH | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
QRF 2019 | Region III | Nueva Ecija | 105656 | San Gregorio ES | RIZAL | 2 | 1 | 0 | REPAIR OF CLASSROOMS | 3156045.84 | 1 |  | Completed | 1
QRF 2021 | Region III | Aurora | 104409 | Baler CS | BALER (Capital) | 0 | 1 | 17 | TY ULYSSES | 12208837.24 | 1 | 12145374.43 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-05 | VANMARVIL CONSTRUCTION
QRF 2021 | Region III | Aurora | 500117 | Mariano L. Sindac IS | BALER (Capital) | 0 | 1 | 4 | TY ULYSSES | 2855188.91 | 1 | 2826418.46 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | VANMARVIL CONSTRUCTION
QRF 2021 | Region III | Aurora | 157513 | Butas na Bato ES | DINGALAN | 0 | 1 | 2 | TY ULYSSES | 1443287.54 | 1 | 824303.98 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | FNR Builders and Sons Supply Inc.
QRF 2021 | Region III | Aurora | 104462 | Umiray ES | DINGALAN | 0 | 1 | 9 | TY ULYSSES | 6119107.42 | 1 | 3473983.7 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | FNR Builders and Sons Supply Inc.
QRF 2021 | Region III | Aurora | 300695 | Umiray NHS | DINGALAN | 0 | 1 | 12 | TY ULYSSES | 14192889.5614 | 1 | 8060094.7 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-12 | FNR Builders and Sons Supply Inc.
QRF 2021 | Region III | Aurora | 104484 | Bagtu ES | MARIA AURORA | 0 | 1 | 7 | TY ULYSSES | 4959821.7155 | 1 | 3124102.63 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | MACCO Construction
QRF 2021 | Region III | Aurora | 104516 | Dikapinisan ES | SAN LUIS | 0 | 1 | 6 | TY ULYSSES | 4282656.05 | 1 | 2698145.03 | Completed | 1 | [5 empty] | 2021-07-01 | 2021-07-13 | 2021-08-02 | 2021-08-04 | MACCO Construction
QRF 2021 | Region III | Bataan | 104577 | Jose C. Payumo Jr. ES | DINALUPIHAN | 1 | 1 | 6 | TY ULYSSES | 3696132.03 | 1 | 3675824.03 | Completed | 1 | 2021-10-20 | 2021-08-31 | QRF2021-001 | 2021-CON-00012 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-24 | T. G. OCAMPO CONSTRUCTION & SURVEYING SERVICES
QRF 2021 | Region III | Bataan | 104544 | Binukawan ES | BAGAC | 2 | 1 | 3 | TY ULYSSES | 1443939.49 | 1 | 1423597.95 | Completed | 1 | 2021-09-20 | 2021-07-26 | QRF2021-002 | 2021-CON-00011 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | TURQUOISE CONSTRUCTION & REALTY DEVELOPMENT
QRF 2021 | Region III | Bataan | 104684 | Puting Buhangin ES | ORION | 2 | 1 | 9 | TY ULYSSES | 4132161.22 | 1 | 4111644.41 | Completed | 1 | 2021-10-20 | 2021-08-31 | QRF2021-003 | 2021-CON-00013 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | RODMAC CONSTRUCTION &TRADING
QRF 2021 | Region III | Bataan | 104685 | Sabatan ES | ORION | 2 | 1 | 5 | TY ULYSSES | 2637397.45 | 1 | 2616736.88 | Completed | 1 | 2021-10-20 | 2021-09-07 | QRF2021-004 | 2021-CON-00014 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-24 | ALTITUDE ENGINEERING AND CONSTRUCTION
QRF 2021 | Region III | Bataan | 104698 | Sta. Rosa ES | PILAR | 2 | 1 | 5 | TY ULYSSES | 3568719.22 | 1 | 3548642.04 | Completed | 1 | 2021-10-20 | 2021-09-06 | QRF2021-005 | 2021-CON-00015 |  |  | 2021-06-15 | 2021-06-15 | 2021-06-23 | RODMAC CONSTRUCTION &TRADING
QRF 2021 | Region III | Bulacan | 158542 | St. Martha Elementary School | BOCAUE | 2 | 1 | 16 | TY ULYSSES | 751760.04 | 1 | 697369.88 | Completed | 1 | 2021-10-22 | 2021-10-12 | PB-21-014 | PB-21--025 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-31 | DUAMON Construction & Supply
QRF 2021 | Region III | Bulacan | 127616 | Cacarong Bata Elementary School | PANDI | 2 | 1 | 15 | TY ULYSSES | 1781937.72 | 1 | 2105320.7 | Completed | 1 | 2021-11-08 | 2021-10-27 | PB-21-013 | PB-21--024 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | EMICA Builders and Supply
QRF 2021 | Region III | Bulacan | 105035 | Garlang Elementary School | SAN ILDEFONSO | 3 | 1 | 0 | TY ULYSSES | 2807039.59 | 1 | 1556027.8 | Completed | 1 | 2021-11-08 | 2021-10-20 | PB-21-012 | PB-21--023 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | RHR Construction
QRF 2021 | Region III | Bulacan | 306728 | Sta. Catalina Bata National High School | SAN ILDEFONSO | 3 | 1 | 4 | TY ULYSSES | 432073.49 | 1 | 358601.03 | Completed | 1 | 2021-09-24 | 2021-09-20 | PB-21-015 | PB-21--026 | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-21 | 2021-08-03 | EMICA Builders and Supply
QRF 2021 | Region III | Gapan City | 500727 | Sto. Cristo Proper Integrated School | CITY OF GAPAN | 4 | 1 | 4 | TY ULYSSES | 573955.04 | 1 | 563657.79 | Completed | 1 | 2021-08-27 | 2021-08-01 | 2021-06-09-002-QRF | 2021-06-09-002-QRF | 2021-06-10 | 2021-06-15 | 2021-06-15 | 2021-06-18 | 2021-06-28 | Joynieltin Construction and Trading
QRF 2021 | Region III | Malolos City | 104867 | Caingin ES | CITY OF MALOLOS (Capital) | 1 | 1 | 4 | TY ULYSSES | 1848240.83 | 1 | 1841861.9 | Completed | 1 | 2021-12-13 |  |  |  | 06/23-06/302021 | 2021-06-30 | 2021-07-12 | 2021-07-15 | 2021-08-16 | POWERMETAL CONSTRUCTION CO.
QRF 2021 | Region III | Nueva Ecija | 159015 | Osmena ES | QUEZON | 1 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105625 | Ricardo L. Joson Elementary School | QUEZON | 1 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105634 | Tomas Joson ES | QUEZON | 1 | 1 | 3 | TY ULYSSES | 1504463.25 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105242 | Carranglan C/S | CARRANGLAN | 2 | 1 | 3 | TY ULYSSES | 1707160.4868 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105498 | General Ricarte ES | LLANERA | 2 | 1 | 4 | TY ULYSSES | 2043160.4652 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105655 | San Esteban ES | RIZAL | 2 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105194 | Antipolo ES | BONGABON | 3 | 1 | 3 | TY ULYSSES | 1436427.5123 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105195 | Ariendo ES | BONGABON | 3 | 1 | 3 | TY ULYSSES | 1690473.37 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105306 | F. Buencamino Sr. Integrated School (F. Buencamino Sr. ES) | GABALDON (BITULOK & SABANI) | 3 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105313 | Tagumpay ES | GABALDON (BITULOK & SABANI) | 3 | 1 | 2 | TY ULYSSES | 1066073.88 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105757 | Pepito B. Bernardo Mem. School | SANTA ROSA | 3 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105227 | San Roque ES | CABIAO | 4 | 1 | 3 | TY ULYSSES | 1942651.42 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105232 | Sta. Isabel Elementary School | CABIAO | 4 | 1 | 4 | TY ULYSSES | 2177382.21 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105454 | San Vicente ES | JAEN | 4 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105681 | Calaba ES | SAN ISIDRO | 4 | 1 | 3 | TY ULYSSES | 1794967.0283 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105683 | Malapit East ES | SAN ISIDRO | 4 | 1 | 2 | TY ULYSSES | 1163078.75 | 1 |  | Completed | 1
QRF 2021 | Region III | Nueva Ecija | 105687 | San Isidro CS | SAN ISIDRO | 4 | 1 | 6 | TY ULYSSES | 3042657.1725 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105899 | Arenas ES | ARAYAT | 3 | 1 | 6 | TY ULYSSES | 3803405 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105903 | Cacutud ES | ARAYAT | 3 | 1 | 7 | TY ULYSSES | 4312538.87 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105882 | Camba ES | ARAYAT | 3 | 1 | 10 | TY ULYSSES | 3124890.21 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 300884 | Camba NHS | ARAYAT | 3 | 1 | 11 | TY ULYSSES | 3191432.34 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 306907 | Candating NHS | ARAYAT | 3 | 1 | 9 | TY ULYSSES | 1574153.2 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105884 | Cupang Elementary School | ARAYAT | 3 | 1 | 3 | TY ULYSSES | 1650713.65 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105891 | San Juan Bano ES | ARAYAT | 3 | 1 | 4 | TY ULYSSES | 2049694.53 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105933 | Dalayap ES | CANDABA | 4 | 1 | 3 | TY ULYSSES | 1899062.95 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105948 | Tenejero ES | CANDABA | 4 | 1 | 2 | TY ULYSSES | 1273776.81 | 1 |  | Completed | 1
QRF 2021 | Region III | Pampanga | 105949 | Vizal San Pablo II ES | CANDABA | 4 | 1 | 7 | TY ULYSSES | 4723728.81 | 1 |  | Completed | 1
QRF 2021 | Region III | Tarlac City | 106729 | Asturias ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | TY ULYSSES | 652501.55 | 1 | 650309.31 | Completed | 1 | 2021-08-31 | 2021-08-31 | [7 empty] | J.P. Aquino Construction
QRF 2021 | Region III | Tarlac City | 106743 | Paraiso ES | CITY OF TARLAC (Capital) | 2 | 1 | 2 | TY ULYSSES | 1093868.34 | 1 | 1040671.09 | Completed | 1 | 2021-08-31 | 2021-08-31 | [7 empty] | J.P. Aquino Construction
QRF 2021 | Region III | Tarlac City | 106744 | San Carlos ES | CITY OF TARLAC (Capital) | 2 | 1 | 1 | TY ULYSSES | 1062165.41 | 1 | 1059953.12 | Completed | 1 | 2021-08-26 | 2021-08-26 | [7 empty] | Boycing Construction Services
QRF 2021 | Region III | Zambales | 106974 | Almasin Elementary School | SANTA CRUZ | 2 | 1 | 13 | TY ULYSSES | 5122463.9104 | 1 |  | Completed | 1
QRF 2021 | Region III | Zambales | 501226 | Don Brigido Miraflor Integrated School | SANTA CRUZ | 2 | 1 | 25 | TY ULYSSES | 6794925.58 | 1 |  | Completed | 1
QRF 2022 REPLENISHMENT | Region III | Aurora | 300685 | Dingalan NHS | DINGALAN | Lone | 1 | 13 | REPAIR OF CLASSROOMS | 6892000 | 1 | 3963054.24 | COMPLETED | 1 | 2023-10-28 |  |  |  | 2023-03-07 | 2023-03-15 | 2023-03-27 | 2023-04-13 | 2023-04-24 | AMC CONSTRUCTION
QRF 2022 REPLENISHMENT | Region III | Bulacan | 306712 | Sto. Nino High School | BALIUAG | 2nd | 1 | 2 | REPAIR OF CLASSROOMS | 466271.98 | 1 | ₱386,515.13 | Completed | 1 | 2023-05-23 | 2023-05-17 | PB-23-001 | 23-03-001 | 2023-02-22 | 2023-03-01 | 2023-03-13 | 2023-03-16 | 2023-03-31 | EMICA Builders and Supply
QRF 2022 REPLENISHMENT | Region III | Bulacan | 158529 | Cucong Elementary School | DOÑA REMEDIOS TRINIDAD | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 3064193.79 | 1 | 2514973.27 | Completed | 1 | 2023-09-29 | 2023-08-09 | PB-23-008 | 23-008 | 2023-04-20 | 2023-05-02 | 2023-05-15 | 2023-05-16 | 2023-05-25 | GELROCK BUILDERS | realigned from felizardo lipana nhs (sta rita hs) and john russel mhs (sibul nhs)
QRF 2022 REPLENISHMENT | Region III | Bulacan | 300774 | John J. Russell MHS (Sibul NHS) | SAN MIGUEL | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 425508.5126 | 1 | ₱417,671.35 | Completed | 1 | 2023-05-23 | 2023-05-22 | PB-23-003 | 23-03-003 | 2023-02-22 | 2023-03-01 | 2023-03-13 | 2023-03-16 | 2023-03-31 | EMICA Builders and Supply
QRF 2022 REPLENISHMENT | Region III | Bulacan | 105111 | San Miguel Elementary | SAN MIGUEL | 3rd | 1 | 4 | REPAIR OF CLASSROOMS | 2301524.74 | 1 | ₱1,891,657.30 | COMPLETED | 1 | 2023-08-06 | 2023-07-28 | PB-23-002 | 23-03-002 | 2023-02-22 | 2023-03-01 | 2023-03-13 | 2023-03-16 | 2023-03-31 | EMICA Builders and Supply
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105216 | Cabiao Central School | CABIAO | 4th | 1 | 22 | REPAIR OF CLASSROOMS | 7950000 | 1 | 7941961.35 | Completed | 1 | 2023-08-17 | 2023-08-17 | INFRA-NE-Emergency-22-2023 | INFRA-NE-Emergency-22-2023 | 2023-02-28 |  | 2023-03-08 | 2023-03-13 | 2023-03-17 | J.V. BUAN CONSTRUCTION *T
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105368 | Gen. Tinio West Central School | GENERAL TINIO (PAPAYA) | 4th | 1 | 3 | REPAIR OF CLASSROOMS | 1650000 | 1 | 1647978.72 | Completed | 1 | 2023-08-17 | 2023-08-17 | INFRA-NE-Emergency-23-2023 | INFRA-NE-Emergency-23-2023 | 2023-02-28 |  | 2023-03-08 | 2023-03-13 | 2023-03-17 | JOYUS CONSTRUCTION
QRF 2022 REPLENISHMENT | Region III | Nueva Ecija | 105741 | San Leonardo Central School | SAN LEONARDO | 4th | 1 | 7 | REPAIR OF CLASSROOMS | 3850000 | 1 | 3846350.56 | Completed | 1 | 2023-08-17 | 2023-08-17 | INFRA-NE-Emergency-24-2023 | INFRA-NE-Emergency-24-2023 | 2023-02-28 |  | 2023-03-08 | 2023-03-13 | 2023-03-17 | IJK MAE CONSTRUCTION INC.
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300989 | San Pedro National High School | MONCADA | 1st | 1 | 12 | Replacement | 36000000 | 1 | 35898680.53 | Completed | 1 | 2025-05-28 |  |  | CSCB-CY2023-002 | 2023-07-27 | 2023-08-04 | 2023-08-17 |  | 2023-09-04 | FROMARC BUILDERS & GENERAL MERCHANDISE
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300989 | San Pedro National High School | MONCADA | 1st | 1 | 2 | REPAIR OF CLASSROOMS | 1300000 | 1 | 35898680.53 | Completed | 1 | 2024-07-01 |  |  | CSCB-CY2023-002 | 2023-07-27 | 2023-08-04 | 2023-08-17 |  | 2023-09-21 | High Vision Builders
QRF 2022 REPLENISHMENT | Region III | Tarlac | 300982 | Ramos National High School | RAMOS | 1st | 1 | 16 | Replacement | 48000000 | 1 | 478945595.27 | Ongoing | 0.25 | 2024-07-01 |  |  | CSCB-CY2023-003 | 2023-07-27 | 2023-08-04 | 2023-08-17 |  | 2023-09-04 | IJK MAE CONSTRUCTION, INC. | Suspended
QRF 2023 | Region III | Tarlac | 106605 | Pura Central ES | PURA | 1st | 1 | 8 | 2STY8CL | 22950000 | 2- NC | 15742082.99 | Completed | 1 | 2024-12-12 | 2025-02-10 |  |  | 2023-11-23 | 2023-11-29 | 2023-12-12 | 2023-12-29 | 2024-01-02 | ARESBI CONSTRUCTION

## DropdownOptions (hidden)
0% - 10%
11% - 25%
26% - 50%
51% - 75%
76% - 90%
91% - 99%
100%