## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region IV-A | ANTIPOLO CITY | 301422 | Mayamot NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15105522.3438 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | ANTIPOLO CITY | 301422 | Mayamot NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | ANTIPOLO CITY | 301423 | Muntindilaw NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15497518.84 |  |  | COMPLETED | 1 | 2016-03-13 |  | 4A0614S00022 | 15DN0099 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | ANTIPOLO CITY | 230003 | Knights of Columbus ES | CITY OF ANTIPOLO | 2 | 1 | 10 | 4STY8CL & 2STY2CL | 2014 K10 BATCH 3 | 19397421.9531 |  |  | COMPLETED | 1 | 2016-02-07 |  | 4A0614S00012 | 15DN0016 | 2015-02-04 | 2015-02-04 | 2015-02-17 | 2015-02-27 | 2015-03-13 | HONEYVILLE CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | ANTIPOLO CITY | 321501 | Marcelino M. Santos NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-04 |  | 4A0614S00024 | 15DN0098 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | ANTIPOLO CITY | 308101 | Maximo L. Gatlabayan MNHS - Boso-boso Extension | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-04 |  | 4A0614S00033 | 15DN0097 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | ANTIPOLO CITY | 321504 | Maximo L. Gatlabayan MNHS - Rizza Extension | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15397518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | 4A0614S00034 | 15DN0108 | 2015-09-16 | 2015-09-16 | 2015-09-29 | 2015-10-13 | 2015-10-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | ANTIPOLO CITY | 109340 | San Luis ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 17216022.3438 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4A0614S00013 | 14DN0087 | 2014-12-10 | 2014-12-10 | 2014-12-23 | 2015-01-15 | 2015-02-03 | CHRISMAN CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | ANTIPOLO CITY | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | Reverted | 0.001
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107877 | Aniban CS | BACOOR | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 11239593.5547 |  |  | COMPLETED | 1 | 2015-11-27 | 2015-11-27 | 4A0314S00036 | 14DF0070 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107878 | Bayanan ES | BACOOR | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20233283.5938 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0314S00044 | 14DF0103 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107868 | Digman ES | BACOOR | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00047 | 14DF0053 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu ES | BACOOR CITY | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-07-10 |  | 4A0314S00083 | 15DF0084 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107870 | Habay ES | Bacoor I | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | COMPLETED | 1 | 2016-07-13 |  | 4A0314S00117 | 15DF0095 | 2015-08-12 | 2015-08-19 | 2015-09-02 | 2015-09-08 | 2015-09-17 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107881 | Ligas I ES | BACOOR | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6549914.7656 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00052 | 14DF0053 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107885 | Malipay ES | BACOOR | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15507522.3438 |  |  | COMPLETED | 1 | 2015-07-27 | 2015-07-27 | 4A0314S00042 | 14DF0064 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107886 | Molino ES | BACOOR | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00041 | 14DF0053 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107887 | Niog Elementary School | Bacoor II | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-25 |  | 4A0314S00111 | 15DF0066 | 2015-07-14 | 2015-07-21 | 2015-08-04 | 2015-08-10 | 2015-08-19 | N.B. AVILA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107888 | Queen's Row ES | BACOOR | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 31970584.375 |  |  | COMPLETED | 1 | 2016-01-30 | 2015-12-30 | 4A0314S00040 | 14DF0108 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107874 | Real ES | BACOOR | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00046 | 14DF0053 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107889 | San Nicolas ES | BACOOR | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7707 |  |  | COMPLETED | 1 | 2015-07-22 | 2015-07-22 | 4A0314S00070 | 14DF0166 | 2014-11-27 | 2014-12-05 | 2014-12-18 | 2014-12-19 | 2014-12-24 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 164015 | Soldiers Hills IV ES | BACOOR CITY | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-18 |  | 4A0314S00074 | 15DF0059 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | N.B. AVILA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Bacoor City | 107891 | Zapote ES | BACOOR | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10988343.5547 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-10-27 | 4A0314S00039 | 14DF0070 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301070 | Ananias C. Hernandez NHS (Arumahan NHS) | LEMERY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00044 | 14DB0026 | 2014-06-25 | 2014-06-27 | 2014-07-08 | 2014-07-17 | 2014-08-07 | JASMIG CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107327 | Angelita Zobel ES (Lucsuhin ES) | CALATAGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 4A0214S00055 | 14DB0021 | 2014-06-25 | 2014-06-27 | 2014-07-07 | 2014-07-18 | 2014-08-07 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107385 | Arumahan ES | LEMERY | 1 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-01-21 | 4A0214S00053 | 14DB0017 | 2014-06-25 | 2014-06-30 | 2014-07-25 | 2014-08-08 | 2014-08-18 | GERSHLI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107397 | Bagong Pook ES | Lian | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-30 |  | 4A0214S00133 | 15DB0088 | 2015-07-29 | 2015-08-11 | 2015-08-13 | 2015-08-26 | 2015-09-02 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301072 | Balayan NHS | Balayan East | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0214S00132 | 4A02-14-S-00132 | 2015-12-09 | 2015-12-18 | 2015-12-21
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107496 | Bilaran ES | NASUGBU | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00049 | 14DB0028 | 2014-06-26 | 2014-06-27 | 2014-07-08 | 2014-07-18 | 2014-08-07 | REE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107822 | Bolbok ES | TUY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6348914.7656 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 4A0214S00088 | 14DB0101 | 2014-12-03 | 2014-12-15 | 2014-12-16 | 2014-12-20 | 2015-01-26 | DY CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107227 | Calan ES | BALAYAN | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2900174.43 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-29 | 4A0214S00059 | 14DB0016 | 2014-06-25 | 2014-06-27 | 2014-07-25 | 2014-08-11 | 2014-08-25 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107289 | Caluangan ES | CALACA | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4367274.6094 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 4A0214S00107 | 14DB0098 | 2014-12-03 | 2014-12-15 | 2014-12-16 | 2014-12-20 | 2015-01-26 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107726 | Carmino Biscocho MES | TAAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1172329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00077 | 14DB0040 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | GERSHLI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107500 | Catandaan ES | NASUGBU | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-09-29 | 4A0214S00068 | 14DB0043 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | QUINI SQUARE CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 307723 | Catandaan Yabut NHS | NASUGBU | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00076 | 14DB0041 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107727 | Cubamba-Gahol ES | TAAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-11-15 | 4A0214S00078 | 14DB0030 | 2014-06-26 | 2014-06-30 | 2014-08-04 | 2014-08-15 | 2014-08-28 | TDR CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107728 | Cultihan-Bolbok ES | TAAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00079 | 14DB0031 | 2014-06-20 | 2014-06-27 | 2014-07-09 | 2014-07-25 | 2014-08-07 | 830 BUILDERS & DEVELOPERS CORP.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107233 | Dilao ES | BALAYAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-10-23 | 4A0214S00058 | 14DB0018 | 2014-06-25 | 2014-06-27 | 2014-07-25 | 2014-08-11 | 2014-08-25 | DY CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107404 | Dita ES | LEMERY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00060 | 14DB0038 | 2014-06-26 | 2014-06-27 | 2014-07-14 | 2014-07-25 | 2014-08-12 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107406 | Esteban E. Vito MES | LEMERY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00048 | 14DB0035 | 2014-06-26 | 2014-06-30 | 2014-07-14 | 2014-07-25 | 2014-08-12 | JUBER CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301102 | Gov. Feliciano Leviste MNHS | LEMERY | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14366368.3984 |  |  | COMPLETED | 1 | 2016-02-17 |  | 4A0214S00109 | 15DB0013 | 2015-02-17 | 2015-03-02 | 2015-03-09 | 2015-03-19 | 2015-03-24 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107825 | Gregorio Agoncillo ES | TUY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00074 | 14DB0033 | 2014-06-26 | 2014-06-27 | 2014-07-09 | 2014-07-25 | 2014-08-07 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107386 | Gulod ES | LEMERY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107729 | Halang ES | TAAL | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00080 | 14DB0032 | 2014-06-26 | 2014-06-27 | 2014-07-09 | 2014-07-25 | 2014-08-07 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107324 | Hukay ES | CALATAGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-06 | 2014-11-06 | 4A0214S00056 | 14DB0020 | 2014-06-25 | 2014-06-27 | 2014-07-25 | 2014-08-12 | 2014-08-25 | GERSHLI CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107241 | Jose Chua Ben Chong MES | BALAYAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 4A0214S00057 | 14DB0019 | 2014-06-25 | 2014-06-27 | 2014-07-07 | 2014-07-18 | 2014-08-07 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107504 | Kaylaway II ES | NASUGBU | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00073 | 14DB0027 | 2014-06-25 | 2014-06-27 | 2014-07-08 | 2014-07-21 | 2014-08-07 | RRE ERECTORs CONST. AND TRADING SPECIALIST
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107410 | Lian CS | LIAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 4A0214S00110 | 14DB0100 | 2014-12-03 | 2014-12-15 | 2014-12-16 | 2014-12-20 | 2015-01-26 | VICMAR CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 307706 | Lian NHS | LIAN | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10897893.5547 |  |  | COMPLETED | 1 | 2015-12-04 |  | 4A0214S00098 | 15DB0014 | 2015-02-24 | 2015-03-06 | 2015-03-09 | 2015-03-20 | 2015-03-24 | RRE ERECTORs CONST. AND TRADING SPECIALIST
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107411 | Lumaniag ES | LIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00051 | 14DB0045 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107412 | Luyahan ES | LIAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00042 | 14DB0044 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | F. CASALME CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107413 | Mahayahay ES | LEMERY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6348914.7656 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-22 | 4A0214S00108 | 14DB0099 | 2014-12-03 | 2014-12-15 | 2014-12-16 | 2014-12-20 | 2015-01-26 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107415 | Masalisi ES | LEMERY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00047 | 14DB0024 | 2014-06-25 | 2014-06-27 | 2014-07-08 | 2014-07-16 | 2014-08-07 | 830 BUILDERS & DEVELOPERS CORP.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107513 | Natipuan ES | NASUGBU | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00071 | 14DB0029 | 2014-06-26 | 2014-06-27 | 2014-07-09 | 2014-07-25 | 2014-08-07 | JUBER CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107242 | Navotas ES | BALAYAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6308714.7656 |  |  | COMPLETED | 1 | 2015-12-12 |  | 4A0214S00099 | 14DB0097 | 2014-12-03 | 2014-12-15 | 2014-12-16 | 2014-12-20 | 2015-03-23 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107330 | Parola PS | CALATAGAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107419 | Payapa Ibaba ES | LEMERY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00046 | 14DB0037 | 2014-06-26 | 2014-06-27 | 2014-07-14 | 2014-07-28 | 2014-08-12 | JUBER CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107517 | Pingkian ES | NASUGBU | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-09-29 | 4A0214S00075 | 14DB0042 | 2014-06-26 | 2014-06-30 | 2014-07-15 | 2014-07-28 | 2014-08-12 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107389 | R. Venturanza CS | LEMERY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0214S00112 | 15DB0082 | 2015-07-03 | 2015-07-08 | 2015-07-20 | 2015-07-27 | 2015-08-05 | NBL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107423 | San Isidro Itaas ES | LEMERY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-11-04 | 2014-11-04 | 4A0214S00066 | 14DB0025 | 2014-06-25 | 2014-06-27 | 2014-07-08 | 2014-07-24 | 2014-08-07 | JASMIG CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107836 | San Jose ES | TUY | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 4A0214S00070 | 14DB0034 | 2014-06-26 | 2014-06-27 | 2014-07-14 | 2014-07-28 | 2014-08-12 | QUINI SQUARE CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107315 | Santiago Zobel ES (Balitoc ES) | Calatagan | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15271327.92 |  |  | reverted | 0 | 2015-12-30 |  | 4A0214S00134 | 4A02-14-S-00134
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301151 | Taal NHS | TAAL | 1 | 1 | 16 | 2UNITS 4STY8CL | 2014 K10 BATCH 3 | 30723594.6875 |  |  | COMPLETED | 1 | 2015-12-15 |  | 4A0214S00097 | 15DB0031 | 2015-03-17 | 2015-03-30 | 2015-03-30 | 2015-04-13 | 2015-04-17 | VICMAR CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107393 | Tubuan ES | LEMERY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00041 | 14DB0036 | 2014-06-26 | 2014-06-27 | 2014-07-14 | 2014-07-25 | 2014-08-12 | F. CASALME CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107394 | V. Ornales MS | LEMERY | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-10 | 2014-10-10 | 4A0214S00050 | 14DB0039 | 2014-06-26 | 2014-06-30 | 2014-07-14 | 2014-07-21 | 2014-08-12 | F. CASALME CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107426 | Apar ES | LOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00061 | 14DE0018 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107428 | Balibago ES | LOBO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3010174.43 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00067 | 14DE0019 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301080 | Bauan Technical HS | BAUAN | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4A | 10667093.5572 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301081 | Bayanan NHS | SAN PASCUAL | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-05-29 | 2015-05-29 | 4A0214S00095 | 14DE0043 | 2014-12-22 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | R.G. EVANGELISTA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107430 | Biga ES | LOBO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00072 | 14DE0019 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107642 | Boboy ES | SAN LUIS | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 4A0214S00043 | 14DE0017 | 2014-06-30 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107643 | Bonliw ES | SAN LUIS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 4A0214S00011 | 14DE0017 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301104 | Inicbulan NHS | BAUAN | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 4A0214S00069 | 14DE0015 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | W. RIVERA CONSTRUCTION & EQUIPMENT RENTALS
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301106 | Jaybanga NHS | LOBO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2065417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00063 | 14DE0018 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107435 | Lagadlarin-Olo-Olo ES | LOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00065 | 14DE0019 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301121 | Malapad na Parang NHS | LOBO | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107272 | Manalupang - San Vicente ES | Bauan | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6419337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0214S00131 | 15DE0071 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-24 | R.G. EVANGELISTA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107440 | Masaguitsit ES | LOBO | 2 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 4A0214S00064 | 14DE0018 | 2014-06-26 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107676 | Mataas Na Lupa - Palsahingin ES | SAN PASCUAL | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-11-09 | 4A0214S00018 | 14DE0016 | 2014-06-30 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107650 | Muzon ES | San Luis | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10467131.51 |  |  | COMPLETED | 1 | 2016-02-10 |  | 4A0214S00138 | 15DE0079 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | VICMAR CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301134 | Papaya NHS | TINGLOY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1147329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301142 | San Pascual NHS | SAN PASCUAL | 2 | 1 | 24 | 2UNITS 4STY12CL | 2014 K10 BATCH 3 | 40009292.1875 |  |  | COMPLETED | 1 | 2016-04-23 |  | 4A0214S00094 | 15DE0005 | 2015-02-08 | 2015-02-09 | 2015-02-24 | 2015-03-05 | 2015-03-13 | N.B. AVILA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107654 | Sta. Monica ES | San Luis | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10517131.51 |  |  | COMPLETED | 1 | 2016-01-20 |  | 4A0214S00137 | 15DE0072 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-24 | VICMAR CONSTRUCTION, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107655 | Taliba ES | San Luis | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6369337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0214S00136 | 15DE0070 | 2015-07-30 | 2015-07-31 | 2015-08-13 | 2015-08-18 | 2015-08-24 | R.G. EVANGELISTA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107656 | Talon ES | SAN LUIS | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-12-12 | 4A0214S00039 | 14DE0017 | 2014-06-30 | 2014-07-03 | 2014-07-15 | 2014-07-31 | 2014-08-08 | RM JOYCE CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301158 | Tingloy NHS | TINGLOY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6474539.7656 |  |  | COMPLETED | 1 | 2015-08-27 | 2015-08-27 | 4A0214S00093 | 14DE0047 | 2014-12-22 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107215 | Alitagtag CS | ALITAGTAG | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 4A0214S00015 | 14DC0017 | 2014-06-17 | 2014-08-05 | 2014-10-01 | 2014-10-08 | 2014-10-14 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301068 | Alitagtag NHS | ALITAGTAG | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 4A0214S00014 | 14DC0018 | 2014-06-17 | 2014-08-05 | 2014-08-05 | 2014-08-06 | 2014-08-20 | STALL CONSTRUCTION SUPPLIES & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107659 | Balete ES | SAN NICOLAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00008 | 14DC0022 | 2014-06-06 | 2014-06-11 | 2014-06-30 | 2014-07-02 | 2014-07-18 | A. SANDOVAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301076 | Banyaga NHS | AGONCILLO | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6394139.7656 |  |  | COMPLETED | 1 | 2016-01-05 |  | 4A0214S00091 | 14DC0065 | 2014-12-02 | 2014-12-20 | 2014-12-22 | 2014-12-29 | 2015-01-07 | GRANBY TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301083 | Bayorbor NHS | Mataas Na Kahoy | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-28 |  | 4A0214S00130 | 15DC0079 | 2015-08-18 | 2015-08-22 | 2015-08-24 | 2015-08-27 | 2015-09-01 | BERTO LUCCI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107688 | Calumala ES | SANTA TERESITA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2945174.43 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 4A0214S00006 | 14DC0023 | 2014-06-17 | 2014-07-09 | 2014-07-11 | 2014-07-18 | 2014-07-18 | 830 BUILDERS & DEVELOPERS CORP.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301096 | Cuenca NHS | CUENCA | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-03 | 4A0214S00102 | 14DC0066 | 2014-12-03 | 2014-12-05 | 2014-12-22 | 2014-12-29 | 2015-01-07 | OIC CONSTRUCTION & SUPPLY(FORMERLY:OIC CONST.)
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107740 | Doña Ma. Laurel Platon MS | TALISAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 4A0214S00003 | 14DC0025 | 2014-06-17 | 2014-07-09 | 2014-07-11 | 2014-07-18 | 2014-07-18 | A. SANDOVAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301100 | Fermin La Rosa NHS (Col. P. Pasia NHS) | Cuenca | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0214S00127 | 15DC0080 | 2015-08-18
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107741 | Jorge B. Vargas MES | TALISAY | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8248553.2031 |  |  | COMPLETED | 1 | 2015-12-05 | 2015-12-05 | 4A0214S00101 | 14DC0072 | 2014-12-03 | 2014-12-20 | 2014-12-22 | 2014-12-29 | 2015-01-07 | GRANBY TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301114 | Maabud NHS | SAN NICOLAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 4A0214S00007 | 14DC0022 | 2014-06-11 | 2014-06-13 | 2014-06-16 | 2014-06-19 | 2014-07-18 | A. SANDOVAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107252 | Magapi ES | BALETE | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-15 | 2014-12-15 | 4A0214S00002 | 14DC0019 | 2014-06-17 | 2014-07-09 | 2014-07-11 | 2014-07-18 | 2014-07-18 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107691 | Mohon ES | SANTA TERESITA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00005 | 14DC0024 | 2014-06-17 | 2014-07-09 | 2014-08-05 | 2014-08-06 | 2014-08-20 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107376 | Molinete ES | LAUREL | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00019 | 14DC0020 | 2014-06-17 | 2014-06-30 | 2014-06-30 | 2014-07-03 | 2014-07-18 | KENSAL RISE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107484 | PAARALANG ELEMENTARYA NG LOOB | MATAASNAKAHOY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00009 | 14DC00021 | 2014-06-17 | 2014-06-30 | 2014-08-05 | 2014-08-06 | 2014-08-20 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107378 | Paliparan PS | LAUREL | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4B | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-27 |  | 4A0214S00115 | 15DC0082 | 2015-07-22 | 2015-07-29 | 2015-07-31 | 2015-08-23 | 2015-09-01 | STALL CONSTRUCTION SUPPLIES & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107256 | Palsara ES | BALETE | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00012 | 14DC0019 | 2014-06-17 | 2014-06-30 | 2014-07-01 | 2014-07-04 | 2014-07-18 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107379 | Pantay PS | LAUREL | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6363989.7656 |  |  | COMPLETED | 1 | 2015-12-05 | 2015-12-05 | 4A0214S00096 | 14DC0067 | 2014-12-08 | 2014-12-20 | 2014-12-21 | 2015-01-05 | 2015-01-07 | GRANBY TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107220 | Pinagkurusan Elementary School | ALITAGTAG | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2014-12-18 | 2014-12-18 | 4A0214S00017 | 14DC0015 | 2014-06-17 | 2014-08-05 | 2014-08-06 | 2014-08-09 | 2014-08-20 | STALL CONSTRUCTION SUPPLIES & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107697 | San Antonio ES | SANTO TOMAS | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00004 | 14DC00021 | 2014-06-17 | 2014-07-09 | 2014-08-05 | 2014-08-06 | 2014-08-20 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107381 | San Gregorio ES | LAUREL | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 4A0214S00104 | 14DC0068 | 2014-12-02 | 2014-12-05 | 2014-12-22 | 2014-12-29 | 2015-01-07 | STALL CONSTRUCTION SUPPLIES & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 163508 | San Guillermo ES | TALISAY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 4A0214S00031 | 14DC0026 | 2014-06-17 | 2014-06-30 | 2014-08-05 | 2014-08-06 | 2014-08-20 | A. SANDOVAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107222 | San Jose T. Reyes ES | ALITAGTAG | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3860805.49 |  |  | COMPLETED | 1 | 2015-02-11 | 2015-02-11 | 4A0214S00016 | 14DC0016 | 2014-06-17 | 2014-06-30 | 2014-08-05 | 2014-10-09 | 2014-10-14 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301143 | San Pedro NHS | SANTO TOMAS | 3 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 32257009.375 |  |  | COMPLETED | 1 | 2016-01-17 |  | 4A0214S00105 | 14DC0070 | 2015-02-17 | 2015-03-03 | 2015-03-03 | 2015-03-06 | 2015-03-23 | HONEYVILLE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301146 | Santa Anastacia-San Rafael NHS | SANTO TOMAS | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10787343.5547 |  |  | COMPLETED | 1 | 2015-12-04 | 2015-12-04 | 4A0214S00103 | 14DC0071 | 2014-12-03 | 2014-12-20 | 2014-12-22 | 2015-12-29 | 2015-01-07 | OIC CONSTRUCTION & SUPPLY(FORMERLY:OIC CONST.)
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107213 | Subic ES | AGONCILLO | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6318764.7656 |  |  | COMPLETED | 1 | 2016-01-05 |  | 4A0214S00092 | 14DC0064 | 2014-12-03 | 2014-12-22 | 2014-12-22 | 2014-12-29 | 2015-01-07 | GRANBY TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 307727 | Talisay School of Agriculture | TALISAY | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 4B | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-27 |  | 4A0214S00114 | 15DC0081 | 2015-07-22 | 2015-07-28 | 2015-07-31 | 2015-08-20 | 2015-09-01 | N.D.M. SANCHEZ BUILDERS & DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107384 | Ticub ES | LAUREL | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-14 | 2014-12-14 | 4A0214S00010 | 14DC0020 | 2014-06-17 | 2014-06-30 | 2014-06-30 | 2014-07-03 | 2014-07-18 | KENSAL RISE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107744 | Tranca ES | TALISAY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-02 | 2014-12-02 | 4A0214S00029 | 14DC0026 | 2014-06-17 | 2014-06-30 | 2014-08-05 | 2014-08-06 | 2014-08-20 | A. SANDOVAL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301164 | Wenceslao Trinidad MNHS | LAUREL | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4392399.6094 |  |  | COMPLETED | 1 | 2015-07-20 | 2015-07-20 | 4A0214S00106 | 14DC0069 | 2015-02-17 | 2015-03-03 | 2015-03-03 | 2015-03-20 | 2015-03-23 | REE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107540 | Alupay ES | ROSARIO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-11-28 | 4A0214S00035 | 14DD0013 | 2014-07-22 | 2014-07-28 | 2014-08-11 | 2014-08-22 | 2014-09-05 | IKM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107601 | Aplaya ES | SAN JUAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-08 | 2014-11-08 | 4A0214S00040 | 14DD0011 | 2014-06-25 | 2014-07-01 | 2014-07-14 | 2014-07-21 | 2014-08-04 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107351 | Balanga ES | IBAAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 4A0214S00013 | 14DD0015 | 2014-06-27 | 2014-07-04 | 2014-07-17 | 2014-07-24 | 2014-08-05 | P-SQUARE CONTRACTING & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107589 | Benigna Dimatatac MES | SAN JOSE | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 4A0214S00090 | 14DD0052 | 2014-11-27 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 2015-01-07 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107548 | Calantas ES | ROSARIO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107610 | Catmon ES | SAN JUAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-12-08 | 4A0214S00028 | 14DD0018 | 2014-06-30 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-12 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107613 | Hugom ES | SAN JUAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-12-08 | 4A0214S00027 | 14DD0012 | 2014-06-28 | 2014-07-04 | 2014-07-17 | 2014-07-24 | 2014-08-05 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301108 | Laiya NHS | SAN JUAN | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2880174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 307725 | Lipahan National High School | SAN JUAN | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2014-11-01 | 2014-12-01 | 4A0214S00023 | 14DD0019 | 2014-06-30 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-12 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301126 | Mayuro National High School | ROSARIO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 4A0214S00020 | 14DD0010 | 2014-06-25 | 2014-07-01 | 2014-07-14 | 2014-07-21 | 2014-08-04 | P-SQUARE CONTRACTING & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107624 | Paaralang Elementarya ng Pal-Sico | SAN JUAN | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 4A0214S00086 | 14DD0053 | 2014-11-27 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 2015-01-07 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107627 | PAARALANG ELEMENTARYA NG PULANGBATO | San Juan West | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-13 |  | 4A0214S00129 | 15DD0179 | 2015-08-01 | 2015-08-07 | 2015-08-19 | 2015-08-27 | 2015-09-15 | UBAMOS CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107638 | Paaralang Elementarya ng Tipas | SAN JUAN | 4 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-11-16 | 2014-12-16 | 4A0214S00026 | 14DD0018 | 2014-06-30 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-12 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107794 | Panghayaan ES | TAYSAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107533 | Pansol ES | PADRE GARCIA | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-10-24 | 2014-10-24 | 4A0214S00037 | 14DD0009 | 2014-06-25 | 2014-07-01 | 2014-07-14 | 2014-07-21 | 2014-08-04 | RRE ERECTORs CONST. AND TRADING SPECIALIST
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301137 | Pinagbayanan NHS | TAYSAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-17 | 2014-10-17 | 4A0214S00021 | 14DD0017 | 2014-07-01 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-12 | TONIJON CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107536 | Quilo-Quilo North ES | PADRE GARCIA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-24 | 2014-10-24 | 4A0214S00036 | 14DD0009 | 2014-06-25 | 2014-07-01 | 2014-07-14 | 2014-07-21 | 2014-08-04 | RRE ERECTORs CONST. AND TRADING SPECIALIST
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107572 | Rosario West CS | ROSARIO | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-11-28 | 4A0214S00033 | 14DD0013 | 2014-07-22 | 2014-07-28 | 2014-08-11 | 2014-08-22 | 2014-09-05 | IKM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107576 | San Ignacio ES | ROSARIO | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6333839.7656 |  |  | COMPLETED | 1 | 2015-06-06 | 2015-06-06 | 4A0214S00100 | 14DD0051 | 2014-11-27 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 2015-01-07 | IKM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107365 | Talaibon ES | IBAAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-10-25 | 2014-10-25 | 4A0214S00038 | 14DD0015 | 2014-06-30 | 2014-07-07 | 2014-07-21 | 2014-07-28 | 2014-08-12 | P-SQUARE CONTRACTING & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 107579 | Tilaga ES | ROSARIO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 4A0214S00032 | 14DD0014 | 2014-07-22 | 2014-07-28 | 2014-08-11 | 2014-08-22 | 2014-09-05 | IKM BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301157 | Timbugan NHS | ROSARIO | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 4A0214S00030 | 14DD0010 | 2014-06-25 | 2014-07-01 | 2014-07-14 | 2014-07-21 | 2014-08-04 | P-SQUARE CONTRACTING & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Batangas | 301160 | Tipas NHS | SAN JUAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-27 | 2015-10-27 | 4A0214S00113 | 15DD0098 | 2015-06-19 | 2015-06-25 | 2015-07-07 | 2015-07-14 | 2015-07-29 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | Batangas | 163510 | Wenceslao I, Llana Memorial School (Aplaya Annex) | SAN JUAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-11-09 | 2014-12-09 | 4A0214S00025 | 14DD0012 | 2014-06-27 | 2014-07-04 | 2014-07-17 | 2014-07-24 | 2014-08-05 | STRUKTURA TEKNIKA SERVICES CO.
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301470 | Balete NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | COMPLETED | 1 | 2016-01-06 |  | 4A0214S00124 | 15DE0053 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | BERTO LUCCI BUILDERS & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 301472 | Batangas NHS | BATANGAS CITY (Capital) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14115218.3984 |  |  | COMPLETED | 1 | 2015-11-25 | 2015-11-25 | 4A0214S00084 | 14DE0048 | 2014-12-22 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | JASMIG CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301473 | Conde Labac NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 | 2015-12-12 | 2015-12-12 | 4A0214S00123 | 15DE0049 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 109603 | Dumuclay ES | BATANGAS CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4311999.6094 |  |  | COMPLETED | 1 | 2015-05-29 | 2015-05-29 | 4A0214S00081 | 14DE0044 | 2014-12-16 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | 6 JEWELS CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 308204 | Libjo National High School | Batangas City New District | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | COMPLETED | 1 | 2016-07-24 |  | 4A0214S00128 | 15DE0128 | 2015-11-30 | 2015-12-01 | 2015-12-15 | 2015-12-18 | 2015-12-28 | N.B. AVILA CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | COMPLETED | 1 | 2016-01-06 |  | 4A0214S00122 | 15DE0054 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | JV: OIC CONSTRUCTION & SUPPLY(FORMERLY:OIC CONST.)/NBL CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 | 2015-12-12 | 2015-12-12 | 4A0214S00121 | 15DE0050 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301475 | Pedro S. Tolentino MNHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6439337.6381 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 4A0214S00120 | 15DE0052 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | SANDSTORM CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 301476 | Pinamucan NHS | BATANGAS CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | [8 empty] | 2015-01-30 | 6 JEWELS CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15017518.84 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 109625 | Sta. Clara ES | BATANGAS CITY (Capital) | 2 | 1 | 14 | 2STY8CL & 2STY6CL | 2014 K10 BATCH 3 | 19536587.5781 |  |  | COMPLETED | 1 | 2015-11-25 | 2015-11-25 | 4A0214S00082 | 14DE0049 | 2014-12-22 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | V.R. PATRON BUILDERS & DEVELOPERS CORP. (PREVIOUSL
NC 2014 | K10 (2014) | Region IV-A | BATANGAS CITY | 308203 | Sta. Rita NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6379064.7656 |  |  | COMPLETED | 1 | 2015-08-27 | 2015-08-27 | 4A0214S00089 | 14DE0046 | 2014-12-22 | 2014-12-22 | 2015-01-06 | 2015-01-26 | 2015-01-30 | 6 JEWELS CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 301481 | Tabangao NHS | BATANGAS CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14967518.84 |  |  | COMPLETED | 1 | 2016-01-17 |  | 4A0214S00117 | 15DE0055 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | JASMIG CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region IV-A | BATANGAS CITY | 308202 | Tinga Sorosoro National High School (TISISI) | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6389337.6381 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 4A0214S00126 | 15DE0051 | 2015-06-10 | 2015-06-11 | 2015-06-26 | 2015-07-07 | 2015-07-16 | 6 JEWELS CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109864 | Barandal ES | Calamba City West | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | reverted | 0.001 | 2016-06-19 |  | 4A0414S00065 | 15DI0169 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109841 | Bunggo ES | Calamba City West | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | reverted | 0.001 |  |  | 4A0414S00060
NC 2014 | SHS (2014) | Region IV-A | Calamba City | 301515 | Calamba National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0414S00034 | 15DI0066 | 2015-06-03 | 2015-06-09 | 2015-06-10 | 2015-06-22 | 2015-06-26 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 308703 | Calamba National High School - Annex | Calamba City East II | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-19 |  | 4A0414S00068 | 15DI0170 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109830 | Crossing ES | Calamba City East II | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | reverted | 0.001 | 2016-03-21 |  | 4A0414S00059 | 15DI0167 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | PUREGOLD CONSTRUCTION & DEVT. CORP.
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109816 | Jose Platon MS | Calamba City East I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-21 |  | 4A0414S00088 | 15DI0166 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 301521 | Kapayapaan NHS | Calamba City West | 2 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4C | 21383013.45 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109818 | La Mesa Elementary School | Calamba City East I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-21 |  | 4A0414S00089 | 15DI0165 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109847 | Latian ES | Calamba City West | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-01 |  | 4A0414S00061 | 15DI0178 | 2015-11-05 | 2015-11-17 | 2015-11-18 | 2015-11-30 | 2015-12-04 | LAKE CITY BUILDER
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109848 | Lawa Elementary School | Calamba City West | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0414S00062 | 4A04-14-S-00062 | 2015-07-06 | 2015-07-18 | 2015-07-20 | 2015-07-23 | 2015-07-27 | 3W CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 301519 | Looc NHS | Calamba City East II | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4C | 22152343.62 |  |  | COMPLETED | 1 |  |  | 4A0414S00057 | 15DI0198 | [5 empty] | GAB-ZION ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109853 | Mapagong ES | Calamba City West | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | reverted | 0.001 |  |  | 4A0414S00063 | 4A04-14-S-00063
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109854 | Mayapa Elementary School | Calamba City West | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-19 |  | 4A0414S00073 | 15DI0168 | 2015-10-23 | 2015-11-04 | 2015-11-05 | 2015-11-20 | 2015-11-23 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109824 | Ronggot MG | Calamba City East I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | reverted | 0.001 |  |  | 4A0414S00066 | 4A04-14-S-00066
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 168501 | Southville VI ES | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15035522.3438 |  |  | COMPLETED | 1 | 2015-10-01 | 2015-10-01 | 4A0414S00010 | 4A04-14-S-00010 | 2014-12-03 | 2014-12-11 | 2014-12-22 | 2014-12-29 | 2015-01-05 | PROTECH CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109825 | Tiyani ES | Calamba City East I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 4A0414S00064 | 15DI0171 | 2015-10-29 | 2015-11-10 | 2015-11-11 | 2015-11-24 | 2015-11-27 | LAKE CITY BUILDER
NC 2014 | K10 (2014) | Region IV-A | Calamba City | 109827 | Turbina ES | Calamba City East I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-11-05 | 2015-11-05 | 4A0414S00081 | 4A04-14-S-00081 | 2015-07-06 | 2015-07-17 | 2015-07-18 | 2015-07-22 | 2015-07-27 | 3W CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108087 | Agustin Abadilla ES | ROSARIO | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10988343.5547 |  |  | COMPLETED | 1 | 2015-09-27 | 2015-09-27 | 4A0314S00050 | 14DF0071 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301172 | Bagbag NHS (Ligtong NHS) | ROSARIO | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14416618.3984 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108017 | Batong Dalig ES | Kawit | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-11 |  | 4A0314S00100 | 15DF0067 | 2015-07-14 | 2015-07-21 | 2015-08-07 | 2015-08-13 | 2015-08-24 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108090 | Mayor Calixto D. Enriquez ES | ROSARIO | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15105522.3438 |  |  | COMPLETED | 1 | 2015-09-27 | 2015-09-27 | 4A0314S00049 | 14DF0061 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | D.V. SALUD CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301208 | Noveleta NHS | NOVELETA | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-07 |  | 4A0314S00084 | 15DF0060 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108025 | Tramo ES | KAWIT | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-08-21 | 2015-08-21 | 4A0314S00051 | 14DF0058 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108100 | Bliss Elementary School | Silang I | 5 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0314S00099 | 15DG0040 | 2015-06-02 | 2015-06-14 | 2015-06-23 | 2015-07-15 | 2015-07-24 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301180 | Bulihan NHS | SILANG | 5 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301177 | Carmona NHS | CAVITE | 5 | 1 | 32 | 2UNITS 4STY16CL | 2014 K10 BATCH 4B | 53404938.84 |  |  | COMPLETED | 1 | 2016-09-11 |  | 4A0314S00082 | 15DF0098 | 2015-08-12 | 2015-08-19 | 2015-09-02 | 2015-09-08 | 2015-09-17 | JV: N.B. AVILA CONSTRUCTION/OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 107938 | F. De Castro ES | GEN. MARIANO ALVAREZ | 5 | 1 | 10 | 4STY8CL & 2STY2CL | 2014 K10 BATCH 3 | 19809421.9531 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 4A0314S00063 | 14DF0054 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 107939 | Family Village Resources ES (FVR) | GEN. MARIANO ALVAREZ | 5 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-21 |  | 4A0314S00081 | 15DF0055 | 2015-07-08 | 2015-07-15 | 2015-08-18 | 2015-08-25 | 2015-09-03 | FE S. REYES GENERAL CONTRACTOR
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301192 | Gen. Mariano Alvarez Tech. HS | GEN. MARIANO ALVAREZ | 5 | 1 | 32 | 2UNITS 4STY16CL | 2014 K10 BATCH 3 | 55541781.25 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108105 | Kasuyan ES (Kasuyan-Ilang Ilang ES) | SILANG | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-06-08 | 2015-06-08 | 4A0314S00069 | 14DG0059 | 2014-11-24 | 2014-12-06 | 2014-12-12 | 2014-12-26 | 2015-01-10 | N.B. AVILA CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301202 | Lumil NHS | SILANG | 5 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-14 |  | 4A0314S00088 | 15DG0050 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-07-31 | 2015-08-18 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108108 | Maguyam ES | SILANG | 5 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 976813.0464 |  |  | COMPLETED | 1 | 2015-02-28 | 2015-02-28 | 4A0314S00059 | 14DG0043 | 2014-10-29 | 2014-11-10 | 2014-11-19 | 2014-12-04 | 2014-12-16 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301205 | Munting Ilog NHS | Silang II | 5 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 307813 | Munting Ilog NHS (Silang West Annex) | SILANG | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15115522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 107940 | San Gabriel I ES | GEN. MARIANO ALVAREZ | 5 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00062 | 14DF0055 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301213 | San Jose Community HS | GEN. MARIANO ALVAREZ | 5 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15517522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108155 | Amaya ES | TANZA | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15216022.3438 |  |  | COMPLETED | 1 | 2015-11-21 | 2015-11-21 | 4A0314S00008 | 14DF0050 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108159 | Antonio B. del Rosario Sr. Mem. Elementary School | TANZA | 6 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27590390.625 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00010 | 14DF0106 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108179 | Bagong Pook ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10847593.5547 |  |  | COMPLETED | 1 | 2016-01-07 |  | 4A0314S00033 | 14DF0067 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 164008 | Belvedere ES | GENERAL TRIAS | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-12 | 2015-07-12 | 4A0314S00054 | 14DF0048 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | VRV CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 307808 | Francisco Osorio NHS (Trece Martires City NHS (Osorio Annex)) | TRECE MARTIRES CITY (Capital) | 6 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-18 |  | 4A0314S00089 | 15DF0058 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 107947 | Gen. Trias MES | GENERAL TRIAS | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 4A0314S00057 | 14DF0052 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 307801 | Gov. Ferrer MNHS (Biclatan Annex) | General Trias I | 6 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-09-19 |  | 4A0314S00103 | 15DF0141 | 2015-10-01 | 2015-10-08 | 2015-10-20 | 2015-10-26 | 2015-11-04 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 307802 | Gov. Ferrer MNHS (Buenavista Annex) | GENERAL TRIAS | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-12 | 2015-07-12 | 4A0314S00013 | 14DF0048 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108157 | Gregorio B. Fojas MS (Calibuyo ES) | TANZA | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10747093.5547 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 4A0314S00009 | 14DF0056 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108164 | Julugan ES | TANZA | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 11199343.5547 |  |  | COMPLETED | 1 | 2015-06-01 | 2015-05-31 | 4A0314S00011 | 14DF0056 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 307809 | Luis Aguado NHS (Southville NHS) | Trece Martirez City | 6 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4C | 22152343.62 |  |  | COMPLETED | 1 | 2016-07-13 |  | 4A0314S00109 | 15DF0093 | 2015-08-12 | 2015-08-19 | 2015-09-02 | 2015-09-08 | 2015-09-17 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 107961 | Mary Cris ES | General Trias II | 6 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-30 |  | 4A0314S00097 | 15DF0088 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108185 | Osorio ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-09-07 | 2015-09-07 | 4A0314S00032 | 14DF0060 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108165 | Paradahan ES | TANZA | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15316522.3438 |  |  | COMPLETED | 1 | 2016-01-27 |  | 4A0314S00012 | 14DF0063 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 107954 | Pasong Kawayan II ES | GENERAL TRIAS | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 4A0314S00056 | 14DF0052 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 107965 | San Francisco ES | GENERAL TRIAS | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-01 | 2015-07-01 | 4A0314S00055 | 14DF0052 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 301214 | Santiago National High School | General Trias II | 6 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-05-11 |  | 4A0314S00098 | 15DF0081 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | D.V. SALUD CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108168 | Santol ES | TANZA | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 164017 | Sunny Brooke ES | GENERAL TRIAS | 6 | 1 | 16 | 2UNITS 4STY8CL | 2014 K10 BATCH 3 | 30231044.6875 |  |  | COMPLETED | 1 | 2015-11-21 | 2015-11-21 | 4A0314S00061 | 14DF0107 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-11 | 2015-02-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301218 | Tanza NCHS | TANZA | 6 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15115522.3438 |  |  | COMPLETED | 1 | 2015-09-27 | 2015-09-27 | 4A0314S00034 | 14DF0062 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 307817 | Tanza NTS Annex | TANZA | 6 | 1 | 24 | 2UNITS 4STY12CL | 2014 K10 BATCH 4B | 44304687.24 |  |  | COMPLETED | 1 | 2016-10-22 |  | 4A0314S00073 | 15DF0137 | 2015-09-24 | 2015-10-01 | 2015-10-13 | 2015-10-19 | 2015-10-28 | JV: KLDS TRADING & CONSTRUCTION/R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108187 | Trece Martirez City ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4342149.6094 |  |  | COMPLETED | 1 | 2015-09-07 | 2015-09-07 | 4A0314S00023 | 14DF0067 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301222 | Trece Martirez City NHS | TRECE MARTIRES CITY (Capital) | 6 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 19941783.5938 |  |  | COMPLETED | 1 | 2015-09-15 | 2015-09-15 | 4A0314S00031 | 14DF0068 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 307819 | Trece Martirez City NHS (Cabezas Annex) | TRECE MARTIRES CITY (Capital) | 6 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 976813.0464 |  |  | COMPLETED | 1 | 2015-06-07 | 2015-03-31 | 4A0314S00007 | 14DF0067 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108171 | Tres Cruses ES | TANZA | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10747093.5547 |  |  | COMPLETED | 1 | 2015-09-07 | 2015-09-07 | 4A0314S00025 | 14DF0060 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 107967 | Tropical Village ES | General Trias II | 6 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-02 |  | 4A0314S00096 | 15DF0096 | 2015-08-12 | 2015-08-19 | 2015-09-02 | 2015-09-08 | 2015-09-17 | D.V. SALUD CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | GENERAL TRIAS CITY | 301223 | Tropical Village National High School | General Trias II | 6 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-05-11 |  | 4A0314S00102 | 15DF0081 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | D.V. SALUD CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301165 | Alfonso NHS | ALFONSO | 8 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-01-05 |  | 4A0314S00090 | 15DG0059 | 2015-07-27 | 2015-08-08 | 2015-08-18 | 2015-08-28 | 2015-09-08 | HAUSLAND CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301173 | Bendita NHS | MAGALLANES | 8 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-02-13 |  | 4A0314S00091 | 15DG0049 | 2015-07-02 | 2015-07-14 | 2015-07-22 | 2015-08-03 | 2015-08-13 | HAUSLAND CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301178 | Cavite Nat'l. Science HS | MARAGONDON | 8 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0314S00092 | 15DG0045 | 2015-06-19 | 2015-07-04 | 2015-07-09 | 2015-07-29 | 2015-08-06 | N.B. AVILA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 107996 | Kayquit ES | Indang I | 7 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-02-03 |  | 4A0314S00105 | 15DG0046 | 2015-06-22 | 2015-07-04 | 2015-07-09 | 2015-07-28 | 2015-08-06 | OMNICON BUILDERS
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301198 | Kaytitinga NHS | ALFONSO | 8 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 15097518.84 |  |  | COMPLETED | 1 | 2016-02-02 |  | 4A0314S00093 | 15DG0048 | 2015-06-22 | 2015-07-04 | 2015-07-09 | 2015-07-21 | 2015-08-06 | HAUSLAND CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301200 | Lumampong NHS | INDANG | 7 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0314S00095 | 15DG0044 | 2015-06-19 | 2015-07-04 | 2015-07-09 | 2015-07-27 | 2015-08-07 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 107933 | Lumipa ES | General E. Aguinaldo | 8 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0314S00104 | 15DG0043 | 2015-05-26 | 2015-06-07 | 2015-06-23 | 2015-07-15 | 2015-07-24 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108146 | Maharlika ES | Tagaytay City | 8 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0314S00107 | 15DG0038 | 2015-06-02 | 2015-06-14 | 2015-06-22 | 2015-07-15 | 2015-07-24 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108043 | Maragondon ES | MARAGONDON | 8 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | COMPLETED | 1 | 2015-06-08 | 2015-06-08 | 4A0314S00071 | 14DG0060 | 2014-11-06 | 2014-11-18 | 2014-12-12 | 2015-01-05 | 2015-01-10 | PGM CONSTRUCTION & PLUMBING SERVICES
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108015 | Mataas Na Lupa ES | Indang II | 7 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0314S00106 | 15DG0042 | 2015-06-02 | 2015-06-14 | 2015-06-22 | 2015-07-15 | 2015-07-24 | MIRASOL M. MEDINA CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 301206 | Naic Coastal NHS | NAIC | 8 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3760805.49 |  |  | COMPLETED | 1 | 2014-12-13 | 2014-12-13 | 4A0314S00004 | 14DG0011 | 2014-06-17 | 2014-06-29 | 2014-07-08 | 2014-07-22 | 2014-08-16 | DALEBO CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 307810 | Naic NHS-Sabang Annex | NAIC | 8 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-09-28 | 2014-09-28 | 4A0314S00005 | 14DG0010 | 2014-06-17 | 2014-06-29 | 2014-07-08 | 2014-07-21 | 2014-08-15 | DALEBO CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region IV-A | CAVITE | 108150 | Patutong Malaki ES | Tagaytay City | 8 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0314S00108 | 4A03-14-S-00108
NC 2014 | SHS (2014) | Region IV-A | CAVITE | 301221 | Ternate NHS | TERNATE | 8 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-03 |  | 4A0314S00086 | 15DG0047 | 2015-06-22 | 2015-07-04 | 2015-07-09 | 2015-07-21 | 2015-08-06 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109634 | Bagumbuhay ES | CAVITE CITY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1803338.6441 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-03-31 | 4A0314S00029 | 14DF0058 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109635 | Dalahican Elem. School | CAVITE CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-08-21 | 2015-08-21 | 4A0314S00028 | 14DF0058 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109637 | Manuel S. Rojas ES | CAVITE CITY | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-06-07 |  | 4A0314S00079 | 15DF0060 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG | Working for building permit
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109633 | Ovidio S. Dela Rosa ES | Cavite City II District | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 4C | 21383013.45 |  |  | COMPLETED | 1 | 2016-07-14 |  | 4A0314S00114 | 15DF0099 | 2015-08-13 | 2015-08-20 | 2015-09-04 | 2015-09-10 | 2015-09-18 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109630 | Porta Vaga ES | CAVITE CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00030 | 14DF0058 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 109638 | San Lorenzo Ruiz ES | Cavite City III District | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-11 |  | 4A0314S00112 | 15DF0067 | 2015-07-14 | 2015-07-21 | 2015-08-07 | 2015-08-13 | 2015-08-24 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | CAVITE CITY | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6479164.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | CITY OF BIÑAN | 301230 | Biñan National High School | CITY OF BIÑAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0414S00039 | 15DI0182 | [5 empty] | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 307915 | Dela Paz NHS (Binan NHS - Annex) | Biñan | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0414S00056 | 4A04-14-S-00056 | 2015-12-03 | 2015-12-15 | 2015-12-16
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 164511 | Dr. Jose Tamayo MES | Biñan | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | Reverted | 0 |  |  | 4A0414S00074 | 4A04-14-S-00074
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108220 | Ganado ES | Biñan | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-20 |  | 4A0414S00070 | 15DI0116 | 2015-08-12 | 2015-08-24 | 2015-08-26 | 2015-09-08 | 2015-09-23 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108221 | Langkiwa ES | Biñan | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-22 |  | 4A0414S00071 | 15DI0106 | 2015-07-20 | 2015-08-03 | 2015-08-05 | 2015-08-20 | 2015-08-26 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108222 | Loma ES | Biñan | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-01-12 |  | 4A0414S00072 | 15DI0110 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-11 | 2015-09-15 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 164513 | Malaban East ES | Biñan | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 |  |  | 4A0414S00090 | 15DI0185 | 2015-11-05 | 2015-11-17 | 2015-11-18 |  |  | 3RB CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108224 | Mampalasan ES | Biñan | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-12 |  | 4A0414S00052 | 15DI0109 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-03 | 2015-09-15 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108214 | Our Lady of Lourdes ES (Brgy. Malamig PS) | Biñan | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | Reverted | 0 |  |  | 4A0414S00069 | 4A04-14-S-00069
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108225 | Pagkakaisa ES | Biñan | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-06 |  | 4A0414S00087 | 15DI0120 | 2015-09-10 | 2015-09-21 | 2015-09-22 | 2015-10-02 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 108232 | Timbao ES | CITY OF BIÑAN | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4A | 4291899.6144 |  |  | Reverted | 0 |  |  | 4A0414S00026 | 4A04-14-S-00026
NC 2014 | K10 (2014) | Region IV-A | CITY OF BIÑAN | 164512 | Zapote ES | Biñan | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | Reverted | 0 |  |  | 4A0414S00082 | 4A04-14-S-00082
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107916 | Burol Elementary School | Dasmariñas II | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-25 |  | 4A0314S00116 | 15DF0064 | 2015-07-14 | 2015-07-21 | 2015-08-04 | 2015-08-10 | 2015-08-19 | RAMON F. JAVALERA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 301179 | Congressional NHS | CITY OF DASMARIÑAS | 4 | 1 | 20 | 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 36092805.9375 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0314S00019 | 14DF0112 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | KLDS TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 301183 | Dasmarinas East NHS (Annex C) | CITY OF DASMARIÑAS | 4 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 3 | 27479390.625 |  |  | COMPLETED | 1 | [9 empty] | Baq Prince Construction
NC 2014 | SHS (2014) | Region IV-A | Dasmarinas City | 301183 | Dasmarinas East NHS (Annex C) | CITY OF DASMARIÑAS | 4 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | [9 empty] | J.S. General Contractor
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107917 | Dasmariñas II CS (Dasmariñas BBES B) | CITY OF DASMARIÑAS | 4 | 1 | 28 | 4STY20CL & 4STY8CL | 2014 K10 BATCH 3 | 48232106.7188 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00035 | 14DF0116 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | KLDS TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 301185 | Dasmariñas West NHS (Annex J) | CITY OF DASMARIÑAS | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15628022.3438 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 4A0314S00016 | 14DF0051 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107900 | Delfin J. Jaranilla Elementary School | Dasmariñas I | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-25 |  | 4A0314S00113 | 15DF0062 | 2015-07-14 | 2015-07-21 | 2015-08-04 | 2015-08-10 | 2015-08-19 | HAUSLAND CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107902 | Francisco E. Barzaga MS | CITY OF DASMARIÑAS | 4 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4B | 26702469.42 |  |  | COMPLETED | 1 | 2016-07-10 |  | 4A0314S00078 | 15DF0083 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 325901 | Langkaan II National High School | CITY OF DASMARIÑAS | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-06-07 |  | 4A0314S00076 | 15DF0061 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 301187 | Pag-asa NHS (Dasmarinas NHS - Pag-asa Annex) | Dasmariñas I | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-25 |  | 4A0314S00110 | 15DF0065 | 2015-07-14 | 2015-07-21 | 2015-08-04 | 2015-08-10 | 2015-08-19 | CBS CONSTRUCTION AND CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 325902 | Paliparan II National High School - Congressional Annex | CITY OF DASMARIÑAS | 4 | 1 | 24 | 4STY16CL & 4STY8CL | 2014 K10 BATCH 3 | 43519912.9688 |  |  | COMPLETED | 1 | 2016-01-30 |  | 4A0314S00045 | 14DF0113 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | JV: KLDS TRADING & CONSTRUCTION/R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107908 | Paliparan III ES | CITY OF DASMARIÑAS | 4 | 1 | 28 | 4STY20CL & 4STY8CL | 2014 K10 BATCH 3 | 47327606.7188 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00026 | 14DF0115 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | KLDS TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 301182 | Paliparan NHS (Dasmarinas NHS - Paliparan Annex) | CITY OF DASMARIÑAS | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15125522.3438 |  |  | COMPLETED | 1 | 2015-08-21 | 2015-08-21 | 4A0314S00018 | 14DF0049 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | R.S. GATBONTON CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107911 | Sabang ES | CITY OF DASMARIÑAS | 4 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20152783.5938 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0314S00014 | 14DF0102 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107912 | Salawag ES | CITY OF DASMARIÑAS | 4 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 19951783.5938 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 4A0314S00024 | 14DF0069 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107924 | Salitran ES | CITY OF DASMARIÑAS | 4 | 1 | 20 | 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 35188305.9375 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0314S00020 | 14DF0111 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107922 | San Miguel ES (Dasmariñas BBES A-3) | CITY OF DASMARIÑAS | 4 | 1 | 20 | 4STY12CL & 4STY8CL | 2014 K10 BATCH 3 | 34987305.9375 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0314S00021 | 14DF0110 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107919 | San Nicolas ES (Dasmariñas BBES D) | CITY OF DASMARIÑAS | 4 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 3 | 31990584.375 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00022 | 14DF0109 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | CAVDEAL-CAVITE IDEAL INTL. CONST. & DEVT. CORP.
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107918 | Sta. Cristina ES (Dasmariñas BBES C) | CITY OF DASMARIÑAS | 4 | 1 | 24 | 4STY24CL | 2014 K10 BATCH 4B | 35596257.14 |  |  | COMPLETED | 1 | 2016-07-30 |  | 4A0314S00077 | 15DF0090 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107913 | V. P. Villanueva MS (Palapala) | CITY OF DASMARIÑAS | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4B | 14897518.84 |  |  | COMPLETED | 1 | 2016-06-07 |  | 4A0314S00075 | 15DF0061 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | R.A. DEL ROSARIO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Dasmarinas City | 107914 | Z. H. Gana Mem. Sch. (San Jose) | Dasmariñas I | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-25 |  | 4A0314S00115 | 15DF0063 | 2015-07-14 | 2015-07-21 | 2015-08-04 | 2015-08-10 | 2015-08-19 | ALMAKAR BUILDERS & METAL WORKS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 107981 | Alapan II ES | IMUS | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-07-21 | 2015-07-21 | 4A0314S00015 | 14DF0057 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-14 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 107969 | Anabu II Elementary School | IMUS | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-28 |  | 4A0314S00085 | 15DF0056 | 2015-07-08 | 2015-07-15 | 2015-07-28 | 2015-08-03 | 2015-08-12 | N.B. AVILA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Imus City | 107972 | Buhay Na Tubig ES | IMUS | 3 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15517522.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Imus City | 107982 | Bukandala ES | IMUS | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 11098843.5547 |  |  | COMPLETED | 1 | 2015-09-07 | 2015-09-07 | 4A0314S00043 | 14DF0059 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 307811 | Gen. Aguinaldo NHS-Annex | IMUS | 3 | 1 | 22 | 2UNITS 4STY8CL & 3STY6CL | 2014 K10 BATCH 3 | 26143615.8984 |  |  | COMPLETED | 1 | 2016-01-12 |  | 4A0314S00065 | 14DF0104 | 2014-10-30 | 2014-11-07 | 2015-01-20 | 2015-01-26 | 2015-02-04 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 301190 | Gen. Emilio Aguinaldo NHS (Imus) | IMUS | 3 | 1 | 32 | 2UNITS 4STY16CL | 2014 K10 BATCH 3 | 54938781.25 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00066 | 14DF0117 | 2014-10-30 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | Imus City | 307821 | Imus NHS (Greengate Annex) | IMUS | 3 | 1 | 28 | 4STY20CL & 4STY8CL | 2014 K10 BATCH 3 | 47096106.7188 |  |  | COMPLETED | 1 | 2016-02-08 |  | 4A0314S00064 | 14DF0114 | 2014-10-31 | 2014-11-07 | 2015-01-29 | 2015-02-04 | 2015-02-13 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 107986 | Malagasang I ES | IMUS | 3 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15517522.3438 |  |  | COMPLETED | 1 | 2015-09-27 | 2015-09-27 | 4A0314S00037 | 14DF0066 | 2014-10-14 | 2014-10-21 | 2014-11-04 | 2014-11-10 | 2014-11-19 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Imus City | 164002 | Palico ES | Imus I | 3 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-03 |  | 4A0314S00118 | 15DF0102 | 2015-08-13 | 2015-08-20 | 2015-09-04 | 2015-09-10 | 2015-09-18 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 164003 | Pasong Buaya II ES | IMUS | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10747093.5547 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 4A0314S00068 | 14DF0057 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Imus City | 164019 | Pasong Santol ES (Golden City Annex) | IMUS | 3 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-08-21 | 2015-08-21 | 4A0314S00067 | 14DF0057 | 2014-10-09 | 2014-10-17 | 2014-10-29 | 2014-11-04 | 2014-11-13 | OMNICON BUILDERS
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108234 | Baclaran ES | Cabuyao | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | Reverted | 0.001 |  |  | 4A0414S00086 | 4A04-14-S-00086
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108425 | Magsaysay ES | San Pedro | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | Reverted | 0.001 |  |  | 4A0414S00085 | 4A04-14-S-00085
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108426 | Pacita Complex I ES | San Pedro | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | COMPLETED | 1 | 2016-03-20 |  | 4A0414S00084 | 15DI0117 | 2015-08-12 | 2015-08-24 | 2015-08-26 | 2015-09-21 | 2015-09-23 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | Laguna | 301261 | Sampaguita Vill. NHS | SAN PEDRO | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4B | 15121327.92 |  |  | COMPLETED | 1 | 2016-01-19 |  | 4A0414S00030 | 4A04-14-S-00030 | 2015-07-07 | 2015-07-20 | 2015-07-21 | 2015-07-24 | 2015-07-29 | 3W CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108432 | San Pedro CES | SAN PEDRO | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4A | 10667093.5572 |  |  | COMPLETED | 1 | 2015-08-02 | 2015-08-02 | 4A0414S00025 | 14DI0071 | 2014-11-28 | 2014-12-15 | 2014-12-17 | 2014-12-23 | 2015-01-05 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | Laguna | 307907 | San Pedro Relocation Center National High School, Main (Langgam) Campus | SAN PEDRO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0414S00033 | 15DI0183 | [5 empty] | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Laguna | 164528 | Southville 3A ES | San Pedro | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-23 |  | 4A0414S00080 | 15DI0175 | 2015-10-29 | 2015-11-10 | 2015-11-11 | 2015-11-24 | 2015-11-27 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108239 | Cabuyao Cs | CABUYAO | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 11018493.5547 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 4A0414S00023 | 14DI0069 | 2014-11-28 | 2014-12-09 | 2014-12-17 | 2015-01-05 | 2015-01-05 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301234 | Cabuyao NHS | CABUYAO | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4A0414S00040 | 15DI0122 | 2015-09-18 | 2015-09-30 | 2015-10-01 | 2015-10-05 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108244 | Mamatid ES | CABUYAO | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 11088843.5547 |  |  | COMPLETED | 1 | 2015-08-27 | 2015-08-27 | 4A0414S00011 | 4A04-14-S-00011 | 2014-12-05 | 2014-12-10 | 2014-12-17 | 2014-12-23 | 2014-12-29 | L.P.O. ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108245 | Marinig South ES | CABUYAO | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15738672.3438 |  |  | COMPLETED | 1 | 2015-10-30 | 2015-10-30 | 4A0414S00012 | 4A04-14-S-00012 | 2014-12-04 | 2014-12-06 | 2014-12-22 | 2014-12-23 | 2015-01-05 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301262 | Nicolas L. Galvez Mem. NHS (San Antonio NHS) | BAY | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0414S00042 | 15DI0184 | [5 empty] | PROTECH CONSTRUCTION & DEVELOPMENT CORP. (FORMERLY
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108312 | P. Rizal ES (Putho ES) | Los Baños | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-20 |  | 4A0414S00079 | 15DI0114 | 2015-08-31 | 2015-09-07 | 2015-09-08 | 2015-09-21 | 2015-09-23 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108249 | Pulo ES | CABUYAO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0414S00031 | 15DI0073 | 2015-06-16 | 2015-06-24 | 2015-06-25 | 2015-07-02 | 2015-07-08 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Laguna | 164516 | Southville I ES | CABUYAO | 2 | 1 | 12 | 3STY9CL & 3STY3CL | 2014 K10 BATCH 3 | 21710472.0312 |  |  | COMPLETED | 1 | 2016-01-31 |  | 4A0414S00013 | 15DI0067 | 2015-06-02 | 2015-06-09 | 2015-06-10 | 2015-06-23 | 2015-06-26 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | Laguna | 307923 | Southville I NHS | CABUYAO | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20132783.5938 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108495 | Banca-Banca ES | VICTORIA | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-05 | 4A0414S00008 | 14dp0011 | 2014-06-30 | 2014-07-14 | 2014-07-24 | 2014-08-08 | 2014-08-22 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108496 | G. Herradura ES (Nanhaya ES) | Victoria | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-18 |  | 4A0414S00058 | 15DP0065 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | JMK BUILDERS CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108259 | Lamot ES - Annex | CALAUAN | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-29 | 2014-11-05 | 4A0414S00004 | 14DP0010 | 2014-06-30 | 2014-07-14 | 2014-07-24 | 2014-08-04 | 2014-08-22 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2014 | K10 (2014) | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6389114.7656 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10667131.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108366 | Santa Lucia ES | NAGCARLAN | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-28 | 2015-04-28 | 4A0414S00017 | 14DP0052 | 2014-12-13 | 2014-12-25 | 2014-12-16 | 2014-12-29 | 2015-01-14 | T.A.D. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301226 | Balian NHS | PANGIL | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10467131.51 |  |  | COMPLETED | 1 | 2016-03-31 |  | 4A0414S00044 | 15DH0050 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108345 | Bukal ES | MAJAYJAY | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4A0414S00016 | 14DH0036 | 2014-11-03 | 2014-12-05 | 2014-12-19 | 2014-12-23 | 2015-01-08 | J.B. ALARCON ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108396 | Galalan ES | PANGIL | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4367274.6094 |  |  | COMPLETED | 1 | 2015-04-08 | 2015-04-08 | 4A0414S00018 | 14DH0038 | 2014-12-03 | 2014-12-05 | 2014-12-19 | 2014-12-23 | 2015-01-08 | J.B. ALARCON ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108276 | Inao-Awan ES | CAVINTI | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-11-15 | 2014-11-15 | 4A0414S00005 | 14DH0002 | 2014-06-19 | 2014-06-20 | 2014-07-04 | 2014-07-18 | 2014-07-28 | R CEL GENERAL CONTRACTOR & GEN MERCHANDISE
NC 2014 | K10 (2014) | Region IV-A | Laguna | 301243 | Kabulusan National High School | PAKIL | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108407 | Labuin ES | PILA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 4A0414S00006 | 14DH0003 | 2014-06-19 | 2014-06-20 | 2014-07-04 | 2014-07-18 | 2014-07-28 | R CEL GENERAL CONTRACTOR & GEN MERCHANDISE
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301279 | Lumban NHS | LUMBAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-31 |  | 4A0414S00045 | 15DH0051 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108441 | Oogong ES | Santa Cruz | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-03 | 2015-12-03 | 4A0414S00077 | 15DH0036 | 2015-06-22 | 2015-07-02 | 2015-07-14 | 2015-07-28 | 2015-08-05 | JOBEL ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108442 | Pagsawitan ES | Santa Cruz | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0414S00076 | 15DH0037 | 2015-06-22 | 2015-07-02 | 2015-07-14 | 2015-07-28 | 2015-08-05 | ENC ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 307913 | Poten & Eliseo M. Quesada Memo. NHS | Paete | 4 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0.001 |  |  | 4A0414S00083 | 15DH00100
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108386 | Sampaloc ES | Pagsanjan | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-03 |  | 4A0414S00078 | 15DH0035 | 2015-06-22 | 2015-07-02 | 2015-07-14 | 2015-07-28 | 2015-08-05 | D.M. CATIGNAS ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | Laguna | 108415 | San Miguel ES | PILA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | Laguna | 301273 | Siniloan NHS | SINILOAN | 4 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10617131.51 |  |  | COMPLETED | 1 | 2016-03-31 |  | 4A0414S00046 | 15DH0052 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Laguna | 301269 | Sta. Maria NHS | SANTA MARIA | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | Laguna | 164505 | Tubog ES | Paete | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-12 |  | 4A0414S00075 | 15DH0082 | 2015-10-23 | 2015-11-04 | 2015-11-16 | 2015-11-27 | 2015-12-14 | JOBEL ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | LIPA CITY | 109676 | Labac ES | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4311999.6094 |  |  | COMPLETED | 1 | 2015-05-07 | 2015-05-07 | 4A0214S00087 | 14DD0054 | 2014-11-27 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 2015-01-07 | VRV CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | LIPA CITY | 301493 | Lipa City NHS | Lipa City West District | 4 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0.001 |  |  | 4A0214S00135 | elem & jhs batch 4c
NC 2014 | K10 (2014) | Region IV-A | LIPA CITY | 109702 | Tagbakin PS | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4311999.6094 |  |  | COMPLETED | 1 | 2016-02-07 |  | 4A0214S00085 | 15DD0055 | 2014-11-27 | 2014-12-03 | 2014-12-15 | 2014-12-19 | 2015-01-07 | VRV CONSTRUCTION AND TRADING
NC 2014 | SHS (2014) | Region IV-A | LUCENA CITY | 308502 | Cotta National High School | LUCENA CITY (Capital) | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1 | 2016-04-15 |  | 4A0514S00163 | 15DJ0050 | 2015-06-28 | 2015-06-29 | 2015-07-14 | 2015-07-21 | 2015-07-24 | JEMAK CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 167503 | Dalahican ES Annex | LUCENA CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-05 |  | 4A0514S00071 | 15DJ0044 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-10 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109718 | Elvira Razon Aranilla ES | Lucena North District | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-05 |  | 4A0514S00170 | 15DJ0052 | 2015-07-01 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-28 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | LUCENA CITY | 308504 | Gulang-Gulang NHS - Iba. Talim Ext. | LUCENA CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-25 |  | 4A0514S00164 | 15DJ0026 | 2015-05-26 | 2015-05-27 | 2015-06-09 | 2015-06-17 | 2015-06-22 | R.T.Y. CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 308506 | LCNHS-Ransohan Extension | LUCENA CITY (Capital) | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 4A0514S00019 | 14DJ012 | 2014-06-30 | 2014-07-01 | 2014-07-15 | 2014-07-22 | 2014-08-11 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 301501 | Lucena City National High School - Ibabang Dupay | LUCENA CITY (Capital) | 2 | 1 | 40 | 2UNITS 4STY20CL | 2014 K10 BATCH 3 | 63876168.75 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109707 | Lucena East I ES | LUCENA CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15110522.3438 |  |  | COMPLETED | 1 | 2015-12-25 | 2015-12-25 | 4A0514S00064 | 4A05-14-S-00064 | 2014-12-04 | 2014-12-05 | 2014-12-18 | 2014-12-21 | 2015-01-06 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109721 | Lucena North I ES | LUCENA CITY (Capital) | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15160772.3438 |  |  | COMPLETED | 1 | 2015-12-15 | 2015-12-15 | 4A0514S00063 | 4A05-14-S-00063 | 2014-12-04 | 2014-12-05 | 2014-12-18 | 2014-12-21 | 2015-01-07 | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109744 | Lucena West III ES | LUCENA CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-05 |  | 4A0514S00076 | 15DJ0043 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-10 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109724 | Reymar Compound ES | Lucena North District | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-05 |  | 4A0514S00174 | 15DJ0051 | 2015-07-01 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-28 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | LUCENA CITY | 109725 | San Lorenzo ES | Lucena North District | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 4A0514S00171 | 15DJ0059 | 2015-07-06 | 2015-07-07 | 2015-07-21 | 2015-07-27 | 2015-07-29 | L.A. CLAMOR CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 165007 | Agos-agos ES |  | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-23 | 2016-02-22 | 4A0514S00175 | 15DK0063 | 2015-07-17 | 2015-07-22 | 2015-08-04 | 2015-08-14 | 2015-08-27 | ALT CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108558 | Anibawan ES | BURDEOS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-01-21 | 4A0514S00021 | 14DK0036 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301292 | Batangan NHS | GENERAL NAKAR | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-30 | 4A0514S00020 | 14DK0040 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | R.L. COLICO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109024 | Binibitinan ES | POLILLO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00027 | 14DK0043 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 500028 | BinulAsan IS | INFANTA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-02 | 2016-03-01 | 4A0514S00111 | 15DK0068 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-14 | 2015-09-04 | PRECIOUS CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109027 | Bucao ES | POLILLO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 4A0514S00004 | 14DK0043 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-12 | 2016-02-12 | 4A0514S00099 | 15DK0075 | 2015-08-05 | 2015-08-07 | 2014-08-24 | 2015-09-03 | 2015-09-16 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2015-01-11 | 4A0514S00024 | 14DK0037 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301301 | Cagbalete Island NHS | MAUBAN | 1 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-28 | 2015-10-28 | 4A0514S00140 | 15DK0051 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-20 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108906 | Cagsiay I ES | MAUBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308005 | Cagsiay I NHS | MAUBAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-10 | 2015-12-10 | 4A0514S00100 | 15DK0057 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | BOMEL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108908 | Cagsiay III ES | Mauban South | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-23 | 2016-01-23 | 4A0514S00173 | 15DK0064 | 2015-07-17 | 2015-07-22 | 2015-08-04 | 2015-08-14 | 2015-08-27 | BOMEL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108564 | Calutcot ES | BURDEOS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-11 | 2015-01-11 | 4A0514S00022 | 14DK0036 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109029 | Canicanian ES | POLILLO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 4A0514S00005 | 14DK0044 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108565 | Caniwan ES | BURDEOS | 1 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00023 | 14DK0037 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108891 | Concepcion ES | MAUBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 4A0514S00033 | 14DK0041 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108785 | Dinahican ES | INFANTA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00030 | 14DK0040 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | R.L. COLICO CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-05-17 | 2016-08-15 | 4A0514S00165 | 15DK0069 | 2015-10-08 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | C.J. CONSTRUCTION INC.
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-12-22 | 4A0514S0035 | 14DK0041 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301332 | Infanta NHS | INFANTA | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1 | 2016-02-12 | 2016-02-12 | 4A0514S00102 | 15DK0076 | 2015-07-29 | 2015-08-07 | 2014-08-24 | 2015-09-03 | 2015-09-16 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301332 | Infanta NHS | INFANTA | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-30 | 4A0514S00031 | 14DK0040 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | R.L. COLICO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108709 | Lagmak ES | GENERAL NAKAR | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2015-12-24 | 4A0514S00083 | 15DK0066 | 2015-07-17 | 2015-07-22 | 2015-08-04 | 2015-08-14 | 2015-08-27 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301344 | Libo NHS | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6669337.6381 |  |  | COMPLETED | 1 | 2015-12-17 | 2015-12-17 | 4A0514S00103 | 15DK0056 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-20 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 308029 | Libo NHS - Bonbon Annex | PANUKULAN | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-21 | 2015-01-21 | 4A0514S00029 | 14DK0043 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308007 | Liwayway NHS | MAUBAN | 1 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-16 | 2015-12-17 | 4A0514S00104 | 15DK0058 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-20 | BOMEL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108711 | Lumutan ES | Gen. Nakar | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-09 | 2016-02-08 | 4A0514S00172 | 15DK0065 | 2015-07-17 | 2015-07-22 | 2015-08-04 | 2015-08-14 | 2015-08-27 | ANNCON BUILDERS
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301350 | Manuel S. Enverga Memorial School of Arts and Trades | MAUBAN | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-18 | 2016-04-18 | 4A0514S00196 | 15DK0070 | 2015-10-08 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | C.J. CONSTRUCTION INC.
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109072 | Maunlad ES | Real | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | Reverted | 0 | 2016-01-31 |  | 4A0514S00183 | 4A05-14-S-00183 | 2015-12-23 | 2015-01-06 | 2016-01-19
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109038 | Milawid ES | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-03-11 | 2015-03-11 | 4A0514S00061 | 4A05-14-S-00061 | 2014-11-12 | 2014-11-20 | 2014-12-02 | 2014-12-09 | 2014-12-22 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109240 | North Palale ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-11-30 | 4A0514S00025 | 14DK0038 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10567131.51 |  |  | COMPLETED | 1 | 2016-03-02 | 2016-03-01 | 4A0514S00106 | 15DK0071 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-19 | 2015-09-04 | W.J. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-28 | 2015-09-28 | 4A0514S00098 | 15DK0052 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-17 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-06-08 |  | 4A0514S00108 | 15DK0080 | 2015-09-03 | 2015-09-03 | 2015-09-22 | 2015-09-30 | 2015-10-12 | BCVILLASENOR CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301367 | Pagbilao Grande Island NHS | PAGBILAO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-03-02 | 2016-03-01 | 4A0514S00093 | 15DK0072 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-24 | 2015-09-04 | W.J. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308004 | Pagbilao NHS | PAGBILAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-12 | 2016-02-12 | 4A0514S00110 | 15DK0077 | 2015-08-05 | 2015-08-07 | 2015-08-24 | 2015-09-03 | 2015-09-16 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109039 | Pagitan ES | PANUKULAN | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-11-30 | 4A0514S00012 | 14DK0042 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109040 | Pamatdan ES | POLILLO | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-12-22 | 4A0514S00006 | 14DK0044 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301374 | Patnanungan NHS | PATNANUNGAN | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-12 | 2016-03-13 | 4A0514S00105 | 15DK0078 | 2015-08-05 | 2015-08-07 | 2015-08-20 | 2015-09-03 | 2015-09-16 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301377 | Polillo NHS | POLILLO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-03-10 | 2016-03-09 | 4A0514S00112 | 15DK0109 | 2015-09-03 | 2015-09-03 | 2015-09-22 | 2015-09-30 | 2015-10-12 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 308047 | Polillo NHS Ext. | POLILLO | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2016-04-02 | 2016-04-02 | 4A0514S00193 | 15DK0150 | 2015-11-23 | 2015-12-04 | 2015-12-16 | 2015-12-23 | 2016-01-04 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109258 | Potol ES | CITY OF TAYABAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00026 | 14DK0038 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-09-28 | 2015-09-28 | 4A0514S00113 | 15DK0053 | 2015-06-24 | 2015-06-25 | 2015-07-09 | 2015-07-17 | 2015-07-31 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-12 | 2016-02-12 | 4A0514S00114 | 15DK0079 | 2015-08-05 | 2015-08-07 | 2015-08-24 | 2015-09-03 | 2015-09-16 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301407 | Talipan NHS | PAGBILAO | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-02 | 2016-03-01 | 4A0514S00107 | 15DK0073 | 2015-07-24 | 2015-07-29 | 2015-08-11 | 2015-08-19 | 2015-09-04 | ALT CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109262 | Tayabas West CS IV | CITY OF TAYABAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00037 | 14DK0039 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 165010 | Tejero ES | MAUBAN | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-24 | 2016-03-23 | 4A0514S00066 | 15DK0067 | 2015-07-17 | 2015-07-22 | 2015-08-04 | 2015-08-14 | 2015-08-27 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301410 | Tongohin NHS | INFANTA | 1 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-01 | 2016-03-01 | 4A0514S00091 | 15DK0074 | 2015-07-17 | 2015-07-29 | 2015-08-11 | 2015-08-24 | 2015-09-04 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301410 | Tongohin NHS | INFANTA | 1 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-12 | 2014-11-30 | 4A0514S00032 | 14DK0042 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301413 | Ungos NHS - Extension (Llavac) | REAL | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-22 | 2014-11-22 | 4A0514S00008 | 14DK0041 | 2014-07-26 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301416 | West Palale NHS | CITY OF TAYABAS | 1 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-22 | 2014-11-30 | 4A0514S00028 | 14DK0039 | 2014-08-07 | 2014-08-14 | 2014-08-26 | 2014-09-25 | 2014-10-14 | JOMZKI CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301299 | Cabay NHS | TIAONG | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-15 |  | 4A0514S00086 | 15DJ0029 | 2015-05-31 | 2015-06-02 | 2015-06-16 | 2015-06-23 | 2015-06-29 | MGDJ CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301305 | Callejon NHS | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301305 | Callejon NHS | SAN ANTONIO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301308 | Canda NHS | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308019 | Dr. Panfilo Castro NHS (Formerly Bukal Sur NHS-Mangilag Annex) | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-05 |  | 4A0514S00101 | 15DJ0047 | 2015-06-22 | 2015-06-24 | 2015-07-07 | 2015-07-14 | 2015-07-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308020 | Governor Anacleto C. Alcala NHS | SARIAYA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-05 |  | 4A0514S00137 | 15DJ0053 | 2015-07-01 | 2015-07-03 | 2015-07-16 | 2015-07-24 | 2015-07-28 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301348 | Lusacan NHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-03 |  | 4A0514S00136 | 15DJ0041 | 2015-06-08 | 2015-06-10 | 2015-06-23 | 2015-06-30 | 2015-07-03 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301349 | Lutucan NHS | SARIAYA | 2 | 1 | 8 | 2STY8CL | 2014 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109107 | Magsaysay ES | SAN ANTONIO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-19 | 2014-10-19 | 4A0514S00054 | 14DJ016 | 2014-07-08 | 2014-07-21 | 2014-07-23 | 2014-07-30 | 2014-08-01 | MGDJ CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108640 | Masalukot 3 ES | CANDELARIA | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-30 | 2014-10-30 | 4A0514S00055 | 14DJ013 | 2014-06-30 | 2014-07-01 | 2014-07-15 | 2014-07-22 | 2014-08-01 | MGDJ CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109108 | Matipunso ES | SAN ANTONIO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-11-03 | 2014-11-03 | 4A0514S00053 | 14DJ014 | 2014-07-08 | 2014-07-21 | 2014-07-23 | 2014-07-30 | 2014-08-01 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108627 | Pahinga Sur ES | Candelaria East | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 | 2016-03-05 |  | 4A0514S00169 | 15DJ0061 | 2015-07-06 | 2015-07-07 | 2015-07-21 | 2015-07-27 | 2015-07-29 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301370 | Paiisa NHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-25 |  | 4A0514S00134 | 15DJ0037 | 2015-06-03 | 2015-06-04 | 2015-06-18 | 2015-06-25 | 2015-06-30 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301380 | Recto MNHS | TIAONG | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301385 | San Antonio NHS | SAN ANTONIO | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-03-25 |  | 4A0514S00132 | 15DJ0027 | 2015-05-26 | 2015-05-27 | 2015-06-09 | 2015-06-17 | 2015-06-22 | JOJR CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301403 | Sta. Catalina NHS | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-04-15 |  | 4A0514S00131 | 15DJ0042 | 2015-06-14 | 2015-06-17 | 2015-06-30 | 2015-07-07 | 2015-07-10 | L.A. CLAMOR CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301318 | Sta. Lucia NHS (Formerly Dagatan NHS Annex - Sta. Lucia) | DOLORES | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-23 |  | 4A0514S00130 | 15DJ0049 | 2015-06-28 | 2015-06-29 | 2015-07-14 | 2015-07-21 | 2015-07-24 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301285 | Amontay NHS | PITOGO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301285 | Amontay NHS | PITOGO | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301288 | Bagupaye NHS | MULANAY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109138 | Bangkuro ES | SAN NARCISO | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2015-03-05 | 2015-03-05 | 4A0514S00058 | 14DM0025 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-05 | 2014-08-11 | WAYCON BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109139 | Bani ES | SAN NARCISO | 3 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4290835.14 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-12-08 | 4A0514S00057 | 14DM0026 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-05 | 2014-08-11 | WAYCON BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109292 | Beredo ES | UNISAN | 3 | 1 | 4 | 1STY 4CL | 2014 K10 BATCH 1 | 3840805.49 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 4A0514S00051 | 14DM0028 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-05 | 2014-08-11 | RGP BUILDERS
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109140 | Binay ES | SAN NARCISO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-09-12 | 2015-09-12 | 4A0514S00080 | 15DM0041 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-15 | RAPID FOREMOST CONST. CO.
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-28 | 2015-12-28 | 4A0514S00116 | 15DM0063 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | M.G. VILLAMIN CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301302 | Caigdal NHS | UNISAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-01-07 | 2015-01-07 | 4A0514S00047 | 14DM0030 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-05 | 2014-08-11 | RGP BUILDERS
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301303 | Calantas NHS | MACALELON | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-12 | 2015-09-12 | 4A0514S00127 | 15DM0045 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-15 | RAPID FOREMOST CONST. CO.
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308024 | Camflora National High School (Annex) | SAN ANDRES | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-20 | 2015-09-20 | 4A0514S00138 | 15DM0046 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-23 | JSP CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108927 | Canuyep ES | MULANAY | 3 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-06 | 2014-10-06 | 4A0514S00015 | 14DM0020 | 2014-06-12 | 2014-06-13 | 2014-06-26 | 2014-07-02 | 2014-07-07 | BOTEY CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109119 | Casay ES | San Francisco | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00167 | 15DM0072 | 2015-05-26 | 2015-06-09 | 2015-06-10 | 2015-06-17 | 2015-07-15 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301309 | Casay NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6569337.6381 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 4A0514S00124 | 15DM0066 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301310 | Catanauan National High School | CATANAUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00123 | 15DM0060 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | RGP BUILDERS
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109120 | Cawayan II ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1884740.174 |  |  | COMPLETED | 1 | 2015-11-11 | 2015-11-11 | 4A0514S00081 | 15DM0040 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-15 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108651 | Dahican ES | CATANAUAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1 | 2015-09-10 | 2015-08-15 | 4A0514S00079 | 15DM0042 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-13 | WAYCON BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308023 | Danlagan NHS (Formerly Kinagunan Ibaba NHS Ext. Classes) | PADRE BURGOS | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-09-15 | 4A0514S00122 | 15DM0047 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-18 | DEMALARAN CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301311 | Doongan Ilaya NHS (Formerly Catanauan NHS - Doongan Ilaya Ext.) | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2790828.124 |  |  | COMPLETED | 1 | 2015-10-15 | 2015-09-15 | 4A0514S00121 | 15DM0048 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-18 | JOJR CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301321 | Elias A. Salvador NHS | AGDANGAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00120 | 15DM0055 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301399 | Godofredo M. Tan Mem. SAT (Formerly San Narciso Voc. HS) | SAN NARCISO | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2015-09-29 | 2015-09-29 | 4A0514S00118 | 15DM0049 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301326 | Hinguiwin NHS | PADRE BURGOS | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1 | 2016-05-13 |  | 4A0514S00117 | 15DM0077 | 2015-07-18 | 2015-07-27 | 2015-07-31 | 2015-08-05 | 2015-08-18 | ALT CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109297 | Kalilayan ES | UNISAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-08 | 2014-11-18 | 4A0514S00050 | 14DM0029 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-05 | 2014-08-11 | RGP BUILDERS
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301337 | Lina Gayeta-Lasquety NHS (Formerly Kinagunan Ibaba NHS) | PADRE BURGOS | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1012049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108932 | Magsaysay ES | MULANAY | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 3065174.43 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-11-21 | 4A0514S00016 | 14DM0021 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-01 | 2014-08-04 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108880 | Mambog ES | MACALELON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 4A0514S00013 | 14DM0018 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-01 | 2014-08-04 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco) | SAN FRANCISCO (AURORA) | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-27 |  | 4A0514S00151 | 15DM0067 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308001 | Matandang Sabang NHS | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-09-29 | 2015-09-29 | 4A0514S00128 | 15DM0050 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109146 | Nangka ES | San Narciso | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00166 | 15DM0073 | 2015-05-26 | 2015-06-09 | 2015-06-10 | 2015-06-16 | 2015-07-15 | C.G. CABANA CONSTRUCTION & SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301360 | Olongtao NHS | MACALELON | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-26 | 2015-12-26 | 4A0514S00160 | 15DM0058 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-01 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301369 | Pagsangahan NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2015-11-28 | 2015-11-28 | 4A0514S00159 | 15DM0068 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108936 | PakIIng ES | Mulanay | 3 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-08 |  | 4A0514S00168 | 15DM0071 | 2015-05-26 | 2015-06-09 | 2015-06-10 | 2015-06-16 | 2015-07-13 | WAYCON BUILDERS & CONSTRUCTION SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301373 | Patabog NHS | MULANAY | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301373 | Patabog NHS | MULANAY | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2210417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301379 | Pugon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-09-29 | 4A0514S00157 | 15DM0051 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-02 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109148 | Punta ES | SAN NARCISO | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-01 | 2014-12-01 | 4A0514S00056 | 14DM0027 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-01 | 2014-08-04 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301391 | San Isidro NHS, Catanauan | CATANAUAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301391 | San Isidro NHS, Catanauan | CATANAUAN | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301393 | San Isidro NHS, Gen. Luna | GENERAL LUNA | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301393 | San Isidro NHS, Gen. Luna | GENERAL LUNA | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301394 | San Isidro NHS, Padre Burgos | PADRE BURGOS | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-23 | 2015-10-23 | 4A0514S00154 | 15DM0052 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-01 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301401 | San Roque NHS, Catanauan | CATANAUAN | 3 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6519337.6381 |  |  | COMPLETED | 1 | 2015-12-11 | 2015-12-11 | 4A0514S00153 | 15DM0062 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-15 | RAPID FOREMOST CONST. CO.
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109096 | Segaras ES | SAN ANDRES | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1082049.6543 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 4A0514S00078 | 15DM0043 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-06-23 | JSP CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya IS) | CATANAUAN | 3 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301312 | Tagbacan NHS (Tagbacan Ilaya IS) | CATANAUAN | 3 | 1 | 3 | 1STY 3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301409 | Tayuman National High School | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-10 | 2015-08-15 | 4A0514S00139 | 15DM0054 | 2015-05-20 | 2015-05-21 | 2015-06-02 | 2015-06-08 | 2015-07-13 | RAPID FOREMOST CONST. CO.
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301414 | Unisan NHS | UNISAN | 3 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-04 |  | 4A0514S00150 | 15DM0056 | 2015-05-27 | 2015-05-28 | 2015-06-11 | 2015-06-20 | 2015-07-09 | RGP BUILDERS
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108553 | VIlla Aurora ES | BUENAVISTA | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-16 | 4A0514S00009 | 14DM0014 | 2014-08-07 | 2014-08-27 | 2014-08-28 | 2014-09-04 | 2014-09-18 | JSP CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108889 | Vista Hermosa ES | MACALELON | 3 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-01 | 2015-01-01 | 4A0514S00014 | 14DM0019 | 2014-06-12 | 2014-06-13 | 2014-07-31 | 2014-08-01 | 2014-08-04 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301284 | Alabat Island NHS | ALABAT | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108591 | Anas ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2016-01-21 |  | 4A0514S00068 | 15-DL-0107 | 2015-06-16 | 2015-06-29 | 2015-06-30 | 2015-07-05 | 2015-07-23 | KKT CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 3 | 15538022.3438 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301287 | Bagong Silang NHS | TAGKAWAYAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301291 | Bantulinao IS | CALAUAG | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-01 | 2015-11-01 | 4A0514S00147 | 15-DL-0077 | 2015-05-24 | 2015-05-28 | 2015-06-06 | 2015-06-12 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109197 | Bosigon ES | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00074 | 15-DL-0104 | 2015-06-16 | 2015-06-28 | 2015-06-30 | 2015-07-04 | 2015-07-23 | BOTEY CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108505 | C.B. Encarnado ES (VIlla Norte) | ALABAT | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1894740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00075 | 15-DL-0108 | 2015-06-16 | 2015-06-29 | 2015-06-30 | 2015-07-03 | 2015-07-23 | KKT CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301304 | Calauag NHS | CALAUAG | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0514S00146 | 15-DL-0076 | 2015-05-27 | 2015-06-10 | 2015-06-11 | 2015-06-18 | 2015-06-29 | T.A.D. CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108802 | Cawayanin ES | Lopez East | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 4A0514S00181 | 4A05-14-S-00181 | 2015-06-29 | 2015-07-11 | 2015-07-14 | 2015-07-20 | 2015-08-15 | A.A. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301346 | Cogorin Ibaba NHS (Formerly Lopez NCHSl - Cogorin Ibaba Extension) | LOPEZ | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2865828.124 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0514S00145 | 15-DL-0079 | 2015-05-27 | 2015-06-09 | 2015-06-10 | 2015-06-17 | 2015-06-29 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301314 | Cometa NHS Annex | QUEZON | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00144 | 15-DL-0089 | 2015-06-03 | 2015-06-16 | 2015-06-17 | 2015-06-20 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108734 | Dungawan Central ES | GUINAYANGAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 4A0514S00049 | 14DL0029 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301323 | Guinayangan NHS | GUINAYANGAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1 | 2016-01-05 |  | 4A0514S00143 | 15DL0134 | 2015-08-29 | 2015-09-03 | 2015-09-04 | 2015-09-08 | 2015-09-15 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301325 | Gumaca National High School | GUMACA | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00142 | 15-DL-0092 | 2015-06-09 | 2015-06-15 | 2015-06-30 | 2015-07-04 | 2015-07-13 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301327 | Hondagua NHS | LOPEZ | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-30 |  | 4A0514S00141 | 15-DL-0083 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-29 | T.A.D. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301340 | Lamon Bay SOF - Main Gumaca | GUMACA | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-30 |  | 4A0514S00109 | 15-DL-0087 | 2015-06-03 | 2015-06-15 | 2015-06-16 | 2015-06-22 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301345 | Lopez National Comprehensive High School | LOPEZ | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00161 | 15-DL-0090 | 2015-06-09 | 2015-06-22 | 2015-06-23 | 2015-06-27 | 2015-07-13 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108811 | Mabamban ES | LOPEZ | 4 | 1 | 4 | 2UNITS 1STY 2CL | 2014 K10 BATCH 1 | 4020835.14 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 4A0514S00042 | 14DL0033 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301351 | Magallanes NHS | LOPEZ | 4 | 1 | 4 | 1STY4CL | 2014 SHS BATCH 1 | 3464886.575 |  |  | COMPLETED | 1 | 2016-01-08 |  | 4A0514S00126 | 15-DL-0080 | 2015-05-27 | 2015-06-02 | 2015-06-03 | 2015-06-11 | 2015-06-16 | R.C. TAGALA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 308048 | Magallanes NHS-Sta. Catalina Extension | LOPEZ | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2760828.124 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00067 | 15-DL-0101 | 2015-06-16 | 2015-06-29 | 2015-06-30 | 2015-07-07 | 2015-07-23 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301357 | Malusak NHS | ATIMONAN | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2015-11-30 | 2015-11-30 | 4A0514S00096 | 15-DL-0084 | 2015-05-28 | 2015-06-09 | 2015-06-10 | 2015-06-16 | 2015-06-29 | R.C. TAGALA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 308045 | Mansilay NHS | TAGKAWAYAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109214 | Mapulot ES | Tagkawayan | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 4A0514S00176 | 4A05-14-S-00176 | 2015-06-29 | 2015-07-11 | 2015-07-14 | 2015-07-20 | 2015-08-15 | A.A. CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108581 | Municipal Sector ES | Calauag East | 4 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-02-12 |  | 4A0514S00180 | 15DL0121 | 2015-08-06 | 2015-08-26 | 2015-08-26 | 2015-08-29 | 2015-09-15 | A.A. CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301359 | Nabangka NHS | GUINAYANGAN | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00095 | 15-DL-0085 | 2015-05-28 | 2015-06-09 | 2015-06-10 | 2015-06-14 | 2015-06-29 | ZELAN CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 308009 | Pamampangin NHS | LOPEZ | 4 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2016-01-08 |  | 4A0514S00094 | 15-DL-0081 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-16 | R.C. TAGALA CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301372 | Panikihan NHS | GUMACA | 4 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-10 |  | 4A0514S00085 | 15-DL-0091 | 2015-06-09 | 2015-06-15 | 2015-06-30 | 2015-07-03 | 2015-07-13 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 109216 | Payapa ES | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1814740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00084 | 15-DL-0105 | 2015-06-16 | 2015-06-29 | 2015-06-30 | 2015-07-05 | 2015-07-23 | HONEYVILLE CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301375 | Perez NHS | PEREZ | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2245417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108773 | Progreso ES | GUMACA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 4A0514S00043 | 14DL0032 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108817 | San Andres ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00073 | 15-DL-0100 | 2015-06-16 | 2015-06-30 | 2015-07-01 | 2015-07-06 | 2015-07-23 | BOTEY CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301386 | San Francisco B NHS | LOPEZ | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2715828.124 |  |  | COMPLETED | 1 | 2016-01-08 |  | 4A0514S00092 | 15-DL-0082 | 2015-05-27 | 2015-06-08 | 2015-06-09 | 2015-06-13 | 2015-06-16 | R.C. TAGALA CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108746 | San Roque PS | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1 | 2015-10-21 | 2015-10-21 | 4A0514S00069 | 15-DL-0103 | 2015-06-16 | 2015-06-30 | 2015-07-01 | 2015-07-06 | 2015-07-23 | BOTEY CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301402 | San Roque-Ilaya NHS, Calauag | CALAUAG | 4 | 1 | 3 | 1STY3CL | 2014 SHS BATCH 1 | 2640828.124 |  |  | COMPLETED | 1 | 2016-01-30 |  | 4A0514S00089 | 15-DL-0088 | 2015-06-03 | 2015-06-15 | 2015-06-16 | 2015-06-20 | 2015-06-29 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108747 | Sta. Cruz ES | GUINAYANGAN | 4 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-02-10 | 2015-02-10 | 4A0514S00045 | 14DL0030 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108857 | Sta. Teresa ES | Lopez West | 4 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-01-15 |  | 4A0514S00182 | 4A05-14-S-00182 | 2015-06-29 | 2015-07-11 | 2015-07-14 | 2015-07-19 | 2015-08-15 | A.A. CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 308011 | Sto. Angel National High School | CALAUAG | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1217329.12 |  |  | COMPLETED | 1 | 2015-01-10 | 2015-01-10 | 4A0514S00046 | 14DL0028 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301404 | Sto. Domingo NHS | CALAUAG | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-23 |  | 4A0514S00088 | 15-DL-0078 | 2015-05-24 | 2015-06-05 | 2015-06-06 | 2015-06-10 | 2015-06-22 | T.A.D. CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 301405 | Tabason NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 3 | 1773888.918 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | QUEZON | 301406 | Tagkawayan NHS | TAGKAWAYAN | 4 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 4A0514S00087 | 15-DL-0074 | 2015-05-21 | 2015-06-02 | 2015-06-03 | 2015-06-07 | 2015-06-22 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108822 | Tan-Ag ES | LOPEZ | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 4A0514S00041 | 14DL0034 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | KKT CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 165009 | Villa Bota ES | GUMACA | 4 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00072 | 15-DL-0106 | 2015-06-16 | 2015-06-30 | 2015-07-01 | 2015-07-06 | 2015-07-23 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108764 | Villa Padua ES | GUMACA | 4 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 4A0514S00044 | 14DL0031 | 2014-08-14 | 2014-08-18 | 2014-08-28 | 2014-09-04 | 2014-09-11 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108830 | VIllaminda Elementary School | LOPEZ | 4 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1964740.174 |  |  | COMPLETED | 1 | 2015-12-21 | 2015-12-21 | 4A0514S00070 | 15-DL-0102 | 2015-06-16 | 2015-06-30 | 2015-07-01 | 2015-07-06 | 2015-07-23 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | QUEZON | 108590 | Yaganak ES | CALAUAG | 4 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 3 | 1017013.0464 |  |  | COMPLETED | 1 | 2015-05-25 | 2015-05-25 | 4A0514S00060 | 14DL0080 | 2014-12-08 | 2014-12-01 | 2014-12-22 | 2014-12-26 | 2014-12-29 | KKT CONSTRUCTION AND SUPPLY
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301417 | Angono NHS | ANGONO | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0614S00031 | 15DN0095 | 2015-09-02 | 2015-09-02 | 2015-09-15 | 2015-09-25
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165506 | Cresdaville Elementary School | Taytay II | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0614S00073 | 15DN0089 | 2015-08-26 | 2015-08-26 | 2015-09-08 | 2015-09-18 |  | MARKNEST CONSTRUCTION AND TRADING (FORMERLY MARKNE
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109538 | Dolores ES | Taytay II | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0614S00070 | 15DN0114 | 2015-10-14 | 2015-10-14 | 2015-10-27 | 2015-11-10
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301436 | Don Jose M. Ynares,Sr. MNHS | Binangonan III | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0614S00047 | 15DN0159 | 2015-11-25 | 2015-11-25 | 2015-12-15 |  |  | CAMIA CONST. DEVELOPMENT CORPORATION (FORMERLY:CAM
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109311 | Doña Nieves Songco MS | Angono | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-12 |  | 4A0614S00058 | 15DN0105 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | GENETIAN BUILDERS
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109399 | Francisco P. Felix ES Unit I | Cainta I (Cainta) | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00061 | 4A06-14-S-00061
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308109 | Francisco P. Felix MNHS - JICA Annex | Cainta I (Cainta) | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00064 | 4A06-14-S-00064
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308110 | Francisco P. Felix MNHS - Karangalan Annex | Cainta I (Cainta) | 1 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | COMPLETED | 1 |  |  | 4A0614S00039 | 15DN0133 | 2015-11-25 | 2015-11-25 | 2015-12-08 | 2015-12-17 |  | ONE EULUZ CONSTRUCTION CORPORATION (FORMERLY: EULUZ CONSTRUCTION & SUPPLY)
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308111 | Francisco P. Felix MNHS - LTO Annex | Cainta I (Cainta) | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | Reverted | 0 |  |  | 4A0614S00040 | 4A06-14-S-00040
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308119 | Guronasyon Foundation Incorporated NHS | Binangonan III | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00041 | 4A06-14-S-00041
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109400 | Halang ES | Cainta II | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | COMPLETED | 1 |  |  | 4A0614S00062 | 15DN0152 | 2015-11-26 | 2015-11-26 | 2015-12-11 | 2015-12-23 |  | DAHL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109401 | Janssenville ES (Mapandan ES) | Cainta II | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0614S00063 | 15DN0162 | 2015-12-02 | 2015-12-02 | 2015-12-15 |  |  | GENETIAN BUILDERS
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109402 | Kabisig ES | Cainta I (Cainta) | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-29 |  | 4A0614S00074 | 15DN0106 | 2015-09-16 | 2015-09-16 | 2015-09-29 | 2015-10-13 | 2015-10-26 | E. M. PAULE CONSTRUCTION & TRADING
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109385 | Lunsad ES | Binangonan II | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-04 |  | 4A0614S00059 | 15DN0094 | 2015-09-02 | 2015-09-02 | 2015-09-15 | 2015-09-25 | 2015-10-07 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109407 | Saint Gregory ES | Cainta II | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-12 |  | 4A0614S00065 | 15DN0113 | 2015-10-07 | 2015-10-07 | 2015-10-20 | 2015-11-02 | 2015-11-13 | A.P. BOISER CONSTRUCTION AND SUPPLY
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109408 | San Francisco ES | Cainta I (Cainta) | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00056 | 4A06-14-S-00056
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109542 | San Francisco ES | Taytay II | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0614S00071 | 15DN0120 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-18 |  | THREE W BUILDERS, INC.
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109543 | San Juan A (Floodway) ES | Taytay II | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00072 | 4A06-14-S-00072
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109409 | San Juan Elementary School | Cainta II | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-23 |  | 4A0614S00067 | 15DN0107 | 2015-09-16 | 2015-09-10 | 2015-09-29 | 2015-10-13 | 2015-10-26 | JRD-D2 ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109410 | San Juan ES Unit I | Cainta II | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-12 |  | 4A0614S00068 | 15DN0112 | 2015-10-07 | 2015-10-07 | 2015-10-20 | 2015-11-02 | 2015-11-13 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301438 | San Juan NHS | Cainta I (Cainta) | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00045 | 4A06-14-S-00045
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308130 | Simona NHS | Taytay I | 1 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | Reverted | 0 |  |  | 4A0614S00042 | 4A06-14-S-00042
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109531 | Sitio Simona ES | Taytay I | 1 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | Reverted | 0 |  |  | 4A0614S00069 | 4A06-14-S-00069
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109390 | Tabon ES | Binangonan II | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0614S00060 | 15DN0117 | 2015-10-15 | 2015-10-15 | 2015-10-29 | 2015-11-11 | 2015-11-24 | PRECIOUS CONSTRUCTION
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301469 | Vicente Madrigal NHS | BINANGONAN | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 308103 | Abuyod NHS | TERESA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-22 |  | 4A0614S00029 | 15DO0048 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165516 | Aldea Elementary School | Tanay I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-17 |  | 4A0614S00038 | 15DO0061 | 2015-09-15 | 2015-09-17 | 2015-10-01 | 2015-10-08 | 2015-10-21 | OLIVER AQUINO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308142 | Aldea NHS | Tanay I | 2 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-06-03 |  | 4A0614S00078 | 15DO0091 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-25 | 2015-12-07 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301428 | Bagumbong NHS | JALA-JALA | 2 | 1 | 4 | 2STY4CL | 2014 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1 | 2015-12-23 | 2015-12-23 | 4A0614S00028 | 15DO0053 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109482 | Banaba ES | San Mateo | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | Reverted | 0 |  |  | 4A0614S00036
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109425 | Baras ES | Baras | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-03 |  | 4A0614S00044 | 15DO0080 | 2015-10-28 | 2015-10-29 | 2015-11-11 | 2015-11-25 | 2015-12-07 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308124 | Baras-Pinugay NHS | Baras | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-08-02 |  | 4A0614S00076 | 15DO0082 | 2015-10-27 | 2015-10-29 | 2015-11-11 | 2015-11-25 | 2015-12-07 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301430 | Bayugo NHS | JALA-JALA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-22 |  | 4A0614S00027 | 15DO0049 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | STEVEN CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301432 | Bernardo F. San Juan NHS | CARDONA | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20142783.5938 |  |  | COMPLETED | 1
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301432 | Bernardo F. San Juan NHS | CARDONA | 2 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10417131.51 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109500 | Bitik ES | Tanay I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-25 |  | 4A0614S00055 | 15DO0072 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | DARCY & ANNA BUILDERS & TRADING
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 308132 | Bugarin NHS | PILILLA | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00025 | 15DO0041 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109463 | Burgos ES Unit I | Rodriguez I (Rodriguez) | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | Reverted | 0 |  |  | 4A0614S00046
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301440 | Burgos NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 3 | 20092533.5938 |  |  | Reverted | 0 | 2016-01-16 |  | 4A0614S00011 | 14DO0058 | 2014-12-24 | 2014-12-22 | 2015-01-08 | 2015-01-13 | 2015-01-26 | CHRISMAN CONSTRUCTION AND SUPPLIES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109501 | Camp Mateo Capinpin ES | Tanay II | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 4C | 15121327.92 |  |  | Reverted | 0 |  |  | 4A0614S00049
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301434 | Catalino D. Salazar NHS | CARDONA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-02-20 |  | 4A0614S00015 | 15DO0050 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | EL KAPITAN CONSTRUCTION SERVICES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301435 | Daraetan NHS | Tanay II | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-21 |  | 4A0614S00079 | 15DO0066 | 2015-10-14 | 2015-10-16 | 2015-10-29 | 2015-11-10 | 2015-11-23 | VIAN BUILDERS
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109485 | Doña Pepeng ES | San Mateo | 2 | 1 | 12 | 3STY12CL | 2014 K10 BATCH 4C | 18222268.79 |  |  | Reverted | 0 |  |  | 4A0614S00048
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109466 | Eulogio Rodriguez Jr. ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 9 | 3STY9CL | 2014 K10 BATCH 3 | 14175368.3984 |  |  | COMPLETED | 1 | 2015-09-21 | 2015-09-21 | 4A0614S00009 | 14DO0057 | 2014-12-24 | 2014-12-22 | 2015-01-08 | 2015-01-13 | 2015-01-26 | V. BERNARDO CONSTRUCTION AND TRADING
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165509 | Kasiglahan Village ES Unit I | Rodriguez II | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00052
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109507 | Laiban ES | TANAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1282329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-09-30 | 4A0614S00003 | 14DO0015 | 2014-07-07 | 2014-07-11 | 2014-08-07 | 2014-08-15 | 2014-08-25 | JRD-D2 ENTERPRISES
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 308133 | Laiban NHS | TANAY | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00023 | 15DO0040 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308137 | Macaingalan HS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1257329.12 |  |  | COMPLETED | 1 | 2014-10-16 | 2014-10-16 | 4A0614S00004 | 14DO0014 | 2014-07-07 | 2014-07-11 | 2014-07-22 | 2014-07-30 | 2014-08-18 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109512 | Mamuyao ES | TANAY | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1282329.12 |  |  | COMPLETED | 1 | 2014-10-23 | 2014-09-30 | 4A0614S00006 | 14DO0016 | 2014-07-07 | 2014-07-11 | 2014-08-07 | 2014-08-15 | 2014-08-25 | JRD-D2 ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165514 | Monte De Tanay ES | Tanay II | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-06-21 |  | 4A0614S00054 | 15DO0069 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165504 | Patiis ES | SAN MATEO | 2 | 1 | 2 | 1STY 2CL | 2014 K10 BATCH 1 | 2170417.57 |  |  | COMPLETED | 1 | 2014-11-17 | 2014-11-17 | 4A0614S00007 | 14DO0017 | 2014-07-16 | 2014-07-17 | 2014-07-31 | 2014-08-11 | 2014-08-20 | OLIVER AQUINO CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109440 | Pulong Kumanoy ES | Morong | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-04-16 |  | 4A0614S00080 | 15DO0059 | 2015-09-15 | 2015-09-17 | 2015-10-01 | 2015-10-08 | 2015-10-21 | DARCY & ANNA BUILDERS & TRADING
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301454 | Quisao NHS | PILILLA | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1 | 2016-01-22 |  | 4A0614S00020 | 15DO0046 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109518 | Rawang ES | Tanay I | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-03-23 |  | 4A0614S00050 | 15DO0073 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301456 | Sampaloc NHS | TANAY | 2 | 1 | 6 | 2STY6CL | 2014 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109477 | San Isidro ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 8 | 2STY8CL | 2014 K10 BATCH 3 | 11428734.375 |  |  | Reverted | 0 |  |  | 4A0614S00010
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165507 | San Isidro ES - Balagbag Annex | RODRIGUEZ (MONTALBAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2014-10-16 | 2014-10-16 | 4A0614S00002 | 14DO0013 | 2014-07-07 | 2014-07-11 | 2014-07-22 | 2014-07-30 | 2014-08-18 | B. VALENCERINA TRADING & CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109464 | San Rafael ES - Casili ES | Rodriguez I (Rodriguez) | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | Reverted | 0 |  |  | 4A0614S00066
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109465 | San Rafael ES - Catmon ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 1 | 1STY 1CL | 2014 K10 BATCH 1 | 1182329.12 |  |  | COMPLETED | 1 | 2014-10-09 | 2014-10-09 | 4A0614S00005 | 14DO0012 | 2014-07-07 | 2014-07-11 | 2014-07-22 | 2014-07-30 | 2014-08-11 | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 136918 | San Roque ES | Baras | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4C | 6319337.6381 |  |  | COMPLETED | 1 | 2016-02-17 |  | 4A0614S00051 | 15DO0060 | 2015-09-15 | 2015-09-17 | 2015-10-01 | 2015-10-08 | 2015-10-21 | DARCY & ANNA BUILDERS & TRADING
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301462 | Silangan NHS | SAN MATEO | 2 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-02-21 |  | 4A0614S00018 | 15DO0052 | 2015-07-14 | 2015-07-16 | 2015-07-29 | 2015-08-13 | 2015-08-26 | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 165510 | Southville 8 ES | Rodriguez II | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0614S00053
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 308134 | Southville 8B NHS | Rodriguez II | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | COMPLETED | 1 | 2016-08-16 |  | 4A0614S00077 | 15DO0099 | 2015-11-10 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-21 | SOUTH BUILDERS & CONSTRUCTION SUPPLIES
NC 2014 | SHS (2014) | Region IV-A | RIZAL | 301461 | Sto. Niño NHS | TANAY | 2 | 1 | 2 | 1STY2CL | 2014 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1 | 2015-10-03 | 2015-10-03 | 4A0614S00016 | 15DO0039 | 2015-07-06 | 2015-07-09 | 2015-07-21 | 2015-07-28 | 2015-08-05 | JRD-D2 ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109422 | Tadlak ES (Korokan ES) | Cardona | 2 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | COMPLETED | 1 | 2016-05-25 |  | 4A0614S00043 | 15DO0101 | 2015-11-19 | 2015-11-23 | 2015-12-04 | 2015-12-15 | 2015-12-28 | DAHL CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 301467 | Teresa NHS | Teresa | 2 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IV-A | RIZAL | 109480 | Wawa ES | Rodriguez I (Rodriguez) | 2 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | Reverted | 0 |  |  | 4A0614S00037
NC 2014 | K10 (2014) | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | SAN PABLO CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 4A0414S00022 | 14DP0053 | 2014-12-13 | 2014-12-25 | 2014-12-16 | 2014-12-29 | 2015-01-14 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | San Pablo City | 109763 | San Cristobal Elementary School | Dapdapan | 3 | 1 | 8 | 4STY8CL | 2014 K10 BATCH 4C | 14897518.84 |  |  | COMPLETED | 1 | 2016-04-18 | 2016-05-16 | 4A0414S00050 | 15DP0066 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | 3RB CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15171327.92 |  |  | COMPLETED | 1 | 2016-04-18 | 2016-04-17 | 4A0414S00035 | 15DP0068 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | DSO ENTERPRISES
NC 2014 | K10 (2014) | Region IV-A | San Pablo City | 109771 | San Marcos Elementary School | SAN PABLO CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 4A0414S00021 | 14DP0054 | 2014-12-13 | 2014-12-25 | 2014-12-16 | 2014-12-29 | 2015-01-14 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | San Pablo City | 301504 | San Pablo City National High School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 3 | 10667093.5547 |  |  | COMPLETED | 1 | 2015-08-14 | 2015-08-14 | 4A0414S00019 | 14DP0056 | 2015-02-10 | 2015-02-08 | 2015-02-10 | 2015-02-27 | 2015-03-18 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2014 | K10 (2014) | Region IV-A | San Pablo City | 109783 | San Roque Elementary School | SAN PABLO CITY | 3 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-04-13 | 2015-04-13 | 4A0414S00020 | 14DP0055 | 2014-12-13 | 2014-12-25 | 2014-12-16 | 2014-12-29 | 2015-01-14 | A.V. CONSTRUCTION & SUPPLY
NC 2014 | SHS (2014) | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | 2014 SHS BATCH 1 | 10517131.51 |  |  | COMPLETED | 1 | 2016-03-19 | 2016-04-02 | 4A0414S00036 | 15DP0069 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 301225 | Aplaya National High School Annex I APEX | City of Sta. Rosa District I | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | COMPLETED | 1 | 2016-07-23 |  | 4A0414S00055 | 15DI0163 | 2015-10-30 | 2015-11-11 | 2015-11-12 | 2015-11-24 | 2015-11-27 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | City of Sta. Rosa District I | 1 | 1 | 12 | 4STY12CL | 2014 K10 BATCH 4C | 22152343.62 |  |  | COMPLETED | 1 | 2016-06-02 | 2016-12-02 |  | 15DI0139 | 2015-10-02 | 2015-10-08 | 2015-10-21 | 2015-10-21 | 2015-11-06 | 3RB CONSTRUCTION & SUPPLY | no remarks
NC 2014 | SHS (2014) | Region IV-A | Sta. Rosa City | 301227 | Balibago National High School | CITY OF SANTA ROSA | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-06-28 |  | 4A0414S00037 | 15DI0187 | 2015-06-10 | 2015-06-15 | 2015-06-29 | 2016-11-25 | 2016-01-31 | HEXAMINDS CORPORATION
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 108472 | Dila Elementary School | City of Sta. Rosa District II | 1 | 1 | 16 | 4STY16CL | 2014 K10 BATCH 4C | 26702469.42 |  |  | Reverted | 0 |  |  | 4A0414S00051 | 4A04-14-S-00051
NC 2014 | SHS (2014) | Region IV-A | Sta. Rosa City | 301239 | Don Jose NHS | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL | 2014 SHS BATCH 1 | 14897518.84 |  |  | COMPLETED | 1 | 2016-01-01 |  | 4A0414S00038 | 15DI0065 | 2015-06-02 | 2015-06-09 | 2015-06-10 | 2015-06-22 | 2015-06-26 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 108480 | Santa Rosa Elementary School Central I | City of Sta. Rosa District I | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4C | 10417131.51 |  |  | Reverted | 0 |  |  | 4A0414S00053 | 4A04-14-S-00053
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 251501 | Southville 4 Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 6 | 3STY6CL | 2014 K10 BATCH 4B | 10417131.51 |  |  | COMPLETED | 1 | 2015-11-23 | 2016-06-30 | 4A0414S00029 | 15DI0085 | 2015-06-26 | 2015-07-02 | 2015-07-15 | 2015-07-20 | 2015-07-27 | ST. GERARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IV-A | Sta. Rosa City | 324001 | Southville IV NHS | City of Sta. Rosa District I | 1 | 1 | 20 | 4STY20CL | 2014 K10 BATCH 4C | 31102890.27 |  |  | Reverted | 0 |  |  | 4A0414S00049 | 4A04-14-S-00049
NC 2014 | SHS (2014) | Region IV-A | Sta. Rosa City | 307902 | Sta. Rosa Science & Technology HS | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL | 2014 SHS BATCH 1 | 22152343.62 |  |  | COMPLETED | 1 | 2016-01-09 |  | 4A0414S00047 | 15DI0077 | 2015-06-16 | 2015-06-25 | 2015-06-29 | 2015-07-10 | 2015-07-14 | L.P.O. ENTERPRISES
NC 2014 | SHS (2014) | Region IV-A | Sta. Rosa City | 301272 | Sto. Domingo National High School | CITY OF SANTA ROSA | 1 | 1 | 9 | 3STY9CL | 2014 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1 | 2016-02-11 |  | 4A0414S00041 | 15DI0112 | 2015-08-12 | 2015-08-24 | 2015-08-26 | 2015-09-11 | 2015-09-15 | MAR-VEL CONSTRUCTION & SUPPLY | no remarks
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 321505 | Antipolo NHS - Dela Paz Extension | CITY OF ANTIPOLO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0615S00004 | 15DN0101 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HI-TRI DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 301426 | San Isidro NHS | CITY OF ANTIPOLO | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0615S00007 | 15DN0102 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | HI-TRI DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 321502 | Antipolo NHS - Canumay Extension | CITY OF ANTIPOLO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0615S00011 | 16DNO002 | 2016-01-15 | 2016-01-15 | 2016-02-04 | 2016-02-12 | 2016-02-23
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 301421 | Antipolo NHS - Kaysakat Extension | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00008 | 15DN0096 | 2015-09-03 | 2015-09-04 | 2015-09-17 | 2015-09-29 | 2015-10-12 | 2H2L CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 301431 | Calawis NHS | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0615S00012 | 15DN0104 | 2015-09-10 | 2015-09-10 | 2015-09-23 | 2015-10-06 | 2015-10-16 | KRBS CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | Region IV-A | ANTIPOLO CITY | 321503 | Calawis NHS - Apia Extension | CITY OF ANTIPOLO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0615S00044 | 16DNO006 | 2016-01-28 | 2016-02-03 | 2016-02-16 | 2016-02-24 | 2016-03-03
NC 2015 | K10 (2015) | Region IV-A | ANTIPOLO CITY | 230006 | Paglitaw PS | CITY OF ANTIPOLO | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00024 | 15DN0161 | 2015-11-26 | 2015-12-02 | 2015-12-15 | 2015-12-23 | 2016-01-09 | KRBS CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | ANTIPOLO CITY | 301427 | San Juan NHS | CITY OF ANTIPOLO | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0615S00009 | 15DN0118 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-18 | 2015-11-25 | M. DEL ROSARIO CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | Region IV-A | ANTIPOLO CITY | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 6 | 1663480.88 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IV-A | ANTIPOLO CITY | 109361 | Sumilang ES | ANTIPOLO CITY | 2 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 1833528.635 |  |  | Reverted | 0 |  |  | 4A0615S00025 | 4A06-15-S-00025
NC 2015 | K10 (2015) | Region IV-A | ANTIPOLO CITY | 109363 | Upper Kilingan ES | CITY OF ANTIPOLO | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00023 | 15DN0125 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-08 | KRBS CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | Bacoor City |  | Proposed Stand-Alone SHS 1- Dulong Bayan | BACOOR | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Bacoor City |  | Proposed Stand-Alone SHS 4- Sineguelasan | BACOOR | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region IV-A | Bacoor City | 107867 | Proposed Stand-Alone SHS 5- Bacoor ES | Bacoor City | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 28002469 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand Alone SHS- Tuy | TUY | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107405 | Doña Matilde MES | LEMERY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00064 | 15DB0098 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | RICH ADS CONSTRUCTION CORP. (FORMERLY RICH ADS CON
NC 2015 | K10 (2015) | Region IV-A | Batangas | 307710 | Jose Lopez Manzano Tuy National High School | TUY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0215S00065 | 15DB0100 | 2015-09-09 | 2015-09-14 | 2015-09-15 | 2015-09-28 | 2015-10-20 | VRV CONSTRUCTION AND TRADING
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107512 | Nasugbu West CS | NASUGBU | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0215S00061 | 15DB0102 | 2015-09-09 | 2015-09-18 | 2015-09-21 | 2015-10-20 | 2015-10-30 | SANDSTORM CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107516 | Papaya ES | NASUGBU | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00058 | 15DB0099 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | M.E. BANING CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand Alone SHS- Calaca | CALACA | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand Alone SHS- Lemery | LEMERY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 8 | 35596257.14 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 13 (LIAN SHS) | LIAN | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 3 (NASUGBU SHS 1) | NASUGBU | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 4 (NASUGBU SHS 2) | NASUGBU | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 8 | 35596257.14 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 5 (NASUGBU SHS 3) | NASUGBU | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Prposed Stand-Alone SHS 2 (TAAL SHS) | TAAL | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107230 | Troadio A. Frontera MES | BALAYAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00057 | 15DB0097 | 2015-09-09 | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2015-10-05 | 830 BUILDERS & DEVELOPERS CORP.
NC 2015 | K10 (2015) | Region IV-A | Batangas | 307719 | Tuy NHS | TUY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0215S00069 | 15DB0101 | 2015-09-09 | 2015-09-14 | 2015-09-15 | 2015-09-28 | 2015-10-20 | VRV CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301115 | Anselmo Sandoval MNHS (Mabini NHS) | MABINI | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00037 | 15DE0076 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | E.M.L. CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301077 | Batangas Province High School for Culture and Arts | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6399338 |  |  | COMPLETED | 1 |  |  | 4A0215S00050 | 15DE0088 | 2015-10-14 | 2015-10-15 | 2015-10-27 | 2015-10-30 |  | SANDSTORM CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301079 | Bauan Mun. Agric'l & Voc. HS | BAUAN | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00038 | 15DE0077 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | E.M.L. CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301080 | Bauan Technical HS | BAUAN | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107434 | Jaybanga ES | LOBO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00053 | 15DE0131 | 2015-11-30 | 2015-12-01 | 2015-12-15 | 2015-12-18 | 2015-12-28 | WESTHOME ENTERPRISES & BUILDERS SUPPLIES, INC.
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107438 | Malabrigo ES | LOBO | 2 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00062 | 15DE0105 | 2015-11-04 | 2015-11-05 | 2015-11-19 | 2015-11-25 | 2015-12-04 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 18 (SAN LUIS SHS) | SAN LUIS | 2 | 1 | 12 | 3STY6CL | 2015 SHS BATCH 5 | 21084263 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 19 (SAN PASCUAL SHS 1) | SAN PASCUAL | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 20 (SAN PASCUAL SHS 2) | SAN PASCUAL | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand Alone SHS- Agoncillo | AGONCILLO | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 10 (MATAASNAKAHOY SHS) | MATAASNAKAHOY | 3 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 8 | 21383013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 22 (MALVAR SHS) | MALVAR | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 23 (TALISAY SHS) | TALISAY | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 7 (ALITAGTAG SHS) | ALITAGTAG | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 8 (BALETE SHS) | BALETE | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 9 (CUENCA SHS) | CUENCA | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas | 307713 | San Nicolas NHS- Maabud Annex | San Nicolas | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26752469.42 |  |  | COMPLETED | 1 |  |  | 4A0215S00040 | 15DC0111 | 2015-10-14 | 2015-10-26 | 2015-10-27 |  |  | N.B. AVILA CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | Batangas | 301147 | Santa Clara NHS | SANTO TOMAS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1988606 |  |  | COMPLETED | 1 |  |  | 4A0215S00070
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301149 | Santa Teresita NHS | SANTA TERESITA | 3 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1 |  |  | 4A0215S00041 | 15DC0090 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-03 | 2015-09-09 | I.A . BOSQUE CONSTRUCTION CORPORATION
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107383 | Sta. Maria ES | LAUREL | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0215S00063
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301069 | Alupay NHS | Rosario | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10817131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00042 | 15DD0182 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | VRV CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301090 | Buhaynasapa NHS | SAN JUAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00033 | 15DD0181 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | N.B. AVILA CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Batangas | 307714 | Dr. Bonifacio Masilungan MNHS | San Jose | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 4A0215S00023 | 15DD0176 | 2015-08-03 | 2015-08-06 | 2015-08-10 | 2015-08-18 | 2015-09-09 | VRV CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301105 | Itlugan NHS | Rosario | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8914965.051 |  |  | COMPLETED | 1 |  |  | 4A0215S00029 | 15DD0177 | 2015-07-27 | 2015-08-05 | 2015-08-10 | 2015-08-18 | 2015-09-09 | VRV CONSTRUCTION AND TRADING
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301108 | Laiya NHS | SAN JUAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107621 | Paaralang Elementarya ng Nagsaulay | SAN JUAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0215S00060 | 15DD0209 | 2015-11-20 | 2015-11-26 | 2015-12-09 | 2015-12-18 |  | MANUEL A. DELA TORRE, JR. BUILDERS
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301130 | Palahanan NHS | SAN JUAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0215S00026 | 15DD0185 | 2015-09-04 | 2015-09-10 | 2015-09-22 | 2015-09-29 | 2015-10-14 | BERTO LUCCI BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region IV-A | Batangas | 107625 | Pinagbayanan ES | SAN JUAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00059 | elem & jhs batch 6
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand Alone SHS- Taysan | TAYSAN | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 8 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 25 (IBAAN SHS) | IBAAN | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas |  | Proposed Stand-Alone SHS 27 (CALANTAS SHS) | ROSARIO | 4 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 5 | 5955185 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Batangas | 301139 | Rosario NHS | Rosario | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00043 | 15DD0183 | 2015-08-26 | 2015-09-01 | 2015-09-14 | 2015-09-23 | 2015-10-07 | BERTO LUCCI BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region IV-A | Batangas | 307708 | Sico 1.0 National High School | SAN JUAN | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0215S00068 | 15DD0208 | 2015-11-20 | 2015-11-26 | 2015-12-09 | 2015-12-18 |  | MANUEL A. DELA TORRE, JR. BUILDERS
NC 2015 | K10 (2015) | Region IV-A | Batangas | 301155 | Taysan NHS | SAN JOSE | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2058606 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region IV-A | Batangas | 301155 | Taysan NHS | SAN JOSE | 4 |  | 6 | 3STY6CL | 2015 K10 BATCH 7 | 10417132 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | BATANGAS CITY | 301471 | Banaba West NHS | BATANGAS CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10487131.51 |  |  | COMPLETED | 1 |  |  | 4A0215S00027 | 15DE0078 | 2015-08-17 | 2015-08-18 | 2015-09-03 | 2015-09-08 | 2015-09-14 | GREAT SWISS METAL BUILDERS CORPORATION
NC 2015 | SHS (2015) | Region IV-A | BATANGAS CITY |  | Proposed Stand-Alone SHS 1(Gulod) | BATANGAS CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 8 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | BATANGAS CITY |  | Proposed Stand-Alone SHS 2(Alangilan) | BATANGAS CITY (Capital) | 2 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 8 | 18222268.79 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | BATANGAS CITY | 301479 | San Agustin NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6639337.6381 |  |  | COMPLETED | 1 |  |  | 4A0215S00025 | 15DE0083 | 2015-09-03 | 2015-09-04 | 2015-09-18 | 2015-09-23 | 2015-09-30 | W. RIVERA CONSTRUCTION & EQUIPMENT RENTALS
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301511 | Bubuyan National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 4A0415S00068 | 15DI0152 | 2015-10-15 | 2015-10-28 | 2015-10-30 | 2015-11-16 | 2015-11-18 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301514 | Calamba Bayside National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0415S00043 | 15DI0123 | 2015-09-09 | 2015-09-21 | 2015-09-22 | 2015-09-27 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301516 | Camp Vicente Lim NHS | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0415S00047 | 15DI0107 | 2015-07-20 | 2015-08-03 | 2015-08-05 | 2015-08-20 | 2015-08-26 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301521 | Kapayapaan National HS | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 308701 | Lawa National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 15197519 |  |  | COMPLETED | 1 |  |  | 4A0415S00065 | 15DI0153 | 2015-10-15 | 2015-10-27 | 2015-10-30 | 2015-11-16 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301523 | Makiling National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 4A0415S00066 | 15DI0151 | 2015-10-15 | 2015-10-27 | 2015-10-30 | 2015-11-16 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | K10 (2015) | Region IV-A | CALAMBA CITY | 109856 | Palo Alto ES | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | 4A0415S00078 | 15DI0129 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301524 | Palo Alto National High School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0415S00038 | 15DI0108 | 2015-07-20 | 2015-08-03 | 2015-08-05 | 2015-08-20 | 2015-08-26 | HONEYVILLE CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | CALAMBA CITY | 109857 | Post ES | CITY OF CALAMBA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0415S00077 | 15DI0149 | 2015-10-15 | 2015-10-27 | 2015-10-28 | 2015-11-13 | 2015-11-18 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | CALAMBA CITY | 301525 | Punta National High School | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 |  |  | 4A0415S00062 | 15DI0148 | 2015-10-14 | 2015-10-26 | 2015-10-27 | 2015-11-09 | 2015-11-13 | GAB-ZION ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301172 | Bagbag NHS (Ligtong NHS) | ROSARIO | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301189 | Emiliano T. Tirona MNHS | KAWIT | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 24152343.62 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301189 | Emiliano T. Tirona MNHS | KAWIT | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301180 | Bulihan NHS | SILANG | 5 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301192 | Gen. Mariano Alvarez Tech. HS | GEN. MARIANO ALVAREZ | 5 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 32102890 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301192 | Gen. Mariano Alvarez Tech. HS | GEN. MARIANO ALVAREZ | 5 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301193 | Gen. Vito Belarmino NHS | SILANG | 5 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21383013.45 |  |  | COMPLETED | 1 |  |  | 4A0315S00011 | 15DG0060 | 2015-07-27 | 2015-08-08 | 2015-08-18 | 2015-08-27 | 2015-09-01 | ALMAKAR BUILDERS & METAL WORKS
NC 2015 | K10 (2015) | Region IV-A | CAVITE | 107895 | Lantic ES | CARMONA | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0315S00043 | 15DF0125 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | KLDS TRADING & CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | CAVITE | 108116 | Mataas Na Burol ES (Burol ES) | SILANG | 5 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1 |  |  | 4A0315S00041 | 15DG0077 | 2015-09-09 | 2015-09-21 | 2015-09-30 | 2015-10-14 | 2015-10-27 | OMNICON BUILDERS
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301205 | Munting Ilog NHS | SILANG | 5 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22352344 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | CAVITE | 107941 | San Gabriel II ES | GEN. MARIANO ALVAREZ | 5 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0315S00042 | 15DF0124 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301213 | San Jose Community HS | GEN. MARIANO ALVAREZ | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | CAVITE | 107943 | San Jose ES | GEN. MARIANO ALVAREZ | 5 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 4A0315S00044 | 15DF0125 | 2015-09-15 | 2015-09-22 | 2015-10-06 | 2015-10-12 | 2015-10-21 | KLDS TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE |  | SHS in Carmona | CARMONA | 5 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 64205781 |  |  | COMPLETED | 1 |  |  | 4A0315S00030 | 15DF0170 | 2015-11-06 | 2015-11-13 | 2015-12-04 | 2015-12-10 | 2015-12-18 | JV: R.A. DEL ROSARIO CONSTRUCTION/KLDS TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE |  | SHS within Ulat ES | SILANG | 5 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 4A0315S00060 | 15DG0085 | 2015-11-02 | 2015-11-14 | 2015-11-24 | 2015-12-11 |  | J.S. GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301166 | Amadeo NHS | AMADEO | 6 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0315S00013 | 15DG0052 | 2015-07-14 | 2015-07-26 | 2015-08-04 | 2015-08-18 | 2015-09-01 | R.D. MANDANAS CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301167 | Amaya Sch. of Home Industries | TANZA | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301167 | Amaya Sch. of Home Industries | TANZA | 6 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301195 | Halang Banaybanay NHS | AMADEO | 6 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10817132 |  |  | COMPLETED | 1 |  |  | 4A0315S00028 | 15DG0072 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-02 | 2015-10-16 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2015 | K10 (2015) | Region IV-A | GENERAL TRIAS CITY | 107951 | Manggahan ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | 2015 K10 BATCH 6 | 14747518.84 |  |  | COMPLETED | 1 |  |  | 4A0315S00045 | 15DF0114 | 2015-09-10 | 2015-09-17 | 2015-10-20 | 2015-10-26 | 2015-11-05 | BAQPRINCE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301217 | Talon NHS | AMADEO | 6 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0315S00027 | 15DG0070 | 2015-08-27 | 2015-09-08 | 2015-09-17 | 2015-10-02 | 2015-10-16 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301219 | Tanza NTS | TANZA | 6 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301219 | Tanza NTS | TANZA | 6 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301168 | Anuling NHS | MENDEZ (MENDEZ-NUÑEZ) | 8 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0315S00034 | 15DG0075 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-13 | 2015-10-27 | PRIJOLES TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301175 | Bucal NHS | MARAGONDON | 8 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301175 | Bucal NHS | MARAGONDON | 8 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 307805 | Buck Estate National HS | ALFONSO | 8 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0315S00023 | 15DG0076 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-14 | 2015-10-27 | PRIJOLES TRADING & CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301191 | Gen. Emilio Aguinaldo NHS (Bailen) | GENERAL EMILIO AGUINALDO | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 4A0315S00025 | 15DG0073 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-02 | 2015-10-16 | R.A. YOLANGCO CONSTRUCTION AND TRADING (FORMERLY:
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301199 | Lucsuhin National High School | ALFONSO | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10917132 |  |  | COMPLETED | 1 |  |  | 4A0315S00026 | 15DG0071 | 2015-08-28 | 2015-09-09 | 2015-09-18 | 2015-10-05 | 2015-10-16 | R.D. MANDANAS CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301201 | Lumampong NHS - Indang NHS Annex | INDANG | 7 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301201 | Lumampong NHS - Indang NHS Annex | INDANG | 7 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301207 | Naic NHS | NAIC | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301207 | Naic NHS | NAIC | 8 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301211 | Pulo ni Sara NHS | MARAGONDON | 8 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 4A0315S00032 | 15DG0074 | 2015-09-03 | 2015-09-15 | 2015-09-24 | 2015-10-13 | 2015-10-27 | N.B. AVILA CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301216 | Tagaytay City National High School | TAGAYTAY CITY | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 15197518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CAVITE | 301216 | Tagaytay City National High School | TAGAYTAY CITY | 8 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region IV-A | CAVITE | 301215 | Tagaytay City Nat'l. Science HS | TAGAYTAY CITY | 8 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1 |  |  | 4A0315S00017 | 15DG0096 | 2015-11-17 | 2015-11-29 | 2015-12-09 | 2015-12-28 |  | HAUSLAND CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE CITY | 301484 | Cavite National High School | CAVITE CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 2 | 31102890.27 |  |  | COMPLETED | 1 |  |  | 4A0315S00018 | 15DF0087 | 2015-08-07 | 2015-08-14 | 2015-08-28 | 2015-09-04 | 2015-09-14 | BAQPRINCE CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | CAVITE CITY | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 4A0315S00046 | 15DF0113 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | BAQPRINCE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CAVITE CITY |  | Proposed Stand Alone SHS (Sangley ES) | Cavite City | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 23052344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CAVITE CITY | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CITY OF BIÑAN |  | Proposed Stand-Alone SHS 14 | Biñan # 1 | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IV-A | CITY OF BIÑAN |  | Proposed Stand-Alone SHS 15 | Biñan # 2 | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CITY OF BIÑAN |  | Propsoed Stand-Alone SHS 16 | Biñan # 3 | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | CITY OF BIÑAN | 307931 | Saint Francis NHS | CITY OF BIÑAN | 1 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00020 | 15DI0087 | 2015-06-30 | 2015-07-14 | 2015-07-15 | 2015-07-22 | 2015-07-27 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14897518.84 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | CITY OF BIÑAN | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | reverted | 0
NC 2015 | K10 (2015) | Region IV-A | Dasmarinas City | 107904 | Langkaan ES | CITY OF DASMARIÑAS | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 4A0315S00047 | 15DF0111 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. YOLANGCO CONSTRUCTION AND TRADING (FORMERLY:
NC 2015 | K10 (2015) | Region IV-A | Dasmarinas City | 107905 | Malinta ES | CITY OF DASMARIÑAS | 4 | 1 | 6 | 3STY6CL | 2015 K10 BATCH 6 | 10267131.51 |  |  | COMPLETED | 1 |  |  | 4A0315S00049 | 15DF0112 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | L.B. SPIRES BUILDERS
NC 2015 | SHS (2015) | Region IV-A | Dasmarinas City |  | Stand Alone 1 - San Jose Site | Dasmariñas City | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31602890 |  |  | COMPLETED | 1 | [9 empty] | KLDS Construction & Trading
NC 2015 | SHS (2015) | Region IV-A | Dasmarinas City |  | Stand Alone 2 - Paliparan Site | Dasmariñas City | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 | [9 empty] | Almakar Builders and Metal Works
NC 2015 | SHS (2015) | Region IV-A | Dasmarinas City |  | Stand Alone 3 - Dr. Jose P. Rizal ES Site | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22552344 |  |  | COMPLETED | 1 | [9 empty] | Ramon F. Jabalera Construction
NC 2015 | SHS (2015) | Region IV-A | Dasmarinas City |  | Stand Alone 4 - Dasmariñas NHS Site | Dasmariñas City | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 5 | 15921328 |  |  | COMPLETED | 1 | [9 empty] | Bacprince Construction
NC 2015 | SHS (2015) | Region IV-A | Dasmarinas City |  | Stand Alone 5 - New Era ES Site | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1 | [9 empty] | R.A. Del Rosario Construction
NC 2015 | K10 (2015) | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 6 | 22002343.62 |  |  | COMPLETED | 1 |  |  | 4A0315S00048 | 15DF0116 | 2015-09-10 | 2015-09-17 | 2015-09-29 | 2015-10-05 | 2015-10-14 | BAQPRINCE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Imus City |  | Proposed Stand Alone SHS (Pedro Reyes) | Imus City | 3 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 5 | 53404939 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Imus City |  | Proposed Stand Alone SHS (Toclong) | Imus City | 3 | 1 | 32 | 4STY16CL | 2015 SHS BATCH 5 | 56404939 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | LAGUNA |  | Proposed Stand-Alone SHS 23 (Pacita I ES) | San Pedro | 1 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | LAGUNA | 108428 | Rosario Complex ES | SAN PEDRO | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0415S00079 | 15DI0128 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | L.P.O. ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | LAGUNA | 307914 | San Pedro Relocation CHS - Landayan Annex | SAN PEDRO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8514965.051 |  |  | COMPLETED | 1 |  |  | 4A0415S00028 | 4A04-15-S-00028 | 2015-12-10 | 2015-12-22 | 2015-12-23
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301229 | Bigaa NHS | CABUYAO | 2 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | COMPLETED | 1 |  |  | 4A0415S00041 | 4A04-15-S-00041 | 2015-11-07 | 2015-11-15 | 2015-11-18
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301235 | Cabuyao NHS - Casile NHS Annex | CABUYAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2238606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00040 | 15DI0126 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | R.D. MANDANAS CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301251 | Masaya NHS | BAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10567131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00039 | 15DI0111 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-11 | 2015-09-15 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 10 (Bayog) | LOS BAÑOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301259 | Proposed Stand-Alone SHS 12 (Pulo NHS) | Cabuyao # 1(Pulo) | 2 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 8 (Bambang Elementary School) | LOS BAÑOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 9 (Lalakay) | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 11 (BN. Calara) | Los Baños # 5 | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108313 | San Antonio Elementary School | LOS BAÑOS | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0415S00081 | 15DI0121 | 2015-09-10 | 2015-09-22 | 2015-09-24 | 2015-10-02 | 2015-10-09 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307923 | Southville I NHS | CABUYAO | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 2 | 22302343.62 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108210 | Sto Domingo ES | BAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00082 | 15DI0125 | 2015-10-02 | 2015-10-14 | 2015-10-15 | 2015-10-19 | 2015-10-23 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307933 | Tuntungin-Putho NHS | LOS BAÑOS | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00044 | 15DI0086 | 2015-06-30 | 2015-07-13 | 2015-07-15 | 2015-07-22 | 2015-07-27 | ST. GERRARD CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301265 | Alaminos NHS | ALAMINOS | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00045 | 15DP0072 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301228 | Banca-Banca NHS | VICTORIA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00056 | 15DP0073 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | MJACQ ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307924 | Buenaventura Fandialan Memo. NHS | ALAMINOS | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00049 | 15DP0074 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301237 | Calumpang NHS - Lowland NHS Annex | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00050 | 15DP0075 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307903 | Cristobal S. Conducto MNHS | RIZAL | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00051 | 15DP0076 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307927 | Dayap NHS (Calauan Annex) | CALAUAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 SHS BATCH 2 | 2952592.44 |  |  | COMPLETED | 1 |  |  | 4A0415S00052 | 15DP0070 | 2015-09-21 | 2015-09-22 | 2015-10-06 | 2015-10-24 | 2015-11-03 | DMLC BUILDERS
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108497 | Masapang ES | VICTORIA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00083 | 15DP0085 | 2015-09-21 | 2015-09-22 | 2015-10-06 | 2015-10-24 | 2015-11-03 | R CEL GENERAL CONTRACTOR & GEN MERCHANDISE
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301250 | Masapang NHS | VICTORIA | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00053 | 15DP0077 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301258 | Plaridel NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10467131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00054 | 15DP0078 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | MJACQ ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 21 | Calauan | 3 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301264 | San Francisco NHS | VICTORIA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1 |  |  | 4A0415S00029 | 15DP0071 | 2015-08-13 | 2015-08-13 | 2015-08-26 | 2015-09-13 | 2015-09-21 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00048 | 15DP0079 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301278 | Upland NHS | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00046 | 15DP0080 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108374 | Ibaba ES | PAETE | 4 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 1344160.8418 |  |  | Reverted | 0 |  |  | 4A0415S00090 | 4A04-15-S-00057
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108446 | Santa Cruz ES | STA. CRUZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 969303.02 |  |  | COMPLETED | 1 |  |  | 4A0415S00087 | 15DH0100 | 2015-10-23
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307918 | Balian NHS (Galalan Annex) | PANGIL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2288606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00019 | 15DH0053 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | ENC ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301232 | Buenavista NHS | MAGDALENA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 4A0415S00018 | 15DH0054 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108339 | Buenavista-Cigaras ES | MAGDALENA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0415S00086 | 15DH0069 | 2015-08-20 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-08 | DMLC BUILDERS
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108340 | Bungkol ES | MAGDALENA | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0415S00080 | 15DH0068 | 2015-08-20 | 2015-09-03 | 2015-09-15 | 2015-09-25 | 2015-10-23 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307911 | Cavinti NHS | CAVINTI | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14947518.84 |  |  | COMPLETED | 1 |  |  | 4A0415S00023 | 15DH0063 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307926 | Cavinti NHS (Calminue Ext.) | CAVINTI | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00017 | 15DH0083 | 2015-10-23 | 2015-11-04 | 2015-11-16 | 2015-11-27 | 2015-12-14 | JOBEL ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301240 | Famy National High School | FAMY | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15271327.92 |  |  | Reverted | 0 |  |  | 4A0415S00025 | 4A04-15-S-00025
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307906 | FELICISIMO T. SAN LUIS NHS | SANTA CRUZ (Capital) | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26852469.42 |  |  | COMPLETED | 1 |  |  | 4A0415S00026 | 15DH0071 | 2015-09-07 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | J.B. ALARCON ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301270 | Gaudencio Octavio National High School | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00037 | 15DH0064 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | K10 (2015) | Region IV-A | Laguna | 164501 | Gisgis ES | PANGIL | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00085 | 15DH0099 | 2015-11-24 | 2015-12-04 | 2015-12-16
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301274 | GOV. FELICISIMO T. SAN LUIS NATIONAL AGRO-INDUSTRIAL HIGH SCHOOL | SINILOAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1 |  |  | 4A0415S00016 | 15DH0055 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | L.P.O. ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301243 | Kabulusan National High School | PAKIL | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15221327.92 |  |  | COMPLETED | 1 |  |  | 4A0415S00032 | 15DH0066 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-10-05 | DSO ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307937 | Magdalena NHS (Buenavista Annex) | MAGDALENA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00033 | 15DH0061 | 2015-07-31 | 2015-08-12 | 2015-08-24 | 2015-09-02 | 2015-09-17 | PROTECH CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301253 | Pagsanjan NHS | PAGSANJAN | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00034 | 15DH0062 | 2015-07-31 | 2015-08-12 | 2015-08-24 | 2015-09-02 | 2015-09-17 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 3 | Pagsanjan | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10877343 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Proposed Stand-Alone SHS 19 (Paete Central Elementary School) | Paete (Paete ES) | 4 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna | 108412 | Proposed Stand-Alone SHS 20 (Pinagbayanan ES) | Pila | 4 | 1 | 30 | 3STY15CL | 2015 SHS BATCH 5 | 42766027 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | Laguna | 108343 | Ricardo A. Pronove ES | MAGDALENA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | Reverted | 0 |  |  | 4A0415S00084 | 15DH0027 | [5 empty] | PHILIPPINE CHEMSTEEL INDUSTRIES, INC.
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301263 | San Buenaventura NHS | LUISIANA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10517131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00035 | 15DH0067 | 2015-08-17 | 2015-08-27 | 2015-09-08 | 2015-09-22 | 2015-09-30 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307935 | San Buenaventura NHS Annex | LUISIANA | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 2 | 2188606.04 |  |  | COMPLETED | 1 |  |  | 4A0415S00015 | 15DH0056 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | ILG ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 307920 | San Juan NHS (San Antonio Annex) | KALAYAAN | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1 |  |  | 4A0415S00014 | 15DH0057 | 2015-07-15 | 2015-07-24 | 2015-08-06 | 2015-08-20 | 2015-09-02 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301271 | Santa Maria NHS - J. Santiago Annex | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00055 | 15DH0072 | 2015-09-01 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301268 | Sta. Catalina NHS | MAJAYJAY | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10617131.51 |  |  | COMPLETED | 1 |  |  | 4A0415S00027 | 15DH0073 | 2015-09-01 | 2015-09-11 | 2015-09-23 | 2015-09-29 | 2015-10-13 | PROTECH CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Laguna | 301269 | Sta. Maria NHS | SANTA MARIA | 4 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 2 | 21533013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Stand Alone SHS No. 20 Santa Cruz | Santa Cruz | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 5 | 26702469 |  |  | COMPLETED | 1 |  |  | 4A0415S00099 | 15DH0097 | 2015-11-24 | 2015-12-04 | 2015-12-16
NC 2015 | SHS (2015) | Region IV-A | Laguna |  | Stand Alone SHS No. 4 Sta. Cruz | Santa Cruz | 4 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31102890 |  |  | COMPLETED | 1 |  |  | 4A0415S00070 | 15DH0080 | 2015-10-19 | 2015-10-22 | 2015-11-03 | 2015-11-16 | 2015-12-01 | C.T. LEONCIO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | LIPA CITY | 301487 | BOLBOK NATIONAL HIGH SCHOOL | LIPA CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  |  | 15DD0189 |  |  |  |  | 2016-10-22 | RV RIETA TRADING AND GENERAL CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region IV-A | LIPA CITY | 301487 | BOLBOK NATIONAL HIGH SCHOOL | LIPA CITY | 4 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1 |  |  |  | 16DD0009 |  |  |  |  | 2016-03-10 | RV RIETA TRADING AND GENERAL CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | LIPA CITY | 301490 | Fernando Air Base NHS | LIPA CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 2 | 10877342.5917 |  |  | COMPLETED | 1 |  |  | 4A0215S00031 | 15DD0178 | 2015-08-06 | 2015-08-18 | 2015-08-19 | 2015-08-27 | 2015-09-15 | F.F. ROSALES GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | LIPA CITY | 301491 | Inosloban-Marawoy NHS | LIPA CITY | 4 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14967518.84 |  |  | COMPLETED | 1 |  |  |  | 15DD0184 |  |  |  |  | 2015-12-01 | RV RIETA TRADING AND GENERAL CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region IV-A | LIPA CITY | 301491 | Inosloban-Marawoy NHS | LIPA CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  |  | 16DD0011 |  |  |  |  | 2016-03-11 | BERTO LUCCI BUILDERS & SUPPLY
NC 2015 | K10 (2015) | Region IV-A | LIPA CITY | 109693 | Padre Valerio Malabanan MS | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0215S00054 | 16DD0078 | 2015-11-20 | 2015-11-26 |  |  | 2016-04-05 | JBL BUILDERS
NC 2015 | SHS (2015) | Region IV-A | LIPA CITY | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  |  | 15DD0187 |  |  |  |  | 2015-10-22 | RV RIETA TRADING AND GENERAL CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region IV-A | LIPA CITY | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1 |  |  |  | 16DD0012 |  |  |  |  | 2016-03-11 | BERTO LUCCI BUILDERS & SUPPLY
NC 2015 | SHS (2015) | Region IV-A | LIPA CITY | 301499 | San Celestino National High School | LIPA CITY | 4 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 5 | 10957343 |  |  | COMPLETED | 1 |  |  | 4A0215S00046 | 15DD0191 | 2015-10-17 | 2015-10-23 | 2015-11-04 | 2015-11-12 | 2015-12-01 | THREE W BUILDERS, INC. | No Remarks
NC 2015 | K10 (2015) | Region IV-A | LIPA CITY | 109686 | San Guillermo ES | LIPA CITY | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0215S00055 | 16DD0076 |  |  |  |  | 2016-04-05 | JBL BUILDERS | No Remarks
NC 2015 | K10 (2015) | Region IV-A | LIPA CITY | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 4 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0215S00056 | 15DD0202 | 2015-11-20 | 2015-11-26
NC 2015 | SHS (2015) | Region IV-A | LUCENA CITY | 308503 | Gulang-Gulang NHS | LUCENA CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0515S00028 | 15DJ0069 | 2015-07-16 | 2015-08-04 | 2015-08-06 | 2015-08-11 | 2015-08-12 | MGDJ CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | LUCENA CITY | 167502 | Isabang ES-Bocohan Annex | LUCENA CITY (Capital) | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0515S00099 | 15DJ0077 | 2015-08-31 | 2015-09-02 | 2015-09-15 | 2015-09-21 | 2015-09-24 | MGDJ CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | LUCENA CITY | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IV-A | LUCENA CITY | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | LUCENA CITY | 308505 | Lucena City NHS -Mayao Parada Extension | LUCENA CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00026 | 15DJ0071 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | SOUTHERN DAWN DEVELOPMENT COMPANY
NC 2015 | SHS (2015) | Region IV-A | LUCENA CITY | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26702469.42 |  |  | COMPLETED | 1 |  |  | 4A0515S00025 | 15DJ0074 | 2015-07-29 | 2015-07-31 | 2015-08-13 | 2015-08-17 | 2015-08-25 | DQT BUILDERS CORPORATION (FORMERLY DQT BUILDERS)
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301292 | Batangan National High School | GENERAL NAKAR | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00124 | 15DK0132 | 2015-10-08 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308028 | Busdak NHS (Formerly Busdak NHS - Patnanungan NHS Annex) | PATNANUNGAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00122 | 15DK0128 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108907 | Cagsiay II ES | MAUBAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00107 | 15DK0098 | 2015-10-07 | 2015-10-09 | 2015-10-30 | 2015-11-10 | 2015-11-20 | L.A. CLAMOR CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301397 | Calasumanga NHS (Formerly San Juan NHS - Calasumanga Ext.) | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00121 | 15DK0131 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301333 | Jomalig NHS | JOMALIG | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00024 | 15DK0061 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301343 | Langgas NHS | INFANTA | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00023 | 15DK0059 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-08-07 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108568 | Palasan ES | BURDEOS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00098 | 15DK0100 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109041 | Pandan ES | PANUKULAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00097 | 15DK0101 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108990 | Patnanungan Norte ES | PATNANUNGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00096 | 15DK0099 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 165002 | Remedios I ES (Annex) Bulusok | MAUBAN | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00106 | 15DK0102 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301382 | Sabang NHS | POLILLO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00108 | 15DK0130 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301396 | San Juan NHS | PANUKULAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00022 | 15DK0060 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | E.A. AYALA CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301408 | Taluong NHS | POLILLO | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00111 | 15DK0129 | 2015-10-08 | 2015-10-13 | 2015-10-30 | 2015-11-10 | 2015-11-20 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108571 | Tulan ES | BURDEOS | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00089 | 15DK0103 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | ANNCON BUILDERS
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301412 | Ungos NHS | REAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0515S00018 | 15DK0126 | 2015-10-15 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301413 | Ungos NHS - Extension (Llavac) | REAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0515S00018 | 15DK0126 | 2015-10-08 | 2015-10-16 | 2015-10-30 | 2015-11-10 | 2015-11-20 | JUNTEREAL INDUSTRIAL AND DEVELOPMENT CORPORATION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308043 | Bignay NHS | SARIAYA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00123 | 15DJ0085 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | Quezon | 301308 | Canda NHS | SARIAYA | 2 | 1 | 4 | ADDITIONAL 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308041 | Castañas NHS | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0515S00119 | 15DJ0088 | 2015-09-28 | 2015-09-30 | 2015-10-22 | 2015-10-27 | 2015-10-30 | M.G. VILLAMIN CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301317 | Dagatan NHS | DOLORES | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 2 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0515S00020 | 15JD0068 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-07 | 2015-08-12 | DL ENTERPRISES
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308040 | Dr. Panfilo Castro NHS - Masalukot I Annex | CANDELARIA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00029 | 15DJ0070 | 2015-07-16 | 2015-07-20 | 2015-08-04 | 2015-08-10 | 2015-08-12 | MGDJ CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308012 | Gloria Umali NHS | TIAONG | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00117 | 15DJ0089 | 2015-09-28 | 2015-09-30 | 2015-10-22 | 2015-10-27 | 2015-10-30 | M.A. GUINTO CONSTRUCTION (SAN JOSE BRANCH)
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301349 | Lutucan National High Scool | SARIAYA | 2 | 1 | 3 | Construction of 3 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308016 | Manuel M. Macasaet NHS (Formerly Sta. Catalina NHS - Amland Ext.) | CANDELARIA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0515S00113 | 15DJ0084 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308032 | Pili NHS (Formerly Lutucan NHS Pili Ext.) | SARIAYA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0515S00112 | 15DJ0086 | 2015-09-27 | 2015-09-28 | 2015-10-20 | 2015-10-26 | 2015-10-28 | M.G. VILLAMIN CONSTRUCTION
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301380 | Recto MNHS | TIAONG | 2 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301280 | Abuyon NHS | SAN NARCISO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0515S00110 | 4A05-15-S-00110 | 2015-09-03 | 2015-08-24 | 2015-09-03 | 2015-12-09 | 2015-12-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108918 | Acaciahan ES | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00070 | 4A05-15-S-00070 | 2015-08-12
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108643 | Ajos ES | CATANAUAN | 3 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  | 4A0515S00093 | 4A05-15-S-00093 | 2015-09-16 | 2015-09-04 | 2015-09-16
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108920 | Anonang ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00104 | 4A05-15-S-00104 | 2015-08-12
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301288 | Bagupaye NHS | MULANAY | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109089 | Banaba ES | SAN ANDRES | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00101 | 4A05-15-S-00101 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-10-27 | JSP CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 4A0515S00040 | 4A05-15-S-00040 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301298 | Busdak NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3747969 |  |  | COMPLETED | 1 |  |  | 4A0515S00030 | 4A05-15-S-00030. | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308014 | Cabong NHS | BUENAVISTA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2008606 |  |  | COMPLETED | 1 |  |  | 4A0515S00059 | 4A05-15-S-00059 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301300 | Cabulihan NHS | PITOGO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0515S00050 | 4A05-15-S-00050 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108946 | Cabuyao ES | PADRE BURGOS | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00071 | 4A05-15-S-00071 | 2015-09-14 | 2015-09-15 | 2015-09-16
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108925 | Calangcang ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00103 | 15DM0109 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-11-06 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109002 | Cawayanin ES | PITOGO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00072 | 4A05-15-S-00072 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-09-22 | 2015-12-16 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301399 | Godofredo M. Tan Mem. SAT (Formerly San Narciso Voc. HS) | SAN NARCISO | 3 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301322 | Gregorio Reyes NHS | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6519338 |  |  | COMPLETED | 1 |  |  | 4A0515S00042 | 4A05-15-S-00042 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-31 | 2015-12-10 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308044 | Huyon-Uyon NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3967969 |  |  | COMPLETED | 1 |  |  | 4A0515S00033 | 4A05-15-S-00033 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | KKT CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301371 | Leonarda D. Vera Cruz NHS (Formerly Panaon NHS) | UNISAN | 3 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10517132 |  |  | COMPLETED | 1 |  |  | 4A0515S00049 | 4A05-15-S-00049 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-30 | 2015-11-17 | RGP BUILDERS
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301337 | Lina Gayeta-Lasquety NHS (Formerly Kinagunan Ibaba NHS) | PADRE BURGOS | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308039 | LUALHATI D. EDAÑO NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00115 | 4A05-15-S-00115 | 2015-09-03 | 2015-08-24 | 2015-09-03
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301283 | Magsaysay NHS (Formerly Ajos NHS - Magsaysay Extension) | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1998606 |  |  | COMPLETED | 1 |  |  | 4A0515S00052 | 4A05-15-S-00052 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108879 | Malabahay ES | MACALELON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00087 | 4A05-15-S-00087 | 2015-08-12
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301354 | Malaya NHS | GENERAL LUNA | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00114 | 4A05-15-S-00114 | 2015-08-21 | 2015-08-24 | 2015-09-03 | 2015-09-10 | 2015-11-17 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108933 | Malibago ES | MULANAY | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00102 | 4A05-15-S-00102 | 2015-09-16 | 2015-09-04 | 2015-09-16
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308008 | Maligaya NHS | BUENAVISTA | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3727969 |  |  | COMPLETED | 1 |  |  | 4A0515S00048 | 15DM0106 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | L.A. PROFUGO CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108934 | Matataja ES | MULANAY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00066 | 4A05-15-S-00066 | 2015-10-28 | 2015-10-16 | 2015-10-28 | 2015-11-03 | 2015-12-16 | RGP BUILDERS
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301330 | PAKIING NATIONALHIGH SCHOOL | MULANAY | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3747969 |  |  | REVERTED | 0 |  |  | 4A0515S00051 | 4A05-15-S-00051 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301376 | Pitogo Community High School | PITOGO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 4A0515S00056 | 4A05-15-S-00056 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108691 | Recto ES | GENERAL LUNA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00076 | 4A05-15-S-00076 | 2015-10-20 | 2015-10-08 | 2015-10-20
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301368 | Renato Edano Vicencio NHS (Formerly Pagsangahan NHS-Don Juan Vercelos Annex) | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 4027969 |  |  | COMPLETED | 1 |  |  | 4A0515S00037 | 4A05-15-S-00037 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109149 | Rizal ES | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00100 | 4A05-15-S-00100 | 2015-08-12 | 2015-08-24 | 2015-08-25 | 2015-09-03 | 2015-09-14 | RAPID FOREMOST CONST. CO.
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108693 | San Ignacio Ilaya ES | GENERAL LUNA | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00105 | 4A05-15-S-00105 | 2015-10-20 | 2015-10-08 | 2015-10-20
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108661 | San Pablo Suha ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00092 | 4A05-15-S-00092 | 2015-08-12
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308010 | San Vicente Kanluran NHS (Formerly San Isidro NHS - San Vicente Kanluran Ext) | CATANAUAN | 3 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 4A0515S00062 | 15DM0081 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-08-30 | 2015-11-17 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308003 | Sto. Niño National High School (Formerly Pagsangahan NHS Ext. Sto. Niño) | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 4077212 |  |  | COMPLETED | 1 |  |  | 4A0515S00057 | 4A05-15-S-00057 | 2015-08-12 | 2015-08-13 | 2015-08-25 | 2015-11-20 | 2015-11-26 | RAPID FOREMOST CONST. CO.
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108697 | Sumilang ES | GENERAL LUNA | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00069 | 4A05-15-S-00069 | 2015-10-20 | 2015-10-08 | 2015-10-20
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS - Tagabas Ibaba Ext) | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0515S00065 | 15DM0100 | 2015-08-27 | 2015-08-28 | 2015-09-09 | 2015-10-09 | 2015-10-27 | KKT CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108669 | Tagbacan Ilaya ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00091 | 4A05-15-S-00091 | 2015-09-16 | 2015-09-04 | 2015-09-16 | 2015-11-20 | 2015-11-26 | RAPID FOREMOST CONST. CO.
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108671 | Tuhian ES | CATANAUAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00090 | 4A05-15-S-00090 | 2015-08-12
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109135 | Tumbaga ES | SAN FRANCISCO (AURORA) | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00073 | 4A05-15-S-00073 | 2015-08-12
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308031 | White Cliff NHS | SAN NARCISO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1 |  |  | 4A0515S00032 | 4A05-15-S-00032 | 2015-08-12 | 2015-08-13 | 2015-08-25
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301284 | Alabat Island NHS | ALABAT | 4 | 1 | 2 | Construction of 2 Workshop Buildings (Standard Technical Vocational Building) | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301342 | Aloneros NHS (Formerly LBS of Fisheries Ext. - Aloneros | GUINAYANGAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0515S00053 | 15DL0163 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-11-02 | E.A. VILLANUEVA CONSTRUCTION
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308017 | Apad NHS (Formerly Sto. Domingo NHS - Apad Ext. Classes) | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | COMPLETED | 1 |  |  | 4A0515S00041 | 15DL0152 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | JUNCAN ENTERPRISES
NC 2015 | TECHVOC (2015) | Region IV-A | QUEZON | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301287 | Bagong Silang NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301289 | Bamban NHS | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0515S00058 | 15DL0161 | 2015-09-24 | 2015-10-01 | 2015-10-19 | 2015-10-22 | 2015-10-28 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108594 | Bantulinao ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00077 | 15DL0141 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308038 | Cabibihan NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2013606 |  |  | COMPLETED | 1 |  |  | 4A0515S00043 | 15DL0154 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301307 | Camohaguin NHS | GUMACA | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0515S00120
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308042 | Cogorin Ibaba NHS - Jongo Ext. | LOPEZ | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00118
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301316 | Concepcion National High School | PLARIDEL | 4 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 8 | 10417131.51 |  |  | COMPLETED | 1 |  |  | 4A0515S00126
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2048606 |  |  | COMPLETED | 1 |  |  | 4A0515S00031 | 15DL0151 | 2015-09-21 | 2015-09-23 | 2015-09-15 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108577 | Dapdap ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00075 | 15DL0136 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308021 | Dr. Arsenio C. Nicolas NHS | CALAUAG | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6369338 |  |  | COMPLETED | 1 |  |  | 4A0515S00047 | 15DL0150 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308027 | Dr. Arsenio C. Nicolas NHS - Dominlog Ext. | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2038606 |  |  | COMPLETED | 1 |  |  | 4A0515S00044
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301320 | Dungawan NHS | GUINAYANGAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3717969 |  |  | COMPLETED | 1 |  |  | 4A0515S00060 | 15DL0157 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | ZELAN CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108735 | Dungawan Paalyunan ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00067 | 15DL0135 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-02 | 2015-10-14 | ZELAN CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108737 | Gregorio M. Mendoza ES | GUINAYANGAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 6 | 3667968.78 |  |  | COMPLETED | 1 |  |  | 4A0515S00094
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301331 | Inaclagan NHS | GUMACA | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 8 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00109
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108808 | Inalusan ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00080 | 15DL0137 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108846 | Jongo ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00083 | 15DL0138 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301336 | Katimo NHS | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6419338 |  |  | COMPLETED | 1 |  |  | 4A0515S00063 | 15DL0160 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-28 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301341 | Lamon Bay SOF Annex - Capalohan, Calauag | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2238606 |  |  | COMPLETED | 1 |  |  | 4A0515S00064 | 15DL0149 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109055 | Ma. Febrer Maningas ES | QUEZON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00078 | 15DL0140 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308045 | Mansilay NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1948606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308002 | Mapulot NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1953606 |  |  | COMPLETED | 1 |  |  | 4A0515S00055 | 15DL0155 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | C.G. CABANA CONSTRUCTION & SUPPLIES
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301375 | Perez National High School | PEREZ | 4 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108814 | Pisipis ES | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00081 | 15DL0141 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308022 | Rufina P. Trinidad Mem. NHS | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | COMPLETED | 1 |  |  | 4A0515S00046 | 15DL0149 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6389338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301398 | SANMANDELCAR NHS | TAGKAWAYAN | 4 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 SHS BATCH 5 | 3877969 |  |  | COMPLETED | 1 |  |  | 4A0515S00038
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108531 | Sta. Catalina ES | ATIMONAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00074 | 15DL0140 | 2015-09-11 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301324 | STA. CRUZ NATIONAL HIGH SCHOOL | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0515S00061 | 15DL0158 | 2015-09-22 | 2015-09-23 | 2015-10-06 | 2015-10-09 | 2015-10-18 | ZELAN CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108748 | Sta. Maria ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00079 | 15DL0135 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-03 | 2015-10-21 | ZELAN CONSTRUCTION AND SUPPLY
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108820 | Sto. Niño ES | LOPEZ | 4 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00068 | 15DL0143 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-03 | 2015-10-21 | JUNCAN ENTERPRISES
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 301389 | Sto. Nino Ilaya NHS (Formerly San Francisco B NHS Sto. Niño Ilaya Ext.) | LOPEZ EAST | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00136
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 301405 | Tabason NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1948606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108587 | Talingting ES | CALAUAG | 4 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1 |  |  | 4A0515S00095 | 15DL0139 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108588 | Tamis ES | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00088 | 15DL0136 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 109060 | Teofilo Olivera ES | QUEZON | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00084 | 15DL0142 | 2015-09-14 | 2015-09-15 | 2015-09-29 | 2015-10-05 | 2015-10-14 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | QUEZON | 108823 | Vegaflor Elementary School | LOPEZ | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0515S00082 | 15DL0137 | 2015-09-11 | 2015-09-16 | 2015-09-29 | 2015-10-05 | 2015-10-21 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | SHS (2015) | Region IV-A | QUEZON | 308013 | Villa San Isidro NHS | CALAUAG | 4 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 2138606 |  |  | COMPLETED | 1 |  |  | 4A0515S00045 | 15DL0150 | 2015-09-21 | 2015-09-23 | 2015-10-05 | 2015-10-08 | 2015-10-23 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109307 | Angono ES | ANGONO | 1 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 6 | 26552469.42 |  |  | COMPLETED | 1 |  |  | 4A0615S00029 | 15DN0119 | 2015-10-22 | 2015-10-23 | 2015-11-05 | 2015-11-18 |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109393 | Balanti ES | CAINTA | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Reverted | 0 |  |  | 4A0615S00032 | 4A06-15-S-00032
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301433 | Carlos "Botong" Francisco MNHS | ANGONO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1 |  |  | 4A0615S00017 | 15DN0127 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-14 | ONE EULUZ CONSTRUCTION CORPORATION (FORMERLY: EULUZ CONSTRUCTION & SUPPLY)
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109366 | Casimiro A. Ynares, Sr. ES | BINANGONAN | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00033 | 15DN0130 | 2015-11-12 | 2015-11-13 | 2015-11-26
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 308131 | Dr. Vivencio B. Villamayor NHS | ANGONO | 1 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 7 | 15121328 |  |  | COMPLETED | 1 |  |  | 4A0615S00041
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301445 | Janosa National High School | BINANGONAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0615S00046 | 15DN0128 | 2015-11-05 | 2015-11-05 | 2015-11-19 | 2015-12-01 | 2015-12-14 | FRAMECON BUILDERS
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308104 | Margarito A. Duavit MNHS | BINANGONAN | 1 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 5 | 14897519 |  |  | COMPLETED | 1 |  |  | 4A0615S00013 | 15DN0123 | 2015-11-04 | 2015-11-04 | 2015-11-17 | 2015-11-27 | 2015-12-14 | STO. CRISTO CONSTRUCTION & TRADING | No Remarks
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109404 | Marick ES | CAINTA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00031 | 15DN0111 | 2015-10-07 | 2015-10-07 | 2015-10-20 | 2015-11-02 | 2015-11-13 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308113 | Regional Lead School for the Arts in Angono | ANGONO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 SHS BATCH 5 | 1938606 |  |  | COMPLETED | 1 |  |  | 4A0615S00021
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109315 | San Vicente ES | ANGONO | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00034 | 15DN0129 | 2015-11-12 | 2015-11-13 | 2015-11-26
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301463 | Talim Point NHS | BINANGONAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00005 | 15DN0090 | 2015-08-26 | 2015-08-26 | 2015-09-08 | 2015-09-18 | 2015-10-01 | MARK CONSTRUCTION CORPORATION
NC 2015 | TECHVOC (2015) | Region IV-A | RIZAL | 301469 | Vicente Madrigal NHS | BINANGONAN | 1 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109499 | Balimbing ES | TANAY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 4A0615S00036 | 15DO0065 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | JRD-D2 ENTERPRISES
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109505 | Daraetan ES | TANAY | 2 | 1 | 10 | 2STY10CL | 2015 K10 BATCH 6 | 12621310.093 |  |  | Reverted | 0 |  |  | 4A0615S00039
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 165503 | Hulo ES | PILILLA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00028 | 15DO0117 | 2015-12-24
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308121 | Hulo NHS | PILILLA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00006 | 15DO0054 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109489 | Justice Vicente Santiago ES | SAN MATEO | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  | 4A0615S00030 | 15DO0094 | 2015-11-10 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-21 | R.F. DIAZ CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109510 | Madilay-dilay ES | TANAY | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00035 | 15DO0064 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | NVF CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109473 | Mascap ES - Magalipit Annex | RODRIGUEZ (MONTALBAN) | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00022 | 15DO0115 | 2015-12-24
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301452 | Morong National High School | MORONG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 8 | 8214965.051 |  |  | COMPLETED | 1 |  |  | 4A0615S00045 | 15DO0093 | 2015-11-10 | 2015-11-13 | 2015-11-25 | 2015-12-10 | 2015-12-21 | MINROCK MULTI-BUILDERS
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308123 | Pantay NHS (Teresa NHS - Pantay Annex) | TERESA | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 4A0615S00018 | 15DO0109 | 2015-12-02 | 2015-12-01 | 2015-12-18 |  |  | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109493 | Pintong Bukawe ES | SAN MATEO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  | 4A0615S00040 | 15DO0068 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301459 | Pintong Bukawe National High School | SAN MATEO | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0615S00014 | 15DO0075 | 2015-10-21 | 2015-10-22 | 2015-11-04 | 2015-11-12 | 2015-11-27 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2015 | SHS (2015) | Region IV-A | RIZAL |  | Proposed Stand-Alone SHS 4 | TANAY | 2 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 5 | 22152344 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109459 | Quisao ES | PILILLA | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0615S00038 | 15DO0116 | 2015-12-24
NC 2015 | TECHVOC (2015) | Region IV-A | RIZAL | 301456 | Sampaloc NHS | TANAY | 2 | 1 | 1 | Construction of 1 unit Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109442 | San Guillermo Elementary School | MORONG | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00027 | 15DO0063 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-30 | 2015-11-11 | FLAG CONSTRUCTION CORPORATION(FOR. FLAG CONSTRUCTI
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 109494 | San Mateo ES | SAN MATEO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00037 | 15DO0062 | 2015-10-06 | 2015-10-09 | 2015-10-22 | 2015-10-27 | 2015-11-11 | R.F. DIAZ CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 308135 | Southville 8C NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 7 | 26702469 |  |  | Reverted | 0 |  |  | 4A0615S00043
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308128 | TANAY EAST NATIONAL HIGH SCHOOL | TANAY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Reverted | 0 |  |  | 4A0615S00015
NC 2015 | K10 (2015) | Region IV-A | RIZAL | 308141 | Tanay North NHS | TANAY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | COMPLETED | 1 |  |  | 4A0615S00042 | 15DO0118
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 308138 | Tanay West NHS | TANAY | 2 | 1 | 6 | 3STY6CL | 2015 SHS BATCH 5 | 10417132 |  |  | COMPLETED | 1 |  |  | 4A0615S00016 | 15DO0108 | 2015-12-02 | 2015-12-01 | 2015-12-18 |  |  | HEXAMINDZ CORPORATION (FORMERLY:KILUSANG MAGKAIBIG
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301467 | Teresa NHS | TERESA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | RIZAL | 301468 | Tuna-Balibago NHS | CARDONA | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0615S00003 | 15DO0055 | 2015-07-21 | 2015-07-23 | 2015-08-05 | 2015-08-13 | 2015-08-26 | C.P.F. CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | 2015 K10 BATCH 7 | 26702469 |  |  | COMPLETED | 1 |  |  | 4A0415S00091 | 15DP0097 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | K10 (2015) | Region IV-A | San Pablo City | 301508 | San Bartolome National High School | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0415S00092 | 15DP0094 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | K10 (2015) | Region IV-A | San Pablo City | 301503 | San Cristobal National High School | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1 |  |  | 4A0415S00093 | 15DP0095 | 2015-10-28 | 2015-10-30 | 2015-11-12 | 2015-11-21 | 2015-11-25 | NEW RICH GENERAL CONTRACTOR SERVICES & TRADING Co.
NC 2015 | SHS (2015) | Region IV-A | San Pablo City | 308605 | San Pablo City Science High School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 2 | 15196327.92 |  |  | COMPLETED | 1 |  |  | 4A0415S00059 | 15DP0081 | 2015-08-25 | 2015-08-27 | 2015-09-08 | 2015-09-26 | 2015-10-02 | STO. CRISTO CONSTRUCTION & TRADING
NC 2015 | SHS (2015) | Region IV-A | Sta. Rosa City | 301224 | Aplaya NHS | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL | 2015 SHS BATCH 8 | 22152343.62 |  |  | COMPLETED | 1 |  |  |  | 15DI0146 | 2015-11-13 | 2015-11-19 | 2015-12-02 | 2015-12-09 | 2015-12-15 | JUNCAN ENTERPRISES | No Remarks
NC 2015 | K10 (2015) | Region IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0415S00089 | 15IDI0176 | 2015-10-30 | 2015-11-05 | 2015-11-18 | 2015-11-25 | 2015-12-04 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | Sta. Rosa City | 108477 | Macabling Elementary School | CITY OF SANTA ROSA | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1 |  |  | 4A0415S00088 | 15IDI0177 | 2015-10-30 | 2015-11-05 | 2015-11-18 | 2015-11-25 | 2015-12-04 | LAKE CITY BUILDER
NC 2015 | SHS (2015) | Region IV-A | TANAUAN CITY | 301089 | Boot NHS | CITY OF TANAUAN | 3 | 1 | 8 | 4STY8CL | 2015 SHS BATCH 2 | 14927518.84 |  |  | COMPLETED | 1 |  |  | 4A0215S00035 | 4A02-15-S-00035 | [5 empty] | EDRES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region IV-A | TANAUAN CITY | 301133 | Pantay NHS | CITY OF TANAUAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8264965 |  |  | COMPLETED | 1 |  |  | 4A0215S00051 | 15DC0109 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | EDRES CONSTRUCTION & SUPPLY
NC 2015 | SHS (2015) | Region IV-A | TANAUAN CITY | 321601 | Tanauan City HS | CITY OF TANAUAN | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26732469.42 |  |  | COMPLETED | 1 |  |  | 4A0215S00034 | 15DC0102 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2015 | SHS (2015) | Region IV-A | TANAUAN CITY | 301154 | Tanuan School of Fisheries | CITY OF TANAUAN | 3 | 1 | 16 | 4STY16CL | 2015 SHS BATCH 2 | 26772469.42 |  |  | COMPLETED | 1 |  |  | 4A0215S00032 | 15DC0103 | 2015-10-01 | 2015-10-13 | 2015-10-14 |  |  | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2015 | K10 (2015) | Region IV-A | TAYABAS CITY | 109253 | Ipilan-Alitao ES | CITY OF TAYABAS | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0515S00085 | 15DK0104 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | F. JIMENEZ CONSTRUCTION AND SUPPLY
NC 2015 | SHS (2015) | Region IV-A | TAYABAS CITY |  | Proposed SHS 1 | Tayabas City | 1 | 1 | 40 | 4STY20CL | 2015 SHS BATCH 5 | 62205781 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IV-A | TAYABAS CITY | 308036 | Quezon Science High School | CITY OF TAYABAS | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1 |  |  | 4A0515S00021 | 15DK0062 | 2015-07-10 | 2015-07-16 | 2015-07-28 | 2015-07-31 | 2015-08-13 | BOMEL CONSTRUCTION
NC 2015 | K10 (2015) | Region IV-A | TAYABAS CITY | 109260 | Tayabas West Central School II | CITY OF TAYABAS | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1 |  |  | 4A0515S00086 | 15DK0105 | 2015-08-27 | 2015-08-28 | 2015-09-15 | 2015-09-22 | 2015-10-05 | ANNCON BUILDERS
NC 2016 | K10 | Region IV-A | Antipolo City | 301448 | Mambugan Nhs | City Of Antipolo | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 32150000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Antipolo City | 301422 | Mayamot Nhs | City Of Antipolo | 1 | 1 | 32 | 4STY8CL | BATCH 13 CL | 60640075.36 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Antipolo City | 301422 | Mayamot Nhs | City Of Antipolo | 1 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109341 | Sapinit Es | Antipolo City | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City |  | Sta. Cruz Es | City Of Antipolo | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32950000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109361 | Sumilang Es | Antipolo City | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 321502 | Antipolo Nhs - Canumay Extension | City Of Antipolo | 2 | 1 | 6 | 3STY6CL | BATCH 1 CL | 10650000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 301421 | Antipolo Nhs - Kaysakat Extension | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 1 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DNO036 | 2016-02-28 | 2016-03-04 | 2016-03-17 | 2016-03-21 | 2016-03-22
NC 2016 | K10 | Region IV-A | Antipolo City | 109335 | Cabading Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Antipolo City | 301431 | Calawis Nhs | City Of Antipolo | 2 | 1 | 4 | 2STY4CL | BATCH 1 CL | 6500000 |  |  | Completed | 1 |  |  |  | 16DNO021 | 2016-02-18 | 2016-02-24 | 2016-03-08 | 2016-03-15 | 2016-03-18
NC 2016 | K10 | Region IV-A | Antipolo City | 230002 | Cupang Es Annex | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1)
NC 2016 | SHS | Region IV-A | Antipolo City | 301420 | Dalig Nhs To Cupang Nhs | City Of Antipolo | 2 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22650000 |  |  | Reverted | 0 | [10 empty] | Realigned to Cupang NHS. Construction was not started because of the informal settlers. Requested for termination by DPWH (terminated)
NC 2016 | K10 | Region IV-A | Antipolo City | 109326 | Inuman Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 5 CL | 15470000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109350 | Isaias S. Tapales Es | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109352 | From Kaysakat Es, Old Boso Boso Es And Pantay Es To Kaysakat Es | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 7806036.0641 |  |  | Completed | 1 | [10 empty] | Terminated
NC 2016 | SHS | Region IV-A | Antipolo City | 321501 | Marcelino M. Santos Nhs | City Of Antipolo | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31650000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Antipolo City | 301450 | Maximo L. Gatlabayan Memorial Nhs | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15470000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 308101 | Maximo L. Gatlabayan Mnhs - Old Boso-Boso Extension | City Of Antipolo | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109333 | Nazarene Ville Es | City Of Antipolo | 2 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31650000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1)
NC 2016 | K10 | Region IV-A | Antipolo City | 109334 | Old Boso-Boso Es | City Of Antipolo | 2 |  |  | 1STY3CL | BATCH 9 CL |  |  |  | Reverted | 0 | [10 empty] | Realigned to Kaysakat ES Terminated
NC 2016 | K10 | Region IV-A | Antipolo City | 109354 | Pantay Es | City Of Antipolo | 2 |  |  | 1STY3CL | BATCH 9 CL |  |  |  | Reverted | 0 | [10 empty] | Realigned to Kaysakat ES Terminated
NC 2016 | K10 | Region IV-A | Antipolo City | 109338 | Peñafrancia Es Annex | City Of Antipolo | 2 | 1 | 6 | 3STY6CL | BATCH 5 CL | 10650000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109357 | Rizza Es | City Of Antipolo | 2 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6650000 |  |  | Completed | 1 |  |  |  | 16DNO034 | 2016-02-26 | 2016-03-04 | 2016-03-17 | 2016-03-21 | 2016-03-22
NC 2016 | SHS | Region IV-A | Antipolo City | 301457 | San Jose Nhs | City Of Antipolo | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Antipolo City | 301427 | San Juan Nhs | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Antipolo City | 109340 | San Luis Es | City Of Antipolo | 2 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22650000 |  |  | Reverted | 0 | [10 empty] | CY 2015-2016 BEFF REVERSIONS (BATCH 1)
NC 2016 | K10 | Region IV-A | Antipolo City | 230001 | Tanza Es | City Of Antipolo | 2 | 1 | 9 | 3STY9CL | BATCH 3 CL | 15470000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Bacoor City | 107877 | Aniban Cs | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Bacoor City | 107867 | Bacoor Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1 |  |  |  | 16DF0161 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107867 | Bacoor Es | Bacoor | 2 |  | 6 | 3STY6CL | BATCH 9 CL | 10420000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Bacoor City | 307803 | Bacoor Nhs - Gawaran Annex | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0151 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Bacoor City | 107878 | Bayanan Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24702577.982 |  |  | Completed | 1 |  |  |  | 16DF0160 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Bacoor City | 107869 | Dulong Bayan Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0152 | [5 empty] | R.D MANDANAS CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 301188 | Eastern Bacoor Nhs | Bacoor | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 32744541.448 |  |  | Completed | 1 |  |  |  | 16DF0163 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107879 | Gawaran Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0153 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24562577.982 |  |  | Completed | 1 |  |  |  | 16DF0157 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107881 | Ligas I Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0154 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 107872 | Maliksi Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29612716.362 |  |  | Completed | 1 |  |  |  | 16DF0162 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107885 | Malipay Es | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0147 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 107873 | Mambog Es | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0148 | [5 empty] | D.V SALUD CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 107886 | Molino Elementary School | Bacoor | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 |  |  |  | 16DF0165 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107886 | Molino Elementary School | Bacoor | 2 |  | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0149 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 164009 | Poblacion Es (Bacoor Es (Annex)) | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16372270.724 |  |  | Completed | 1 |  |  |  | 16DF0150 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | K10 | Region IV-A | Bacoor City | 107888 | Queen'S Row Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0155 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107875 | Salinas Es | Bacoor | 2 | 1 | 16 | 4STY8CL | BATCH 9 CL | 32744541.448 |  |  | Completed | 1 |  |  |  | 16DF0164 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107889 | San Nicolas Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24563880.2731 |  |  | Completed | 1 |  |  |  | 16DF0159 | [5 empty] | R.A DEL ROSARIO CONSTRUCTION
NC 2016 | SHS | Region IV-A | Bacoor City |  | Shs In Progressive, Bacoor City | Bacoor City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24352577.982 |  |  | Completed | 1 |  |  |  | 16DF0156 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | SHS | Region IV-A | Bacoor City |  | Shs In San Nicholas Iii, Bacoor City | Bacoor City | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 |  |  |  | 16DF0166 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Bacoor City | 107890 | Sineguelasan Es To Talaba Es | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 31451110.2855 |  |  | Completed | 1 |  |  |  | 16DF0229
NC 2016 | K10 | Region IV-A | Bacoor City | 107891 | Zapote Es | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24562577.982 |  |  | Terminated | 0 |  |  |  | 16DF0158 | [5 empty] | BAQPRINCE CONSTRUCTION | CONTRACT TERMINATED (no access to site due to informal settlers)
NC 2016 | K10 | Region IV-A | Batangas | 307728 | Angeles Luistro Nhs | San Juan | 1 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2690828.12 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 307729 | Aplaya National High School | San Juan | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301088 | Bolbok Nhs | Tuy | 1 | 1 | 4 | 2STY4CL | BATCH 11 CL | 6469337.6381 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107228 | Caloocan Es | Balayan | 1 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107228 | Caloocan Es | Balayan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107229 | Canda Es | Balayan | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107229 | Canda Es | Balayan | 1 |  | 8 | 4STY8CL | BATCH 5 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107236 | Cipriana Ascue Mes | Balayan | 1 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107727 | Cubamba-Gahol Es | Taal | 1 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1914740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 | 1 | 48 | 4STY24CL | BATCH 9 CL | 78281765.708 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 301102 | Gov. Feliciano Leviste Mnhs | Lemery | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4836000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 307710 | Jose Lopez Manzano Community Hs | Tuy | 1 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1814740.174 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301111 | Lucsuhin Nhs | Calatagan | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107511 | Nasugbu East Central School | Nasugbu | 1 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | Pantalan Es | Nasugbu | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 107514 | Pantalan Es | Nasugbu | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | Santol Es Realigned To Balayan Shs | Balayan | 1 | 1 | 24 | 4STY24CL | BATCH 9 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | Santol Es Realigned To Balayan Shs | Balayan | 1 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 307718 | Sen. Gil Puyat Nhs | Nasugbu | 1 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.64 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Calaca | Calaca | 1 | 1 | 24 | 4STY24CL | BATCH 5 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Calaca | Calaca | 1 |  | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Calaca | Calaca | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Calatagan | Calatagan | 1 | 1 | 48 | 4STY24CL | BATCH 1 CL | 71442514.28 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Lian | Lian | 1 | 1 | 24 | 4STY24CL | BATCH 11 CL | 35596257.14 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Tuy | Tuy | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Tuy | Tuy | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107734 | Taal Cs | Taal | 1 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107734 | Taal Cs | Taal | 1 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107521 | Wawa Es | Nasugbu | 1 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14991327.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107668 | Alalum Es | San Pascual | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10467131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 301115 | Anselmo Sandoval Mnhs (Mabini Nhs) | Mabini | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107260 | Baguilawa Es | Bauan | 2 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 301080 | Bauan Technical High School | Bauan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2658700 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107431 | Bignay Ps | Lobo | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1062049.65 |  |  | Completed | 1 |  |  | P00073165LZ-CW1 | [6 empty] | TRISTAN TEJADA CONST.
NC 2016 | K10 | Region IV-A | Batangas | 107645 | Calumpang Es | San Luis | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301104 | Inicbulan Nhs | Bauan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107675 | Malakimpook Es | San Pascual | 2 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107273 | Manghinao Es | Bauan | 2 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107442 | Nagtoctoc Ps | Lobo | 2 | 1 | 1 | 1STY1CL | BATCH 9 CL | 1087049.65 |  |  | Completed | 1 |  |  | P00073169LZ-CW1
NC 2016 | K10 | Region IV-A | Batangas | 307730 | Rosario Technical High School | Rosario | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22227343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | San Antonio Es | San Pascual | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | Shs In Batangas City (Sports) | Batangas City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Lobo | Lobo | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26882469.42 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Rosario, Batangas | Rosario | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Sto. Tomas | Santo Tomas | 2 | 1 | 48 | 4STY24CL | BATCH 5 CL | 71192514.28 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Sto. Tomas | Santo Tomas | 2 |  | 40 | 4STY20CL | BATCH 5 CL | 62205780.54 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Sto. Tomas | Santo Tomas | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2418000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107817 | Sto. Tomas Ps | Tingloy | 2 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107820 | Tingloy Cs | Tingloy | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107264 | West Bauan Cs | Bauan | 2 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107215 | Alitagtag Central School | Alitagtag | 3 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301073 | Balete Nhs | Balete | 3 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301076 | Banyaga Nhs | Agoncillo | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107336 | Briccio Pantas Mes | Cuenca | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107371 | Bugaan Es | Laurel | 3 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107662 | Calangay Es | San Nicolas | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107339 | Cuenca Cs | Cuenca | 3 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107339 | Cuenca Cs | Cuenca | 3 |  | 6 | 2STY6CL | BATCH 7 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107486 | Lumanglipa Es | Mataas Na Kahoy | 3 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107254 | Malabanan Es | Balete | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6369337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107218 | Munlawin Es | Alitagtag | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107218 | Munlawin Es | Alitagtag | 3 |  | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107256 | Palsara Es | Balete | 3 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107212 | Pook Es | Agoncillo | 3 | 1 | 4 | 1STY2CL | BATCH 7 CL | 3629480.34 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107382 | San Gregorio Es - Annex | Laurel | 3 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10492131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 307713 | San Nicolas Nhs | San Nicolas | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.64 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Agoncillo | Agoncillo | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 |  | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Brgy. Bugaan East, Laurel, Batangas | Laurel | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas |  | Shs In Malvar | Malvar | 3 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107695 | Tambo Es | Santa Teresita | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8314965.05 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107736 | Venancio Trinidad Sr. Memorial School | Talisay | 3 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 301069 | Alupay Nhs | Rosario | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2483000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107584 | Aya Es | San Jose | 4 | 1 | 2 | 1STY1CL | BATCH 7 CL | 2099099.3 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107525 | Bawi Es | Padre Garcia | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301082 | Baybayin Nhs | Rosario | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301082 | Baybayin Nhs | Rosario | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301090 | Buhaynasapa Nhs | San Juan | 4 | 1 | 16 | 4STY16CL | BATCH 5 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301090 | Buhaynasapa Nhs | San Juan | 4 |  | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107547 | Cahigam Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 1938606.04 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107548 | Calantas Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 301098 | Dagatan Nhs | Taysan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 307714 | Dr. Bonifacio A. Masilungan National High School | San Jose | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas | 307714 | Dr. Bonifacio A. Masilungan National High School | San Jose | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301153 | Dr. Juan A. Pastor Mnhs (Talaibon Nhs) | Ibaan | 4 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Reverted | 0
NC 2016 | K10 | Region IV-A | Batangas | 107597 | Florencia A. Masilungan Mes | San Jose | 4 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107355 | Ibaan Cs | Ibaan | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301105 | Itlugan Nhs | Rosario | 4 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107552 | Julian D. Luna Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301108 | Laiya Nhs | San Juan | 4 | 1 | 32 | 4STY16CL | BATCH 5 CL | 53404938.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107593 | Lapolapo Es | San Jose | 4 | 1 | 3 | 1STY3CL | BATCH 7 CL | 2640828.12 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 307725 | Lipahan National High School | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107529 | Manggas-Tamak Es | Padre Garcia | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107561 | Masaya Es | Rosario | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 307707 | Nagsaulay Nhs | San Juan | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107564 | Namuco Es | Rosario | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107635 | Paaralang Elementarya Ng Talahiban 1.0 1.0 | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301129 | Padre Garcia Nhs | Padre Garcia | 4 | 1 | 24 | 4STY24CL | BATCH 9 CL | 39140882.854 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301129 | Padre Garcia Nhs | Padre Garcia | 4 |  | 16 | 4STY16CL | BATCH 9 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301130 | Palahanan Nhs | San Juan | 4 | 1 | 40 | 4STY20CL | BATCH 5 CL | 62205780.54 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301132 | Pansol Nhs | Padre Garcia | 4 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6394337.64 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107595 | Pinagtungulan Es | San Jose | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 107591 | Roman Ozaeta M/S | San Jose | 4 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301139 | Rosario Nhs | Rosario | 4 | 1 | 16 | 4STY16CL | BATCH 1 CL | 26802469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas |  | San Juan East Shs | San Juan | 4 | 1 | 6 | 2STY6CL | BATCH 11 CL | 10691021.92 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Batangas |  | Shs In Taysan | Taysan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2418000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Batangas | 301155 | Taysan Nhs | San Jose | 4 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1 | [10 empty] | With approved additional funds
NC 2016 | K10 | Region IV-A | Batangas | 301156 | Tilambo Nhs | Taysan | 4 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1814740.17 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas | 301160 | Tipas Nhs | San Juan | 4 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Batangas City | 109582 | Alangilan Es | Batangas City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26782469.42 |  |  | Completed | 1 |  |  |  |  | 2016-07-08 | 2016-07-15 | 2016-07-28 | 2016-08-16 | 2016-08-26 | W. Rivera Construction & Equipment
NC 2016 | K10 | Region IV-A | Batangas City | 301470 | Balete National High School | Batangas City (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22272343.62 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 2016-05-26 | Granby Trading & Const.
NC 2016 | K10 | Region IV-A | Batangas City |  | Gulod Es | Batangas City (Capital) | 2 | 1 | 32 | 4STY16CL | BATCH 11 CL | 53693014.0853 |  |  | Completed | 1 | [8 empty] | 2016-11-14 | Great Swiss Metal Builders Corp.
NC 2016 | SHS | Region IV-A | Batangas City | 301474 | Paharang Nhs | Batangas City (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14997518.84 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 2016-05-26 | Granby Trading & Const.
NC 2016 | SHS | Region IV-A | Batangas City | 301475 | Pedro S. Tolentino Mnhs | Batangas City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11065000 |  |  | Completed | 1 |  |  |  |  | 2016-02-24 | 2016-03-02 | 2016-03-16 | 2016-05-11 | 2016-05-26 | Granby Trading & Const.
NC 2016 | SHS | Region IV-A | Batangas City | 301479 | San Agustin Nhs | Batangas City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6782000 |  |  | Completed | 1 |  |  |  | 16DE-0135 | 2016-10-09 | 2016-10-13 | 2016-10-25 | 2016-11-13 | 2016-11-21 | W. Rivera Construction & Equipment
NC 2016 | K10 | Region IV-A | Biñan City |  | Stand Alone 3 (Bsc) | Binan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890 |  |  | Completed | 1 |  |  |  | 16DI0103 |  |  |  | 2016-09-05 | 2016-09-14 | Miclover General Construction & Iron Works
NC 2016 | K10 | Region IV-A | Biñan City |  | Stand Alone 3 (Bsc) | Binan City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DI0102 |  |  |  | 2016-09-05 | 2016-09-14 | 11 Diamond Eagle Construction
NC 2016 | K10 | Region IV-A | Biñan City |  | Stand Alone 4 (Colegio San Antonio) | Binan City | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31252890 |  |  | Completed | 1 |  |  |  | 16DI0106 |  |  |  | 2016-09-26 | 2016-10-04 | St. Gerrard Construction
NC 2016 | K10 | Region IV-A | Biñan City |  | Stand Alone 4 (Colegio San Antonio) | Binan City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DI0104 |  |  |  | 2016-09-26 | 2016-10-04 | Power K Construction Supply & Services
NC 2016 | SHS | Region IV-A | Calamba City | 301514 | Calamba Bayside National High School | City Of Calamba | 2 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29893354.4723 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Calamba City | 301516 | Camp Vicente Lim Nhs | City Of Calamba | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 29029387.4 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Calamba City | 301516 | Camp Vicente Lim Nhs | City Of Calamba | 2 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 108087 | Agustin Abadilla Es | Rosario | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0112 | [5 empty] | R.D MANDANAS CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108084 | Ambrocio Robles Mes (San Jose Es) | Noveleta | 1 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073182LZ | 16DF0185 | [5 empty] | FE S. REYES GEN CONTRACTOR
NC 2016 | SHS | Region IV-A | Cavite | 301189 | Emiliano T. Tirona Mnhs | Kawit | 1 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 16DF0120 | [5 empty] | C.T LEONCIO CONST. & TRADING
NC 2016 | K10 | Region IV-A | Cavite | 108020 | Gahak-Marulas Es | Kawit | 1 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10517131.51 |  |  | Completed | 1 |  |  |  | 16DF0092 | [5 empty] | ALMAKAR BUILDERS & METAL WORKS
NC 2016 | K10 | Region IV-A | Cavite | 108081 | Noveleta Es | Noveleta | 1 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16DF0116 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Cavite | 108091 | Rosario Es | Rosario | 1 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0107 | [5 empty] | R.A DEL ROSARIO CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108095 | Bagong Buhay Es | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 108095 | Bagong Buhay Es | Silang | 5 |  | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301180 | Bulihan Nhs | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301180 | Bulihan Nhs | Silang | 5 |  | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301192 | Gen. Mariano Alvarez Tech. Hs | Gen. Mariano Alvarez | 5 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62505780.54 |  |  | Completed | 1 |  |  |  | 16DF0216 | [5 empty] | HAUSLAND CONSTRUCTION
NC 2016 | SHS | Region IV-A | Cavite | 301193 | Gen. Vito Belarmino Nhs | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301197 | Kaong Nhs | Silang | 5 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301203 | Malabag Nhs | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 307813 | Munting Ilog Nhs (Silang West Annex) | Silang | 5 | 1 | 16 | 4STY8CL | BATCH 7 CL | 29795037.68 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 107940 | San Gabriel I Es | Gen. Mariano Alvarez | 5 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0105 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Cavite | 107940 | San Gabriel I Es | Gen. Mariano Alvarez | 5 |  | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0099 | [5 empty] | OMNICON BUILDERS
NC 2016 | SHS | Region IV-A | Cavite | 301213 | San Jose Community Hs | Gen. Mariano Alvarez | 5 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite |  | Shs In Carmona | Carmona | 5 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0174 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | SHS | Region IV-A | Cavite |  | Shs In Carmona | Carmona | 5 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0173 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Cavite | 108136 | Tartaria Es | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301180 | Ulat Es Realigned To Bulihan Nhs | Silang | 5 |  | 16 | 4STY16CL | BATCH 1 CL | 27702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301166 | Amadeo Nhs | Amadeo | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0206 | [5 empty] | C.T LEONCIO CONST& TRADING
NC 2016 | K10 | Region IV-A | Cavite | 108155 | Amaya Es | Tanza | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0108 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | SHS | Region IV-A | Cavite | 301167 | Amaya Sch. Of Home Industries | Tanza | 6 | 1 | 20 | 4STY20CL | BATCH 13 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0213 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108163 | Bienvenido R. Fojas Mes | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0101 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | General Trias City | 107946 | Buenavista Es | General Trias | 6 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0176 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108170 | Felipe Calderon Es (Tanza Es) | Tanza | 6 | 1 | 24 | 4STY12CL | BATCH 7 CL | 44304687.24 |  |  | Completed | 1 |  |  |  | 16DF0117 | [5 empty] | C.T LEONCIO CONST. & TRADING
NC 2016 | SHS | Region IV-A | Cavite | 307808 | Francisco Osorio Nhs (Trece Martires City Nhs (Osorio Annex)) | Trece Martires City (Capital) | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0098 | [5 empty] | J.S. CONTRACTOR
NC 2016 | K10 | Region IV-A | General Trias City | 301194 | Gov. Ferrer Mnhs (Main) | General Trias | 6 | 1 | 32 | 4STY16CL | BATCH 7 CL | 53404938.84 |  |  | Completed | 1 |  |  |  | 16DF0118 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | General Trias City | 307802 | Governor Ferrer Memorial National High School (Buenavista Annex) | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22352343.62 |  |  | Completed | 1 |  |  |  | 16DF0111 | [5 empty] | D.V SALUD CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108157 | Gregorio B. Fojas Ms | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0096 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | General Trias City | 107953 | Juliano C. Brosas Es | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0172 | [5 empty] | MONTADEL ENTERPRISES
NC 2016 | K10 | Region IV-A | General Trias City | 307822 | Luis Y. Ferrer Jr. West National High School | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0093 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | K10 | Region IV-A | General Trias City | 307823 | Luis Y. Ferrer, Jr. North National High School | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0207 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108165 | Paradahan Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0100 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | General Trias City | 107964 | Pasong Camachile Es | General Trias | 6 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10517131.51 |  |  | Completed | 1 |  |  |  | 16DF0182 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | General Trias City | 107954 | Pasong Kawayan Ii Es | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0094 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | General Trias City | 107965 | San Francisco Es | General Trias | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0095 | [5 empty] | N.B AVILA CONSTRUCTION
NC 2016 | K10 | Region IV-A | General Trias City | 107966 | Santiago Es | General Trias | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0106 | [5 empty] | D.V SALUD CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite | 108168 | Santol Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0102 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | SHS | Region IV-A | General Trias City |  | Shs In Gen. Trias | Gen. Trias | 6 | 1 | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Completed | 1 |  |  |  | 16DF0200 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Cavite |  | Shs In Tanza | Tanza | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0104 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Cavite |  | Shs In Tanza | Tanza | 6 |  | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0113 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Cavite |  | Shs In Trece Martires | Trece Martires City | 6 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0186 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | General Trias City | 164017 | Sunny Brooke Elementary School | General Trias | 6 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0114 | [5 empty] | D.V SALUD CONSTRUCTION
NC 2016 | SHS | Region IV-A | Cavite | 301219 | Tanza Nts | Tanza | 6 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0199 | [5 empty] | OMNICON BUILDERS
NC 2016 | K10 | Region IV-A | Cavite | 301222 | Trece Martires City Nhs | Trece Martires City (Capital) | 6 | 1 | 40 | 4STY20CL | BATCH 7 CL | 62205780.54 |  |  | Completed | 1 |  |  |  | 16DF0119 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Cavite | 307819 | Trece Martirez City Nhs (Cabezas Annex) | Trece Martires City (Capital) | 6 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0109 | [5 empty] | J.S. GEN CONTRACTOR
NC 2016 | K10 | Region IV-A | Cavite | 108171 | Tres Cruses Es | Tanza | 6 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14997518.84 |  |  | Completed | 1 |  |  |  | 16DF0103 | [5 empty] | HEXAMINDZ CORPORATION
NC 2016 | K10 | Region IV-A | Cavite | 301165 | Alfonso National High School | Alfonso | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301173 | Bendita Nhs | Magallanes | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301175 | Bucal Nhs | Maragondon | 8 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301178 | Cavite Nat'L. Science Hs | Maragondon | 8 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 108055 | Galicia Es | Mendez (Mendez-Nuñez) | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301191 | Gen. Emilio Aguinaldo Nhs (Bailen) | General Emilio Aguinaldo | 8 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301198 | Kaytitinga Nhs | Alfonso | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301204 | Maragondon Nhs | Maragondon | 8 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 108056 | Mendez Cs | Mendez (Mendez-Nuñez) | 8 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301206 | Naic Coastal Nhs | Naic | 8 | 1 | 5 | 1STY5CL | BATCH 13 CL | 4523636.82 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 301206 | Naic Coastal Nhs | Naic | 8 |  | 4 | 1STY2CL | BATCH 13 CL | 3877212.08 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301207 | Naic Nhs | Naic | 8 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301207 | Naic Nhs | Naic | 8 |  | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite | 108077 | Petronilo L. Torres Mes (Sabang Es) | Naic | 8 | 1 | 8 | 4STY8CL | BATCH 7 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301211 | Pulo Ni Sara Nhs | Maragondon | 8 | 1 | 6 | 3STY6CL | BATCH 7 CL | 10417131.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite |  | Shs In Mendez | Mendez | 8 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301216 | Tagaytay City National High School | Tagaytay City | 8 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Cavite | 301221 | Ternate Nhs | Ternate | 8 | 1 | 12 | 4STY12CL | BATCH 7 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Cavite City | 109635 | Dalahican Elem. School | Cavite City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22314343.62 |  |  | Completed | 1 |  |  |  | 16DF0211 | [5 empty] | BAQPRINCE CONSTRUCTION
NC 2016 | K10 | Region IV-A | Cavite City | 109637 | Manuel S. Rojas Es | Cavite City | 1 | 1 | 20 | 4STY20CL | BATCH 13 CL | 33861208.37 |  |  | Terminated | 1 |  |  |  | 16DF0222 | [5 empty] | BAQPRINCE CONSTRUCTION | CONTRACT TERMINATED (insufficient area for size of building and building permit issues)
NC 2016 | SHS | Region IV-A | Cavite City | 301485 | Sangley Point Nhs To Sangley Es | Cavite City | 1 | 1 | 12 | 4STY12CL | BATCH 13 CL | 24514577.982 |  |  | Completed | 1 |  |  |  | 16DF0228
NC 2016 | K10 | Region IV-A | Dasmarinas City | 301179 | Congressional Nhs | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0196 |  |  | 2016-11-04 |  | 2016-11-18 | Baqprince Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 301183 | Dasmarinas East Nhs (Annex C) | City Of Dasmariñas | 4 | 1 | 32 | 4STY32CL | BATCH 13 CL | 44532220.04 |  |  | Completed | 1 |  |  |  | 16DF0215 |  |  | 2016-12-20 |  | 2017-01-27 | KLDS Trading and Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107917 | Dasmariñas Ii Cs (Dasmariñas Bbes B) | City Of Dasmariñas | 4 | 1 | 16 | 4STY16CL | BATCH 13 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0212 |  |  | 2016-12-20 |  | 2017-01-27 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107917 | Dasmariñas Ii Cs (Dasmariñas Bbes B) | City Of Dasmariñas | 4 |  | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0208 |  |  | 2016-12-20 |  | 2017-01-27 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 | 1 | 28 | 4STY28CL | BATCH 11 CL | 40067946.14 |  |  | Completed | 1 |  |  |  | 16DF0202 |  |  | 2016-11-04 |  | 2016-11-18 | D.V. Salud Construction / KLDS Trading & Construction (JV) | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0201 |  |  | 2016-11-04 |  | 2016-11-18 | D.V. Salud Construction / KLDS Trading & Construction (JV) | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 301186 | Dasmarinas Nhs | City Of Dasmariñas | 4 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0195 |  |  | 2016-11-04 |  | 2016-11-18 | C.T. LEONCIO CONST. & TRADING
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107921 | Dr. J. P. Rizal Es (Dasmariñas Bbes A-1) | City Of Dasmariñas | 4 | 1 | 24 | 4STY24CL | BATCH 7 CL | 35596257.14 |  |  | Completed | 1 |  |  |  | 16DF0115 |  |  | 2016-03-16 |  | 2016-07-07 | C.T. Leoncio Construction & Trading , Omnicon builders
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107902 | Francisco E. Barzaga Ms | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0170 |  |  | 2016-06-22 |  | 2016-07-07 | KLDS Trading and Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107907 | Paliparan Es | City Of Dasmariñas | 4 | 1 | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1 |  |  |  | 16DF0175 |  |  | 2016-06-22 |  | 2016-07-07 | KLDS Trading and Construction
NC 2016 | SHS | Region IV-A | Dasmarinas City | 325902 | Paliparan Ii National High School | City Of Dasmariñas | 4 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  |  | 16DF0198 |  |  | 2016-11-04 |  | 2016-11-18 | R.A. Del Rosario | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107908 | Paliparan Iii Es | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0110 |  |  | 2016-03-15 |  | 2016-05-25 | Baqprince Construction | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107910 | Ramona S. Tirona Ms | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0183 |  |  | 2016-06-28 |  | 2016-07-13 | Baqprince Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107911 | Sabang Es | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 3 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0097 |  |  | 2016-03-15 |  | 2016-07-13 | Baqprince Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107924 | Salitran Elementary | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0210 |  |  | 2016-12-20 |  | 2017-01-27 | R.A. Del Rosario
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107922 | San Miguel Es (Dasmariñas Bbes A-3) | City Of Dasmariñas | 4 | 1 | 2 | 2STY2CL | BATCH 9 CL | 5014253.339 |  |  | Completed | 1 |  |  | P00073191LZ | 16DF0181 |  |  | 2016-06-28 |  | 2016-07-13 | Fe S. Reyes General Contractor
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107919 | San Nicolas Es (Dasmariñas Bbes D) | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0171 |  |  | 2016-06-22 |  | 2016-07-07 | KLDS Trading and Construction
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107919 | San Nicolas Es (Dasmariñas Bbes D) | City Of Dasmariñas | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0184 |  |  | 2016-06-28 |  | 2016-07-13 | Fe S. Reyes General Contractor
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107918 | Sta. Cristina Es (Dasmariñas Bbes C) | City Of Dasmariñas | 4 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1 |  |  |  | 16DF0205 |  |  | 2016-12-20 |  | 2017-01-27 | RAMON F. JAVALERA CONSTRUCTION
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107920 | Sta. Cruz Es (Dasmariñas Bbes E) | City Of Dasmariñas | 4 | 1 | 12 | 4STY12CL | BATCH 13 CL | 22152343.62 |  |  | Completed | 1 |  |  |  | 16DF0209 |  |  | 2016-12-20 |  | 2017-01-27 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Dasmarinas City | 107920 | Sta. Cruz Es (Dasmariñas Bbes E) | City Of Dasmariñas | 4 |  | 24 | 4STY24CL | BATCH 13 CL | 35596257.14 |  |  | Completed | 1 |  |  |  | 16DF0214 |  |  | 2016-12-20 |  | 2017-01-27 | KLDS Trading and Construction | Completed as per POW, Requested for additional fund
NC 2016 | K10 | Region IV-A | Imus City | 107968 | Anabu I Es | Imus | 3 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19060000 |  |  | Completed | 1 |  |  | P00073194LZ | 16DF0131 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Montadel Enterprises
NC 2016 | K10 | Region IV-A | Imus City | 107969 | Anabu Ii Elementary School | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16370000 |  |  | Completed | 1 |  |  | P00073195LZ | 16DF0128 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | N. B. Avila Construction
NC 2016 | K10 | Region IV-A | Imus City | 107971 | Bayan Luma Ii Elementary School | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16370000 |  |  | Completed | 1 |  |  | P00073196LZ | 16DF0129 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | J. S. Gen Contractor
NC 2016 | K10 | Region IV-A | Imus City | 107972 | Buhay Na Tubig Elementary School | Imus | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24555000 |  |  | Completed | 1 |  |  | P00073197LZ | 16DF0133 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Omnicon Builders
NC 2016 | K10 | Region IV-A | Imus City | 107982 | Bukandala Es | Imus | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34148000 |  |  | Completed | 1 |  |  | P00073198LZ | 16DF0139 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Omnicon Builders
NC 2016 | K10 | Region IV-A | Imus City | 107983 | Carsadang Bago Es | Imus | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24555000 |  |  | Completed | 1 |  |  | P00073199LZ | 16DF0134 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Baqprice Const.
NC 2016 | SHS | Region IV-A | Imus City |  | Gen. Flaviano Yengko Shs (Shs In Pasong Buaya) | Imus City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16078602.8 |  |  | Completed | 1 |  |  | P00073203LZ | 16DF0126 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Omnicon Builders
NC 2016 | SHS | Region IV-A | Imus City |  | Gen. Pantaleon Garcia Shs (Shs In Pedro Reyes) | Imus City | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34023208.37 |  |  | Completed | 1 |  |  | P00073204LZ | 16DF0137 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Baqprice Const.
NC 2016 | K10 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino Es | Imus | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00073200LZ | 16DF0125 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Omnicon Builders
NC 2016 | SHS | Region IV-A | Imus City |  | Gov. Juanito Reyes Remulla Shs (Shs In Toclong) | Imus City | 3 | 1 | 8 | 4STY8CL | BATCH 9 CL | 16127354.99 |  |  | Completed | 1 |  |  | P00073205LZ | 16DF0127 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Montadel Enterprises
NC 2016 | K10 | Region IV-A | Imus City | 301196 | Imus Nhs | Imus | 3 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29350000 |  |  | Completed | 1 |  |  | P00073201LZ | 16DF0136 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | R. V. Rieta Trading & Gen. Construction
NC 2016 | K10 | Region IV-A | Imus City | 107987 | Malagasang Ii Es | Imus | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34140000 |  |  | Completed | 1 |  |  | P00073202LZ | 16DF0138 | 2016-02-26 | 2016-03-04 | 2016-03-16 | 2106-05-16 | 2016-05-25 | Almakr Bldrs. & Metal Works/KLDS Trading & Construction (JV)
NC 2016 | SHS | Region IV-A | Laguna |  | Stand Alone Shs No. 20 Santa Cruz | Santa Cruz | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna |  | Stand Alone Shs No. 4 Sta. Cruz | Santa Cruz | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna |  | Stand Alone Shs No. 7 San Antonio Lb | Los Banos | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7139736.1681 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 | 1 | 12 | 4STY12CL | BATCH 9 CL | 24485957.982 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 |  | 6 | 3STY6CL | BATCH 9 CL | 11506366.536 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna | 307903 | Cristobal S. Conducto Mnhs | Rizal | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2674056.25 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307927 | Dayap Nhs (Calauan Annex) | Calauan | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48971915.964 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301258 | Plaridel Nhs | Nagcarlan | 3 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29524441.362 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301258 | Plaridel Nhs | Nagcarlan | 3 |  | 24 | 4STY12CL | BATCH 9 CL | 48838535.964 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna |  | Stand Alone Shs No. 5 Nagcarlan | Nagcarlan | 3 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301226 | Balian Nhs | Pangil | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301226 | Balian Nhs | Pangil | 4 |  | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307918 | Balian Nhs (Galalan Annex) | Pangil | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 307940 | Calangay Elementary School To Sta. Maria Nhs-Calangay Annex | Santa Maria | 4 | 1 | 6 | 2STY6CL | BATCH 9 CL | 8288590.65 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307926 | Cavinti Nhs (Calminue Ext.) | Cavinti | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna | 307926 | Cavinti Nhs (Calminue Ext.) | Cavinti | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108459 | Cueva Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301240 | Famy National High School | Famy | 4 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301270 | Gaudencio Octavio National High School | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301243 | Kabulusan National High School | Pakil | 4 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15495611.118 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna | 301243 | Kabulusan National High School | Pakil | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108407 | Labuin Es | Pila | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 164506 | Laurel Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 301279 | Lumban National High School | Lumban | 4 | 1 | 12 | 3STY12CL | BATCH 9 CL | 19680456.62 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307937 | Magdalena Nhs (Buenavista Annex) | Magdalena | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108400 | Maulawin Es | Pakil | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 164507 | New Little Baguio Es | Santa Maria | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2061872.3726 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 301253 | Pagsanjan National High School | Pagsanjan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 301253 | Pagsanjan National High School | Pagsanjan | 4 |  | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108401 | Pakil Es | Pakil | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108376 | Papatahan Es | Paete | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6373289.51 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna | 108412 | Pinagbayanan Es | Pila | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2430000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307935 | San Buenaventura Nhs Annex | Luisiana | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 307920 | San Juan Nhs (San Antonio Annex) | Kalayaan | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6528871.7478 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108403 | Saray Es | Pakil | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 301273 | Siniloan National High School | Siniloan | 4 | 1 | 15 | 3STY15CL | BATCH 11 CL | 23037143.68 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 301273 | Siniloan National High School | Siniloan | 4 |  | 6 | 3STY6CL | BATCH 11 CL | 11443844.661 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 164519 | Sitio Pulot/Bay Es | Kalayaan | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301268 | Sta. Catalina Nhs | Majayjay | 4 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301268 | Sta. Catalina Nhs | Majayjay | 4 |  | 4 | 2STY4CL | BATCH 11 CL | 6373289.51 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna | 301269 | Sta. Maria Nhs | Santa Maria | 4 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna |  | Stand Alone Shs No. 1 Kalayaan | Kalayaan | 4 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna |  | Stand Alone Shs No. 1 Kalayaan | Kalayaan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2490750 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Laguna |  | Stand Alone Shs No. 3 Pagsanjan | Pagsanjan | 4 | 1 | 8 | 2STY8CL | BATCH 9 CL | 11141456.81 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IV-A | Laguna |  | Stand Alone Shs No. 3 Pagsanjan | Pagsanjan | 4 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2430000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Laguna | 108280 | Sumucab Es | Cavinti | 4 | 1 | 2 | 1STY2CL | BATCH 9 CL | 2050929.3424 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lipa City | 301489 | Bulacnin Nhs | Lipa City | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6419338 |  |  | Completed | 1 |  |  |  | 16DD0201 |  |  |  | 2016-07-05 | 2016-07-13 | EDISON DEV'T CONST.
NC 2016 | SHS | Region IV-A | Lipa City | 301491 | Inosloban-Marawoy Nhs | Lipa City | 4 | 1 | 40 | 4STY20CL | BATCH 13 CL | 68396358.594 |  |  | Completed | 1 |  |  |  | 16DD0233 |  |  |  | 2017-04-02 | 2017-04-10 | PRECIOUS CONST.
NC 2016 | K10 | Region IV-A | Lipa City | 301495 | Lumbang Nhs | Lipa City | 4 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6319338 |  |  | Completed | 1 |  |  |  | 16DD0197 |  |  |  | 2016-06-22 | 2016-06-30 | A.SANDOVAL CONST. & SUPPLY
NC 2016 | K10 | Region IV-A | Lucena City | 308502 | Cotta National High School | Lucena City (Capital) | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 23944914.795 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 308503 | Gulang-Gulang Nhs | Lucena City (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34783029.297 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 109740 | Isabang Es | Lucena City (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 9 CL | 20398270.669 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Lucena City | 308501 | Lucena Dalahican Nhs | Lucena City (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 9 CL | 29845066.362 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 109707 | Lucena East I Es | Lucena City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11628224.661 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 109714 | Lucena East Vii Es | Lucena City (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11628344.661 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 109744 | Lucena West Iii Es | Lucena City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7010521.4019 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Lucena City | 109736 | Talao-Talao Es | Lucena City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 9 CL | 7059196.4019 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301332 | Infanta Nhs | Infanta | 1 | 1 | 15 | 3STY15CL | BATCH 11 CL | 21383013.45 |  |  | Completed | 1 |  |  |  | 16DK0062 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-10-13 | 2016-10-24 | LUCBAN BUILDERS
NC 2016 | SHS | Region IV-A | Quezon | 301332 | Infanta Nhs | Infanta | 1 |  | 9 | 3STY9CL | BATCH 11 CL | 14941327.92 |  |  | Completed | 1 |  |  |  | 16DK0063 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-10-13 | 2016-10-24 | SARCA STATE & DEVT CORP
NC 2016 | SHS | Region IV-A | Quezon | 301297 | Bukal Sur Nhs | Candelaria | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301348 | Lusacan Nhs | Tiaong | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 16618460.712 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Quezon | 301349 | Lutucan National High Scool | Sariaya | 2 | 1 | 20 | 4STY20CL | BATCH 13 CL | 34198179.297 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301380 | Recto Mnhs | Tiaong | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29357716.362 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301403 | Sta. Catalina Nhs | Candelaria | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. Hs | Mulanay | 3 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8214965.05 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Quezon | 301304 | Calauag Nhs | Calauag | 4 | 1 | 12 | 4STY12CL | BATCH 3 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00070472LZ | 16-DL-0058 | 2016-04-29 |  | 2016-05-23 | 2016-05-27 | 2016-06-07 | JUNCAN ENTERPRISES
NC 2016 | SHS | Region IV-A | Quezon | 301304 | Calauag Nhs | Calauag | 4 |  | 6 | 3STY6CL | BATCH 3 CL | 10417131.51 |  |  | Completed | 1 |  |  | P00070473LZ | 16-DL-0050 | 2016-03-17 |  | 2016-04-12 | 2016-04-21 | 2016-05-23 | JUNCAN ENTERPRISES
NC 2016 | SHS | Region IV-A | Quezon | 301323 | Guinayangan Nhs | Guinayangan | 4 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18222268.79 |  |  | Completed | 1 |  |  | P00074788LZ-CW1 | 16-DL-0093 | 2016-08-25 |  |  |  | 2016-10-07 | JUNCAN ENTERPRISES
NC 2016 | SHS | Region IV-A | Quezon | 301328 | Guites Nhs | Lopez | 4 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8514965.05 |  |  | Completed | 1 |  |  | P00075549LZ-CW1 | 17-DL-0102 | 2017-01-26 | 2017-02-02 | 2017-02-15 | 2017-02-17 | 2017-02-22 | C.T. Leoncio Construction & Trading/Katha Builders & Supplies (J.V.)
NC 2016 | SHS | Region IV-A | Quezon | 301325 | Gumaca National High School | Gumaca | 4 | 1 | 27 | 3STY9CL | BATCH 13 CL | 49855382.136 |  |  | Completed | 1 |  |  | P00075550LZ-CW1 | 17-DL-0100 | 2017-01-26 | 2017-02-02 | 2017-02-15 | 2017-02-17 | 2017-02-22 | Katha Builders & Supplies
NC 2016 | SHS | Region IV-A | Quezon | 301325 | Gumaca National High School | Gumaca | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00074789LZ-CW1 | 16-DL-0094 | 2016-08-25 |  |  |  | 2016-10-07 | ZELAN CONSTRUCTION AND SUPPLY
NC 2016 | SHS | Region IV-A | Quezon | 301387 | Ilayang Ilog-A Nhs (Formerly San Francisco B Nhs Ilayang Ilog A Ext.) | Lopez | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1 |  |  | P00074792LZ-CW1 | 16-DL-0095 | 2016-08-25 |  |  |  | 2016-10-07 | RA MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2016 | SHS | Region IV-A | Quezon | 301338 | Kinatakutan Nhs | Tagkawayan | 4 | 1 | 5 | 1STY5CL | BATCH 9 CL | 4648392.2452 |  |  | Completed | 1 |  |  | P00075551LZ-CW1 | 17-DL-0103 | 2017-01-26 | 2017-02-02 | 2017-02-15 | 2017-02-17 | 2017-02-22 | Juncan Enterprises
NC 2016 | SHS | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | Lopez | 4 | 1 | 20 | 2STY10CL | BATCH 13 CL | 25542620.18 |  |  | Completed | 1 |  |  | P00075552LZ-CW1 | 17-DL-0101 | 2017-01-26 | 2017-02-02 | 2017-02-15 | 2017-02-17 | 2017-02-22 | Juncan Enterprises
NC 2016 | SHS | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | Lopez | 4 |  | 4 | 2STY4CL | BATCH 13 CL | 6319337.64 |  |  | Completed | 1 |  |  | P00074793LZ-CW1 | 16-DL-0096 | 2016-08-25 |  |  |  | 2016-10-07 | RA MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2016 | SHS | Region IV-A | Quezon | 301352 | Pisipis Nhs (Formerly Magallanes Nhs Pisipis Extension) | Lopez | 4 | 1 | 2 | 1STY2CL | BATCH 11 CL | 2132466.644 |  |  | Completed | 1 |  |  | P00073251LZ | 16-DL-0055 | 2016-04-12 |  | 2016-05-03 | 2016-05-12 | 2016-05-17 | ZELAN CONSTRUCTION AND SUPPLY
NC 2016 | SHS | Region IV-A | Rizal | 301417 | Angono Nhs | Angono | 1 | 1 | 12 | 4STY12CL | BATCH 11 CL | 23912531.11 |  |  | Completed | 1 |  |  | P00074795LZ | 16DN0087 | 2016-07-14 | 2016-07-20 | 2016-08-02 | 2016-08-16 | 2016-08-29 | SUPREME ABF CONST. & CONST. SUPPLY COMPANY INC.
NC 2016 | SHS | Region IV-A | Rizal | 301417 | Angono Nhs | Angono | 1 |  | 16 | 4STY8CL | BATCH 11 CL | 29795037.68 |  |  | Reverted | 0
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone 8 | Taytay | 1 | 1 | 40 | 4STY20CL | BATCH 11 CL | 62505780.54 |  |  | Completed | 1 |  |  | P0074809LZ | 16DN0108 | 2016-12-09 | 2016-12-16 | 2016-12-29 | 2016-12-29 | 2017-12-12 | D.R. ROBLES CONSTRUCTION
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone Shs 3 | Cainta | 1 | 1 | 60 | 4STY20CL | BATCH 11 CL | 93758671 |  |  | Completed | 1 |  |  | P0074803LZ | 16DN0102 | 2016-11-25 | 2016-12-01 | 2016-12-15 | 2016-12-27 | 2017-03-27 | ATLANTIC ERECTORS INC.
NC 2016 | SHS | Region IV-A | Rizal | 301469 | Vicente Madrigal Nhs | Binangonan | 1 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32650534.78 |  |  | Completed | 1 |  |  | P0074802LZ | 16DN0083 | 2016-07-08 | 2016-07-15 | 2016-07-28 | 2016-08-10 | 2016-08-24 | GENETIAN BUILDERS
NC 2016 | SHS | Region IV-A | Rizal | 301428 | Bagumbong Nhs | Jala-Jala | 2 | 1 | 12 | 4STY12CL | BATCH 13 CL | 23912531.11 |  |  | Completed | 1 |  |  | P00075559LZ-CW1 | 160050 | 2016-12-03 | 2016-12-09 | 2016-12-23 | 2016-12-28 | 2017-01-11 | Atlantic Erectors Inc.
NC 2016 | SHS | Region IV-A | Rizal | 301434 | Catalino D. Salazar Nhs | Cardona | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 12573229.1271 |  |  | Completed | 1 |  |  | P00075557LZ-CW1 | 160059 | 2017-01-20 | 2017-01-27 | 2017-02-09 | 2017-03-16 | 2017-03-29 | Flag Const. Corp
NC 2016 | SHS | Region IV-A | Rizal | 301434 | Catalino D. Salazar Nhs | Cardona | 2 |  | 1 | 1STY1CL | BATCH 13 CL | 1103134.12 |  |  | Completed | 1 |  |  | P00075558LZ-CW1 | 160059 | 2017-01-20 | 2017-01-27 | 2017-02-09 | 2017-03-16 | 2017-03-29 | Flag Const. Corp
NC 2016 | SHS | Region IV-A | Rizal | 308120 | Jalajala Nhs | Jala-Jala | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074794LZ-CW1 | 16D00039 | 2016-10-03 | 2016-10-07 | 2016-10-20 | 2016-10-27 | 2016-11-07 | ALPHA & OMEGA GENERAL CONTRACTOR & DEV'T. CORP.
NC 2016 | SHS | Region IV-A | Rizal | 301447 | Malaya Nhs | Pililla | 2 | 1 | 15 | 3STY15CL | BATCH 11 CL | 22444664.12 |  |  | Completed | 1 |  |  | P00074797LZ-CW1 | 16D00034 | 2016-09-09 | 2016-09-16 | 2016-09-30 | 2016-10-06 | 2016-10-14 | HEXAMINDZ CORP.
NC 2016 | SHS | Region IV-A | Rizal | 301452 | Morong National High School | Morong | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 32850534.78 |  |  | Completed | 1 |  |  | P00074798LZ-CW1 | 16D00035 | 2016-09-09 | 2016-09-16 | 2016-09-30 | 2016-10-06 | 2016-10-14 | ALPHA & OMEGA GENERAL CONTRACTOR & DEV'T. CORP.
NC 2016 | SHS | Region IV-A | Rizal | 301452 | Morong National High School | Morong | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1 |  |  | P00074798LZ-CW1 | 16D00035 | 2016-09-02 | 2016-09-09 | 2016-09-22 | 2016-09-28 | 2016-10-05 | GENETIAN BUILDERS
NC 2016 | SHS | Region IV-A | Rizal | 308123 | Pantay Nhs (Teresa Nhs - Pantay Annex) | Teresa | 2 | 1 | 16 | 4STY16CL | BATCH 13 CL | 28826666.97 |  |  | Completed | 1 |  |  | P00075561LZ-CW1 | 160051 | 2016-12-03 | 2016-12-09 | 2016-12-23 | 2016-12-29 | 2017-01-19 | Alpha & Omega General Contractor & Devl't Corp.
NC 2016 | SHS | Region IV-A | Rizal | 301453 | Pililla Nhs | Pililla | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074804LZ-CW1 | 160040 | 2016-10-03 | 2016-10-07 | 2016-10-20 | 2016-11-21 | 2016-12-02 | Honeyville Const.
NC 2016 | SHS | Region IV-A | Rizal | 301454 | Quisao Nhs | Pililla | 2 | 1 | 8 | 4STY8CL | BATCH 11 CL | 16077320.35 |  |  | Completed | 1 |  |  | P00074810LZ-CW1 | 160025 | 2016-08-22 | 2016-09-01 | 2016-09-13 | 2016-09-20 | 2016-09-23 | Alpha & Omega General Contractor & Devl't Corp.
NC 2016 | SHS | Region IV-A | Rizal | 301456 | Sampaloc Nhs | Tanay | 2 | 1 | 12 | 3STY12CL | BATCH 11 CL | 19668050.29 |  |  | Completed | 1 |  |  | P00074800LZ-CW1 | 16D00033 | 2016-09-09 | 2016-09-16 | 2016-09-30 | 2016-10-06 | 2016-10-14 | HEXAMINDZ CORP.
NC 2016 | K10 | Region IV-A | Rizal | 301462 | Silangan National High School | San Mateo | 2 | 1 | 8 | 4STY8CL | BATCH 13 CL | 16224795.54 |  |  | Completed | 1 |  |  | P00075560LZ-CW1 | 160052 | 2016-12-03 | 2016-12-09 | 2016-12-23 | 2016-12-29 | 2017-01-19 | IM Const. Corp
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone 10 ( Rizal Arts Academy) | Tanay 2 | 2 | 1 | 6 | 2STY6CL | BATCH 11 CL | 8214965.05 |  |  | Completed | 1 |  |  | P00074808LZ-CW1 | 160044 | 2016-11-19 | 2016-11-25 | 2016-12-09 | 2016-12-28 | 2017-01-19 | MPJR Builders Co.
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone 7 | Baras | 2 | 1 | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1 |  |  | P00074801LZ-CW1 | 16D00041 | 2016-10-03 | 2016-10-07 | 2016-10-20 | 2016-11-21 | 2016-11-29 | HONEYVILLE CORP.
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone 9 | Rodriguez Ii Eastwood | 2 | 1 | 16 | 4STY16CL | BATCH 11 CL | 26702469.42 |  |  | Completed | 1 |  |  | P00074805LZ-CW1 | 160031 | 2016-09-02 | 2016-09-09 | 2016-09-22 | 2016-09-28 | 2016-10-05 | Chrisman Const. & Supplies
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone 9 | Rodriguez Ii Eastwood | 2 |  | 12 | 4STY12CL | BATCH 11 CL | 22152343.62 |  |  | Completed | 1 |  |  | P00074806LZ-CW1 | 160030 | 2016-09-02 | 2016-09-09 | 2016-09-22 | 2016-09-28 | 2016-10-05 | Precious Const.
NC 2016 | SHS | Region IV-A | Rizal |  | Stand Alone Shs 2 | San Mateo | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 67158242.98 |  |  | Completed | 1 |  |  | P00074807LZ-CW1 | 160060 | 2017-09-18 | 2017-03-24 | 2017-04-07 | 2017-04-21 | 2017-05-04 | Atlantic Erectors Inc.
NC 2016 | SHS | Region IV-A | Rizal |  | Stand Alone Shs 4 | Tanay | 2 | 1 | 32 | 4STY16CL | BATCH 11 CL | 53404938.84 |  |  | Completed | 1 |  |  | P00074811LZ-CW1 | 160046 | 2016-11-09 | 2016-11-25 | 2016-12-09 | 2016-12-28 | 2017-01-19 | Sarca Estates Development Corp.
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone Shs 5 | Rodriguez I Litex | 2 | 1 | 40 | 4STY20CL | BATCH 11 CL | 67158242.98 |  |  | Completed | 1 |  |  | P00074812LZ-CW1 | 160029 | 2016-09-02 | 2016-09-09 | 2016-09-22 | 2016-09-28 | 2016-10-05 | Hexamindz Corp.
NC 2016 | K10 | Region IV-A | Rizal |  | Stand Alone Shs 5 | Rodriguez I Litex | 2 |  | 8 | 4STY8CL | BATCH 11 CL | 16077320.35 |  |  | Completed | 1 |  |  | P00074813LZ-CW1 | 160045 | 2016-11-19 | 2016-11-25 | 2016-12-09 | 2016-12-16 | 2016-12-23 | Hexamindz Corp.
NC 2016 | K10 | Region IV-A | San Pablo City | 109749 | Ambray Elementary School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073252LZ_CW1 | 16DP0034 | 2016-06-10 | 2016-06-16 | 2016-07-01 |  | 2016-08-17 | DSO ENTERPRISES
NC 2016 | K10 | Region IV-A | San Pablo City | 301506 | Del Remedio National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073253LZ_CW1 | 16DP0021 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | STO CRISTO CONST & TRADING
NC 2016 | K10 | Region IV-A | San Pablo City | 308606 | Prudencia D. Fule Memorial National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073254LZ_CW1 | 16DP0019 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | POWER K CONST. SUPPLY & SERVICES
NC 2016 | SHS | Region IV-A | San Pablo City | 308602 | San Jose National High School | San Pablo City | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48705155.964 |  |  | Completed | 1 |  |  | P00073255LZ_CW1 | 16DP0029 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 2016-07-06 | STO CRISTO CONST & TRADING
NC 2016 | K10 | Region IV-A | San Pablo City | 301504 | San Pablo City National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073256LZ_CW1 | 16DP0022 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | POWER K CONST. SUPPLY & SERVICES
NC 2016 | SHS | Region IV-A | San Pablo City | 308605 | San Pablo City Science High School | San Pablo City | 3 | 1 | 24 | 4STY12CL | BATCH 9 CL | 48705155.964 |  |  | Completed | 1 |  |  | P00073257LZ_CW1 | 16DP0027 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 2016-07-06 | STO CRISTO CONST & TRADING
NC 2016 | SHS | Region IV-A | San Pablo City |  | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 68396358.594 |  |  | Completed | 1 |  |  | P00073258LZ_CW1 | 16DP0023 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | JAIME B. CHING ENTERPRISES
NC 2016 | SHS | Region IV-A | San Pablo City |  | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 |  | 48 | 4STY16CL | BATCH 9 CL | 88073149.086 |  |  | Completed | 1 |  |  | P00073259LZ_CW1 | 16DP0024 | 2016-05-13 | 2016-05-18 | 2016-06-02 | 2016-07-26 | 2016-08-17 | NEW BIG FOUR J CONST. INC.
NC 2016 | TECHVOC | Region IV-A | San Pablo City |  | San Pablo City Senior High School (Stand Alone) | San Pablo City | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5317400 |  |  | Completed | 1 |  |  | P00074444LZ_CW1 | 16DP0017 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | R'CEL GEN. CONT. 7 GEN. MDSE.
NC 2016 | SHS | Region IV-A | San Pablo City | 308601 | San Vicente National High School | San Pablo City | 3 | 1 | 6 | 3STY6CL | BATCH 9 CL | 11500313.8843 |  |  | Completed | 1 |  |  | P00073260LZ_CW1 | 16DP0020 | 2016-05-02 | 2016-05-12 | 2016-05-24 |  | 2016-06-30 | POWER K CONST. SUPPLY & SERVICES
NC 2016 | SHS | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | San Pablo City | 3 | 1 | 2 | 1STY2CL | BATCH 9 CL | 1996214.1914 |  |  | Reverted | 0
NC 2016 | TECHVOC | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | San Pablo City | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Reverted | 0
NC 2016 | K10 | Region IV-A | Sta. Rosa City | 301224 | Aplaya Nhs | City Of Santa Rosa | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 15421327.92 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Sta. Rosa City | 108471 | Caingin Elementary School | City Of Santa Rosa | 1 | 1 | 6 | 3STY6CL | BATCH 9 CL | 10417131.51 |  |  | Completed | 1 |  |  |  | 16DI0089 | 2016-06-29 | 2016-07-04 | 2016-07-19 | 2016-07-26 | 2016-08-01 | ST. GERRARD CONSTRUCTION
NC 2016 | K10 | Region IV-A | Sta. Rosa City | 301239 | Don Jose Nhs | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 11 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Sta. Rosa City | 108479 | Pulong Sta. Cruz Elementary School | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 13 CL | 15047518.84 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa1 | Santa Rosa City | 1 | 1 | 16 | 4STY8CL | BATCH 7 CL | 30095037.68 |  |  | Completed | 1 |  |  |  | 16DI0075 | 2016-04-21 | 2016-04-28 | 2016-05-06 | 2016-05-14 | 2016-05-22 | ST. GERRARD CONSTRUCTION
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa1 | Santa Rosa City | 1 |  | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1 |  |  |  | 16DI0074 | 2016-04-21 | 2016-04-28 | 2016-05-06 | 2016-05-14 | 2016-05-16 | ST. GERRARD CONSTRUCTION
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa2 | Santa Rosa City | 1 | 1 | 24 | 4STY12CL | BATCH 11 CL | 44604688 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 16 | 4STY16CL | BATCH 11 CL | 26852469 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 20 | 4STY20CL | BATCH 11 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Sta. Rosa City |  | Shs In Santa Rosa2 | Santa Rosa City | 1 |  | 8 | 4STY8CL | BATCH 11 CL | 14897518.84 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Sta. Rosa City | 108485 | Tagapo Elementary School | City Of Santa Rosa | 1 | 1 | 8 | 4STY8CL | BATCH 7 CL | 15047518.84 |  |  | Completed | 1 |  |  |  | 16DI0089 | 2016-02-28 | 2016-03-05 | 2016-03-18 | 2016-03-23 | 2016-05-22 | ST. GERRARD CONSTRUCTION
NC 2016 | K10 | Region IV-A | Tanauan City | 321602 | Balele National High School | City Of Tanauan | 3 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 321604 | Dr. Alcantara National High School | City Of Tanauan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 107760 | Janopol Es | City Of Tanauan | 3 | 1 | 6 | 2STY6CL | BATCH 7 CL | 8296000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 321603 | Janopol Oriental National High School | City Of Tanauan | 3 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6382000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 301119 | Malaking Pulo National High School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 107776 | Santol Elementary School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Tanauan City | 321601 | Tanauan City Nhs | City Of Tanauan | 3 | 1 | 15 | 3STY15CL | BATCH 13 CL | 23506314.795 |  |  | Completed | 1
NC 2016 | SHS | Region IV-A | Tanauan City | 321601 | Tanauan City Nhs | City Of Tanauan | 3 |  | 12 | 3STY12CL | BATCH 13 CL | 18222268.79 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tanauan City | 321605 | Ulango Integrated School | City Of Tanauan | 3 | 1 | 2 | 1STY2CL | BATCH 7 CL | 1959000 |  |  | Completed | 1
NC 2016 | K10 | Region IV-A | Tayabas City | 301347 | Luis Palad Nhs | City Of Tayabas | 1 | 1 | 16 | 4STY16CL | BATCH 7 CL | 26852469 |  |  | Completed | 1 |  |  |  | 16DK0019 | 2016-02-24 | 2016-03-04 | 2016-03-17 | 2016-03-23 | 2016-04-04 | DQT Builders
NC 2016 | K10 | Region IV-A | Tayabas City | 301347 | Luis Palad Nhs | City Of Tayabas | 1 |  | 6 | 3STY6CL | BATCH 7 CL | 10763758.08 |  |  | Completed | 1 |  |  |  | 16DK0020 | 2016-02-24 | 2016-03-04 | 2016-03-17 | 2016-03-23 | 2016-04-04 | Lucban Builders
NC 2016 | TECHVOC | Region IV-A | Tayabas City | 109258 | Stand Aloneshs To Potol Es | Tayabas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2606823.98 |  |  | Completed | 1 |  |  |  | 16DK0064 | 2016-08-11 | 2016-08-17 | 2016-09-02 | 2016-09-12 | 2016-09-19 | WJ Construction
NC 2016 | K10 | Region IV-A | Tayabas City | 109262 | Tayabas West Cs Iv | City Of Tayabas | 1 | 1 | 4 | 2STY4CL | BATCH 9 CL | 6936271.4019 |  |  | Completed | 1 |  |  |  | 16DK0043 | 2016-04-11 | 2016-04-18 | 2016-04-29 | 2016-05-06 | 2016-05-12 | Tan Tay Lim Builders
NC 2017 | K10 | Region IV-A | Cavite | 108060 | Bancaan ES | NAIC | 8 | 1 | 5 | 1STY5CL | BATCH 2 | 6253584.75 |  |  | Completed | 1 |  |  | 17DG0065 | [6 empty] | One Euluz Construction
NC 2017 | TVL | Region IV-A | Laguna | 307926 | Cavinti NHS (Calminue Ext.) | CAVINTI | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 2705397.5 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301240 | Famy National High School | FAMY | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 2737411.21 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 3347222.58 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 342358 | Stand Alone SHS No. 16 Pila | PILA | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 2661038.39 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 307906 | Gov. Felicisimo T. San Luis Memorial National High School | SANTA CRUZ (Capital) | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 2743730.47 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301274 | GOV. FELICISIMO T. SAN LUIS NATIONAL AGRO-INDUSTRIAL HIGH SCHOOL | SINILOAN | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 2693681.87 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301273 | Siniloan National High School | SINILOAN | 4 | 1 | 1 | 1 Unique Workshop Building | BATCH 2 | 3384894.02 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Quezon | 301335 | Bonifacio National High School | BURDEOS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0080 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | Juntereal Industrial & Devt Corporation
NC 2017 | K10 | Region IV-A | Quezon | 108621 | MANGILAG NORTE ES | CANDELARIA | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 3898590.53 |  |  | Completed | 1 |  |  |  | 17DJ0088 | [5 empty] | PY LACORTE BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 108629 | San Isidro ES | CANDELARIA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2800519.1 |  |  | Completed | 1 |  |  |  | 17DJ0033 | [5 empty] | SOUTHER DAWN DEVELOPMENT COMPANY
NC 2017 | K10 | Region IV-A | Quezon | 108708 | Gen. Nakar Central School | GENERAL NAKAR | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4497261.17 |  |  | Completed | 1 |  |  |  | 17DK0081 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | E.A.Ayala Const. & Supply
NC 2017 | SHS | Region IV-A | Quezon | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3277000 |  |  | Completed | 1 |  |  |  | 17DK0082 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | Juntereal Industrial & Devt Corporation
NC 2017 | SHS | Region IV-A | Quezon | 301362 | Paaralang Sek. Ng Hen. Nakar - Maligaya Extension | GENERAL NAKAR | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3677000 |  |  | Completed | 1 |  |  |  | 17DK0083 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | E.A.Ayala Const. & Supply
NC 2017 | K10 | Region IV-A | Quezon | 108783 | Binulasan Integrated Sch. (Elem) | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2956339.6 |  |  | Completed | 1 |  |  |  | 17DK0084 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | E.A.Ayala Const. & Supply
NC 2017 | SHS | Region IV-A | Quezon | 301294 | BinulAsan IS | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2956339.6 |  |  | Completed | 1 |  |  |  | 17DK0085 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | Ultragreen Venture Structure Corp
NC 2017 | K10 | Region IV-A | Quezon | 108795 | Tongohin ES | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2956339.6 |  |  | Completed | 1 |  |  |  | 17DK0086 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | Ultragreen Venture Structure Corp
NC 2017 | K10 | Region IV-A | Quezon | 108864 | Prlng. Elem. Ng Lucban 2 (PEL II-A & II-B) | LUCBAN | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4347261.17 |  |  | Completed | 1 |  |  |  | 17DK0087 | 2017-07-25 | 2017-08-04 | 2017-08-17 | 2017-09-19 | 2017-10-09 | Lucban Builders
NC 2017 | SHS | Region IV-A | Quezon | 308015 | Cagsiay III - Cagsiay I NHS Ext. | MAUBAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3677000 |  |  | Completed | 1 |  |  |  | 17DK0141 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | WJ Construction
NC 2017 | K10 | Region IV-A | Quezon | 108910 | Doña Aurora ES | MAUBAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2906339.6 |  |  | Completed | 1 |  |  |  | 17DK0088 | 2017-07-28 | 2017-08-10 | 2017-08-22 | 2017-09-19 | 2017-10-09 | WJ Construction
NC 2017 | SHS | Region IV-A | Quezon | 308029 | Libo NHS - Bonbon Annex | PANUKULAN | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3877000 |  |  | Completed | 1 |  |  |  | 17DK0089 | 2017-07-28 | 2017-08-10 | 2017-08-22 | 2017-09-19 | 2017-10-09 | MJ Apin Builders
NC 2017 | SHS | Region IV-A | Quezon | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4669000 |  |  | Completed | 1 |  |  |  | 17DK0090 | 2017-07-28 | 2017-08-10 | 2017-08-22 | 2017-09-19 | 2017-10-09 | E.A.Ayala Const. & Supply
NC 2017 | K10 | Region IV-A | Quezon | 109101 | Arawan ES | SAN ANTONIO | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 4632753.25 |  |  | Completed | 1 |  |  |  | 17DJ0031 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109104 | Callejon ES | SAN ANTONIO | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 4619815.3 |  |  | Completed | 1 |  |  |  | 17DJ0031 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109160 | Bucal ES | SARIAYA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2767619.53 |  |  | Completed | 1 |  |  |  | 17DJ0035 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109177 | Concepcion Ibaba ES | SARIAYA | 2 | 1 | 4 | 1STY4CL | BATCH 2 | 4689596.79 |  |  | Completed | 1 |  |  |  | 17DJ0035 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109166 | Morong ES | SARIAYA | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2890038.5 |  |  | Completed | 1 |  |  |  | 17DJ0034 | [5 empty] | SOUTHER DAWN DEVELOPMENT COMPANY
NC 2017 | K10 | Region IV-A | Quezon | 109170 | Talaan ES | SARIAYA | 2 | 1 | 3 | 1STY3CL | BATCH 2 | 4039644.35 |  |  | Completed | 1 |  |  |  | 17DJ0034 | [5 empty] | SOUTHER DAWN DEVELOPMENT COMPANY
NC 2017 | K10 | Region IV-A | Quezon | 109284 | San Jose ES | TIAONG | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2808235.2 |  |  | Completed | 1 |  |  |  | 17DJ0032 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 109284 | San Jose ES | TIAONG | 2 |  | 3 | 1STY3CL | BATCH 2 | 3989650 |  |  | Completed | 1 |  |  |  | 17DJ0032 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 109285 | San Juan ES | TIAONG | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2814242 |  |  | Completed | 1 |  |  |  | 17DJ0032 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Tayabas City | 109231 | Alsam ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0091 | 2017-07-28 | 2017-08-10 | 2017-08-22 |  | 2017-10-09 | SARCA ESTATE DEVT CORP
NC 2017 | K10 | Region IV-A | Tayabas City | 109252 | Gibanga ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3277000 |  |  | Completed | 1 |  |  |  | 17DK0092 | 2017-07-28 | 2017-08-10 | 2017-08-22 |  | 2017-10-09 | SARCA ESTATE DEVT CORP
NC 2017 | K10 | Region IV-A | Tayabas City | 109238 | Masin Elementary School | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3477000 |  |  | Completed | 1 |  |  |  | 17DK0093 | 2017-07-28 | 2017-08-10 | 2017-08-22 |  | 2017-10-09 | WJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Tayabas City | 109239 | Mate ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3277000 |  |  | Completed | 1 |  |  |  | 17DK0094 | 2017-07-28 | 2017-08-10 | 2017-08-22 |  | 2017-10-09 | KKT CONST & SUPPLY
NC 2017 | SHS | Region IV-A | BIÑAN CITY | 301230 | Biñan National High School | CITY OF BIÑAN | 1 | 1 | 20 | 4STY20CL | BATCH 4 | 44326971.63 |  |  | Completed | 1 |  |  |  | 17DI0103 | 2017-10-14 | 2017-10-20 | 2017-11-03 | 2017-11-27 | 2017-12-13 | MICLOVER
NC 2017 | TVL | Region IV-A | BIÑAN CITY | 301230 | Biñan National High School | CITY OF BIÑAN | 1 |  | 8 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 38339521.08 |  |  | Completed | 1 |  |  |  | 17DI0104 | 2017-10-27 | 2017-10-27 | 2017-11-10 | 2017-11-28 | 2017-12-11 | MICLOVER
NC 2017 | K10 | Region IV-A | Batangas | 107225 | Balayan East CS | BALAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107236 | Cepriana Ascue MES | BALAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2690745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107237 | Dr. Jose A. Alaras ES | BALAYAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2733745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107247 | Sampaga ES | BALAYAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3795435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107256 | Palsara ES | BALETE | 3 | 1 | 12 | 1STY5CL | BATCH 4 | 6172650.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107257 | Solis ES | BALETE | 3 | 1 | 12 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301079 | Bauan National Agricultural and Vocational High School | BAUAN | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5565517 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107267 | COLVO ELEMENTARY SCHOOL | BAUAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2677745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107302 | Pedro A. Paterno MES | CALACA | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3876435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107398 | Balibago ES | LIAN | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 3896435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107402 | Cumba ES | LIAN | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2747745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301115 | Anselmo Sandoval MNHS (Mabini NHS) | MABINI | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5317400 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301162 | Tumalim NHS | NASUGBU | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2673745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107643 | Bonliw ES | SAN LUIS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2834862.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107701 | San Francisco ES | SANTO TOMAS | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2688745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107702 | San Isidro ES | SANTO TOMAS | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107710 | San Roque ES | SANTO TOMAS | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107711 | San Vicente ES | SANTO TOMAS | 3 | 1 | 4 | 1STY4CL | BATCH 4 | 4988351.15 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301147 | Santa Clara NHS | SANTO TOMAS | 3 | 1 | 12 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107730 | ISABELO BALEROS MES | TAAL | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2667745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107744 | Tranca ES | TALISAY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301088 | Bolbok NHS | TUY | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2649745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas City | 301473 | Conde Labac SHS | BATANGAS CITY (Capital) | 5 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5317400 |  |  | Completed | 1 |  |  |  | 17DE0062 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | Greenfield Const.
NC 2017 | TVL | Region IV-A | Batangas City | 342234 | Gulod Senior High School | BATANGAS CITY (Capital) | 5 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 5398400 |  |  | Completed | 1 |  |  |  | 17DE0063 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | 6 Jewels Construction
NC 2017 | K10 | Region IV-A | Batangas City | 109569 | Liponpon ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2677745.92 |  |  | Completed | 1 |  |  |  | 17DE0067 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | Cedric B. Construction
NC 2017 | TVL | Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2685700 |  |  | Completed | 1 |  |  |  | 17DE0064 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | Tonijon Const. & Dev't Inc.
NC 2017 | K10 | Region IV-A | Batangas City | 109625 | Sta. Clara ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | 1STY2CL | BATCH 4 | 2731745.92 |  |  | Completed | 1 |  |  |  | 17DE0066 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | 6 Jewels Construction
NC 2017 | TVL | Region IV-A | Batangas City | 301481 | Tabangao Senior High School | BATANGAS CITY (Capital) | 5 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 2722700 |  |  | Completed | 1 |  |  |  | 17DE0065 | 2017-08-31 |  |  | 2017-10-12 | 2017-10-17 | 6 Jewels Onntaruction
NC 2017 | K10 | Region IV-A | Calamba City | 109829 | Calamba Central School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | BATCH 4 | 17742299.58 |  |  | Completed | 1 |  |  |  | 17DI0086 | 2017-08-24 | 2017-08-31 | 2017-09-13 | 2017-10-11 | 2017-10-23 | GAB-ZION ENTERPRISES
NC 2017 | K10 | Region IV-A | Calamba City | 109851 | Majada Out Elementary School | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 31842818.43 |  |  | Completed | 1 |  |  |  | 17DI0093 | 2017-09-01 | 2017-09-08 | 2017-09-22 | 2017-10-18 | 2017-10-27 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2017 | K10 | Region IV-A | Calamba City | 109836 | Sampiruhan ES | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL | BATCH 4 | 18759570.67 |  |  | Completed | 1 |  |  |  | 17DI0090 | 2017-08-24 | 2017-08-31 | 2017-09-13 | 2017-10-11 | 2017-10-23 | HYPER J CONSTRUCTION & SUPPLY
NC 2017 | SHS | Region IV-A | Laguna | 301262 | Nicolas L. Galvez Memorial national High School | BAY | 2 |  | 8 | 4STY8CL | BATCH 4 | 18759570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | CABUYAO | 108235 | Banay-Banay ES | CABUYAO | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32154947.25 |  |  | Completed | 1 |  |  |  | 17DI0095 | 2017-09-01 | 2017-09-08 | 2017-09-22 | 2017-10-18 | 2017-10-27 | Hyper J
NC 2017 | K10 | Region IV-A | CABUYAO | 108237 | Bigaa ES | CABUYAO | 2 | 1 | 8 | 4STY8CL | BATCH 4 | 19217755.14 |  |  | Completed | 1 |  |  |  | 17DI0091 | 2017-08-24 | 2017-08-31 | 2017-09-13 | 2017-10-11 | 2017-10-23 | Hyper J
NC 2017 | TVL | Region IV-A | CABUYAO | 301229 | Bigaa NHS | CABUYAO | 2 | 1 | 8 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 38883709.83 |  |  | Completed | 1 |  |  |  | 17DI0105 | 2017-10-21 | 2017-10-27 | 2017-11-10 | 2017-11-28 | 2017-12-11 | Hyper J
NC 2017 | SHS | Region IV-A | CABUYAO | 301234 | Cabuyao NHS | CABUYAO | 2 | 1 | 16 | 4STY16CL | BATCH 4 | 37851476.54 |  |  | Completed | 1 |  |  |  | 17DI0098 | 2017-10-06 | 2017-10-13 | 2017-10-26 | 2017-10-30 | 2017-11-17 | Hyper J
NC 2017 | K10 | Region IV-A | CABUYAO | 301241 | Gulod NHS | CABUYAO | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32146330.2 |  |  | Completed | 1 |  |  |  | 17DI0094 | 2017-09-01 | 2017-09-08 | 2017-09-22 | 2017-10-18 | 2017-10-27 | Hyper J
NC 2017 | TVL | Region IV-A | CABUYAO | 342355 | Mamatid Senior High School | CABUYAO | 2 | 1 | 10 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 43565975.98 |  |  | Completed | 1 |  |  |  | 17DI0110 | 2017-10-29 | 2017-11-07 | 2017-11-17 | 2017-11-29 | 2017-12-15 | Hyper J
NC 2017 | K10 | Region IV-A | CABUYAO | 108249 | Pulo ES | CABUYAO | 2 | 1 | 12 | 4STY12CL | BATCH 4 | 32994458.5 |  |  | Completed | 1 |  |  |  | 17DI0096 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-10-23 | 2017-11-06 | Hyper J
NC 2017 | K10 | Region IV-A | Laguna | 108308 | Los Banos CES | LOS BAÑOS | 2 | 1 | 8 | 4STY8CL | BATCH 4 | 17994433.01 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108426 | Pacita Complex I ES | SAN PEDRO | 1 | 1 | 20 | 4STY20CL | BATCH 4 | 42327338.23 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Quezon | 108944 | Agdangan CS | Agdangan | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0118 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-19 | 2017-10-26 | SOUTH BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 301293 | Binagbag NHS | Agdangan | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0118 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-19 | 2017-10-26 | SOUTH BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 108537 | Buenavista CS | Buenavista | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9865318.3 |  |  | Completed | 1 |  |  |  | 17DM0119 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-19 | 2017-10-26 | SOUTH BUILDERS
NC 2017 | SHS | Region IV-A | Quezon | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 | 6 | 2STY6CL | BATCH 4 | 12352418.8 |  |  | Completed | 1 |  |  |  | 17DM0119 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-19 | 2017-10-26 | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301296 | Buenavista NHS | BUENAVISTA | 3 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4040868.28 |  |  | Completed | 1 |  |  |  | 17DM0114 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 4040868.28 |  |  | Completed | 1 |  |  |  | 17DM0015 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0120 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0121 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301334 | Burdeos NHS (Judith NHS) | BURDEOS | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3663000 |  |  | Completed | 1 |  |  |  | 17K0122 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | K10 | Region IV-A | Quezon | 108647 | Bulagsong ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108652 | Don Abadilla ES | CATANAUAN | 3 | 1 | 12 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | M.G SALAZAR/ MJIEL
NC 2017 | SHS | Region IV-A | Quezon | 301391 | San Isidro NHS, Catanauan | Catanauan | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 |  | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 43034
NC 2017 | SHS | Region IV-A | Quezon | 308025 | San Jose NHS (Formerly Tagbacan Ilaya Integ. Sec. Ext. Classes) | CATANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 |  | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 43034
NC 2017 | TVL | Region IV-A | Quezon | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS - Tagabas Ibaba Ext) | CATANAUAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3915433.24 |  |  | Completed | 1 |  |  |  | 17DM0117 |  | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 43034
NC 2017 | K10 | Region IV-A | Quezon | 108669 | Tagbacan Ilaya ES | CATANAUAN | 3 | 1 | 12 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya IS) | CATANAUAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3915433.24 |  |  | Completed | 1 |  |  |  | 17DM0116 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108671 | Tuhian ES | CATANAUAN | 3 | 1 | 12 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0120 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-23 | 2017-10-26 | M.G SALAZAR/ MJIEL
NC 2017 | SHS | Region IV-A | Quezon | 301393 | San Isidro NHS, Gen.Luna | Gen. Luna | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0121 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-20 | 2017-10-26 | RCEL
NC 2017 | K10 | Region IV-A | Quezon | 108685 | Bacong Ilaya ES | GENERAL LUNA | 3 | 1 | 12 | 2STY6CL | BATCH 4 | 12430342.21 |  |  | Completed | 1 |  |  |  | 17DM0121 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-20 | 2017-10-26 | RCEL
NC 2017 | K10 | Region IV-A | Quezon | 108694 | San Isidro ES | GENERAL LUNA | 3 | 1 | 12 | 2STY6CL | BATCH 4 | 12430342.21 |  |  | Completed | 1 |  |  |  | 17DM0121 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-20 | 2017-10-26 | RCEL
NC 2017 | TVL | Region IV-A | Quezon | 301292 | Batangan National High School | GENERAL NAKAR | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3613000 |  |  | Completed | 1 |  |  |  | 17DK0146 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | MJ Apin Builders
NC 2017 | TVL | Region IV-A | Quezon | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3663000 |  |  | Completed | 1 |  |  |  | 17DK0132 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Juntereal Industrial & Devt Corporation
NC 2017 | TVL | Region IV-A | Quezon | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7326000 |  |  | Completed | 1 |  |  |  | 17DK0134 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Juntereal Industrial & Devt Corporation
NC 2017 | TVL | Region IV-A | Quezon | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7326000 |  |  | Completed | 1 |  |  |  | 17DK0133 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Juntereal Industrial & Devt Corporation
NC 2017 | K10 | Region IV-A | Quezon | 108787 | Infanta CS | INFANTA | 1 | 1 | 6 | 2STY6CL | BATCH 4 | 12341541.06 |  |  | Completed | 1 |  |  |  | 17DK0158 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Precious Costruction
NC 2017 | TVL | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 | 1 | 3 | WORKSHOP BLDG (7X18) | BATCH 4 | 10089000 |  |  | Completed | 1 |  |  |  | 17DK0142 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0124 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0125 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301343 | Langgas NHS | INFANTA | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17K0126 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Precious Costruction
NC 2017 | TVL | Region IV-A | Quezon | 301343 | Langgas NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0127 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301343 | Langgas NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0128 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | TAD Construction
NC 2017 | SHS | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 | 1 | 4 | 2STY4CL | BATCH 4 | 7939635.18 |  |  | Completed | 1 |  |  |  | 17DK0156 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Juntereal Industrial & Devt Corporation
NC 2017 | TVL | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3859000 |  |  | Completed | 1 |  |  |  | 17DK0135 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17K0129 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0131 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301410 | Tongohin NHS | INFANTA | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0130 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301333 | Jomalig NHS | JOMALIG | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0136 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301333 | Jomalig NHS | JOMALIG | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0137 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301333 | Jomalig NHS | JOMALIG | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0138 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301366 | Nagsinamo NHS | LUCBAN | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0102 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Lucban Builders
NC 2017 | TVL | Region IV-A | Quezon | 301366 | Nagsinamo NHS | LUCBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0103 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Lucban Builders
NC 2017 | SHS | Region IV-A | Quezon | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 | 1 | 6 | 2STY6CL | BATCH 4 | 13041541.06 |  |  | Completed | 1 |  |  |  | 17DK0160 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Lucban Builders
NC 2017 | TVL | Region IV-A | Quezon | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 |  | 4 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 15436000 |  |  | Completed | 1 |  |  |  | 17DK0154 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Lucban Builders
NC 2017 | TVL | Region IV-A | Quezon | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 |  | 6 | WORKSHOP BLDG (7X18) | BATCH 4 | 20178000 |  |  | Completed | 1 |  |  |  | 17DK0159 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Lucban Builders
NC 2017 | SHS | Region IV-A | Quezon | 301360 | Olongtao National High School | MACALELON | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0118 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-19 | 2017-10-26 | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301301 | Cagbalete Island NHS | MAUBAN | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0104 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | CJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301301 | Cagbalete Island NHS | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0106 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | CJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301301 | Cagbalete Island NHS | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0105 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | CJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3959000 |  |  | Completed | 1 |  |  |  | 17DK0107 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3463000 |  |  | Completed | 1 |  |  |  | 17DK0108 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6926000 |  |  | Completed | 1 |  |  |  | 17DK0109 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | CJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308005 | Cagsiay I National High School | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6926000 |  |  | Completed | 1 |  |  |  | 17DK0110 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | CJ Construction
NC 2017 | SHS | Region IV-A | Quezon | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 | 1 | 9 | 3STY9CL | BATCH 4 | 24618047.73 |  |  | Completed | 1 |  |  |  | 17DK0229 | 2017-12-03 | 2017-12-06 | 2017-12-18 | 2017-12-26 | 2017-12-29 | B.C. Cuerpo Const Corp
NC 2017 | TVL | Region IV-A | Quezon | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3463000 |  |  | Completed | 1 |  |  |  | 17DK0123 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 308007 | Liwayway National High School | MAUBAN | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK011 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308007 | Liwayway National High School | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0113 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308007 | Liwayway National High School | MAUBAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0112 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301350 | Manuel S. Enverga Memorial School of Arts and Trades | MAUBAN | 1 | 1 | 3 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 11827000 |  |  | Completed | 1 |  |  |  | 17DK0153 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | JOJR Construction
NC 2017 | TVL | Region IV-A | Quezon | 301350 | Manuel S. Enverga Memorial School of Arts and Trades | MAUBAN | 1 |  | 8 | WORKSHOP BLDG (7X18) | BATCH 4 | 27104000 |  |  | Completed | 1 |  |  |  | 17DK0161 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Steven Const & Supply
NC 2017 | SHS | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9651900.49 |  |  | Completed | 1 |  |  |  | 17DM0122 | [5 empty] | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108924 | Burgos ES | MULANAY | 3 | 1 | 12 | 2STY4CL | BATCH 4 | 9651900.49 |  |  | Completed | 1 |  |  |  | 17DM0122 | [5 empty] | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108938 | Patabog ES | MULANAY | 3 | 1 | 4 | 2STY4CL | BATCH 4 | 9651900.49 |  |  | Completed | 1 |  |  |  | 17DM0122 | [5 empty] | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108938 | Patabog ES | Mulanay | 3 |  | 4 | 2STY4CL | BATCH 4 | 9651900.49 |  |  | Completed | 1 |  |  |  | 17DM0122 | [5 empty] | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301367 | Pagbilao Grande Island NHS | PAGBILAO | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0116 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 301367 | Pagbilao Grande Island NHS | PAGBILAO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0114 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 301367 | Pagbilao Grande Island NHS | PAGBILAO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0115 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | Sarca Estate Devt Corp
NC 2017 | SHS | Region IV-A | Quezon | 308004 | Pagbilao NHS | PAGBILAO | 1 | 1 | 4 | 2STY4CL | BATCH 4 | 9095901.76 |  |  | Completed | 1 |  |  |  | 17DK0118 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | ALT Construction
NC 2017 | TVL | Region IV-A | Quezon | 308004 | Pagbilao NHS | PAGBILAO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0155 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | JOMZKI Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3363000 |  |  | Completed | 1 |  |  |  | 17K0119 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0139 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 308030 | Silangang Malicboy NHS | PAGBILAO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0140 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 301407 | Talipan National High School | PAGBILAO | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0117 |  | 2017-09-29 | 2017-10-12 | 2017-10-31 | 2017-11-17 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301397 | Calasumanga NHS (Formerly San Juan NHS - Calasumanga Ext.) | PANUKULAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3513000 |  |  | Completed | 1 |  |  |  | 17DK0149 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | MJ Apin Builders
NC 2017 | TVL | Region IV-A | Quezon | 301397 | Calasumanga NHS (Formerly San Juan NHS - Calasumanga Ext.) | PANUKULAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3513000 |  |  | Completed | 1 |  |  |  | 17DK0150 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Gemellus Builders
NC 2017 | TVL | Region IV-A | Quezon | 301396 | San Juan NHS | PANUKULAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3863000 |  |  | Completed | 1 |  |  |  | 17DK0147 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Steven Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301396 | San Juan NHS | PANUKULAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 4 | 3863000 |  |  | Completed | 1 |  |  |  | 17DK0148 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Gemellus Builders
NC 2017 | TVL | Region IV-A | Quezon | 308028 | Busdak NHS (Formerly Busdak NHS - Patnanungan NHS Annex) | PATNANUNGAN | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7526000 |  |  | Completed | 1 |  |  |  | 17DK0151 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 308028 | Busdak NHS (Formerly Busdak NHS - Patnanungan NHS Annex) | PATNANUNGAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 4 | 7526000 |  |  | Completed | 1 |  |  |  | 17DK0152 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | E.A.Ayala Const. & Supply
NC 2017 | SHS | Region IV-A | Quezon | 308026 | Ungos NHS - Lubayat Extension Class | REAL | 1 | 1 | 4 | 2STY4CL | BATCH 4 | 9195901.76 |  |  | Completed | 1 |  |  |  | 17DK0157 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-10-03 | 2017-11-22 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Rizal | 308124 | Baras-Pinugay NHS | Baras | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 18100382.7 |  |  | Completed | 1 |  |  | P00172839LZ-CW1 | 17D00100 | 2017-09-07 | 2017-09-15 | 2017-09-26 | 2017-10-10 | 2017-10-20 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T CORP.
NC 2017 | TVL | Region IV-A | Rizal | 301434 | Catalino D. Salazar NHS - Senior High School | Cardona | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 19605339.767 |  |  | Completed | 1 |  |  | P00172841LZ-CW1 | 17D00096 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109422 | Tadlak ES (Korokan ES) | Cardona | 2 | 1 | 4 | 2STY4CL | BATCH 4 | 10043103.79 |  |  | Completed | 1 |  |  | P00172840LZ-CW1 | 17D00079 | 2017-07-22 | 2017-07-18 | 2017-08-10 | 2017-10-10 | 2017-10-20 | FLAG CONST. CORP.
NC 2017 | TVL | Region IV-A | Rizal | 301468 | Tuna-Balibago NHS | Cardona | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 4 | 11165727.412 |  |  | Completed | 1 |  |  | P00172842LZ-CW1 | 17D00098 | 2017-09-07 | 2017-09-14 | 2017-09-26 | 2017-10-10 | 2017-10-20 | DARCY & ANNA BUILDERS & TRADING
NC 2017 | K10 | Region IV-A | Rizal | 109417 | Mariano C. San Juan ES | Cardona | 2 | 1 | 4 | 2STY4CL | BATCH 4 | 10317137.236 |  |  | Completed | 1 |  |  | P00172843LZ-CW1 | 17D00082 | 2017-07-22 | 2017-07-28 | 2017-08-10 | 2017-10-10 | 2017-10-20 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T CORP.
NC 2017 | TVL | Region IV-A | Rizal | 301430 | Bayugo NHS | Jala-jala | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 18890861.23 |  |  | Completed | 1 |  |  | P00172844LZ-CW1 | 17D00097 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | PRECIOUS CONSTRUCTION
NC 2017 | TVL | Region IV-A | Rizal | 301430 | Bayugo NHS | Jala-jala | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3255000 |  |  | Completed | 1 |  |  | P00172845LZ-CW1 | 17D00094 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | RESPANZ BUILDERS INC
NC 2017 | K10 | Region IV-A | Rizal | 109437 | Talaga ES (Maybancal ES - Talaga ES) | Morong | 2 | 1 | 12 | 4STY8CL | BATCH 4 | 17500382.7 |  |  | Completed | 1 |  |  | P00172846LZ-CW1 | 17D00087 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-10-10 | 2017-10-20 | GENETIAN BUILDERS
NC 2017 | TVL | Region IV-A | Rizal | 308121 | Hulo National High School | Pililla | 2 | 1 | 2 | 2STY WORKSHOP BLDG (7X18) | BATCH 4 | 10371342.148 |  |  | Completed | 1 |  |  | P00172849LZ-CW1 | 17D00081 | 2017-07-22 | 2017-07-28 | 2017-08-10 | 2017-10-10 | 2017-10-20 | ST. MATTHEW GEN. CONTRACTOR & DEV'T. CORP.
NC 2017 | TVL | Region IV-A | Rizal | 301454 | Quisao NHS | Pililla | 2 | 1 | 4 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 19570382.7 |  |  | Completed | 1 |  |  | P00172847LZ-CW1 | 17D00101 | 2017-09-07 | 2017-09-14 | 2017-09-26 | 2017-10-10 | 2017-10-20 | ST. TIMOTHY CONST. CORP.
NC 2017 | TVL | Region IV-A | Rizal | 301454 | Quisao NHS | Pililla | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3150000 |  |  | Completed | 1 |  |  | P00172848LZ-CW1 | 17D00092 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | POWER K CONST. SUPPLY & SERVICES
NC 2017 | K10 | Region IV-A | Rizal | 308127 | Cuyambay National High School | Tanay | 2 | 1 | 8 | 4STY8CL | BATCH 4 | 17525382.7 |  |  | Completed | 1 |  |  | P00172852LZ-CW1 | 17D00086 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-10-10 | 2017-10-20 | JRD-D2 ENTERPRISES
NC 2017 | SHS | Region IV-A | Rizal | 301456 | Sampaloc NHS | Tanay | 2 | 1 | 6 | 2STY6CL | BATCH 4 | 12362243.75 |  |  | Completed | 1 |  |  | P00172850LZ-CW1 | 17D00099 | 2017-09-07 | 2017-09-14 | 2017-09-26 | 2017-10-10 | 2017-10-20 | V. BERNARDO CONST. & TRADING
NC 2017 | TVL | Region IV-A | Rizal | 301456 | Sampaloc NHS | Tanay | 2 |  | 6 | 3STY WORKSHOP BLDG (7X18) | BATCH 4 | 30206106.96 |  |  | Completed | 1 |  |  | P00172851LZ-CW1 | 17D00088 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-10-10 | 2017-10-20 | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2017 | SHS | Region IV-A | Rizal | 342571 | Stand Alone 10 (Rizal Sports Academy) | Tanay | 2 | 1 | 4 | 2STY4CL | BATCH 4 | 9486547.06 |  |  | Completed | 1 |  |  | P00172853LZ-CW1 | 17D00090 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-10-10 | 2017-10-20 | MPJR BUILDERS CO.
NC 2017 | TVL | Region IV-A | Rizal | 308103 | Abuyod NHS | Teresa | 2 | 1 | 6 | 3STY WORKSHOP BLDG (7X18) | BATCH 4 | 30046106.96 |  |  | Completed | 1 |  |  | P00172854LZ-CW1 | 17D00095 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | GENETIAN BUILDERS/JAKE BUILDER (JV)
NC 2017 | TVL | Region IV-A | Rizal | 308103 | Abuyod NHS | Teresa | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 4 | 3100000 |  |  | Completed | 1 |  |  | P00172855LZ-CW1 | 17D00093 | 2017-09-01 | 2017-09-08 | 2017-09-21 | 2017-10-10 | 2017-10-20 | T.Q. CONST. & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Sta. Rosa City | 108470 | Balibago Elementary School | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL | BATCH 4 | 17583312.6 |  |  | Completed | 1 |  |  |  | 17DI0085 | 2017-08-31 | 2017-09-06 | 2017-09-13 | 2017-10-11 | 2017-10-20 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA | 1 | 1 | 16 | 4STY16CL | BATCH 4 | 37584919.82 |  |  | Completed | 1 |  |  |  | 17DI0097 | 2017-10-13 | 2017-10-19 | 2017-10-26 | 2017-10-30 | 2017-11-17 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS/HARVEE ENTERPRISES JV,
NC 2017 | K10 | Region IV-A | Sta. Rosa City | 108474 | Don Jose Elementary School | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL | BATCH 4 | 18226995.96 |  |  | Completed | 1 |  |  |  | 17DI0088 | 2017-08-31 | 2017-09-06 | 2017-09-13 | 2017-10-11 | 2017-10-20 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2017 | TVL | Region IV-A | Sta. Rosa City | 342597 | Sinalhan Senior High School | CITY OF SANTA ROSA | 1 | 1 | 6 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 68609579.44 |  |  | Completed | 1 |  |  |  | 17DI0088 | 2017-11-11 | 2017-11-17 | 2017-11-24 | 2017-11-29 | 2017-12-20 | ROBIG BUILDERS & DEVELOPMENT CORPS.
NC 2017 | TVL | Region IV-A | Sta. Rosa City | 342597 | Sinalhan Senior High School | CITY OF SANTA ROSA | 1 |  | 6 | 4STY WORKSHOP BLDG (7X18) | BATCH 4 | 68609579.44 |  |  | Completed | 1 |  |  |  | 17DI0088 | 2017-11-11 | 2017-11-17 | 2017-11-24 | 2017-11-29 | 2017-12-20 | ROBIG BUILDERS & DEVELOPMENT CORPS.
NC 2017 | K10 | Region IV-A | Tanauan City | 107745 | Altura ES | CITY OF TANAUAN | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 107746 | Ambulong ES | CITY OF TANAUAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 3221379.92 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Tayabas City | 301347 | Luis Palad NHS | CITY OF TAYABAS | 1 |  | 12 | 4STY12CL | BATCH 4 | 32188155.07 |  |  | Completed | 1 |  |  |  | 17DK0162 | 2017-10-08 | 2017-10-11 | 2017-10-23 | 2017-11-02 | 2017-11-20 | DQT BUILDERS
NC 2017 | SHS | Region IV-A | Antipolo City | 342175 | Antipolo City Senior High School | CITY OF ANTIPOLO | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 54270850.74 |  |  | Completed | 1 |  |  |  | 17DN0145 |  |  | 2017-10-19 |  | 2017-11-29 | ST. TIMOTHY CONST. CORP
NC 2017 | K10 | Region IV-A | Antipolo City | 109319 | Bagong Nayon I ES | CITY OF ANTIPOLO | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 19844095.47 |  |  | Completed | 1 | [6 empty] | 2017-10-26 |  | 2017-11-30
NC 2017 | K10 | Region IV-A | Antipolo City | 109319 | Bagong Nayon I ES | CITY OF ANTIPOLO | 1 |  | 8 | 4STY8CL | BATCH 7 | 22374742.85 |  |  | Completed | 1 | [6 empty] | 2017-10-26 |  | 2017-11-30
NC 2017 | K10 | Region IV-A | Antipolo City | 109320 | Bagong Nayon II ES | CITY OF ANTIPOLO | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 34614377.08 |  |  | Completed | 1 |  |  |  | 17DN0147 |  |  | 2017-10-26 |  | 2017-11-30 | BELL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Antipolo City | 109348 | Calawis ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17486593.31 |  |  | Completed | 1 |  |  |  | 17DN0139 |  |  | 2017-10-19 |  | 2017-11-22 | 3-L CONSTRUCTION
NC 2017 | SHS | Region IV-A | Antipolo City | 301431 | Calawis NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17585873.59 |  |  | reverted | 0 |  |  |  | 17DN0157 |  |  | 2017-10-27 |  | 2017-11-30 | PACIFIC SUMMIT CONST
NC 2017 | SHS | Region IV-A | Antipolo City | 321502 | Canumay NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18413146.31 |  |  | Completed | 1 |  |  |  | 17DN0161 |  |  | 2017-11-07 |  | 2017-10-12 | EMIRAM CONST & SUPPLY
NC 2017 | K10 | Region IV-A | Antipolo City | 109324 | Dalig ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17522237.22 |  |  | Completed | 1 |  |  |  | 17DN0140 |  |  | 2017-10-19 |  | 2017-11-22 | HEXAMINDZ CORP
NC 2017 | TVL | Region IV-A | Antipolo City | 321505 | Dela Paz NHS | CITY OF ANTIPOLO | 1 | 1 | 3 | 3STY3CL | BATCH 7 | 10956669.05 |  |  | Completed | 1 | [6 empty] | 2017-10-19 |  | 2017-11-22
NC 2017 | K10 | Region IV-A | Antipolo City | 109326 | Inuman ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17649509.95 |  |  | Completed | 1 | [6 empty] | 2017-11-09 |  | 2017-12-13
NC 2017 | K10 | Region IV-A | Antipolo City | 109351 | Jesus S. Cabarrus ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17394964.49 |  |  | Completed | 1 |  |  |  | 17DN0152 |  |  | 2017-10-27 |  | 2017-11-30 | PACIFIC SUMMIT CONST
NC 2017 | K10 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 41560023.45 |  |  | Completed | 1 |  |  |  | 17DN0178 |  |  | 2017-11-16 |  | 2017-12-21 | JHASEN CONST./ KARPA BLDRS.
NC 2017 | K10 | Region IV-A | Antipolo City | 109327 | Juan Sumulong ES | CITY OF ANTIPOLO | 2 |  | 20 | 4STY20CL | BATCH 7 | 41560023.45 |  |  | Completed | 1 |  |  |  | 17DN0179 |  |  | 2017-11-16 |  | 2017-12-21 | JHASEN CONST./ KARPA BLDRS.
NC 2017 | SHS | Region IV-A | Antipolo City | 301421 | Kaysakat NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18158600.86 |  |  | Completed | 1 |  |  |  | 17DN0162 |  |  | 2017-11-07 |  | 2017-12-12 | EMIRAM CONST & SUPPLY
NC 2017 | K10 | Region IV-A | Antipolo City | 109322 | Libis ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18285873.59 |  |  | Terminated | 0 |  |  |  | 17DN0151 |  |  | 2017-10-27 |  | 2017-11-30 | PACIFIC SUMMIT CONST | DPWH Reported: With Mutual Termination and requesting for completion amount of 15,5B;Suspended indefinite suspension due to contractor's performance
NC 2017 | K10 | Region IV-A | Antipolo City | 109329 | Lores ES | CITY OF ANTIPOLO | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 31970374.45 |  |  | Completed | 1 |  |  |  | 17DN0175 |  |  | 2017-11-16 |  | 2017-12-21 | MICLOVER GEN CONST
NC 2017 | SHS | Region IV-A | Antipolo City | 321501 | Marcelino M. Santos NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17840419.04 |  |  | Completed | 1 |  |  |  | 17DN0163 |  |  | 2017-11-07 |  | 2017-12-12 | EASTERN CONST CO INC
NC 2017 | TVL | Region IV-A | Antipolo City | 301423 | Muntindilaw NHS | CITY OF ANTIPOLO | 1 | 1 | 4 | 4STY4CL | BATCH 7 | 13519550.81 |  |  | Completed | 1 | [6 empty] | 2017-10-26 |  | 2017-11-30
NC 2017 | SHS | Region IV-A | Antipolo City | 308101 | Old Boso-boso NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17840419.04 |  |  | Completed | 1 |  |  |  | 17DN0164 |  |  | 2017-11-07 |  | 2017-12-12 | EASTERN CONST CO INC
NC 2017 | SHS | Region IV-A | Antipolo City | 321504 | Rizza NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17585873.59 |  |  | Completed | 1 | [6 empty] | 2017-10-27 |  | 2017-11-30
NC 2017 | K10 | Region IV-A | Antipolo City | 109358 | San Antonio Village ES | CITY OF ANTIPOLO | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 31970374.45 |  |  | Completed | 1 | [6 empty] | 2017-11-16 |  | 2017-12-21 | BELL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Antipolo City | 109339 | San Isidro ES | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 19923699.46 |  |  | Completed | 1 |  |  |  | 17DN0141 |  |  | 2017-10-19 |  | 2017-11-30 | BELL CONSTRUCTION
NC 2017 | SHS | Region IV-A | Antipolo City | 301426 | San Isidro NHS | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 19667694.9 |  |  | Completed | 1 |  |  |  | 17DN0149 |  |  | 2017-10-26 |  | 2017-11-30 | BELL CONSTRUCTION
NC 2017 | SHS | Region IV-A | Antipolo City | 301427 | San Juan NHS | CITY OF ANTIPOLO | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 14168118.68 |  |  | Completed | 1 | [6 empty] | 2017-10-19 |  | 2017-11-22
NC 2017 | SHS | Region IV-A | Antipolo City | 301425 | San Roque NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 17585873.59 |  |  | Completed | 1 | [6 empty] | 2017-11-09 |  | 2017-12-13
NC 2017 | K10 | Region IV-A | Antipolo City | 109341 | Sapinit ES | CITY OF ANTIPOLO | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 31970374.45 |  |  | Completed | 1 |  |  |  | 17DN0177 |  |  | 2017-11-16 |  | 2017-12-21 | HEXAMINDZ CORP
NC 2017 | K10 | Region IV-A | Antipolo City | 109342 | Sta. Cruz ES | CITY OF ANTIPOLO | 1 |  | 20 | 4STY20CL | BATCH 7 | 48436068.82 |  |  | Completed | 1 |  |  |  | 17DN0143 |  |  | 2017-10-19 |  | 2017-11-22 | VINELL-BELVOR CORP
NC 2017 | K10 | Region IV-A | Antipolo City | 109342 | Sta. Cruz ES | CITY OF ANTIPOLO | 1 |  | 20 | 4STY20CL | BATCH 7 | 48436068.82 |  |  | Completed | 1 |  |  |  | 17DN0142 |  |  | 2017-10-19 |  | 2017-11-22 | LTDL BUILDERS
NC 2017 | K10 | Region IV-A | Antipolo City | 109342 | Sta. Cruz ES | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 22374742.85 |  |  | Completed | 1 |  |  |  | 17DN0145 |  |  | 2017-10-19 |  | 2017-11-22 | BELL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Bacoor City |  | Bacoor NHS- Georgetown | Bacoor | 2 | 1 | 9 | 3STY9CL | BATCH 7 | 24627652.63 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107869 | Dulong Bayan ES | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 28350738.95 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107881 | Ligas I Elementary School | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 37296066.73 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107887 | Niog ES | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 37296066.73 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107874 | Real ES | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 21874666.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107889 | San Nicolas ES | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 7 | 43832290.62 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Bacoor City | 342598 | SHS Dulong Bayan | Bacoor | 2 | 1 | 8 | 2STY8CL | BATCH 7 | 20273037.46 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Bacoor City | 342598 | SHS Dulong Bayan | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 37296066.73 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Bacoor City | 342601 | SHS in Sineguelasan | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 21874666.16 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Bacoor City | 342600 | SHS San Nicolas III | Bacoor | 2 | 1 | 8 | 2STY8CL | BATCH 7 | 20273037.46 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Bacoor City | 342600 | SHS San Nicolas III | Bacoor | 2 | 1 | 16 | 4STY16CL | BATCH 7 | 37049099.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107226 | Balayan West CS | BALAYAN | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 31999789.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107234 | Don Leon Martinez MES | BALAYAN | 1 | 1 | 9 | 3STY9CL | BATCH 7 | 24718047.73 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107248 | Santol ES | BALAYAN | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13889515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107287 | Calaca Central School | CALACA | 1 | 1 | 12 | 3STY12CL | BATCH 7 | 29609267.25 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107355 | Ibaan CS | IBAAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9128058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107356 | Lucsuhin ES | IBAAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9098058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107356 | Lucsuhin ES | IBAAN | 4 |  | 6 | 2STY6CL | BATCH 7 | 11872992.95 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107356 | Lucsuhin ES | IBAAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9098058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107356 | Lucsuhin ES | IBAAN | 4 |  | 6 | 2STY6CL | BATCH 7 | 11872992.95 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107358 | Malainin ES | IBAAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9183058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107358 | Malainin ES | IBAAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9183058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas |  | Dionisio Vito MNHS | LEMERY | 1 | 1 | 9 | 3STY9CL | BATCH 7 | 24618047.73 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107387 | Marcos Catibog Memorial Elementary School | LEMERY | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 14039515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107388 | Mayasang ES | LEMERY | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 14039515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107417 | Niogan ES | LEMERY | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13919515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107389 | R. Venturanza CS | LEMERY | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107391 | Sinisian ES | LEMERY | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107391 | Sinisian ES | LEMERY | 1 |  | 6 | 3STY6CL | BATCH 7 | 13739515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 307706 | Lian NHS | LIAN | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 31769789.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107513 | Natipuan Elementary School | NASUGBU | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17359570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107519 | Tumalim Elementay School | NASUGBU | 1 | 1 | 9 | 3STY9CL | BATCH 7 | 24668047.73 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 301069 | Alupay NHS | ROSARIO | 4 | 1 | 12 | 4STY12CL | BATCH 7 | 33031921.62 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107575 | San Carlos ES | ROSARIO | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9253058.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107638 | Paaralang Elementarya ng Tipas | SAN JUAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9140558.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107631 | San Juan East Central School | SAN JUAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9171458.48 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 361016 | San Juan Senior High School | SAN JUAN | 4 | 1 | 20 | 4STY20CL | BATCH 7 | 41629036.47 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107632 | San Juan West CS | SAN JUAN | 4 | 1 | 9 | 3STY9CL | BATCH 7 | 24875122.17 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 307708 | Sico 1.0 National High School | SAN JUAN | 4 | 1 | 12 | 4STY12CL | BATCH 7 | 31862609.55 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107722 | Apacay ES | TAAL | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13799515.1 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 342221 | SHS in Taysan | TAYSAN | 4 | 1 | 12 | 4STY12CL | BATCH 7 | 31862609.55 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107839 | Alfonso ES | ALFONSO | 8 | 1 | 20 | 4STY20CL | BATCH 7 | 41362000 |  |  | Completed | 1 |  |  | 17DG0075 | [6 empty] | Jojalie Construction
NC 2017 | SHS | Region IV-A | Cavite | 301199 | Lucsuhin National High School | ALFONSO | 8 | 1 | 8 | 4STY8CL | BATCH 7 | 16890500 |  |  | Completed | 1 |  |  | 17DG0072 | [6 empty] | N.V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 107850 | Pansin Elementary School | ALFONSO | 8 | 1 | 8 | 4STY8CL | BATCH 7 | 18753000 |  |  | Completed | 1 |  |  | 17DG0099 | [6 empty] | Huasland Construction
NC 2017 | SHS | Region IV-A | Cavite | 301166 | Amadeo National High School | Amadeo | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31649789.72 |  |  | Completed | 1 |  |  | 17DF0092
NC 2017 | SHS | Region IV-A | Cavite | 301195 | Halang Banaybanay NHS | Amadeo | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 8945901.76 |  |  | Completed | 1 |  |  | 17DF0100C
NC 2017 | SHS | Region IV-A | Cavite | 301217 | Talon National High School | Amadeo | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17222570.67 |  |  | Completed | 1 |  |  | 17DF0100A
NC 2017 | SHS | Region IV-A | Cavite | 301217 | Talon National High School | Amadeo | 6 |  | 4 | 2STY4CL | BATCH 7 | 9008901.76 |  |  | Completed | 1 |  |  | 17DF0100B
NC 2017 | SHS | Region IV-A | Cavite | 342284 | SHS in Carmona | CARMONA | 5 | 1 | 8 | 4STY16CL | BATCH 7 | 36652910.69 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 342284 | SHS in Carmona | CARMONA | 5 |  | 8 | 4STY16CL | BATCH 7 | 36652910.69 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301192 | Gen. Mariano Alvarez Tech. HS | GEN. MARIANO ALVAREZ | 5 | 1 | 12 | 4STY24CL | BATCH 7 | 47143836.68 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301213 | San Jose Community HS | GEN. MARIANO ALVAREZ | 5 | 1 | 12 | 4STY24CL | BATCH 7 | 47143836.68 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | General Trias City | 107960 | Gen. Artemio Ricarte MS | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17222570.67 |  |  | Completed | 1 |  |  | 17DF0127A
NC 2017 | K10 | Region IV-A | General Trias City | 107945 | Gen. Gregorio S. Alona, Sr. MES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17348570.67 |  |  | Completed | 1 |  |  | 17DF0103A
NC 2017 | K10 | Region IV-A | General Trias City | 107945 | Gen. Gregorio S. Alona, Sr. MES | GENERAL TRIAS | 6 |  | 4 | 2STY4CL | BATCH 7 | 9134901.76 |  |  | Completed | 1 |  |  | 17DF0103B
NC 2017 | K10 | Region IV-A | General Trias City | 107947 | Gen. Trias MES | GENERAL TRIAS | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31775789.72 |  |  | Completed | 1 |  |  | 17DF0105
NC 2017 | K10 | Region IV-A | General Trias City | 107949 | Javalera ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17537570.67 |  |  | Completed | 1 |  |  | 17DF0108B
NC 2017 | K10 | Region IV-A | General Trias City | 107951 | Manggahan ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17285570.67 |  |  | Completed | 1 |  |  | 17DF0133
NC 2017 | K10 | Region IV-A | General Trias City | 107961 | Mary Cris ES | GENERAL TRIAS | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31964789.72 |  |  | Completed | 1 |  |  | 17DF0097
NC 2017 | K10 | Region IV-A | General Trias City | 107962 | Navarro ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17285570.67 |  |  | Completed | 1 |  |  | 17DF0127B
NC 2017 | K10 | Region IV-A | General Trias City | 107954 | Pasong Kawayan II ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17348570.67 |  |  | Completed | 1 |  |  | 17DF0114
NC 2017 | K10 | Region IV-A | General Trias City | 164020 | Pasong Kawayan II West ES | GENERAL TRIAS | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31901789.72 |  |  | Completed | 1 |  |  | 17DF0095
NC 2017 | K10 | Region IV-A | General Trias City | 107955 | Tapia ES | GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17411570.67 |  |  | Completed | 1 |  |  | 17DF0108B
NC 2017 | SHS | Region IV-A | Cavite | 301192 | Gen. Mariano Alvarez Tech. HS | GMA | 5 | 1 | 20 | 4STY20CL | BATCH 7 | 41009817.75 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301192 | Gen. Mariano Alvarez Tech. HS | GMA | 5 |  | 20 | 4STY20CL | BATCH 7 | 41009817.75 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107941 | San Gabriel II ES | GMA | 5 | 1 | 20 | 4STY20CL | BATCH 7 | 40934817.75 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107941 | San Gabriel II ES | GMA | 5 |  | 8 | 4STY8CL | BATCH 7 | 17932365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107941 | San Gabriel II ES | GMA | 5 |  | 8 | 4STY8CL | BATCH 7 | 17932365.45 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301201 | Lumampong NHS - Indang Annex | INDANG | 7 | 1 | 8 | 4STY8CL | BATCH 7 | 17945800 |  |  | Completed | 1 |  |  | 17DG0078 | [6 empty] | Hausland Constrcution
NC 2017 | K10 | Region IV-A | Cavite | 108022 | Panamitan ES | KAWIT | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17474570.67 |  |  | Completed | 1 |  |  | 17DF0099A
NC 2017 | K10 | Region IV-A | Cavite | 108022 | Panamitan ES | KAWIT | 1 |  | 8 | 4STY8CL | BATCH 7 | 17474570.67 |  |  | Completed | 1 |  |  | 17DF0099B
NC 2017 | K10 | Region IV-A | Cavite | 108033 | Pacheco ES | MAGALLANES | 8 | 1 | 6 | 3STY6CL | BATCH 7 | 14597500 |  |  | Completed | 1 |  |  | 17DG0081 | [6 empty] | One Euluz Construction
NC 2017 | K10 | Region IV-A | Cavite | 108056 | Mendez CS | MENDEZ (MENDEZ-NUÑEZ) | 8 | 1 | 12 | 4STY12CL | BATCH 7 | 33505000 |  |  | Completed | 1 |  |  | 17DG0089 | [6 empty] | N.V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 108070 | Halang ES | NAIC | 8 | 1 | 12 | 4STY12CL | BATCH 7 | 33650500 |  |  | Completed | 1 |  |  | 17DG0090 | [6 empty] | Hausland Constrcution
NC 2017 | K10 | Region IV-A | Cavite | 108063 | Ibayo ES | NAIC | 8 | 1 | 12 | 4STY12CL | BATCH 7 | 31620000 |  |  | Completed | 1 |  |  | 17DG0091 | [6 empty] | Hausland Construction
NC 2017 | K10 | Region IV-A | Cavite | 108063 | Ibayo ES | NAIC | 8 |  | 12 | 4STY12CL | BATCH 7 | 31620000 |  |  | Completed | 1 |  |  | 17DG0091 | [6 empty] | Hausland Construction
NC 2017 | K10 | Region IV-A | Cavite | 108074 | Palangue 3 ES | NAIC | 8 | 1 | 8 | 4STY8CL | BATCH 7 | 17951850 |  |  | Completed | 1 |  |  | 17DG0088 | [6 empty] | One Euluz Construction
NC 2017 | K10 | Region IV-A | Cavite | 108076 | Palangue CS | NAIC | 8 | 1 | 8 | 4STY8CL | BATCH 7 | 17029700 |  |  | Completed | 1 |  |  | 17DG0086 | [6 empty] | Metrics Construction
NC 2017 | K10 | Region IV-A | Cavite | 108077 | Petronilo L. Torres MES | NAIC | 8 | 1 | 20 | 4STY20CL | BATCH 7 | 41360000 |  |  | Completed | 1 |  |  | 17DG0074 | [6 empty] | Jojalie Construction
NC 2017 | K10 | Region IV-A | Cavite | 108086 | Pacifico O. Aquino ES (San Rafael ES) | NOVELETA | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 31901789.72 |  |  | Completed | 1 |  |  | 17DF0107
NC 2017 | K10 | Region IV-A | Cavite | 108086 | Pacifico O. Aquino ES (San Rafael ES) | NOVELETA | 1 |  | 8 | 4STY8CL | BATCH 7 | 17537570.67 |  |  | Completed | 1 |  |  | 17DF0090
NC 2017 | K10 | Region IV-A | Cavite | 108091 | Rosario ES | ROSARIO | 1 | 1 | 12 | 4STY12CL | BATCH 7 | 31933289.72 |  |  | Completed | 1 |  |  | 17DF0120
NC 2017 | K10 | Region IV-A | Cavite | 108091 | Rosario ES | ROSARIO | 1 |  | 12 | 4STY12CL | BATCH 7 | 31933289.72 |  |  | Completed | 1 |  |  | 17DF0125
NC 2017 | K10 | Region IV-A | Cavite | 301212 | Rosario National High School | ROSARIO | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17348570.67 |  |  | Completed | 1 |  |  | 17DF0101
NC 2017 | K10 | Region IV-A | Cavite | 107936 | Area J ES | Silang | 5 | 1 | 16 | 4STY16CL | BATCH 7 | 36638207.71 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107936 | Area J ES | Silang | 5 |  | 12 | 4STY12CL | BATCH 7 | 31218955.15 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108102 | Bulihan Sites & Services Project ES | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 7 | 40934817.75 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108102 | Bulihan Sites & Services Project ES | Silang | 5 |  | 12 | 4STY12CL | BATCH 7 | 31218955.15 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108102 | Bulihan Sites & Services Project ES | Silang | 5 |  | 8 | 4STY8CL | BATCH 7 | 17782365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108145 | Carlos S. Batino Sr. MES | TAGAYTAY CITY | 8 | 1 | 4 | 2STY4CL | BATCH 7 | 8983000 |  |  | Completed | 1 |  |  | 17DG0071 | [6 empty] | PGM Construction & Plumbing Services
NC 2017 | SHS | Region IV-A | Cavite | 301216 | Tagaytay City National High School | TAGAYTAY CITY | 8 | 1 | 16 | 4STY16CL | BATCH 7 | 37350000 |  |  | Completed | 1 |  |  | 17DG0102 | [6 empty] | New Vic Construction Corp.
NC 2017 | SHS | Region IV-A | Cavite | 301215 | Tagaytay City Nat'l. Science HS | TAGAYTAY CITY | 8 | 1 | 12 | 4STY12CL | BATCH 7 | 31619000 |  |  | Completed | 1 |  |  | 17DG0084 | [6 empty] | Jojalie Construction
NC 2017 | SHS | Region IV-A | Cavite | 301167 | Amaya Sch. of Home Industries | TANZA | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37137537.96 |  |  | Completed | 1 |  |  | 17DF0129
NC 2017 | SHS | Region IV-A | Cavite | 301167 | Amaya Sch. of Home Industries | TANZA | 6 |  | 12 | 4STY12CL | BATCH 7 | 31819889.72 |  |  | Completed | 1 |  |  | 17DF0106
NC 2017 | SHS | Region IV-A | Cavite | 301167 | Amaya Sch. of Home Industries | TANZA | 6 |  | 12 | 4STY12CL | BATCH 7 | 31819889.72 |  |  | Completed | 1 |  |  | 17DF0118
NC 2017 | K10 | Region IV-A | Cavite | 108159 | Antonio B. del Rosario Sr. Mem. Elementary School | TANZA | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41912409.74 |  |  | Completed | 1 |  |  | 17DF0133
NC 2017 | K10 | Region IV-A | Cavite | 108163 | Bienvenido R. Fojas MES | TANZA | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 9071901.76 |  |  | Completed | 1 |  |  | 17DF0135
NC 2017 | K10 | Region IV-A | Cavite | 108170 | Felipe Calderon ES | TANZA | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31838789.72 |  |  | Completed | 1 |  |  | 17DF0093
NC 2017 | K10 | Region IV-A | Cavite | 108162 | Halayhay ES | TANZA | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31901789.72 |  |  | Completed | 1 |  |  | 17DF0096
NC 2017 | K10 | Region IV-A | Cavite | 108166 | Punta ES | TANZA | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 8945901.76 |  |  | Completed | 1 |  |  | 17DF0136B
NC 2017 | SHS | Region IV-A | Cavite | 301218 | Tanza National Comprehensive High School | TANZA | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 42169659.74 |  |  | Completed | 1 |  |  | 17DF0134A
NC 2017 | SHS | Region IV-A | Cavite | 301218 | Tanza National Comprehensive High School | TANZA | 6 |  | 20 | 4STY20CL | BATCH 7 | 42169659.74 |  |  | Completed | 1 |  |  | 17DF0134B
NC 2017 | SHS | Region IV-A | Cavite | 301218 | Tanza National Comprehensive High School | TANZA | 6 |  | 4 | 2STY4CL | BATCH 7 | 9250401.76 |  |  | Completed | 1 |  |  | 17DF0136A
NC 2017 | SHS | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41637499.74 |  |  | Completed | 1 |  |  | 17DF0112
NC 2017 | SHS | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 |  | 20 | 4STY20CL | BATCH 7 | 41637499.74 |  |  | Completed | 1 |  |  | 17DF0141B
NC 2017 | SHS | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 |  | 16 | 4STY16CL | BATCH 7 | 37094011.2933 |  |  | Completed | 1 |  |  | 17DF0109
NC 2017 | SHS | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 |  | 16 | 4STY16CL | BATCH 7 | 37094011.2933 |  |  | Completed | 1 |  |  | 17DF0122
NC 2017 | SHS | Region IV-A | Cavite | 301219 | Tanza National Trade School | TANZA | 6 |  | 16 | 4STY16CL | BATCH 7 | 37094011.2933 |  |  | Completed | 1 |  |  | 17DF0141A
NC 2017 | SHS | Region IV-A | Cavite | 307807 | Ternate West NHS | TERNATE | 8 | 1 | 8 | 4STY8CL | BATCH 7 | 16855000 |  |  | Completed | 1 |  |  | 17DG0083 | [6 empty] | Metrics Construction & Trading
NC 2017 | K10 | Region IV-A | Cavite | 108177 | Aguado ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41901409.74 |  |  | Completed | 1 |  |  | 17DF0123
NC 2017 | K10 | Region IV-A | Cavite | 108180 | Conchu ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 9197901.76 |  |  | Completed | 1 |  |  | 17DF0116A
NC 2017 | K10 | Region IV-A | Cavite | 108182 | Hugo Perez ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41408409.74 |  |  | Completed | 1 |  |  | 17DF0130
NC 2017 | K10 | Region IV-A | Cavite | 108182 | Hugo Perez ES | TRECE MARTIRES CITY (Capital) | 6 |  | 8 | 4STY8CL | BATCH 7 | 17159570.67 |  |  | Completed | 1 |  |  | 17DF0098A
NC 2017 | K10 | Region IV-A | Cavite | 108182 | Hugo Perez ES | TRECE MARTIRES CITY (Capital) | 6 |  | 8 | 4STY8CL | BATCH 7 | 17159570.67 |  |  | Completed | 1 |  |  | 17DF0098B
NC 2017 | K10 | Region IV-A | Cavite | 108183 | Kanggahan ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37126737.96 |  |  | Completed | 1 |  |  | 17DF0110
NC 2017 | K10 | Region IV-A | Cavite | 108183 | Kanggahan ES | TRECE MARTIRES CITY (Capital) | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31811789.72 |  |  | Completed | 1 |  |  | 17DF0117
NC 2017 | K10 | Region IV-A | Cavite | 108186 | PALAWIT ELEMENTARY SCHOOL | TRECE MARTIRES CITY (Capital) | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17285570.67 |  |  | Completed | 1 |  |  | 17DF0116B
NC 2017 | SHS | Region IV-A | Cavite | 342292 | Trece Martires City Senior High School | TRECE MARTIRES CITY (Capital) | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37423737.96 |  |  | Completed | 1 |  |  | 17DF0111
NC 2017 | SHS | Region IV-A | Cavite | 342292 | Trece Martires City Senior High School | TRECE MARTIRES CITY (Capital) | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 9166901.76 |  |  | Completed | 1 |  |  | 17DF0091A
NC 2017 | SHS | Region IV-A | Cavite | 342292 | Trece Martires City Senior High School | TRECE MARTIRES CITY (Capital) | 6 | 1 | 4 | 2STY4CL | BATCH 7 | 9166901.76 |  |  | Completed | 1 |  |  | 17DF0091B
NC 2017 | SHS | Region IV-A | Cavite City | 301484 | Cavite National High School | CAVITE CITY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 48451608.68 |  |  | Completed | 1 |  |  |  | 17Df0140 |  |  | 2017-10-26 | 2017-12-06 | 2017-12-15 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Cavite City | 301485 | Sangley Point NHS | CAVITE CITY | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 21379508.64 |  |  | Completed | 1 |  |  |  | 17DF0139 |  |  | 2017-10-26 | 2017-12-06 | 2017-12-15 | Power K Const. Supply & Services
NC 2017 | K10 | Region IV-A | Dasmarinas | 107915 | Bautista ES | Dasmarinas | 4 | 1 | 8 | 4STY8CL | BATCH 7 | 17974428.44 |  |  | Completed | 1 |  |  |  | 17DQ0088 |  |  | 2017-10-13 | 2017-11-27 | 2017-11-27 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301183 | Dasmarinas East NHS | Dasmarinas | 4 | 1 | 20 | 4STY20CL | BATCH 7 | 41186654.43 |  |  | Completed | 1 |  |  |  | 17DQ0102 |  | 2017-10-05 | 2017-10-17 | 2017-11-24 | 2017-11-24 | Almakar Builders and Metal works
NC 2017 | SHS | Region IV-A | Dasmarinas | 301183 | Dasmarinas East NHS | Dasmarinas | 4 | 1 | 8 | 4STY8CL | BATCH 7 | 17974428.44 |  |  | Completed | 1 |  |  |  | 17DQ0087 |  | 2017-09-29 | 2017-12-07 | 2017-11-29 | 2017-11-29 | Almakar Builders and Metal works
NC 2017 | K10 | Region IV-A | Dasmarinas | 107917 | Dasmarinas II CS | Dasmarinas | 4 | 1 | 20 | 4STY20CL | BATCH 7 | 41111654.43 |  |  | Completed | 1 |  |  |  | 17DQ0100 |  | 2017-10-05 | 2017-10-17 | 2017-12-05 | 2017-12-05 | R.A. Del Rosario Construction
NC 2017 | K10 | Region IV-A | Dasmarinas | 107917 | Dasmarinas II CS | Dasmarinas | 4 |  | 20 | 4STY20CL | BATCH 7 | 41111654.43 |  |  | Completed | 1 |  |  |  | 17DQ0101 |  | 2017-10-05 | 2017-10-17 | 2017-12-05 | 2017-12-05 | R.A. Del Rosario Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301186 | Dasmarinas NHS | Dasmarinas | 4 | 1 | 24 | 4STY24CL | BATCH 7 | 47260828.91 |  |  | Completed | 1 |  |  |  | 17DQ0110 |  | 2017-10-09 | 2017-10-23 | 2017-12-15 | 2017-12-15 | KLDS Trading & Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301186 | Dasmarinas NHS | Dasmarinas | 4 | 1 | 20 | 4STY20CL | BATCH 7 | 39947573.18 |  |  | Completed | 1 |  |  |  | 17DQ0120 |  | 2017-10-13 | 2017-10-25 | 2017-12-15 | 2017-12-15 | KLDS Trading & Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301186 | Dasmarinas NHS | Dasmarinas | 4 | 1 | 28 | 4STY28CL | BATCH 7 | 53014557.01 |  |  | Completed | 1 |  |  |  | 17DQ0111 |  | 2017-10-09 | 2017-10-23 | 2017-12-15 | 2017-12-15 | KLDS Trading & Construction
NC 2017 | K10 | Region IV-A | Dasmarinas | 107900 | Delfin Jaranilla ES | Dasmarinas | 4 | 1 | 16 | 4STY16CL | BATCH 7 | 36727910.69 |  |  | Completed | 1 |  |  |  | 17DQ0093 |  | 2017-09-29 | 2017-10-13 | 2017-12-27 | 2017-12-07 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 328201 | Paliparan II NHS | Dasmarinas | 4 | 1 | 16 | 4STY16CL | BATCH 7 | 33805450.32 |  |  | Completed | 1 |  |  |  | 17DQ0115 |  | 2017-10-13 | 2017-10-25 | 2017-12-15 | 2017-12-15 | Omnicon builders
NC 2017 | SHS | Region IV-A | Dasmarinas | 328201 | Paliparan II NHS | Dasmarinas | 4 | 1 | 12 | 4STY12CL | BATCH 7 | 27893519.87 |  |  | Completed | 1 |  |  |  | 17DQ0113 |  | 2017-10-13 | 2017-10-25 | 2017-12-06 | 2017-12-15 | Omnicon builders
NC 2017 | K10 | Region IV-A | Imus City | 107980 | Alapan I ES | IMUS | 3 | 1 | 12 | 4STY12CL | BATCH 7 | 31901789.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107968 | Anabu I ES | IMUS | 3 | 1 | 12 | 4STY12CL | BATCH 7 | 31964789.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107970 | Bayan Luma I Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17348570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107970 | Bayan Luma I Elementary School | IMUS | 3 |  | 8 | 4STY8CL | BATCH 7 | 17348570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107971 | Bayan Luma II Elementary School | IMUS | 3 | 1 | 4 | 2STY4CL | BATCH 7 | 9197901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107972 | Buhay na Tubig Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17474570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 301196 | Imus NHS | IMUS | 3 | 1 | 20 | 4STY20CL | BATCH 7 | 41498409.74 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 301196 | Imus NHS | IMUS | 3 |  | 12 | 4STY12CL | BATCH 7 | 31874789.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107974 | Imus Pilot ES | IMUS | 3 | 1 | 15 | 3STY15CL | BATCH 7 | 34155689.69 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107979 | Tanzang Luma ES | IMUS | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17569070.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107979 | Tanzang Luma ES | IMUS | 3 |  | 8 | 4STY8CL | BATCH 7 | 17569070.67 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301265 | Alaminos National High School | ALAMINOS | 3 | 1 | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 7 | 37798952.72 |  |  | reverted | 0
NC 2017 | K10 | Region IV-A | Laguna | 108192 | San Agustin ES | ALAMINOS | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17877762.08 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108256 | Dayap ES | CALAUAN | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17652762.08 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108273 | Calminue ES | CAVINTI | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9520835.77 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108275 | Cavinti Elementary | CAVINTI | 4 | 1 | 6 | 3STY6CL | BATCH 7 | 13929932.17 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108279 | Paowin ES | CAVINTI | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9345029.5 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108327 | Longos ES | KALAYAAN | 4 | 1 | 8 | 4STY8CL | BATCH 7 | 17384440.5 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108331 | San Antonio ES | KALAYAAN | 4 | 1 | 12 | 4STY12CL | BATCH 7 | 31884422.74 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 7 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108317 | Luisiana CES | LUISIANA | 4 | 1 | 15 | 3STY15CL | BATCH 7 | 34202152.25 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108317 | Luisiana CES | LUISIANA | 4 |  | 15 | 3STY15CL | BATCH 7 | 34202152.25 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108317 | Luisiana CES | LUISIANA | 4 |  | 12 | 3STY12CL | BATCH 7 | 29818956.27 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 12 | 3STY12CL | BATCH 7 | 30546452.6 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 42836577.93 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 42836577.93 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108374 | Ibaba ES | PAETE | 4 | 1 | 6 | 3STY6CL | BATCH 7 | 14278782.43 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108379 | Dr. Augusto E. Hocson Elem. School | PAGSANJAN | 4 | 1 | 4 | 2STY4CL | BATCH 7 | 9186809.24 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108384 | FRANCISCO BENITEZ MEMORIAL SCHOOL | PAGSANJAN | 4 | 1 | 6 | 3STY6CL | BATCH 7 | 14086572.99 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108404 | Sulib ES | PANGIL | 4 | 1 | 9 | 3STY9CL | BATCH 7 | 24897783.92 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342346 | LAGUNA SENIOR HIGH SCHOOL | SANTA CRUZ (Capital) | 4 | 1 | 12 | 3STY12CL | BATCH 7 | 30200393.1 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342346 | LAGUNA SENIOR HIGH SCHOOL | SANTA CRUZ (Capital) | 4 |  | 12 | 3STY12CL | BATCH 7 | 30200393.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108448 | Santo Angel Central ES | SANTA CRUZ (Capital) | 4 | 1 | 6 | 2STY6CL | BATCH 7 | 12067729.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108448 | Santo Angel Central ES | SANTA CRUZ (Capital) | 4 |  | 6 | 2STY6CL | BATCH 7 | 12067729.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108460 | J. Santiago ES | SANTA MARIA | 4 | 1 | 6 | 3STY6CL | BATCH 7 | 14207486.32 |  |  | reverted | 0
NC 2017 | K10 | Region IV-A | Laguna | 108466 | Santa Maria ES | SANTA MARIA | 4 | 1 | 15 | 3STY15CL | BATCH 7 | 34621219.61 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108466 | Santa Maria ES | SANTA MARIA | 4 |  | 9 | 3STY9CL | BATCH 7 | 25189361.88 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108490 | Kapatalan ES | SINILOAN | 4 | 1 | 6 | 3STY6CL | BATCH 7 | 13936780.01 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301273 | Siniloan National High School | SINILOAN | 4 | 1 | 20 | 4STY20CL | BATCH 7 | 42268145.66 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301264 | San Francisco NHS | VICTORIA | 3 | 1 | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 7 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lipa City | 109658 | Abundio Torre MS | Lipa City | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37110266.55 |  |  | Completed | 1 |  |  |  | 17DD0259 |  |  |  | 2017-12-05 | 2017-12-13 | POWER K. CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | Lipa City | 109671 | Anilao ES | Lipa City | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31900109.55 |  |  | Completed | 1 |  |  |  | 17DD0260 |  |  |  | 2017-11-20 | 2017-11-28 | GREAT SWISS METAL BUILDERS CORP. | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 301486 | Anilao National High School | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17475000 |  |  | Completed | 1 |  |  |  | 17DD0261 |  |  |  | 2017-11-20 | 2017-11-28 | ROMAL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 109688 | Bagongpook ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17373298.33 |  |  | Completed | 1 |  |  |  | 17DD0262 |  |  |  | 2017-11-20 | 2017-11-28 | BERTO LUCCI BUILDERS AND SUPPLY
NC 2017 | SHS | Region IV-A | Lipa City | 301487 | Bolbok NHS | LIPA CITY | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37393500 |  |  | Completed | 1 |  |  |  | 17DD0263 |  |  |  | 2017-12-05 | 2017-12-13 | COORS CONSTRUCTION CO., INC.
NC 2017 | K10 | Region IV-A | Lipa City | 301488 | Bugtongnapulo NHS | LIPA CITY | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 32135500 |  |  | Completed | 1 |  |  |  | 17DD0264 |  |  |  | 2017-11-20 | 2017-11-28 | RUSMEN BUILDERS AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region IV-A | Lipa City | 109689 | Bulaklakan ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17410000 |  |  | Completed | 1 |  |  |  | 17DD0265 |  |  |  | 2017-11-20 | 2017-11-28 | GRANDY TRADING AND CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 109673 | Calamias ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17373298.33 |  |  | Completed | 1 |  |  |  | 17DD0266 |  |  |  | 2017-11-20 | 2017-11-28 | DELA ROSA CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region IV-A | Lipa City | 109690 | Duhatan ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17373298.33 |  |  | Completed | 1 |  |  |  | 17DD0267 |  |  |  | 2017-11-20 | 2017-11-28 | OIC CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Lipa City | 109644 | GAUDENCIO B. LONTOK MEMORIAL SCHOOL | Lipa City | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31900109.55 |  |  | Completed | 1 |  |  |  | 17DD0268 |  |  |  | 2017-11-20 | 2017-11-28 | VITALTECH CONSTRUCTION CORP.
NC 2017 | K10 | Region IV-A | Lipa City | 301494 | Lodlod National High School | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17507500 |  |  | Completed | 1 |  |  |  | 17DD0269 |  |  |  | 2017-12-13 | 2017-12-21 | BERTO LUCCI BUILDERS AND SUPPLY | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 301494 | Lodlod National High School | LIPA CITY | 6 |  | 8 | 4STY8CL | BATCH 7 | 17507500 |  |  | Completed | 1 |  |  |  | 17DD0270 |  |  |  | 2017-12-13 | 2017-12-21 | BERTO LUCCI BUILDERS AND SUPPLY | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 109663 | Lumbang ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17373298.33 |  |  | Completed | 1 |  |  |  | 17DD0271 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 301495 | Lumbang NHS | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17500000 |  |  | Completed | 1 |  |  |  | 17DD0272 |  |  |  | 2017-11-29 | 2017-12-07 | PRECIOUS CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 301495 | Lumbang NHS | LIPA CITY | 6 |  | 12 | 4STY12CL | BATCH 7 | 32218000 |  |  | Completed | 1 |  |  |  | 17DD0273 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 301495 | Lumbang NHS | LIPA CITY | 6 |  | 20 | 4STY20CL | BATCH 7 | 41999500 |  |  | Completed | 1 |  |  |  | 17DD0274 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 109693 | Padre Valerio Malabanan MS | Lipa City | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41791536.47 |  |  | Completed | 1 |  |  |  | 17DD0214 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 109695 | Paninsingin ES | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17400000 |  |  | Completed | 1 |  |  |  | 17DD0229 |  |  |  | 2017-11-20 | 2017-11-28 | DELA ROSA CONSTRUCTION AND DEVELOPMENT CORPORATION
NC 2017 | K10 | Region IV-A | Lipa City | 109696 | Pinagtongulan ES | Lipa City | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31900109.55 |  |  | Completed | 1 |  |  |  | 17DD0204 |  |  |  | 2017-11-20 | 2017-11-28 | OIC CONSTRUCTION AND SUPPLY
NC 2017 | SHS | Region IV-A | Lipa City | 301497 | Pinagtongulan NHS | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17400000 |  |  | Completed | 1 |  |  |  | 17DD0230 |  |  |  | 2017-11-20 | 2017-11-28 | OIC CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Lipa City | 301498 | Rizal NHS | LIPA CITY | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17400000 |  |  | Completed | 1 |  |  |  | 17DD0228 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 301498 | Rizal NHS | LIPA CITY | 6 |  | 12 | 4STY12CL | BATCH 7 | 32045500 |  |  | Completed | 1 |  |  |  | 17DD0205 |  |  |  | 2017-11-20 | 2017-11-28 | PRECIOUS CONSTRUCTION
NC 2017 | SHS | Region IV-A | Lipa City | 301499 | San Celestino NHS | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17400000 |  |  | Completed | 1 |  |  |  | 17DD0227 |  |  |  | 2017-11-20 | 2017-11-28 | ROMAL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Lipa City | 109652 | San Isidro ES | Lipa City | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37190266.55 |  |  | Completed | 1 |  |  |  | 17DD0255 |  |  |  | 2017-12-05 | 2017-12-13 | URBAN CONSOLIDATED CONTRACTORS PHILS. INC.
NC 2017 | K10 | Region IV-A | Lipa City | 301500 | San Isidro NHS (Formerly Sapac NHS) | LIPA CITY | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 32037500 |  |  | Completed | 1 |  |  |  | 17DD0206 |  |  |  | 2017-11-20 | 2017-11-28 | VITALTECH CONSTRUCTION CORP.
NC 2017 | K10 | Region IV-A | Lipa City | 109653 | San Jose ES | Lipa City | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37433500 |  |  | Completed | 1 |  |  |  | 17DD0256 |  |  |  | 2017-12-05 | 2017-12-13 | URBAN CONSOLIDATED CONTRACTORS PHILS. INC.
NC 2017 | K10 | Region IV-A | Lipa City | 109687 | San Sebastian ES | Lipa City | 6 | 1 | 12 | 4STY12CL | BATCH 7 | 31900109.55 |  |  | Completed | 1 |  |  |  | 17DD0202 |  |  |  | 2017-11-20 | 2017-11-28 | VITALTECH CONSTRUCTION CORP.
NC 2017 | K10 | Region IV-A | Lipa City | 109677 | Sen. Claro M. Recto MS (Lipa City South CS) | LIPA CITY | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41379000 |  |  | Completed | 1 |  |  |  | 17DD0240 |  |  |  | 2017-11-27 | 2017-12-07 | JASMIG CONSTRUCTION CORPORATION
NC 2017 | K10 | Region IV-A | Lipa City | 109668 | Talisay ES | Lipa City | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37190266.55 |  |  | Completed | 1 |  |  |  | 17DD0258 |  |  |  | 2017-12-05 | 2017-12-13 | POWER K. CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | Lipa City | 109703 | Tambo ES | Lipa City | 6 | 1 | 20 | 4STY20CL | BATCH 7 | 41379000 |  |  | Completed | 1 |  |  |  | 17DD0215 |  |  |  | 2017-11-20 | 2017-11-28 | JASMIG CONSTRUCTION CORPORATION
NC 2017 | K10 | Region IV-A | Lipa City | 109669 | Teodoro M. Kalaw MS | LIPA CITY | 6 | 1 | 16 | 4STY16CL | BATCH 7 | 37433500 |  |  | Completed | 1 |  |  |  | 17DD0254 |  |  |  | 2017-12-05 | 2017-12-13 | POWER K. CONSTRUCTION SUPPLY AND SERVICES | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lipa City | 109706 | Tibig ES | Lipa City | 6 | 1 | 8 | 4STY8CL | BATCH 7 | 17425000 |  |  | Completed | 1 |  |  |  | 17DD0241 |  |  |  | 2017-11-27 | 2017-12-07 | LIBRIUS CONSTRUCTION AND SUPPLY CORPORATION
NC 2017 | K10 | Region IV-A | Lucena City | 109717 | Gulang-gulang Elementary School | LUCENA CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18098791.62 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City |  | Gulang-gulang NHS- Domoit Extension | LUCENA CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 7 | 27108727.1 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Lucena City | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18144482.23 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City |  | Lucena City SHS (Stand Alone) Silangan Mayao | LUCENA CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 50182692.09 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109745 | Lucena West IV ES | LUCENA CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10651808.24 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109745 | Lucena West IV ES | LUCENA CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10651808.24 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 301321 | Ellas A. Salvador NHS | Agdangan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0127 | 2017-10-06 | 2017-10-13 | 2017-10-25 | 2017-11-07 | 2017-11-10 | JOJR CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301296 | Buenavista NHS | Buenavista | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10433430.91 |  |  | Completed | 1 |  |  |  | 17DM0134 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301296 | Buenavista NHS | Buenavista | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0134 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301296 | Buenavista NHS | Buenavista | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0134 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 308014 | Cabong NHS | Buenavista | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0128 | 2017-10-06 | 2017-10-13 | 2017-10-25 | 2017-11-07 | 2017-11-10 | JOJR CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | Buenavista | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | I A BOSQUE CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | Buenavista | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | I A BOSQUE CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108637 | Candelaria ES, Main | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10842552.03 |  |  | Completed | 1 |  |  |  | 17DJ0064 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 308016 | Dolores Macasaet National High School | CANDELARIA | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18188146.25 |  |  | Completed | 1 |  |  |  | 17DJ0051 | [5 empty] | ST. TIMOTHY CONTS. CORP
NC 2017 | K10 | Region IV-A | Quezon | 108622 | Mangilag Sur ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10694978.06 |  |  | Completed | 1 |  |  |  | 17DJ0074 | [5 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region IV-A | Quezon | 108622 | Mangilag Sur ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10694978.06 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Quezon | 301403 | Sta. Catalina National High School | CANDELARIA | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18207723.56 |  |  | Completed | 1 |  |  |  | 17DJ0053 | [5 empty] | RTY CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301311 | Doongan Ilaya National High School | Catanauan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0130 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301311 | Doongan Ilaya National High School | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0130 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | Catanauan | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10014378.6 |  |  | Completed | 1 |  |  |  | 17DM0131 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0131 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0131 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301401 | San Roque NHS, Catanauan | Catanauan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301401 | San Roque NHS, Catanauan | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS-Tagabas Ibaba Ext.) | Catanauan | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10014378.6 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301392 | Tagabas Ibaba NHS (Formerly San Isidro NHS-Tagabas Ibaba Ext.) | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya ES) | Catanauan | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10014378.6 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya ES) | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0136 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | K10 | Region IV-A | Quezon | 108674 | Bulakin ES | DOLORES | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 16772545.1 |  |  | Completed | 1 |  |  |  | 17DJ0083 | [5 empty] | RTY CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES | 2 | 1 | 12 | 3STY12CL | BATCH 7 | 32431588.4 |  |  | Completed | 1 |  |  |  | 17DJ0067 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108677 | Dolores CS | DOLORES | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10797292.76 |  |  | Completed | 1 |  |  |  | 17DJ0089 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108677 | Dolores CS | DOLORES | 2 |  | 4 | 2STY4CL | BATCH 7 | 10797292.76 |  |  | Completed | 1 |  |  |  | 17DJ0081 | [5 empty] | MGDJ CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108676 | Dolores CS Annex | DOLORES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2869000 |  |  | Completed | 1 |  |  |  | 17DJ0086 | [5 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region IV-A | Quezon | 108676 | Dolores CS Annex | DOLORES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2869000 |  |  | Completed | 1 |  |  |  | 17DJ0045 | [5 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region IV-A | Quezon | 108683 | Pinagdanlayan ES | DOLORES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2867680.15 |  |  | Completed | 1 | [9 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region IV-A | Quezon | 108683 | Pinagdanlayan ES | DOLORES | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2867680.15 |  |  | Completed | 1 |  |  |  | 17DJ0044 | [5 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | TVL | Region IV-A | Quezon | 301354 | Malaya NHS | General Luna | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10014378.6 |  |  | Completed | 1 |  |  |  | 17DM0137 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | I A BOSQUE CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301354 | Malaya NHS | General Luna | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0137 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | I A BOSQUE CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301393 | San Isidro NHS, Gen. Luna | General Luna | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0138 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301393 | San Isidro NHS, Gen. Luna | General Luna | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0138 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | SOUTH BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 301502 | Quezon National High School | LUCENA CITY (Capital) | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 35901645.35 |  |  | Completed | 1 |  |  |  | 17DJ0097
NC 2017 | TVL | Region IV-A | Quezon | 301303 | Calantas NHS | Macalelon | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0139 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301303 | Calantas NHS | Macalelon | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0139 | 2017-10-18 | 2017-10-25 | 2017-11-06 | 2017-11-15 | 2017-11-20 | M.G SALAZAR/ MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301360 | Olongtao National High School | Macalelon | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10014378.6 |  |  | Completed | 1 |  |  |  | 17DM0132 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301360 | Olongtao National High School | Macalelon | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0132 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301360 | Olongtao National High School | Macalelon | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0132 | 2017-10-11 | 2017-10-18 | 2017-10-30 | 2017-11-08 | 2017-11-15 | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | Mulanay | 3 | 1 | 2 | 2 Storey 2 Unit Workshop | BATCH 7 | 10133726.96 |  |  | Completed | 1 |  |  |  | 17DM0140 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | Mulanay | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0140 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | Mulanay | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0140 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | Mulanay | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0140 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301329 | Ilayang Yuni NHS | Mulanay | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0141 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301329 | Ilayang Yuni NHS | Mulanay | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0141 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301330 | Pakiing National High School | Mulanay | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0141 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 308023 | Danlagan NHS (Formerly Kinagunan Ibaba NHS Ext. Classes) | Padre Burgos | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0142 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 308023 | Danlagan NHS (Formerly Kinagunan Ibaba NHS Ext. Classes) | Padre Burgos | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0142 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301330 | Cabulihan NHS | Pitogo | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0129 | [5 empty] | RGP BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301376 | Pitogo Community High School | Pitogo | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0133 | [5 empty] | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301376 | Pitogo Community High School | Pitogo | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0133 | [5 empty] | RCEL/QVLGC
NC 2017 | TVL | Region IV-A | Quezon | 301280 | Abuyon NHS | San Narciso | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0143 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301280 | Abuyon NHS | San Narciso | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0143 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301399 | Godofredo M. Tan Memorial School of Arts and Trades | San Narciso | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0144 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301399 | Godofredo M. Tan Memorial School of Arts and Trades | San Narciso | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0144 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | San Narciso | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0144 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301322 | Gregorio Reyes NHS | San Narciso | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 7 | 15812378.66 |  |  | Completed | 1 |  |  |  | 17DM0144 | [5 empty] | SOUTH BUILDERS
NC 2017 | SHS | Region IV-A | Quezon | 308020 | GOV. ANACLETO C. ALCALA NATIONAL HIGH SCHOOL | SARIAYA | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 16574753.33 |  |  | Completed | 1 |  |  |  | 17DJ0071 | [5 empty] | DQT BUILDERS CORP
NC 2017 | SHS | Region IV-A | Quezon | 301349 | Lutucan National High Scool | SARIAYA | 2 | 1 | 9 | 3STY9CL | BATCH 7 | 27416273.14 |  |  | Completed | 1 |  |  |  | 17DJ0066 | [5 empty] | DQT BUILDERS CORP/ JSP CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109165 | Mamala ES | SARIAYA | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 13994505.72 |  |  | Completed | 1 |  |  |  | 17DJ0059 | [5 empty] | AM ABDON CONSTRUCTION AND SUPPLIES
NC 2017 | K10 | Region IV-A | Quezon | 109164 | Manuel L. Quezon ES | SARIAYA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 5017170.22 |  |  | Completed | 1 |  |  |  | 17DJ0046 | [5 empty] | BOMEL CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109169 | Sariaya East Central Main ES | SARIAYA | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10591287.22 |  |  | Completed | 1 |  |  |  | 17DJ0082 | [5 empty] | SOUTHER DAWN DEVELOPMENT COMPANY
NC 2017 | K10 | Region IV-A | Quezon | 109269 | Bulakin Elementary School | TIAONG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10535521.76 |  |  | Completed | 1 |  |  |  | 17DJ0069 | [5 empty] | N.M PARAFINA BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 109272 | Claro M. Recto Mem. CS | TIAONG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10700201.91 |  |  | Completed | 1 |  |  |  | 17DJ0070 | [5 empty] | SOUTHER DAWN DEVELOPMENT COMPANY
NC 2017 | K10 | Region IV-A | Quezon | 109278 | Lusacan ES | TIAONG | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 10371211.76 |  |  | Completed | 1 |  |  |  | 17DJ0073 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301380 | Recto MNHS | TIAONG | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 20278243.4 |  |  | Completed | 1 |  |  |  | 17DJ0055 | [5 empty] | I A BOSQUE CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109290 | Tiaong East ES | TIAONG | 2 | 1 | 6 | 2STY6CL | BATCH 7 | 13566403.02 |  |  | Completed | 1 |  |  |  | 17DJ0061 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Rizal | 109307 | Angono ES | ANGONO | 1 | 1 | 16 | 4STY16CL | BATCH 7 | 36910737.96 |  |  | Completed | 1 |  |  | P00175573LZ | 17DN0165 | 2017-10-20 | 2017-10-27 | 2017-11-09 | 2017-11-24 | 2017-12-06 | C.F. TRINIDAD CONSTRUCTION AND SUPPLIES CORP.
NC 2017 | SHS | Region IV-A | Rizal | 301433 | Carlos "Botong" V. Francisco MNHS | ANGONO | 1 | 1 | 4 | 2STY4CL | BATCH 7 | 8945901.76 |  |  | Completed | 1 |  |  | P00175575LZ | 17DN0136 |  | 2017-10-06 | 2017-10-19 | 2017-11-09 | 2017-11-16 | FRAMECON BUILDERS
NC 2017 | K10 | Region IV-A | Rizal | 109313 | Joaquin Guido ES (Angono ES Unit I) | ANGONO | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 41408409.74 |  |  | Completed | 1 |  |  | P00175574LZ | 17DN0172 | 2017-10-27 | 2017-11-03 | 2017-11-16 | 2017-12-06 | 2017-12-15 | EL-JAKE BUILDERS/SUPREME ABF CONST. & CONST. SUPPLY CO. INC.(Joint Venture)
NC 2017 | K10 | Region IV-A | Rizal | 109308 | Bilibiran ES | BINANGONAN | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17159570.67 |  |  | Completed | 1 |  |  | P00175576LZ | 17DN0155 | 2017-10-06 | 2017-10-13 | 2017-10-27 | 2017-11-15 | 2017-11-23 | PACIFIC SUMMIT CONSTRUCTION GROUP, INC.
NC 2017 | K10 | Region IV-A | Rizal | 109367 | Darangan ES | BINANGONAN | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17159570.67 |  |  | Completed | 1 |  |  | P00175577LZ | 17DN0154 | 2017-10-06 | 2017-10-13 | 2017-10-27 | 2017-11-15 | 2017-11-23 | JRD-D2 ENTERPRISES
NC 2017 | K10 | Region IV-A | Rizal | 308110 | Francisco P. Felix MNHS - Karangalan Annex | CAINTA | 1 | 1 | 6 | 3STY6CL | BATCH 7 | 13739515.1 |  |  | Completed | 1 |  |  | P00175578LZ | 17DN0137 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-11-09 | 2017-11-16 | HEXAMINDZ CORPORATION | minor defects not yet complied by the contractor
NC 2017 | K10 | Region IV-A | Rizal | 109466 | Eulogio Rodriguez Jr. ES | Rodriguez (Montalban) | 2 | 1 | 16 | 4STY16CL | BATCH 7 | 38538185.39 |  |  | Completed | 1 |  |  | P00175583LZ-CW1 | 17D00152 | 2017-12-01 | 2017-12-08 | 2017-12-21 | 2017-12-27 | 2018-01-03 | ST.TIMOTHY CONST. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109466 | Eulogio Rodriguez Jr. ES | Rodriguez (Montalban) | 2 |  | 20 | 4STY20CL | BATCH 7 | 43344413.42 |  |  | Completed | 1 |  |  | P00175584LZ-CW1 | 17D00136 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-18 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109466 | Eulogio Rodriguez Jr. ES | Rodriguez (Montalban) | 2 |  | 20 | 4STY20CL | BATCH 7 | 43344413.42 |  |  | Completed | 1 |  |  | P00175585LZ-CW1 | 17D00137 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-18 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 301439 | Gen. Licerio Geronimo NHS | Rodriguez (Montalban) | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 44979413.42 |  |  | Completed | 1 |  |  | P00175590LZ-CW1 | 17D00143 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-03 | ROGENOX CONST. & SUPPLY CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109467 | Geronimo ES | Rodriguez (Montalban) | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18888520.6 |  |  | Completed | 1 |  |  | P00175586LZ-CW1 | 17D00135 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-18 | ROGENOX CONST. & SUPPLY CORP.
NC 2017 | SHS | Region IV-A | Rizal | 342562 | Kasiglahan Village Senior High School | Rodriguez (Montalban) | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 14371998.91 |  |  | Completed | 1 |  |  | P00175592LZ-CW1 | 17D00134 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-20 | C.L. MORALES CONST. & TRADING
NC 2017 | K10 | Region IV-A | Rizal | 109471 | Manggahan ES | Rodriguez (Montalban) | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 45030149.81 |  |  | Completed | 1 |  |  | P00175594LZ-CW1 | 17D00144 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-03 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109477 | San Isidro ES | Rodriguez (Montalban) | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 44436979.34 |  |  | Completed | 1 |  |  | P00175587LZ-CW1 | 17D00145 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-03 | SARCA ESTATE & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109478 | San Jose ES | Rodriguez (Montalban) | 2 | 1 | 20 | 4STY20CL | BATCH 7 | 44954083.91 |  |  | Completed | 1 |  |  | P00175588LZ-CW1 | 17D00138 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-18 | ST. TIMOTHY CONST. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109479 | San Rafael ES | Rodriguez (Montalban) | 2 | 1 | 12 | 4STY12CL | BATCH 7 | 34377323.64 |  |  | Completed | 1 |  |  | P00175589LZ-CW1 | 17D00141 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-11 | 2018-01-03 | HONEYVILLE CONST.
NC 2017 | SHS | Region IV-A | Rizal | 342567 | Southville 8B Senior High School | Rodriguez (Montalban) | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18088140.27 |  |  | Completed | 1 |  |  | P00175593LZ-CW1 | 17D00132 | 2017-10-27 | 2017-11-03 | 2017-11-17 | 2017-11-29 | 2017-12-08 | M.J. APIN BUILDERS
NC 2017 | K10 | Region IV-A | Rizal | 308135 | Southville 8C NHS | Rodriguez (Montalban) | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 15154764.97 |  |  | Completed | 1 |  |  | P00175591LZ-CW1 | 17D00129 | 2017-10-27 | 2017-11-03 | 2017-11-17 | 2017-11-29 | 2017-12-08 | ALPHA & OMEGA GEN. CONTRACTORS & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109488 | Gulod Malaya ES | San Mateo | 2 | 1 | 16 | 4STY16CL | BATCH 7 | 38688185.39 |  |  | Completed | 1 |  |  | P00175598LZ-CW1 | 17D00142 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-03 | JEPA CONST. & DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109489 | Justice Vicente Santiago ES | San Mateo | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 14700312.48 |  |  | Completed | 1 |  |  | P00175595LZ-CW1 | 17D00127 | 2017-10-27 | 2017-11-03 | 2017-11-16 | 2017-12-11 | 2017-12-20 | R.F. DIAZ CONST.
NC 2017 | K10 | Region IV-A | Rizal | 109491 | Malanday ES | San Mateo | 2 | 1 | 4 | 2STY4CL | BATCH 7 | 9880255.44 |  |  | Completed | 1 |  |  | P00175599LZ-CW1 | 17D00125 | 2017-10-07 | 2017-10-13 | 2017-10-26 | 2017-11-08 | 2017-11-21 | R.F. TARUC CONST.
NC 2017 | K10 | Region IV-A | Rizal | 109494 | San Mateo ES | San Mateo | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 14952724.67 |  |  | Completed | 1 |  |  | P00175596LZ-CW1 | 17D00131 | 2017-10-27 | 2017-11-03 | 2017-11-23 | 2017-11-29 | 2017-12-08 | R.F. DIAZ CONST.
NC 2017 | K10 | Region IV-A | Rizal | 109495 | Silangan ES (Labahan ES) | San Mateo | 2 | 1 | 8 | 4STY8CL | BATCH 7 | 18822386.26 |  |  | Completed | 1 |  |  | P00175597LZ-CW1 | 17D00128 | 2017-10-27 | 2017-11-03 | 2017-11-16 | 2017-11-27 | 2017-12-08 | ST. TIMOTHY CONST. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109496 | Sto. Niño ES | San Mateo | 2 | 1 | 6 | 3STY6CL | BATCH 7 | 14859419.51 |  |  | Completed | 1 |  |  | P00175600LZ-CW1 | 17D00130 | 2017-10-07 | 2017-10-13 | 2017-10-26 | 2017-11-08 | 2017-11-21 | VERET CONST.
NC 2017 | K10 | Region IV-A | Rizal | 308108 | Antonio C. Esguerra Mem. NHS | TAYTAY | 1 | 1 | 20 | 4STY20CL | BATCH 7 | 50999786.96 |  |  | Completed | 1 |  |  | P00175579LZ | 17DN0173 | 2017-10-20 | 2017-11-03 | 2017-11-16 | 2017-12-05 | 2017-12-15 | MICLOVER GENERAL CONSTRUCTION AND IRON WORKS
NC 2017 | K10 | Region IV-A | Rizal | 109537 | Bagong Pag-Asa ES (San Juan B Floodway ES) | TAYTAY | 1 | 1 | 16 | 4STY16CL | BATCH 7 | 45316486.165 |  |  | Completed | 1 |  |  | P00175580LZ | 17DN0166 | 2017-10-20 | 2017-10-27 | 2017-11-09 | 2017-11-24 | 2017-12-06 | UNIMASTERS CONGLOMERATION INC.
NC 2017 | K10 | Region IV-A | Rizal | 109537 | Bagong Pag-Asa ES (San Juan B Floodway ES) | TAYTAY | 1 |  | 16 | 4STY16CL | BATCH 7 | 45316486.165 |  |  | Completed | 1 |  |  | P00175581LZ | 17DN0167 | 2017-10-20 | 2017-10-27 | 2017-11-09 | 2017-11-24 | 2017-12-06 | UNIMASTERS CONGLOMERATION INC.
NC 2017 | SHS | Region IV-A | Rizal | 342569 | Taytay Senior High School | TAYTAY | 1 | 1 | 8 | 4STY8CL | BATCH 7 | 17640803.49 |  |  | Completed | 1 |  |  | P00175582LZ | 17DN0174 | 2017-10-27 | 2017-11-03 | 2017-11-16 | 2017-12-05 | 2017-12-15 | MICLOVER GENERAL CONSTRUCTION AND IRON WORKS
NC 2017 | K10 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 17952762.08 |  |  | Completed | 1 |  |  | P00175603LZ_CW1 | 17DP0089 | 2017-10-11 | 2017-10-20 | 2017-11-02 | 2017-11-13 | 2017-11-16 | R'CEL GEN. CONTRACTOR & GEN. MERCHANDISE
NC 2017 | K10 | Region IV-A | San Pablo City | 109760 | Magcaseville Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 7 | 32957785.51 |  |  | Completed | 1 |  |  | P00175604LZ_CW1 | 17DP0077 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-11-13 | 2017-11-16 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109795 | San Antonio I Elementary School | SAN PABLO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 18177762.08 |  |  | Completed | 1 |  |  | P00175605LZ_CW1 | 17DP0080 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-11-13 | 2017-11-16 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | San Pablo City | 109772 | San Mateo Elementary School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 7 | 14614305.4 |  |  | Completed | 1 |  |  | P00175606LZ_CW1 | 17DP0108 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | San Pablo City | 109791 | San Pablo Central Elementary School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 7 | 25857408.68 |  |  | Completed | 1 |  |  | P00175607LZ_CW1 | 17DP0090 | 2017-10-11 | 2017-10-20 | 2017-11-02 | 2017-11-13 | 2017-11-16 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | San Pablo City | 109791 | San Pablo Central Elementary School | SAN PABLO CITY | 3 |  | 9 | 3STY9CL | BATCH 7 | 25332408.68 |  |  | Completed | 1 |  |  | P00175608LZ_CW1 | 17DP0086 | 2017-09-27 | 2017-10-04 | 2017-10-18 | 2017-11-13 | 2017-11-16 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | TVL | Region IV-A | San Pablo City | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 | 1 | 8 | 4STY REG. WORKSHOP | BATCH 7 | 37060737.96 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | San Pablo City | 301509 | Santisimo Rosario National High School | SAN PABLO CITY | 3 | 1 | 8 | 4STY REG. WORKSHOP | BATCH 7 | 37060737.96 |  |  | Completed | 1 |  |  | P00175602LZ_CW1 | 17DP0116 | 2017-11-15 | 2017-11-24 | 2017-12-07 | 2017-12-12 | 2017-12-15 | R.V. LABORTE BUILDERS
NC 2017 | K10 | Region IV-A | Tanauan City | 107756 | Cale Elementary School | CITY OF TANAUAN | 3 | 1 | 8 | 2STY8CL | BATCH 7 | 17582424.26 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 107760 | Janopol ES | CITY OF TANAUAN | 3 | 1 | 6 | 2STY6CL | BATCH 7 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 107780 | Paaralang Sentral ng Talaga | CITY OF TANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 7 | 8970901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 107770 | Pagaspas ES | CITY OF TANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 7 | 9287218.76 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Tanauan City | 301133 | Pantay NHS | CITY OF TANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 7 | 8995901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 107781 | Tanauan North CS | CITY OF TANAUAN | 3 | 1 | 12 | 3STY12CL | BATCH 7 | 29359267.25 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Tanauan City | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 |  | 16 | 4STY16CL | BATCH 7 | 21720767.67 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Tanauan City | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 | 1 | 8 | 4STY8CL | BATCH 7 | 21720767.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | BIÑAN CITY | 108213 | Biñan ES | CITY OF BIÑAN | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 38339521.08 |  |  | Completed | 1 |  |  |  | 17DI0130 | 2017-11-23 | 2017-11-23 | 2017-12-07 | 2017-12-21 | 2017-12-28 | MICLOVER
NC 2017 | K10 | Region IV-A | BIÑAN CITY | 108216 | Canlalay ES | CITY OF BIÑAN | 1 | 1 | 28 | 4STY20CL & 4STY8CL | BATCH 10 | 70568940.12 |  |  | Completed | 1 |  |  |  | 17DI0124 | 2017-11-17 | 2017-11-17 | 2017-12-01 | 2017-12-21 | 2017-12-28 | 806 BUILDERS
NC 2017 | K10 | Region IV-A | BIÑAN CITY | 307901 | Jacobo Z. Gonzales Memorial National High School | CITY OF BIÑAN | 1 | 1 | 28 | 4STY20CL & 4STY8CL | BATCH 10 | 68041245.96 |  |  | Completed | 1 |  |  |  | 17DI0123 | 2017-11-12 | 2017-11-12 | 2017-12-01 | 2017-12-21 | 2017-12-28 | SBR
NC 2017 | K10 | Region IV-A | BIÑAN CITY | 164513 | Malaban East ES | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 17199861.43 |  |  | Completed | 1 |  |  |  | 17DI0133 | 2017-12-04 | 2017-12-04 | 2017-12-15 | 2017-12-21 | 2017-12-28 | POWER K
NC 2017 | K10 | Region IV-A | BIÑAN CITY | 108228 | San Francisco ES | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 23560701.25 |  |  | Completed | 1 |  |  |  | 17DI0134 | 2017-12-04 | 2017-12-04 | 2017-12-15 | 2017-12-21 | 2017-12-28 | POWER K
NC 2017 | SHS | Region IV-A | BIÑAN CITY | 307934 | SOUTHVILLE 5-A NATIONAL HIGH SCHOOL | CITY OF BIÑAN | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 38104521.08 |  |  | Completed | 1 |  |  |  | 17DI0129 | 2017-11-23 | 2017-11-23 | 2017-12-07 | 2017-12-21 | 2017-12-28 | POWER K
NC 2017 | K10 | Region IV-A | Antipolo City | 109333 | Nazarene Ville ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17458600.86 |  |  | Completed | 1 |  |  |  | 17DN0180 |  |  | 2017-11-16 |  | 2017-12-21 | M.J. APIN BUILDERS
NC 2017 | K10 | Region IV-A | Antipolo City | 109354 | Pantay ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17585873.59 |  |  | Completed | 1 |  |  |  | 17DN0153 |  |  | 2017-10-27 |  | 2017-12-21 | EMIRAM CONST & SUPPLY
NC 2017 | K10 | Region IV-A | Antipolo City | 109336 | Peace Village ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17585873.59 |  |  | Completed | 1 |  |  |  | 17DN0156 |  |  | 2017-10-27 |  | 2017-12-21 | KARPA BUILDERS
NC 2017 | K10 | Region IV-A | Antipolo City | 109357 | Rizza ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17267691.77 |  |  | Completed | 1 |  |  |  | 17DN0159 |  |  | 2017-10-27 |  | 2017-12-21 | KARPA BUILDERS
NC 2017 | K10 | Region IV-A | Antipolo City | 109359 | San Joseph ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17904055.4 |  |  | Completed | 1 |  |  |  | 17DN0160 |  |  | 2017-11-07 |  | 2017-12-21 | EMIRAM CONST & SUPPLY
NC 2017 | K10 | Region IV-A | Bacoor City | 107877 | Aniban CS | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 21874666.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 301171 | Bacoor NHS- Molino Main | Bacoor | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 41543627.55 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107878 | Bayanan ES | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 31746183.43 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107869 | Dulong Bayan ES | Bacoor | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 8945327.78 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107880 | Gov P.F. Espiritu ES | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 21874666.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107871 | Mabolo ES | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 21874666.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Bacoor City | 107890 | Talaba ES | Bacoor | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 21874666.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107207 | Bilibinwang ES | AGONCILLO | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2930062.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107213 | Subic ES | AGONCILLO | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 3171379.92 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 342200 | Alitagtag Senior High School | ALITAGTAG | 3 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107229 | Canda ES | BALAYAN | 1 | 1 | 4 | 2UNITS 1STY2CL | BATCH 10 | 5335491.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107249 | Juan C. de Lunas MES | BALAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9025901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107239 | Lanatan-Muntingtubig ES | BALAYAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11856168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107240 | Lucban ES | BALAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9095901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107240 | Lucban ES | BALAYAN | 1 |  | 4 | 2STY4CL | BATCH 10 | 9095901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107244 | Pook ES | BALAYAN | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9025901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107250 | Balete CS | BALETE | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301073 | Balete NHS | BALETE | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107251 | Looc ES | BALETE | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2663745.92 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Batangas | 342201 | SHS within Palsara Elementary School | BALETE | 3 | 1 | 5 | 1STY5CL | BATCH 10 | 6172650.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107291 | Coral ni Bacal Elementary School | CALACA | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9035901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107295 | Lumbang Calzada PS | CALACA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107310 | Talisay School | CALACA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2693745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301153 | Dr. Juan A. Pastor MNHS (Talaibon NHS) | IBAAN | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13488220.35 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301164 | Wenceslao Trinidad MNHS | LAUREL | 3 | 1 | 3 | 1STY3CL | BATCH 10 | 4614729.21 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107385 | Arumahan ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11886168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107404 | Dita ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107413 | Mahayahay ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11956168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107418 | Payapa ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9120901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107418 | Payapa ES | LEMERY | 1 |  | 4 | 2STY4CL | BATCH 10 | 9120901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107419 | Payapa Ibaba ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9125901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107423 | San Isidro Itaas ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9145901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107393 | Tubuan ES | LEMERY | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2693745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107397 | Bagong Pook ES | LIAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11736168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107408 | Kapito ES | LIAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107412 | Luyahan ES | LIAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11856168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107422 | San Diego ES | LIAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11856168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 163514 | San Pedro I Elementary School | MALVAR | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107491 | Aga ES | NASUGBU | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 13998515.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107494 | Banilad ES | NASUGBU | 1 | 1 | 3 | 1STY3CL | BATCH 10 | 3868435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107494 | Banilad ES | NASUGBU | 1 |  | 3 | 1STY3CL | BATCH 10 | 3868435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107495 | Bayabasan ES | NASUGBU | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11906168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107497 | Bulihan Elementary School | NASUGBU | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107500 | Catandaan ES | NASUGBU | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9075901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107506 | Latag ES | NASUGBU | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2703745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107507 | Looc ES | NASUGBU | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 2703745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107511 | Nasugbu East Central School | NASUGBU | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107511 | Nasugbu East Central School | NASUGBU | 1 |  | 4 | 2STY4CL | BATCH 10 | 9045901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107514 | Pantalan ES | NASUGBU | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11656168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107518 | Tala ES | NASUGBU | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301129 | Padre Garcia NHS | PADRE GARCIA | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13488220.35 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107544 | Bayawang ES | ROSARIO | 4 | 1 | 8 | 2STY8CL | BATCH 10 | 18500000 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301082 | Baybayin NHS | ROSARIO | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13458220.35 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301105 | Itlugan Senior High School | ROSARIO | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13458220.35 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301139 | Rosario NHS | ROSARIO | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13680268.35 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 307714 | Dr. Bonifacio A. Masilungan National High School | SAN JOSE | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13438220.35 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301155 | Taysan NHS | SAN JOSE | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13503220.35 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301090 | Buhaynasapa NHS | SAN JUAN | 4 | 1 | 8 | 4STY REG. WORKSHOP | BATCH 10 | 18702955.21 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301090 | Buhaynasapa NHS | SAN JUAN | 4 |  | 2 | 2STY REG. WORKSHOP | BATCH 10 | 7024908.06 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301108 | Laiya NHS | SAN JUAN | 4 | 1 | 8 | 4STY REG. WORKSHOP | BATCH 10 | 18702955.21 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Batangas | 301130 | Palahanan NHS | SAN JUAN | 4 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 13589866.35 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107661 | Bangin ES | SAN NICOLAS | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 2880062.92 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 301114 | Maabud National High School | SAN NICOLAS | 3 | 1 | 2 | 1STY2CL | BATCH 10 | 3088221.42 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107723 | Balisong Elementary School | TAAL | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107726 | Carmino Biscocho MES | TAAL | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 24818047.73 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107729 | Halang ES | TAAL | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11806168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107732 | Latag ES | TAAL | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 11906168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107840 | Amuyong ES | ALFONSO | 8 | 1 | 8 | 4STY8CL | BATCH 10 | 17169500 |  |  | Completed | 1 |  |  | 17DG0073 | [6 empty] | N.V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 107846 | Marahan ES | ALFONSO | 8 | 1 | 8 | 4STY8CL | BATCH 10 | 16943100 |  |  | Completed | 1 |  |  | 17DG0098 | [6 empty] | CBS Construction and Construction Supply
NC 2017 | K10 | Region IV-A | Cavite | 107850 | Pansin Elementary School | ALFONSO | 8 | 1 | 16 | 4STY16CL | BATCH 10 | 37350000 |  |  | Completed | 1 |  |  | 17DG0101 | [6 empty] | Hausland Construction
NC 2017 | K10 | Region IV-A | Cavite | 107853 | Sinaliw ES | ALFONSO | 8 | 1 | 12 | 4STY12CL | BATCH 10 | 33505000 |  |  | Completed | 1 |  |  | 17DG0096 | [6 empty] | Hausland Construction
NC 2017 | K10 | Region IV-A | Cavite | 107854 | Sulsugin ES | ALFONSO | 8 | 1 | 12 | 4STY12CL | BATCH 10 | 33707000 |  |  | Completed | 1 |  |  | 17DG0097 | [6 empty] | Hausland Construction
NC 2017 | K10 | Region IV-A | Cavite | 107855 | Taywanak ES | ALFONSO | 8 | 1 | 8 | 4STY8CL | BATCH 10 | 21156000 |  |  | Completed | 1 |  |  | 17DG0092 | [6 empty] | Metrics Construction & Trading
NC 2017 | SHS | Region IV-A | Cavite | 301217 | Talon National High School | Amadeo | 6 | 1 | 4 | 2STY4CL | BATCH 10 | 9008901.76 |  |  | Completed | 1 |  |  | 17DF0167A
NC 2017 | K10 | Region IV-A | Cavite | 107937 | Bulihan ES | GMA | 5 | 1 | 8 | 4STY8CL | BATCH 10 | 17932365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107940 | San Gabriel I ES | GMA | 5 | 1 | 12 | 4STY12CL | BATCH 10 | 31368955.14 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 107943 | San Jose ES | GMA | 5 | 1 | 20 | 4STY20CL | BATCH 10 | 41084817.75 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108007 | Bancod ES | INDANG | 7 | 1 | 8 | 4STY8CL | BATCH 10 | 17951850 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108009 | Buna Lejos ES | INDANG | 7 | 1 | 8 | 4STY8CL | BATCH 10 | 17951850 |  |  | Completed | 1 |  |  | 17DG0079 | [6 empty] | St. Gerald Construction, Gen. Contractor & Devt. Corp.
NC 2017 | K10 | Region IV-A | Cavite | 108009 | Buna Lejos ES | INDANG | 7 |  | 8 | 4STY8CL | BATCH 10 | 17951850 |  |  | Completed | 1 |  |  | 17DG0079
NC 2017 | K10 | Region IV-A | Cavite | 108012 | Dr. Alfredo Pio De Roda ES | INDANG | 7 | 1 | 6 | 3STY6CL | BATCH 10 | 14677100 |  |  | Completed | 1 |  |  | 17DG0082 | [6 empty] | Fe Reyes Gen. Contractor
NC 2017 | K10 | Region IV-A | Cavite | 107992 | Guyam ES | INDANG | 7 | 1 | 8 | 4STY8CL | BATCH 10 | 21156000 |  |  | Completed | 1 |  |  | 17DG0083 | [6 empty] | N. V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 107994 | Indang CES | INDANG | 7 | 1 | 8 | 4STY8CL | BATCH 10 | 23069906.1 |  |  | Completed | 1 |  |  | 17DG0084 | [6 empty] | Hausland Construction
NC 2017 | SHS | Region IV-A | Cavite | 301189 | Emiliano T. Tirona MNHS | KAWIT | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 41408409.74 |  |  | Completed | 1 |  |  | 17DF0162
NC 2017 | K10 | Region IV-A | Cavite | 108028 | Bendita ES | MAGALLANES | 8 | 1 | 12 | 4STY12CL | BATCH 10 | 31633000 |  |  | Completed | 1 |  |  | 17DG0095 | [6 empty] | N. V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 108036 | Urdaneta ES | MAGALLANES | 8 | 1 | 12 | 4STY12CL | BATCH 10 | 31633000 |  |  | Completed | 1 |  |  | 17DG0100 | [6 empty] | N. V. Avila Construction
NC 2017 | SHS | Region IV-A | Cavite | 342287 | Noveleta Senior High School | NOVELETA | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 17348570.67 |  |  | Completed | 1 |  |  | 17DF0145
NC 2017 | SHS | Region IV-A | Cavite | 301172 | Bagbag NHS | ROSARIO | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 41786409.74 |  |  | Completed | 1 |  |  | 17DF0150
NC 2017 | K10 | Region IV-A | Cavite | 108095 | Bagong Buhay ES | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 10 | 17932365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108098 | Biga ES | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 10 | 17857365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108098 | Biga ES | Silang | 5 |  | 8 | 4STY8CL | BATCH 10 | 17857365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108099 | Biluso ES | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 10 | 17932365.45 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301180 | Bulihan NHS | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 10 | 41084817.75 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301180 | Bulihan NHS | Silang | 5 |  | 8 | 4STY16CL | BATCH 10 | 33877393.59 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301193 | Gen. Vito Belarmino NHS | Silang | 5 | 1 | 4 | 4STY8CL | BATCH 10 | 17932365.45 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108108 | Maguyam ES | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 10 | 41084817.75 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108127 | Malabag ES | Silang | 5 | 1 | 8 | 4STY8CL | BATCH 10 | 17932365.45 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301205 | Munting Ilog NHS | Silang | 5 | 1 | 8 | 4STY16CL | BATCH 10 | 33877393.59 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Cavite | 108110 | Silang Central School | Silang | 5 | 1 | 20 | 4STY20CL | BATCH 10 | 41084817.75 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301218 | Tanza National Comprehensive High School | TANZA | 6 | 1 | 4 | 2STY4CL | BATCH 10 | 9250401.76 |  |  | Completed | 1 |  |  | 17DF0136A
NC 2017 | SHS | Region IV-A | Cavite City | 301484 | Cavite National High School | CAVITE CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 50325135.84 |  |  | Completed | 1 |  |  |  | 17DF0153 |  |  | 2018-12-19 | 2017-12-27 | 2018-01-03 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Cavite City | 301484 | Cavite National High School | CAVITE CITY | 1 |  | 12 | 4STY12CL | BATCH 10 | 44917187.6 |  |  | Completed | 1 |  |  |  | 17DF0164 |  |  | 2017-12-19 | 2017-12-27 | 2018-01-03 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Cavite City | 301484 | Cavite National High School | CAVITE CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 30279968.55 |  |  | Completed | 1 |  |  |  | 17DF0148 |  |  | 2017-12-19 | 2017-12-27 | 2018-01-03 | Baqprince Construction
NC 2017 | K10 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 42538772.62 |  |  | Completed | 1 |  |  |  | 17DF0152 |  |  | 2017-12-19 | 2017-12-27 | 2018-01-03 | Hexamindz Corporation
NC 2017 | K10 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 22736362.12 |  |  | Completed | 1 |  |  |  | 17DF0147 |  |  | 2017-12-19 | 2017-12-27 | 2018-01-03 | Fe S. Reyes Gen. Contractor
NC 2017 | K10 | Region IV-A | Cavite City | 109629 | Julian R. Felipe ES | CAVITE CITY | 1 |  | 8 | 4STY8CL | BATCH 10 | 22736362.12 |  |  | Completed | 1 |  |  |  | 17DF0147 |  |  | 2017-12-19 | 2017-12-27 | 2018-01-03 | Fe S. Reyes Gen. Contractor
NC 2017 | K10 | Region IV-A | Cavite City | 109632 | Ladislao Diwa ES | CAVITE CITY | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 47884608.68 |  |  | Completed | 1 |  |  |  | 17DF0165 |  |  | 2017-11-24 | 2017-12-01 | 2017-12-12 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301183 | Dasmarinas East NHS | Dasmarinas | 4 | 1 | 8 | 4STY8CL | BATCH 10 | 17974428.44 |  |  | Completed | 1 |  |  |  | 17DQ0138 |  | 2017-11-22 | 2017-12-07 | 2017-12-15 | 2018-01-03 | KLDS Trading & Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 301186 | Dasmarinas NHS | Dasmarinas | 4 | 1 | 20 | 4STY20CL | BATCH 10 | 1239081.25 |  |  | Completed | 1 |  |  |  | 17DQ0150 |  | 2017-12-27 | 2017-12-05 | 2017-12-29 | 2018-01-17 | KLDS Trading & Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 328201 | Paliparan II NHS | Dasmarinas | 4 | 1 | 16 | 4STY16CL | BATCH 10 | 2922460.37 |  |  | Completed | 1 |  |  |  | 17DQ0150 |  | 2017-12-27 | 2017-12-05 | 2017-12-29 | 2018-01-10 | Baqprince Construction
NC 2017 | SHS | Region IV-A | Dasmarinas | 328201 | Paliparan II NHS | Dasmarinas | 4 |  | 12 | 4STY12CL | BATCH 10 | 3401293.16 |  |  | Completed | 1 |  |  |  | 17DQ0150 |  | 2017-12-27 | 2017-12-05 | 2017-12-29 | 2018-01-10 | Baqprince Construction
NC 2017 | K10 | Region IV-A | Imus City | 107984 | E. Villanueva ES | IMUS | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17852570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino ES | IMUS | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 41678409.74 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino ES | IMUS | 3 |  | 20 | 4STY20CL | BATCH 10 | 41678409.74 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107985 | Gov. D. M. Camerino ES | IMUS | 3 |  | 8 | 4STY8CL | BATCH 10 | 17249570.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107974 | Imus Pilot ES | IMUS | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 41933409.74 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107974 | Imus Pilot ES | IMUS | 3 |  | 20 | 4STY20CL | BATCH 10 | 41933409.74 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107974 | Imus Pilot ES | IMUS | 3 |  | 8 | 4STY8CL | BATCH 10 | 17364320.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107974 | Imus Pilot ES | IMUS | 3 |  | 8 | 4STY8CL | BATCH 10 | 17364320.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107988 | Malagasang III ES | IMUS | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12286168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Imus City | 107988 | Malagasang III ES | IMUS | 3 |  | 6 | 2STY6CL | BATCH 10 | 12286168.02 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301265 | Alaminos National High School | ALAMINOS | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 38173952.72 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 307924 | Buenaventura E. Fandialan Memo. NHS | ALAMINOS | 3 | 1 | 8 | 4STY LAB | BATCH 10 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108194 | San Benito ES | ALAMINOS | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14464305.4 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108200 | Bay CS | BAY | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34454629.8 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301262 | Nicolas L. Galvez Memorial National High School | BAY | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 38883709.83 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | CABUYAO | 301235 | Cabuyao NHS - Casile NHS Annex | CABUYAO | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 19342664.81 |  |  | Completed | 1 |  |  |  | 17DI0112 | 2017-11-09 | 2017-11-16 | 2017-11-29 | 2017-12-21 | 2017-12-28 | Miclover
NC 2017 | K10 | Region IV-A | CABUYAO | 301259 | Pulo NHS (Birmingham Subdivision) | CABUYAO | 2 | 1 | 8 | 4STY16CL | BATCH 10 | 42446205.56 |  |  | Completed | 1 |  |  |  | 17DI0136 | 2017-11-25 |  | 2017-12-15 |  | 2017-12-28 | Alpha & Omega
NC 2017 | K10 | Region IV-A | Laguna | 108255 | Calauan CES | CALAUAN | 3 | 1 | 15 | 3STY15CL | BATCH 10 | 34987258.48 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108255 | Calauan CES | CALAUAN | 3 |  | 12 | 3STY12CL | BATCH 10 | 30471452.6 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108256 | Dayap ES | CALAUAN | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32432785.51 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 307927 | Dayap NHS (Calauan Annex) | CALAUAN | 3 | 1 | 4 | 4STY LAB | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108259 | Lamot ES - Annex | CALAUAN | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14464305.4 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 301266 | San Juan NHS | KALAYAAN | 4 | 1 | 8 | 4STY8CL | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301244 | Liliw National High School | LILIW | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42836577.93 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Laguna | 342350 | Bambang Stand Alone SHS | LOS BAÑOS | 2 |  | 8 | 4STY8CL | BATCH 10 | 23337263.81 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 301247 | Los Banos NHS (Batong Malake) | LOS BAÑOS | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 45345420.81 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 301247 | Los Banos NHS (Batong Malake) | LOS BAÑOS | 2 |  | 20 | 4STY20CL | BATCH 10 | 45345420.81 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 301247 | Los Baños NHS (Batong Malake) | LOS BAÑOS | 2 |  | 20 | 4STY20CL | BATCH 10 | 48394705.1 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108309 | Maahas ES | LOS BAÑOS | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 43549874.55 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108311 | Mayondon Elementary School | LOS BAÑOS | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 18910813.43 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108312 | P. Rizal ES (Putho ES) | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | BATCH 10 | 34716169.63 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342350 | Stand Alone SHS No. 8 Bambang | LOS BAÑOS | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 19126276.29 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108318 | San Antonio ES | LUISIANA | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 24791511.52 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108328 | Lumban CS | LUMBAN | 4 | 1 | 12 | 4STY12CL | BATCH 10 | 37648952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108337 | Wawa ES | LUMBAN | 4 | 1 | 4 | 2STY4CL | BATCH 10 | 9813553.96 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108286 | Matalatala ES | MABITAC | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 24732026.51 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108291 | Paagahan ES | MABITAC | 4 | 1 | 8 | 4STY8CL | BATCH 10 | 17335683.91 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108348 | Majayjay Elementary School | MAJAYJAY | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 24791511.52 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108352 | Alumbrado ES | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14454305.4 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301237 | Calumpang NHS - Lowland NHS Annex | NAGCARLAN | 3 | 1 | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 10 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108357 | Crisanto Guysayko MES | NAGCARLAN | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 42836577.93 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301258 | Plaridel NHS | NAGCARLAN | 3 | 1 | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 10 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108366 | Santa Lucia ES | NAGCARLAN | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12264291.38 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108368 | Sinipian ES | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14464305.4 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342347 | Stand Alone SHS No. 5 Nagcarlan | NAGCARLAN | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 342347 | Stand Alone SHS No. 5 Nagcarlan | NAGCARLAN | 3 |  | 8 | 4STY LAB./ REG. WORKSHOP | BATCH 10 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108369 | Talangan ES | NAGCARLAN | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14464305.4 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42836577.93 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301276 | Talangan NHS | NAGCARLAN | 3 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 2700000 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108370 | Taytay-Malaya ES | NAGCARLAN | 3 | 1 | 10 | 2STY10CL | BATCH 10 | 20552318.78 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301278 | Upland NHS | NAGCARLAN | 3 | 1 | 4 | 4STY LAB | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108380 | C. Lanuza ES | PAGSANJAN | 4 | 1 | 6 | 3STY6CL | BATCH 10 | 13871096.82 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108398 | Kabulusan ES | PAKIL | 4 | 1 | 6 | 2STY6CL | BATCH 10 | 12067729.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108404 | Sulib ES | Pangil | 4 | 1 | 15 | 3STY15CL | BATCH 10 | 37798952.72 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108407 | Labuin ES | PILA | 4 | 1 | 12 | 3STY12CL | BATCH 10 | 29785307.07 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108411 | Pila ES | PILA | 4 | 1 | 12 | 3STY12CL | BATCH 10 | 29818956.27 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108354 | Rizal ES | Rizal | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42686577.93 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108354 | Rizal ES | Rizal | 3 |  | 12 | 4STY12CL | BATCH 10 | 32657785.51 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108434 | San Vicente Elementary School | SAN PEDRO | 1 | 1 | 20 | 4STY20CL | BATCH 10 | 42464861.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108441 | Oogong ES | SANTA CRUZ (Capital) | 4 | 1 | 6 | 3STY6CL | BATCH 10 | 13985995.5 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 301257 | Pedro Guevara MNHS | SANTA CRUZ (Capital) | 4 | 1 | 20 | 4STY20CL | BATCH 10 | 42422542.18 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108445 | San Jose ES | SANTA CRUZ (Capital) | 4 | 1 | 6 | 3STY6CL | BATCH 10 | 13937833.36 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108447 | Santisima Cruz ES | SANTA CRUZ (Capital) | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 24875160.33 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108448 | Santo Angel CES | SANTA CRUZ (Capital) | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 28175421.44 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108466 | Santa Maria ES | SANTA MARIA | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 25189361.88 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301269 | Sta. Maria NHS | SANTA MARIA | 4 | 1 | 20 | 4STY20CL | BATCH 10 | 41909892.1 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301273 | Siniloan National High School | SINILOAN | 4 | 1 | 20 | 4STY20CL | BATCH 10 | 42268145.66 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301228 | Banca-Banca NHS - Integrated Senior High School | VICTORIA | 3 | 1 | 4 | 4STY LAB | BATCH 10 | 18102762.08 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301250 | Masapang NHS | VICTORIA | 3 | 1 | 6 | 3STY LAB./ REG. WORKSHOP | BATCH 10 | 30096452.6 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 301264 | San Francisco NHS | VICTORIA | 3 | 1 | 2 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 5625000 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 108502 | Victoria ES | VICTORIA | 3 |  | 6 | 3STY LAB./ REG. WORKSHOP | BATCH 10 | 30096452.6 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 108502 | Victoria ES | VICTORIA | 3 |  | 4 | 4STY LAB | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Laguna | 108502 | Victoria ES | VICTORIA | 3 |  | 2 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 5400000 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342348 | Victoria Senior High School | VICTORIA | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17652762.08 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308502 | Cotta National High School | LUCENA CITY (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 6218062.57 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308502 | Cotta National High School | LUCENA CITY (Capital) | 2 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 6218062.57 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308502 | Cotta National High School | LUCENA CITY (Capital) | 2 |  | 4 | 4STY REG. WORKSHOP | BATCH 10 | 20748690.27 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308503 | Gulang-Gulang NHS | LUCENA CITY (Capital) | 2 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 20379870 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308504 | Gulang-Gulang NHS - Iba. Talim Ext. | LUCENA CITY (Capital) | 2 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 6415700 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308504 | Gulang-Gulang NHS - Iba. Talim Ext. | LUCENA CITY (Capital) | 2 |  | 4 | 4STY REG. WORKSHOP | BATCH 10 | 20443327.7 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 301501 | Lucena City National High School | LUCENA CITY (Capital) | 2 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 20458339.2 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308505 | Lucena City NHS -Mayao Parada Extension | LUCENA CITY (Capital) | 2 | 1 | 4 | 4STY REG. WORKSHOP with classroom | BATCH 10 | 35133697.75 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 | 1 | 4 | 4STY REG. WORKSHOP | BATCH 10 | 21637649.2 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Lucena City | 308501 | Lucena Dalahican NHS | LUCENA CITY (Capital) | 2 |  | 4 | 4STY REG. WORKSHOP | BATCH 10 | 21637649.2 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Funds 2018
NC 2017 | K10 | Region IV-A | Lucena City | 109707 | Lucena East I ES | LUCENA CITY (Capital) | 2 | 1 | 6 | 3STY6CL | BATCH 10 | 16101410.67 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109715 | Lucena East VIII ES | LUCENA CITY (Capital) | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 20196002.12 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 46185690.84 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109742 | Lucena West I ES | LUCENA CITY (Capital) | 2 |  | 16 | 4STY16CL | BATCH 10 | 42754759.44 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109727 | Zaballero Subd. ES | LUCENA CITY (Capital) | 2 | 1 | 20 | 4STY20CL | BATCH 10 | 46384436.99 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Quezon | 301321 | Elias A. Salvador NHS | AGDANGAN | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0158 | 2017-11-16 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-22 | RGP BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301284 | Alabat Island National High School | ALABAT | 4 | 1 | 1 | ICT LAB | BATCH 10 | 3846397.08 |  |  | Completed | 1 |  |  | P00179392LZ-CW1 | 18DL0113 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-09 | E.A. AYALA CONSTRUCTION & SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301284 | Alabat Island National High School | ALABAT | 4 |  | 20 | 4STY20CL | BATCH 10 | 41408409.74 |  |  | Completed | 1 |  |  | P00179393LZ-CW1 | 18DL0053 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-11 | 2017-12-27 | EXCELSIUS ENGINEERING SERVICES / KATHA BUILDERS & SUPPLIES (JV)
NC 2017 | K10 | Region IV-A | Quezon | 108509 | Atimonan CES (Merged Atimonan CS I & Atimonan CS II) | ATIMONAN | 4 | 1 | 6 | 2STY6CL | BATCH 10 | 11656168.02 |  |  | Completed | 1 |  |  | P00179370LZ-CW1 | 17DL0227 | 2017-09-08 | 2017-09-20 | 2017-10-02 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301286 | Atimonan NCHS | ATIMONAN | 4 | 1 | 12 | (8) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 37710453.12 |  |  | Completed | 1 |  |  | P00179394LZ-CW1 | 18DL0091 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-21 | 2018-01-09 | POWER K CONSTRUCTION SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301286 | Atimonan NCHS | ATIMONAN | 4 |  | 9 | 3STY9CL | BATCH 10 | 24468047.73 |  |  | Completed | 1 |  |  | P00179395LZ-CW1 | 18DL0054 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-29 | 2017-01-15 | RAPID FOREMOST CONSTRUCTION COMPANY
NC 2017 | SHS | Region IV-A | Quezon | 301286 | Atimonan NCHS | ATIMONAN | 4 |  | 9 | 3STY9CL | BATCH 10 | 24468047.73 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 301296 | Buenavista NHS | BUENAVISTA | 3 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4040868.28 |  |  | Completed | 1 |  |  |  | 17DM0169 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | MJIEL
NC 2017 | SHS | Region IV-A | Quezon | 308006 | Hagonghong Integrated HS | BUENAVISTA | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9865318.3 |  |  | Completed | 1 |  |  |  | 17DM0165 | 2017-11-16 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-18 | QVL
NC 2017 | TVL | Region IV-A | Quezon | 308008 | Maligaya NHS | Buenavista | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15493726.14 |  |  | Completed | 1 |  |  |  | 17DM0188 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | RGP BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301335 | Bonifacio National High School | BURDEOS | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0175 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Steven Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301335 | Bonifacio National High School | BURDEOS | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0176 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Steven Const & Supply
NC 2017 | K10 | Region IV-A | Quezon | 108563 | Cabungalunan ES | BURDEOS | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3477000 |  |  | Completed | 1 |  |  |  | 17DK0164 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | K10 | Region IV-A | Quezon | 108592 | Apad ES | CALAUAG | 4 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179372LZ-CW1 | 17DL0165 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-12-11 | 2017-12-19
NC 2017 | K10 | Region IV-A | Quezon | 108601 | Kinamaligan ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179373LZ-CW1 | 17DL0152 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19
NC 2017 | TVL | Region IV-A | Quezon | 301339 | Lagay NHS | CALAUAG | 4 | 1 | 5 | (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 17643155.66 |  |  | Completed | 1 |  |  | P00179401LZ-CW1 | 18DL0121 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-21 | 2018-01-09 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301339 | Lagay NHS | CALAUAG | 4 |  | 4 | 2STY4CL | BATCH 10 | 8945901.76 |  |  | Completed | 1 |  |  | P00179402LZ-CW1 | 17DL0205 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108580 | Mambaling ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179371LZ-CW1 | 17DL0153 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108605 | Pangahoy ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179374LZ-CW1 | 17DL0154 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108606 | Pinagkamaligan ES | CALAUAG | 4 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Reverted | 0
NC 2017 | K10 | Region IV-A | Quezon | 108610 | Sta. Rosa ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179376LZ-CW1 | 17DL0175 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 308011 | Sto. Angel National High School | CALAUAG | 4 | 1 | 5 | (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 17643155.66 |  |  | Completed | 1 |  |  | P00179415LZ-CW1 | 18DL0124 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-21 | 2018-01-09 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 308011 | Sto. Angel National High School | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179416LZ-CW1 | 17DL0176 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-19 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108611 | Sto. Domingo ES | CALAUAG | 4 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179377LZ-CW1 | 17DL0156 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108616 | VIlla San Isidro ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179378LZ-CW1 | 17DL0157 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 308016 | Dolores Macasaet National High School | CANDELARIA | 2 | 1 | 4 | Regular Workshop (4STY) | BATCH 10 | 17924820.2 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Quezon | 308019 | Dr. Panfilo Castro NHS (Formerly Bukal Sur NHS-Mangilag Annex) | CANDELARIA | 2 | 1 | 6 | 3STY6CL | BATCH 10 | 15597004.08 |  |  | Completed | 1 |  |  |  | 17DJ0093 | [5 empty] | R.A MENDIOLA CONST & DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 308019 | Dr. Panfilo Castro NHS (Formerly Bukal Sur NHS-Mangilag Annex) | CANDELARIA | 2 |  | 4 | Regular Workshop (4STY) | BATCH 10 | 17839780.25 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 308019 | Dr. Panfilo Castro NHS (Formerly Bukal Sur NHS-Mangilag Annex) | CANDELARIA | 2 |  | 4 | Science lab (4STY) | BATCH 10 | 17744840.55 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 301403 | Sta. Catalina National High School | CANDELARIA | 2 | 1 | 4 | Science lab (4STY) | BATCH 10 | 17074360.15 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 301310 | Catanauan National High School | Catanauan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0179 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | RGP BUILDERS
NC 2017 | SHS | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | CATANAUAN | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0164 | 2017-11-16 | 2017-11-23 | 2017-12-05 | 2017-12-11 | 2017-12-18 | KKT CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | CATANAUAN | 3 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3915433.24 |  |  | Completed | 1 |  |  |  | 17DM0171 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301391 | San Isidro National High School | Catanauan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0185 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | KKT CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 308025 | San Jose NHS (Formerly Tagbacan Ilaya Integ. Sec. Ext. Classes) | CATANAUAN | 3 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3915433.24 |  |  | Completed | 1 |  |  |  | 17DM0172 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 308025 | San Jose NHS (Formerly Tagbacan Ilaya Integ. Sec. Ext. Classes) | Catanauan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0189 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | QUEZON VICTORY LUMBER
NC 2017 | TVL | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES | 2 | 1 | 4 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 16848715.22 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES | 2 |  | 4 | Regular Workshop (4STY) | BATCH 10 | 17673980 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301318 | Sta. Lucia NHS (Formerly Dagatan NHS Annex - Sta. Lucia) | DOLORES | 2 | 1 | 4 | Regular Workshop (4STY) | BATCH 10 | 19322980 |  |  | Reverted | 0
NC 2017 | K10 | Region IV-A | Quezon | 108696 | San Vicente ES | General Luna | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14783898.05 |  |  | Completed | 1
NC 2017 | TVL | Region IV-A | Quezon | 301292 | Batangan National High School | GENERAL NAKAR | 1 | 1 | 4 | 4STY Science & ICT | BATCH 10 | 32288155.07 |  |  | Completed | 1 |  |  |  | 17DK0238 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | Steven Const & Supply
NC 2017 | K10 | Region IV-A | Quezon | 108705 | Cynthia Village ES | GENERAL NAKAR | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3577000 |  |  | Completed | 1 |  |  |  | 17DK0171 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 | 1 | 3 | WORKSHOP BLDG (7X18) | BATCH 10 | 10089000 |  |  | Completed | 1 |  |  |  | 17DK0177 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Juntereal Industrial & Devt Corporation
NC 2017 | TVL | Region IV-A | Quezon | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0178 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | MJ Apin Builders
NC 2017 | TVL | Region IV-A | Quezon | 301361 | Paaralang Sek. Ng Hen. Nakar | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0179 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301362 | Paaralang Sek. Ng Hen. Nakar - Maligaya Extension | GENERAL NAKAR | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0180 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301362 | Paaralang Sek. Ng Hen. Nakar - Maligaya Extension | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0181 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301362 | Paaralang Sek. Ng Hen. Nakar - Maligaya Extension | GENERAL NAKAR | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0182 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Precious Costruction
NC 2017 | TVL | Region IV-A | Quezon | 301363 | Paaralang Sek. Ng Hen. Nakar - Umiray Extension | GENERAL NAKAR | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4159000 |  |  | Completed | 1 |  |  |  | 17DK0203 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-12 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | K10 | Region IV-A | Quezon | 108726 | Aloneros ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179379LZ-CW1 | 17DL0149 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | DZEE BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 108730 | Dancalan Caimawan ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179380LZ-CW1 | 17DL0150 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | DZEE BUILDERS AND CONSTRUCTION SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 108733 | Don Guillermo Eleazer ES | GUINAYANGAN | 4 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179381LZ-CW1 | 17DL0151 | 2017-08-10 | 2017-08-24 | 2017-09-07 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108733 | Don Guillermo Eleazer ES | GUINAYANGAN | 4 |  | 10 | 2STY10CL | BATCH 10 | 19708155.67 |  |  | Completed | 1 |  |  | P00179382LZ-CW1 | 17DL0201 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-12-11 | 2017-12-19 | EXCELSIUS ENGG. SERVICES
NC 2017 | K10 | Region IV-A | Quezon | 108751 | Anonangin ES | GUMACA | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179383LZ-CW1 | 17DL0186 | 2017-08-22 | 2017-09-06 |  | 2017-12-11 | 2017-12-19 | L.A. PROFUGO CONSTRUCTION & SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301415 | Villa Perez NHS | GUMACA | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 20509912.44 |  |  | Completed | 1 |  |  | P00179411LZ-CW1 | 18DL0112 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-09 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301415 | Villa Perez NHS | GUMACA | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179412LZ-CW1 | 17DL0148 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108783 | Binulasan Integrated Sch. (Elem) | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0250 | 2017-12-04 | 2017-12-06 | 2017-12-20 | 2017-12-22 | 2017-12-27 | Ultragreen Venture Structure Corp
NC 2017 | SHS | Region IV-A | Quezon | 301294 | Binulasan IS | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0249 | 2017-12-04 | 2017-12-06 | 2017-12-20 | 2017-12-22 | 2017-12-27 | Ultragreen Venture Structure Corp
NC 2017 | K10 | Region IV-A | Quezon | 108785 | Dinahican ES | INFANTA | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0172 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Juntereal Industrial & Devt Corporation
NC 2017 | SHS | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9445901.76 |  |  | Completed | 1 |  |  |  | 17DK0217 | 2017-10-19 | 2017-10-20 | 2017-11-02 | 2017-12-12 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301332 | Infanta NHS | INFANTA | 1 |  | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3859000 |  |  | Completed | 1 |  |  |  | 17DK0183 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301333 | Jomalig NHS | JOMALIG | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4109000 |  |  | Completed | 1 |  |  |  | 17DK0204 | 2017-10-14 | 2017-10-18 | 2017-11-29 | 2017-12-12 | 2017-12-15 | TAD Construction
NC 2017 | K10 | Region IV-A | Quezon | 108805 | Don Emilio Salumbides ES | LOPEZ | 4 | 1 | 15 | 3STY15CL | BATCH 10 | 33656939.69 |  |  | Completed | 1 |  |  | P00179384LZ-CW1 | 17DL0179 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108839 | Don Mateo Lopez ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179388LZ-CW1 | 17DL0140 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108843 | Hondagua ES | LOPEZ | 4 | 1 | 8 | 2STY8CL | BATCH 10 | 16974790.26 |  |  | Completed | 1 |  |  | P00179389LZ-CW1 | 17DL0183 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-12-11 | 2017-12-19 | EXCELSIUS ENGINEERING SERVICES
NC 2017 | TVL | Region IV-A | Quezon | 301327 | Hondagua NHS | LOPEZ | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 20509912.44 |  |  | Completed | 1 |  |  | P00179399LZ-CW1 | 18DL0100 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-21 | 2018-01-09 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301327 | Hondagua NHS | LOPEZ | 4 |  | 8 | 2STY8CL | BATCH 10 | 16974790.26 |  |  | Completed | 1 |  |  | P00179400LZ-CW1 | 17DL0192 | 2017-08-22 | 2017-09-06 |  | 2017-12-11 | 2017-12-19 | EXCELSIUS ENGG. SERVICES
NC 2017 | TVL | Region IV-A | Quezon | 308048 | Magallanes NHS-Sta. Catalina Extension | LOPEZ | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 20840236.33 |  |  | Completed | 1 |  |  | P00179417LZ-CW1 | 18DL0104 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-21 | 2017-12-29 | DZEE CONSTRUCTION AND SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 308048 | Magallanes NHS-Sta. Catalina Extension | LOPEZ | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179418LZ-CW1 | 17DL0142 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-19 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308009 | Pamampangin NHS | LOPEZ | 4 | 1 | 4 | (2) SCIENCE LAB /(2) ICT LAB | BATCH 10 | 14776398.88 |  |  | Completed | 1 |  |  | P00179413LZ-CW1 | 18DL0106 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-09 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 308009 | Pamampangin NHS | LOPEZ | 4 |  | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179414LZ-CW1 | 17DL0146 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108835 | San Francisco B (Culong) ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179386LZ-CW1 | 17DL0185 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-12-29 | 2018-01-11 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108835 | San Francisco B (Culong) ES | LOPEZ | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179387LZ-CW1
NC 2017 | TVL | Region IV-A | Quezon | 301386 | San Francisco B NHS | LOPEZ | 4 | 1 | 8 | (2) UNIQUE/ (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 26904073.78 |  |  | Completed | 1 |  |  | P00179406LZ-CW1 | 18DL0109 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-09 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301386 | San Francisco B NHS | LOPEZ | 4 |  | 6 | 3STY6CL | BATCH 10 | 13739515.1 |  |  | Completed | 1 |  |  | P00179407LZ-CW1 | 17DL0198 | 2017-08-22 | 2017-09-06 |  | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301353 | Veronica NHS (Formerly Magallanes NHS Veronica Extension) | LOPEZ | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 10 | 20509912.44 |  |  | Completed | 1 |  |  | P00179403LZ-CW1 | 18DL0111 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-03 | DZEE BUILDERS & CONSTRUCTION SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301353 | Veronica NHS (Formerly Magallanes NHS Veronica Extension) | LOPEZ | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179404LZ-CW1 | 17DL0144 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-19 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108829 | Villahermosa ES | LOPEZ | 4 | 1 | 4 | 2STY4CL | BATCH 10 | 8945901.76 |  |  | Completed | 1 |  |  | P00179385LZ-CW1 | 17DL0252 | 2017-09-26 | 2017-10-05 | 2017-10-16 | 2017-12-21 | 2017-12-29 | N.M. PARAFINA BUILDERS INC.
NC 2017 | TVL | Region IV-A | Quezon | 301364 | Paaralang Sek. Ng Lukban | LUCBAN | 1 |  | 4 | 4STY Science lab & ICT | BATCH 10 | 32888155.07 |  |  | Completed | 1 |  |  |  | 17DK0239 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | St. Timothy Const Corp
NC 2017 | K10 | Region IV-A | Quezon | 108863 | Prlng. Elem. Ng Lucban 1 | LUCBAN | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 20016091.35 |  |  | Completed | 1 |  |  |  | 17DK0244 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | CJ Construction
NC 2017 | K10 | Region IV-A | Quezon | 108859 | Prlng. Elem. Ng Nagsinamo | LUCBAN | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12041541.06 |  |  | Completed | 1 |  |  |  | 17DK0218 | 2017-10-17 | 2017-10-20 | 2017-11-02 | 2017-12-12 | 2017-12-15 | B.C. Villaseñor Construction
NC 2017 | TVL | Region IV-A | Quezon | 301360 | Olongtao National High School | MACALELON | 3 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3915433.24 |  |  | Completed | 1 |  |  |  | 17DM0170 | 2017-11-20 | 2017-11-27 | 2017-12-11 | 2017-12-15 | 2017-12-28 | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 308015 | Cagsiay III - Cagsiay I NHS Ext. | MAUBAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0184 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308015 | Cagsiay III - Cagsiay I NHS Ext. | MAUBAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0185 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308015 | Cagsiay III - Cagsiay I NHS Ext. | MAUBAN | 1 |  | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3563000 |  |  | Completed | 1 |  |  |  | 17DK0186 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301319 | Dr. Maria D. Pastrana National High School | MAUBAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3463000 |  |  | Completed | 1 |  |  |  | 17DK0123 | 2017-09-28 | 2017-10-06 | 2017-10-26 | 2017-11-03 | 2017-11-22 | Sarca Estate Devt Corp
NC 2017 | TVL | Region IV-A | Quezon | 301350 | Manuel S. Enverga Memorial School of Arts and Trades | MAUBAN | 1 |  | 4 | 4STY Science lab & ICT | BATCH 10 | 36888155.07 |  |  | Completed | 1 |  |  |  | 17DK0240 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | CJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301288 | Bagupaye NHS | Mulanay | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0178 | [5 empty] | M.G VILLAMIN
NC 2017 | TVL | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4006457.67 |  |  | Completed | 1 |  |  |  | 17DM0168 | [5 empty] | MJIEL
NC 2017 | TVL | Region IV-A | Quezon | 301283 | Magsaysay NHS (Formerly Ajos NHS-Magsaysay Ext.) | Mulanay | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0176 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301373 | Patabog NHS | Mulanay | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14984174.34 |  |  | Completed | 1 |  |  |  | 17DM0182 | [5 empty] | RFCC
NC 2017 | SHS | Region IV-A | Quezon | 308023 | Danlagan NHS (Formerly Kinagunan Ibaba NHS Ext. Classes) | PADRE BURGOS | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0166 | [5 empty] | SOUTH BUILDERS
NC 2017 | TVL | Region IV-A | Quezon | 301326 | Hinguiwin National High School | Padre Burgos | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0180 | [5 empty] | ADAD ENG'G SERVICES AND SUPPLIES
NC 2017 | TVL | Region IV-A | Quezon | 301394 | San Isidro NHS, Padre Burgos | Padre Burgos | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0186 | [5 empty] | WAYCON
NC 2017 | K10 | Region IV-A | Quezon | 108963 | Bantigue Elementary School | PAGBILAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0165 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | ALT Construction
NC 2017 | TVL | Region IV-A | Quezon | 308004 | Pagbilao NHS | PAGBILAO | 1 |  | 4 | 4STY Science lab & ICT | BATCH 10 | 32888155.07 |  |  | Completed | 1 |  |  |  | 17DK0241 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | CJ Construction
NC 2017 | K10 | Region IV-A | Quezon | 108972 | Pagbilao West ES | PAGBILAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3377000 |  |  | Completed | 1 |  |  |  | 17DK0163 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | ALT Construction
NC 2017 | K10 | Region IV-A | Quezon | 108973 | Palsabangon ES | PAGBILAO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3477000 |  |  | Completed | 1 |  |  |  | 17DK0166 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | WJ Construction
NC 2017 | SHS | Region IV-A | Quezon | 301407 | Talipan National High School | PAGBILAO | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 9445901.76 |  |  | Completed | 1 |  |  |  | 17DK0219 | 2017-10-17 | 2017-10-20 | 2017-11-02 | 2017-12-12 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301407 | Talipan National High School | PAGBILAO | 1 |  | 4 | 4STY Science lab & ICT | BATCH 10 | 33088155.07 |  |  | Completed | 1 |  |  |  | 17DK0242 | 2017-12-04 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 2017-12-28 | CJ Construction
NC 2017 | K10 | Region IV-A | Quezon | 109026 | Bonbon ES | PANUKULAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3427000 |  |  | Completed | 1 |  |  |  | 17DK0168 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 308029 | Libo NHS - Bonbon Annex | PANUKULAN | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3763000 |  |  | Completed | 1 |  |  |  | 17DK0205 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-12 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 308029 | Libo NHS - Bonbon Annex | PANUKULAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7526000 |  |  | Completed | 1 |  |  |  | 17DK0207 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-12 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 308029 | Libo NHS - Bonbon Annex | PANUKULAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7526000 |  |  | Completed | 1 |  |  |  | 17DK0206 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-12 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 301396 | San Juan NHS | PANUKULAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4259000 |  |  | Completed | 1 |  |  |  | 17DK0208 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-12 | 2017-12-15 | Zelan Construction & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4109000 |  |  | Completed | 1 |  |  |  | 17DK0210 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 |  | 3 | WORKSHOP BLDG (7X18) | BATCH 10 | 10689000 |  |  | Completed | 1 |  |  |  | 17DK0211 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0200 | 2017-12-03 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 371816 | ANNCON Builders
NC 2017 | TVL | Region IV-A | Quezon | 301374 | Patnanungan NHS | PATNANUNGAN | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0199 | 2017-12-03 | 2017-12-06 | 2017-12-22 | 2017-12-27 | 371816 | TAD Construction
NC 2017 | K10 | Region IV-A | Quezon | 108990 | Patnanungan Norte ES | PATNANUNGAN | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3577000 |  |  | Completed | 1 |  |  |  | 17DK0167 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Gemellus Builders
NC 2017 | K10 | Region IV-A | Quezon | 108994 | Mainit Sur ES | PEREZ | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179390LZ-CW1 | 17DL0237 | 2017-09-20 | 2017-09-30 | 2017-10-12 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301285 | Amontay National High School | Pitogo | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0177 | [5 empty] | RGP BUILDERS
NC 2017 | K10 | Region IV-A | Quezon | 109004 | Gangahin ES | PITOGO | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0145 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 109008 | Pitogo CES II | Pitogo | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0146 | [5 empty] | RFCC
NC 2017 | K10 | Region IV-A | Quezon | 109033 | Libjo ES | POLILLO | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3527000 |  |  | Completed | 1 |  |  |  | 17DK0169 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | MJ Apin Builders
NC 2017 | TVL | Region IV-A | Quezon | 301377 | Polillo National High School (Pollilo Annex) | POLILLO | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0170 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301377 | Polillo National High School (Pollilo Annex) | POLILLO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0201 | 2017-10-14 | 2017-10-18 | 2017-11-29 | 2017-12-12 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301377 | Polillo National High School (Pollilo Annex) | POLILLO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0202 | 2017-10-14 | 2017-10-18 | 2017-11-29 | 2017-12-12 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | SHS | Region IV-A | Quezon | 301377 | Polillo National High School-Polillo Annex | POLILLO | 1 |  | 8 | 2 units 2STY4CL | BATCH 10 | 18691803.52 |  |  | Completed | 1 |  |  |  | 17DK0220 | 2017-10-17 | 2017-10-20 | 2017-11-02 | 2017-12-12 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 301382 | Sabang National High School | POLILLO | 1 | 1 | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0213 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 301382 | Sabang National High School | POLILLO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0212 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | I A Bosque Construction
NC 2017 | TVL | Region IV-A | Quezon | 301408 | Taluong NHS | POLILLO | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 4009000 |  |  | Completed | 1 |  |  |  | 17DK0214 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301408 | Taluong NHS | POLILLO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0215 | 2017-10-14 | 2017-10-18 | 2017-11-23 | 2017-12-14 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301408 | Taluong NHS | POLILLO | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7026000 |  |  | Completed | 1 |  |  |  | 17DK0216 | 2017-10-19 | 2017-10-20 | 2017-11-02 | 2017-12-12 | 2017-12-15 | I A Bosque Construction
NC 2017 | SHS | Region IV-A | Quezon | 301365 | JOEL B. ARQUIZA NHS | QUEZON | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179405LZ-CW1 | 18DL0207 | 2017-12-05 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301315 | Pablo D. Maningas National High School | QUEZON | 4 | 1 | 2 | SCIENCE / ICT LAB | BATCH 10 | 7388199.44 |  |  | Completed | 1 |  |  | P00179397LZ-CW1 | 18DL0116 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-09 | E.A. AYALA CONSTRUCTION & SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301315 | Pablo D. Maningas National High School | QUEZON | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179398LZ-CW1 | 17DL0238 | 2017-09-20 | 2017-09-30 | 2017-10-12 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 109069 | Malapad ES | REAL | 1 | 1 | 2 | 1STY2CL | BATCH 10 | 3277000 |  |  | Completed | 1 |  |  |  | 17DK0173 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-08 | 2017-12-15 | Ultragreen Venture Structure Corp
NC 2017 | TVL | Region IV-A | Quezon | 301413 | Ungos National High School Extension - Llavac | REAL | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3859000 |  |  | Completed | 1 |  |  |  | 17DK0188 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Steven Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301413 | Ungos National High School Extension - Llavac | REAL | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0189 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Steven Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301413 | Ungos National High School Extension - Llavac | REAL | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0191 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Steven Const & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301413 | Ungos National High School Extension - Llavac | REAL | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0190 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 308026 | Ungos NHS - Lubayat Extension Class | REAL | 1 | 1 | 1 | WORKSHOP BLDG (7X18) | BATCH 10 | 3363000 |  |  | Completed | 1 |  |  |  | 17DK0192 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Precious Costruction
NC 2017 | TVL | Region IV-A | Quezon | 308026 | Ungos NHS - Lubayat Extension Class | REAL | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0194 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Juntereal Industrial & Devt Corporation
NC 2017 | TVL | Region IV-A | Quezon | 308026 | Ungos NHS - Lubayat Extension Class | REAL | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 6726000 |  |  | Completed | 1 |  |  |  | 17DK0193 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | Precious Costruction
NC 2017 | TVL | Region IV-A | Quezon | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 | 1 | 2 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 7718000 |  |  | Completed | 1 |  |  |  | 17DK0195 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | E.A.Ayala Const. & Supply
NC 2017 | TVL | Region IV-A | Quezon | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 |  | 3 | WORKSHOP BLDG (7X18) | BATCH 10 | 10089000 |  |  | Completed | 1 |  |  |  | 17DK0196 | 2017-10-11 | 2017-10-13 | 2017-10-25 | 2017-11-08 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0198 | 2017-10-14 | 2017-10-20 | 2017-10-30 | 2017-12-12 | 2017-12-15 | TAD Construction
NC 2017 | TVL | Region IV-A | Quezon | 301384 | Sampaloc NHS, Sampaloc | SAMPALOC | 1 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 7126000 |  |  | Completed | 1 |  |  |  | 17DK0197 | 2017-10-14 | 2017-10-20 | 2017-10-30 | 2017-12-12 | 2017-12-15 | WJ Construction
NC 2017 | TVL | Region IV-A | Quezon | 308024 | Camflora National High School (Annex) | San Andres | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15786842.7 |  |  | Completed | 1 |  |  |  | 17DM0173 | [5 empty] | RFCC
NC 2017 | SHS | Region IV-A | Quezon | 301306 | Camflora NHS | SAN ANDRES | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 22228203.19 |  |  | Completed | 1 |  |  |  | 17DM0157 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301306 | Camflora NHS | San Andres | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15786842.7 |  |  | Completed | 1 |  |  |  | 17DM0173 | [5 empty] | RFCC
NC 2017 | K10 | Region IV-A | Quezon | 109093 | Mangero Elementary School | San Andres | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10095784.71 |  |  | Completed | 1 |  |  |  | 17DM0147 | [5 empty] | QVL
NC 2017 | K10 | Region IV-A | Quezon | 109104 | Callejon ES | SAN ANTONIO | 2 | 1 | 8 | 2 units 1STY4CL | BATCH 10 | 10842552.03 |  |  | Completed | 1 | [9 empty] | GREENGAGE CORP
NC 2017 | SHS | Region IV-A | Quezon | 301305 | Callejon NHS | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10651808.24 |  |  | Completed | 1 |  |  |  | 17DJ0114 | [5 empty] | GREENGAGE CORP
NC 2017 | TVL | Region IV-A | Quezon | 301305 | Callejon NHS | SAN ANTONIO | 2 |  | 4 | Regular Workshop (4STY) | BATCH 10 | 17169720.5 |  |  | Reverted | 0
NC 2017 | K10 | Region IV-A | Quezon | 109115 | Aurora Central Annex I ES | San Francisco | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10018479.42 |  |  | Completed | 1 |  |  |  | 17DM0148 | [5 empty] | RFCC
NC 2017 | K10 | Region IV-A | Quezon | 109116 | Bayog ES | San Francisco | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10018479.42 |  |  | Completed | 1 |  |  |  | 17DM0149 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301298 | Busdak National High School | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0175 | [5 empty] | R'CEL
NC 2017 | TVL | Region IV-A | Quezon | 308034 | Butanguiad NHS | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0190 | [5 empty] | L.A CLAMOR
NC 2017 | TVL | Region IV-A | Quezon | 301309 | Casay National High School | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0173 | [5 empty] | RFCC
NC 2017 | K10 | Region IV-A | Quezon | 109122 | Don Juan Vercelos ES | San Francisco | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10018479.42 |  |  | Completed | 1 |  |  |  | 17DM0150 | [5 empty] | QVL
NC 2017 | TVL | Region IV-A | Quezon | 308044 | Huyon-Uyon National High School | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0174 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301409 | Jacinto G. Esplana National High School | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0175 | [5 empty] | RCEL
NC 2017 | TVL | Region IV-A | Quezon | 308039 | Lualhati D. Edaño NHS | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0191 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0184 | [5 empty] | QUEZON VICTORY LUMBER
NC 2017 | TVL | Region IV-A | Quezon | 301369 | Pagsangahan NHS | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0192 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301379 | Pugon NHS | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0183 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 301368 | Renato Edaño Vicenclo NHS (Formerly Pagsangahan NHS-Don Juan | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0175 | [5 empty] | RCEL
NC 2017 | TVL | Region IV-A | Quezon | 308003 | Sto. Niño National High School (Formerly Pagsangahan NHS Ext.) | San Francisco | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 15012504.58 |  |  | Completed | 1 |  |  |  | 17DM0175 | [5 empty] | RCEL
NC 2017 | K10 | Region IV-A | Quezon | 109134 | Tayuman Elementary School | San Francisco | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10018479.42 |  |  | Completed | 1 |  |  |  | 17DM0151 | [5 empty] | RFCC
NC 2017 | SHS | Region IV-A | Quezon | 308034 | Butanguiad NHS | SAN FRANCISCO (AURORA) | 3 |  | 4 | 2STY4CL | BATCH 10 | 10018479.92 |  |  | Completed | 1 |  |  |  | 17DM0167 | [5 empty] | L.A CLAMOR
NC 2017 | SHS | Region IV-A | Quezon | 301390 | Marcial B. Villanueva NHS (Formerly San Francisco NHS, San Francisco) | SAN FRANCISCO (AURORA) | 3 |  | 9 | 3STY9CL | BATCH 10 | 22131903.27 |  |  | Completed | 1 |  |  |  | 17DM0161 | [5 empty] | QUEZON VICTORY LUMBER
NC 2017 | SHS | Region IV-A | Quezon | 301369 | Pagsangahan NHS | SAN FRANCISCO (AURORA) | 3 |  | 4 | 2STY4CL | BATCH 10 | 10018479.42 |  |  | Completed | 1 |  |  |  | 17DM0160 | [5 empty] | RFCC
NC 2017 | SHS | Region IV-A | Quezon | 301399 | Godofredo M. Tan Memorial School of Arts and Trades (Formerly San Narciso Voc. HS) | SAN NARCISO | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 22158247.82 |  |  | Completed | 1 |  |  |  | 17DM0162 | [5 empty] | MICLOVER
NC 2017 | K10 | Region IV-A | Quezon | 109147 | Pinagsama ES | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10031179.94 |  |  | Completed | 1 |  |  |  | 17DM0152 | [5 empty] | L.A.CLAMOR
NC 2017 | K10 | Region IV-A | Quezon | 109154 | Vigo CES | SAN NARCISO | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 10031179.94 |  |  | Completed | 1 |  |  |  | 17DM0153 | [5 empty] | RFCC
NC 2017 | TVL | Region IV-A | Quezon | 308043 | Bignay National High School | SARIAYA | 2 | 1 | 5 | WORKSHOP BLDG (7X18) | BATCH 10 | 18102500 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Quezon | 308041 | Castañas NHS | SARIAYA | 2 | 1 | 6 | 3STY6CL | BATCH 10 | 15299818.48 |  |  | Completed | 1 |  |  |  | 17DJ0076 | [5 empty] | JEMAK CONSTRUCTION & SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 308041 | Castañas NHS | SARIAYA | 2 |  | 4 | Regular Workshop (4STY) | BATCH 10 | 17814250 |  |  | Reverted | 0 | [9 empty] | JEMAK CONSTRUCTION & SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 308020 | GOV. ANACLETO C. ALCALA NATIONAL HIGH SCHOOL | SARIAYA | 2 | 1 | 4 | Regular Workshop (4STY) | BATCH 10 | 18334765.12 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301349 | Lutucan National High School | SARIAYA | 2 | 1 | 4 | Regular Workshop (4STY) | BATCH 10 | 17879420.3 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301349 | Lutucan National High School | SARIAYA | 2 |  | 4 | Science lab (4STY) | BATCH 10 | 17882540.4 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Quezon | 308032 | Pili NHS (Formerly Lutucan NHS Pili Ext.) | SARIAYA | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10001503.88 |  |  | Completed | 1 |  |  |  | 17DJ0092 | [5 empty] | BOMEL CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 308032 | Pili NHS (Formerly Lutucan NHS Pili Ext.) | SARIAYA | 2 |  | 4 | Regular Workshop (4STY) | BATCH 10 | 17829310.6 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Quezon | 301395 | San Isidro NHS, Tagkawayan | TAGKAWAYAN | 4 | 1 | 3 | 1STY3CL | BATCH 10 | 3768435.02 |  |  | Completed | 1 |  |  | P00179408LZ-CW1 | 17DL0247 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 109229 | Tagkawayan CES | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179391LZ-CW1 | 17DL0249 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301406 | Tagkawayan NHS | TAGKAWAYAN | 4 | 1 | 9 | 3STY9CL | BATCH 10 | 24468047.73 |  |  | Completed | 1 |  |  | P00179409LZ-CW1 | 18DL0051 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-11 | 2017-12-27 | R.V. LABORTE BUILDERS
NC 2017 | SHS | Region IV-A | Quezon | 301406 | Tagkawayan NHS | TAGKAWAYAN | 4 |  | 2 | 1STY2CL | BATCH 10 | 2613745.92 |  |  | Completed | 1 |  |  | P00179410LZ-CW1 | 17DL0250 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-12-11 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301299 | Cabay NHS | TIAONG | 2 | 1 | 4 | WORKSHOP BLDG (7X18) | BATCH 10 | 17014280.1 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Quezon | 308012 | Gloria Umali NHS | TIAONG | 2 | 1 | 6 | 3STY6CL | BATCH 10 | 16494685.1 |  |  | Completed | 1 |  |  |  | 17DJ0078 | [5 empty] | POWER K CONST. SUPPLY& SERVICES
NC 2017 | TVL | Region IV-A | Quezon | 308012 | Gloria Umali NHS | TIAONG | 2 |  | 4 | Science lab (4STY) | BATCH 10 | 17134230.25 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301348 | Lusacan National High School | TIAONG | 2 | 1 | 4 | WORKSHOP BLDG (7X18) | BATCH 10 | 17478512.23 |  |  | Reverted | 0
NC 2017 | SHS | Region IV-A | Quezon | 301370 | Paiisa NHS | TIAONG | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 13523667.39 |  |  | Completed | 1 |  |  |  | 17DJ0060 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301370 | Paiisa NHS | TIAONG | 2 |  | 2 | WORKSHOP BLDG (7X18) | BATCH 10 | 16974500 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301380 | Recto MNHS | TIAONG | 2 | 1 | 4 | ICT LAB (4STY) | BATCH 10 | 17862030 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301371 | Leonarda D. Vera Cruz NHS (Formerly Panaon NHS) | Unisan | 3 | 1 | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0181 | [5 empty] | RFCC
NC 2017 | K10 | Region IV-A | Quezon | 109299 | Muliguin ES | Unisan | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0154 | [5 empty] | WAYCON
NC 2017 | K10 | Region IV-A | Quezon | 109301 | Poctol ES | Unisan | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0155 | [5 empty] | C.G CABANA
NC 2017 | K10 | Region IV-A | Quezon | 109306 | Unisan CES | Unisan | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9196271.45 |  |  | Completed | 1 |  |  |  | 17DM0156 | [5 empty] | C.G CABANA
NC 2017 | SHS | Region IV-A | Quezon | 301414 | Unisan NHS | UNISAN | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12430342.31 |  |  | Completed | 1 |  |  |  | 17DM0163 | [5 empty] | I.A.BOSQUE
NC 2017 | TVL | Region IV-A | Quezon | 301414 | Unisan NHS | Unisan | 3 |  | 3 | 3 Storey 3 Unit Workshop | BATCH 10 | 14783898.05 |  |  | Completed | 1 |  |  |  | 17DM0187 | [5 empty] | L.A.PROFUGO CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region IV-A | Rizal | 109424 | Tuna-Balibago ES | Cardona | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4762122.024 |  |  | Completed | 1 |  |  | P00179421LZ-CW1 | 17D00117 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-12-11 | 2017-12-20 | CHRISMAN CONST. & SUPPLIES
NC 2017 | TVL | Region IV-A | Rizal | 308132 | Bugarin NHS | Pililla | 2 | 1 | 1 | UNIQUE WORKSHOP | BATCH 10 | 4125000 |  |  | Completed | 1 |  |  | P00179436LZ-CW1 | 17DO0124 | 2017-10-07 | 2017-10-13 | 2017-10-26 | 2017-12-20 | 2017-12-20 | FLS Construction & Builders
NC 2017 | K10 | Region IV-A | Rizal | 109470 | Macabud ES | Rodriguez (Montalban) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10206946.848 |  |  | Completed | 1 |  |  | P00179422LZ-CW1 | 17D00148 | 2017-11-24 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-03 | NEW RICH GEN. CONST. SERVICES AND TRADING CO. INC.
NC 2017 | K10 | Region IV-A | Rizal | 165515 | Malasya Uyungan Elementary School | Rodriguez (Montalban) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10915082.112 |  |  | Reverted | 0 |  |  | P00179427LZ-CW1 | 17DO0147 | 2017-11-24 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-03 | Traccor Builders | cancelled; area infested as per DPWH
NC 2017 | K10 | Region IV-A | Rizal | 109474 | Puray Elementary School | Rodriguez (Montalban) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10005491.936 |  |  | Completed | 1 |  |  | P00179423LZ-CW1 | 17D00146 | 2017-11-24 | 2017-12-01 | 2017-12-13 | 2017-12-21 | 2018-01-03 | TRACCOR BUILDERS
NC 2017 | K10 | Region IV-A | Rizal | 109476 | Rodriguez Heights ES | Rodriguez (Montalban) | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 18416549.2035 |  |  | Completed | 1 |  |  | P00179424LZ-CW1 | 17D00140 | 2017-11-22 | 2017-11-29 | 2017-12-11 | 2017-12-20 | 2018-01-03 | C.R. Domingo Const. & Power Dev't Inc. / Montalban Concrete & Asphalt Inc. (JV)
NC 2017 | TVL | Region IV-A | Rizal | 342567 | SOUTHVILLE 8B SENIOR HIGH SCHOOL | RODRIGUEZ (MONTALBAN) | 2 | 1 | 1 | UNIQUE WORKSHOP | BATCH 10 | 3100000 |  |  | Completed | 1 |  |  | P00179439LZ-CW1 | 17DO0123 | 2017-10-07 | 2017-10-13 | 2017-10-26 | 2017-12-11 | 2017-12-20 | Kevin Yoshi Builder
NC 2017 | SHS | Region IV-A | Rizal | 301459 | Pintung Bukawe National High School | San Mateo | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10005491.936 |  |  | Completed | 1 |  |  | P00179429LZ-CW1 | 17DO0133 | 2017-11-09 | 2017-11-16 | 2017-11-28 | 2017-12-11 | 2017-12-20 | Traccor Builders
NC 2017 | K10 | Region IV-A | Rizal | 301435 | Daraetan NHS | Tanay | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10526137.236 |  |  | Completed | 1 |  |  | P00179428LZ-CW1 | 17DO0089 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-12-11 | 2017-12-20 | Flag Const. Corp.
NC 2017 | SHS | Region IV-A | Rizal | 308133 | Laiban National High School | TANAY | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 10081137.236 |  |  | Completed | 1 |  |  | P00179437LZ-CW1 | 17DO0111 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-11-22 | 2017-12-05 | Alpha & Omega Gen. Contractors & Devl't Corp.
NC 2017 | SHS | Region IV-A | Rizal | 308133 | Laiban National High School | TANAY | 2 |  | 4 | 2STY4CL | BATCH 10 | 10081137.236 |  |  | Completed | 1 |  |  | P00179438LZ-CW1 | 17DO0112 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-12-11 | 2017-12-20 | Alpha & Omega Gen. Contractors & Devl't Corp.
NC 2017 | K10 | Region IV-A | Rizal | 109514 | Nayon ES | Tanay | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3196495.104 |  |  | Completed | 1 |  |  | P00179425LZ-CW1 | 17DO0115 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-12-11 | 2017-12-20 | St.Matthew Gen. Contractor & Dev't. Corp
NC 2017 | K10 | Region IV-A | Rizal | 109520 | Sampaloc ES | Tanay | 2 | 1 | 8 | 4STY8CL | BATCH 10 | 17970382.7 |  |  | Completed | 1 |  |  | P00179426LZ-CW1 | 17DO0085 | 2017-08-03 | 2017-08-10 | 2017-08-22 | 2017-12-11 | 2017-12-20 | Hexamindz Corp.
NC 2017 | K10 | Region IV-A | Rizal | 308118 | Sta. Ines NHS | Tanay | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 4522122.024 |  |  | Completed | 1 |  |  | P00179433LZ-CW1 | 17DO0116 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-12-11 | 2017-12-20 | St.Matthew Gen. Contractor & Dev't. Corp
NC 2017 | SHS | Region IV-A | Rizal | 342571 | Stand Alone 10 (Rizal Sports Academy) | Tanay | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 17831628.51 |  |  | Completed | 1 |  |  | P00179440LZ-CW1 | 17DO0121 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-12-11 | 2017-12-20 | MPJR Builders Co.
NC 2017 | SHS | Region IV-A | Rizal | 301461 | Sto. Niño NHS | Tanay | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 18442868.02 |  |  | Completed | 1 |  |  | P00179430LZ-CW1 | 17DO0113 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-12-11 | 2017-12-20 | South Builders & Const. Supplies
NC 2017 | SHS | Region IV-A | Rizal | 301461 | Sto. Niño NHS | Tanay | 2 |  | 8 | 2STY8CL | BATCH 10 | 18442868.02 |  |  | Completed | 1 |  |  | P00179431LZ-CW1 | 17DO0114 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-12-11 | 2017-12-20 | South Builders & Const. Supplies
NC 2017 | SHS | Region IV-A | Rizal | 301461 | Sto. Niño NHS | Tanay | 2 |  | 3 | 1STY3CL | BATCH 10 | 4019856.77 |  |  | Completed | 1 |  |  | P00179432LZ-CW1 | 17DO0118 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-12-11 | 2017-12-20 | L.A. Profugo Const. & Supply
NC 2017 | SHS | Region IV-A | Rizal | 308128 | Tanay East National High School | Tanay | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 12388378.09 |  |  | Completed | 1 |  |  | P00179435LZ-CW1 | 17DO0126 | 2017-10-27 | 2017-11-03 | 2017-11-16 | 2017-12-11 | 2017-12-20 | Pearlcast Const. & Trading
NC 2017 | K10 | Region IV-A | Rizal | 109346 | Bagumbayan ES | Teresa | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9837524.1128 |  |  | Completed | 1 |  |  | P00179419LZ-CW1 | 17D00080 | 2017-07-22 | 2017-07-28 | 2017-08-10 | 2017-10-10 | 2017-10-20 | SARCA ESTATE DEV'T. CORP.
NC 2017 | K10 | Region IV-A | Rizal | 109353 | Pantay ES | Teresa | 2 | 1 | 6 | 3STY6CL | BATCH 10 | 14698386.07 |  |  | Completed | 1 |  |  | P00179420LZ-CW1 | 17D00083 | 2017-07-22 | 2017-07-28 | 2017-08-10 | 2017-12-11 | 2018-12-20 | MEGASTRUCTURE BUILDER & TRADING CORP.
NC 2017 | SHS | Region IV-A | Rizal | 308123 | Pantay NHS (Teresa NHS - Pantay Annex) | Teresa | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 30119028.94 |  |  | Completed | 1 |  |  | P00179434LZ-CW1 | 17DO0122 | 2017-09-29 | 2017-10-06 | 2017-10-19 |  | 2017-12-20 | Alpha & Omega Gen. Contractors & Devl't Corp.
NC 2017 | K10 | Region IV-A | San Pablo City | 109777 | Bagong Bayan Elementary School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 38323952.72 |  |  | Completed | 1 |  |  | P00179457LZ_CW1 | 17DP0084 | 2017-09-27 | 2017-10-04 | 2017-10-18 | 2017-12-12 | 2017-12-15 | C.T. LEONCIO CONSTRUCTION AND TRADING
NC 2017 | K10 | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42536577.93 |  |  | Completed | 1 |  |  | P00179466LZ_CW1 | 17DP0127 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | ST. GERARD CONSTRUCTION
NC 2017 | K10 | Region IV-A | San Pablo City | 109751 | Col. Lauro P. Dizon Elementary School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14539305.4 |  |  | Completed | 1 |  |  | P00179442LZ_CW1 | 17DP0112 | 2017-11-15 | 2017-11-24 | 2017-12-07 | 2017-12-12 | 2017-12-15 | JOJR CONSTRUCTION
NC 2017 | K10 | Region IV-A | San Pablo City | 109759 | Dapdapan Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32732785.51 |  |  | Completed | 1 |  |  | P00179446LZ_CW1 | 17DP0087 | 2017-09-27 | 2017-10-04 | 2017-10-18 | 2017-12-12 | 2017-12-15 | STO. CRISTO CONST. & TRADING
NC 2017 | K10 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32957785.53 |  |  | Completed | 1 |  |  | P00179451LZ_CW1 | 17DP0131 | 2017-11-23 | 2017-11-29 | 2017-12-13 | 2017-12-18 | 2017-12-21 | JAIME B. CHING ENTERPRISE
NC 2017 | K10 | Region IV-A | San Pablo City | 109768 | Del Remedio Elementary School | SAN PABLO CITY | 3 |  | 16 | 4STY16CL | BATCH 10 | 38323952.72 |  |  | Completed | 1 |  |  | P00179452LZ_CW1 | 17DP0097 | 2017-10-26 | 2017-11-09 | 2017-11-21 | 2017-12-12 | 2017-12-15 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109793 | Don Enrique Bautista Elementary School | SAN PABLO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42986577.93 |  |  | Completed | 1 |  |  | P00179461LZ_CW1 | 17DP0124 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109794 | Fernando A. Quisumbing Elementary School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 25482408.68 |  |  | Completed | 1 |  |  | P00179462LZ_CW1 | 17DP0113 | 2017-11-15 | 2017-11-24 | 2017-12-07 | 2017-12-12 | 2017-12-15 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | San Pablo City | 109750 | Guadalupe Elementary School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14314305.4 |  |  | Completed | 1 |  |  | P00179441LZ_CW1 | 17DP0143 | 2017-11-24 | 2017-12-01 | 2017-12-15 | 2017-12-20 | 2017-12-27 | ISRAEL BUILDERS AND DEVELOPMENT CORP.
NC 2017 | K10 | Region IV-A | San Pablo City | 109774 | Margarita Lopez Laurel Memorial School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL | BATCH 10 | 14314305.4 |  |  | Completed | 1 |  |  | P00179455LZ_CW1 | 17DP0107 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | 11 DIAMOND CONSTRUCTION
NC 2017 | K10 | Region IV-A | San Pablo City | 109761 | Placido Escudero Memorial School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 37948952.72 |  |  | Completed | 1 |  |  | P00179447LZ_CW1 | 17DP0099 | 2017-10-26 | 2017-11-09 | 2017-11-21 | 2017-12-12 | 2017-12-15 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109773 | Prudencia D. Fule Memorial Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 3STY12CL | BATCH 10 | 30471452.6 |  |  | Completed | 1 |  |  | P00179454LZ_CW1 | 17DP0121 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | STO. CRISTO CONST. & TRADING
NC 2017 | K10 | Region IV-A | San Pablo City | 109769 | San Crispin Elementary School | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9574819.8 |  |  | Completed | 1 |  |  | P00179453LZ_CW1 | 17DP0101 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | ROSSLANCE CONSTRUCTION AND DEVELOPMENT
NC 2017 | K10 | Region IV-A | San Pablo City | 301503 | San Cristobal National High School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32582785.51 |  |  | Completed | 1 |  |  | P00179465LZ_CW1 | 17DP0140 | 2017-11-24 | 2017-12-01 | 2017-12-15 | 2017-12-20 | 2017-12-27 | SARCA ESTATE DEVELOPMENT CORPORATION
NC 2017 | K10 | Region IV-A | San Pablo City | 109808 | San Diego ES | SAN PABLO CITY | 3 | 1 | 20 | 4STY20CL | BATCH 10 | 42761577.93 |  |  | Completed | 1 |  |  | P00179464LZ-CW1 | 17DP0133 | 2017-11-23 | 2017-11-29 | 2017-12-13 | 2017-12-18 | 2017-12-21 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109754 | San Gabriel Elementary School | SAN PABLO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 18027762.08 |  |  | Completed | 1 |  |  | P00179443LZ_CW1 | 17DP0103 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | T. SOLOMON CONSTRUCTION & DEVELOPMENT CORPORATION
NC 2017 | K10 | Region IV-A | San Pablo City | 109797 | San Gregorio ES | SAN PABLO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17802762.08 |  |  | Completed | 1 |  |  | P00179448LZ_CW1 | 17DP0119 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | JTC CRUZ CONST.CO., INC.
NC 2017 | K10 | Region IV-A | San Pablo City | 109799 | San Isidro Elementary School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | BATCH 10 | 26157408.68 |  |  | Completed | 1 |  |  | P00179463LZ_CW1 | 17DP0130 | 2017-11-23 | 2017-11-29 | 2017-12-13 | 2017-12-18 | 2017-12-21 | JAIME B. CHING ENTERPRISE
NC 2017 | K10 | Region IV-A | San Pablo City | 109764 | San Jose Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32657785.51 |  |  | Completed | 1 |  |  | P00179449LZ_CW1 | 17DP0105 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | CHRISTIAN LEY CONSTRUCTION
NC 2017 | TVL | Region IV-A | San Pablo City | 308602 | San Jose National High School | SAN PABLO CITY | 3 | 1 | 4 | 4STY LAB | BATCH 10 | 17309570.67 |  |  | Completed | 1 |  |  | P00179467LZ_CW1 | 17DP0139 | 2017-11-23 | 2017-11-29 | 2017-12-13 | 2017-12-18 | 2017-12-21 | JAIME B. CHING ENTERPRISE
NC 2017 | K10 | Region IV-A | San Pablo City | 109790 | San Lucas II Elementary School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 37948952.72 |  |  | Completed | 1 |  |  | P00179460LZ_CW1 | 17DP0098 | 2017-10-26 | 2017-11-09 | 2017-11-21 | 2017-12-12 | 2017-12-15 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | San Pablo City | 109755 | San Miguel Elementary School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 38023952.72 |  |  | Completed | 1 |  |  | P00179444LZ_CW1 | 17DP0104 | 2017-11-13 | 2017-11-23 | 2017-12-05 | 2017-12-12 | 2017-12-15 | NEWBIG FOUR J CONST. INC
NC 2017 | TVL | Region IV-A | San Pablo City | 308605 | San Pablo City Science High School | SAN PABLO CITY | 3 | 1 | 4 | 4STY LAB | BATCH 10 | 17309570.67 |  |  | Completed | 1 |  |  | P00179468LZ_CW1 | 17DP0137 | 2017-11-23 | 2017-11-29 | 2017-12-13 | 2017-12-18 | 2017-12-21 | JTC CRUZ CONST.CO., INC.
NC 2017 | SHS | Region IV-A | San Pablo City | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 | 1 | 4 | 2STY4CL | BATCH 10 | 9274819.8 |  |  | Completed | 1 |  |  | P00179469LZ_CW1 | 17DP0128 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | NEW RICH GEN. CONTRACTOR SERVICES & TRADING COMPANY INC.
NC 2017 | TVL | Region IV-A | San Pablo City | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 |  | 4 | 2STY LAB | BATCH 10 | 17124790.26 |  |  | Completed | 1 |  |  | P00179470LZ_CW1 | 17DP0155 | 2017-11-27 | 2017-12-06 | 2017-12-19 | 2017-12-27 | 2017-12-29 | JAIME B. CHING ENTERPRISE
NC 2017 | TVL | Region IV-A | San Pablo City | 342575 | SAN PABLO CITY SENIOR HIGH SCHOOL (STAND ALONE) | SAN PABLO CITY | 3 |  | 2 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 5100000 |  |  | Completed | 1 |  |  | P00179471LZ_CW1 | 17DP0145 | 2017-11-24 | 2017-12-01 | 2017-12-15 | 2017-12-20 | 2017-12-27 | HIGH TWELVE CONSTRUCTION GENERAL MERCHANDISE
NC 2017 | K10 | Region IV-A | San Pablo City | 109783 | San Roque Elementary School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 38398952.72 |  |  | Completed | 1 |  |  | P00179458LZ_CW1 | 17DP0085 | 2017-09-27 | 2017-10-04 | 2017-10-18 | 2017-12-12 | 2017-12-15 | NEWBIG FOUR J CONST. INC
NC 2017 | K10 | Region IV-A | San Pablo City | 109784 | Santiago I Elementary School | SAN PABLO CITY | 3 | 1 | 8 | 4STY8CL | BATCH 10 | 17802762.08 |  |  | Completed | 1 |  |  | P00179459LZ_CW1 | 17DP0081 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-12-12 | 2017-12-15 | STO. CRISTO CONST. & TRADING
NC 2017 | K10 | Region IV-A | San Pablo City | 109811 | Sta. Catalina ES | SAN PABLO CITY | 3 | 1 | 12 | 3STY12CL | BATCH 10 | 30621452.6 |  |  | Completed | 1 |  |  | P00179450LZ_CW1 | 17DP0125 | 2017-11-21 | 2017-11-28 | 2017-12-11 | 2017-12-18 | 2017-12-21 | MSV CONST. AND SUPPLIES/NORTHERN BUILDERS (JV)
NC 2017 | K10 | Region IV-A | San Pablo City | 109775 | Sta. Filomena Integrated School | SAN PABLO CITY | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 38173952.72 |  |  | Completed | 1 |  |  | P00179456LZ_CW1 | 17DP0082 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-12-12 | 2017-12-15 | M.G. SALAZAR CONSTRUCTION CORP.
NC 2017 | K10 | Region IV-A | San Pablo City | 109758 | Stmo. Rosario Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | BATCH 10 | 32882785.51 |  |  | Completed | 1 |  |  | P00179445LZ_CW1 | 17DP0079 | 2017-09-22 | 2017-09-29 | 2017-10-12 | 2017-12-12 | 2017-12-15 | LE BRON CONSTRUCTION
NC 2017 | K10 | Region IV-A | Tanauan City | 107750 | Banadero ES | CITY OF TANAUAN | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 12408802.02 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tanauan City | 301084 | Bernardo Lirio Memorial National High School | CITY OF TANAUAN | 3 | 1 | 6 | 2STY6CL | BATCH 10 | 11656168.02 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Tanauan City | 301154 | Tanauan School of Fisheries | CITY OF TANAUAN | 3 | 1 | 16 | 4STY16CL | BATCH 10 | 22984750.29 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Tayabas City | 109256 | Lalo ES | CITY OF TAYABAS | 1 | 1 | 2 | 1SY2CL | BATCH 10 | 3527000 |  |  | Completed | 1 |  |  |  | 17DK0174 | 2017-10-10 | 2017-10-12 | 2017-10-24 | 2017-11-06 | 2017-12-15 | TANTAY LIM BUILDERS
NC 2017 | SHS | Region IV-A | Tayabas City | 301347 | Luis Palad NHS | CITY OF TAYABAS | 1 | 1 | 8 | 4STY8CL | BATCH 10 | 21101528.97 |  |  | Completed | 1 |  |  |  | 17DK0245 | 2017-12-04 | 2017-12-06 | 2017-12-18 | 2017-12-27 | 2017-12-28 | STEVEN CONST & SUPPLY
NC 2017 | SHS | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone | CITY OF TAYABAS | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 46342590.1 |  |  | Completed | 1 |  |  |  | 17DK0247 | 2017-12-04 | 2017-12-06 | 2017-12-18 | 2017-12-27 | 2017-12-28 | DQT BUILDERS
NC 2017 | SHS | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone | CITY OF TAYABAS | 1 |  | 6 | 3STY6CL | BATCH 10 | 19440642.13 |  |  | Completed | 1 |  |  |  | 17DK0248 | 2017-12-04 | 2017-12-06 | 2017-12-18 | 2017-12-27 | 2017-12-28 | CTC BUILDERS & SUPPLIES INC
NC 2017 | TVL | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone SHS | CITY OF TAYABAS | 1 |  | 4 | 4STY SCIENCE & ICT | BATCH 10 | 35888155.07 |  |  | Completed | 1 |  |  |  | 17DK0243 | 2017-12-04 | 2017-12-06 | 2017-12-18 | 2017-12-27 | 2017-12-28 | TANTAY LIM BUILDERS
NC 2017 | TVL | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone SHS | CITY OF TAYABAS | 1 | 1 | 1 | UNIQUE WORKSHOP (7X22.5) | BATCH 10 | 3959000 |  |  | Completed | 1 |  |  |  | 17DK0251 | 2017-12-05 | 2017-12-08 | 2017-12-20 | 2017-12-22 | 2017-12-29 | ANNCON BUILDERS
NC 2017 | TVL | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone SHS | CITY OF TAYABAS | 1 |  | 4 | 4STY UNIQUE WORKSHOP | BATCH 10 | 34738155.07 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Tayabas City | 342576 | Tayabas City Division Stand Alone SHS | CITY OF TAYABAS | 1 |  | 4 | 4STY UNIQUE WORKSHOP | BATCH 10 | 34738155.07 |  |  | Reverted | 0
NC 2017 | K10 | Region IV-A | Tayabas City | 109261 | Tayabas West CS III | CITY OF TAYABAS | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 13341541.06 |  |  | Completed | 1 |  |  |  | 17DK0246 | 2017-12-04 | 2017-12-06 | 2017-12-18 | 2017-12-27 | 2017-12-28 | TANTAY LIM BUILDERS
NC 2017 | K10 | Region IV-A | Antipolo City | 109349 | Canumay ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 12 | 18285873.59 |  |  | Completed | 1 |  |  |  | 17DN0183 |  |  | 2017-12-01 |  | 2018-01-04 | EL KAPITAN CONST
NC 2017 | SHS | Region IV-A | Laguna | 301251 | Masaya NHS | BAY | 2 | 1 | 20 | 4STY20CL | BATCH 12 | 45008676.91 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Quezon | 108507 | R. T. Camacho ES | ALABAT | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181482LZ-CW1 | 17DL0240 | 2017-09-20 | 2017-09-30 | 2017-10-12 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108512 | Balubad ES | ATIMONAN | 4 | 1 | 10 | 2STY10CL | BATCH 12 | 19708155.67 |  |  | Completed | 1 |  |  | P00181483LZ-CW1 | 17DL0231 | 2017-09-08 | 2017-09-20 | 2017-10-02 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108515 | Caridad Ilaya ES | ATIMONAN | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1 |  |  | P00181484LZ-CW1 | 17DL0229 | 2017-09-08 | 2017-09-20 | 2017-10-02 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108520 | Malinao Ilaya ES | ATIMONAN | 4 | 1 | 6 | 2STY6CL | BATCH 12 | 11656168.02 |  |  | Completed | 1 |  |  | P00181485LZ-CW1 | 17DL0230 | 2017-09-08 | 2017-09-20 | 2017-10-02 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301357 | Malusak National High School | ATIMONAN | 4 | 1 | 3 | (1) REGULAR WORKSHOP/ (2)ICT LAB | BATCH 12 | 20509912.44 |  |  | Completed | 1 |  |  | P00181509LZ-CW1 | 18DL0204 | 2017-12-05 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 301357 | Malusak National High School | ATIMONAN | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181510LZ-CW1 | 18DL0050 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-11 | 2017-12-19 | KKT CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 108529 | San Rafael ES | ATIMONAN | 4 | 1 | 3 | 1STY3CL | BATCH 12 | 3768435.02 |  |  | Completed | 1 |  |  | P00181486LZ-CW1 | 17DL0228 | 2017-09-08 | 2017-09-20 | 2017-10-02 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108533 | Tagbakin ES | ATIMONAN | 4 | 1 | 8 | 4STY8CL | BATCH 12 | 17159570.67 |  |  | Completed | 1 |  |  | P00181487LZ-CW1 | 18DL0056 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-11 | 2017-12-27 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308017 | Apad NHS (Formerly Sto. Domingo NHS - Apad Ext. Classes) | CALAUAG | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20509912.44 |  |  | Completed | 1 |  |  | P00181514LZ-CW1 | 18DL0117 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 308017 | Apad NHS (Formerly Sto. Domingo NHS - Apad Ext. Classes) | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181515LZ-CW1 | 17DL0166 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301291 | Bantulinao Integrated School | CALAUAG | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20509912.44 |  |  | Completed | 1 |  |  | P00181497LZ-CW1 | 18DL0118 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301291 | Bantulinao Integrated School | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181498LZ-CW1 | 17DL0167 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-27 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308021 | Dr. Arsenio C. Nicolas NHS | CALAUAG | 4 | 1 | 7 | (2) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 24037317 |  |  | Completed | 1 |  |  | P00181516LZ-CW1 | 18DL0119 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 308021 | Dr. Arsenio C. Nicolas NHS | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181517LZ-CW1 | 17DL0168 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308027 | Dr. Arsenio C. Nicolas NHS - Dominlog Ext. | CALAUAG | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20509912.44 |  |  | Completed | 1 |  |  | P00181520LZ-CW1 | 18DL0120 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 308027 | Dr. Arsenio C. Nicolas NHS - Dominlog Ext. | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181521LZ-CW1 | 17DL0169 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301341 | Lamon Bay SOF Annex - Capaluhan, Calauag | CALAUAG | 4 | 1 | 5 | (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 17643155.66 |  |  | Completed | 1 |  |  | P00181505LZ-CW1 | 18DL0203 | 2017-12-05 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 301341 | Lamon Bay SOF Annex - Capaluhan, Calauag | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181506LZ-CW1 | 17DL0170 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308022 | Rufina P. Trinidad Mem. NHS | CALAUAG | 4 | 1 | 5 | (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 17643155.66 |  |  | Completed | 1 |  |  | P00181518LZ-CW1 | 18DL0122 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 308022 | Rufina P. Trinidad Mem. NHS | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181519LZ-CW1 | 17DL0172 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108607 | SABANG ES | CALAUAG | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1 |  |  | P00181489LZ-CW1 | 17DL0206 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301402 | San Roque-Ilaya NHS, Calauag | CALAUAG | 4 | 1 | 4 | (2) SCIENCE LAB /(2) ICT LAB | BATCH 12 | 14776398.88 |  |  | Completed | 1 |  |  | P00181513LZ-CW1 | 18DL0123 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | KKT CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 108609 | Sta. Maria ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181490LZ-CW1 | 17DL0174 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108585 | SUMILANG ES | CALAUAG | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1 |  |  | P00181488LZ-CW1 | 17DL0207 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108612 | SUMULONG ES | CALAUAG | 4 | 1 | 6 | 3STY6CL | BATCH 12 | 13739515.1 |  |  | Completed | 1 |  |  | P00181491LZ-CW1 | 17DL0208 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108614 | Tiniguiban ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181492LZ-CW1 | 17DL0177 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108614 | Tiniguiban ES | CALAUAG | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181493LZ-CW1 | 17DL0178 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108626 | Pahinga Norte ES | CANDELARIA | 2 | 1 | 8 | 4STY8CL | BATCH 12 | 20315242.33 |  |  | Completed | 1 |  |  |  | 17DJ0054 | [5 empty] | ST. TIMOTHY CONTS. CORP
NC 2017 | TVL | Region IV-A | Quezon | 301342 | Aloneros NHS (Formerly LBS of Fisheries Ext. - Aloneros | GUINAYANGAN | 4 | 1 | 4 | (2) SCIENCE LAB /(2) ICT LAB | BATCH 12 | 14776398.88 |  |  | Completed | 1 |  |  | P00181507LZ-CW1 | 18DL0125 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301342 | Aloneros NHS (Formerly LBS of Fisheries Ext. - Aloneros | GUINAYANGAN | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181508LZ-CW1 | 17DL0164 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301320 | Dungawan NHS | GUINAYANGAN | 4 | 1 | 4 | (2) SCIENCE LAB /(2) ICT LAB | BATCH 12 | 14776398.88 |  |  | Completed | 1 |  |  | P00181500LZ-CW1 | 18DL0126 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301320 | Dungawan NHS | GUINAYANGAN | 4 |  | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1 |  |  | P00181501LZ-CW1 | 17DL0203 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108738 | Guinayangan ES | GUINAYANGAN | 4 | 1 | 4 | 2STY4CL | BATCH 12 | 8945901.76 |  |  | Completed | 1 |  |  | P00181495LZ-CW1 | 17DL0204 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-12-28 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301323 | Guinayangan NHS | GUINAYANGAN | 4 | 1 | 7 | (3) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 23376669.22 |  |  | Completed | 1 |  |  | P00181502LZ-CW1 | 18DL0128 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301359 | Nabangka NHS | GUINAYANGAN | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20509912.44 |  |  | Completed | 1 |  |  | P00181511LZ-CW1 | 18DL0127 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301359 | Nabangka NHS | GUINAYANGAN | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181512LZ-CW1 | 17DL0171 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301324 | STA. CRUZ NATIONAL HIGH SCHOOL | GUINAYANGAN | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20840236.33 |  |  | Completed | 1 |  |  | P00181503LZ-CW1 | 18DL0129 | 2017-11-21 | 2017-12-01 | 2017-12-14 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301324 | STA. CRUZ NATIONAL HIGH SCHOOL | GUINAYANGAN | 4 |  | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181504LZ-CW1 | 17DL0173 | 2017-08-18 | 2017-09-01 | 2017-09-14 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301290 | Bantad National High School | GUMACA | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 12 | 20840236.33 |  |  | Completed | 1 |  |  | P00181496LZ-CW1 | 18DL0092 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301307 | Camohaguin National High School | GUMACA | 4 | 1 | 2 | 1STY2CL | BATCH 12 | 2613745.92 |  |  | Completed | 1 |  |  | P00181499LZ-CW1 | 17DL0145 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Rizal | 109443 | Santiago ES | Baras | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 7312019.11 |  |  | Completed | 1 |  |  | P00181524LZ-CW1 | 17DO0119 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-11-22 | 2017-12-05 | Pearlcast Const. & Trading
NC 2017 | TVL | Region IV-A | Rizal | 109449 | Jalajala ES | Jalajala | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 6886618.86 |  |  | Completed | 1 |  |  | P00181525LZ-CW1 | 17DO0110 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-11-22 | 2017-12-05 | Pearlcast Const. & Trading
NC 2017 | TVL | Region IV-A | Rizal | 109436 | Maybancal ES | Morong | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 6960118.86 |  |  | Completed | 1 |  |  | P00181522LZ-CW1 | 17DO0120 | 2017-09-29 | 2017-10-06 | 2017-10-19 | 2017-11-22 | 2017-12-05 | T.Q. Const.& Development Corp.
NC 2017 | TVL | Region IV-A | Rizal | 109442 | San Guillermo Elementary School | Morong | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 6886618.86 |  |  | Completed | 1 |  |  | P00181523LZ-CW1 | 17DO0109 | 2017-09-22 | 2017-09-29 | 2017-10-11 | 2017-10-25 | 2017-11-08 | Flag Const. Corp.
NC 2017 | TVL | Region IV-A | Rizal | 301441 | Macabud NHS | Rodriguez (Montalban) | 2 | 1 | 2 | 2STY2CL | BATCH 12 | 6750527.2 |  |  | Completed | 1 |  |  | P00181526LZ-CW1 | 17DO0150 | 2017-12-01 | 2017-12-08 | 2017-12-21 | 2017-12-27 | 2018-01-03 | J.G. Gutierrez Const. & Trading
NC 2017 | K10 | Region IV-A | Rizal | 308106 | San Isidro NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 20 | 4STY20CL | BATCH 12 | 44436979.34 |  |  | Completed | 1 |  |  | P00181527LZ-CW1 | 17DO0154 | 2017-12-01 | 2017-12-08 | 2017-12-21 | 2017-12-27 | 2018-01-03 | Hexamindz Corp.
NC 2017 | K10 | Region IV-A | Rizal | 308106 | San Isidro NHS | RODRIGUEZ (MONTALBAN) | 2 |  | 20 | 4STY20CL | BATCH 12 | 44436979.34 |  |  | Completed | 1 |  |  | P00181528LZ-CW1 | 17DO0153 | 2017-12-01 | 2017-12-08 | 2017-12-21 | 2017-12-27 | 2018-01-03 | St. Timothy Const. Corp.
NC 2017 | K10 | Region IV-A | Rizal |  | Casili ES | San Mateo | 2 | 1 | 6 | 2STY6CL | BATCH 12 | 13591784.822 |  |  | Completed | 1 |  |  | P00181529LZ-CW1 | 17DO0151 | 2017-12-01 | 2017-12-08 | 2017-12-21 | 2017-12-29 | 2018-01-05 | M.J. Bevant Corp.
NC 2017 | K10 | Region IV-A | Sta. Rosa City | 251501 | Southville 4 Caingin Elementary School | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL | BATCH 12 | 32480517.46 |  |  | Completed | 1 |  |  |  | 17DI0120 | 2017-11-09 | 2017-11-21 | 2017-12-01 | 2017-12-05 | 2017-12-28 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2017 | K10 | Region IV-A | Batangas | 107363 | San Agustin ES | IBAAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2540475.16 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107605 | Paaralang Elementarya ng Buhaynasapa | SAN JUAN | 4 | 1 | 4 | 1STY4CL | BATCH 13 | 4901473.21 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301165 | Alfonso National High School | ALFONSO | 8 | 1 | 12 | 4STY12CL | BATCH 13 | 30040000 |  |  | Completed | 1 |  |  | 17DG0108 | [6 empty] | Hausland Construction
NC 2017 | SHS | Region IV-A | Cavite | 301201 | Lumampong NHS - Indang Annex | INDANG | 7 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1 |  |  | 17DG0110 | [6 empty] | St. Gerald Construction, Gen. Contractor & Devt. Corp.
NC 2017 | SHS | Region IV-A | Cavite | 301173 | Bendita NHS | MAGALLANES | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1 |  |  | 17DG0095 | [6 empty] | Alpha & Omega Gen. Contractor & Devt. Corp.
NC 2017 | SHS | Region IV-A | Cavite | 301175 | Bucal NHS | MARAGONDON | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1 |  |  | 17DG0117 | [6 empty] | N. V. Avila Construction
NC 2017 | SHS | Region IV-A | Cavite | 301175 | Bucal NHS | MARAGONDON | 8 |  | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301175 | Bucal NHS | MARAGONDON | 8 |  | 4 | 2STY4CL | BATCH 13 | 12580000 |  |  | Completed | 1 |  |  | 17DG0117 | [6 empty] | R. A. Del Rosario Construction
NC 2017 | SHS | Region IV-A | Cavite | 301178 | Cavite National Science High School | MARAGONDON | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Cavite | 301211 | Pulo ni Sara NHS | MARAGONDON | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1 | [9 empty] | Hausland Construction
NC 2017 | SHS | Region IV-A | Cavite | 301168 | Anuling NHS | MENDEZ (MENDEZ-NUÑEZ) | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30190000 |  |  | Completed | 1 | [9 empty] | Hausland Construction
NC 2017 | TVL | Region IV-A | Cavite | 342286 | Pedro Alegre Aure Senior High School | MENDEZ (MENDEZ-NUÑEZ) | 8 | 1 | 8 | 4STYLAB | BATCH 13 | 30040000 |  |  | Completed | 1 | [9 empty] | M. J. Apin Builders
NC 2017 | SHS | Region IV-A | Cavite | 342286 | Pedro Alegre Aure Senior High School | MENDEZ (MENDEZ-NUÑEZ) | 8 |  | 6 | 3STY6CL | BATCH 13 | 13937400 |  |  | Completed | 1 | [9 empty] | Czerj Construction and Trading
NC 2017 | SHS | Region IV-A | Cavite | 301207 | Naic NHS | NAIC | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 33040000 |  |  | Completed | 1 | [9 empty] | N. V. Avila Construction
NC 2017 | K10 | Region IV-A | Cavite | 108174 | San Juan ES | TERNATE | 8 | 1 | 12 | 4STY12CL | BATCH 13 | 31620000 |  |  | Completed | 1 | [9 empty] | M. J. Apin Builders
NC 2017 | SHS | Region IV-A | Cavite | 301221 | Ternate NHS | TERNATE | 8 | 1 | 4 | 4STY8CL | BATCH 13 | 30040000 |  |  | Completed | 1 | [9 empty] | Metrics Construction & Trading
NC 2017 | SHS | Region IV-A | CABUYAO | 342355 | Mamatid Senior High School | CABUYAO | 2 | 1 | 20 | 4STY20CL | BATCH 13 | 46128447.33 |  |  | Completed | 1 |  |  |  | 17DI0132 | 2017-11-17 | 2017-11-23 | 2017-12-07 | 2017-12-21 | 2017-12-28 | Power K
NC 2017 | K10 | Region IV-A | Laguna | 108303 | Bambang Elementary School | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 32267213.4 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Laguna | 108306 | Lalakay Elementary School | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 32959113.34 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342353 | Stand Alone SHS No. 11 BN Calara | LOS BAÑOS | 2 | 1 | 16 | 4STY16CL | BATCH 13 | 40087854.6 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342353 | Stand Alone SHS No. 11 BN Calara | LOS BAÑOS | 2 |  | 8 | 4STY8CL | BATCH 13 | 18372544.86 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 342351 | Stand Alone SHS No. 9 Lalakay | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | BATCH 13 | 32721253.52 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 308506 | Gulang-Gulang NHS, Bocohan Extension | Lucena City | 2 | 1 | 6 | 3STY6CL | BATCH 13 | 16739049.68 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Lucena City | 109734 | Mayao Crossing ES | Lucena City | 2 | 1 | 16 | 4STY16CL | BATCH 13 | 39300967.96 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Quezon | 301297 | Bukal Sur National High School | CANDELARIA | 2 | 1 | 6 | 3STY6CL | BATCH 13 | 15954157.7 |  |  | Completed | 1 |  |  |  | 17DJ0095 | [5 empty] | R.A MENDIOLA CONST & DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301307 | Camohaguin National High School | GUMACA | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20509912.44 |  |  | Completed | 1 |  |  | P00182752LZ-CW1 | 18DL0093 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108759 | Gumaca East CES | GUMACA | 4 | 1 | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Reverted | 0
NC 2017 | TVL | Region IV-A | Quezon | 301331 | Gumaca Integrated School | GUMACA | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20509912.44 |  |  | Completed | 1 |  |  | P00182762LZ-CW1 | 18DL0098 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 301331 | Gumaca Integrated School | GUMACA | 4 |  | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00182763LZ-CW1 | 17DL0191 | 2017-08-22 | 2017-09-06 |  | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301325 | Gumaca National High School | GUMACA | 4 | 1 | 18 | (4) UNIQUE/ (10) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 56232289.36 |  |  | Completed | 1 |  |  | P00182758LZ-CW1 | 18DL0099 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | JAIME B. CHING ENTERPRISES/ BCVILLASEÑOR CONSTRUCTION (JV)
NC 2017 | SHS | Region IV-A | Quezon | 301325 | GUMACA NHS | GUMACA | 4 |  | 20 | 2STY10CL (2 UNITS) | BATCH 13 | 39416311.34 |  |  | Completed | 1 |  |  | P00182759LZ-CW1 | 17DL0181 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-11-27 | 2017-12-15 | EXCELSIUS ENGINEERING SERVICES/ KNOV BUILDERS & SUPPLIES (JV)
NC 2017 | K10 | Region IV-A | Quezon | 108767 | Gumaca West CES (Gumaca West I & II CS merged) | GUMACA | 4 | 1 | 20 | 2STY10CL (2 UNITS) | BATCH 13 | 39416311.34 |  |  | Completed | 1 |  |  | P00182744LZ-CW1 | 17DL0182 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-11-27 | 2017-12-05 | EXCELSIUS ENGG. SERVICES/KNOV BUILDERS & SUPPLIES (J.V.)
NC 2017 | K10 | Region IV-A | Quezon | 301331 | INACLAGAN NHS | GUMACA | 4 |  | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00182764LZ-CW1 | 17DL0184 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-11-27 | 2017-12-05 | ADAD ENGINEERING SERVICES & SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301340 | Lamon Bay SOF - Main Gumaca | GUMACA | 4 | 1 | 19 | (4) REGULAR WORKSHOP/ (10)SCIENCE LAB / (5)ICT LAB | BATCH 13 | 66117036.12 |  |  | Completed | 1 |  |  | P00182766LZ-CW1 | 18DL0102 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | RV LABORTE BUILDERS/TANTUCO CONSTRUCTION AND TRADING CORP. (JV)
NC 2017 | TVL | Region IV-A | Quezon | 301372 | Panikihan NHS | GUMACA | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20840236.33 |  |  | Completed | 1 |  |  | P00182772LZ-CW1 | 18DL0107 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-18 | 2018-01-03 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301372 | Panikihan NHS | GUMACA | 4 |  | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00182773LZ-CW1 | 17DL0196 | 2017-08-22 | 2017-09-06 |  | 2017-11-24 | 2017-12-04 | ADAD ENGINEERING SERVICES & SUPPLY
NC 2017 | K10 | Region IV-A | Quezon |  | SAN DIEGO BUKID ES | GUMACA | 4 | 1 | 3 | 1STY3CL | BATCH 13 | 3768435.02 |  |  | Completed | 1 |  |  | P00182785LZ-CW1 | 17DL0147 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-19 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108799 | CAGACAG ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182745LZ-CW1 | 17DL0137 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 308042 | Cogorin Ibaba National High School - Jongo Extension | LOPEZ | 4 | 1 | 8 | (2) UNIQUE/ (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 26904073.78 |  |  | Completed | 1 |  |  | P00182782LZ-CW1 | 18DL0094 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | DZEE BUILDERS CONSTRUCTION & SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 308042 | Cogorin Ibaba National High School - Jongo Extension | LOPEZ | 4 |  | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182783LZ-CW1 | 17DL0138 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301346 | Cogorin Ibaba NHS (Formerly Lopez NCHSl - Cogorin Ibaba Extension) | LOPEZ | 4 | 1 | 4 | (2) SCIENCE LAB /(2) ICT LAB | BATCH 13 | 14776398.88 |  |  | Completed | 1 |  |  | P00182768LZ-CW1 | 18DL0095 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | BC VILLASEÑOR CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182775LZ-CW1 | 17DL0139 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301388 | Dao National High School (Formerly San Francisco B NHS - San Miguel Dao II Ext.) | LOPEZ | 4 |  | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20840236.33 |  |  | Completed | 1 |  |  | P00182776LZ-CW1 | 18DL0096 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | TVL | Region IV-A | Quezon | 301328 | Guites NHS | LOPEZ | 4 | 1 | 5 | (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 17643155.66 |  |  | Completed | 1 |  |  | P00182760LZ-CW1 | 18DL0097 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301328 | Guites NHS | LOPEZ | 4 |  | 4 | 2STY4CL | BATCH 13 | 8945901.76 |  |  | Completed | 1 |  |  | P00182761LZ-CW1 | 17DL0180 | 2017-08-12 | 2017-09-04 | 2017-09-15 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301387 | Ilayang Ilog-A NHS (Formerly San Francisco B NHS Ilayang Ilog A Ext.) | LOPEZ | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20840236.33 |  |  | Completed | 1 |  |  | P00182774LZ-CW1 | 18DL0101 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2017-12-28 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4 | 1 | 10 | (1) UNIQUE/ (5) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 32307263.45 |  |  | Completed | 1 |  |  | P00182767LZ-CW1 | 18DL0103 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108847 | Lopez West Elementary School Bldg. I | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182748LZ-CW1 | 17DL0193 | 2017-08-22 | 2017-09-06 |  | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301351 | Magallanes NHS | LOPEZ | 4 | 1 | 10 | (1) UNIQUE/ (5) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 32307263.45 |  |  | Completed | 1 |  |  | P00182769LZ-CW1 | 18DL0105 | 2017-11-20 | 2017-12-01 | 2017-12-12 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | SHS | Region IV-A | Quezon | 301351 | MAGALLANES NHS | LOPEZ | 4 |  | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182770LZ-CW1 | 17DL0141 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301352 | Pisipis NHS (Formerly Magallanes NHS Pisipis Extension) | LOPEZ | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20509912.44 |  |  | Completed | 1 |  |  | P00182771LZ-CW1 | 18DL0108 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-18 | 2018-01-03 | DZEE BUILDERS & CONSTRUCTION SUPPLY
NC 2017 | TVL | Region IV-A | Quezon | 301389 | Sto. Nino Ilaya NHS (Formerly San Francisco B NHS Sto. NiÃ±o Ilaya Ext.) | LOPEZ | 4 | 1 | 6 | (1) UNIQUE/ (1) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 20840236.33 |  |  | Completed | 1 |  |  | P00182777LZ-CW1 | 18DL0110 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-18 | 2018-01-03 | R.T.Y. CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 108825 | VERONICA ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00179404LZ-CW1 | 17DL0143 | 2017-08-09 | 2017-08-22 | 2017-09-05 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 108826 | VILLA AURORA ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182747LZ-CW1 | 17DL0209 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | K10 | Region IV-A | Quezon | 108996 | Perez CS | PEREZ | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182749LZ-CW1 | 17DL0239 | 2017-09-20 | 2017-09-30 | 2017-10-12 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301316 | Concepcion National High School | PLARIDEL | 4 | 1 | 6 | (2) REGULAR WORKSHOP/ (2)SCIENCE LAB / (2)ICT LAB | BATCH 13 | 29440506.67 |  |  | Completed | 1 |  |  | P00182756LZ-CW1 | 18DL0205 | 2017-12-05 | 2017-12-15 | 2017-12-27 | 2017-12-28 | 2018-01-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 301316 | Concepcion National High School | PLARIDEL | 4 |  | 6 | 3STY6CL | BATCH 13 | 20005936.84 |  |  | Completed | 1 |  |  | P00182757LZ-CW1 | 18DL0055 | 2017-11-13 | 2017-11-22 | 2017-12-06 | 2017-12-11 | 2017-12-27 | JUNCAN ENTERPRISES
NC 2017 | TVL | Region IV-A | Quezon | 301314 | Cometa NHS Annex | QUEZON | 4 | 1 | 6 | REGULAR WORKSHOP/SCIENCE/ICT LAB | BATCH 13 | 20509912.44 |  |  | Completed | 1 |  |  | P00182754LZ-CW1 | 18DL0114 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-18 | 2018-01-03 | R.V. LABORTE BUILDERS
NC 2017 | SHS | Region IV-A | Quezon | 301314 | Cometa NHS Annex | QUEZON | 4 |  | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182755LZ-CW1 | 17DL0235 | 2017-09-20 | 2017-09-30 | 2017-10-12 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | TVL | Region IV-A | Quezon | 301313 | Evaristo R. Macalintal MNHS (Formerly Cometa NHS) | QUEZON | 4 | 1 | 2 | SCIENCE / ICT LAB | BATCH 13 | 7388199.44 |  |  | Completed | 1 |  |  | P00182753LZ-CW1 | 18DL0115 | 2017-11-20 | 2017-12-01 | 2017-12-13 | 2017-12-18 | 2018-01-03 | E.A. AYALA CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 308046 | San Antonio NHS - Annex | SAN ANTONIO | 2 | 1 | 6 | 3STY6CL | BATCH 13 | 15128023.04 |  |  | Completed | 1 |  |  |  | 17DJ0094 | [5 empty] | VICMAR CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109174 | Bignay II ES | SARIAYA | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 10675853.53 |  |  | Completed | 1 |  |  |  | 17DJ0084 | [5 empty] | KKT CONSTRUCTION AND SUPPLY
NC 2017 | SHS | Region IV-A | Quezon | 301308 | Canda National High School | SARIAYA | 2 | 1 | 8 | 4STY8CL | BATCH 13 | 18675623.3 |  |  | Completed | 1 |  |  |  | 17DJ0050 | [5 empty] | I A BOSQUE CONSTRUCTION
NC 2017 | K10 | Region IV-A | Quezon | 109162 | CASTAÑAS E/S | SARIAYA | 2 | 1 | 6 | 3STY6CL | BATCH 13 | 16692255.75 |  |  | Completed | 1 |  |  |  | 17DJ0079 | [5 empty] | JEMAK CONSTRUCTION & SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 109199 | CABIBIHAN ES | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182750LZ-CW1 | 17DL0202 | 2017-08-24 | 2017-09-08 | 2017-09-19 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 308038 | CABIBIHAN NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182780LZ-CW1 | 17DL0241 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 308038 | CABIBIHAN NHS | TAGKAWAYAN | 4 |  | 3 | 1STY3CL | BATCH 13 | 3768435.02 |  |  | Completed | 1 |  |  | P00182781LZ-CW1 | 17DL0242 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | R.A. MENDIOLA CONSTRUCTION AND DEVELOPER
NC 2017 | SHS | Region IV-A | Quezon | 301336 | KATIMO NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182765LZ-CW1 | 17DL0243 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 109212 | Manato ES | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182751LZ-CW1 | 17DL0244 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 308045 | MANSILAY NHS | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182784LZ-CW1 | 17DL0245 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 308002 | MAPULOT NATIONAL HIGH SCHOOL | TAGKAWAYAN | 4 | 1 | 2 | 1STY2CL | BATCH 13 | 2613745.92 |  |  | Completed | 1 |  |  | P00182779LZ-CW1 | 17DL0246 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | SHS | Region IV-A | Quezon | 301398 | SANMANDELCAR NHS | TAGKAWAYAN | 4 | 1 | 3 | 1STY3CL | BATCH 13 | 3768435.02 |  |  | Completed | 1 |  |  | P00182778LZ-CW1 | 17DL0248 | 2017-09-21 | 2017-10-02 | 2017-10-13 | 2017-11-27 | 2017-12-05 | JUNCAN ENTERPRISES
NC 2017 | K10 | Region IV-A | Quezon | 109263 | Anastacia ES | TIAONG | 2 | 1 | 4 | 2STY4CL | BATCH 13 | 10326732.26 |  |  | Completed | 1 |  |  |  | 17DJ0090 | [5 empty] | DZEE BUILDERS & CONSTRUCTION SUPPLY
NC 2017 | K10 | Region IV-A | Quezon | 308033 | Recto Mem. NHS - Annex (Brgy. Lalig) | TIAONG | 2 | 1 | 9 | 3STY9CL | BATCH 13 | 27108727.34 |  |  | Completed | 1 |  |  |  | 17DJ0080 | [5 empty] | M.A GUINTO CONSTRUCTION
NC 2017 | K10 | Region IV-A | Batangas | 107259 | As-is ES | BAUAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9019901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107270 | Inicbulan ES | BAUAN | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9233901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107454 | Mabini CS | MABINI | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9034401.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107454 | Mabini CS | MABINI | 2 |  | 4 | 2STY4CL | BATCH 14 | 9034401.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107672 | Ilat ES | SAN PASCUAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9503901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas | 107675 | Malakimpook Elementary School | SAN PASCUAL | 2 | 1 | 4 | 2STY4CL | BATCH 14 | 9041901.76 |  |  | Completed | 1
NC 2017 | K10 | Region IV-A | Batangas City | 109558 | Talumpok Silangan ES | BATANGAS CITY(Capital) | 5 | 1 | 4 | 2STY4CL | BATCH 14 | 9280901.76 |  |  | Completed | 1 |  |  |  | 17DE0075 |  | 2017-10-04 | 2017-10-18 | 2017-10-24 | 2017-10-26 | GCF Fetalvero Construction and Enterprises
NC 2017 | K10 | Region IV-A | Batangas City | 109588 | Banaba West ES | BATANGAS CITY(Capital) | 5 | 1 | 6 | 2STY6CL | BATCH 14 | 11838168.02 |  |  | Completed | 1 |  |  |  | 17DE0084 | 2017-10-02 | 2017-10-09 | 2017-10-24 | 2017-10-30 | 2017-11-07 | 6 Jewels Construction
NC 2017 | K10 | Region IV-A | Batangas City | 109590 | Concepcion Es | BATANGAS CITY(Capital) | 5 | 1 | 4 | 2STY4CL | BATCH 14 | 9026901.76 |  |  | Completed | 1 |  |  |  | 17DE0081 |  | 2017-10-06 | 2017-10-20 | 2017-10-26 | 2017-10-30 | Rusmen Builders & Development Corp.
NC 2017 | TVL | Region IV-A | Batangas City | 109591 | Melecio Arceo MES (MAMES) | BATANGAS CITY(Capital) | 5 | 1 | 2 | 2STY2CL | BATCH 14 | 6317008.53 |  |  | Completed | 1 |  |  |  | 17DE0079 |  | 2017-10-06 | 2017-10-20 | 2017-10-26 | 2017-10-30 | 6 Jewels Construction
NC 2017 | K10 | Region IV-A | Batangas City | 109614 | Dao ES | BATANGAS CITY(Capital) | 5 | 1 | 4 | 2STY4CL | BATCH 14 | 9019901.76 |  |  | Completed | 1 |  |  |  | 17DE0080 |  | 2017-10-06 | 2017-10-20 | 2017-10-26 | 2017-10-30 | Westhome Enterprises and Builders Supplies, Inc.
NC 2017 | K10 | Region IV-A | Batangas City | 301472 | Batangas NHS | BATANGAS CITY(Capital) | 5 | 1 | 6 | 3STY6CL | BATCH 14 | 13820515.1 |  |  | Completed | 1 |  |  |  | 17DE0085 | 2017-10-02 | 2017-10-09 | 2017-10-24 | 2017-10-30 | 2017-11-07 | 6 Jewels Onnbaruction
NC 2017 | SHS | Region IV-A | Batangas City | 301474 | Paharang NHS | BATANGAS CITY (Capital) | 5 | 1 | 12 | 4STY12CL | BATCH 14 | 31703789.72 |  |  | Completed | 1 |  |  |  | 17DE0077 |  | 2017-10-04 | 2017-10-18 | 2017-10-24 | 2017-10-26 | Hexamindz Corporation
NC 2017 | SHS | Region IV-A | Batangas City | 301476 | Pinamukan NHS | BATANGAS CITY (Capital) | 5 | 1 | 16 | 4STY16CL | BATCH 14 | 37099737.96 |  |  | Completed | 1 |  |  |  | 17DE0086 | 2017-10-02 | 2017-10-09 | 2017-10-24 | 2017-10-30 | 2017-11-07 | Granby Trading and Construction
NC 2017 | SHS | Region IV-A | Batangas City | 342234 | Gulod Senior High School | BATANGAS CITY(Capital) | 5 | 1 | 20 | 4STY20CL | BATCH 14 | 41570409.74 |  |  | Completed | 1 |  |  |  | 17DE0073 |  |  | 2017-10-04 | 2017-10-10 | 2017-10-18 | Hexamindz Corporation
NC 2017 | SHS | Region IV-A | Batangas City | 342234 | Gulod Senior High School | BATANGAS CITY (Capital) | 5 |  | 16 | 4STY16CL | BATCH 14 | 36991737.96 |  |  | Completed | 1 |  |  |  | 17DE0072 |  |  | 2017-10-04 | 2017-10-10 | 2017-10-18 | Hexamindz Corporation
NC 2017 | SHS | Region IV-A | Batangas City | 342235 | Alangilan Senior High School | BATANGAS CITY(Capital) | 5 | 1 | 16 | 4STY16CL | BATCH 14 | 37126737.96 |  |  | Completed | 1 |  |  |  | 17DE0083 |  | 2017-10-06 | 2017-10-20 | 2017-10-26 | 2017-10-30 | C.S. Rayos Construction & General Services, Inc.
NC 2017 | SHS | Region IV-A | Batangas City | 342235 | Alangilan Senior High School | BATANGAS CITY (Capital) | 5 |  | 12 | 4STY12CL | BATCH 14 | 31723789.72 |  |  | Completed | 1 |  |  |  | 17DE0082 |  | 2017-10-06 | 2017-10-20 | 2017-10-26 | 2017-10-30 | Great Swiss Metal Builders Corp.
NC 2017 | SHS | Region IV-A | Laguna | 301232 | Buenavista NHS | MAGDALENA | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17328973.76 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301249 | Mabitac NHS | MABITAC | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17354738.08 |  |  | Completed | 1
NC 2017 | SHS | Region IV-A | Laguna | 301274 | Gov. Felicisimo T. San Luis National Agro-Industrial High School | SINILOAN | 4 | 1 | 8 | 4STY8CL | BATCH 14 | 17336683.91 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109330 | Mambugan I ES | CITY OF ANTIPOLO | 1 | 1 | 12 | 4STY12CL | BATCH 1 | 34614377.08 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109331 | Mayamot ES | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 19329728.35 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109332 | Muntindilaw ES | CITY OF ANTIPOLO | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 14314903.2 |  |  | Reverted | 0 | [10 empty] | Terminated
NC 2018 | K10 | Region IV-A | Antipolo City | 109334 | Old Boso-boso ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 17776782.68 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109352 | Kaysakat ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 17585873.59 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109357 | Rizza ES | CITY OF ANTIPOLO | 2 | 1 | 12 | 4STY12CL | BATCH 1 | 31970374.45 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Antipolo City | 109319 | Bagong Nayon I ES | CITY OF ANTIPOLO | 1 | 1 | 2 | 2STY2CL | Batch 3 | 7712829.45 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109319 | Bagong Nayon I ES | CITY OF ANTIPOLO | 1 |  | 3 | 3STY3CL | Batch 3 | 11681170.3 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109321 | Bagong Nayon IV ES | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | Batch 3 | 20745430.11 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109342 | Sta. Cruz ES | CITY OF ANTIPOLO | 1 | 1 | 8 | 4STY8CL | Batch 3 | 20745430.11 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109326 | Inuman ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 19684788.4 |  |  | Completed | 1 | [6 empty] | 2018-12-04
NC 2018 | K10 | Region IV-A | Antipolo City | 109326 | Inuman ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20114094.05 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109334 | Old Boso-boso ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20989090.18 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109336 | Peace Village ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 19951599.22 |  |  | Completed | 1 | [6 empty] | 2018-12-11
NC 2018 | K10 | Region IV-A | Antipolo City | 109348 | Calawis ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20176183.35 |  |  | Completed | 1 | [6 empty] | 2018-12-04
NC 2018 | K10 | Region IV-A | Antipolo City | 109357 | Rizza ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21229771.29 |  |  | Completed | 1 | [6 empty] | 2018-11-27
NC 2018 | K10 | Region IV-A | Antipolo City | 109360 | San Ysiro ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 22911459.73 |  |  | Completed | 1 | [6 empty] | 2018-12-04
NC 2018 | K10 | Region IV-A | Antipolo City | 109363 | Upper Kilingan ES | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 21672909.28 |  |  | Completed | 1 | [6 empty] | 2018-12-04
NC 2018 | SHS | Region IV-A | Antipolo City | 301431 | Calawis NHS | CITY OF ANTIPOLO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 20057304.33 |  |  | Completed | 1 | [6 empty] | 2018-12-04
NC 2018 | K10 | Region IV-A | Antipolo City | 109347 | Binayoyo ES (Binayoyo Integrated HS) | CITY OF ANTIPOLO | 2 | 1 | 16 | 4STY16CL | Batch 3 Realignment | 39053328.54 |  |  | Completed | 1 | [6 empty] | 2018-12-11
NC 2018 | K10 | Region IV-A | Bacoor City | 107870 | Habay ES | BACOOR | 2 | 1 | 20 | 4STY20CL | Batch 3 | 65371354.08 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107888 | Queen's Row ES | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 3 | 24456616.73 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107873 | Mambog ES | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 5 | 24742836.33 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107875 | Salinas ES | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 5 | 24735248.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107877 | Aniban CS | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 5 | 24810809.81 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107880 | Gov. P. F. Espiritu ES | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 5 | 27944440.87 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Bacoor City | 107887 | Niog Elementary School | BACOOR | 2 | 1 | 8 | 4STY8CL | Batch 5 | 24860488.91 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107292 | Dacanlao G. Agoncillo Elementary School | CALACA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9053901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107319 | Jocobo Zobel ES (Calatagan ES) | CALATAGAN | 1 | 1 | 9 | 3STY9CL | BATCH 1 | 24538047.73 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107386 | Gulod ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9153901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107390 | Sambal ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11787168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107392 | Talaga ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9133901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107400 | Bukal ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11756168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107403 | Dayapan ES | LEMERY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11841168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107405 | Doña Matilde MES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9026901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107409 | Lemery Pilot ES | LEMERY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9053901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107410 | Lian CS | LIAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9103901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107420 | Prenza ES | LIAN | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9066901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107503 | Kaylaway ES | NASUGBU | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9076901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107512 | Nasugbu West CS | NASUGBU | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 17260570.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107521 | Wawa ES | NASUGBU | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9026901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107707 | Doña Tiburcia Carpio Malvar ES | SANTO TOMAS | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 8901172.25 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107724 | Buli ES | TAAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9029901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107725 | Butong Elementary School | TAAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9053901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107728 | Cultihan-Bolbok ES | TAAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9046901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107734 | Taal CS | TAAL | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9076901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107735 | Tulo ES | TAAL | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11818168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107826 | Gregorio Paradero ES | TUY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9080901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301086 | Bilaran National High School | NASUGBU | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 17317570.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301097 | Dacanlao G. Agoncillo NHS | CALACA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11964168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301097 | Dacanlao Gregorio Agoncillo National High School | CALACA | 1 |  | 12 | 4STY12CL | BATCH 1 | 31952789.72 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342206 | SHS in Lian | LIAN | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 41408409.74 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342211 | SHS in Calatagan | CALATAGAN | 1 | 1 | 16 | 4STY16CL | BATCH 1 | 36910737.96 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107280 | Sinala ES | BAUAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9560901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107433 | Calumpit Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 16795085.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107436 | Lobo Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11856168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107439 | Malapad Na Parang ELEMENTARY SCHOOL | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 16331085.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107440 | Masaguitsit ES | LOBO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9230901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107441 | Nagtaluntong ES | LOBO | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9380901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107442 | Nagtoctoc PS | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 16613085.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107447 | Sawang Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 16079085.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107448 | Soloc Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12314168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107449 | Anilao ES | MABINI | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11891168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107455 | Mainaga-San Francisco ES | MABINI | 2 | 1 | 8 | 2STY8CL | BATCH 1 | 17107790.26 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107464 | Solo ES | MABINI | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12298168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107669 | Banaba ES | SAN PASCUAL | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11910168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107820 | Tingloy CS | TINGLOY | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9826901.76 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 301115 | Anselmo Sandoval MNHS (Mabini NHS) | MABINI | 2 | 1 | 8 | 4STY8CL | BATCH 1 | 17336570.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107212 | Pook ES | AGONCILLO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 8945901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107220 | Pinagkurusan Elementary School | ALITAGTAG | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12288802.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107252 | Magapi ES | BALETE | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9262218.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107254 | Malabanan ES | BALETE | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9287218.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107694 | Sta. Teresita CS | SANTA TERESITA | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12197485.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107720 | Sto. Tomas North CS | SANTO TOMAS | 3 | 1 | 6 | 3STY6CL | BATCH 1 | 13839515.1 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107736 | Venancio Trinidad Sr. Memorial School | TALISAY | 3 | 1 | 6 | 2STY6CL | BATCH 1 | 12313802.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107741 | Jorge B. Vargas MES | TALISAY | 3 | 1 | 9 | 3ST9CL | BATCH 1 | 27818047.73 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301095 | Coral na Munti NHS | AGONCILLO | 3 | 1 | 4 | 2STY4CL | BATCH 1 | 9287218.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301122 | Malvar National High School | MALVAR | 3 | 1 | 20 | 4STY20CL | BATCH 1 | 45108409.74 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301143 | San Pedro NHS | SANTO TOMAS | 3 | 1 | 12 | 4ST12CL | BATCH 1 | 35249789.72 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301146 | Santa Anastacia-San Rafael NHS | SANTO TOMAS | 3 | 1 | 8 | 4STY8CL | BATCH 2 Realignment | 20208521.67 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342219 | SHS in Sto. Tomas | SANTO TOMAS | 3 | 1 | 8 | 4STY8CL | BATCH 2 Realignment | 17506643.07 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas |  | Talisay SHS | TALISAY | 3 | 1 | 8 | 4STY8CL | BATCH 1 | 21329450.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107352 | Bungahan ES | Ibaan | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 13691000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107353 | Coliat ES | Ibaan | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10210500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107554 | Maalas-as ES | Rosario | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10260500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107616 | Laiya ES | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10160500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107617 | Libato ES | San Juan | 4 | 1 | 6 | 3STY6CL | BATCH 1 | 16055000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107634 | Subukin ES | San Juan | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10210500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107638 | Tipas ES | San Juan | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 13691000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301094 | Calubcob I.0 NHS | San Juan | 4 | 1 | 12 | 4STY 12CL | BATCH 1 | 35326250 |  |  | Completed | 1
NC 2018 | TVL | Region IV-A | Batangas | 301098 | Dagatan NHS | Taysan | 4 | 1 | 8 | 4STY 8WS | BATCH 1 | 41320900 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 301137 | Pinagbayanan NHS | Taysan | 4 | 1 | 4 | 2STY4CL | BATCH 1 | 10185500 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 301153 | Dr. Juan A. Pastor MNHS (Talaibon NHS) | Ibaan | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 13641000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 307707 | Nagsaulay NHS | San Juan | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 13571000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas |  | Munting Tubig ES | Ibaan | 4 | 1 | 6 | 2STY6CL | BATCH 1 | 13721000 |  |  | Completed | 1
NC 2018 | TVL | Region IV-A | Batangas |  | San Juan Senior High School | San Juan | 4 | 1 | 4 | 4STY 4WS | BATCH 1 | 20513220.35 |  |  | Completed | 1
NC 2018 | TVL | Region IV-A | Batangas |  | Taysan SHS | Taysan | 4 | 1 | 4 | 4STY 4WS | BATCH 1 | 20513220.35 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107292 | Dacanlao G. Agoncillo Elementary School | CALACA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 9103901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107397 | Bagong Pook Elementary School | LIAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 29482715 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107503 | Kaylaway Elementary School | NASUGBU | 1 | 1 | 4 | 2STY4CL | Batch 3 | 14774182 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342207 | SHS in Tuy | TUY | 1 | 1 | 12 | 4STY12CL | Batch 3 | 52043677 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342211 | SHS in Calatagan | CALATAGAN | 1 | 1 | 16 | 4STY16CL | Batch 3 | 55388356 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342204 | Laurel SHS | LAUREL | 3 | 1 | 16 | 4STY16CL | Batch 3 | 37177053.96 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Batangas | 342216 | Agoncillo SHS | AGONCILLO | 3 | 1 | 8 | 4STY8CL | Batch 3 | 17521770.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas | 107585 | Bagong Pook Elementary School | SAN JOSE | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10235500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Batangas City | 109601 | Conde Labac Elementary School | BATANGAS CITY (Capital) | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 9128972.94 |  |  | Completed | 1 |  |  |  | 18DEO241 | 2018-08-09 | 2018-08-16 | 2018-08-28 | 2018-08-31 | 2018-09-07 | Greenfields Construction
NC 2018 | K10 | Region IV-A | Batangas City | 109603 | Dumuclay ES | BATANGAS CITY (Capital) | 5 | 1 | 4 | 2STY4CL | BATCH 1 | 9280901.76 |  |  | Completed | 1 |  |  |  | 18DEO239 | 2018-08-09 | 2018-08-16 | 2018-08-28 | 2018-08-31 | 2018-09-07 | Greenfields Construction
NC 2018 | K10 | Region IV-A | Batangas City | 109616 | Libjo ES | BATANGAS CITY (Capital) | 5 | 1 | 8 | 2STY8CL | BATCH 1 | 15702147.49 |  |  | Completed | 1 |  |  |  | 18DEO242 | 2018-08-09 | 2018-08-16 | 2018-08-28 | 2018-08-31 | 2018-09-07 | Sandstorm Construction
NC 2018 | SHS | Region IV-A | Batangas City | 301471 | Banaba West NHS | BATANGAS CITY (Capital) | 5 | 1 | 8 | 4STY8CL | BATCH 1 | 17640570.67 |  |  | Completed | 1 |  |  |  | 18DEO224 | 2018-07-10 | 2018-07-17 | 2018-07-31 | 2018-08-15 | 2018-08-24 | Greenfields Construction
NC 2018 | SHS | Region IV-A | Batangas City | 301473 | Conde Labac SHS | BATANGAS CITY (Capital) | 5 | 1 | 8 | 4STY8CL | BATCH 1 | 17509570.67 |  |  | Completed | 1 |  |  |  | 18DEO216 | 2018-07-03 | 2018-07-10 | 2018-07-24 | 2018-08-13 | 2018-08-22 | 6 Jewels Construction
NC 2018 | SHS | Region IV-A | Batangas City | 301473 | Conde Labac SHS | BATANGAS CITY (Capital) | 5 |  | 4 | 2STY4CL | BATCH 1 | 9070901.76 |  |  | Completed | 1 |  |  |  | 18DEO214 | 2018-07-03 | 2018-07-10 | 2018-07-24 | 2018-08-13 | 2018-08-22 | 6 Jewels Construction
NC 2018 | SHS | Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 5 | 1 | 16 | 4STY16CL | BATCH 1 | 37245737.96 |  |  | Completed | 1 |  |  |  | 18DEO210 | 2018-08-01 | 2018-08-08 | 2018-08-23 | 2018-08-29 | 2018-09-07 | Vicmar Construction Inc./ RM Tejada Construction and Supplies Corp.
NC 2018 | SHS | Region IV-A | Batangas City | 308201 | Natalia V. Ramos Memorial National High School | BATANGAS CITY (Capital) | 5 |  | 8 | 4STY8CL | BATCH 1 | 17417570.67 |  |  | Completed | 1 |  |  |  | 18DEO211 | 2018-06-27 | 2018-07-04 | 2018-07-17 | 2018-07-31 | 2018-08-09 | Tristan Tejada Construction
NC 2018 | SHS | Region IV-A | Batangas City |  | Conde Labac NHS | BATANGAS CITY (Capital) | 5 | 1 | 12 | 4STY12CL | BATCH 1 | 31723789.72 |  |  | Completed | 1 |  |  |  | 18DEO240 | 2018-08-09 | 2018-08-16 | 2018-08-28 | 2018-08-31 | 2018-09-07 | South Builders and Construction Supplies
NC 2018 | K10 | Region IV-A | Binan City | 108218 | Dela Paz West ES | CITY OF BIÑAN | 1 | 1 | 12 | 4STY12CL | Batch 3 | 41530000 |  |  | Completed | 1 |  |  |  | 18DI0171 | 2018-11-30 | 2018-12-07 | 2018-12-19 |  | 2019-01-11 | Rey-Jan Enterprises
NC 2018 | K10 | Region IV-A | Binan City | 108227 | Platero ES | CITY OF BIÑAN | 1 | 1 | 12 | 4STY12CL | Batch 3 | 41488400 |  |  | Completed | 1 |  |  |  | 18DI0170 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | Harvee Enterprises
NC 2018 | K10 | Region IV-A | Binan City | 108228 | San Francisco ES | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25497800 |  |  | Completed | 1 |  |  |  | 18DI0160 | 2018-11-29 | 2018-12-06 | 2018-12-18 | 2018-12-21 | 2019-01-10 | Yurusa Construction & Development Corp.
NC 2018 | K10 | Region IV-A | Binan City | 108232 | Timbao ES | CITY OF BIÑAN | 1 | 1 | 16 | 4STY16CL | Batch 3 | 51050300 |  |  | Completed | 1 |  |  |  | 18DI0173 | 2018-11-30 | 2018-12-07 | 2018-12-19 |  | 2019-01-11 | Rey-Jan Enterprises
NC 2018 | K10 | Region IV-A | Binan City | 164513 | Malaban East ES | CITY OF BIÑAN | 1 | 1 | 12 | 4STY12CL | Batch 3 | 41377300 |  |  | Completed | 1 |  |  |  | 18DI0169 | 2018-11-30 | 2018-12-07 | 2018-12-19 |  | 2019-01-11 | 806 Builders/Wilcu Construction, JV
NC 2018 | K10 | Region IV-A | Binan City | 301254 | Nereo R. Joaquin National High School | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25244500 |  |  | Completed | 1 |  |  |  | 18DI0165 | 2018-11-30 | 2018-12-07 | 2018-12-19 |  | 2019-01-11 | Le Bron Construction
NC 2018 | K10 | Region IV-A | Binan City | 307901 | Jacobo Z. Gonzales Memorial National High School | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25111684 |  |  | Completed | 1 |  |  |  | 18DI0157 | 2018-11-29 | 2018-12-06 | 2018-12-18 |  | 2019-01-10 | SBR Center Builders Inc.
NC 2018 | K10 | Region IV-A | Binan City | 307901 | Jacobo Z. Gonzales Memorial National High School | CITY OF BIÑAN | 1 |  | 8 | 4STY8CL | Batch 3 | 25275174 |  |  | Completed | 1 |  |  |  | 18DI0158 | 2018-11-29 | 2018-12-06 | 2018-12-18 |  | 2019-01-10 | SBR Center Builders Inc.
NC 2018 | K10 | Region IV-A | Binan City | 307901 | Jacobo Z. Gonzales Memorial National High School | CITY OF BIÑAN | 1 |  | 8 | 4STY8CL | Batch 3 | 25130980 |  |  | Completed | 1 |  |  |  | 18DI0159 | 2018-11-29 | 2018-12-06 | 2018-12-18 | 2018-12-21 | 2019-01-10 | C.S. Rayos Construction and General Services, Inc.
NC 2018 | K10 | Region IV-A | Cabuyao City | 108239 | Cabuyao CS | CABUYAO | 2 | 1 | 16 | 4STY16CL | Batch 3 | 49960590 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Calamba City | 109817 | Jose Rizal MS | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 38934100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Calamba City | 109827 | Turbina Elementary School | CITY OF CALAMBA | 2 | 1 | 20 | 4STY20CL | Batch 3 | 57593500 |  |  | Completed | 1 |  |  |  | 18DI0163 |  |  | 2018-12-18 | 2018-12-26
NC 2018 | K10 | Region IV-A | Calamba City | 109840 | Bubuyan ES | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 39063290 |  |  | Completed | 1 |  |  |  | 18DI0162 |  |  | 2018-12-18 | 2018-12-26
NC 2018 | K10 | Region IV-A | Calamba City | 109858 | Punta Elementary School | CITY OF CALAMBA | 2 | 1 | 12 | 4STY12CL | Batch 3 | 41562900 |  |  | Completed | 1 |  |  |  | 18DI0172 |  |  | 2018-12-19
NC 2018 | K10 | Region IV-A | Calamba City | 308702 | Lecheria National High School | CITY OF CALAMBA | 2 | 1 | 20 | 4STY20CL | Batch 3 | 58457400 |  |  | Completed | 1 |  |  |  | 18DI0164 |  |  | 2018-12-18 | 2018-12-26
NC 2018 | K10 | Region IV-A | Cavite | 108081 | Noveleta ES | NOVELETA | 1 | 1 | 20 | 4STY20CL | BATCH 1 | 41723409.74 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108085 | San Juan Elementary School | NOVELETA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9071901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107857 | Amadeo ES | AMADEO | 6 | 1 | 16 | 4STY16CL | BATCH 1 | 37162737.96 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107858 | Dagatan ES | AMADEO | 6 | 1 | 6 | 3STY6CL | BATCH 1 | 13823515.1 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107860 | Loma ES | AMADEO | 6 | 1 | 4 | 2STY4CL | BATCH 1 | 9571901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107861 | Maitim ES | AMADEO | 6 | 1 | 4 | 2STY4CL | BATCH 1 | 9071901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107863 | Pangil ES | AMADEO | 6 | 1 | 8 | 4STY8CL | BATCH 1 | 17285570.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107864 | Salaban ES | AMADEO | 6 | 1 | 4 | 2STY4CL | BATCH 1 | 9071901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107866 | Tamakan ES | AMADEO | 6 | 1 | 4 | 2STY4CL | BATCH 1 | 9071901.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | General trias City | 107953 | Juliano C. Brosas ES | CITY OF GENERAL TRIAS | 6 | 1 | 8 | 4STY8CL | BATCH 1 | 17285570.67 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108155 | Amaya ES | TANZA | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41828409.74 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108158 | Capipisa ES | TANZA | 6 | 1 | 16 | 4STY16CL | BATCH 1 | 37162737.96 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108161 | Florentino Joya ES | TANZA | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.725 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108165 | Paradahan ES | TANZA | 6 | 1 | 20 | 4STY20CL | BATCH 1 | 41660409.74 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108167 | Sanja Mayor ES | TANZA | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 31901789.72 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108169 | Sta. Cruz (Bucal) ES | TANZA | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 31649789.72 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | General trias City | 164017 | Sunny Brooke Elementary School | CITY OF GENERAL TRIAS | 6 | 1 | 12 | 4STY12CL | BATCH 1 | 33649789.72 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107895 | Lantic ES | CARMONA | 5 | 1 | 16 | 4STY16CL | Batch 3 | 45785232.32 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 107941 | San Gabriel II ES | GEN. MARIANO ALVAREZ | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54156382.12 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108110 | Silang Central School | SILANG | 5 | 1 | 20 | 4STY20CL | Batch 3 | 54126785.44 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108111 | Silang West ES | SILANG | 5 | 1 | 12 | 4STY12CL | Batch 3 | 40952142.03 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Cavite | 342284 | SHS in Carmona | CARMONA | 5 | 1 | 8 | 4STY8CL | Batch 3 | 19953162.24 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Cavite | 342284 | SHS in Carmona | CARMONA | 5 |  | 12 | 4STY12CL | Batch 3 | 40354184.78 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 307809 | Luis Aguado NHS | TRECE MARTIRES CITY (Capital) | 6 | 1 | 20 | 4STY20CL | Batch 3 | 61158848.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Cavite | 108130 | Pasong Langka ES | SILANG | 5 | 1 | 8 | 4STY8CL | Batch 5 | 19955229.37 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Cavite | 301216 | Tagaytay City NHS Annex (Senior HS) | TAGAYTAY CITY | 8 | 1 | 64 | 4STY100CL (PHASE 1) | Batch 5 | 210000000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107904 | Langkaan ES | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | Batch 3 | 40985068.89 |  |  | Completed | 1 |  |  |  | 18DQ0104 |  | 2018-09-13 | 2018-10-10 | 2018-11-15 | 2018-12-13 | KLDS Trading and Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107907 | Paliparan II ES | Dasmariñas City | 4 |  | 24 | 4STY24CL | Batch 3 | 62294037.58 |  |  | Completed | 1 |  |  |  | 18DQ0115 |  | 2018-09-18 | 2018-10-12 | 2018-11-15 | 2018-12-06 | KLDS Trading and Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107913 | Vicente P. Villanueva MS | Dasmariñas City | 4 | 1 | 20 | 4STY20CL | Batch 3 | 55534418.01 |  |  | Completed | 1 |  |  |  | 18DQ0107 |  | 2018-09-13 | 2018-10-10 | 2018-11-15 | 2018-12-06 | R.A. Del Rosario Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107919 | San Nicolas ES | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | Batch 3 | 40520525.77 |  |  | Completed | 1 |  |  |  | 18DQ0111 |  | 2018-09-18 | 2018-10-12 | 2018-11-15 | 2018-12-13 | KLDS Trading and Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107920 | Sta Cruz ES | Dasmariñas City | 4 | 1 | 24 | 4STY24CL | Batch 3 | 61203640.62 |  |  | Completed | 1 |  |  |  | 18DQ0114 |  | 2018-09-18 | 2018-10-12 | 2018-11-15 | 2018-12-06 | KLDS Trading and Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 107921 | Dr. Jose P. Rizal ES | Dasmariñas City | 4 | 1 | 24 | 4STY24CL | Batch 3 | 61187890.75 |  |  | Completed | 1 |  |  |  | 18DQ0113 |  | 2018-09-18 | 2018-10-12 | 2018-11-15 | 2018-12-07 | R.A. Del Rosario Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 300536 | Salawag NHS | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | Batch 3 | 41016237.56 |  |  | Completed | 1 |  |  |  | 18DQ0112 |  | 2018-09-18 | 2018-10-12 | 2018-11-15 | 2018-12-07 | R.A. Del Rosario Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 301181 | New Era NHS | Dasmariñas City | 4 | 1 | 12 | 4STY12CL | Batch 3 | 41177217.25 |  |  | Completed | 1 |  |  |  | 18DQ0105 |  | 2018-09-13 | 2018-10-10 | 2018-11-15 | 2018-12-17 | Hausland Construction/CBS Construction
NC 2018 | K10 | Region IV-A | Dasmariñas City | 301181 | New Era NHS | Dasmariñas City | 4 |  | 12 | 4STY12CL | Batch 3 | 41039248.44 |  |  | Completed | 1 |  |  |  | 18DQ0106 |  | 2018-09-13 | 2018-10-10 | 2018-11-15 | 2018-12-14 | Hausland Construction/CBS Construction
NC 2018 | K10 | Region IV-A | Imus City | 107969 | Anabu II Elementary School | IMUS | 3 | 1 | 20 | 4STY20CL | Batch 3 | 61637522.36 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Imus City | 107973 | Cayetano Topacio Elementary School | IMUS | 3 | 1 | 20 | 4STY20CL | Batch 3 | 61797080.15 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Imus City | 107981 | Alapan II Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL | Batch 3 | 26487315.32 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Imus City | 107987 | Malagasang II ES | IMUS | 3 | 1 | 20 | 4STY20CL (L-Type) | Batch 3 | 61797080.15 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Imus City | 107990 | Toclong ES | IMUS | 3 | 1 | 20 | 4STY20CL (L-Type) | Batch 3 | 61637522.36 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Imus City | 164002 | Palico Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL | Batch 3 | 26646873.11 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Laguna | 108419 | Chrysanthemum Village Elementary School | SAN PEDRO | 1 | 1 | 20 | 4STY20CL | Batch 3 | 59950370 |  |  | Completed | 1 |  |  |  | 18DI0175 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2018 | K10 | Region IV-A | Laguna | 108420 | Cuyab Elementary School | SAN PEDRO | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40347700 |  |  | Completed | 1 |  |  |  | 18DI0166 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | LE BRON CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108423 | Landayan ES | SAN PEDRO | 1 | 1 | 12 | 4STY12CL | Batch 3 | 40653300 |  |  | Completed | 1 |  |  |  | 18DI0168 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | MAGNA RICH TRADING & CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108426 | Pacita Complex I ES | SAN PEDRO | 1 | 1 | 8 | 4STY8CL | Batch 3 | 24261670 |  |  | Completed | 1 |  |  |  | 18DI0149 | 2018-11-24 | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2019-01-10 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORPORATION
NC 2018 | K10 | Region IV-A | Laguna | 108432 | San Pedro CES | SAN PEDRO | 1 | 1 | 8 | 4STY8CL | Batch 3 | 25001900 |  |  | Completed | 1 |  |  |  | 18DI0156 | 2018-11-29 | 2018-12-06 | 2018-12-18 | 2018-12-21 | 2019-01-10 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORPORATION
NC 2018 | K10 | Region IV-A | Laguna | 164528 | Southville 3A ES | SAN PEDRO | 1 | 1 | 8 | 4STY8CL | Batch 3 | 24713700 |  |  | Completed | 1 |  |  |  | 18DI0155 | 2018-11-29 | 2018-12-06 | 2018-12-18 | 2018-12-21 | 2019-01-10 | EBUILDERS CONSTRUCTION & DEVELOPMENT CORP.
NC 2018 | K10 | Region IV-A | Laguna | 108201 | Bitin Elementary School | BAY | 2 | 1 | 12 | 4STY12CL | Batch 3 | 40620200 |  |  | Completed | 1 |  |  |  | 18DI0152 | 2018-11-24 | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2019-01-10 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2018 | K10 | Region IV-A | Laguna | 108202 | Calo ES | BAY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 25033120 |  |  | Completed | 1 |  |  |  | 18DI0150 | 2018-11-24 | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2019-01-10 | BHENLLABIEN BUILDERS CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108209 | Sta. Cruz Elementary School | BAY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 25880800 |  |  | Completed | 1 |  |  |  | 18DI0161 | 2018-11-29 | 2018-12-06 | 2018-12-14 | 2018-12-21 | 2019-01-10 | ST. MATTHEW GEN. CONTRACTOR & DEVELOPMENT CORPORATION
NC 2018 | K10 | Region IV-A | Laguna | 108312 | P. Rizal ES (Putho ES) | LOS BAÑOS | 2 | 1 | 12 | 4STY12CL | Batch 3 | 40595800 |  |  | Completed | 1 |  |  |  | 18DI0167 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2018 | K10 | Region IV-A | Laguna | 301231 | Bitin NHS | BAY | 2 | 1 | 20 | 4STY20CL | Batch 3 | 57475000 |  |  | Completed | 1 |  |  |  | 18DI0154 | 2018-11-24 | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2019-01-10 | HYPER J CONSTRUCTION AND SUPPLY
NC 2018 | K10 | Region IV-A | Laguna | 301246 | Los Baños National High School - Poblacion | LOS BAÑOS | 2 | 1 | 20 | 4STY20CL | Batch 3 | 59379400 |  |  | Completed | 1 |  |  |  | 18DI0174 | 2018-11-30 | 2018-12-07 | 2018-12-19 | 2018-12-26 | 2019-01-11 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2018 | K10 | Region IV-A | Laguna | 108195 | San Ildefonso Es | Alaminos | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10088560.79 |  |  | Completed | 1 |  |  | P00273941LZ_CW1 | 18DP0099 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2018 | K10 | Region IV-A | Laguna | 108198 | San Roque Elementary | Alaminos | 3 | 1 | 4 | 2STY4CL | Batch 3 | 10274057.19 |  |  | Completed | 1 |  |  | P00273942LZ_CW1 | 18DP0098 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | NEW RICH GENERAL CONT. SERVICES & TRADING COMPANY INC.
NC 2018 | K10 | Region IV-A | Laguna | 108257 | Imok ES | Calauan | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13550148.86 |  |  | Completed | 1 |  |  | P00273943LZ_CW1 | 18DP0091 |  | 2018-11-07 | 2018-11-20 | 2018-12-07 | 2018-12-12 | NEW RICH GENERAL CONT. SERVICES & TRADING COMPANY INC.
NC 2018 | K10 | Region IV-A | Laguna | 108268 | T.C Dator MES (Pulong Dayap ES) | Calauan | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13250148.86 |  |  | Completed | 1 |  |  | P00273944LZ_CW1 | 18DP0095 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | ROSTEL CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108297 | Liliw CES | Liliw | 3 | 1 | 20 | 4STY20CL | Batch 3 | 45449656.83 |  |  | Completed | 1 |  |  | P00273945LZ_CW1 | 18DP0096 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | JAIME B. CHING ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108355 | Banka-Banka ES | Nagcarlan | 3 | 1 | 12 | 2STY12CL | Batch 3 | 26445921.67 |  |  | Completed | 1 |  |  | P00273946LZ_CW1 | 18DP0094 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | MEGA M BUILDERS
NC 2018 | K10 | Region IV-A | Laguna | 108356 | Bunga ES | Nagcarlan | 3 | 1 | 12 | 2STY12CL | Batch 3 | 26045921.67 |  |  | Completed | 1 |  |  | P00273947LZ_CW1 | 18DP0093 |  | 2018-11-21 | 2018-12-04 | 2018-12-21 | 2018-12-27 | LPO ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108496 | G. Herradura ES (Nanhaya ES) | Victoria | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13227505.95 |  |  | Completed | 1 |  |  | P00273948LZ_CW1 | 18DP0092 |  | 2018-11-07 | 2018-11-20 | 2018-12-07 | 2018-12-12 | LPO ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108501 | T. Daguinsin ES (San Roque ES) | Victoria | 3 | 1 | 6 | 2STY6CL | Batch 3 | 13227505.95 |  |  | Completed | 1 |  |  | P00273949LZ_CW1 | 18DP0088 |  | 2018-11-07 | 2018-11-20 | 2018-12-07 | 2018-12-12 | POWER K CONSTRUCTION SUPPLY AND SERVICES
NC 2018 | K10 | Region IV-A | Laguna | 301242 | Ibayiw National High School | Alaminos | 3 | 1 | 20 | 4STY20CL | Batch 3 | 45049656.83 |  |  | Completed | 1 |  |  | P00273950LZ_CW1 | 18DP0090 |  | 2018-11-07 | 2018-11-20 | 2018-12-07 | 2018-12-12 | NEWBIG FOUR J CONSTRUCTION INC.
NC 2018 | K10 | Region IV-A | Laguna | 108272 | Burol Elementary School | CAVINTI | 4 | 1 | 9 | 3STY9CL | Batch 3 | 25465575.24 |  |  | Completed | 1 |  |  | P00273951LZ-CW1 | 18DH0101 |  | 2018-10-19 | 2018-10-31 | 2018-11-21 | 2018-11-28 | J.B. ALARCON ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108278 | LUMOT ES | CAVINTI | 4 | 1 | 12 | 3STY12CL | Batch 3 | 30465465.14 |  |  | Completed | 1 |  |  | P00273952LZ-CW1 | 18DH0102 |  | 2018-10-19 | 2018-10-31 | 2018-11-21 | 2018-11-28 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2018 | K10 | Region IV-A | Laguna | 108280 | Sumucab ES | CAVINTI | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9517388.94 |  |  | Completed | 1 |  |  | P00273953LZ-CW1 | 18DH0105 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | 11 DIAMOND EAGLE CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108284 | Famy Elementary School | FAMY | 4 | 1 | 6 | 2STY6CL | Batch 3 | 12298609.36 |  |  | Completed | 1 |  |  | P00273954LZ-CW1 | 18DH0106 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | ENC ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108320 | San Isidro Elementary School | LUISIANA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9517388.94 |  |  | Completed | 1 |  |  | P00273955LZ-CW1 | 18DH0107 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | BCVILLASENOR CONSTRUCTION
NC 2018 | K10 | Region IV-A | Laguna | 108332 | San Juan CS (Kalayaan) | KALAYAAN | 4 | 1 | 12 | 4STY12CL | Batch 3 | 32672511.39 |  |  | Completed | 1 |  |  | P00273956LZ-CW1 | 18DH0114 |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2018-01-07 | R'CEL GENERAL CONTRACTOR & GEN
NC 2018 | K10 | Region IV-A | Laguna | 108410 | Pansol ES | PILA | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17851629.25 |  |  | Completed | 1 |  |  | P00273957LZ-CW1 | 18DH0115 |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2018-01-07 | J.B. ALARCON ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108412 | Pinagbayanan ES | PILA | 4 | 1 | 8 | 4STY8CL | Batch 3 | 17783036.11 |  |  | Completed | 1 |  |  | P00273958LZ-CW1 | 18DH0116 |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2018-01-07 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2018 | K10 | Region IV-A | Laguna | 108436 | Bagumbayan ES | SANTA CRUZ (Capital) | 4 | 1 | 9 | 3STY9CL | Batch 3 | 25483270.44 |  |  | Completed | 1 |  |  | P00273959LZ-CW1 | 18DH0099 |  | 2018-10-19 | 2018-10-31 | 2018-11-21 | 2018-11-28 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2018 | K10 | Region IV-A | Laguna | 108439 | Duhat ES | SANTA CRUZ (Capital) | 4 | 1 | 9 | 3STY9CL | Batch 3 | 25483270.44 |  |  | Completed | 1 |  |  | P00273960LZ-CW1 | 18DH0108 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | J.B. ALARCON ENTERPRISES
NC 2018 | K10 | Region IV-A | Laguna | 108440 | Gatid ES | SANTA CRUZ (Capital) | 4 | 1 | 16 | 4STY16CL | Batch 3 | 38222970.83 |  |  | Completed | 1 |  |  | P00273961LZ-CW1 | 18DH0117 |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2018-01-07 | J.B. ALARCON ENTERPRISES / MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2018 | K10 | Region IV-A | Laguna | 108446 | Santa Cruz CES | SANTA CRUZ (Capital) | 4 | 1 | 16 | 4STY16CL | Batch 3 | 38222970.83 |  |  | Completed | 1 |  |  | P00273962LZ-CW1 | 18DH0100 |  | 2018-10-19 | 2018-10-31 | 2018-11-21 | 2018-11-28 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2018 | K10 | Region IV-A | Laguna | 108456 | Calangay Elementary School | SANTA MARIA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 9535084.14 |  |  | Completed | 1 |  |  | P00273963LZ-CW1 | 18DH0109 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2018 | SHS | Region IV-A | Laguna | 301226 | Balian NHS | PANGIL | 4 | 1 | 16 | 4STY16CL | Batch 3 | 38222970.83 |  |  | Completed | 1 |  |  | P00273964LZ-CW1 | 18DH0118 |  | 2018-12-14 | 2018-12-26 | 2018-12-28 | 2018-01-03 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2018 | K10 | Region IV-A | Laguna | 301255 | Paagahan NHS | MABITAC | 4 | 1 | 6 | 3STY6CL | Batch 3 | 14371042.29 |  |  | Completed | 1 |  |  | P00273965LZ-CW1 | 18DH0110 |  | 2018-11-26 | 2018-12-07 | 2018-12-21 | 2018-01-03 | DSO ENTERPRISES
NC 2018 | SHS | Region IV-A | Laguna | 342344 | Pakil SHS | PAKIL | 4 | 1 | 2 | 1STY2CL | Batch 3 | 2880991.06 |  |  | Completed | 1 |  |  | P00273966LZ-CW1 | 18DH0103 |  | 2018-10-19 | 2018-10-31 | 2018-11-21 | 2018-11-28 | J.B. ALARCON ENTERPRISES
NC 2018 | K10 | Region IV-A | Lipa City | 109642 | Brion- Silva ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37166250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109643 | Don Leon E. Dolor MS | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109645 | Edilberto L. Mendoza MES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36836250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109646 | Malitlit ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20817500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36946250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109648 | San Adriano ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36836250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109649 | San Benito ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109650 | San Celestino ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36946250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109651 | San Francisco ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109654 | Sto. Niño ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109655 | Sto. Toribio ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109660 | Bulacnin ES | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42185000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109661 | Dagatan ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109662 | Inosloban-Marawoy ES | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42625000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109662 | Inosloban-Marawoy ES | LIPA CITY | 4 |  | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109664 | Plaridel ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109665 | San Lucas ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 4 | 1 | 20 | 4STY20CL | BATCH 1 | 46576200 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109670 | Leoncio L Patulot Memorial school | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109672 | Bolbok Elementary School | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42625000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109675 | Kayumanggi ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42625000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109680 | Mabini ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109681 | Malagonlong ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20817500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109682 | Pagolingin Bata ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109683 | Pagolingin ES | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42625000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109684 | Rizal ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109685 | Sampaguita ES | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109686 | San Guillermo ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20707500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109691 | Fernando Air Base ES | LIPA CITY | 4 | 1 | 20 | 4STY20CL | BATCH 1 | 46326200 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109691 | Fernando Air Base ES | LIPA CITY | 4 |  | 12 | 4STY12CL | BATCH 1 | 36736250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109694 | Pangao Elementary | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 37386250 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109697 | Rafael M. Lojo MS | LIPA CITY | 4 | 1 | 20 | 4STY20CL | BATCH 1 | 46796200 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109699 | San Salvador ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20817500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 109704 | Tangway ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lipa City | 167001 | Pusil ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 21257500 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Lipa City | 301490 | Fernando Air Base NHS | LIPA CITY | 4 | 1 | 80 | 4 UNITS 4STY20CL | BATCH 1 | 185304800 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Lipa City | 301496 | Pinagkawitan NHS | LIPA CITY | 4 | 1 | 16 | 4STY16CL | BATCH 1 | 42625000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Lipa City | 301497 | Pinagtongulan NHS | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36946250 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region IV-A | Lipa City | 301500 | San Isidro NHS | LIPA CITY | 4 | 1 | 12 | 4STY12CL | BATCH 1 | 36946250 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region IV-A | Lipa City |  | Anangi ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20707500 |  |  | Completed | 1
NC 2018 | k10 | Region IV-A | Lipa City |  | Anilao Labac ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | BATCH 1 | 20597500 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lucena City | 109717 | Gulang - Gulang ES | LUCENA CITY (Capital) | 2 | 1 | 20 | 4STY20CL | Batch 3 | 47711096.85 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Lucena City | 109730 | Dalahican ES | LUCENA CITY (Capital) | 2 | 1 | 20 | 4STY20CL | Batch 3 | 54100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108978 | Amaga ES | PATNANUNGAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4690100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108984 | Guinaygayan ES | PATNANUNGAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4690100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108986 | Katakian ES | PATNANUNGAN | 1 | 1 | 10 | 2STY10CL | Batch 3 | 29598528.125 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108987 | Kilogan ES | PATNANUNGAN | 1 | 1 | 10 | 2STY10CL | Batch 3 | 29339818.75 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108990 | Patnanungan Norte ES | PATNANUNGAN | 1 | 1 | 10 | 2STY10CL | Batch 3 | 29117625.625 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109019 | Anawan ES | POLILLO | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4619624.5 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109024 | Binibitinan ES | POLILLO | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4669624.5 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109026 | Bonbon ES | PANUKULAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4690100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109046 | Sabang ES | POLILLO | 1 | 1 | 4 | 2STY4CL | Batch 3 | 13933000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109065 | Kiloloron ES | REAL | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4440100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109077 | Tignoan ES | REAL | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4588515 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 165006 | Mauban South CES II | MAUBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4788515 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 165010 | Tejero ES | MAUBAN | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4688515 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 308047 | Polillo NHS Ext. | POLILLO | 1 | 1 | 3 | 1STY3CL | Batch 3 | 6491100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108617 | Kinatihan I ES | CANDELARIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3800000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108618 | Kinatihan II ES | CANDELARIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3910000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108622 | Mangilag Sur ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11581021.41 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108623 | Masalukot IV ES | CANDELARIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3945000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108624 | Masalukot V ES | CANDELARIA | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3945000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108673 | Antonino ES Annex (San Mateo) | DOLORES | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11565502.12 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108674 | Bulakin ES | DOLORES | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11521469.96 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108677 | Dolores CS | DOLORES | 2 | 1 | 6 | 3STY6CL | Batch 3 | 17350704.46 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108678 | Don Eulogio Capino ES | DOLORES | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11542240.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108679 | Don Eulogio Capino ES Annex (Putol) | DOLORES | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11533065.59 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109101 | Arawan ES | SAN ANTONIO | 2 | 1 | 2 | 1STY2CL w/ CR | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109102 | Briones ES | SAN ANTONIO | 2 | 1 | 3 | 1STY3CL w/ CR | Batch 3 | 5490000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109103 | Bulihan ES | SAN ANTONIO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11899459.94 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109104 | Callejon ES | SAN ANTONIO | 2 | 1 | 2 | 1STY2CL w/ CR | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109160 | Bucal ES | SARIAYA | 2 | 1 | 4 | 1STY4CL w/ CR | Batch 3 | 7069051.44 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109166 | Morong ES | SARIAYA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11511277.1 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109169 | Sariaya East Central Main ES | SARIAYA | 2 | 1 | 9 | 3STY9CL | Batch 3 | 28041325.76 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109171 | Tumbaga I ES | SARIAYA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11930366.05 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109192 | Sto. Cristo ES | SARIAYA | 2 | 1 | 9 | 3STY9CL | Batch 3 | 28243552.86 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109263 | Anastacia ES | TIAONG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11533605.83 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109264 | Aquino ES | TIAONG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 4515000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109265 | Ayusan ES | TIAONG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109266 | Behia ES | TIAONG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109268 | Bula ES | TIAONG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11672141.84 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109282 | San Francisco ES | TIAONG | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3900000 |  |  | Completed | 1
NC 2018 | TVL | Region IV-A | Quezon | 301318 | Sta. Lucia NHS | DOLORES | 2 | 1 | 4 | 4STY REGULAR WORKSHOP (4STY8CL) | Batch 3 | 24957000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301318 | Sta. Lucia NHS | DOLORES | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11541890.46 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108649 | Catanauan CS | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108651 | Dahican ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108659 | San Isidro ES | CATANAUAN | 3 | 1 | 8 | 2 UNITS 2STY4CL | Batch 3 | 24300000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108666 | Tagabas Ibaba ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108668 | Tagbacan Ibaba ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108671 | Tuhian ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12150000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108684 | Bacong Ibaba ES | GENERAL LUNA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 16550000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108692 | San Ignacio Ibaba ES | GENERAL LUNA | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108694 | San Isidro ES | GENERAL LUNA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 17000000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108696 | San Vicente ES | GENERAL LUNA | 3 | 1 | 6 | 2STY6CL | Batch 3 | 16750000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108874 | Calantas ES | MACALELON | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108919 | Ajos ES | MULANAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12050000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108924 | Burgos ES | MULANAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12350000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108938 | Patabog ES | MULANAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12350000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108944 | Agdangan Central Elementary School | AGDANGAN | 3 | 1 | 6 | 2STY6CL | Batch 3 | 16700000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108952 | Kinagunan ES | PADRE BURGOS | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109004 | Gangahin ES | PITOGO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109009 | Poctol ES | PITOGO | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109098 | Talisay ES | SAN ANDRES | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12450000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109114 | Aurora ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12350000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109122 | Don Juan Vercelos ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12250000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109298 | Mabini ES | UNISAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12100000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 165008 | Sabang Primary School | BUENAVISTA | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12300000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301288 | Bagupaye NHS | MULANAY | 3 | 1 | 6 | 2STY6CL | Batch 3 | 16800000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12050000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301295 | Bondoc Peninsula Agri. HS | MULANAY | 3 |  | 4 | 2STY4CL | Batch 3 | 12200000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301310 | Catanauan National High School | CATANAUAN | 3 | 1 | 6 | 2STY6CL | Batch 3 | 16550000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301312 | Tagbacan NHS (Formerly Tagbacan Ilaya IS) | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301329 | Ilayang Yuni NHS | MULANAY | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12150000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301337 | Lina Gayeta-Lasquety NHS (Formerly Kinagunan Ibaba NHS) | PADRE BURGOS | 3 | 1 | 4 | 2STY4CL | Batch 3 | 11950000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301360 | Olongtao National High School | MACALELON | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12150000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301368 | Renato Edaño Vicencio NHS (Formerly Pagsangahan NHS-Don Juan Vercelos Annex) | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12350000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301391 | San Isidro National High School | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12150000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 301411 | Tumbaga NHS | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12350000 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 308001 | Matandang Sabang National High School | CATANAUAN | 3 | 1 | 4 | 2STY4CL | Batch 3 | 12150000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108504 | Angeles-Caglate ES | ALABAT | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032989.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108506 | Pambilan ES | ALABAT | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3301498.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108507 | R. T. Camacho ES | ALABAT | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032989.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108509 | Atimonan CES (Merged Atimonan CS I & Atimonan CS II) | ATIMONAN | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13524725.54 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108516 | Inalig ES | ATIMONAN | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3354020.21 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108518 | Maligaya ES | ATIMONAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10246241.06 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108520 | Malinao Ilaya ES | ATIMONAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10246241.05 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108521 | Malusak ES | ATIMONAN | 4 | 1 | 3 | 1STY3CL | Batch 3 | 4493240.68 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108526 | Ponon ES | ATIMONAN | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3140282.1 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108528 | San Andres Bundok ES | ATIMONAN | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3247340.2 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108572 | Anahawan Elementary School | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3201994.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108576 | Catangtang ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3225348.53 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108595 | Binutas ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 6 Realignment | 3192972.56 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108580 | Mambaling ES | CALAUAG | 4 | 1 | 3 | 1STY3CL | Batch 3 | 5241055.15 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108581 | Municipal Sector ES | CALAUAG | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13492837.58 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108583 | San Roque ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032641.33 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108585 | Sumilang ES | CALAUAG | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13492837.58 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108590 | Yaganak ES | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3499070.01 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108602 | Lagay ES | CALAUAG | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10408740.3 |  |  | Completed | 1
NC 2018 | TVL | Region IV-A | Quezon | 108726 | Aloneros NHS | GUINAYANGAN | 4 | 1 | 1 | 1-Science Laboratory | Batch 3 | 3929070.01 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108731 | Dancalan Central ES | GUINAYANGAN | 4 | 1 | 3 | 1STY3CL | Batch 3 | 4391105.15 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108738 | Guinayangan ES | GUINAYANGAN | 4 | 1 | 3 | 1STY3CL | Batch 3 | 4391105.15 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108745 | San Luis II ES | GUINAYANGAN | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3034070.01 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108747 | Sta. Cruz ES | GUINAYANGAN | 4 | 1 | 4 | 1STY4CL | Batch 3 | 5878140.2 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108754 | Biga-Labnig ES | GUMACA | 4 | 1 | 6 | 2STY4CL and 1STY2CL | Batch 3 | 13354505.81 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108762 | Panikihan Elementary school | GUMACA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10245658.09 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108764 | Villa Padua ES | GUMACA | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3031619.89 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108766 | Casasahan ES | GUMACA | 4 | 1 | 4 | 2 UNITS-1STY2CL | Batch 3 | 6061740.53 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108769 | Gumaca Integrated School (JUNIOR HS) | GUMACA | 4 | 1 | 8 | 4STY8CL | Batch 3 | 19815913.41 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108770 | Mabunga ES | GUMACA | 4 | 1 | 4 | 2 UNITS-1STY2CL | Batch 3 | 6060214.64 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108773 | Progreso ES | GUMACA | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13492837.58 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108775 | Sastre ES | GUMACA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10397135.91 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108776 | VIlla Arcaya ES | GUMACA | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10362186.89 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108798 | Bebito ES | LOPEZ | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10298964.38 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108801 | Canda Ilaya ES | LOPEZ | 4 | 1 | 6 | 2STY6CL | Batch 3 | 13448716.78 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108804 | Cogorin Ilaya ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032738.78 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108812 | Magallanes Elementary School | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3139594.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108817 | San Andres Elementary School | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3245794.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108819 | Sta. Catalina ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3245794.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108827 | VIllaespina ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3139594.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108828 | Villageda ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3245794.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108829 | Villahermosa ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3192344.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108838 | Don Marcos Villegas Sr. ES | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3139594.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108993 | Mainit Norte ES | PEREZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3056748.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108995 | PAMBUHAN ES | PEREZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3248748.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108997 | Perez West Elementary School | PEREZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032989.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109016 | Ilosong ES | PLARIDEL | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3192086.17 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109051 | Cometa ES | QUEZON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3032989.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109056 | Pedro Cabangon ES | QUEZON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3141148.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109061 | Ulpiano Camacho ES | QUEZON | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3301498.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109199 | Cabibihan ES | TAGKAWAYAN | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10898140.2 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109228 | Tagkawayan NHS | TAGKAWAYAN | 4 | 1 | 10 | 2STY10CL | Batch 3 | 24520350.5 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301314 | Cesar C. Tan Memorial NHS | QUEZON | 4 | 1 | 10 | 2STY10CL | Batch 3 | 22571986.04 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301338 | Kinatakutan NHS | TAGKAWAYAN | 4 | 1 | 4 | 1STY4CL | Batch 3 | 6513140.2 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ | 4 | 1 | 8 | 2STY8CL | Batch 3 | 19544321.7 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 301353 | Veronica NHS | LOPEZ | 4 | 1 | 4 | 2STY4CL | Batch 3 | 10458978.38 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 308011 | Sto. Angel NHS | CALAUAG | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3299110.2 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 308038 | Cabibihan NHS | TAGKAWAYAN | 4 | 1 | 6 | 2STY6CL | Batch 3 | 14237210.3 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Quezon | 308048 | Magallanes NHS Sta. Catalina Ext. | LOPEZ | 4 | 1 | 2 | 1STY2CL | Batch 3 | 3139594.29 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 108680 | Don Severo Filismino ES | DOLORES | 2 | 1 | 6 | 2STY6CL | Batch 5 | 14481884.91 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Quezon | 109179 | Emiliano Gala Memorial ES | SARIAYA | 2 | 1 | 9 | 3STY9CL | Batch 5 | 28287846.96 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109312 | Doña Susana Madrigal Elementary School | BINANGONAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18985650.02 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region IV-A | Rizal | 109313 | Joaquin Guido ES (Angono ES Unit I) | ANGONO | 1 | 1 | 24 | 2 UNITS 4STY12CL | Batch 3 | 69606936.84 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109385 | Lunsad ES | BINANGONAN | 1 | 1 | 8 | 4STY8CL | Batch 3 | 18985650.02 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | K10 | Region IV-A | Rizal | 109406 | Saint Anthony ES | CAINTA | 1 | 1 | 4 | 2STY4CL | Batch 3 | 10144490.72 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109533 | Sta. Ana Elementary School | TAYTAY | 1 | 1 | 8 | 4STY8CL | Batch 3 | 19544207.84 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301417 | Angono NHS | ANGONO | 1 | 1 | 12 | 4STY12CL | Batch 3 | 34803468.42 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301445 | Janosa National High School | BINANGONAN | 1 | 1 | 15 | 3STY15CL | Batch 3 | 36379530.29 |  |  | Completed | 1 | [10 empty] | With Approved Buffer Fund 2018
NC 2018 | SHS | Region IV-A | Rizal | 301463 | Talim Point NHS | BINANGONAN | 1 | 1 | 6 | 2STY6CL | Batch 3 | 13491950.53 |  |  | Reverted | 0
NC 2018 | K10 | Region IV-A | Rizal | 109346 | Bagumbayan ES | TERESA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 26128201.93 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109353 | Pantay ES | TERESA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 24696497.3 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109362 | Teresa ES | Teresa | 2 | 1 | 12 | 4STY12CL | Batch 3 | 43698232.73 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109417 | Mariano C. San Juan ES | CARDONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13925924.01 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109422 | Tadlak ES (Korokan ES) | CARDONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 15176773.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109424 | Tuna-Balibago ES | CARDONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 17724132.06 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109437 | Talaga ES (Maybancal, Morong, Rizal) | Morong | 2 | 1 | 8 | 4STY8CL | Batch 3 | 28078113.86 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109442 | San Guillermo Elementary School | MORONG | 2 | 1 | 4 | 2STY4CL | Batch 3 | 13787165.55 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109444 | Tomas Claudio Memorial Elementary Sschool | MORONG | 2 | 1 | 6 | 3STY6CL | Batch 3 | 18515938.09 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109466 | Eulogio Rodriguez Jr. ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 16 | 4STY16CL | Batch 3 | 49547485.25 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109477 | San Isidro Elementary School | RODRIGUEZ (MONTALBAN) | 2 | 1 | 12 | 4STY12CL | Batch 3 | 40995171.7 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109477 | San Isidro Elementary School | RODRIGUEZ (MONTALBAN) | 2 |  | 12 | 4STY12CL | Batch 3 | 40567087.08 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109478 | San Jose ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 26848071.65 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109486 | Dulongbayan ES | San Mateo | 2 | 1 | 8 | 4STY8CL | Batch 3 | 27159270.61 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109489 | Justice Vicente Santiago ES | SAN MATEO | 2 | 1 | 6 | 3STY6CL | Batch 3 | 19840028.82 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109493 | Pintung Bukawe ES | San Mateo | 2 | 1 | 8 | 2STY8CL | Batch 3 | 29485143.24 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109494 | San Mateo ES | SAN MATEO | 2 |  | 8 | 4STY8CL | Batch 3 | 26515320.51 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109495 | Silangan ES (Labahan ES) | SAN MATEO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 25480142.07 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109505 | Daraetan ES | Tanay | 2 | 1 | 6 | 3STY6CL | Batch 3 | 21998614.99 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109510 | Madilay-dilay ES | Tanay | 2 | 1 | 6 | 2STY6CL | Batch 3 | 22782639.62 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109520 | Sampaloc ES | TANAY | 2 | 1 | 8 | 4STY8CL | Batch 3 | 29308365.11 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109521 | San Andres ES | Tanay | 2 | 1 | 6 | 2STY6CL | Batch 3 | 21752929.83 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 165511 | Southville 8C ES | Rodriguez (Montalban) | 2 | 1 | 6 | 3STY6CL | Batch 3 | 21286583.77 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 165515 | Malasya Uyungan Elementary School | RODRIGUEZ (MONTALBAN) | 2 | 1 | 4 | 2STY4CL | Batch 3 | 16657621.18 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301430 | Bayugo NHS | JALA-JALA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 26197610.5 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301432 | Bernardo F. San Juan NHS | Cardona | 2 | 1 | 8 | 2STY8CL | Batch 3 | 26442815.74 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301434 | Catalino D. Salazar NHS-Senior High School | CARDONA | 2 | 1 | 8 | 4STY8CL | Batch 3 | 29375098.02 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 301440 | Burgos NHS | Rodriguez (Montalban) | 2 | 1 | 8 | 4STY8CL | Batch 3 | 27100065.46 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301452 | Morong NHS | Morong | 2 | 1 | 12 | 4STY12CL | Batch 3 | 45851143 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301456 | Sampaloc NHS | TANAY | 2 | 1 | 6 | 2STY6CL | Batch 3 | 18572898.22 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301456 | Sampaloc NHS | Tanay | 2 | 1 | 4 | 2STY4CL | Batch 3 | 16160487.21 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301459 | Pintong Bukawe National High School | SAN MATEO | 2 | 1 | 4 | 2STY4CL | Batch 3 | 14349798.32 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301461 | Sto. Nino Integrated School | TANAY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 16530635.8 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301461 | Sto.Niño Integrated School | Tanay | 2 |  | 4 | 2STY4CL | Batch 3 | 18587034.62 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301462 | Silangan NHS | San Mateo | 2 | 1 | 8 | 4STY8CL | Batch 3 | 28649910.31 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 301468 | Tuna-Balibago NHS | CARDONA | 2 | 1 | 4 | 2STY4CL | Batch 3 | 19175698.89 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 308103 | Abuyod NHS | TERESA | 2 | 1 | 12 | 3STY12CL | Batch 3 | 37456909.3 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Rizal | 308133 | Laiban National High School | TANAY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 19278910.9 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal |  | Morong SHS | MORONG | 2 | 1 | 16 | 4STY16CL | Batch 3 | 49766299.85 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal |  | San Mateo SHS | SAN MATEO | 2 | 1 | 8 | 4STY8CL | Batch 3 | 25844959.88 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Rizal | 109494 | San Mateo ES | SAN MATEO | 2 | 1 | 8 | 4STY8CL | Batch 5 | 26233743.19 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | San Pablo City | 109762 | Platon Elementary School | SAN PABLO CITY | 3 | 1 | 9 | 3STY9CL | Batch 3 | 27464029.11 |  |  | Completed | 1 |  |  | P00274152LZ | 18DP0097 | 2018-11-13 | 2018-11-21 | 2018-12-04 |  | 2018-12-19 | 43455
NC 2018 | K10 | Region IV-A | San Pablo City | 109785 | Sta. Monica Elementary School | SAN PABLO CITY | 3 | 1 | 12 | 4STY12CL | Batch 3 | 35276924.79 |  |  | Completed | 1 |  |  | P00274153LZ | 18DP0089 | 2018-10-26 | 2018-11-07 | 2018-11-20 |  | 2018-12-13 | 43455
NC 2018 | K10 | Region IV-A | Sta. Rosa City | 108474 | Don Jose Elementary School | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL | BATCH 1 | 18076995.96 |  |  | Completed | 1
NC 2018 | SHS | Region IV-A | Sta. Rosa City | 342597 | Sinalhan Senior High School | CITY OF SANTA ROSA | 1 | 1 | 24 | 2 UNITS 4STY12CL | BATCH 1 | 68609579 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tanauan City | 301138 | Pres. Jose P. Laurel NHS | CITY OF TANAUAN | 3 | 1 | 12 | 3STY12CL | BATCH 1 | 29359267.25 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tanauan City | 107753 | Bernardo Lirio Memorial Central School | CITY OF TANAUAN | 3 | 1 | 12 | 3STY12CL | Batch 3 | 29067605.89 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 109233 | East Palale ES (Silangan Palale ES) | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4590100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 109239 | Mate ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4489307.5 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 109251 | Domoit ES | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4440100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4390100 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 109261 | Tayabas West CS III | CITY OF TAYABAS | 1 | 1 | 4 | 2STY4CL | Batch 3 | 13633000 |  |  | Completed | 1
NC 2018 | K10 | Region IV-A | Tayabas City | 301381 | Rosario Quesada Mem. NHS | CITY OF TAYABAS | 1 | 1 | 2 | 1STY2CL | Batch 3 | 4390100 |  |  | Completed | 1
NC 2019 | SHS | Region IV-A | Antipolo City | 321505 | Dela Paz NHS | CITY OF ANTIPOLO | 1 | 1 | 3 | 3STY3CL |  | 12888626.6035 |  | reverted | 0 | [10 empty] | Reverted due to unavailability of buildable space | 1
NC 2019 | K10 | Region IV-A | Bacoor City | 107886 | Molino Elementary School | BACOOR | 2 | 1 | 8 | 4STY8CL |  | 24636588.7371 |  | COMPLETED | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107725 | Butong Elementary School | TAAL | 1 | 1 | 12 | 2STY12CL |  | 30482344.8225 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107511 | Nasugbu East Central School | NASUGBU | 1 | 1 | 9 | 3STY9CL |  | 26827497.49 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 307702 | Banoyo National High School | SAN LUIS | 2 | 1 | 8 | 4STY8CL |  | 23842206.875 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107432 | Calo Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL |  | 21343926.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107433 | Calumpit Elementary School | LOBO | 2 | 1 | 2 | 1STY2CL |  | 5675803.6238 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107645 | Calumpang Elementary School | SAN LUIS | 2 | 1 | 6 | 2STY6CL |  | 18205600.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107435 | Lagadlarin/Olo-Olo Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL |  | 19219629.25 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107647 | Locloc Elementary School | SAN LUIS | 2 | 1 | 6 | 2STY4CL & 1STY2CL |  | 18266652.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107649 | Mahabang Parang Primary School | SAN LUIS | 2 | 1 | 2 | 1STY2CL |  | 5002575.25 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107439 | Malapad Na Parang Elementary School | LOBO | 2 | 1 | 2 | 1STY2CL |  | 5230142.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107442 | Nagtoctoc Elementary School | LOBO | 2 | 1 | 2 | 1STY2CL |  | 5704325.25 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107447 | Sawang Elementary School | LOBO | 2 | 1 | 2 | 1STY2CL |  | 5311345.25 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Batangas | 342199 | Tingloy Senior High School | TINGLOY | 2 | 1 | 16 | 4STY16CL |  | 38368419.8049 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107657 | Tungal Elementary School | SAN LUIS | 2 | 1 | 8 | 4STY8CL |  | 23453236.875 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107426 | Apar Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL |  | 21197561.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Batangas | 342216 | Agoncillo SHS | AGONCILLO | 3 | 1 | 8 | 4STY8CL |  | 17202469.5967 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107707 | Doña Tiburcia Carpio Malvar Elementary School | SANTO TOMAS | 3 | 1 | 4 | 2STY4CL |  | 8923425.1806 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107741 | Jorge B. Vargas MES | TALISAY | 3 | 1 | 4 | 2STY4CL |  | 9018391.5144 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107585 | Bagong Pook Elementary School | SAN JOSE | 4 | 1 | 4 | 2STY4CL |  | 10261088.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107603 | Barualte Elementary School | San Juan | 4 | 1 | 2 | 2STY2CL |  | 7035043.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107590 | Dagatan Elementary School | San Jose | 4 | 1 | 4 | 2STY4CL |  | 10261088.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107614 | Imelda Elementary School | San Juan | 4 | 1 | 4 | 2STY4CL |  | 10311213.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107561 | Masaya Elementary School | Rosario | 4 | 1 | 3 | 3STY3CL |  | 11035018.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107622 | Palahanan ES | San Juan | 4 | 1 | 2 | 2STY2CL |  | 7080156.25 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas | 107629 | Quipot ES | San Juan | 4 | 1 | 2 | 2STY2CL |  | 7095193.75 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas City | 301472 | Batangas National High School | BATANGAS CITY (Capital) | 5 | 1 | 16 | 4STY16CL |  | 56173976.73 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Batangas City | 109620 | Piit ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | 2STY2CL |  | 6857108.5513 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Batangas City | 301481 | Tabangao Senior High School | BATANGAS CITY (Capital) | 5 | 1 | 8 | 4STY8CL |  | 17503219.5967 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Binan City | 108219 | Dr. Marcelino Z. Batista Memorial Elementary School | CITY OF BIÑAN | 1 | 1 | 12 | 4STY12CL |  | 42478752.05 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Calamba City | 109861 | San Ramon Elementary School | CITY OF CALAMBA | 2 | 1 | 8 | 4STY8CL |  | 24287667.75 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108016 | Aguinaldo ES | KAWIT | 1 | 1 | 20 | 4STY20CL |  | 62433177.8804 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108083 | San Antonio ES | Noveleta | 1 | 1 | 8 | 4STY8CL |  | 26793468.6341 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108026 | Wakas ES | KAWIT | 1 | 1 | 8 | 4STY8CL |  | 26736887.3997 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108096 | Balubad ES | SILANG | 5 | 1 | 20 | 4STY20CL |  | 53412970.9288 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 107892 | Bancal ES | CARMONA | 5 | 1 | 16 | 4STY16CL |  | 46774716.3279 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108118 | Carmen ES | SILANG | 5 | 1 | 6 | 2STY6CL |  | 28410465.7718 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108124 | Lalaan CS | SILANG | 5 | 1 | 20 | 4STY20CL |  | 54928314.7209 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 107942 | San Gabriel III ES | GEN. MARIANO ALVAREZ | 5 | 1 | 16 | 4STY16CL |  | 47026140.1299 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite | 108111 | Silang West ES | Silang | 5 | 1 | 20 | 4STY20CL |  | 53616691.4399 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Cavite |  | Tagaytay City NHS Annex (Senior HS) | Cavite | 7 | 1 | 36 | 4STY100CL (Phase 2) |  | 91182387.5 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Cavite City | 109634 | Bagumbuhay ES | Cavite City | 1 | 1 | 4 | 2STY4CL |  | 14918543.5806 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Dasmarinas City | 107903 | Humayao ES | CITY OF DASMARIÑAS | 4 | 1 | 8 | 4STY8CL |  | 21480347.5415 |  | completed | 1 | [10 empty] | Completed as per POW, requested for additional Fund | 0
NC 2019 | SHS | Region IV-A | Gen. Trias City |  | Luis Y. Ferrer Jr. SHS-Sta. Clara Annex | City of Gen. Trias | 6 | 1 | 40 | 2UNITS 4STY20CL |  | 121379917.551 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Imus City | 107986 | Malagasang I Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL |  | 26873446.9772 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Imus City | 107978 | Pasong Santol Elementary School | IMUS | 3 | 1 | 12 | 4STY12CL (L-Type) |  | 42578127.1582 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Laguna | 301240 | Famy National High School | FAMY | 4 | 1 | 8 | 4STY8CL |  | 18378632 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Laguna | 108314 | Tadlac Elementary School | LOS BAÑOS | 2 | 1 | 8 | 4STY8CL |  | 24445651.725 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Laguna | 108294 | Calumpang ES | LILIW | 3 | 1 | 4 | 2STY4CL |  | 10113782.192 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Laguna | 108442 | Pagsawitan ES | SANTA CRUZ (Capital) | 4 | 1 | 12 | 4STY12CL |  | 32754192.6685 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Laguna | 108281 | Talaongan East ES | CAVINTI | 4 | 1 | 12 | 4STY12CL |  | 31964133.7968 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6 | 1 | 12 | 4STY12CL |  | 41663900 |  | Completed | 1 | [10 empty] | Waiting for Final Documentary requirement for Completion | 0
NC 2019 | K10 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6 |  | 8 | 4STY8CL |  | 24125162.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Lipa City | 109641 | Jose K. Obando MES (Antipolo ES) | LIPA CITY | 6 | 1 | 8 | 4STY8CL |  | 24210375 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Lipa City | 109653 | San Jose ES | LIPA CITY | 6 | 1 | 12 | 4STY12CL |  | 42245350 |  | Completed | 1 | [10 empty] | Waiting for Final Documentary requirement for Completion | 0
NC 2019 | K10 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6 | 1 | 8 | 4STY8CL |  | 24240450 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Lucena City | 308505 | Lucena City NHS - Mayao Parada Extension | LUCENA CITY (Capital) | 2 | 1 | 4 | 2STY4CL |  | 11759459.8362 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109021 | Balungay ES | PANUKULAN | 1 | 1 | 6 | 2STY6CL |  | 18892313 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108701 | Batangan ES | General Nakar | 1 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109022 | Bato ES | PANUKULAN | 1 | 1 | 6 | 2STY6CL |  | 18892313 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108559 | Bongliw ES | Burdeos | 1 | 1 | 6 | 2STY6CL |  | 20964592.369 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108561 | Burdeos CS | Burdeos | 1 | 1 | 10 | 2STY10CL |  | 31101560 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109028 | Calasumanga ES | PANUKULAN | 1 | 1 | 6 | 2STY6CL |  | 18892313 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108706 | Dadyangaw ES | GENERAL NAKAR | 1 | 1 | 4 | 1STY4CL |  | 10305900.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109034 | Libo ES | PANUKULAN | 1 | 1 | 6 | 2STY6CL |  | 18892313 |  | Completed | 1 | [11 empty] | 0
NC 2019 | TVL | Region IV-A | Tayabas City | 308036 | Quezon Science High School | CITY OF TAYABAS | 1 | 1 | 3 | 3STY LABORATORY |  | 27284941.2275 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108680 | Don Severo Filismino ES | DOLORES | 2 | 1 | 6 | 2STY6CL |  | 14518089.6223 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109181 | Lutgarda Causapin ES | SARIAYA | 2 | 1 | 6 | 2STY6CL |  | 14360232.3031 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109191 | San Roque ES | SARIAYA | 2 | 1 | 6 | 2STY6CL |  | 14729340.4924 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109003 | Dulong Bayan ES | PITOGO | 3 | 1 | 6 | 2STY6CL |  | 17042488.6116 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108951 | Ilayang Kinagunan ES | AGDANGAN | 3 | 1 | 4 | 2STY4CL |  | 12130250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109127 | Mabunga ES | SAN FRANCISCO (AURORA) | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108655 | Macpac ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108658 | Navitas ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108659 | San Isidro ES | CATANAUAN | 3 | 1 | 6 | 2STY6CL |  | 14530824.5602 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Quezon | 308010 | San Vicente Kanluran NHS | Catanauan | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108664 | San Vicente Silangan ES | CATANAUAN | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108511 | Atimonan Central School Annex | ATIMONAN | 4 | 1 | 16 | 4STY16CL |  | 43703997.0237 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108816 | Samat ES | LOPEZ | 4 | 1 | 2 | 1STY2CL |  | 3808567.685 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 109205 | Kinatakutan ES | TAGKAWAYAN | 4 | 1 | 6 | 2STY6CL |  | 14272803.3258 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108607 | Sabang ES | CALAUAG | 4 | 1 | 12 | 2STY8CL & 2STY4CL |  | 31719803.1334 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Quezon | 108824 | Vergaña ES | LOPEZ | 4 | 1 | 6 | 2STY6CL |  | 14272803.3258 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Rizal | 109396 | Cainta Elementary School | CAINTA | 1 | 1 | 8 | 4STY8CL |  | 22003064.4549 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Rizal | 109372 | Tatala ES | BINANGONAN | 1 | 1 | 8 | 4STY8CL |  | 21627885.4966 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Rizal | 308103 | Abuyod NHS | TERESA | 2 | 1 | 6 | 3STY6CL |  | 18279860.3166 |  | completed | 1 |  |  |  | 19 DO 0110 | [7 empty] | 0
NC 2019 | K10 | Region IV-A | Rizal | 109472 | Mascap ES | RODRIGUEZ (MONTALBAN) | 2 | 1 | 6 | 2STY6CL |  | 19795085.2023 |  | completed | 1 |  |  |  | 19 DO 0111 | [7 empty] | 0
NC 2019 | K10 | Region IV-A | Rizal | 301449 | Mascap NHS | RODRIGUEZ (MONTALBAN) | 2 | 1 | 6 | 2STY6CL |  | 20330429.3751 |  | completed | 1 |  |  |  | 19 DO 0112 | [7 empty] | 0
NC 2019 | SHS | Region IV-A | Rizal | 301452 | Morong National High School - SHS | MORONG | 2 | 1 | 16 | 4STY16CL |  | 49890715.5996 |  | completed | 1 |  |  |  | 19 DO 0113 | [7 empty] | 0
NC 2019 | K10 | Region IV-A | San Pablo City | 109776 | Sta. Maria Magdalena Elementary School | SAN PABLO CITY | 3 | 1 | 6 | 3STY6CL |  | 15618970.7217 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA | 1 | 1 | 8 | 4STY8CL |  | 25594099.685 |  | completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IV-A | Tanauan City | 321601 | Tanauan City NHS | CITY OF TANAUAN | 3 | 1 | 3 | 1STY3CL |  | 4511250 |  | completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IV-A | Tayabas City | 109257 | Malao-Calantas Elementary School | CITY OF TAYABAS | 1 | 1 | 4 | 2STY4CL |  | 13466582.5 |  | completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region IV-A | Antipolo City | 109339 | San Isidro ES | CITY OF ANTIPOLO | 1 | 1 | 4 | 2STY4CL |  | 10025000 |  |  | completed | 1 | [10 empty] | Suspended
NC 2020 | K10 | Region IV-A | Bacoor City | 107879 | Gawaran ES | BACOOR | 2 | 1 | 8 | 4STY8CL |  | 25943024.94 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Bacoor City | 301171 | Bacoor NHS - Molino Main | BACOOR | 2 | 1 | 8 | 4STY8CL |  | 26854158.44 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 163505 | Antonio Bonsol Elementary School | TAAL | 1 | 1 | 8 | 4STY8CL |  | 29662736.91 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 301070 | Ananias C. Hernandez Memorial National High School | LEMERY | 1 | 1 | 6 | 2STY6CL |  | 20746466.83 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107427 | Balatbat Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL |  | 19802081.75 |  |  | COMPLETED | 1 | [10 empty] | For Turn Over, waiting for Final Documentary Requirement from DPWH for completion
NC 2020 | K10 | Region IV-A | Batangas | 107428 | Balibago Elementary School | LOBO | 2 | 1 | 6 | 2STY6CL |  | 18937926.75 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107642 | Boboy Elementary School | SAN LUIS | 2 | 1 | 6 | 2STY6CL |  | 20491100 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 301148 | Santa Monica NHS | SAN LUIS | 2 | 1 | 2 | 2STY2CL |  | 6425031.05 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107342 | Dalipit Elementary School | CUENCA | 3 | 1 | 6 | 2STY6CL |  | 14873090 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107560 | Marilag Elementary School | ROSARIO | 4 | 1 | 4 | 2STY4CL |  | 12422980 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107563 | Mayuro ES | ROSARIO | 4 | 1 | 4 | 2STY4CL |  | 14269585 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Batangas | 107584 | Aya Elementary School | SAN JOSE | 4 | 1 | 4 | 2STY4CL |  | 14244522.5 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Batangas City | 109548 | Dumantay ES | BATANGAS CITY (Capital) | 5 | 1 | 2 | 2STY2CL |  | 6984426.05 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Biñan City | 307932 | Mamplasan NHS | CITY OF BIÑAN | 1 | 1 | 8 | 4STY8CL |  | 26322051.03 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Cavite | 108118 | Carmen ES | SILANG | 5 | 1 | 10 | 2STY10CL |  | 30877000 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Cavite | 108013 | Mahabang Kahoy Cerca ES | INDANG | 7 | 1 | 8 | 4STY8CL |  | 26566250 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Cavite | 108027 | Baliwag ES | MAGALLANES | 8 | 1 | 8 | 4STY8CL |  | 32581250 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Cavite | 108036 | Urdaneta ES | MAGALLANES | 8 | 1 | 12 | 4STY12CL |  | 45112500 |  |  | completed | 1
NC 2020 | K10 | Region IV-A | Cavite City | 109634 | Bagumbuhay ES | Cavite City | 1 | 1 | 4 | 2STY4CL |  | 15129730 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Dasmarinas City | 107905 | Malinta Elementary School | CITY OF DASMARIÑAS | 4 | 1 | 16 | 4STY16CL |  | 46765132.72 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | GEN. TRIAS CITY | 107948 | Ipilan Barrio School | GEN. TRIAS CITY | 6 | 1 | 8 | 4STY8CL |  | 24953227.5 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Imus City | 107981 | Alapan II Elementary School | IMUS | 3 | 1 | 8 | 4STY8CL |  | 25062500 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Laguna | 108305 | B.N. Calara ES | BAY | 2 | 1 | 8 | 4STY8CL |  | 24694136.39 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Laguna | 108188 | Alaminos CS | ALAMINOS | 3 | 1 | 16 | 4STY16CL |  | 45449926.56 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Laguna | 108365 | San Francisco ES | NAGCARLAN | 3 | 1 | 12 | 4STY12CL |  | 38901628.81 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Laguna | 108497 | Masapang ES | VICTORIA | 3 | 1 | 8 | 4STY8CL |  | 20465184.76 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Laguna | 108329 | Maytalang I ES | LUMBAN | 4 | 1 | 12 | 3STY12CL |  | 37868721.72 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Lipa City | 500781 | Gaudencio B. Lontok Memorial Integrated School | LIPA CITY | 6 | 1 | 20 | 4STY20CL |  | 73986680.44 |  |  | Completed | 1 | [10 empty] | For Turn Over, waiting for Final Documentary Requirement from DPWH for completion
NC 2020 | K10 | Region IV-A | Lipa City | 500889 | Sen. Claro M. Recto Memorial Integrated School | LIPA CITY | 6 | 1 | 12 | 4STY12CL |  | 45405230 |  |  | completed | 1 | [10 empty] | For Turn Over, waiting for Final Documentary Requirement from DPWH for completion
NC 2020 | K10 | Region IV-A | Lucena City | 109716 | Camp Nakar ES | Lucena City | 2 | 1 | 8 | 4STY8CL |  | 23059505 |  |  | Completed | 1 | [10 empty] | For Turn Over, waiting for Final Documentary Requirement from DPWH for completion
NC 2020 | K10 | Region IV-A | Quezon | 108705 | Cynthia Village ES | Gen. Nakar | 1 | 1 | 3 | 1STY3CL |  | 6507327.75 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108707 | Dinigman ES | Gen. Nakar | 1 | 1 | 3 | 1STY3CL |  | 6305825.25 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109023 | Bigyan ES | Polillo | 1 | 1 | 6 | 2STY6CL |  | 20964592.37 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108617 | Kinatihan I ES | CANDELARIA | 2 | 1 | 4 | 2STY4CL |  | 12024386 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109112 | San Antonio Central School | San Antonio | 2 | 1 | 12 | 3STY12CL |  | 36017970.38 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109187 | Manggalang I ES | Sariaya | 2 | 1 | 6 | 2STY6CL |  | 16566262.38 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109290 | Tiaong East ES | TIAONG | 2 | 1 | 10 | 2STY10CL |  | 30278269.41 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Quezon | 301305 | Callejon NHS | San Antonio | 2 | 1 | 4 | 2STY4CL |  | 11904687.5 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Quezon | 308016 | Dolores Macasaet National High School | CANDELARIA | 2 | 1 | 20 | 4STY20CL |  | 49780791.63 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108933 | Malibago ES | Mulanay | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108945 | Binagbag ES | Agdangan | 3 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109124 | Loawan ES | San Francisco | 3 | 1 | 4 | 2STY4CL |  | 11528750 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 165001 | Bagong Silang ES | Buenavista | 3 | 1 | 4 | 2STY4CL |  | 11528750 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108509 | Atimonan CES | Atimonan | 4 | 1 | 4 | 2STY4CL |  | 15193544.76 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108514 | Caridad Ibaba ES | Atimonan | 4 | 1 | 6 | 2STY6CL |  | 17829113.99 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108581 | Municipal Sector ES | Calauag | 4 | 1 | 4 | 2STY4CL |  | 15283769.76 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108599 | Dona Aurora ES | Calauag | 4 | 1 | 4 | 2STY4CL |  | 15283769.76 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 108759 | Gumaca East Central School | Gumaca | 4 | 1 | 8 | 2STY8CL |  | 20829825.4 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Quezon | 109228 | Tabason ES | Tagkawayan | 4 | 1 | 4 | 2STY4CL |  | 11832749.54 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Quezon | 301389 | Sto Nino Ilaya NHS | Lopez | 4 | 1 | 6 | 2STY6CL |  | 17829113.99 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Rizal | 109535 | Taytay ES | Taytay | 1 | 1 | 20 | 4STY20CL |  | 55007661.14 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Rizal | 301417 | Angono NHS | ANGONO | 1 | 1 | 8 | 4STY8CL |  | 26926246.1 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Rizal | 301436 | Don Jose M. Ynares,Sr. Memorial National High School | BINANGONAN | 1 | 1 | 8 | 4STY8CL |  | 23039798.18 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Rizal | 109459 | Quisao ES | Pililla | 2 | 1 | 6 | 2STY6CL |  | 19027789.42 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Rizal | 109477 | San Isidro ES | Rodriguez | 2 | 1 | 16 | 4STY16CL |  | 48299624.3 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Rizal | 109502 | Cayabu ES | Tanay | 2 | 1 | 4 | 2STY4CL |  | 15136252.92 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | San Pablo City | 109806 | Guerilla Elementary School | San Pablo City | 3 | 1 | 8 | 4STY8CL |  | 20504240.46 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | San Pablo City | 301505 | Col. Lauro D. Dizon Memorial National High School | SAN PABLO CITY | 3 | 1 | 20 | 4STY20CL |  | 50248631.51 |  |  | Completed | 1
NC 2020 | SHS | Region IV-A | Sta. Rosa City | 307902 | Santa Rosa Science and Technology High School | CITY OF SANTA ROSA | 1 | 1 | 12 | 4STY12CL |  | 41767458.25 |  |  | Completed | 1
NC 2020 | K10 | Region IV-A | Tanauan City | 230501 | Dayapan Elementary School | CITY OF TANAUAN | 3 | 1 | 4 | 2STY4CL |  | 10617828.38 |  |  | COMPLETED | 1
NC 2021 | K10 | Region IV-A | Bacoor City | 107886 | Molino Elementary School | BACOOR | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 23128431.1356 | 23070754.25 |  | COMPLETED | 1 | 2022-06-13 | 2022-06-13 | P00575782LZ | 21DQ0120 | 2021-10-04 | 2021-10-12 | 2021-10-20 | 2021-10-26 | 2021-11-10 | Omnicon Builders | waiting for turnover of Keys
NC 2021 | K10 | Region IV-A | Batangas | 107292 | Dacanlao G. Agoncillo Elementary School | CALACA | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6444430.9 | 6428360 |  | Completed | 1 | 2021-12-01 |  | P00575785LZ-CW1 | 21DE0144 | 2021-07-28 | 2021-08-04 | 2021-08-17 | 2021-09-13 | 2021-09-15 | GREENFIELD CONSTRUCTION | waiting for request of final inspection from DPWH
NC 2021 | K10 | Region IV-A | Batangas | 107503 | Kaylaway ES | Nasugbu | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 329190.925 | 328370 |  | Completed | 1 | 2021-12-01 | 2021-12-28 | P00575783LZ-CW1 | 21DB0159 | 2021-06-18 | 2021-06-25 | 2024-07-07 | 2024-09-13 | 2024-09-24 | DATZLAV CONSTRUCTION
NC 2021 | SHS | Region IV-A | Batangas | 307702 | Banoyo NHS | San Luis | 2 | 1 | 8 | Construction/Completion (4STY8CL) |  | 13160123.042 | 13127304.78 |  | Completed | 1 | 2021-12-01 | 2021-10-29 | P00575784LZ-CW1 | 21DB0160 | 2021-06-18 | 2021-06-25 | 2024-07-07 | 2024-09-13 | 2024-09-24 | W AND F ENTERPRISES AND GENERAL CONTRACTOR CO.
NC 2021 | SHS | Region IV-A | Batangas | 301155 | Taysan National High School | SAN JOSE | 4 | 1 | 24 | Construction/Completion (4STY12CL) |  | 6851085 | 6834000 |  | Completed | 1 | 2021-12-01 |  | P00575786LZ | 21DD0350 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | waiting for request of final inspection from DPWH
NC 2021 | SHS | Region IV-A | Batangas City | 301479 | San Agustin NHS | BATANGAS CITY (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 902250 | 900000 | 891000 | Completed | 1 | 2021-12-23 |  | P00575787LZ-CW1 | 21DEO145 | 2021-07-28 | 2021-08-04 | 2021-08-17 | 2021-09-13 | 2021-09-21 | Greenfield Construction
NC 2021 | SHS | Region IV-A | Cavite | 301212 | Rosario National High School | ROSARIO | 1 | 1 | 8 | Construction/Completion (4STY8CL) |  | 8020000 | 8000000 | 4895888.57 | Completed | 1 | 2022-04-03 | 2022-04-03 | P00575789LZ | 21DF0228 | 2021-10-20 | 2021-10-27 | 2021-11-10 | 2021-11-22 | 2021-11-29 | ELIJENRAE BUILDERS AND CONSTRUCTION SUPPLY
NC 2021 | K10 | Region IV-A | Cavite | 108159 | Antonio B. del Rosario Sr. Mem. Elementary School | TANZA | 7 | 1 | 20 | Construction/Completion (4STY20CL) |  | 5012500 | 5000000 | 2806749.71 | Completed | 1 | 2022-02-28 | 2022-02-28 |  | 21DG0085 | 2021-10-13 |  | 2021-11-03 | 2021-11-16 | 2021-11-22 | FE S. REYES GENERAL CONTRACTOR
NC 2021 | SHS | Region IV-A | Cavite | 301204 | Maragondon NHS | Maragondon | 7 | 1 | 4 | Construction/Completion (2STY4CL) |  | 2871160 | 2864000 | 7999396.36 | Completed | 1 | 2022-05-03 | 2022-05-03 | P00575788LZ | 21DF0226 | 2021-10-14 | 2021-10-21 | 2021-11-04 | 2021-11-19 | 2021-11-29 | ILFREO Construction & Trading Corp.
NC 2021 | SHS | Region IV-A | Cavite | 342292 | Trece Martires City Senior High School | TRECE MARTIRES CITY (Capital) | 7 | 1 | 16 | Construction/Completion (4STY16CL) |  | 8020000 | 8000000 | 7834658.11 | Completed | 1 | 2022-05-03 | 2022-05-03 | P00575791LZ | 21DF0227 | 2021-10-14 | 2021-10-21 | 2021-11-04 | 2021-11-19 | 2021-11-29 | C.B. Tampengco Const. & Supply
NC 2021 | K10 | Region IV-A | Dasmarinas City | 107913 | V. P. Villanueva MS (Palapala) | CITY OF DASMARIÑAS | 4 | 1 | 8 | Construction/Completion (4STY8CL) |  | 1670028.7201 | 1665864.06 | 4010690.09 | Completed | 1 | 2022-05-13 | 2022-05-13 | P00575793LZ | 21DQ0118 | 2021-09-29 | 2021-10-07 | 2021-10-20 | 2021-11-12 | 2021-11-19 | RA Del Rosario Construction
NC 2021 | K10 | Region IV-A | Dasmarinas City | 107917 | Dasmariñas II CS (Dasmariñas BBES B) | Dasmariñas City | 4 | 1 | 12 | Construction/Completion (4STY12CL) |  | 4020747.5519 | 4010720.75 | 2025774.58 | Completed | 1 | 2022-05-13 | 2022-05-13 | P00575795LZ | 21DQ0118 | 2021-09-29 | 2021-10-07 | 2021-10-20 | 2021-11-12 | 2021-11-19 | RA Del Rosario Construction | Completed as per POW Remaining works: painting, grills on window, ceiling installation,toilet fixture and other plumbing works, improvement of school ground are not included
NC 2021 | K10 | Region IV-A | Dasmarinas City | 107920 | Sta. Cruz ES (Dasmariñas BBES E) | CITY OF DASMARIÑAS | 4 | 1 | 24 | Construction/Completion (4STY24CL) |  | 9465391.668 | 9441787.2 | 9441584.08 | Completed | 1 | 2022-05-13 | 2022-05-13 | P00575794LZ | 21DQ0118 | 2021-09-29 | 2021-10-07 | 2021-10-20 | 2021-11-12 | 2021-11-19 | RA Del Rosario Construction
NC 2021 | SHS | Region IV-A | Dasmarinas City | 325902 | Paliparan II National High School - Congressional Annex | Dasmariñas City | 4 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2030900.8807 | 2025836.29 | 1665599.93 | Completed | 1 | 2022-05-13 | 2022-05-13 | P00575792LZ | 21DQ0118 | 2021-09-29 | 2021-10-07 | 2021-10-20 | 2021-11-12 | 2021-11-19 | RA Del Rosario Construction
NC 2021 | K10 | Region IV-A | General Trias City | 107961 | Mary Cris Elementary School | CITY OF GENERAL TRIAS | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 5012500 | 5000000 | 4897442.94 | Completed | 1 | 2022-05-03 | 2022-05-03 | P00575796LZ | 21DF0225 | 2021-10-14 | 2021-10-21 | 2021-11-04 | 2021-11-19 | 2021-11-29 | 747 Builders & Traders Inc.
NC 2021 | K10 | Region IV-A | Laguna | 108189 | De Mesa ES | ALAMINOS | 3 | 1 | 6 | Construction/Completion (3STY6CL) |  | 20601194.931 | 20549820.38 | 19912775.95 | Completed | 1 | 2022-04-07 |  | P00575797LZ | 21DP0078 | 2021-10-04 | 2021-10-12 | 2021-10-25 | 2021-10-29 | 2021-11-08 | MJACQ ENTERPRISES
NC 2021 | K10 | Region IV-A | Laguna | 108364 | Rizal ES | RIZAL | 3 | 1 | 8 | Construction/Completion (4STY8CL) |  | 26960465.1201 | 26893232.04 | 26059542 | Completed | 1 | 2022-06-06 |  | P00575798LZ | 21DP0077 | 2021-10-04 | 2021-10-12 | 2021-10-25 | 2021-10-29 | 2021-11-08 | MEGA M BUILDERS CORPORATION
NC 2021 | K10 | Region IV-A | Lipa City | 109640 | Anangi ES | LIPA CITY | 6 | 1 | 8 | Construction/Completion (4STY8CL) |  | 8020000 | 8000000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575799LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | Waiting for Transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109642 | Brion- Silva ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575812LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES | Waiting for Transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109643 | Don Leon E. Dolor MS | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575800LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION
NC 2021 | K10 | Region IV-A | Lipa City | 109645 | Edilberto L. Mendoza MES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575807LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION
NC 2021 | K10 | Region IV-A | Lipa City | 109647 | Pinagkawitan ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575808LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION
NC 2021 | K10 | Region IV-A | Lipa City | 109648 | San Adriano ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P005757801LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | K10 | Region IV-A | Lipa City | 109650 | San Celestino ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P005757802LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | K10 | Region IV-A | Lipa City | 109656 | Tangob ES | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575809LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION | Ongoing rectification of punclist of contractor
NC 2021 | K10 | Region IV-A | Lipa City | 109660 | Bulacnin ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575813LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES | Waiting for Transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109661 | Dagatan ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575814LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES | Ongoing rectification of punclist of contractor - CCTV
NC 2021 | K10 | Region IV-A | Lipa City | 109662 | Inosloban-Marawoy ES | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575819LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION | Waiting for Transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109664 | Plaridel ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575815LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2021 | K10 | Region IV-A | Lipa City | 109667 | Sen. Ma. E. Kalaw Katigbak MS | LIPA CITY | 6 | 1 | 20 | Construction/Completion (4STY20CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575816LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | for inspection and validation of scope of works
NC 2021 | K10 | Region IV-A | Lipa City | 109672 | Bolbok Elementary School | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 2606500 | 2600000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575823LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES | for inspection and validation of scope of works
NC 2021 | K10 | Region IV-A | Lipa City | 109675 | Kayumanggi ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575803LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | waiting for transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109679 | Lodlod ES | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575820LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | waiting for transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109680 | Mabini ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1804500 | 1800000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575821LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES | waiting for transformer
NC 2021 | K10 | Region IV-A | Lipa City | 109683 | Pagolingin ES | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1503750 | 1500000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575810LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION
NC 2021 | K10 | Region IV-A | Lipa City | 109685 | Sampaguita ES | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575818LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2021 | K10 | Region IV-A | Lipa City | 109697 | Rafael M. Lojo MS | LIPA CITY | 6 | 1 | 20 | Construction/Completion (4STY20CL) |  | 1002500 | 1000000 | 12804617 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575817LZ | 21DD0346 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | POWER K CONSTRUCTION SUPPLY & SERVICES
NC 2021 | SHS | Region IV-A | Lipa City | 301495 | Lumbang Integrated NHS | LIPA CITY | 6 | 1 | 20 | Construction/Completion (4STY20CL) |  | 1604000 | 1600000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575804LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | SHS | Region IV-A | Lipa City | 301496 | Pinagkawitan Integrated National Hgh School | LIPA CITY | 6 | 1 | 16 | Construction/Completion (4STY16CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575805LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | SHS | Region IV-A | Lipa City | 301497 | Pinagtongulan Integrated National High School | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575822LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | SHS | Region IV-A | Lipa City | 301500 | San Isidro Integrated National High School | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1503750 | 1500000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575824LZ | 21DD0344 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY | for inspection and validation of scope of works - Clarification on POW
NC 2021 | SHS | Region IV-A | Lipa City | 500888 | Pangao Integrated School - Elem | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1804500 | 1800000 | 10282446 | Completed | 1 | 2021-11-05 | 2021-11-05 | P00575811LZ | 21DD0345 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | VITALTECH CONSTRUCTION CORPORATION | waiting for transformer
NC 2021 | SHS | Region IV-A | Lipa City | 501185 | San Jose Integrated School - Elem | LIPA CITY | 6 | 1 | 12 | Construction/Completion (4STY12CL) |  | 4711750 | 4700000 | 23968143 | Completed | 1 | 2021-12-20 | 2021-12-21 | P00575806LZ | 21DD0350 | 2021-07-07 | 2021-07-14 | 2021-07-27 | 2021-09-09 | 2021-09-16 | ALPHA VECTOR CONSTRUCTION AND SUPPLY
NC 2021 | SHS | Region IV-A | Quezon | 301292 | Batangan National High School | GENERAL NAKAR | 1 | 1 | 4 | Construction/Completion (4STY Science & ICT ) |  | 1872358.8641 | 1867689.64 | 1867178.28 | Ongoing | 0 |  |  | 11 30 2021 | 12 09 2021 | 2021-12-21 | 2021-12-28 | 2021-12-31 |  |  | NT Sotelo Construction Supply Corporation | Downloaded to 4th district (Pending issue to be determined by the DPWH)
NC 2021 | TVL | Region IV-A | Quezon | 301407 | Talipan National High School | PAGBILAO | 1 | 1 | 2 | Construction/Completion (WORKSHOP BLDG (7X18)) |  | 784538.5552 | 782582.1 | 9672000 | Completed | 1 | 2022-03-20 | 2022-02-18 | P00575830LZ | 21DM0095 | 2021-06-29 | 2021-07-08 | 2021-07-22 | 2021-07-27 | 2021-09-16
NC 2021 | K10 | Region IV-A | Quezon | 108680 | Don Severo Filismino ES | DOLORES | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1698762.6057 | 1694526.29 | 4690494.01 | Completed | 1 | 2022-08-08 | 2022-06-15 | P00575827LZ | 21DJ0131 | 2021-12-02 | 2021-12-09 | 2021-12-22 | 2021-12-28 |  |  | substantially completed
NC 2021 | K10 | Region IV-A | Quezon | 109181 | Lutgarda Causapin ES | SARIAYA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1737528.579 | 1733195.59 | 4690494.01 | Completed | 1 | 2022-08-08 | 2022-06-15 | P00575828LZ | 21DJ0131 | 2021-12-02 | 2021-12-09 | 2021-12-22 | 2021-12-28 |  |  | substantially completed
NC 2021 | K10 | Region IV-A | Quezon | 109191 | San Roque ES | SARIAYA | 2 | 1 | 6 | Construction/Completion (2STY6CL) |  | 1266186.2517 | 1263028.68 | 2500000 | Completed | 1 | 2021-11-20 | 2021-11-20 | P00575831LZ | 21DM0094 | 2021-06-29 | 2021-07-08 | 2021-07-22 | 2021-07-27 | 2021-09-16
NC 2021 | K10 | Region IV-A | Quezon | 108645 | Bolo Elementary School | CATANAUAN | 3 | 1 | 4 | Construction/Completion (1STY4CL) |  | 9696180 | 9672000 | 4690494.01 | Completed | 1 | 2022-08-08 | 2022-06-15 | P00575829LZ | 21DJ0131 | 2021-12-02 | 2021-12-09 | 2021-12-22 | 2021-12-28 |  |  | substantially completed
NC 2021 | K10 | Region IV-A | Quezon | 108659 | San Isidro ES | CATANAUAN | 3 | 1 | 6 | Construction/Completion (2STY6CL) |  | 2506250 | 2500000 |  | Ongoing | 0 | [10 empty] | Downloaded to 4th district (Pending issue to be determined by the DPWH) - Waiting for transfer of fund (dpwh)
NC 2021 | K10 | Region IV-A | San Pablo City | 109779 | Banaad Elementary School | SAN PABLO CITY | 3 | 1 | 6 | Construction/Completion (3STY6CL) |  | 20601194.7104 | 20549820.16 | 19912776 | Completed | 1 | 2022-04-07 |  | P00575832LZ | 21DP0079 | 2021-10-04 | 2021-10-12 | 2021-10-25 | 2021-10-29 | 2021-11-08 | MEGA M BUILDERS CORPORATION
NC 2022 | K10 | Region IV-A | Batangas | 107818 | Talahib Elementary School | TINGLOY | 2 | 1 | 6 | 2STY6CL | 2 |  | 25062500 | 24250986.29 | Completed | 1 | 2023-07-24 | 2023-07-24 | P00675127LZ | 22DE0142 | 2022-08-23 | 2022-08-30 | 2022-09-13 | 2022-11-11 | 2022-11-15 | LLEB Construction and Trading
NC 2022 | K10 | Region IV-A | Batangas | 107471 | Malvar Central School | MALVAR | 3 | 1 | 12 | 4STY12CL | 2 |  | 49065874.6898 | 47276547.85 | Completed | 1 | 2023-07-25 | 2023-09-22 | P00675128LZ | 22DC0162 | 2022-11-16 | 2022-11-23 | 2022-06-12 | 2022-12-12 | 2022-12-16 | Miclover General Construction & Iron Works
NC 2022 | K10 | Region IV-A | Laguna | 108392 | Casa Real ES | PAKIL | 4 | 1 | 4 | 2STY4CL | 2 |  | 11679537.0275 | 11297612.27 | Completed | 1 | 2023-05-06 | 2023-06-30 | P00675130LZ | 22DH0090 | 2022-11-30 | 2022-07-12 | 2022-12-20 | 2022-12-23 | 2023-05-01 | DATZLAV CONSTRUCTION | Phase 1: 2CL only
NC 2022 | K10 | Region IV-A | Laguna | 108401 | Pakil ES | PAKIL | 4 | 1 | 6 | 3STY6CL | 2 |  | 17638305.8 | 17063088.13 | Completed | 1 | 2023-04-08 | 2023-04-08 | P00675128LZ | 22DH0087 | 2022-11-30 | 2022-07-12 | 2022-12-20 | 2023-04-04 | 2023-04-19 | MAGNA RICH TRADING AND CONSTRUCTION | Phase 1: 3CL only
NC 2022 | K10 | Region IV-A | Laguna | 108442 | Pagsawitan ES | SANTA CRUZ (Capital) | 4 | 1 | 8 | 4STY8CL | 2 |  | 23075535.9775 | 22318176.89 | Completed | 1 | 2023-04-08 | 2023-04-08 | P00675131LZ | 22DH0088 | 2022-11-30 | 2022-07-12 | 2022-12-20 | 2023-04-04 | 2023-04-19 | TRIPLE EAGLE CONSTRUCTION AND TRADING | Phase 1: 2CL only
NC 2022 | K10 | Region IV-A | Laguna | 108451 | Sto. Angel Norte E/S | SANTA CRUZ (Capital) | 4 | 1 | 9 | 3STY9CL | 2 |  | 29084541.0275 | 28132737.76 | Completed | 1 | 2023-11-16 | 2024-01-15 | P00675132LZ | 22DH0089 | 2022-11-30 | 2022-07-12 | 2022-12-20 | 2023-04-04 | 2023-04-19 | TRIPLE EAGLE CONSTRUCTION AND TRADING | Modified: 3STRY6CL Phase 1 No ceiling & no installation of electrical fixtures & wiring
NC 2022 | K10 | Region IV-A | Lipa City | 109665 | San Lucas ES | LIPA CITY | 4 | 1 | 8 | 4STY8CL | 1 |  | 33082500 | 32010000 | completed | 1 | 2022-12-31 | 2024-12-12 | P00675032LZ | 22DD0333 | 2022-05-20 | 2022-05-27 | 2022-08-06 | 2020-08-28 | 2020-04-09 | M.V. CALDO CONSTRUCTION AND SUPPLY CORPORATION
NC 2022 | K10 | Region IV-A | Quezon | 109084 | Caldong Resettlement ES | SAMPALOC | 1 | 1 | 4 | 1STY4CL | 2 |  | 11740459.5339 | 11711181.37 | Completed | 1 | 2023-12-05 | 2023-12-05 | P00675133LZ | 22DK0191 | 2022-11-25 | 2022-02-12 |  | 2022-12-28 | 2023-12-01 | W.J. CONSTRUCTION
NC 2022 | K10 | Region IV-A | Quezon | 108948 | DAYAP ES | AGDANGAN | 3 | 1 | 4 | 2STY4CL | 2 |  | 14159044.3375 | 13687062.72 | Completed | 1 | 2023-09-18 | 2023-05-22 | P00675135LZ | 22DM0150 | 2022-07-07 | 2022-07-15 | 2022-01-08 | 2022-11-14 | 2022-11-23 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP.
NC 2022 | K10 | Region IV-A | Quezon | 108949 | E. LICUP ES | AGDANGAN | 3 | 1 | 4 | 2STY4CL | 2 |  | 14109285.25 | 13650916.3 | Completed | 1 | 2023-07-21 | 2023-05-22 | P00675136LZ | 22DM0151 | 2022-07-07 | 2022-07-15 | 2022-01-08 | 2022-11-14 | 2022-11-23 | JSP CONSTRUCTION
NC 2022 | SHS | Region IV-A | Lipa City | 301499 | San Celestino Integrated National High School | LIPA CITY | 4 | 1 | 16 | 4STY16CL | 1 |  | 67167500 | 64990000 | Completed | 1 | 2023-01-30 | 2025-03-18 | P00675033LZ | 22DD0332 | 2022-05-20 | 2022-05-27 | 2022-08-06 | 2020-08-28 | 2020-04-09 | C.T. LEONCIO CONSTRUCTION AND TRADING / M.V. CALDO CONSTRUCTION AND SUPPLY CORPORATION (JV) | with punchlist
NC 2022 | SHS | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES | 2 | 1 | 12 | 3STY12CL | 2 |  | 39194849.2963 | 39097106.53 | Ongoing | 0.29 | 2024-02-02 | 2023-10-11 | P00675134LZ | 22DJ0176 | 2022-01-12 | 2022-09-12 | 2022-12-22 | 2022-12-23 | 2023-04-01 | WAYCON BUILDERS & CONSTRUCTION SUPPLY CORP. / ROMHEAD S.J. BUILDERS & DEV'T INC. (JV) | With Official Communication Requesting for the Details of Suspension
NC 2022 | SHS | Region IV-A | Tayabas City | 500496 | Dapdap Integrated School | CITY OF TAYABAS | 1 | 1 | 6 | 2STY6CL | 2 |  | 19691418.7825 |  | Completed | 1 | 2023-06-21 |  |  | 22DK0192 | 2022-11-25 | 2022-11-25 | 2022-11-25 | 2022-11-25 | 2022-11-25 | VFL Construction
NC 2023 | K10 | Region IV-A | Antipolo City | 109321 | Bagong Nayon IV ES | CITY OF ANTIPOLO |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29695500 | Completed | 1 | 2024-06-21 | 2024-11-06 | 23DN0136 | 0 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-09-12 | 2023-09-26 | LTDL BUILDERS
NC 2023 | K10 | Region IV-A | Antipolo City | 109322 | Libis ES | CITY OF ANTIPOLO |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29699997.52 | Completed | 0.95 | 2024-06-21 | 00:00:00 | 23DN0135 | 0 | 2023-07-21 | 2023-07-28 | 2023-08-10 | 2023-09-12 | 2023-09-26 | 1C4M BUILDERS, INC.
NC 2023 | K10 | Region IV-A | Bacoor City | 107877 | Aniban Central School | BACOOR |  | 1 |  | 9 | Batch 1 | 30262500 | 30000000 | 29545530 | Completed | 1 | 2024-10-01 |  | P00775307LZ | 23DQ0136 | 2023-10-04 | 2023-10-12 | 2023-10-24 | 2023-11-20 | 2023-12-14 | Omnicon Builders | - 100 % base in Financial Accomplishment '- 98 % base in Actual Accomplishment
NC 2023 | K10 | Region IV-A | Batangas | 107239 | Lanatan-Muntingtubig Elementary School | BALAYAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9794558 | Completed | 1 | 2024-03-24 | 2024-03-24 | P00775308LZ | 23DB0151 | 2023-08-18 |  | 2023-09-07 | 2023-09-27 | 2023-10-05 | RICH ADS CONSTRUCTION CORP.
NC 2023 | K10 | Region IV-A | Batangas | 107320 | Carlosa Elementary School | CALATAGAN |  | 1 |  | 8 | Batch 1 | 20175000 | 10000000 | 9699999.83 | Completed | 1 | 2024-03-13 | 2024-03-13 | P00775309LZ | 23DB0152 | 2023-08-18 |  | 2023-09-07 | 2023-09-13 | 2023-09-20 | SANDSTORM CONSTRUCTION
NC 2023 | K10 | Region IV-A | Batangas | 107403 | Dayapan Elementary School | LEMERY |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9698965.38 | Completed | 1 | 2024-04-25 | 2024-04-25 | P00775311LZ | 23DB0154 | 2023-08-18 |  | 2023-09-07 | 2023-09-13 | 2023-09-20 | 816 EMBER CONSTRUCTION CORPORATION
NC 2023 | K10 | Region IV-A | Batangas | 107497 | Bulihan Elementary School | NASUGBU |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29099985 | Completed | 1 | 2024-06-26 | 2024-06-26 | P00775312LZ | 23DB0155 | 2023-09-08 | 2023-09-09 | 2023-09-28 | 2023-10-05 | 2023-10-12 | FRAMECON BUILDERS
NC 2023 | K10 | Region IV-A | Batangas | 501538 | As-Is Integrated School | BAUAN |  | 1 |  | 4 | Batch 1 | 18661875 | 18500000 | 17945137.32 | Completed | 1 | 2024-01-21 | 2024-01-21 | P00775314LZ | 23DE0156 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | VICMAR CONSTRUCTION, INC. | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107279 | San Teodoro Elementary School | BAUAN |  | 1 |  | 4 | Batch 1 | 18661875 | 18500000 | 18102458.05 | Completed | 1 | 2024-01-21 | 2024-01-21 | P00775313LZ | 23DE0158 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | GREENFIELD CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107431 | Bignay Primary School | LOBO |  | 1 |  | 2 | Batch 1 | 6708187.5 | 6650000 | 6525000 | Completed | 1 | 2023-12-07 | 2023-12-19 | P00775315LZ | 23DE0162 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | TETR SUPPLIES & CONSTRUCTION SERVICES | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107437 | Mabilog Na Bundok Elementary School | LOBO |  | 1 |  | 2 | Batch 1 | 6708187.5 | 6650000 | 6530000 | Completed | 1 | 2023-12-19 | 2023-12-07 | P00775316LZ | 23DE0161 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | TETR SUPPLIES & CONSTRUCTION SERVICES | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107446 | San Nicolas Elementary School | LOBO |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9797342.1 | Completed | 1 | 2023-12-25 | 2023-12-25 | P00775317LZ | 23DE0159 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | EFREN RAMIREZ CONSTRUCTION AND GENERAL SERVICES CORPORATION | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107462 | San Juan-Sto. Niño Elementary School | MABINI |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9698051.03 | Completed | 1 | 2023-10-23 | 2023-10-23 | P00775318LZ | 23DE0134 | 2023-04-14 | 2023-04-21 | 2023-05-09 | 2023-06-08 | 2023-06-14 | VICMAR CONSTRUCTION, INC. | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107653 | San Luis Central School | SAN LUIS |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9714790.23 | Completed | 1 | 2023-10-23 | 2023-10-23 | P00775319LZ | 23DE0133 | 2023-04-14 | 2023-04-21 | 2023-05-09 | 2023-06-08 | 2023-06-14 | GREENFIELD CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107813 | Pisa Elementary School | TINGLOY |  | 1 |  | 4 | Batch 1 | 18661875 | 18500000 | 17944880.1 | Completed | 1 | 2024-02-20 | 2024-02-20 | P00775320LZ | 23DE0160 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-14 | 2023-08-16 | GREENFIELD CONSTRUCTION | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 301095 | Coral na Munti National High School | AGONCILLO |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 14696318.15 | Completed | 1 | 2024-05-12 | 2024-05-12 | P00775321LZ | 23DC0152 | 2023-06-07 | 2023-06-14 | 2023-06-27 | 2023-07-12 | 2023-07-18 | Van MakJay Construction | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107349 | San Felipe Elementary School | CUENCA |  | 1 |  | 6 | Batch 1 | 20175000 | 20000000 | 19600110 | Completed | 1 | 2024-04-15 |  | P00775322LZ | 23DC151 | 2023-06-07 | 2023-06-14 | 2023-06-27 | 2023-07-12 | 2023-07-18 | NDA Builders & Developers | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107373 | Gulod Elementary School | LAUREL |  | 1 |  | 3 | Batch 1 | 10087500 | 10000000 | 9797029 | Completed | 1 | 2024-02-12 | 2024-02-12 | P00775323LZ | 23DC0154 | 2023-06-07 | 2023-06-14 | 2023-06-27 | 2023-07-12 | 2023-07-18 | OIC Conztruct and Supply Corporation | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 501541 | Sampa-Pacifico Integrated School | SANTA TERESITA |  | 1 |  | 6 | Batch 1 | 15131250 | 15000000 | 14680000 | Completed | 1 | 2024-05-11 | 2024-05-09 | P00775324LZ | 23DC0153 | 2023-06-07 | 2023-06-14 | 2023-06-27 | 2023-07-12 | 2023-07-18 | 88 Builders Construction | COMPLETED
NC 2023 | K10 | Region IV-A | Batangas | 107576 | San Ignacio Elementary School | ROSARIO |  | 1 |  | 2 | Batch 1 | 8675250 | 8600000 | 8342425 | Completed | 1 | 2023-11-21 | 2024-12-16 | P00775325LZ | 23DD0332 | 2023-07-07 | 2023-07-14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | ARE Construction and Supply | FINAL INSPECTION CONDUCTED IN December 16, 2024
NC 2023 | K10 | Region IV-A | Batangas | 107589 | Benigna Dimatatac Memorial Elementary School | SAN JOSE |  | 1 |  | 2 | Batch 1 | 12609375 | 12500000 | 12125537 | Completed | 1 | 2024-01-30 | 2024-09-20 | P00775326LZ | 23DD0328 | 2023-07-07 | 2023-07-14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | Power K Construction Supply & Services | FINAL INSPECTION CONDUCTED IN September 20, 2024
NC 2023 | K10 | Region IV-A | Batangas | 107592 | Galamay-Amo Elementary School | SAN JOSE |  | 1 |  | 2 | Batch 1 | 12609375 | 12500000 | 12125579 | Completed | 1 | 2024-01-30 | 2024-09-20 | P00775327LZ | 23DD0329 | 2023-07-07 | 2023-07-14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | Power K Construction Supply & Services | FINAL INSPECTION CONDUCTED IN September 20, 2024
NC 2023 | K10 | Region IV-A | Batangas | 107598 | Taysan Elementary School | SAN JOSE |  | 1 |  | 2 | Batch 1 | 6556875 | 6500000 | 6305325 | Completed | 1 | 2023-11-21 | 2023-11-21 | P00775328LZ | 23DD0333 | 2023-07-07 | 2023-07-14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | Power K Construction Supply & Services
NC 2023 | K10 | Region IV-A | Batangas | 107607 | Calabasahan Elementary School | SAN JUAN |  | 1 |  | 4 | Batch 1 | 21587250 | 21400000 | 20758967 | Completed | 1 | 2023-08-03 | 2023-08-03 | P00775329LZ | 23DD0325 | 2023-07-07 | 2023-07-14 | 2023-07-31 | 2023-08-15 | 2023-08-29 | Alpha Vector Construction and Supply
NC 2023 | K10 | Region IV-A | Batangas | 305560 | Mahanadiong National High School | TAYSAN |  | 1 |  | 8 | Batch 1 | 15131250 | 15000000 | 14550000 | Completed | 1 | 2024-04-20 | 2024-09-19 | P00775330LZ | 23DD0337 | 2023-10-05 | 2023-10-12 | 2023-10-24 | 2023-11-08 | 2023-11-20 | Makiling Construction Ventures Corp. | PHASE 1-4CL ONLY. FINAL INSPECTION CONDUCTED IN September 19, 2024
NC 2023 | K10 | Region IV-A | Batangas City | 109605 | Haligue Silangan ES | BATANGAS CITY (Capital) |  | 1 |  | 4 | Batch 1 | 18661875 | 18500000 | 17964270.78 | Completed | 1 | 2024-01-23 | 2024-10-09 | P00775332LZ | 23DE0157 | 2023-07-18 | 2023-07-25 | 2023-08-08 | 2023-08-11 | 2023-08-23 | VicMar Construction, Inc. | No Building Permit *with discrepancy on Data vs DPWH
NC 2023 | K10 | Region IV-A | Batangas City | 109575 | San Agapito ES | BATANGAS CITY (Capital) |  | 1 |  | 3 | Batch 1 | 11600625 | 11500000 | 11155086.14 | Completed | 1 | 2023-10-18 | 2024-07-12 | P00775331LZ | 23DE0131 | 2023-04-15 | 2023-04-21 | 2023-05-04 | 2023-05-12 | 2023-06-14 | GCF Fetalvero Construction & Enterprise | Not Yet Turn-over from DPWH, No Building Permit and Occupancy Permit *with discrepancy on Data vs DPWH
NC 2023 | K10 | Region IV-A | Binan City | 108221 | Langkiwa ES | CITY OF BIÑAN |  | 1 |  | 8 | Batch 1 | 35306250 | 35000000 | 34056362.14 | Completed | 1 | 2024-05-29 | 2024-04-25 | 23DI0167 | 0 | 2023-09-01 | 2023-08-31 | 2023-09-21 | 2023-09-26 | 2023-10-03 | M.T. Maliuanag Construction Services
NC 2023 | K10 | Region IV-A | Cabuyao City | 108234 | Baclaran ES | CABUYAO |  | 1 |  | 12 | Batch 1 | 35306250 | 35000000 | 34261718.65 | Ongoing | 0.95 | 2024-05-23 |  | P00775334LZ | 23DI0171 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-19 | 2023-10-27 | DATZLAV CONSTRUCTION
NC 2023 | K10 | Region IV-A | Calamba City | 109845 | Kay Anlog ES | CITY OF CALAMBA |  | 1 |  | 12 | Batch 1 | 33288750 | 33000000 | 32207266.34 | Ongoing | 0.95 | 2024-05-23 |  | 23DI170 | 23DI0170 | 2023-09-22 | 2023-09-29 | 2023-10-12 | 2023-10-19 | 2023-10-27 | TERAVERA CORPORATION
NC 2023 | K10 | Region IV-A | Cavite | 164013 | Bagbag II Elementary School | ROSARIO |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29680235.53 | Completed | 1 | 2024-03-23 |  | P00775336LZ | 23DF0170 | 2023-06-27 | 2023-07-04 | 2023-07-18 | 2023-07-26 | 2023-08-01 | Tiongco-Mendoza Const. Co. Inc.
NC 2023 | K10 | Region IV-A | Cavite | 108131 | Pooc Elementary School | SILANG |  | 1 |  | 9 | Batch 1 | 26297213.44 | 26069108.74 | 25674187.82 | Completed | 1 | 2024-10-23 |  | P00775337LZ | 23DQ0139 | 2023-10-17 | 2023-10-26 | 2023-11-07 | 2023-11-22 | 2023-12-14 | Omnicon Builders
NC 2023 | K10 | Region IV-A | Cavite | 107928 | Dao Elementary School | GENERAL EMILIO AGUINALDO |  | 1 |  | 4 | Batch 1 | 17653125 | 17500000 | 17303483.57 | Completed | 1 | 2023-12-29 | 2023-12-29 | P00775338LZ | 23DG0084 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-14 | N.B. AVILA CONSTRUCTION
NC 2023 | K10 | Region IV-A | Cavite | 107934 | Narvaez Elementary School | GENERAL EMILIO AGUINALDO |  | 1 |  | 4 | Batch 1 | 17653125 | 17500000 | 17307421.62 | Completed | 1 | 2023-12-18 | 2023-12-18 | P00775339LZ | 23DG0083 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-14 | WRC CONSTRUCTION AND GENERAL MERCHANDISE
NC 2023 | K10 | Region IV-A | Cavite | 108147 | Maitim II Elementary School | TAGAYTAY CITY |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29646696.77 | Completed | 1 | 2024-04-16 | 2024-04-16 | P00775340LZ | 23DG0085 | 2023-06-30 | 2023-07-07 | 2023-07-20 | 2023-07-28 | 2023-08-14 | MICHAEL M. LAPITAN CONST. SERVICES &TRADING OPC
NC 2023 | K10 | Region IV-A | Dasmarinas City |  | Mabuhay ES | CITY OF DASMARIÑAS |  | 1 |  | 12 | Batch 1 | 32693832.93 | 32410243.3 | 31765436.01 | Completed | 1 | 2025-02-13 | 2025-02-04 | P00775341LZ | 23DQ0140 | 2023-10-17 | 2023-10-26 | 2023-11-07 | 2023-11-29 | 2023-12-20 | L.A. Clamor Construction Corporation | Only Phase 1 is completed as per POW (GF and 2F-bare, 3F-bare with Roof) Proposed Works for Phase 2: 1. Plumbing & Sanitary Works 2. Electrical Works 3. Concrete and Masonry for 2F-3F 4. Finishing Works 5. Doors and Windows 6. Site Development
NC 2023 | K10 | Region IV-A | Imus City |  | Imus Integrated School | IMUS |  | 1 |  | 12 | Batch 1 | 33711931.83 | 33419511.11 | 33079417.56 | Completed | 1 | 2024-07-16 |  | 23DF0171 | 23DF0171 | 2023-06-27 | 2023-07-04 | 2023-07-18 | 2023-07-26 | 2023-08-01 | OMNICON BUILDERS | Phase 2 is still ongoing
NC 2023 | K10 | Region IV-A | Laguna | 108358 | Kabubuhayan ES | NAGCARLAN |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9669040.83 | Completed | 1 | 2024-08-04 |  | P00775343LZ | 23DP0101 | 2024-09-08 | 2023-09-15 | 2023-09-28 | 2024-02-22 | 2024-03-08 | TONWAY BUILDERS AND SUPPLY / A.V. CONSTRUCTION SUPPLY JV
NC 2023 | K10 | Region IV-A | Laguna | 307929 | Nanhaya NHS (San Francisco NHS - Nanhaya Ext.) | VICTORIA |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9620000 | Completed | 1 | 2024-08-04 |  | P00775344LZ | 23DP0102 | 2023-09-08 | 2023-09-15 | 2023-09-28 | 2024-02-22 | 2024-03-08 | E. AGLAHI URBAN BUILDERS
NC 2023 | K10 | Region IV-A | Laguna | 108287 | Mayatba ES | FAMY |  | 1 |  | 8 | Batch 1 | 47411250 | 47000000 | 45579897.93 | Completed | 1 | 2024-09-14 |  | P00775345LZ | 23DH0089 | 2023-07-08 | 2023-08-04 | 2023-08-17 | 2023-09-04 | 2023-09-20 | DATZLAV CONSTRUCTION
NC 2023 | K10 | Region IV-A | Laguna | 108444 | Patimbao ES | SANTA CRUZ (Capital) |  | 1 |  | 6 | Batch 1 | 30262500 | 30000000 | 29085396.23 | Completed | 1 | 2024-06-04 | 2024-06-04 | P00775346LZ | 23DH0084 | 2023-07-15 | 2023-07-21 | 2023-08-03 | 2023-08-11 | 2023-08-28 | MAR-VEL CONSTRUCTION & SUPPLY
NC 2023 | K10 | Region IV-A | Lipa City | 109692 | Cipriano M. Andal MES (Halang ES) | LIPA CITY |  | 1 |  | 6 | Batch 1 | 3026250 | 3000000 | 2910129 | Completed | 1 | 2024-04-25 | 2024-04-25 | P0077534LZ | 23DD0338 | 2023-10-05 | 2023-10-12 | 2023-10-24 | 2023-11-08 | 2023-11-20 | VRV CONSTRUCTION AND TRADING
NC 2023 | K10 | Region IV-A | Lipa City | 109692 | Cipriano M. Andal MES (Halang ES) | LIPA CITY |  | 1 |  | 6 | Batch 2 | 27945000 | 27000000 | 26188985.08 | Ongoing | 0.85 | 2024-11-21 |  | P0077595LZ | 23DD0343 | 2023-10-27 | 2023-11-03 | 2023-11-16 | 2023-11-28 | 2024-12-01 | FB PABITO BUILDERS SUPPLY AND GENERAL SERVICES
NC 2023 | K10 | Region IV-A | Lucena City | 167501 | Hermana Fausta Elementary School | LUCENA CITY (Capital) |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 11239396.71 | Completed | 1 | 2024-04-18 |  | P00775349LZ | 23DJ0162 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-14 | 2023-09-21 | JAICA CONST. CORP.
NC 2023 | K10 | Region IV-A | Lucena City | 308508 | Lucena City National High School - Mayao Crossing Extension | LUCENA CITY (Capital) |  | 1 |  | 6 | Batch 1 | 18422474.39 | 18262675.97 | 17897422.45 | Completed | 1 | 2024-05-18 |  | P00775350LZ | 23DJ0161 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-14 | 2023-09-21 | ROMHEAD S.J. BUILDERS & DEV'T INC.
NC 2023 | K10 | Region IV-A | Lucena City | 109732 | Lucena South II Elementary School | LUCENA CITY (Capital) |  | 1 |  | 12 | Batch 1 | 33711931.83 | 33419511.11 | 32751120.88 | Ongoing | 0.95 | 2024-07-17 |  | P00775348LZ | 23DJ0160 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-14 | 2023-09-21 | ROMHEAD S.J. BUILDERS & DEV'T INC.
NC 2023 | K10 | Region IV-A | Quezon | 501453 | Calutcot Integrated School | BURDEOS |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4900030.69 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775352LZ | 23DK0112 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | S.A.N.D. CONSTRUCTION
NC 2023 | K10 | Region IV-A | Quezon | 501452 | Carlagan Integrated School | BURDEOS |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4900030.69 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775351LZ | 23DK0111 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | S.A.N.D. CONSTRUCTION
NC 2023 | K10 | Region IV-A | Quezon | 108725 | Umiray ES | GENERAL NAKAR |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4652135.32 | Completed | 1 | 2023-12-21 | 2023-12-21 | P00775353LZ | 23DK0113 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | S.A.N.D. CONSTRUCTION
NC 2023 | K10 | Region IV-A | Quezon | 302394 | Apad Jomalig National High School (Apad NHS) | JOMALIG |  | 1 |  | 2 | Batch 1 | 7418779.35 | 7354428.1 | 7208163.35 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775354LZ | 23DK0117 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | F.M. PUJEDA BUILDERS AND CONSTRUCTION SUPPLIES
NC 2023 | K10 | Region IV-A | Quezon | 108911 | Mauban South CES I (SPED) | MAUBAN |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4652135.32 | Completed | 1 | 2023-12-21 | 2023-12-21 | P00775355LZ | 23DK0114 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | S.A.N.D. CONSTRUCTION
NC 2023 | K10 | Region IV-A | Quezon | 109034 | Libo ES | PANUKULAN |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4652135.32 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775356LZ | 23DK0115 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | S.A.N.D. CONSTRUCTION
NC 2023 | K10 | Region IV-A | Quezon | 108984 | Guinaygayan ES | PATNANUNGAN |  | 1 |  | 2 | Batch 1 | 7418779.35 | 7354428.1 | 7208163.35 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775357LZ | 23DK0118 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | N.T. SOTELO CONSTRUCTION AND SUPPLY CORPORATION
NC 2023 | K10 | Region IV-A | Quezon | 501326 | Luod Integrated School | PATNANUNGAN |  | 1 |  | 2 | Batch 1 | 7418779.35 | 7354428.1 | 7208163.35 | Completed | 1 | 2024-01-15 | 2024-01-15 | P00775358LZ | 23DK0119 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 | 2023-09-18 | N.T. SOTELO CONSTRUCTION AND SUPPLY CORPORATION
NC 2023 | K10 | Region IV-A | Quezon | 108617 | Kinatihan I ES | CANDELARIA |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 11125424.77 | Completed | 1 | 2024-04-18 |  | P00775359LZ | 23DJ0163 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-14 | 2023-09-21 | ROMHEAD S.J. BUILDERS & DEV'T INC.
NC 2023 | K10 | Region IV-A | Quezon | 305598 | SARIAYA NATIONAL HIGH SCHOOL | SARIAYA |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 11125424.77 | Completed | 1 | 2024-04-18 |  | P00775360LZ | 23DJ0159 | 2023-08-18 | 2023-08-25 | 2023-09-07 | 2023-09-14 | 2023-09-21 | ROMHEAD S.J. BUILDERS & DEV'T INC. | PROJECT COMPLETED, SUBJECT FOR FINAL INSPECTION.
NC 2023 | K10 | Region IV-A | Quezon | 108652 | Don Abadilla ES | CATANAUAN |  | 1 |  | 4 | Batch 1 | 15232125 | 15100000 | 15232125 | Completed | 1 | 2024-04-12 | 2024-02-12 | P00775361LZ | 23DM0124 | 2023-06-26 | 2023-07-03 | 2023-07-18 | 2023-07-27 | 2023-08-11 | R.T.Y. CONSTRUCTION | COMPLETED
NC 2023 | SHS | Region IV-A | Quezon | 301302 | Caigdal National High School | UNISAN |  | 1 |  | 4 | Batch 1 | 15030375 | 14900000 | 14900000 | Completed | 1 | 2024-03-04 | 2024-02-12 | P00775362LZ | 23DM0125 | 2023-06-26 | 2023-07-03 | 2023-07-18 | 2023-07-27 | 2023-08-11 | RSP BUILDERS GENERAL CONTRACTOR CORP. | COMPLETED
NC 2023 | K10 | Region IV-A | Quezon |  | Matanag NHS | ATIMONAN |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 |  | Completed | 1 | [10 empty] | Reallign to Malinaw Ilaya ES
NC 2023 | K10 | Region IV-A | Quezon | 108738 | Guinayangan ES | GUINAYANGAN |  | 1 |  | 3 | Batch 1 | 6661039.51 | 6603260.98 | 6500294.82 | Completed | 1 | 2024-02-13 | 2024-02-13 | P00775364LZ | 23DL0190 | 2023-07-12 | 2023-07-20 | 2023-08-01 | 2023-08-08 | 2023-08-17 | JSP CONSTRUCTION | Completed
NC 2023 | K10 | Region IV-A | Quezon | 108847 | Lopez West Elementary School Bldg. I | LOPEZ |  | 1 |  | 4 | Batch 1 | 11451808.4 | 11352474.25 | 11091398.64 | Completed | 1 | 2024-03-13 | 2024-03-13 | P00775365LZ | 23DL0187 | 2023-07-12 | 2023-07-20 | 2023-08-01 | 2023-08-08 | 2023-08-17 | KKT CONSTRUCTION & SUPPLY | Completed
NC 2023 | SHS | Region IV-A | Quezon | 301375 | Perez National High School | PEREZ |  | 1 |  | 10 | Batch 1 | 29859000 | 16350000 | 15983908.13 | Completed | 1 | 2024-03-14 | 2024-05-13 | P00775366LZ | 23DL0189 | 2023-07-12 | 2023-07-20 | 2023-08-01 | 2023-08-08 | 2023-08-17 | R.A. MENDIOLA CONSTRUCTION & DEVELOPER | Completed
NC 2023 | K10 | Region IV-A | Rizal | 109312 | Doña Susana Madrigal Elementary School | BINANGONAN |  | 1 |  | 8 | Batch 1 | 30262500 | 30000000 | 29837962.92 | Completed | 1 | 2024-04-17 | 2024-04-17 | 23DN0133 | 0 | 2023-07-05 | 2023-07-12 | 2023-07-25 | 2023-08-14 | 2023-08-22 | MICLOVER GENERAL CONSTRUCTION & IRON WORKS
NC 2023 | SHS | Region IV-A | Rizal | 301468 | Tuna-Balibago National High School | CARDONA |  | 1 |  | 2 | Batch 1 | 10087500 | 10000000 | 9600003.92 | Completed | 1 | 2024-02-24 |  | 23DO0104 | 0 | 2023-07-29 | 2023-08-04 | 2023-08-17 | 2023-09-12 | 2023-10-09 | FLAG CONSTRUCTION CORPORATION
NC 2023 | K10 | Region IV-A | Rizal | 109516 | Doña Paz Sumulong Tanjuatco Elementary School | TANAY |  | 1 |  | 4 | Batch 1 | 20175000 | 20000000 | 19199166.94 | Completed | 1 | 2024-04-04 | 2024-07-18 | 23DO0103 | 0 | 2023-07-29 | 2023-08-04 | 2023-08-17 | 2023-09-12 | 2023-10-09 | OLIVER AQUINO CONSTRUCTION | July 18, 2024, DPWH-DepEd conducted joint final inspection
NC 2023 | K10 | Region IV-A | Rizal |  | Banaba High School | SAN MATEO |  | 1 |  | 12 | Batch 1 | 32693832.93 | 32410243.3 | 31194768.08 | Completed | 1 | 2024-10-27 |  | 23DO0122 |  | 2023-12-08 | 2023-12-15 | 2023-12-27 | 2024-01-17 | 2024-02-17 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, INC. | received approved request for modification last Dec. 14, 2023 (From Banaba High School 3STY12CL to Banaba National High School 4STY8CL)
NC 2023 | K10 | Region IV-A | Rizal | 109493 | Pintong Bukawe Elementary School | SAN MATEO |  | 1 |  | 6 | Batch 1 | 26227500 | 26000000 | 24959293.13 | Completed | 1 | 2024-08-01 |  | 23DO0118 | 0 | 2023-10-18 | 2023-10-26 | 2023-11-07 | 2023-11-30 | 2023-12-22 | OLIVER AQUINO CONSTRUCTION
NC 2023 | K10 | Region IV-A | Rizal | 109478 | San Jose Elementary School | RODRUGUEZ (MONTALBAN) |  | 1 |  | 10 | Batch 1 | 30262500 | 30000000 | 28867241.32 | Ongoing | 0.99 | 2025-01-02 |  | P00775373LZ | 23DO121 | 2023-12-08 | 2023-12-15 | 2024-01-11 | 2024-01-30 | 2024-04-08 | T. REYES CONSTRUCTION | received approved request for modification last Dec. 14, 2023 (From Southville 8C National High School 2STY10CL to San Jose Elementary School 4STY8CL)
NC 2023 | K10 | Region IV-A | San Pablo City | 109785 | Bagong Lipunan Elementary School | SAN PABLO CITY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9690000 | Completed | 1 | 2024-09-21 | 2025-02-18 | 23DP0103 | 23DP0103 | 2023-09-08 | 2023-09-18 | 2023-10-04 | 2024-04-08 | 2024-04-25 | A.H. RAGA CONSTRUCTION | With porject title modification from Sta Monica ES
NC 2023 | K10 | Region IV-A | San Pablo City | 301507 | Dolores National High School | SAN PABLO CITY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9693862 | Completed | 1 | 2024-08-04 | 2024-11-18 | 23DP0106 | 23DP0106 | 2023-09-08 | 2023-09-18 | 2023-10-04 | 2024-02-22 | 2024-03-08 | JOBEL ENTERPRISES
NC 2023 | K10 | Region IV-A | San Pablo City | 109791 | SAN PABLO CENTRAL SCHOOL | SAN PABLO CITY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9690000 | Completed | 1 | 2024-09-21 | 2025-02-18 | 23DP0105 | 23DP0105 | 2023-09-08 | 2023-09-18 | 2023-10-04 | 2024-04-08 | 2024-04-25 | A.H. RAGA CONSTRUCTION | With project title modification
NC 2023 | K10 | Region IV-A | San Pablo City | 109786 | Sta. Veronica Elementary School | SAN PABLO CITY |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9700000 | Completed | 1 | 2024-08-04 | 2025-02-18 | 23DP0104 | 23DP0104 | 2023-09-08 | 2023-09-18 | 2023-10-04 | 2024-02-22 | 2024-03-08 | MAGNA RICH TRADING & CONSTRUCTION
NC 2023 | K10 | Region IV-A | San Pedro City | 108420 | Cuyab Elementary School | SAN PEDRO |  | 1 |  | 5 | Batch 1 | 10087500 | 10000000 | 14624849.43 | Completed | 1 | 2024-07-10 | 2024-11-22 | 23DI0173 | 23DI0173 | 2023-10-13 | 2023-10-20 | 2023-11-03 | 2023-12-04 | 2023-12-12 | WAY MAKER GENERAL CONTRACTOR OPC | With Suspension due to demolition permit
NC 2023 | K10 | Region IV-A | San Pedro City | 108422 | Laguna Resettlement Community School | SAN PEDRO |  | 1 |  | 5 | Batch 1 | 10087500 | 10000000 | 14624849.43 | Completed | 1 | 2024-07-10 | 2024-11-22 | 23DI0172 | 23DI0172 | 2023-10-13 | 2023-10-20 | 2023-11-03 | 2023-12-04 | 2023-12-12 | WAY MAKER GENERAL CONTRACTOR OPC | With Suspension due to demolition permit
NC 2023 | K10 | Region IV-A | San Pedro City | 301256 | Pacita Complex NHS | SAN PEDRO |  | 1 |  | 5 | Batch 1 | 10087500 | 10000000 | - | Reverted | 0 | [10 empty] | no fund; REVERTED
NC 2023 | K10 | Region IV-A | Tayabas City | 109254 | Froilan E. Lopez ES | CITY OF TAYABAS |  | 1 |  | 6 | Batch 1 | 20919697.28 | 20738237.7 | 20323340.38 | Completed | 1 | 2024-05-01 |  | P00775382LZ | 23DK0122 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-15 |  | Tantay Lim Construction | *With discrepancy on data vs DPWH Actual Percentage of the project is 80%, still on-going as to date October 18, 2024
NC 2023 | K10 | Region IV-A | Tayabas City | 109255 | Kalumpang Elementary School (SPED) | CITY OF TAYABAS |  | 1 |  | 2 | Batch 1 | 4788571.5 | 4747034.94 | 4652135.32 | Completed | 1 | 2023-12-21 | 2023-12-21 | P00775383LZ | 23DK0116 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 |  | KKT Construction and Supply
NC 2023 | K10 | Region IV-A | Tayabas City | 109243 | Tayabas East CS I | CITY OF TAYABAS |  | 1 |  | 9 | Batch 1 | 29187191.23 | 28934018.57 | 28355324.05 | Completed | 1 | 2024-05-24 | 2024-08-27 | P00775381LZ | 23DK0120 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 |  | VFL Construction | *With discrepancy on data vs DPWH
NC 2023 | SHS | Region IV-A | Tayabas City | 301416 | West Palale National High School | CITY OF TAYABAS |  | 1 |  | 9 | Batch 1 | 29187191.23 | 28934018.57 | 28355324.05 | Completed | 1 | 2024-05-24 |  | P00775384LZ | 23DK0121 | 2023-08-09 | 2023-08-16 | 2023-08-29 | 2023-09-13 |  | SOTELO Construction | *With discrepancy on data vs DPWH Actual Percentage of the project is 80% still on-going as to date October 18, 2024
NC 2024 |  | Region IV-A | Antipolo City | 109320 | Bagong Nayon II ES | CITY OF ANTIPOLO |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39197030 | Ongoing | 0.25 | 2026-01-16 |  | P00875464LZ | 24DN0129 | 2024-04-17 | 2024-04-24 | 2024-07-05 | 2024-05-17 | 2024-05-24 | LTDL Builders
NC 2024 |  | Region IV-A | Antipolo City | 109332 | Muntindilaw ES | CITY OF ANTIPOLO |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39175683.31 | Ongoing | 0.05 | 2026-02-04 |  | P00875463LZ | 24DN0131 | 2024-04-17 | 2024-04-24 | 2024-07-05 | 2024-05-17 | 2024-05-24 | LTDL Builders
NC 2024 |  | Region IV-A | Antipolo City | 500391 | Apia IS | CITY OF ANTIPOLO |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39202994.03 | Ongoing | 0.29 | 2026-04-21 |  | P00875465LZ | 24DN0128 | 2024-04-17 | 2024-04-24 | 2024-07-05 | 2024-05-17 | 2024-05-24 | LTDL Builders
NC 2024 |  | Region IV-A | Bacoor City | 107882 | Ligas II Elementary School | BACOOR |  | 1 | 4 | 4STY4CL | GAA 17B | 14000000 |  | no available data | Ongoing | 0 |  |  | no available data | no available data | [5 empty] | Selphar Construction | ongoing demolition
NC 2024 |  | Region IV-A | Bacoor City | 107887 | Niog Elementary School | BACOOR |  | 1 | 8 | 4STY8CL | BATCH 1 | 33251771.44 |  | 32752029.62 | Completed | 1 |  | 2025-05-29 | no available data | 24DQ0113 | [5 empty] | Selphar Construction | Procurement dates are to be request in DPWH Cavite 3rd DEO
NC 2024 |  | Region IV-A | Bacoor City | 305689 | Responsible Village Leaders Learning Academy (REVILLA) High School | BACOOR |  | 1 | 8 | 2STY8CL | GAA 17B | 26000000 |  | 25536777.21 | Completed | 1 | 2025-03-01 |  |  | 24DQ0062 | 2024-04-04 | 2024-12-04 | 2024-04-24 | 2024-04-30 | 2024-05-20 | Selphar Construction | Phase 1 Completed
NC 2024 |  | Region IV-A | Batangas | 301072 | Balayan National High School | BALAYAN |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19303400 | Ongoing | 0.6 | 2024-12-19 |  | P00875360LZ | 24DB0142 | 2024-06-28 | 2024-07-05 | 2024-07-17 | 2024-07-26 | 2024-08-05 | MAKILING CONSTRUCTION VENTURES CORP.
NC 2024 |  | Region IV-A | Batangas | 107245 | Putol Elementary School | BALAYAN |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9950000 | Ongoing | 0.4 | 2024-12-22 |  | P00875371LZ | 240B0140 | 2024-04-20 |  | 2024-09-05 | 2024-05-28 | 2024-10-06 | W. RIVERA CONSTRUCTION AND EQUIPMENT RENTALS INC.
NC 2024 |  | Region IV-A | Batangas |  | Payapa Senior High School | LEMERY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9651418 | Ongoing | 0.05 | 2025-08-07 |  | P00875368LZ | 24DB0141 | 2024-05-09 |  | 2024-11-14 | 2024-09-12 | 2024-12-18 | H ROCK CONST. INC.
NC 2024 |  | Region IV-A | Batangas | 301120 | Malapad na Bato National High School | NASUGBU |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9651500 | Ongoing | 0.2 | 2024-11-14 |  | P00875369LZ | 24DB0139 | 2024-04-20 | 2024-04-26 | 2024-05-09 | 2024-05-27 | 2024-06-04 | VICMAR CONSTRUCTION INC.
NC 2024 |  | Region IV-A | Batangas | 307710 | Jose Lopez Manzano National High School | TUY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9651500 | Ongoing | 0.6 | 2024-10-20 |  | P00875371LZ | 24DB0138 | 2024-05-31 | 2024-06-07 | 2024-06-19 | 2024-06-25 | 2024-07-05 | RICH ADS CONSTRUCTION CORP.
NC 2024 |  | Region IV-A | Batangas | 107258 | Alagao-Malindig Elementary School | BAUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4824257.5 | Completed | 1 | 2024-10-14 | 2024-10-14 | P00875378LZ | 24DE0180 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 301080 | Bauan Technical Integrated High School | BAUAN |  | 1 | 20 | 4STY20CL | BATCH 1 | 59628720.6 |  | 57847300 | Ongoing | 0.52 | 2025-08-05 |  | P00875855LZ | 24DE0192 | 2024-04-27 | 2024-05-06 | 2024-05-21 | 2024-05-27 | 2024-05-29 | TRISTAN TEJADA CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 301080 | Bauan Technical Integrated High School | BAUAN |  |  | 9 | Completion of 3STY9CL | BATCH 1 | 2000000 |  | 1930002.98 | Completed | 1 | 2024-08-29 | 2024-08-29 | P00875855LZ | 24DE0208 | 2024-05-16 | 2024-05-23 | 2024-06-04 | 2024-06-10 | 2024-06-13 | REE CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107273 | Manghinao Elementary School | BAUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825615.06 | Completed | 1 | 2025-06-04 | 2025-06-04 | P00875379LZ | 24DE0220 | 2024-08-02 | 2024-08-15 | 2024-08-27 | 2024-10-29 | 2024-05-11 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107264 | West Bauan Central School | BAUAN |  | 1 | 24 | Completion of 4STY24CL | BATCH 1 | 13000000 |  | 12549363.87 | Completed | 1 | 2024-12-30 | 2024-12-30 | P00875853LZ | 24DEO206 | 2024-05-16 | 2024-05-23 | 2024-04-06 | 2024-10-06 | 2024-06-13 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107428 | Balibago Elementary School | LOBO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4830510.13 | Ongoing | 1 | 2024-10-14 | 2024-10-14 | P00875363LZ | 24DE0177 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 301106 | Jaybanga Integrated National High School | LOBO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825072 | Ongoing | 1 | 2024-10-14 | 2024-10-14 | P00875362LZ | 24DE0176 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107448 | Soloc Elementary School | LOBO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4824755 | Completed | 1 | 2024-10-14 | 2024-10-14 | P00875361LZ | 24DEO170 | 2024-03-22 | 2024-03-04 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107449 | Anilao Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4828167.34 | Completed | 1 | 2024-10-14 | 2024-10-14 | P00875376LZ | 24DE0179 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107450 | Bagalangit Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4824153.79 | Completed | 1 | 2024-10-14 | 2024-10-14 | P00875375LZ | 24DE0178 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 502223 | Mainaga-San Francisco Integrated School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4823652.62 | Completed | 1 | 2024-02-12 | 2024-02-10 | P00875377LZ | 24DE0175 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107457 | Malimatoc Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4824755 | Completed | 1 | 2024-11-14 | 2024-11-14 | P00875373LZ | 24DE0174 | 2024-03-22 | 2024-04-03 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107463 | San Teodoro Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-10-14 |  | P00875374LZ-CW1 | 24DE0172 | 2024-03-22 | 2024-03-04 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107464 | Solo Elementary School | MABINI |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4820775 | Completed | 1 | 2024-10-14 | 2024-10-14 | P00875377LZ | 24DEO171 | 2024-03-22 | 2024-03-04 | 2024-04-25 | 2024-05-13 | 2024-05-15 | GREENFIELD CONSTRUCTION
NC 2024 |  | Region IV-A | Batangas | 107251 | Looc Elementary School | BALETE |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19493946 | Ongoing | 0.8 | 2024-02-12 |  | P00875380LZ | 24DC0136 | 2024-01-03 | 2024-03-08 | 2024-03-21 | 2024-04-30 | 2024-07-05 | GAWANATO CONSTRUCTION CORPORATION
NC 2024 |  | Region IV-A | Batangas | 107383 | Sta. Maria Elementary School | LAUREL |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19478763 | Ongoing | 0.95 | 2024-12-02 |  | P00875380LZ | 24DC0136 | 2024-03-01 | 2024-03-08 | 2024-03-21 | 2024-04-30 | 2024-05-07 | GAWANATO CONSTRUCTION CORPORATION
NC 2024 |  | Region IV-A | Batangas | 301083 | Bayorbor National High School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4872128 | Ongoing | 0.95 | 2024-12-02 |  | P00875359LZ-CW1 | 24DC0137 | 2024-03-02 | 2024-03-09 | 2024-03-21 | 2024-04-30 | 2024-05-07 | JERIS CONSTRUCTION AND SUPPLY
NC 2024 |  | Region IV-A | Batangas | 107485 | Bubuyan Elementary School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4873711 | Ongoing | 0.6 | 2025-04-18 |  | P00875390LZ-CW1 | 24DC0194 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC.
NC 2024 |  | Region IV-A | Batangas | 301124 | Mataas na Kahoy National High School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4870740 | Ongoing | 0.05 | 2025-04-18 |  | P00875385LZ-CW1 | 24DC0196 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 342203 | Mataasnakahoy Senior High School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4873810 | Ongoing | 0.82 | 2025-04-18 |  | P00875382LZ-CW1 | 24DC0190 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107480 | Paaralang Elementarya ng Bayorbor | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4873810 | Ongoing | 0.95 | 2025-04-18 |  | P00875390LZ-CW1 | 24DC0186 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107482 | Paaralang Elementarya ng Kinalaglagan | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4871739 | Ongoing | 0.95 | 2025-04-18 |  | P00875388LZ-CW1 | 24DC0188 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107484 | Paaralang Elementarya Ng Loob | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4871374 | Ongoing | 0.95 | 2025-04-18 |  | P00875394LZ-CW1 | 24DC0189 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107486 | Paaralang Elementarya ng Lumanglipa | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4875306 | Ongoing | 0 | 2025-04-18 |  | P00875386LZ-CW1 | 24DC0193 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107489 | Paaralang Elementarya ng Nangkaan | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4871139 | Ongoing | 0 | 2025-04-18 |  | P00875393LZ-CW1 | 24DC0192 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107487 | Paaralang Sentral ng Mataasnakahoy | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4872335 | Ongoing | 0 | 2025-04-18 |  | P00875392LZ-CW1 | 24DC0191 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC. | For Modification
NC 2024 |  | Region IV-A | Batangas | 107483 | San Sebastian Elementary School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4872919 | Ongoing | 0.95 | 2025-04-18 |  | P00875383LZ-CW1 | 24DC0187 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC.
NC 2024 |  | Region IV-A | Batangas | 107490 | Santol - Manggahan Elementary School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4824755 | Ongoing | 0.85 | 2025-04-18 |  | P00875391-LZ-CW1 | 24DC0185 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC.
NC 2024 |  | Region IV-A | Batangas | 107488 | Upa Primary School | MATAASNAKAHOY |  | 1 | 1 | 1STY1CL | GAA 17B | 5000000 |  | 4871353 | Ongoing | 0 | 2025-04-18 |  | P00875387LZ-CW1 | 24DC0195 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC.
NC 2024 |  | Region IV-A | Batangas | 107666 | San Nicolas Central School | SAN NICOLAS |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 45577 | Ongoing | 0 | 2025-04-18 |  | P00875384LZ-CW1 | 24DC0197 | 2024-08-31 | 2024-09-07 | 2024-09-19 | 2024-12-12 | 2024-12-20 | PRIME MOVER'S PHILS. CONSTRUCTION AND SUPPLIES INC.
NC 2024 |  | Region IV-A | Batangas | 301071 | Balas Buco Sta. Maria National High School | TALISAY |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19483933 | Ongoing | 0.95 | 2024-10-03 |  | P00875357LZ-CW1 | 24DC0138 | 2024-03-02 | 2024-03-09 | 2024-03-21 | 2024-04-30 | 2024-05-07 | OIC CONZTRUCT AND SUPPLY CORPORATION
NC 2024 |  | Region IV-A | Batangas | 107354 | Gregorio Sison Memorial Elementary School | IBAAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4826754.13 | Ongoing | 1 | 2025-02-02 | 2025-05-02 | P00875381LZ | 24DC0169 | 2024-05-31 | 2024-06-07 | 2024-06-20 | 2024-06-27 | 2024-07-08 | LLEB CONSTRUCTION AND TRADING
NC 2024 |  | Region IV-A | Batangas | 107542 | Bagong Pook Elementary School | ROSARIO |  | 1 | 4 | 2STY4CL | GAA 17B | 17500000 |  | 16890797 | Ongoing | 0.98 | 2024-01-11 |  | P00875396LZ | 24DD0213 | 2024-05-23 | 2024-05-30 | 2024-06-11 | 2024-06-25 | 2024-07-05 | Megajes Construction Corp.
NC 2024 |  | Region IV-A | Batangas | 102259 | Banaybanay 1 Elementary School | SAN JOSE |  | 1 | 2 | 2STY2CL | GAA 17B | 15000000 |  | 14477250 | Ongoing | 0.3 | 2024-01-12 |  | P00875367LZ | 24DD0246 | 2024-07-04 | 2024-07-11 | 2024-07-24 | 2024-07-31 | 2024-08-09 | Tristan Tejada Construction
NC 2024 |  | Region IV-A | Batangas | 301085 | Bigain Integrated School | SAN JOSE |  | 1 | 4 | 2STY4CL | GAA 17B | 17500000 |  | 16890426 | Ongoing | 0.78 | 2024-01-11 |  | P00875397LZ | 24DD0214 | 2024-05-23 | 2024-05-30 | 2024-06-11 | 2024-06-25 | 2024-07-05 | Power K Construction Supply & Services
NC 2024 |  | Region IV-A | Batangas | 501569 | Marcos Espejo Integrated School | San Jose |  | 1 | 9 | 3STY9CL | BATCH 1 | 39000000 |  | 37640850 | Ongoing | 0.7 | 2024-04-02 |  | P00875856LZ | 24DD0243 | 2024-07-04 | 2024-07-11 | 2024-07-24 | 2024-07-31 | 2024-08-09 | Tristan Tejada Construction
NC 2024 |  | Region IV-A | Batangas | 107596 | Salaban Elementary School | SAN JOSE |  | 1 | 4 | 2STY4CL | GAA 17B | 25000000 |  | 24128750 | Ongoing | 0.52 | 2025-05-01 |  | P00875366LZ | 24DD0229 | 2024-06-20 | 2024-06-27 | 2024-07-09 | 2024-07-19 | 2024-07-30 | Tristan Tejada Construction
NC 2024 |  | Region IV-A | Batangas | 163511 | Libjo Sapangan Elementary School | SAN JUAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4825808.55 | Completed | 1 | 2024-12-10 | 2024-12-10 | P00875395LZ | 24DD0238 | 2024-06-20 | 2024-06-27 | 2024-07-09 | 2024-07-22 | 2024-07-30 | Coors Construction Co., Inc.
NC 2024 |  | Region IV-A | Batangas City | 109602 | Cumba ES | BATANGAS CITY (Capital) |  | 1 | 3 | 1STY3CL | GAA 17B | 9657000 |  | 9464048.2 | Completed | 1 | 2024-06-12 | 2025-03-28 | 24DE0213 | 24DE0213 | 2024-12-06 | 2024-06-19 | 2024-02-07 | 2024-08-07 | 2024-10-07 | R.M. Tejada Construction and Supplies Corp. | Completed
NC 2024 |  | Region IV-A | Batangas City | 109560 | Katandala ES | BATANGAS CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5757000 |  | 5556159.96 | Completed | 1 | 2024-10-11 | 2024-11-14 | 24DE0189 | 24DE0189 | 2024-03-04 | 2024-12-04 | 2024-04-25 | 2024-10-05 | 2024-05-15 | Greenfield Construction | Completed
NC 2024 |  | Region IV-A | Batangas City | 109617 | Lilinggiwan ES | BATANGAS CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 9586000 |  | 9242389.83 | Completed | 1 | 2024-11-25 | 2025-03-24 | 24DE0186 | 24DE0186 | 2024-03-04 | 2024-12-04 | 2024-04-25 | 2024-10-05 | 2024-05-15 | MGS Builders and General Contractor OPC | Completed
NC 2024 |  | Region IV-A | Batangas City | 137130 | Niño Jesus Elementary School | BATANGAS CITY (Capital) |  | 1 | 3 | 1STY3CL | BATCH 1 | 9657229 |  | 9633085.93 | Completed | 1 | 2024-03-12 | 2025-03-28 | 24DE0207 | 24DE0207 | 2024-05-16 | 2024-05-23 | 2024-07-06 | 2024-10-06 | 2024-06-13 | Tristan Tejada Construction | Completed
NC 2024 |  | Region IV-A | Batangas City | 109576 | San Agustin Kanluran ES | BATANGAS CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7236410.77 | Completed | 1 | 2024-11-25 | 2025-04-04 | 24DE0188 | 24DE0188 | 2024-03-04 | 2024-12-04 | 2024-04-25 | 2024-10-05 | 2024-05-15 | GCF Fetalvero Construction and Enterprises | Completed
NC 2024 |  | Region IV-A | Batangas City | 109577 | San Agustin Silangan ES | BATANGAS CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 7500000 |  | 7237582.27 | Completed | 1 | 2024-11-25 | 2025-10-01 | 24DE0187 | 24DE0187 | 2024-03-04 | 2024-12-04 | 2024-04-25 | 2024-10-05 | 2024-05-15 | GCF Fetalvero Construction and Enterprises | Completed
NC 2024 |  | Region IV-A | Binan City | 108213 | Biñan CES (Doña Aurora ES) | CITY OF BIÑAN |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38963391.74 | Ongoing | 0.65 | 2025-05-14 |  | P00875432LZ | 24DI0131 | 2024-05-31 | 2024-07-06 | 2024-06-20 | 2024-10-07 | 2024-07-19 | ALPHA & OMEGA GENERAL CONTRACTOR AND DEVELOPMENT CORPORATION
NC 2024 |  | Region IV-A | Binan City | 301230 | Biñan National High School | CITY OF BIÑAN |  | 1 | 8 | 4STY8CL | BATCH 1 | 37345000 |  | 36297795.01 | Ongoing | 0.93 | 2025-08-05 |  | P00875858LZ | 24DI0141 | 2024-06-21 | 2024-01-07 | 2024-07-22 | 2024-01-08 | 2024-12-08 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION
NC 2024 |  | Region IV-A | Cabuyao City | 330524 | MARINIG NATIONAL HIGH SCHOOL | CABUYAO |  | 1 | 20 | 4STY20CL | BATCH 1 | 70000000 |  | 68187856 | Ongoing | 0.3 | 2025-03-03 |  |  | 24DI0157 | 2024-02-08 | 2024-09-08 | 2024-08-23 | 2024-06-09 | 2024-09-09 | RAPID FOREMOST CONSTRUCTION CO. | With approved modification to construct at Niugan ES with school ID 108246
NC 2024 |  | Region IV-A | Calamba City | 109828 | Banlic Elementary School | CITY OF CALAMBA |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  |  | Ongoing | 0.01
NC 2024 |  | Region IV-A | CALAMBA CITY | 109835 | Parian ES | CITY OF CALAMBA |  | 1 | 12 | 4STY12CL | BATCH 1 | 30000000 |  |  | Ongoing | 0.1
NC 2024 |  | Region IV-A | Cavite | 108016 | Aguinaldo Elementary School | KAWIT |  | 1 | 16 | 4STY16CL | GAA 17B | 40000000 |  | 39400888.51 | Completed | 1 | 2025-05-04 | 2025-05-04 | P00875403LZ-CW1 | 24DF0275 | 2024-09-04 | 2024-04-26 | 2024-09-05 | 2024-01-08 | 2024-05-08 | Miclover General Construction & Iron Works
NC 2024 |  | Region IV-A | Cavite | 108107 | Lucsuhin Elementary School | SILANG |  | 1 | 8 | 4STY8CL | BATCH 1 | 35000000 |  |  | Ongoing | 0.4 | [10 empty] | Ongoing construction
NC 2024 |  | Region IV-A | Cavite | 108132 | Pulong Bunga Elementary School | SILANG |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  |  | Ongoing | 0.4 | [10 empty] | Ongoing construction
NC 2024 |  | Region IV-A | Cavite | 108135 | Santol Elementary School | SILANG |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  |  | Ongoing | 0.4 | [10 empty] | Ongoing construction
NC 2024 |  | Region IV-A | Cavite | 108003 | Agus-os Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4924075.84 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875418LZ-CW1 | 24DF0253 | 2024-09-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | 1024 Construction & Development Corp.
NC 2024 |  | Region IV-A | Cavite | 108011 | Daine Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4922565.18 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875417LZ-CW1 | 24DF0254 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | Elijenrae Builders & Construction Supply
NC 2024 |  | Region IV-A | Cavite | 107993 | Guyam Munti Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4922565.18 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875413LZ-CW1 | 24DF0255 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | Elijenrae Builders & Construction Supply
NC 2024 |  | Region IV-A | Cavite | 107994 | Indang Central Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4923215.18 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875414LZ-CW1 | 24DF0256 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | Elijenrae Builders & Construction Supply
NC 2024 |  | Region IV-A | Cavite | 107997 | Kaytambog Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4923215.18 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875419LZ-CW1 | 24DF0257 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | Elijenrae Builders & Construction Supply
NC 2024 |  | Region IV-A | Cavite | 108000 | Lumampong Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 5000000 |  | 4925006.09 | Completed | 1 | 2024-10-17 | 2024-10-17 | P00875416LZ-CW1 | 24DF0258 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-06 | 2024-06-14 | Southfour Builders Corp.
NC 2024 |  | Region IV-A | Cavite | 108001 | Tambo Elementary School | INDANG |  | 1 |  | Construction of Classroom School Building | GAA 17B | 10000000 |  | 9848562.6 | Completed | 1 | 2025-03-01 | 2025-03-01 | P00875415LZ-CW1 | 24DF0262 | 2024-04-04 | 2024-11-04 | 2024-04-24 | 2024-05-14 | 2024-07-06 | Southfour Builders Corp.
NC 2024 |  | Region IV-A | Cavite | 108052 | Anuling Elementary School | MENDEZ (MENDEZ-NUÑEZ) |  | 1 | 4 | 2STY4CL | GAA 17B | 17000000 |  | 16728582.26 | Completed | 1 | 2024-12-16 | 2024-12-16 | 24DG0106 | 24DG0106 | 2024-07-03 | 2024-03-15 | 2024-03-27 | 2024-08-04 | 2024-04-25 | SDWC Construction
NC 2024 |  | Region IV-A | Cavite | 137106 | Timalan Hillsview Royale Elementary School | NAIC |  | 1 | 20 | 4STY20CL | BATCH 1 | 80000000 |  | 78740147.93 | Ongoing | 0.35 | 2025-07-19 | 2025-07-19 | 24DG0089 | 24DG0089 | 2024-06-08 | 2024-08-15 | 2024-08-27 | 2024-08-30 | 2024-09-16 | WRC Construction and General Merchandise/ SDWC Construction (JV)
NC 2024 |  | Region IV-A | Cavite | 500871 | Tagaytay City Integrated School | TAGAYTAY CITY |  | 1 | 6 | 3STY6CL | GAA 17B | 23000000 |  |  | Completed | 1
NC 2024 |  | Region IV-A | Cavite City | 301484 | Cavite National High School | CAVITE CITY |  | 1 | 16 | 2UNITS 4STY8CL | BATCH 1 | 64879800.6 |  | 63898155 | Ongoing | 0.95 | 2025-05-05 |  | 24DF0278 | 24DF0278 | 2024-04-19 | 2024-04-25 | 2024-09-05 | 2024-05-06 | 2024-06-20 | Miclover General Construction & Iron Works
NC 2024 |  | Region IV-A | Dasmarinas City | 301186 | Dasmariñas Integrated High School | CITY OF DASMARIÑAS |  | 1 | 20 | 4STY20CL | BATCH 1 | 59300000 |  | 58123741.18 | Ongoing | 0.65 | 2025-06-15 |  | 24DQ0106 | 24DQ0106 | 2024-07-06 | 2024-06-18 | 2024-02-07 | 2024-07-23 | 2024-08-15 | LA Clamor Construction Corp.
NC 2024 |  | Region IV-A | Dasmarinas City | 301184 | Dasmarinas North National High School (Annex G) | CITY OF DASMARIÑAS |  | 1 | 16 | 4STY16CL | BATCH 1 | 53000000 |  | 52207575.07 | Ongoing | 0.35 | 2025-06-15 |  | 24DQ0108 | 24DQ0108 | 2024-06-25 | 2024-03-07 | 2024-07-16 | 2024-07-30 | 2024-08-15 | KLDS Trading and Construction
NC 2024 |  | Region IV-A | Dasmarinas City |  | Green Breeze Integrated High School | CITY OF DASMARIÑAS |  | 1 | 6 | 3STY6CL | GAA 17B | 20000000 |  | 19602175.46 | Ongoing | 0.7 | 2025-04-19 |  | 24DQ0109 | 24DQ0109 | 2024-08-07 | 2024-07-16 | 2024-02-08 | 2024-08-19 | 2024-08-28 | LA Clamor Construction Corp.
NC 2024 |  | Region IV-A | Dasmarinas City | 107903 | Humayao ES | CITY OF DASMARIÑAS |  | 1 | 8 | Completion of 4STY8CL | BATCH 1 | 5241510.65 |  | 5124016.27 | Completed | 1 | 2024-01-13 | 2024-03-12 | 24DQ0084 | 24DQ0084 | 2024-03-06 | 2024-11-06 | 2024-06-24 | 2024-06-28 | 2024-12-07 | LA Clamor Construction Corp
NC 2024 |  | Region IV-A | Dasmarinas City |  | Salitran Integrated High School | CITY OF DASMARIÑAS |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39921699.29 | Ongoing | 0.65 | 2025-03-01 |  | 24DQ0064 | 24DQ0064 | 2024-04-04 | 2024-12-04 | 2024-04-24 | 2024-04-30 | 2024-09-05 | KLDS Trading & Construction
NC 2024 |  | Region IV-A | General Trias City | 307822 | Luis Y. Ferrer Jr. West National High School | CITY OF GENERAL TRIAS |  | 1 | 16 | 4STY16CL | GAA 17B | 40000000 |  | 39412746.87 | Ongoing | 0.97 | 2025-05-04 |  | 24DF0276 | 24DF0276 | 2024-04-19 | 2024-04-26 | 2024-09-05 | 2024-01-08 | 2024-05-08 | R.V. Rieta Trading & General Construction | For Completion
NC 2024 |  | Region IV-A | Imus City |  | City of Imus Integrated School | IMUS |  | 1 | 12 | 4STY12CL (Phase 2) | GAA 17B | 10000000 |  | 9846168.77 | Ongoing | 0.95 |  |  | P00875406LZ | 24DF0270 | 2024-04-19 | 2024-04-26 | 2024-09-05 | 2024-05-06 | 2024-06-14 | Omnicon Builders | Anastasio Advincula Integrated School (formerly City of Imus Integrated School) - 502871
NC 2024 |  | Region IV-A | Imus City |  | City of Imus Integrated School | IMUS |  | 1 | 8 | 4STY8CL | GAA 17B | 30000000 |  | 29547185.99 | Ongoing | 0.7 | 2025-01-05 |  | P00875407LZ | 24DF0274 | 2024-04-19 | 2024-04-26 | 2024-09-05 | 2024-05-06 | 2024-06-14 | Keascia Construction & Supply | Anastasio Advincula Integrated School (formerly City of Imus Integrated School) - 502871
NC 2024 |  | Region IV-A | Imus City | 107986 | Malagasang I Elementary School | IMUS |  | 1 | 12 | 4STY12CL | BATCH 1 | 46176738.79 |  | 45486300 | Ongoing | 0.25 | 2025-03-15 |  | P00875867LZ | 24DF0280 | 2024-05-14 | 2024-05-21 | 2024-05-06 | 2024-06-24 | 2024-01-07 | V.R. Patron Builders & Developers Corp.
NC 2024 |  | Region IV-A | Laguna | 164502 | Kabaritan Elementary School | BAY |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19793326.05 | Completed | 1 | 2025-04-14 | 2025-04-04 |  | 24DI0130 |  | 2024-07-06 |  | 2024-10-07 | 2024-07-19 | KAEL CONSTRUCTION AND SUPPLY | with revisions due to variation order
NC 2024 |  | Region IV-A | Laguna | 307936 | Los Banos Integrated Sch. (LBCHS-Annex) | LOS BAÑOS |  | 1 | 4 | 2STY4CL | GAA 17B | 20000000 |  | 19894600.24 | Ongoing | 0.5 | 2025-07-03 |  |  | 24DI0144 |  | 2024-05-07 |  | 2024-01-08 | 2024-08-12 | 11 DIAMOND EAGLE CONSTRUCTION CORPORATION | with revisions due to variation order
NC 2024 |  | Region IV-A | Laguna | 108189 | De Mesa ES | ALAMINOS |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9647639 | Ongoing | 0.7 | 2025-08-04 | 2025-08-04 | P00875436LZ | 24DP0165 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | R'CEL GENERAL CONTRACTOR & GENERAL MERCHANDISE | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108191 | Palma ES | ALAMINOS |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9661450 | Ongoing | 0.4 | 2025-08-04 |  | P00875428LZ | 24DP0161 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | MEGA M BUILDERS CORPORATION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108192 | San Agustin ES | ALAMINOS |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9650732 | Ongoing | 0.7 | 2025-08-04 |  | P00875429LZ | 24DP0159 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | BHENLLABIEN BUILDERS CONSTRUCTION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108260 | Limao ES | CALAUAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9651691.2 | Ongoing | 0.4 | 2025-08-04 |  | P00875427LZ | 24DP0162 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | BHENLLABIEN BUILDERS CONSTRUCTION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108354 | Banilad ES | NAGCARLAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9661450 | Ongoing | 0.4 | 2025-08-04 |  | P00875434LZ | 24DP0163 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | MEGA M BUILDERS CORPORATION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108368 | Sinipian ES | NAGCARLAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9671400 | Ongoing | 0.5 | 2025-08-04 |  | P00875435LZ | 24DP0164 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | MEGA M BUILDERS CORPORATION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108370 | Taytay-Malaya ES | NAGCARLAN |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9671400 | Ongoing | 0.5 | 2025-08-04 |  | P00875433LZ | 24DP0160 | 2024-09-08 | 2024-08-16 | 2024-08-28 | 2024-09-09 | 2024-11-09 | MEGA M BUILDERS CORPORATION | DepEd 2024 Phase 1
NC 2024 |  | Region IV-A | Laguna | 108449 | Santo Angel Sur ES | SANTA CRUZ (Capital) |  | 1 | 12 | 4STY12CL (Phase 1) | GAA 17B | 40000000 |  | 38983504.4 | Completed | 1 | 2025-03-22 | 2025-03-18 | P00875431LZ | 24DH0048 | 2024-04-04 | 2024-11-04 | 2024-04-23 | 2024-04-25 | 2024-06-05 | DATZLAV CONSTRUCTION | Ongoing construction
NC 2024 |  | Region IV-A | Lipa City | 501185 | San Jose Integrated School | LIPA CITY |  | 1 |  | Construction of School Building | GAA 17B | 40000000 |  | 38605619.36 | Ongoing | 0.6 | 2025-01-25 |  | 24DD0226 | 24DD0226 |  | 2024-06-27 |  | 2024-07-22 | 2024-07-30 | T. SOLOMON CONSTRUCTION AND DEVELOPMENT CORP. | Building Permit/Demolition Permit on process
NC 2024 |  | Region IV-A | Lipa City | 109657 | Tipakan ES | LIPA CITY |  | 1 |  | Construction of School Building | GAA 17B | 40000000 |  | 38608313.1 | Ongoing | 0.9 | 2024-12-31 |  | 24DD0211 | 24DD0211 |  | 2024-05-30 |  | 2024-06-25 | 2024-05-07 | RANRAC CONSTRUCTION/ARE CONSTRUCTION AND SUPPLY JV | Building Permit on process
NC 2024 |  | Region IV-A | Lucena City | 308507 | Lucena Dalahican National High School - Barra Annex | LUCENA CITY (Capital) |  | 1 | 12 | 4STY12CL | BATCH 1 | 49388138.8 |  |  | Not Yet Started | 0.2
NC 2024 |  | Region IV-A | Quezon | 301334 | Burdeos NHS (Judith NHS) | BURDEOS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875200.33 | Completed | 1 | 2024-08-20 | 2024-08-20 | P00875446LZ | 24DK0061 | 2024-03-15 | 2024-03-22 | 2024-03-04 | 2024-04-16 | 2024-04-22 | C. VILLASEÑOR JR. CONSTRUCTION
NC 2024 |  | Region IV-A | Quezon | 502072 | Magsikap Integrated School | GENERAL NAKAR |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875226.46 | Completed | 1 | 2024-08-20 | 2024-08-20 | P00875443LZ | 24DK0062 | 2024-03-15 | 2024-03-22 | 2024-03-04 | 2024-04-16 | 2024-04-22 | F.M. PUJEDA BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region IV-A | Quezon | 108910 | Doña Aurora ES | MAUBAN |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7313250 | Completed | 1 | 2024-11-25 | 2024-11-25 | P00875441LZ | 24DK0067 | 2024-03-27 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-04-29 | W.J. CONSTRUCTION
NC 2024 |  | Region IV-A | Quezon | 108569 | Rizal ES | PANUKULAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875739.13 | Completed | 1 | 2024-08-20 | 2024-08-20 | P00875444LZ | 24DK0065 | 2024-03-15 | 2024-03-22 | 2024-03-04 | 2024-04-16 | 2024-04-22 | C. VILLASEÑOR JR. CONSTRUCTION
NC 2024 |  | Region IV-A | Quezon | 305524 | Paaralang Sekundarya ng Patnanungan Norte | PATNANUNGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4876076.48 | Completed | 1 | 2024-08-20 | 2024-08-20 | P00875445LZ | 24DK0063 | 2024-03-15 | 2024-03-22 | 2024-03-04 | 2024-04-16 | 2024-04-22 | C. VILLASEÑOR JR. CONSTRUCTION
NC 2024 |  | Region IV-A | Quezon | 301377 | Polillo National High School (SHS) | POLILLO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4875714.86 | Completed | 1 | 2024-08-20 | 2024-08-20 | P00875447LZ | 24DK0064 | 2024-03-15 | 2024-03-22 | 2024-03-04 | 2024-04-16 | 2024-04-22 | C. VILLASEÑOR JR. CONSTRUCTION
NC 2024 |  | Region IV-A | Quezon | 109074 | Real Central Elementary School | REAL |  | 1 | 3 | 1STY3CL | GAA 17B | 7500000 |  | 7313250 | Completed | 1 | 2024-10-26 | 2024-10-26 | P00875442LZ | 24DK0068 | 2024-03-27 | 2024-04-04 | 2024-04-16 | 2024-04-22 | 2024-04-29 | F.M. PUJEDA BUILDERS AND CONSTRUCTION SUPPLIES
NC 2024 |  | Region IV-A | Quezon | 108622 | Mangilag Sur ES | CANDELARIA |  | 1 | 4 | 2STY4CL | GAA 17B | 12000000 |  | 11701200 | Ongoing | 0.07 | 2025-10-03 | 2025-10-03 | 24DJ0177 | 24DJ0177 | 2024-07-06 | 2024-06-17 | 2024-02-07 | 2024-07-31 | 2024-07-17 | ROMHEAD S.J. BUILDERS & DEV'T INC.
NC 2024 |  | Region IV-A | Quezon | 301317 | Dagatan National High School | DOLORES |  | 1 | 12 | Completion of 3STY12CL | BATCH 1 | 6048728.66 |  | 5880059.86 | Ongoing | 0.48 | 2024-12-15 | 2024-12-15 | 24DJ0156 | 24DJ0156 | 2024-03-05 | 2024-10-05 | 2024-05-23 | 2024-06-06 | 2024-06-18 | ROMHEAD S.J. BUILDERS & DEV'T INC.
NC 2024 |  | Region IV-A | Quezon | 109109 | Niing ES | SAN ANTONIO |  | 1 | 12 | 3STY12CL | GAA 17B | 30000000 |  | 29251764.28 | Ongoing | 0.28 | 2025-10-08 |  | 24DJ0176 | 24DJ0176 | 2024-07-06 | 2024-06-17 | 2024-02-07 | 2024-12-07 | 2024-07-17 | ROMHEAD S.J. BUILDERS & DEV'T INC./ I.A. BOSQUE CONSTRUCTION CORP.
NC 2024 |  | Region IV-A | Quezon | 301348 | Lusacan National High School | TIAONG |  | 1 | 10 | 2STY10CL | GAA 17B | 28000000 |  | 27302800 | Ongoing | 0.01 | 2025-07-08 |  | 24DJ0178 | 24DJ0178 | 2024-07-06 | 2024-06-17 | 2024-02-07 | 2024-12-07 | 2024-07-17 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP. | Suspended
NC 2024 |  | Region IV-A | Quezon | 109283 | San Isidro ES | TIAONG |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9760950 | Ongoing | 0.29 | 2025-12-02 | 2025-12-02 | 24DJ0175 | 24DJ0175 | 2024-07-06 | 2024-06-17 | 2024-02-07 | 2024-12-07 | 2024-07-17 | WAYCON BUILDERS AND CONSTRUCTION SUPPLY CORP.
NC 2024 |  | Region IV-A | Quezon | 108944 | Agdangan Central Elementary School | AGDANGAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-16 | 2024-11-16 | P00875452LZ | 24DM0138 | 2024-04-24 | 2024-05-02 | 2024-05-14 | 2024-05-27 | 2024-06-05 | RPS BUILDERS GENERAL CONTRACTOR CORP.
NC 2024 |  | Region IV-A | Quezon | 305767 | General Luna National High School | GENERAL LUNA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-10 | 2024-11-08 | P00875453LZ | 24DM0145 | 2024-05-07 | 2024-05-15 | 2024-05-28 | 2024-06-06 | 2024-06-14 | RPS BUILDERS GENERAL CONTRACTOR CORP.
NC 2024 |  | Region IV-A | Quezon | 108880 | Mambog ES | MACALELON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-08 | 2024-11-08 | P00875454LZ | 24DM0146 | 2024-05-07 | 2024-05-15 | 2024-05-28 | 2024-06-06 | 2024-06-14 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2024 |  | Region IV-A | Quezon | 108919 | Ajos ES | MULANAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-10-08 | 2024-10-08 | P00875455LZ | 24DM0139 | 2024-04-24 | 2024-05-02 | 2024-05-14 | 2024-05-27 | 2024-06-05 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2024 |  | Region IV-A | Quezon | 108954 | Padre Burgos CS | PADRE BURGOS |  | 1 | 6 | 2STY6CL | BATCH 1 | 20000000 |  | 19900000 | Ongoing | 0.82 | 2025-06-28 |  |  | 24DM0158 | 2024-05-18 | 2024-05-27 | 2024-06-11 | 2024-07-01 | 2024-07-11 | LAICAN ENTERPRISES, INC
NC 2024 |  | Region IV-A | Quezon | 109012 | Sampaloc ES | PITOGO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-11 | 2024-11-11 | P00875456LZ | 24DM0147 | 2024-05-07 | 2024-05-15 | 2024-05-28 | 2024-06-06 | 2024-06-14 | RPS BUILDERS GENERAL CONTRACTOR CORP.
NC 2024 |  | Region IV-A | Quezon | 109118 | Butanguiad ES | SAN FRANCISCO (AURORA) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-10-08 | 2024-10-08 | P00875458LZ | 24DM0140 | 2024-04-24 | 2024-05-02 | 2024-05-14 | 2024-05-22 | 2024-06-05 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2024 |  | Region IV-A | Quezon | 109120 | Cawayan II ES | SAN FRANCISCO (AURORA) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-11-11 | 2024-11-11 | P00875457LZ | 24DM0141 | 2024-05-07 | 2024-05-15 | 2024-05-28 | 2024-06-06 | 2024-06-14 | QUEZON VICTORY LUMBER AND GENERAL CONTRACTOR
NC 2024 |  | Region IV-A | Quezon | 109296 | Caigdal ES | UNISAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 | 2024-10-08 | 2024-10-08 | P00875459LZ | 24DM0144 | 2024-04-24 | 2024-05-02 | 2024-05-14 | 2024-05-27 | 2024-06-05 | RPS BUILDERS GENERAL CONTRACTOR CORP.
NC 2024 |  | Region IV-A | Quezon | 108732 | Danlagan ES | GUINAYANGAN |  | 1 | 3 | 1STY3CL | GAA 17B | 7000000 |  | 6982500 | Completed | 1 | 2024-03-11 | 2024-03-11 | P00875461LZ-CW1 | 24DL0153 | 2024-02-21 | 2024-02-28 | 2024-03-11 | 2024-03-19 | 2024-02-04 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP.
NC 2024 |  | Region IV-A | Quezon | 108744 | San Luis I Elementary School | GUINAYANGAN |  | 1 | 3 | 1STY3CL | GAA 17B | 7000000 |  | 6982500 | Completed | 1 | 2024-03-11 | 2024-03-11 | P00875462LZ-CW1 | 24DL0154 | 2024-02-21 | 2024-02-28 | 2024-03-11 | 2024-03-19 | 2024-02-04 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP.
NC 2024 |  | Region IV-A | Quezon | 108809 | Lalaguna I ES | LOPEZ |  | 1 | 8 | 4STY8CL | BATCH 1 | 25350000 |  | 25286625 | Ongoing |  | 2024-08-02 | 2025-09-05 | P00875871LZ-CW1 | 24DL0175 | 2024-03-28 | 2024-04-04 | 2024-04-16 | 2024-04-23 | 2024-09-05 | MURIELEVEN BUILDERS AND CONSTRUCTION SUPPLY CORP.
NC 2024 |  | Region IV-A | Quezon | 301345 | Lopez National Comprehensive High School | LOPEZ |  | 1 | 8 | 2STY8CL | GAA 17B | 26000000 |  | 25935000 | Completed | 1 | 2024-01-02 | 2024-01-02 | P00875460LZ-CW1 | 24DL0155 | 2024-02-21 | 2024-02-28 | 2024-03-11 | 2024-03-19 | 2024-02-04 | KKT CONSTRUCTION AND SUPPLY
NC 2024 |  | Region IV-A | Rizal |  | Binangonan Integrated National High School | BINANGONAN |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 39800000 | Completed | 1 | 2025-12-04 | 2025-12-04 | P00875466LZ | 24DN0130 | 2024-04-17 | 2024-04-24 | 2024-07-05 | 2024-05-16 | 2024-05-27 | Miclover Gen. Const. and Iron Works
NC 2024 |  | Region IV-A | Rizal | 301469 | Vicente Madrigal National High School | BINANGONAN |  | 1 | 12 | Construction of School Building | BATCH 1 | 50000000 |  | 49875000 | Ongoing | 0.6 | 2025-09-07 |  | P00875872LZ | 24DN0172 | 2024-05-24 | 2024-05-31 | 2024-06-13 | 2024-06-25 | 2024-06-15 | Miclover Gen. Const. and Iron Works | 4STY12CL
NC 2024 |  | Region IV-A | Rizal | 109507 | Laiban Elementary School | TANAY |  | 1 | 8 | 2STY8CL | GAA 17B | 40000000 |  | 38405858.07 | Ongoing | 0.8 | 2025-04-25 |  | P000875467LZ-CW1 | 24DO0104 | 2024-08-04 | 2024-04-18 | 2024-04-30 | 2024-06-26 | 2024-10-07 | ASCENTIA CONSTRUCTION, INC.
NC 2024 |  | Region IV-A | Rizal | 109487 | Guitnangbayan ES | SAN MATEO |  | 1 | 8 | 3STY8CL | GAA 17B | 40000000 |  | 38307536.16 | Ongoing | 0.2 | 2025-08-09 |  | P000875468LZ-CW1 | 24DO0120 | 2024-07-09 | 2024-09-13 | 2024-09-26 | 2024-11-18 | 2024-11-27 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, INC. | with approved modification to 4STY8CL - Bidded last September 26, 2024
NC 2024 |  | Region IV-A | Rizal |  | Montalban Science High School | RODRIGUEZ (MONTALBAN) |  | 1 | 12 | 3STY12CL | GAA 17B | 40000000 |  | 38407754.87 | Ongoing | 0.1 | 2025-10-27 |  | P000875469LZ-CW1 | 24DO0121 | 2024-11-22 | 2024-11-29 | 2024-12-12 | 2024-12-23 | 2025-01-15 | D.C. SANDIL CONSTRUCTION AND REALTY DEVELOPMENT, INC. | Montalban Science High School, 3STY12CL ; modified to Amityville ES, 4STY8CL
NC 2024 |  | Region IV-A | San Pablo City | 109804 | Concepcion Elementary School | SAN PABLO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9731581 | Ongoing | 0.75 | 2025-08-04 |  | P00875437LZ-CW1 | 24DP0157 | 2024-07-20 | 2024-07-29 | 2024-08-20 | 2024-08-30 | 2024-11-09 | L.P.O. Enterprises
NC 2024 |  | Region IV-A | San Pablo City | 109771 | San Marcos Elementary School | SAN PABLO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9731581 | Ongoing | 0.45 | 2025-08-04 |  | P00875430LZ-CW1 | 24DP0153 | 2024-07-20 | 2024-07-29 | 2024-08-20 | 2024-08-30 | 2024-11-09 | L.P.O. Enterprises
NC 2024 |  | Region IV-A | San Pablo City | 109802 | Sta. Ana Elementary School | SAN PABLO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9651264 | Ongoing | 0.7 | 2025-08-04 |  | P00875439LZ-CW1 | 24DP0154 | 2024-07-20 | 2024-07-29 | 2024-08-20 | 2024-08-30 | 2024-11-09 | Magna Rich Trading & Construction
NC 2024 |  | Region IV-A | San Pablo City | 109811 | Sta. Catalina Elementary School | SAN PABLO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9731581 | Ongoing | 0.55 | 2025-08-04 |  | P00875438LZ-CW1 | 24DP0155 | 2024-07-20 | 2024-07-29 | 2024-08-20 | 2024-08-30 | 2024-11-09 | L.P.O. Enterprises
NC 2024 |  | Region IV-A | San Pablo City | 109767 | Sto. Niño Elementary School | SAN PABLO CITY |  | 1 | 4 | 2STY4CL | GAA 17B | 10000000 |  | 9651264 | Ongoing | 0.7 | 2025-08-04 |  | P00875440LZ-CW1 | 24DP0156 | 2024-07-20 | 2024-07-29 | 2024-08-20 | 2024-08-30 | 2024-11-09 | Magna Rich Trading & Construction
NC 2024 |  | Region IV-A | San Pedro City | 307921 | Adelina I National High School (Sampaguita Annex) | SAN PEDRO |  | 1 | 8 | 4STY8CL | GAA 17B | 40000000 |  | 38606000 | Not Yet Started | 0 |  |  | 24DI0145 | 24DI0145 | 2024-06-28 | 2024-05-07 | 2024-07-22 | 2024-05-08 | 2024-08-19 | TERAVERA CORPORATION | on going demolition of existing building
NC 2024 |  | Region IV-A | San Pedro City | 108427 | Pacita Complex II ES | SAN PEDRO |  | 1 | 12 | 4STY12CL | BATCH 1 | 55687403.24 |  | 54012660 | Ongoing | 0.85 | 2025-06-13 |  | 24DI0132 | 24DI0132 | 2024-05-31 | 2024-07-06 | 2024-06-20 | 2024-11-07 | 2024-07-22 | GMO CONSTRUCTION
NC 2024 |  | Region IV-A | Santo Tomas City | 107718 | Sta. Maria Elementary School | SANTO TOMAS |  | 1 | 9 | 3STY9CL | BATCH 1 | 36000000 |  | 35070928 | Ongoing | 0.9 | 2025-03-15 |  | P00986974LZ-CW1 | 24DC0145 | 2024-04-03 | 2024-04-10 | 2024-04-23 | 2024-06-09 | 2024-06-19 | ARCEGA ACUZAR CONSTRUCTION AND DEVELOPMENT CORPORATION/ KAEL CONSTRUCTION AND SUPPLY JV | with suspension order but no copy furnish, delayed
NC 2024 |  | Region IV-A | Sta. Rosa City | 108473 | Dita Elementary School | CITY OF SANTA ROSA |  | 1 | 12 | 4STY12CL | GAA 17B | 40000000 |  | 38845165 | Ongoing | 0.4 | 2025-10-30 |  | 24DI0183 | 24DI0183 | 2024-10-18 | 2024-10-28 | 2024-11-11 | 2024-12-27 | 2025-06-01 | R.R. ENCABO CONSTRUCTORS, INC. | with approved modification to 4STY8CL - Bidded
NC 2024 |  | Region IV-A | Tanauan City | 301084 | Bernardo Lirio Memorial National High School | CITY OF TANAUAN |  | 1 | 8 | 4STY8CL | BATCH 1 | 35000000 |  |  | Ongoing | 0.35
NC 2024 |  | Region IV-A | Tayabas City | 301347 | Luis Palad Integrated High School | CITY OF TAYABAS |  | 1 | 16 | 4STY16CL | BATCH 1 | 52000000 |  | 51739996.64 | Ongoing | 0.6 | 2025-02-28 | 2025-09-26 | P0087586L2 | 24DK0119 | 2024-05-24 | 2024-05-31 | 2024-06-13 | 2024-06-27 | 2024-03-07 | WJ Construction | With suspension

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.