## Sheet1
Program-Year | CATEGORY | Region | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | NO. OF SITES | PHYSICAL TARGET (# OF CL) | SCOPE OF WORK | Batch | Total Project Allocation | Total Project Cost | CONTRACT AMOUNT | STATUS | PERCENTAGE OF COMPLETION | Target Completion Date | Actual Date of Completion | Project ID | Contract ID | Issuance of Invitation to Bid | Pre-Submission Conference | Bid Opening | Issuance of Resolution to Award | Issuance of Notice to Proceed | Name of Contractor | Other Remarks | Status as of July 11, 2025
NC 2014 | K10 (2014) | Region IX | Dapitan City | 125913 | Burgos ES | DAPITAN CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 090414S00160 | 14JD0018 | 2014-06-13 | 2014-06-30 | 2014-07-21 | 2014-08-04 | 2014-08-19 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Dapitan City | 125948 | Opao ES | DAPITAN CITY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-12-26 | 2014-12-26 | 090414S00159 | 14JD0018 | 2014-06-13 | 2014-06-30 | 2014-07-21 | 2014-08-04 | 2014-08-19 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Dipolog City | 125986 | Cogon ES | DIPOLOG CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-07-30 | 090414S00158 | 14JB0005 | 2014-07-15 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Dipolog City | 303886 | Cogon NHS | DIPOLOG CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Dipolog City | 125992 | Olingan South ES | DIPOLOG CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-01-30 | 090414S00157 | 14JB0005 | 2014-07-15 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Dipolog City | 125977 | Sta. Isabel ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-06-05 | 2015-05-28 | 090414S00164 | 14JB0026 | 2014-10-31 | 2014-11-24 | 2014-11-27 | 2015-01-02 | 2015-01-06 | DIPOLOG TOP CONSTRUCTION & DEVT. CORP
NC 2014 | K10 (2014) | Region IX | Dipolog City | 125970 | Turno ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-05-05 | 2015-05-28 | 090414S00165 | 14JB0025 | 2014-10-31 | 2014-11-24 | 2014-11-27 | 2015-01-02 | 2015-01-06 | DIPOLOG TOP CONSTRUCTION & DEVT. CORP
NC 2014 | K10 (2014) | Region IX | Dipolog City | 125999 | Virginia ES | DIPOLOG CITY (Capital) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-05-28 | 090414S00156 | 14JB0005 | 2014-07-15 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 | 0 | 6 | 2STY6CL | 2014 K10 BATCH 4A | 8228453.2031 |  |  | COMPLETED | 1 | 2015-10-14 | [7 empty] | 2015-05-13 | 2M Construction & Enterprises | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 126019 | Diki ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 090114S00002 | 090114S00002 | 2014-07-06 | 2014-07-14 | 2014-07-15 | 2014-07-19 | 2014-07-29 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 198015 | Ismael Primary School | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-10-29 | 2015-10-25 | 090114S00007 | 14JH0025 | 2015-02-02 | 2015-02-19 | 2015-02-20 | 2015-02-24 | 2015-03-02 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 303899 | Kumalarang NHS | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 3 | 4291899.6094 |  |  | COMPLETED | 1 | 2015-10-25 |  | 090114S00006 | 14JH0025 | 2015-02-10 | 2015-02-20 | 2015-02-20 | 2015-02-25 | 2015-03-02 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 126022 | Lukbuton ES | CITY OF ISABELA (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 090114S00004 | 090114S00004 | 2014-07-06 | 2014-07-14 | 2014-07-15 | 2014-07-19 | 2014-07-29 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 126006 | Simeon & Josefa Obsequio ES (Binuangan ES) | CITY OF ISABELA (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 090114S00003 | 090114S00003 | 2014-07-06 | 2014-07-14 | 2014-07-15 | 2014-07-19 | 2014-07-29 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Isabela City | 126016 | Spillway ES | CITY OF ISABELA (Capital) | 0 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 090114S00005 | 090114S00005 | 2014-07-06 | 2014-07-14 | 2014-07-15 | 2014-07-19 | 2014-07-29 | By Administration | No Certificate of Turnover/Completion
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126037 | Bogo ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 090514S00085 | 14JE0031 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 314705 | Co Tek Chun Trade School | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8303753.2031 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126071 | Dumagoc ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00081 | 14JE0035 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | KVC CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126043 | Gubang ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 090514S00084 | 14JE0033 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | GCMG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2310417.57 |  |  | COMPLETED | 1 | 2014-12-31 | 2014-12-31 | 090514S00083 | 14JE0036 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | GCMG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126064 | Lenienza ES | PAGADIAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2935174.43 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00082 | 14JE0035 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | KVC CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126091 | Lison Valley ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2045417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 090514S00062 | 14JE0031 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126074 | Lumad ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 090514S00080 | 14JE0033 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | GCMG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 314701 | Macasing NHS (PCNHS Annex, Macasing) | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-24 | 090514S00086 | 14JE0033 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | GCMG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00079 | 14JE0034 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126076 | Nazareth ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 090514S00078 | 14JE0036 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | GCMG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126077 | Palpalan ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00077 | 14JE0034 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 303912 | Sta. Lucia NHS (ZDS NHS, Sta. Lucia Annex) | PAGADIAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00074 | 14JE0032 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126095 | Sto. Nino Elementary School | PAGADIAN CITY (Capital) | 1 | 0 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 4A | 5266825.7381 |  |  | COMPLETED | 1 | 2016-03-06 |  | 090514S00121 | 15JE0078 | 2015-05-31 | 2015-06-30 | 2015-07-13 | 2015-07-27 | 2015-08-25 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Pagadian City | 126080 | Upper Sibatang ES | PAGADIAN CITY (Capital) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-14 | 2015-02-14 | 090514S00076 | 14JE0032 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126097 | Ayala CS | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 3 | 22475411.7188 |  |  | COMPLETED | 1 | 2016-04-28 |  | 090614S00015 | 14JA0044 | 2015-02-16 | 2015-02-28 | 2015-03-01 | 2015-03-05 | 2015-03-09 | RCDG CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126099 | Cabigan ES | ZAMBOANGA CITY | 1 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126215 | Luyahan ES | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6298664.7656 |  |  | COMPLETED | 1 | 2015-11-02 | 2015-11-30 | 090614S00017 | 14JA0043 | 2015-02-23 | 2015-03-07 | 2015-03-08 | 2015-03-12 | 2015-03-16 | LL CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126218 | Salum ES | ZAMBOANGA CITY | 1 | 1 | 3 | 1STY1CL & 1STY2CL | 2014 K10 BATCH 1 | 3062746.69 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126219 | San Roque Elementary School | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 303925 | Sinubong NHS | ZAMBOANGA CITY | 1 | 1 | 2 | 1STY1CL | 2014 K10 BATCH 4B | 1162049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126104 | Sinunuc ES | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2014 K10 BATCH 3 | 8228453.2031 |  |  | COMPLETED | 1 | 2015-12-30 | 2015-12-30 | 090614S00013 | 14JA0041 | 2015-04-07 | 2015-04-19 | 2015-04-20 | 2015-04-24 | 2015-05-25 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126210 | Sta. Barbara CS | ZAMBOANGA CITY | 1 | 1 | 30 | 3STY15CL | 2014 K10 BATCH 3 | 44950823.4375 |  |  | COMPLETED | 1 | 2016-04-28 |  | 090614S00016 | 14JA0045 | 2015-02-16 | 2015-02-28 | 2015-03-01 | 2015-03-05 | 2015-03-09 | RCDG CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126220 | Sta. Maria CS | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | 2014 K10 BATCH 3 | 22475411.7188 |  |  | COMPLETED | 1 | 2016-04-28 |  | 090614S00014 | 14JA0042 | 2015-02-16 | 2015-02-28 | 2015-03-01 | 2015-03-05 | 2015-03-09 | RCDG CONSTRUCTION CORPORATION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126223 | Arena Blanco East ES | ZAMBOANGA CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-02-28 | 090614S00006 | 14JA0022 | 2014-07-29 | 2014-08-10 | 2014-08-11 | 2014-08-15 | 2014-08-19 | AEJ HARDWARE CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126232 | Bincul ES | ZAMBOANGA CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00008 | 14JA0021 | 2014-08-29 | 2014-09-10 | 2014-09-11 | 2014-09-15 | 2014-09-19 | IIEE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126185 | Lanote ES | ZAMBOANGA CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-04-30 | 090614S00001 | 14JA0025 | 2014-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-02 | 2015-01-05 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126238 | Malanta ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00009 | 14JA0021 | 2014-09-29 | 2014-10-10 | 2014-09-11 | 2014-10-15 | 2014-10-20 | IIEE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 314806 | Mangusu IS | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126227 | Pangapuyan ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-02-28 | 090614S00007 | 14JA0022 | 2014-07-29 | 2014-08-10 | 2014-08-11 | 2014-08-15 | 2014-08-19 | AEJ HARDWARE CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126204 | Putik CS | ZAMBOANGA CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00005 | 14JA0026 | 2015-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-02 | 2015-01-05 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126170 | Sangali ES | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126131 | Sapa Moro ES | ZAMBOANGA CITY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00011 | 14JA0025 | 2015-12-15 | 2014-12-27 | 2014-12-28 | 2015-01-02 | 2015-01-05 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126132 | Sibutat ES | ZAMBOANGA CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00004 | 14JA0021 | 2014-08-29 | 2014-09-10 | 2014-09-11 | 2014-09-15 | 2014-09-19 | IIEE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126250 | Talaga ES | ZAMBOANGA CITY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-04-05 | 2015-04-05 | 090614S00012 | 14JA0021 | 2014-08-29 | 2014-09-10 | 2014-09-11 | 2014-09-15 | 2014-09-19 | IIEE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 303937 | Tolosa NHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga City | 126206 | Zambowood ES | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 4B | 6319337.6381 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124657 | Bagumbayan ES | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2920174.43 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 090414S00040 | 14JD0028 | 2014-08-06 | 2014-08-29 | 2014-09-15 | 2014-10-06 | 2014-10-20 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124550 | Boboringan ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 090414S00099 | 14JD0021 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124640 | Buenavista ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-17 | 090414S00046 | 14JD0027 | 2014-06-20 | 2014-07-16 | 2014-07-28 | 2014-08-12 | 2014-09-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124554 | Dilawa ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 090414S00055 | 14JD0021 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124555 | Dionum ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 090414S00054 | 14JD0021 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124643 | Don Eleno Razo ES | SERGIO OSMEÑA SR. | 1 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3519886.575 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124658 | Kauswagan ES | SERGIO OSMEÑA SR. | 1 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 4B | 4525568.2979 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124399 | La Union ES | LA LIBERTAD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00163 | 14JD0019 | 2014-08-06 | 2014-08-29 | 2014-09-15 | 2014-10-06 | 2014-10-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124588 | Lapayan Baja ES | POLANCO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00051 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124589 | Letapan ES | POLANCO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00050 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124645 | Liwanag ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090414S00056 | 14JD0023 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124402 | Mercedes ES | LA LIBERTAD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1109829.12 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090414S00161 | 14JD0019 | 2014-08-06 | 2014-08-29 | 2014-09-15 | 2014-10-06 | 2014-10-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124592 | Milad ES | POLANCO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1114329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00049 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124663 | Nazareth ES | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-05-20 | 2015-05-20 | 090414S00039 | 14JD0028 | 2014-08-06 | 2014-08-29 | 2014-09-15 | 2014-10-06 | 2014-10-20 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124664 | Nebo ES | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2918674.43 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 090414S00017 | 14JD0029 | 2014-06-30 | 2014-07-11 | 2014-07-21 | 2014-08-11 | 2014-09-01 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124665 | Nueva Vista ES | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2700828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124748 | Oyan ES | SIBUTAD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2013917.57 |  |  | COMPLETED | 1 | 2014-12-16 | 2014-12-16 | 090414S00074 | 14JD0020 | 2014-06-13 | 2014-06-30 | 2014-07-21 | 2014-08-04 | 2014-08-19 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124667 | Princesa Freshia ES | SERGIO OSMEÑA SR. | 1 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4900592 |  |  | COMPLETED | 1 | 2015-05-17 | 2015-05-17 | 090414S00045 | 14JD0032 | 2014-06-30 | 2014-07-18 | 2014-08-04 | 2014-08-20 | 2014-09-19 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124670 | San Francisco ES | SERGIO OSMEÑA SR. | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-05-30 | 2015-05-30 | 090414S00038 | 14JD0032(goods) | 2014-08-20 | 2014-09-22 | 2014-11-15 | 2014-12-29 | 2015-02-23 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124671 | San Isidro CS | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2918674.43 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 090414S00075 | 14JD0029 | 2014-06-30 | 2014-07-11 | 2014-07-21 | 2014-08-04 | 2014-09-01 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124404 | San Jose ES | LA LIBERTAD | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090414S00162 | 14JD0019 | 2014-08-06 | 2014-08-29 | 2014-09-15 | 2014-10-06 | 2014-10-20 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124648 | San Jose ES | SERGIO OSMEÑA SR. | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090414S00044 | 14JD0023 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124581 | San Miguel ES | POLANCO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00052 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303695 | Sawang NHS | SIBUTAD | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124650 | Senai ES | SERGIO OSMEÑA SR. | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-05-15 | 2015-05-15 | 090414S00043 | 14JD0035 | 2014-08-20 | 2014-09-22 | 2014-11-15 | 2014-12-29 | 2015-02-16 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314126 | Sergio Osmena NHS Ext. - Marapong | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-29 | 2015-03-29 | 090414S00071 | 14JD0029 | 2014-06-30 | 2014-07-21 | 2014-07-25 | 2014-08-11 | 2014-09-01 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124596 | Sianib ES | POLANCO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2003417.57 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00048 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124597 | Silawe CS | POLANCO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2003417.57 |  |  | COMPLETED | 1 | 2015-02-16 | 2015-02-16 | 090414S00037 | 14JD0025 | 2014-06-13 | 2014-07-04 | 2014-07-07 | 2014-07-30 | 2014-08-12 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124567 | Tinaytayan ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-02-08 | 2015-02-08 | 090414S00053 | 14JD0021 | 2014-07-22 | 2014-08-19 | 2014-08-22 | 2014-09-15 | 2014-09-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124653 | Tinindugan ES | SERGIO OSMEÑA SR. | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-17 | 2015-02-17 | 090414S00042 | 14JD0027 | 2014-06-20 | 2014-07-28 | 2014-08-04 | 2014-08-15 | 2014-09-09 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124654 | Tuburan ES | SERGIO OSMEÑA SR. | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-02-26 | 090414S00041 | 14JD0034 | 2014-08-11 | 2014-09-01 | 2014-09-05 | 2014-09-22 | 2014-10-13 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124359 | Balok ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2002917.57 |  |  | COMPLETED | 1 | 2015-03-16 |  | 090414S00076 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124493 | Balubohan ES | PRES. MANUEL A. ROXAS | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4010835.14 |  |  | COMPLETED | 1 | 2015-04-30 |  | 090414S00019 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124804 | Bartolome Tobias ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00024 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124787 | Bato ES | SINDANGAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3549886.575 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124757 | Binuangan ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1118129.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-02-27 | 090414S00032 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124323 | Bitoon ES | JOSE DALMAN (PONOT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1126329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00070 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124362 | Bulawan ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-05-28 | 090414S00064 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124494 | Canibongan ES | PRES. MANUEL A. ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-05-28 | 090414S00006 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124363 | Carupay ES | KATIPUNAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-05-28 | 090414S00063 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-25 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124792 | Dagohoy ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1118829.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00028 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124769 | Dagum ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00030 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124677 | Datagan ES | SIAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1139329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00008 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195541 | Diongan ES Ext. - Diwait | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00016 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124794 | Doroteo Noval ES (Liguiran) | SINDANGAN | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4005835.14 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00027 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195505 | Dr. Jose Rizal ES | KATIPUNAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-07-30 | 090414S00020 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124681 | Dumuyog ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2075417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00009 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124756 | Gopek ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117829.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00033 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124498 | Gubat ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2007417.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-03-27 | 090414S00012 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124685 | Guigang PS | SIAYAN | 2 | 1 | 4 | 1STY4CL | 2014 K10 BATCH 4B | 3549886.575 |  |  | REVERTED | 0
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195540 | Guimotan PS | BALIGUIAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2023417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00018 | 14JC0093 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124776 | Guisokan ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119828.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00029 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124796 | Gusane ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1124329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00026 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124797 | Inuman ES | SINDANGAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-26 | 090414S00013 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124370 | Kitonok PS | KATIPUNAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | Terminated | 0.1 | 2015-03-16 |  | 090414S00062 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION | Mutual Agreement for Termination;no access road leading to jobsite
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124327 | Labakid ES | JOSE DALMAN (PONOT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-05-28 | 2015-05-28 | 090414S00069 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124500 | Labakid ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2003417.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-05-28 | 090414S00005 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124329 | Litalip ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2012917.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00068 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124527 | Loquilos ES | MANUKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00003 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124689 | Macasing ES | SIAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00010 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124690 | Mangilay I ES | SIAYAN | 2 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4015835.14 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-02-26 | 090414S00011 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195536 | Maras East ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1114329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-02-26 | 090414S00023 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124334 | Marupay ES | JOSE DALMAN (PONOT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00057 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124805 | Mawal ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2016417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00036 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124503 | Moliton ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2003917.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-05-28 | 090414S00004 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124768 | Nato ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00031 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124377 | New Tambo ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1991417.57 |  |  | COMPLETED | 1 | 2015-03-16 | 2015-05-28 | 090414S00061 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124504 | Panampalay ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-07-30 | 090414S00002 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124484 | Pangulogon ES | PRES. MANUEL A. ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-05-28 | 090414S00059 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124696 | Pase ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2023417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00007 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124486 | Piñamar ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-03-27 | 090414S00058 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124487 | Pongolan ES | PRES. MANUEL A. ROXAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-04-30 | 2015-05-28 | 090414S00067 | 14JB0006 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124384 | Saluwagan PS | KATIPUNAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1118829.12 |  |  | COMPLETED | 1 | 2015-07-30 | 2015-07-30 | 090414S00060 | 14JB0005 | 2014-08-27 | 2014-09-30 | 2014-09-30 | 2014-10-27 | 2014-11-17 | SOY ENG CONSTRUCTION | Delayed due to inaccessible road leading to jobsite.
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314118 | Saluyong NHS | MANUKAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00014 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303739 | Sindangan NHS | SINDANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124519 | Suisayan ES | MANUKAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-31 | 2015-05-28 | 090414S00001 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124702 | Suminalum ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2015-03-30 |  | 090414S00025 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124703 | Suminogod ES | SIAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1227329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00035 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124339 | Tamarok ES | JOSE DALMAN (PONOT) | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00066 | 14JB0007 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124807 | Tinaplan ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2018417.57 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-03-27 | 090414S00022 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124808 | Titik ES | SINDANGAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00021 | 14JB0008 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124705 | Tulohon ES | SIAYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-03-30 | 2015-05-28 | 090414S00034 | 14JB0009 | 2014-07-15 | 2014-07-25 | 2014-08-05 | 2014-08-20 | 2014-09-26 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124261 | Alegria ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00047 | 14JC0081 | 2014-05-09 | 2014-05-06 | 2014-07-15 | 2014-07-30 | 2014-08-28 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124407 | Antonino ES | LABASON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00153 | 14JC0069 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3990835.14 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124847 | Balacbaan ES | TAMPILISAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-22 | 090414S00108 | 14JC0046 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124408 | Balas ES | LABASON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1116329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00147 | 14JC0070 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124292 | Banganon ES | GUTALAC | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1124329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00117 | 14JC0050 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124709 | Binawing ES | SIBUCO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1909740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314114 | Binoni NHS | SALUG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124275 | Bunawan ES | GODOD | 3 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4915592 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-03-02 | 090414S00126 | 14JC0035 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195526 | Butin ES | BALIGUIAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1134329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00079 | 14JC0085 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124858 | Camul ES | TAMPILISAN | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2940174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-22 | 090414S00110 | 14JC0048 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314109 | Canatuan NHS | SIOCON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-04-20 | 090414S00095 | 14JC0059 | 2014-08-25 | 2014-08-22 | 2014-09-02 | 2014-09-12 | 2014-10-09 | ABSOLUTE ENGINEERING AND SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124466 | Candelaria ES | LILOY | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1192329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00116 | 14JC0042 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124430 | Cilago ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00152 | 14JC0063 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124816 | Cuyan ES | SIOCON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-02-01 | 090414S00096 | 14JC0054 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124836 | Dacon Learning Center Annex - Sahara | SIRAWAI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00101 | 14JC0060 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124276 | Delucot ES | GODOD | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1124329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-03-02 | 090414S00115 | 14JC0036 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124263 | Diculom ES | BALIGUIAN | 3 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 3995835.14 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-05 | 090414S00144 | 14JC0082 | 2014-05-08 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124617 | Dinuan ES | SALUG | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1118829.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 090414S00092 | 14JC0032 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124838 | Doña Cecilia ES | SIRAWAI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1134329.12 |  |  | COMPLETED | 1 | 2015-02-02 | 2015-02-20 | 090414S00100 | 14JC0061 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124411 | Felix Quimbo Mem. ES | LABASON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00146 | 14JC0070 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124412 | Gabu ES | LABASON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2014-12-31 | 090414S00145 | 14JC0072 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124452 | Goaw ES | LILOY | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-02 | 090414S00135 | 14JC0042 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124413 | Imelda ES | LABASON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00134 | 14JC0073 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124312 | Immaculada Concepcion ES | GUTALAC | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1120829.12 |  |  | COMPLETED | 1 | 2015-02-01 | 2015-02-01 | 090414S00151 | 14JC0051 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124414 | Immaculada ES | LABASON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2008417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00094 | 14JC0074 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124349 | Kalawit CS | KALAWIT | 3 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4905592 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-05-01 | 090414S00149 | 14JC0077 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195524 | Kilalaban ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00104 | 14JC0089 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124619 | Lanawan ES | SALUG | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-02-01 | 090414S00091 | 14JC0034 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303706 | Liloy NHS | LILOY | 3 | 0 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124280 | Limbonga ES | GODOD | 3 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4005835.14 |  |  | COMPLETED | 1 | 2015-02-06 | 2015-03-02 | 090414S00124 | 14JC0037 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124281 | Lomogom ES | GODOD | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1128329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-03-02 | 090414S00133 | 14JC0036 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124266 | Lumay ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00132 | 14JC0083 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124825 | Lutian Po PS (Manaol PS) | SIOCON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1139329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00114 | 14JC0056 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124298 | Lux ES | GUTALAC | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00142 | 14JC0051 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124821 | Makiang ES | SIOCON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-02 | 090414S00105 | 14JC0055 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124421 | Malintuboan ES | LABASON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2680828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124267 | Mamad ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2002917.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00131 | 14JC0084 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124268 | Mamawan ES | BALIGUIAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1114829.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00130 | 14JC0085 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124433 | Mangop ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1119329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-01 | 090414S00141 | 14JC0064 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124351 | Marcelo ES | KALAWIT | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1874740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124826 | Matiag ES | SIOCON | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2025417.57 |  |  | COMPLETED | 1 | 2015-01-02 | 2015-01-02 | 090414S00103 | 14JC0058 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124841 | Mauricio V. Landingin Mem. ES | SIRAWAI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-01-05 | 090414S00097 | 14JC0061 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124283 | Miampic ES | GODOD | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2928174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-01 | 090414S00122 | 14JC0038 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124436 | Midatag ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2007417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-22 | 090414S00140 | 14JC0065 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124269 | Milidan ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00129 | 14JC0086 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124437 | Murob ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-02 | 090414S00139 | 14JC0066 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124352 | New Calamba ES | KALAWIT | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-02 | 090414S00098 | 14JC0078 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124857 | New Dapitan ES | TAMPILISAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1120329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-03-22 | 090414S00109 | 14JC0047 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124422 | New Salvacion ES | LABASON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1120829.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00143 | 14JC0073 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124270 | Nonoyan ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2015-02-15 | 2015-02-15 | 090414S00128 | 14JC0087 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124423 | Osukan ES | LABASON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2014-12-31 | 090414S00065 | 14JC0075 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124471 | Overview ES | LILOY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2002417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-04-30 | 090414S00093 | 14JC0045 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124441 | P.T. Martinez ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115329.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-01 | 090414S00137 | 14JC0064 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124354 | Palalihan ES | KALAWIT | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2006417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-03-02 | 090414S00148 | 14JC0079 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124439 | Palandok ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1115829.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-01 | 090414S00138 | 14JC0064 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124299 | Panganuran ES | GUTALAC | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125829.12 |  |  | COMPLETED | 1 | 2015-01-06 | 2015-01-06 | 090414S00123 | 14JC0050 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124730 | Pangian ES | SIBUCO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00090 | 14JC0090 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124731 | Paniran ES | SIBUCO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1157329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00089 | 14JC0090 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124285 | Rambon ES | GODOD | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 090414S00121 | 14JC0039 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124300 | Rosalina M. Carloto Mem. ES | GUTALAC | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-02-22 | 2015-02-22 | 090414S00125 | 14JC0052 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124459 | San Francisco ES | LILOY | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00106 | 14JC0043 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195509 | San Roque ES | KALAWIT | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2015417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00085 | 14JC0080 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124859 | Sandayong ES | TAMPILISAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-03-23 | 090414S00111 | 14JC0047 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124288 | Sarawagan ES | GODOD | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00120 | 14JC0040 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 500240 | Siay Integrated School | SIOCON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1142329.12 |  |  | COMPLETED | 1 | 2015-03-02 | 2015-03-02 | 090414S00102 | 14JC0056 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314107 | Sibuco NHS Ext. - Cawit-Cawit | SIBUCO | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-11-28 | 2015-03-22 | 090414S00084 | 14JC0091 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124290 | Sioran ES | GODOD | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1128829.12 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-03-22 | 090414S00119 | 14JC0036 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124442 | Sipakong ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 5 | 1STY2CL & 1STY3CL | 2014 K10 BATCH 1 | 4893092 |  |  | COMPLETED | 1 | 2015-02-26 | 2015-04-01 | 090414S00136 | 14JC0067 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124291 | Sipit ES | GODOD | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2933174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-01 | 090414S00118 | 14JC0041 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124844 | Sirawai CS | SIRAWAI | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2035417.57 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 090414S00107 | 14JC0062 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124860 | Situbo ES | TAMPILISAN | 3 | 1 | 4 | 1STY 2CL | 2014 K10 BATCH 1 | 4015835.14 |  |  | COMPLETED | 1 | 2015-01-27 | 2015-04-30 | 090414S00112 | 14JC0049 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124734 | Sta. Maria ES | SIBUCO | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2040417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2015-04-20 | 090414S00088 | 14JC0092 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303741 | Sta. Maria NHS | SIOCON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1126329.12 |  |  | COMPLETED | 1 | 2015-01-05 | 2015-01-05 | 090414S00082 | 14JC0057 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 195539 | Sta. Maria PS | SIRAWAI | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 090414S00080 | 14JC0061 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124861 | Sto. Niño ES | TAMPILISAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-22 | 090414S00113 | 14JC0046 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124272 | Tamao ES | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2007417.57 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090414S00127 | 14JC0088 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124462 | Tapican ES | LILOY | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-02 | 090414S00078 | 14JC0044 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124320 | Tipan ES | GUTALAC | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2015-02-20 | 2015-02-20 | 090414S00150 | 14JC0053 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 124865 | Tubod ES | TAMPILISAN | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1125329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-03-22 | 090414S00087 | 14JC0046 | 2014-07-01 | 2014-07-01 | 2014-07-15 | 2014-07-30 | 2014-08-28 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Norte | 314128 | Ubay NHS Ext. - Lawigan | LABASON | 3 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2915174.43 |  |  | COMPLETED | 1 | 2015-01-27 | 2014-12-28 | 090414S00077 | 14JC0076 | 2014-05-09 | 2014-05-06 | 2014-06-11 | 2014-07-07 | 2014-08-01 | RCM CONSTRUCTION & SUPPLIES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125418 | Alang-Alang ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 090514S00092 | 14JE0029 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125419 | Angeles ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 090514S00094 | 14JE0056 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125198 | Balanan ES | MAHAYAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00110 | 14JE0026 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124890 | Bemposa Elementary School | AURORA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-24 | 090514S00097 | 14JE0022 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314256 | Bogo Calabat Integrated School | JOSEFINA | 1 | 1 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5296975.7381 |  |  | COMPLETED | 1 | 2016-03-06 |  | 090514S00114 | 15JE0074 | 2015-06-01 | 2015-06-30 | 2015-07-13 | 2015-07-27 | 2015-08-25 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125381 | Bulanay ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00088 | 14JE0028 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125425 | Cabgan ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1212329.12 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-04-26 | 090514S00096 | 14JE0042 (Goods) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125426 | Calolot ES | TAMBULIG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-30 | 2014-12-30 | 090514S00057 | 14JE0029 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125112 | Cogonan ES | LABANGAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-26 | 090514S00095 | 14JE0045 (Goods) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125039 | Dapiwak ES | DUMINGAG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2910174.43 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090514S00071 | 14JE0023 | 2014-08-05 | 2014-09-23 | 2014-09-23 | 2014-10-20 | 2014-11-17 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125238 | Duelic ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-01-19 | 2015-01-19 | 090514S00106 | 14JE0039 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 | 0 | 4 | 2STY4CL | 2014 K10 BATCH 4A | 6298664.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125439 | Florentino B. Dag-uman ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 090514S00111 | 14JE0030 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | PRESLI DELES CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125043 | Guintananan ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090514S00070 | 14JE0024 | 2014-08-05 | 2014-09-23 | 2014-09-23 | 2014-10-20 | 2014-11-17 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125243 | Guitalos PS | MIDSALIP | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00105 | 14JE0027 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125431 | Libato ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 090514S00068 | 14JE0030 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | PRESLI DELES CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125046 | Licabang ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2070417.57 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090514S00069 | 14JE0024 | 2014-08-05 | 2014-09-23 | 2014-09-23 | 2014-10-20 | 2014-11-17 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125246 | Licuro-an PS | MIDSALIP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090514S00104 | 14JE0055 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-08 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125049 | Macasing ES | DUMINGAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 090514S00093 | 14JE0040 (Godds) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125051 | Malagalad ES | DUMINGAG | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-03-08 | 2015-03-08 | 090514S00067 | 14JE0037 | 2014-08-05 | 2014-09-23 | 2014-09-23 | 2014-10-20 | 2014-11-17 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125283 | Malili ES | MOLAVE | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 090514S00089 | 14JE0025 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | PAGADIAN AGGREGATES & MARKETING
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125186 | Malubo ES | MAHAYAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00109 | 14JE0026 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314257 | Midsalip NHS - Buloron Ext. | MIDSALIP | 1 | 1 | 5 | 1STY1CL & 2STY4CL | 2014 K10 BATCH 3 | 7273590.8944 |  |  | COMPLETED | 1 | 2016-03-06 |  | 090514S00115 | 15JE0075 | 2015-06-01 | 2015-06-30 | 2015-07-13 | 2015-07-27 | 2015-08-25 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125085 | Moradje ES | JOSEFINA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-02-23 | 090514S00073 | 14JE0025 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | PAGADIAN AGGREGATES & MARKETING
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125250 | New Katipunan ES | MIDSALIP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00103 | 14JE0027 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125387 | New Oroquieta ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-01-29 | 2015-01-29 | 090514S00098 | 14JE0028 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125188 | Paraiso ES | MAHAYAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 090514S00108 | 14JE0054 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-08 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125388 | Pictoran ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 090514S00091 | 14JE0041 (Goods) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125254 | Pili PS | MIDSALIP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090514S00102 | 14JE0051 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-08 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125255 | Pisompongan ES | MIDSALIP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090514S00101 | 14JE0053 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-08 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125256 | Piwan PS | MIDSALIP | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-28 | 2014-12-28 | 090514S00090 | 14JE0052 (Goods) | 2014-07-31 | 2014-08-25 | 2014-09-08 | 2014-09-18 | 2014-10-08 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 196015 | Riverside ES | TAMBULIG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-02-03 | 2015-02-03 | 090514S00087 | 14JE0030 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | PRESLI DELES CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125054 | Saad ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-12-27 | 2014-12-27 | 090514S00075 | 14JE0044 (Goods) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125031 | Salvador ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-01-26 | 2015-01-26 | 090514S00065 | 14JE0043 (Goods) | 2014-08-06 | 2014-08-27 | 2014-08-27 | 2014-09-10 | 2014-10-07 | By Administration
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314233 | San Jose NHS - DCM Annex | MAHAYAG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00107 | 14JE0038 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125056 | Sunop ES | DUMINGAG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-03-03 | 2015-03-03 | 090514S00064 | 14JE0023 | 2014-08-05 | 2014-09-23 | 2014-09-23 | 2014-10-20 | 2014-11-17 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314254 | Tukuran TVHS - Baclay Extension | TUKURAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-24 | 090514S00100 | 14JE0022 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124882 | Veronico J. Cabahug ES | AURORA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2015-01-24 | 2015-01-24 | 090514S00072 | 14JE0022 | 2014-08-05 | 2014-08-20 | 2014-08-20 | 2014-09-10 | 2014-09-30 | RAMONA CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303754 | Baganian NHS | TABINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00053 | 14JG0017 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124991 | Bag-ong Silao ES | DUMALINAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00017 | 14JG0013 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314224 | Balintawak NHS | MARGOSATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00042 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124992 | Baloboan IES | DUMALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00012 | 14JG0013 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124907 | Balukbahan ES | BAYOG | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00066 | 14JG0014 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314258 | Bayog National High School - Balukbahan Extension | BAYOG | 2 | 1 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5372350.7381 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 090514S00119 | 14JG0063 | 2014-12-08 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-09 | JIMWEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124911 | Bobuan ES | BAYOG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00059 | 14JG0014 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125092 | Bolisong ES | KUMALARANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00007 | 14JG0016 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125094 | Boyugan West ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00008 | 14JG0016 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125352 | Bubual ES | SAN PABLO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00050 | 14JG0013 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314216 | Bulawan NHS | LAPUYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00034 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125451 | Caluma ES | TIGBAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00060 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124914 | Conacon IS | BAYOG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1874740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303769 | Culabay NHS | TABINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125065 | Dagohoy ES | GUIPOS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00005 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125066 | Dalapan ES | GUIPOS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00006 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125153 | Danganan ES | LAPUYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00035 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125154 | Dansal ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00036 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125452 | Diana Countryside ES | TIGBAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00047 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314206 | Diosdado Macapagal MNHS | LAKEWOOD | 2 | 1 | 3 | 2STY2CL & 1STY1CL | 2014 K10 BATCH 3 | 5387425.7381 |  |  | COMPLETED | 1 | 2015-07-05 | 2015-07-05 | 090514S00116 | 14JG0064 | 2014-12-08 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-09 | JIMWEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124942 | Grap ES | DIMATALING | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00027 | 14JG0018 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124943 | Josefina ES | DIMATALING | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00026 | 14JG0018 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125216 | Josefina ES | MARGOSATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1152329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00043 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124966 | Kinakap ES | DINAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00022 | 14JG0019 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125454 | Lacarayan Elementary School | TIGBAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00019 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303788 | Lapuyan NHS | LAPUYAN | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6338864.7656 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314261 | Lapuyan NHS - Maralag Extension | LAPUYAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2750828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125158 | Lenok Madalum ES | LAPUYAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00037 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124926 | Liba ES | BAYOG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00030 | 14JG0014 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125456 | Libayoy ES | TIGBAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2090417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00015 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125297 | Limbayan ES | PITOGO | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2865174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00061 | 14JG0021 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124971 | Lower Dimaya ES | DINAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00014 | 14JG0019 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125404 | Lumbia ES | TABINA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00055 | 14JG0017 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125503 | Maculay ES | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2050417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00011 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125002 | Mama ES | DUMALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1162329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00003 | 14JG0013 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125163 | Mandeg ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00038 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 196005 | Mataga ES | BAYOG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00029 | 14JG0014 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125145 | Matalang IPS | LAKEWOOD | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 2024740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124928 | Matin-ao CPS | BAYOG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00028 | 14JG0014 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314237 | Mecolong NHS | DUMALINAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125461 | Nangan-nangan ES | TIGBAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2110417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00002 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125105 | Pangi ES | KUMALARANG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00009 | 14JG0016 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125300 | Panubigan ES | PITOGO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00046 | 14JG0021 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303804 | Paulino Dari NHS | PITOGO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314260 | Paulino Dari NHS - Punta Flecha Ext. | PITOGO | 2 | 1 | 4 | 2STY4CL | 2014 K10 BATCH 3 | 6358964.7656 |  |  | COMPLETED | 1 | 2015-07-04 | 2015-07-04 | 090514S00118 | 14JG0066 | 2014-12-08 | 2014-12-10 | 2014-12-22 | 2014-12-29 | 2015-01-09 | JIMWEN CONSTRUCTION & GENERAL MERCHANDISE
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314249 | Poblacion Comprehensive HS | LAKEWOOD | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125369 | Sagasan Elementary School | SAN PABLO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2030417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00051 | 14JG0013 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125170 | Salambuyan ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00039 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303810 | Saloagan NHS | DIMATALING | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00025 | 14JG0018 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124980 | Sambulawan ES | DINAS | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00020 | 14JG0019 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125412 | San Francisco ES | TABINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00056 | 14JG0017 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124981 | San Isidro ES | DINAS | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2925174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00031 | 14JG0019 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125303 | San Isidro ES | PITOGO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00048 | 14JG0021 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125347 | San Isidro ES | SAN MIGUEL | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2955174.43 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00112 | 14JG0015 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Ext. | SAN PABLO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00052 | 14JG0031 | 2014-07-30 | 2014-10-08 | 2014-10-09 | 2014-10-13 | 2014-10-15
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125413 | San Roque ES | TABINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00021 | 14JG0017 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125108 | Sayao ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00010 | 14JG0016 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125172 | Sayog ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00040 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124952 | Sugbay Uno ES | DIMATALING | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00024 | 14JG0018 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124953 | Sumbato IPS | DIMATALING | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00023 | 14JG0018 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303768 | Tabina NHS (Culabay NHS - Tabina Annex) | TABINA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125176 | Tipasan ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-12-20 | 2014-12-20 | 090514S00041 | 14JG0020 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125305 | Tongao ES | PITOGO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00049 | 14JG0021 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 303822 | Toribio Minor National High School | MARGOSATUBIG | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1122329.12 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125150 | Tubod ES | LAKEWOOD | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-11 | 2014-10-11 | 090514S00033 | 14JG0016 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125466 | Upper Nilo ES | TIGBAO | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00013 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 124988 | West Migpulao ES | DINAS | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00018 | 14JG0019 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | ST. GERRARD CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga del Sur | 125467 | Woodland ES | TIGBAO | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2130417.57 |  |  | COMPLETED | 1 | 2014-10-21 | 2014-10-21 | 090514S00016 | 14JG0022 | 2014-07-25 | 2014-08-05 | 2014-08-08 | 2014-08-19 | 2014-08-29 | BAQPRINCE CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125509 | Alegria ES | ALICIA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1087049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125751 | Balian ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 090714S00076 | 14JI0027 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125590 | Balugo ES | IMELDA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 090714S00064 | 14JI0011 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125752 | Balungisan ES | PAYAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 090714S00092 | 14JI0028 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125685 | Basakbawang ES | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00057 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125539 | Basalem ES | BUUG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-23 | 090714S00032 | 14JI0008 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 314305 | Basalem NHS | BUUG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1082049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125511 | Bella ES | ALICIA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00098 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125754 | Bulacan ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 090714S00091 | 14JI0027 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125755 | Bulawan ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 090714S00090 | 14JI0028 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125756 | Calape ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 090714S00089 | 14JI0028 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125667 | Caliran ES | MABUHAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 090714S00062 | 14JI0014 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125668 | Catipan ES | MABUHAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1137329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 090714S00061 | 14JI0014 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125544 | Compostela ES | BUUG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1103329.12 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-23 | 090714S00070 | 14JI0008 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125513 | Concepcion ES | ALICIA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00097 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125690 | Dansulao ES | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00056 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125735 | Fama ES | OLUTANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00050 | 14JI0016 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125846 | Florida ES | TALUSAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00026 | 14JI0015 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125692 | Guilawa ES | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00074 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125549 | Guminta ES | BUUG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-23 | 090714S00069 | 14JI0008 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125517 | J. Luna PS | ALICIA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1990417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00099 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125519 | Kauswagan ES | ALICIA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00094 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125693 | Kigay ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2005417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00054 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125765 | Kulisap ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 090714S00083 | 14JI0027 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125766 | La Fortuna ES | PAYAO | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-12-10 | 2014-12-10 | 090714S00085 | 14JI0028 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2790828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125523 | Lapirawan ES | ALICIA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00095 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125671 | Ligaya ES | MABUHAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 090714S00047 | 14JI0014 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125600 | Little Baguio ES | IMELDA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1099329.12 |  |  | COMPLETED | 1 | 2014-10-05 | 2014-10-05 | 090714S00063 | 14JI0011 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125696 | Logpond PS | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00060 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125525 | Lutiman Elementary School | ALICIA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1112049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125697 | Mabini ES | MALANGAS | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2885174.43 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00052 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial HS | MABUHAY | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1137049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125699 | Malongon ES | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1062049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125741 | Matim ES | OLUTANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00049 | 14JI0016 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125851 | Moalboal ES | TALUSAN | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00027 | 14JI0015 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125772 | Mt. View ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 090714S00024 | 14JI0027 | 2014-07-21 | 2014-07-30 | 2014-09-25 | 2014-10-02 | 2014-10-20 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125557 | Pamintayan ES | BUUG | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-09-23 | 2014-09-23 | 090714S00068 | 14JI0008 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125529 | Pandan-Pandan ES | ALICIA | 1 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2881174.43 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00096 | 14JI0012 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125580 | Paradise ES | DIPLAHAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00067 | 14JI0009 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125744 | Pulo Laum ES | OLUTANGA | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00048 | 14JI0016 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125585 | Sampoli-B ES | DIPLAHAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00066 | 14JI0009 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125677 | San Roque ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 090714S00059 | 14JI0014 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125680 | Sto. Niño ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-10-13 | 2014-10-13 | 090714S00071 | 14JI0014 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125779 | Sumilong ES | PAYAO | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-30 | 2014-11-30 | 090714S00025 | 14JI0027 | 2014-07-21 | 2014-07-30 | 2014-09-05 | 2014-10-02 | 2014-10-20 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 500241 | Talairan Integrated School | BUUG | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1087049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125708 | Tigabon PS | MALANGAS | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00051 | 14JI0010 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125588 | Tinongtongan ES | DIPLAHAN | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2014-11-02 | 2014-11-02 | 090714S00065 | 14JI0009 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125855 | Tuburan ES | TALUSAN | 1 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 4B | 1122049.6543 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125750 | Villagonzalo ES | OLUTANGA | 1 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2000417.57 |  |  | COMPLETED | 1 | 2014-10-03 | 2014-10-03 | 090714S00058 | 14JI0016 | 2014-06-26 | 2014-06-27 | 2014-07-10 | 2014-07-25 | 2014-08-08 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125857 | Balucon ES | TITAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2010417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00021 | 14FJ0024 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125635 | Buayan ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00038 | 14JF0021 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125611 | Caparan ES | IPIL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00028 | 14JF0022 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-21 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125612 | Caparan Samporna PS | IPIL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00029 | 14JF0023 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-23 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125784 | Casacon ES | ROSELLER LIM | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-01-23 | 090714S00008 | 14JF0029 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125862 | Dalisay ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00010 | 14FJ0024 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125639 | Datagan ES | KABASALAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2895174.43 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00040 | 14JF0019 | 2014-06-04 | 2014-06-16 | 2014-07-17 | 2014-07-21 | 2014-07-22 | PINS CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125641 | Dipala ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00041 | 14JF0020 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125614 | Don Andres ES | IPIL | 2 | 1 | 2 | 2STY2CL | 2014 K10 BATCH 4B | 4572048.49 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125642 | Gacbusan ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00042 | 14JF0023 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-20 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125863 | Gomotoc ES | TITAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00053 | 14JF0025 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 196516 | Gugawang Bugas ES | TITAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00087 | 14JF027 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125716 | Guintoloan ES | NAGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00002 | 14JF0021 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125820 | Gusawan ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00013 | 14JF0018 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 196526 | Gutayan PS | ROSELLER LIM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1132329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00088 | 14JF0028 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125625 | Habib Moin Anduhol MES | IPIL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1092329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00023 | 14JF0021 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125821 | I. Miranda Mem. ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-25 | 2015-01-25 | 090714S00014 | 14JF0018 | 2014-05-06 | 2014-05-16 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125637 | Ignacio Canoy ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00039 | 14JF0022 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-20 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125623 | Jesus Lauron Elementary School | IPIL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00046 | 14FJ0024 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125718 | Kaliantana ES | NAGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00003 | 14JF0022 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-20 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125788 | Katipunan ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00009 | 14JF0029 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125822 | Kimos ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00055 | 14JF0017 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 314324 | Kitabog NHS | TITAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 4B | 2640828.124 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125867 | La Libertad ES | TITAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00078 | 14JF0026 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125823 | Labasan ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00015 | 14JF0017 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125646 | Lacnapan ES | KABASALAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00043 | 14JF0020 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125621 | Logan ES | IPIL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1978417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00030 | 14JF0021 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | MJMARI BUILDERS AND ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125868 | Longilog ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00077 | 14JF0025 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125895 | Looc Labuan ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1995417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00081 | 14JF027 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125622 | Luis Ruiz Sr. ES | IPIL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00031 | 14JF0025 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125624 | Maasin ES | IPIL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00034 | 14JF0023 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-20 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125827 | Maligaya ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00045 | 14JF0016 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125720 | Mamagon ES | NAGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 2020417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00004 | 14JF0023 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-21 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125828 | Maniha ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00016 | 14JF0016 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 196504 | Masao ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00086 | 14JF0028 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125830 | Mirangan ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00017 | 14JF0017 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125793 | Motop PS | ROSELLER LIM | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2870174.43 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00022 | 14JF0029 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125873 | Namnama ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00075 | 14JF027 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125649 | Nazareth ES | KABASALAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00044 | 14JF0020 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125864 | Paaralang Buhay ng Imelda ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00079 | 14JF0026 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125650 | Palinta ES | KABASALAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00012 | 14JF0018 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125796 | Palmera ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 4B | 1864740.174 |  |  | COMPLETED | 1
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125651 | Peñaranda ES | KABASALAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00035 | 14JF0018 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125876 | Pob. Muslim ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1097329.12 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00073 | 14JF0025 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125898 | Ponciano Pagdanganan Sr. Mem. ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2014-11-18 | 090714S00093 | 14JF0028 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125835 | Salinding ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1107329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00018 | 14JF0017 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | RUDHIL CONSTRUCTION & ENTERPRISES, INC.(FORMERLY R
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125879 | San Isidro ES | TITAY | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2905174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-01-15 | 090714S00082 | 14JF0026 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125724 | Sandayong ES | NAGA | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2890174.43 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00005 | 14FJ0024 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | HENSO CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125629 | Sanito ES | IPIL | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1970417.57 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00036 | 14JF0022 | 2014-06-04 | 2014-06-16 | 2014-06-17 | 2014-06-22 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125880 | Santa Fe ES | TITAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1127329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00080 | 14JF0026 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125801 | Siawang ES | ROSELLER LIM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1117329.12 |  |  | COMPLETED | 1 | 2014-11-25 | 2014-11-18 | 090714S00011 | 14JF0029 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125839 | Siloh ES | SIAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1975417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00019 | 14JF0016 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125658 | Sininan ES | KABASALAN | 2 | 1 | 3 | 1STY3CL | 2014 K10 BATCH 1 | 2875174.43 |  |  | COMPLETED | 1 | 2015-02-23 | 2015-01-23 | 090714S00033 | 14JF0020 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-22 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125803 | Sto. Rosario ES | ROSELLER LIM | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-02-21 | 2015-02-21 | 090714S00001 | 14JF0029 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125881 | Supit ES | TITAY | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1985417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00084 | 14JF027 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | CPAN ENGINEERING & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125905 | Tigbucay ES | TUNGAWAN | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00072 | 14JF0028 | 2014-05-06 | 2014-05-19 | 2014-05-19 | 2014-05-23 | 2014-07-22 | 2M CONSTRUCTION & ENTERPRISES
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125728 | Tilubog ES | NAGA | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1112329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00006 | 14JF0019 | 2014-06-04 | 2014-06-16 | 2014-07-17 | 2014-07-21 | 2014-07-22 | PINS CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125632 | Timalang ES | IPIL | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1100329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00037 | 14JF0019 | 2014-06-04 | 2014-06-16 | 2014-07-17 | 2014-07-21 | 2014-07-22 | PINS CONSTRUCTION
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125840 | Upper Balagon ES | SIAY | 2 | 1 | 1 | 1STY1CL | 2014 K10 BATCH 1 | 1102329.12 |  |  | COMPLETED | 1 | 2015-01-15 | 2015-01-15 | 090714S00020 | 14JF0016 | 2014-04-21 | 2014-04-30 | 2014-05-02 | 2014-05-08 | 2014-07-22 | GJD CONSTRUCTION & SUPPLY
NC 2014 | K10 (2014) | Region IX | Zamboanga Sibugay | 125730 | Upper Sulitan ES | NAGA | 2 | 1 | 2 | 1STY2CL | 2014 K10 BATCH 1 | 1980417.57 |  |  | COMPLETED | 1 | 2015-01-04 | 2015-01-04 | 090714S00007 | 14JF0019 | 2014-06-04 | 2014-06-16 | 2014-07-17 | 2014-07-21 | 2014-07-22 | PINS CONSTRUCTION
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303877 | Barcelona NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303878 | Baylimango NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303879 | Dakak NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8444965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Dapitan City | 125939 | Dapitan City Experimental ES | DAPITAN CITY | 1 | 1 | 8 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Dapitan City | 125939 | Dapitan City Experimental ES | DAPITAN CITY | 1 |  | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2879549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303880 | Dapitan City NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303881 | Ilaya NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303883 | Potungan NHS | DAPITAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Dapitan City | 125934 | Sto Nino ES | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6669337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 2 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'l. Sci. HS | DIPOLOG CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8374965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303886 | Cogon NHS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6444337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Dipolog City | 500046 | Gulayon IS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | REVERTED | 0
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. HS | DIPOLOG CITY (Capital) | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303891 | Punta NHS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6419337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303891 | Punta NHS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2669549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS (Main) | DIPOLOG CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8454965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS (Main) | DIPOLOG CITY (Capital) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | ISABELA CITY | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 8 | 31102890.27 |  |  | REVERTED | 0 | [9 empty] | 2M Construction & Enterprises
NC 2015 | SHS (2015) | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8664965.051 |  |  | COMPLETED | 1 |  |  |  | 15JH0014 | 2015-07-14 | 2015-07-22 | 2015-08-19 | 2015-08-21 | 2015-09-23 | 2M Construction & Enterprises
NC 2015 | K10 (2015) | Region IX | Isabela City | 198006 | Bishop Querexeta Elem. School | CITY OF ISABELA (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1 |  |  |  | 15JH0021 | 2015-02-12 | 2015-10-12 | 2015-12-22 | 2015-12-28 | 2015-08-01 | RJLP Construction and Supplies
NC 2015 | K10 (2015) | Region IX | Isabela City | 500243 | Geras Integrated School | CITY OF ISABELA (Capital) | 0 | 1 | 9 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15JH0019 | 2015-02-09 | 2015-10-09 | 2015-09-29 | 2015-05-10 | 2015-10-15 | RJLP Construction and Supplies
NC 2015 | K10 (2015) | Region IX | Isabela City | 500243 | Geras Integrated School | CITY OF ISABELA (Capital) | 0 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15JH0018 | 2015-07-14 | 2015-07-22 | 2015-08-18 | 2015-08-21 | 2015-09-23 | 2M Construction & Enterprises
NC 2015 | K10 (2015) | Region IX | Isabela City | 198014 | Hji. Maulana PS | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15JH0023 | 2015-10-19 | 2015-10-29 | 2015-10-11 | 2015-11-19 | 2015-01-12 | RJLP Construction and Supply
NC 2015 | K10 (2015) | Region IX | Isabela City | 198010 | ICEPS Night | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15JHOO26 | 2015-10-19 | 2015-10-29 | 2015-10-11 | 2015-11-17 | 2015-01-12 | RJLP Construction and Supply
NC 2015 | SHS (2015) | Region IX | Isabela City | 314601 | Isabela City NHS | CITY OF ISABELA (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1 |  |  |  | 15JH0015 | 2015-07-14 | 2015-07-22 | 2015-08-19 | 2015-08-21 | 2015-09-23 | 2M Construction & Enterprises
NC 2015 | K10 (2015) | Region IX | Isabela City | 126008 | Kapatagan Diutay PS | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15JH0025 | 2015-10-19 | 2015-10-29 | 2015-10-11 | 2015-11-17 | 2015-01-12 | RJLP Construction and Supply
NC 2015 | K10 (2015) | Region IX | Isabela City | 126010 | Kawa-Kawa ES | CITY OF ISABELA (Capital) | 0 | 1 | 5 | 1STY5CL (Toilet Attached) | 2015 K10 BATCH 6 | 4523636.82 |  |  | COMPLETED | 1 |  |  |  | 15JH0022 | 2015-02-12 | 2015-10-12 | 2015-12-22 | 2015-12-29 | 2016-08-01 | RJLP Construction and Supply
NC 2015 | SHS (2015) | Region IX | Isabela City | 303895 | Malamawi National High School | CITY OF ISABELA (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8714965.051 |  |  | COMPLETED | 1 |  |  |  | 15JH0016 | 2015-05-08 | 2015-12-08 | 2015-08-18 | 2015-08-21 | 2015-09-23 | RCM Construction & Supplies
NC 2015 | K10 (2015) | Region IX | Isabela City | 126035 | Old Camp ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1 |  |  |  | 15JH0024 | 2015-10-19 | 2016-10-29 | 2015-10-11 | 2015-11-19 | 2015-01-12 | RJLP Construction and Supply
NC 2015 | K10 (2015) | Region IX | Isabela City | 126014 | Panunsulan ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1 |  |  |  | 15JH0020 | 2015-02-09 | 2015-10-09 | 2015-09-29 | 2015-05-10 | 2023-10-15 | RJLP Construction and Supply
NC 2015 | K10 (2015) | Region IX | Isabela City | 198016 | Ustadz Wahab M. Akbar Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1 |  |  |  | 15JHOO17 | 2015-05-08 | 2015-05-08 | 2015-08-18 | 2015-08-21 | 2015-09-23 | RCM Construction & Supplies
NC 2015 | SHS (2015) | Region IX | Pagadian City | 314705 | Co Tek Chun National Trade School | PAGADIAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6489337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303901 | Lala NHS | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303903 | Lison Valley NHS | PAGADIAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6789337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303904 | Manga NHS | PAGADIAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6374337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Pagadian City | 303905 | Napolan NHS | PAGADIAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 314702 | Norberta Guillar NHS (Napolan NHS - Norberta Guillar Mem. School Ext.) | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Pagadian City | 303907 | Otto Lingue NHS (PCNHS Annex, Lower Sibatang) | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303906 | Pagadian City NCHS | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303908 | Pagadian City NHS | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 314704 | Pagadian City Science High School | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8269965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303909 | Tawagan Sur NHS | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8704965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303910 | Zamboanga del Sur National High School | PAGADIAN CITY | 1 | 1 | 24 | 4STY24CL | 2015 SHS BATCH 5 | 35596257 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303910 | Zamboanga del Sur National High School | PAGADIAN CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 5 | 8214965 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Pagadian City | 303910 | Zamboanga del Sur NHS | PAGADIAN CITY (Capital) | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 11077342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Pagadian City | 303911 | Zamboanga del Sur NHS - San Pedro NHS Annex | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8714965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Pagadian City | 303913 | Zamboanga del Sur SAT | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8914965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Pagadian City | 303913 | Zamboanga del Sur SAT | PAGADIAN CITY (Capital) | 1 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 5479098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303915 | Ayala NHS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126212 | Cabatangan ES | ZAMBOANGA CITY | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126109 | Capisan ES | ZAMBOANGA CITY | 1 | 1 | 8 | 2STY8CL | 2015 K10 BATCH 3 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126100 | Cawit ES | ZAMBOANGA CITY | 1 | 1 | 12 | 4STY12CL | 2015 K10 BATCH 3 | 22152343.62 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303923 | Don Pablo Lorenzo Memorial High School | ZAMBOANGA CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31752890 |  |  | Reverted | 0 |  |  | 090615S00041
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303916 | ECC-Baluno NHS | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 6 | 18072268.79 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 199005 | Latap ES-Lacumba Annex | ZAMBOANGA CITY | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 314808 | Pasonanca NHS | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 3 | 21383013.45 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126146 | Patalon ES | ZAMBOANGA CITY | 1 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303924 | Ramon Enriquez HS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 314805 | Recodo NHS | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303943 | Regional Science HS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126209 | Rio Hondo ES | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 345869 | SHS within Baliwasan Central School | ZAMBOANGA CITY | 1 | 1 | 20 | 4STY20CL | 2015 SHS BATCH 5 | 31752890 |  |  | COMPLETED | 1 |  |  | 090615S00040 | 15JA0156 | 2015-12-04 | 2015-12-16 | 2015-12-22
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303932 | Sinunuc NHS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8864965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303935 | Talisayan NHS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 314807 | Tulungatung National High School | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 303942 | Zamboanga NHS (West) | ZAMBOANGA CITY | 1 | 1 | 64 | 4STY24CL | 2015 K10 BATCH 3 | 35596257.14 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 303942 | Zamboanga NHS (West) | ZAMBOANGA CITY | 1 |  | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 303942 | Zamboanga NHS (West) | ZAMBOANGA CITY | 1 |  | 20 | 4STY20CL | 2015 K10 BATCH 3 | 31102890.27 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 303914 | Arena Blanco NHS | ZAMBOANGA CITY | 2 |  | 15 | 3STY15CL | 2015 K10 BATCH 3 | 21383013.45 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303914 | Arena Blanco NHS | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 314803 | Arena Blanco NHS- Landang Gua Annex | ZAMBOANGA CITY | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303917 | Bolong NHS | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 5 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126178 | Buenakapok ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303918 | Bunguiao NHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303918 | Bunguiao NHS | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2015 ADDITIONAL FUND BATCH 9 | 5444220.51 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126154 | Busay ES | ZAMBOANGA CITY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4622048.49 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126118 | Camp Pilar Elementary School | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303920 | Culianan NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303921 | Curuan NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126160 | Landang Laum ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2138606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 303926 | Limaong NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126162 | Manalipa ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126164 | Manicahan CS | ZAMBOANGA CITY | 2 | 1 | 9 | 3STY9CL | 2015 K10 BATCH 3 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303928 | Manicahan NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303922 | Maria Clara L. Lobregat NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303929 | Mercedes NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303930 | Sangali NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126243 | Sibuktok ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126133 | Simanta ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303934 | Tagasilay NHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126228 | Talon-Talon ES | ZAMBOANGA CITY | 2 | 1 | 15 | 3STY15CL | 2015 K10 BATCH 6 | 21233013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 314801 | Talon-Talon NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126194 | Taluksangay ES | ZAMBOANGA CITY | 2 | 1 | 12 | 3STY12CL | 2015 K10 BATCH 3 | 18222268.79 |  |  | Reverted | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga City | 126253 | Tarlago ES | ZAMBOANGA CITY | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 6 | 4422048.49 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303936 | Tictapul NHS | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303937 | Tolosa NHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303938 | Tuan Datu Hj. Abdulla Nuno MHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | 2015 SHS BATCH 1 | 1814740.174 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga City | 303939 | Vitali NHS | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | Reverted | 0
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8349965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8339965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195504 | New Rizal ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124666 | Pedagan ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124666 | Pedagan ES | SERGIO OSMEÑA SR. | 1 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8309965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8289965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303717 | Polanco NHS Annex - Sianib | POLANCO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124668 | Princesa Lamaya ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303720 | Rizal NHS | RIZAL | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124580 | San Antonio ES | POLANCO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303737 | Sibutad NHS | SIBUTAD | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124772 | Bago ES | SINDANGAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6189337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303678 | Bartolome C. Lira, Sr. NHS | SINDANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195529 | Basak PS | SIAYAN | 2 | 1 | 8 | 2STY4CL | 2015 K10 BATCH 6 | 12378675.2761 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124788 | Benigno Aquino ES | SINDANGAN | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124788 | Benigno Aquino ES | SINDANGAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124791 | Calubian ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124364 | Dabiak ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124773 | Dalongdong ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124773 | Dalongdong ES | SINDANGAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124508 | Disakan ES | MANUKAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124508 | Disakan ES | MANUKAN | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124775 | Don Ricardo G. Macias ES | SINDANGAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124775 | Don Ricardo G. Macias ES | SINDANGAN | 2 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303683 | Dumalogdog NHS | SINDANGAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124684 | Guibo ES | SIAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124686 | Gunyan ES | SIAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2822592 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303696 | Katipunan NHS | KATIPUNAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10957342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124761 | Layawan ES | SINDANGAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8319965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124512 | Mate ES | MANUKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124512 | Mate ES | MANUKAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124529 | Meses ES | MANUKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1963606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124513 | Palaranan ES | MANUKAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124694 | Pange ES | SIAYAN | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8304965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195530 | Sapa Ralum PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1 | [10 empty] | Delayed due to Inaccessibility leading to jobsite.; CR not yet constructed
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124699 | Selese ES | SIAYAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303730 | Siayan NHS | SIAYAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | 6 | 1STY6CL | 2015 SHS BATCH 1 | 5186910.09 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303739 | Sindangan NHS | SINDANGAN | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 11127342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195535 | Sindangan Special Education Center | SINDANGAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195535 | Sindangan Special Education Center | SINDANGAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124392 | Singatong ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124392 | Singatong ES | KATIPUNAN | 2 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195531 | Sulot Sumayong PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | REVERTED | 0
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124704 | Tague ES | SIAYAN | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 3907212.08 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303674 | Bacungan NHS Annex - Talinga | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8439965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124273 | Baluno ES | GODOD | 3 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124274 | Banuangan ES | GODOD | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124343 | Bayanihan ES | KALAWIT | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124463 | Baybay CS | LILOY | 3 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124463 | Baybay CS | LILOY | 3 |  | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124308 | Buenavista ES | GUTALAC | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124813 | C. Callao ES | SIOCON | 3 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124813 | C. Callao ES | SIOCON | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124465 | Canaan ES | LILOY | 3 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124465 | Canaan ES | LILOY | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303707 | COMPRA NHS | LILOY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195538 | Dela Paz ES | LILOY | 3 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124277 | Dipopor ES | GODOD | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124311 | Gacsod ES | GUTALAC | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195548 | Ganase ES | LILOY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195548 | Ganase ES | LILOY | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124348 | Gatas ES | KALAWIT | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303684 | Godod NHS | GODOD | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8344965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 314115 | Godod NHS Ext. - Sianan | GODOD | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124279 | Guisapong ES | GODOD | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 314122 | Gutalac NHS Ext. - Tipan | GUTALAC | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195537 | Imam Nasaron Haron PS | SIOCON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School | SIOCON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8514965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8324965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195545 | Kono Mais ES | SIOCON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195545 | Kono Mais ES | SIOCON | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124718 | Lambaguan ES | SIBUCO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124719 | Lanote ES | SIBUCO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303706 | Liloy NHS | LILOY | 3 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10977342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 314127 | Liloy NHS Ext. - Patawag | LILOY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 314127 | Liloy NHS Ext. - Patawag | LILOY | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124723 | Lipuno ES Annex - Limpapa | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195532 | Litawan ES | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124724 | Lubay ES | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124725 | Lunday Valley ES | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195549 | Maigang P/S | LILOY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195549 | Maigang P/S | LILOY | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195528 | Makinaryas ES | GODOD | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124822 | Malambuhangin ES | SIOCON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303708 | Malayal NHS | SIBUCO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124727 | Mantivoh ES | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124282 | Mauswagon ES | GODOD | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124728 | Nala ES | SIBUCO | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124842 | Panglima Utoh Aban ES | SIRAWAI | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124817 | Pedro Torio ES | SIOCON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124817 | Pedro Torio ES | SIOCON | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124827 | Pisawak ES | SIOCON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303722 | Ramon Magsaysay National High School | SALUG | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124286 | Rebe ES | GODOD | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303721 | Salug National High School | SALUG | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195507 | San Isidro ES | GUTALAC | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195525 | San Isidro ES | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124357 | San Jose ES | KALAWIT | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124287 | San Pedro ES | GODOD | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124287 | San Pedro ES | GODOD | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303734 | Sibuco NHS | SIBUCO | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8564965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303736 | Sibuco NHS Annex - Pangian | SIBUCO | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 124426 | Sibulan Paaralan Ng Buhay | LABASON | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8614965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303742 | Sirawai NHS | SIRAWAI | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8724965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195551 | Sta. Cruz | LILOY | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195551 | Sta. Cruz | LILOY | 3 |  | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 303748 | Tampilisan NHS Annex - Situbo | TAMPILISAN | 3 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Norte | 195544 | Tan-awan PS | BALIGUIAN | 3 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8349965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124867 | Anonang ES | AURORA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125308 | Bambong Daku ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 314203 | Boniao National High School | MAHAYAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125113 | Combo Elementary School | LABANGAN | 1 | 1 | 3 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125113 | Combo Elementary School | LABANGAN | 1 |  |  | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8234965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125179 | Compound ES | MAHAYAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125314 | Dipalusan Elementary School | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1968606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125242 | Guinabot Elementary School | MIDSALIP | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125244 | Guma ES | MIDSALIP | 1 | 1 | 3 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125244 | Guma ES | MIDSALIP | 1 |  |  | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314212 | Juan Lumosad MNHS - Monte Alegre Annex | AURORA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125319 | Kauswagan ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125143 | Lakewood CES | LAKEWOOD | 1 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 3 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125131 | Lantian ES | LABANGAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303787 | Laperian National High School | TUKURAN | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125321 | Mabini Elementary School | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125052 | Maralag ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303796 | Midsalip NHS- Main | MIDSALIP | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124869 | Mohammad Ali Dimaporo ES (Balas ES) | AURORA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2238606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | 15 | 3STY15CL | 2015 SHS BATCH 1 | 21833013.45 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | 9 | 3STY9CL | 2015 SHS BATCH 1 | 15121327.92 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 5229098.54 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303798 | Navalan NHS | TUKURAN | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 12838675.2761 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125252 | Palili ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1978606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 |  |  | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196036 | Panuguton PS | DUMINGAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125325 | Paradise ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125253 | Pawan Elementary School | MIDSALIP | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2018606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303814 | Sapa Anding Agricultural Vocational Technical School | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 314228 | Sapa Anding NHS - R. Magsaysay Ext. | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125192 | Sebastian Lobitaña ES | MAHAYAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 345844 | SHS in Labangan, Zamboanga Del Sur | LABANGAN | 1 | 1 | 12 | 2STY6CL | 2015 SHS BATCH 5 | 17289930 |  |  | COMPLETED | 1 |  |  | 090515S00090
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303815 | Simata NHS | MOLAVE | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196040 | Simuyak Elementary School | DINAS | 1 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196040 | Simuyak Elementary School | DINAS | 1 |  |  | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196033 | Sinatalan Elementary School | DUMINGAG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 3012592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125055 | Sinonok Elementary School | DUMINGAG | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303817 | Sominot NHS | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125329 | Sto. Rosario CPS | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303818 | SUBANEN AGRICULTURAL NHS | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314204 | Sumalig NHS | TAMBULIG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196037 | Sumibang Indigenous Elem. School | DUMINGAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125057 | Tagun Elementary School | DUMINGAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125149 | Tiwales CPS | LAKEWOOD | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303811 | Tukuran Tech. Voc'l. HS | TUKURAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6479337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303811 | Tukuran Tech. Voc'l. HS | TUKURAN | 1 | 1 | 4 | 2STY4CL | 2015 SHS BATCH 1 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125209 | Tumapic ES | MAHAYAG | 1 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196029 | Upper Danlugan PS | DUMINGAG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2038606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125448 | Upper Tiparak ES | TAMBULIG | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303753 | Antonio NHS | TIGBAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125398 | Baganian ES | TABINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2158606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125137 | Baking ES | LAKEWOOD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124937 | Balanagan ES | DIMATALING | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125138 | Bal-lao ES | LAKEWOOD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303757 | Bayog NHS | BAYOG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196038 | Benuatan ES | DINAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303791 | Betinan NHS | SAN MIGUEL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314217 | Bibilik NHS | DUMALINAO | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125139 | Biswangan ES | LAKEWOOD | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2368606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303769 | Culabay NHS | TABINA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124918 | Depase ES | BAYOG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303770 | Dimataling NHS | DIMATALING | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303771 | Dinas NHS | DINAS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125403 | Doña Josefina ES | TABINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303774 | Dumalinao NHS | DUMALINAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124964 | East Migpulao ES | DINAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314240 | FATIMA NATIONAL HIGH SCHOOL | SAN MIGUEL | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125453 | Guinlin ES | TIGBAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2388606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303778 | Guipos NHS | GUIPOS | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314207 | Guling National High School | GUIPOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125215 | Igat ES | MARGOSATUBIG | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 6 | 8064965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303782 | Kabatan NHS | VINCENZO A. SAGUN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303783 | Kalian NHS | MARGOSATUBIG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125070 | Katipunan ES | GUIPOS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1998606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303784 | Kumalarang NHS | KUMALARANG | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303788 | Lapuyan NHS | LAPUYAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8334965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125221 | Limbatong ES | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124972 | Ludiong ES | DINAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125405 | Mabuhay ES | TABINA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1958606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303795 | Maestro Cornelio S. Minor NHS | KUMALARANG | 2 | 1 | 2 | 2STY2CL | 2015 K10 BATCH 7 | 4572048 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124947 | Mahayag Primary School | DIMATALING | 2 | 1 | 5 | 2STY4CL | 2015 K10 BATCH 3 | 6319337.6381 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124947 | Mahayag Primary School | DIMATALING | 2 |  |  | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 303789 | Maruing NHS | LAPUYAN | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 7 | 6319338 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125460 | Mate ES | TIGBAO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 2078606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303800 | Nilo NHS | TIGBAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124976 | Old Mirapao Elementary School | DINAS | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314255 | Old Mirapao National High School | DINAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 2338606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303804 | Paulino Dari NHS | PITOGO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 314249 | Poblacion Comprehensive NHS | LAKEWOOD | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8274965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303808 | Rebokon AVHS | DUMALINAO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314208 | Sagucan NHS | VINCENZO A. SAGUN | 2 | 1 | 3 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314208 | Sagucan NHS | VINCENZO A. SAGUN | 2 |  |  | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303813 | San Pablo NHS | SAN PABLO | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314250 | San Pablo NHS - Pongapong Ext. | SAN PABLO | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1988606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314129 | Sikatuna NHS | GUIPOS | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 314129 | Sikatuna NHS | GUIPOS | 2 |  |  | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124983 | Sumilom PS | DINAS | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303768 | Tabina NHS | TABINA | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 12838675.2761 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 124957 | Tipange CPS | DIMATALING | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303822 | Toribio Minor National High School | MARGOSATUBIG | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 12838675.2761 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga del Sur | 303823 | Tubod NHS | LAKEWOOD | 2 | 1 | 8 | 2STY4CL | 2015 SHS BATCH 2 | 12818675.2761 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 125228 | Tulapok ES | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196043 | Upper Mate ES | TIGBAO | 2 | 1 | 4 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga del Sur | 196043 | Upper Mate ES | TIGBAO | 2 |  |  | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 3 | 2088606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2499549.27 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303857 | Balungisan NHS | PAYAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303858 | Bulawan National High School | PAYAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303829 | Buug NHS | BUUG | 1 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303829 | Buug NHS | BUUG | 1 | 1 | 12 | 3STY12CL | 2015 SHS BATCH 2 | 18222268.79 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303846 | Catituan NHS | MALANGAS | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125758 | Datu Mama ES | PAYAO | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303825 | Dawa-Dawa NHS | ALICIA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303830 | Del Monte NHS | BUUG | 1 | 1 | 1 | 1STY1CL (Toilet Attached) | 2015 K10 BATCH 3 | 1248449.69 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303828 | Diplahan NHS | DIPLAHAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 314314 | Ditay NHS | DIPLAHAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8264965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125603 | Lumpanac ES | IMELDA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial HS | MABUHAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303852 | Mabuhay NHS | MABUHAY | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303845 | Malangas NHS | MALANGAS | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303851 | Olutanga NHS | OLUTANGA | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8414965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 314310 | Pantaleon Cudiera NHS | OLUTANGA | 1 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303856 | Payao NHS | PAYAO | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125605 | Pulawan ES | IMELDA | 1 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125854 | Talusan CES | TALUSAN | 1 | 1 | 4 | 1STY4CL (Toilet Attached) | 2015 K10 BATCH 3 | 3817968.78 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303870 | Talusan NHS | TALUSAN | 1 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8364965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303855 | Bacalan NHS | IPIL | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125812 | Balagon ES | SIAY | 2 | 1 | 6 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125812 | Balagon ES | SIAY | 2 |  |  | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125887 | Batungan ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303827 | Buayan NHS | KABASALAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 196525 | Cose Abdudan PS | TITAY | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125787 | Habib Ibrahim Mem.ES | ROSELLER LIM | 2 | 1 | 4 | 2STY4CL | 2015 K10 BATCH 6 | 6169337.6381 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303838 | Ipil NHS | IPIL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303838 | Ipil NHS | IPIL | 2 | 1 | 1 | Construction of Standard Technical and Vocational Building | 2015 TVL | 2429549.27 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303839 | Kabasalan NHS | KABASALAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303839 | Kabasalan NHS | KABASALAN | 2 | 1 | 3 | Construction of Standard Technical and Vocational Building | 2015 TVL | 7128647.81 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303840 | Kabasalan Science & Technology HS | KABASALAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125719 | Lower Sulitan Elementary School | NAGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 3 | 2952592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303867 | Malubal NHS | ROSELLER LIM | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8314965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125627 | Moreno Tadeo Mem. ES | IPIL | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303849 | Naga NHS | NAGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 196505 | New Dalangin ES | TITAY | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 6 | 2802592.44 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303859 | Pioneer NHS | TUNGAWAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303860 | San Antonio NHS | TITAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 2 | 8294965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125799 | San Ernesto ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 303868 | San Fernandino NHS | ROSELLER LIM | 2 | 1 | 6 | 2STY6CL | 2015 K10 BATCH 7 | 8214965 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303861 | Santa Clara NHS | NAGA | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8284965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303864 | Siay National High School | SIAY | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 314304 | Sisay NHS | TUNGAWAN | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 7 | 1938606 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303866 | Surabay National High School | ROSELLER LIM | 2 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303866 | Surabay NHS | ROSELLER LIM | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 314307 | Tambanan NHS | NAGA | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 314322 | Taway NHS | IPIL | 2 | 1 | 3 | 1STY3CL (Toilet Attached) | 2015 K10 BATCH 7 | 2802592 |  |  | COMPLETED | 1
NC 2015 | TECHVOC (2015) | Region IX | Zamboanga Sibugay | 303872 | Titay National High School | TITAY | 2 | 1 | 2 | Construction of Standard Technical and Vocational Building | 2015 TVL | 4779098.54 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303872 | Titay NHS | TITAY | 2 | 1 | 8 | 2STY8CL | 2015 SHS BATCH 1 | 10877342.5917 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303874 | Tungawan National High School | TUNGAWAN | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | K10 (2015) | Region IX | Zamboanga Sibugay | 125731 | Upper Tipan ES | NAGA | 2 | 1 | 2 | 1STY2CL (Toilet Attached) | 2015 K10 BATCH 6 | 1938606.04 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay NHS | IPIL | 2 | 1 | 6 | 2STY6CL | 2015 SHS BATCH 1 | 8214965.051 |  |  | COMPLETED | 1
NC 2015 | SHS (2015) | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay NHS | IPIL | 2 | 1 | 8 | 2STY8CL | 2015 ADDITIONAL FUND BATCH 9 | 2512377.5407 |  |  | COMPLETED | 1
NC 2016 | K10 | Region IX | Dapitan City | 125911 | Baao Es | Dapitan City | 1 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2000214.1914 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Dapitan City | 303877 | Barcelona National High School | Dapitan City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668064.9172 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Dapitan City | 303878 | Baylimango Nhs | Dapitan City | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17070000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dapitan City | 125937 | Capucao Ps | Dapitan City | 1 | 1 | 1 | 1STY1CL | BATCH 3 CL | 1128000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Dapitan City | 303879 | Dakak National High School | Dapitan City | 1 | 1 | 12 | 3STY12CL | BATCH 3 CL | 17070000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 28350000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 |  | 6 | 3STY6CL | BATCH 9 CL | 11503844.661 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dapitan City | 303880 | Dapitan City National High School | Dapitan City | 1 |  | 9 | 3STY9CL | BATCH 9 CL | 16708460.712 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dapitan City | 303880 | Dapitan City National High School/Talisay Extension | Dapitan City | 1 |  | 15 | 3STY15CL | BATCH 9 CL | 21300000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Dapitan City | 303881 | Ilaya Nhs | Dapitan City | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14133441.1023 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Dapitan City | 303883 | Potungan Nhs | Dapitan City | 1 | 1 | 10 | 2STY10CL | BATCH 5 CL | 14138441.1023 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Dapitan City | 303884 | Sulangon Nhs | Dapitan City | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2668064.9172 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'L. Sci. Hs | Dipolog City (Capital) | 2 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11141570 |  |  | Completed | 1 |  |  | P00072438MN - CW1 | 16JB0020 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-06-28 | 2016-08-08 | Dipolog Top Construction & Devt. Corp.
NC 2016 | TECHVOC | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'L. Sci. Hs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788710 |  |  | Completed | 1 |  |  | P00072634MN - CW1 | 16JB0029 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-06-28 | 2016-08-08 | Dipolog Top Construction & Devt. Corp.
NC 2016 | SHS | Region IX | Dipolog City | 303886 | Cogon Nhs | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6545000 |  |  | Completed | 1 | [6 empty] | 2017-06-22 |  |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | K10 | Region IX | Dipolog City | 303887 | Dipolog City Nhs (Barra) | Dipolog City (Capital) | 2 | 1 | 16 | 2STY8CL | BATCH 5 CL | 22283140 |  |  | Completed | 1 |  |  | P00071085MN - CW1 | 16JB0023 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-07-25 |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | K10 | Region IX | Dipolog City | 125972 | Galas Nhs To Galas Es | Dipolog City (Capital) | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18267268.79 |  |  | Completed | 1 | [6 empty] | 2017-06-22 |  |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | K10 | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. Hs | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6545000 |  |  | Completed | 1 |  |  | P00072439MN - CW1 | 16JB0019 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-07-25 |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | TECHVOC | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. Hs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2788710 |  |  | Completed | 1 |  |  | P00072635MN - CW1 | 16JB0030 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-07-25 |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | SHS | Region IX | Dipolog City | 303891 | Punta National High School | Dipolog City (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6535000 |  |  | Completed | 1 |  |  | P00072440MN - CW1 | 16JB0018 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-07-25 |  | Rudhil Construction & Enterprises, Inc.
NC 2016 | K10 | Region IX | Dipolog City | 303893 | Zamboanga Norte Nhs | Dipolog City (Capital) | 2 | 1 | 120 | 4STY20CL | BATCH 9 CL | 192423168 |  |  | Completed | 1 |  |  | P00073354MN - CW1 | 16JB0032 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-07-04 |  | Vicente T. Lao Construction
NC 2016 | TECHVOC | Region IX | Dipolog City | 303893 | Zamboanga Norte Nhs | Dipolog City (Capital) | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2658700 |  |  | Completed | 1 |  |  | P00074474MN - CW1 | 16JB0028 | 2016-05-06 | 2016-05-20 | 2016-06-07 | 2016-06-28 | 2016-08-08 | Dipolog Top Construction & Devt. Corp.
NC 2016 | K10 | Region IX | Isabela City | 126018 | Badjao Es | City Of Isabela (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3971375.2325 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 126018 | Badjao Es | City Of Isabela (Capital) | 0 |  | 3 | 1STY3CL | BATCH 5 CL | 3024910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198005 | Balawatin Ps | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2056214.1914 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Isabela City | 303894 | Basilan Nhs | City Of Isabela (Capital) | 0 | 1 | 60 | 4STY20CL | BATCH 9 CL | 103794537.891 |  |  | Completed | 1 | [10 empty] | With approved additional funds
NC 2016 | SHS | Region IX | Isabela City | 303894 | Basilan Nhs | City Of Isabela (Capital) | 0 |  | 10 | 2STY10CL | BATCH 9 CL | 14233441.1023 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Isabela City | 303897 | Begang Nhs | City Of Isabela (Capital) | 0 | 1 | 18 | 2STY6CL | BATCH 1 CL | 25334895.153 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 314602 | Calvario Peak Nhs | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2994910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 133031 | Caro Elementary School | City Of Isabela (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 3 CL | 6270000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 126019 | Diki Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2076214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198012 | Geras Es | City Of Isabela (Capital) | 0 | 1 | 12 | 2STY4CL | BATCH 5 CL | 18690000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198012 | Geras Es | City Of Isabela (Capital) | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1133254.6197 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Isabela City | 314601 | Isabela City Nhs | City Of Isabela (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2705618.2353 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198015 | Ismael Primary School | City Of Isabela (Capital) | 0 | 1 | 4 | 2STY4CL | BATCH 5 CL | 6230000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198015 | Ismael Primary School | City Of Isabela (Capital) | 0 |  | 1 | 1STY1CL | BATCH 5 CL | 1133254.6197 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Isabela City | 303899 | Kumalarang Nhs | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 126022 | Lukbuton Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2036214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198008 | M.S. Bernardo Elementary School | City Of Isabela (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 5 CL | 3931375.2325 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198008 | M.S. Bernardo Elementary School | City Of Isabela (Capital) | 0 |  | 2 | 1STY2CL | BATCH 5 CL | 2036214.1914 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Isabela City | 303895 | Malamawi National High School | City Of Isabela (Capital) | 0 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2752536.4706 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Isabela City | 303895 | Malamawi National High School | City Of Isabela (Capital) | 0 | 1 | 12 | 2STY6CL | BATCH 13 CL | 18762923.11 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198009 | Masola Es | City Of Isabela (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 5 CL | 2056214.1914 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 198013 | N.R. Hugo Ps | City Of Isabela (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Isabela City | 303898 | Tandung Ahas Nhs | City Of Isabela (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 5 CL | 2964910.9364 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Pagadian City | 126081 | Bagong Silang Es | Pagadian City (Capital) | 1 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6386012.64 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Pagadian City | 303903 | Lison Valley Nhs | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2636730 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Pagadian City | 314702 | Norberta Guillar Memorial Nhs | Pagadian City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 9 CL | 26482375 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Pagadian City | 303906 | Pagadian City National Comprehensive High School | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2612200 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Pagadian City | 303908 | Pagadian City Nhs | Pagadian City (Capital) | 1 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22655968.62 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Pagadian City | 303908 | Pagadian City Nhs | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2612125 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Pagadian City | 314704 | Pagadian City Science High School | Pagadian City (Capital) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Pagadian City | 314704 | Pagadian City Science High School | Pagadian City (Capital) | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 17199085.712 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Pagadian City | 303910 | Zamboanga Del Sur Nhs | Pagadian City (Capital) | 1 | 1 | 48 | 4STY24CL | BATCH 11 CL | 71865115.9179 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Pagadian City | 345814 | Zamboanga Del Sur Sports Academy | Pagadian City (Capital) | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 28475000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303915 | Ayala Nhs | Zamboanga City | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 32402890 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303915 | Ayala Nhs | Zamboanga City | 1 |  | 24 | 4STY24CL | BATCH 9 CL | 36296257 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126108 | Baliwasan Cs | Zamboanga City | 1 | 1 | 20 | 4STY20CL | BATCH 7 CL | 31752891 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 303923 | Don Pablo A. Lorenzo Mhs | Zamboanga City | 1 | 1 | 8 | 2STY4CL | BATCH 9 CL | 12638675.2761 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126110 | John Spirig S. Mes | Zamboanga City | 1 | 1 | 40 | 4STY20CL | BATCH 13 CL | 62905782 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126104 | Labuan Cs To Sinunuc Es | Zamboanga City | 1 |  | 15 | 3STY15CL | BATCH 3 CL | 21740665.56 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City |  | Labuan Cs 2Sty4Cl To Sinunuc Es | Zamboanga City | 1 |  |  |  | BATCH 3 CL |  |  |  | Reverted | 0
NC 2016 | SHS | Region IX | Zamboanga City | 303924 | Ramon Enriquez Hs | Zamboanga City | 1 | 1 | 16 | 4STY16CL | BATCH 13 CL | 29857716.362 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126104 | Sinunuc Es | Zamboanga City | 1 | 1 | 15 | 3STY15CL | BATCH 13 CL | 24852577.982 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126210 | Sta. Barbara Cs | Zamboanga City | 1 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15471328 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303918 | Bunguiao Nhs | Zamboanga City | 2 | 1 | 9 | 3STY9CL | BATCH 9 CL | 15571328 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303919 | Cabaluay Nhs | Zamboanga City | 2 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12771310.093 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303921 | Curuan Nhs | Zamboanga City | 2 | 1 | 24 | 4STY24CL | BATCH 9 CL | 36546257 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126182 | Guisao Es | Zamboanga City | 2 | 1 | 6 | 2STY6CL | BATCH 13 CL | 8564965 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 314806 | Mangusu Is | Zamboanga City | 2 | 1 | 9 | 3STY9CL | BATCH 13 CL | 15571328 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303922 | Maria Clara L. Lobregat Nhs | Zamboanga City | 2 |  | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 303922 | Maria Clara L. Lobregat Nhs | Zamboanga City | 2 | 1 | 8 | 4STY8CL | BATCH 9 CL | 14897518.84 |  |  | Reverted | 0
NC 2016 | K10 | Region IX | Zamboanga City | 126204 | Putik Cs | Zamboanga City | 2 | 1 | 12 | 3STY12CL | BATCH 13 CL | 18422269 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 314801 | Talon-Talon Nhs | Zamboanga City | 2 | 1 | 12 | 4STY12CL | BATCH 9 CL | 22152343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga City | 314801 | Talon-Talon Nhs | Zamboanga City | 2 |  | 20 | 4STY20CL | BATCH 9 CL | 31102890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126231 | Tugbungan Es | Zamboanga City | 2 | 1 | 6 | 3STY6CL | BATCH 13 CL | 11843844.661 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga City | 126206 | Zambowood Es | Zamboanga City | 2 | 1 | 4 | 2STY4CL | BATCH 13 CL | 6619338 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22020000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303715 | Pinan National High School | Piñan (New Piñan) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303728 | Sergio Osmena Nhs | Sergio Osmeña Sr. | 1 | 1 | 24 | 2STY8CL | BATCH 9 CL | 33005000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303728 | Sergio Osmena Nhs | Sergio Osmeña Sr. | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303737 | Sibutad National High School | Jose Dalman (Ponot) | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 31152890.27 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21423013.45 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 |  | 12 | 3STY12CL | BATCH 9 CL | 18262268.79 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303696 | Katipunan National High School | Katipunan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303710 | Manukan Nhs | Manukan | 2 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62230780.54 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303738 | Sindangan National Agricultural School | Sindangan | 2 | 1 | 36 | 3STY12CL | BATCH 9 CL | 54716806.37 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303738 | Sindangan National Agricultural School | Sindangan | 2 | 1 | 4 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 9958040 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303739 | Sindangan Nhs | Bacungan (Leon T. Postigo) | 2 | 1 | 40 | 4STY20CL | BATCH 13 CL | 68471358.594 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303672 | Bacungan Nhs | Bacungan (Leon T. Postigo) | 3 | 1 | 15 | 3STY15CL | BATCH 9 CL | 21433013.45 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303672 | Bacungan Nhs | Bacungan (Leon T. Postigo) | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303686 | Gutalac Nhs | Gutalac | 3 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64199040.35 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303686 | Gutalac Nhs | Gutalac | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303703 | Kipit Agro-Fishery Nhs | Labason | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2771079.0067 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303706 | Liloy National High School | Liloy | 3 | 1 | 40 | 4STY20CL | BATCH 9 CL | 62255780.54 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303706 | Liloy National High School | Liloy | 3 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4979020 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303721 | Salug National High School | Salug | 3 | 1 | 40 | 2STY10CL | BATCH 9 CL | 51642000 |  |  | Terminated | 0 | [10 empty] | MUTUAL AND PARTIAL TERMINATION (Only 50% of the contract was terminated, instead of 4 units of 2 storey 10 classroom only 2 units was implemented due to no buildable space to construct the remaining units)
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303721 | Salug National High School | Salug | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303740 | Siocon National High School | Sirawai | 3 | 1 | 24 | 3STY12CL | BATCH 3 CL | 36494537.58 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Norte | 303742 | Sirawai National High School | Sirawai | 3 | 1 | 32 | 2STY8CL | BATCH 9 CL | 43990000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303742 | Sirawai National High School | Sirawai | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 | 1 | 16 | 2STY8CL | BATCH 9 CL | 22020000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 |  | 6 | 2STY6CL | BATCH 9 CL | 8296000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303745 | Tampilisan Nhs | Tampilisan | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2489510 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Norte | 303750 | Ubay Nhs | Labason | 3 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2771079.0067 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Norte | 303750 | Ubay Nhs | Labason | 3 | 1 | 10 | 2STY10CL | BATCH 13 CL | 13018000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303780 | Aurora National High School | Aurora | 1 | 1 | 30 | 3STY15CL | BATCH 5 CL | 48433129.59 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303780 | Aurora National High School | Aurora | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2624700 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 314203 | Boniao National High School | Mahayag | 1 | 1 | 8 | 2STY4CL | BATCH 3 CL | 13617375 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 314203 | Boniao National High School | Mahayag | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 5252750 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303766 | Commonwealth Nhs | Aurora | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2624700 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 | 1 | 40 | 2STY8CL | BATCH 5 CL | 61684484.2543 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 |  | 4 | 2STY4CL | BATCH 5 CL | 6804875 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303773 | Dumingag National High School | Dumingag | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2701200 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303792 | Leonardo Nhs | Josefina | 1 | 1 | 9 | 3STY9CL | BATCH 11 CL | 16797750 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303792 | Leonardo Nhs | Josefina | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2624700 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303803 | Mahayag School Of Arts And Trade (Mahayag Nhs) | Mahayag | 1 | 1 | 20 | 4STY20CL | BATCH 9 CL | 33604750 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303803 | Mahayag School Of Arts And Trade (Mahayag Nhs) | Mahayag | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 5352000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303796 | Midsalip Nhs- Main | Midsalip | 1 | 1 | 32 | 4STY16CL | BATCH 3 CL | 54132400 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303796 | Midsalip Nhs- Main | Midsalip | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2639640 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303797 | Molave Vocational Technical School | Molave | 1 | 1 | 24 | 4STY24CL | BATCH 11 CL | 40334132.854 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303799 | New Labangan Nhs | Labangan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | Ramon Magsaysay (Liargo) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur |  | Shs In Labangan, Zamboanga Del Sur | Labangan | 1 | 1 | 12 | 3STY12CL | BATCH 11 CL | 18696088.4293 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303817 | Sominot National High School | Sominot (Don Mariano Marcos) | 1 | 1 | 6 | 2STY6CL | BATCH 5 CL | 9321681.5561 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303817 | Sominot National High School | Sominot (Don Mariano Marcos) | 1 |  | 8 | 2STY4CL | BATCH 5 CL | 13701540 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303817 | Sominot Nhs | Sominot (Don Mariano Marcos) | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2650000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 | 1 | 20 | 4STY20CL | BATCH 3 CL | 33604750 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 |  | 9 | 3STY9CL | BATCH 3 CL | 15203700 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303819 | Tambulig Nhs | Tambulig | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 4 TVL | 2651200 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 14412150 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 |  | 30 | 3STY15CL | BATCH 9 CL | 44180526.9 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303811 | Tukuran Tech. Voc'L. Hs | Tukuran | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2612000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303753 | Antonio Nhs | Tigbao | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2610000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303757 | Bayog Nhs | Bayog | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 55632400 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303757 | Bayog Nhs | Bayog | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2570000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303791 | Betinan Nhs | San Miguel | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303791 | Betinan Nhs | San Miguel | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303770 | Dimataling National High School | Dimataling | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2570000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303771 | Dinas Nhs | Dinas | 2 | 1 | 36 | 4STY12CL | BATCH 9 CL | 62308950 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303771 | Dinas Nhs | Dinas | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4852956.8627 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303776 | Eugenia Andrin Nhs | San Pablo | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303776 | Eugenia Andrin Nhs | San Pablo | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2550000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303778 | Guipos Nhs | Guipos | 2 | 1 | 24 | 4STY12CL | BATCH 5 CL | 44304687.24 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 | 1 | 16 | 4STY16CL | BATCH 4 TVL | 2570000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 27776200 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303782 | Kabatan Nhs | Vincenzo A. Sagun | 2 |  | 1 | SHS UNIQUE WORKSHOP | BATCH 3 CL | 11180000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 | 1 | 12 | 4STY12CL | BATCH 5 CL | 22212343.62 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 |  | 9 | 3STY9CL | BATCH 5 CL | 14820000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303783 | Kalian Nhs | Margosatubig | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 6 TVL | 2560000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303788 | Lapuyan Nhs | Lapuyan | 2 | 1 | 24 | 4STY12CL | BATCH 3 CL | 41619300 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303788 | Lapuyan Nhs | Lapuyan | 2 |  | 6 | 3STY6CL | BATCH 3 CL | 10680000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303764 | Laureano Salusod Nhs | Dimataling | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 20809650 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303764 | Laureano Salusod Nhs | Dimataling | 2 |  | 9 | 3STY9CL | BATCH 7 CL | 14820000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 314252 | Locuban Nhs Realigned To Maria Clara L. Lobregat Nhs | Dumalinao | 2 | 1 | 8 | 2STY8CL | BATCH 3 CL | 13858100 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 314217 | Locuban Nhs Realigned Bibilik Nhs | Dumalinao | 2 | 1 | 6 | 2STY6CL | BATCH 3 CL | 13858100 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14800000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 |  | 4 | 2STY4CL | BATCH 7 CL | 6675000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303804 | Paulino Dari Nhs | Pitogo | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5125000 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Del Sur | 303808 | Rebokon Avhs | Dumalinao | 2 | 1 | 8 | 2STY4CL | BATCH 7 CL | 13300000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303808 | Rebokon Avhs | Dumalinao | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303768 | Tabina Nhs | Tabina | 2 | 1 | 12 | 4STY12CL | BATCH 7 CL | 20949650 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 | 1 | 9 | 3STY9CL | BATCH 7 CL | 14775000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 |  | 12 | 4STY12CL | BATCH 7 CL | 20749650 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303822 | Toribio Minor Nhs | Margosatubig | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 5100000 |  |  | Completed | 1
NC 2016 | TECHVOC | Region IX | Zamboanga Del Sur | 303823 | Tubod Nhs | Lakewood | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 12 TVL | 2550000 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12871310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | RAMONA CONST. & ENT.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12871310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | JAYKRIS ENT. & CONST.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | Alicia | 1 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18347268.79 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | GENETIAN BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303825 | Dawa-Dawa Nhs | Alicia | 1 | 1 | 8 | 2STY8CL | BATCH 3 CL | 11235000 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | MINDANAO ROCK
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303825 | Dawa-Dawa Nhs | Alicia | 1 | 1 | 6 | 2STY6CL | BATCH 9 CL | 9171461.5561 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-08-15 | 2016-08-31 | 2016-09-15 | GENETIAN BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12771310.09 |  |  | Terminated | 0 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 2016-08-23 | RUDHIL CONST. & ENT. INC. | Due to NGCP work stoppage order; Contract Termination;With approved buffer fund 2019
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 |  | 16 | 2STY8CL | BATCH 7 CL | 21754685.18 |  |  | Terminated | 0 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | RCDG CONST. CROP JV DIPLAHAN COMM. & CONST. | With approved buffer fund 2019
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303828 | Diplahan Nhs | Diplahan | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 2016-07-15 | JAYKRIS ENT. & CONST.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 314314 | Ditay Nhs | Diplahan | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 2016-08-23 | MJMARI BUILD. & ENT.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 20 | 2STY10CL | BATCH 7 CL | 25542620.18 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 2016-08-23 | GENETIAN BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-07-25 | 2016-07-12 | 2016-07-25 | 2016-08-09 | 2016-08-23 | GENETIAN BUILDERS
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303837 | Imelda Nhs | Imelda | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 8 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 2016-07-04 | JAYKRIS ENT. & CONST.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 314315 | Mabuhay Agro-Industrial Hs | Mabuhay | 1 | 1 | 8 | 2STY8CL | BATCH 7 CL | 11077342.59 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 2016-10-04 | JAYKRIS ENT. & CONST.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303852 | Mabuhay Nhs | Mabuhay | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12896310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 2016-10-04 | JAYKRIS ENT. & CONST.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 | 1 | 10 | 2STY10CL | BATCH 9 CL | 12846310.09 |  |  | Completed | 1 |  |  |  |  | 2016-07-10 | 2016-09-26 | 2016-10-24 | 2016-03-11 | 2016-11-11 | HENSO CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 |  | 16 | 2STY8CL | BATCH 9 CL | 21854685.18 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-08-15 | 2016-08-31 | 2016-09-15 | RUDHIL CONST. & ENT. INC.
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303845 | Malangas Nhs | Malangas | 1 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 2016-07-15 | JAYKRIS ENT. & CONST.
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | Olutanga | 1 | 1 | 18 | 2STY6CL | BATCH 9 CL | 25094895.18 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 2016-10-04 | RAMONA CONST. & ENT.
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | Olutanga | 1 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4984923.92 |  |  | Completed | 1 |  |  |  |  | 2016-04-21 | 2016-04-08 | 2016-04-21 | 2016-05-06 | 2016-07-15 | ST. JOSEPH CONST. & TRADING
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | Payao | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12896310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-30 | 2016-08-16 | 2016-08-30 | 2016-09-14 | 2016-09-27 | RAMONA CONST. & ENT.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303870 | Talusan Nhs | Talusan | 1 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 2016-10-04 | RAMONA CONST. & ENT.
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303870 | Talusan Nhs | Talusan | 1 |  | 8 | 2STY8CL | BATCH 7 CL | 10977342.59 |  |  | Completed | 1 |  |  |  |  | 2016-08-01 | 2016-08-03 | 2016-09-07 | 2016-09-22 | 2016-10-04 | JAYKRIS ENT. & CONST.
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 125640 | Diampak Elementary School | Kabasalan | 2 | 1 | 2 | 1STY1CL | BATCH 13 CL | 2396899.38 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303827 | Francisco Ramos Nhs (Formerly Buayan Nhs) | Kabasalan | 2 | 1 | 20 | 4STY20CL | BATCH 9 CL | 34198179.297 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | BARILLO CONSTRUCTION
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303827 | Francisco Ramos Nhs (Formerly Buayan Nhs) | Kabasalan | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | JGC CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303838 | Ipil Nhs | Ipil | 2 | 1 | 24 | 4STY24CL | BATCH 3 CL | 35596000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 407764 | LONG ISLAND BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303839 | Kabasalan Nhs | Kabasalan | 2 | 1 | 16 | 4STY16CL | BATCH 3 CL | 26702000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 2016-06-16 | JGC CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303840 | Kabasalan Science & Technology High School | Kabasalan | 2 | 1 | 4 | 2STY4CL | BATCH 7 CL | 6319337.63 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-22 | JGC CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 125826 | Mahayahay Es | Siay | 2 | 1 | 2 | 1STY2CL | BATCH 13 CL | 2038606.04 |  |  | Completed | 1
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303867 | Malubal Nhs | Roseller Lim | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | LONG ISLAND BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 | 1 | 8 | 2STY8CL | BATCH 9 CL | 10877342.59 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | HENSO CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 |  | 6 | 2STY6CL | BATCH 9 CL | 8214965.06 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | HENSO CONSTRUCTION
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303849 | Naga Nhs | Naga | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | JGC CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303859 | Pioneer Nhs | Tungawan | 2 | 1 | 12 | 3STY12CL | BATCH 7 CL | 18222268.79 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | LONG ISLAND BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303859 | Pioneer Nhs | Tungawan | 2 |  | 1 | 1STY1CL | BATCH 7 CL | 1098449.69 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | GJD CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303860 | San Antonio Nhs | Titay | 2 | 1 | 10 | 2STY10CL | BATCH 7 CL | 12921310.09 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | RUDHIL CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303864 | Siay National High School | Siay | 2 | 1 | 28 | 4STY28CL | BATCH 3 CL | 40067000 |  |  | Completed | 1 |  |  |  |  | 2016-03-01 | 2016-03-10 | 2016-03-22 | 2016-05-24 | 2016-06-30 | ESR CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303861 | Sta. Clara National High School | Naga | 2 | 1 | 16 | 2STY8CL | BATCH 7 CL | 21854685.18 |  |  | Completed | 1 |  |  |  |  | 2016-06-29 | 2016-06-02 | 2016-07-19 | 2016-08-01 | 2016-08-16 | RUDHIL CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303866 | Surabay National High School | Roseller Lim | 2 | 1 | 36 | 3STY12CL | BATCH 9 CL | 54666806.37 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | OG SANTOS CONSTRUCTION
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303866 | Surabay National High School | Roseller Lim | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | BARILLO CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 303872 | Titay National High School | Titay | 2 | 1 | 45 | 3STY15CL | BATCH 9 CL | 64149040.35 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | OG SANTOS CONSTRUCTION
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303872 | Titay National High School | Titay | 2 | 1 | 1 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 2417461.96 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-07-21 | 2016-08-16 | GJD CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303874 | Tungawan National High School | Tungawan | 2 | 1 | 32 | 4STY16CL | BATCH 9 CL | 58715432.724 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | ESR CONSTRUCTION
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 | 1 | 20 | 2STY10CL | BATCH 9 CL | 25542620.18 |  |  | Completed | 1 |  |  |  |  | 2016-06-29 | 2016-06-02 | 1900-02-08 | 2016-08-01 | 2016-08-16 | LONG ISLAND BUILDERS
NC 2016 | SHS | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 |  | 9 | 3STY9CL | BATCH 9 CL | 15121327.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | LONG ISLAND BUILDERS
NC 2016 | TECHVOC | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay Nhs | Ipil | 2 | 1 | 2 | SHS UNIQUE WORKSHOP | BATCH 10 TVL | 4834923.92 |  |  | Completed | 1 |  |  |  |  | 2016-05-17 | 2016-06-02 | 2016-06-28 | 2016-08-01 | 2016-08-16 | GJD CONSTRUCTION
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 125891 | Langon Elementary School | Tungawan | 2 | 1 | 2 | 1STY1CL w/ toilet attached | BATCH 14 CL | 2196899.38 |  |  | Completed | 1
NC 2016 | K10 | Region IX | Zamboanga Sibugay | 125866 | Kitabog Es | Titay | 2 | 1 | 10 | 2STY10CL | BATCH 14 CL | 12771310.09 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125954 | Antipolo ES | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2805398 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Dapitan City | 125912 | Barcelona CS | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2787398 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Dapitan City | 125926 | Canlucani ES | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2925563 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Dapitan City | 125916 | Ilaya ES | DAPITAN CITY | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 5000000 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | STARS & STRIPES
NC 2017 | K10 | Region IX | Dapitan City | 125950 | San Francisco ES | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2855398 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Dapitan City | 125959 | San Vicente ES | DAPITAN CITY | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 3170212 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Dapitan City | 125920 | Tamion ES | DAPITAN CITY | 1 | 1 | 4 | 1STY4CL | BATCH 2 | 5300000 |  |  | Completed | 1 | [7 empty] | 2017-09-04 | 2017-09-26 | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | TVL | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4517422.26 |  |  | COMPLETED | 1
NC 2017 | TVL | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 4117966.82 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 4517422.26 |  |  | COMPLETED | 1
NC 2017 | TVL | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 8 | 4117966.82 |  |  | COMPLETED | 1
NC 2017 | SHS | Region IX | Dapitan City | 303878 | Baylimango NHS | DAPITAN CITY | 1 | 1 | 6 | 3STY6CL | BATCH 12 | 14883294 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303878 | Baylimango NHS | DAPITAN CITY | 1 |  | 4 | 2STY4CL | BATCH 13 | 10777517.62 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303879 | Dakak National High School | DAPITAN CITY | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 18823602.67 |  |  | COMPLETED | 1
NC 2017 | SHS | Region IX | Dapitan City | 303879 | Dakak National High School | DAPITAN CITY | 1 |  | 4 | 2STY4CL | BATCH 13 | 10051065.07 |  |  | COMPLETED | 1
NC 2017 | K10 | Region IX | Dapitan City | 125938 | Dapitan City CS | DAPITAN CITY | 1 | 1 | 12 | 2 units 2STY6CL | BATCH 13 | 26287825 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125938 | Dapitan City CS | DAPITAN CITY | 1 |  | 8 | 2STY8CL | BATCH 13 | 19032294 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125938 | Dapitan City CS | DAPITAN CITY | 1 |  | 10 | 2STY10CL | BATCH 13 | 21672360 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 19332746 |  |  | COMPLETED | 1
NC 2017 | SHS | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 |  | 4 | 2STY4CL | BATCH 13 | 10037976 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303880 | Dapitan City National High School | DAPITAN CITY | 1 |  | 4 | 2STY4CL | BATCH 13 | 10037976 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125915 | Hilltop ES | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10037977 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303881 | Ilaya NHS | DAPITAN CITY | 1 | 1 | 8 | 2STY8CL | BATCH 13 | 19032294 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125949 | Potungan CS | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 9672960 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dapitan City | 125958 | San Pedro ES | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL | BATCH 13 | 10238737 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 | 1 | 8 | 4STY8CL | BATCH 13 | 18545663 |  |  | COMPLETED | 1
NC 2017 | SHS | Region IX | Dapitan City | 303884 | Sulangon NHS | DAPITAN CITY | 1 |  | 16 | 4STY16CL | BATCH 13 | 38704664.39 |  | 38481119.94 | Completed | 1 | [10 empty] | No Certificate of Completion and No Certificate of Turn- Over
NC 2017 | K10 | Region IX | Dipolog City | 125983 | Sicayab ES | DIPOLOG CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2776502.57 |  |  | Completed | 1 | [9 empty] | Dipolog Top Construction & Dev't.Corp.
NC 2017 | K10 | Region IX | Dipolog City | 125978 | Tubod ES | DIPOLOG CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2771502.57 |  |  | Completed | 1 | [9 empty] | Dipolog Top Construction & Dev't.Corp.
NC 2017 | K10 | Region IX | Dipolog City | 314501 | Upper Dicayas IS | DIPOLOG CITY (Capital) | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2756502.57 |  |  | Completed | 1 | [9 empty] | Dipolog Top Construction & Dev't.Corp.
NC 2017 | SHS | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'l. Sci. HS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9682893.7 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303885 | Alberto Q. Ubay Mem. Agro-Tech'l. Sci. HS | DIPOLOG CITY (Capital) | 2 |  | 6 | 2STY6CL | BATCH 10 | 12147462.46 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9662893.7 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dipolog City | 125982 | Dipolog Pilot Demonstration School | DIPOLOG CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 10 | 25501544.66 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dipolog City | 125972 | Galas ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9792893.7 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dipolog City | 125973 | Magsaysay ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9687893.7 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Dipolog City | 125974 | Miputak East CS | DIPOLOG CITY (Capital) | 2 | 1 | 18 | 2 units 3STY9CL | BATCH 10 | 50833089.32 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303890 | Pamansalan Eco. Tech. HS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9662893.7 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303891 | Punta National High School | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9662893.7 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 38895333.68 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Dipolog City | 303893 | Zamboanga Norte NHS | DIPOLOG CITY (Capital) | 2 |  | 4 | 2STY4CL | BATCH 10 | 9762893.7 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 5184634.7 |  |  | Completed | 1 |  |  |  | 17JH0019 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | RJLP Const. & Supplies
NC 2017 | SHS | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 |  | 4 | 1STY4CL | BATCH 2 | 5160694.7 |  |  | Completed | 1 |  |  |  | 17JH0020 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | RJLP Const. & Supplies
NC 2017 | SHS | Region IX | Isabela City | 303894 | Basilan NHS | CITY OF ISABELA (Capital) | 0 |  | 4 | 1STY4CL | BATCH 2 | 5184634.7 |  |  | Completed | 1 |  |  |  | 17JH0021 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | RJLP Const. & Supplies
NC 2017 | K10 | Region IX | Isabela City | 303896 | Basilan NHS - Night | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 5184634.7 |  |  | Completed | 1 |  |  |  | 17JH0022 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | RJLP Const. & Supplies
NC 2017 | TVL | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL (SCI-LAB) | BATCH 2 | 5131986.7 |  |  | Completed | 1 |  |  |  | 17JJH0050 |  | 2017-09-27 | 2017-10-10 | 2017-12-08 | 2017-12-14 | ABSOLUTE ENG. & SUP.
NC 2017 | TVL | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 |  | 2 | 1STY2CL (SCI-LAB) | BATCH 2 | 5131986.7 |  |  | Completed | 1 |  |  |  | 17JH0051 |  | 2017-09-27 | 2017-10-10 | 2017-12-08 | 2017-12-14 | ABSOLUTE ENG. & SUP.
NC 2017 | TVL | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 |  | 2 | 1STY2CL (ICT LAB) | BATCH 2 | 5131981.7 |  |  | Completed | 1 |  |  |  | 17JH0082 |  | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-21 | JAMARI CONSTRUCTION
NC 2017 | TVL | Region IX | Isabela City | 303897 | Begang NHS | CITY OF ISABELA (Capital) | 0 |  | 2 | 1STY2CL (ICT LAB) | BATCH 2 | 5131981.7 |  |  | Completed | 1 |  |  |  | 17JH0083 |  | 2017-11-16 | 2017-11-28 | 2017-12-07 | 2017-12-21 | JAMARI CONSTRUCTION
NC 2017 | K10 | Region IX | Isabela City | 126002 | Isabela Central Elementary Pilot School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 5184634.7 |  |  | Completed | 1 |  |  |  | 17JH0023 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | HHHS Development & Const.
NC 2017 | K10 | Region IX | Isabela City | 126001 | Isabela East CES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2762194.17 |  |  | Completed | 1 |  |  |  | 17JH0024 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | HHHS Development & Const.
NC 2017 | K10 | Region IX | Isabela City | 126001 | Isabela East CES | CITY OF ISABELA (Capital) | 0 |  | 3 | 1STY3CL | BATCH 2 | 3834565.34 |  |  | Completed | 1 |  |  |  | 17JH0025 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | Absolute Engineering & Supplies
NC 2017 | SHS | Region IX | Isabela City | 303899 | Kumalarang NHS | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3905434.34 |  |  | Completed | 1 |  |  |  | 17JH0026 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | HHHS Development & Const.
NC 2017 | K10 | Region IX | Isabela City | 126011 | Latuan Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 2 | 5215311.5882 |  |  | Completed | 1 |  |  |  | 17JH0027 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | 2M Construction
NC 2017 | K10 | Region IX | Isabela City | 126025 | Panigayan Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 2 | 3869076.43 |  |  | Completed | 1 |  |  |  | 17JH0028 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | 2M Construction
NC 2017 | K10 | Region IX | Isabela City | 126004 | Westside ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 2 | 2762194.17 |  |  | Completed | 1 |  |  |  | 17JH0029 |  | 2017-08-08 | 2017-08-22 | 2017-09-04 | 2017-09-11 | HHHS Development & Const.
NC 2017 | K10 | Region IX | Isabela City | 126018 | Badjao ES | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 7 | 5308830.0323 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Isabela City | 314603 | Baluno National High School | CITY OF ISABELA (Capital) | 0 | 1 | 4 | 1STY4CL | BATCH 7 | 5148604.4029 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126000 | Bliss ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126028 | Cabunbata ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3834565.34 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126021 | Lampinigan Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2757421.9492 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 198008 | M.S. BERNARDO ELEMENTARY SCHOOL | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2762898.4575 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Isabela City | 303895 | MALAMAWI NATIONAL HIGH SCHOOL | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 3869076.4281 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Isabela City | 303895 | MALAMAWI NATIONAL HIGH SCHOOL | CITY OF ISABELA (Capital) | 0 |  | 2 | 1STY2CL | BATCH 10 | 2762898.4575 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 198009 | Masola Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2762898.4575 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 198001 | Menzi ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 1STY2CL | BATCH 10 | 2738254.17 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126026 | Tampalan ES | CITY OF ISABELA (Capital) | 0 | 1 | 3 | 1STY3CL | BATCH 10 | 4169076.4235 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126026 | Tampalan ES | CITY OF ISABELA (Capital) | 0 |  | 3 | 1STY3CL | BATCH 10 | 4169076.4235 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Isabela City | 126026 | Tampalan ES | CITY OF ISABELA (Capital) | 0 |  | 2 | 1STY2CL | BATCH 10 | 2912898.4575 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 3 | 1STY3CL | BATCH 4 | 4831837 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126057 | White Beach ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3166000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126070 | Buenavista ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3147000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126087 | Dampalan Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3175000 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Pagadian City | 126088 | Dumalian ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3204000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126063 | Kalasan Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3134000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126072 | La Suerte ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3213500 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126045 | Lower Sibatang | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3175000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126074 | Lumad ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3134000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Pagadian City | 126068 | Tulangan ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3145000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga City | 126232 | Bincul ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2650000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga City | 126119 | Cansilayan ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga City | 199002 | Niyog-Niyog ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 2720000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga City | 126244 | Sibulao ES | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | BATCH 2 | 3100000 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga City | 303931 | Sibulao NHS | ZAMBOANGA CITY | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3100000 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga City | 126197 | Boalan ES | ZAMBOANGA CITY | 2 | 1 | 15 | 3STY15CL | BATCH 8 | 34113054.96 |  |  | REVERTED | 0
NC 2017 | K10 | Region IX | Zamboanga City | 126181 | Culianan Learning Center E-IMPACT | ZAMBOANGA CITY | 2 | 1 | 15 | 3STY15CL | BATCH 8 | 34010214.34 |  |  | Completed | 1 |  |  | P00177752MN | 17JA0153 | [5 empty] | AMARRO CONST./ LONG ISLAND JV
NC 2017 | SHS | Region IX | Zamboanga City | 303920 | Culianan NHS | ZAMBOANGA CITY | 2 | 1 | 9 | 3STY9CL | BATCH 8 | 24526826.04 |  |  | Completed | 1 |  |  | P00177755MN | 17JA0155 | [5 empty] | LC CONSTRUCTION CORPORATION
NC 2017 | K10 | Region IX | Zamboanga City | 126198 | Divisoria ES | ZAMBOANGA CITY | 2 | 1 | 12 | 3STY12CL | BATCH 8 | 29325155.91 |  |  | Completed | 1 |  |  | P00177754MN | 17JA0154 | [5 empty] | GHR CONST.
NC 2017 | K10 | Region IX | Zamboanga City | 126221 | Catalina Vda de Jalon MS | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | BATCH 10 | 33671709.45 |  |  | Completed | 1 |  |  | P00179578MN | 17JA0139 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 14487676.68 |  |  | Completed | 1 |  |  | P00179572MN | 17JA0137 | [5 empty] | AEJ CONSTRUCTION
NC 2017 | K10 | Region IX | Zamboanga City | 126222 | Pasonanca ES | ZAMBOANGA CITY | 1 | 1 | 10 | 2STY10CL | BATCH 10 | 20768324.59 |  |  | Completed | 1 |  |  | P00179579MN | 17JA0152 | [5 empty] | RUDHIL CONSTRUCTION AND ENTERPRISES
NC 2017 | K10 | Region IX | Zamboanga City | 126146 | Patalon Elementary School | ZAMBOANGA CITY | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 25659716.8 |  |  | Completed | 1 |  |  | P00179573MN | 17JA0136 | [5 empty] | CGR CAMILLE BUILDERS
NC 2017 | K10 | Region IX | Zamboanga City | 126103 | Recodo ES | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | BATCH 10 | 34430840.82 |  |  | Completed | 1 |  |  | P00179568MN | 17JA0148 | [5 empty] | EDISON DEVELOPMENT/ AHE CONST. JV
NC 2017 | SHS | Region IX | Zamboanga City | 314805 | Recodo NHS | ZAMBOANGA CITY | 1 | 1 | 6 | 3STY6CL | BATCH 10 | 14004713.95 |  |  | Completed | 1 |  |  | P00179583MN | 17JA0143 | [5 empty] | LONG ISLAND BUILDERS AND CONSTRUCTION
NC 2017 | SHS | Region IX | Zamboanga City | 303943 | Regional Science HS | ZAMBOANGA CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 31650258.15 |  |  | Completed | 1 |  |  | P00179582MN | 17JA0144 | [5 empty] | LONG ISLAND BUILDER
NC 2017 | K10 | Region IX | Zamboanga City | 126209 | Rio Hondo ES | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL | BATCH 10 | 10829618.79 |  |  | Completed | 1 |  |  | P00179574MN | 17JA0141 | [5 empty] | ASEAS CONST.
NC 2017 | K10 | Region IX | Zamboanga City | 126112 | San Jose Gusu Elementary School | ZAMBOANGA CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 33234345.68 |  |  | Completed | 1 |  |  | P00179570MN | 17JA0151 | [5 empty] | EDISON DEV.& CONST.
NC 2017 | K10 | Region IX | Zamboanga City | 126219 | San Roque Elementary School | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | BATCH 10 | 34175694.53 |  |  | Completed | 1 |  |  | P00179575MN | 17JA0147 | [5 empty] | GHR CONSTRUCTION
NC 2017 | K10 | Region IX | Zamboanga City | 314809 | San Roque NHS | ZAMBOANGA CITY | 1 | 1 | 16 | 4STY16CL | BATCH 10 | 39248338.89 |  |  | Completed | 1 |  |  | P00179584MN | 17JA0142 | [5 empty] | GHR CONSTRUCTION
NC 2017 | K10 | Region IX | Zamboanga City | 126104 | Sinunuc ES | ZAMBOANGA CITY | 1 | 1 | 12 | 3STY12CL | BATCH 10 | 29422827.32 |  |  | Completed | 1 |  |  | P00181176MN | 17JA0163 | [5 empty] | LONG ISLAND BUILDERS AND CONSTRUCTION
NC 2017 | SHS | Region IX | Zamboanga City | 303932 | Sinunuc NHS | ZAMBOANGA CITY | 1 | 1 | 12 | 4STY12CL | BATCH 10 | 32261985.26 |  |  | Completed | 1 |  |  | P00179580MN | 17JA0140 | [5 empty] | LONG ISLAND BUILDER
NC 2017 | K10 | Region IX | Zamboanga City | 126113 | Southcom Elementary School | ZAMBOANGA CITY | 1 | 1 | 24 | 4STY12CL | BATCH 10 | 62763412.08 |  |  | Completed | 1 |  |  | P00179571MN | 17JA0149 | [5 empty] | BENDIMIL CONT.
NC 2017 | K10 | Region IX | Zamboanga City | 126220 | Sta. Maria Central School | ZAMBOANGA CITY | 1 | 1 | 9 | 3STY9CL | BATCH 10 | 24317302.26 |  |  | Completed | 1 |  |  | P00179576MN | 17JA0145 | [5 empty] | EDISON DEVELOPMENT/ LL CONSTRUCTION
NC 2017 | K10 | Region IX | Zamboanga City | 126220 | Sta. Maria Central School | ZAMBOANGA CITY | 1 |  | 6 | 3STY6CL | BATCH 10 | 13857580.58 |  |  | Completed | 1 |  |  | P00179577MN | 17JA0146 | [5 empty] | LL CONSTRUCTION
NC 2017 | SHS | Region IX | Zamboanga City | 303935 | Talisayan NHS | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | BATCH 10 | 12979031.38 |  |  | Completed | 1 |  |  | P00179581MN | 17JA0150 | [5 empty] | MOTHER ROLE CONT.
NC 2017 | K10 | Region IX | Zamboanga City | 126229 | Tetuan CS | ZAMBOANGA CITY | 2 | 1 | 40 | 2 UNITS 4STY20CL | BATCH 14 | 81723759.43 |  |  | Completed | 1 |  |  | P00184306MN | 17JA0156 | [5 empty] | BENDIMIL CONSTRUCTION DEV'T. CORP.
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303674 | Talinga National High School | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2683547.75 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303675 | Tinuyop National High school | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2638914.79 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195510 | Malinao PS | BALIGUIAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314122 | Gutalac NHS Ext. - Tipan | GUTALAC | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2699131.68 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2649090.72 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124323 | Bitoon ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124324 | Dinasan ES | JOSE DALMAN (PONOT) | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303680 | DINASAN NATIONAL HIGH SCHOOL | JOSE DALMAN (PONOT) | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4288486.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303680 | DINASAN NATIONAL HIGH SCHOOL | JOSE DALMAN (PONOT) | 2 |  | 4 | 1STY4CL | BATCH 4 | 4288486.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124325 | Diongan ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124333 | Manawan ES | JOSE DALMAN (PONOT) | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303709 | Manawan National High School | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303709 | Manawan National High School | JOSE DALMAN (PONOT) | 2 |  | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314112 | Bulawan Integrated School | KATIPUNAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314112 | Bulawan Integrated School | KATIPUNAN | 2 |  | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303697 | Katipunan NHS Annex - Basagan | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303697 | Katipunan NHS Annex - Basagan | KATIPUNAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303702 | Katipunan NHS Annex - Sitog | KATIPUNAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303702 | Katipunan NHS Annex - Sitog | KATIPUNAN | 2 |  | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303701 | Katipunan NHS -Sinuyak Annex | KATIPUNAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 314120 | Balas National High School | LABASON | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124421 | Malintuboan ES | LABASON | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3803631 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124423 | Osukan ES | LABASON | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124463 | Baybay Central School | LILOY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 |  | 2 | 1STY2CL | BATCH 4 | 2631533.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124521 | Bartolome Aripal ES | MANUKAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303681 | Bartolome Aripal Memorial NHS | MANUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314102 | Don Jose Aguirre NHS | MANUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303711 | Manukan NHS - Serongan Annex | MANUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303679 | Dilawa NHS | PIÑAN (NEW PIÑAN) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2894915 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124559 | Napuyan ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3053767.81 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3031687.4 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124580 | San Antonio ES | POLANCO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2783398 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303725 | San Pedro National High School | POLANCO | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2782398 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 314123 | Lipakan NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195555 | Malicas Elementary School | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4288486.85 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 |  | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124505 | Situbo ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2484241.98 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124491 | Tantingon ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124634 | Ramon Magsaysay ES | SALUG | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2692914.79 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124639 | Biayon ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3015079.22 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124659 | Lebote ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2866898.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124662 | Mahayahay ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2866898.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124663 | Nazareth ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2866898.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124669 | San Antonio ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2866898.2 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3125122.31 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314126 | Sergio Osmena NHS Ext. - Marapong | SERGIO OSMEÑA SR. | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5322120 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314126 | Sergio Osmena NHS Ext. - Marapong | SERGIO OSMEÑA SR. | 1 |  | 4 | 1STY4CL | BATCH 4 | 5322120 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124655 | Venus ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 2841898.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124679 | Diongan Elementary School | SIAYAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124681 | Dumoyog ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124685 | Guigang ES | SIAYAN | 2 | 1 | 4 | 1STY4CL | BATCH 4 | 4360716.61 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124689 | Macasing ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303733 | Mangilay NHS | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124693 | Muñoz ES | SIAYAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124694 | Pange ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124703 | Suminogod ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124705 | Tulohon ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303736 | Sibuco NHS Annex - Pangian | SIBUCO | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2714567.93 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124754 | Apolonio Molina ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303678 | Bartolome Lira, Sr. NHS | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314117 | Bartolome C. Lira, Sr. NHS Ext. - Siasin | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124789 | Bucana ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124791 | Calubian ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195513 | Dipodog ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303683 | Dumalogdog National High School | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195536 | Maras East ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124805 | Mawal ES | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303741 | Sta. Maria NHS | SIOCON | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3875212.99 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124838 | Doña Cecilia ES | SIRAWAI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2741689.16 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124841 | Mauricio V. Landingin Memorial ES | SIRAWAI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2674418.53 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124844 | Sirawai CS | SIRAWAI | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2738204.94 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303744 | Sirawai NHS Annex - Piacan | SIRAWAI | 3 | 1 | 3 | 1STY3CL | BATCH 4 | 3900412.99 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2703090.72 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303748 | Tampilisan NHS Annex - Situbo | TAMPILISAN | 3 | 1 | 2 | 1STY2CL | BATCH 4 | 2722001.68 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124338 | Tabon ES | JOSE DALMAN (PONOT) | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4288486.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124338 | Tabon ES | JOSE DALMAN (PONOT) | 2 |  | 3 | 1STY3CL | BATCH 7 | 3781044.29 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303727 | Seres NHS | KATIPUNAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124303 | Sinuyak National High School | Katipunan | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124396 | Taga Central School | Katipunan | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124396 | Taga Central School | Katipunan | 2 |  | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124465 | Canaan ES | LILOY | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2706533.61 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124529 | Meses Elementary School | Manukan | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124535 | Delampinas ES | MUTIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2796533.37 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 314119 | Mutia National High School Extension - Alvenda | MUTIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2818398 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303714 | Mutia NHS Annex - Tubak | MUTIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2818398 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124541 | New Siquijor ES | MUTIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2827398 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124545 | Totongon ES | MUTIA | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2810398 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124552 | Daan Tipan ES | PIÑAN (NEW PIÑAN) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2886889 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124588 | Lapayanbaja ES | POLANCO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2819392.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124589 | Letapan ES | POLANCO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2944642 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2953499.9 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124502 | Ma. Adaza ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124637 | Antonino ES | SERGIO OSMEÑA SR. | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2974507 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303723 | San Isidro NHS | SERGIO OSMEÑA SR. | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4509186.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124674 | Balok ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124674 | Balok ES | SIAYAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124675 | Balonokan ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124684 | Guibo ES | SIAYAN | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4360716.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124684 | Guibo ES | SIAYAN | 2 |  | 4 | 1STY4CL | BATCH 7 | 4360716.61 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124686 | Gunyan Elementary School | Siayan | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124686 | Gunyan Elementary School | Siayan | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124692 | Moyo ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124692 | Moyo ES | SIAYAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124696 | Pase ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124696 | Pase ES | SIAYAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124702 | Suminalum ES | SIAYAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 123704 | Tague Elementary School | Siayan | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124711 | Cawit-Cawit ES | SIBUCO | 3 | 1 | 2 | 1STY2CL | BATCH 7 | 2717249.96 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2465635.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3324501 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195535 | Sindangan Special Education Center | SINDANGAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2540635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124779 | Laparo Elementary School | Sindangan | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 4288486.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Del Norte | 124797 | Upper Inuman Elementary School | Sindangan | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124328 | Lipay ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124335 | Ponot CS | JOSE DALMAN (PONOT) | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12067462.46 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 | 1 | 16 | 4STY16CL | BATCH 10 | 38924018.3 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303719 | Ponot NHS | JOSE DALMAN (PONOT) | 2 |  | 6 | 3STY6CL | BATCH 10 | 15765110.24 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124339 | Tamarok ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124360 | Banbanan ES | KATIPUNAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124360 | Banbanan ES | KATIPUNAN | 2 |  | 3 | 1STY3CL | BATCH 10 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124365 | Danao ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195505 | Dr. Jose Rizal ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2540635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124366 | Fimagas ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124379 | Guisokan ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2465635.35 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195522 | Gulapa PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124368 | Jose Ochotorena ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2465635.35 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 30189578.31 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303696 | Katipunan National High School | KATIPUNAN | 2 |  | 6 | 3STY6CL | BATCH 10 | 15710361.66 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195542 | Katipunan SPED Center | KATIPUNAN | 2 | 1 | 3 | 1STY3CL | BATCH 10 | 3781044.29 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124370 | Kitonok PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2520357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124371 | Macayas ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195523 | Sapa Naga ES | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195530 | Sapa Ralum PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 195531 | Sulot Sumayong PS | KATIPUNAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2520357.76 |  |  | Reverted | 0
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4391922.44 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4057134.73 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4057134.73 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124510 | Manukan East CS | MANUKAN | 2 | 1 | 16 | 2 units 2STY8CL | BATCH 10 | 34753618.78 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 30189578.31 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303710 | Manukan NHS | MANUKAN | 2 |  | 8 | 2STY8CL | BATCH 10 | 17256809.39 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124519 | Suisayan ES | MANUKAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2520357.76 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4354262.7 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 3994080.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4109753.61 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4109755.61 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4362447.8 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4009500.75 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303716 | Polanco NHS | POLANCO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4036918.06 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4360660.08 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124493 | Balubohan ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2595357.76 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 | 1 | 8 | 2STY8CL | BATCH 10 | 17256809.39 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 |  | 16 | 4STY16CL | BATCH 10 | 38836261.52 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 |  | 6 | 3STY6CL | BATCH 10 | 15710361.66 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303705 | Langatian NHS | PRES. MANUEL A. ROXAS | 2 |  | 8 | 2 units 2STY4CL | BATCH 10 | 19267875.04 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124489 | Sibatog ES | PRES. MANUEL A. ROXAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2540635.35 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga del Norte | 303720 | Rizal National High School | RIZAL | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 4380397.19 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124772 | Bago ES | SINDANGAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9633937.52 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124783 | Motibot ES | SINDANGAN | 2 | 1 | 6 | 2STY6CL | BATCH 10 | 12112462.46 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124783 | Motibot ES | SINDANGAN | 2 |  | 4 | 2STY4CL | BATCH 10 | 9633937.52 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | 4 | 2STY4CL | BATCH 10 | 9633937.52 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 |  | 12 | 3STY12CL | BATCH 10 | 30189578.31 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 |  | 8 | 2STY8CL | BATCH 10 | 17256809.39 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOO | SINDANGAN | 2 |  | 12 | 3STY12CL | BATCH 10 | 30339578.31 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303738 | SINDANGAN NATIONAL AGRICULTURAL SCHOOL | SINDANGAN | 2 | 1 | 24 | 2 units 3STY12CL | BATCH 10 | 60379156.62 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 | 1 | 12 | 3STY12CL | BATCH 10 | 30189578.31 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga del Norte | 303739 | Sindangan National High School | SINDANGAN | 2 |  | 8 | 2STY8CL | BATCH 10 | 17256809.39 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 303729 | Siari John H. Roemer NHS | SINDANGAN | 2 | 1 | 8 | 2STY8CL | BATCH 13 | 17256809.39 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del Norte | 124610 | Rizal CS | RIZAL | 1 | 1 | 10 | 2STY10CL | BATCH 14 | 20420689.31 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga del sur | 124963 | Dongos ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2728788.13 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124979 | Sagacad ES | DINAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3109566.58 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124981 | San Isidro ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2728734.41 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 196039 | Pinig Elementary School | DUMALINAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3350687.07 |  |  | COMPLETED | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125058 | Tamurayan ES | Dumingag | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 5863681.53 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303784 | Kumalarang NHS | KUMALARANG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2803959.86 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303784 | Kumalarang NHS | KUMALARANG | 2 |  | 2 | 1STY2CL | BATCH 4 | 2803959.86 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303784 | Kumalarang NHS | KUMALARANG | 2 |  | 2 | 1STY2CL | BATCH 4 | 2803959.86 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303784 | Kumalarang NHS | KUMALARANG | 2 |  | 4 | 1STY4CL | BATCH 4 | 4643157.79 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125119 | Langapod ES | Labangan | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3272000 |  |  | Completed | 1 | [9 empty] | M.S. CONST. MARKETING
NC 2017 | K10 | Region IX | Zamboanga del sur | 125137 | Baking ES | LAKE WOOD | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3457162.59 |  |  | COMPLETED | 1 | [9 empty] | RUDHIL CONST. & ENT., INC
NC 2017 | K10 | Region IX | Zamboanga del sur | 125139 | Biswangan ES | LAKE WOOD | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2731502.42 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125139 | Biswangan ES | LAKE WOOD | 2 |  | 2 | 1STY2CL | BATCH 4 | 2731502.42 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125140 | Dagum ES | LAKE WOOD | 1 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 4 | 5066328.83 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del sur | 314249 | Poblacion Comprehensive NHS | LAKE WOOD | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3599267.01 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125149 | Tiwales ES | LAKE WOOD | 1 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3415514.15 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125149 | Tiwales ES | LAKE WOOD | 1 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3415514.15 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 314229 | Lapuyan NHS - Tiguha Ext. Class | LAPUYAN | 1 | 1 | 4 | 1STY4CL | BATCH 4 | 4427884.31 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125162 | Mala-Tiguha ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2742607.81 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 314224 | Balintawak NHS | MARGOSA TUBIG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3284432.46 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 314224 | Balintawak NHS | MARGOSA TUBIG | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3284432.46 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125228 | Tulapok ES | MARGOSA TUBIG | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 3106355.01 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125236 | Cumarom ES | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3173610.83 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MDSE.
NC 2017 | SHS | Region IX | Zamboanga del Sur | 314222 | Golictop National High School | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3215377.18 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125242 | Guinabot Elementary School | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3127745.74 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MDSE.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125243 | Guitalos ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3210402.04 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MDSE.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125245 | Kahayagan ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3156681.66 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125248 | Matalang ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3176120.09 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125254 | Pili ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3259139.04 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MDSE.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125255 | Pisompongan ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3171143.83 |  |  | Completed | 1 | [9 empty] | CRF CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125261 | Tuluan Elem. School | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3041477.89 |  |  | Completed | 1 | [9 empty] | FJ CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125274 | Anatalio T. Lobitana Elem.School-(formerly Sudlon ES | MOLAVE | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3172000 |  |  | Completed | 1 | [9 empty] | PRELI DELES CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125311 | Campo IV ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 2 | 1STY2CL | BATCH 4 | 3215192.53 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2017 | K10 | Region IX | Zamboanga del sur | 125340 | Langilan Elementary School | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2901669.8 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2817590.54 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3610038.68 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 4 | 3457362.74 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303753 | Antonio NHS | TIGBAO | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3681688.22 |  |  | Completed | 1 | [9 empty] | MJMARI BUILDERS & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 314241 | Libayoy NHS | TIGBAO | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 4 | 5462013.09 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303765 | Cogon NHS | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2729488.03 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST. & ENT., INC.
NC 2017 | K10 | Region IX | Zamboanga del sur | 124907 | Balukbahan ES | BAYOG | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 7 | 5171579.91 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124967 | San Miguel ES | DIMATALING | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 7 | 4439100 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Legarda Dos ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3228073.04 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Legarda Dos ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3228073.04 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Legarda Dos ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3228073.04 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Legarda Dos ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3228073.04 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124983 | Sumilom PS | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3259689.35 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124983 | Sumilom PS | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3259690.35 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Upper Sibul ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3244986.58 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Upper Sibul ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3244987.58 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Upper Sibul ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3244988.58 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124987 | Upper Sibul ES | DINAS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3244989.58 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124997 | Dumalinao RPS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2687603.12 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 124997 | Dumalinao RPS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2687603.12 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 124997 | Dumalinao RPS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2687603.12 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125011 | Sumadat ES | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2876081.15 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125011 | Sumadat ES | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 7 | 2876081.15 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125011 | Sumadat ES | DUMALINAO | 2 |  | 3 | 1STY3CL | BATCH 7 | 3557806.79 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125017 | Bag-ong Silang ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3483018.76 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125036 | Canibongan ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3226184.45 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125038 | Danlugan ES | Dumingag | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4739615.78 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125040 | Dilud ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3377417.85 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125021 | Dulop ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3115490.94 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 314253 | Dulop NHS - Labangon Extension | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3115490.94 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | SHS | Region IX | Zamboanga del Sur | 314234 | Dulop NHS Bag-ong Valencia Extension | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3106070.92 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125045 | La Fortuna ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3450461.55 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125025 | Labangon ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3107173.18 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125046 | Licabang ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3391513.84 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125049 | Macasing ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3455899.18 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 196031 | Paliran ES | DUMINGAG | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4630046.99 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125054 | Saad ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3187050.81 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125033 | San Vicente ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3344072.14 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 196033 | Sinatalan ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3178699.89 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125055 | Sinonok Elementary School | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3479099.73 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 196037 | Sumibang IES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3191576.83 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125056 | Sunop ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3329779.36 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125057 | Tagun ES | Dumingag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3166022.56 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125063 | Canunan ES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2997810.18 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125063 | Canunan ES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2997810.18 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125063 | Canunan ES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2997810.18 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2984470.1 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2984470.1 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2984470.1 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2984470.1 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3202520.63 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 2984470.1 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125068 | Guipos CES | GUIPOS | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3202520.63 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125079 | Ebarle Integrated ES | Josefina | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3262532.44 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125093 | Boyugan East ES | KUMALARANG | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3414249.06 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125093 | Boyugan East ES | KUMALARANG | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3414249.06 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125111 | Balimbingan ES | Labangan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3140000 |  |  | Completed | 1 | [9 empty] | SJ BONIFACIO BUILDERS
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125488 | Datu Ampanas ES | Tukuran | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3145000 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125115 | Dimasangca ES | Labangan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3140000 |  |  | Completed | 1 | [9 empty] | FJ CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125115 | Dimasangca ES | Labangan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3140000 |  |  | Completed | 1 | [9 empty] | FJ CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125124 | Sang-an ES | Labangan | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3145000 |  |  | Completed | 1 | [9 empty] | SJ BONIFACIO BUILDERS
NC 2017 | K10 | Region IX | Zamboanga del sur | 125136 | Bag-ong Kahayag ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3307932.97 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125136 | Bag-ong Kahayag ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3307933.97 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125136 | Bag-ong Kahayag ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3307934.97 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125143 | Lakewood CES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3305706.34 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125143 | Lakewood CES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3305707.34 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125150 | Tubod ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3269766.96 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125150 | Tubod ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3269767.96 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125150 | Tubod ES | LAKEWOOD | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3269768.96 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125151 | Bulawan ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3233259.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125151 | Bulawan ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3233260.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125151 | Bulawan ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3233261.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125151 | Bulawan ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3233262.12 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125156 | Karpok ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3048932.22 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125156 | Karpok ES | LAPUYAN | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3048932.22 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125181 | Guripan ES | Mahayag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3140000 |  |  | Completed | 1 | [9 empty] | GENETIAN BUILDERS
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125182 | Kaangayan ES | MAHAYAG | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3156500 |  |  | Completed | 1 | [9 empty] | GCMG CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125201 | Kabuhi ES | Mahayag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3156500 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 314244 | Paraiso NHS | Mahayag | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3175000 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125233 | Cabaluran ES | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3201519.23 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125237 | Dakayakan IES | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3219052.42 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125239 | Dumalinao ES | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2953222.745 |  |  | Completed | 1 | [9 empty] | GENETIAN BUILDERS
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125239 | Dumalinao ES | Midsalip | 1 |  | 2 | 1STY2CL | BATCH 7 | 2953222.745 |  |  | Completed | 1 | [9 empty] | GENETIAN BUILDERS
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125240 | Ecuan ES | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3211556.27 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | SHS | Region IX | Zamboanga del Sur | 303766 | Golictop NHS | Midsalip | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3197126.63 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125244 | Guma ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3035421.09 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST.& GEN. MSDE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125246 | Licuro-an Elementary School | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3179080.62 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Sur | 314243 | Matalang NHS | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3185925.66 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125250 | New Katipunan ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3146976.64 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125251 | New Unidos IPS | MIDSALIP | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4541523.79 |  |  | Completed | 1 | [9 empty] | L.C. CONST. CORP.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125252 | Palili ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3198254.16 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125256 | Piwan ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3154124.23 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125257 | Sapa Butong PS | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3209565.59 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125258 | Sigapod ES | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3150239.76 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125260 | Tulbong PS | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3169987 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125330 | Sapa Anding ES | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3108203.88 |  |  | Completed | 1 | [9 empty] | LMD CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125348 | San Miguel CES | SAN MIGUEL | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3020370.51 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125348 | San Miguel CES | SAN MIGUEL | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3020370.51 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125348 | San Miguel CES | SAN MIGUEL | 2 |  | 2 | 1STY2CL w/ TOILET | BATCH 7 | 3020370.51 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125380 | Barubuhan ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3112918.14 |  |  | Completed | 1 | [9 empty] | L.C. CONST. CORP.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125383 | Lantawan ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3152651.28 |  |  | Completed | 1 | [9 empty] | L.C. CONST. CORP.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125443 | Tambulig CES | TAMBULIG | 1 | 1 | 3 | 1STY3CL | BATCH 7 | 4922000 |  |  | Completed | 1 | [9 empty] | PRESLI DELES CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 124909 | Bantal ES | 125209 | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3414658.61 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124910 | Bayog CES | BAYOG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3125279.9 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 196035 | Bayog CES SPED | BAYOG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3125279.9 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303760 | Bobuan NHS | BAYOG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2846678.51 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124914 | Conacon ES | BAYOG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3004603.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124915 | Dagum IPS | BAYOG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3326637.49 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 124916 | Damit ES | BAYOG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3250242.75 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124917 | Datagan ES | BAYOG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3184838.7 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124920 | Deporehan ES | BAYOG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3858639.92 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124921 | Dimalinao ES | BAYOG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3478077.14 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124922 | Dipili ES | BAYOG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3478077.14 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124923 | Kahayagan ES | BAYOG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3215207.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124928 | Matin - ao Elementary School | BAYOG | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4752209.09 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124933 | Sigacad ES | BAYOG | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 5206954.89 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124933 | Sigacad ES | BAYOG | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3332945.68 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 196006 | Upper Paya CPS | BAYOG | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 5388773.27 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 124950 | Binuay ES | DIMATALING | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3047242.97 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124962 | Don Jose ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2836725.54 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 124964 | East Migpulao ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2728889.24 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | TVL | Region IX | Zamboanga del sur | 303777 | Guinicolalay NHS | DINAS | 2 | 1 | 2 | 1STY2CL SCIENCE LAB | BATCH 10 | 2739726.63 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303777 | Guinicolalay NHS | DINAS | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2739726.63 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303777 | Guinocolalay NHS | DINAS | 2 |  | 2 | 1STY2CL | BATCH 10 | 2763215.452 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 314205 | Ignacio Garrata NHS | DINAS | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3116143.02 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303790 | Legarda Dos NHS | DINAS | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3307136.81 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124975 | Nian ES | DINAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3073650.53 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | SHS | Region IX | Zamboanga del sur | 303807 | Proper Dimaya NHS | DINAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3163033.29 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 124980 | Sambulawan ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2718905.76 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 196040 | Simuyak ES | DINAS | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3066609.6 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 124982 | Songayan ES | DINAS | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2719901.11 |  |  | Completed | 1 | [9 empty] | ST JOSEPH CONST. & TRADING
NC 2017 | SHS | Region IX | Zamboanga del sur | 314217 | Bibilik NHS | DUMALINAO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3851640.51 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | SHS | Region IX | Zamboanga del sur | 314217 | Bibilik NHS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 3851640.51 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | TVL | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 10 | 3064569.92 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | TVL | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.2) | BATCH 10 | 3064569.92 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | TVL | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.3) | BATCH 10 | 3064569.92 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | TVL | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.4) | BATCH 10 | 3064569.92 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | TVL | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 10 | 2792952.36 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | SHS | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 2749136.89 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | SHS | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 2749136.89 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | SHS | Region IX | Zamboanga del sur | 303774 | Dumalinao NHS | DUMALINAO | 2 |  | 2 | 1STY2CL | BATCH 10 | 2749136.89 |  |  | Completed | 1 | [9 empty] | M&L CONST. & ENT
NC 2017 | K10 | Region IX | Zamboanga del sur | 125062 | Balongating ES | GUIPOS | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2989466.36 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303756 | Balongating NHS | GUIPOS | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 2989466.36 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 314129 | Sikatuna NHS | GUIPOS | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 4515493.63 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125091 | Bogayo ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3003951.69 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125092 | Bolisong ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3414500 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST. & TRADING
NC 2017 | K10 | Region IX | Zamboanga del sur | 125094 | Boyugan West ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3214863.84 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125096 | Diplo ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2757256.33 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125097 | Gawil ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3434348.12 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125099 | Kitaan Dagat ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3287556.79 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | SHS | Region IX | Zamboanga del sur | 303795 | Maestro Cornelio s. Minor NHS | KUMALARANG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2829342.88 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125104 | Mapao CPS | KUMALARANG | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3314500.75 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 303785 | Picanan ES | KUMALARANG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2835149.82 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125146 | Pegampuan ES | LAKE WOOD | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 4388486.65 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125148 | Sibuguey ES | LAKE WOOD | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3177450.59 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del sur | 303755 | Bag-ong Kahayag NHS | LAKEWOOD | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3148265.07 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 314216 | Bulawan NHS | LAPUYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2727211.38 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 314216 | Bulawan NHS | LAPUYAN | 2 |  | 2 | 1STY2CL | BATCH 10 | 2727211.38 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125165 | Maruing ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3269257.94 |  |  | Reverted | 0
NC 2017 | SHS | Region IX | Zamboanga del sur | 303789 | Maruing NHS | LAPUYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3163131.89 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125166 | Molum ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2739904.58 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125169 | Pingalay ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3722087.44 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125172 | Sayog ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3135805.9 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125173 | Tabon ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3214102.41 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125212 | Bularong ES | MARGOSA TUBIG | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3023703.02 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125215 | Igat ES | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3044803.1 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125217 | Kalian ES | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3124201.55 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125222 | Lumbog ES | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3115886 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125224 | Margosatubig RPS | MARGOSATUBIG | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3233093.57 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125300 | Panubigan ES | PITOGO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3285115.57 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125301 | Pitogo CES | PITOGO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3283846.93 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125302 | Punta Flecha ES | PITOGO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3308084.37 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125304 | Sugbay Dos ES | PITOGO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3269994.66 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125333 | Betinan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 3235705.09 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125337 | Dao-an ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3174798.26 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 314240 | Fatima NHS | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2919254.6 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125341 | Lantawan ES | SAN MIGUEL | 2 | 1 | 3 | 1STY3CL W/ TOILET | BATCH 10 | 3849603.55 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125344 | Limonan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3186794.66 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST. & GEN. MDSE
NC 2017 | K10 | Region IX | Zamboanga del sur | 125346 | Ocapan ES | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3377603.92 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125351 | Bag - ong Misamis ES | SAN PABLO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2889046.2 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125355 | Digos ES | SAN PABLO | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2879141.32 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125371 | San Pablo CES | SAN PABLO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3283620.64 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125376 | Ticala ES | SAN PABLO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3727720.8 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125376 | Ticala ES | SAN PABLO | 2 |  | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3727720.8 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125398 | Baganian ES | TABINA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3306437.24 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125402 | Culabay ES | TABINA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3284254.96 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125406 | Malim ES | TABINA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3306877.28 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125415 | Tabina CES | TABINA | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3285574.7 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125449 | Begong ES | TIGBAO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3358383.05 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125450 | Busol ES | TIGBAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3382457.66 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125458 | Longmot ES | TIGBAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 2816286.64 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125460 | Mate ES | TIGBAO | 2 | 1 | 4 | 1STY4CL W/ TOILET | BATCH 10 | 6940240.77 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125464 | Tigbao CES | TIGBAO | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3285574.7 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 196043 | Upper Mate Elementary school | TIGBAO | 2 | 1 | 2 | 1STY2CL W/ TOILET | BATCH 10 | 3316255.77 |  |  | Reverted | 0
NC 2017 | K10 | Region IX | Zamboanga del sur | 125497 | Danan ES | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3160969.05 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 | 1 | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | WORKSHOPS | BATCH 10 | 3069812.09 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 10 | 2827672.42 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303781 | Judge Edmundo Pinga NHS | VINCENZO A. SAGUN | 2 |  | 2 | 1STY2CL | BATCH 10 | 2713831.27 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125498 | Kapatagan ES | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 10 | 3178203.52 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125499 | Limason ES | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL | BATCH 10 | 2730513.4 |  |  | Completed | 1 | [9 empty] | PINS CONST. & ENT.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303757 | Bayog NHS | BAYOG | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2906275.73 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303757 | Bayog NHS | BAYOG | 2 |  | 2 | 1STY2CL | BATCH 13 | 2906275.73 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303757 | Bayog NHS | BAYOG | 2 |  | 1 | TVL | BATCH 13 | 3084573.13 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 2956536.04 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2783006.72 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2783006.72 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2763006.72 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 2 | TVL (Bldg.1) | BATCH 13 | 3068560.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303770 | Dimataling NHS | DIMATALING | 2 |  | 2 | TVL (Bldg.2) | BATCH 13 | 3068560.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 | 1 | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2854093.88 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303764 | Laureano Salusod NHS | DIMATALING | 2 |  | 1 | TVL | BATCH 13 | 3052910.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303771 | Dinas NHS | DINAS | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 2906690.89 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303771 | Dinas NHS | DINAS | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2906690.89 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303771 | Dinas NHS | DINAS | 2 |  | 1 | TVL | BATCH 13 | 3063740.12 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3064639.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3064639.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3064639.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3064639.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303808 | Rebokon AVHS | DUMALINAO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga del sur | 125011 | Sumadat ES | DUMALINAO | 2 | 1 | 3 | 1STY3CL | BATCH 13 | 3557806.79 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303778 | Guipos NHS | GUIPOS | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3048513.99 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303778 | Guipos NHS | GUIPOS | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3048513.99 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303778 | Guipos NHS | GUIPOS | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3048513.99 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303778 | Guipos NHS | GUIPOS | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3048513.99 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303778 | Guipos NHS | GUIPOS | 2 |  | 1 | TVL (Bldg.5) | BATCH 13 | 3048513.99 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125100 | Kumalarang CES | KUMALARANG | 2 | 1 | 2 | 1STY2CL w/ Toilet | BATCH 13 | 3208295.19 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST. & ENT. , INC.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST. & ENT. , INC.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.5) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.6) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 1 | TVL (Bldg.7) | BATCH 13 | 3067049.92 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303788 | Lapuyan NHS | LAPUYAN | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2805653.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 314229 | Lapuyan NHS-Tiguha Ext. | LAPUYAN | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2948255.96 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303783 | Kalian NHS | MARGOSA TUBIG | 2 | 1 | 2 | WORKSHOPS | BATCH 13 | 3066614.78 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303783 | Kalian NHS | MARGOSA TUBIG | 2 |  | 2 | WORKSHOPS | BATCH 13 | 3066614.78 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303783 | Kalian NHS | MARGOSA TUBIG | 2 |  | 2 | WORKSHOPS | BATCH 13 | 3066614.78 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303822 | Toribio Minor NHS | MARGOSA TUBIG | 2 | 1 | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2800819.7 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303822 | Toribio Minor NHS | MARGOSA TUBIG | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2800819.7 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303822 | Toribio Minor NHS | MARGOSA TUBIG | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2800819.7 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303822 | Toribio Minor NHS | MARGOSA TUBIG | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2800819.7 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3069987.17 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3069987.17 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3069987.17 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3069987.17 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2799427.24 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2799427.24 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2799427.24 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303804 | Paulino Dari NHS | PITOGO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2799427.24 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303791 | Betinan NHS | SAN MIGUEL | 2 | 1 | 2 | 1STY2CL | BATCH 13 | 2800077.78 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303791 | Betinan NHS | SAN MIGUEL | 2 |  | 2 | 1STY2CL | BATCH 13 | 3115246.66 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303791 | Betinan NHS | SAN MIGUEL | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2802981.89 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303791 | Betinan NHS | SAN MIGUEL | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2802981.89 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3064877.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3064877.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3064877.21 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2966777.04 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2966777.04 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2966777.04 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303776 | Eugenia Andrin NHS | SAN PABLO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2966777.04 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3068482.85 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3068482.85 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3068482.85 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2815657.55 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2815657.55 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303813 | San Pablo NHS | SAN PABLO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2815657.55 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3072115.32 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3072115.32 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2834130.05 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2834130.05 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2834130.05 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303754 | Baganian NHS | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2834130.05 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 303767 | Conception NHS | TABINA | 2 | 1 | 2 | 1STY2CL w/ Toilet | BATCH 13 | 3307136.81 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3002196.62 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3002196.62 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3002196.62 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 1 | TVL (Bldg.1) | BATCH 13 | 3059072.13 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3508144.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3508144.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3508144.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 1 | TVL (Bldg.5) | BATCH 13 | 3508144.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2835837.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2835837.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2835837.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303769 | Culabay NHS | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2835837.26 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125403 | Dona Josefina ES | TABINA | 2 | 1 | 2 | 1STY2CL w/ Toilet | BATCH 13 | 3307570.13 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 | 1 | 1 | TVL (Bldg.1) | BATCH 13 | 3070835.37 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 1 | TVL (Bldg.2) | BATCH 13 | 3070835.37 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 1 | TVL (Bldg.3) | BATCH 13 | 3070835.37 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 1 | TVL (Bldg.4) | BATCH 13 | 3070835.37 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2836520.48 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2836520.48 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2836520.48 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303768 | Tabina National High School | TABINA | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2836520.48 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 314241 | Libayoy NHS | TIGBAO | 2 | 1 | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 3109088.02 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 314241 | Libayoy NHS | TIGBAO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 3109088.02 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga del Sur | 125463 | Nilo ES | TIGBAO | 2 | 1 | 2 | 1STY2CL w/ Toilet | BATCH 13 | 3130004.25 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 | 1 | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3127962.8 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3127962.8 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | UNIQUE WORKSHOP (7x22.5) | BATCH 13 | 3127962.8 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2832104.69 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | 1STY2CL SCIENCE LAB | BATCH 13 | 2832104.69 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2832104.69 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | TVL | Region IX | Zamboanga del sur | 303800 | Nilo NHS | TIGBAO | 2 |  | 2 | 1STY2CL ICT BLDG. | BATCH 13 | 2832104.69 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | TIGBAO | 2 | 1 | 2 | 1STY2CL w/ Toilet | BATCH 13 | 2991243.47 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | SHS | Region IX | Zamboanga del sur | 303782 | Kabatan National High School | VINCENZO A. SAGUN | 2 | 1 | 2 | 1STY2CL w/ TOILET | BATCH 13 | 3387044.89 |  |  | Completed | 1 | [9 empty] | EDISON DEV'T. & CONST.
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125513 | Concepcion ES | ALICIA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4163469.12 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125518 | Kapatagan ES | ALICIA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2771268.9 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125560 | San Jose ES | BUUG | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2875732.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125575 | Mahayahay ES | DIPLAHAN | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4149958.65 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125607 | Sta. Barbara ES | IMELDA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2875732.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125685 | Basakbawang ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2732231.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125691 | Del Pilar ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2732231.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125700 | Molom ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2732231.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125706 | Sinusayan ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2732231.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125707 | Tackling ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2732231.77 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125736 | Galas ES | OLUTANGA | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4238021.68 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | OLUTANGA | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2823515.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125756 | Calape ES | PAYAO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2862981.45 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 314301 | Dalama NHS | PAYAO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4211495.73 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125760 | Guintolan ES | PAYAO | 1 | 1 | 2 | 1STY2CL | BATCH 2 | 2875732.85 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125778 | Upper Sumilong ES | PAYAO | 1 | 1 | 3 | 1STY3CL | BATCH 2 | 4363150.59 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 303839 | Kabasalan NHS | KABASALAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3968435.02 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 303839 | Kabasalan NHS | KABASALAN | 2 |  | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 314321 | Palinta NHS | KABASALAN | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3843435.02 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 314321 | Palinta NHS | KABASALAN | 2 |  | 3 | 1STY3CL | BATCH 4 | 3843435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314320 | Baga National High School | NAGA | 2 | 1 | 3 | 1STY3CL | BATCH 4 | 3968435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 303868 | San Fernandino NHS | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314319 | Sto. Rosario NHS | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2788745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314319 | Sto. Rosario NHS | ROSELLER LIM | 2 |  | 2 | 1STY2CL | BATCH 4 | 2788745.92 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 314304 | Sisay NHS | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 4 | 2713745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 3001529.57 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303824 | Alicia National High School | ALICIA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2984097.2717 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2844240.4043 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2833025.065 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2856592.825 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125614 | Don Andres ES | IPIL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314313 | Magdaup NHS | IPIL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314322 | Taway NHS | IPIL | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3818435.05 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125631 | Tiayon ES | IPIL | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125631 | Tiayon ES | IPIL | 2 |  | 2 | 1STY2CL | BATCH 7 | 2638745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125640 | Diampak ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 3013745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125647 | Little Baguio ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125653 | Salupan PS | KABASALAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125654 | Sanghanan ES | KABASALAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125654 | Sanghanan ES | KABASALAN | 2 |  | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125664 | Timuay Danda ES | KABASALAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303852 | Mabuhay NHS | MABUHAY | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2973172.435 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303852 | Mabuhay NHS | MABUHAY | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2973172.435 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125675 | Pamansaan PS | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 3000276.34 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125677 | San Roque ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2823515.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125678 | Sawa ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2823515.2 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125680 | Sto. Nino ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2907484.8 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125682 | Tandu-Comot ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 7 | 2907484.8 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303845 | Malangas National High School | MALANGAS | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2866955.174 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303845 | Malangas National High School | MALANGAS | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2866955.174 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303845 | Malangas National High School | MALANGAS | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2866955.174 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303845 | Malangas National High School | MALANGAS | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2866955.174 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303845 | Malangas National High School | MALANGAS | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2866955.174 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125710 | Baga ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125711 | Baluno ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125712 | Bangkaw-Bangkaw ES | NAGA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125712 | Bangkaw-Bangkaw ES | NAGA | 2 |  | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125714 | Capt. Pedro Changco Sr. Mem. Elem.Sch. | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125715 | Crossing Sta. Clara ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125717 | Hipolito B. Marcelo Sr. Mem. Elem. Sch. | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2637236.955 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125717 | Hipolito B. Marcelo Sr. Mem. Elem. Sch. | NAGA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2637236.955 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125720 | Mamagon ES | NAGA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3843435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125720 | Mamagon ES | NAGA | 2 |  | 3 | 1STY3CL | BATCH 7 | 3843435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125722 | Pisaan ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125723 | San Isidro ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2737236.955 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125723 | San Isidro ES | NAGA | 2 |  | 2 | 1STY2CL | BATCH 7 | 2737236.955 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125724 | Sandayong ES | NAGA | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.05 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125727 | Tambanan ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | OLUTANGA | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3025369.95 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | OLUTANGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3025369.95 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | OLUTANGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3025369.95 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303851 | Olutanga National High School | OLUTANGA | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3025369.95 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 | 1 | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2997312.9267 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2997312.9267 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | UNIQUE WORKSHOP (7x22.5) | BATCH 7 | 2997312.9267 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3096495.094 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3096495.094 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3096495.094 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3096495.094 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303836 | Guintolan NHS | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3096495.094 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | PAYAO | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3248840.146 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3248840.146 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3248840.146 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3248840.146 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303856 | Payao National High School | PAYAO | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 3248840.146 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125782 | Butalian ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125785 | Fatima ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2863745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125793 | Motop Elementary School | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125794 | New Antique ES | ROSELLER LIM | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 4018435.05 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 196508 | Pinili ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2913745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125804 | Surabay CES | ROSELLER LIM | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.05 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125809 | Tupilac ES | ROSELLER LIM | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125810 | Z-Gold (Hose) Elementary School | ROSELLER LIM | 2 | 1 | 4 | 1STY4CL | BATCH 7 | 5188351.15 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314316 | Camanga National High School | SIAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2738745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314316 | Camanga National High School | SIAY | 2 |  | 2 | 1STY2CL | BATCH 7 | 2738745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125824 | Lagting ES | SIAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 303865 | Monching NHS | SIAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125835 | Salinding ES | SIAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125835 | Salinding ES | SIAY | 2 |  | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 | 1 | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | TVL | Region IX | Zamboanga Sibugay | 303870 | Talusan National High School | TALUSAN | 1 |  | 1 | WORKSHOP BLDG (7x18) | BATCH 7 | 2944009.0167 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 196525 | Cose Abdudan Elementary Schooll | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125865 | Kipit ES | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 314324 | Kitabog NHS | TITAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3918435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 303873 | Malagandis NHS | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125873 | Namnama ES | TITAY | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3818435.05 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125874 | New Canaan ES | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125875 | Palomoc ES | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2763745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125882 | Titay CES | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125885 | Tugop Muslim ES | TITAY | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2813745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125887 | Batungan ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2663745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125897 | Malungon ES | TUNGAWAN | 2 | 1 | 3 | 1STY3CL | BATCH 7 | 3868435.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125900 | San Vicente ES | TUNGAWAN | 2 | 1 | 2 | 1STY2CL | BATCH 7 | 2713745.92 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125710 | Baga ES | NAGA | 2 | 1 | 2 | 2STY6CL | BATCH 14 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125790 | Mabuhay Elementary School | ROSELLER LIM | 2 | 1 | 2 | 2STY6CL | BATCH 14 | 11706168.02 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125804 | Surabay CES | ROSELLER LIM | 2 | 1 | 16 | 2 UNITS 2STY8CL | BATCH 14 | 34049580.52 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 125882 | Titay CES | TITAY | 2 | 1 | 20 | 2 UNITS 2STY10CL | BATCH 14 | 39666311.34 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 303853 | Palomoc NHS | TITAY | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 17074790.26 |  |  | Completed | 1
NC 2017 | K10 | Region IX | Zamboanga Sibugay | 303865 | Monching NHS | SIAY | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 17074790.26 |  |  | Completed | 1
NC 2017 | SHS | Region IX | Zamboanga Sibugay | 303875 | San Isidro NHS | TUNGAWAN | 2 | 1 | 8 | 2STY8CL | BATCH 14 | 17224790.26 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Dapitan City | 125949 | Potungan CS | Dapitan City | 1 | 1 | 4 | 1STY4CL | Batch 3 | 4876065.77 |  |  | COMPLETED | 1
NC 2018 | K10 | Region IX | Dapitan City | 125951 | San Nicolas ES | Dapitan City | 1 | 1 | 4 | 1STY4CL | Batch 3 | 4876727.8 |  |  | COMPLETED | 1
NC 2018 | K10 | Region IX | Dapitan City | 125953 | Aliguay ES | Dapitan City | 1 | 1 | 4 | 1STY4CL | Batch 3 | 5396812.43 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Dapitan City | 303878 | Baylimango NHS (Selinog Ext) | Dapitan City | 1 | 1 | 4 | 1STY4CL | Batch 3 | 5409123.13 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Dipolog City | 125963 | Estaka Central School | DIPOLOG CITY (Capital) | 2 | 1 | 9 | 3STY9CL | BATCH 1 | 25451544.66 |  |  | COMPLETED | 1 |  |  | P00271256MN-CW1
NC 2018 | K10 | Region IX | Dipolog City | 125980 | Biasong ES | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9662893.7 |  |  | COMPLETED | 1 |  |  | P00271257MN-CW1
NC 2018 | SHS | Region IX | Dipolog City | 303886 | Cogon NHS | DIPOLOG CITY (Capital) | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9662893.7 |  |  | COMPLETED | 1 |  |  | P00271258MN-CW1
NC 2018 | K10 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 1 | 38323888.94 |  |  | Completed | 1 |  |  | POO27159MN | 18JH0037 | 2018-06-27 | 2018-07-05 | 2018-07-17 |  | 2018-07-17 | FFJJ Construction
NC 2018 | K10 | Region IX | Isabela City | 126001 | Isabela East Central Elementary School | CITY OF ISABELA (Capital) | 0 |  | 6 | 2STY6CL | BATCH 1 | 12068739.31 |  |  | Completed | 1 |  |  | POO27160MN | 18JH0038 | 2018-06-06 | 2018-06-18 | 2018-06-28 |  | 2018-08-06 | ASAP General Trading Construction & Maintenance
NC 2018 | SHS | Region IX | Isabela City | 303895 | MALAMAWI NATIONAL HIGH SCHOOL | CITY OF ISABELA (Capital) | 0 | 1 | 15 | 3STY15CL | BATCH 1 | 38537888.94 |  |  | Completed | 1 |  |  | POO27161MN | 18JH0039 | 2018-05-29 | 2018-06-07 | 2018-06-19 |  | 2018-07-17 | C.B.GarayPhilwide Builders
NC 2018 | K10 | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3150000 |  |  | Completed | 1 |  |  | P00271262MN-CW1 | 18JE0185 | 2018-08-03 |  | 2018-08-03 | 2018-08-20 | 2018-09-03 | GENETIAN BUILDERS
NC 2018 | K10 | Region IX | Pagadian City | 126054 | Tawagan Sur ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3150000 |  |  | Completed | 1 |  |  | P00271263MN-CW1 | 18JE0186 | 2018-08-09 |  | 2018-08-09 | 2018-08-30 | 2018-09-13 | L.C. CONST. & CORP.
NC 2018 | K10 | Region IX | Pagadian City | 126057 | White Beach ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3210500 |  |  | Completed | 1 |  |  | P00271264MN-CW1 | 18JE0187 | 2018-09-04 |  | 2018-09-04 | 2018-09-26 | 2018-10-10 | SAIMAN CONST. DEV.
NC 2018 | K10 | Region IX | Pagadian City | 126064 | Lenienza ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3150000 |  |  | Completed | 1 |  |  | P00271265MN-CW1 | 18JE0188 | 2018-08-09 |  | 2018-08-09 | 2018-08-30 | 2018-09-13 | LMD CONST.
NC 2018 | K10 | Region IX | Pagadian City | 126078 | Poloyagan ES | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3150000 |  |  | Completed | 1 |  |  | P00271266MN-CW1 | 18JE0189 | 2018-08-09 |  | 2018-08-09 | 2018-08-30 | 2018-09-13 | LMD CONST.
NC 2018 | K10 | Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3114200 |  |  | Completed | 1 |  |  | P00271268MN-CW1 | 18JE0191 | 2018-07-17 |  | 2018-07-17 | 2018-07-30 | 2018-08-15 | RAMONA CONST. & ENT.
NC 2018 | K10 | Region IX | Pagadian City | 198502 | Rotary Inner Wheel Village Elementary School | PAGADIAN CITY (Capital) | 1 |  | 2 | 1STY2CL | BATCH 1 | 3147000 |  |  | Completed | 1 |  |  | P00271267MN-CW1 | 18JE0190 | 2018-08-03 |  | 2018-08-03 | 2018-08-20 | 2018-09-03 | RAMONA CONST. & ENT.
NC 2018 | TVL | Region IX | Pagadian City | 303913 | ZAMBOANGA DEL SUR SCHOOL OF ARTS AND TRADES | PAGADIAN CITY (Capital) | 1 | 1 | 11 | 3STY4LABS W/ 7CL | Batch 3 | 37022633.66 |  |  | Completed | 1 |  |  | P00274195MN-CW1 | 18JE0247 | 2018-12-04 |  | 2018-12-04 | 2018-12-10 | 2018-12-21 | RAMONA CONST. & ENT.
NC 2018 | K10 | Region IX | Zamboanga City | 126106 | Tulungatung ES | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12756156.06 |  |  | Completed | 1 |  |  | P00271269MN-CW1 | 18JA0116 |  |  |  |  | 2018-08-18 | PM CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126136 | Cadalagan ES | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12846566.87 |  |  | Completed | 1 |  |  | P00271270MN-CW1 | 18JA0117 |  |  |  |  | 2018-08-17 | KLC BUILDERS
NC 2018 | K10 | Region IX | Zamboanga City | 126149 | Sinubong ES | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12859347.15 |  |  | COMPLETED | 1 |  |  | P00271271MN-CW1 | 18JA0118 |  |  |  |  | 2018-08-17 | BDA CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126260 | Canelar ES | ZAMBOANGA CITY | 1 | 1 | 15 | 3STY15CL | BATCH 1 | 38296410.54 |  |  | Completed | 1 |  |  | P00271272MN-CW1 | 18JA0119 |  |  |  |  | 2018-08-17 | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | K10 | Region IX | Zamboanga City | 126170 | Sangali ES | ZAMBOANGA CITY | 2 | 1 | 20 | 4STY20CL | BATCH 1 | 46155724.97 |  |  | Completed | 1 |  |  | P00271273MN-CW1 | 18JA0120 |  |  |  |  | 2018-08-17 | GHR CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126190 | Mulu-Muluan ES | ZAMBOANGA CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 34348634.08 |  |  | Completed | 1 |  |  | P00271274MN-CW1 | 18JA0121 |  |  |  |  | 2018-08-17 | RUDHIL CONSTRUCTION & ENTERPRISES
NC 2018 | K10 | Region IX | Zamboanga City | 126223 | Arena Blanco East ES | ZAMBOANGA CITY | 2 | 1 | 6 | 3STY6CL | BATCH 1 | 15655028.64 |  |  | Completed | 1 |  |  | P00271275MN-CW1 | 18JA0122 |  |  |  |  | 2018-08-17 | ABSOLUTE ENGINEERING AND SUPPLIES
NC 2018 | K10 | Region IX | Zamboanga City | 126224 | Arena Blanco West ES | ZAMBOANGA CITY | 2 | 1 | 12 | 3STY12CL | BATCH 1 | 32359568.79 |  |  | Completed | 1 |  |  | P00271276MN-CW1 | 18JA0123 |  |  |  |  | 2018-08-18 | LONG ISLAND BUILDERS & CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126233 | Davuy ES | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13521266.26 |  |  | Completed | 1 |  |  | P00271277MN-CW1 | 18JA0124 |  |  |  |  | 2018-08-16 | ROAD EDGE TRADING & DEVELOPMENT
NC 2018 | K10 | Region IX | Zamboanga City | 126244 | Sibulao ES | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 13497982.15 |  |  | Completed | 1 |  |  | P00271278MN-CW1 | 18JA0125 |  |  |  |  | 2018-08-16 | ROAD EDGE TRADING & DEVELOPMENT
NC 2018 | K10 | Region IX | Zamboanga City | 199006 | Zamboanga Central School Sped Center | ZAMBOANGA CITY | 1 | 1 | 20 | 4STY20CL | Batch 3 | 55249117.72 |  |  | COMPLETED | 1 |  |  |  | 18JA0137 |  |  |  |  | 2019-01-16 | DAWING/ASAP GENERAL CONSTRUCTION & MAINTENANCE
NC 2018 | K10 | Region IX | Zamboanga City | 126177 | Victoria ES | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12212544.6 |  |  | COMPLETED | 1 |  |  |  | 18JA0140 |  |  |  |  | 2018-07-12 | FOOTPRINT CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126188 | Lumbayao ES | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 11716985.63 |  |  | Completed | 1 |  |  |  | 18JA0139 |  |  |  |  | 2018-07-12 | 2M CONSTRUCTION
NC 2018 | SHS | Region IX | Zamboanga City | 314802 | Lubigan NHS, Curuan Annex | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL | Batch 3 | 12923828 |  |  | COMPLETED | 1 |  |  |  | 18JA0123 |  |  |  |  | 2018-07-12 | BDA CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126114 | Southern Support Command ES | ZAMBOANGA CITY | 1 | 1 | 6 | 2STY6CL | Batch 5 | 12785974.22 |  |  | COMPLETED | 1 |  |  |  | 18JA0145 |  |  |  |  | 2019-01-14 | AEJ CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 | 1 | 9 | 3STY9CL | Batch 5 | 32526419.83 |  |  | COMPLETED | 1 |  |  |  | 18JA0146 |  |  |  |  | 2019-01-14 | ST. JOSEPH CONSTRUCTION
NC 2018 | K10 | Region IX | Zamboanga City | 126140 | Labuan CS | ZAMBOANGA CITY | 1 |  | 6 | 3STY6CL | Batch 5 | 20179751.63 |  |  | COMPLETED | 1 |  |  |  | 18JA0147 |  |  |  |  | 2019-11-01 | PM CONSTRUCTION
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 | 1 | 6 | 3STY6CL REGULAR WORKSHOP | BATCH 1 | 14366874.41 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303704 | La Libertad NHS | LA LIBERTAD | 1 |  | 4 | 2STY4CL RE.GULAR WORKSHOP | BATCH 1 | 9743021.86 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 303713 | Mutia NHS | MUTIA | 1 | 1 | 12 | 3 UNITS 2STY4CL | BATCH 1 | 29463948.05 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 |  | 6 | 3STY6CL SCI LAB & ICT | BATCH 1 | 14781990.33 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 303715 | Pinan National High School | PIÑAN (NEW PIÑAN) | 1 | 1 | 12 | 2STY12CL | BATCH 1 | 23453005.89 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303718 | Silawe NHS | POLANCO | 1 | 1 | 8 | 2STY4CL REGULAR WORKSHOP | BATCH 1 | 9791233.06 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303720 | Rizal National High School | RIZAL | 1 | 1 | 8 | 2STY8CL SCI LAB & ICT | BATCH 1 | 18611616.16 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303720 | Rizal National High School | RIZAL | 1 |  | 8 | 2 UNITS 2STY4CL REGULAR WORSHOP | BATCH 1 | 19424600.32 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 | 1 | 12 | 3STY12CL REGULAR WORKSHOP | BATCH 1 | 29080892.09 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303728 | Sergio Osmena NHS | SERGIO OSMEÑA SR. | 1 |  | 8 | 2STY8CL SCI LAB & ICT | BATCH 1 | 19027462.53 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303737 | Sibutad National High School | SIBUTAD | 1 | 1 | 12 | 2STY12CL REGULAR WORKSHOP | BATCH 1 | 24881260.11 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | 4 | 2STY4CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 16188866.98 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16328587.67 |  |  | Completed | 1 |  |  | P00271291MN-CW1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36381104.58 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303672 | Bacungan NHS | BACUNGAN (LEON T. POSTIGO) | 3 |  | 4 | 2STY4CL SCILAB & ICT COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303675 | Tinuyop National High school | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36804200.79 |  |  | COMPLETED | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303675 | Tinuyop National High school | BACUNGAN (LEON T. POSTIGO) | 3 |  | 4 | 2STY4CL SCILAB & ICT COMBINED w/ TOILET | BATCH 1 | 16306368.08 |  |  | COMPLETED | 1 |  |  | P00271294MN-CW1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 | 1 | 6 | 3STY6CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 29594088.48 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 |  | 4 | 2STY4CL SCILAB & ICT COMBINED w/ TOILET | BATCH 1 | 16785340.01 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303684 | GODOD NATIONAL HIGH SCHOOL | GODOD | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 37001867.28 |  |  | COMPLETED | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303684 | GODOD NATIONAL HIGH SCHOOL | GODOD | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16458125 |  |  | COMPLETED | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36983198.77 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303686 | Gutalac NHS | GUTALAC | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16458125 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 | 1 | 4 | 2STY4CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 16844920.74 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16972400.99 |  |  | Completed | 1 |  |  | P00271302MN-CW1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36870089 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16427501.5 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36381104.58 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3 | 1 | 12 | 2 UNITS 3STY6CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 56572221.92 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303706 | Liloy National High School | LILOY | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 | 1 | 4 | 2STY4CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 16119092.77 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303734 | Sibuco National High School | SIBUCO | 3 | 1 | 6 | 3STY6CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 29567914.43 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303734 | Sibuco National High School | SIBUCO | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 17385210.62 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 38407715.28 |  |  | COMPLETED | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303740 | Siocon National High School | SIOCON | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16972400.99 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | 6 | 3STY6CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 30341820.63 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 17151093.07 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303743 | Dacon National High School (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16968335.01 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 | 1 | 6 | 3STY6CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 28482100.17 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303745 | Tampilisan NHS | TAMPILISAN | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 | 1 | 8 | 4STY8CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 36381104.58 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 303750 | Ubay NHS | LABASON | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 314120 | Balas National High School | LABASON | 3 | 1 | 4 | 2STY4CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 16119092.77 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 314120 | Balas National High School | LABASON | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16240425.52 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | 4 | 2STY4CL REGULAR WORKSHOP w/ TOILET | BATCH 1 | 16425115.81 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 |  | 4 | 2STY4CL WORKSHOP COMBINED w/ TOILET | BATCH 1 | 16549063.66 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga del Norte | 124770 | Sindangan Pilot Demonstration School | SINDANGAN | 2 | 1 | 15 | 3STY15CL | Batch 3 | 35295115.67 |  |  | COMPLETED | 1
NC 2018 | K10 | Region IX | Zamboanga del Norte | 124784 | Siari P. Escabarte ES | SINDANGAN | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10106201.88 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 303727 | Seres NHS | KATIPUNAN | 2 | 1 | 8 | 2 UNITS 2STY4CL | Batch 3 | 19868215.04 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 303732 | Gunyan NHS | SIAYAN | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17933481.34 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 303739 | Sindangan NHS | Sinandigan | 2 | 1 | 8 | 2STY8CL | Batch 3 | 17994656.33 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 | 1 | 4 | 2STY4CL | Batch 3 | 10106201.88 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga del Norte | 314103 | Moliton National High School | PRES. MANUEL A. ROXAS | 2 |  | 12 | 2 UNITS 3STY6CL | Batch 3 | 32068089.72 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124868 | Aurora Reg'L Pilot School Regular | AURORA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 9583296.69 |  |  | Completed | 1 | [9 empty] | FJ CONST.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124875 | Inasagan ES | AURORA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3180000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124896 | Lantungan ES | AURORA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3180000 |  |  | Completed | 1 | [9 empty] | L.C. CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125031 | Salvador ES | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3159241.87 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125037 | Caridad ES | DUMINGAG | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 7379792.42 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125041 | Ditulan ES | DUMINGAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 9606399.08 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125044 | Guitran CES | DUMINGAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 9560322.86 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125050 | Mahayahay ES | DUMINGAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 9462873.06 |  |  | Completed | 1 | [9 empty] | MJ MARI BUILDERS & ENT.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125052 | Maralag ES | DUMINGAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 9465078.44 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125117 | Glab ES | LABANGAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3245750 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125121 | New Labangan Primary School | LABANGAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3114200 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125183 | Lactayan ES | MAHAYAG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3140000 |  |  | Completed | 1 | [9 empty] | MJ MARI BUILDERS & ENT.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125185 | Mahayag CES | MAHAYAG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 7354340.3 |  |  | Completed | 1 | [9 empty] | GENETIAN BUILDERS
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125246 | Licuro-an PS | MIDSALIP | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3179050.62 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125274 | Anatalio T. Lobitana Elem.School-(formerly Sudlon ES | MOLAVE | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3172000 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125287 | Silangit ES | MOLAVE | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3319750 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125389 | Rizal ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3114824.45 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125424 | Baluran ES | TAMBULIG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3282000 |  |  | Completed | 1 | [9 empty] | PRESLI DELES CONST.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125488 | Datu Ampanas ES | TUKURAN | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3180000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 196036 | Panuguton PS | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3131894.75 |  |  | Completed | 1 | [9 empty] | NRMM CONST & DEVT CORP
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303766 | Commonwealth NHS | AURORA | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 3134000 |  |  | Completed | 1 | [9 empty] | LC CONST & CORP
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303773 | Dumingag National High School | DUMINGAG | 1 | 1 | 4 | 2STY4LABS | BATCH 1 | 13382969.01 |  |  | Completed | 1 | [9 empty] | NRMM CONST.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303780 | Aurora National High School | AURORA | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 3145000 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303792 | Leonardo NHS | JOSEFINA | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 3134000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 6366000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT.
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 |  | 6 | 3STY6CL | BATCH 1 | 10104431.53 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1 | 1 | 4 | 2STY4LABS | BATCH 1 | 26067705.69 |  |  | Completed | 1 | [9 empty] | GENETIAN BUILDERS
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303799 | New Labangan NHS | LABANGAN | 1 |  | 1 | WORKSHOP BLDG. | BATCH 1 | 3091375 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303803 | Mahayag School of Arts and Trade (Mahayag NHS) | MAHAYAG | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 3145000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303815 | Simata NHS | MOLAVE | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3319750 |  |  | Completed | 1 | [9 empty] | MJ BUILDERS
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303819 | Tambulig NHS | TAMBULIG | 1 | 1 | 1 | WORKSHOP BLDG. | BATCH 1 | 3091375 |  |  | Completed | 1 | [9 empty] | PRESLI DELES CONST.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 314203 | Boniao National High School | MAHAYAG | 1 | 1 | 4 | 2STY4LABS | BATCH 1 | 12879199.33 |  |  | Completed | 1 | [9 empty] | RUDHIL CONST.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 314203 | Boniao National High School | MAHAYAG | 1 |  | 1 | WORKSHOP BLDG. | BATCH 1 | 3145000 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT
NC 2018 | SHS | Region IX | Zamboanga del Sur | 314204 | Sumalig NHS | TAMBULIG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3180000 |  |  | Completed | 1 | [9 empty] | PRESLI DELES CONST.
NC 2018 | TVL | Region IX | Zamboanga del Sur | 314228 | Sapa Anding National High School - Ramon Magsaysay Extension | RAMON MAGSAYSAY (LIARGO) | 1 | 1 | 4 | 2STY4LABS | BATCH 1 | 13253912.2 |  |  | Completed | 1 | [9 empty] | RAMONA CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125059 | Upper Landing Indigenous Peoples School | DUMINGAG | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 3224688.59 |  |  | Completed | 1 | [9 empty] | RAMONA CONST. & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124965 | Guinicolalay ES | DINAS | 2 | 1 | 6 | 6CL W/ TOILET | BATCH 1 | 6152195.14 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125348 | San Miguel CES | SAN MIGUEL | 2 | 1 | 2 | 2CL W/ TOILET (BLDG. 1) | BATCH 1 | 2932754.89 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303769 | Culabay NHS | TABINA | 2 | 1 | 12 | 4STY12CL | BATCH 1 | 31688799.72 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303770 | Dimataling NHS | DIMATALING | 2 | 1 | 10 | 2STY10CL | BATCH 1 | 19958155.67 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303774 | Dumalinao NHS | DUMALINAO | 2 | 1 | 16 | 4STY16CL | BATCH 1 | 37064739.9 |  |  | Completed | 1 | [9 empty] | JIMWEN CONST & GEN. MDSE
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125140 | Dagum ES | LAKEWOOD | 1 | 1 | 3 | 3CL w/ TOILET | Batch 3 | 5066328.83 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | TVL | Region IX | Zamboanga del Sur | 303797 | Molave Vocational Technical School | MOLAVE | 1 | 1 | 4 | 4STY4LABS | Batch 3 | 18875527.74 |  |  | Completed | 1 |  |  | Not included in their report. To confirm | [6 empty] | RAMONA CONST & ENT.
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124915 | Dagum Elementary School | BAYOG | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3326637.49 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124933 | Sigacad ES | BAYOG | 2 | 1 | 3 | 3CL w/ TOILET | Batch 3 | 5206954.89 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 124981 | San Isidro ES | DINAS | 2 | 1 | 2 | 2CL | Batch 3 | 2728734.41 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125104 | Mapao CPS | KUMALARANG | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3314500.75 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125146 | Pegampuan ES | LAKEWOOD | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 4388486.65 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125148 | Sibuguey ES | LAKEWOOD | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3177450.59 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125156 | Karpok Elementary School | LAPUYAN | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3048932.22 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125165 | Maruing ES | LAPUYAN | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3269257.94 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125169 | Pingalay ES | LAPUYAN | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3722087.44 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125173 | Tabon ES | LAPUYAN | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3214102.41 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125215 | Igat ES | MARGOSATUBIG | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3044803.19 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125351 | Bag-ong Misamis ES | SAN PABLO | 2 | 1 | 2 | 2CL | Batch 3 | 2889046.2 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125355 | Digos ES | SAN PABLO | 2 | 1 | 2 | 2CL | Batch 3 | 2879141.32 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125450 | Busol ES | TIGBAO | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3382457.66 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 125460 | Mate ES | TIGBAO | 2 | 1 | 4 | 4CL w/ TOILET | Batch 3 | 6940240.77 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | K10 | Region IX | Zamboanga del Sur | 196006 | Upper Paya CP | BAYOG | 2 | 1 | 3 | 3CL w/ TOILET | Batch 3 | 5388773.27 |  |  | Completed | 1 | [9 empty] | LUCKY SAVER CONST
NC 2018 | K10 | Region IX | Zamboanga del Sur | 196043 | Upper Mate Elementary School | TIGBAO | 2 | 1 | 2 | 2CL w/ TOILET | Batch 3 | 3316255.77 |  |  | Completed | 1 | [9 empty] | VANNEMAR CONST & ENT
NC 2018 | SHS | Region IX | Zamboanga del Sur | 303770 | Dimataling National High School | DIMATALING | 2 | 1 | 10 | 2STY10CL | Batch 3 | 19958155.47 |  |  | Completed | 1 | [9 empty] | PINS CONST.
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125514 | Dawa-Dawa ES | ALICIA | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12084548.35 |  |  | Completed | 1 |  |  |  | 18JI0093
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125516 | Ilisan ES | ALICIA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2756749.52 |  |  | Completed | 1 |  |  |  | 18JI0094
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125526 | Milagrosa ES | ALICIA | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2774403.37 |  |  | Completed | 1 |  |  |  | 18JI0098
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125537 | Timbang-Timbang ES | ALICIA | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9306065.24 |  |  | Completed | 1 |  |  |  | 18JI0089
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125553 | Mabuhay ES | BUUG | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9241390.18 |  |  | Completed | 1 |  |  |  | 18JI0091
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125579 | Natan ES | DIPLAHAN | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 12001329.85 |  |  | Completed | 1 |  |  |  | 18JI0092
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125665 | Abunda ES | MABUHAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9771707.71 |  |  | Completed | 1 |  |  |  | 18JI0085
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125670 | Kauswagan ES | MABUHAY | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2853646.82 |  |  | Completed | 1 |  |  |  | 18JI0097
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125673 | Mabuhay CES | MABUHAY | 1 | 1 | 12 | 2STY12CL | BATCH 1 | 23999417.1 |  |  | Completed | 1 |  |  |  | 18JI0086
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125674 | Malinao ES | MABUHAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9672029.8 |  |  | Completed | 1 |  |  |  | 18JI0087
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125681 | Taguisian ES | MABUHAY | 1 | 1 | 4 | 2STY4CL | BATCH 1 | 9816055.75 |  |  | Completed | 1 |  |  |  | 18JI0088
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125699 | Malongon ES | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2713488.62 |  |  | Completed | 1 |  |  |  | 18JI0095
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125708 | Tigabon PS | MALANGAS | 1 | 1 | 2 | 1STY2CL | BATCH 1 | 2724671.21 |  |  | Completed | 1 |  |  |  | 18JI0096
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 196521 | Buug Central SPED Center | BUUG | 1 | 1 | 6 | 2STY6CL | BATCH 1 | 11949239.33 |  |  | Completed | 1 |  |  |  | 18JI0090
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125615 | Doña Josefa ES | IPIL | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 12056174.02 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125618 | Ipil Heights ES | IPIL | 2 | 1 | 20 | 2 UNITS 2STY10CL | BATCH 1 | 40016331.34 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125635 | Buayan ES | KABASALAN | 2 | 1 | 6 | 2STY6CL | BATCH 1 | 11906168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125651 | Peñaranda ES | KABASALAN | 2 | 1 | 4 | 2STY4CL | BATCH 1 | 9395903.76 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 196523 | Goling ES | NAGA | 2 | 1 | 2 | 1STY2CL | BATCH 1 | 2913745.92 |  |  | Completed | 1
NC 2018 | SHS | Region IX | Zamboanga Sibugay | 314323 | Sta. Fe NHS | TITAY | 2 | 1 | 3 | 1STY3CL | BATCH 1 | 3968435.02 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan NHS | DIPLAHAN | 1 | 1 | 2 | 2STY SCI LAB | Batch 3 | 9226287.98 |  |  | Completed | 1 |  |  |  | 18JI0129
NC 2018 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug NHS | BUUG | 1 | 1 | 2 | 2STY SCI LAB | Batch 3 | 9357712.64 |  |  | Completed | 1
NC 2018 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 | 1 | 2 | 2STY ICT LAB | Batch 3 | 9508902.65 |  |  | Completed | 1 |  |  |  | 18JI0131
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125634 | Upper Pangi ES | IPIL | 2 | 1 | 2 | 1STY2CL | Batch 3 | 2963745.92 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125817 | Camanga ES | SIAY | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3063745.92 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125840 | Upper Balagon ES | SIAY | 2 | 1 | 2 | 1STY2CL | Batch 3 | 3063745.92 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 125899 | San Isidro ES | TUNGAWAN | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4318435.02 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 196519 | Ipil Special Education Center | IPIL | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12406168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 314326 | Langon NHS | TUNGAWAN | 2 | 1 | 6 | 2STY6CL | Batch 3 | 12556168.02 |  |  | Completed | 1
NC 2018 | K10 | Region IX | Zamboanga Sibugay | 330533 | Sandayong NHS | NAGA | 2 | 1 | 3 | 1STY3CL | Batch 3 | 4318435.02 |  |  | Completed | 1
NC 2019 | K10 | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Dipolog City | 125976 | Sta. Filomena ES | Dipolog City | 2 | 1 | 9 | 3STY9CL |  | 25203542.1561 |  | Completed | 1 | [11 empty] | 0
NC 2019 | TVL | Region IX | Isabela City | 198004 | Ajibon ES | CITY OF ISABELA (Capital) | 0 | 1 | 2 | 2STY2LAB |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Pagadian City | 126056 | Tulawas ES | PAGADIAN CITY (Capital) | 1 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga City | 126145 | Pamucutan ES | ZAMBOANGA CITY | 1 | 1 | 4 | 2STY4CL |  | 11445595.9032 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga City | 126223 | Arena Blanco East ES | ZAMBOANGA CITY | 2 | 1 | 6 | 3STY6CL |  | 14743773.6654 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga City | 126197 | Boalan ES | ZAMBOANGA CITY | 2 | 1 | 20 | 2UNITS 2STY10CL |  | 55532309.5926 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga City | 126189 | Mercedes CS | ZAMBOANGA CITY | 2 | 1 | 20 | 4STY20CL |  | 52046376.9036 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga City | 126169 | Poso ES | ZAMBOANGA CITY | 2 | 1 | 6 | 2STY6CL |  | 16242649.0993 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Norte | 124575 | Lingasad ES | POLANCO | 1 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Norte | 124531 | San Antonio ES | MANUKAN | 2 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 314254 | Baclay Ext. TTVHS | TUKURAN | 1 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 124893 | Commonwealth CS with SPED Classes | AURORA | 1 | 1 | 10 | 2STY10CL |  | 24144478.3893 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 124895 | La Victoria PS | AURORA | 1 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur |  | Lower Bayao ES | TUKURAN | 1 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur |  | Tagulo ES | TUKURAN | 1 | 1 | 2 | 1STY2CL |  | 4117214.7284 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 124978 | Proper Dimaya ES | DINAS | 2 | 1 | 4 | 2STY4CL |  | 10674931.3765 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 314251 | San Pablo NHS - Sacbulan Extension | SAN PABLO | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 3384182.2472 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga del Sur | 125173 | Tabon ES | LAPUYAN | 2 | 1 | 2 | 1STY2CL W/ TOILET |  | 3222137.666 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IX | Zamboanga Sibugay | 303829 | Buug National High School | BUUG | 1 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IX | Zamboanga Sibugay | 303828 | Diplahan National High School | DIPLAHAN | 1 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2019 | K10 | Region IX | Zamboanga Sibugay | 125654 | Sanghanan ES | KABASALAN | 2 | 1 | 4 | 1STY4CL |  | 8234429.4568 |  | Completed | 1 | [11 empty] | 0
NC 2019 | SHS | Region IX | Zamboanga Sibugay | 303854 | Zamboanga Sibugay NHS | IPIL | 2 | 1 | 4 | 2STY4CL |  | 13616957.5 |  | Completed | 1 | [11 empty] | 0
NC 2020 | K10 | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1 | 1 | 8 | 2STY8CL |  | 21078060.72 |  |  | COMPLETED | 1 | [10 empty] | No Certificate of Completion
NC 2020 | SHS | Region IX | Dapitan City | 303884 | Sulangon NHS- Aliguay Ext. | Dapitan City | 1 | 1 | 4 | 1STY4CL |  | 9624000 |  |  | COMPLETED | 1
NC 2020 | SHS | Region IX | Dipolog City | 303888 | GALAS NHS | Dipolog City | 2 | 1 | 4 | 2STY4CL |  | 11380855.44 |  |  | Completed | 1 | [10 empty] | delayed due to school campus utilization as covid10 isolation site
NC 2020 | K10 | Region IX | Isabela City | 126002 | ISABELA CENTRAL PILOT ES | ISABELA CITY(Capital) | 0 | 1 | 6 | 3STY6CL |  | 20050000 |  |  | Completed | 1
NC 2020 | K10 | Region IX | Pagadian City | 126060 | Bulatok ES | PAGADIAN CITY (Capital) | 1 | 1 | 4 | 2STY4CL |  | 12531250 |  |  | Completed | 1
NC 2020 | SHS | Region IX | Zamboanga City | 345869 | ZNHS West-Baliwasan Senior High School | ZAMBOANGA CITY | 1 | 1 | 12 | 4STY12CL |  | 27568750 |  |  | COMPLETED | 1
NC 2020 | K10 | Region IX | Zamboanga City | 126201 | Lumbangan ES | ZAMBOANGA CITY | 2 | 1 | 4 | 2STY4CL |  | 12832000 |  |  | COMPLETED | 1
NC 2020 | K10 | Region IX | Zamboanga City | 126225 | Guiwan ES | ZAMBOANGA CITY | 2 | 1 | 8 | 4STY8CL |  | 32581250 |  |  | Completed | 1
NC 2020 | K10 | Region IX | Zamboanga del Norte | 124540 | Mutia CS | MUTIA | 1 | 1 | 5 | 1STY - 5CL with attached toilet |  | 10025000 |  |  | COMPLETED | 1 | [9 empty] | RUDHIL CONST
NC 2020 | K10 | Region IX | Zamboanga del Norte | 124374 | Mias ES | KATIPUNAN | 2 | 1 | 5 | 1STY - 5CL with attached toilet |  | 10592239.56 |  |  | COMPLETED | 1 | [9 empty] | RUDHIL CONST
NC 2020 | K10 | Region IX | Zamboanga del Norte | 124495 | Dohinob CS | PRES. MANUEL A. ROXAS | 2 | 1 | 3 | 1 STY 3 CL with attached toilet |  | 6566375 |  |  | COMPLETED | 1 | [9 empty] | NRMM CONST
NC 2020 | K10 | Region IX | Zamboanga del Norte | 124309 | Canupong ES | GUTALAC | 3 | 1 | 2 | 1 STY - 2 CL without toilet |  | 3789450 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST
NC 2020 | K10 | Region IX | Zamboanga del Norte | 124428 | Bacungan CS | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 4 | 2STY4CL |  | 9624000 |  |  | Completed | 1 | [9 empty] | ST. JOSEPH CONST
NC 2020 | SHS | Region IX | Zamboanga del Norte | 303685 | Raba National High School | GODOD | 3 | 1 | 2 | 1 STY - 2 CL without toilet |  | 3789450 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST
NC 2020 | SHS | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS - Lupoc Ext. | LABASON | 3 | 1 | 6 | 2STY6CL |  | 14436000 |  |  | COMPLETED | 1 | [9 empty] | ST. JOSEPH CONST
NC 2020 | K10 | Region IX | Zamboanga del Sur | 196022 | Dumingag SPED Center | DUMINGAG | 1 | 1 | 6 | 2STY6CL |  | 16774346.96 |  |  | COMPLETED | 1
NC 2020 | SHS | Region IX | Zamboanga del Sur | 303786 | Lantungan NHS | AURORA | 1 | 1 | 4 | 2STY4CL |  | 12743412.56 |  |  | COMPLETED | 1
NC 2020 | K10 | Region IX | Zamboanga del Sur | 125008 | Rebokon ES | DUMALINAO | 2 | 1 | 6 | 2STY6CL |  | 17953772.5 |  |  | COMPLETED | 1
NC 2020 | K10 | Region IX | Zamboanga Sibugay | 125564 | Balangao ES | DIPLAHAN | 1 | 1 | 6 | 2STY6CL |  | 17543750 |  |  | Terminated | 0 | [10 empty] | DPWH REQUESTED FOR CONTRACT TERMINATION
NC 2020 | K10 | Region IX | Zamboanga Sibugay | 125571 | Kauswagan ES | DIPLAHAN | 1 | 1 | 3 | 1STY3CL |  | 5012500 |  |  | COMPLETED | 1
NC 2020 | K10 | Region IX | Zamboanga Sibugay | 125628 | Pangi ES | IPIL | 2 | 1 | 8 | 2STY8CL |  | 22761710.88 |  |  | COMPLETED | 1
NC 2021 | K10 | Region IX | Dapitan City | 125949 | Potungan CS | Dapitan City | 1 | 1 | 4 | Construction/Completion (1STY4CL) |  | 1860720.8717 | 1856080.67 | 1836020 | Completed | 1 | [7 empty] | 2021-09-08 | 2021-09-16 | Westmin Ent. & Const. Services
NC 2021 | K10 | Region IX | Dapitan City | 125951 | San Nicolas ES | Dapitan City | 1 | 1 | 4 | Construction/Completion (1STY4CL) |  | 1867919.4533 | 1863261.3 | 1848261.3 | Completed | 1 | [7 empty] | 2021-09-08 | 2021-09-16 | Animas Bros. Const.
NC 2021 | K10 | Region IX | Dapitan City | 125953 | Aliguay ES | Dapitan City | 1 | 1 | 4 | Construction/Completion (1STY4CL) |  | 2292156.8519 | 2286440.75 | 2276477.1 | COMPLETED | 1 | [7 empty] | 2021-09-08 | 2021-09-16 | Montphil Contruction Corp.
NC 2021 | K10 | Region IX | Dapitan City | 125960 | Sicayab ES | DAPITAN CITY | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1656767.5699 | 1652635.98 | 1643619.31 | COMPLETED | 1 | [7 empty] | 2021-09-08 | 2021-09-16 | G. Baron Const.
NC 2021 | SHS | Region IX | Dapitan City | 303878 | Baylimango NHS (Selinog Ext) | Dapitan City | 1 | 1 | 4 | Construction/Completion (1STY4CL) |  | 2142522.7294 | 2137179.78 | 21121794.84 | COMPLETED | 1 | [7 empty] | 2021-09-08 | 2021-09-20 | BTM Const. & Ent
NC 2021 | SHS | Region IX | Dipolog City | 303887 | Dipolog City NHS (Barra) | DIPOLOG CITY (Capital) | 2 | 1 | 4 | Construction/Completion (2STY4CL) |  | 6015000 | 6000000 |  | Completed | 1 | [10 empty] | Delayed due to site finalization
NC 2021 | SHS | Region IX | Isabela City | 303894 | Basilan NHS | City of Isabela | 0 | 1 | 60 | Construction/Completion (4STY20CL) |  | 19142808.2364 | 19095070.56 |  | Completed | 1 | [10 empty] | physically completed but not yet turned over to DepEd for booking up
NC 2021 | TVL | Region IX | Pagadian City | 303913 | Zamboanga del sur school of Arts & Trades | Pagadian City | 1 | 1 | 15 | Construction/Completion (3STY15CL ( 3sty 4 Laboratory with 7 Classroom)) |  | 13777406.5924 | 13743048.97 |  | Completed | 1
NC 2021 | K10 | Region IX | Zamboanga City | 126110 | JOHN SPIRIG S. MES | ZAMBOANGA CITY | 1 | 1 | 40 | Construction/Completion (4STY20CL) |  | 1612658.2516 | 1608636.66 |  | Completed | 1
NC 2021 | K10 | Region IX | Zamboanga City | 126114 | Southern Support Command ES | ZAMBOANGA CITY | 1 | 1 | 6 | Construction/Completion (2STY6CL) |  | 2563587.8271 | 2557194.84 |  | Completed | 1
NC 2021 | SHS | Region IX | Zamboanga City | 303943 | Regional Science HS | ZAMBOANGA CITY | 1 | 1 | 12 | Construction/Completion (4STY12CL) |  | 1876135.5122 | 1871456.87 |  | Completed | 1
NC 2021 | K10 | Region IX | Zamboanga City | 126223 | Arena Blanco East ES | ZAMBOANGA CITY | 2 | 1 | 6 | Construction/Completion (3STY6CL) |  | 1827322.3837 | 1822765.47 |  | COMPLETED | 1
NC 2021 | K10 | Region IX | Zamboanga del Norte | 124575 | Lingasad ES | POLANCO | 1 | 1 | 4 | Construction/Completion (2STY4CL) |  | 1661011.8342 | 1656869.66 |  | Completed | 1 | 2021-10-15 | [8 empty] | WESTMIN ENT. & CONST. SERVICES | Additional fund for completion
NC 2021 | K10 | Region IX | Zamboanga del Norte | 124325 | Diongan ES | JOSE DALMAN (PONOT) | 2 | 1 | 2 | Construction/Completion (1STY2CL) |  | 250625 | 250000 |  | Reverted | 0
NC 2021 | K10 | Region IX | Zamboanga del Norte | 124337 | Siparok ES | JOSE DALMAN (PONOT) | 2 | 1 | 4 | Construction/Completion (2UNITS 2CL) |  | 250625 | 250000 |  | Reverted | 0
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303671 | Bacong NHS | SALUG | 3 | 1 | 4 | Construction/Completion (2STY4CL REGULAR WORKSHOP w/ TOILET) |  | 2196445.2496 | 2190967.83 | 2180012.93 | COMPLETED | 1 | 2021-11-19 | [8 empty] | MJ MARI BUILDERS & DEV'T CORP | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303675 | Tinuyop National High school | BACUNGAN (LEON T. POSTIGO) | 3 | 1 | 8 | Construction/Completion (4STY8CL REGULAR WORKSHOP w/ TOILET) |  | 3391740.6962 | 3383282.49 | 3367431.11 | Completed | 1 | 2021-11-24 | [8 empty] | JZL BUILDERS & ENT. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303675 | Tinuyop National High school | BACUNGAN (LEON T. POSTIGO) | 3 |  | 4 | Construction/Completion (2STY4CL SCILAB & ICT COMBINED w/ TOILET) |  | 1144799.7622 | 1141944.9 | 1136103.35 | Completed | 1 | 2021-11-09 | [8 empty] | JZL BUILDERS & ENT. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303677 | Baliguian NHS | BALIGUIAN | 3 |  | 4 | Construction/Completion (2STY4CL SCILAB & ICT COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 890169.76 | COMPLETED | 1 | 2021-11-04 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303684 | GODOD NATIONAL HIGH SCHOOL | GODOD | 3 | 1 | 8 | Construction/Completion (4STY8CL REGULAR WORKSHOP w/ TOILET) |  | 2358836.9564 | 2352954.57 | 2341133.05 | COMPLETED | 1 | 2021-11-19 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303684 | GODOD NATIONAL HIGH SCHOOL | GODOD | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 890178.24 | COMPLETED | 1 | 2021-11-04 | [8 empty] | MJ MARI BUILDERS & DEV'T CORP | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 | 1 | 4 | Construction/Completion (2STY4CL REGULAR WORKSHOP w/ TOILET) |  | 1646420.3364 | 1642314.55 | 1642314.55 | COMPLETED | 1 | 2021-11-14 | [8 empty] | RUDHIL CONST. & ENT. INC. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303689 | Julian Soriano Memorial Comprehensive High School- Senior High | SIOCON | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 891957.34 | COMPLETED | 1 | 2021-11-04 | [8 empty] | RUDHIL CONST. & ENT. INC. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 | 1 | 8 | Construction/Completion (4STY8CL REGULAR WORKSHOP w/ TOILET) |  | 2481711.9278 | 2475523.12 | 2463116.93 | COMPLETED | 1 | 2021-11-19 | [8 empty] | ST. JOSEPH CONST. & TRADING | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303690 | Kalawit NHS | KALAWIT | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 1144799.7622 | 1141944.9 | 1136209.3 | COMPLETED | 1 | 2021-11-09 | [8 empty] | ST. JOSEPH CONST. & TRADING | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 | 1 | 8 | Construction/Completion (4STY8CL REGULAR WORKSHOP w/ TOILET) |  | 2423020.9863 | 2416978.54 | 2406295.24 | Completed | 1 | 2021-11-19 | [8 empty] | JZL BUILDERS & ENT. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303703 | Kipit Agro-Fishery NHS | LABASON | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 1365639.4346 | 1362233.85 | 1359120.04 | Completed | 1 | 2021-11-09 | [8 empty] | JZL BUILDERS & ENT. | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 | 1 | 4 | Construction/Completion (2STY4CL REGULAR WORKSHOP w/ TOILET) |  | 2298756.8006 | 2293024.24 | 2281490.9 | COMPLETED | 1 | 2021-11-19 | [8 empty] | ST. JOSEPH CONST. & TRADING | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303707 | COMPRA NATIONAL HIGH SCHOOL | LILOY | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 1144999.0292 | 1142143.67 | 1136389.71 | COMPLETED | 1 | 2021-11-09 | [8 empty] | ST. JOSEPH CONST. & TRADING | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303734 | Sibuco National High School | SIBUCO | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 608785.8793 | 607267.71 | 602925.5 | COMPLETED | 1 | 2021-11-29 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 | 1 | 6 | Construction/Completion (3STY6CL REGULAR WORKSHOP w/ TOILET) |  | 3069447.7933 | 3061793.31 | 3046458.77 | COMPLETED | 1 | 2021-11-24 | [8 empty] | ST. JOSEPH CONST. & TRADING | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303742 | Sirawai National High School | SIRAWAI | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 890173.08 | COMPLETED | 1 | 2021-11-04 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 303743 | Dacon National High School (Sirawai NHS - Guban Annex) | SIRAWAI | 3 | 1 | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 890165.8 | COMPLETED | 1 | 2021-11-09 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 314120 | Balas National High School | LABASON | 3 | 1 | 4 | Construction/Completion (2STY4CL REGULAR WORKSHOP w/ TOILET) |  | 2227325.0866 | 2221770.66 | 2210643.29 | COMPLETED | 1 | 2021-11-11 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 314120 | Balas National High School | LABASON | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 1144799.7622 | 1141944.9 | 1136037.44 | COMPLETED | 1 | 2021-11-09 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 | 1 | 4 | Construction/Completion (2STY4CL REGULAR WORKSHOP w/ TOILET) |  | 2097042.9135 | 2091813.38 | 2081125.49 | Completed | 1 | 2021-11-19 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga del Norte | 314124 | Gutalac NHS-Panganuran Ext. | GUTALAC | 3 |  | 4 | Construction/Completion (2STY4CL WORKSHOP COMBINED w/ TOILET) |  | 898694.6037 | 896453.47 | 890165.8 | COMPLETED | 1 | 2021-11-09 | [8 empty] | LONG ISLAND BUILDERS & CONST | Additional fund for completion
NC 2021 | TVL | Region IX | Zamboanga Sibugay | 303828 | Diplahan NHS | DIPLAHAN | 1 | 1 | 2 | Construction/Completion (2STY SCI LAB) |  | 1996741.2546 | 1991761.85 |  | COMPLETED | 1
NC 2021 | TVL | Region IX | Zamboanga Sibugay | 303829 | Buug NHS | BUUG | 1 | 1 | 2 | Construction/Completion (2STY SCI LAB) |  | 1997360.3686 | 1992379.42 |  | COMPLETED | 1
NC 2021 | TVL | Region IX | Zamboanga Sibugay | 303837 | Imelda NHS | IMELDA | 1 | 1 | 2 | Construction/Completion (2STY ICT LAB) |  | 1997360.3686 | 1992379.42 |  | COMPLETED | 1
NC 2022 | K10 | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD | 1 | 1 | 2 | 1STY2CL | 2 |  | 5204602.9898 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga del Norte | 124750 | SAWANG ES | SIBUTAD | 1 | 1 | 2 | 1STY2CL | 2 |  | 5185539.7205 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga del Sur | 125087 | Nopulan ES | JOSEFINA | 1 | 1 | 2 | 1STY2CL | 2 |  | 3690188.5853 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga del Sur | 125394 | Eastern Sominot ES | SOMINOT (DON MARIANO MARCOS) | 1 | 1 | 2 | 1STY2CL | 2 |  | 3729209.9454 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga del Sur | 125451 | Caluma ES | TIGBAO | 1 | 1 | 2 | 1STY2CL | 2 |  | 4636665.3365 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga del Sur | 125502 | Lunib ES | VINCENZO A. SAGUN | 2 | 1 | 4 | 1STY4CL | 2 |  | 8813563.752 |  | Completed | 1
NC 2022 | K10 | Region IX | Zamboanga Sibugay | 125849 | Laparay ES | Talusan | 1 | 1 | 3 | 1STY3CL | 2 |  | 5422691.2508 |  | Completed | 1
NC 2023 | K10 | Region IX | Isabela City | 502129 | Badjao Floating Integrated School | CITY OF ISABELA (Capital) |  | 1 |  | 0 | Batch 1 | 18157500 | 18000000 | 7638953.93 | Completed | 1 | 2023-12-25 | 2023-11-24 | P00775432LZ | 23EHO165 | 2023-06-21 |  | 2023-07-10 |  | 2023-08-10 |  | Booked(February 15,2024)
NC 2023 | K10 | Region IX | Isabela City | 126025 | Panigayan Elementary School | CITY OF ISABELA (Capital) |  | 1 |  | 0 | Batch 1 | 12105000 | 12000000 |  | Ongoing | 0.9 | 2024-09-06
NC 2023 | SHS | Region IX | Pagadian City | 314706 | Bulatok Integrated School | PAGADIAN CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4460730.24 | Completed | 1 | 2024-01-22 | 2024-01-22 | P00775278MN-CW1 | 23JE0084 | 2023-08-01 | 2023-08-08 | 2023-08-22 | 2023-09-21 | 2023-10-04 | GENETIAN BUILDERS & ENTERPRISES | Turned Over, COC - not yet signed due to balance building permits
NC 2023 | K10 | Region IX | Pagadian City | 126071 | Dumagoc ES | PAGADIAN CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4508654.01 | Completed | 1 | 2024-01-22 | 2024-03-22 | P00775276MN-CW1 | 23JE0085 | 2023-08-01 | 2023-08-08 | 2023-08-22 | 2023-09-21 | 2023-10-04 | GENETIAN BUILDERS & ENTERPRISES | Turned Over, COC - not yet signed due to balance building permits
NC 2023 | K10 | Region IX | Pagadian City | 501979 | Kalasan Integrated School | PAGADIAN CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4463904.62 | Completed | 1 | 2023-12-17 | 2023-12-17 | P00775279MN-CW1 | 23JE0083 | 2023-07-22 | 2023-07-31 | 2023-08-14 | 2023-08-23 | 2023-09-01 | KS AGAD CONSTRUCTION | Turned Over, COC - not yet signed due to balance building permits
NC 2023 | K10 | Region IX | Pagadian City | 126050 | Kawit ES | PAGADIAN CITY (Capital) |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4994597.74 | Completed | 1 | 2024-05-21 | 2024-05-21 | P00775275MN | 23JE0089 | 2023-10-21 | 2023-11-03 | 2023-11-15 | 2023-11-30 | 2023-12-13 | DIPLAHAN COMMERCIAL AND CONSTRUCTION | Turned Over, COC - not yet signed due to balance building permits
NC 2023 | K10 | Region IX | Pagadian City | 126075 | Napolan ES | PAGADIAN CITY (Capital) |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 | 9656071.21 | Completed | 1 | 2024-02-06 | 2024-03-07 | P00775277MN-CW1 | 23JE0086 | 2023-08-04 | 2023-08-11 | 2023-08-23 | 2023-09-21 | 2023-10-04 | NRMM CONST. DEVELOPMENT CORP. | Turned Over, COC - not yet signed due to balance building permits
NC 2023 | SHS | Region IX | Zamboanga City | 345869 | Baliwasan SHS - Stand Alone | ZAMBOANGA CITY |  | 1 |  | 20 | Batch 2 | 18112500 | 17500000 | 17361442.59 | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga City | 126098 | Baluno ES | ZAMBOANGA CITY |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10634126.22 | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga City | 126137 | Camp Susana ES | ZAMBOANGA CITY |  |  |  | 4 | Batch 1 | 10087500 | 10000000 | 9999007.82 | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga City | 126138 | Datu Panguluhan ES | ZAMBOANGA CITY |  | 1 |  | 5 | Batch 1 | 10732989.77 | 10639890.72 | 10629229.8 | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga City | 305996 | Mampang National High School | ZAMBOANGA CITY |  | 1 |  | 9 | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.95
NC 2023 | K10 | Region IX | Zamboanga City | 126178 | Buenakapok ES | ZAMBOANGA CITY |  | 1 |  | 4 | Batch 1 | 16927632 | 16780800 |  | Ongoing | 0.95
NC 2023 | K10 | Region IX | Zamboanga City | 126207 | Don Gregorio Evangelista MS | ZAMBOANGA CITY |  | 1 |  | 12 | Batch 1 | 37424625 | 37100000 |  | Ongoing | 0.75
NC 2023 | K10 | Region IX | Zamboanga City | 126225 | Guiwan ES | ZAMBOANGA CITY |  | 1 |  | 12 | Batch 2 | 2070000 | 2000000 |  | Ongoing | 0
NC 2023 | K10 | Region IX | Zamboanga City | 126201 | Lumbangan ES | ZAMBOANGA CITY |  | 1 |  | 9 | Batch 1 | 30262500 | 30000000 |  | Ongoing | 0.8
NC 2023 | K10 | Region IX | Zamboanga City | 126195 | Tolosa ES | ZAMBOANGA CITY |  | 1 |  | 4 | Batch 1 | 14547183.75 | 14421000 |  | Ongoing | 0.95
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124398 | La Libertad CS | LA LIBERTAD |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4992320.34 | Ongoing | 0.9 | 2023-12-28 | 2024-03-27 | P00775288MN-CW1 | 23JB0076 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-28 | 2023-08-31 | MDS Construction & Enterprises | none
NC 2023 | SHS | Region IX | Zamboanga del Norte | 314119 | Mutia National High School Extension - Alvenda | MUTIA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4985073.34 | Ongoing | 0.9 | 2023-12-27 |  | P00775289MN-CW1 | 23JB0074 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-17 | 2023-08-24 | DEBRIS Enterprises & Construction
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124604 | Mapang ES II | RIZAL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989979.43 | Completed | 1 | 2023-12-28 | 2024-03-27 | P00775290MN-CW1 | 23JB0075 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-28 | 2023-08-31 | MDS Construction & Enterprises | none
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124605 | Nangca ES | RIZAL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4955537.8 | Completed | 1 | 2023-12-27 |  | P00775291MN-CW1 | 23JB0073 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-17 | 2023-08-24 | BTM Construction & Enterprises
NC 2023 | SHS | Region IX | Zamboanga del Norte | 303726 | Sebaca NHS | RIZAL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989176.98 | Completed | 1 | 2023-12-28 | 2024-03-27 | P00775292MN-CW1 | 23JB0078 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-28 | 2023-08-31 | MDS Construction & Enterprises | none
NC 2023 | SHS | Region IX | Zamboanga del Norte | 303694 | Kanim NHS | SIBUTAD |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989573.8 | Completed | 1 | 2023-12-28 | 2024-03-27 | P00775293MN-CW1 | 23JB0077 | 2023-07-03 | 2023-07-12 | 2023-08-08 | 2023-08-28 | 2023-08-31 | MDS Construction & Enterprises | none
NC 2023 | SHS | Region IX | Zamboanga del Norte | 314118 | Saluyong NHS | MANUKAN |  | 1 |  | 2 | Batch 1 | 5425703.18 | 5378640.08 |  | Completed | 1 | 2024-01-13 | 2025-01-26 | P0077294MN | 23JC0072 | 2023-08-08 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-25 | D' DREAMER DEV'T CORP.
NC 2023 | SHS | Region IX | Zamboanga del Norte | 303682 | Dohinob NHS | PRES. MANUEL A. ROXAS |  | 1 |  | 4 | Batch 1 | 13985390.46 | 13864079.76 |  | Completed | 1 | 2024-02-20 | 2024-09-30 | P00775295MN | 23JC0071 | 2023-08-08 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-25 | D' DREAMER DEV'T CORP.
NC 2023 | SHS | Region IX | Zamboanga del Norte | 303731 | Diongan NHS | SIAYAN |  | 1 |  | 2 | Batch 1 | 5425703.18 | 5378640.08 |  | Ongoing | 0.95 | 2024-01-13 |  | P00775296MN | 23JC0074 | 2023-08-08 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-25 | D' DREAMER DEV'T CORP.
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124763 | Fatima ES | SINDANGAN |  | 1 |  | 2 | Batch 1 | 5425703.18 | 5378640.08 |  | Completed | 1 | 2024-01-13 | 2025-03-03 | P00775297MN | 23JC0073 | 2023-08-08 | 2023-08-18 | 2023-08-29 | 2023-09-11 | 2023-09-25 | D' DREAMER DEV'T CORP.
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124318 | Sas Integrated School | GUTALAC |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124342 | Batayan Elementary School | KALAWIT |  | 1 |  | 2 | Batch 3 | 7000000 | 6755000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124453 | Goin Elementary School | LILOY |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Norte | 501730 | Lintangan Integrated School | SIBUCO |  | 1 |  | 4 | Batch 1 | 10087500 | 10000000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124843 | Piacan ES | SIRAWAI |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Norte | 124862 | Tampilisan CS | TAMPILISAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125083 | Lower Bagong Tudela IPS | JOSEFINA |  | 1 |  | 2 | Batch 1 | 3961443.08 | 3927081.12 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125388 | Pictoran ES | SOMINOT (DON MARIANO MARCOS) |  | 1 |  | 2 | Batch 1 | 3976478.5 | 3941986.12 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Sur | 196032 | Sominot CES-SPED | SOMINOT (DON MARIANO MARCOS) |  | 1 |  | 3 | Batch 1 | 5660755.39 | 5611653.42 |  | Completed | 1
NC 2023 | SHS | Region IX | Zamboanga del Sur | 303818 | Subanen Agricultural NHS | SOMINOT (DON MARIANO MARCOS) |  | 1 |  | 2 | Batch 1 | 4042475.01 | 4007410.17 |  | Completed | 1
NC 2023 | K10 | Region IX | Zamboanga del Sur | 124941 | Dimataling CES | DIMATALING |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989935.7 | Completed | 1 | 2024-01-13 | 2024-07-11 | P00775307MN-CW1 | 23JG0072 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | ILMW Construction & Enterprises
NC 2023 | K10 | Region IX | Zamboanga del Sur | 314206 | Diosdado Macapagal Memorial NHS | LAKEWOOD |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989920.38 | Completed | 1 | 2024-01-13 |  | P00775308MN-CW1 | 23JG0073 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | ILMW Construction & Enterprises | Delayed: Issue regarding site relocation as per request by LGU-Lakewood
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125162 | Mala-Tiguha ES | LAPUYAN |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4998496.29 | Completed | 1 | 2024-02-03 | 2024-10-23 | P00775309MN-CW1 | 23JG0074 |  |  | 2023-09-05 | 2023-09-18 | 2023-10-09 | AJT Construction
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125348 | San Miguel CES & SPED Center | SAN MIGUEL |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4990000 | Completed | 1 | 2024-01-13 | 2024-04-05 | P00775310MN-CW1 | 23JG0075 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | GAF Trading & Construction
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125415 | Tabina CES | TABINA |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989279.74 | Completed | 1 | 2024-01-13 | 2024-04-11 | P00775311MN-CW1 | 23JG0076 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | KS Agad Construction
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125450 | Busol ES | TIGBAO |  | 1 |  | 2 | Batch 1 | 4726097.23 | 4685102.58 | 4682598.18 | Completed | 1 | 2024-01-13 | 2024-06-06 | P00775312MN-CW1 | 23JG0077 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | NRMM Const. & Dev't. Corp.
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125461 | Nangan-nangan ES | TIGBAO |  | 1 |  | 2 | Batch 1 | 4927847.23 | 4885102.58 | 4874400.24 | Completed | 1 | 2024-01-13 | 2024-03-18 | P00775313MN-CW1 | 23JG0078 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | KS Agad Construction
NC 2023 | SHS | Region IX | Zamboanga del Sur | 303821 | Tigbao NHS | TIGBAO |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 | 4989935.7 | Completed | 1 | 2024-01-13 | 2024-03-04 | P00775314MN-CW1 | 23JG0079 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | ILMW Construction & Enterprises
NC 2023 | K10 | Region IX | Zamboanga del Sur | 125495 | Biu-os ES | VINCENZO A. SAGUN |  | 1 |  | 2 | Batch 1 | 4776534.73 | 4735102.58 | 4724212.8 | Completed | 1 | 2024-01-13 | 2024-01-12 | P00775315MN-CW1 | 23JG0080 |  |  | 2023-08-09 | 2023-08-25 | 2023-09-18 | KS Agad Construction
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125563 | Villacastor ES | BUUG |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125566 | Diplahan CES | DIPLAHAN |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125581 | Pilar ES | DIPLAHAN |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125596 | Imelda CES | IMELDA |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125743 | Olutanga CES | OLUTANGA |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125774 | Payao CES | PAYAO |  | 1 |  | 3 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | SHS | Region IX | Zamboanga Sibugay | 314308 | Laparay NHS | TALUSAN |  | 1 |  | 8 | Batch 1 | 25292090.42 | 25072704.26 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125852 | Sagay Elementay School | Talusan |  | 1 |  | 4 | Batch 1 | 7666500 | 7600000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 196526 | Gutayan ES | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125800 | San Jose ES | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 501386 | Silingan Integrated School | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125803 | Sto. Rosario ES | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | SHS | Region IX | Zamboanga Sibugay | 314319 | Sto. Rosario National High School | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2023 | K10 | Region IX | Zamboanga Sibugay | 125805 | Taruc ES | ROSELLER LIM |  | 1 |  | 2 | Batch 1 | 5043750 | 5000000 |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Dapitan City | 125952 | Sigayan Elementary School | DAPITAN CITY |  | 1 | 6 | 2STY6CL | BATCH 1 | 19198000 |  |  | Ongoing | 0.68
NC 2024 |  | Region IX | Dipolog City | 125985 | Cayasan ES | DIPOLOG CITY (Capital) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4880743.82 | Completed | 1 | 2024-09-17 | 2025-01-26 | P00875007MN-CW1 | 24JC0055 | 2024-04-04 | 2024-04-12 | 2024-05-07 | 2024-05-15 | 2024-05-30 | Lakewood Const. Company | Delayed due to bad weather occurrence and variations approval.
NC 2024 |  | Region IX | Zamboanga City | 303915 | Ayala NHS | ZAMBOANGA CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19950000 | Ongoing | 0.8 |  | 2024-01-08 | P00875018MN-CW1 | 24JA0130 | [5 empty] | MOTHER'S ROLE CONSTRUCTION
NC 2024 |  | Region IX | Zamboanga City | 305994 | Lamisahan National High School | ZAMBOANGA CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 22200000 |  | 22144500 | Ongoing | 0.25 |  | 2024-10-28 | P00875016MN-CW1 | 24JA0143 | [5 empty] | HHH DEVELOPER AND REAL ESTATE INC
NC 2024 |  | Region IX | Zamboanga City | 314808 | Pasonanca NHS | ZAMBOANGA CITY |  | 1 | 16 | 4STY16CL | BATCH 1 | 57600000 |  | 57456000 | Ongoing | 0.25 |  | 2025-10-01 | P00875403MN-CW1 | 24JA0147 | [5 empty] | ATLANTIC ERECTORS INC.
NC 2024 |  | Region IX | Zamboanga City | 305995 | Tigtabon National High School | ZAMBOANGA CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 26400000 |  | 26334000 | Ongoing | 0.25 |  | 2024-12-13 | P00875015MN-CW1 | 24JA0145 | [5 empty] | SHERKAD CONSTRUCTION
NC 2024 |  | Region IX | Zamboanga City |  | Tumaga National High School | ZAMBOANGA CITY |  | 1 | 6 | 2STY6CL | GAA 17B | 20000000 |  | 19950000 | Ongoing | 0.4 |  | 2024-09-25 | P00875019MN-CW1 | 24JA0135 | [5 empty] | RJLP CONSTRUCTION & SUPPLIES
NC 2024 |  | Region IX | Zamboanga City | 501887 | Buenavista IS | ZAMBOANGA CITY |  | 1 | 20 | 4STY20CL | GAA 17B | 64000000 |  | 63840000 | Ongoing | 0.6 |  | 2024-06-24 | P00875021MN-CW1 | 24JA0111 | [5 empty] | HHH DEVELOPER AND CONSTRUCTION/ SK PATH CONSTRUCTION
NC 2024 |  | Region IX | Zamboanga City | 126193 | Talabaan ES | ZAMBOANGA CITY |  | 1 | 4 | 1STY4CL | GAA 17B | 10000000 |  | 9975000 | Ongoing | 0.9 |  | 2024-05-30 | P00875017MN-CW1 | 24JA0106 | [5 empty] | 3GE CONSTRUCTION
NC 2024 |  | Region IX | Zamboanga City | 303939 | Vitali NHS | ZAMBOANGA CITY |  | 1 | 20 | 4STY20CL | GAA 17B | 67400000 |  | 67231500 | Ongoing | 0.7 |  | 2024-06-06 | P00875020MN-CW1 | 24JA0108 | [5 empty] | HHH DEVELOPER AND CONSTRUCTION/ JH CONSTRUCTION INC. (JV)
NC 2024 |  | Region IX | Zamboanga del Norte | 303725 | San Pedro National High School | POLANCO |  | 1 | 6 | 2STY6CL | BATCH 1 | 20061000 |  | 19995000 | Ongoing | 0.85 | 2024-12-15 |  |  | 24JB0055 | 2024-08-04 | 2024-04-15 |  | 2024-07-05 | 2024-05-14 | A.I.YU Builders & Enterprises
NC 2024 |  | Region IX | Zamboanga del Norte | 303888 | Galas NHS | Dipolog City |  | 1 | 20 | 4STY20CL | BATCH 1 | 54012367.94 |  |  | Ongoing | 0.25 | 2025-02-22 |  | P0087540M | 24JC0061 | 2024-09-04 | 2024-04-17 | 2024-04-29 | 2024-05-13 | 2024-05-27 | D' DREAMER DEV'T CORP
NC 2024 |  | Region IX | Zamboanga del Norte | 124372 | Malasay ES | KATIPUNAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.45 | 2024-09-17 |  | P00875001MN | 24JC0056 | 2024-04-04 | 2024-12-04 | 2024-12-05 | 2024-05-15 | 2024-05-30 | Golden Lion Construction
NC 2024 |  | Region IX | Zamboanga del Norte | 303681 | Bartolome Aripal Memorial NHS | MANUKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.45 | 2024-09-17 |  | P00875004MN | 24JC0064 | 2024-09-04 | 2024-04-17 | 2024-07-05 | 2024-05-13 | 2024-05-30 | D' DREAMER DEV'T CORP
NC 2024 |  | Region IX | Zamboanga del Norte | 303752 | Jesus A. Ramos NHS | MANUKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | 2024-09-17 | 2025-03-23 | P00875005MN | 24JC0059 | 2024-04-04 | 2024-12-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | D' DREAMER DEV'T CORP
NC 2024 |  | Region IX | Zamboanga del Norte | 124515 | Patagan ES | MANUKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | 2024-09-17 | 2025-02-02 | P00875006MN | 24JC0057 | 2024-04-04 | 2024-12-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | D' DREAMER DEV'T CORP
NC 2024 |  | Region IX | Zamboanga del Norte | 124516 | Patunan ES | MANUKAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | 2024-09-17 | 2025-02-23 | P00875003MN | 24JC0058 | 2024-04-04 | 2024-12-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | Long Island Builders
NC 2024 |  | Region IX | Zamboanga del Norte | 124482 | Minang ES | PRES. MANUEL A. ROXAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.9 | 2024-07-11 |  | P00875008MN | 24JC0066 | 2024-05-31 | 2024-10-06 | 2024-06-24 | 2024-08-07 | 2024-07-22 | Golden Lion Construction
NC 2024 |  | Region IX | Zamboanga del Norte | 305977 | Feliciano Castillo National High School | SIAYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.7 | 2024-09-17 |  | P00875002MN | 24JC0060 | 2024-04-04 | 2024-12-04 | 2024-02-05 | 2024-05-15 | 2024-05-30 | D' DREAMER DEV'T CORP
NC 2024 |  | Region IX | Zamboanga del Norte | 124296 | La Libertad ES | GUTALAC |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  | 5970000 | Completed | 1 |  | 2024-09-16 |  | 24JD0064 | [5 empty] | ST. JOSEPH CONSTRUCTION & TRADING
NC 2024 |  | Region IX | Zamboanga del Norte | 502329 | La Union Integrated School | LABASON |  | 1 | 4 | 2STY4CL | GAA 17B | 13000000 |  | 12935000 | Completed | 1 |  | 2024-08-09 |  | 24JD0063 | [5 empty] | BORGONIA CONSTRUCTION & ENTERPRISES
NC 2024 |  | Region IX | Zamboanga del Norte | 124423 | Osukan ES | LABASON |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4975000 | Completed | 1 |  | 2024-08-30 |  | 24JD0062 | [5 empty] | BORGONIA CONSTRUCTION & ENTERPRISES
NC 2024 |  | Region IX | Zamboanga del Norte | 314114 | Binoni NHS | SALUG |  | 1 | 10 | 2STY10CL | BATCH 2 | 26019966.61 |  |  | Ongoing | 0.48
NC 2024 |  | Region IX | Zamboanga del Norte | 124715 | Guimba Parang ES | SIBUCO |  | 1 | 3 | 1STY3CL | GAA 17B | 9000000 |  |  | Completed | 1
NC 2024 |  | Region IX | Zamboanga del Norte | 124825 | Lu Tian Po ES | SIOCON |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  |  | Completed | 1
NC 2024 |  | Region IX | Zamboanga del Norte | 303747 | New Dapitan National High School | TAMPILISAN |  | 1 | 2 | 1STY2CL | GAA 17B | 6000000 |  |  | Completed | 1
NC 2024 |  | Region IX | Zamboanga del Sur |  | Balas National High School | AURORA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.8
NC 2024 |  | Region IX | Zamboanga del Sur | 196040 | Simuyak Elementary School | DINAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4970000 | Completed | 1 | 2024-02-10 |  | P00875031MN-CW1 | 24JG0061 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | JZL Builders & Enterprises
NC 2024 |  | Region IX | Zamboanga del Sur | 196030 | BIGAAN ELEMENTARY SCHOOL | DUMINGAG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.8
NC 2024 |  | Region IX | Zamboanga del Sur | 125082 | Litapan ES | JOSEFINA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region IX | Zamboanga del Sur | 196048 | Tebed PS | MIDSALIP |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.7
NC 2024 |  | Region IX | Zamboanga del Sur | 125280 | Dipolo ES | MOLAVE |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.9
NC 2024 |  | Region IX | Zamboanga del Sur | 125379 | Bag-ong Baroy ES | SOMINOT (DON MARIANO MARCOS) |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.95
NC 2024 |  | Region IX | Zamboanga del Sur | 314218 | Bag-ong Kauswagan NHS | TAMBULIG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.7
NC 2024 |  | Region IX | Zamboanga del Sur | 125478 | San Antonio ES | TUKURAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1
NC 2024 |  | Region IX | Zamboanga del Sur | 314236 | Depase National High School | BAYOG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4969553.41 | Completed | 1 | 2024-02-10 |  | P00875030MN-CW1 | 24JG0063 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | DOMNPHIL Construction
NC 2024 |  | Region IX | Zamboanga del Sur | 314247 | Camalig NHS | DUMALINAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967082.82 | Completed | 1 | 2024-02-10 |  | P00875035MN-CW1 | 24JG0062 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | ILMW Construction & Enterprises
NC 2024 |  | Region IX | Zamboanga del Sur | 306031 | Karpok National High School | LAPUYAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964736.58 | Completed | 1 | 2024-02-10 |  | P00875036MN-CW1 | 24JG0064 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | KS Agad Construction
NC 2024 |  | Region IX | Zamboanga del Sur | 300000 | Digon National High School | MARGOSATUBIG |  | 1 | 6 | 2STY6CL | BATCH 1 | 18386674.6 |  | 18279538.92 | Ongoing | 0.7 | 2024-11-28 |  | P00875406MN-CW1 | 24JG0068 |  |  | 2024-07-06 | 2024-06-24 | 2024-08-07 | NRMM Const. & Dev't. Corp.
NC 2024 |  | Region IX | Zamboanga del Sur | 125338 | Dumalian ES | SAN MIGUEL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967084.04 | Ongoing | 0.9 | 2024-02-10 |  | P00875037MN-CW1 | 24JG0059 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | ILMW Construction & Enterprises
NC 2024 |  | Region IX | Zamboanga del Sur | 125463 | Nilo ES | TIGBAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4964528.02 | Completed | 1 | 2024-02-10 |  | P00875032MN-CW1 | 24JG0060 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | KS Agad Construction
NC 2024 |  | Region IX | Zamboanga del Sur | 125504 | Maraya Elementary School | VINCENZO A. SAGUN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4967084.04 | Completed | 1 | 2024-02-10 |  | P00875034MN-CW1 | 24JG0065 |  |  | 2024-07-05 | 2024-05-20 | 2024-03-06 | ILMW Construction & Enterprises
NC 2024 |  | Region IX | Zamboanga del Sur |  | Maraya National High School | VINCENZO A. SAGUN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  | 4968409.49 | Completed | 1 | 2024-10-19 |  | P00875033MN-CW1 | 24JG0067 |  |  | 2024-05-21 | 2024-03-06 | 2024-06-18 | ILMW Construction & Enterprises
NC 2024 |  | Region IX | Zamboanga Sibugay | 125510 | Alicia Central Elementary School | ALICIA |  | 1 | 17 | 2STY10CL, 2STY4CL & 1STY3CL | BATCH 1 | 46960505.48 |  |  | Ongoing | 0.6 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 196501 | Bagong Buhay Elementary School | ALICIA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.6 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125546 | Del Monte Elementary School | BUUG |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125567 | Ditay Elementary School | DIPLAHAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.8 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125681 | Taguisian Elementary School | MABUHAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.65 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125688 | Candiis Elementary School | MALANGAS |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125735 | Fama Elementary School | OLUTANGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125755 | Bulawan Elementary School | PAYAO |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125854 | Talusan Central Elementary School | TALUSAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125608 | Bakalan Elementary School | IPIL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.95 | [10 empty] | Requested for modification
NC 2024 |  | Region IX | Zamboanga Sibugay | 196519 | Ipil Special Education Center | IPIL |  | 1 | 4 | 2STY4CL | BATCH 1 | 9657229 |  |  | Ongoing | 0.05 | [10 empty] | Requested for modification
NC 2024 |  | Region IX | Zamboanga Sibugay | 303844 | Makilas National High School | IPIL |  | 1 | 8 | 2STY8CL | BATCH 1 | 19314458 |  |  | Ongoing | 0.25 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125631 | Tiayon Elementary School | IPIL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Completed | 1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125633 | Tomitom Elementary School | IPIL |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.95 | [10 empty] | Requested for modification
NC 2024 |  | Region IX | Zamboanga Sibugay | 125656 | Shiolan Elementary School | KABASALAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.1 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125724 | Sandayong Elementary School | NAGA |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.88 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125801 | Siawang Elementary School | ROSELLER LIM |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.88 | [10 empty] | NO PROCUREMENT DATA PROVIDED BY DPWH
NC 2024 |  | Region IX | Zamboanga Sibugay | 125859 | Camanga Elementary School | TITAY |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.88 | [10 empty] | Requested for modification
NC 2024 |  | Region IX | Zamboanga Sibugay | 125910 | Upper Tungawan Elementary School | TUNGAWAN |  | 1 | 2 | 1STY2CL | GAA 17B | 5000000 |  |  | Ongoing | 0.15 | [10 empty] | Requested for modification

## DropdownOptions (hidden)
0% - 10%: Foundation completed: Groundwork finished; no vertical structure yet.
11% - 25%: Structure and rough-in started: Structural framing in progress; initial MEP rough-in.
26% - 50%: Structure erected, partial roofing: Building shape defined; roof and systems advancing.
51% - 75%: Exterior sealed, interior work underway: Enclosed structure; painting, flooring, and testing begin.
76% - 90%: Final finishes and inspections: Systems tested;
91% - 99%: Final touches and punch list: Minor adjustments; final inspections and approvals.
100% - Construction complete: Ready for handover and occupancy.